## LOM_17Mt_Schedule_RM_output pat
XPAC7 Scheduling Path Output File
Database Name : C:\Users\dnelmes\Documents\Rolleston Phase 2\From_ROB\LOM WORKING XPAC Schedule 17Mt\LOM WORKING XPAC Schedule 17Mt\2015_LOM_17Mt_Schedule_RM.xpk
Scenario Name : LOM2014_SP
Export Date/Time : 15/05/2014 3:50:29 PM
Resource | Scheduling Task | Area |  |  | Seam | Activity | Entered% / Delay | Released% | Actual% / Delay | Start Date | Finish Date | Actual Quantity | Prestrip - Shovels | Prestrip - Hydraulic | Post Strip - Hydraulics | Blast Prime Volume | Dragline Total Waste Removal Volume | Dragline Prime Volume | Coal (t) | Seam Volume | Seam Thickness | In Situ Block Thickness | In Situ Block Thickness | Ash (% Prod) | Calorific Value GAR (MProd)
DRE1 | SC\18\011\D | SC | 18 | 11 | D | 6 DL | 100 | 0 | 0 | 2014-04-01 | 2014-04-01 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | MC\27\003\B | MC | 27 | 3 | B | 6 DL | 100 | 0 | 10 | 2014-04-01 | 2014-04-01 16:05 | 54837.8746 |  |  |  |  | 54838 | 42183 |  |  | 0 | 22.16 | 0 | 0 | 0
TS5500Exc | SC\19\001\B | SC | 19 | 1 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-04-01 | 2014-04-03 18:56 | 88102.9614 | [6 empty] | 88103 | 64895 | 3.95 | 0 | 0 | 8.61 | 5619
PH4100A | SC\19\004\D | SC | 19 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-04-01 | 2014-04-03 16:35 | 93556.9463 | 93557 | [7 empty] | 0 | 0 | 7.67 | 5.82 | 5902.72
PH4100XPC#1 | BW\17\001\B | BW | 17 | 1 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-01 | 2014-04-03 10:27 | 142820.5674 | 142821 | [7 empty] | 0 | 0 | 10.34 | 10.86 | 5373.97
TS5500Shv | SC\21\003\B | SC | 21 | 3 | B | 8 Coal Mining | 100 | 0 | 86.4 | 2014-04-01 | 2014-04-06 21:36 | 54123.9942 | [6 empty] | 54124 | 40036 | 3.33 | 0 | 0 | 8.89 | 5586
TS6060#1 | MC\25\001\D | MC | 25 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-04-01 | 2014-04-05 22:00 | 166861 | [6 empty] | 166861 | 50913 | 4.71 | 0 | 0 | 6.49 | 5843
DRE1 | SC\18\010\D | SC | 18 | 10 | D | 6 DL | 100 | 0 | 0 | 2014-04-01 | 2014-04-01 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE1 | SC\18\009\D | SC | 18 | 9 | D | 6 DL | 100 | 0 | 0 | 2014-04-01 | 2014-04-01 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE1 | SC\18\008\D | SC | 18 | 8 | D | 6 DL | 100 | 0 | 0 | 2014-04-01 | 2014-04-01 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE1 | SC\18\007\D | SC | 18 | 7 | D | 6 DL | 100 | 0 | 0 | 2014-04-01 | 2014-04-01 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE1 | SC\18\001\D | SC | 18 | 1 | D | 6 DL | 100 | 100 | 100 | 2014-04-01 | 2014-04-19 21:54 | 1247288.682 |  |  |  | 70053 | 1247289 | 542914 |  |  | 0 | 40 | 0 | 6.51 | 5843.42
TS Fleet 5 | No Production | No Production | [7 empty] | 2014-04-01 | 2014-05-01
DRE2 | MC\27\004\B | MC | 27 | 4 | B | 6 DL | 100 | 100 | 10 | 2014-04-01 16:05 | 2014-04-01 21:25 | 18173.7335 |  |  |  |  | 18174 | 15145 |  |  | 0 | 16.18 | 0 | 11.72 | 5262.13
DRE2 | MC\27\005\A2 | MC | 27 | 5 | A2 | 6 DL | 100 | 0 | 0 | 2014-04-01 21:25 | 2014-04-01 21:25 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | MC\27\006\A2 | MC | 27 | 6 | A2 | 6 DL | 100 | 0 | 0 | 2014-04-01 21:25 | 2014-04-01 21:25 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | MC\27\007\A2 | MC | 27 | 7 | A2 | 6 DL | 100 | 0 | 0 | 2014-04-01 21:25 | 2014-04-01 21:25 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | MC\27\008\A2 | MC | 27 | 8 | A2 | 6 DL | 100 | 0 | 0 | 2014-04-01 21:25 | 2014-04-01 21:25 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | MC\27\012\B | MC | 27 | 12 | B | 6 DL | 100 | 0 | 10 | 2014-04-01 21:25 | 2014-04-02 15:35 | 61943.0483 |  |  |  |  | 61943 | 51619 |  |  | 0 | 22.84 | 0 | 0 | 0
DRE2 | MC\26\001\D | MC | 26 | 1 | D | 6 DL | 100 | 100 | 100 | 2014-04-02 15:35 | 2014-04-12 14:16 | 813596.9215 |  |  |  | 61870 | 813597 | 556834 |  |  | 0 | 40 | 0 | 6.49 | 5843.12
PH4100XPC#1 | BW\18\001\B | BW | 18 | 1 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-03 10:27 | 2014-04-06 20:56 | 202218.6452 | 202219 | [7 empty] | 0 | 0 | 17.04 | 10.85 | 5373.9
PH4100A | SC\19\003\D | SC | 19 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-04-03 16:35 | 2014-04-06 22:40 | 113072.9949 | 113073 | [7 empty] | 0 | 0 | 9.4 | 6 | 5886.6
TS5500Exc | SC\19\002\B | SC | 19 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-04-03 18:56 | 2014-04-05 18:00 | 61937.6941 | [6 empty] | 61938 | 45717 | 3.87 | 0 | 0 | 8.73 | 5604
TS5500Exc | SC\20\001\B | SC | 20 | 1 | B | 8 Coal Mining | 100 | 0 | 50.3 | 2014-04-05 18:00 | 2014-04-06 21:36 | 36320.3503 | [6 empty] | 36320 | 26772 | 1.98 | 0 | 0 | 8.61 | 5615
TS6060#1 | BW\17\003\X1 | BW | 17 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2014-04-05 22:00 | 2014-04-06 09:24 | 16128.0675 | [6 empty] | 16128 | 11283 | 1.28 | 0 | 0 | 18.55 | 4666
TS6060#1 | BW\18\003\X1 | BW | 18 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2014-04-06 09:24 | 2014-04-06 20:13 | 15299.5845 | [6 empty] | 15300 | 10762 | 1.04 | 0 | 0 | 17.83 | 4746
TS6060#1 | MW\15\003\D | MW | 15 | 3 | D | 1 Prestrip - Thick | 20 | 20 | 20 | 2014-04-06 20:13 | 2014-04-08 18:20 | 49070.5515 | 49071 | [7 empty] | 0 | 0 | 5.78 | 5.29 | 5947.52
PH4100XPC#1 | BW\17\002\B | BW | 17 | 2 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-06 20:56 | 2014-04-08 09:52 | 88675.4464 | 88675 | [7 empty] | 0 | 0 | 6.87 | 11.02 | 5353.69
TS5500Shv | DT\17\003\B | DT | 17 | 3 | B | 7 PostStrip | 100 | 100 | 100 | 2014-04-06 21:36 | 2014-04-06 21:36 | 1 |  |  | 1 | [5 empty] | 0 | 0 | 0 | 18.64 | 4793.76
TS5500Exc | SC\19\002\D | SC | 19 | 2 | D | 1 Prestrip - Thick | 20.0539 | 20.0539 | 20.0539 | 2014-04-06 21:36 | 2014-04-07 23:34 | 23990.3065 | 23990 | [7 empty] | 0 | 0 | 2 | 6.27 | 5863.28
TS5500Shv | DT\17\005\A | DT | 17 | 5 | A | 7 PostStrip | 100 | 100 | 100 | 2014-04-06 21:36 | 2014-04-06 21:37 | 1 |  |  | 1 | [5 empty] | 0 | 0 | 0 | 10.7 | 5429.87
TS5500Shv | DT\20\004\A | DT | 20 | 4 | A | 1 Prestrip - Thick | 43.3841 | 34.8511 | 34.8511 | 2014-04-06 21:37 | 2014-05-01 | 193763.2111 | 193763 | [7 empty] | 0 | 0 | 13.12 | 12.31 | 5314.21
PH4100A | SC\19\002\D | SC | 19 | 2 | D | 1 Prestrip - Thick | 100 | 79.9461 | 79.9461 | 2014-04-06 22:40 | 2014-04-09 16:42 | 95638.6384 | 95639 | [7 empty] | 0 | 0 | 7.99 | 6.27 | 5863.28
TS5500Exc | MC\26\002\D | MC | 26 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-04-07 23:34 | 2014-04-09 21:31 | 60466.1422 | [6 empty] | 60466 | 45749 | 4.79 | 0 | 0 | 6.33 | 5858
PH4100XPC#1 | BW\18\002\B | BW | 18 | 2 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-08 09:52 | 2014-04-10 22:49 | 148180.9402 | 148181 | [7 empty] | 0 | 0 | 16.94 | 11.22 | 5340.85
TS6060#1 | DT\19\003\A2 | DT | 19 | 3 | A2 | 1 Prestrip - Thick | 20 | 85 | 20 | 2014-04-08 18:20 | 2014-04-13 07:46 | 116745.8963 | 116746 | [7 empty] | 0 | 0 | 6.17 | 15.68 | 5033.99
PH4100A | SC\19\001\D | SC | 19 | 1 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-04-09 16:42 | 2014-04-13 21:31 | 146026.4436 | 146026 | [7 empty] | 0 | 0 | 10.74 | 6.64 | 5831.9
TS5500Exc | MC\27\005\A2 | MC | 27 | 5 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2014-04-09 21:31 | 2014-04-10 01:43 | 5537.9981 | [6 empty] | 5538 | 3945 | 1.12 | 0 | 0 | 19.71 | 4670
TS5500Exc | MC\27\007\A2 | MC | 27 | 7 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2014-04-10 01:43 | 2014-04-11 18:58 | 54271.9375 | [6 empty] | 54272 | 38967 | 3.93 | 0 | 0 | 14.56 | 5135
PH4100XPC#1 | BW\17\003\B | BW | 17 | 3 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-10 22:49 | 2014-04-11 22:16 | 55368.7542 | 55369 | [7 empty] | 0 | 0 | 4.78 | 10.85 | 5370.37
TS5500Exc | MC\27\008\A2 | MC | 27 | 8 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2014-04-11 18:58 | 2014-04-12 02:41 | 10159.6427 | [6 empty] | 10160 | 7562 | 2.96 | 0 | 0 | 12.58 | 5169
PH4100XPC#1 | BW\18\003\B | BW | 18 | 3 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-11 22:16 | 2014-04-12 06:48 | 20141.5935 | 20142 | [7 empty] | 0 | 0 | 2.01 | 10.94 | 5367.82
TS5500Exc | MW\15\003\D | MW | 15 | 3 | D | 1 Prestrip - Thick | 3.7208 | 3.7208 | 3.7208 | 2014-04-12 02:41 | 2014-04-12 12:33 | 9129.0808 | 9129 | [7 empty] | 0 | 0 | 1.08 | 5.29 | 5947.52
PH4100XPC#1 | BW\17\004\B | BW | 17 | 4 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-12 06:48 | 2014-04-12 22:22 | 36930.1738 | 36930 | [7 empty] | 0 | 0 | 2.58 | 11.08 | 5370.66
TS5500Exc | MW\15\003\D | MW | 15 | 3 | D | 1 Prestrip - Thick | 76.2792 | 76.2792 | 76.2792 | 2014-04-12 12:33 | 2014-04-20 22:43 | 187153.1254 | 187153 | [7 empty] | 0 | 0 | 22.06 | 5.29 | 5947.52
DRE2 | MC\26\002\D | MC | 26 | 2 | D | 6 DL | 100 | 0 | 0 | 2014-04-12 14:16 | 2014-04-12 14:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | MC\26\003\D | MC | 26 | 3 | D | 6 DL | 100 | 100 | 100 | 2014-04-12 14:16 | 2014-04-17 07:55 | 387372.2861 |  |  |  | 9019 | 387372 | 171364 |  |  | 0 | 21.85 | 0 | 6.08 | 5879.63
PH4100XPC#1 | BW\18\004\B | BW | 18 | 4 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-12 22:22 | 2014-04-14 19:35 | 107206.115 | 107206 | [7 empty] | 0 | 0 | 10.98 | 11.22 | 5364.65
TS6060#1 | DT\20\003\A2 | DT | 20 | 3 | A2 | 1 Prestrip - Thick | 20 | 85 | 20 | 2014-04-13 07:46 | 2014-04-22 15:43 | 237901.1501 | 237901 | [7 empty] | 0 | 0 | 7.26 | 15.94 | 5016.11
PH4100A | BW\16\002\D | BW | 16 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-04-13 21:31 | 2014-04-19 19:28 | 205582.9342 | 205583 | [7 empty] | 0 | 0 | 19.32 | 5.6 | 5922.42
PH4100XPC#1 | BW\17\005\B | BW | 17 | 5 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-14 19:35 | 2014-04-16 06:42 | 85487.5069 | 85488 | [7 empty] | 0 | 0 | 6.09 | 10.49 | 5431.58
PH4100XPC#1 | BW\18\005\B | BW | 18 | 5 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-16 06:42 | 2014-04-18 09:43 | 122962.5312 | 122963 | [7 empty] | 0 | 0 | 11.12 | 10.5 | 5438.76
DRE2 | BC\29\006\D | BC | 29 | 6 | D | 6 DL | 100 | 100 | 100 | 2014-04-17 07:55 | 2014-04-23 17:19 | 522854.9225 |  |  |  | 9076 | 522855 | 167860 |  |  | 0 | 22.71 | 0 | 6.59 | 5833.71
PH4100XPC#1 | BW\17\006\B | BW | 17 | 6 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-18 09:43 | 2014-04-19 00:32 | 35158.8691 | 35159 | [7 empty] | 0 | 0 | 2.79 | 11.06 | 5416.41
PH4100XPC#1 | BW\18\006\B | BW | 18 | 6 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-19 00:32 | 2014-04-20 20:50 | 104808.0536 | 104808 | [7 empty] | 0 | 0 | 10.12 | 10.73 | 5446.04
PH4100A | BW\16\003\D | BW | 16 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-04-19 19:28 | 2014-04-23 08:00 | 122436.1027 | 122436 | [7 empty] | 0 | 0 | 11.5 | 6.03 | 5883.43
DRE1 | SC\18\002\D | SC | 18 | 2 | D | 6 DL | 100 | 100 | 100 | 2014-04-19 21:54 | 2014-04-30 19:43 | 719448.2294 |  |  |  | 54711 | 719448 | 492398 |  |  | 0 | 40 | 0 | 6.15 | 5874.05
PH4100XPC#1 | BW\17\007\B | BW | 17 | 7 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-20 20:50 | 2014-04-21 19:46 | 55518.9848 | 55519 | [7 empty] | 0 | 0 | 4.3 | 12.86 | 5289.86
TS5500Exc | MC\26\001\D | MC | 26 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-04-20 22:43 | 2014-04-23 01:48 | 67221.1598 | [6 empty] | 67221 | 50913 | 4.71 | 0 | 0 | 6.49 | 5843
PH4100XPC#1 | BW\18\007\B | BW | 18 | 7 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-21 19:46 | 2014-04-23 11:47 | 95556.0274 | 95556 | [7 empty] | 0 | 0 | 8.7 | 12.88 | 5290.01
TS6060#1 | DT\21\003\A1 | DT | 21 | 3 | A1 | 1 Prestrip - Thick | 20 | 85 | 20 | 2014-04-22 15:43 | 2014-04-25 14:28 | 76006.2627 | 76006 | [7 empty] | 0 | 0 | 4.74 | 15.23 | 5092.98
TS5500Exc | MC\26\003\D | MC | 26 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-04-23 01:48 | 2014-04-24 21:37 | 57668.203 | [6 empty] | 57668 | 43714 | 4.82 | 0 | 0 | 6.08 | 5880
PH4100A | BW\16\004\D | BW | 16 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-04-23 08:00 | 2014-04-28 17:15 | 187194.5396 | 187195 | [7 empty] | 0 | 0 | 17.71 | 5.75 | 5907.82
PH4100XPC#1 | BW\17\008\B | BW | 17 | 8 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-23 11:47 | 2014-04-24 11:44 | 56868.727 | 56869 | [7 empty] | 0 | 0 | 4.56 | 13.24 | 5250.17
DRE2 | BC\29\005\D | BC | 29 | 5 | D | 6 DL | 100 | 100 | 100 | 2014-04-23 17:19 | 2014-04-29 06:53 | 455315.8939 |  |  |  | 10360 | 455316 | 196838 |  |  | 0 | 22.24 | 0 | 6.33 | 5857.82
PH4100XPC#1 | BW\18\008\B | BW | 18 | 8 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-24 11:44 | 2014-04-26 06:41 | 101485.3135 | 101485 | [7 empty] | 0 | 0 | 9.93 | 13.99 | 5190.83
TS5500Exc | SC\18\001\D | SC | 18 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2014-04-24 21:37 | 2014-04-28 20:23 | 87566.8223 |  |  | 87567 | [5 empty] | 0 | 0 | 0 | 6.51 | 5843.42
TS6060#1 | DT\22\003\A1 | DT | 22 | 3 | A1 | 1 Prestrip - Thick | 20 | 100 | 20 | 2014-04-25 14:28 | 2014-04-28 16:40 | 79578.9602 | 79579 | [7 empty] | 0 | 0 | 5.11 | 15.3 | 5089.98
PH4100XPC#1 | BW\17\009\B | BW | 17 | 9 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-26 06:41 | 2014-04-26 17:54 | 27170.125 | 27170 | [7 empty] | 0 | 0 | 2.28 | 12.48 | 5296.99
PH4100XPC#1 | BW\18\009\B | BW | 18 | 9 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-26 17:54 | 2014-04-27 22:31 | 69593.5192 | 69594 | [7 empty] | 0 | 0 | 6.73 | 12.89 | 5264.3
PH4100XPC#1 | BW\17\010\B | BW | 17 | 10 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-27 22:31 | 2014-04-28 01:25 | 6840.6414 | 6841 | [7 empty] | 0 | 0 | 1.03 | 11.33 | 5379.68
PH4100XPC#1 | BW\18\010\B | BW | 18 | 10 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-28 01:25 | 2014-04-28 05:02 | 8483.6636 | 8484 | [7 empty] | 0 | 0 | 1.21 | 10.65 | 5433.88
PH4100XPC#1 | BW\18\011\B | BW | 18 | 11 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-28 05:02 | 2014-04-28 07:11 | 4978.7277 | 4979 | [7 empty] | 0 | 0 | 0.54 | 0 | 0
PH4100XPC#1 | DT\16\003\B | DT | 16 | 3 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-04-28 07:11 | 2014-04-28 08:13 | 2462.3793 | 2462 | [7 empty] | 0 | 0 | 0.11 | 0 | 0
PH4100XPC#1 | MW\15\013\D | MW | 15 | 13 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-04-28 08:13 | 2014-04-30 10:32 | 110447.6813 | 110448 | [7 empty] | 0 | 0 | 14.64 | 5.84 | 5895.38
TS6060#1 | DT\23\003\A2 | DT | 23 | 3 | A2 | 1 Prestrip - Thick | 20 | 56.5966 | 11.3193 | 2014-04-28 16:40 | 2014-05-01 | 59318.9247 | 59319 | [7 empty] | 0 | 0 | 3.67 | 14.82 | 5134.23
PH4100A | BW\16\005\D | BW | 16 | 5 | D | 1 Prestrip - Thick | 100 | 34.4326 | 34.4326 | 2014-04-28 17:15 | 2014-05-01 | 79281.8003 | 79282 | [7 empty] | 0 | 0 | 7.55 | 5.4 | 5938.31
TS5500Exc | BC\29\006\D | BC | 29 | 6 | D | 7 PostStrip | 100 | 0 | 95.4332 | 2014-04-28 20:23 | 2014-05-01 | 47685.1007 |  |  | 47685 | [5 empty] | 0 | 0 | 0 | 6.59 | 5833.71
DRE2 | BC\29\004\D | BC | 29 | 4 | D | 6 DL | 100 | 30.4964 | 30.4964 | 2014-04-29 06:53 | 2014-05-01 | 140097.3196 |  |  |  | 3273 | 140097 | 62186 |  |  | 0 | 21.98 | 0 | 6.04 | 5883.72
PH4100XPC#1 | MW\16\013\D | MW | 16 | 13 | D | 1 Prestrip - Thick | 50 | 0 | 17.9073 | 2014-04-30 10:32 | 2014-05-01 | 29688.0426 | 29688 | [7 empty] | 0 | 0 | 3.97 | 5.85 | 5896.04
DRE1 | SC\18\003\D | SC | 18 | 3 | D | 6 DL | 100 | 1.6325 | 1.6325 | 2014-04-30 19:43 | 2014-05-01 | 11769.0891 |  |  |  | 895 | 11769 | 8055 |  |  | 0 | 40 | 0 | 5.96 | 5890.43
| EOP 4 : 2014\Apr | EOP 4 : 2014 | Apr | [6 empty] | 2014-05-01 | 2014-05-01 |  | 3794501 |  | 135254 | 219258 | 4432698 | 2307396 | 694099 | 441228 | 42.49 | 0 | 322.56 | 8.03 | 5694.93
TS5500Shv | DT\20\004\A | DT | 20 | 4 | A | 1 Prestrip - Thick | 43.3841 | 8.533 | 8.533 | 2014-05-01 | 2014-05-06 21:36 | 47441.1769 | 47441 | [7 empty] | 0 | 0 | 3.21 | 12.31 | 5314.21
DRE1 | SC\18\003\D | SC | 18 | 3 | D | 6 DL | 100 | 98.3675 | 98.3675 | 2014-05-01 | 2014-05-09 16:02 | 709150.2506 |  |  |  | 53928 | 709150 | 485350 |  |  | 0 | 40 | 0 | 5.96 | 5890.43
PH4100A | BW\16\005\D | BW | 16 | 5 | D | 1 Prestrip - Thick | 100 | 65.5674 | 65.5674 | 2014-05-01 | 2014-05-04 10:15 | 150970.5607 | 150971 | [7 empty] | 0 | 0 | 14.37 | 5.4 | 5938.31
TS6060#1 | DT\23\003\A2 | DT | 23 | 3 | A2 | 1 Prestrip - Thick | 20 | 43.4034 | 8.6807 | 2014-05-01 | 2014-05-02 17:50 | 45491.1787 | 45491 | [7 empty] | 0 | 0 | 2.82 | 14.82 | 5134.23
TS5500Exc | BC\29\006\D | BC | 29 | 6 | D | 7 PostStrip | 100 | 0 | 4.5668 | 2014-05-01 | 2014-05-01 02:26 | 2281.8863 |  |  | 2282 | [5 empty] | 0 | 0 | 0 | 6.59 | 5833.71
PH4100XPC#1 | MW\16\013\D | MW | 16 | 13 | D | 1 Prestrip - Thick | 50 | 0 | 32.0927 | 2014-05-01 | 2014-05-01 23:47 | 53205.8646 | 53206 | [7 empty] | 0 | 0 | 7.12 | 5.85 | 5896.04
TS Fleet 5 | No Production | No Production | [7 empty] | 2014-05-01 | 2014-06-01
DRE2 | No Production | No Production | [7 empty] | 2014-05-01 | 2014-06-01
TS5500Exc | SC\20\001\B | SC | 20 | 1 | B | 8 Coal Mining | 100 | 0 | 49.7 | 2014-05-01 02:26 | 2014-05-02 05:17 | 35842.3059 | [6 empty] | 35842 | 26419 | 1.95 | 0 | 0 | 8.61 | 5615
PH4100XPC#1 | MW\15\012\D | MW | 15 | 12 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-05-01 23:47 | 2014-05-03 08:36 | 75056.3584 | 75056 | [7 empty] | 0 | 0 | 9.75 | 5.64 | 5915.07
TS5500Exc | SC\20\002\B | SC | 20 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-05-02 05:17 | 2014-05-04 04:01 | 62390.3141 | [6 empty] | 62390 | 46050 | 3.86 | 0 | 0 | 8.75 | 5600
TS6060#1 | DT\24\003\A2 | DT | 24 | 3 | A2 | 1 Prestrip - Thick | 20 | 100 | 20 | 2014-05-02 17:50 | 2014-05-06 23:18 | 109650.2903 | 109650 | [7 empty] | 0 | 0 | 7.58 | 15.37 | 5096.2
PH4100XPC#1 | MW\16\012\D | MW | 16 | 12 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-05-03 08:36 | 2014-05-05 06:53 | 103670.5609 | 103671 | [7 empty] | 0 | 0 | 10.3 | 5.65 | 5915.03
TS5500Exc | SC\20\003\B | SC | 20 | 3 | B | 8 Coal Mining | 70.9 | 0 | 70.9 | 2014-05-04 04:01 | 2014-05-05 12:59 | 43994.3357 | [6 empty] | 43994 | 32519 | 2.72 | 0 | 0 | 8.87 | 5589
PH4100A | SC\20\002\D | SC | 20 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-05-04 10:15 | 2014-05-06 23:46 | 112892.9525 | 112893 | [7 empty] | 0 | 0 | 9.41 | 6.37 | 5854.81
PH4100XPC#1 | MW\15\011\D | MW | 15 | 11 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-05-05 06:53 | 2014-05-07 05:46 | 104668.6056 | 104669 | [7 empty] | 0 | 0 | 12.57 | 5.63 | 5916.55
TS5500Exc | SC\20\001\D | SC | 20 | 1 | D | 1 Prestrip - Thick | 79.4972 | 53.7084 | 53.7084 | 2014-05-05 12:59 | 2014-05-08 03:07 | 58242.3122 | 58242 | [7 empty] | 0 | 0 | 5.42 | 6.69 | 5827.3
TS5500Shv | SC\21\003\B | SC | 21 | 3 | B | 8 Coal Mining | 100 | 0 | 13.6 | 2014-05-06 21:36 | 2014-05-07 19:51 | 8501.9153 | [6 empty] | 8502 | 6289 | 0.52 | 0 | 0 | 8.89 | 5586
TS6060#1 | DT\25\003\A | DT | 25 | 3 | A | 1 Prestrip - Thick | 20 | 0 | 20 | 2014-05-06 23:18 | 2014-05-11 19:37 | 124938.945 | 124939 | [7 empty] | 0 | 0 | 8.18 | 0 | 0
PH4100A | SC\20\001\D | SC | 20 | 1 | D | 1 Prestrip - Thick | 100 | 46.2916 | 46.2916 | 2014-05-06 23:46 | 2014-05-08 03:07 | 50199.4362 | 50199 | [7 empty] | 0 | 0 | 4.67 | 6.69 | 5827.3
PH4100XPC#1 | MW\16\011\D | MW | 16 | 11 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-05-07 05:46 | 2014-05-09 09:16 | 115140.1309 | 115140 | [7 empty] | 0 | 0 | 11.29 | 5.64 | 5915.15
TS5500Shv | SC\21\003\D | SC | 21 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-05-07 19:51 | 2014-05-22 11:04 | 118008.932 | 118009 | [7 empty] | 0 | 0 | 9.83 | 6.12 | 5877.22
TS5500Exc | SC\20\003\B | SC | 20 | 3 | B | 8 Coal Mining | 29.1 | 0 | 12.9 | 2014-05-08 03:07 | 2014-05-08 09:08 | 8028.1291 | [6 empty] | 8028 | 5934 | 0.5 | 0 | 0 | 8.87 | 5589
PH4100A | BW\16\006\D | BW | 16 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-05-08 03:07 | 2014-05-12 19:35 | 206375.3316 | 206375 | [7 empty] | 0 | 0 | 20.03 | 5.46 | 5934.58
TS5500Exc | SC\18\001\D | SC | 18 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-05-08 09:08 | 2014-05-11 13:44 | 102230.3354 | [6 empty] | 102230 | 76592 | 5.14 | 0 | 0 | 6.51 | 5843
PH4100XPC#1 | MW\15\010\D | MW | 15 | 10 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-05-09 09:16 | 2014-05-11 15:49 | 122434.8027 | 122435 | [7 empty] | 0 | 0 | 14.48 | 5.65 | 5914.45
DRE1 | SC\18\004\D | SC | 18 | 4 | D | 6 DL | 100 | 0 | 0 | 2014-05-09 16:02 | 2014-05-09 16:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE1 | SC\18\005\D | SC | 18 | 5 | D | 6 DL | 100 | 0 | 0 | 2014-05-09 16:02 | 2014-05-09 16:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE1 | SC\18\006\D | SC | 18 | 6 | D | 6 DL | 100 | 0 | 0 | 2014-05-09 16:02 | 2014-05-09 16:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE1 | SC\19\011\D | SC | 19 | 11 | D | 6 DL | 100 | 100 | 90 | 2014-05-09 16:02 | 2014-05-21 17:21 | 986118.6574 |  |  |  | 51022 | 986119 | 451761 |  |  | 0 | 44.5 | 0 | 7.11 | 5788.29
TS5500Exc | SC\18\002\D | SC | 18 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-05-11 13:44 | 2014-05-14 01:33 | 79852.8612 | [6 empty] | 79853 | 60206 | 5.02 | 0 | 0 | 6.15 | 5874
PH4100XPC#1 | MW\16\010\D | MW | 16 | 10 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-05-11 15:49 | 2014-05-13 20:09 | 117018.6694 | 117019 | [7 empty] | 0 | 0 | 11.63 | 5.7 | 5910.28
TS6060#1 | DT\26\003\A | DT | 26 | 3 | A | 1 Prestrip - Thick | 20 | 0 | 20 | 2014-05-11 19:37 | 2014-05-14 15:28 | 73030.5474 | 73031 | [7 empty] | 0 | 0 | 4.86 | 0 | 0
PH4100A | BW\16\007\D | BW | 16 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-05-12 19:35 | 2014-05-17 07:09 | 197405.1928 | 197405 | [7 empty] | 0 | 0 | 18.58 | 5.8 | 5904.49
PH4100XPC#1 | MW\15\009\D | MW | 15 | 9 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-05-13 20:09 | 2014-05-16 11:54 | 143268.4665 | 143268 | [7 empty] | 0 | 0 | 16.64 | 5.6 | 5919.22
TS5500Exc | SC\18\003\D | SC | 18 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-05-14 01:33 | 2014-05-16 11:59 | 77990.8568 | [6 empty] | 77991 | 58896 | 4.91 | 0 | 0 | 5.96 | 5890
TS6060#1 | DT\27\003\A | DT | 27 | 3 | A | 1 Prestrip - Thick | 20 | 100 | 20 | 2014-05-14 15:28 | 2014-05-15 21:26 | 32599.8918 | 32600 | [7 empty] | 0 | 0 | 2.04 | 19.49 | 4771.52
TS6060#1 | DT\28\003\A | DT | 28 | 3 | A | 1 Prestrip - Thick | 20 | 0 | 20 | 2014-05-15 21:26 | 2014-05-16 16:28 | 20667.6083 | 20668 | [7 empty] | 0 | 0 | 1.93 | 0 | 0
PH4100XPC#1 | MW\16\009\D | MW | 16 | 9 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-05-16 11:54 | 2014-05-18 14:04 | 112481.0155 | 112481 | [7 empty] | 0 | 0 | 11.22 | 5.75 | 5906.67
TS5500Exc | SC\18\004\D | SC | 18 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-05-16 11:59 | 2014-05-18 21:56 | 77345.4117 | [6 empty] | 77345 | 58408 | 4.87 | 0 | 0 | 5.81 | 5903
TS6060#1 | DT\18\004\A | DT | 18 | 4 | A | 1 Prestrip - Thick | 20 | 100 | 20 | 2014-05-16 16:28 | 2014-05-17 22:28 | 32693.068 | 32693 | [7 empty] | 0 | 0 | 2.51 | 11.72 | 5380.89
PH4100A | BW\16\008\D | BW | 16 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-05-17 07:09 | 2014-05-22 04:06 | 214650.7018 | 214651 | [7 empty] | 0 | 0 | 20.22 | 6.02 | 5885.31
TS6060#1 | MW\15\004\D | MW | 15 | 4 | D | 1 Prestrip - Thick | 20 | 20 | 20 | 2014-05-17 22:28 | 2014-05-20 00:10 | 52565.4612 | 52565 | [7 empty] | 0 | 0 | 6.27 | 5.57 | 5922.54
PH4100XPC#1 | MW\15\008\D | MW | 15 | 8 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-05-18 14:04 | 2014-05-20 10:49 | 102154.6654 | 102155 | [7 empty] | 0 | 0 | 12.58 | 5.63 | 5916.91
TS5500Exc | SC\18\005\D | SC | 18 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-05-18 21:56 | 2014-05-21 08:48 | 78587.8951 | [6 empty] | 78588 | 59438 | 5.01 | 0 | 0 | 5.74 | 5910
TS6060#1 | MW\15\005\D | MW | 15 | 5 | D | 1 Prestrip - Thick | 20 | 20 | 20 | 2014-05-20 00:10 | 2014-05-21 23:05 | 49531.1177 | 49531 | [7 empty] | 0 | 0 | 5.91 | 5.9 | 5893.21
PH4100XPC#1 | MW\16\008\D | MW | 16 | 8 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-05-20 10:49 | 2014-05-21 14:47 | 63692.1718 | 63692 | [7 empty] | 0 | 0 | 6.44 | 5.8 | 5901.82
TS5500Exc | SC\18\006\D | SC | 18 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-05-21 08:48 | 2014-05-23 17:19 | 75435.8877 | [6 empty] | 75436 | 57239 | 4.81 | 0 | 0 | 5.84 | 5900
PH4100XPC#1 | MW\15\007\D | MW | 15 | 7 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-05-21 14:47 | 2014-05-23 21:20 | 122200.4688 | 122200 | [7 empty] | 0 | 0 | 14.05 | 6.08 | 5875.92
DRE1 | SC\19\010\D | SC | 19 | 10 | D | 6 DL | 100 | 100 | 90 | 2014-05-21 17:21 | 2014-05-29 18:02 | 656789.1698 |  |  |  | 55207 | 656789 | 433348 |  |  | 0 | 45 | 0 | 6.66 | 5829.38
TS6060#1 | MW\15\006\D | MW | 15 | 6 | D | 1 Prestrip - Thick | 20 | 20 | 20 | 2014-05-21 23:05 | 2014-05-23 14:23 | 41393.8204 | 41394 | [7 empty] | 0 | 0 | 5.15 | 6.03 | 5881.33
PH4100A | BW\16\009\D | BW | 16 | 9 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-05-22 04:06 | 2014-05-26 14:40 | 195568.7789 | 195569 | [7 empty] | 0 | 0 | 18.5 | 5.72 | 5910.86
TS5500Shv | DT\20\004\A | DT | 20 | 4 | A | 1 Prestrip - Thick | 44.8306 | 13.7942 | 13.7942 | 2014-05-22 11:04 | 2014-06-01 | 76692.426 | 76692 | [7 empty] | 0 | 0 | 5.19 | 12.31 | 5314.21
TS6060#1 | MW\15\007\D | MW | 15 | 7 | D | 1 Prestrip - Thick | 20 | 20 | 20 | 2014-05-23 14:23 | 2014-05-25 12:24 | 48880.1875 | 48880 | [7 empty] | 0 | 0 | 5.62 | 6.08 | 5875.92
TS5500Exc | SC\19\011\D | SC | 19 | 11 | D | 7 PostStrip | 100 | 0 | 100 | 2014-05-23 17:19 | 2014-05-26 21:21 | 71251.2253 |  |  | 71251 | [5 empty] | 0 | 0 | 0 | 7.11 | 5788.29
PH4100XPC#1 | MW\16\007\D | MW | 16 | 7 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-05-23 21:20 | 2014-05-26 01:00 | 115650.2954 | 115650 | [7 empty] | 0 | 0 | 11.5 | 6.1 | 5874.65
TS6060#1 | MW\15\008\D | MW | 15 | 8 | D | 1 Prestrip - Thick | 20 | 40 | 20 | 2014-05-25 12:24 | 2014-05-27 02:34 | 40861.8662 | 40862 | [7 empty] | 0 | 0 | 5.03 | 5.63 | 5916.91
PH4100XPC#1 | MW\15\006\D | MW | 15 | 6 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-05-26 01:00 | 2014-05-28 00:10 | 103484.551 | 103485 | [7 empty] | 0 | 0 | 12.88 | 6.03 | 5881.33
PH4100A | BW\16\010\D | BW | 16 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-05-26 14:40 | 2014-05-30 11:55 | 171126.0552 | 171126 | [7 empty] | 0 | 0 | 17.92 | 5.99 | 5887.46
TS5500Exc | SC\19\011\D | SC | 19 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-05-26 21:21 | 2014-05-29 09:45 | 80626.9276 | [6 empty] | 80627 | 60069 | 4.76 | 0 | 0 | 7.11 | 5788
TS6060#1 | MW\15\009\D | MW | 15 | 9 | D | 1 Prestrip - Thick | 20 | 20 | 20 | 2014-05-27 02:34 | 2014-05-29 08:26 | 57307.3866 | 57307 | [7 empty] | 0 | 0 | 6.66 | 5.6 | 5919.22
PH4100XPC#1 | MW\16\006\D | MW | 16 | 6 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-05-28 00:10 | 2014-05-30 07:37 | 121441.9482 | 121442 | [7 empty] | 0 | 0 | 12.16 | 6.11 | 5874.79
TS6060#1 | BW\16\002\D | BW | 16 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2014-05-29 08:26 | 2014-05-31 09:06 | 53206.1912 |  |  | 53206 | [5 empty] | 0 | 0 | 0 | 5.6 | 5922.42
TS5500Exc | BC\29\005\D | BC | 29 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-05-29 09:45 | 2014-05-31 10:33 | 65153.2398 | [6 empty] | 65153 | 49075 | 4.88 | 0 | 0 | 6.33 | 5858
DRE1 | SC\19\009\D | SC | 19 | 9 | D | 6 DL | 100 | 27.9613 | 25.1652 | 2014-05-29 18:02 | 2014-06-01 | 183940.3222 |  |  |  | 15461 | 183940 | 121364 |  |  | 0 | 45 | 0 | 6.34 | 5855.91
PH4100XPC#1 | MW\15\005\D | MW | 15 | 5 | D | 1 Prestrip - Thick | 50 | 0 | 36.0086 | 2014-05-30 07:37 | 2014-06-01 | 89177.4198 | 89177 | [7 empty] | 0 | 0 | 10.64 | 5.9 | 5893.21
PH4100A | DT\19\003\A2 | DT | 19 | 3 | A2 | 1 Prestrip - Thick | 70 | 0 | 11.5417 | 2014-05-30 11:55 | 2014-06-01 | 67372.0626 | 67372 | [7 empty] | 0 | 0 | 3.56 | 15.68 | 5033.99
TS6060#1 | MW\15\010\D | MW | 15 | 10 | D | 1 Prestrip - Thick | 20 | 12.9325 | 6.4663 | 2014-05-31 09:06 | 2014-06-01 | 15833.8916 | 15834 | [7 empty] | 0 | 0 | 1.87 | 5.65 | 5914.45
TS5500Exc | SC\19\010\D | SC | 19 | 10 | D | 8 Coal Mining | 100 | 0 | 22.6 | 2014-05-31 10:33 | 2014-06-01 | 17932.5511 | [6 empty] | 17933 | 13456 | 1.12 | 0 | 0 | 6.66 | 5829
| EOP 5 : 2014\May | EOP 5 : 2014 | May | [6 empty] | 2014-06-01 | 2014-06-01 |  | 4077137 |  | 126739 | 175618 | 2535998 | 1491823 | 813913 | 610590 | 50.06 | 0 | 402.6 | 6.43 | 5845.16
TS5500Shv | DT\20\004\A | DT | 20 | 4 | A | 1 Prestrip - Thick | 44.8306 | 31.0364 | 31.0364 | 2014-06-01 | 2014-06-22 11:04 | 172554.1688 | 172554 | [7 empty] | 0 | 0 | 11.69 | 12.31 | 5314.21
DRE2 | BC\29\004\D | BC | 29 | 4 | D | 6 DL | 100 | 69.5036 | 69.5036 | 2014-06-01 | 2014-06-06 19:35 | 319292.2796 |  |  |  | 7459 | 319292 | 141727 |  |  | 0 | 21.98 | 0 | 6.04 | 5883.72
DRE1 | SC\19\009\D | SC | 19 | 9 | D | 6 DL | 100 | 72.0387 | 64.8348 | 2014-06-01 | 2014-06-06 19:01 | 473897.9244 |  |  |  | 39834 | 473898 | 312677 |  |  | 0 | 45 | 0 | 6.34 | 5855.91
PH4100A | DT\19\003\A2 | DT | 19 | 3 | A2 | 1 Prestrip - Thick | 70 | 0 | 53.4583 | 2014-06-01 | 2014-06-07 23:04 | 312052.1005 | 312052 | [7 empty] | 0 | 0 | 16.49 | 15.68 | 5033.99
TS6060#1 | MW\15\010\D | MW | 15 | 10 | D | 1 Prestrip - Thick | 20 | 27.0675 | 13.5337 | 2014-06-01 | 2014-06-02 07:10 | 33140.0294 | 33140 | [7 empty] | 0 | 0 | 3.92 | 5.65 | 5914.45
TS5500Exc | SC\19\010\D | SC | 19 | 10 | D | 8 Coal Mining | 100 | 0 | 77.4 | 2014-06-01 | 2014-06-02 21:56 | 61327.131 | [6 empty] | 61327 | 46018 | 3.83 | 0 | 0 | 6.66 | 5829
PH4100XPC#1 | MW\15\005\D | MW | 15 | 5 | D | 1 Prestrip - Thick | 50 | 0 | 13.9914 | 2014-06-01 | 2014-06-01 15:41 | 34650.3745 | 34650 | [7 empty] | 0 | 0 | 4.13 | 5.9 | 5893.21
TS Fleet 5 | No Production | No Production | [7 empty] | 2014-06-01 | 2014-07-01
PH4100XPC#1 | MW\16\005\D | MW | 16 | 5 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-06-01 15:41 | 2014-06-04 01:50 | 127993.4315 | 127993 | [7 empty] | 0 | 0 | 12.86 | 6.03 | 5882.21
TS6060#1 | BW\16\003\D | BW | 16 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2014-06-02 07:10 | 2014-06-04 07:52 | 53245.0429 |  |  | 53245 | [5 empty] | 0 | 0 | 0 | 6.03 | 5883.43
TS5500Exc | SC\20\003\B | SC | 20 | 3 | B | 8 Coal Mining | 29.1 | 0 | 16.1 | 2014-06-02 21:56 | 2014-06-03 05:27 | 10018.4922 | [6 empty] | 10018 | 7405 | 0.62 | 0 | 0 | 8.87 | 5589
TS5500Exc | SC\20\004\B | SC | 20 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-06-03 05:27 | 2014-06-05 01:10 | 58366.7895 | [6 empty] | 58367 | 43148 | 3.93 | 0 | 0 | 8.93 | 5584
PH4100XPC#1 | MW\15\004\D | MW | 15 | 4 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-06-04 01:50 | 2014-06-06 13:05 | 131413.6531 | 131414 | [7 empty] | 0 | 0 | 15.68 | 5.57 | 5922.54
TS6060#1 | MW\15\011\D | MW | 15 | 11 | D | 1 Prestrip - Thick | 20 | 20 | 20 | 2014-06-04 07:52 | 2014-06-05 23:20 | 41867.4422 | 41867 | [7 empty] | 0 | 0 | 5.03 | 5.63 | 5916.55
TS5500Exc | SC\20\005\B | SC | 20 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-06-05 01:10 | 2014-06-06 09:58 | 43771.4505 | [6 empty] | 43771 | 32279 | 2.98 | 0 | 0 | 9.33 | 5550
TS6060#1 | MW\15\012\D | MW | 15 | 12 | D | 1 Prestrip - Thick | 20 | 40 | 20 | 2014-06-05 23:20 | 2014-06-07 03:21 | 30022.5433 | 30023 | [7 empty] | 0 | 0 | 3.9 | 5.64 | 5915.07
TS5500Exc | SC\21\001\B | SC | 21 | 1 | B | 8 Coal Mining | 66.4 | 0 | 66.4 | 2014-06-06 09:58 | 2014-06-07 14:52 | 38572.1386 | [6 empty] | 38572 | 28451 | 2.59 | 0 | 0 | 8.65 | 5609
PH4100XPC#1 | MW\16\004\D | MW | 16 | 4 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-06-06 13:05 | 2014-06-08 22:31 | 126818.5158 | 126819 | [7 empty] | 0 | 0 | 12.69 | 5.75 | 5906.75
DRE1 | SC\19\008\D | SC | 19 | 8 | D | 6 DL | 100 | 100 | 90 | 2014-06-06 19:01 | 2014-06-14 20:40 | 660050.7515 |  |  |  | 55481 | 660051 | 435500 |  |  | 0 | 45 | 0 | 6.34 | 5855.66
DRE2 | BC\29\003\D | BC | 29 | 3 | D | 6 DL | 100 | 100 | 100 | 2014-06-06 19:35 | 2014-06-14 06:58 | 410301.819 |  |  |  | 9138 | 410302 | 173630 |  |  | 0 | 20.93 | 0 | 5.58 | 5924.05
TS6060#1 | BW\16\004\D | BW | 16 | 4 | D | 7 PostStrip | 85.3751 | 0 | 85.3751 | 2014-06-07 03:21 | 2014-06-08 20:36 | 45111.7467 |  |  | 45112 | [5 empty] | 0 | 0 | 0 | 5.75 | 5907.82
TS5500Exc | SC\20\003\D | SC | 20 | 3 | D | 1 Prestrip - Thick | 91.4891 | 91.4891 | 91.4891 | 2014-06-07 14:52 | 2014-06-12 07:47 | 105833.4753 | 105833 | [7 empty] | 0 | 0 | 8.81 | 6.06 | 5882.29
PH4100A | SC\20\005\D | SC | 20 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-06-07 23:04 | 2014-06-10 14:47 | 116926.6657 | 116927 | [7 empty] | 0 | 0 | 9.74 | 5.82 | 5903.64
TS6060#1 | BW\16\004\D | BW | 16 | 4 | D | 7 PostStrip | 14.6249 | 0 | 14.6249 | 2014-06-08 20:36 | 2014-06-09 03:41 | 7727.7072 |  |  | 7728 | [5 empty] | 0 | 0 | 0 | 5.75 | 5907.82
PH4100XPC#1 | MW\16\003\D | MW | 16 | 3 | D | 1 Prestrip - Thick | 50 | 0 | 50 | 2014-06-08 22:31 | 2014-06-09 19:58 | 49849.2715 | 49849 | [7 empty] | 0 | 0 | 5.01 | 5.38 | 5939.4
TS6060#1 | BW\16\002\D | BW | 16 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-06-09 03:41 | 2014-06-11 01:33 | 65805.3161 | [6 empty] | 65805 | 49837 | 4.98 | 0 | 0 | 5.6 | 5922
PH4100XPC#1 | DT\15\005\B | DT | 15 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-06-09 19:58 | 2014-06-09 23:11 | 7466.3839 | 7466 | [7 empty] | 0 | 0 | 0.99 | 18.41 | 4812.77
PH4100XPC#1 | DT\16\005\A | DT | 16 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-06-09 23:11 | 2014-06-10 01:16 | 4944.0068 | 4944 | [7 empty] | 0 | 0 | 0.96 | 10.45 | 5468.92
PH4100XPC#1 | DT\16\004\B | DT | 16 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-06-10 01:16 | 2014-06-10 03:38 | 5661.4795 | 5661 | [7 empty] | 0 | 0 | 0.94 | 16.11 | 5001.7
PH4100XPC#1 | MW\15\013\D | MW | 15 | 13 | D | 1 Prestrip - Thick | 30 | 0 | 30 | 2014-06-10 03:38 | 2014-06-11 09:25 | 66268.6088 | 66269 | [7 empty] | 0 | 0 | 8.78 | 5.84 | 5895.38
PH4100A | SC\20\004\D | SC | 20 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-06-10 14:47 | 2014-06-13 08:33 | 120687.9651 | 120688 | [7 empty] | 0 | 0 | 10.04 | 5.87 | 5898.98
TS6060#1 | BW\16\003\D | BW | 16 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-06-11 01:33 | 2014-06-12 22:14 | 64068.8826 | [6 empty] | 64069 | 48329 | 4.83 | 0 | 0 | 6.03 | 5883
PH4100XPC#1 | MW\16\013\D | MW | 16 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 50 | 2014-06-11 09:25 | 2014-06-12 22:29 | 82893.9071 | 82894 | [7 empty] | 0 | 0 | 11.09 | 5.85 | 5896.04
TS5500Exc | BC\29\006\D | BC | 29 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-06-12 07:47 | 2014-06-14 11:01 | 68381.079 | [6 empty] | 68381 | 51428 | 4.76 | 0 | 0 | 6.59 | 5834
TS6060#1 | BW\16\004\D | BW | 16 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-06-12 22:14 | 2014-06-14 18:30 | 63485.0863 | [6 empty] | 63485 | 47928 | 4.79 | 0 | 0 | 5.75 | 5908
PH4100XPC#1 | MW\15\012\D | MW | 15 | 12 | D | 1 Prestrip - Thick | 30 | 60 | 30 | 2014-06-12 22:29 | 2014-06-13 18:11 | 45033.815 | 45034 | [7 empty] | 0 | 0 | 5.85 | 5.64 | 5915.07
PH4100A | SC\20\003\D | SC | 20 | 3 | D | 1 Prestrip - Thick | 100 | 8.5109 | 8.5109 | 2014-06-13 08:33 | 2014-06-13 13:55 | 9845.2468 | 9845 | [7 empty] | 0 | 0 | 0.82 | 6.06 | 5882.29
PH4100A | DT\20\003\A2 | DT | 20 | 3 | A2 | 1 Prestrip - Thick | 70 | 0 | 65 | 2014-06-13 13:55 | 2014-06-30 15:35 | 773178.7379 | 773179 | [7 empty] | 0 | 0 | 23.59 | 15.94 | 5016.11
PH4100XPC#1 | MW\16\012\D | MW | 16 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 50 | 2014-06-13 18:11 | 2014-06-15 16:27 | 103670.5609 | 103671 | [7 empty] | 0 | 0 | 10.3 | 5.65 | 5915.03
DRE2 | BC\29\002\D | BC | 29 | 2 | D | 6 DL | 100 | 100 | 100 | 2014-06-14 06:58 | 2014-06-19 12:36 | 287379.5586 |  |  |  | 11556 | 287380 | 181050 |  |  | 0 | 28.29 | 0 | 5.04 | 5959.82
TS5500Exc | DT\17\005\A | DT | 17 | 5 | A | 8 Coal Mining | 50.3 | 0 | 50.3 | 2014-06-14 11:01 | 2014-06-14 16:44 | 7626.9455 | [6 empty] | 7627 | 5595 | 1.9 | 0 | 0 | 10.7 | 5430
TS5500Exc | SC\21\001\B | SC | 21 | 1 | B | 8 Coal Mining | 33.6 | 0 | 33.6 | 2014-06-14 16:44 | 2014-06-15 07:20 | 19491.7919 | [6 empty] | 19492 | 14377 | 1.31 | 0 | 0 | 8.65 | 5609
TS6060#1 | BW\16\005\D | BW | 16 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2014-06-14 18:30 | 2014-06-16 18:31 | 52513.0901 |  |  | 52513 | [5 empty] | 0 | 0 | 0 | 5.4 | 5938.31
DRE1 | SC\19\007\D | SC | 19 | 7 | D | 6 DL | 100 | 100 | 90 | 2014-06-14 20:40 | 2014-06-22 22:21 | 660221.7646 |  |  |  | 55495 | 660222 | 435613 |  |  | 0 | 45 | 0 | 6.06 | 5881.07
TS5500Exc | SC\21\002\B | SC | 21 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-06-15 07:20 | 2014-06-17 06:13 | 62584.0653 | [6 empty] | 62584 | 46227 | 3.85 | 0 | 0 | 8.78 | 5596
PH4100XPC#1 | MW\15\011\D | MW | 15 | 11 | D | 1 Prestrip - Thick | 30 | 80 | 30 | 2014-06-15 16:27 | 2014-06-16 20:35 | 62801.1633 | 62801 | [7 empty] | 0 | 0 | 7.54 | 5.63 | 5916.55
TS6060#1 | BW\16\005\D | BW | 16 | 5 | D | 8 Coal Mining | 31.9 | 0 | 6.6 | 2014-06-16 18:31 | 2014-06-16 21:25 | 4154.7149 | [6 empty] | 4155 | 3147 | 0.31 | 0 | 0 | 5.4 | 5938
PH4100XPC#1 | MW\16\011\D | MW | 16 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 50 | 2014-06-16 20:35 | 2014-06-19 00:05 | 115140.1309 | 115140 | [7 empty] | 0 | 0 | 11.29 | 5.64 | 5915.15
TS6060#1 | BW\16\006\D | BW | 16 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2014-06-16 21:25 | 2014-06-18 20:32 | 51510.46 |  |  | 51510 | [5 empty] | 0 | 0 | 0 | 5.46 | 5934.58
TS5500Exc | SC\21\001\D | SC | 21 | 1 | D | 1 Prestrip - Thick | 24.307 | 24.307 | 24.307 | 2014-06-17 06:13 | 2014-06-18 01:10 | 17752.4777 | 17752 | [7 empty] | 0 | 0 | 2.28 | 6.67 | 5828.55
TS5500Exc | SC\21\002\D | SC | 21 | 2 | D | 1 Prestrip - Thick | 98.5252 | 98.5252 | 98.5252 | 2014-06-18 01:10 | 2014-06-22 21:27 | 108995.2461 | 108995 | [7 empty] | 0 | 0 | 9.08 | 6.43 | 5849.61
TS6060#1 | MW\15\003\D | MW | 15 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2014-06-18 20:32 | 2014-06-20 20:01 | 51917.3492 |  |  | 51917 | [5 empty] | 0 | 0 | 0 | 5.29 | 5947.52
PH4100XPC#1 | MW\15\010\D | MW | 15 | 10 | D | 1 Prestrip - Thick | 30 | 60 | 30 | 2014-06-19 00:05 | 2014-06-20 08:48 | 73460.8816 | 73461 | [7 empty] | 0 | 0 | 8.69 | 5.65 | 5914.45
DRE2 | BC\29\001\D | BC | 29 | 1 | D | 6 DL | 100 | 67.2574 | 67.2574 | 2014-06-19 12:36 | 2014-07-01 | 629918.3428 |  |  |  | 20454 | 629918 | 271739 |  |  | 0 | 30 | 0 | 5.33 | 5940.57
PH4100XPC#1 | MW\16\010\D | MW | 16 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 50 | 2014-06-20 08:48 | 2014-06-22 13:09 | 117018.6694 | 117019 | [7 empty] | 0 | 0 | 11.63 | 5.7 | 5910.28
TS6060#1 | BW\16\007\D | BW | 16 | 7 | D | 7 PostStrip | 100 | 0 | 100 | 2014-06-20 20:01 | 2014-06-22 20:35 | 53111.4236 |  |  | 53111 | [5 empty] | 0 | 0 | 0 | 5.8 | 5904.49
TS5500Shv | DT\20\004\A | DT | 20 | 4 | A | 1 Prestrip - Thick | 11.7853 | 11.7853 | 11.7853 | 2014-06-22 11:04 | 2014-06-30 14:39 | 65523.3414 | 65523 | [7 empty] | 0 | 0 | 4.44 | 12.31 | 5314.21
PH4100XPC#1 | MW\15\009\D | MW | 15 | 9 | D | 1 Prestrip - Thick | 30 | 80 | 30 | 2014-06-22 13:09 | 2014-06-24 03:24 | 85961.0799 | 85961 | [7 empty] | 0 | 0 | 9.98 | 5.6 | 5919.22
TS6060#1 | MW\15\013\D | MW | 15 | 13 | D | 1 Prestrip - Thick | 20 | 100 | 20 | 2014-06-22 20:35 | 2014-06-24 14:18 | 44179.0725 | 44179 | [7 empty] | 0 | 0 | 5.85 | 5.84 | 5895.38
TS5500Exc | MW\15\003\D | MW | 15 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-06-22 21:27 | 2014-06-24 18:47 | 60510.2619 | [6 empty] | 60510 | 45902 | 4.59 | 0 | 0 | 5.29 | 5948
DRE1 | SC\19\001\D | SC | 19 | 1 | D | 6 DL | 100 | 0 | 57.9143 | 2014-06-22 22:21 | 2014-07-01 | 660021.5595 |  |  |  | 40054 | 660022 | 275018 |  |  | 0 | 45 | 0 | 6.64 | 5831.9
PH4100XPC#1 | MW\16\009\D | MW | 16 | 9 | D | 1 Prestrip - Thick | 100 | 100 | 50 | 2014-06-24 03:24 | 2014-06-26 05:34 | 112481.0155 | 112481 | [7 empty] | 0 | 0 | 11.22 | 5.75 | 5906.67
TS6060#1 | BW\16\001\D | BW | 16 | 1 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-06-24 14:18 | 2014-06-30 22:56 | 166899.8489 | 166900 | [7 empty] | 0 | 0 | 19.42 | 5.51 | 5930.26
TS5500Exc | SC\19\009\D | SC | 19 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-06-24 18:47 | 2014-06-27 03:33 | 75764.9392 | [6 empty] | 75765 | 57077 | 4.76 | 0 | 0 | 6.34 | 5856
PH4100XPC#1 | MW\15\008\D | MW | 15 | 8 | D | 1 Prestrip - Thick | 30 | 60 | 30 | 2014-06-26 05:34 | 2014-06-27 08:25 | 61292.7993 | 61293 | [7 empty] | 0 | 0 | 7.55 | 5.63 | 5916.91
TS5500Exc | SC\19\008\D | SC | 19 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-06-27 03:33 | 2014-06-29 12:03 | 75412.8791 | [6 empty] | 75413 | 56767 | 4.73 | 0 | 0 | 6.34 | 5856
PH4100XPC#1 | MW\16\008\D | MW | 16 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 50 | 2014-06-27 08:25 | 2014-06-28 12:22 | 63692.1718 | 63692 | [7 empty] | 0 | 0 | 6.44 | 5.8 | 5901.82
PH4100XPC#1 | MW\15\007\D | MW | 15 | 7 | D | 1 Prestrip - Thick | 30 | 80 | 30 | 2014-06-28 12:22 | 2014-06-29 21:06 | 73320.2813 | 73320 | [7 empty] | 0 | 0 | 8.43 | 6.08 | 5875.92
TS5500Exc | SC\19\007\D | SC | 19 | 7 | D | 8 Coal Mining | 100 | 0 | 62.3 | 2014-06-29 12:03 | 2014-07-01 | 47976.0256 | [6 empty] | 47976 | 36317 | 3.03 | 0 | 0 | 6.06 | 5881
PH4100XPC#1 | MW\16\007\D | MW | 16 | 7 | D | 1 Prestrip - Thick | 100 | 52.035 | 26.0175 | 2014-06-29 21:06 | 2014-07-01 | 60178.605 | 60179 | [7 empty] | 0 | 0 | 5.98 | 6.1 | 5874.65
TS5500Shv | DT\20\004\A | DT | 20 | 4 | A | 8 Coal Mining | 26 | 0 | 4.1 | 2014-06-30 14:39 | 2014-07-01 | 3569.6215 | [6 empty] | 3570 | 2596 | 0.16 | 0 | 0 | 12.31 | 5314
PH4100A | DT\21\003\A1 | DT | 21 | 3 | A1 | 1 Prestrip - Thick | 70 | 0 | 4.0721 | 2014-06-30 15:35 | 2014-07-01 | 15475.345 | 15475 | [7 empty] | 0 | 0 | 0.97 | 15.23 | 5092.98
TS6060#1 | BW\16\001\D | BW | 16 | 1 | D | 7 PostStrip | 100 | 0 | 2.6738 | 2014-06-30 22:56 | 2014-07-01 | 1149.018 |  |  | 1149 | [5 empty] | 0 | 0 | 0 | 5.51 | 5930.26
| EOP 6 : 2014\Jun | EOP 6 : 2014 | Jun | [6 empty] | 2014-07-01 | 2014-07-01 |  | 3746945 |  | 316286 | 239471 | 4101084 | 2226955 | 830888 | 622830 | 57.96 | 0 | 314.11 | 6.84 | 5808.44
TS5500Shv | DT\20\004\A | DT | 20 | 4 | A | 8 Coal Mining | 26 | 0 | 21.8 | 2014-07-01 | 2014-07-03 03:47 | 18852.5504 | [6 empty] | 18853 | 13710 | 0.86 | 0 | 0 | 12.31 | 5314
DRE2 | BC\29\001\D | BC | 29 | 1 | D | 6 DL | 100 | 32.7426 | 32.7426 | 2014-07-01 | 2014-07-04 16:47 | 306660.0238 |  |  |  | 9957 | 306660 | 132290 |  |  | 0 | 30 | 0 | 5.33 | 5940.57
DRE1 | SC\19\001\D | SC | 19 | 1 | D | 6 DL | 100 | 0 | 42.0857 | 2014-07-01 | 2014-07-06 15:22 | 479630.1374 |  |  |  | 29106 | 479630 | 199853 |  |  | 0 | 45 | 0 | 6.64 | 5831.9
PH4100A | DT\21\003\A1 | DT | 21 | 3 | A1 | 1 Prestrip - Thick | 70 | 0 | 60.9279 | 2014-07-01 | 2014-07-06 04:05 | 231545.0089 | 231545 | [7 empty] | 0 | 0 | 14.45 | 15.23 | 5092.98
TS6060#1 | BW\16\001\D | BW | 16 | 1 | D | 7 PostStrip | 100 | 0 | 97.3262 | 2014-07-01 | 2014-07-02 13:43 | 41824.0837 |  |  | 41824 | [5 empty] | 0 | 0 | 0 | 5.51 | 5930.26
TS5500Exc | SC\19\007\D | SC | 19 | 7 | D | 8 Coal Mining | 100 | 0 | 37.7 | 2014-07-01 | 2014-07-01 21:25 | 28993.4006 | [6 empty] | 28993 | 21947 | 1.83 | 0 | 0 | 6.06 | 5881
PH4100XPC#1 | MW\16\007\D | MW | 16 | 7 | D | 1 Prestrip - Thick | 100 | 47.965 | 23.9825 | 2014-07-01 | 2014-07-02 00:27 | 55471.6904 | 55472 | [7 empty] | 0 | 0 | 5.52 | 6.1 | 5874.65
TS Fleet 5 | No Production | No Production | [7 empty] | 2014-07-01 | 2014-08-01
TS5500Exc | BC\29\002\D | BC | 29 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-07-01 21:25 | 2014-07-02 06:34 | 12402.174 | [6 empty] | 12402 | 9419 | 4.21 | 0 | 0 | 5.04 | 5960
PH4100XPC#1 | MW\15\006\D | MW | 15 | 6 | D | 1 Prestrip - Thick | 30 | 80 | 30 | 2014-07-02 00:27 | 2014-07-03 04:22 | 62090.7306 | 62091 | [7 empty] | 0 | 0 | 7.73 | 6.03 | 5881.33
TS5500Exc | BC\29\003\D | BC | 29 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-07-02 06:34 | 2014-07-04 06:41 | 65123.3331 | [6 empty] | 65123 | 49364 | 5.01 | 0 | 0 | 5.58 | 5924
TS6060#1 | BW\16\005\D | BW | 16 | 5 | D | 8 Coal Mining | 31.9 | 0 | 25.3 | 2014-07-02 13:43 | 2014-07-03 00:41 | 15961 | [6 empty] | 15961 | 12089 | 1.21 | 0 | 0 | 5.4 | 5938
TS6060#1 | BW\16\008\D | BW | 16 | 8 | D | 7 PostStrip | 100 | 0 | 100 | 2014-07-03 00:41 | 2014-07-05 00:33 | 53067.079 |  |  | 53067 | [5 empty] | 0 | 0 | 0 | 6.02 | 5885.31
TS5500Shv | MW\15\012\D | MW | 15 | 12 | D | 7 PostStrip | 24.2323 | 0 | 24.2323 | 2014-07-03 03:47 | 2014-07-04 19:48 | 12802.7254 |  |  | 12803 | [5 empty] | 0 | 0 | 0 | 5.64 | 5915.07
PH4100XPC#1 | MW\16\006\D | MW | 16 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 50 | 2014-07-03 04:22 | 2014-07-05 11:05 | 121441.9482 | 121442 | [7 empty] | 0 | 0 | 12.16 | 6.11 | 5874.79
TS5500Exc | BC\29\004\D | BC | 29 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-07-04 06:41 | 2014-07-06 06:42 | 64983.9535 | [6 empty] | 64984 | 49096 | 4.91 | 0 | 0 | 6.04 | 5884
DRE2 | BC\30\006\D | BC | 30 | 6 | D | 6 DL | 100 | 100 | 100 | 2014-07-04 16:47 | 2014-07-08 08:27 | 302753.0906 |  |  |  | 9889 | 302753 | 183095 |  |  | 0 | 22.79 | 0 | 6.56 | 5837.56
TS5500Shv | MW\15\013\D | MW | 15 | 13 | D | 7 PostStrip | 100 | 0 | 100 | 2014-07-04 19:48 | 2014-07-10 19:39 | 46031.9919 |  |  | 46032 | [5 empty] | 0 | 0 | 0 | 5.84 | 5895.38
TS6060#1 | BW\16\009\D | BW | 16 | 9 | D | 7 PostStrip | 100 | 0 | 100 | 2014-07-05 00:33 | 2014-07-07 00:13 | 52859.266 |  |  | 52859 | [5 empty] | 0 | 0 | 0 | 5.72 | 5910.86
PH4100XPC#1 | MW\15\005\D | MW | 15 | 5 | D | 1 Prestrip - Thick | 30 | 80 | 30 | 2014-07-05 11:05 | 2014-07-06 20:16 | 74296.6766 | 74297 | [7 empty] | 0 | 0 | 8.86 | 5.9 | 5893.21
PH4100A | DT\22\003\A1 | DT | 22 | 3 | A1 | 1 Prestrip - Thick | 70 | 0 | 70 | 2014-07-06 04:05 | 2014-07-12 08:43 | 278526.3606 | 278526 | [7 empty] | 0 | 0 | 17.88 | 15.3 | 5089.98
TS5500Exc | BC\29\001\D | BC | 29 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-07-06 06:42 | 2014-07-08 17:01 | 78941.5851 | [6 empty] | 78942 | 59892 | 4.45 | 0 | 0 | 5.33 | 5941
DRE1 | SC\19\002\D | SC | 19 | 2 | D | 6 DL | 100 | 0 | 100 | 2014-07-06 15:22 | 2014-07-15 03:49 | 724423.9707 |  |  |  | 60892 | 724424 | 477974 |  |  | 0 | 45 | 0 | 6.27 | 5863.28
PH4100XPC#1 | MW\16\005\D | MW | 16 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 50 | 2014-07-06 20:16 | 2014-07-09 05:39 | 127993.4315 | 127993 | [7 empty] | 0 | 0 | 12.86 | 6.03 | 5882.21
TS6060#1 | BW\16\010\D | BW | 16 | 10 | D | 7 PostStrip | 51.0631 | 0 | 51.0631 | 2014-07-07 00:13 | 2014-07-07 22:12 | 24375.3015 |  |  | 24375 | [5 empty] | 0 | 0 | 0 | 5.99 | 5887.46
TS6060#1 | BW\16\010\D | BW | 16 | 10 | D | 7 PostStrip | 48.9369 | 0 | 48.9369 | 2014-07-07 22:12 | 2014-07-08 19:16 | 23360.3696 |  |  | 23360 | [5 empty] | 0 | 0 | 0 | 5.99 | 5887.46
DRE2 | BC\30\005\D | BC | 30 | 5 | D | 6 DL | 100 | 100 | 100 | 2014-07-08 08:27 | 2014-07-12 08:02 | 330079.0989 |  |  |  | 18839 | 330079 | 250284 |  |  | 0 | 30 | 0 | 6.34 | 5856.59
TS5500Exc | SC\19\001\D | SC | 19 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2014-07-08 17:01 | 2014-07-11 16:34 | 68003.8881 |  |  | 68004 | [5 empty] | 0 | 0 | 0 | 6.64 | 5831.9
TS6060#1 | BW\16\001\D | BW | 16 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-07-08 19:16 | 2014-07-10 08:02 | 53478.5423 | [6 empty] | 53479 | 40533 | 5.06 | 0 | 0 | 5.51 | 5930
PH4100XPC#1 | MW\15\004\D | MW | 15 | 4 | D | 1 Prestrip - Thick | 30 | 80 | 30 | 2014-07-09 05:39 | 2014-07-10 16:43 | 78848.1919 | 78848 | [7 empty] | 0 | 0 | 9.41 | 5.57 | 5922.54
TS6060#1 | BW\16\005\D | BW | 16 | 5 | D | 8 Coal Mining | 68.1 | 0 | 68.1 | 2014-07-10 08:02 | 2014-07-11 13:34 | 42939.9639 | [6 empty] | 42940 | 32522 | 3.25 | 0 | 0 | 5.4 | 5938
PH4100XPC#1 | MW\16\004\D | MW | 16 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 50 | 2014-07-10 16:43 | 2014-07-13 01:23 | 126818.5158 | 126819 | [7 empty] | 0 | 0 | 12.69 | 5.75 | 5906.75
TS5500Shv | MW\15\010\D | MW | 15 | 10 | D | 7 PostStrip | 20.0686 | 0 | 20.0686 | 2014-07-10 19:39 | 2014-07-12 04:04 | 10377.1783 |  |  | 10377 | [5 empty] | 0 | 0 | 0 | 5.65 | 5914.45
TS6060#1 | BW\16\006\D | BW | 16 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-07-11 13:34 | 2014-07-13 10:09 | 64850.1961 | [6 empty] | 64850 | 49194 | 4.92 | 0 | 0 | 5.46 | 5935
TS5500Exc | SC\21\001\D | SC | 21 | 1 | D | 1 Prestrip - Thick | 100 | 75.693 | 75.693 | 2014-07-11 16:34 | 2014-07-14 02:44 | 55281.8167 | 55282 | [7 empty] | 0 | 0 | 7.1 | 6.67 | 5828.55
TS5500Shv | DT\21\004\A | DT | 21 | 4 | A | 1 Prestrip - Thick | 10.9854 | 10.9854 | 10.9854 | 2014-07-12 04:04 | 2014-07-20 11:07 | 63721.2766 | 63721 | [7 empty] | 0 | 0 | 4.28 | 13.93 | 5178.06
DRE2 | BC\30\004\D | BC | 30 | 4 | D | 6 DL | 100 | 100 | 100 | 2014-07-12 08:02 | 2014-07-15 04:34 | 236642.9199 |  |  |  | 10588 | 236643 | 201173 |  |  | 0 | 21.67 | 0 | 6.08 | 5879.38
PH4100A | DT\23\003\A2 | DT | 23 | 3 | A2 | 1 Prestrip - Thick | 70 | 0 | 70 | 2014-07-12 08:43 | 2014-07-20 12:15 | 366835.3619 | 366835 | [7 empty] | 0 | 0 | 22.71 | 14.82 | 5134.23
PH4100XPC#1 | MW\16\003\D | MW | 16 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 50 | 2014-07-13 01:23 | 2014-07-13 22:34 | 49849.2715 | 49849 | [7 empty] | 0 | 0 | 5.01 | 5.38 | 5939.4
TS6060#1 | BW\16\007\D | BW | 16 | 7 | D | 8 Coal Mining | 55.6 | 0 | 55.6 | 2014-07-13 10:09 | 2014-07-14 11:04 | 36245.2977 | [6 empty] | 36245 | 27450 | 2.75 | 0 | 0 | 5.8 | 5904
PH4100XPC#1 | BW\18\011\B | BW | 18 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 65 | 2014-07-13 22:34 | 2014-07-14 02:26 | 9246.2087 | 9246 | [7 empty] | 0 | 0 | 1.01 | 0 | 0
PH4100XPC#1 | BW\17\010\B | BW | 17 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 65 | 2014-07-14 02:26 | 2014-07-14 07:40 | 12704.0483 | 12704 | [7 empty] | 0 | 0 | 1.91 | 11.33 | 5379.68
TS5500Exc | BC\30\005\D | BC | 30 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-07-14 02:44 | 2014-07-16 02:46 | 65026.9207 | [6 empty] | 65027 | 48917 | 4.89 | 0 | 0 | 6.34 | 5857
PH4100XPC#1 | BW\18\010\B | BW | 18 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 65 | 2014-07-14 07:40 | 2014-07-14 14:12 | 15755.3752 | 15755 | [7 empty] | 0 | 0 | 2.26 | 10.65 | 5433.88
TS6060#1 | DT\20\004\A | DT | 20 | 4 | A | 8 Coal Mining | 74 | 0 | 74 | 2014-07-14 11:04 | 2014-07-16 07:04 | 63981.5566 | [6 empty] | 63982 | 46528 | 2.9 | 0 | 0 | 12.31 | 5314
PH4100XPC#1 | BW\17\009\B | BW | 17 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 65 | 2014-07-14 14:12 | 2014-07-15 10:28 | 50458.8036 | 50459 | [7 empty] | 0 | 0 | 4.24 | 12.48 | 5296.99
DRE1 | SC\19\003\D | SC | 19 | 3 | D | 6 DL | 100 | 0 | 100 | 2014-07-15 03:49 | 2014-07-23 17:07 | 727383.5061 |  |  |  | 61141 | 727384 | 479926 |  |  | 0 | 45 | 0 | 6 | 5886.6
DRE2 | BC\30\003\D | BC | 30 | 3 | D | 6 DL | 100 | 100 | 100 | 2014-07-15 04:34 | 2014-07-18 00:03 | 233071.0243 |  |  |  | 10428 | 233071 | 198136 |  |  | 0 | 21.37 | 0 | 5.47 | 5932.56
PH4100XPC#1 | BW\18\009\B | BW | 18 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 65 | 2014-07-15 10:28 | 2014-07-17 14:13 | 129245.1071 | 129245 | [7 empty] | 0 | 0 | 12.51 | 12.89 | 5264.3
TS5500Exc | BC\30\004\D | BC | 30 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-07-16 02:46 | 2014-07-18 02:49 | 65040.0301 | [6 empty] | 65040 | 49070 | 4.91 | 0 | 0 | 6.08 | 5879
TS6060#1 | DT\20\004\B | DT | 20 | 4 | B | 1 Prestrip - Thick | 76.4936 | 76.4936 | 76.4936 | 2014-07-16 07:04 | 2014-07-17 15:28 | 35922.0616 | 35922 | [7 empty] | 0 | 0 | 2.24 | 9.75 | 5479.03
PH4100XPC#1 | BW\17\008\B | BW | 17 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 65 | 2014-07-17 14:13 | 2014-07-19 09:31 | 105613.3502 | 105613 | [7 empty] | 0 | 0 | 8.46 | 13.24 | 5250.17
TS6060#1 | SC\21\002\D | SC | 21 | 2 | D | 1 Prestrip - Thick | 1.4748 | 1.4748 | 1.4748 | 2014-07-17 15:28 | 2014-07-17 16:56 | 1631.564 | 1632 | [7 empty] | 0 | 0 | 0.14 | 6.43 | 5849.61
TS6060#1 | MW\15\012\D | MW | 15 | 12 | D | 7 PostStrip | 75.7677 | 0 | 75.7677 | 2014-07-17 16:56 | 2014-07-19 05:02 | 40030.6383 |  |  | 40031 | [5 empty] | 0 | 0 | 0 | 5.64 | 5915.07
DRE2 | BC\30\001\D | BC | 30 | 1 | D | 6 DL | 100 | 100 | 100 | 2014-07-18 00:03 | 2014-07-25 04:50 | 596708.8785 |  |  |  | 34056 | 596709 | 452458 |  |  | 0 | 30 | 0 | 5.42 | 5935.64
TS5500Exc | BC\30\003\D | BC | 30 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-07-18 02:49 | 2014-07-20 12:06 | 77541.4948 | [6 empty] | 77541 | 58790 | 4.86 | 0 | 0 | 5.47 | 5933
TS6060#1 | MW\15\012\D | MW | 15 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-07-19 05:02 | 2014-07-20 20:53 | 57956.8588 | [6 empty] | 57957 | 43781 | 4.42 | 0 | 0 | 5.64 | 5915
PH4100XPC#1 | BW\18\008\B | BW | 18 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 65 | 2014-07-19 09:31 | 2014-07-22 15:09 | 188472.7251 | 188473 | [7 empty] | 0 | 0 | 18.44 | 13.99 | 5190.83
TS5500Shv | DT\20\004\B | DT | 20 | 4 | B | 1 Prestrip - Thick | 23.5064 | 23.5064 | 23.5064 | 2014-07-20 11:07 | 2014-07-21 21:37 | 11038.7897 | 11039 | [7 empty] | 0 | 0 | 0.69 | 9.75 | 5479.03
TS5500Exc | DT\15\005\B | DT | 15 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-07-20 12:06 | 2014-07-21 08:16 | 27276.711 | [6 empty] | 27277 | 19214 | 3.82 | 0 | 0 | 18.41 | 4813
PH4100A | DT\24\003\A2 | DT | 24 | 3 | A2 | 1 Prestrip - Thick | 70 | 0 | 70 | 2014-07-20 12:15 | 2014-07-28 22:17 | 383776.0161 | 383776 | [7 empty] | 0 | 0 | 26.54 | 15.37 | 5096.2
TS6060#1 | MW\15\011\D | MW | 15 | 11 | D | 7 PostStrip | 100 | 0 | 100 | 2014-07-20 20:53 | 2014-07-22 20:26 | 52725.7103 |  |  | 52726 | [5 empty] | 0 | 0 | 0 | 5.63 | 5916.55
TS5500Exc | DT\16\004\B | DT | 16 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-07-21 08:16 | 2014-07-22 15:48 | 42699.2255 | [6 empty] | 42699 | 30391 | 4.02 | 0 | 0 | 16.11 | 5002
TS5500Shv | DT\20\004\B | DT | 20 | 4 | B | 8 Coal Mining | 21 | 0 | 21 | 2014-07-21 21:37 | 2014-07-23 12:49 | 14272.0193 | [6 empty] | 14272 | 10490 | 0.65 | 0 | 0 | 9.75 | 5479
PH4100XPC#1 | BW\17\007\B | BW | 17 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 65 | 2014-07-22 15:09 | 2014-07-24 08:34 | 103106.6861 | 103107 | [7 empty] | 0 | 0 | 7.99 | 12.86 | 5289.86
TS5500Exc | BC\30\006\D | BC | 30 | 6 | D | 7 PostStrip | 62.0664 | 0 | 62.0664 | 2014-07-22 15:48 | 2014-07-24 03:14 | 33665.18 |  |  | 33665 | [5 empty] | 0 | 0 | 0 | 6.56 | 5837.56
TS6060#1 | DT\20\004\B | DT | 20 | 4 | B | 8 Coal Mining | 79 | 0 | 79 | 2014-07-22 20:26 | 2014-07-24 09:16 | 53555.547 | [6 empty] | 53556 | 39363 | 2.45 | 0 | 0 | 9.75 | 5479
TS5500Shv | DT\21\004\A | DT | 21 | 4 | A | 1 Prestrip - Thick | 100 | 11.2134 | 11.2134 | 2014-07-23 12:49 | 2014-08-01 | 65043.6861 | 65044 | [7 empty] | 0 | 0 | 4.37 | 13.93 | 5178.06
DRE1 | SC\19\004\D | SC | 19 | 4 | D | 6 DL | 100 | 0 | 95.5176 | 2014-07-23 17:07 | 2014-08-01 | 704665.9858 |  |  |  | 59231 | 704666 | 464938 |  |  | 0 | 45 | 0 | 5.82 | 5902.72
TS5500Exc | BC\30\006\D | BC | 30 | 6 | D | 7 PostStrip | 37.9336 | 0 | 37.9336 | 2014-07-24 03:14 | 2014-07-25 00:53 | 20575.4062 |  |  | 20575 | [5 empty] | 0 | 0 | 0 | 6.56 | 5837.56
PH4100XPC#1 | BW\18\007\B | BW | 18 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 65 | 2014-07-24 08:34 | 2014-07-27 08:55 | 177461.1938 | 177461 | [7 empty] | 0 | 0 | 16.16 | 12.88 | 5290.01
TS6060#1 | MW\15\011\D | MW | 15 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-07-24 09:16 | 2014-07-26 02:08 | 59449.5907 | [6 empty] | 59450 | 44877 | 4.49 | 0 | 0 | 5.63 | 5917
TS5500Exc | SC\19\001\D | SC | 19 | 1 | D | 8 Coal Mining | 13.5 | 0 | 13.5 | 2014-07-25 00:53 | 2014-07-25 10:01 | 12377.1789 | [6 empty] | 12377 | 9266 | 0.7 | 0 | 0 | 6.64 | 5832
DRE2 | MC\26\004\D | MC | 26 | 4 | D | 6 DL | 100 | 100 | 100 | 2014-07-25 04:50 | 2014-07-31 06:21 | 502510.6075 |  |  |  | 11700 | 502511 | 222298 |  |  | 0 | 23.85 | 0 | 6.02 | 5885.09
TS5500Exc | BC\30\001\D | BC | 30 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-07-25 10:01 | 2014-07-27 14:42 | 71301.1603 | [6 empty] | 71301 | 54076 | 4.5 | 0 | 0 | 5.42 | 5936
TS6060#1 | MW\15\010\D | MW | 15 | 10 | D | 7 PostStrip | 79.9314 | 0 | 79.9314 | 2014-07-26 02:08 | 2014-07-27 15:25 | 41331.2438 |  |  | 41331 | [5 empty] | 0 | 0 | 0 | 5.65 | 5914.45
PH4100XPC#1 | BW\17\006\B | BW | 17 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 65 | 2014-07-27 08:55 | 2014-07-28 11:42 | 65295.0426 | 65295 | [7 empty] | 0 | 0 | 5.19 | 11.06 | 5416.41
TS5500Exc | BC\30\006\D | BC | 30 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-07-27 14:42 | 2014-07-29 18:27 | 70055.6004 | [6 empty] | 70056 | 52673 | 4.78 | 0 | 0 | 6.56 | 5838
TS6060#1 | MW\15\010\D | MW | 15 | 10 | D | 8 Coal Mining | 3.3 | 0 | 3.3 | 2014-07-27 15:25 | 2014-07-27 16:45 | 1945.5505 | [6 empty] | 1946 | 1469 | 0.15 | 0 | 0 | 5.65 | 5914
TS6060#1 | BW\17\001\B | BW | 17 | 1 | B | 1 Prestrip - Thick | 35 | 78.7633 | 27.5672 | 2014-07-27 16:45 | 2014-08-01 | 112490.2451 | 112490 | [7 empty] | 0 | 0 | 8.15 | 10.86 | 5373.97
PH4100XPC#1 | BW\18\006\B | BW | 18 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 65 | 2014-07-28 11:42 | 2014-07-31 19:48 | 194643.5281 | 194644 | [7 empty] | 0 | 0 | 18.79 | 10.73 | 5446.04
PH4100A | DT\25\003\A | DT | 25 | 3 | A | 1 Prestrip - Thick | 70 | 0 | 22.7041 | 2014-07-28 22:17 | 2014-08-01 | 141831.1506 | 141831 | [7 empty] | 0 | 0 | 9.28 | 0 | 0
TS5500Exc | MW\17\003\B | MW | 17 | 3 | B | 1 Prestrip - Thick | 13.9915 | 0 | 13.9915 | 2014-07-29 18:27 | 2014-07-31 07:12 | 35043.3515 | 35043 | [7 empty] | 0 | 0 | 2.33 | 0 | 0
DRE2 | MC\26\005\D | MC | 26 | 5 | D | 6 DL | 100 | 12.4297 | 12.4297 | 2014-07-31 06:21 | 2014-08-01 | 60941.1566 |  |  |  | 1419 | 60941 | 26959 |  |  | 0 | 23.69 | 0 | 6.43 | 5848.15
TS5500Exc | MC\26\004\D | MC | 26 | 4 | D | 8 Coal Mining | 100 | 0 | 35.1 | 2014-07-31 07:12 | 2014-08-01 | 22719.7866 | [6 empty] | 22720 | 17218 | 1.72 | 0 | 0 | 6.02 | 5885
PH4100XPC#1 | BW\17\005\B | BW | 17 | 5 | B | 1 Prestrip - Thick | 100 | 6.61 | 4.2965 | 2014-07-31 19:48 | 2014-08-01 | 10494.1858 | 10494 | [7 empty] | 0 | 0 | 0.75 | 10.49 | 5431.58
| EOP 7 : 2014\Jul | EOP 7 : 2014 | Jul | [6 empty] | 2014-08-01 | 2014-08-01 |  | 3541993 |  | 521030 | 317246 | 5205470 | 3289383 | 1187971 | 891338 | 87.72 | 0 | 292.08 | 7.33 | 5765
TS5500Shv | DT\21\004\A | DT | 21 | 4 | A | 1 Prestrip - Thick | 100 | 41.0623 | 41.0623 | 2014-08-01 | 2014-09-01 | 238183.8618 | 238184 | [7 empty] | 0 | 0 | 15.99 | 13.93 | 5178.06
DRE1 | SC\19\004\D | SC | 19 | 4 | D | 6 DL | 100 | 0 | 4.4824 | 2014-08-01 | 2014-08-01 08:39 | 33067.9434 |  |  |  | 2780 | 33068 | 21818 |  |  | 0 | 45 | 0 | 5.82 | 5902.72
DRE2 | MC\26\005\D | MC | 26 | 5 | D | 6 DL | 100 | 87.5703 | 87.5703 | 2014-08-01 | 2014-08-06 04:19 | 429347.0844 |  |  |  | 9996 | 429347 | 189932 |  |  | 0 | 23.69 | 0 | 6.43 | 5848.15
PH4100A | DT\25\003\A | DT | 25 | 3 | A | 1 Prestrip - Thick | 70 | 0 | 47.2959 | 2014-08-01 | 2014-08-07 07:32 | 295455.1571 | 295455 | [7 empty] | 0 | 0 | 19.34 | 0 | 0
TS6060#1 | BW\17\001\B | BW | 17 | 1 | B | 1 Prestrip - Thick | 35 | 21.2367 | 7.4328 | 2014-08-01 | 2014-08-02 03:27 | 30330.3223 | 30330 | [7 empty] | 0 | 0 | 2.2 | 10.86 | 5373.97
TS5500Exc | MC\26\004\D | MC | 26 | 4 | D | 8 Coal Mining | 100 | 0 | 64.9 | 2014-08-01 | 2014-08-02 06:33 | 41933.0296 | [6 empty] | 41933 | 31778 | 3.18 | 0 | 0 | 6.02 | 5885
PH4100XPC#1 | BW\17\005\B | BW | 17 | 5 | B | 1 Prestrip - Thick | 100 | 93.39 | 60.7035 | 2014-08-01 | 2014-08-03 10:30 | 148268.3269 | 148268 | [7 empty] | 0 | 0 | 10.57 | 10.49 | 5431.58
TS Fleet 5 | No Production | No Production | [7 empty] | 2014-08-01 | 2014-09-01
DRE1 | SC\19\005\D | SC | 19 | 5 | D | 6 DL | 100 | 100 | 90 | 2014-08-01 08:39 | 2014-08-08 12:46 | 656699.4955 |  |  |  | 55199 | 656699 | 433289 |  |  | 0 | 45 | 0 | 5.77 | 5907.72
TS6060#1 | MW\15\008\D | MW | 15 | 8 | D | 7 PostStrip | 100 | 0 | 100 | 2014-08-02 03:27 | 2014-08-04 01:11 | 51420.1326 |  |  | 51420 | [5 empty] | 0 | 0 | 0 | 5.63 | 5916.91
TS5500Exc | MW\17\003\B | MW | 17 | 3 | B | 1 Prestrip - Thick | 86.0085 | 0 | 86.0085 | 2014-08-02 06:33 | 2014-08-11 13:24 | 215417.9434 | 215418 | [7 empty] | 0 | 0 | 14.33 | 0 | 0
PH4100XPC#1 | BW\18\005\B | BW | 18 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 65 | 2014-08-03 10:30 | 2014-08-07 05:31 | 228358.9865 | 228359 | [7 empty] | 0 | 0 | 20.65 | 10.5 | 5438.76
TS6060#1 | MW\15\007\D | MW | 15 | 7 | D | 7 PostStrip | 16.8604 | 0 | 16.8604 | 2014-08-04 01:11 | 2014-08-04 09:13 | 9027.9454 |  |  | 9028 | [5 empty] | 0 | 0 | 0 | 6.08 | 5875.92
TS6060#1 | MW\15\007\D | MW | 15 | 7 | D | 7 PostStrip | 83.1396 | 0 | 83.1396 | 2014-08-04 09:13 | 2014-08-06 00:49 | 44517.4086 |  |  | 44517 | [5 empty] | 0 | 0 | 0 | 6.08 | 5875.92
TS6060#1 | MW\15\010\D | MW | 15 | 10 | D | 8 Coal Mining | 96.7 | 0 | 96.7 | 2014-08-06 00:49 | 2014-08-07 15:08 | 56506.9508 | [6 empty] | 56507 | 42655 | 4.27 | 0 | 0 | 5.65 | 5914
DRE2 | MC\26\006\D | MC | 26 | 6 | D | 6 DL | 100 | 100 | 100 | 2014-08-06 04:19 | 2014-08-09 08:54 | 264465.5087 |  |  |  | 11833 | 264466 | 224825 |  |  | 0 | 23.86 | 0 | 7.09 | 5788.92
PH4100XPC#1 | BW\17\004\B | BW | 17 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 35 | 2014-08-07 05:31 | 2014-08-07 20:27 | 36930.1738 | 36930 | [7 empty] | 0 | 0 | 2.58 | 11.08 | 5370.66
PH4100A | DT\26\003\A | DT | 26 | 3 | A | 1 Prestrip - Thick | 70 | 0 | 70 | 2014-08-07 07:32 | 2014-08-12 18:01 | 255606.9159 | 255607 | [7 empty] | 0 | 0 | 17.01 | 0 | 0
TS6060#1 | MW\15\013\D | MW | 15 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-08-07 15:08 | 2014-08-08 22:51 | 46757.0071 | [6 empty] | 46757 | 35314 | 4.22 | 0 | 0 | 5.84 | 5895
PH4100XPC#1 | BW\18\004\B | BW | 18 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 35 | 2014-08-07 20:27 | 2014-08-09 15:53 | 107206.115 | 107206 | [7 empty] | 0 | 0 | 10.98 | 11.22 | 5364.65
DRE1 | SC\19\006\D | SC | 19 | 6 | D | 6 DL | 100 | 100 | 90 | 2014-08-08 12:46 | 2014-08-16 12:04 | 729987.5616 |  |  |  | 55307 | 729988 | 434139 |  |  | 0 | 45 | 0 | 5.83 | 5901.96
TS6060#1 | MW\15\004\D | MW | 15 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2014-08-08 22:51 | 2014-08-10 19:43 | 50437.9459 |  |  | 50438 | [5 empty] | 0 | 0 | 0 | 5.57 | 5922.54
DRE2 | MC\26\007\D | MC | 26 | 7 | D | 6 DL | 100 | 100 | 100 | 2014-08-09 08:54 | 2014-08-15 11:46 | 507197.017 |  |  |  | 15088 | 507197 | 236373 |  |  | 0 | 25.22 | 0 | 7.38 | 5765.04
PH4100XPC#1 | BW\17\003\B | BW | 17 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 65 | 2014-08-09 15:53 | 2014-08-11 09:44 | 102827.6863 | 102828 | [7 empty] | 0 | 0 | 8.87 | 10.85 | 5370.37
TS6060#1 | MW\15\004\D | MW | 15 | 4 | D | 8 Coal Mining | 27.1 | 0 | 27.1 | 2014-08-10 19:43 | 2014-08-11 06:37 | 16088.0421 | [6 empty] | 16088 | 12184 | 1.22 | 0 | 0 | 5.57 | 5923
TS6060#1 | MW\15\005\D | MW | 15 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2014-08-11 06:37 | 2014-08-13 04:02 | 51059.4682 |  |  | 51059 | [5 empty] | 0 | 0 | 0 | 5.9 | 5893.21
PH4100XPC#1 | BW\18\003\B | BW | 18 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 65 | 2014-08-11 09:44 | 2014-08-12 00:57 | 37405.8165 | 37406 | [7 empty] | 0 | 0 | 3.74 | 10.94 | 5367.82
TS5500Exc | MC\26\005\D | MC | 26 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-08-11 13:24 | 2014-08-13 11:03 | 62628.3761 | [6 empty] | 62628 | 47188 | 4.71 | 0 | 0 | 6.43 | 5848
PH4100XPC#1 | BW\17\002\B | BW | 17 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 35 | 2014-08-12 00:57 | 2014-08-13 12:26 | 88675.4464 | 88675 | [7 empty] | 0 | 0 | 6.87 | 11.02 | 5353.69
PH4100A | DT\27\003\A | DT | 27 | 3 | A | 1 Prestrip - Thick | 70 | 0 | 70 | 2014-08-12 18:01 | 2014-08-15 05:52 | 114099.6213 | 114100 | [7 empty] | 0 | 0 | 7.13 | 19.49 | 4771.52
TS6060#1 | MW\15\006\D | MW | 15 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2014-08-13 04:02 | 2014-08-15 01:03 | 50594.9284 |  |  | 50595 | [5 empty] | 0 | 0 | 0 | 6.03 | 5881.33
TS5500Exc | MC\26\006\D | MC | 26 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-08-13 11:03 | 2014-08-15 07:19 | 60761.7111 | [6 empty] | 60762 | 45372 | 4.53 | 0 | 0 | 7.09 | 5789
PH4100XPC#1 | BW\18\002\B | BW | 18 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 35 | 2014-08-13 12:26 | 2014-08-15 22:58 | 148180.9402 | 148181 | [7 empty] | 0 | 0 | 16.94 | 11.22 | 5340.85
TS6060#1 | MW\15\009\D | MW | 15 | 9 | D | 7 PostStrip | 100 | 0 | 100 | 2014-08-15 01:03 | 2014-08-16 22:35 | 51186.7213 |  |  | 51187 | [5 empty] | 0 | 0 | 0 | 5.6 | 5919.22
PH4100A | DT\28\003\A | DT | 28 | 3 | A | 1 Prestrip - Thick | 70 | 0 | 70 | 2014-08-15 05:52 | 2014-08-16 19:32 | 72336.629 | 72337 | [7 empty] | 0 | 0 | 6.75 | 0 | 0
TS5500Exc | SC\19\001\D | SC | 19 | 1 | D | 8 Coal Mining | 86.5 | 0 | 86.5 | 2014-08-15 07:19 | 2014-08-17 16:58 | 79112.5326 | [6 empty] | 79113 | 59226 | 4.45 | 0 | 0 | 6.64 | 5832
DRE2 | MW\16\003\D | MW | 16 | 3 | D | 6 DL | 100 | 0 | 100 | 2014-08-15 11:46 | 2014-08-20 01:29 | 378886.9559 |  |  |  | 21624 | 378887 | 287293 |  |  | 0 | 30.13 | 0 | 5.38 | 5939.4
PH4100XPC#1 | BW\18\001\B | BW | 18 | 1 | B | 1 Prestrip - Thick | 100 | 100 | 35 | 2014-08-15 22:58 | 2014-08-19 06:11 | 202218.6452 | 202219 | [7 empty] | 0 | 0 | 17.04 | 10.85 | 5373.9
DRE1 | SC\20\011\D | SC | 20 | 11 | D | 6 DL | 100 | 100 | 90 | 2014-08-16 12:04 | 2014-08-31 09:00 | 1361905.159 |  |  |  | 68328 | 1361905 | 582517 |  |  | 0 | 45 | 0 | 7.18 | 5782.67
PH4100A | DT\18\004\A | DT | 18 | 4 | A | 1 Prestrip - Thick | 70 | 0 | 70 | 2014-08-16 19:32 | 2014-08-19 08:25 | 114425.7381 | 114426 | [7 empty] | 0 | 0 | 8.8 | 11.72 | 5380.89
TS6060#1 | DT\15\005\D | DT | 15 | 5 | D | 7 PostStrip | 100 | 100 | 100 | 2014-08-16 22:35 | 2014-08-18 14:42 | 45102.6343 |  |  | 45103 | [5 empty] | 0 | 0 | 0 | 5.34 | 5941.73
TS5500Exc | MW\15\009\D | MW | 15 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-08-17 16:58 | 2014-08-19 11:47 | 58776.0569 | [6 empty] | 58776 | 44440 | 4.44 | 0 | 0 | 5.6 | 5919
TS6060#1 | MW\15\004\D | MW | 15 | 4 | D | 8 Coal Mining | 72.9 | 0 | 72.9 | 2014-08-18 14:42 | 2014-08-19 20:04 | 43323.0438 | [6 empty] | 43323 | 32810 | 3.28 | 0 | 0 | 5.57 | 5923
PH4100XPC#1 | DT\18\004\A | DT | 18 | 4 | A | 1 Prestrip - Thick | 100 | 0 | 10 | 2014-08-19 06:11 | 2014-08-19 12:53 | 16346.534 | 16347 | [7 empty] | 0 | 0 | 1.26 | 11.72 | 5380.89
PH4100A | SC\22\006\B | SC | 22 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-08-19 08:25 | 2014-08-23 00:53 | 159212.4396 | 159212 | [7 empty] | 0 | 0 | 13.49 | 11.49 | 5372.61
TS5500Exc | DT\15\005\D | DT | 15 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-08-19 11:47 | 2014-08-21 00:51 | 50856.6428 | [6 empty] | 50857 | 38545 | 4.41 | 0 | 0 | 5.34 | 5942
PH4100XPC#1 | DT\17\004\B | DT | 17 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-08-19 12:53 | 2014-08-19 14:48 | 4738.1909 | 4738 | [7 empty] | 0 | 0 | 0.82 | 18.34 | 4821.95
PH4100XPC#1 | DT\22\004\A | DT | 22 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-08-19 14:48 | 2014-08-29 07:16 | 598446.7047 | 598447 | [7 empty] | 0 | 0 | 42.33 | 16.14 | 5000.44
TS6060#1 | MW\15\005\D | MW | 15 | 5 | D | 8 Coal Mining | 100 | 0 | 92.5 | 2014-08-19 20:04 | 2014-08-21 09:21 | 54953.8993 | [6 empty] | 54954 | 41484 | 4.15 | 0 | 0 | 5.9 | 5893
DRE2 | MW\16\004\D | MW | 16 | 4 | D | 6 DL | 100 | 0 | 100 | 2014-08-20 01:29 | 2014-08-21 18:01 | 140028.4501 |  |  |  | 5345 | 140028 | 128270 |  |  | 0 | 13.22 | 0 | 5.75 | 5906.75
TS5500Exc | MC\26\007\D | MC | 26 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-08-21 00:51 | 2014-08-22 23:30 | 64032.416 | [6 empty] | 64032 | 47656 | 4.76 | 0 | 0 | 7.38 | 5765
TS6060#1 | BW\19\001\B | BW | 19 | 1 | B | 1 Prestrip - Thick | 61.8021 | 35.5382 | 35.5382 | 2014-08-21 09:21 | 2014-09-01 | 280653.8722 | 280654 | [7 empty] | 0 | 0 | 22.72 | 10.85 | 5372.12
DRE2 | MW\16\005\D | MW | 16 | 5 | D | 6 DL | 100 | 0 | 100 | 2014-08-21 18:01 | 2014-08-23 06:25 | 125687.7505 |  |  |  | 4797 | 125688 | 115134 |  |  | 0 | 11.91 | 0 | 6.03 | 5882.21
TS5500Exc | SC\19\002\D | SC | 19 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-08-22 23:30 | 2014-08-25 08:57 | 78846.8199 | [6 empty] | 78847 | 59400 | 4.95 | 0 | 0 | 6.27 | 5863
PH4100A | SC\21\005\B | SC | 21 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-08-23 00:53 | 2014-08-25 09:15 | 106220.3394 | 106220 | [7 empty] | 0 | 0 | 8.94 | 9.2 | 5559.43
DRE2 | MW\16\006\D | MW | 16 | 6 | D | 6 DL | 100 | 0 | 100 | 2014-08-23 06:25 | 2014-08-24 11:08 | 99186.6681 |  |  |  | 3786 | 99187 | 90858 |  |  | 0 | 9.36 | 0 | 6.11 | 5874.79
DRE2 | MW\16\007\D | MW | 16 | 7 | D | 6 DL | 100 | 0 | 100 | 2014-08-24 11:08 | 2014-08-27 00:32 | 212040.7981 |  |  |  | 7597 | 212041 | 182327 |  |  | 0 | 18.64 | 0 | 6.1 | 5874.65
TS5500Exc | SC\19\003\D | SC | 19 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-08-25 08:57 | 2014-08-27 17:15 | 77268.8164 | [6 empty] | 77269 | 58351 | 4.86 | 0 | 0 | 6 | 5887
PH4100A | SC\22\005\B | SC | 22 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-08-25 09:15 | 2014-08-28 11:03 | 138166.3708 | 138166 | [7 empty] | 0 | 0 | 11.63 | 9.07 | 5569.39
DRE2 | MW\16\008\D | MW | 16 | 8 | D | 6 DL | 100 | 0 | 100 | 2014-08-27 00:32 | 2014-08-29 10:10 | 199019.8746 |  |  |  | 7596 | 199020 | 182308 |  |  | 0 | 18.77 | 0 | 5.8 | 5901.82
TS5500Exc | SC\21\005\B | SC | 21 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-08-27 17:15 | 2014-08-29 08:25 | 53739.2915 | [6 empty] | 53739 | 39657 | 3.3 | 0 | 0 | 9.2 | 5559
PH4100A | SC\21\004\B | SC | 21 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-08-28 11:03 | 2014-08-30 22:18 | 111694.8735 | 111695 | [7 empty] | 0 | 0 | 9.49 | 8.96 | 5580.67
PH4100XPC#1 | DT\16\003\B | DT | 16 | 3 | B | 1 Prestrip - Thick | 100 | 0 | 65 | 2014-08-29 07:16 | 2014-08-29 09:07 | 4572.9902 | 4573 | [7 empty] | 0 | 0 | 0.2 | 0 | 0
TS5500Exc | SC\21\005\D | SC | 21 | 5 | D | 1 Prestrip - Thick | 100 | 52.8708 | 52.8708 | 2014-08-29 08:25 | 2014-09-01 | 61263.7779 | 61264 | [7 empty] | 0 | 0 | 5.1 | 5.86 | 5899.9
PH4100XPC#1 | DT\18\005\A | DT | 18 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-08-29 09:07 | 2014-08-30 16:59 | 77866.2073 | 77866 | [7 empty] | 0 | 0 | 7.69 | 10.7 | 5415.35
DRE2 | MW\16\009\D | MW | 16 | 9 | D | 6 DL | 100 | 0 | 100 | 2014-08-29 10:10 | 2014-08-31 21:38 | 205370.2383 |  |  |  | 7839 | 205370 | 188125 |  |  | 0 | 19.28 | 0 | 5.75 | 5906.67
PH4100XPC#1 | DT\18\003\A2 | DT | 18 | 3 | A2 | 1 Prestrip - Thick | 100 | 44.0514 | 44.0514 | 2014-08-30 16:59 | 2014-09-01 | 76654.6075 | 76655 | [7 empty] | 0 | 0 | 3.95 | 15.18 | 5075.38
PH4100A | SC\22\004\B | SC | 22 | 4 | B | 1 Prestrip - Thick | 100 | 32.7875 | 32.7875 | 2014-08-30 22:18 | 2014-09-01 | 48416.073 | 48416 | [7 empty] | 0 | 0 | 4.06 | 8.99 | 5576.75
DRE1 | SC\20\010\D | SC | 20 | 10 | D | 6 DL | 100 | 8.6589 | 7.793 | 2014-08-31 09:00 | 2014-09-01 | 57220.6406 |  |  |  | 4810 | 57221 | 37754 |  |  | 0 | 45 | 0 | 6.72 | 5823.87
DRE2 | MW\16\010\D | MW | 16 | 10 | D | 6 DL | 100 | 0 | 4.1848 | 2014-08-31 21:38 | 2014-09-01 | 8136.4543 |  |  |  | 311 | 8136 | 7453 |  |  | 0 | 18.21 | 0 | 5.7 | 5910.28
| EOP 8 : 2014\Aug | EOP 8 : 2014 | Aug | [6 empty] | 2014-09-01 | 2014-09-01 |  | 4120181 |  | 353347 | 282235 | 5408248 | 3342419 | 845585 | 636059 | 60.72 | 0 | 321.46 | 7.47 | 5745.16
TS5500Shv | DT\21\004\A | DT | 21 | 4 | A | 1 Prestrip - Thick | 100 | 36.739 | 36.739 | 2014-09-01 | 2014-09-27 09:58 | 213106.4077 | 213106 | [7 empty] | 0 | 0 | 14.31 | 13.93 | 5178.06
DRE1 | SC\20\010\D | SC | 20 | 10 | D | 6 DL | 100 | 91.3411 | 82.207 | 2014-09-01 | 2014-09-07 18:18 | 603611.9232 |  |  |  | 50737 | 603612 | 398262 |  |  | 0 | 45 | 0 | 6.72 | 5823.87
DRE2 | MW\16\010\D | MW | 16 | 10 | D | 6 DL | 100 | 0 | 95.8152 | 2014-09-01 | 2014-09-03 05:56 | 186292.3207 |  |  |  | 7110 | 186292 | 170649 |  |  | 0 | 18.21 | 0 | 5.7 | 5910.28
PH4100A | SC\22\004\B | SC | 22 | 4 | B | 1 Prestrip - Thick | 100 | 67.2125 | 67.2125 | 2014-09-01 | 2014-09-03 05:21 | 99250.056 | 99250 | [7 empty] | 0 | 0 | 8.32 | 8.99 | 5576.75
TS5500Exc | SC\21\005\D | SC | 21 | 5 | D | 1 Prestrip - Thick | 100 | 47.1292 | 47.1292 | 2014-09-01 | 2014-09-03 09:27 | 54610.7473 | 54611 | [7 empty] | 0 | 0 | 4.54 | 5.86 | 5899.9
TS6060#1 | BW\19\001\B | BW | 19 | 1 | B | 1 Prestrip - Thick | 61.8021 | 26.2639 | 26.2639 | 2014-09-01 | 2014-09-08 22:48 | 207412.4293 | 207412 | [7 empty] | 0 | 0 | 16.79 | 10.85 | 5372.12
PH4100XPC#1 | DT\18\003\A2 | DT | 18 | 3 | A2 | 1 Prestrip - Thick | 100 | 40.9486 | 40.9486 | 2014-09-01 | 2014-09-02 05:12 | 71255.2688 | 71255 | [7 empty] | 0 | 0 | 3.67 | 15.18 | 5075.38
TS Fleet 5 | No Production | No Production | [7 empty] | 2014-09-01 | 2014-10-01
PH4100XPC#1 | DT\22\003\A1 | DT | 22 | 3 | A1 | 1 Prestrip - Thick | 100 | 0 | 10 | 2014-09-02 05:12 | 2014-09-02 21:30 | 39789.4801 | 39789 | [7 empty] | 0 | 0 | 2.55 | 15.3 | 5089.98
PH4100XPC#1 | DT\23\003\A2 | DT | 23 | 3 | A2 | 1 Prestrip - Thick | 100 | 0 | 10 | 2014-09-02 21:30 | 2014-09-03 18:56 | 52405.0517 | 52405 | [7 empty] | 0 | 0 | 3.24 | 14.82 | 5134.23
PH4100A | SC\21\003\B | SC | 21 | 3 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2014-09-03 05:21 | 2014-09-03 05:21 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\22\003\B | SC | 22 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-09-03 05:21 | 2014-09-07 15:48 | 197277.6848 | 197278 | [7 empty] | 0 | 0 | 16.2 | 8.92 | 5582.21
DRE2 | MW\16\011\D | MW | 16 | 11 | D | 6 DL | 100 | 0 | 100 | 2014-09-03 05:56 | 2014-09-05 13:35 | 192191.8471 |  |  |  | 7336 | 192192 | 176054 |  |  | 0 | 17.75 | 0 | 5.64 | 5915.15
TS5500Exc | MC\27\004\B | MC | 27 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-09-03 09:27 | 2014-09-04 16:32 | 42062.6622 | [6 empty] | 42063 | 30306 | 3.11 | 0 | 0 | 11.72 | 5262
PH4100XPC#1 | DT\24\003\A2 | DT | 24 | 3 | A2 | 1 Prestrip - Thick | 100 | 0 | 10 | 2014-09-03 18:56 | 2014-09-04 17:06 | 54825.1452 | 54825 | [7 empty] | 0 | 0 | 3.79 | 15.37 | 5096.2
TS5500Exc | BW\17\003\B | BW | 17 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-09-04 16:32 | 2014-09-05 22:53 | 41098.2705 | [6 empty] | 41098 | 30015 | 3.62 | 0 | 0 | 10.85 | 5370
PH4100XPC#1 | DT\25\003\A | DT | 25 | 3 | A | 1 Prestrip - Thick | 100 | 0 | 10 | 2014-09-04 17:06 | 2014-09-05 18:01 | 62469.4725 | 62469 | [7 empty] | 0 | 0 | 4.09 | 0 | 0
DRE2 | MW\16\012\D | MW | 16 | 12 | D | 6 DL | 100 | 0 | 100 | 2014-09-05 13:35 | 2014-09-07 19:24 | 185841.5875 |  |  |  | 7093 | 185842 | 170237 |  |  | 0 | 17.37 | 0 | 5.65 | 5915.03
PH4100XPC#1 | DT\25\003\B | DT | 25 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-09-05 18:01 | 2014-09-06 22:48 | 69823.8574 | 69824 | [7 empty] | 0 | 0 | 4.35 | 10.52 | 5352.85
TS5500Exc | MW\16\005\D | MW | 16 | 5 | D | 8 Coal Mining | 96.2 | 0 | 96.2 | 2014-09-05 22:53 | 2014-09-07 18:00 | 58364.3974 | [6 empty] | 58364 | 44061 | 4.41 | 0 | 0 | 6.03 | 5882
PH4100XPC#1 | DT\26\003\A | DT | 26 | 3 | A | 1 Prestrip - Thick | 100 | 0 | 10 | 2014-09-06 22:48 | 2014-09-07 13:16 | 36515.2737 | 36515 | [7 empty] | 0 | 0 | 2.43 | 0 | 0
PH4100XPC#1 | DT\26\003\B | DT | 26 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-09-07 13:16 | 2014-09-08 22:06 | 79595.4336 | 79595 | [7 empty] | 0 | 0 | 5.01 | 10.64 | 5344.41
PH4100A | SC\22\002\B | SC | 22 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-09-07 15:48 | 2014-09-21 21:25 | 631951.5974 | 631952 | [7 empty] | 0 | 0 | 30.22 | 8.77 | 5595.42
TS5500Exc | SC\20\011\D | SC | 20 | 11 | D | 7 PostStrip | 100 | 0 | 100 | 2014-09-07 18:00 | 2014-09-09 07:56 | 36040.0137 |  |  | 36040 | [5 empty] | 0 | 0 | 0 | 7.18 | 5782.67
DRE1 | SC\20\009\D | SC | 20 | 9 | D | 6 DL | 100 | 100 | 90 | 2014-09-07 18:18 | 2014-09-15 02:50 | 656600.0729 |  |  |  | 55191 | 656600 | 433224 |  |  | 0 | 45 | 0 | 6.33 | 5857.23
DRE2 | MW\16\013\D | MW | 16 | 13 | D | 6 DL | 100 | 0 | 100 | 2014-09-07 19:24 | 2014-09-09 14:08 | 147593.4853 |  |  |  | 5317 | 147593 | 90206 |  |  | 0 | 17.54 | 0 | 5.85 | 5896.04
PH4100XPC#1 | DT\27\003\A | DT | 27 | 3 | A | 1 Prestrip - Thick | 100 | 0 | 10 | 2014-09-08 22:06 | 2014-09-09 04:44 | 16299.9459 | 16300 | [7 empty] | 0 | 0 | 1.02 | 19.49 | 4771.52
TS6060#1 | MW\15\006\D | MW | 15 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-09-08 22:48 | 2014-09-10 15:29 | 59178.8142 | [6 empty] | 59179 | 44566 | 4.46 | 0 | 0 | 6.03 | 5881
PH4100XPC#1 | DT\28\003\A | DT | 28 | 3 | A | 1 Prestrip - Thick | 100 | 0 | 10 | 2014-09-09 04:44 | 2014-09-09 08:55 | 10333.8041 | 10334 | [7 empty] | 0 | 0 | 0.96 | 0 | 0
TS5500Exc | MW\16\012\D | MW | 16 | 12 | D | 8 Coal Mining | 100 | 0 | 86.3 | 2014-09-09 07:56 | 2014-09-10 21:14 | 50502.088 | [6 empty] | 50502 | 38152 | 3.82 | 0 | 0 | 5.65 | 5915
PH4100XPC#1 | DT\28\003\B | DT | 28 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-09-09 08:55 | 2014-09-10 03:01 | 43895.5427 | 43896 | [7 empty] | 0 | 0 | 3.65 | 10.65 | 5351.14
DRE2 | MC\26\008\D | MC | 26 | 8 | D | 6 DL | 100 | 100 | 100 | 2014-09-09 14:08 | 2014-09-15 20:21 | 518740.1076 |  |  |  | 15431 | 518740 | 241753 |  |  | 0 | 26.15 | 0 | 7.18 | 5782.97
PH4100XPC#1 | MW\18\003\B | MW | 18 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-09-10 03:01 | 2014-09-12 17:23 | 146945.6434 | 146946 | [7 empty] | 0 | 0 | 14.11 | 17.23 | 4905.53
TS6060#1 | MW\15\007\D | MW | 15 | 7 | D | 8 Coal Mining | 100 | 0 | 14.6 | 2014-09-10 15:29 | 2014-09-10 21:14 | 8359.7003 | [6 empty] | 8360 | 6299 | 0.65 | 0 | 0 | 6.08 | 5876
TS6060#1 | DT\23\003\A2 | DT | 23 | 3 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2014-09-10 21:14 | 2014-09-12 00:59 | 40365.1936 | [6 empty] | 40365 | 28923 | 1.79 | 0 | 0 | 14.82 | 5134
TS5500Exc | SC\19\004\D | SC | 19 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-09-10 21:14 | 2014-09-13 07:02 | 78230.1848 | [6 empty] | 78230 | 59077 | 4.92 | 0 | 0 | 5.82 | 5903
TS6060#1 | BW\19\001\B | BW | 19 | 1 | B | 1 Prestrip - Thick | 38.1979 | 38.1979 | 38.1979 | 2014-09-12 00:59 | 2014-09-23 14:30 | 301658.1579 | 301658 | [7 empty] | 0 | 0 | 24.42 | 10.85 | 5372.12
PH4100XPC#1 | DT\23\003\B | DT | 23 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-09-12 17:23 | 2014-09-13 16:57 | 57156.6379 | 57157 | [7 empty] | 0 | 0 | 3.54 | 10.13 | 5391.51
TS5500Exc | MW\18\003\B | MW | 18 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-09-13 07:02 | 2014-09-14 14:53 | 43120.0482 | [6 empty] | 43120 | 30559 | 3.02 | 0 | 0 | 17.23 | 4906
PH4100XPC#1 | MW\17\004\D | MW | 17 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-09-13 16:57 | 2014-09-17 18:49 | 221227.3863 | 221227 | [7 empty] | 0 | 0 | 21.96 | 5.93 | 5891.02
TS5500Exc | SC\19\005\D | SC | 19 | 5 | D | 8 Coal Mining | 92.2 | 0 | 92.2 | 2014-09-14 14:53 | 2014-09-16 21:11 | 73489.6363 | [6 empty] | 73490 | 55586 | 4.63 | 0 | 0 | 5.77 | 5908
DRE1 | SC\20\008\D | SC | 20 | 8 | D | 6 DL | 100 | 100 | 90 | 2014-09-15 02:50 | 2014-09-22 11:08 | 655634.2635 |  |  |  | 55110 | 655634 | 432586 |  |  | 0 | 45 | 0 | 6.21 | 5867.88
DRE2 | MC\26\009\D | MC | 26 | 9 | D | 6 DL | 100 | 100 | 100 | 2014-09-15 20:21 | 2014-09-22 04:40 | 525999.514 |  |  |  | 15647 | 526000 | 245136 |  |  | 0 | 26.04 | 0 | 7.34 | 5769.06
TS5500Exc | SC\20\009\D | SC | 20 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-09-16 21:11 | 2014-09-19 05:16 | 75909.3703 | [6 empty] | 75909 | 57232 | 4.77 | 0 | 0 | 6.33 | 5857
PH4100XPC#1 | MW\18\004\D | MW | 18 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-09-17 18:49 | 2014-09-21 05:34 | 189187.4459 | 189187 | [7 empty] | 0 | 0 | 18.8 | 6.1 | 5875.55
TS5500Exc | MW\16\013\D | MW | 16 | 13 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2014-09-19 05:16 | 2014-09-19 23:26 | 17265.5079 |  |  | 17266 | [5 empty] | 0 | 0 | 0 | 5.85 | 5896.04
TS5500Exc | MW\17\006\D | MW | 17 | 6 | D | 1 Prestrip - Thick | 1.3254 | 1.3254 | 1.3254 | 2014-09-19 23:26 | 2014-09-20 02:58 | 3386.4253 | 3386 | [7 empty] | 0 | 0 | 0.34 | 6.19 | 5868.18
TS5500Exc | MW\17\006\D | MW | 17 | 6 | D | 1 Prestrip - Thick | 34.2707 | 34.2707 | 34.2707 | 2014-09-20 02:58 | 2014-09-23 22:37 | 87560.1936 | 87560 | [7 empty] | 0 | 0 | 8.74 | 6.19 | 5868.18
PH4100XPC#1 | MW\17\005\D | MW | 17 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-09-21 05:34 | 2014-09-25 21:14 | 250632.6063 | 250633 | [7 empty] | 0 | 0 | 24.89 | 6.16 | 5870.9
PH4100A | SC\21\006\D | SC | 21 | 6 | D | 1 Prestrip - Thick | 100 | 90 | 90 | 2014-09-21 21:25 | 2014-09-27 00:37 | 226770.3445 | 226770 | [7 empty] | 0 | 0 | 19.1 | 5.81 | 5903.95
DRE2 | MC\26\010\D | MC | 26 | 10 | D | 6 DL | 100 | 100 | 100 | 2014-09-22 04:40 | 2014-09-28 11:58 | 522508.7503 |  |  |  | 15543 | 522509 | 243509 |  |  | 0 | 25.85 | 0 | 7.67 | 5740.15
DRE1 | SC\20\007\D | SC | 20 | 7 | D | 6 DL | 100 | 100 | 90 | 2014-09-22 11:08 | 2014-09-29 19:52 | 657279.035 |  |  |  | 55248 | 657279 | 433672 |  |  | 0 | 45 | 0 | 5.95 | 5891.16
TS6060#1 | DT\23\003\B | DT | 23 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-09-23 14:30 | 2014-09-25 13:27 | 68274.8207 | [6 empty] | 68275 | 49892 | 3.1 | 0 | 0 | 10.13 | 5392
TS5500Exc | SC\19\005\D | SC | 19 | 5 | D | 8 Coal Mining | 7.8 | 0 | 7.8 | 2014-09-23 22:37 | 2014-09-24 03:13 | 6232.9475 | [6 empty] | 6233 | 4714 | 0.39 | 0 | 0 | 5.77 | 5908
TS5500Exc | SC\19\006\D | SC | 19 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-09-24 03:13 | 2014-09-26 12:07 | 77005.1287 | [6 empty] | 77005 | 58432 | 4.87 | 0 | 0 | 5.83 | 5902
TS6060#1 | MC\26\008\D | MC | 26 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-09-25 13:27 | 2014-09-27 09:47 | 64494.3317 | [6 empty] | 64494 | 48126 | 4.81 | 0 | 0 | 7.18 | 5783
PH4100XPC#1 | MW\18\005\D | MW | 18 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-09-25 21:14 | 2014-09-30 09:38 | 244741.1377 | 244741 | [7 empty] | 0 | 0 | 24.5 | 6.28 | 5859.36
TS5500Exc | SC\20\008\D | SC | 20 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-09-26 12:07 | 2014-09-28 20:09 | 75841.5665 | [6 empty] | 75842 | 57273 | 4.77 | 0 | 0 | 6.21 | 5868
PH4100A | SC\21\007\D | SC | 21 | 7 | D | 1 Prestrip - Thick | 100 | 71.7235 | 71.7235 | 2014-09-27 00:37 | 2014-10-01 | 174986.7505 | 174987 | [7 empty] | 0 | 0 | 14.73 | 5.81 | 5903.16
TS6060#1 | DT\22\004\A | DT | 22 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2014-09-27 09:47 | 2014-09-28 15:15 | 42858.2875 | [6 empty] | 42858 | 30528 | 1.96 | 0 | 0 | 16.14 | 5000
TS5500Shv | SC\21\004\B | SC | 21 | 4 | B | 8 Coal Mining | 100 | 0 | 54.7 | 2014-09-27 09:58 | 2014-10-01 | 32881.1653 | [6 empty] | 32881 | 24304 | 2.1 | 0 | 0 | 8.96 | 5581
DRE2 | MC\26\011\D | MC | 26 | 11 | D | 6 DL | 100 | 44.6195 | 44.6195 | 2014-09-28 11:58 | 2014-10-01 | 207316.3875 |  |  |  | 4827 | 207316 | 91712 |  |  | 0 | 24.06 | 0 | 7.63 | 5742.52
TS6060#1 | DT\18\005\A | DT | 18 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2014-09-28 15:15 | 2014-09-29 11:23 | 29262.3041 | [6 empty] | 29262 | 21477 | 3.85 | 0 | 0 | 10.7 | 5415
TS5500Exc | BW\17\010\B | BW | 17 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-09-28 20:09 | 2014-09-29 20:58 | 33597.995 | [6 empty] | 33598 | 24610 | 4.02 | 0 | 0 | 11.33 | 5380
TS6060#1 | MC\26\009\D | MC | 26 | 9 | D | 8 Coal Mining | 100 | 0 | 82.8 | 2014-09-29 11:23 | 2014-10-01 | 53252.5304 | [6 empty] | 53253 | 39767 | 3.97 | 0 | 0 | 7.34 | 5769
DRE1 | SC\20\001\D | SC | 20 | 1 | D | 6 DL | 100 | 0 | 11.6198 | 2014-09-29 19:52 | 2014-10-01 | 104626.7054 |  |  |  | 6349 | 104627 | 43596 |  |  | 0 | 45 | 0 | 6.69 | 5827.3
TS5500Exc | SC\20\007\D | SC | 20 | 7 | D | 8 Coal Mining | 100 | 0 | 47.3 | 2014-09-29 20:58 | 2014-10-01 | 36585.7329 | [6 empty] | 36586 | 27739 | 2.31 | 0 | 0 | 5.95 | 5891
PH4100XPC#1 | DT\18\005\B | DT | 18 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-09-30 09:38 | 2014-09-30 16:01 | 15478.432 | 15478 | [7 empty] | 0 | 0 | 1.63 | 8.94 | 5560.25
PH4100XPC#1 | MW\17\006\D | MW | 17 | 6 | D | 1 Prestrip - Thick | 100 | 6.9587 | 6.9587 | 2014-09-30 16:01 | 2014-10-01 | 17779.1791 | 17779 | [7 empty] | 0 | 0 | 1.78 | 6.19 | 5868.18
| EOP 9 : 2014\Sep | EOP 9 : 2014 | Sep | [6 empty] | 2014-10-01 | 2014-10-01 |  | 3878328 |  | 53306 | 300939 | 5164236 | 3170596 | 1090967 | 811639 | 75.34 | 0 | 303.71 | 7.98 | 5688.23
TS5500Shv | SC\21\004\B | SC | 21 | 4 | B | 8 Coal Mining | 100 | 0 | 45.3 | 2014-10-01 | 2014-10-04 02:47 | 27226.2052 | [6 empty] | 27226 | 20124 | 1.74 | 0 | 0 | 8.96 | 5581
DRE1 | SC\20\001\D | SC | 20 | 1 | D | 6 DL | 100 | 0 | 88.3802 | 2014-10-01 | 2014-10-10 00:47 | 795791.4395 |  |  |  | 48293 | 795791 | 331591 |  |  | 0 | 45 | 0 | 6.69 | 5827.3
PH4100A | SC\21\007\D | SC | 21 | 7 | D | 1 Prestrip - Thick | 100 | 18.2765 | 18.2765 | 2014-10-01 | 2014-10-02 01:19 | 44590.0623 | 44590 | [7 empty] | 0 | 0 | 3.75 | 5.81 | 5903.16
DRE2 | MC\26\011\D | MC | 26 | 11 | D | 6 DL | 100 | 55.3805 | 55.3805 | 2014-10-01 | 2014-10-04 03:29 | 257315.5932 |  |  |  | 5991 | 257316 | 113830 |  |  | 0 | 24.06 | 0 | 7.63 | 5742.52
TS6060#1 | MC\26\009\D | MC | 26 | 9 | D | 8 Coal Mining | 100 | 0 | 17.2 | 2014-10-01 | 2014-10-01 08:04 | 11083.3558 | [6 empty] | 11083 | 8277 | 0.83 | 0 | 0 | 7.34 | 5769
TS5500Exc | SC\20\007\D | SC | 20 | 7 | D | 8 Coal Mining | 100 | 0 | 52.7 | 2014-10-01 | 2014-10-02 07:54 | 40784.0555 | [6 empty] | 40784 | 30922 | 2.58 | 0 | 0 | 5.95 | 5891
PH4100XPC#1 | MW\17\006\D | MW | 17 | 6 | D | 1 Prestrip - Thick | 100 | 57.4452 | 57.4452 | 2014-10-01 | 2014-10-03 20:34 | 146770.1628 | 146770 | [7 empty] | 0 | 0 | 14.66 | 6.19 | 5868.18
TS Fleet 5 | No Production | No Production | [7 empty] | 2014-10-01 | 2014-11-01
TS6060#1 | MW\15\007\D | MW | 15 | 7 | D | 8 Coal Mining | 100 | 0 | 85.4 | 2014-10-01 08:04 | 2014-10-02 19:40 | 48916.8741 | [6 empty] | 48917 | 36859 | 3.8 | 0 | 0 | 6.08 | 5876
PH4100A | SC\22\007\D | SC | 22 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-10-02 01:19 | 2014-10-08 11:04 | 270638.9365 | 270639 | [7 empty] | 0 | 0 | 22.8 | 5.67 | 5915.43
TS5500Exc | MW\16\012\D | MW | 16 | 12 | D | 8 Coal Mining | 100 | 0 | 13.7 | 2014-10-02 07:54 | 2014-10-02 14:08 | 7985.9024 | [6 empty] | 7986 | 6033 | 0.6 | 0 | 0 | 5.65 | 5915
TS5500Exc | MW\16\005\D | MW | 16 | 5 | D | 8 Coal Mining | 3.8 | 0 | 3.8 | 2014-10-02 14:08 | 2014-10-02 15:57 | 2303.3833 | [6 empty] | 2303 | 1739 | 0.17 | 0 | 0 | 6.03 | 5882
TS5500Exc | MW\16\004\D | MW | 16 | 4 | D | 8 Coal Mining | 100 | 0 | 99.4 | 2014-10-02 15:57 | 2014-10-04 14:04 | 58965.6673 | [6 empty] | 58966 | 44621 | 4.46 | 0 | 0 | 5.75 | 5907
TS6060#1 | MW\15\008\D | MW | 15 | 8 | D | 8 Coal Mining | 100 | 0 | 98.6 | 2014-10-02 19:40 | 2014-10-04 14:04 | 58233.1728 | [6 empty] | 58233 | 44101 | 4.41 | 0 | 0 | 5.63 | 5917
PH4100XPC#1 | MW\18\006\D | MW | 18 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-10-03 20:34 | 2014-10-09 00:22 | 266019.9826 | 266020 | [7 empty] | 0 | 0 | 26.49 | 6.26 | 5861.57
TS5500Shv | SC\22\003\B | SC | 22 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-10-04 02:47 | 2014-10-11 04:01 | 61596.1716 | [6 empty] | 61596 | 45560 | 3.8 | 0 | 0 | 8.92 | 5582
DRE2 | MC\26\012\D | MC | 26 | 12 | D | 6 DL | 100 | 100 | 100 | 2014-10-04 03:29 | 2014-10-13 20:52 | 795496.6285 |  |  |  | 56574 | 795497 | 572028 |  |  | 0 | 35.68 | 0 | 6.47 | 5844.51
TS6060#1 | DT\18\005\B | DT | 18 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-10-04 14:04 | 2014-10-05 10:52 | 28559.4671 | [6 empty] | 28559 | 21131 | 3.16 | 0 | 0 | 8.94 | 5560
TS5500Exc | BW\18\010\B | BW | 18 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-10-04 14:04 | 2014-10-05 04:22 | 18272.0827 | [6 empty] | 18272 | 13433 | 3.97 | 0 | 0 | 10.65 | 5434
TS5500Exc | DT\25\003\B | DT | 25 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-10-05 04:22 | 2014-10-07 09:10 | 67505.3769 | [6 empty] | 67505 | 49187 | 3.09 | 0 | 0 | 10.52 | 5353
TS6060#1 | MC\26\010\D | MC | 26 | 10 | D | 8 Coal Mining | 56.4 | 0 | 56.4 | 2014-10-05 10:52 | 2014-10-06 13:06 | 36038.6591 | [6 empty] | 36039 | 26892 | 2.69 | 0 | 0 | 7.67 | 5740
TS6060#1 | MW\16\013\D | MW | 16 | 13 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2014-10-06 13:06 | 2014-10-07 08:20 | 20143.0926 |  |  | 20143 | [5 empty] | 0 | 0 | 0 | 5.85 | 5896.04
TS6060#1 | BW\19\002\B | BW | 19 | 2 | B | 1 Prestrip - Thick | 0.69181 | 0.69181 | 0.69181 | 2014-10-07 08:20 | 2014-10-07 12:05 | 3865.8387 | 3866 | [7 empty] | 0 | 0 | 0.41 | 11.46 | 5325.04
TS5500Exc | MW\17\012\D | MW | 17 | 12 | D | 1 Prestrip - Thick | 89.6617 | 89.6617 | 89.6617 | 2014-10-07 09:10 | 2014-10-15 22:41 | 185170.5845 | 185171 | [7 empty] | 0 | 0 | 18.39 | 5.65 | 5914.44
TS6060#1 | BW\19\002\B | BW | 19 | 2 | B | 1 Prestrip - Thick | 99.3082 | 99.3082 | 99.3082 | 2014-10-07 12:05 | 2014-10-29 22:49 | 554932.9389 | 554933 | [7 empty] | 0 | 0 | 58.7 | 11.46 | 5325.04
PH4100A | SC\21\004\D | SC | 21 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-10-08 11:04 | 2014-10-11 07:09 | 121563.5371 | 121564 | [7 empty] | 0 | 0 | 10.16 | 5.93 | 5894.02
PH4100XPC#1 | MW\17\007\D | MW | 17 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-10-09 00:22 | 2014-10-13 08:09 | 227160.7283 | 227161 | [7 empty] | 0 | 0 | 22.69 | 6.13 | 5872.11
DRE1 | SC\20\002\D | SC | 20 | 2 | D | 6 DL | 100 | 0 | 100 | 2014-10-10 00:47 | 2014-10-18 06:33 | 725980.6957 |  |  |  | 61023 | 725981 | 479001 |  |  | 0 | 45 | 0 | 6.37 | 5854.81
TS5500Shv | SC\22\004\B | SC | 22 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-10-11 04:01 | 2014-10-18 00:53 | 60015.1239 | [6 empty] | 60015 | 44384 | 3.71 | 0 | 0 | 8.99 | 5577
PH4100A | SC\22\003\D | SC | 22 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-10-11 07:09 | 2014-10-14 03:26 | 121941.2472 | 121941 | [7 empty] | 0 | 0 | 10.16 | 6.17 | 5872.1
PH4100XPC#1 | MW\18\007\D | MW | 18 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-10-13 08:09 | 2014-10-17 15:53 | 227745.7628 | 227746 | [7 empty] | 0 | 0 | 22.8 | 6.16 | 5869.88
DRE2 | BC\31\004\B | BC | 31 | 4 | B | 6 DL | 100 | 0 | 0 | 2014-10-13 20:52 | 2014-10-13 20:52 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BC\31\003\B | BC | 31 | 3 | B | 6 DL | 100 | 0 | 0 | 2014-10-13 20:52 | 2014-10-13 20:52 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BC\31\006\D | BC | 31 | 6 | D | 6 DL | 100 | 100 | 100 | 2014-10-13 20:52 | 2014-10-20 11:24 | 540373.8124 |  |  |  | 23210 | 540374 | 264262 |  |  | 0 | 30 | 0 | 6.52 | 5840.87
PH4100A | SC\21\011\D | SC | 21 | 11 | D | 1 Prestrip - Thick | 100 | 90 | 90 | 2014-10-14 03:26 | 2014-10-19 11:02 | 224318.443 | 224318 | [7 empty] | 0 | 0 | 11.53 | 7.25 | 5776.43
TS5500Exc | SC\20\001\D | SC | 20 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2014-10-15 22:41 | 2014-10-18 10:33 | 53728.6391 |  |  | 53729 | [5 empty] | 0 | 0 | 0 | 6.69 | 5827.3
PH4100XPC#1 | MW\17\008\D | MW | 17 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-10-17 15:53 | 2014-10-19 23:44 | 124193.6817 | 124194 | [7 empty] | 0 | 0 | 12.64 | 5.96 | 5887.09
TS5500Shv | SC\20\011\D | SC | 20 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-10-18 00:53 | 2014-10-29 00:03 | 95792.8436 | [6 empty] | 95793 | 71368 | 4.74 | 0 | 0 | 7.18 | 5783
DRE1 | SC\20\003\D | SC | 20 | 3 | D | 6 DL | 100 | 0 | 100 | 2014-10-18 06:33 | 2014-10-26 12:28 | 726513.8027 |  |  |  | 61067 | 726514 | 479353 |  |  | 0 | 45 | 0 | 6.06 | 5882.29
TS5500Exc | SC\20\001\D | SC | 20 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-10-18 10:33 | 2014-10-20 18:00 | 70886.1048 | [6 empty] | 70886 | 53109 | 5.09 | 0 | 0 | 6.69 | 5827
PH4100A | SC\22\004\D | SC | 22 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-10-19 11:02 | 2014-10-22 06:14 | 119990.6133 | 119991 | [7 empty] | 0 | 0 | 10.01 | 5.98 | 5889.09
PH4100XPC#1 | MW\18\008\D | MW | 18 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-10-19 23:44 | 2014-10-22 16:49 | 144501.2345 | 144501 | [7 empty] | 0 | 0 | 14.49 | 6.11 | 5874.62
DRE2 | BC\31\005\D | BC | 31 | 5 | D | 6 DL | 100 | 100 | 100 | 2014-10-20 11:24 | 2014-10-24 08:53 | 318657.561 |  |  |  | 18187 | 318658 | 241624 |  |  | 0 | 30 | 0 | 6.34 | 5856.17
TS5500Exc | SC\20\002\D | SC | 20 | 2 | D | 8 Coal Mining | 2.1 | 0 | 2.1 | 2014-10-20 18:00 | 2014-10-20 19:17 | 1648.0314 | [6 empty] | 1648 | 1242 | 0.1 | 0 | 0 | 6.37 | 5855
TS5500Exc | MW\17\013\D | MW | 17 | 13 | D | 1 Prestrip - Thick | 28.7944 | 28.7944 | 28.7944 | 2014-10-20 19:17 | 2014-10-22 16:13 | 40487.6364 | 40488 | [7 empty] | 0 | 0 | 6.4 | 5.85 | 5896.37
PH4100A | SC\22\012\D | SC | 22 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-10-22 06:14 | 2014-10-26 03:22 | 163088.2001 | 163088 | [7 empty] | 0 | 0 | 16.12 | 7.34 | 5767.51
TS5500Exc | MW\17\013\D | MW | 17 | 13 | D | 1 Prestrip - Thick | 42.7047 | 42.7047 | 42.7047 | 2014-10-22 16:13 | 2014-10-25 10:51 | 60046.8545 | 60047 | [7 empty] | 0 | 0 | 9.49 | 5.85 | 5896.37
PH4100XPC#1 | MW\17\009\D | MW | 17 | 9 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-10-22 16:49 | 2014-10-27 04:10 | 234909.7394 | 234910 | [7 empty] | 0 | 0 | 23.41 | 5.89 | 5893.85
DRE2 | BC\31\004\D | BC | 31 | 4 | D | 6 DL | 100 | 100 | 100 | 2014-10-24 08:53 | 2014-10-27 00:37 | 217227.4341 |  |  |  | 9719 | 217227 | 184668 |  |  | 0 | 20.99 | 0 | 6.15 | 5873.42
TS5500Exc | BC\31\005\D | BC | 31 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-10-25 10:51 | 2014-10-27 13:05 | 64215.8973 | [6 empty] | 64216 | 48268 | 4.83 | 0 | 0 | 6.34 | 5856
PH4100A | SC\22\011\D | SC | 22 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-10-26 03:22 | 2014-10-29 04:56 | 129797.9474 | 129798 | [7 empty] | 0 | 0 | 11.14 | 7.28 | 5774.35
DRE1 | SC\20\004\D | SC | 20 | 4 | D | 6 DL | 100 | 0 | 66.3725 | 2014-10-26 12:28 | 2014-11-01 | 482789.2622 |  |  |  | 40581 | 482789 | 318544 |  |  | 0 | 45 | 0 | 5.87 | 5898.98
DRE2 | BC\31\003\D | BC | 31 | 3 | D | 6 DL | 100 | 100 | 100 | 2014-10-27 00:37 | 2014-10-30 05:01 | 260416.1966 |  |  |  | 11652 | 260416 | 221383 |  |  | 0 | 22.27 | 0 | 5.51 | 5928.92
PH4100XPC#1 | MW\18\009\D | MW | 18 | 9 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-10-27 04:10 | 2014-10-31 11:39 | 227623.1434 | 227623 | [7 empty] | 0 | 0 | 22.68 | 6.02 | 5881.97
TS5500Exc | BC\31\004\D | BC | 31 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-10-27 13:05 | 2014-10-29 15:58 | 65049.7265 | [6 empty] | 65050 | 49008 | 4.9 | 0 | 0 | 6.15 | 5873
TS5500Shv | SC\20\003\D | SC | 20 | 3 | D | 8 Coal Mining | 100 | 0 | 33.2 | 2014-10-29 00:03 | 2014-11-01 | 26185.6557 | [6 empty] | 26186 | 19790 | 1.65 | 0 | 0 | 6.06 | 5882
PH4100A | SC\21\010\D | SC | 21 | 10 | D | 1 Prestrip - Thick | 100 | 70 | 70 | 2014-10-29 04:56 | 2014-10-31 13:57 | 100758.3229 | 100758 | [7 empty] | 0 | 0 | 8.56 | 6.76 | 5819.97
TS5500Exc | SC\20\002\D | SC | 20 | 2 | D | 8 Coal Mining | 97.9 | 0 | 91.4 | 2014-10-29 15:58 | 2014-11-01 | 71619.4499 | [6 empty] | 71619 | 53955 | 4.5 | 0 | 0 | 6.37 | 5855
TS6060#1 | MC\26\012\D | MC | 26 | 12 | D | 8 Coal Mining | 100 | 0 | 94.2 | 2014-10-29 22:49 | 2014-11-01 | 67536.2828 | [6 empty] | 67536 | 50924 | 4.34 | 0 | 0 | 6.47 | 5845
DRE2 | BC\32\004\B | BC | 32 | 4 | B | 6 DL | 100 | 0 | 0 | 2014-10-30 05:01 | 2014-10-30 05:01 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BC\32\003\B | BC | 32 | 3 | B | 6 DL | 100 | 0 | 0 | 2014-10-30 05:01 | 2014-10-30 05:01 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BC\32\006\D | BC | 32 | 6 | D | 6 DL | 100 | 28.9004 | 28.9004 | 2014-10-30 05:01 | 2014-11-01 | 146511.1742 |  |  |  | 6443 | 146511 | 71980 |  |  | 0 | 30 | 0 | 6.49 | 5843.01
PH4100XPC#1 | MW\17\010\D | MW | 17 | 10 | D | 1 Prestrip - Thick | 100 | 11.1565 | 11.1565 | 2014-10-31 11:39 | 2014-11-01 | 26941.6096 | 26942 | [7 empty] | 0 | 0 | 2.69 | 5.75 | 5906.21
PH4100A | SC\22\010\D | SC | 22 | 10 | D | 1 Prestrip - Thick | 100 | 12.0915 | 12.0915 | 2014-10-31 13:57 | 2014-11-01 | 17759.827 | 17760 | [7 empty] | 0 | 0 | 1.52 | 6.8 | 5816.38
| EOP 10 : 2014\Oct | EOP 10 : 2014 | Oct | [6 empty] | 2014-11-01 | 2014-11-01 |  | 3784817 |  | 73872 | 342740 | 5267074 | 3278263 | 990419 | 740927 | 69.14 | 0 | 361.7 | 6.69 | 5817.61
TS5500Shv | SC\20\003\D | SC | 20 | 3 | D | 8 Coal Mining | 100 | 0 | 66.8 | 2014-11-01 | 2014-11-06 17:59 | 52742.2945 | [6 empty] | 52742 | 39861 | 3.32 | 0 | 0 | 6.06 | 5882
DRE1 | SC\20\004\D | SC | 20 | 4 | D | 6 DL | 100 | 0 | 33.6275 | 2014-11-01 | 2014-11-03 19:31 | 244604.1507 |  |  |  | 20560 | 244604 | 161389 |  |  | 0 | 45 | 0 | 5.87 | 5898.98
PH4100A | SC\22\010\D | SC | 22 | 10 | D | 1 Prestrip - Thick | 100 | 87.9085 | 87.9085 | 2014-11-01 | 2014-11-04 04:10 | 129118.9824 | 129119 | [7 empty] | 0 | 0 | 11.05 | 6.8 | 5816.38
DRE2 | BC\32\006\D | BC | 32 | 6 | D | 6 DL | 100 | 71.0996 | 71.0996 | 2014-11-01 | 2014-11-05 11:09 | 360441.584 |  |  |  | 15852 | 360442 | 177082 |  |  | 0 | 30 | 0 | 6.49 | 5843.01
TS6060#1 | MC\26\012\D | MC | 26 | 12 | D | 8 Coal Mining | 100 | 0 | 5.8 | 2014-11-01 | 2014-11-01 03:07 | 4161.4247 | [6 empty] | 4161 | 3138 | 0.27 | 0 | 0 | 6.47 | 5845
TS5500Exc | SC\20\002\D | SC | 20 | 2 | D | 8 Coal Mining | 97.9 | 0 | 6.5 | 2014-11-01 | 2014-11-01 04:05 | 5067.3545 | [6 empty] | 5067 | 3818 | 0.32 | 0 | 0 | 6.37 | 5855
PH4100XPC#1 | MW\17\010\D | MW | 17 | 10 | D | 1 Prestrip - Thick | 100 | 88.8435 | 88.8435 | 2014-11-01 | 2014-11-05 06:35 | 214545.608 | 214546 | [7 empty] | 0 | 0 | 21.45 | 5.75 | 5906.21
TS Fleet 5 | No Production | No Production | [7 empty] | 2014-11-01 | 2014-12-01
TS6060#1 | MW\15\008\D | MW | 15 | 8 | D | 8 Coal Mining | 100 | 0 | 1.4 | 2014-11-01 03:07 | 2014-11-01 03:44 | 825.1728 | [6 empty] | 825 | 625 | 0.06 | 0 | 0 | 5.63 | 5917
TS6060#1 | MW\15\005\D | MW | 15 | 5 | D | 8 Coal Mining | 100 | 0 | 7.5 | 2014-11-01 03:44 | 2014-11-01 07:05 | 4472.4703 | [6 empty] | 4472 | 3376 | 0.34 | 0 | 0 | 5.9 | 5893
TS5500Exc | MW\16\013\D | MW | 16 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-11-01 04:05 | 2014-11-02 13:07 | 40991.7793 | [6 empty] | 40992 | 30964 | 4.24 | 0 | 0 | 5.85 | 5896
TS6060#1 | MW\16\003\D | MW | 16 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-11-01 07:05 | 2014-11-03 03:45 | 59552.6121 | [6 empty] | 59553 | 45174 | 4.52 | 0 | 0 | 5.38 | 5939
TS5500Exc | MW\16\004\D | MW | 16 | 4 | D | 8 Coal Mining | 100 | 0 | 0.6 | 2014-11-02 13:07 | 2014-11-02 13:25 | 377.2164 | [6 empty] | 377 | 285 | 0.03 | 0 | 0 | 5.75 | 5907
TS5500Exc | MW\16\007\D | MW | 16 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-11-02 13:25 | 2014-11-04 12:02 | 57835.8948 | [6 empty] | 57836 | 43552 | 4.36 | 0 | 0 | 6.1 | 5875
TS6060#1 | MC\26\011\D | MC | 26 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-11-03 03:45 | 2014-11-05 02:54 | 62846.7866 | [6 empty] | 62847 | 46933 | 4.69 | 0 | 0 | 7.63 | 5743
DRE1 | SC\20\005\D | SC | 20 | 5 | D | 6 DL | 100 | 0 | 100 | 2014-11-03 19:31 | 2014-11-12 04:05 | 726553.9164 |  |  |  | 61071 | 726554 | 479379 |  |  | 0 | 45 | 0 | 5.82 | 5903.64
PH4100A | SC\21\009\D | SC | 21 | 9 | D | 1 Prestrip - Thick | 100 | 90 | 90 | 2014-11-04 04:10 | 2014-11-08 07:10 | 167938.3615 | 167938 | [7 empty] | 0 | 0 | 14.22 | 6.33 | 5856.94
TS5500Exc | BC\31\003\D | BC | 31 | 3 | D | 8 Coal Mining | 29.2 | 0 | 29.2 | 2014-11-04 12:02 | 2014-11-05 06:33 | 22986.7021 | [6 empty] | 22987 | 17415 | 1.38 | 0 | 0 | 5.51 | 5929
TS6060#1 | MC\26\010\D | MC | 26 | 10 | D | 8 Coal Mining | 43.6 | 0 | 43.6 | 2014-11-05 02:54 | 2014-11-05 23:48 | 27878.7757 | [6 empty] | 27879 | 20803 | 2.08 | 0 | 0 | 7.67 | 5740
TS5500Exc | BC\31\003\D | BC | 31 | 3 | D | 8 Coal Mining | 70.8 | 0 | 70.8 | 2014-11-05 06:33 | 2014-11-07 03:30 | 55777.7669 | [6 empty] | 55778 | 42257 | 3.36 | 0 | 0 | 5.51 | 5929
PH4100XPC#1 | MW\18\010\D | MW | 18 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-11-05 06:35 | 2014-11-12 05:08 | 346915.7857 | 346916 | [7 empty] | 0 | 0 | 27.47 | 5.82 | 5900.15
DRE2 | BC\32\005\D | BC | 32 | 5 | D | 6 DL | 100 | 100 | 100 | 2014-11-05 11:09 | 2014-11-08 19:45 | 271151.1832 |  |  |  | 15475 | 271151 | 205602 |  |  | 0 | 30 | 0 | 6.34 | 5855.6
TS6060#1 | MW\16\006\D | MW | 16 | 6 | D | 8 Coal Mining | 26.9 | 0 | 26.9 | 2014-11-05 23:48 | 2014-11-06 11:45 | 15931.0588 | [6 empty] | 15931 | 11988 | 1.2 | 0 | 0 | 6.11 | 5875
TS6060#1 | DT\21\004\A | DT | 21 | 4 | A | 8 Coal Mining | 10.1 | 0 | 10.1 | 2014-11-06 11:45 | 2014-11-06 17:46 | 8007.7 | [6 empty] | 8008 | 5771 | 0.36 | 0 | 0 | 13.93 | 5178
TS6060#1 | DT\21\004\A | DT | 21 | 4 | A | 8 Coal Mining | 89.9 | 0 | 89.9 | 2014-11-06 17:46 | 2014-11-08 23:28 | 71602.2668 | [6 empty] | 71602 | 51604 | 3.25 | 0 | 0 | 13.93 | 5178
TS5500Shv | SC\20\010\D | SC | 20 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-11-06 17:59 | 2014-11-15 06:44 | 78251.6656 | [6 empty] | 78252 | 58671 | 4.89 | 0 | 0 | 6.72 | 5824
TS5500Exc | BC\32\006\D | BC | 32 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2014-11-07 03:30 | 2014-11-09 09:37 | 47145.7228 |  |  | 47146 | [5 empty] | 0 | 0 | 0 | 6.49 | 5843.01
PH4100A | SC\22\009\D | SC | 22 | 9 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-11-08 07:10 | 2014-11-13 15:40 | 217622.0278 | 217622 | [7 empty] | 0 | 0 | 18.48 | 6.33 | 5857.76
DRE2 | BC\32\004\D | BC | 32 | 4 | D | 6 DL | 100 | 100 | 100 | 2014-11-08 19:45 | 2014-11-11 02:29 | 184080.3709 |  |  |  | 8236 | 184080 | 156489 |  |  | 0 | 20.99 | 0 | 6.2 | 5867.75
TS6060#1 | MW\16\006\D | MW | 16 | 6 | D | 8 Coal Mining | 73.1 | 0 | 73.1 | 2014-11-08 23:28 | 2014-11-10 08:00 | 43370.4822 | [6 empty] | 43370 | 32635 | 3.26 | 0 | 0 | 6.11 | 5875
TS5500Exc | BC\32\006\D | BC | 32 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-11-09 09:37 | 2014-11-11 18:03 | 70022.8669 | [6 empty] | 70023 | 52605 | 4.78 | 0 | 0 | 6.49 | 5843
TS6060#1 | MW\16\008\D | MW | 16 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-11-10 08:00 | 2014-11-12 03:43 | 58284.2704 | [6 empty] | 58284 | 44067 | 4.41 | 0 | 0 | 5.8 | 5902
DRE2 | BC\32\003\D | BC | 32 | 3 | D | 6 DL | 100 | 100 | 100 | 2014-11-11 02:29 | 2014-11-14 06:39 | 256241.2866 |  |  |  | 11465 | 256241 | 217834 |  |  | 0 | 22.68 | 0 | 5.62 | 5918.17
TS5500Exc | BC\32\005\D | BC | 32 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-11-11 18:03 | 2014-11-13 20:05 | 62066.3106 | [6 empty] | 62066 | 46637 | 4.67 | 0 | 0 | 6.34 | 5856
TS6060#1 | MW\16\009\D | MW | 16 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-11-12 03:43 | 2014-11-14 00:07 | 59186.111 | [6 empty] | 59186 | 44715 | 4.47 | 0 | 0 | 5.75 | 5907
DRE1 | SC\20\006\D | SC | 20 | 6 | D | 6 DL | 100 | 100 | 90 | 2014-11-12 04:05 | 2014-11-20 13:33 | 729819.7029 |  |  |  | 55293 | 729820 | 434028 |  |  | 0 | 45 | 0 | 5.82 | 5902.81
PH4100XPC#1 | MW\17\011\D | MW | 17 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-11-12 05:08 | 2014-11-16 20:21 | 233873.5843 | 233874 | [7 empty] | 0 | 0 | 23 | 5.65 | 5913.99
PH4100A | SC\21\008\D | SC | 21 | 8 | D | 1 Prestrip - Thick | 100 | 90 | 90 | 2014-11-13 15:40 | 2014-11-18 16:31 | 204594.3382 | 204594 | [7 empty] | 0 | 0 | 17.26 | 6.05 | 5881.97
TS5500Exc | SC\20\005\D | SC | 20 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-11-13 20:05 | 2014-11-16 12:48 | 80299.7052 | [6 empty] | 80300 | 60689 | 5.06 | 0 | 0 | 5.82 | 5904
TS6060#1 | MW\16\011\D | MW | 16 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-11-14 00:07 | 2014-11-15 20:15 | 58852.2408 | [6 empty] | 58852 | 44424 | 4.44 | 0 | 0 | 5.64 | 5915
DRE2 | MC\27\002\D | MC | 27 | 2 | D | 6 DL | 100 | 100 | 100 | 2014-11-14 06:39 | 2014-11-23 23:40 | 783764.3741 |  |  |  | 55740 | 783764 | 563592 |  |  | 0 | 37.53 | 0 | 6.32 | 5858.54
TS5500Shv | SC\22\005\B | SC | 22 | 5 | B | 8 Coal Mining | 100 | 0 | 56.2 | 2014-11-15 06:44 | 2014-11-18 23:06 | 33777.7293 | [6 empty] | 33778 | 24944 | 2.08 | 0 | 0 | 9.07 | 5569
TS6060#1 | MW\16\010\D | MW | 16 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-11-15 20:15 | 2014-11-17 15:48 | 58061.3893 | [6 empty] | 58061 | 43827 | 4.38 | 0 | 0 | 5.7 | 5910
TS5500Exc | BC\32\004\D | BC | 32 | 4 | D | 8 Coal Mining | 97.5 | 0 | 97.5 | 2014-11-16 12:48 | 2014-11-18 13:17 | 60167.8651 | [6 empty] | 60168 | 45275 | 4.56 | 0 | 0 | 6.2 | 5868
PH4100XPC#1 | MW\18\011\B | MW | 18 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-11-16 20:21 | 2014-11-24 05:35 | 353163.8774 | 353164 | [7 empty] | 0 | 0 | 23.75 | 14.05 | 5217.78
TS6060#1 | DT\24\003\A2 | DT | 24 | 3 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2014-11-17 15:48 | 2014-11-18 16:29 | 32903.2969 | [6 empty] | 32903 | 23504 | 1.47 | 0 | 0 | 15.37 | 5096
TS5500Exc | BC\32\003\D | BC | 32 | 3 | D | 8 Coal Mining | 100 | 0 | 16.9 | 2014-11-18 13:17 | 2014-11-18 23:06 | 12185.5867 | [6 empty] | 12186 | 9219 | 0.79 | 0 | 0 | 5.62 | 5918
TS6060#1 | BC\32\004\D | BC | 32 | 4 | D | 8 Coal Mining | 2.5 | 0 | 2.5 | 2014-11-18 16:29 | 2014-11-18 17:37 | 1513.2035 | [6 empty] | 1513 | 1139 | 0.11 | 0 | 0 | 6.2 | 5868
PH4100A | SC\22\008\D | SC | 22 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-11-18 16:31 | 2014-11-24 22:46 | 254036.5902 | 254037 | [7 empty] | 0 | 0 | 21.47 | 5.9 | 5895.57
TS6060#1 | BC\31\006\D | BC | 31 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2014-11-18 17:37 | 2014-11-20 13:00 | 44094.5724 |  |  | 44095 | [5 empty] | 0 | 0 | 0 | 6.52 | 5840.87
TS5500Shv | DT\19\004\A | DT | 19 | 4 | A | 1 Prestrip - Thick | 67.6244 | 32.4998 | 32.4998 | 2014-11-18 23:06 | 2014-12-01 | 96737.1991 | 96737 | [7 empty] | 0 | 0 | 9.21 | 11.78 | 5365.73
TS5500Exc | DT\24\003\B | DT | 24 | 3 | B | 1 Prestrip - Thick | 15.7426 | 15.7426 | 15.7426 | 2014-11-18 23:06 | 2014-11-19 10:53 | 10266.0985 | 10266 | [7 empty] | 0 | 0 | 0.64 | 10.32 | 5368.99
TS5500Exc | MW\19\006\D | MW | 19 | 6 | D | 1 Prestrip - Thick | 29.5981 | 29.5981 | 29.5981 | 2014-11-19 10:53 | 2014-11-23 00:33 | 74963.264 | 74963 | [7 empty] | 0 | 0 | 7.41 | 6.35 | 5854.39
TS6060#1 | BW\19\003\B | BW | 19 | 3 | B | 1 Prestrip - Thick | 57.5609 | 53.5416 | 53.5416 | 2014-11-20 13:00 | 2014-12-01 | 253235.3283 | 253235 | [7 empty] | 0 | 0 | 25.04 | 11.17 | 5355.2
DRE1 | SC\21\011\D | SC | 21 | 11 | D | 6 DL | 100 | 0 | 56.2914 | 2014-11-20 13:33 | 2014-12-01 | 907222.23 |  |  |  | 49735 | 907222 | 393488 |  |  | 0 | 44.46 | 0 | 7.25 | 5776.43
TS5500Exc | MW\19\007\D | MW | 19 | 7 | D | 1 Prestrip - Thick | 58.6281 | 58.6281 | 58.6281 | 2014-11-23 00:33 | 2014-11-29 07:14 | 131747.8375 | 131748 | [7 empty] | 0 | 0 | 13.21 | 6.14 | 5871.48
DRE2 | MC\27\001\D | MC | 27 | 1 | D | 6 DL | 100 | 75.1237 | 75.1237 | 2014-11-23 23:40 | 2014-12-01 | 566221.2013 |  |  |  | 43059 | 566221 | 387528 |  |  | 0 | 40 | 0 | 6.49 | 5842.52
PH4100XPC#1 | DT\24\003\B | DT | 24 | 3 | B | 1 Prestrip - Thick | 100 | 84.2574 | 84.2574 | 2014-11-24 05:35 | 2014-11-25 06:12 | 54946.2947 | 54946 | [7 empty] | 0 | 0 | 3.41 | 10.32 | 5368.99
PH4100A | SC\23\002\B | SC | 23 | 2 | B | 1 Prestrip - Thick | 100 | 44.5324 | 44.5324 | 2014-11-24 22:46 | 2014-12-01 | 247742.9855 | 247743 | [7 empty] | 0 | 0 | 14.31 | 8.83 | 5589.14
PH4100XPC#1 | MW\17\012\D | MW | 17 | 12 | D | 1 Prestrip - Thick | 100 | 10.3383 | 10.3383 | 2014-11-25 06:12 | 2014-11-25 16:21 | 21350.7838 | 21351 | [7 empty] | 0 | 0 | 2.12 | 5.65 | 5914.44
PH4100XPC#1 | MW\18\012\D | MW | 18 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-11-25 16:21 | 2014-11-29 16:52 | 204091.9373 | 204092 | [7 empty] | 0 | 0 | 20.28 | 5.63 | 5915.88
TS5500Exc | MW\19\007\D | MW | 19 | 7 | D | 1 Prestrip - Thick | 21.747 | 15.8541 | 15.8541 | 2014-11-29 07:14 | 2014-12-01 | 35627.1221 | 35627 | [7 empty] | 0 | 0 | 3.57 | 6.14 | 5871.48
PH4100XPC#1 | MW\17\013\D | MW | 17 | 13 | D | 1 Prestrip - Thick | 100 | 28.5009 | 28.5009 | 2014-11-29 16:52 | 2014-11-30 11:58 | 40074.9329 | 40075 | [7 empty] | 0 | 0 | 6.34 | 5.85 | 5896.37
PH4100XPC#1 | MW\18\013\D | MW | 18 | 13 | D | 1 Prestrip - Thick | 100 | 23.048 | 23.048 | 2014-11-30 11:58 | 2014-12-01 | 25351.8801 | 25352 | [7 empty] | 0 | 0 | 5.01 | 5.84 | 5897.2
| EOP 11 : 2014\Nov | EOP 11 : 2014 | Nov | [6 empty] | 2014-12-01 | 2014-12-01 |  | 3317945 |  | 91240 | 336486 | 5030100 | 3176412 | 1200000 | 899915 | 83.14 | 0 | 288.7 | 6.87 | 5804.29
TS5500Shv | DT\19\004\A | DT | 19 | 4 | A | 1 Prestrip - Thick | 67.6244 | 35.1247 | 35.1247 | 2014-12-01 | 2014-12-14 15:49 | 104550.3223 | 104550 | [7 empty] | 0 | 0 | 9.96 | 11.78 | 5365.73
DRE1 | SC\21\011\D | SC | 21 | 11 | D | 6 DL | 100 | 0 | 33.7086 | 2014-12-01 | 2014-12-08 05:02 | 543266.1899 |  |  |  | 29782 | 543266 | 235630 |  |  | 0 | 44.46 | 0 | 7.25 | 5776.43
PH4100A | SC\23\002\B | SC | 23 | 2 | B | 1 Prestrip - Thick | 100 | 55.4676 | 55.4676 | 2014-12-01 | 2014-12-10 02:57 | 308578.3547 | 308578 | [7 empty] | 0 | 0 | 17.83 | 8.83 | 5589.14
DRE2 | MC\27\001\D | MC | 27 | 1 | D | 6 DL | 100 | 24.8763 | 24.8763 | 2014-12-01 | 2014-12-03 16:18 | 187497.5741 |  |  |  | 14258 | 187498 | 128325 |  |  | 0 | 40 | 0 | 6.49 | 5842.52
TS6060#1 | BW\19\003\B | BW | 19 | 3 | B | 1 Prestrip - Thick | 57.5609 | 4.0193 | 4.0193 | 2014-12-01 | 2014-12-01 23:01 | 19010.0031 | 19010 | [7 empty] | 0 | 0 | 1.88 | 11.17 | 5355.2
TS5500Exc | MW\19\007\D | MW | 19 | 7 | D | 1 Prestrip - Thick | 21.747 | 5.8929 | 5.8929 | 2014-12-01 | 2014-12-01 18:30 | 13242.4227 | 13242 | [7 empty] | 0 | 0 | 1.33 | 6.14 | 5871.48
PH4100XPC#1 | MW\18\013\D | MW | 18 | 13 | D | 1 Prestrip - Thick | 100 | 76.952 | 76.952 | 2014-12-01 | 2014-12-03 00:35 | 84644.0853 | 84644 | [7 empty] | 0 | 0 | 16.73 | 5.84 | 5897.2
TS Fleet 5 | No Production | No Production | [7 empty] | 2014-12-01 | 2015-01-01
TS5500Exc | SC\20\006\D | SC | 20 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-12-01 18:30 | 2014-12-04 23:14 | 77895.1231 | [6 empty] | 77895 | 59107 | 4.93 | 0 | 0 | 5.82 | 5903
TS6060#1 | BC\31\006\D | BC | 31 | 6 | D | 8 Coal Mining | 65.3 | 0 | 65.3 | 2014-12-01 23:01 | 2014-12-03 16:43 | 45482.2968 | [6 empty] | 45482 | 34183 | 3.11 | 0 | 0 | 6.52 | 5841
PH4100XPC#1 | DT\19\005\A | DT | 19 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-12-03 00:35 | 2014-12-07 22:28 | 215780.3585 | 215780 | [7 empty] | 0 | 0 | 16.83 | 10.35 | 5429.78
DRE2 | MC\27\012\D | MC | 27 | 12 | D | 6 DL | 100 | 100 | 100 | 2014-12-03 16:18 | 2014-12-08 20:36 | 362342.6934 |  |  |  | 6748 | 362343 | 161941 |  |  | 0 | 16.3 | 0 | 6.42 | 5847.56
TS6060#1 | BW\19\003\B | BW | 19 | 3 | B | 1 Prestrip - Thick | 42.4391 | 42.4391 | 42.4391 | 2014-12-03 16:43 | 2014-12-13 19:52 | 200723.6583 | 200724 | [7 empty] | 0 | 0 | 19.85 | 11.17 | 5355.2
TS5500Exc | BC\32\003\D | BC | 32 | 3 | D | 8 Coal Mining | 100 | 0 | 83.1 | 2014-12-04 23:14 | 2014-12-07 10:11 | 59848.5265 | [6 empty] | 59849 | 45277 | 3.87 | 0 | 0 | 5.62 | 5918
TS5500Exc | BC\31\006\D | BC | 31 | 6 | D | 8 Coal Mining | 34.7 | 0 | 34.7 | 2014-12-07 10:11 | 2014-12-08 09:57 | 24125.683 | [6 empty] | 24126 | 18132 | 1.65 | 0 | 0 | 6.52 | 5841
PH4100XPC#1 | DT\20\005\A | DT | 20 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-12-07 22:28 | 2014-12-18 02:55 | 448249.7621 | 448250 | [7 empty] | 0 | 0 | 30.17 | 10.43 | 5421.6
DRE1 | SC\21\010\D | SC | 21 | 10 | D | 6 DL | 100 | 0 | 90 | 2014-12-08 05:02 | 2014-12-16 22:22 | 657190.2219 |  |  |  | 55240 | 657190 | 433613 |  |  | 0 | 45 | 0 | 6.76 | 5819.97
TS5500Exc | SC\20\004\D | SC | 20 | 4 | D | 8 Coal Mining | 58.6 | 0 | 58.6 | 2014-12-08 09:57 | 2014-12-10 08:04 | 46820.2596 | [6 empty] | 46820 | 35357 | 2.95 | 0 | 0 | 5.87 | 5899
DRE2 | MC\27\011\D | MC | 27 | 11 | D | 6 DL | 100 | 100 | 100 | 2014-12-08 20:36 | 2014-12-22 03:01 | 928269.2684 |  |  |  | 70591 | 928269 | 635317 |  |  | 0 | 40 | 0 | 7.71 | 5735.75
PH4100A | SC\23\003\B | SC | 23 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-12-10 02:57 | 2014-12-18 04:20 | 273241.5196 | 273242 | [7 empty] | 0 | 0 | 21.19 | 8.94 | 5579.51
TS5500Exc | SC\21\011\D | SC | 21 | 11 | D | 7 PostStrip | 100 | 0 | 100 | 2014-12-10 08:04 | 2014-12-15 22:58 | 96153.6004 |  |  | 96154 | [5 empty] | 0 | 0 | 0 | 7.25 | 5776.43
TS6060#1 | DT\19\005\A | DT | 19 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2014-12-13 19:52 | 2014-12-15 20:50 | 53403.8568 | [6 empty] | 53404 | 39263 | 3.89 | 0 | 0 | 10.35 | 5430
TS5500Shv | SC\23\002\B | SC | 23 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-12-14 15:49 | 2014-12-24 16:03 | 87443.5007 | [6 empty] | 87444 | 64686 | 3.88 | 0 | 0 | 8.83 | 5589
TS6060#1 | DT\18\003\A2 | DT | 18 | 3 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2014-12-15 20:50 | 2014-12-16 12:37 | 17216.3479 | [6 empty] | 17216 | 12339 | 1.82 | 0 | 0 | 15.18 | 5075
TS5500Exc | SC\20\004\D | SC | 20 | 4 | D | 8 Coal Mining | 41.4 | 0 | 41.4 | 2014-12-15 22:58 | 2014-12-17 07:35 | 33116.2639 | [6 empty] | 33116 | 25008 | 2.08 | 0 | 0 | 5.87 | 5899
TS6060#1 | DT\17\003\B | DT | 17 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2014-12-16 12:37 | 2014-12-17 21:53 | 36294.5571 | [6 empty] | 36295 | 25519 | 4.14 | 0 | 0 | 18.64 | 4794
DRE1 | SC\21\009\D | SC | 21 | 9 | D | 6 DL | 100 | 0 | 90 | 2014-12-16 22:22 | 2014-12-25 15:12 | 655634.5602 |  |  |  | 55110 | 655635 | 432587 |  |  | 0 | 45 | 0 | 6.33 | 5856.94
TS5500Exc | SC\21\010\D | SC | 21 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-12-17 07:35 | 2014-12-20 12:26 | 78015.7048 | [6 empty] | 78016 | 58494 | 4.88 | 0 | 0 | 6.76 | 5820
TS6060#1 | DT\20\003\A2 | DT | 20 | 3 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2014-12-17 21:53 | 2014-12-20 18:06 | 74412.7358 | [6 empty] | 74413 | 53074 | 1.62 | 0 | 0 | 15.94 | 5016
PH4100XPC#1 | DT\18\003\B | DT | 18 | 3 | B | 1 Prestrip - Thick | 35 | 0 | 35 | 2014-12-18 02:55 | 2014-12-18 07:28 | 8390.5563 | 8391 | [7 empty] | 0 | 0 | 0.48 | 19.28 | 4740.82
PH4100A | SC\23\004\B | SC | 23 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-12-18 04:20 | 2014-12-29 15:58 | 381042.8983 | 381043 | [7 empty] | 0 | 0 | 26.25 | 9.01 | 5574.46
PH4100XPC#1 | DT\18\003\B | DT | 18 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 65 | 2014-12-18 07:28 | 2014-12-18 15:55 | 15582.4617 | 15582 | [7 empty] | 0 | 0 | 0.89 | 19.28 | 4740.82
PH4100XPC#1 | DT\20\007\A | DT | 20 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-12-18 15:55 | 2014-12-22 18:25 | 180063.5869 | 180064 | [7 empty] | 0 | 0 | 18.46 | 9.66 | 5456.68
TS5500Exc | SC\21\011\D | SC | 21 | 11 | D | 8 Coal Mining | 86.3 | 0 | 86.3 | 2014-12-20 12:26 | 2014-12-24 10:27 | 95453.9809 | [6 empty] | 95454 | 71058 | 4.06 | 0 | 0 | 7.25 | 5776
TS6060#1 | DT\20\005\A | DT | 20 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2014-12-20 18:06 | 2014-12-23 11:03 | 70853.6418 | [6 empty] | 70854 | 52068 | 3.83 | 0 | 0 | 10.43 | 5422
DRE2 | MC\27\010\D | MC | 27 | 10 | D | 6 DL | 100 | 70.1145 | 70.1145 | 2014-12-22 03:01 | 2015-01-01 | 690836.4641 |  |  |  | 52535 | 690836 | 472816 |  |  | 0 | 41.47 | 0 | 7.61 | 5744.77
PH4100XPC#1 | DT\20\003\B | DT | 20 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-12-22 18:25 | 2014-12-25 19:35 | 134862.1592 | 134862 | [7 empty] | 0 | 0 | 4.14 | 9.82 | 5474.73
TS6060#1 | DT\20\007\A | DT | 20 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2014-12-23 11:03 | 2014-12-25 09:01 | 50130.5307 | [6 empty] | 50131 | 36981 | 3.83 | 0 | 0 | 9.66 | 5457
TS5500Exc | SC\21\011\D | SC | 21 | 11 | D | 8 Coal Mining | 13.7 | 0 | 13.7 | 2014-12-24 10:27 | 2014-12-25 01:21 | 15111.4697 | [6 empty] | 15111 | 11249 | 0.64 | 0 | 0 | 7.25 | 5776
TS5500Shv | SC\23\003\B | SC | 23 | 3 | B | 8 Coal Mining | 100 | 0 | 44.9 | 2014-12-24 16:03 | 2014-12-27 18:36 | 27135.4042 | [6 empty] | 27135 | 20084 | 1.69 | 0 | 0 | 8.94 | 5580
TS5500Exc | SC\22\002\B | SC | 22 | 2 | B | 8 Coal Mining | 100 | 0 | 63.8 | 2014-12-25 01:21 | 2014-12-27 18:36 | 66247.0951 | [6 empty] | 66247 | 48969 | 2.47 | 0 | 0 | 8.77 | 5595
TS6060#1 | DT\19\003\A2 | DT | 19 | 3 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2014-12-25 09:01 | 2014-12-26 22:27 | 40829.9432 | [6 empty] | 40830 | 29188 | 1.64 | 0 | 0 | 15.68 | 5034
DRE1 | SC\21\008\D | SC | 21 | 8 | D | 6 DL | 100 | 0 | 90 | 2014-12-25 15:12 | 2014-12-31 22:42 | 475618.1731 |  |  |  | 55108 | 655618 | 432576 |  |  | 0 | 45 | 0 | 6.05 | 5881.97
PH4100XPC#1 | MW\19\003\A | MW | 19 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-12-25 19:35 | 2014-12-28 15:03 | 120803.2184 | 120803 | [7 empty] | 0 | 0 | 11.83 | 10.5 | 5411.1
TS6060#1 | DT\20\003\B | DT | 20 | 3 | B | 8 Coal Mining | 100 | 0 | 89.1 | 2014-12-26 22:27 | 2014-12-31 15:51 | 123699.5638 | [6 empty] | 123700 | 90994 | 2.82 | 0 | 0 | 9.82 | 5475
TS5500Shv | DT\19\004\A | DT | 19 | 4 | A | 1 Prestrip - Thick | 32.3756 | 10.8636 | 10.8636 | 2014-12-27 18:36 | 2015-01-01 | 32336.0349 | 32336 | [7 empty] | 0 | 0 | 3.08 | 11.78 | 5365.73
TS5500Exc | SC\21\009\D | SC | 21 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2014-12-27 18:36 | 2014-12-30 21:55 | 76463.5147 | [6 empty] | 76464 | 57650 | 4.8 | 0 | 0 | 6.33 | 5857
PH4100XPC#1 | DT\19\003\B | DT | 19 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2014-12-28 15:03 | 2014-12-30 07:40 | 74864.8924 | 74865 | [7 empty] | 0 | 0 | 4.13 | 17.86 | 4848.42
PH4100A | SC\23\005\B | SC | 23 | 5 | B | 1 Prestrip - Thick | 100 | 37.8351 | 37.8351 | 2014-12-29 15:58 | 2015-01-01 | 78283.6892 | 78284 | [7 empty] | 0 | 0 | 6.17 | 9.06 | 5569.47
PH4100XPC#1 | MW\20\003\A | MW | 20 | 3 | A | 1 Prestrip - Thick | 100 | 34.7965 | 34.7965 | 2014-12-30 07:40 | 2015-01-01 | 71956.1615 | 71956 | [7 empty] | 0 | 0 | 4.6 | 9.21 | 5502.33
TS5500Exc | SC\23\002\D | SC | 23 | 2 | D | 1 Prestrip - Thick | 73.9559 | 15.276 | 15.276 | 2014-12-30 21:55 | 2015-01-01 | 18586.0143 | 18586 | [7 empty] | 0 | 0 | 1.39 | 6.47 | 5845.94
TS6060#1 | BW\19\004\B | BW | 19 | 4 | B | 1 Prestrip - Thick | 23.6885 | 1.3782 | 1.3782 | 2014-12-31 15:51 | 2015-01-01 | 6739.0518 | 6739 | [7 empty] | 0 | 0 | 0.64 | 11.37 | 5357.54
DRE1 | SC\21\007\D | SC | 21 | 7 | D | 6 DL | 100 | 0 | 0.66958 | 2014-12-31 22:42 | 2015-01-01 | 4078.8549 |  |  |  | 410 | 5418 | 3221 |  |  | 0 | 45 | 0 | 5.81 | 5903.16
| EOP 12 : 2014\Dec | EOP 12 : 2014 | Dec | [6 empty] | 2015-01-01 | 2015-01-01 |  | 2791531 |  | 96154 | 339783 | 4686073 | 2936027 | 1200000 | 888683 | 64.58 | 0 | 217.81 | 9.28 | 5569.55
TS5500Shv | DT\19\004\A | DT | 19 | 4 | A | 1 Prestrip - Thick | 32.3756 | 21.512 | 21.512 | 2015-01-01 | 2015-01-03 16:46 | 64031.548 | 64032 | [7 empty] | 0 | 0 | 6.1 | 11.78 | 5365.73
DRE1 | SC\21\007\D | SC | 21 | 7 | D | 6 DL | 100 | 0 | 89.3304 | 2015-01-01 | 2015-01-07 13:53 | 544170.5211 |  |  |  | 54751 | 722831 | 429771 |  |  | 0 | 45 | 0 | 5.81 | 5903.16
PH4100A | SC\23\005\B | SC | 23 | 5 | B | 1 Prestrip - Thick | 100 | 62.1649 | 62.1649 | 2015-01-01 | 2015-01-04 08:43 | 128624.1008 | 128624 | [7 empty] | 0 | 0 | 10.13 | 9.06 | 5569.47
DRE2 | MC\27\010\D | MC | 27 | 10 | D | 6 DL | 100 | 29.8855 | 29.8855 | 2015-01-01 | 2015-01-04 16:43 | 294461.3097 |  |  |  | 22392 | 294461 | 201532 |  |  | 0 | 41.47 | 0 | 7.61 | 5744.77
TS6060#1 | BW\19\004\B | BW | 19 | 4 | B | 1 Prestrip - Thick | 23.6885 | 22.3103 | 22.3103 | 2015-01-01 | 2015-01-05 18:49 | 109092.0666 | 109092 | [7 empty] | 0 | 0 | 10.29 | 11.37 | 5357.54
TS5500Exc | SC\23\002\D | SC | 23 | 2 | D | 1 Prestrip - Thick | 73.9559 | 58.6799 | 58.6799 | 2015-01-01 | 2015-01-04 15:14 | 71394.6453 | 71395 | [7 empty] | 0 | 0 | 5.32 | 6.47 | 5845.94
PH4100XPC#1 | MW\20\003\A | MW | 20 | 3 | A | 1 Prestrip - Thick | 100 | 65.2035 | 65.2035 | 2015-01-01 | 2015-01-03 18:16 | 134835.4249 | 134835 | [7 empty] | 0 | 0 | 8.61 | 9.21 | 5502.33
TS Fleet 5 | No Production | No Production | [7 empty] | 2015-01-01 | 2015-02-01
TS5500Shv | SC\23\003\B | SC | 23 | 3 | B | 8 Coal Mining | 100 | 0 | 55.1 | 2015-01-03 16:46 | 2015-01-04 22:19 | 33350.4555 | [6 empty] | 33350 | 24685 | 2.07 | 0 | 0 | 8.94 | 5580
PH4100XPC#1 | MW\19\004\D | MW | 19 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-03 18:16 | 2015-01-06 08:38 | 125945.8411 | 125946 | [7 empty] | 0 | 0 | 12.51 | 6.22 | 5865.74
PH4100A | SC\23\006\B | SC | 23 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-04 08:43 | 2015-01-08 12:22 | 153863.6888 | 153864 | [7 empty] | 0 | 0 | 12.89 | 10.03 | 5488.62
TS5500Exc | SC\21\008\D | SC | 21 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-01-04 15:14 | 2015-01-07 09:04 | 76732.1929 | [6 empty] | 76732 | 58131 | 4.84 | 0 | 0 | 6.05 | 5882
DRE2 | MC\27\009\D | MC | 27 | 9 | D | 6 DL | 100 | 100 | 100 | 2015-01-04 16:43 | 2015-01-13 13:13 | 705252.4619 |  |  |  | 53631 | 705252 | 482682 |  |  | 0 | 41.46 | 0 | 7.27 | 5774.94
TS5500Shv | SC\23\004\B | SC | 23 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-01-04 22:19 | 2015-01-07 02:29 | 58861.9014 | [6 empty] | 58862 | 43528 | 3.65 | 0 | 0 | 9.01 | 5574
TS6060#1 | BW\16\007\D | BW | 16 | 7 | D | 8 Coal Mining | 44.4 | 0 | 44.4 | 2015-01-05 18:49 | 2015-01-06 17:57 | 28980.0278 | [6 empty] | 28980 | 21948 | 2.2 | 0 | 0 | 5.8 | 5904
PH4100XPC#1 | MW\20\004\D | MW | 20 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-06 08:38 | 2015-01-09 01:59 | 133908.1677 | 133908 | [7 empty] | 0 | 0 | 8.52 | 6.25 | 5863.73
TS6060#1 | BW\16\008\D | BW | 16 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-01-06 17:57 | 2015-01-08 23:11 | 66664.594 | [6 empty] | 66665 | 50327 | 5.03 | 0 | 0 | 6.02 | 5885
TS5500Shv | SC\23\005\B | SC | 23 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-01-07 02:29 | 2015-01-09 08:03 | 60452.5518 | [6 empty] | 60453 | 44676 | 3.72 | 0 | 0 | 9.06 | 5569
TS5500Exc | SC\22\002\B | SC | 22 | 2 | B | 8 Coal Mining | 100 | 0 | 36.2 | 2015-01-07 09:04 | 2015-01-08 17:19 | 37597.8961 | [6 empty] | 37598 | 27792 | 1.4 | 0 | 0 | 8.77 | 5595
DRE1 | SC\21\001\D | SC | 21 | 1 | D | 6 DL | 100 | 0 | 100 | 2015-01-07 13:53 | 2015-01-15 11:03 | 652000.4527 |  |  |  | 39567 | 652000 | 271676 |  |  | 0 | 45 | 0 | 6.67 | 5828.55
PH4100A | SC\23\008\D | SC | 23 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-08 12:22 | 2015-01-15 22:36 | 283277.8155 | 283278 | [7 empty] | 0 | 0 | 23.97 | 5.78 | 5905.87
TS5500Exc | SC\22\002\D | SC | 22 | 2 | D | 1 Prestrip - Thick | 100 | 95.4647 | 95.4647 | 2015-01-08 17:19 | 2015-01-16 02:53 | 145322.7962 | 145323 | [7 empty] | 0 | 0 | 8.74 | 6.51 | 5842.79
TS6060#1 | BW\16\009\D | BW | 16 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-01-08 23:11 | 2015-01-11 02:25 | 64155.3213 | [6 empty] | 64155 | 48395 | 4.85 | 0 | 0 | 5.72 | 5911
PH4100XPC#1 | DT\19\005\B | DT | 19 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-09 01:59 | 2015-01-09 14:42 | 26727.241 | 26727 | [7 empty] | 0 | 0 | 2.27 | 8.83 | 5566.02
TS5500Shv | SC\22\005\B | SC | 22 | 5 | B | 8 Coal Mining | 100 | 0 | 43.8 | 2015-01-09 08:03 | 2015-01-10 07:21 | 26287.0482 | [6 empty] | 26287 | 19412 | 1.62 | 0 | 0 | 9.07 | 5569
PH4100XPC#1 | DT\20\005\B | DT | 20 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-09 14:42 | 2015-01-10 09:03 | 38580.3656 | 38580 | [7 empty] | 0 | 0 | 2.87 | 8.83 | 5559.6
TS5500Shv | SC\22\006\B | SC | 22 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-01-10 07:21 | 2015-01-11 00:22 | 19198.8593 | [6 empty] | 19199 | 14002 | 1.16 | 0 | 0 | 11.49 | 5373
PH4100XPC#1 | DT\20\007\B | DT | 20 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-10 09:03 | 2015-01-10 21:50 | 26850.5792 | 26851 | [7 empty] | 0 | 0 | 2.81 | 8.27 | 5606.86
PH4100XPC#1 | MW\19\005\D | MW | 19 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-10 21:50 | 2015-01-15 21:22 | 234196.66 | 234197 | [7 empty] | 0 | 0 | 23.76 | 6.38 | 5850.71
TS5500Shv | SC\22\006\D | SC | 22 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-11 00:22 | 2015-01-15 00:04 | 94938.6322 | 94939 | [7 empty] | 0 | 0 | 7.87 | 5.8 | 5904.43
TS6060#1 | BW\16\010\D | BW | 16 | 10 | D | 8 Coal Mining | 99.5 | 0 | 99.5 | 2015-01-11 02:25 | 2015-01-13 01:11 | 58571.057 | [6 empty] | 58571 | 44078 | 4.89 | 0 | 0 | 5.99 | 5887
TS6060#1 | DT\19\003\B | DT | 19 | 3 | B | 8 Coal Mining | 37 | 0 | 37 | 2015-01-13 01:11 | 2015-01-14 08:19 | 38992.5257 | [6 empty] | 38993 | 27500 | 1.6 | 0 | 0 | 17.86 | 4848
DRE2 | MC\27\004\D | MC | 27 | 4 | D | 6 DL | 100 | 100 | 100 | 2015-01-13 13:13 | 2015-01-19 23:16 | 511272.1269 |  |  |  | 11904 | 511272 | 226174 |  |  | 0 | 23.82 | 0 | 5.97 | 5889.64
TS6060#1 | DT\20\003\B | DT | 20 | 3 | B | 8 Coal Mining | 100 | 0 | 10.9 | 2015-01-14 08:19 | 2015-01-14 20:20 | 15056.7714 | [6 empty] | 15057 | 11076 | 0.34 | 0 | 0 | 9.82 | 5475
TS6060#1 | DT\19\004\A | DT | 19 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2015-01-14 20:20 | 2015-01-16 15:14 | 53730.972 | [6 empty] | 53731 | 39199 | 3.92 | 0 | 0 | 11.78 | 5366
TS5500Shv | SC\22\005\D | SC | 22 | 5 | D | 1 Prestrip - Thick | 100 | 52.0726 | 52.0726 | 2015-01-15 00:04 | 2015-01-17 13:55 | 61355.4553 | 61355 | [7 empty] | 0 | 0 | 5.11 | 5.9 | 5896.43
DRE1 | SC\21\002\D | SC | 21 | 2 | D | 6 DL | 100 | 0 | 100 | 2015-01-15 11:03 | 2015-01-24 05:45 | 726164.5914 |  |  |  | 61038 | 726165 | 479122 |  |  | 0 | 45 | 0 | 6.43 | 5849.61
PH4100XPC#1 | MW\20\005\D | MW | 20 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-15 21:22 | 2015-01-23 15:00 | 365446.146 | 365446 | [7 empty] | 0 | 0 | 22.77 | 6.48 | 5842.78
PH4100A | SC\22\002\D | SC | 22 | 2 | D | 1 Prestrip - Thick | 100 | 4.5353 | 4.5353 | 2015-01-15 22:36 | 2015-01-16 02:53 | 6903.9743 | 6904 | [7 empty] | 0 | 0 | 0.42 | 6.51 | 5842.79
PH4100A | SC\22\005\D | SC | 22 | 5 | D | 1 Prestrip - Thick | 100 | 47.9274 | 47.9274 | 2015-01-16 02:53 | 2015-01-17 13:55 | 56471.3948 | 56471 | [7 empty] | 0 | 0 | 4.7 | 5.9 | 5896.43
TS5500Exc | SC\21\001\D | SC | 21 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2015-01-16 02:53 | 2015-01-18 02:25 | 38905.3655 |  |  | 38905 | [5 empty] | 0 | 0 | 0 | 6.67 | 5828.55
TS6060#1 | DT\21\003\A1 | DT | 21 | 3 | A1 | 8 Coal Mining | 100 | 0 | 100 | 2015-01-16 15:14 | 2015-01-17 14:48 | 29521.9295 | [6 empty] | 29522 | 21117 | 1.33 | 0 | 0 | 15.23 | 5093
TS5500Shv | MC\27\005\B | MC | 27 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-17 13:55 | 2015-01-18 05:49 | 15766.521 | 15767 | [7 empty] | 0 | 0 | 3.74 | 11.52 | 5183.83
PH4100A | SC\24\008\D | SC | 24 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-17 13:55 | 2015-01-24 21:59 | 279768.0878 | 279768 | [7 empty] | 0 | 0 | 23.5 | 5.72 | 5911.41
TS6060#1 | DT\22\003\A1 | DT | 22 | 3 | A1 | 8 Coal Mining | 100 | 0 | 100 | 2015-01-17 14:48 | 2015-01-18 16:00 | 31546.1845 | [6 empty] | 31546 | 22556 | 1.42 | 0 | 0 | 15.3 | 5090
TS5500Exc | SC\21\001\D | SC | 21 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-01-18 02:25 | 2015-01-19 21:26 | 50139.7694 | [6 empty] | 50140 | 37625 | 5.02 | 0 | 0 | 6.67 | 5829
TS5500Shv | MC\27\006\B | MC | 27 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-18 05:49 | 2015-01-19 20:36 | 38480.1698 | 38480 | [7 empty] | 0 | 0 | 3.81 | 10.73 | 5290.87
TS6060#1 | DT\24\003\B | DT | 24 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-01-18 16:00 | 2015-01-20 22:30 | 68257.9428 | [6 empty] | 68258 | 49771 | 3.09 | 0 | 0 | 10.32 | 5369
TS5500Shv | MC\27\007\B | MC | 27 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-19 20:36 | 2015-01-21 21:05 | 48092.7477 | 48093 | [7 empty] | 0 | 0 | 4.81 | 10.04 | 5343
TS5500Exc | MC\27\005\B | MC | 27 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-01-19 21:26 | 2015-01-20 16:06 | 21751.8006 | [6 empty] | 21752 | 15580 | 2.73 | 0 | 0 | 11.52 | 5184
DRE2 | MC\27\003\D | MC | 27 | 3 | D | 6 DL | 100 | 100 | 100 | 2015-01-19 23:16 | 2015-01-23 16:43 | 296881.7465 |  |  |  | 5529 | 296882 | 132685 |  |  | 0 | 17.84 | 0 | 6.04 | 5882.84
TS5500Exc | MC\27\006\B | MC | 27 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-01-20 16:06 | 2015-01-22 04:05 | 41943.1103 | [6 empty] | 41943 | 30278 | 3.01 | 0 | 0 | 10.73 | 5291
TS6060#1 | DT\26\003\B | DT | 26 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-01-20 22:30 | 2015-01-23 04:15 | 67319.7579 | [6 empty] | 67320 | 49016 | 3.08 | 0 | 0 | 10.64 | 5344
TS5500Shv | MC\27\008\B | MC | 27 | 8 | B | 1 Prestrip - Thick | 74.8788 | 74.8788 | 74.8788 | 2015-01-21 21:05 | 2015-01-22 12:26 | 15227.819 | 15228 | [7 empty] | 0 | 0 | 2.63 | 9.6 | 5373.31
TS5500Exc | MC\27\007\B | MC | 27 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-01-22 04:05 | 2015-01-23 15:41 | 41487.8985 | [6 empty] | 41488 | 30070 | 3 | 0 | 0 | 10.04 | 5343
TS5500Shv | MC\27\008\B | MC | 27 | 8 | B | 1 Prestrip - Thick | 25.1212 | 25.1212 | 25.1212 | 2015-01-22 12:26 | 2015-01-22 17:35 | 5108.7961 | 5109 | [7 empty] | 0 | 0 | 0.88 | 9.6 | 5373.31
TS5500Shv | DT\19\004\B | DT | 19 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-22 17:35 | 2015-01-23 23:15 | 29438.4474 | 29438 | [7 empty] | 0 | 0 | 2.93 | 9.97 | 5476.53
TS6060#1 | DT\27\003\A | DT | 27 | 3 | A | 8 Coal Mining | 100 | 0 | 84.2 | 2015-01-23 04:15 | 2015-01-23 19:12 | 18733.2357 | [6 empty] | 18733 | 13087 | 0.83 | 0 | 0 | 19.49 | 4772
PH4100XPC#1 | DT\21\003\A2 | DT | 21 | 3 | A2 | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-23 15:00 | 2015-01-24 11:11 | 42439.2724 | 42439 | [7 empty] | 0 | 0 | 2.67 | 14.42 | 5157.52
TS5500Exc | MC\27\008\B | MC | 27 | 8 | B | 8 Coal Mining | 100 | 0 | 12.4 | 2015-01-23 15:41 | 2015-01-23 19:12 | 4113.1964 | [6 empty] | 4113 | 2994 | 0.36 | 0 | 0 | 9.6 | 5373
DRE2 | MC\27\007\D | MC | 27 | 7 | D | 6 DL | 100 | 100 | 100 | 2015-01-23 16:43 | 2015-01-30 03:51 | 514877.4364 |  |  |  | 15316 | 514877 | 239953 |  |  | 0 | 25.49 | 0 | 7.23 | 5778.53
TS6060#1 | BW\19\004\B | BW | 19 | 4 | B | 1 Prestrip - Thick | 76.3115 | 38.2359 | 38.2359 | 2015-01-23 19:12 | 2015-02-01 | 186964.6069 | 186965 | [7 empty] | 0 | 0 | 17.63 | 11.37 | 5357.54
TS5500Exc | SC\23\005\D | SC | 23 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-23 19:12 | 2015-01-29 19:33 | 118127.0778 | 118127 | [7 empty] | 0 | 0 | 9.84 | 5.95 | 5891.31
TS5500Shv | DT\21\002\A2 | DT | 21 | 2 | A2 | 1 Prestrip - Thick | 28.8682 | 20.7307 | 20.7307 | 2015-01-23 23:15 | 2015-02-01 | 191470.925 | 191471 | [7 empty] | 0 | 0 | 8.26 | 17.69 | 4871.6
DRE1 | SC\21\003\D | SC | 21 | 3 | D | 6 DL | 100 | 0 | 88.3716 | 2015-01-24 05:45 | 2015-02-01 | 641897.6348 |  |  |  | 53955 | 641898 | 423523 |  |  | 0 | 45 | 0 | 6.12 | 5877.22
PH4100XPC#1 | DT\22\003\A2 | DT | 22 | 3 | A2 | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-01-24 11:11 | 2015-01-25 09:51 | 47651.0482 | 47651 | [7 empty] | 0 | 0 | 2.99 | 14.61 | 5145.11
PH4100A | SC\23\007\D | SC | 23 | 7 | D | 1 Prestrip - Thick | 100 | 97.4439 | 97.4439 | 2015-01-24 21:59 | 2015-02-01 | 270232.9915 | 270233 | [7 empty] | 0 | 0 | 22.68 | 5.56 | 5925.07
PH4100XPC#1 | MW\19\006\D | MW | 19 | 6 | D | 1 Prestrip - Thick | 100 | 70.4019 | 70.4019 | 2015-01-25 09:51 | 2015-01-29 05:02 | 178307.6651 | 178308 | [7 empty] | 0 | 0 | 17.62 | 6.35 | 5854.39
PH4100XPC#1 | MW\20\006\D | MW | 20 | 6 | D | 1 Prestrip - Thick | 100 | 33.8508 | 33.8508 | 2015-01-29 05:02 | 2015-02-01 | 132265.2043 | 132265 | [7 empty] | 0 | 0 | 8.18 | 6.46 | 5844.68
TS5500Exc | SC\23\004\D | SC | 23 | 4 | D | 1 Prestrip - Thick | 52.8167 | 37.571 | 37.571 | 2015-01-29 19:33 | 2015-02-01 | 42921.1297 | 42921 | [7 empty] | 0 | 0 | 3.59 | 6.03 | 5884.56
DRE2 | MC\27\006\D | MC | 27 | 6 | D | 6 DL | 100 | 28.0962 | 28.0962 | 2015-01-30 03:51 | 2015-02-01 | 146516.5186 |  |  |  | 3411 | 146517 | 64815 |  |  | 0 | 24.22 | 0 | 6.92 | 5803.6
| EOP 13 : 2015\Jan | EOP 13 : 2015 | Jan | [6 empty] | 2015-02-01 | 2015-02-01 |  | 3904029 |  | 38905 | 321495 | 5212156 | 2951934 | 1013447 | 746844 | 65.18 | 0 | 315.43 | 8.02 | 5678.61
DRE1 | SC\21\003\D | SC | 21 | 3 | D | 6 DL | 100 | 0 | 11.6284 | 2015-02-01 | 2015-02-01 23:51 | 84464.5428 |  |  |  | 7100 | 84465 | 55730 |  |  | 0 | 45 | 0 | 6.12 | 5877.22
TS5500Shv | DT\21\002\A2 | DT | 21 | 2 | A2 | 1 Prestrip - Thick | 28.8682 | 8.1376 | 8.1376 | 2015-02-01 | 2015-02-04 06:10 | 75159.849 | 75160 | [7 empty] | 0 | 0 | 3.24 | 17.69 | 4871.6
PH4100A | SC\23\007\D | SC | 23 | 7 | D | 1 Prestrip - Thick | 100 | 2.5561 | 2.5561 | 2015-02-01 | 2015-02-01 04:31 | 7088.6673 | 7089 | [7 empty] | 0 | 0 | 0.6 | 5.56 | 5925.07
DRE2 | MC\27\006\D | MC | 27 | 6 | D | 6 DL | 100 | 71.9038 | 71.9038 | 2015-02-01 | 2015-02-05 14:00 | 374965.486 |  |  |  | 8730 | 374965 | 165875 |  |  | 0 | 24.22 | 0 | 6.92 | 5803.6
TS6060#1 | BW\19\004\B | BW | 19 | 4 | B | 1 Prestrip - Thick | 76.3115 | 38.0756 | 38.0756 | 2015-02-01 | 2015-02-09 10:29 | 186180.8561 | 186181 | [7 empty] | 0 | 0 | 17.55 | 11.37 | 5357.54
TS5500Exc | SC\23\004\D | SC | 23 | 4 | D | 1 Prestrip - Thick | 52.8167 | 15.2457 | 15.2457 | 2015-02-01 | 2015-02-01 21:37 | 17416.756 | 17417 | [7 empty] | 0 | 0 | 1.46 | 6.03 | 5884.56
PH4100XPC#1 | MW\20\006\D | MW | 20 | 6 | D | 1 Prestrip - Thick | 100 | 66.1492 | 66.1492 | 2015-02-01 | 2015-02-06 12:52 | 258464.8801 | 258465 | [7 empty] | 0 | 0 | 15.99 | 6.46 | 5844.68
TS Fleet 5 | No Production | No Production | [7 empty] | 2015-02-01 | 2015-03-01
PH4100A | SC\24\007\D | SC | 24 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-02-01 04:31 | 2015-02-08 18:56 | 286074.6617 | 286075 | [7 empty] | 0 | 0 | 23.9 | 5.51 | 5929.46
TS5500Exc | MC\27\008\B | MC | 27 | 8 | B | 8 Coal Mining | 100 | 0 | 87.6 | 2015-02-01 21:37 | 2015-02-02 23:00 | 29095.8293 | [6 empty] | 29096 | 21182 | 2.53 | 0 | 0 | 9.6 | 5373
DRE1 | SC\21\004\D | SC | 21 | 4 | D | 6 DL | 100 | 0 | 100 | 2015-02-01 23:51 | 2015-02-10 12:26 | 724162.6521 |  |  |  | 60870 | 724163 | 477801 |  |  | 0 | 45 | 0 | 5.93 | 5894.02
TS5500Exc | SC\21\007\D | SC | 21 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-02-02 23:00 | 2015-02-05 18:17 | 77165.5207 | [6 empty] | 77166 | 58648 | 4.89 | 0 | 0 | 5.81 | 5903
TS5500Shv | MC\27\001\D | MC | 27 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-02-04 06:10 | 2015-02-06 07:52 | 54263.9015 | [6 empty] | 54264 | 40990 | 4.7 | 0 | 0 | 6.49 | 5843
DRE2 | MC\27\008\D | MC | 27 | 8 | D | 6 DL | 100 | 100 | 100 | 2015-02-05 14:00 | 2015-02-12 03:07 | 535574.4296 |  |  |  | 15932 | 535574 | 249598 |  |  | 0 | 26.58 | 0 | 7.04 | 5795.47
TS5500Exc | SC\21\002\D | SC | 21 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-02-05 18:17 | 2015-02-08 14:33 | 78299.2595 | [6 empty] | 78299 | 59035 | 4.92 | 0 | 0 | 6.43 | 5850
TS5500Shv | MC\27\002\D | MC | 27 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-02-06 07:52 | 2015-02-08 19:46 | 65416.9833 | [6 empty] | 65417 | 49516 | 4.76 | 0 | 0 | 6.32 | 5859
PH4100XPC#1 | MW\19\007\D | MW | 19 | 7 | D | 1 Prestrip - Thick | 100 | 19.6249 | 19.6249 | 2015-02-06 12:52 | 2015-02-07 11:24 | 44100.7083 | 44101 | [7 empty] | 0 | 0 | 4.42 | 6.14 | 5871.48
PH4100XPC#1 | MW\20\007\D | MW | 20 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-02-07 11:24 | 2015-02-15 00:11 | 355186.1939 | 355186 | [7 empty] | 0 | 0 | 22.23 | 6.11 | 5874.77
TS5500Exc | SC\21\003\D | SC | 21 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-02-08 14:33 | 2015-02-11 12:01 | 79664.211 | [6 empty] | 79664 | 60208 | 5.02 | 0 | 0 | 6.12 | 5877
PH4100A | SC\24\006\B | SC | 24 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-02-08 18:56 | 2015-02-13 03:55 | 160429.8489 | 160430 | [7 empty] | 0 | 0 | 13.39 | 9.6 | 5522.48
TS5500Shv | MC\27\011\D | MC | 27 | 11 | D | 8 Coal Mining | 14.3 | 0 | 14.3 | 2015-02-08 19:46 | 2015-02-09 04:06 | 9106.4613 | [6 empty] | 9106 | 6791 | 0.68 | 0 | 0 | 7.71 | 5736
TS5500Shv | MC\27\011\D | MC | 27 | 11 | D | 8 Coal Mining | 85.7 | 0 | 85.7 | 2015-02-09 04:06 | 2015-02-11 05:55 | 54397.0831 | [6 empty] | 54397 | 40566 | 4.05 | 0 | 0 | 7.71 | 5736
TS6060#1 | DT\21\003\A2 | DT | 21 | 3 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2015-02-09 10:29 | 2015-02-10 21:01 | 41851.442 | [6 empty] | 41851 | 30070 | 1.9 | 0 | 0 | 14.42 | 5158
DRE1 | SC\21\005\D | SC | 21 | 5 | D | 6 DL | 100 | 0 | 100 | 2015-02-10 12:26 | 2015-02-19 01:49 | 727008.1741 |  |  |  | 61109 | 727008 | 479679 |  |  | 0 | 45 | 0 | 5.86 | 5899.9
TS6060#1 | DT\22\003\A2 | DT | 22 | 3 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2015-02-10 21:01 | 2015-02-12 07:27 | 41729.9073 | [6 empty] | 41730 | 29940 | 1.89 | 0 | 0 | 14.61 | 5145
TS5500Shv | DT\20\005\B | DT | 20 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-02-11 05:55 | 2015-02-13 07:59 | 54677.2495 | [6 empty] | 54677 | 40446 | 3.05 | 0 | 0 | 8.83 | 5560
TS5500Exc | SC\21\004\D | SC | 21 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-02-11 12:01 | 2015-02-14 10:09 | 80426.2482 | [6 empty] | 80426 | 60736 | 5.07 | 0 | 0 | 5.93 | 5894
DRE2 | MC\27\005\D | MC | 27 | 5 | D | 6 DL | 100 | 100 | 100 | 2015-02-12 03:07 | 2015-02-18 06:05 | 500922.033 |  |  |  | 11663 | 500922 | 221595 |  |  | 0 | 23.67 | 0 | 6.34 | 5855.18
TS6060#1 | DT\19\004\B | DT | 19 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-02-12 07:27 | 2015-02-13 18:32 | 42529.6198 | [6 empty] | 42530 | 31237 | 3.12 | 0 | 0 | 9.97 | 5477
PH4100A | SC\24\005\B | SC | 24 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-02-13 03:55 | 2015-02-19 02:04 | 223876.6428 | 223877 | [7 empty] | 0 | 0 | 18.44 | 9.06 | 5569.15
TS5500Shv | MC\27\009\D | MC | 27 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-02-13 07:59 | 2015-02-15 18:44 | 64146.0508 | [6 empty] | 64146 | 47900 | 4.78 | 0 | 0 | 7.27 | 5775
TS6060#1 | DT\27\003\A | DT | 27 | 3 | A | 8 Coal Mining | 100 | 0 | 15.8 | 2015-02-13 18:32 | 2015-02-13 21:26 | 3512.6792 | [6 empty] | 3513 | 2454 | 0.16 | 0 | 0 | 19.49 | 4772
TS6060#1 | DT\28\003\B | DT | 28 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-02-13 21:26 | 2015-02-15 15:11 | 50606.585 | [6 empty] | 50607 | 36872 | 3.07 | 0 | 0 | 10.65 | 5351
TS5500Exc | SC\23\006\B | SC | 23 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-02-14 10:09 | 2015-02-15 15:17 | 33401.249 | [6 empty] | 33401 | 24551 | 2.03 | 0 | 0 | 10.03 | 5489
PH4100XPC#1 | DT\27\003\B | DT | 27 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-02-15 00:11 | 2015-02-16 07:57 | 65766.3743 | 65766 | [7 empty] | 0 | 0 | 4.14 | 10.67 | 5344.26
TS6060#1 | DT\17\004\B | DT | 17 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-02-15 15:11 | 2015-02-17 06:07 | 47184.9376 | [6 empty] | 47185 | 33158 | 4.13 | 0 | 0 | 18.34 | 4822
TS5500Exc | SC\24\006\B | SC | 24 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-02-15 15:17 | 2015-02-17 04:32 | 42724.9291 | [6 empty] | 42725 | 31477 | 2.62 | 0 | 0 | 9.6 | 5522
TS5500Shv | MC\27\010\D | MC | 27 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-02-15 18:44 | 2015-02-18 05:13 | 63860.1157 | [6 empty] | 63860 | 47614 | 4.77 | 0 | 0 | 7.61 | 5745
PH4100XPC#1 | DT\21\003\B | DT | 21 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-02-16 07:57 | 2015-02-17 13:21 | 60837.1055 | 60837 | [7 empty] | 0 | 0 | 3.82 | 10.12 | 5432.76
TS5500Exc | SC\23\006\D | SC | 23 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-02-17 04:32 | 2015-02-23 02:13 | 114082.1826 | 114082 | [7 empty] | 0 | 0 | 9.48 | 5.79 | 5905.1
TS6060#1 | DT\18\004\A | DT | 18 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2015-02-17 06:07 | 2015-02-18 12:37 | 36959.6136 | [6 empty] | 36960 | 26968 | 3.93 | 0 | 0 | 11.72 | 5381
PH4100XPC#1 | DT\22\003\B | DT | 22 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-02-17 13:21 | 2015-02-18 15:38 | 54371.8954 | 54372 | [7 empty] | 0 | 0 | 3.41 | 10.07 | 5415.47
TS5500Shv | BW\19\004\B | BW | 19 | 4 | B | 8 Coal Mining | 64.5 | 0 | 64.5 | 2015-02-18 05:13 | 2015-02-19 13:03 | 34761.1649 | [6 empty] | 34761 | 25297 | 2.54 | 0 | 0 | 11.37 | 5358
DRE2 | BC\31\001\D | BC | 31 | 1 | D | 6 DL | 100 | 91.8688 | 91.8688 | 2015-02-18 06:05 | 2015-03-01 | 879117.2514 |  |  |  | 50174 | 879117 | 666595 |  |  | 0 | 30 | 0 | 5.43 | 5932.73
TS6060#1 | DT\21\003\B | DT | 21 | 3 | B | 8 Coal Mining | 100 | 0 | 92.3 | 2015-02-18 12:37 | 2015-02-20 17:36 | 64218.9587 | [6 empty] | 64219 | 47038 | 2.94 | 0 | 0 | 10.12 | 5433
PH4100XPC#1 | DT\18\004\B | DT | 18 | 4 | B | 1 Prestrip - Thick | 100 | 0 | 100 | 2015-02-18 15:38 | 2015-02-19 18:00 | 54578.862 | 54579 | [7 empty] | 0 | 0 | 5.01 | 0 | 0
DRE1 | SC\21\006\D | SC | 21 | 6 | D | 6 DL | 100 | 0 | 90 | 2015-02-19 01:49 | 2015-02-26 19:02 | 655573.1464 |  |  |  | 55105 | 655573 | 432546 |  |  | 0 | 45 | 0 | 5.81 | 5903.95
PH4100A | SC\24\004\B | SC | 24 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-02-19 02:04 | 2015-02-28 06:43 | 347690.2546 | 347690 | [7 empty] | 0 | 0 | 28.2 | 9.01 | 5574.18
TS5500Shv | DT\21\002\A2 | DT | 21 | 2 | A2 | 1 Prestrip - Thick | 69.9494 | 23.6231 | 23.6231 | 2015-02-19 13:03 | 2015-03-01 | 218186.3691 | 218186 | [7 empty] | 0 | 0 | 9.41 | 17.69 | 4871.6
PH4100XPC#1 | MW\19\008\D | MW | 19 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-02-19 18:00 | 2015-02-24 14:16 | 227577.3541 | 227577 | [7 empty] | 0 | 0 | 22.6 | 6.09 | 5876.16
TS6060#1 | BW\19\005\B | BW | 19 | 5 | B | 1 Prestrip - Thick | 47.6573 | 34.0916 | 34.0916 | 2015-02-20 17:36 | 2015-03-01 | 182410.0567 | 182410 | [7 empty] | 0 | 0 | 16.85 | 10.45 | 5450.87
TS5500Exc | SC\23\004\D | SC | 23 | 4 | D | 1 Prestrip - Thick | 47.1833 | 47.1833 | 47.1833 | 2015-02-23 02:13 | 2015-02-25 21:10 | 53902.2677 | 53902 | [7 empty] | 0 | 0 | 4.51 | 6.03 | 5884.56
PH4100XPC#1 | MW\20\008\B | MW | 20 | 8 | B | 1 Prestrip - Thick | 100 | 42.0624 | 42.0624 | 2015-02-24 14:16 | 2015-03-01 | 195516.0234 | 195516 | [7 empty] | 0 | 0 | 9.53 | 19.26 | 4726.51
TS5500Exc | SC\23\003\D | SC | 23 | 3 | D | 1 Prestrip - Thick | 100 | 50.7743 | 50.7743 | 2015-02-25 21:10 | 2015-03-01 | 60253.8502 | 60254 | [7 empty] | 0 | 0 | 5.04 | 6.23 | 5867.38
DRE1 | SC\22\012\D | SC | 22 | 12 | D | 6 DL | 100 | 0 | 24.3357 | 2015-02-26 19:02 | 2015-03-01 | 187469.8845 |  |  |  | 10334 | 187470 | 81378 |  |  | 0 | 41.37 | 0 | 7.34 | 5767.51
PH4100A | SC\24\003\B | SC | 24 | 3 | B | 1 Prestrip - Thick | 100 | 6.8838 | 6.8838 | 2015-02-28 06:43 | 2015-03-01 | 27195.4971 | 27195 | [7 empty] | 0 | 0 | 2.18 | 8.94 | 5578.42
| EOP 14 : 2015\Feb | EOP 14 : 2015 | Feb | [6 empty] | 2015-03-01 | 2015-03-01 |  | 3276347 |  |  | 281016 | 4669258 | 2830798 | 1150000 | 852691 | 77.54 | 0 | 245.39 | 8.15 | 5673.67
DRE1 | SC\22\012\D | SC | 22 | 12 | D | 6 DL | 100 | 0 | 75.6643 | 2015-03-01 | 2015-03-07 20:40 | 582878.3909 |  |  |  | 32131 | 582878 | 253019 |  |  | 0 | 41.37 | 0 | 7.34 | 5767.51
TS5500Shv | DT\21\002\A2 | DT | 21 | 2 | A2 | 1 Prestrip - Thick | 69.9494 | 46.3263 | 46.3263 | 2015-03-01 | 2015-03-17 14:33 | 427875.2517 | 427875 | [7 empty] | 0 | 0 | 18.46 | 17.69 | 4871.6
DRE2 | BC\31\001\D | BC | 31 | 1 | D | 6 DL | 100 | 8.1312 | 8.1312 | 2015-03-01 | 2015-03-01 22:49 | 77809.3597 |  |  |  | 4441 | 77809 | 58999 |  |  | 0 | 30 | 0 | 5.43 | 5932.73
PH4100A | SC\24\003\B | SC | 24 | 3 | B | 1 Prestrip - Thick | 100 | 93.1162 | 93.1162 | 2015-03-01 | 2015-03-10 00:46 | 367872.1042 | 367872 | [7 empty] | 0 | 0 | 29.44 | 8.94 | 5578.42
TS6060#1 | BW\19\005\B | BW | 19 | 5 | B | 1 Prestrip - Thick | 47.6573 | 13.5657 | 13.5657 | 2015-03-01 | 2015-03-03 22:41 | 72584.4003 | 72584 | [7 empty] | 0 | 0 | 6.7 | 10.45 | 5450.87
TS5500Exc | SC\23\003\D | SC | 23 | 3 | D | 1 Prestrip - Thick | 100 | 49.2257 | 49.2257 | 2015-03-01 | 2015-03-03 18:03 | 58416.2415 | 58416 | [7 empty] | 0 | 0 | 4.89 | 6.23 | 5867.38
PH4100XPC#1 | MW\20\008\B | MW | 20 | 8 | B | 1 Prestrip - Thick | 100 | 57.9376 | 57.9376 | 2015-03-01 | 2015-03-06 15:04 | 269307.1693 | 269307 | [7 empty] | 0 | 0 | 13.12 | 19.26 | 4726.51
TS Fleet 5 | No Production | No Production | [7 empty] | 2015-03-01 | 2015-04-01
DRE2 | BW\17\009\B | BW | 17 | 9 | B | 6 DL | 100 | 0 | 100 | 2015-03-01 22:49 | 2015-03-05 06:35 | 271908.2873 |  |  |  |  | 271908 | 226590 |  |  | 0 | 18.34 | 0 | 12.48 | 5296.99
TS5500Exc | SC\21\005\D | SC | 21 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-03-03 18:03 | 2015-03-06 09:41 | 80150.9102 | [6 empty] | 80151 | 60575 | 5.06 | 0 | 0 | 5.86 | 5900
TS6060#1 | DT\21\003\B | DT | 21 | 3 | B | 8 Coal Mining | 100 | 0 | 7.7 | 2015-03-03 22:41 | 2015-03-04 02:39 | 5354.9208 | [6 empty] | 5355 | 3922 | 0.25 | 0 | 0 | 10.12 | 5433
TS6060#1 | DT\22\003\B | DT | 22 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-03-04 02:39 | 2015-03-06 05:22 | 68654.3207 | [6 empty] | 68654 | 50246 | 3.14 | 0 | 0 | 10.07 | 5415
DRE2 | BW\17\008\B | BW | 17 | 8 | B | 6 DL | 100 | 0 | 100 | 2015-03-05 06:35 | 2015-03-08 08:22 | 251494.9722 |  |  |  |  | 251495 | 209579 |  |  | 0 | 16.49 | 0 | 13.24 | 5250.17
TS6060#1 | DT\16\005\A | DT | 16 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2015-03-06 05:22 | 2015-03-06 06:30 | 1517.185 | [6 empty] | 1517 | 1115 | 2.94 | 0 | 0 | 10.45 | 5469
TS6060#1 | DT\17\005\A | DT | 17 | 5 | A | 8 Coal Mining | 100 | 0 | 49.7 | 2015-03-06 06:30 | 2015-03-06 12:04 | 7544.0454 | [6 empty] | 7544 | 5535 | 1.88 | 0 | 0 | 10.7 | 5430
TS5500Exc | SC\24\005\B | SC | 24 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-03-06 09:41 | 2015-03-08 09:40 | 60456.1588 | [6 empty] | 60456 | 44679 | 3.72 | 0 | 0 | 9.06 | 5569
TS6060#1 | DT\17\005\B | DT | 17 | 5 | B | 1 Prestrip - Thick | 100 | 66.2532 | 66.2532 | 2015-03-06 12:04 | 2015-03-06 21:27 | 9679.4592 | 9679 | [7 empty] | 0 | 0 | 1.31 | 19.53 | 4719.67
PH4100XPC#1 | DT\16\005\B | DT | 16 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-03-06 15:04 | 2015-03-06 19:14 | 9320.0843 | 9320 | [7 empty] | 0 | 0 | 1.3 | 17.14 | 4911.91
PH4100XPC#1 | DT\17\005\B | DT | 17 | 5 | B | 1 Prestrip - Thick | 100 | 33.7468 | 33.7468 | 2015-03-06 19:14 | 2015-03-06 21:27 | 4930.3435 | 4930 | [7 empty] | 0 | 0 | 0.67 | 19.53 | 4719.67
TS6060#1 | DT\17\005\B | DT | 17 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-03-06 21:27 | 2015-03-08 03:38 | 40856.0741 | [6 empty] | 40856 | 28574 | 4.2 | 0 | 0 | 19.53 | 4720
PH4100XPC#1 | MW\19\009\D | MW | 19 | 9 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-03-06 21:27 | 2015-03-11 07:20 | 224087.6263 | 224088 | [7 empty] | 0 | 0 | 22.36 | 6.1 | 5875.11
DRE1 | SC\22\011\D | SC | 22 | 11 | D | 6 DL | 100 | 0 | 100 | 2015-03-07 20:40 | 2015-03-16 09:14 | 724096.8576 |  |  |  | 60864 | 724097 | 477758 |  |  | 0 | 45 | 0 | 7.28 | 5774.35
TS6060#1 | DT\16\005\B | DT | 16 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-03-08 03:38 | 2015-03-09 03:50 | 32738.4221 | [6 empty] | 32738 | 23212 | 3.82 | 0 | 0 | 17.14 | 4912
DRE2 | BW\17\007\B | BW | 17 | 7 | B | 6 DL | 100 | 0 | 100 | 2015-03-08 08:22 | 2015-03-11 10:20 | 252126.7761 |  |  |  |  | 252127 | 210106 |  |  | 0 | 15.98 | 0 | 12.86 | 5289.86
TS5500Exc | SC\22\012\D | SC | 22 | 12 | D | 7 PostStrip | 100 | 0 | 100 | 2015-03-08 09:40 | 2015-03-10 15:42 | 47786.4246 |  |  | 47786 | [5 empty] | 0 | 0 | 0 | 7.34 | 5767.51
TS6060#1 | DT\19\005\B | DT | 19 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-03-09 03:50 | 2015-03-10 13:07 | 45046.7338 | [6 empty] | 45047 | 33352 | 3.13 | 0 | 0 | 8.83 | 5566
PH4100A | SC\24\002\B | SC | 24 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-03-10 00:46 | 2015-03-21 11:45 | 468879.3002 | 468879 | [7 empty] | 0 | 0 | 34.55 | 8.88 | 5583.57
TS6060#1 | MW\19\003\A | MW | 19 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2015-03-10 13:07 | 2015-03-11 08:23 | 26074.7298 | [6 empty] | 26075 | 19165 | 1.85 | 0 | 0 | 10.5 | 5411
TS5500Exc | SC\21\006\D | SC | 21 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-03-10 15:42 | 2015-03-13 05:50 | 78249.9134 | [6 empty] | 78250 | 59329 | 4.94 | 0 | 0 | 5.81 | 5904
PH4100XPC#1 | MW\20\009\B | MW | 20 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-03-11 07:20 | 2015-03-22 12:13 | 539159.2003 | 539159 | [7 empty] | 0 | 0 | 25.24 | 19.04 | 4781.46
TS6060#1 | DT\20\007\B | DT | 20 | 7 | B | 8 Coal Mining | 84.7 | 0 | 84.7 | 2015-03-11 08:23 | 2015-03-12 08:31 | 32661.4053 | [6 empty] | 32661 | 24247 | 2.56 | 0 | 0 | 8.27 | 5607
DRE2 | BW\17\006\B | BW | 17 | 6 | B | 6 DL | 100 | 0 | 100 | 2015-03-11 10:20 | 2015-03-14 06:41 | 232962.0184 |  |  |  |  | 232962 | 194135 |  |  | 0 | 14.97 | 0 | 11.06 | 5416.41
TS6060#1 | BW\19\005\B | BW | 19 | 5 | B | 1 Prestrip - Thick | 52.3427 | 52.3427 | 52.3427 | 2015-03-12 08:31 | 2015-03-23 17:17 | 280063.7045 | 280064 | [7 empty] | 0 | 0 | 25.87 | 10.45 | 5450.87
TS5500Exc | MW\19\003\B | MW | 19 | 3 | B | 1 Prestrip - Thick | 73.9988 | 73.9988 | 73.9988 | 2015-03-13 05:50 | 2015-03-13 21:22 | 13740.1578 | 13740 | [7 empty] | 0 | 0 | 1.37 | 8.56 | 5597.18
TS5500Exc | SC\22\012\D | SC | 22 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-03-13 21:22 | 2015-03-15 12:23 | 49150.6811 | [6 empty] | 49151 | 36559 | 4.59 | 0 | 0 | 7.34 | 5768
DRE2 | BW\17\005\B | BW | 17 | 5 | B | 6 DL | 100 | 0 | 100 | 2015-03-14 06:41 | 2015-03-17 15:25 | 275181.5414 |  |  |  |  | 275182 | 229318 |  |  | 0 | 16.14 | 0 | 10.49 | 5431.58
TS5500Exc | SC\24\003\B | SC | 24 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-03-15 12:23 | 2015-03-17 12:40 | 60811.0125 | [6 empty] | 60811 | 45010 | 3.77 | 0 | 0 | 8.94 | 5578
DRE1 | SC\22\010\D | SC | 22 | 10 | D | 6 DL | 100 | 0 | 100 | 2015-03-16 09:14 | 2015-03-24 21:45 | 723954.7858 |  |  |  | 60852 | 723955 | 477664 |  |  | 0 | 45 | 0 | 6.8 | 5816.38
TS5500Exc | SC\22\011\D | SC | 22 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-03-17 12:40 | 2015-03-20 01:57 | 77195.0213 | [6 empty] | 77195 | 57513 | 4.79 | 0 | 0 | 7.28 | 5774
TS5500Shv | DT\21\002\A2 | DT | 21 | 2 | A2 | 1 Prestrip - Thick | 1.1823 | 1.1823 | 1.1823 | 2015-03-17 14:33 | 2015-03-18 00:43 | 10920.2123 | 10920 | [7 empty] | 0 | 0 | 0.47 | 17.69 | 4871.6
DRE2 | BW\17\004\B | BW | 17 | 4 | B | 6 DL | 100 | 0 | 100 | 2015-03-17 15:25 | 2015-03-21 10:51 | 311634.9614 |  |  |  |  | 311635 | 259696 |  |  | 0 | 17.64 | 0 | 11.08 | 5370.66
TS5500Shv | DT\21\002\A2 | DT | 21 | 2 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2015-03-18 00:43 | 2015-03-19 12:58 | 44197.5022 | [6 empty] | 44198 | 31222 | 1.45 | 0 | 0 | 17.69 | 4872
TS5500Shv | BC\31\001\D | BC | 31 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-03-19 12:58 | 2015-03-22 15:11 | 90510.2693 | [6 empty] | 90510 | 68809 | 4.06 | 0 | 0 | 5.43 | 5933
TS5500Exc | SC\24\004\B | SC | 24 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-03-20 01:57 | 2015-03-22 01:11 | 59506.2412 | [6 empty] | 59506 | 44006 | 3.68 | 0 | 0 | 9.01 | 5574
DRE2 | BW\17\002\B | BW | 17 | 2 | B | 6 DL | 100 | 0 | 100 | 2015-03-21 10:51 | 2015-03-24 18:29 | 271436.9975 |  |  |  |  | 271437 | 226197 |  |  | 0 | 17.32 | 0 | 11.02 | 5353.69
PH4100A | SC\23\012\D | SC | 23 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-03-21 11:45 | 2015-03-25 19:54 | 175132.3009 | 175132 | [7 empty] | 0 | 0 | 14.23 | 7.36 | 5766.67
TS5500Exc | SC\23\002\D | SC | 23 | 2 | D | 1 Prestrip - Thick | 26.0441 | 26.0441 | 26.0441 | 2015-03-22 01:11 | 2015-03-23 13:01 | 31687.2698 | 31687 | [7 empty] | 0 | 0 | 2.36 | 6.47 | 5845.94
PH4100XPC#1 | MW\19\003\B | MW | 19 | 3 | B | 1 Prestrip - Thick | 100 | 26.0012 | 26.0012 | 2015-03-22 12:13 | 2015-03-22 14:23 | 4827.9242 | 4828 | [7 empty] | 0 | 0 | 0.48 | 8.56 | 5597.18
PH4100XPC#1 | MW\19\010\B | MW | 19 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-03-22 14:23 | 2015-03-28 21:18 | 304640.313 | 304640 | [7 empty] | 0 | 0 | 28.42 | 16.36 | 5031.67
TS5500Shv | DT\21\002\B | DT | 21 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-03-22 15:11 | 2015-03-25 19:16 | 81557.0269 | 81557 | [7 empty] | 0 | 0 | 3.83 | 9.87 | 5467.6
TS5500Exc | SC\24\002\B | SC | 24 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-03-23 13:01 | 2015-03-25 18:25 | 67249.318 | [6 empty] | 67249 | 49785 | 3.9 | 0 | 0 | 8.88 | 5584
TS6060#1 | DT\20\007\B | DT | 20 | 7 | B | 8 Coal Mining | 15.3 | 0 | 15.3 | 2015-03-23 17:17 | 2015-03-23 21:39 | 5896.8847 | [6 empty] | 5897 | 4378 | 0.46 | 0 | 0 | 8.27 | 5607
TS6060#1 | BW\16\010\D | BW | 16 | 10 | D | 8 Coal Mining | 0.5 | 0 | 0.5 | 2015-03-23 21:39 | 2015-03-23 21:52 | 297.5368 | [6 empty] | 298 | 224 | 0.02 | 0 | 0 | 5.99 | 5887
TS6060#1 | BW\19\001\B | BW | 19 | 1 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-03-23 21:52 | 2015-03-25 15:51 | 56815.8628 | [6 empty] | 56816 | 41535 | 3.77 | 0 | 0 | 10.85 | 5372
DRE2 | BW\17\001\B | BW | 17 | 1 | B | 6 DL | 100 | 0 | 100 | 2015-03-24 18:29 | 2015-03-31 04:55 | 526420.8516 |  |  |  |  | 526421 | 250677 |  |  | 0 | 18.05 | 0 | 10.86 | 5373.97
DRE1 | SC\22\009\D | SC | 22 | 9 | D | 6 DL | 100 | 0 | 83.2069 | 2015-03-24 21:45 | 2015-04-01 | 602606.7657 |  |  |  | 50652 | 602607 | 397599 |  |  | 0 | 45 | 0 | 6.33 | 5857.76
TS6060#1 | BW\19\002\B | BW | 19 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-03-25 15:51 | 2015-03-27 03:25 | 48146.8853 | [6 empty] | 48147 | 35047 | 3.51 | 0 | 0 | 11.46 | 5325
TS5500Exc | SC\22\010\D | SC | 22 | 10 | D | 8 Coal Mining | 100 | 0 | 67.3 | 2015-03-25 18:25 | 2015-03-27 12:04 | 52477.3179 | [6 empty] | 52477 | 39347 | 3.28 | 0 | 0 | 6.8 | 5816
TS5500Shv | DT\21\002\B | DT | 21 | 2 | B | 8 Coal Mining | 100 | 0 | 55 | 2015-03-25 19:16 | 2015-03-27 12:04 | 49752.9686 | [6 empty] | 49753 | 36598 | 1.74 | 0 | 0 | 9.87 | 5468
PH4100A | SC\24\012\D | SC | 24 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-03-25 19:54 | 2015-03-30 10:20 | 185984.4662 | 185984 | [7 empty] | 0 | 0 | 12.81 | 7.36 | 5765.51
TS6060#1 | BW\19\003\B | BW | 19 | 3 | B | 8 Coal Mining | 100 | 0 | 22.8 | 2015-03-27 03:25 | 2015-03-27 12:04 | 11710.6787 | [6 empty] | 11711 | 8523 | 0.85 | 0 | 0 | 11.17 | 5355
TS5500Shv | DT\21\004\B | DT | 21 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-03-27 12:04 | 2015-03-29 07:44 | 46803.8489 | 46804 | [7 empty] | 0 | 0 | 2.92 | 9.64 | 5468.31
TS6060#1 | BW\19\006\B | BW | 19 | 6 | B | 1 Prestrip - Thick | 33.8525 | 23.5227 | 23.5227 | 2015-03-27 12:04 | 2015-04-01 | 110658.1606 | 110658 | [7 empty] | 0 | 0 | 10.7 | 10.51 | 5467.83
TS5500Exc | SC\24\006\D | SC | 24 | 6 | D | 1 Prestrip - Thick | 100 | 81.0079 | 81.0079 | 2015-03-27 12:04 | 2015-04-01 | 95445.6987 | 95446 | [7 empty] | 0 | 0 | 7.95 | 5.79 | 5905.45
PH4100XPC#1 | MW\20\010\A | MW | 20 | 10 | A | 1 Prestrip - Thick | 100 | 34.6257 | 34.6257 | 2015-03-28 21:18 | 2015-04-01 | 149387.4601 | 149387 | [7 empty] | 0 | 0 | 9.1 | 12.26 | 5363.78
TS5500Shv | DT\21\005\A | DT | 21 | 5 | A | 1 Prestrip - Thick | 37.087 | 10.9712 | 10.9712 | 2015-03-29 07:44 | 2015-04-01 | 68618.3965 | 68618 | [7 empty] | 0 | 0 | 3.92 | 10.43 | 5410.12
PH4100A | SC\23\011\D | SC | 23 | 11 | D | 1 Prestrip - Thick | 100 | 59.7295 | 59.7295 | 2015-03-30 10:20 | 2015-04-01 | 63698.3628 | 63698 | [7 empty] | 0 | 0 | 5.51 | 7.31 | 5771.97
DRE2 | BW\16\006\D | BW | 16 | 6 | D | 6 DL | 100 | 0 | 0 | 2015-03-31 04:55 | 2015-03-31 04:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\16\005\D | BW | 16 | 5 | D | 6 DL | 100 | 0 | 0 | 2015-03-31 04:55 | 2015-03-31 04:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\16\004\D | BW | 16 | 4 | D | 6 DL | 100 | 0 | 0 | 2015-03-31 04:55 | 2015-03-31 04:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\16\003\D | BW | 16 | 3 | D | 6 DL | 100 | 0 | 0 | 2015-03-31 04:55 | 2015-03-31 04:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\16\002\D | BW | 16 | 2 | D | 6 DL | 100 | 0 | 0 | 2015-03-31 04:55 | 2015-03-31 04:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\16\001\D | BW | 16 | 1 | D | 6 DL | 100 | 0 | 0 | 2015-03-31 04:55 | 2015-03-31 04:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\16\007\D | BW | 16 | 7 | D | 6 DL | 100 | 0 | 0 | 2015-03-31 04:55 | 2015-03-31 04:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\16\008\D | BW | 16 | 8 | D | 6 DL | 100 | 0 | 0 | 2015-03-31 04:55 | 2015-03-31 04:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\16\009\D | BW | 16 | 9 | D | 6 DL | 100 | 0 | 0 | 2015-03-31 04:55 | 2015-03-31 04:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\16\010\D | BW | 16 | 10 | D | 6 DL | 100 | 0 | 0 | 2015-03-31 04:55 | 2015-03-31 04:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | DT\16\003\D | DT | 16 | 3 | D | 6 DL | 100 | 40.7944 | 40.7944 | 2015-03-31 04:55 | 2015-04-01 | 65022.6344 |  |  |  | 2482 | 65023 | 59563 |  |  | 0 | 18.48 | 0 | 6.05 | 5883.11
| EOP 15 : 2015\Mar | EOP 15 : 2015 | Mar | [6 empty] | 2015-04-01 | 2015-04-01 |  | 4075276 |  | 47786 | 211422 | 5169535 | 3530900 | 1153023 | 852507 | 77.37 | 0 | 287.98 | 9.75 | 5529.47
DRE1 | SC\22\009\D | SC | 22 | 9 | D | 6 DL | 100 | 0 | 16.7931 | 2015-04-01 | 2015-04-02 10:21 | 121620.2985 |  |  |  | 10223 | 121620 | 80245 |  |  | 0 | 45 | 0 | 6.33 | 5857.76
TS5500Shv | DT\21\005\A | DT | 21 | 5 | A | 1 Prestrip - Thick | 37.087 | 26.1158 | 26.1158 | 2015-04-01 | 2015-04-07 02:24 | 163339.0163 | 163339 | [7 empty] | 0 | 0 | 9.34 | 10.43 | 5410.12
PH4100A | SC\23\011\D | SC | 23 | 11 | D | 1 Prestrip - Thick | 100 | 40.2705 | 40.2705 | 2015-04-01 | 2015-04-01 23:59 | 42946.3826 | 42946 | [7 empty] | 0 | 0 | 3.71 | 7.31 | 5771.97
DRE2 | DT\16\003\D | DT | 16 | 3 | D | 6 DL | 100 | 59.2056 | 59.2056 | 2015-04-01 | 2015-04-02 03:41 | 94368.2487 |  |  |  | 3602 | 94368 | 86444 |  |  | 0 | 18.48 | 0 | 6.05 | 5883.11
TS6060#1 | BW\19\006\B | BW | 19 | 6 | B | 1 Prestrip - Thick | 33.8525 | 10.3298 | 10.3298 | 2015-04-01 | 2015-04-02 21:21 | 48594.5199 | 48595 | [7 empty] | 0 | 0 | 4.7 | 10.51 | 5467.83
PH4100XPC#1 | MW\20\010\A | MW | 20 | 10 | A | 1 Prestrip - Thick | 100 | 65.3743 | 65.3743 | 2015-04-01 | 2015-04-07 08:02 | 282047.5371 | 282048 | [7 empty] | 0 | 0 | 17.19 | 12.26 | 5363.78
TS5500Exc | SC\24\006\D | SC | 24 | 6 | D | 1 Prestrip - Thick | 100 | 18.9921 | 18.9921 | 2015-04-01 | 2015-04-02 00:13 | 22377.0669 | 22377 | [7 empty] | 0 | 0 | 1.86 | 5.79 | 5905.45
TS Fleet 5 | No Production | No Production | [7 empty] | 2015-04-01 | 2015-05-01
PH4100A | SC\24\011\D | SC | 24 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-04-01 23:59 | 2015-04-04 14:17 | 111415.7032 | 111416 | [7 empty] | 0 | 0 | 9.61 | 7.3 | 5772.49
TS5500Exc | SC\22\010\D | SC | 22 | 10 | D | 8 Coal Mining | 100 | 0 | 32.7 | 2015-04-02 00:13 | 2015-04-02 19:35 | 25496.7979 | [6 empty] | 25497 | 19117 | 1.59 | 0 | 0 | 6.8 | 5816
DRE2 | DT\16\004\D | DT | 16 | 4 | D | 6 DL | 100 | 100 | 100 | 2015-04-02 03:41 | 2015-04-04 08:29 | 180011.0202 |  |  |  | 8054 | 180011 | 153030 |  |  | 0 | 21.55 | 0 | 5.4 | 5938.17
DRE1 | SC\22\008\D | SC | 22 | 8 | D | 6 DL | 100 | 0 | 100 | 2015-04-02 10:21 | 2015-04-10 23:25 | 725889.5559 |  |  |  | 61015 | 725890 | 478941 |  |  | 0 | 45 | 0 | 5.9 | 5895.57
TS5500Exc | SC\22\009\D | SC | 22 | 9 | D | 8 Coal Mining | 29.5 | 0 | 29.5 | 2015-04-02 19:35 | 2015-04-03 12:53 | 22764.506 | [6 empty] | 22765 | 17177 | 1.43 | 0 | 0 | 6.33 | 5858
TS6060#1 | BW\19\003\B | BW | 19 | 3 | B | 8 Coal Mining | 100 | 0 | 77.2 | 2015-04-02 21:21 | 2015-04-04 01:27 | 39719.9598 | [6 empty] | 39720 | 28906 | 2.88 | 0 | 0 | 11.17 | 5355
TS5500Exc | SC\22\009\D | SC | 22 | 9 | D | 8 Coal Mining | 70.5 | 0 | 70.5 | 2015-04-03 12:53 | 2015-04-05 06:10 | 54329.1022 | [6 empty] | 54329 | 40995 | 3.42 | 0 | 0 | 6.33 | 5858
TS6060#1 | BW\19\004\B | BW | 19 | 4 | B | 8 Coal Mining | 35.5 | 0 | 35.5 | 2015-04-04 01:27 | 2015-04-04 14:59 | 19140.9352 | [6 empty] | 19141 | 13929 | 1.4 | 0 | 0 | 11.37 | 5358
DRE2 | DT\16\005\D | DT | 16 | 5 | D | 6 DL | 100 | 100 | 100 | 2015-04-04 08:29 | 2015-04-06 07:27 | 160087.302 |  |  |  | 7163 | 160087 | 136092 |  |  | 0 | 23.21 | 0 | 5.35 | 5941.8
PH4100A | SC\23\010\D | SC | 23 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-04-04 14:17 | 2015-04-07 19:33 | 138429.0638 | 138429 | [7 empty] | 0 | 0 | 11.9 | 6.85 | 5812.15
TS6060#1 | BW\19\005\B | BW | 19 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-04-04 14:59 | 2015-04-06 04:43 | 53356.4058 | [6 empty] | 53356 | 38985 | 3.91 | 0 | 0 | 10.45 | 5451
TS5500Exc | SC\24\005\D | SC | 24 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-04-05 06:10 | 2015-04-10 14:09 | 118250.4658 | 118250 | [7 empty] | 0 | 0 | 9.85 | 6.02 | 5885.53
TS6060#1 | BW\19\006\B | BW | 19 | 6 | B | 1 Prestrip - Thick | 66.1475 | 66.1475 | 66.1475 | 2015-04-06 04:43 | 2015-04-18 07:11 | 311178.1633 | 311178 | [7 empty] | 0 | 0 | 30.09 | 10.51 | 5467.83
DRE2 | MW\17\003\D | MW | 17 | 3 | D | 6 DL | 100 | 100 | 100 | 2015-04-06 07:27 | 2015-04-09 14:24 | 269123.4238 |  |  |  | 12041 | 269123 | 228785 |  |  | 0 | 23.93 | 0 | 5.47 | 5931.08
TS5500Shv | DT\21\002\B | DT | 21 | 2 | B | 8 Coal Mining | 100 | 0 | 45 | 2015-04-07 02:24 | 2015-04-08 10:19 | 40668.2495 | [6 empty] | 40668 | 29916 | 1.42 | 0 | 0 | 9.87 | 5468
PH4100XPC#1 | MW\19\011\B | MW | 19 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-04-07 08:02 | 2015-04-14 07:16 | 312154.449 | 312154 | [7 empty] | 0 | 0 | 29.09 | 13.98 | 5221.76
PH4100A | SC\24\010\D | SC | 24 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-04-07 19:33 | 2015-04-10 23:27 | 135747.4934 | 135747 | [7 empty] | 0 | 0 | 11.67 | 6.89 | 5808.07
TS5500Shv | MC\27\003\D | MC | 27 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-04-08 10:19 | 2015-04-10 11:39 | 62835.4174 | [6 empty] | 62835 | 47617 | 4.8 | 0 | 0 | 6.04 | 5883
DRE2 | MW\17\004\D | MW | 17 | 4 | D | 6 DL | 100 | 0 | 100 | 2015-04-09 14:24 | 2015-04-11 16:28 | 170632.5897 |  |  |  | 6513 | 170633 | 156305 |  |  | 0 | 15.95 | 0 | 5.93 | 5891.02
TS5500Shv | MC\27\004\D | MC | 27 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-04-10 11:39 | 2015-04-12 14:50 | 65207.4352 | [6 empty] | 65207 | 49387 | 4.93 | 0 | 0 | 5.97 | 5890
TS5500Exc | SC\24\004\D | SC | 24 | 4 | D | 1 Prestrip - Thick | 18.752 | 18.752 | 18.752 | 2015-04-10 14:09 | 2015-04-11 11:03 | 19311.5518 | 19312 | [7 empty] | 0 | 0 | 1.61 | 6.08 | 5880
DRE1 | SC\22\002\D | SC | 22 | 2 | D | 6 DL | 100 | 0 | 100 | 2015-04-10 23:25 | 2015-04-27 09:12 | 1393866.308 |  |  |  | 84587 | 1393866 | 580798 |  |  | 0 | 45 | 0 | 6.51 | 5842.79
PH4100A | SC\23\009\D | SC | 23 | 9 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-04-10 23:27 | 2015-04-16 15:36 | 243301.1383 | 243301 | [7 empty] | 0 | 0 | 20.69 | 6.31 | 5859.58
TS5500Exc | SC\22\008\D | SC | 22 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-04-11 11:03 | 2015-04-13 21:42 | 77196.5556 | [6 empty] | 77197 | 58624 | 4.89 | 0 | 0 | 5.9 | 5896
DRE2 | MW\17\005\D | MW | 17 | 5 | D | 6 DL | 100 | 0 | 100 | 2015-04-11 16:28 | 2015-04-13 13:15 | 152642.7974 |  |  |  | 5826 | 152643 | 139825 |  |  | 0 | 14.29 | 0 | 6.16 | 5870.9
TS5500Shv | MC\27\005\D | MC | 27 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-04-12 14:50 | 2015-04-14 14:51 | 61173.6578 | [6 empty] | 61174 | 46080 | 4.61 | 0 | 0 | 6.34 | 5855
DRE2 | MW\17\006\D | MW | 17 | 6 | D | 6 DL | 100 | 0 | 100 | 2015-04-13 13:15 | 2015-04-15 01:24 | 123230.0978 |  |  |  | 4703 | 123230 | 112883 |  |  | 0 | 11.61 | 0 | 6.19 | 5868.18
TS5500Exc | SC\24\003\D | SC | 24 | 3 | D | 1 Prestrip - Thick | 33.8046 | 33.8046 | 33.8046 | 2015-04-13 21:42 | 2015-04-15 12:15 | 35625.2735 | 35625 | [7 empty] | 0 | 0 | 2.98 | 6.27 | 5863.35
PH4100XPC#1 | MW\20\011\A | MW | 20 | 11 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-04-14 07:16 | 2015-04-23 22:25 | 428240.1961 | 428240 | [7 empty] | 0 | 0 | 25.6 | 11.02 | 5447.28
TS5500Shv | MC\27\006\D | MC | 27 | 6 | D | 8 Coal Mining | 34.5 | 0 | 34.5 | 2015-04-14 14:51 | 2015-04-15 06:48 | 20328.3299 | [6 empty] | 20328 | 15206 | 1.52 | 0 | 0 | 6.92 | 5804
DRE2 | MW\17\007\D | MW | 17 | 7 | D | 6 DL | 100 | 0 | 100 | 2015-04-15 01:24 | 2015-04-18 07:29 | 266173.583 |  |  |  | 10970 | 266174 | 208425 |  |  | 0 | 21.63 | 0 | 6.13 | 5872.11
TS5500Shv | DT\21\005\A | DT | 21 | 5 | A | 1 Prestrip - Thick | 62.913 | 62.913 | 62.913 | 2015-04-15 06:48 | 2015-04-29 23:30 | 393483.4325 | 393483 | [7 empty] | 0 | 0 | 22.5 | 10.43 | 5410.12
TS5500Exc | SC\24\002\D | SC | 24 | 2 | D | 1 Prestrip - Thick | 33.8046 | 33.8046 | 33.8046 | 2015-04-15 12:15 | 2015-04-16 18:44 | 28151.7845 | 28152 | [7 empty] | 0 | 0 | 3.02 | 6.42 | 5850.79
PH4100A | SC\24\009\D | SC | 24 | 9 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-04-16 15:36 | 2015-04-22 09:37 | 246199.82 | 246200 | [7 empty] | 0 | 0 | 20.92 | 6.3 | 5860.17
TS5500Exc | MW\21\003\A | MW | 21 | 3 | A | 1 Prestrip - Thick | 0.8692 | 0.8692 | 0.8692 | 2015-04-16 18:44 | 2015-04-16 21:26 | 2498.8231 | 2499 | [7 empty] | 0 | 0 | 0.15 | 8.89 | 5517.72
TS5500Exc | MW\21\003\A | MW | 21 | 3 | A | 1 Prestrip - Thick | 99.1308 | 99.1308 | 99.1308 | 2015-04-16 21:26 | 2015-04-29 17:22 | 284986.4482 | 284986 | [7 empty] | 0 | 0 | 16.8 | 8.89 | 5517.72
TS6060#1 | DT\19\003\B | DT | 19 | 3 | B | 8 Coal Mining | 100 | 0 | 63 | 2015-04-18 07:11 | 2015-04-20 06:06 | 66329.3587 | [6 empty] | 66329 | 46780 | 2.73 | 0 | 0 | 17.86 | 4848
DRE2 | MW\17\008\D | MW | 17 | 8 | D | 6 DL | 100 | 0 | 100 | 2015-04-18 07:29 | 2015-04-21 02:55 | 229825.8002 |  |  |  | 10283 | 229826 | 195378 |  |  | 0 | 20.44 | 0 | 5.96 | 5887.09
TS6060#1 | DT\18\003\B | DT | 18 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-04-20 06:06 | 2015-04-21 16:39 | 48846.9978 | [6 empty] | 48847 | 34211 | 4.2 | 0 | 0 | 19.28 | 4741
DRE2 | MW\17\009\D | MW | 17 | 9 | D | 6 DL | 100 | 0 | 100 | 2015-04-21 02:55 | 2015-04-24 05:01 | 252604.1776 |  |  |  | 11302 | 252604 | 214742 |  |  | 0 | 22.24 | 0 | 5.89 | 5893.85
TS6060#1 | DT\27\003\B | DT | 27 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-04-21 16:39 | 2015-04-23 15:55 | 66833.5964 | [6 empty] | 66834 | 48657 | 3.04 | 0 | 0 | 10.67 | 5344
PH4100A | SC\24\004\D | SC | 24 | 4 | D | 1 Prestrip - Thick | 100 | 81.248 | 81.248 | 2015-04-22 09:37 | 2015-04-24 07:51 | 83672.2779 | 83672 | [7 empty] | 0 | 0 | 6.99 | 6.08 | 5880
TS6060#1 | BW\17\007\B | BW | 17 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-04-23 15:55 | 2015-04-24 13:01 | 29833.1096 | [6 empty] | 29833 | 21472 | 2.14 | 0 | 0 | 12.86 | 5290
PH4100XPC#1 | MW\19\012\B | MW | 19 | 12 | B | 1 Prestrip - Thick | 100 | 86.5378 | 86.5378 | 2015-04-23 22:25 | 2015-05-01 | 313872.1317 | 313872 | [7 empty] | 0 | 0 | 20.49 | 12.82 | 5311.48
DRE2 | MW\17\010\D | MW | 17 | 10 | D | 6 DL | 100 | 0 | 100 | 2015-04-24 05:01 | 2015-04-27 02:46 | 237715.9591 |  |  |  | 10636 | 237716 | 202085 |  |  | 0 | 21 | 0 | 5.75 | 5906.21
PH4100A | SC\24\003\D | SC | 24 | 3 | D | 1 Prestrip - Thick | 100 | 66.1954 | 66.1954 | 2015-04-24 07:51 | 2015-04-25 22:23 | 69760.4588 | 69760 | [7 empty] | 0 | 0 | 5.83 | 6.27 | 5863.35
TS6060#1 | BW\17\006\B | BW | 17 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-04-24 13:01 | 2015-04-25 16:48 | 39287.2318 | [6 empty] | 39287 | 28559 | 3.14 | 0 | 0 | 11.06 | 5416
TS6060#1 | BW\17\008\B | BW | 17 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-04-25 16:48 | 2015-04-27 02:27 | 47584.5724 | [6 empty] | 47585 | 34280 | 3.58 | 0 | 0 | 13.24 | 5250
PH4100A | SC\24\002\D | SC | 24 | 2 | D | 1 Prestrip - Thick | 100 | 66.1954 | 66.1954 | 2015-04-25 22:23 | 2015-04-27 04:50 | 55126.0723 | 55126 | [7 empty] | 0 | 0 | 5.91 | 6.42 | 5850.79
TS6060#1 | BW\17\009\B | BW | 17 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-04-27 02:27 | 2015-04-28 14:24 | 50838.1583 | [6 empty] | 50838 | 36894 | 3.83 | 0 | 0 | 12.48 | 5297
DRE2 | MW\17\011\D | MW | 17 | 11 | D | 6 DL | 100 | 0 | 100 | 2015-04-27 02:46 | 2015-04-30 11:24 | 274861.5985 |  |  |  | 12298 | 274862 | 233663 |  |  | 0 | 23.88 | 0 | 5.65 | 5913.99
PH4100A | SC\25\008\D | SC | 25 | 8 | D | 1 Prestrip - Thick | 100 | 65.276 | 65.276 | 2015-04-27 04:50 | 2015-05-01 | 163385.8213 | 163386 | [7 empty] | 0 | 0 | 13.54 | 5.7 | 5912.83
DRE1 | SC\22\003\D | SC | 22 | 3 | D | 6 DL | 100 | 0 | 42.322 | 2015-04-27 09:12 | 2015-05-01 | 307207.8379 |  |  |  | 25823 | 307208 | 202695 |  |  | 0 | 45 | 0 | 6.17 | 5872.1
TS6060#1 | BW\17\005\B | BW | 17 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-04-28 14:24 | 2015-04-30 01:08 | 49123.4508 | [6 empty] | 49123 | 35895 | 3.81 | 0 | 0 | 10.49 | 5432
TS5500Exc | SC\22\002\D | SC | 22 | 2 | D | 7 PostStrip | 100 | 0 | 34.0161 | 2015-04-29 17:22 | 2015-05-01 | 28292.2289 |  |  | 28292 | [5 empty] | 0 | 0 | 0 | 6.51 | 5842.79
TS5500Shv | BW\19\006\B | BW | 19 | 6 | B | 8 Coal Mining | 100 | 0 | 63.3 | 2015-04-29 23:30 | 2015-05-01 | 31193.6424 | [6 empty] | 31194 | 22737 | 2.26 | 0 | 0 | 10.51 | 5468
TS6060#1 | BW\19\007\B | BW | 19 | 7 | B | 1 Prestrip - Thick | 55.3381 | 4.7113 | 4.7113 | 2015-04-30 01:08 | 2015-05-01 | 24388.7906 | 24389 | [7 empty] | 0 | 0 | 2.24 | 12.4 | 5330.83
DRE2 | MW\17\012\D | MW | 17 | 12 | D | 6 DL | 100 | 0 | 17.7212 | 2015-04-30 11:24 | 2015-05-01 | 42915.402 |  |  |  | 1920 | 42915 | 36483 |  |  | 0 | 21.22 | 0 | 5.65 | 5914.44
| EOP 16 : 2015\Apr | EOP 16 : 2015 | Apr | [6 empty] | 2015-05-01 | 2015-05-01 |  | 4078484 |  | 28292 | 286959 | 5002776 | 3446817 | 972087 | 715424 | 65.54 | 0 | 308.26 | 8.05 | 5694.06
DRE1 | SC\22\003\D | SC | 22 | 3 | D | 6 DL | 100 | 0 | 57.678 | 2015-05-01 | 2015-05-06 02:49 | 418673.8085 |  |  |  | 35192 | 418674 | 276240 |  |  | 0 | 45 | 0 | 6.17 | 5872.1
TS5500Shv | BW\19\006\B | BW | 19 | 6 | B | 8 Coal Mining | 100 | 0 | 36.7 | 2015-05-01 | 2015-05-01 13:58 | 18064.1146 | [6 empty] | 18064 | 13167 | 1.31 | 0 | 0 | 10.51 | 5468
PH4100A | SC\25\008\D | SC | 25 | 8 | D | 1 Prestrip - Thick | 100 | 34.724 | 34.724 | 2015-05-01 | 2015-05-02 23:50 | 86914.3236 | 86914 | [7 empty] | 0 | 0 | 7.2 | 5.7 | 5912.83
DRE2 | MW\17\012\D | MW | 17 | 12 | D | 6 DL | 100 | 0 | 82.2788 | 2015-05-01 | 2015-05-03 10:27 | 199254.1197 |  |  |  | 8915 | 199254 | 169388 |  |  | 0 | 21.22 | 0 | 5.65 | 5914.44
PH4100XPC#1 | MW\19\012\B | MW | 19 | 12 | B | 1 Prestrip - Thick | 100 | 13.4622 | 13.4622 | 2015-05-01 | 2015-05-01 22:48 | 48827.169 | 48827 | [7 empty] | 0 | 0 | 3.19 | 12.82 | 5311.48
TS6060#1 | BW\19\007\B | BW | 19 | 7 | B | 1 Prestrip - Thick | 55.3381 | 50.6268 | 50.6268 | 2015-05-01 | 2015-05-11 02:05 | 262076.4343 | 262076 | [7 empty] | 0 | 0 | 24.04 | 12.4 | 5330.83
TS5500Exc | SC\22\002\D | SC | 22 | 2 | D | 7 PostStrip | 100 | 0 | 65.9839 | 2015-05-01 | 2015-05-03 10:33 | 54880.8394 |  |  | 54881 | [5 empty] | 0 | 0 | 0 | 6.51 | 5842.79
TS Fleet 5 | No Production | No Production | [7 empty] | 2015-05-01 | 2015-06-01
TS5500Shv | DT\21\004\B | DT | 21 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-05-01 13:58 | 2015-05-03 17:49 | 66984.2151 | [6 empty] | 66984 | 49194 | 3.07 | 0 | 0 | 9.64 | 5468
PH4100XPC#1 | MW\19\013\D | MW | 19 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-05-01 22:48 | 2015-05-06 00:57 | 217324.0565 | 217324 | [7 empty] | 0 | 0 | 32.26 | 5.82 | 5899.94
PH4100A | SC\26\008\D | SC | 26 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-05-02 23:50 | 2015-05-09 08:29 | 278322.35 | 278322 | [7 empty] | 0 | 0 | 23.27 | 5.75 | 5908.44
DRE2 | MW\17\013\D | MW | 17 | 13 | D | 6 DL | 100 | 0 | 100 | 2015-05-03 10:27 | 2015-05-05 12:23 | 170191.2462 |  |  |  | 6827 | 170191 | 98138 |  |  | 0 | 21.31 | 0 | 5.85 | 5896.37
TS5500Exc | SC\22\002\D | SC | 22 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-05-03 10:33 | 2015-05-06 18:49 | 107150.7021 | [6 empty] | 107151 | 80789 | 4.95 | 0 | 0 | 6.51 | 5843
TS5500Shv | DT\21\005\A | DT | 21 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2015-05-03 17:49 | 2015-05-06 14:18 | 88494.1767 | [6 empty] | 88494 | 65015 | 3.78 | 0 | 0 | 10.43 | 5410
DRE2 | BW\18\001\B | BW | 18 | 1 | B | 6 DL | 100 | 0 | 100 | 2015-05-05 12:23 | 2015-05-11 02:16 | 456362.5939 |  |  |  |  | 456363 | 217316 |  |  | 0 | 18.24 | 0 | 10.85 | 5373.9
PH4100XPC#1 | MW\20\012\A | MW | 20 | 12 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-05-06 00:57 | 2015-05-18 12:26 | 647981.5785 | 647982 | [7 empty] | 0 | 0 | 24.02 | 10.61 | 5465.34
DRE1 | SC\22\004\D | SC | 22 | 4 | D | 6 DL | 100 | 0 | 100 | 2015-05-06 02:49 | 2015-05-14 23:34 | 725147.6493 |  |  |  | 60953 | 725148 | 478451 |  |  | 0 | 45 | 0 | 5.98 | 5889.09
TS5500Shv | DT\21\005\B | DT | 21 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-05-06 14:18 | 2015-05-08 09:56 | 49572.4567 | 49572 | [7 empty] | 0 | 0 | 2.91 | 8.66 | 5562.72
TS5500Exc | SC\22\003\D | SC | 22 | 3 | D | 8 Coal Mining | 82.5 | 0 | 82.5 | 2015-05-06 18:49 | 2015-05-08 19:52 | 65459.3255 | [6 empty] | 65459 | 49512 | 4.13 | 0 | 0 | 6.17 | 5872
TS5500Shv | DT\21\005\B | DT | 21 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-05-08 09:56 | 2015-05-10 14:06 | 67423.7544 | [6 empty] | 67424 | 49901 | 2.96 | 0 | 0 | 8.66 | 5563
TS5500Exc | SC\22\003\D | SC | 22 | 3 | D | 8 Coal Mining | 17.5 | 0 | 17.5 | 2015-05-08 19:52 | 2015-05-09 06:15 | 13871.0729 | [6 empty] | 13871 | 10492 | 0.87 | 0 | 0 | 6.17 | 5872
TS5500Exc | MW\17\008\D | MW | 17 | 8 | D | 8 Coal Mining | 8 | 0 | 8 | 2015-05-09 06:15 | 2015-05-09 09:46 | 4674.02 | [6 empty] | 4674 | 3528 | 0.35 | 0 | 0 | 5.96 | 5887
PH4100A | SC\25\009\D | SC | 25 | 9 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-05-09 08:29 | 2015-05-14 13:29 | 225970.4729 | 225970 | [7 empty] | 0 | 0 | 19.13 | 6.33 | 5857.5
TS5500Exc | MW\17\009\D | MW | 17 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-05-09 09:46 | 2015-05-11 05:48 | 58776.8584 | [6 empty] | 58777 | 44405 | 4.44 | 0 | 0 | 5.89 | 5894
TS5500Shv | MC\27\006\D | MC | 27 | 6 | D | 8 Coal Mining | 36.6 | 0 | 36.6 | 2015-05-10 14:06 | 2015-05-11 06:46 | 21538.0916 | [6 empty] | 21538 | 16111 | 1.61 | 0 | 0 | 6.92 | 5804
TS6060#1 | BW\19\007\B | BW | 19 | 7 | B | 1 Prestrip - Thick | 44.6619 | 44.6619 | 44.6619 | 2015-05-11 02:05 | 2015-05-19 23:40 | 231198.2623 | 231198 | [7 empty] | 0 | 0 | 21.21 | 12.4 | 5330.83
DRE2 | BW\18\002\B | BW | 18 | 2 | B | 6 DL | 100 | 0 | 100 | 2015-05-11 02:16 | 2015-05-13 09:51 | 189482.6324 |  |  |  |  | 189483 | 157902 |  |  | 0 | 17.93 | 0 | 11.22 | 5340.85
TS5500Exc | MW\17\010\D | MW | 17 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-05-11 05:48 | 2015-05-13 01:24 | 58204.4575 | [6 empty] | 58204 | 43936 | 4.39 | 0 | 0 | 5.75 | 5906
TS5500Shv | DT\21\007\A | DT | 21 | 7 | A | 1 Prestrip - Thick | 46.3155 | 46.3155 | 46.3155 | 2015-05-11 06:46 | 2015-05-15 06:47 | 108233.309 | 108233 | [7 empty] | 0 | 0 | 9.33 | 9.31 | 5466.21
TS5500Exc | MW\17\011\D | MW | 17 | 11 | D | 8 Coal Mining | 54.4 | 0 | 54.4 | 2015-05-13 01:24 | 2015-05-14 00:49 | 31253.6296 | [6 empty] | 31254 | 23609 | 2.36 | 0 | 0 | 5.65 | 5914
DRE2 | BW\18\003\B | BW | 18 | 3 | B | 6 DL | 100 | 0 | 100 | 2015-05-13 09:51 | 2015-05-15 22:40 | 207271.6373 |  |  |  |  | 207272 | 172726 |  |  | 0 | 17.25 | 0 | 10.94 | 5367.82
TS5500Exc | MW\21\004\A | MW | 21 | 4 | A | 1 Prestrip - Thick | 76.7978 | 76.7978 | 76.7978 | 2015-05-14 00:49 | 2015-05-18 18:04 | 106292.0771 | 106292 | [7 empty] | 0 | 0 | 5.1 | 12.11 | 5288.18
PH4100A | SC\26\009\D | SC | 26 | 9 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-05-14 13:29 | 2015-05-18 22:58 | 191177.79 | 191178 | [7 empty] | 0 | 0 | 16.12 | 6.39 | 5852.38
DRE1 | SC\22\005\D | SC | 22 | 5 | D | 6 DL | 100 | 0 | 100 | 2015-05-14 23:34 | 2015-05-23 20:39 | 726335.9813 |  |  |  | 61053 | 726336 | 479235 |  |  | 0 | 45 | 0 | 5.9 | 5896.43
TS5500Shv | DT\21\007\A | DT | 21 | 7 | A | 1 Prestrip - Thick | 53.6845 | 53.6845 | 53.6845 | 2015-05-15 06:47 | 2015-05-19 22:04 | 125453.8313 | 125454 | [7 empty] | 0 | 0 | 10.81 | 9.31 | 5466.21
DRE2 | BW\18\004\B | BW | 18 | 4 | B | 6 DL | 100 | 0 | 100 | 2015-05-15 22:40 | 2015-05-18 08:12 | 196144.9808 |  |  |  |  | 196145 | 163454 |  |  | 0 | 16.59 | 0 | 11.22 | 5364.65
DRE2 | BW\18\005\B | BW | 18 | 5 | B | 6 DL | 100 | 0 | 100 | 2015-05-18 08:12 | 2015-05-20 21:34 | 209168.3589 |  |  |  |  | 209168 | 174307 |  |  | 0 | 15.63 | 0 | 10.5 | 5438.76
PH4100XPC#1 | BW\20\001\B | BW | 20 | 1 | B | 1 Prestrip - Thick | 100 | 56.5662 | 56.5662 | 2015-05-18 12:26 | 2015-06-01 | 797529.7471 | 797530 | [7 empty] | 0 | 0 | 30.32 | 10.93 | 5365.88
TS5500Exc | SC\22\004\D | SC | 22 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-05-18 18:04 | 2015-05-21 05:54 | 79864.8861 | [6 empty] | 79865 | 60312 | 5.03 | 0 | 0 | 5.98 | 5889
PH4100A | SC\25\007\B | SC | 25 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-05-18 22:58 | 2015-05-23 03:58 | 176533.4483 | 176533 | [7 empty] | 0 | 0 | 14.74 | 11.11 | 5394.84
TS5500Shv | MW\17\013\D | MW | 17 | 13 | D | 7 PostStrip | 100 | 0 | 100 | 2015-05-19 22:04 | 2015-05-21 01:52 | 31574.0483 |  |  | 31574 | [5 empty] | 0 | 0 | 0 | 5.85 | 5896.37
TS6060#1 | DT\16\003\D | DT | 16 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-05-19 23:40 | 2015-05-21 08:23 | 46920.4241 | [6 empty] | 46920 | 35374 | 4.83 | 0 | 0 | 6.05 | 5883
DRE2 | BW\18\006\B | BW | 18 | 6 | B | 6 DL | 100 | 0 | 100 | 2015-05-20 21:34 | 2015-05-23 10:20 | 207087.1284 |  |  |  |  | 207087 | 159298 |  |  | 0 | 15.22 | 0 | 10.73 | 5446.04
TS5500Shv | BW\19\007\B | BW | 19 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-05-21 01:52 | 2015-05-22 11:10 | 43041.4678 | [6 empty] | 43041 | 31022 | 3.04 | 0 | 0 | 12.4 | 5331
TS5500Exc | MW\21\004\A | MW | 21 | 4 | A | 1 Prestrip - Thick | 23.2022 | 23.2022 | 23.2022 | 2015-05-21 05:54 | 2015-05-22 16:07 | 32112.9729 | 32113 | [7 empty] | 0 | 0 | 1.54 | 12.11 | 5288.18
TS6060#1 | DT\16\004\D | DT | 16 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-05-21 08:23 | 2015-05-22 15:28 | 44577.7539 | [6 empty] | 44578 | 33735 | 4.63 | 0 | 0 | 5.4 | 5938
TS5500Shv | MC\27\006\D | MC | 27 | 6 | D | 8 Coal Mining | 28.9 | 0 | 28.9 | 2015-05-22 11:10 | 2015-05-23 00:19 | 16976.25 | [6 empty] | 16976 | 12699 | 1.27 | 0 | 0 | 6.92 | 5804
TS6060#1 | DT\16\005\D | DT | 16 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-05-22 15:28 | 2015-05-23 17:10 | 36872.0987 | [6 empty] | 36872 | 27971 | 4.59 | 0 | 0 | 5.35 | 5942
TS5500Exc | MW\21\005\D | MW | 21 | 5 | D | 1 Prestrip - Thick | 48.0916 | 48.0916 | 48.0916 | 2015-05-22 16:07 | 2015-05-28 21:08 | 140075.6264 | 140076 | [7 empty] | 0 | 0 | 8.67 | 6.59 | 5832.8
TS5500Shv | MC\27\007\D | MC | 27 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-05-23 00:19 | 2015-05-25 01:50 | 63999.52 | [6 empty] | 64000 | 47708 | 4.77 | 0 | 0 | 7.23 | 5779
PH4100A | SC\26\007\B | SC | 26 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-05-23 03:58 | 2015-05-27 00:56 | 164475.6295 | 164476 | [7 empty] | 0 | 0 | 13.24 | 9.48 | 5524.24
DRE2 | BW\18\007\B | BW | 18 | 7 | B | 6 DL | 100 | 0 | 100 | 2015-05-23 10:20 | 2015-05-26 08:21 | 238667.6451 |  |  |  |  | 238668 | 198890 |  |  | 0 | 17.92 | 0 | 12.88 | 5290.01
TS6060#1 | BW\17\001\B | BW | 17 | 1 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-05-23 17:10 | 2015-05-25 09:38 | 58036.0823 | [6 empty] | 58036 | 42468 | 3.86 | 0 | 0 | 10.86 | 5374
DRE1 | SC\22\006\D | SC | 22 | 6 | D | 6 DL | 100 | 0 | 91.1849 | 2015-05-23 20:39 | 2015-06-01 | 665840.9609 |  |  |  | 55968 | 665841 | 439321 |  |  | 0 | 45 | 0 | 5.8 | 5904.43
TS5500Shv | MC\27\008\D | MC | 27 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-05-25 01:50 | 2015-05-27 03:34 | 64250.5304 | [6 empty] | 64251 | 48002 | 4.8 | 0 | 0 | 7.04 | 5795
TS6060#1 | BW\17\002\B | BW | 17 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-05-25 09:38 | 2015-05-26 19:35 | 48675.2347 | [6 empty] | 48675 | 35569 | 3.58 | 0 | 0 | 11.02 | 5354
DRE2 | BW\18\008\B | BW | 18 | 8 | B | 6 DL | 100 | 0 | 100 | 2015-05-26 08:21 | 2015-05-28 22:12 | 210867.0557 |  |  |  |  | 210867 | 175723 |  |  | 0 | 17.02 | 0 | 13.99 | 5190.83
TS6060#1 | BW\17\004\B | BW | 17 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-05-26 19:35 | 2015-05-28 02:14 | 43979.8491 | [6 empty] | 43980 | 32057 | 3.89 | 0 | 0 | 11.08 | 5371
PH4100A | SC\25\006\B | SC | 25 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-05-27 00:56 | 2015-05-30 23:13 | 167662.2426 | 167662 | [7 empty] | 0 | 0 | 13.94 | 9.37 | 5540.15
TS5500Shv | MC\27\012\D | MC | 27 | 12 | D | 8 Coal Mining | 100 | 0 | 97.8 | 2015-05-27 03:34 | 2015-05-29 07:32 | 67152.2618 | [6 empty] | 67152 | 50637 | 4.4 | 0 | 0 | 6.42 | 5848
TS6060#1 | BW\19\008\B | BW | 19 | 8 | B | 1 Prestrip - Thick | 67.619 | 21.0114 | 21.0114 | 2015-05-28 02:14 | 2015-06-01 | 102194.3794 | 102194 | [7 empty] | 0 | 0 | 10.08 | 14.63 | 5140
TS5500Exc | SC\22\005\D | SC | 22 | 5 | D | 8 Coal Mining | 100 | 0 | 17.4 | 2015-05-28 21:08 | 2015-05-29 07:32 | 13883.2231 | [6 empty] | 13883 | 10484 | 0.87 | 0 | 0 | 5.9 | 5896
DRE2 | BW\18\009\B | BW | 18 | 9 | B | 6 DL | 100 | 0 | 100 | 2015-05-28 22:12 | 2015-05-31 18:58 | 234389.0158 |  |  |  |  | 234389 | 195324 |  |  | 0 | 18.62 | 0 | 12.89 | 5264.3
TS5500Shv | DT\22\002\A2 | DT | 22 | 2 | A2 | 1 Prestrip - Thick | 6.3919 | 6.3919 | 6.3919 | 2015-05-29 07:32 | 2015-05-31 20:25 | 69266.8202 | 69267 | [7 empty] | 0 | 0 | 2.39 | 17.63 | 4900.85
TS5500Exc | MW\21\005\D | MW | 21 | 5 | D | 1 Prestrip - Thick | 51.9084 | 20.8061 | 20.8061 | 2015-05-29 07:32 | 2015-06-01 | 60601.7276 | 60602 | [7 empty] | 0 | 0 | 3.75 | 6.59 | 5832.8
PH4100A | SC\26\006\B | SC | 26 | 6 | B | 1 Prestrip - Thick | 100 | 23.5366 | 23.5366 | 2015-05-30 23:13 | 2015-06-01 | 44468.7982 | 44469 | [7 empty] | 0 | 0 | 3.56 | 9.2 | 5553.71
DRE2 | BW\17\011\D | BW | 17 | 11 | D | 6 DL | 100 | 6.985 | 6.985 | 2015-05-31 18:58 | 2015-06-01 | 17111.9859 |  |  |  | 653 | 17112 | 15675 |  |  | 0 | 20.25 | 0 | 6.91 | 5808.02
TS5500Shv | DT\22\002\A2 | DT | 22 | 2 | A2 | 1 Prestrip - Thick | 75.5781 | 0.37489 | 0.37489 | 2015-05-31 20:25 | 2015-06-01 | 4062.6181 | 4063 | [7 empty] | 0 | 0 | 0.14 | 17.63 | 4900.85
| EOP 17 : 2015\May | EOP 17 : 2015 | May | [6 empty] | 2015-06-01 | 2015-06-01 |  | 4338328 |  | 86455 | 229560 | 5071997 | 3571389 | 1230124 | 917695 | 83.79 | 0 | 300.97 | 8.28 | 5658.43
DRE1 | SC\22\006\D | SC | 22 | 6 | D | 6 DL | 100 | 0 | 8.8151 | 2015-06-01 | 2015-06-01 18:53 | 64368.4302 |  |  |  | 5411 | 64368 | 42470 |  |  | 0 | 45 | 0 | 5.8 | 5904.43
TS5500Shv | DT\22\002\A2 | DT | 22 | 2 | A2 | 1 Prestrip - Thick | 75.5781 | 75.2032 | 75.2032 | 2015-06-01 | 2015-06-30 20:25 | 814954.7953 | 814955 | [7 empty] | 0 | 0 | 28.09 | 17.63 | 4900.85
PH4100A | SC\26\006\B | SC | 26 | 6 | B | 1 Prestrip - Thick | 100 | 76.4634 | 76.4634 | 2015-06-01 | 2015-06-04 08:30 | 144466.2116 | 144466 | [7 empty] | 0 | 0 | 11.56 | 9.2 | 5553.71
DRE2 | BW\17\011\D | BW | 17 | 11 | D | 6 DL | 100 | 93.015 | 93.015 | 2015-06-01 | 2015-06-03 18:51 | 227870.5153 |  |  |  | 8697 | 227871 | 208736 |  |  | 0 | 20.25 | 0 | 6.91 | 5808.02
PH4100XPC#1 | BW\20\001\B | BW | 20 | 1 | B | 1 Prestrip - Thick | 100 | 43.4338 | 43.4338 | 2015-06-01 | 2015-06-11 08:26 | 612375.087 | 612375 | [7 empty] | 0 | 0 | 23.28 | 10.93 | 5365.88
TS6060#1 | BW\19\008\B | BW | 19 | 8 | B | 1 Prestrip - Thick | 67.619 | 46.6076 | 46.6076 | 2015-06-01 | 2015-06-09 15:57 | 226688.6075 | 226689 | [7 empty] | 0 | 0 | 22.36 | 14.63 | 5140
TS5500Exc | MW\21\005\D | MW | 21 | 5 | D | 1 Prestrip - Thick | 51.9084 | 31.1023 | 31.1023 | 2015-06-01 | 2015-06-05 00:21 | 90591.2633 | 90591 | [7 empty] | 0 | 0 | 5.61 | 6.59 | 5832.8
TS Fleet 5 | No Production | No Production | [7 empty] | 2015-06-01 | 2015-07-01
DRE1 | SC\22\007\D | SC | 22 | 7 | D | 6 DL | 100 | 0 | 100 | 2015-06-01 18:53 | 2015-06-11 15:52 | 807780.877 |  |  |  | 61174 | 807781 | 480189 |  |  | 0 | 45 | 0 | 5.67 | 5915.43
DRE2 | BW\17\010\D | BW | 17 | 10 | D | 6 DL | 100 | 100 | 100 | 2015-06-03 18:51 | 2015-06-06 20:45 | 251934.9988 |  |  |  | 11272 | 251935 | 214173 |  |  | 0 | 22.57 | 0 | 6.25 | 5864.69
PH4100A | SC\25\005\B | SC | 25 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-06-04 08:30 | 2015-06-09 23:51 | 247667.2977 | 247667 | [7 empty] | 0 | 0 | 20.24 | 9.06 | 5568.67
TS5500Exc | SC\22\005\D | SC | 22 | 5 | D | 8 Coal Mining | 100 | 0 | 82.6 | 2015-06-05 00:21 | 2015-06-07 01:38 | 65784.4718 | [6 empty] | 65784 | 49679 | 4.14 | 0 | 0 | 5.9 | 5896
DRE2 | BW\17\009\D | BW | 17 | 9 | D | 6 DL | 100 | 100 | 100 | 2015-06-06 20:45 | 2015-06-12 13:08 | 464832.9323 |  |  |  | 10823 | 464833 | 205630 |  |  | 0 | 21.66 | 0 | 5.78 | 5905.78
TS5500Exc | SC\22\006\D | SC | 22 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-06-07 01:38 | 2015-06-09 12:18 | 78305.5828 | [6 empty] | 78306 | 59371 | 4.95 | 0 | 0 | 5.8 | 5904
TS5500Exc | SC\25\006\B | SC | 25 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-06-09 12:18 | 2015-06-11 02:03 | 50385.8592 | [6 empty] | 50386 | 37166 | 3.09 | 0 | 0 | 9.37 | 5540
TS6060#1 | BW\19\008\B | BW | 19 | 8 | B | 1 Prestrip - Thick | 32.381 | 32.381 | 32.381 | 2015-06-09 15:57 | 2015-06-15 16:26 | 157493.8737 | 157494 | [7 empty] | 0 | 0 | 15.53 | 14.63 | 5140
PH4100A | SC\26\005\B | SC | 26 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-06-09 23:51 | 2015-06-16 21:08 | 302791.9754 | 302792 | [7 empty] | 0 | 0 | 24.23 | 9.06 | 5568.16
TS5500Exc | SC\25\007\B | SC | 25 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-06-11 02:03 | 2015-06-11 19:18 | 23024.9362 | [6 empty] | 23025 | 16828 | 1.37 | 0 | 0 | 11.11 | 5395
PH4100XPC#1 | BW\20\002\B | BW | 20 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-06-11 08:26 | 2015-06-27 17:13 | 958993.2955 | 958993 | [7 empty] | 0 | 0 | 48.98 | 11.67 | 5312.95
DRE1 | SC\23\012\D | SC | 23 | 12 | D | 6 DL | 100 | 0 | 100 | 2015-06-11 15:52 | 2015-06-23 08:49 | 957657.0277 |  |  |  | 52803 | 957657 | 415719 |  |  | 0 | 42.16 | 0 | 7.36 | 5766.67
TS5500Exc | SC\22\007\D | SC | 22 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-06-11 19:18 | 2015-06-14 05:02 | 77056.6814 | [6 empty] | 77057 | 58754 | 4.9 | 0 | 0 | 5.67 | 5915
DRE2 | BW\17\008\D | BW | 17 | 8 | D | 6 DL | 100 | 100 | 100 | 2015-06-12 13:08 | 2015-06-18 17:00 | 504025.5438 |  |  |  | 11735 | 504026 | 222968 |  |  | 0 | 23.51 | 0 | 5.95 | 5891.08
TS5500Exc | SC\26\007\B | SC | 26 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-06-14 05:02 | 2015-06-15 19:22 | 51163.0121 | [6 empty] | 51163 | 37717 | 3.15 | 0 | 0 | 9.48 | 5524
TS6060#1 | DT\21\007\A | DT | 21 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2015-06-15 16:26 | 2015-06-17 09:36 | 59051.9792 | [6 empty] | 59052 | 43667 | 3.77 | 0 | 0 | 9.31 | 5466
TS5500Exc | SC\25\007\D | SC | 25 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-06-15 19:22 | 2015-06-20 22:30 | 115398.2718 | 115398 | [7 empty] | 0 | 0 | 9.59 | 5.53 | 5928.02
PH4100A | SC\25\004\B | SC | 25 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-06-16 21:08 | 2015-06-25 16:22 | 386013.8145 | 386014 | [7 empty] | 0 | 0 | 31.08 | 9 | 5574.37
TS6060#1 | BW\19\008\B | BW | 19 | 8 | B | 8 Coal Mining | 8 | 0 | 8 | 2015-06-17 09:36 | 2015-06-17 12:28 | 4095.6946 | [6 empty] | 4096 | 2927 | 0.29 | 0 | 0 | 14.63 | 5140
TS6060#1 | BW\19\009\B | BW | 19 | 9 | B | 1 Prestrip - Thick | 100 | 86.9257 | 86.9257 | 2015-06-17 12:28 | 2015-07-01 | 349346.5981 | 349347 | [7 empty] | 0 | 0 | 35.74 | 13.29 | 5232.04
DRE2 | BW\17\007\D | BW | 17 | 7 | D | 6 DL | 100 | 100 | 100 | 2015-06-18 17:00 | 2015-06-24 23:42 | 513673.9348 |  |  |  | 11960 | 513674 | 227236 |  |  | 0 | 24.02 | 0 | 5.7 | 5913.04
TS5500Exc | SC\25\005\B | SC | 25 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-06-20 22:30 | 2015-06-22 19:48 | 60467.1489 | [6 empty] | 60467 | 44687 | 3.72 | 0 | 0 | 9.06 | 5569
TS5500Exc | SC\26\006\B | SC | 26 | 6 | B | 8 Coal Mining | 53.2 | 0 | 53.2 | 2015-06-22 19:48 | 2015-06-23 19:01 | 30993.1161 | [6 empty] | 30993 | 22883 | 1.91 | 0 | 0 | 9.2 | 5554
DRE1 | SC\23\011\D | SC | 23 | 11 | D | 6 DL | 100 | 0 | 88.8747 | 2015-06-23 08:49 | 2015-07-01 | 624385.6651 |  |  |  | 47482 | 624386 | 427336 |  |  | 0 | 44.69 | 0 | 7.31 | 5771.97
TS5500Exc | SC\23\012\D | SC | 23 | 12 | D | 7 PostStrip | 100 | 0 | 100 | 2015-06-23 19:01 | 2015-06-26 10:31 | 59508.3986 |  |  | 59508 | [5 empty] | 0 | 0 | 0 | 7.36 | 5766.67
DRE2 | BW\17\006\D | BW | 17 | 6 | D | 6 DL | 100 | 87.7462 | 87.7462 | 2015-06-24 23:42 | 2015-07-01 | 491854.075 |  |  |  | 11023 | 491854 | 209432 |  |  | 0 | 25.03 | 0 | 5.44 | 5936.51
PH4100A | SC\26\004\B | SC | 26 | 4 | B | 1 Prestrip - Thick | 100 | 53.69 | 53.69 | 2015-06-25 16:22 | 2015-07-01 | 233745.5819 | 233746 | [7 empty] | 0 | 0 | 19.01 | 8.99 | 5574.46
TS5500Exc | SC\23\012\D | SC | 23 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-06-26 10:31 | 2015-06-28 11:25 | 65285.7523 | [6 empty] | 65286 | 48562 | 4.66 | 0 | 0 | 7.36 | 5767
PH4100XPC#1 | BW\20\003\X2 | BW | 20 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 51.2737 | 2015-06-27 17:13 | 2015-07-01 | 190145.6901 | 190146 | [7 empty] | 0 | 0 | 10.73 | 0 | 0
TS5500Exc | SC\25\006\D | SC | 25 | 6 | D | 1 Prestrip - Thick | 100 | 48.1164 | 48.1164 | 2015-06-28 11:25 | 2015-07-01 | 56768.4427 | 56768 | [7 empty] | 0 | 0 | 4.73 | 5.79 | 5905.29
TS5500Shv | BW\19\008\B | BW | 19 | 8 | B | 8 Coal Mining | 92 | 0 | 9.1 | 2015-06-30 20:25 | 2015-07-01 | 4615.036 | [6 empty] | 4615 | 3298 | 0.33 | 0 | 0 | 14.63 | 5140
| EOP 18 : 2015\Jun | EOP 18 : 2015 | Jun | [6 empty] | 2015-07-01 | 2015-07-01 |  | 4887441 |  | 59508 | 232379 | 4908384 | 2653891 | 570229 | 425538 | 36.28 | 0 | 310.78 | 8.04 | 5686.34
DRE1 | SC\23\011\D | SC | 23 | 11 | D | 6 DL | 100 | 0 | 11.1253 | 2015-07-01 | 2015-07-01 22:37 | 78160.451 |  |  |  | 5944 | 78160 | 53494 |  |  | 0 | 44.69 | 0 | 7.31 | 5771.97
TS5500Shv | BW\19\008\B | BW | 19 | 8 | B | 8 Coal Mining | 92 | 0 | 82.9 | 2015-07-01 | 2015-07-02 08:16 | 42282.9512 | [6 empty] | 42283 | 30214 | 3.02 | 0 | 0 | 14.63 | 5140
PH4100A | SC\26\004\B | SC | 26 | 4 | B | 1 Prestrip - Thick | 100 | 46.31 | 46.31 | 2015-07-01 | 2015-07-05 12:37 | 201616.0255 | 201616 | [7 empty] | 0 | 0 | 16.4 | 8.99 | 5574.46
DRE2 | BW\17\006\D | BW | 17 | 6 | D | 6 DL | 100 | 12.2538 | 12.2538 | 2015-07-01 | 2015-07-01 19:53 | 68687.3846 |  |  |  | 1539 | 68687 | 29247 |  |  | 0 | 25.03 | 0 | 5.44 | 5936.51
PH4100XPC#1 | BW\20\003\X2 | BW | 20 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 48.7263 | 2015-07-01 | 2015-07-04 01:51 | 180699.0411 | 180699 | [7 empty] | 0 | 0 | 10.2 | 0 | 0
TS6060#1 | BW\19\009\B | BW | 19 | 9 | B | 1 Prestrip - Thick | 100 | 13.0743 | 13.0743 | 2015-07-01 | 2015-07-02 23:59 | 52544.2294 | 52544 | [7 empty] | 0 | 0 | 5.38 | 13.29 | 5232.04
TS5500Exc | SC\25\006\D | SC | 25 | 6 | D | 1 Prestrip - Thick | 100 | 51.8836 | 51.8836 | 2015-07-01 | 2015-07-03 16:24 | 61213.0271 | 61213 | [7 empty] | 0 | 0 | 5.1 | 5.79 | 5905.29
TS Fleet 5 | No Production | No Production | [7 empty] | 2015-07-01 | 2015-08-01
DRE2 | BW\17\005\D | BW | 17 | 5 | D | 6 DL | 100 | 100 | 100 | 2015-07-01 19:53 | 2015-07-08 00:36 | 513598.2335 |  |  |  | 11958 | 513598 | 227203 |  |  | 0 | 23.86 | 0 | 5.44 | 5935.38
DRE1 | SC\23\010\D | SC | 23 | 10 | D | 6 DL | 100 | 0 | 100 | 2015-07-01 22:37 | 2015-07-10 15:38 | 721823.7216 |  |  |  | 60673 | 721824 | 476258 |  |  | 0 | 45 | 0 | 6.85 | 5812.15
TS5500Shv | MC\27\012\D | MC | 27 | 12 | D | 8 Coal Mining | 100 | 0 | 2.2 | 2015-07-02 08:16 | 2015-07-02 09:23 | 1481.9239 | [6 empty] | 1482 | 1117 | 0.1 | 0 | 0 | 6.42 | 5848
TS5500Shv | MW\17\003\D | MW | 17 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-07-02 09:23 | 2015-07-04 06:16 | 58801.598 | [6 empty] | 58802 | 44604 | 4.46 | 0 | 0 | 5.47 | 5931
TS6060#1 | BW\17\008\D | BW | 17 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-07-02 23:59 | 2015-07-04 21:02 | 65530.2258 | [6 empty] | 65530 | 49511 | 4.95 | 0 | 0 | 5.95 | 5891
TS5500Exc | SC\25\005\D | SC | 25 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-07-03 16:24 | 2015-07-08 21:45 | 119129.5933 | 119130 | [7 empty] | 0 | 0 | 9.93 | 6.07 | 5881.28
PH4100XPC#1 | BW\20\004\X1 | BW | 20 | 4 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-07-04 01:51 | 2015-07-09 20:56 | 339349.1649 | 339349 | [7 empty] | 0 | 0 | 18.72 | 14.6 | 5072
TS5500Shv | MW\17\004\D | MW | 17 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-07-04 06:16 | 2015-07-06 03:33 | 59353.3502 | [6 empty] | 59353 | 44914 | 4.49 | 0 | 0 | 5.93 | 5891
TS6060#1 | BW\17\007\D | BW | 17 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-07-04 21:02 | 2015-07-06 18:06 | 65549.723 | [6 empty] | 65550 | 49684 | 4.97 | 0 | 0 | 5.7 | 5913
PH4100A | SC\25\003\B | SC | 25 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-07-05 12:37 | 2015-07-15 00:38 | 421846.7871 | 421847 | [7 empty] | 0 | 0 | 34.69 | 8.94 | 5577.46
TS5500Shv | MW\17\005\D | MW | 17 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-07-06 03:33 | 2015-07-08 01:17 | 59926.2246 | [6 empty] | 59926 | 45202 | 4.52 | 0 | 0 | 6.16 | 5871
TS6060#1 | BW\17\006\D | BW | 17 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-07-06 18:06 | 2015-07-08 15:12 | 65581.5116 | [6 empty] | 65582 | 49787 | 4.98 | 0 | 0 | 5.44 | 5937
DRE2 | BW\17\004\D | BW | 17 | 4 | D | 6 DL | 100 | 100 | 100 | 2015-07-08 00:36 | 2015-07-13 20:29 | 483067.7876 |  |  |  | 11247 | 483068 | 213697 |  |  | 0 | 22.36 | 0 | 5.89 | 5896.64
TS5500Shv | MW\17\006\D | MW | 17 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-07-08 01:17 | 2015-07-09 23:07 | 60044.0144 | [6 empty] | 60044 | 45146 | 4.52 | 0 | 0 | 6.19 | 5868
TS6060#1 | BW\17\005\D | BW | 17 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-07-08 15:12 | 2015-07-10 11:21 | 64221.0819 | [6 empty] | 64221 | 48639 | 4.86 | 0 | 0 | 5.44 | 5935
TS5500Exc | SC\26\007\D | SC | 26 | 7 | D | 1 Prestrip - Thick | 9.4609 | 9.4609 | 9.4609 | 2015-07-08 21:45 | 2015-07-09 09:44 | 11384.6437 | 11385 | [7 empty] | 0 | 0 | 0.95 | 5.6 | 5921.26
TS5500Exc | SC\26\007\D | SC | 26 | 7 | D | 1 Prestrip - Thick | 90.5391 | 90.5391 | 90.5391 | 2015-07-09 09:44 | 2015-07-14 04:22 | 108949.0763 | 108949 | [7 empty] | 0 | 0 | 9.07 | 5.6 | 5921.26
PH4100XPC#1 | BW\20\005\X2 | BW | 20 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2015-07-09 20:56 | 2015-07-17 15:52 | 454008.0017 | 454008 | [7 empty] | 0 | 0 | 26.17 | 0 | 0
TS5500Shv | MW\17\007\D | MW | 17 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-07-09 23:07 | 2015-07-11 19:29 | 58148.6101 | [6 empty] | 58149 | 43718 | 4.37 | 0 | 0 | 6.13 | 5872
TS6060#1 | BW\18\001\B | BW | 18 | 1 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-07-10 11:21 | 2015-07-12 02:53 | 57491.7128 | [6 empty] | 57492 | 42052 | 3.83 | 0 | 0 | 10.85 | 5374
DRE1 | SC\23\009\D | SC | 23 | 9 | D | 6 DL | 100 | 0 | 100 | 2015-07-10 15:38 | 2015-07-19 08:41 | 721901.1678 |  |  |  | 60680 | 721901 | 476309 |  |  | 0 | 45 | 0 | 6.31 | 5859.58
TS5500Shv | BW\19\009\B | BW | 19 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-07-11 19:29 | 2015-07-13 11:50 | 52878.6197 | [6 empty] | 52879 | 38201 | 3.83 | 0 | 0 | 13.29 | 5232
TS6060#1 | BW\18\002\B | BW | 18 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-07-12 02:53 | 2015-07-13 11:41 | 47717.9564 | [6 empty] | 47718 | 34806 | 3.49 | 0 | 0 | 11.22 | 5341
TS6060#1 | BW\18\003\B | BW | 18 | 3 | B | 8 Coal Mining | 53.1 | 0 | 53.1 | 2015-07-13 11:41 | 2015-07-14 06:03 | 26705.4461 | [6 empty] | 26705 | 19476 | 1.95 | 0 | 0 | 10.94 | 5368
TS5500Shv | MW\17\008\D | MW | 17 | 8 | D | 8 Coal Mining | 92 | 0 | 92 | 2015-07-13 11:50 | 2015-07-15 04:52 | 53765.3171 | [6 empty] | 53765 | 40586 | 4.06 | 0 | 0 | 5.96 | 5887
DRE2 | BW\17\003\D | BW | 17 | 3 | D | 6 DL | 100 | 100 | 100 | 2015-07-13 20:29 | 2015-07-16 21:06 | 250810.2369 |  |  |  | 11222 | 250810 | 213217 |  |  | 0 | 22.4 | 0 | 6.16 | 5872.28
TS5500Exc | SC\23\010\D | SC | 23 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-07-14 04:22 | 2015-07-16 13:52 | 77837.5056 | [6 empty] | 77838 | 58360 | 4.86 | 0 | 0 | 6.85 | 5812
TS6060#1 | BW\17\004\D | BW | 17 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-07-14 06:03 | 2015-07-16 02:56 | 65280.4224 | [6 empty] | 65280 | 49244 | 4.92 | 0 | 0 | 5.89 | 5897
PH4100A | SC\26\003\B | SC | 26 | 3 | B | 1 Prestrip - Thick | 100 | 94.8404 | 94.8404 | 2015-07-15 00:38 | 2015-08-01 | 751743.849 | 751744 | [7 empty] | 0 | 0 | 36.69 | 8.92 | 5578.46
TS5500Shv | DT\21\007\B | DT | 21 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-07-15 04:52 | 2015-07-16 10:52 | 34563.6245 | 34564 | [7 empty] | 0 | 0 | 3.01 | 7.91 | 5631.09
TS6060#1 | BW\19\010\B | BW | 19 | 10 | B | 1 Prestrip - Thick | 51.2049 | 51.2049 | 51.2049 | 2015-07-16 02:56 | 2015-07-19 20:59 | 99338.6948 | 99339 | [7 empty] | 0 | 0 | 8.4 | 10.09 | 5478.19
TS5500Shv | DT\22\002\A2 | DT | 22 | 2 | A2 | 1 Prestrip - Thick | 18.0301 | 3.0301 | 3.0301 | 2015-07-16 10:52 | 2015-07-17 15:20 | 32836.0247 | 32836 | [7 empty] | 0 | 0 | 1.13 | 17.63 | 4900.85
TS5500Exc | SC\23\011\D | SC | 23 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-07-16 13:52 | 2015-07-19 00:12 | 78961.962 | [6 empty] | 78962 | 58830 | 4.9 | 0 | 0 | 7.31 | 5772
DRE2 | BW\17\002\D | BW | 17 | 2 | D | 6 DL | 100 | 100 | 100 | 2015-07-16 21:06 | 2015-07-22 17:49 | 485915.5561 |  |  |  | 11314 | 485916 | 214957 |  |  | 0 | 22.68 | 0 | 5.68 | 5914.88
TS5500Shv | DT\21\007\B | DT | 21 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-07-17 15:20 | 2015-07-19 01:31 | 44789.7813 | [6 empty] | 44790 | 33316 | 2.93 | 0 | 0 | 7.91 | 5631
PH4100XPC#1 | BW\20\006\B | BW | 20 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-07-17 15:52 | 2015-07-30 16:35 | 769917.5472 | 769918 | [7 empty] | 0 | 0 | 48.44 | 10.54 | 5469.66
TS5500Exc | SC\25\004\B | SC | 25 | 4 | B | 8 Coal Mining | 100 | 0 | 30 | 2015-07-19 00:12 | 2015-07-19 13:31 | 18037.5245 | [6 empty] | 18038 | 13340 | 1.12 | 0 | 0 | 9 | 5574
TS5500Shv | MW\17\011\D | MW | 17 | 11 | D | 8 Coal Mining | 45.6 | 0 | 27.4 | 2015-07-19 01:31 | 2015-07-19 13:31 | 15736.5371 | [6 empty] | 15737 | 11888 | 1.19 | 0 | 0 | 5.65 | 5914
DRE1 | SC\23\008\D | SC | 23 | 8 | D | 6 DL | 100 | 0 | 100 | 2015-07-19 08:41 | 2015-07-28 02:21 | 724069.1927 |  |  |  | 60862 | 724069 | 477740 |  |  | 0 | 45 | 0 | 5.78 | 5905.87
TS5500Shv | DT\22\004\B | DT | 22 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-07-19 13:31 | 2015-07-21 06:28 | 47156.0641 | 47156 | [7 empty] | 0 | 0 | 2.95 | 9.69 | 5444.4
TS5500Exc | MW\21\006\B | MW | 21 | 6 | B | 1 Prestrip - Thick | 35.9144 | 0 | 35.9144 | 2015-07-19 13:31 | 2015-07-28 06:14 | 199709.8943 | 199710 | [7 empty] | 0 | 0 | 9.75 | 0 | 0
TS6060#1 | BW\19\010\B | BW | 19 | 10 | B | 1 Prestrip - Thick | 48.7951 | 48.7951 | 48.7951 | 2015-07-19 20:59 | 2015-07-23 10:48 | 94663.541 | 94664 | [7 empty] | 0 | 0 | 8.01 | 10.09 | 5478.19
TS5500Shv | DT\22\005\A | DT | 22 | 5 | A | 1 Prestrip - Thick | 33.3873 | 33.3873 | 33.3873 | 2015-07-21 06:28 | 2015-07-27 03:41 | 162299.3811 | 162299 | [7 empty] | 0 | 0 | 14.52 | 11.27 | 5350.17
DRE2 | BW\17\001\D | BW | 17 | 1 | D | 6 DL | 100 | 100 | 100 | 2015-07-22 17:49 | 2015-07-28 06:59 | 459923.9486 |  |  |  | 7193 | 459924 | 131669 |  |  | 0 | 21.95 | 0 | 5.56 | 5926.42
TS6060#1 | BW\19\011\A2 | BW | 19 | 11 | A2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2015-07-23 10:48 | 2015-07-27 14:46 | 110002.7011 | 110003 | [7 empty] | 0 | 0 | 9.34 | 0 | 0
TS5500Shv | DT\22\005\A | DT | 22 | 5 | A | 1 Prestrip - Thick | 66.6127 | 27.4996 | 27.4996 | 2015-07-27 03:41 | 2015-08-01 | 133678.6948 | 133679 | [7 empty] | 0 | 0 | 11.96 | 11.27 | 5350.17
TS6060#1 | BW\19\011\B | BW | 19 | 11 | B | 1 Prestrip - Thick | 32.5654 | 32.5654 | 32.5654 | 2015-07-27 14:46 | 2015-07-28 02:29 | 12998.6848 | 12999 | [7 empty] | 0 | 0 | 1.23 | 9.99 | 5478.27
DRE1 | SC\23\002\D | SC | 23 | 2 | D | 6 DL | 100 | 0 | 28.7715 | 2015-07-28 02:21 | 2015-08-01 | 323412.267 |  |  |  | 19626 | 323412 | 134760 |  |  | 0 | 45 | 0 | 6.47 | 5845.94
TS6060#1 | BW\19\011\B | BW | 19 | 11 | B | 1 Prestrip - Thick | 67.4346 | 67.4346 | 67.4346 | 2015-07-28 02:29 | 2015-07-29 02:46 | 26916.999 | 26917 | [7 empty] | 0 | 0 | 2.55 | 9.99 | 5478.27
TS5500Exc | MW\21\006\B | MW | 21 | 6 | B | 1 Prestrip - Thick | 50.126 | 0 | 15.4468 | 2015-07-28 06:14 | 2015-08-01 | 85895.2663 | 85895 | [7 empty] | 0 | 0 | 4.19 | 0 | 0
DRE2 | DT\17\005\D | DT | 17 | 5 | D | 6 DL | 100 | 100 | 100 | 2015-07-28 06:59 | 2015-07-30 11:53 | 182658.1092 |  |  |  | 8173 | 182658 | 155280 |  |  | 0 | 22.88 | 0 | 5.38 | 5940.23
TS6060#1 | BW\17\001\D | BW | 17 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2015-07-29 02:46 | 2015-07-30 15:42 | 40961.8819 |  |  | 40962 | [5 empty] | 0 | 0 | 0 | 5.56 | 5926.42
DRE2 | DT\17\004\D | DT | 17 | 4 | D | 6 DL | 100 | 57.2727 | 57.2727 | 2015-07-30 11:53 | 2015-08-01 | 124705.5435 |  |  |  | 5580 | 124706 | 106014 |  |  | 0 | 21.92 | 0 | 5.41 | 5938.27
TS6060#1 | BW\20\003\B | BW | 20 | 3 | B | 1 Prestrip - Thick | 100 | 9.5745 | 9.5745 | 2015-07-30 15:42 | 2015-08-01 | 35799.9387 | 35800 | [7 empty] | 0 | 0 | 2.21 | 11.65 | 5323.17
PH4100XPC#1 | BW\20\007\B | BW | 20 | 7 | B | 1 Prestrip - Thick | 100 | 9.0681 | 9.0681 | 2015-07-30 16:35 | 2015-08-01 | 77985.4872 | 77985 | [7 empty] | 0 | 0 | 4.82 | 11.91 | 5372.45
| EOP 19 : 2015\Jul | EOP 19 : 2015 | Jul | [6 empty] | 2015-08-01 | 2015-08-01 |  | 4626246 |  | 40962 | 276010 | 5138734 | 2909844 | 1140124 | 852634 | 82.32 | 0 | 305.79 | 7.41 | 5744.02
DRE1 | SC\23\002\D | SC | 23 | 2 | D | 6 DL | 100 | 0 | 71.2285 | 2015-08-01 | 2015-08-10 15:50 | 800659.1106 |  |  |  | 48588 | 800659 | 333619 |  |  | 0 | 45 | 0 | 6.47 | 5845.94
PH4100A | SC\26\003\B | SC | 26 | 3 | B | 1 Prestrip - Thick | 100 | 5.1596 | 5.1596 | 2015-08-01 | 2015-08-01 21:52 | 40897.3718 | 40897 | [7 empty] | 0 | 0 | 2 | 8.92 | 5578.46
TS5500Shv | DT\22\005\A | DT | 22 | 5 | A | 1 Prestrip - Thick | 66.6127 | 39.1131 | 39.1131 | 2015-08-01 | 2015-08-07 19:10 | 190133.0323 | 190133 | [7 empty] | 0 | 0 | 17.01 | 11.27 | 5350.17
DRE2 | DT\17\004\D | DT | 17 | 4 | D | 6 DL | 100 | 42.7273 | 42.7273 | 2015-08-01 | 2015-08-02 02:56 | 93034.4377 |  |  |  | 4163 | 93034 | 79090 |  |  | 0 | 21.92 | 0 | 5.41 | 5938.27
PH4100XPC#1 | BW\20\007\B | BW | 20 | 7 | B | 1 Prestrip - Thick | 100 | 90.9319 | 90.9319 | 2015-08-01 | 2015-08-13 22:50 | 782015.8101 | 782016 | [7 empty] | 0 | 0 | 48.3 | 11.91 | 5372.45
TS6060#1 | BW\20\003\B | BW | 20 | 3 | B | 1 Prestrip - Thick | 100 | 90.4255 | 90.4255 | 2015-08-01 | 2015-08-13 12:45 | 338108.0762 | 338108 | [7 empty] | 0 | 0 | 20.83 | 11.65 | 5323.17
TS5500Exc | MW\21\006\B | MW | 21 | 6 | B | 1 Prestrip - Thick | 50.126 | 0 | 34.6792 | 2015-08-01 | 2015-08-09 06:45 | 192840.8721 | 192841 | [7 empty] | 0 | 0 | 9.42 | 0 | 0
TS Fleet 5 | No Production | No Production | [7 empty] | 2015-08-01 | 2015-09-01
PH4100A | SC\25\002\B | SC | 25 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-08-01 21:52 | 2015-08-10 15:15 | 392975.8223 | 392976 | [7 empty] | 0 | 0 | 37.22 | 8.9 | 5581.09
DRE2 | DT\17\003\D | DT | 17 | 3 | D | 6 DL | 100 | 100 | 100 | 2015-08-02 02:56 | 2015-08-06 01:41 | 327241.4365 |  |  |  | 14642 | 327241 | 278192 |  |  | 0 | 22.61 | 0 | 6.28 | 5861.87
DRE2 | MW\18\003\D | MW | 18 | 3 | D | 6 DL | 100 | 100 | 100 | 2015-08-06 01:41 | 2015-08-09 10:08 | 277825.4488 |  |  |  | 12431 | 277825 | 236183 |  |  | 0 | 24.88 | 0 | 5.56 | 5923.04
TS5500Shv | MW\17\011\D | MW | 17 | 11 | D | 8 Coal Mining | 45.6 | 0 | 18.2 | 2015-08-07 19:10 | 2015-08-08 03:02 | 10459.6678 | [6 empty] | 10460 | 7901 | 0.79 | 0 | 0 | 5.65 | 5914
TS5500Shv | MW\17\012\D | MW | 17 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-08-08 03:02 | 2015-08-09 22:51 | 58214.0863 | [6 empty] | 58214 | 44014 | 4.4 | 0 | 0 | 5.65 | 5914
TS5500Exc | SC\23\009\D | SC | 23 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-08-09 06:45 | 2015-08-11 15:17 | 77572.5934 | [6 empty] | 77573 | 58580 | 4.88 | 0 | 0 | 6.31 | 5860
DRE2 | MW\18\004\D | MW | 18 | 4 | D | 6 DL | 100 | 0 | 100 | 2015-08-09 10:08 | 2015-08-11 23:08 | 210651.3208 |  |  |  | 8040 | 210651 | 192963 |  |  | 0 | 19.66 | 0 | 6.1 | 5875.55
TS5500Shv | MW\17\013\D | MW | 17 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-08-09 22:51 | 2015-08-11 00:35 | 34193.6562 | [6 empty] | 34194 | 25851 | 4.22 | 0 | 0 | 5.85 | 5896
PH4100A | SC\25\012\D | SC | 25 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-08-10 15:15 | 2015-08-15 00:11 | 194901.2974 | 194901 | [7 empty] | 0 | 0 | 11.59 | 7.38 | 5763.42
DRE1 | SC\23\003\D | SC | 23 | 3 | D | 6 DL | 100 | 0 | 100 | 2015-08-10 15:50 | 2015-08-19 09:11 | 722965.1547 |  |  |  | 60769 | 722965 | 477011 |  |  | 0 | 45 | 0 | 6.23 | 5867.38
TS5500Shv | MW\18\011\B | MW | 18 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-08-11 00:35 | 2015-08-12 14:06 | 49847.3292 | [6 empty] | 49847 | 36056 | 2.75 | 0 | 0 | 14.05 | 5218
TS5500Exc | SC\25\004\B | SC | 25 | 4 | B | 8 Coal Mining | 100 | 0 | 70 | 2015-08-11 15:17 | 2015-08-12 21:57 | 42099.5333 | [6 empty] | 42100 | 31135 | 2.6 | 0 | 0 | 9 | 5574
DRE2 | MW\18\005\D | MW | 18 | 5 | D | 6 DL | 100 | 0 | 100 | 2015-08-11 23:08 | 2015-08-14 03:29 | 180800.0819 |  |  |  | 6901 | 180800 | 165618 |  |  | 0 | 17.06 | 0 | 6.28 | 5859.36
TS5500Shv | MW\19\003\B | MW | 19 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-08-12 14:06 | 2015-08-13 19:15 | 38731.1449 | [6 empty] | 38731 | 28743 | 2.88 | 0 | 0 | 8.56 | 5597
TS5500Exc | SC\26\004\B | SC | 26 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-08-12 21:57 | 2015-08-14 17:35 | 59876.5319 | [6 empty] | 59877 | 44318 | 3.76 | 0 | 0 | 8.99 | 5574
TS6060#1 | BW\19\011\B | BW | 19 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-08-13 12:45 | 2015-08-14 23:56 | 51896.5137 | [6 empty] | 51897 | 38349 | 3.98 | 0 | 0 | 9.99 | 5478
TS5500Shv | MW\19\010\B | MW | 19 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-08-13 19:15 | 2015-08-14 22:12 | 35785.8173 | [6 empty] | 35786 | 25543 | 2.5 | 0 | 0 | 16.36 | 5032
PH4100XPC#1 | BW\20\008\B | BW | 20 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-08-13 22:50 | 2015-08-27 01:46 | 780680.5282 | 780681 | [7 empty] | 0 | 0 | 51.6 | 14.63 | 5140.82
DRE2 | MW\18\006\D | MW | 18 | 6 | D | 6 DL | 100 | 0 | 100 | 2015-08-14 03:29 | 2015-08-15 22:06 | 147149.8528 |  |  |  | 5616 | 147150 | 134794 |  |  | 0 | 13.83 | 0 | 6.26 | 5861.57
TS5500Exc | SC\23\008\D | SC | 23 | 8 | D | 8 Coal Mining | 94 | 0 | 94 | 2015-08-14 17:35 | 2015-08-16 22:28 | 72583.1606 | [6 empty] | 72583 | 55254 | 4.6 | 0 | 0 | 5.78 | 5906
TS5500Shv | MW\19\011\B | MW | 19 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-08-14 22:12 | 2015-08-16 14:45 | 53889.5725 | [6 empty] | 53890 | 39004 | 3.83 | 0 | 0 | 13.98 | 5222
TS6060#1 | BW\19\010\B | BW | 19 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-08-14 23:56 | 2015-08-16 07:43 | 46863.6141 | [6 empty] | 46864 | 34552 | 3.91 | 0 | 0 | 10.09 | 5478
PH4100A | SC\26\013\D | SC | 26 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-08-15 00:11 | 2015-08-17 21:34 | 128096.247 | 128096 | [7 empty] | 0 | 0 | 16.8 | 7.41 | 5760.83
DRE2 | MW\18\007\D | MW | 18 | 7 | D | 6 DL | 100 | 0 | 100 | 2015-08-15 22:06 | 2015-08-19 11:10 | 293755.2854 |  |  |  | 12204 | 293755 | 231873 |  |  | 0 | 24.12 | 0 | 6.16 | 5869.88
TS6060#1 | DT\22\002\A2 | DT | 22 | 2 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2015-08-16 07:43 | 2015-08-17 18:12 | 50838.613 | [6 empty] | 50839 | 35885 | 1.37 | 0 | 0 | 17.63 | 4901
TS5500Shv | MW\19\012\B | MW | 19 | 12 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-08-16 14:45 | 2015-08-17 22:06 | 41656.1994 | [6 empty] | 41656 | 30362 | 2.29 | 0 | 0 | 12.82 | 5311
TS5500Exc | SC\25\004\D | SC | 25 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-08-16 22:28 | 2015-08-21 02:09 | 96044.7025 | 96045 | [7 empty] | 0 | 0 | 8.02 | 6.13 | 5875.57
TS6060#1 | DT\22\004\B | DT | 22 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-08-17 18:12 | 2015-08-19 15:13 | 66380.8533 | [6 empty] | 66381 | 48677 | 3.04 | 0 | 0 | 9.69 | 5444
PH4100A | SC\26\012\D | SC | 26 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-08-17 21:34 | 2015-08-20 08:53 | 110673.1269 | 110673 | [7 empty] | 0 | 0 | 9.51 | 7.42 | 5760.48
TS5500Shv | MW\20\003\A | MW | 20 | 3 | A | 8 Coal Mining | 35.6 | 0 | 35.6 | 2015-08-17 22:06 | 2015-08-18 18:28 | 27056.4145 | [6 empty] | 27056 | 20017 | 1.28 | 0 | 0 | 9.21 | 5502
TS5500Shv | DT\22\002\B | DT | 22 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-08-18 18:28 | 2015-08-22 00:42 | 91367.4907 | 91367 | [7 empty] | 0 | 0 | 3.5 | 10.51 | 5415.29
DRE1 | SC\23\004\D | SC | 23 | 4 | D | 6 DL | 100 | 0 | 100 | 2015-08-19 09:11 | 2015-08-28 02:38 | 723312.5152 |  |  |  | 60798 | 723313 | 477240 |  |  | 0 | 45 | 0 | 6.03 | 5884.56
DRE2 | MW\18\008\D | MW | 18 | 8 | D | 6 DL | 100 | 0 | 100 | 2015-08-19 11:10 | 2015-08-22 12:07 | 251938.0487 |  |  |  | 11272 | 251938 | 214176 |  |  | 0 | 22.14 | 0 | 6.11 | 5874.62
TS6060#1 | DT\22\005\A | DT | 22 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2015-08-19 15:13 | 2015-08-21 01:16 | 50226.0357 | [6 empty] | 50226 | 36730 | 3.03 | 0 | 0 | 11.27 | 5350
PH4100A | SC\25\011\D | SC | 25 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-08-20 08:53 | 2015-08-23 00:38 | 118591.3262 | 118591 | [7 empty] | 0 | 0 | 10.19 | 7.3 | 5772.51
TS6060#1 | BW\17\003\D | BW | 17 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-08-21 01:16 | 2015-08-22 20:41 | 64022.4221 | [6 empty] | 64022 | 48256 | 4.83 | 0 | 0 | 6.16 | 5872
TS5500Exc | SC\26\004\D | SC | 26 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-08-21 02:09 | 2015-08-24 05:23 | 72492.309 | 72492 | [7 empty] | 0 | 0 | 6.1 | 6.17 | 5871.73
TS5500Shv | BW\20\006\B | BW | 20 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-08-22 00:42 | 2015-08-24 15:22 | 83253.4514 | [6 empty] | 83253 | 60664 | 3.83 | 0 | 0 | 10.54 | 5470
DRE2 | MW\18\009\D | MW | 18 | 9 | D | 6 DL | 100 | 0 | 100 | 2015-08-22 12:07 | 2015-08-26 03:16 | 300999.7621 |  |  |  | 15476 | 301000 | 242451 |  |  | 0 | 25.36 | 0 | 6.02 | 5881.97
TS6060#1 | BW\17\002\D | BW | 17 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-08-22 20:41 | 2015-08-24 17:06 | 65484.8169 | [6 empty] | 65485 | 49555 | 4.96 | 0 | 0 | 5.68 | 5915
PH4100A | SC\26\011\D | SC | 26 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-08-23 00:38 | 2015-08-25 18:54 | 123246.7632 | 123247 | [7 empty] | 0 | 0 | 10.56 | 7.32 | 5770.42
TS5500Exc | SC\23\002\D | SC | 23 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2015-08-24 05:23 | 2015-08-27 02:59 | 67074.1985 |  |  | 67074 | [5 empty] | 0 | 0 | 0 | 6.47 | 5845.94
TS5500Shv | BW\20\007\B | BW | 20 | 7 | B | 8 Coal Mining | 100 | 0 | 69.6 | 2015-08-24 15:22 | 2015-08-26 10:45 | 57648.2982 | [6 empty] | 57648 | 41638 | 2.61 | 0 | 0 | 11.91 | 5372
TS6060#1 | BW\17\001\D | BW | 17 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-08-24 17:06 | 2015-08-26 05:41 | 53951.9219 | [6 empty] | 53952 | 40892 | 5.1 | 0 | 0 | 5.56 | 5926
PH4100A | SC\25\010\D | SC | 25 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-08-25 18:54 | 2015-08-28 21:27 | 138567.1519 | 138567 | [7 empty] | 0 | 0 | 11.9 | 6.93 | 5804.67
DRE2 | MW\18\010\D | MW | 18 | 10 | D | 6 DL | 100 | 0 | 100 | 2015-08-26 03:16 | 2015-08-29 17:06 | 296385.8568 |  |  |  | 13261 | 296386 | 251961 |  |  | 0 | 20.82 | 0 | 5.82 | 5900.15
TS6060#1 | BW\17\011\D | BW | 17 | 11 | D | 8 Coal Mining | 100 | 0 | 9.9 | 2015-08-26 05:41 | 2015-08-26 10:45 | 7467.7525 | [6 empty] | 7468 | 5611 | 0.49 | 0 | 0 | 6.91 | 5808
TS5500Shv | DT\22\005\B | DT | 22 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-08-26 10:45 | 2015-08-27 16:19 | 34536.9804 | 34537 | [7 empty] | 0 | 0 | 2.84 | 8.99 | 5516.72
TS6060#1 | BW\20\005\B | BW | 20 | 5 | B | 1 Prestrip - Thick | 5.493 | 5.493 | 5.493 | 2015-08-26 10:45 | 2015-08-27 09:17 | 25324.6745 | 25325 | [7 empty] | 0 | 0 | 1.57 | 10.27 | 5475.87
PH4100XPC#1 | BW\20\009\B | BW | 20 | 9 | B | 1 Prestrip - Thick | 100 | 48.5598 | 48.5598 | 2015-08-27 01:46 | 2015-09-01 | 300974.1552 | 300974 | [7 empty] | 0 | 0 | 19.96 | 14.01 | 5174.59
TS5500Exc | MW\21\008\B | MW | 21 | 8 | B | 1 Prestrip - Thick | 8.0616 | 8.0616 | 8.0616 | 2015-08-27 02:59 | 2015-08-28 17:52 | 37714.4238 | 37714 | [7 empty] | 0 | 0 | 2.26 | 20.7 | 4601.18
TS6060#1 | BW\21\001\X2 | BW | 21 | 1 | X2 | 1 Prestrip - Thick | 24.8988 | 0 | 12.7691 | 2015-08-27 09:17 | 2015-09-01 | 123356.34 | 123356 | [7 empty] | 0 | 0 | 5.17 | 0 | 0
TS5500Shv | DT\22\006\A | DT | 22 | 6 | A | 1 Prestrip - Thick | 100 | 40.6015 | 40.6015 | 2015-08-27 16:19 | 2015-09-01 | 119449.9542 | 119450 | [7 empty] | 0 | 0 | 14.12 | 10.25 | 5412.63
DRE1 | SC\23\005\D | SC | 23 | 5 | D | 6 DL | 100 | 0 | 44.4047 | 2015-08-28 02:38 | 2015-09-01 | 322430.0195 |  |  |  | 27102 | 322430 | 212739 |  |  | 0 | 45 | 0 | 5.95 | 5891.31
TS5500Exc | MW\21\009\B | MW | 21 | 9 | B | 1 Prestrip - Thick | 57.687 | 15.9978 | 15.9978 | 2015-08-28 17:52 | 2015-09-01 | 75727.0578 | 75727 | [7 empty] | 0 | 0 | 4.66 | 21.05 | 4615.28
PH4100A | SC\26\010\D | SC | 26 | 10 | D | 1 Prestrip - Thick | 100 | 95.1232 | 95.1232 | 2015-08-28 21:27 | 2015-09-01 | 138386.0829 | 138386 | [7 empty] | 0 | 0 | 11.85 | 6.97 | 5801.3
DRE2 | MW\18\011\D | MW | 18 | 11 | D | 6 DL | 100 | 64.3719 | 64.3719 | 2015-08-29 17:06 | 2015-09-01 | 189585.2686 |  |  |  | 9747 | 189585 | 152708 |  |  | 0 | 25.11 | 0 | 5.66 | 5913.43
| EOP 20 : 2015\Aug | EOP 20 : 2015 | Aug | [6 empty] | 2015-09-01 | 2015-09-01 |  | 4647102 |  | 67074 | 311010 | 5138734 | 3680617 | 1200000 | 887586 | 77.93 | 0 | 336.96 | 8.41 | 5661.49
DRE1 | SC\23\005\D | SC | 23 | 5 | D | 6 DL | 100 | 0 | 55.5953 | 2015-09-01 | 2015-09-05 20:53 | 403686.2018 |  |  |  | 33932 | 403686 | 266352 |  |  | 0 | 45 | 0 | 5.95 | 5891.31
PH4100A | SC\26\010\D | SC | 26 | 10 | D | 1 Prestrip - Thick | 100 | 4.8768 | 4.8768 | 2015-09-01 | 2015-09-01 03:52 | 7094.8535 | 7095 | [7 empty] | 0 | 0 | 0.61 | 6.97 | 5801.3
TS5500Shv | DT\22\006\A | DT | 22 | 6 | A | 1 Prestrip - Thick | 100 | 59.3985 | 59.3985 | 2015-09-01 | 2015-09-07 09:46 | 174750.5739 | 174751 | [7 empty] | 0 | 0 | 20.66 | 10.25 | 5412.63
DRE2 | MW\18\011\D | MW | 18 | 11 | D | 6 DL | 100 | 35.6281 | 35.6281 | 2015-09-01 | 2015-09-02 06:23 | 104930.4291 |  |  |  | 5395 | 104930 | 84520 |  |  | 0 | 25.11 | 0 | 5.66 | 5913.43
PH4100XPC#1 | BW\20\009\B | BW | 20 | 9 | B | 1 Prestrip - Thick | 100 | 51.4402 | 51.4402 | 2015-09-01 | 2015-09-06 06:54 | 318827.4664 | 318827 | [7 empty] | 0 | 0 | 21.15 | 14.01 | 5174.59
TS6060#1 | BW\21\001\X2 | BW | 21 | 1 | X2 | 1 Prestrip - Thick | 24.8988 | 0 | 12.1297 | 2015-09-01 | 2015-09-05 10:37 | 117179.4222 | 117179 | [7 empty] | 0 | 0 | 4.92 | 0 | 0
TS5500Exc | MW\21\009\B | MW | 21 | 9 | B | 1 Prestrip - Thick | 57.687 | 41.6892 | 41.6892 | 2015-09-01 | 2015-09-09 14:25 | 197339.6366 | 197340 | [7 empty] | 0 | 0 | 12.13 | 21.05 | 4615.28
TS Fleet 5 | No Production | No Production | [7 empty] | 2015-09-01 | 2015-10-01
PH4100A | SC\27\009\D | SC | 27 | 9 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-09-01 03:52 | 2015-09-06 10:39 | 234065.1477 | 234065 | [7 empty] | 0 | 0 | 19.48 | 6.46 | 5846.3
DRE2 | MW\18\012\D | MW | 18 | 12 | D | 6 DL | 100 | 0 | 100 | 2015-09-02 06:23 | 2015-09-05 21:27 | 300689.6342 |  |  |  | 15460 | 300690 | 242201 |  |  | 0 | 25.23 | 0 | 5.63 | 5915.88
TS6060#1 | BW\17\011\D | BW | 17 | 11 | D | 8 Coal Mining | 100 | 0 | 90.1 | 2015-09-05 10:37 | 2015-09-07 09:26 | 68081.2317 | [6 empty] | 68081 | 51157 | 4.46 | 0 | 0 | 6.91 | 5808
DRE1 | SC\23\006\D | SC | 23 | 6 | D | 6 DL | 100 | 0 | 100 | 2015-09-05 20:53 | 2015-09-14 15:41 | 727960.7552 |  |  |  | 61189 | 727961 | 480307 |  |  | 0 | 45 | 0 | 5.79 | 5905.1
DRE2 | MW\18\013\D | MW | 18 | 13 | D | 6 DL | 100 | 0 | 100 | 2015-09-05 21:27 | 2015-09-07 21:33 | 166109.7227 |  |  |  | 6307 | 166110 | 94616 |  |  | 0 | 24.61 | 0 | 5.84 | 5897.2
PH4100XPC#1 | BW\20\010\B | BW | 20 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-09-06 06:54 | 2015-09-12 18:26 | 376015.5157 | 376016 | [7 empty] | 0 | 0 | 23.17 | 10.46 | 5447.75
PH4100A | SC\27\010\D | SC | 27 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-09-06 10:39 | 2015-09-10 17:08 | 187876.454 | 187876 | [7 empty] | 0 | 0 | 15.87 | 7.02 | 5796.73
TS6060#1 | BW\18\003\B | BW | 18 | 3 | B | 8 Coal Mining | 46.9 | 0 | 46.9 | 2015-09-07 09:26 | 2015-09-08 01:39 | 23574.1761 | [6 empty] | 23574 | 17192 | 1.72 | 0 | 0 | 10.94 | 5368
TS5500Shv | BW\20\007\B | BW | 20 | 7 | B | 8 Coal Mining | 100 | 0 | 30.4 | 2015-09-07 09:46 | 2015-09-08 04:58 | 25166.2734 | [6 empty] | 25166 | 18177 | 1.14 | 0 | 0 | 11.91 | 5372
DRE2 | DT\18\003\D | DT | 18 | 3 | D | 6 DL | 100 | 100 | 100 | 2015-09-07 21:33 | 2015-09-12 05:23 | 358621.7522 |  |  |  | 16046 | 358622 | 304869 |  |  | 0 | 21.62 | 0 | 6.49 | 5843.81
TS6060#1 | BW\17\010\D | BW | 17 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-09-08 01:39 | 2015-09-09 22:52 | 65773.2214 | [6 empty] | 65773 | 49418 | 4.94 | 0 | 0 | 6.25 | 5865
TS5500Shv | MW\18\003\D | MW | 18 | 3 | D | 8 Coal Mining | 48.1 | 0 | 48.1 | 2015-09-08 04:58 | 2015-09-09 02:33 | 28284.5107 | [6 empty] | 28285 | 21438 | 2.14 | 0 | 0 | 5.56 | 5923
TS5500Shv | DT\22\007\A | DT | 22 | 7 | A | 1 Prestrip - Thick | 13.2985 | 13.2985 | 13.2985 | 2015-09-09 02:33 | 2015-09-10 13:57 | 40015.6482 | 40016 | [7 empty] | 0 | 0 | 2.97 | 9.58 | 5450.69
TS5500Exc | SC\23\002\D | SC | 23 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-09-09 14:25 | 2015-09-12 06:26 | 86634.848 | [6 empty] | 86635 | 65477 | 4.98 | 0 | 0 | 6.47 | 5846
TS6060#1 | BW\18\004\B | BW | 18 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-09-09 22:52 | 2015-09-11 12:03 | 54078.7145 | [6 empty] | 54079 | 39388 | 3.93 | 0 | 0 | 11.22 | 5365
TS5500Shv | DT\22\007\A | DT | 22 | 7 | A | 1 Prestrip - Thick | 86.7015 | 86.7015 | 86.7015 | 2015-09-10 13:57 | 2015-09-20 04:45 | 260888.8791 | 260889 | [7 empty] | 0 | 0 | 19.34 | 9.58 | 5450.69
PH4100A | SC\27\008\B | SC | 27 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-09-10 17:08 | 2015-09-15 09:53 | 205600.4724 | 205600 | [7 empty] | 0 | 0 | 17 | 12.21 | 5300.39
TS6060#1 | BW\18\005\B | BW | 18 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-09-11 12:03 | 2015-09-13 00:24 | 52862.625 | [6 empty] | 52863 | 38620 | 3.86 | 0 | 0 | 10.5 | 5439
DRE2 | DT\18\004\D | DT | 18 | 4 | D | 6 DL | 100 | 100 | 100 | 2015-09-12 05:23 | 2015-09-15 02:51 | 239900.3832 |  |  |  | 10734 | 239900 | 203942 |  |  | 0 | 21.73 | 0 | 5.45 | 5935.05
TS5500Exc | SC\23\003\D | SC | 23 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-09-12 06:26 | 2015-09-14 16:35 | 78730.0493 | [6 empty] | 78730 | 59549 | 4.96 | 0 | 0 | 6.23 | 5867
PH4100XPC#1 | BW\20\011\A2 | BW | 20 | 11 | A2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2015-09-12 18:26 | 2015-09-21 07:36 | 508103.3327 | 508103 | [7 empty] | 0 | 0 | 32.92 | 0 | 0
TS6060#1 | BW\18\006\B | BW | 18 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-09-13 00:24 | 2015-09-14 06:43 | 44095.7854 | [6 empty] | 44096 | 32106 | 3.22 | 0 | 0 | 10.73 | 5446
TS6060#1 | BW\17\009\D | BW | 17 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-09-14 06:43 | 2015-09-16 02:26 | 63584.8202 | [6 empty] | 63585 | 47928 | 4.79 | 0 | 0 | 5.78 | 5906
DRE1 | SC\23\007\D | SC | 23 | 7 | D | 6 DL | 100 | 0 | 100 | 2015-09-14 15:41 | 2015-09-24 10:15 | 810074.8983 |  |  |  | 61367 | 810075 | 481702 |  |  | 0 | 45 | 0 | 5.56 | 5925.07
TS5500Exc | SC\23\008\D | SC | 23 | 8 | D | 8 Coal Mining | 6 | 0 | 6 | 2015-09-14 16:35 | 2015-09-14 20:00 | 4619.0094 | [6 empty] | 4619 | 3516 | 0.29 | 0 | 0 | 5.78 | 5906
TS5500Exc | SC\25\002\B | SC | 25 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-09-14 20:00 | 2015-09-16 10:35 | 52226.4373 | [6 empty] | 52226 | 38693 | 3.93 | 0 | 0 | 8.9 | 5581
DRE2 | DT\18\005\D | DT | 18 | 5 | D | 6 DL | 100 | 100 | 100 | 2015-09-15 02:51 | 2015-09-17 18:33 | 219958.4079 |  |  |  | 9842 | 219958 | 186989 |  |  | 0 | 23.72 | 0 | 5.39 | 5938.69
PH4100A | SC\27\007\B | SC | 27 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-09-15 09:53 | 2015-09-19 15:49 | 187092.3048 | 187092 | [7 empty] | 0 | 0 | 14.76 | 9.33 | 5536.39
TS6060#1 | BW\18\007\B | BW | 18 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-09-16 02:26 | 2015-09-17 00:07 | 31527.9611 | [6 empty] | 31528 | 22678 | 2.25 | 0 | 0 | 12.88 | 5290
TS5500Exc | SC\23\004\D | SC | 23 | 4 | D | 8 Coal Mining | 92.5 | 0 | 92.5 | 2015-09-16 10:35 | 2015-09-18 16:31 | 73009.1735 | [6 empty] | 73009 | 55091 | 4.59 | 0 | 0 | 6.03 | 5885
TS6060#1 | BW\18\008\B | BW | 18 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-09-17 00:07 | 2015-09-18 10:38 | 50209.618 | [6 empty] | 50210 | 36016 | 3.61 | 0 | 0 | 13.99 | 5191
DRE2 | BW\19\010\B | BW | 19 | 10 | B | 6 DL | 100 | 0 | 0 | 2015-09-17 18:33 | 2015-09-17 18:33 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\19\009\B | BW | 19 | 9 | B | 6 DL | 100 | 0 | 0 | 2015-09-17 18:33 | 2015-09-17 18:33 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\19\008\B | BW | 19 | 8 | B | 6 DL | 100 | 0 | 0 | 2015-09-17 18:33 | 2015-09-17 18:33 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\19\007\B | BW | 19 | 7 | B | 6 DL | 100 | 0 | 0 | 2015-09-17 18:33 | 2015-09-17 18:33 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\19\006\B | BW | 19 | 6 | B | 6 DL | 100 | 0 | 0 | 2015-09-17 18:33 | 2015-09-17 18:33 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\19\005\B | BW | 19 | 5 | B | 6 DL | 100 | 0 | 0 | 2015-09-17 18:33 | 2015-09-17 18:33 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\19\004\B | BW | 19 | 4 | B | 6 DL | 100 | 0 | 0 | 2015-09-17 18:33 | 2015-09-17 18:33 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\19\003\B | BW | 19 | 3 | B | 6 DL | 100 | 0 | 0 | 2015-09-17 18:33 | 2015-09-17 18:33 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\19\002\B | BW | 19 | 2 | B | 6 DL | 100 | 0 | 0 | 2015-09-17 18:33 | 2015-09-17 18:33 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\19\001\B | BW | 19 | 1 | B | 6 DL | 100 | 0 | 0 | 2015-09-17 18:33 | 2015-09-17 18:33 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | BW\18\011\D | BW | 18 | 11 | D | 6 DL | 100 | 100 | 100 | 2015-09-17 18:33 | 2015-09-20 18:48 | 249497.588 |  |  |  | 11163 | 249498 | 212101 |  |  | 0 | 22.45 | 0 | 7.33 | 5770.75
TS6060#1 | BW\18\009\B | BW | 18 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-09-18 10:38 | 2015-09-19 23:01 | 52926.8715 | [6 empty] | 52927 | 38324 | 3.84 | 0 | 0 | 12.89 | 5264
TS5500Exc | SC\25\002\D | SC | 25 | 2 | D | 1 Prestrip - Thick | 100 | 57.8909 | 57.8909 | 2015-09-18 16:31 | 2015-09-20 05:35 | 35227.1921 | 35227 | [7 empty] | 0 | 0 | 5.24 | 6.39 | 5853.4
PH4100A | SC\25\002\D | SC | 25 | 2 | D | 1 Prestrip - Thick | 100 | 42.1091 | 42.1091 | 2015-09-19 15:49 | 2015-09-20 05:35 | 25623.783 | 25624 | [7 empty] | 0 | 0 | 3.81 | 6.39 | 5853.4
TS6060#1 | BW\20\001\B | BW | 20 | 1 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-09-19 23:01 | 2015-09-22 13:02 | 90177.4065 | [6 empty] | 90177 | 65866 | 3.73 | 0 | 0 | 10.93 | 5366
TS5500Shv | BW\20\008\B | BW | 20 | 8 | B | 8 Coal Mining | 100 | 0 | 91.1 | 2015-09-20 04:45 | 2015-09-22 13:37 | 74518.011 | [6 empty] | 74518 | 53215 | 3.33 | 0 | 0 | 14.63 | 5141
PH4100A | SC\27\006\B | SC | 27 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-09-20 05:35 | 2015-09-25 18:56 | 245941.1954 | 245941 | [7 empty] | 0 | 0 | 19.78 | 9.2 | 5553.13
TS5500Exc | SC\23\004\D | SC | 23 | 4 | D | 8 Coal Mining | 7.5 | 0 | 7.5 | 2015-09-20 05:35 | 2015-09-20 09:57 | 5900.9557 | [6 empty] | 5901 | 4453 | 0.37 | 0 | 0 | 6.03 | 5885
TS5500Exc | SC\23\005\D | SC | 23 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-09-20 09:57 | 2015-09-22 20:42 | 79531.7026 | [6 empty] | 79532 | 60012 | 5 | 0 | 0 | 5.95 | 5891
DRE2 | BW\18\010\D | BW | 18 | 10 | D | 6 DL | 100 | 100 | 100 | 2015-09-20 18:48 | 2015-09-23 17:15 | 243342.3985 |  |  |  | 10888 | 243342 | 206868 |  |  | 0 | 21.81 | 0 | 6.44 | 5848.47
PH4100XPC#1 | BW\20\005\B | BW | 20 | 5 | B | 1 Prestrip - Thick | 100 | 94.507 | 94.507 | 2015-09-21 07:36 | 2015-09-28 19:15 | 435707.6921 | 435708 | [7 empty] | 0 | 0 | 26.95 | 10.27 | 5475.87
TS6060#1 | BW\20\002\B | BW | 20 | 2 | B | 8 Coal Mining | 100 | 0 | 1.1 | 2015-09-22 13:02 | 2015-09-22 13:37 | 862.5575 | [6 empty] | 863 | 627 | 0.04 | 0 | 0 | 11.67 | 5313
TS5500Shv | MW\18\013\D | MW | 18 | 13 | D | 7 PostStrip | 50.9554 | 0 | 50.9554 | 2015-09-22 13:37 | 2015-09-23 00:47 | 12853.5336 |  |  | 12854 | [5 empty] | 0 | 0 | 0 | 5.84 | 5897.2
TS6060#1 | BW\20\004\X1 | BW | 20 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2015-09-22 13:37 | 2015-09-23 04:49 | 22099.0482 | [6 empty] | 22099 | 15898 | 0.88 | 0 | 0 | 14.6 | 5072
TS5500Exc | SC\23\006\D | SC | 23 | 6 | D | 8 Coal Mining | 100 | 0 | 91.4 | 2015-09-22 20:42 | 2015-09-25 01:33 | 71524.992 | [6 empty] | 71525 | 54230 | 4.52 | 0 | 0 | 5.79 | 5905
TS5500Shv | DT\23\001\A2 | DT | 23 | 1 | A2 | 1 Prestrip - Thick | 32.8889 | 30.8669 | 30.8669 | 2015-09-23 00:47 | 2015-10-01 | 220415.3357 | 220415 | [7 empty] | 0 | 0 | 13.06 | 19.45 | 4765.03
TS6060#1 | BW\20\004\X2 | BW | 20 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2015-09-23 04:49 | 2015-09-28 07:11 | 135680.414 | 135680 | [7 empty] | 0 | 0 | 7.6 | 0 | 0
DRE2 | BW\18\009\D | BW | 18 | 9 | D | 6 DL | 100 | 100 | 100 | 2015-09-23 17:15 | 2015-09-29 06:05 | 458732.2158 |  |  |  | 10681 | 458732 | 202932 |  |  | 0 | 21.38 | 0 | 5.82 | 5901.48
DRE1 | SC\24\012\D | SC | 24 | 12 | D | 6 DL | 100 | 0 | 47.0634 | 2015-09-24 10:15 | 2015-10-01 | 544762.1447 |  |  |  | 29986 | 544762 | 236422 |  |  | 0 | 42.98 | 0 | 7.36 | 5765.51
TS5500Exc | MW\21\009\B | MW | 21 | 9 | B | 1 Prestrip - Thick | 0.85528 | 0.85528 | 0.85528 | 2015-09-25 01:33 | 2015-09-25 05:47 | 4048.5541 | 4049 | [7 empty] | 0 | 0 | 0.25 | 21.05 | 4615.28
TS5500Exc | MW\21\010\A | MW | 21 | 10 | A | 1 Prestrip - Thick | 4.0825 | 4.0825 | 4.0825 | 2015-09-25 05:47 | 2015-09-26 02:43 | 20031.2507 | 20031 | [7 empty] | 0 | 0 | 1.28 | 13.47 | 5264.68
PH4100A | SC\27\005\B | SC | 27 | 5 | B | 1 Prestrip - Thick | 100 | 61.6746 | 61.6746 | 2015-09-25 18:56 | 2015-10-01 | 233227.4558 | 233227 | [7 empty] | 0 | 0 | 20.05 | 9.06 | 5567.76
TS5500Exc | MW\21\011\A | MW | 21 | 11 | A | 1 Prestrip - Thick | 27.9446 | 21.6357 | 21.6357 | 2015-09-26 02:43 | 2015-10-01 | 112151.7932 | 112152 | [7 empty] | 0 | 0 | 6.91 | 11.09 | 5441.26
TS6060#1 | BW\20\004\B | BW | 20 | 4 | B | 1 Prestrip - Thick | 94.1408 | 18.8155 | 18.8155 | 2015-09-28 07:11 | 2015-10-01 | 71860.972 | 71861 | [7 empty] | 0 | 0 | 4.47 | 11.46 | 5357.12
PH4100XPC#1 | BW\20\004\B | BW | 20 | 4 | B | 1 Prestrip - Thick | 100 | 33.4866 | 33.4866 | 2015-09-28 19:15 | 2015-10-01 | 127893.5928 | 127894 | [7 empty] | 0 | 0 | 7.96 | 11.46 | 5357.12
DRE2 | BW\18\008\D | BW | 18 | 8 | D | 6 DL | 100 | 29.3687 | 29.3687 | 2015-09-29 06:05 | 2015-10-01 | 144701.4684 |  |  |  | 3369 | 144701 | 64012 |  |  | 0 | 22.98 | 0 | 5.9 | 5896.06
| EOP 21 : 2015\Sep | EOP 21 : 2015 | Sep | [6 empty] | 2015-10-01 | 2015-10-01 |  | 4482659 |  | 12854 | 286357 | 4972968 | 3267832 | 1200000 | 889070 | 76.53 | 0 | 322.32 | 8.43 | 5655.46
DRE1 | SC\24\012\D | SC | 24 | 12 | D | 6 DL | 100 | 0 | 52.9366 | 2015-10-01 | 2015-10-08 11:45 | 612744.2084 |  |  |  | 33728 | 612744 | 265925 |  |  | 0 | 42.98 | 0 | 7.36 | 5765.51
PH4100A | SC\27\005\B | SC | 27 | 5 | B | 1 Prestrip - Thick | 100 | 38.3254 | 38.3254 | 2015-10-01 | 2015-10-04 08:56 | 144930.5473 | 144931 | [7 empty] | 0 | 0 | 12.46 | 9.06 | 5567.76
TS5500Shv | DT\23\001\A2 | DT | 23 | 1 | A2 | 1 Prestrip - Thick | 32.8889 | 2.022 | 2.022 | 2015-10-01 | 2015-10-01 13:15 | 14438.9958 | 14439 | [7 empty] | 0 | 0 | 0.86 | 19.45 | 4765.03
DRE2 | BW\18\008\D | BW | 18 | 8 | D | 6 DL | 100 | 70.6313 | 70.6313 | 2015-10-01 | 2015-10-05 06:05 | 348005.0013 |  |  |  | 8103 | 348005 | 153949 |  |  | 0 | 22.98 | 0 | 5.9 | 5896.06
PH4100XPC#1 | BW\20\004\B | BW | 20 | 4 | B | 1 Prestrip - Thick | 100 | 32.8998 | 32.8998 | 2015-10-01 | 2015-10-03 05:58 | 125652.3391 | 125652 | [7 empty] | 0 | 0 | 7.82 | 11.46 | 5357.12
TS6060#1 | BW\20\004\B | BW | 20 | 4 | B | 1 Prestrip - Thick | 94.1408 | 14.798 | 14.798 | 2015-10-01 | 2015-10-03 05:58 | 56517.3016 | 56517 | [7 empty] | 0 | 0 | 3.52 | 11.46 | 5357.12
TS5500Exc | MW\21\011\A | MW | 21 | 11 | A | 1 Prestrip - Thick | 27.9446 | 6.3089 | 6.3089 | 2015-10-01 | 2015-10-02 12:12 | 32702.8818 | 32703 | [7 empty] | 0 | 0 | 2.01 | 11.09 | 5441.26
TS Fleet 5 | No Production | No Production | [7 empty] | 2015-10-01 | 2015-11-01
TS5500Shv | BW\20\008\B | BW | 20 | 8 | B | 8 Coal Mining | 100 | 0 | 8.9 | 2015-10-01 13:15 | 2015-10-01 19:07 | 7261.9074 | [6 empty] | 7262 | 5186 | 0.32 | 0 | 0 | 14.63 | 5141
TS5500Shv | BW\20\009\B | BW | 20 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-10-01 19:07 | 2015-10-04 15:48 | 84987.116 | [6 empty] | 84987 | 61143 | 3.78 | 0 | 0 | 14.01 | 5175
TS5500Exc | SC\23\006\D | SC | 23 | 6 | D | 8 Coal Mining | 100 | 0 | 8.6 | 2015-10-02 12:12 | 2015-10-02 17:29 | 6745.5544 | [6 empty] | 6746 | 5114 | 0.43 | 0 | 0 | 5.79 | 5905
TS5500Exc | SC\23\007\D | SC | 23 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-10-02 17:29 | 2015-10-05 05:37 | 76873.4533 | [6 empty] | 76873 | 58709 | 4.89 | 0 | 0 | 5.56 | 5925
PH4100XPC#1 | BW\20\011\B | BW | 20 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-10-03 05:58 | 2015-10-04 12:06 | 70149.9474 | 70150 | [7 empty] | 0 | 0 | 4.37 | 10.06 | 5471.76
TS6060#1 | BW\20\002\B | BW | 20 | 2 | B | 8 Coal Mining | 100 | 0 | 98.9 | 2015-10-03 05:58 | 2015-10-05 15:27 | 78966.0125 | [6 empty] | 78966 | 57370 | 3.58 | 0 | 0 | 11.67 | 5313
PH4100A | SC\27\004\B | SC | 27 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-10-04 08:56 | 2015-10-15 13:02 | 478184.246 | 478184 | [7 empty] | 0 | 0 | 39.74 | 8.98 | 5574.7
PH4100XPC#1 | MW\22\003\A | MW | 22 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-10-04 12:06 | 2015-10-10 16:47 | 340616.9799 | 340617 | [7 empty] | 0 | 0 | 21.01 | 9.11 | 5507.89
TS5500Shv | BW\20\004\B | BW | 20 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-10-04 15:48 | 2015-10-07 12:45 | 85348.6099 | [6 empty] | 85349 | 62032 | 3.89 | 0 | 0 | 11.46 | 5357
TS5500Exc | SC\25\003\B | SC | 25 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-10-05 05:37 | 2015-10-07 05:22 | 61063.7049 | [6 empty] | 61064 | 45231 | 3.78 | 0 | 0 | 8.94 | 5577
DRE2 | BW\18\007\D | BW | 18 | 7 | D | 6 DL | 100 | 100 | 100 | 2015-10-05 06:05 | 2015-10-11 01:07 | 473893.1303 |  |  |  | 11034 | 473893 | 209638 |  |  | 0 | 22.08 | 0 | 5.62 | 5920.66
TS6060#1 | DT\17\004\D | DT | 17 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-10-05 15:27 | 2015-10-07 08:13 | 56002.0993 | [6 empty] | 56002 | 42384 | 4.81 | 0 | 0 | 5.41 | 5938
TS5500Exc | SC\26\003\B | SC | 26 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-10-07 05:22 | 2015-10-10 12:22 | 100992.0071 | [6 empty] | 100992 | 74815 | 3.86 | 0 | 0 | 8.92 | 5578
TS6060#1 | DT\22\002\B | DT | 22 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-10-07 08:13 | 2015-10-10 17:09 | 111168.7949 | [6 empty] | 111169 | 81419 | 3.14 | 0 | 0 | 10.51 | 5415
TS5500Shv | BW\20\010\B | BW | 20 | 10 | B | 8 Coal Mining | 37 | 0 | 37 | 2015-10-07 12:45 | 2015-10-08 14:15 | 31548.6609 | [6 empty] | 31549 | 23216 | 1.45 | 0 | 0 | 10.46 | 5448
DRE1 | SC\24\011\D | SC | 24 | 11 | D | 6 DL | 100 | 0 | 100 | 2015-10-08 11:45 | 2015-10-16 20:17 | 683533.6763 |  |  |  | 51980 | 683534 | 467818 |  |  | 0 | 43.41 | 0 | 7.3 | 5772.49
TS5500Shv | DT\23\001\A2 | DT | 23 | 1 | A2 | 1 Prestrip - Thick | 67.1111 | 67.1111 | 67.1111 | 2015-10-08 14:15 | 2015-10-26 22:26 | 479228.9884 | 479229 | [7 empty] | 0 | 0 | 28.4 | 19.45 | 4765.03
TS5500Exc | SC\26\005\B | SC | 26 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-10-10 12:22 | 2015-10-12 11:30 | 60245.3113 | [6 empty] | 60245 | 44523 | 3.73 | 0 | 0 | 9.06 | 5568
PH4100XPC#1 | MW\22\004\A | MW | 22 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-10-10 16:47 | 2015-10-15 13:46 | 268653.4971 | 268653 | [7 empty] | 0 | 0 | 15.17 | 9.27 | 5523.15
TS6060#1 | DT\17\003\D | DT | 17 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-10-10 17:09 | 2015-10-13 05:41 | 83153.8487 | [6 empty] | 83154 | 62583 | 4.87 | 0 | 0 | 6.28 | 5862
DRE2 | BW\18\006\D | BW | 18 | 6 | D | 6 DL | 100 | 100 | 100 | 2015-10-11 01:07 | 2015-10-17 16:54 | 544636.5849 |  |  |  | 9900 | 544637 | 237603 |  |  | 0 | 24.78 | 0 | 5.43 | 5936.7
TS5500Exc | SC\24\012\D | SC | 24 | 12 | D | 7 PostStrip | 92.8216 | 0 | 92.8216 | 2015-10-12 11:30 | 2015-10-15 13:00 | 65974.1261 |  |  | 65974 | [5 empty] | 0 | 0 | 0 | 7.36 | 5765.51
TS6060#1 | DT\17\005\D | DT | 17 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-10-13 05:41 | 2015-10-14 13:15 | 43353.4201 | [6 empty] | 43353 | 32888 | 4.65 | 0 | 0 | 5.38 | 5940
TS6060#1 | DT\22\005\B | DT | 22 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-10-14 13:15 | 2015-10-16 00:14 | 48046.3242 | [6 empty] | 48046 | 35428 | 2.93 | 0 | 0 | 8.99 | 5517
TS5500Exc | SC\24\012\D | SC | 24 | 12 | D | 7 PostStrip | 7.1784 | 0 | 7.1784 | 2015-10-15 13:00 | 2015-10-15 18:41 | 5102.1619 |  |  | 5102 | [5 empty] | 0 | 0 | 0 | 7.36 | 5765.51
PH4100A | SC\26\005\D | SC | 26 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-10-15 13:02 | 2015-10-18 05:57 | 115914.2774 | 115914 | [7 empty] | 0 | 0 | 9.68 | 6.09 | 5879.97
PH4100XPC#1 | MW\22\005\B | MW | 22 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-10-15 13:46 | 2015-10-25 07:16 | 505718.0053 | 505718 | [7 empty] | 0 | 0 | 23.44 | 11.31 | 5424.12
TS5500Exc | SC\24\012\D | SC | 24 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-10-15 18:41 | 2015-10-18 08:58 | 79620.2579 | [6 empty] | 79620 | 59223 | 4.61 | 0 | 0 | 7.36 | 5766
TS6060#1 | MW\18\007\D | MW | 18 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-10-16 00:14 | 2015-10-17 18:59 | 58714.2267 | [6 empty] | 58714 | 44109 | 4.41 | 0 | 0 | 6.16 | 5870
DRE1 | SC\24\010\D | SC | 24 | 10 | D | 6 DL | 100 | 0 | 100 | 2015-10-16 20:17 | 2015-10-25 16:10 | 722184.8235 |  |  |  | 60704 | 722185 | 476496 |  |  | 0 | 45 | 0 | 6.89 | 5808.07
DRE2 | BW\18\005\D | BW | 18 | 5 | D | 6 DL | 100 | 100 | 100 | 2015-10-17 16:54 | 2015-10-24 02:15 | 522728.7829 |  |  |  | 12171 | 522729 | 231242 |  |  | 0 | 24.37 | 0 | 5.51 | 5930.46
TS6060#1 | MW\18\008\D | MW | 18 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-10-17 18:59 | 2015-10-19 13:57 | 59036.045 | [6 empty] | 59036 | 44494 | 4.45 | 0 | 0 | 6.11 | 5875
PH4100A | SC\25\003\D | SC | 25 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-10-18 05:57 | 2015-10-20 10:15 | 93396.2571 | 93396 | [7 empty] | 0 | 0 | 7.8 | 6.29 | 5860.53
TS5500Exc | SC\26\006\B | SC | 26 | 6 | B | 8 Coal Mining | 46.8 | 0 | 46.8 | 2015-10-18 08:58 | 2015-10-19 06:18 | 27271.8837 | [6 empty] | 27272 | 20136 | 1.68 | 0 | 0 | 9.2 | 5554
TS5500Exc | SC\27\007\B | SC | 27 | 7 | B | 8 Coal Mining | 100 | 0 | 41.2 | 2015-10-19 06:18 | 2015-10-20 01:12 | 24159.3209 | [6 empty] | 24159 | 17825 | 1.48 | 0 | 0 | 9.33 | 5536
TS6060#1 | MW\18\009\D | MW | 18 | 9 | D | 8 Coal Mining | 100 | 0 | 26.3 | 2015-10-19 13:57 | 2015-10-20 01:12 | 15441.4409 | [6 empty] | 15441 | 11656 | 1.17 | 0 | 0 | 6.02 | 5882
TS6060#1 | MW\18\013\D | MW | 18 | 13 | D | 7 PostStrip | 49.0446 | 0 | 49.0446 | 2015-10-20 01:12 | 2015-10-20 13:01 | 12371.5261 |  |  | 12372 | [5 empty] | 0 | 0 | 0 | 5.84 | 5897.2
TS5500Exc | SC\26\006\D | SC | 26 | 6 | D | 1 Prestrip - Thick | 5.3479 | 5.3479 | 5.3479 | 2015-10-20 01:12 | 2015-10-20 08:20 | 6401.1765 | 6401 | [7 empty] | 0 | 0 | 0.53 | 5.8 | 5904.06
TS5500Exc | MW\21\011\A | MW | 21 | 11 | A | 1 Prestrip - Thick | 34.1165 | 34.1165 | 34.1165 | 2015-10-20 08:20 | 2015-10-28 12:08 | 176847.9533 | 176848 | [7 empty] | 0 | 0 | 10.9 | 11.09 | 5441.26
PH4100A | SC\26\006\D | SC | 26 | 6 | D | 1 Prestrip - Thick | 100 | 94.6521 | 94.6521 | 2015-10-20 10:15 | 2015-10-23 01:42 | 113295.0438 | 113295 | [7 empty] | 0 | 0 | 9.43 | 5.8 | 5904.06
TS6060#1 | BW\21\001\X2 | BW | 21 | 1 | X2 | 1 Prestrip - Thick | 75.1012 | 0 | 29.5425 | 2015-10-20 13:01 | 2015-11-01 | 285396.2075 | 285396 | [7 empty] | 0 | 0 | 11.97 | 0 | 0
PH4100A | SC\26\003\D | SC | 26 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-10-23 01:42 | 2015-10-25 22:27 | 122739.5642 | 122740 | [7 empty] | 0 | 0 | 7.52 | 6.33 | 5857.77
DRE2 | BW\18\004\D | BW | 18 | 4 | D | 6 DL | 100 | 100 | 100 | 2015-10-24 02:15 | 2015-10-30 05:56 | 503347.9553 |  |  |  | 11719 | 503348 | 222668 |  |  | 0 | 23.41 | 0 | 6 | 5888
PH4100XPC#1 | MW\21\006\B | MW | 21 | 6 | B | 1 Prestrip - Thick | 100 | 0 | 13.9596 | 2015-10-25 07:16 | 2015-10-26 20:31 | 77625.3213 | 77625 | [7 empty] | 0 | 0 | 3.79 | 0 | 0
DRE1 | SC\24\009\D | SC | 24 | 9 | D | 6 DL | 100 | 0 | 71.6324 | 2015-10-25 16:10 | 2015-11-01 | 517535.6918 |  |  |  | 43502 | 517536 | 341469 |  |  | 0 | 45 | 0 | 6.3 | 5860.17
PH4100A | SC\28\009\D | SC | 28 | 9 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-10-25 22:27 | 2015-10-31 16:47 | 246254.8038 | 246255 | [7 empty] | 0 | 0 | 20.54 | 6.55 | 5838.19
PH4100XPC#1 | MW\22\006\D | MW | 22 | 6 | D | 1 Prestrip - Thick | 100 | 74.0403 | 74.0403 | 2015-10-26 20:31 | 2015-11-01 | 272992.87 | 272993 | [7 empty] | 0 | 0 | 17.15 | 6.83 | 5812.23
TS5500Shv | DT\23\002\A2 | DT | 23 | 2 | A2 | 1 Prestrip - Thick | 68.2257 | 24.5476 | 24.5476 | 2015-10-26 22:26 | 2015-11-01 | 132031.4128 | 132031 | [7 empty] | 0 | 0 | 8.9 | 16.97 | 4981.92
TS5500Exc | MW\23\003\A | MW | 23 | 3 | A | 1 Prestrip - Thick | 4.9371 | 4.9371 | 4.9371 | 2015-10-28 12:08 | 2015-10-29 12:41 | 22072.2647 | 22072 | [7 empty] | 0 | 0 | 1.42 | 9.44 | 5494.96
TS5500Exc | MW\23\003\A | MW | 23 | 3 | A | 1 Prestrip - Thick | 95.0629 | 11.9209 | 11.9209 | 2015-10-29 12:41 | 2015-11-01 | 53294.0721 | 53294 | [7 empty] | 0 | 0 | 3.43 | 9.44 | 5494.96
DRE2 | BW\18\003\D | BW | 18 | 3 | D | 6 DL | 100 | 29.3439 | 29.3439 | 2015-10-30 05:56 | 2015-11-01 | 143386.9453 |  |  |  | 3338 | 143387 | 63431 |  |  | 0 | 22.75 | 0 | 6.37 | 5854.41
PH4100A | SC\28\010\D | SC | 28 | 10 | D | 1 Prestrip - Thick | 100 | 6.8385 | 6.8385 | 2015-10-31 16:47 | 2015-11-01 | 12733.5224 | 12734 | [7 empty] | 0 | 0 | 1.07 | 7.09 | 5790.4
| EOP 22 : 2015\Oct | EOP 22 : 2015 | Oct | [6 empty] | 2015-11-01 | 2015-11-01 |  | 4247788 |  | 83448 | 246178 | 5071997 | 2670240 | 1200000 | 889485 | 67.91 | 0 | 272.92 | 8.01 | 5686.92
DRE1 | SC\24\009\D | SC | 24 | 9 | D | 6 DL | 100 | 0 | 28.3676 | 2015-11-01 | 2015-11-03 12:55 | 204952.4509 |  |  |  | 17227 | 204952 | 135227 |  |  | 0 | 45 | 0 | 6.3 | 5860.17
PH4100A | SC\28\010\D | SC | 28 | 10 | D | 1 Prestrip - Thick | 100 | 93.1615 | 93.1615 | 2015-11-01 | 2015-11-05 06:28 | 173468.8361 | 173469 | [7 empty] | 0 | 0 | 14.61 | 7.09 | 5790.4
TS5500Shv | DT\23\002\A2 | DT | 23 | 2 | A2 | 1 Prestrip - Thick | 68.2257 | 43.6781 | 43.6781 | 2015-11-01 | 2015-11-10 06:49 | 234926.6237 | 234927 | [7 empty] | 0 | 0 | 15.83 | 16.97 | 4981.92
DRE2 | BW\18\003\D | BW | 18 | 3 | D | 6 DL | 100 | 70.6561 | 70.6561 | 2015-11-01 | 2015-11-05 06:38 | 345256.2239 |  |  |  | 8039 | 345256 | 152733 |  |  | 0 | 22.75 | 0 | 6.37 | 5854.41
PH4100XPC#1 | MW\22\006\D | MW | 22 | 6 | D | 1 Prestrip - Thick | 100 | 25.9597 | 25.9597 | 2015-11-01 | 2015-11-02 21:10 | 95715.7577 | 95716 | [7 empty] | 0 | 0 | 6.01 | 6.83 | 5812.23
TS6060#1 | BW\21\001\X2 | BW | 21 | 1 | X2 | 1 Prestrip - Thick | 75.1012 | 0 | 45.5586 | 2015-11-01 | 2015-11-19 04:54 | 440119.995 | 440120 | [7 empty] | 0 | 0 | 18.46 | 0 | 0
TS5500Exc | MW\23\003\A | MW | 23 | 3 | A | 1 Prestrip - Thick | 95.0629 | 83.142 | 83.142 | 2015-11-01 | 2015-11-18 18:08 | 371698.8581 | 371699 | [7 empty] | 0 | 0 | 23.89 | 9.44 | 5494.96
TS Fleet 5 | No Production | No Production | [7 empty] | 2015-11-01 | 2015-12-01
PH4100XPC#1 | MW\21\007\B | MW | 21 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-11-02 21:10 | 2015-11-13 17:28 | 519767.368 | 519767 | [7 empty] | 0 | 0 | 24.72 | 10.32 | 5491.86
DRE1 | SC\24\008\D | SC | 24 | 8 | D | 6 DL | 100 | 0 | 100 | 2015-11-03 12:55 | 2015-11-12 13:44 | 729323.9906 |  |  |  | 61304 | 729324 | 481207 |  |  | 0 | 45 | 0 | 5.72 | 5911.41
PH4100A | SC\28\008\B | SC | 28 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-11-05 06:28 | 2015-11-10 10:30 | 211808.8066 | 211809 | [7 empty] | 0 | 0 | 18.21 | 11.18 | 5382.25
DRE2 | BW\18\002\D | BW | 18 | 2 | D | 6 DL | 100 | 100 | 100 | 2015-11-05 06:38 | 2015-11-11 03:17 | 473119.9679 |  |  |  | 11016 | 473120 | 209296 |  |  | 0 | 22.07 | 0 | 5.88 | 5897.42
TS5500Shv | BW\18\010\D | BW | 18 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-11-10 06:49 | 2015-11-12 13:29 | 65659.5575 | [6 empty] | 65660 | 49294 | 4.93 | 0 | 0 | 6.44 | 5848
PH4100A | SC\28\007\B | SC | 28 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-11-10 10:30 | 2015-11-16 17:52 | 262147.6699 | 262148 | [7 empty] | 0 | 0 | 22.78 | 9.32 | 5537.31
DRE2 | BW\18\001\D | BW | 18 | 1 | D | 6 DL | 100 | 100 | 100 | 2015-11-11 03:17 | 2015-11-16 18:37 | 455196.2134 |  |  |  | 7140 | 455196 | 130358 |  |  | 0 | 21.76 | 0 | 5.67 | 5916.48
TS5500Shv | BW\18\009\D | BW | 18 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-11-12 13:29 | 2015-11-14 17:47 | 62821.31 | [6 empty] | 62821 | 47353 | 4.73 | 0 | 0 | 5.82 | 5901
DRE1 | SC\24\002\D | SC | 24 | 2 | D | 6 DL | 100 | 0 | 100 | 2015-11-12 13:44 | 2015-11-22 06:11 | 781852.9529 |  |  |  | 47447 | 781853 | 325783 |  |  | 0 | 45 | 0 | 6.42 | 5850.79
PH4100XPC#1 | MW\22\007\B | MW | 22 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-11-13 17:28 | 2015-11-22 15:05 | 430530.1912 | 430530 | [7 empty] | 0 | 0 | 26.86 | 9.88 | 5529.71
TS5500Shv | BW\18\011\D | BW | 18 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-11-14 17:47 | 2015-11-17 00:43 | 65984.4863 | [6 empty] | 65984 | 49459 | 4.95 | 0 | 0 | 7.33 | 5771
PH4100A | SC\28\006\B | SC | 28 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-11-16 17:52 | 2015-11-24 15:11 | 331108.303 | 331108 | [7 empty] | 0 | 0 | 30.2 | 9.23 | 5550.43
DRE2 | DT\19\004\D | DT | 19 | 4 | D | 6 DL | 100 | 100 | 100 | 2015-11-16 18:37 | 2015-11-19 23:45 | 259472.1018 |  |  |  | 11609 | 259472 | 220580 |  |  | 0 | 23.21 | 0 | 5.51 | 5929.07
TS5500Shv | BW\20\010\B | BW | 20 | 10 | B | 8 Coal Mining | 63 | 0 | 63 | 2015-11-17 00:43 | 2015-11-18 21:23 | 53663.2151 | [6 empty] | 53663 | 39490 | 2.46 | 0 | 0 | 10.46 | 5448
TS5500Exc | SC\27\007\B | SC | 27 | 7 | B | 8 Coal Mining | 100 | 0 | 58.8 | 2015-11-18 18:08 | 2015-11-19 21:54 | 34454.6099 | [6 empty] | 34455 | 25421 | 2.12 | 0 | 0 | 9.33 | 5536
TS5500Shv | BW\20\011\B | BW | 20 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-11-18 21:23 | 2015-11-21 22:51 | 88231.2897 | [6 empty] | 88231 | 65220 | 4.07 | 0 | 0 | 10.06 | 5472
TS6060#1 | MW\18\009\D | MW | 18 | 9 | D | 8 Coal Mining | 100 | 0 | 73.7 | 2015-11-19 04:54 | 2015-11-20 13:23 | 43298.7203 | [6 empty] | 43299 | 32685 | 3.27 | 0 | 0 | 6.02 | 5882
TS5500Exc | SC\24\011\D | SC | 24 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-11-19 21:54 | 2015-11-22 13:26 | 78841.8012 | [6 empty] | 78842 | 58741 | 4.9 | 0 | 0 | 7.3 | 5772
DRE2 | DT\19\005\D | DT | 19 | 5 | D | 6 DL | 100 | 100 | 100 | 2015-11-19 23:45 | 2015-11-23 08:45 | 272497.3998 |  |  |  | 12192 | 272497 | 231653 |  |  | 0 | 23.67 | 0 | 5.41 | 5937.11
TS6060#1 | MW\18\010\D | MW | 18 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-11-20 13:23 | 2015-11-22 10:02 | 59526.1146 | [6 empty] | 59526 | 44935 | 4.49 | 0 | 0 | 5.82 | 5900
TS5500Shv | MW\18\003\D | MW | 18 | 3 | D | 8 Coal Mining | 51.9 | 0 | 51.9 | 2015-11-21 22:51 | 2015-11-23 00:14 | 30502.7583 | [6 empty] | 30503 | 23119 | 2.31 | 0 | 0 | 5.56 | 5923
DRE1 | SC\24\003\D | SC | 24 | 3 | D | 6 DL | 100 | 0 | 97.4965 | 2015-11-22 06:11 | 2015-12-01 | 705770.6056 |  |  |  | 59324 | 705771 | 465666 |  |  | 0 | 45 | 0 | 6.27 | 5863.35
TS6060#1 | DT\22\006\A | DT | 22 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2015-11-22 10:02 | 2015-11-23 18:42 | 43558.9231 | [6 empty] | 43559 | 32028 | 3.78 | 0 | 0 | 10.25 | 5413
TS5500Exc | SC\27\008\B | SC | 27 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-11-22 13:26 | 2015-11-23 03:14 | 17109.3335 | [6 empty] | 17109 | 12430 | 1.02 | 0 | 0 | 12.21 | 5300
PH4100XPC#1 | MW\21\008\B | MW | 21 | 8 | B | 1 Prestrip - Thick | 100 | 85.9251 | 85.9251 | 2015-11-22 15:05 | 2015-12-01 | 401979.5823 | 401980 | [7 empty] | 0 | 0 | 24.14 | 20.7 | 4601.18
TS5500Shv | MW\18\004\D | MW | 18 | 4 | D | 8 Coal Mining | 15.4 | 0 | 15.4 | 2015-11-23 00:14 | 2015-11-23 07:50 | 9128.2719 | [6 empty] | 9128 | 6902 | 0.69 | 0 | 0 | 6.1 | 5876
TS5500Exc | MW\18\012\D | MW | 18 | 12 | D | 8 Coal Mining | 12.2 | 0 | 12.2 | 2015-11-23 03:14 | 2015-11-23 08:57 | 7107.781 | [6 empty] | 7108 | 5378 | 0.54 | 0 | 0 | 5.63 | 5916
TS5500Shv | MW\18\004\D | MW | 18 | 4 | D | 8 Coal Mining | 84.6 | 0 | 84.6 | 2015-11-23 07:50 | 2015-11-25 01:38 | 50213.7902 | [6 empty] | 50214 | 37967 | 3.8 | 0 | 0 | 6.1 | 5876
DRE2 | MW\19\003\D | MW | 19 | 3 | D | 6 DL | 100 | 100 | 100 | 2015-11-23 08:45 | 2015-11-26 17:56 | 273068.8094 |  |  |  | 12218 | 273069 | 232139 |  |  | 0 | 24.64 | 0 | 5.63 | 5916.78
TS5500Exc | MW\18\013\D | MW | 18 | 13 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2015-11-23 08:57 | 2015-11-23 20:13 | 13976.7991 | [6 empty] | 13977 | 10567 | 2.17 | 0 | 0 | 5.84 | 5897
TS6060#1 | DT\22\007\A | DT | 22 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2015-11-23 18:42 | 2015-11-25 22:17 | 68779.2294 | [6 empty] | 68779 | 50785 | 3.78 | 0 | 0 | 9.58 | 5451
TS5500Exc | MW\20\003\A | MW | 20 | 3 | A | 8 Coal Mining | 32.7 | 0 | 32.7 | 2015-11-23 20:13 | 2015-11-24 16:18 | 24917.7475 | [6 empty] | 24918 | 18435 | 1.18 | 0 | 0 | 9.21 | 5502
PH4100A | SC\28\005\B | SC | 28 | 5 | B | 1 Prestrip - Thick | 100 | 61.1146 | 61.1146 | 2015-11-24 15:11 | 2015-12-01 | 265924.0197 | 265924 | [7 empty] | 0 | 0 | 23.69 | 9.08 | 5565.59
TS5500Exc | MW\20\008\B | MW | 20 | 8 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2015-11-24 16:18 | 2015-11-25 22:42 | 37710.4838 | [6 empty] | 37710 | 26481 | 1.39 | 0 | 0 | 19.26 | 4727
TS5500Shv | DT\22\006\B | DT | 22 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-11-25 01:38 | 2015-11-26 01:50 | 25545.6079 | 25546 | [7 empty] | 0 | 0 | 3.04 | 8.34 | 5590.21
TS6060#1 | DT\18\003\D | DT | 18 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-11-25 22:17 | 2015-11-28 21:52 | 95423.1061 | [6 empty] | 95423 | 71760 | 4.87 | 0 | 0 | 6.49 | 5844
TS5500Exc | MW\20\009\B | MW | 20 | 9 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2015-11-25 22:42 | 2015-11-27 01:21 | 33084.71 | [6 empty] | 33085 | 23255 | 1.22 | 0 | 0 | 19.04 | 4781
TS5500Shv | DT\22\007\B | DT | 22 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-11-26 01:50 | 2015-11-27 16:44 | 41078.3166 | 41078 | [7 empty] | 0 | 0 | 3.08 | 7.92 | 5632.37
DRE2 | MW\19\004\D | MW | 19 | 4 | D | 6 DL | 100 | 0 | 100 | 2015-11-26 17:56 | 2015-11-30 07:01 | 286189.6508 |  |  |  | 12805 | 286190 | 243293 |  |  | 0 | 24.84 | 0 | 6.22 | 5865.74
TS5500Exc | SC\24\010\D | SC | 24 | 10 | D | 8 Coal Mining | 6.7 | 0 | 6.7 | 2015-11-27 01:21 | 2015-11-27 05:31 | 5165.2709 | [6 empty] | 5165 | 3870 | 0.32 | 0 | 0 | 6.89 | 5808
TS5500Exc | SC\24\009\D | SC | 24 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-11-27 05:31 | 2015-11-29 20:11 | 77759.6023 | [6 empty] | 77760 | 58721 | 4.89 | 0 | 0 | 6.3 | 5860
TS5500Shv | MW\18\005\D | MW | 18 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-11-27 16:44 | 2015-11-29 16:31 | 57403.5568 | [6 empty] | 57404 | 43295 | 4.33 | 0 | 0 | 6.28 | 5859
TS6060#1 | DT\18\004\D | DT | 18 | 4 | D | 8 Coal Mining | 100 | 0 | 70.8 | 2015-11-28 21:52 | 2015-11-30 07:11 | 44419.4516 | [6 empty] | 44419 | 33618 | 3.42 | 0 | 0 | 5.45 | 5935
TS5500Shv | MW\18\006\D | MW | 18 | 6 | D | 8 Coal Mining | 100 | 0 | 29.2 | 2015-11-29 16:31 | 2015-11-30 07:11 | 17615.861 | [6 empty] | 17616 | 13234 | 1.32 | 0 | 0 | 6.26 | 5862
TS5500Exc | SC\24\008\D | SC | 24 | 8 | D | 8 Coal Mining | 100 | 0 | 17.7 | 2015-11-29 20:11 | 2015-11-30 07:11 | 13642.219 | [6 empty] | 13642 | 10402 | 0.87 | 0 | 0 | 5.72 | 5911
DRE2 | MW\19\005\D | MW | 19 | 5 | D | 6 DL | 100 | 0 | 31.5426 | 2015-11-30 07:01 | 2015-12-01 | 57099.6331 |  |  |  | 2179 | 57100 | 52305 |  |  | 0 | 17.31 | 0 | 6.38 | 5850.71
TS5500Shv | DT\23\002\A2 | DT | 23 | 2 | A2 | 1 Prestrip - Thick | 31.7743 | 3.2948 | 3.2948 | 2015-11-30 07:11 | 2015-12-01 | 17721.1855 | 17721 | [7 empty] | 0 | 0 | 1.19 | 16.97 | 4981.92
TS6060#1 | BW\21\001\B | BW | 21 | 1 | B | 1 Prestrip - Thick | 86.6197 | 3.6602 | 3.6602 | 2015-11-30 07:11 | 2015-12-01 | 17084.4354 | 17084 | [7 empty] | 0 | 0 | 0.88 | 11.09 | 5369.87
TS5500Exc | SC\24\002\D | SC | 24 | 2 | D | 7 PostStrip | 44.0187 | 0 | 31.3883 | 2015-11-30 07:11 | 2015-12-01 | 14643.8018 |  |  | 14644 | [5 empty] | 0 | 0 | 0 | 6.42 | 5850.79
| EOP 23 : 2015\Nov | EOP 23 : 2015 | Nov | [6 empty] | 2015-12-01 | 2015-12-01 |  | 3840626 |  | 14644 | 262500 | 4843800 | 2880241 | 1200000 | 894846 | 77.82 | 0 | 257.59 | 8.15 | 5678.22
DRE1 | SC\24\003\D | SC | 24 | 3 | D | 6 DL | 100 | 0 | 2.5035 | 2015-12-01 | 2015-12-01 06:12 | 18122.4078 |  |  |  | 1523 | 18122 | 11957 |  |  | 0 | 45 | 0 | 6.27 | 5863.35
PH4100A | SC\28\005\B | SC | 28 | 5 | B | 1 Prestrip - Thick | 100 | 38.8854 | 38.8854 | 2015-12-01 | 2015-12-05 21:41 | 169199.421 | 169199 | [7 empty] | 0 | 0 | 15.07 | 9.08 | 5565.59
TS5500Shv | DT\23\002\A2 | DT | 23 | 2 | A2 | 1 Prestrip - Thick | 31.7743 | 28.4795 | 28.4795 | 2015-12-01 | 2015-12-08 09:34 | 153179.4411 | 153179 | [7 empty] | 0 | 0 | 10.32 | 16.97 | 4981.92
DRE2 | MW\19\005\D | MW | 19 | 5 | D | 6 DL | 100 | 0 | 68.4574 | 2015-12-01 | 2015-12-02 18:30 | 123924.2585 |  |  |  | 4730 | 123924 | 113518 |  |  | 0 | 17.31 | 0 | 6.38 | 5850.71
PH4100XPC#1 | MW\21\008\B | MW | 21 | 8 | B | 1 Prestrip - Thick | 100 | 6.0132 | 6.0132 | 2015-12-01 | 2015-12-01 17:01 | 28131.4628 | 28131 | [7 empty] | 0 | 0 | 1.69 | 20.7 | 4601.18
TS6060#1 | BW\21\001\B | BW | 21 | 1 | B | 1 Prestrip - Thick | 86.6197 | 82.9596 | 82.9596 | 2015-12-01 | 2015-12-20 09:38 | 387224.9185 | 387225 | [7 empty] | 0 | 0 | 19.84 | 11.09 | 5369.87
TS5500Exc | SC\24\002\D | SC | 24 | 2 | D | 7 PostStrip | 44.0187 | 0 | 12.6305 | 2015-12-01 | 2015-12-01 08:16 | 5892.5878 |  |  | 5893 | [5 empty] | 0 | 0 | 0 | 6.42 | 5850.79
TS Fleet 5 | No Production | No Production | [7 empty] | 2015-12-01 | 2016-01-01
DRE1 | SC\24\004\D | SC | 24 | 4 | D | 6 DL | 100 | 0 | 100 | 2015-12-01 06:12 | 2015-12-11 14:46 | 724600.2128 |  |  |  | 60907 | 724600 | 478090 |  |  | 0 | 45 | 0 | 6.08 | 5880
TS5500Exc | SC\24\008\D | SC | 24 | 8 | D | 8 Coal Mining | 100 | 0 | 82.3 | 2015-12-01 08:16 | 2015-12-03 22:45 | 63441.7508 | [6 empty] | 63442 | 48373 | 4.03 | 0 | 0 | 5.72 | 5911
PH4100XPC#1 | MW\22\008\B | MW | 22 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-12-01 17:01 | 2015-12-12 18:54 | 444492.37 | 444492 | [7 empty] | 0 | 0 | 27.64 | 10.15 | 5495.57
DRE2 | MW\19\006\D | MW | 19 | 6 | D | 6 DL | 100 | 0 | 100 | 2015-12-02 18:30 | 2015-12-05 09:25 | 183415.9048 |  |  |  | 7001 | 183416 | 168015 |  |  | 0 | 17.09 | 0 | 6.35 | 5854.39
TS5500Exc | SC\24\010\D | SC | 24 | 10 | D | 8 Coal Mining | 93.3 | 0 | 93.3 | 2015-12-03 22:45 | 2015-12-06 22:06 | 72440.1792 | [6 empty] | 72440 | 54270 | 4.52 | 0 | 0 | 6.89 | 5808
DRE2 | MW\19\007\D | MW | 19 | 7 | D | 6 DL | 100 | 0 | 100 | 2015-12-05 09:25 | 2015-12-10 06:05 | 340124.9344 |  |  |  | 15893 | 340125 | 248995 |  |  | 0 | 26.21 | 0 | 6.14 | 5871.48
PH4100A | SC\28\004\B | SC | 28 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-12-05 21:41 | 2015-12-20 | 476756.0912 | 476756 | [7 empty] | 0 | 0 | 40.99 | 8.99 | 5573.8
TS5500Exc | SC\27\006\B | SC | 27 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-12-06 22:06 | 2015-12-09 07:10 | 57932.2201 | [6 empty] | 57932 | 42772 | 3.57 | 0 | 0 | 9.2 | 5553
TS5500Shv | MW\18\006\D | MW | 18 | 6 | D | 8 Coal Mining | 100 | 0 | 70.8 | 2015-12-08 09:34 | 2015-12-10 04:56 | 42623.3633 | [6 empty] | 42623 | 32022 | 3.2 | 0 | 0 | 6.26 | 5862
TS5500Exc | SC\28\006\B | SC | 28 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-12-09 07:10 | 2015-12-11 14:45 | 56432.196 | [6 empty] | 56432 | 41659 | 3.49 | 0 | 0 | 9.23 | 5550
TS5500Shv | MW\18\011\D | MW | 18 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-12-10 04:56 | 2015-12-12 14:59 | 57041.2541 | [6 empty] | 57041 | 43090 | 4.31 | 0 | 0 | 5.66 | 5913
DRE2 | MW\19\008\D | MW | 19 | 8 | D | 6 DL | 100 | 0 | 100 | 2015-12-10 06:05 | 2015-12-14 17:05 | 311924.3063 |  |  |  | 16037 | 311924 | 251250 |  |  | 0 | 26.2 | 0 | 6.09 | 5876.16
TS5500Exc | SC\28\007\B | SC | 28 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-12-11 14:45 | 2015-12-14 00:57 | 59081.804 | [6 empty] | 59082 | 43594 | 3.63 | 0 | 0 | 9.32 | 5537
DRE1 | SC\24\005\D | SC | 24 | 5 | D | 6 DL | 100 | 0 | 100 | 2015-12-11 14:46 | 2015-12-21 23:54 | 726273.0504 |  |  |  | 61047 | 726273 | 479194 |  |  | 0 | 45 | 0 | 6.02 | 5885.53
TS5500Shv | MW\18\012\D | MW | 18 | 12 | D | 8 Coal Mining | 87.8 | 0 | 87.8 | 2015-12-12 14:59 | 2015-12-14 18:50 | 50956.6032 | [6 empty] | 50957 | 38557 | 3.86 | 0 | 0 | 5.63 | 5916
PH4100XPC#1 | MW\21\009\B | MW | 21 | 9 | B | 1 Prestrip - Thick | 100 | 41.4577 | 41.4577 | 2015-12-12 18:54 | 2015-12-17 15:53 | 196244.0096 | 196244 | [7 empty] | 0 | 0 | 12.07 | 21.05 | 4615.28
TS5500Exc | SC\28\008\B | SC | 28 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-12-14 00:57 | 2015-12-14 23:46 | 23159.0089 | [6 empty] | 23159 | 16918 | 1.39 | 0 | 0 | 11.18 | 5382
DRE2 | MW\19\009\D | MW | 19 | 9 | D | 6 DL | 100 | 0 | 100 | 2015-12-14 17:05 | 2015-12-19 13:03 | 338080.2937 |  |  |  | 17382 | 338080 | 272318 |  |  | 0 | 28.52 | 0 | 6.1 | 5875.11
TS5500Shv | MW\18\013\D | MW | 18 | 13 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2015-12-14 18:50 | 2015-12-15 08:36 | 13530.731 | [6 empty] | 13531 | 10229 | 2.1 | 0 | 0 | 5.84 | 5897
TS5500Exc | MW\19\004\D | MW | 19 | 4 | D | 8 Coal Mining | 33.9 | 0 | 33.9 | 2015-12-14 23:46 | 2015-12-15 20:07 | 20662.3815 | [6 empty] | 20662 | 15611 | 1.56 | 0 | 0 | 6.22 | 5866
TS5500Shv | MW\20\003\A | MW | 20 | 3 | A | 8 Coal Mining | 31.7 | 0 | 31.7 | 2015-12-15 08:36 | 2015-12-16 09:08 | 24122.5003 | [6 empty] | 24123 | 17846 | 1.14 | 0 | 0 | 9.21 | 5502
TS5500Exc | MW\19\005\D | MW | 19 | 5 | D | 8 Coal Mining | 20.3 | 0 | 20.3 | 2015-12-15 20:07 | 2015-12-16 07:51 | 11915.7966 | [6 empty] | 11916 | 8981 | 0.9 | 0 | 0 | 6.38 | 5851
TS5500Exc | SC\24\003\D | SC | 24 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-12-16 07:51 | 2015-12-19 12:08 | 77434.9068 | [6 empty] | 77435 | 58616 | 4.88 | 0 | 0 | 6.27 | 5863
TS5500Shv | MW\20\008\B | MW | 20 | 8 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2015-12-16 09:08 | 2015-12-17 22:17 | 36506.9578 | [6 empty] | 36507 | 25635 | 1.35 | 0 | 0 | 19.26 | 4727
PH4100XPC#1 | MW\20\003\B | MW | 20 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-12-17 15:53 | 2015-12-18 12:17 | 37611.0491 | 37611 | [7 empty] | 0 | 0 | 2.42 | 8.27 | 5620.69
TS5500Shv | MW\20\009\B | MW | 20 | 9 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2015-12-17 22:17 | 2015-12-19 06:53 | 32028.815 | [6 empty] | 32029 | 22513 | 1.18 | 0 | 0 | 19.04 | 4781
PH4100XPC#1 | MW\22\009\A | MW | 22 | 9 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-12-18 12:17 | 2015-12-29 01:03 | 414095.0444 | 414095 | [7 empty] | 0 | 0 | 24.93 | 11.34 | 5399.29
TS5500Shv | MW\20\010\A | MW | 20 | 10 | A | 8 Coal Mining | 13.4 | 0 | 13.4 | 2015-12-19 06:53 | 2015-12-19 11:58 | 5000.4218 | [6 empty] | 5000 | 3631 | 0.22 | 0 | 0 | 12.26 | 5364
TS5500Shv | BW\18\001\D | BW | 18 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2015-12-19 11:58 | 2015-12-21 11:26 | 41007.5739 |  |  | 41008 | [5 empty] | 0 | 0 | 0 | 5.67 | 5916.48
TS5500Exc | SC\24\004\D | SC | 24 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-12-19 12:08 | 2015-12-22 17:07 | 78150.7102 | [6 empty] | 78151 | 58922 | 4.91 | 0 | 0 | 6.08 | 5880
DRE2 | MW\19\010\D | MW | 19 | 10 | D | 6 DL | 100 | 100 | 100 | 2015-12-19 13:03 | 2015-12-23 19:13 | 297847.9077 |  |  |  | 15314 | 297848 | 239912 |  |  | 0 | 25.47 | 0 | 5.93 | 5889.74
PH4100A | SC\27\003\B | SC | 27 | 3 | B | 1 Prestrip - Thick | 100 | 56.2471 | 56.2471 | 2015-12-20 | 2016-01-01 | 403926.875 | 403927 | [7 empty] | 0 | 0 | 22.62 | 8.93 | 5577.93
TS6060#1 | DT\18\004\D | DT | 18 | 4 | D | 8 Coal Mining | 100 | 0 | 29.2 | 2015-12-20 09:38 | 2015-12-21 02:25 | 18308.0133 | [6 empty] | 18308 | 13856 | 1.41 | 0 | 0 | 5.45 | 5935
TS6060#1 | DT\18\005\D | DT | 18 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-12-21 02:25 | 2015-12-23 00:34 | 50347.8075 | [6 empty] | 50348 | 38194 | 4.67 | 0 | 0 | 5.39 | 5939
TS5500Shv | SC\24\002\D | SC | 24 | 2 | D | 7 PostStrip | 55.9813 | 0 | 55.9813 | 2015-12-21 11:26 | 2015-12-22 17:39 | 26117.3739 |  |  | 26117 | [5 empty] | 0 | 0 | 0 | 6.42 | 5850.79
DRE1 | SC\24\006\D | SC | 24 | 6 | D | 6 DL | 100 | 0 | 96.4148 | 2015-12-21 23:54 | 2016-01-01 | 699950.3289 |  |  |  | 58835 | 699950 | 461826 |  |  | 0 | 45 | 0 | 5.79 | 5905.45
TS5500Exc | SC\24\005\D | SC | 24 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-12-22 17:07 | 2015-12-25 23:56 | 80015.8531 | [6 empty] | 80016 | 60282 | 5.02 | 0 | 0 | 6.02 | 5886
TS5500Shv | SC\24\002\D | SC | 24 | 2 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2015-12-22 17:39 | 2015-12-23 23:41 | 29512.7373 | [6 empty] | 29513 | 22359 | 2.47 | 0 | 0 | 6.42 | 5851
TS6060#1 | DT\22\006\B | DT | 22 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2015-12-23 00:34 | 2015-12-24 06:54 | 33084.053 | [6 empty] | 33084 | 24556 | 2.94 | 0 | 0 | 8.34 | 5590
DRE2 | MW\19\011\D | MW | 19 | 11 | D | 6 DL | 100 | 100 | 100 | 2015-12-23 19:13 | 2015-12-28 02:06 | 299889.5218 |  |  |  | 15418 | 299890 | 241556 |  |  | 0 | 25.67 | 0 | 5.66 | 5913.14
TS5500Shv | MW\19\003\D | MW | 19 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2015-12-23 23:41 | 2015-12-26 11:58 | 59241.1508 | [6 empty] | 59241 | 44901 | 4.49 | 0 | 0 | 5.63 | 5917
TS6060#1 | DT\22\007\B | DT | 22 | 7 | B | 8 Coal Mining | 54.8 | 0 | 54.8 | 2015-12-24 06:54 | 2015-12-25 09:11 | 28669.8288 | [6 empty] | 28670 | 21342 | 1.61 | 0 | 0 | 7.92 | 5632
TS6060#1 | DT\22\007\B | DT | 22 | 7 | B | 8 Coal Mining | 45.2 | 0 | 45.2 | 2015-12-25 09:11 | 2015-12-26 06:53 | 23666.2035 | [6 empty] | 23666 | 17617 | 1.33 | 0 | 0 | 7.92 | 5632
TS5500Exc | SC\24\002\D | SC | 24 | 2 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2015-12-25 23:56 | 2015-12-27 05:58 | 30485.6847 | [6 empty] | 30486 | 23096 | 2.56 | 0 | 0 | 6.42 | 5851
TS6060#1 | DT\23\001\A2 | DT | 23 | 1 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2015-12-26 06:53 | 2015-12-27 01:35 | 20407.4016 | [6 empty] | 20407 | 14253 | 0.9 | 0 | 0 | 19.45 | 4765
TS5500Shv | MW\19\004\D | MW | 19 | 4 | D | 8 Coal Mining | 66.1 | 0 | 40.1 | 2015-12-26 11:58 | 2015-12-27 12:52 | 24479.7151 | [6 empty] | 24480 | 18496 | 1.85 | 0 | 0 | 6.22 | 5866
TS6060#1 | BW\18\004\D | BW | 18 | 4 | D | 8 Coal Mining | 100 | 0 | 18.3 | 2015-12-27 01:35 | 2015-12-27 12:52 | 12305.6208 | [6 empty] | 12306 | 9282 | 0.93 | 0 | 0 | 6 | 5888
TS5500Exc | SC\27\004\B | SC | 27 | 4 | B | 8 Coal Mining | 100 | 0 | 11.6 | 2015-12-27 05:58 | 2015-12-27 12:52 | 7014.3299 | [6 empty] | 7014 | 5192 | 0.44 | 0 | 0 | 8.98 | 5575
TS5500Shv | DT\23\001\B | DT | 23 | 1 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2015-12-27 12:52 | 2015-12-30 01:38 | 52505.66 | 52506 | [7 empty] | 0 | 0 | 3.3 | 11.06 | 5379.69
TS6060#1 | BW\21\001\B | BW | 21 | 1 | B | 1 Prestrip - Thick | 13.3803 | 13.3803 | 13.3803 | 2015-12-27 12:52 | 2015-12-30 15:58 | 62454.1263 | 62454 | [7 empty] | 0 | 0 | 3.2 | 11.09 | 5369.87
TS5500Exc | MW\23\004\A | MW | 23 | 4 | A | 1 Prestrip - Thick | 2.503 | 2.503 | 2.503 | 2015-12-27 12:52 | 2015-12-27 21:40 | 6278.7692 | 6279 | [7 empty] | 0 | 0 | 0.41 | 9.12 | 5545.59
TS5500Exc | MW\23\004\A | MW | 23 | 4 | A | 1 Prestrip - Thick | 97.497 | 27.9672 | 27.9672 | 2015-12-27 21:40 | 2016-01-01 | 70156.9989 | 70157 | [7 empty] | 0 | 0 | 4.56 | 9.12 | 5545.59
DRE2 | MW\19\012\D | MW | 19 | 12 | D | 6 DL | 100 | 92.9954 | 92.9954 | 2015-12-28 02:06 | 2016-01-01 | 273738.8727 |  |  |  | 14074 | 273739 | 220492 |  |  | 0 | 25.14 | 0 | 5.6 | 5919.16
PH4100XPC#1 | MW\20\009\D | MW | 20 | 9 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2015-12-29 01:03 | 2015-12-29 01:03 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | MW\21\010\A | MW | 21 | 10 | A | 1 Prestrip - Thick | 100 | 23.99 | 23.99 | 2015-12-29 01:03 | 2016-01-01 | 117709.329 | 117709 | [7 empty] | 0 | 0 | 7.5 | 13.47 | 5264.68
TS5500Shv | DT\23\004\B | DT | 23 | 4 | B | 1 Prestrip - Thick | 21.1075 | 5.8651 | 5.8651 | 2015-12-30 01:38 | 2016-01-01 | 40170.0051 | 40170 | [7 empty] | 0 | 0 | 2.7 | 9.84 | 5412.99
TS6060#1 | BW\21\002\X2 | BW | 21 | 2 | X2 | 1 Prestrip - Thick | 39.0737 | 0 | 5.4426 | 2015-12-30 15:58 | 2016-01-01 | 26544.3135 | 26544 | [7 empty] | 0 | 0 | 1.58 | 0 | 0
| EOP 24 : 2015\Dec | EOP 24 : 2015 | Dec | [6 empty] | 2016-01-01 | 2016-01-01 |  | 3086680 |  | 73018 | 288161 | 4337892 | 3187124 | 1200000 | 896670 | 80.87 | 0 | 200.83 | 7.94 | 5699.16
TS Fleet 5 | BW\21\002\X2 | BW | 21 | 2 | X2 | 1 Prestrip - Thick | 62.4207 | 0 | 61.0728 | 2016-01-01 | 2016-01-08 03:34 | 297861.5983 | 297862 | [7 empty] | 0 | 0 | 17.7 | 0 | 0
DRE1 | SC\24\006\D | SC | 24 | 6 | D | 6 DL | 100 | 0 | 3.5852 | 2016-01-01 | 2016-01-01 07:33 | 26027.878 |  |  |  | 2188 | 26028 | 17173 |  |  | 0 | 45 | 0 | 5.79 | 5905.45
PH4100A | SC\27\003\B | SC | 27 | 3 | B | 1 Prestrip - Thick | 100 | 43.7529 | 43.7529 | 2016-01-01 | 2016-01-09 04:26 | 314202.8135 | 314203 | [7 empty] | 0 | 0 | 17.6 | 8.93 | 5577.93
TS5500Shv | DT\23\004\B | DT | 23 | 4 | B | 1 Prestrip - Thick | 21.1075 | 15.2424 | 15.2424 | 2016-01-01 | 2016-01-05 08:54 | 104394.5968 | 104395 | [7 empty] | 0 | 0 | 7.01 | 9.84 | 5412.99
DRE2 | MW\19\012\D | MW | 19 | 12 | D | 6 DL | 100 | 7.0046 | 7.0046 | 2016-01-01 | 2016-01-01 06:12 | 20618.6106 |  |  |  | 1060 | 20619 | 16608 |  |  | 0 | 25.14 | 0 | 5.6 | 5919.16
PH4100XPC#1 | MW\21\010\A | MW | 21 | 10 | A | 1 Prestrip - Thick | 100 | 71.9275 | 71.9275 | 2016-01-01 | 2016-01-08 18:30 | 352920.3068 | 352920 | [7 empty] | 0 | 0 | 22.48 | 13.47 | 5264.68
TS6060#1 | BW\21\002\X2 | BW | 21 | 2 | X2 | 1 Prestrip - Thick | 39.0737 | 0 | 33.4846 | 2016-01-01 | 2016-01-08 03:34 | 163309.5371 | 163310 | [7 empty] | 0 | 0 | 9.7 | 0 | 0
TS5500Exc | MW\23\004\A | MW | 23 | 4 | A | 1 Prestrip - Thick | 97.497 | 69.5298 | 69.5298 | 2016-01-01 | 2016-01-09 20:53 | 174418.802 | 174419 | [7 empty] | 0 | 0 | 11.33 | 9.12 | 5545.59
DRE2 | MW\19\013\D | MW | 19 | 13 | D | 6 DL | 100 | 0 | 100 | 2016-01-01 06:12 | 2016-01-03 06:22 | 159830.2312 |  |  |  | 4920 | 159830 | 96002 |  |  | 0 | 18.17 | 0 | 5.82 | 5899.94
DRE1 | SC\24\007\D | SC | 24 | 7 | D | 6 DL | 100 | 0 | 100 | 2016-01-01 07:33 | 2016-01-11 03:30 | 813260.5188 |  |  |  | 61635 | 813261 | 483804 |  |  | 0 | 45 | 0 | 5.51 | 5929.46
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2016-01-03 06:22 | 2016-01-05 06:22
DRE2 | DT\19\003\D | DT | 19 | 3 | D | 6 DL | 100 | 100 | 100 | 2016-01-05 06:22 | 2016-01-10 05:13 | 394465.3135 |  |  |  | 17649 | 394465 | 335340 |  |  | 0 | 21.1 | 0 | 6.6 | 5834.03
TS5500Shv | BW\21\001\B | BW | 21 | 1 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-01-05 08:54 | 2016-01-08 19:48 | 93538.5664 | [6 empty] | 93539 | 68207 | 3.83 | 0 | 0 | 11.09 | 5370
TS Fleet 5 | BW\21\002\B | BW | 21 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-01-08 03:34 | 2016-01-18 02:10 | 414200.8802 | 414201 | [7 empty] | 0 | 0 | 25.61 | 11.57 | 5334.06
TS6060#1 | BW\18\004\D | BW | 18 | 4 | D | 8 Coal Mining | 100 | 0 | 81.7 | 2016-01-08 03:34 | 2016-01-09 23:28 | 54983.5693 | [6 empty] | 54984 | 41475 | 4.15 | 0 | 0 | 6 | 5888
PH4100XPC#1 | MW\22\010\A | MW | 22 | 10 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-01-08 18:30 | 2016-01-20 18:53 | 546337.5093 | 546338 | [7 empty] | 0 | 0 | 31.81 | 12.19 | 5354.68
TS5500Shv | MW\19\004\D | MW | 19 | 4 | D | 8 Coal Mining | 66.1 | 0 | 26 | 2016-01-08 19:48 | 2016-01-09 09:53 | 15898.1841 | [6 empty] | 15898 | 12012 | 1.2 | 0 | 0 | 6.22 | 5866
PH4100A | SC\28\003\B | SC | 28 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-01-09 04:26 | 2016-01-24 11:39 | 587764.0198 | 587764 | [7 empty] | 0 | 0 | 40.91 | 8.94 | 5577.35
TS5500Shv | MW\19\005\D | MW | 19 | 5 | D | 8 Coal Mining | 19.7 | 0 | 19.7 | 2016-01-09 09:53 | 2016-01-09 20:07 | 11535.5053 | [6 empty] | 11536 | 8694 | 0.87 | 0 | 0 | 6.38 | 5851
TS5500Shv | DT\23\004\B | DT | 23 | 4 | B | 1 Prestrip - Thick | 78.8925 | 77.2735 | 77.2735 | 2016-01-09 20:07 | 2016-02-01 | 529242.7044 | 529243 | [7 empty] | 0 | 0 | 35.53 | 9.84 | 5412.99
TS5500Exc | SC\27\004\B | SC | 27 | 4 | B | 8 Coal Mining | 100 | 0 | 88.4 | 2016-01-09 20:53 | 2016-01-11 18:41 | 53373.7282 | [6 empty] | 53374 | 39507 | 3.35 | 0 | 0 | 8.98 | 5575
TS6060#1 | BW\18\003\D | BW | 18 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-01-09 23:28 | 2016-01-12 03:05 | 64637.9183 | [6 empty] | 64638 | 48642 | 4.86 | 0 | 0 | 6.37 | 5854
DRE2 | BW\19\011\D | BW | 19 | 11 | D | 6 DL | 100 | 100 | 100 | 2016-01-10 05:13 | 2016-01-15 18:55 | 443718.3927 |  |  |  | 10731 | 443718 | 203885 |  |  | 0 | 21.47 | 0 | 7.47 | 5757.91
DRE1 | SC\25\012\D | SC | 25 | 12 | D | 6 DL | 100 | 0 | 100 | 2016-01-11 03:30 | 2016-01-27 14:50 | 1362489.159 |  |  |  | 74931 | 1362489 | 591231 |  |  | 0 | 43.52 | 0 | 7.38 | 5763.42
TS5500Exc | SC\24\006\D | SC | 24 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-01-11 18:41 | 2016-01-14 13:28 | 77837.483 | [6 empty] | 77837 | 59016 | 4.92 | 0 | 0 | 5.79 | 5905
TS6060#1 | BW\18\005\D | BW | 18 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-01-12 03:05 | 2016-01-14 07:30 | 65641.0878 | [6 empty] | 65641 | 49714 | 4.97 | 0 | 0 | 5.51 | 5930
TS6060#1 | BW\18\006\D | BW | 18 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-01-14 07:30 | 2016-01-16 11:59 | 65742.718 | [6 empty] | 65743 | 49909 | 4.99 | 0 | 0 | 5.43 | 5937
TS5500Exc | SC\27\005\B | SC | 27 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-01-14 13:28 | 2016-01-16 17:06 | 60185.655 | [6 empty] | 60186 | 44480 | 3.73 | 0 | 0 | 9.06 | 5568
DRE2 | BW\19\010\D | BW | 19 | 10 | D | 6 DL | 100 | 100 | 100 | 2016-01-15 18:55 | 2016-01-21 07:05 | 438685.9005 |  |  |  | 10609 | 438686 | 201573 |  |  | 0 | 21.24 | 0 | 6.56 | 5838.02
TS6060#1 | BW\18\002\D | BW | 18 | 2 | D | 8 Coal Mining | 89.6 | 0 | 89.6 | 2016-01-16 11:59 | 2016-01-18 10:25 | 58142.421 | [6 empty] | 58142 | 43929 | 4.39 | 0 | 0 | 5.88 | 5897
TS5500Exc | SC\28\005\B | SC | 28 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-01-16 17:06 | 2016-01-18 19:33 | 58808.6063 | [6 empty] | 58809 | 43457 | 3.66 | 0 | 0 | 9.08 | 5566
TS Fleet 5 | BW\21\003\X2 | BW | 21 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2016-01-18 02:10 | 2016-01-27 15:51 | 398722.1616 | 398722 | [7 empty] | 0 | 0 | 23.83 | 0 | 0
TS6060#1 | DT\23\001\B | DT | 23 | 1 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-01-18 10:25 | 2016-01-20 17:37 | 69143.5553 | [6 empty] | 69144 | 50501 | 3.2 | 0 | 0 | 11.06 | 5380
TS5500Exc | SC\27\004\D | SC | 27 | 4 | D | 1 Prestrip - Thick | 95.3005 | 95.3005 | 95.3005 | 2016-01-18 19:33 | 2016-01-23 06:00 | 87114.3914 | 87114 | [7 empty] | 0 | 0 | 7.33 | 6.2 | 5868.94
TS6060#1 | DT\19\004\D | DT | 19 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-01-20 17:37 | 2016-01-22 20:16 | 63426.1139 | [6 empty] | 63426 | 47964 | 4.8 | 0 | 0 | 5.51 | 5929
PH4100XPC#1 | MW\21\011\A | MW | 21 | 11 | A | 1 Prestrip - Thick | 100 | 37.9389 | 37.9389 | 2016-01-20 18:53 | 2016-01-25 02:21 | 196661.9592 | 196662 | [7 empty] | 0 | 0 | 12.12 | 11.09 | 5441.26
DRE2 | BW\19\009\D | BW | 19 | 9 | D | 6 DL | 100 | 100 | 100 | 2016-01-21 07:05 | 2016-01-26 18:13 | 435200.8373 |  |  |  | 10525 | 435201 | 199971 |  |  | 0 | 21.07 | 0 | 5.85 | 5898.34
TS6060#1 | DT\19\005\D | DT | 19 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-01-22 20:16 | 2016-01-24 22:04 | 62377.1131 | [6 empty] | 62377 | 47320 | 4.67 | 0 | 0 | 5.41 | 5937
TS5500Exc | SC\27\004\D | SC | 27 | 4 | D | 1 Prestrip - Thick | 4.6995 | 4.6995 | 4.6995 | 2016-01-23 06:00 | 2016-01-23 11:15 | 4295.8455 | 4296 | [7 empty] | 0 | 0 | 0.36 | 6.2 | 5868.94
TS5500Exc | SC\24\007\D | SC | 24 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-01-23 11:15 | 2016-01-26 04:39 | 76243.6157 | [6 empty] | 76244 | 58323 | 4.86 | 0 | 0 | 5.51 | 5929
PH4100A | SC\27\011\D | SC | 27 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-01-24 11:39 | 2016-01-28 20:18 | 166408.3567 | 166408 | [7 empty] | 0 | 0 | 14.13 | 7.36 | 5766.67
TS6060#1 | DT\23\002\A2 | DT | 23 | 2 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2016-01-24 22:04 | 2016-01-25 22:24 | 30464.7693 | [6 empty] | 30465 | 21556 | 1.41 | 0 | 0 | 16.97 | 4982
PH4100XPC#1 | MW\22\011\A | MW | 22 | 11 | A | 1 Prestrip - Thick | 100 | 55.5211 | 55.5211 | 2016-01-25 02:21 | 2016-02-01 | 315267.0554 | 315267 | [7 empty] | 0 | 0 | 19.54 | 11.13 | 5438.08
TS6060#1 | BW\18\002\D | BW | 18 | 2 | D | 8 Coal Mining | 10.4 | 0 | 10.4 | 2016-01-25 22:24 | 2016-01-26 03:46 | 6717.8398 | [6 empty] | 6718 | 5076 | 0.51 | 0 | 0 | 5.88 | 5897
TS6060#1 | BW\18\007\D | BW | 18 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-01-26 03:46 | 2016-01-28 07:41 | 65034.8092 | [6 empty] | 65035 | 49373 | 4.94 | 0 | 0 | 5.62 | 5921
TS5500Exc | SC\28\004\B | SC | 28 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-01-26 04:39 | 2016-01-28 09:17 | 61340.763 | [6 empty] | 61341 | 45403 | 3.78 | 0 | 0 | 8.99 | 5574
DRE2 | BW\19\008\D | BW | 19 | 8 | D | 6 DL | 100 | 89.69 | 89.69 | 2016-01-26 18:13 | 2016-02-01 | 417435.1142 |  |  |  | 10095 | 417435 | 191808 |  |  | 0 | 22.53 | 0 | 5.85 | 5900.86
DRE1 | SC\25\011\D | SC | 25 | 11 | D | 6 DL | 100 | 0 | 53.4864 | 2016-01-27 14:50 | 2016-02-01 | 362455.6439 |  |  |  | 27563 | 362456 | 248069 |  |  | 0 | 42.99 | 0 | 7.3 | 5772.51
TS Fleet 5 | BW\21\003\B | BW | 21 | 3 | B | 1 Prestrip - Thick | 56.1831 | 43.1676 | 43.1676 | 2016-01-27 15:51 | 2016-02-01 | 180799.36 | 180799 | [7 empty] | 0 | 0 | 11.34 | 11.5 | 5348.34
TS6060#1 | BW\21\003\B | BW | 21 | 3 | B | 1 Prestrip - Thick | 100 | 20.1297 | 20.1297 | 2016-01-28 07:41 | 2016-02-01 | 84309.5242 | 84310 | [7 empty] | 0 | 0 | 5.29 | 11.5 | 5348.34
TS5500Exc | BW\21\003\B | BW | 21 | 3 | B | 1 Prestrip - Thick | 100 | 16.9435 | 16.9435 | 2016-01-28 09:17 | 2016-02-01 | 70964.5233 | 70965 | [7 empty] | 0 | 0 | 4.45 | 11.5 | 5348.34
PH4100A | SC\28\011\D | SC | 28 | 11 | D | 1 Prestrip - Thick | 100 | 68.8179 | 68.8179 | 2016-01-28 20:18 | 2016-02-01 | 120467.4807 | 120467 | [7 empty] | 0 | 0 | 10.19 | 7.41 | 5762.43
| EOP 25 : 2016\Jan | EOP 25 : 2016 | Jan | [6 empty] | 2016-02-01 | 2016-02-01 |  | 5109663 |  |  | 231906 | 4874188 | 2585464 | 1115074 | 834556 | 73.09 | 0 | 328.25 | 7.86 | 5704.7
TS Fleet 5 | BW\21\003\B | BW | 21 | 3 | B | 1 Prestrip - Thick | 56.1831 | 9.8124 | 9.8124 | 2016-02-01 | 2016-02-02 00:03 | 41097.2868 | 41097 | [7 empty] | 0 | 0 | 2.58 | 11.5 | 5348.34
DRE1 | SC\25\011\D | SC | 25 | 11 | D | 6 DL | 100 | 0 | 46.5136 | 2016-02-01 | 2016-02-04 15:53 | 315204.0908 |  |  |  | 23970 | 315204 | 215729 |  |  | 0 | 42.99 | 0 | 7.3 | 5772.51
PH4100A | SC\28\011\D | SC | 28 | 11 | D | 1 Prestrip - Thick | 100 | 31.1821 | 31.1821 | 2016-02-01 | 2016-02-02 09:46 | 54585.0313 | 54585 | [7 empty] | 0 | 0 | 4.62 | 7.41 | 5762.43
TS5500Shv | DT\23\004\B | DT | 23 | 4 | B | 1 Prestrip - Thick | 78.8925 | 1.619 | 1.619 | 2016-02-01 | 2016-02-01 11:19 | 11088.2223 | 11088 | [7 empty] | 0 | 0 | 0.74 | 9.84 | 5412.99
DRE2 | BW\19\008\D | BW | 19 | 8 | D | 6 DL | 100 | 10.31 | 10.31 | 2016-02-01 | 2016-02-01 13:53 | 47985.0115 |  |  |  | 1160 | 47985 | 22049 |  |  | 0 | 22.53 | 0 | 5.85 | 5900.86
PH4100XPC#1 | MW\22\011\A | MW | 22 | 11 | A | 1 Prestrip - Thick | 100 | 44.4789 | 44.4789 | 2016-02-01 | 2016-02-06 10:41 | 252565.7382 | 252566 | [7 empty] | 0 | 0 | 15.65 | 11.13 | 5438.08
TS6060#1 | BW\21\003\B | BW | 21 | 3 | B | 1 Prestrip - Thick | 100 | 5.3968 | 5.3968 | 2016-02-01 | 2016-02-02 00:03 | 22603.5078 | 22604 | [7 empty] | 0 | 0 | 1.42 | 11.5 | 5348.34
TS5500Exc | BW\21\003\B | BW | 21 | 3 | B | 1 Prestrip - Thick | 100 | 4.55 | 4.55 | 2016-02-01 | 2016-02-02 00:03 | 19056.8215 | 19057 | [7 empty] | 0 | 0 | 1.2 | 11.5 | 5348.34
TS5500Shv | DT\23\002\B | DT | 23 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-02-01 11:19 | 2016-02-03 19:09 | 54494.353 | 54494 | [7 empty] | 0 | 0 | 3.58 | 11.12 | 5359.57
DRE2 | BW\19\007\D | BW | 19 | 7 | D | 6 DL | 100 | 100 | 100 | 2016-02-01 13:53 | 2016-02-07 06:18 | 471115.9013 |  |  |  | 11393 | 471116 | 216474 |  |  | 0 | 22.74 | 0 | 5.54 | 5927.19
TS Fleet 5 | BW\21\004\X1 | BW | 21 | 4 | X1 | 1 Prestrip - Thick | 6.6951 | 6.6951 | 6.6951 | 2016-02-02 00:03 | 2016-02-02 13:08 | 22329.2767 | 22329 | [7 empty] | 0 | 0 | 1.35 | 12.63 | 5252.78
TS6060#1 | BW\18\001\D | BW | 18 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-02-02 00:03 | 2016-02-03 19:44 | 53831.6831 | [6 empty] | 53832 | 40768 | 5.08 | 0 | 0 | 5.67 | 5916
TS5500Exc | MW\19\008\D | MW | 19 | 8 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2016-02-02 00:03 | 2016-02-03 01:24 | 28598.7932 | [6 empty] | 28599 | 21554 | 2.16 | 0 | 0 | 6.09 | 5876
PH4100A | SC\27\012\D | SC | 27 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-02-02 09:46 | 2016-02-07 01:16 | 180727.0591 | 180727 | [7 empty] | 0 | 0 | 15.34 | 7.46 | 5757
TS Fleet 5 | BW\21\004\X1 | BW | 21 | 4 | X1 | 1 Prestrip - Thick | 93.3049 | 93.3049 | 93.3049 | 2016-02-02 13:08 | 2016-02-10 03:19 | 311186.1605 | 311186 | [7 empty] | 0 | 0 | 18.8 | 12.63 | 5252.78
TS5500Exc | MW\19\009\D | MW | 19 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-02-03 01:24 | 2016-02-05 05:39 | 58932.5243 | [6 empty] | 58933 | 44451 | 4.44 | 0 | 0 | 6.1 | 5875
TS5500Shv | MW\21\011\A | MW | 21 | 11 | A | 8 Coal Mining | 100 | 0 | 100 | 2016-02-03 19:09 | 2016-02-06 18:29 | 79197.2892 | [6 empty] | 79197 | 57897 | 3.63 | 0 | 0 | 11.09 | 5441
TS6060#1 | BW\18\008\D | BW | 18 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-02-03 19:44 | 2016-02-06 01:33 | 66306.8635 | [6 empty] | 66307 | 50137 | 5.01 | 0 | 0 | 5.9 | 5896
DRE1 | SC\25\010\D | SC | 25 | 10 | D | 6 DL | 100 | 0 | 100 | 2016-02-04 15:53 | 2016-02-13 01:23 | 722647.5012 |  |  |  | 60742 | 722648 | 476802 |  |  | 0 | 45 | 0 | 6.93 | 5804.67
TS5500Exc | MW\19\010\D | MW | 19 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-02-05 05:39 | 2016-02-07 09:45 | 58774.0277 | [6 empty] | 58774 | 44330 | 4.43 | 0 | 0 | 5.93 | 5890
TS6060#1 | BW\20\003\B | BW | 20 | 3 | B | 8 Coal Mining | 75.8 | 0 | 75.8 | 2016-02-06 01:33 | 2016-02-08 03:32 | 61578.5505 | [6 empty] | 61579 | 44685 | 2.79 | 0 | 0 | 11.65 | 5323
PH4100XPC#1 | MW\21\012\A | MW | 21 | 12 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-02-06 10:41 | 2016-02-21 07:39 | 693862.483 | 693862 | [7 empty] | 0 | 0 | 32.6 | 10.31 | 5490.38
TS5500Shv | MW\21\011\B | MW | 21 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-02-06 18:29 | 2016-02-08 09:29 | 38063.355 | 38063 | [7 empty] | 0 | 0 | 2.38 | 16.58 | 5010.57
PH4100A | SC\28\012\D | SC | 28 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-02-07 01:16 | 2016-02-11 23:00 | 190991.0643 | 190991 | [7 empty] | 0 | 0 | 16.22 | 7.5 | 5753.14
DRE2 | BW\19\006\D | BW | 19 | 6 | D | 6 DL | 100 | 100 | 100 | 2016-02-07 06:18 | 2016-02-13 21:37 | 550159.404 |  |  |  | 10003 | 550159 | 240071 |  |  | 0 | 24.98 | 0 | 5.45 | 5935.62
TS5500Exc | MW\19\011\D | MW | 19 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-02-07 09:45 | 2016-02-09 12:53 | 57677.5249 | [6 empty] | 57678 | 43607 | 4.36 | 0 | 0 | 5.66 | 5913
TS6060#1 | DT\23\002\B | DT | 23 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-02-08 03:32 | 2016-02-10 07:18 | 63789.7209 | [6 empty] | 63790 | 46479 | 3.09 | 0 | 0 | 11.12 | 5360
TS5500Shv | MW\21\011\B | MW | 21 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-02-08 09:29 | 2016-02-11 16:55 | 88176.0401 | [6 empty] | 88176 | 62935 | 3.94 | 0 | 0 | 16.58 | 5011
TS5500Exc | MW\19\012\D | MW | 19 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-02-09 12:53 | 2016-02-11 16:34 | 58296.7368 | [6 empty] | 58297 | 44147 | 4.41 | 0 | 0 | 5.6 | 5919
TS Fleet 5 | BW\21\005\X2 | BW | 21 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2016-02-10 03:19 | 2016-02-21 13:58 | 469083.7948 | 469084 | [7 empty] | 0 | 0 | 28.93 | 0 | 0
TS6060#1 | BW\20\003\B | BW | 20 | 3 | B | 8 Coal Mining | 24.2 | 0 | 24.2 | 2016-02-10 07:18 | 2016-02-10 23:17 | 19692.349 | [6 empty] | 19692 | 14290 | 0.89 | 0 | 0 | 11.65 | 5323
TS6060#1 | BW\20\005\B | BW | 20 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-02-10 23:17 | 2016-02-13 20:18 | 85043.809 | [6 empty] | 85044 | 62187 | 3.9 | 0 | 0 | 10.27 | 5476
TS5500Exc | SC\25\012\D | SC | 25 | 12 | D | 7 PostStrip | 100 | 0 | 100 | 2016-02-11 16:34 | 2016-02-16 01:34 | 83151.2711 |  |  | 83151 | [5 empty] | 0 | 0 | 0 | 7.38 | 5763.42
TS5500Shv | MW\19\005\D | MW | 19 | 5 | D | 8 Coal Mining | 27.5 | 0 | 27.5 | 2016-02-11 16:55 | 2016-02-12 07:26 | 16113.1509 | [6 empty] | 16113 | 12144 | 1.21 | 0 | 0 | 6.38 | 5851
PH4100A | SC\27\013\D | SC | 27 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-02-11 23:00 | 2016-02-16 05:42 | 164842.4579 | 164842 | [7 empty] | 0 | 0 | 16.4 | 7.44 | 5758.53
TS5500Shv | MW\19\005\D | MW | 19 | 5 | D | 8 Coal Mining | 32.6 | 0 | 32.6 | 2016-02-12 07:26 | 2016-02-13 00:39 | 19121.2429 | [6 empty] | 19121 | 14411 | 1.44 | 0 | 0 | 6.38 | 5851
TS5500Shv | MW\19\006\D | MW | 19 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-02-13 00:39 | 2016-02-15 07:16 | 60634.5067 | [6 empty] | 60635 | 45554 | 4.56 | 0 | 0 | 6.35 | 5854
DRE1 | SC\25\009\D | SC | 25 | 9 | D | 6 DL | 100 | 0 | 100 | 2016-02-13 01:23 | 2016-02-21 11:48 | 725911.4303 |  |  |  | 61017 | 725911 | 478955 |  |  | 0 | 45 | 0 | 6.33 | 5857.5
TS6060#1 | DT\19\003\D | DT | 19 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-02-13 20:18 | 2016-02-17 11:23 | 107306.7314 | [6 empty] | 107307 | 80632 | 4.85 | 0 | 0 | 6.6 | 5834
DRE2 | BW\19\005\D | BW | 19 | 5 | D | 6 DL | 100 | 100 | 100 | 2016-02-13 21:37 | 2016-02-19 21:58 | 498509.1193 |  |  |  | 12056 | 498509 | 229061 |  |  | 0 | 24.14 | 0 | 5.58 | 5924.54
TS5500Shv | MW\19\007\D | MW | 19 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-02-15 07:16 | 2016-02-17 12:31 | 59127.8118 | [6 empty] | 59128 | 44420 | 4.44 | 0 | 0 | 6.14 | 5871
TS5500Exc | SC\25\012\D | SC | 25 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-02-16 01:34 | 2016-02-19 12:40 | 93743.5716 | [6 empty] | 93744 | 69727 | 4.55 | 0 | 0 | 7.38 | 5763
PH4100A | SC\28\013\D | SC | 28 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-02-16 05:42 | 2016-02-21 09:52 | 199502.7789 | 199503 | [7 empty] | 0 | 0 | 16.02 | 7.47 | 5756.18
TS6060#1 | MW\19\013\D | MW | 19 | 13 | D | 7 PostStrip | 100 | 0 | 100 | 2016-02-17 11:23 | 2016-02-18 10:52 | 22065.5553 |  |  | 22066 | [5 empty] | 0 | 0 | 0 | 5.82 | 5899.94
TS5500Shv | MW\19\008\D | MW | 19 | 8 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2016-02-17 12:31 | 2016-02-18 16:10 | 30698.9939 | [6 empty] | 30699 | 23137 | 2.31 | 0 | 0 | 6.09 | 5876
TS6060#1 | BW\21\002\B | BW | 21 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-02-18 10:52 | 2016-02-21 06:04 | 82802.7633 | [6 empty] | 82803 | 60150 | 3.74 | 0 | 0 | 11.57 | 5334
TS5500Shv | MW\19\013\D | MW | 19 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-02-18 16:10 | 2016-02-19 11:25 | 21368.3981 | [6 empty] | 21368 | 16169 | 4.43 | 0 | 0 | 5.82 | 5900
TS5500Shv | MW\20\003\B | MW | 20 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-02-19 11:25 | 2016-02-21 21:53 | 64911.6834 | [6 empty] | 64912 | 48232 | 3.09 | 0 | 0 | 8.27 | 5621
TS5500Exc | SC\25\011\D | SC | 25 | 11 | D | 8 Coal Mining | 40.6 | 0 | 40.6 | 2016-02-19 12:40 | 2016-02-20 16:50 | 31771.1729 | [6 empty] | 31771 | 23690 | 1.97 | 0 | 0 | 7.3 | 5773
DRE2 | BW\19\004\D | BW | 19 | 4 | D | 6 DL | 100 | 100 | 100 | 2016-02-19 21:58 | 2016-02-25 19:54 | 490181.1832 |  |  |  | 11854 | 490181 | 225234 |  |  | 0 | 23.69 | 0 | 6.09 | 5880.64
TS5500Exc | SC\25\010\D | SC | 25 | 10 | D | 8 Coal Mining | 100 | 0 | 44.4 | 2016-02-20 16:50 | 2016-02-21 23:19 | 34380.8309 | [6 empty] | 34381 | 25757 | 2.15 | 0 | 0 | 6.93 | 5805
TS6060#1 | BW\19\011\D | BW | 19 | 11 | D | 8 Coal Mining | 100 | 0 | 32.3 | 2016-02-21 06:04 | 2016-02-21 23:19 | 21245.8067 | [6 empty] | 21246 | 15925 | 1.59 | 0 | 0 | 7.47 | 5758
PH4100XPC#1 | MW\22\012\A | MW | 22 | 12 | A | 1 Prestrip - Thick | 100 | 59.8732 | 59.8732 | 2016-02-21 07:39 | 2016-03-01 | 405850.0069 | 405850 | [7 empty] | 0 | 0 | 21.59 | 10.62 | 5469.76
PH4100A | SC\27\008\D | SC | 27 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-02-21 09:52 | 2016-02-25 03:48 | 147195.2248 | 147195 | [7 empty] | 0 | 0 | 12.18 | 5.87 | 5897.73
DRE1 | SC\25\008\D | SC | 25 | 8 | D | 6 DL | 100 | 0 | 89.2644 | 2016-02-21 11:48 | 2016-03-01 | 732284.3778 |  |  |  | 55550 | 732284 | 436043 |  |  | 0 | 45 | 0 | 5.7 | 5912.83
TS Fleet 5 | BW\21\005\B | BW | 21 | 5 | B | 1 Prestrip - Thick | 80.1486 | 76.2166 | 69.186 | 2016-02-21 13:58 | 2016-02-29 13:40 | 327450.3272 | 327450 | [7 empty] | 0 | 0 | 20.37 | 10.39 | 5475.26
TS5500Shv | MW\21\012\A | MW | 21 | 12 | A | 8 Coal Mining | 100 | 0 | 1.5 | 2016-02-21 21:53 | 2016-02-21 23:19 | 1577.4233 | [6 empty] | 1577 | 1160 | 0.06 | 0 | 0 | 10.31 | 5490
TS5500Shv | DT\23\005\A | DT | 23 | 5 | A | 1 Prestrip - Thick | 18.7697 | 18.7697 | 18.7697 | 2016-02-21 23:19 | 2016-02-26 23:08 | 116616.1321 | 116616 | [7 empty] | 0 | 0 | 8.09 | 12.91 | 5221.57
TS6060#1 | BW\21\005\B | BW | 21 | 5 | B | 1 Prestrip - Thick | 23.7834 | 23.7834 | 23.7834 | 2016-02-21 23:19 | 2016-02-26 23:08 | 112564.2518 | 112564 | [7 empty] | 0 | 0 | 7 | 10.39 | 5475.26
TS5500Exc | MW\23\005\A | MW | 23 | 5 | A | 1 Prestrip - Thick | 1.5114 | 1.5114 | 1.5114 | 2016-02-21 23:19 | 2016-02-22 05:57 | 5295.5667 | 5296 | [7 empty] | 0 | 0 | 0.34 | 10.59 | 5430.08
TS5500Exc | MW\23\005\A | MW | 23 | 5 | A | 1 Prestrip - Thick | 98.4886 | 42.3016 | 42.3016 | 2016-02-22 05:57 | 2016-03-01 | 148217.5006 | 148218 | [7 empty] | 0 | 0 | 9.49 | 10.59 | 5430.08
PH4100A | SC\28\008\D | SC | 28 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-02-25 03:48 | 2016-02-29 08:45 | 165231.12 | 165231 | [7 empty] | 0 | 0 | 13.73 | 6.04 | 5883.45
DRE2 | BW\19\003\D | BW | 19 | 3 | D | 6 DL | 100 | 73.0527 | 73.0527 | 2016-02-25 19:54 | 2016-03-01 | 345650.5807 |  |  |  | 8359 | 345651 | 158824 |  |  | 0 | 22.87 | 0 | 6.6 | 5834.35
TS5500Shv | DT\23\005\A | DT | 23 | 5 | A | 1 Prestrip - Thick | 81.2303 | 11.4121 | 11.4121 | 2016-02-26 23:08 | 2016-03-01 | 70903.4767 | 70903 | [7 empty] | 0 | 0 | 4.92 | 12.91 | 5221.57
TS6060#1 | BW\21\005\B | BW | 21 | 5 | B | 1 Prestrip - Thick | 7.0306 | 0 | 7.0306 | 2016-02-26 23:08 | 2016-02-28 10:34 | 33275.0026 | 33275 | [7 empty] | 0 | 0 | 2.07 | 10.39 | 5475.26
TS6060#1 | BW\21\007\B | BW | 21 | 7 | B | 1 Prestrip - Thick | 7.3172 | 4.0497 | 4.0497 | 2016-02-28 10:34 | 2016-03-01 | 34642.9665 | 34643 | [7 empty] | 0 | 0 | 2.43 | 11.82 | 5379.13
PH4100A | SC\27\007\D | SC | 27 | 7 | D | 1 Prestrip - Thick | 100 | 13.7006 | 13.7006 | 2016-02-29 08:45 | 2016-03-01 | 24949.8619 | 24950 | [7 empty] | 0 | 0 | 2.08 | 5.7 | 5912.53
TS Fleet 5 | BW\21\006\B | BW | 21 | 6 | B | 1 Prestrip - Thick | 26.7653 | 2.1896 | 2.1896 | 2016-02-29 13:40 | 2016-03-01 | 17621.1539 | 17621 | [7 empty] | 0 | 0 | 1.07 | 10.91 | 5442.71
| EOP 26 : 2016\Feb | EOP 26 : 2016 | Feb | [6 empty] | 2016-03-01 | 2016-03-01 |  | 4335892 |  | 105217 | 256105 | 4899649 | 2699242 | 1424700 | 1058577 | 88.54 | 0 | 283.18 | 8.24 | 5680.31
TS Fleet 5 | BW\21\006\B | BW | 21 | 6 | B | 1 Prestrip - Thick | 26.7653 | 24.5757 | 24.5757 | 2016-03-01 | 2016-03-05 09:25 | 197774.0267 | 197774 | [7 empty] | 0 | 0 | 12.01 | 10.91 | 5442.71
DRE1 | SC\25\008\D | SC | 25 | 8 | D | 6 DL | 100 | 0 | 10.7356 | 2016-03-01 | 2016-03-02 00:52 | 88070.0805 |  |  |  | 6681 | 88070 | 52442 |  |  | 0 | 45 | 0 | 5.7 | 5912.83
PH4100A | SC\27\007\D | SC | 27 | 7 | D | 1 Prestrip - Thick | 100 | 86.2994 | 86.2994 | 2016-03-01 | 2016-03-04 19:50 | 157157.9115 | 157158 | [7 empty] | 0 | 0 | 13.09 | 5.7 | 5912.53
TS5500Shv | DT\23\005\A | DT | 23 | 5 | A | 1 Prestrip - Thick | 81.2303 | 69.8182 | 69.8182 | 2016-03-01 | 2016-03-17 21:48 | 433780.2262 | 433780 | [7 empty] | 0 | 0 | 30.11 | 12.91 | 5221.57
DRE2 | BW\19\003\D | BW | 19 | 3 | D | 6 DL | 100 | 26.9473 | 26.9473 | 2016-03-01 | 2016-03-02 13:24 | 127501.4713 |  |  |  | 3083 | 127501 | 58586 |  |  | 0 | 22.87 | 0 | 6.6 | 5834.35
PH4100XPC#1 | MW\22\012\A | MW | 22 | 12 | A | 1 Prestrip - Thick | 100 | 40.1268 | 40.1268 | 2016-03-01 | 2016-03-06 13:33 | 271998.803 | 271999 | [7 empty] | 0 | 0 | 14.47 | 10.62 | 5469.76
TS6060#1 | BW\21\007\B | BW | 21 | 7 | B | 1 Prestrip - Thick | 7.3172 | 3.2676 | 3.2676 | 2016-03-01 | 2016-03-02 03:29 | 27952.6428 | 27953 | [7 empty] | 0 | 0 | 1.96 | 11.82 | 5379.13
TS5500Exc | MW\23\005\A | MW | 23 | 5 | A | 1 Prestrip - Thick | 98.4886 | 56.187 | 56.187 | 2016-03-01 | 2016-03-10 05:16 | 196869.7068 | 196870 | [7 empty] | 0 | 0 | 12.6 | 10.59 | 5430.08
DRE1 | SC\25\002\D | SC | 25 | 2 | D | 6 DL | 100 | 0 | 100 | 2016-03-02 00:52 | 2016-03-08 16:05 | 563575.4966 |  |  |  | 34201 | 563575 | 234831 |  |  | 0 | 45 | 0 | 6.39 | 5853.4
TS6060#1 | BW\19\011\D | BW | 19 | 11 | D | 8 Coal Mining | 100 | 0 | 67.7 | 2016-03-02 03:29 | 2016-03-03 12:25 | 44569.3206 | [6 empty] | 44569 | 33407 | 3.34 | 0 | 0 | 7.47 | 5758
DRE2 | BW\19\002\D | BW | 19 | 2 | D | 6 DL | 100 | 100 | 100 | 2016-03-02 13:24 | 2016-03-08 00:03 | 445363.4093 |  |  |  | 10771 | 445363 | 204641 |  |  | 0 | 21.57 | 0 | 6.11 | 5876.71
TS6060#1 | MW\22\011\A | MW | 22 | 11 | A | 8 Coal Mining | 100 | 0 | 100 | 2016-03-03 12:25 | 2016-03-05 23:52 | 80460.7548 | [6 empty] | 80461 | 58763 | 3.64 | 0 | 0 | 11.13 | 5438
PH4100A | SC\28\007\D | SC | 28 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-03-04 19:50 | 2016-03-09 06:04 | 181795.0554 | 181795 | [7 empty] | 0 | 0 | 15.15 | 5.81 | 5903.03
TS Fleet 5 | BW\21\006\B | BW | 21 | 6 | B | 1 Prestrip - Thick | 73.2347 | 73.2347 | 73.2347 | 2016-03-05 09:25 | 2016-03-18 11:34 | 589360.5724 | 589361 | [7 empty] | 0 | 0 | 35.8 | 10.91 | 5442.71
TS6060#1 | DT\23\004\B | DT | 23 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-03-05 23:52 | 2016-03-07 22:11 | 62685.4292 | [6 empty] | 62685 | 45882 | 2.87 | 0 | 0 | 9.84 | 5413
PH4100XPC#1 | MW\22\011\B | MW | 22 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-03-06 13:33 | 2016-03-07 06:49 | 38516.0084 | 38516 | [7 empty] | 0 | 0 | 2.39 | 18.83 | 4826.12
PH4100XPC#1 | BW\22\011\A2 | BW | 22 | 11 | A2 | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-03-07 06:49 | 2016-03-18 10:03 | 621759.9905 | 621760 | [7 empty] | 0 | 0 | 32.72 | 19.79 | 4659.31
TS6060#1 | BW\19\009\D | BW | 19 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-03-07 22:11 | 2016-03-09 19:36 | 61453.6141 | [6 empty] | 61454 | 46360 | 4.64 | 0 | 0 | 5.85 | 5898
DRE2 | BW\19\001\D | BW | 19 | 1 | D | 6 DL | 100 | 100 | 100 | 2016-03-08 00:03 | 2016-03-13 12:20 | 450858.9664 |  |  |  | 7092 | 450859 | 129156 |  |  | 0 | 21.59 | 0 | 5.79 | 5905.18
DRE1 | SC\25\003\D | SC | 25 | 3 | D | 6 DL | 100 | 0 | 100 | 2016-03-08 16:05 | 2016-03-17 04:43 | 724348.7102 |  |  |  | 60885 | 724349 | 477924 |  |  | 0 | 45 | 0 | 6.29 | 5860.53
PH4100A | SC\27\006\D | SC | 27 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-03-09 06:04 | 2016-03-13 15:30 | 180402.5889 | 180403 | [7 empty] | 0 | 0 | 15.05 | 5.84 | 5900.35
TS6060#1 | BW\19\010\D | BW | 19 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-03-09 19:36 | 2016-03-11 19:47 | 65207.1376 | [6 empty] | 65207 | 48954 | 4.9 | 0 | 0 | 6.56 | 5838
TS5500Exc | SC\25\008\D | SC | 25 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-03-10 05:16 | 2016-03-12 18:12 | 76733.1197 | [6 empty] | 76733 | 58507 | 4.88 | 0 | 0 | 5.7 | 5913
TS6060#1 | BW\21\003\B | BW | 21 | 3 | B | 8 Coal Mining | 2.6 | 0 | 2.6 | 2016-03-11 19:47 | 2016-03-11 21:20 | 2101.8197 | [6 empty] | 2102 | 1526 | 0.1 | 0 | 0 | 11.5 | 5348
TS6060#1 | BW\21\003\B | BW | 21 | 3 | B | 8 Coal Mining | 66.3 | 0 | 66.3 | 2016-03-11 21:20 | 2016-03-13 13:11 | 53926.7098 | [6 empty] | 53927 | 39157 | 2.45 | 0 | 0 | 11.5 | 5348
TS5500Exc | SC\25\009\D | SC | 25 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-03-12 18:12 | 2016-03-15 07:52 | 77687.3608 | [6 empty] | 77687 | 58667 | 4.89 | 0 | 0 | 6.33 | 5858
DRE2 | DT\20\004\D | DT | 20 | 4 | D | 6 DL | 100 | 100 | 100 | 2016-03-13 12:20 | 2016-03-19 13:50 | 495957.5465 |  |  |  | 21630 | 495958 | 357850 |  |  | 0 | 23.7 | 0 | 5.6 | 5921.19
TS6060#1 | BW\19\008\D | BW | 19 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-03-13 13:11 | 2016-03-15 14:52 | 67261.4545 | [6 empty] | 67261 | 50899 | 5.09 | 0 | 0 | 5.85 | 5901
PH4100A | SC\28\006\D | SC | 28 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-03-13 15:30 | 2016-03-17 22:44 | 176648.2692 | 176648 | [7 empty] | 0 | 0 | 14.74 | 5.91 | 5894.61
TS5500Exc | SC\25\010\D | SC | 25 | 10 | D | 8 Coal Mining | 100 | 0 | 55.6 | 2016-03-15 07:52 | 2016-03-16 18:00 | 42995.1074 | [6 empty] | 42995 | 32211 | 2.68 | 0 | 0 | 6.93 | 5805
TS6060#1 | BW\21\003\B | BW | 21 | 3 | B | 8 Coal Mining | 31.1 | 0 | 31.1 | 2016-03-15 14:52 | 2016-03-16 09:32 | 25253.848 | [6 empty] | 25254 | 18337 | 1.15 | 0 | 0 | 11.5 | 5348
TS6060#1 | BW\19\007\D | BW | 19 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-03-16 09:32 | 2016-03-18 09:15 | 64578.2742 | [6 empty] | 64578 | 49066 | 4.91 | 0 | 0 | 5.54 | 5927
TS5500Exc | SC\25\002\D | SC | 25 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2016-03-16 18:00 | 2016-03-18 08:02 | 33628.9808 |  |  | 33629 | [5 empty] | 0 | 0 | 0 | 6.39 | 5853.4
DRE1 | SC\25\004\D | SC | 25 | 4 | D | 6 DL | 100 | 0 | 100 | 2016-03-17 04:43 | 2016-03-25 17:24 | 724501.0844 |  |  |  | 60898 | 724501 | 478025 |  |  | 0 | 45 | 0 | 6.13 | 5875.57
TS5500Shv | MW\21\012\A | MW | 21 | 12 | A | 8 Coal Mining | 100 | 0 | 98.5 | 2016-03-17 21:48 | 2016-03-21 09:20 | 101856.9043 | [6 empty] | 101857 | 74894 | 3.6 | 0 | 0 | 10.31 | 5490
PH4100A | SC\27\005\D | SC | 27 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-03-17 22:44 | 2016-03-21 22:27 | 163814.1558 | 163814 | [7 empty] | 0 | 0 | 13.7 | 6.08 | 5880.25
TS5500Exc | SC\25\002\D | SC | 25 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-03-18 08:02 | 2016-03-19 17:31 | 42185.6429 | [6 empty] | 42186 | 32012 | 5.02 | 0 | 0 | 6.39 | 5853
TS6060#1 | BW\21\004\X1 | BW | 21 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2016-03-18 09:15 | 2016-03-19 04:15 | 25719.8137 | [6 empty] | 25720 | 18729 | 1.12 | 0 | 0 | 12.63 | 5253
PH4100XPC#1 | BW\21\010\A2 | BW | 21 | 10 | A2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2016-03-18 10:03 | 2016-03-25 19:25 | 395258.2074 | 395258 | [7 empty] | 0 | 0 | 25.43 | 0 | 0
TS Fleet 5 | BW\21\007\B | BW | 21 | 7 | B | 1 Prestrip - Thick | 80.8931 | 71.1446 | 71.1446 | 2016-03-18 11:34 | 2016-04-01 | 608609.4009 | 608609 | [7 empty] | 0 | 0 | 42.72 | 11.82 | 5379.13
TS6060#1 | BW\21\004\X2 | BW | 21 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2016-03-19 04:15 | 2016-03-25 08:42 | 153172.58 | 153173 | [7 empty] | 0 | 0 | 9.27 | 0 | 0
DRE2 | DT\20\005\D | DT | 20 | 5 | D | 6 DL | 100 | 100 | 100 | 2016-03-19 13:50 | 2016-03-24 06:17 | 383286.0781 |  |  |  | 16716 | 383286 | 276554 |  |  | 0 | 24.29 | 0 | 5.44 | 5935.03
TS5500Exc | SC\25\011\D | SC | 25 | 11 | D | 8 Coal Mining | 2.3 | 0 | 2.3 | 2016-03-19 17:31 | 2016-03-19 18:55 | 1770.1172 | [6 empty] | 1770 | 1320 | 0.11 | 0 | 0 | 7.3 | 5773
TS5500Exc | SC\25\003\D | SC | 25 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-03-19 18:55 | 2016-03-22 07:26 | 76207.7656 | [6 empty] | 76208 | 57734 | 4.81 | 0 | 0 | 6.29 | 5861
TS5500Shv | MW\21\012\B | MW | 21 | 12 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-03-21 09:20 | 2016-03-23 12:27 | 54810.1239 | 54810 | [7 empty] | 0 | 0 | 2.66 | 14.52 | 5172.04
PH4100A | SC\28\005\D | SC | 28 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-03-21 22:27 | 2016-03-25 12:04 | 146497.0403 | 146497 | [7 empty] | 0 | 0 | 12.27 | 6.07 | 5880.26
TS5500Exc | SC\25\011\D | SC | 25 | 11 | D | 8 Coal Mining | 57.1 | 0 | 57.1 | 2016-03-22 07:26 | 2016-03-23 18:56 | 44717.5218 | [6 empty] | 44718 | 33343 | 2.78 | 0 | 0 | 7.3 | 5773
TS5500Shv | MW\21\012\B | MW | 21 | 12 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-03-23 12:27 | 2016-03-27 03:36 | 106271.3049 | [6 empty] | 106271 | 76784 | 3.95 | 0 | 0 | 14.52 | 5172
TS5500Exc | SC\27\003\B | SC | 27 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-03-23 18:56 | 2016-03-26 16:38 | 87811.4989 | [6 empty] | 87811 | 65051 | 3.86 | 0 | 0 | 8.93 | 5578
DRE2 | DT\20\007\D | DT | 20 | 7 | D | 6 DL | 100 | 100 | 100 | 2016-03-24 06:17 | 2016-03-27 14:57 | 274961.7291 |  |  |  | 11992 | 274962 | 198394 |  |  | 0 | 23.79 | 0 | 5.42 | 5935.66
TS6060#1 | BW\21\004\B | BW | 21 | 4 | B | 1 Prestrip - Thick | 100 | 36.5055 | 36.5055 | 2016-03-25 08:42 | 2016-04-01 | 164352.4483 | 164352 | [7 empty] | 0 | 0 | 10.19 | 11.26 | 5385.16
PH4100A | SC\28\004\D | SC | 28 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-03-25 12:04 | 2016-03-27 02:55 | 66487.1098 | 66487 | [7 empty] | 0 | 0 | 5.54 | 6.22 | 5867.75
DRE1 | SC\25\005\D | SC | 25 | 5 | D | 6 DL | 100 | 0 | 73.4523 | 2016-03-25 17:24 | 2016-04-01 | 533041.4283 |  |  |  | 44805 | 533041 | 351700 |  |  | 0 | 45 | 0 | 6.07 | 5881.28
PH4100XPC#1 | BW\22\010\A2 | BW | 22 | 10 | A2 | 1 Prestrip - Thick | 100 | 0 | 65.3835 | 2016-03-25 19:25 | 2016-04-01 | 333306.7381 | 333307 | [7 empty] | 0 | 0 | 20.05 | 0 | 0
TS5500Exc | SC\25\004\D | SC | 25 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-03-26 16:38 | 2016-03-29 06:28 | 77882.0759 | [6 empty] | 77882 | 58720 | 4.89 | 0 | 0 | 6.13 | 5876
PH4100A | SC\27\003\D | SC | 27 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-03-27 02:55 | 2016-03-30 21:44 | 155399.7266 | 155400 | [7 empty] | 0 | 0 | 11.32 | 6.33 | 5857.97
TS5500Shv | MW\20\010\A | MW | 20 | 10 | A | 8 Coal Mining | 86.6 | 0 | 86.6 | 2016-03-27 03:36 | 2016-03-28 06:02 | 32216.3654 | [6 empty] | 32216 | 23397 | 1.41 | 0 | 0 | 12.26 | 5364
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2016-03-27 14:57 | 2016-03-29 14:57
TS5500Shv | MW\20\011\A | MW | 20 | 11 | A | 8 Coal Mining | 100 | 0 | 100 | 2016-03-28 06:02 | 2016-03-30 17:59 | 73109.8814 | [6 empty] | 73110 | 53502 | 3.32 | 0 | 0 | 11.02 | 5447
TS5500Exc | MW\20\010\B | MW | 20 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-03-29 06:28 | 2016-03-30 19:15 | 32520.2962 | 32520 | [7 empty] | 0 | 0 | 1.99 | 16.75 | 5001.56
DRE2 | MW\20\003\D | MW | 20 | 3 | D | 6 DL | 100 | 40.7274 | 40.7274 | 2016-03-29 14:57 | 2016-04-01 | 194456.3993 |  |  |  | 8481 | 194456 | 140307 |  |  | 0 | 22.91 | 0 | 5.68 | 5912.82
TS5500Shv | MW\20\012\A | MW | 20 | 12 | A | 8 Coal Mining | 7.7 | 0 | 7.7 | 2016-03-30 17:59 | 2016-03-30 23:15 | 6427.6887 | [6 empty] | 6428 | 4720 | 0.19 | 0 | 0 | 10.61 | 5465
TS5500Exc | MW\20\011\B | MW | 20 | 11 | B | 1 Prestrip - Thick | 100 | 63.0333 | 63.0333 | 2016-03-30 19:15 | 2016-04-01 | 25425.1382 | 25425 | [7 empty] | 0 | 0 | 1.59 | 14.52 | 5177.78
PH4100A | SC\29\003\B | SC | 29 | 3 | B | 1 Prestrip - Thick | 100 | 9.7624 | 9.7624 | 2016-03-30 21:44 | 2016-04-01 | 44647.292 | 44647 | [7 empty] | 0 | 0 | 4.01 | 8.95 | 5576.9
TS5500Shv | DT\20\004\D | DT | 20 | 4 | D | 8 Coal Mining | 40.7 | 0 | 23.5 | 2016-03-30 23:15 | 2016-03-31 18:37 | 23609.469 | [6 empty] | 23609 | 17853 | 1.12 | 0 | 0 | 5.6 | 5921
TS5500Shv | DT\23\006\A | DT | 23 | 6 | A | 1 Prestrip - Thick | 60.415 | 1.7886 | 1.7886 | 2016-03-31 18:37 | 2016-04-01 | 5675.4389 | 5675 | [7 empty] | 0 | 0 | 0.62 | 10.84 | 5371.32
| EOP 27 : 2016\Mar | EOP 27 : 2016 | Mar | [6 empty] | 2016-04-01 | 2016-04-01 |  | 5423991 |  | 33629 | 287236 | 5005922 | 2960409 | 1424700 | 1059795 | 81.7 | 0 | 361.44 | 8.59 | 5657.84
TS Fleet 5 | BW\21\007\B | BW | 21 | 7 | B | 1 Prestrip - Thick | 80.8931 | 9.7486 | 9.7486 | 2016-04-01 | 2016-04-02 18:32 | 83394.4728 | 83394 | [7 empty] | 0 | 0 | 5.85 | 11.82 | 5379.13
DRE1 | SC\25\005\D | SC | 25 | 5 | D | 6 DL | 100 | 0 | 26.5477 | 2016-04-01 | 2016-04-03 06:25 | 192656.0722 |  |  |  | 16194 | 192656 | 127114 |  |  | 0 | 45 | 0 | 6.07 | 5881.28
PH4100A | SC\29\003\B | SC | 29 | 3 | B | 1 Prestrip - Thick | 100 | 90.2376 | 90.2376 | 2016-04-01 | 2016-04-10 13:24 | 412690.2287 | 412690 | [7 empty] | 0 | 0 | 37.07 | 8.95 | 5576.9
TS5500Shv | DT\23\006\A | DT | 23 | 6 | A | 1 Prestrip - Thick | 60.415 | 58.6263 | 58.6263 | 2016-04-01 | 2016-04-08 00:43 | 186024.011 | 186024 | [7 empty] | 0 | 0 | 20.23 | 10.84 | 5371.32
DRE2 | MW\20\003\D | MW | 20 | 3 | D | 6 DL | 100 | 59.2726 | 59.2726 | 2016-04-01 | 2016-04-04 11:01 | 283001.986 |  |  |  | 12343 | 283002 | 204196 |  |  | 0 | 22.91 | 0 | 5.68 | 5912.82
PH4100XPC#1 | BW\22\010\A2 | BW | 22 | 10 | A2 | 1 Prestrip - Thick | 100 | 0 | 34.6165 | 2016-04-01 | 2016-04-04 02:20 | 176465.0071 | 176465 | [7 empty] | 0 | 0 | 10.62 | 0 | 0
TS6060#1 | BW\21\004\B | BW | 21 | 4 | B | 1 Prestrip - Thick | 100 | 29.1031 | 29.1031 | 2016-04-01 | 2016-04-06 01:32 | 131026.1039 | 131026 | [7 empty] | 0 | 0 | 8.12 | 11.26 | 5385.16
TS5500Exc | MW\20\011\B | MW | 20 | 11 | B | 1 Prestrip - Thick | 100 | 36.9667 | 36.9667 | 2016-04-01 | 2016-04-01 16:08 | 14910.9287 | 14911 | [7 empty] | 0 | 0 | 0.93 | 14.52 | 5177.78
TS5500Exc | SC\28\003\B | SC | 28 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-04-01 16:08 | 2016-04-03 22:18 | 71281.0112 | [6 empty] | 71281 | 52805 | 3.85 | 0 | 0 | 8.94 | 5577
TS Fleet 5 | BW\21\004\B | BW | 21 | 4 | B | 1 Prestrip - Thick | 20.798 | 20.798 | 20.798 | 2016-04-02 18:32 | 2016-04-04 18:19 | 93635.5539 | 93636 | [7 empty] | 0 | 0 | 5.8 | 11.26 | 5385.16
DRE1 | SC\25\006\D | SC | 25 | 6 | D | 6 DL | 100 | 0 | 100 | 2016-04-03 06:25 | 2016-04-11 19:29 | 725857.1174 |  |  |  | 61012 | 725857 | 478919 |  |  | 0 | 45 | 0 | 5.79 | 5905.29
TS5500Exc | SC\25\005\D | SC | 25 | 5 | D | 8 Coal Mining | 16 | 0 | 16 | 2016-04-03 22:18 | 2016-04-04 08:02 | 12823.9131 | [6 empty] | 12824 | 9653 | 0.8 | 0 | 0 | 6.07 | 5881
PH4100XPC#1 | BW\21\009\B | BW | 21 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-04-04 02:20 | 2016-04-15 07:06 | 656666.0733 | 656666 | [7 empty] | 0 | 0 | 38.41 | 14.45 | 5139.62
TS5500Exc | SC\25\005\D | SC | 25 | 5 | D | 8 Coal Mining | 84 | 0 | 84 | 2016-04-04 08:02 | 2016-04-06 11:20 | 67503.1447 | [6 empty] | 67503 | 50814 | 4.24 | 0 | 0 | 6.07 | 5881
DRE2 | MW\20\004\D | MW | 20 | 4 | D | 6 DL | 100 | 0 | 100 | 2016-04-04 11:01 | 2016-04-12 14:18 | 665628.8368 |  |  |  | 49756 | 665629 | 457956 |  |  | 0 | 31.17 | 0 | 6.25 | 5863.73
TS Fleet 5 | BW\21\004\B | BW | 21 | 4 | B | 1 Prestrip - Thick | 29.6125 | 13.5934 | 13.5934 | 2016-04-04 18:19 | 2016-04-06 01:32 | 61199.2531 | 61199 | [7 empty] | 0 | 0 | 3.79 | 11.26 | 5385.16
TS Fleet 5 | BW\21\008\B | BW | 21 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-04-06 01:32 | 2016-04-22 14:07 | 777297.7676 | 777298 | [7 empty] | 0 | 0 | 51.46 | 14.12 | 5181.02
TS6060#1 | BW\19\006\D | BW | 19 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-04-06 01:32 | 2016-04-08 00:06 | 65845.8328 | [6 empty] | 65846 | 49988 | 5 | 0 | 0 | 5.45 | 5936
TS5500Exc | MW\23\006\B | MW | 23 | 6 | B | 1 Prestrip - Thick | 30.2283 | 30.2283 | 30.2283 | 2016-04-06 11:20 | 2016-04-12 00:54 | 124264.7294 | 124265 | [7 empty] | 0 | 0 | 7.69 | 10.2 | 5538.37
TS6060#1 | MW\22\012\A | MW | 22 | 12 | A | 8 Coal Mining | 22.1 | 0 | 22.1 | 2016-04-08 00:06 | 2016-04-08 13:50 | 19413.1323 | [6 empty] | 19413 | 14243 | 0.8 | 0 | 0 | 10.62 | 5470
TS5500Shv | DT\20\004\D | DT | 20 | 4 | D | 8 Coal Mining | 40.7 | 0 | 17.2 | 2016-04-08 00:43 | 2016-04-08 14:19 | 17326.1685 | [6 empty] | 17326 | 13102 | 0.82 | 0 | 0 | 5.6 | 5921
TS6060#1 | MW\22\012\A | MW | 22 | 12 | A | 8 Coal Mining | 77.9 | 0 | 77.9 | 2016-04-08 13:50 | 2016-04-10 14:11 | 68357.546 | [6 empty] | 68358 | 50154 | 2.83 | 0 | 0 | 10.62 | 5470
TS5500Shv | MW\20\010\B | MW | 20 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-04-08 14:19 | 2016-04-11 04:30 | 79216.9285 | [6 empty] | 79217 | 56414 | 3.51 | 0 | 0 | 16.75 | 5002
PH4100A | SC\28\003\D | SC | 28 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-04-10 13:24 | 2016-04-13 00:51 | 107627.4816 | 107627 | [7 empty] | 0 | 0 | 10.43 | 6.32 | 5859.16
TS6060#1 | BW\19\003\D | BW | 19 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-04-10 14:11 | 2016-04-12 12:36 | 65636.3879 | [6 empty] | 65636 | 49315 | 4.93 | 0 | 0 | 6.6 | 5834
TS5500Shv | DT\20\005\D | DT | 20 | 5 | D | 8 Coal Mining | 42.2 | 0 | 42.2 | 2016-04-11 04:30 | 2016-04-12 04:44 | 30865.5576 | [6 empty] | 30866 | 23415 | 1.97 | 0 | 0 | 5.44 | 5935
DRE1 | SC\25\007\D | SC | 25 | 7 | D | 6 DL | 100 | 0 | 100 | 2016-04-11 19:29 | 2016-04-20 09:06 | 727822.6891 |  |  |  | 61177 | 727823 | 480216 |  |  | 0 | 45 | 0 | 5.53 | 5928.02
TS5500Exc | SC\25\006\D | SC | 25 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-04-12 00:54 | 2016-04-14 11:48 | 77505.9814 | [6 empty] | 77506 | 58765 | 4.9 | 0 | 0 | 5.79 | 5905
TS5500Shv | MW\20\011\B | MW | 20 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-04-12 04:44 | 2016-04-15 00:19 | 86114.6779 | [6 empty] | 86115 | 62160 | 3.88 | 0 | 0 | 14.52 | 5178
TS6060#1 | BW\19\004\D | BW | 19 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-04-12 12:36 | 2016-04-14 13:39 | 69353.9303 | [6 empty] | 69354 | 52272 | 5.23 | 0 | 0 | 6.09 | 5881
DRE2 | MW\20\005\D | MW | 20 | 5 | D | 6 DL | 100 | 0 | 100 | 2016-04-12 14:18 | 2016-04-17 14:53 | 411032.7979 |  |  |  | 17927 | 411033 | 296574 |  |  | 0 | 19.34 | 0 | 6.48 | 5842.78
PH4100A | SC\29\004\B | SC | 29 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-04-13 00:51 | 2016-04-23 15:48 | 459232.6886 | 459233 | [7 empty] | 0 | 0 | 39.02 | 9.02 | 5571.12
TS5500Exc | MW\23\006\B | MW | 23 | 6 | B | 1 Prestrip - Thick | 69.7717 | 69.7717 | 69.7717 | 2016-04-14 11:48 | 2016-04-27 08:05 | 286822.2623 | 286822 | [7 empty] | 0 | 0 | 17.74 | 10.2 | 5538.37
TS6060#1 | BW\19\002\D | BW | 19 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-04-14 13:39 | 2016-04-16 11:10 | 64377.4668 | [6 empty] | 64377 | 48562 | 4.86 | 0 | 0 | 6.11 | 5877
TS5500Shv | DT\20\007\D | DT | 20 | 7 | D | 8 Coal Mining | 36.6 | 0 | 36.6 | 2016-04-15 00:19 | 2016-04-15 15:28 | 19288.9841 | [6 empty] | 19289 | 14644 | 1.67 | 0 | 0 | 5.42 | 5936
PH4100XPC#1 | MW\22\012\B | MW | 22 | 12 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-04-15 07:06 | 2016-04-16 02:24 | 45567.3911 | 45567 | [7 empty] | 0 | 0 | 2.6 | 15.2 | 5115.78
TS5500Shv | MW\20\012\A | MW | 20 | 12 | A | 8 Coal Mining | 79.3 | 0 | 79.3 | 2016-04-15 15:28 | 2016-04-17 19:37 | 66443.1078 | [6 empty] | 66443 | 48786 | 1.96 | 0 | 0 | 10.61 | 5465
PH4100XPC#1 | BW\22\009\B | BW | 22 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-04-16 02:24 | 2016-04-28 11:55 | 721919.9424 | 721920 | [7 empty] | 0 | 0 | 44.24 | 13.73 | 5197.49
TS6060#1 | BW\19\005\D | BW | 19 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-04-16 11:10 | 2016-04-18 10:42 | 67194.4256 | [6 empty] | 67194 | 50889 | 5.09 | 0 | 0 | 5.58 | 5925
DRE2 | MW\20\006\D | MW | 20 | 6 | D | 6 DL | 100 | 0 | 100 | 2016-04-17 14:53 | 2016-04-23 14:47 | 490496.0692 |  |  |  | 21392 | 490496 | 353910 |  |  | 0 | 22.94 | 0 | 6.46 | 5844.68
TS5500Shv | MW\20\012\A | MW | 20 | 12 | A | 8 Coal Mining | 13 | 0 | 13 | 2016-04-17 19:37 | 2016-04-18 04:11 | 10918.5974 | [6 empty] | 10919 | 8017 | 0.32 | 0 | 0 | 10.61 | 5465
TS5500Shv | MW\21\003\A | MW | 21 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2016-04-18 04:11 | 2016-04-20 23:49 | 86161.6269 | [6 empty] | 86162 | 63877 | 3.86 | 0 | 0 | 8.89 | 5518
TS6060#1 | BW\21\004\B | BW | 21 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-04-18 10:42 | 2016-04-20 21:51 | 83648.8867 | [6 empty] | 83649 | 60869 | 3.81 | 0 | 0 | 11.26 | 5385
DRE1 | SC\26\013\D | SC | 26 | 13 | D | 6 DL | 100 | 0 | 100 | 2016-04-20 09:06 | 2016-04-26 14:51 | 530076.6862 |  |  |  | 27489 | 530077 | 242933 |  |  | 0 | 39.52 | 0 | 7.41 | 5760.83
TS6060#1 | BW\21\005\B | BW | 21 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-04-20 21:51 | 2016-04-23 09:12 | 83909.4566 | [6 empty] | 83909 | 61351 | 3.84 | 0 | 0 | 10.39 | 5475
TS5500Shv | MW\20\003\D | MW | 20 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-04-20 23:49 | 2016-04-24 02:18 | 94885.7199 | [6 empty] | 94886 | 71976 | 4.5 | 0 | 0 | 5.68 | 5913
TS Fleet 5 | BW\21\010\B | BW | 21 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-04-22 14:07 | 2016-04-23 21:57 | 62397.3552 | 62397 | [7 empty] | 0 | 0 | 3.94 | 11.47 | 5367.1
TS6060#1 | BW\22\011\A2 | BW | 22 | 11 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2016-04-23 09:12 | 2016-04-24 02:47 | 24871.4415 | [6 empty] | 24871 | 17405 | 1.09 | 0 | 0 | 19.79 | 4659
DRE2 | MW\20\007\D | MW | 20 | 7 | D | 6 DL | 100 | 0 | 97.9539 | 2016-04-23 14:47 | 2016-05-01 | 604032.3103 |  |  |  | 36073 | 604032 | 426403 |  |  | 0 | 29.16 | 0 | 6.11 | 5874.77
PH4100A | SC\29\005\B | SC | 29 | 5 | B | 1 Prestrip - Thick | 100 | 72.37 | 72.37 | 2016-04-23 15:48 | 2016-05-01 | 326703.2098 | 326703 | [7 empty] | 0 | 0 | 29.58 | 9.16 | 5559.47
TS Fleet 5 | BW\21\011\B | BW | 21 | 11 | B | 1 Prestrip - Thick | 62.3905 | 51.7263 | 51.7263 | 2016-04-23 21:57 | 2016-05-01 | 333275.5974 | 333276 | [7 empty] | 0 | 0 | 23.85 | 11.04 | 5393.38
TS5500Shv | MW\21\004\A | MW | 21 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2016-04-24 02:18 | 2016-04-24 21:57 | 25047.9166 | [6 empty] | 25048 | 18281 | 0.88 | 0 | 0 | 12.11 | 5288
TS6060#1 | BW\19\001\D | BW | 19 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2016-04-24 02:47 | 2016-04-25 16:52 | 41059.5224 |  |  | 41060 | [5 empty] | 0 | 0 | 0 | 5.79 | 5905.18
TS5500Shv | MW\21\007\B | MW | 21 | 7 | B | 8 Coal Mining | 100 | 0 | 76.8 | 2016-04-24 21:57 | 2016-04-26 08:43 | 44292.2521 | [6 empty] | 44292 | 32565 | 1.5 | 0 | 0 | 10.32 | 5492
TS6060#1 | DT\20\004\D | DT | 20 | 4 | D | 8 Coal Mining | 59.3 | 0 | 22.3 | 2016-04-25 16:52 | 2016-04-26 08:43 | 22415.9058 | [6 empty] | 22416 | 16951 | 1.06 | 0 | 0 | 5.6 | 5921
TS5500Shv | DT\23\006\A | DT | 23 | 6 | A | 1 Prestrip - Thick | 39.585 | 38.6606 | 38.6606 | 2016-04-26 08:43 | 2016-05-01 | 122671.7673 | 122672 | [7 empty] | 0 | 0 | 13.34 | 10.84 | 5371.32
TS6060#1 | BW\21\007\B | BW | 21 | 7 | B | 1 Prestrip - Thick | 11.7896 | 11.7896 | 11.7896 | 2016-04-26 08:43 | 2016-04-30 07:41 | 100854.8639 | 100855 | [7 empty] | 0 | 0 | 7.08 | 11.82 | 5379.13
DRE1 | SC\26\012\D | SC | 26 | 12 | D | 6 DL | 100 | 0 | 51.1882 | 2016-04-26 14:51 | 2016-05-01 | 372171.4352 |  |  |  | 31283 | 372171 | 245558 |  |  | 0 | 45 | 0 | 7.42 | 5760.48
TS5500Exc | SC\26\013\D | SC | 26 | 13 | D | 7 PostStrip | 100 | 0 | 100 | 2016-04-27 08:05 | 2016-04-28 21:58 | 35010.1288 |  |  | 35010 | [5 empty] | 0 | 0 | 0 | 7.41 | 5760.83
PH4100XPC#1 | MW\20\012\B | MW | 20 | 12 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-04-28 11:55 | 2016-04-29 12:36 | 58260.9639 | 58261 | [7 empty] | 0 | 0 | 2.42 | 13.54 | 5251.76
TS5500Exc | MW\23\008\B | MW | 23 | 8 | B | 1 Prestrip - Thick | 25.5683 | 10.0945 | 10.0945 | 2016-04-28 21:58 | 2016-05-01 | 46495.3694 | 46495 | [7 empty] | 0 | 0 | 2.85 | 9.96 | 5505.72
PH4100XPC#1 | MW\21\003\B | MW | 21 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-04-29 12:36 | 2016-04-30 07:56 | 45632.4258 | 45632 | [7 empty] | 0 | 0 | 2.77 | 8.07 | 5637.25
TS6060#1 | BW\21\011\B | BW | 21 | 11 | B | 1 Prestrip - Thick | 23.6075 | 2.6759 | 2.6759 | 2016-04-30 07:41 | 2016-05-01 | 17241.0699 | 17241 | [7 empty] | 0 | 0 | 1.23 | 11.04 | 5393.38
PH4100XPC#1 | MW\21\004\B | MW | 21 | 4 | B | 1 Prestrip - Thick | 100 | 0 | 75.6686 | 2016-04-30 07:56 | 2016-05-01 | 37906.3072 | 37906 | [7 empty] | 0 | 0 | 1.84 | 0 | 0
| EOP 28 : 2016\Apr | EOP 28 : 2016 | Apr | [6 empty] | 2016-05-01 | 2016-05-01 |  | 5490183 |  | 76070 | 334646 | 5002776 | 3313779 | 1424700 | 1057275 | 77.19 | 0 | 392.92 | 9.23 | 5592.9
TS Fleet 5 | BW\21\011\B | BW | 21 | 11 | B | 1 Prestrip - Thick | 62.3905 | 10.6642 | 10.6642 | 2016-05-01 | 2016-05-02 10:33 | 68709.8314 | 68710 | [7 empty] | 0 | 0 | 4.92 | 11.04 | 5393.38
DRE1 | SC\26\012\D | SC | 26 | 12 | D | 6 DL | 100 | 0 | 48.8118 | 2016-05-01 | 2016-05-05 04:15 | 354893.7877 |  |  |  | 29831 | 354894 | 234158 |  |  | 0 | 45 | 0 | 7.42 | 5760.48
PH4100A | SC\29\005\B | SC | 29 | 5 | B | 1 Prestrip - Thick | 100 | 27.63 | 27.63 | 2016-05-01 | 2016-05-03 18:21 | 124731.2209 | 124731 | [7 empty] | 0 | 0 | 11.29 | 9.16 | 5559.47
TS5500Shv | DT\23\006\A | DT | 23 | 6 | A | 1 Prestrip - Thick | 39.585 | 0.92446 | 0.92446 | 2016-05-01 | 2016-05-01 02:37 | 2933.3546 | 2933 | [7 empty] | 0 | 0 | 0.32 | 10.84 | 5371.32
DRE2 | MW\20\007\D | MW | 20 | 7 | D | 6 DL | 100 | 0 | 2.0461 | 2016-05-01 | 2016-05-01 03:42 | 12617.3248 |  |  |  | 754 | 12617 | 8907 |  |  | 0 | 29.16 | 0 | 6.11 | 5874.77
PH4100XPC#1 | MW\21\004\B | MW | 21 | 4 | B | 1 Prestrip - Thick | 100 | 0 | 24.3314 | 2016-05-01 | 2016-05-01 05:05 | 12188.8778 | 12189 | [7 empty] | 0 | 0 | 0.59 | 0 | 0
TS6060#1 | BW\21\011\B | BW | 21 | 11 | B | 1 Prestrip - Thick | 23.6075 | 20.9316 | 20.9316 | 2016-05-01 | 2016-05-06 05:42 | 134863.4636 | 134863 | [7 empty] | 0 | 0 | 9.65 | 11.04 | 5393.38
TS5500Exc | MW\23\008\B | MW | 23 | 8 | B | 1 Prestrip - Thick | 25.5683 | 15.4738 | 15.4738 | 2016-05-01 | 2016-05-04 03:35 | 71272.2105 | 71272 | [7 empty] | 0 | 0 | 4.37 | 9.96 | 5505.72
TS5500Shv | MW\21\007\B | MW | 21 | 7 | B | 8 Coal Mining | 100 | 0 | 23.2 | 2016-05-01 02:37 | 2016-05-01 12:59 | 13399.3965 | [6 empty] | 13399 | 9852 | 0.45 | 0 | 0 | 10.32 | 5492
DRE2 | MW\20\008\D | MW | 20 | 8 | D | 6 DL | 100 | 100 | 100 | 2016-05-01 03:42 | 2016-05-07 23:13 | 557374.8086 |  |  |  | 33287 | 557375 | 393466 |  |  | 0 | 26.6 | 0 | 6.03 | 5881.71
PH4100XPC#1 | BW\22\008\B | BW | 22 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-05-01 05:05 | 2016-05-14 18:49 | 796865.8434 | 796866 | [7 empty] | 0 | 0 | 47.48 | 13.45 | 5233.43
TS5500Shv | MW\21\008\B | MW | 21 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-05-01 12:59 | 2016-05-04 14:28 | 94962.3421 | [6 empty] | 94962 | 66140 | 4.1 | 0 | 0 | 20.7 | 4601
TS Fleet 5 | BW\21\011\B | BW | 21 | 11 | B | 1 Prestrip - Thick | 14.002 | 14.002 | 14.002 | 2016-05-02 10:33 | 2016-05-04 07:56 | 90215.4906 | 90215 | [7 empty] | 0 | 0 | 6.46 | 11.04 | 5393.38
PH4100A | SC\29\006\B | SC | 29 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-05-03 18:21 | 2016-05-12 14:20 | 405321.5431 | 405322 | [7 empty] | 0 | 0 | 35.34 | 9.26 | 5547.34
TS5500Exc | SC\25\007\D | SC | 25 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-05-04 03:35 | 2016-05-06 12:19 | 75720.1271 | [6 empty] | 75720 | 57875 | 4.82 | 0 | 0 | 5.53 | 5928
TS Fleet 5 | BW\22\001\X2 | BW | 22 | 1 | X2 | 1 Prestrip - Thick | 91.8401 | 0 | 91.8401 | 2016-05-04 07:56 | 2016-05-20 23:28 | 794259.3952 | 794259 | [7 empty] | 0 | 0 | 40.39 | 0 | 0
TS5500Shv | MW\20\004\D | MW | 20 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-05-04 14:28 | 2016-05-07 18:40 | 98460.4366 | [6 empty] | 98460 | 74393 | 4.65 | 0 | 0 | 6.25 | 5864
DRE1 | SC\26\011\D | SC | 26 | 11 | D | 6 DL | 100 | 0 | 100 | 2016-05-05 04:15 | 2016-05-13 03:37 | 677381.2136 |  |  |  | 51512 | 677381 | 463607 |  |  | 0 | 42.9 | 0 | 7.32 | 5770.42
TS6060#1 | DT\20\004\D | DT | 20 | 4 | D | 8 Coal Mining | 59.3 | 0 | 37 | 2016-05-06 05:42 | 2016-05-07 07:37 | 37151.5358 | [6 empty] | 37152 | 28094 | 1.76 | 0 | 0 | 5.6 | 5921
TS5500Exc | SC\26\012\D | SC | 26 | 12 | D | 8 Coal Mining | 78.8 | 0 | 78.8 | 2016-05-06 12:19 | 2016-05-08 07:53 | 58153.1654 | [6 empty] | 58153 | 43289 | 3.61 | 0 | 0 | 7.42 | 5760
TS6060#1 | DT\23\005\A | DT | 23 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2016-05-07 07:37 | 2016-05-08 02:09 | 26601.5751 | [6 empty] | 26602 | 19282 | 1.38 | 0 | 0 | 12.91 | 5222
TS5500Shv | MW\20\005\D | MW | 20 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-05-07 18:40 | 2016-05-10 20:58 | 96005.5901 | [6 empty] | 96006 | 72301 | 4.52 | 0 | 0 | 6.48 | 5843
DRE2 | MW\20\009\D | MW | 20 | 9 | D | 6 DL | 100 | 0 | 100 | 2016-05-07 23:13 | 2016-05-14 22:11 | 569135.3508 |  |  |  | 33989 | 569135 | 401768 |  |  | 0 | 27.16 | 0 | 6.19 | 5867.27
TS6060#1 | BW\19\001\D | BW | 19 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-05-08 02:09 | 2016-05-09 15:16 | 53227.1894 | [6 empty] | 53227 | 40278 | 5.02 | 0 | 0 | 5.79 | 5905
TS5500Exc | SC\26\012\D | SC | 26 | 12 | D | 8 Coal Mining | 21.2 | 0 | 21.2 | 2016-05-08 07:53 | 2016-05-08 19:36 | 15649.529 | [6 empty] | 15650 | 11650 | 0.97 | 0 | 0 | 7.42 | 5760
TS5500Exc | SC\26\013\D | SC | 26 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-05-08 19:36 | 2016-05-09 21:33 | 34629.5568 | [6 empty] | 34630 | 25798 | 4.47 | 0 | 0 | 7.41 | 5761
TS6060#1 | DT\20\005\D | DT | 20 | 5 | D | 8 Coal Mining | 57.8 | 0 | 57.8 | 2016-05-09 15:16 | 2016-05-10 20:48 | 42350.6981 | [6 empty] | 42351 | 32128 | 2.7 | 0 | 0 | 5.44 | 5935
TS5500Exc | SC\29\003\B | SC | 29 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-05-09 21:33 | 2016-05-11 13:19 | 53089.6608 | [6 empty] | 53090 | 39328 | 3.85 | 0 | 0 | 8.95 | 5577
TS6060#1 | BW\21\006\B | BW | 21 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-05-10 20:48 | 2016-05-13 07:06 | 83613.3335 | [6 empty] | 83613 | 60851 | 3.81 | 0 | 0 | 10.91 | 5443
TS5500Shv | DT\23\005\B | DT | 23 | 5 | B | 1 Prestrip - Thick | 29.3566 | 29.3566 | 29.3566 | 2016-05-10 20:58 | 2016-05-11 03:39 | 7602.6904 | 7603 | [7 empty] | 0 | 0 | 0.53 | 9.63 | 5459.41
TS5500Shv | DT\23\005\B | DT | 23 | 5 | B | 1 Prestrip - Thick | 70.6434 | 70.6434 | 70.6434 | 2016-05-11 03:39 | 2016-05-11 19:46 | 18295.0461 | 18295 | [7 empty] | 0 | 0 | 1.28 | 9.63 | 5459.41
TS5500Exc | SC\29\004\B | SC | 29 | 4 | B | 8 Coal Mining | 87.1 | 0 | 87.1 | 2016-05-11 13:19 | 2016-05-13 05:19 | 53392.3065 | [6 empty] | 53392 | 39514 | 3.21 | 0 | 0 | 9.02 | 5571
TS5500Shv | DT\23\005\B | DT | 23 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-05-11 19:46 | 2016-05-13 03:34 | 41097.5594 | [6 empty] | 41098 | 30191 | 2.07 | 0 | 0 | 9.63 | 5459
PH4100A | SC\30\004\B | SC | 30 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-05-12 14:20 | 2016-05-31 06:02 | 818470.8464 | 818471 | [7 empty] | 0 | 0 | 41.06 | 9.04 | 5569.49
TS5500Shv | MW\20\012\B | MW | 20 | 12 | B | 8 Coal Mining | 58.6 | 0 | 58.6 | 2016-05-13 03:34 | 2016-05-15 09:31 | 69716.5082 | [6 empty] | 69717 | 50629 | 2.24 | 0 | 0 | 13.54 | 5252
DRE1 | SC\26\010\D | SC | 26 | 10 | D | 6 DL | 100 | 0 | 100 | 2016-05-13 03:37 | 2016-05-21 09:22 | 699988.7246 |  |  |  | 53231 | 699989 | 479080 |  |  | 0 | 44.46 | 0 | 6.97 | 5801.3
TS5500Exc | SC\26\011\D | SC | 26 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-05-13 05:19 | 2016-05-15 15:25 | 77536.0625 | [6 empty] | 77536 | 57813 | 4.82 | 0 | 0 | 7.32 | 5770
TS6060#1 | DT\20\007\D | DT | 20 | 7 | D | 8 Coal Mining | 63.4 | 0 | 63.4 | 2016-05-13 07:06 | 2016-05-14 06:22 | 33373.1484 | [6 empty] | 33373 | 25337 | 2.9 | 0 | 0 | 5.42 | 5936
TS6060#1 | BW\21\007\B | BW | 21 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-05-14 06:22 | 2016-05-16 18:39 | 86457.567 | [6 empty] | 86458 | 62510 | 3.89 | 0 | 0 | 11.82 | 5379
PH4100XPC#1 | MW\21\007\D | MW | 21 | 7 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2016-05-14 18:49 | 2016-05-14 18:49 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | BW\22\007\B | BW | 22 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-05-14 18:49 | 2016-05-29 06:45 | 865393.0024 | 865393 | [7 empty] | 0 | 0 | 50.32 | 11.93 | 5366.57
DRE2 | MW\20\010\D | MW | 20 | 10 | D | 6 DL | 100 | 100 | 100 | 2016-05-14 22:11 | 2016-05-21 13:47 | 543999.5992 |  |  |  | 32488 | 544000 | 384024 |  |  | 0 | 25.95 | 0 | 6.08 | 5876.31
TS5500Shv | MW\20\006\D | MW | 20 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-05-15 09:31 | 2016-05-18 13:50 | 98623.0171 | [6 empty] | 98623 | 74038 | 4.63 | 0 | 0 | 6.46 | 5845
TS5500Exc | MW\23\008\B | MW | 23 | 8 | B | 1 Prestrip - Thick | 74.4317 | 74.4317 | 74.4317 | 2016-05-15 15:25 | 2016-05-30 19:02 | 342831.7227 | 342832 | [7 empty] | 0 | 0 | 21 | 9.96 | 5505.72
TS6060#1 | BW\21\009\B | BW | 21 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-05-16 18:39 | 2016-05-19 06:07 | 85283.071 | [6 empty] | 85283 | 61215 | 3.8 | 0 | 0 | 14.45 | 5140
TS5500Shv | MW\20\007\D | MW | 20 | 7 | D | 8 Coal Mining | 100 | 0 | 59.4 | 2016-05-18 13:50 | 2016-05-20 09:41 | 56660.9471 | [6 empty] | 56661 | 42602 | 2.66 | 0 | 0 | 6.11 | 5875
TS6060#1 | BW\21\008\B | BW | 21 | 8 | B | 8 Coal Mining | 100 | 0 | 47.3 | 2016-05-19 06:07 | 2016-05-20 09:41 | 39545.6764 | [6 empty] | 39546 | 28321 | 1.76 | 0 | 0 | 14.12 | 5181
TS5500Shv | DT\23\007\A | DT | 23 | 7 | A | 1 Prestrip - Thick | 29.6945 | 29.6945 | 29.6945 | 2016-05-20 09:41 | 2016-05-24 19:13 | 116480.647 | 116481 | [7 empty] | 0 | 0 | 7.44 | 9.93 | 5432.92
TS6060#1 | BW\22\001\X2 | BW | 22 | 1 | X2 | 1 Prestrip - Thick | 3.7337 | 0 | 3.7337 | 2016-05-20 09:41 | 2016-05-21 15:20 | 32290.3568 | 32290 | [7 empty] | 0 | 0 | 1.64 | 0 | 0
TS Fleet 5 | BW\22\002\X2 | BW | 22 | 2 | X2 | 1 Prestrip - Thick | 10.6612 | 0 | 10.6612 | 2016-05-20 23:28 | 2016-05-22 02:04 | 52896.0162 | 52896 | [7 empty] | 0 | 0 | 3.36 | 0 | 0
DRE1 | SC\26\009\D | SC | 26 | 9 | D | 6 DL | 100 | 0 | 100 | 2016-05-21 09:22 | 2016-05-29 23:56 | 731134.4349 |  |  |  | 61456 | 731134 | 482401 |  |  | 0 | 45 | 0 | 6.39 | 5852.38
DRE2 | MW\20\011\D | MW | 20 | 11 | D | 6 DL | 100 | 100 | 100 | 2016-05-21 13:47 | 2016-05-28 05:27 | 544266.3544 |  |  |  | 32504 | 544266 | 384213 |  |  | 0 | 26.01 | 0 | 5.67 | 5912.38
TS6060#1 | BW\22\001\X2 | BW | 22 | 1 | X2 | 1 Prestrip - Thick | 33.2363 | 0 | 4.4261 | 2016-05-21 15:20 | 2016-05-23 02:28 | 38278.3698 | 38278 | [7 empty] | 0 | 0 | 1.95 | 0 | 0
TS Fleet 5 | BW\22\002\X2 | BW | 22 | 2 | X2 | 1 Prestrip - Thick | 67.6323 | 0 | 67.6323 | 2016-05-22 02:04 | 2016-05-29 02:52 | 335561.5922 | 335562 | [7 empty] | 0 | 0 | 21.3 | 0 | 0
TS6060#1 | BW\22\002\X2 | BW | 22 | 2 | X2 | 1 Prestrip - Thick | 21.7065 | 0 | 21.7065 | 2016-05-23 02:28 | 2016-05-27 05:02 | 107697.8857 | 107698 | [7 empty] | 0 | 0 | 6.84 | 0 | 0
TS5500Shv | DT\23\007\A | DT | 23 | 7 | A | 1 Prestrip - Thick | 70.3055 | 48.6165 | 48.6165 | 2016-05-24 19:13 | 2016-06-01 | 190704.4112 | 190704 | [7 empty] | 0 | 0 | 12.18 | 9.93 | 5432.92
TS6060#1 | BW\23\002\X2 | BW | 23 | 2 | X2 | 1 Prestrip - Thick | 3.6643 | 0 | 3.6643 | 2016-05-27 05:02 | 2016-05-28 14:55 | 36985.392 | 36985 | [7 empty] | 0 | 0 | 1.42 | 0 | 0
DRE2 | DT\20\003\D | DT | 20 | 3 | D | 6 DL | 100 | 35.1291 | 35.1291 | 2016-05-28 05:27 | 2016-06-01 | 308604.9622 |  |  |  | 13459 | 308605 | 222669 |  |  | 0 | 21.89 | 0 | 6.67 | 5828.25
TS6060#1 | BW\23\002\X2 | BW | 23 | 2 | X2 | 1 Prestrip - Thick | 33.6829 | 0 | 8.7678 | 2016-05-28 14:55 | 2016-06-01 | 88495.6376 | 88496 | [7 empty] | 0 | 0 | 3.39 | 0 | 0
TS Fleet 5 | BW\22\001\B | BW | 22 | 1 | B | 1 Prestrip - Thick | 100 | 31.4032 | 31.4032 | 2016-05-29 02:52 | 2016-06-01 | 137429.6744 | 137430 | [7 empty] | 0 | 0 | 8.02 | 11.12 | 5388.89
PH4100XPC#1 | BW\22\011\B | BW | 22 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-05-29 06:45 | 2016-05-30 08:07 | 60678.4982 | 60678 | [7 empty] | 0 | 0 | 3.8 | 12.79 | 5255.19
DRE1 | SC\26\008\D | SC | 26 | 8 | D | 6 DL | 100 | 0 | 20.9279 | 2016-05-29 23:56 | 2016-06-01 | 170138.6393 |  |  |  | 12894 | 170139 | 101211 |  |  | 0 | 45 | 0 | 5.75 | 5908.44
PH4100XPC#1 | BW\22\010\B | BW | 22 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-05-30 08:07 | 2016-05-31 07:51 | 56792.4371 | 56792 | [7 empty] | 0 | 0 | 3.54 | 11.83 | 5337.92
TS5500Exc | MW\23\009\A | MW | 23 | 9 | A | 1 Prestrip - Thick | 75.4349 | 5.9922 | 5.9922 | 2016-05-30 19:02 | 2016-06-01 | 27315.7006 | 27316 | [7 empty] | 0 | 0 | 1.64 | 10.46 | 5444.74
PH4100A | SC\30\005\B | SC | 30 | 5 | B | 1 Prestrip - Thick | 100 | 7.1084 | 7.1084 | 2016-05-31 06:02 | 2016-06-01 | 34071.5257 | 34072 | [7 empty] | 0 | 0 | 2.98 | 9.24 | 5552.89
PH4100XPC#1 | BW\22\006\B | BW | 22 | 6 | B | 1 Prestrip - Thick | 100 | 4.8122 | 4.8122 | 2016-05-31 07:51 | 2016-06-01 | 39237.0134 | 39237 | [7 empty] | 0 | 0 | 2.5 | 11.08 | 5430.19
| EOP 29 : 2016\May | EOP 29 : 2016 | May | [6 empty] | 2016-06-01 | 2016-06-01 |  | 5908870 |  |  | 355404 | 5169535 | 3555504 | 1424700 | 1053429 | 78.1 | 0 | 356.97 | 9.09 | 5600.49
TS Fleet 5 | BW\22\001\B | BW | 22 | 1 | B | 1 Prestrip - Thick | 100 | 68.5968 | 68.5968 | 2016-06-01 | 2016-06-07 07:00 | 300199.4236 | 300199 | [7 empty] | 0 | 0 | 17.51 | 11.12 | 5388.89
DRE1 | SC\26\008\D | SC | 26 | 8 | D | 6 DL | 100 | 0 | 79.0721 | 2016-06-01 | 2016-06-08 13:36 | 642834.6322 |  |  |  | 48717 | 642835 | 382404 |  |  | 0 | 45 | 0 | 5.75 | 5908.44
PH4100A | SC\30\005\B | SC | 30 | 5 | B | 1 Prestrip - Thick | 100 | 92.8916 | 92.8916 | 2016-06-01 | 2016-06-10 18:34 | 445243.0038 | 445243 | [7 empty] | 0 | 0 | 39 | 9.24 | 5552.89
DRE2 | DT\20\003\D | DT | 20 | 3 | D | 6 DL | 100 | 64.8709 | 64.8709 | 2016-06-01 | 2016-06-07 23:11 | 569883.831 |  |  |  | 24855 | 569884 | 411190 |  |  | 0 | 21.89 | 0 | 6.67 | 5828.25
TS5500Shv | DT\23\007\A | DT | 23 | 7 | A | 1 Prestrip - Thick | 70.3055 | 21.689 | 21.689 | 2016-06-01 | 2016-06-04 05:04 | 85078.0023 | 85078 | [7 empty] | 0 | 0 | 5.43 | 9.93 | 5432.92
PH4100XPC#1 | BW\22\006\B | BW | 22 | 6 | B | 1 Prestrip - Thick | 100 | 95.1878 | 95.1878 | 2016-06-01 | 2016-06-14 07:18 | 776125.5894 | 776126 | [7 empty] | 0 | 0 | 49.48 | 11.08 | 5430.19
TS6060#1 | BW\23\002\X2 | BW | 23 | 2 | X2 | 1 Prestrip - Thick | 33.6829 | 0 | 24.9151 | 2016-06-01 | 2016-06-10 14:24 | 251475.9295 | 251476 | [7 empty] | 0 | 0 | 9.63 | 0 | 0
TS5500Exc | MW\23\009\A | MW | 23 | 9 | A | 1 Prestrip - Thick | 75.4349 | 69.4427 | 69.4427 | 2016-06-01 | 2016-06-14 23:31 | 316558.2678 | 316558 | [7 empty] | 0 | 0 | 19.02 | 10.46 | 5444.74
TS5500Shv | MW\20\007\D | MW | 20 | 7 | D | 8 Coal Mining | 100 | 0 | 40.6 | 2016-06-04 05:04 | 2016-06-05 11:04 | 38759.7548 | [6 empty] | 38760 | 29142 | 1.82 | 0 | 0 | 6.11 | 5875
TS5500Shv | MW\20\008\D | MW | 20 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-06-05 11:04 | 2016-06-08 12:29 | 94873.1636 | [6 empty] | 94873 | 71561 | 4.47 | 0 | 0 | 6.03 | 5882
TS Fleet 5 | BW\22\002\B | BW | 22 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-06-07 07:00 | 2016-06-16 00:33 | 416578.7852 | 416579 | [7 empty] | 0 | 0 | 26.33 | 11.45 | 5359.57
DRE2 | BW\20\011\D | BW | 20 | 11 | D | 6 DL | 100 | 100 | 100 | 2016-06-07 23:11 | 2016-06-13 08:58 | 442357.2606 |  |  |  | 19293 | 442357 | 319176 |  |  | 0 | 21.16 | 0 | 7.65 | 5741.87
TS5500Shv | MW\20\009\D | MW | 20 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-06-08 12:29 | 2016-06-11 13:06 | 93828.9146 | [6 empty] | 93829 | 70772 | 4.42 | 0 | 0 | 6.19 | 5867
DRE1 | SC\26\003\D | SC | 26 | 3 | D | 6 DL | 100 | 0 | 100 | 2016-06-08 13:36 | 2016-06-24 15:51 | 1367189.051 |  |  |  | 82968 | 1367189 | 569682 |  |  | 0 | 45 | 0 | 6.33 | 5857.77
TS6060#1 | DT\20\003\D | DT | 20 | 3 | D | 8 Coal Mining | 100 | 0 | 88.7 | 2016-06-10 14:24 | 2016-06-15 16:10 | 174635.2323 | [6 empty] | 174635 | 131224 | 4.3 | 0 | 0 | 6.67 | 5828
PH4100A | SC\30\006\B | SC | 30 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-06-10 18:34 | 2016-06-21 08:17 | 486886.2585 | 486886 | [7 empty] | 0 | 0 | 40.6 | 9.34 | 5541.43
TS5500Shv | MW\20\012\B | MW | 20 | 12 | B | 8 Coal Mining | 41.4 | 0 | 41.4 | 2016-06-11 13:06 | 2016-06-13 03:13 | 49264.738 | [6 empty] | 49265 | 35776 | 1.58 | 0 | 0 | 13.54 | 5252
TS5500Shv | MW\21\003\B | MW | 21 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-06-13 03:13 | 2016-06-15 07:26 | 67458.972 | [6 empty] | 67459 | 50194 | 3.06 | 0 | 0 | 8.07 | 5637
DRE2 | MW\20\012\D | MW | 20 | 12 | D | 6 DL | 100 | 100 | 100 | 2016-06-13 08:58 | 2016-06-23 01:27 | 792455.5689 |  |  |  | 28591 | 792456 | 375325 |  |  | 0 | 25.68 | 0 | 5.59 | 5920.29
PH4100XPC#1 | BW\22\005\X1 | BW | 22 | 5 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-06-14 07:18 | 2016-06-20 08:41 | 345612.1517 | 345612 | [7 empty] | 0 | 0 | 21.54 | 11.24 | 5401.07
TS5500Exc | DT\20\003\D | DT | 20 | 3 | D | 8 Coal Mining | 100 | 0 | 11.3 | 2016-06-14 23:31 | 2016-06-15 16:10 | 22205.3304 | [6 empty] | 22205 | 16685 | 0.55 | 0 | 0 | 6.67 | 5828
TS5500Shv | MW\20\010\D | MW | 20 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-06-15 07:26 | 2016-06-18 06:34 | 91924.7044 | [6 empty] | 91925 | 69332 | 4.33 | 0 | 0 | 6.08 | 5876
TS5500Exc | SC\26\010\D | SC | 26 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-06-15 16:10 | 2016-06-18 01:57 | 77144.9512 | [6 empty] | 77145 | 57795 | 4.82 | 0 | 0 | 6.97 | 5801
TS6060#1 | BW\21\008\B | BW | 21 | 8 | B | 8 Coal Mining | 100 | 0 | 52.7 | 2016-06-15 16:10 | 2016-06-16 22:53 | 44060.9519 | [6 empty] | 44061 | 31555 | 1.96 | 0 | 0 | 14.12 | 5181
TS Fleet 5 | BW\22\003\X1 | BW | 22 | 3 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-06-16 00:33 | 2016-06-22 10:33 | 306172.2898 | 306172 | [7 empty] | 0 | 0 | 18.74 | 12.68 | 5245.14
TS6060#1 | BW\21\010\B | BW | 21 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-06-16 22:53 | 2016-06-19 10:24 | 85356.91 | [6 empty] | 85357 | 62488 | 3.92 | 0 | 0 | 11.47 | 5367
TS5500Exc | SC\26\009\D | SC | 26 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-06-18 01:57 | 2016-06-20 11:46 | 77174.4635 | [6 empty] | 77174 | 58278 | 4.87 | 0 | 0 | 6.39 | 5852
TS5500Shv | MW\21\009\B | MW | 21 | 9 | B | 8 Coal Mining | 59.9 | 0 | 59.9 | 2016-06-18 06:34 | 2016-06-20 00:54 | 54695.6718 | [6 empty] | 54696 | 38002 | 2.36 | 0 | 0 | 21.05 | 4615
TS6060#1 | BW\22\009\B | BW | 22 | 9 | B | 8 Coal Mining | 44.9 | 0 | 44.9 | 2016-06-19 10:24 | 2016-06-20 13:07 | 38324.0915 | [6 empty] | 38324 | 27610 | 1.73 | 0 | 0 | 13.73 | 5197
TS5500Shv | MW\20\011\D | MW | 20 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-06-20 00:54 | 2016-06-23 00:04 | 91961.6508 | [6 empty] | 91962 | 69640 | 4.35 | 0 | 0 | 5.67 | 5912
PH4100XPC#1 | BW\22\004\X1 | BW | 22 | 4 | X1 | 1 Prestrip - Thick | 100 | 80.6719 | 80.6719 | 2016-06-20 08:41 | 2016-06-25 16:13 | 303348.0442 | 303348 | [7 empty] | 0 | 0 | 18.9 | 11.33 | 5375.09
TS5500Exc | SC\26\008\D | SC | 26 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-06-20 11:46 | 2016-06-22 20:31 | 75753.0899 | [6 empty] | 75753 | 57667 | 4.82 | 0 | 0 | 5.75 | 5908
TS6060#1 | DT\23\006\A | DT | 23 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2016-06-20 13:07 | 2016-06-21 22:37 | 48053.2926 | [6 empty] | 48053 | 35215 | 3.78 | 0 | 0 | 10.84 | 5371
PH4100A | SC\29\007\B | SC | 29 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-06-21 08:17 | 2016-06-28 02:32 | 308313.647 | 308314 | [7 empty] | 0 | 0 | 27.17 | 9.33 | 5536.46
TS6060#1 | BW\21\011\B | BW | 21 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-06-21 22:37 | 2016-06-24 14:44 | 91952.7633 | [6 empty] | 91953 | 67567 | 4.22 | 0 | 0 | 11.04 | 5393
TS Fleet 5 | BW\22\004\X1 | BW | 22 | 4 | X1 | 1 Prestrip - Thick | 19.3281 | 19.3281 | 19.3281 | 2016-06-22 10:33 | 2016-06-23 23:07 | 72679.0434 | 72679 | [7 empty] | 0 | 0 | 4.53 | 11.33 | 5375.09
TS5500Exc | SC\29\004\B | SC | 29 | 4 | B | 8 Coal Mining | 12.9 | 0 | 12.9 | 2016-06-22 20:31 | 2016-06-23 02:27 | 7908.5609 | [6 empty] | 7909 | 5853 | 0.48 | 0 | 0 | 9.02 | 5571
TS5500Shv | DT\23\006\B | DT | 23 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-06-23 00:04 | 2016-06-24 02:13 | 29712.134 | 29712 | [7 empty] | 0 | 0 | 3.21 | 8.44 | 5578.89
DRE2 | BW\20\010\D | BW | 20 | 10 | D | 6 DL | 100 | 100 | 100 | 2016-06-23 01:27 | 2016-06-28 12:26 | 446507.8686 |  |  |  | 19474 | 446508 | 322171 |  |  | 0 | 21.33 | 0 | 6.71 | 5824.66
TS5500Exc | SC\29\005\B | SC | 29 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-06-23 02:27 | 2016-06-24 20:29 | 56107.3983 | [6 empty] | 56107 | 41445 | 3.44 | 0 | 0 | 9.16 | 5559
TS Fleet 5 | BW\23\002\X2 | BW | 23 | 2 | X2 | 1 Prestrip - Thick | 24.1752 | 0 | 24.1752 | 2016-06-23 23:07 | 2016-06-29 01:51 | 244008.2893 | 244008 | [7 empty] | 0 | 0 | 9.35 | 0 | 0
TS5500Shv | MW\20\012\D | MW | 20 | 12 | D | 7 PostStrip | 100 | 0 | 100 | 2016-06-24 02:13 | 2016-06-27 16:12 | 97675.3261 |  |  | 97675 | [5 empty] | 0 | 0 | 0 | 5.59 | 5920.29
TS6060#1 | BW\22\007\B | BW | 22 | 7 | B | 8 Coal Mining | 100 | 0 | 50.5 | 2016-06-24 14:44 | 2016-06-25 20:54 | 43255.3943 | [6 empty] | 43255 | 31283 | 1.96 | 0 | 0 | 11.93 | 5367
DRE1 | SC\26\004\D | SC | 26 | 4 | D | 6 DL | 100 | 0 | 74.8511 | 2016-06-24 15:51 | 2016-07-01 | 538560.3167 |  |  |  | 45269 | 538560 | 355341 |  |  | 0 | 45 | 0 | 6.17 | 5871.73
TS5500Exc | SC\26\003\D | SC | 26 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2016-06-24 20:29 | 2016-06-28 11:32 | 81581.216 |  |  | 81581 | [5 empty] | 0 | 0 | 0 | 6.33 | 5857.77
PH4100XPC#1 | DT\24\004\B | DT | 24 | 4 | B | 1 Prestrip - Thick | 100 | 44.9414 | 44.9414 | 2016-06-25 16:13 | 2016-07-01 | 321698.9275 | 321699 | [7 empty] | 0 | 0 | 20.04 | 10.56 | 5336.63
TS6060#1 | BW\23\005\X1 | BW | 23 | 5 | X1 | 1 Prestrip - Thick | 28.944 | 28.944 | 28.944 | 2016-06-25 20:54 | 2016-06-29 17:45 | 101177.5585 | 101178 | [7 empty] | 0 | 0 | 6.31 | 10.47 | 5467.33
TS5500Shv | DT\24\001\B | DT | 24 | 1 | B | 1 Prestrip - Thick | 10.6813 | 10.2226 | 10.2226 | 2016-06-27 16:12 | 2016-07-01 | 90501.5665 | 90502 | [7 empty] | 0 | 0 | 4.49 | 11.34 | 5359.39
PH4100A | SC\30\007\B | SC | 30 | 7 | B | 1 Prestrip - Thick | 100 | 35.1825 | 35.1825 | 2016-06-28 02:32 | 2016-07-01 | 132886.2212 | 132886 | [7 empty] | 0 | 0 | 11.23 | 9.51 | 5521.6
TS5500Exc | MW\23\009\A | MW | 23 | 9 | A | 1 Prestrip - Thick | 24.5651 | 12.5131 | 12.5131 | 2016-06-28 11:32 | 2016-07-01 | 57041.764 | 57042 | [7 empty] | 0 | 0 | 3.43 | 10.46 | 5444.74
DRE2 | BW\20\009\D | BW | 20 | 9 | D | 6 DL | 100 | 44.3358 | 44.3358 | 2016-06-28 12:26 | 2016-07-01 | 202987.4709 |  |  |  | 8853 | 202987 | 146462 |  |  | 0 | 21.77 | 0 | 5.9 | 5893.75
TS Fleet 5 | BW\23\002\X2 | BW | 23 | 2 | X2 | 1 Prestrip - Thick | 38.4775 | 0 | 9.0874 | 2016-06-29 01:51 | 2016-07-01 | 91722.1686 | 91722 | [7 empty] | 0 | 0 | 3.51 | 0 | 0
TS6060#1 | BW\23\006\B | BW | 23 | 6 | B | 1 Prestrip - Thick | 27.4358 | 3.9231 | 3.9231 | 2016-06-29 17:45 | 2016-07-01 | 32751.5511 | 32752 | [7 empty] | 0 | 0 | 2.06 | 10.79 | 5455.07
| EOP 30 : 2016\Jun | EOP 30 : 2016 | Jun | [6 empty] | 2016-07-01 | 2016-07-01 |  | 5515771 |  | 179257 | 278018 | 5002776 | 2881750 | 1424700 | 1059086 | 67.24 | 0 | 361.53 | 8.32 | 5666.46
TS Fleet 5 | BW\23\002\X2 | BW | 23 | 2 | X2 | 1 Prestrip - Thick | 38.4775 | 0 | 29.3901 | 2016-07-01 | 2016-07-07 03:08 | 296643.675 | 296644 | [7 empty] | 0 | 0 | 11.37 | 0 | 0
DRE1 | SC\26\004\D | SC | 26 | 4 | D | 6 DL | 100 | 0 | 25.1489 | 2016-07-01 | 2016-07-03 02:27 | 180948.1274 |  |  |  | 15210 | 180948 | 119389 |  |  | 0 | 45 | 0 | 6.17 | 5871.73
PH4100A | SC\30\007\B | SC | 30 | 7 | B | 1 Prestrip - Thick | 100 | 64.8175 | 64.8175 | 2016-07-01 | 2016-07-06 06:16 | 244819.7713 | 244820 | [7 empty] | 0 | 0 | 20.68 | 9.51 | 5521.6
DRE2 | BW\20\009\D | BW | 20 | 9 | D | 6 DL | 100 | 55.6642 | 55.6642 | 2016-07-01 | 2016-07-04 01:47 | 254853.983 |  |  |  | 11115 | 254854 | 183886 |  |  | 0 | 21.77 | 0 | 5.9 | 5893.75
TS5500Shv | DT\24\001\B | DT | 24 | 1 | B | 1 Prestrip - Thick | 10.6813 | 0.45872 | 0.45872 | 2016-07-01 | 2016-07-01 03:31 | 4061.0849 | 4061 | [7 empty] | 0 | 0 | 0.2 | 11.34 | 5359.39
PH4100XPC#1 | DT\24\004\B | DT | 24 | 4 | B | 1 Prestrip - Thick | 100 | 55.0586 | 55.0586 | 2016-07-01 | 2016-07-07 10:27 | 394120.1909 | 394120 | [7 empty] | 0 | 0 | 24.56 | 10.56 | 5336.63
TS6060#1 | BW\23\006\B | BW | 23 | 6 | B | 1 Prestrip - Thick | 27.4358 | 23.5127 | 23.5127 | 2016-07-01 | 2016-07-08 10:42 | 196290.4569 | 196290 | [7 empty] | 0 | 0 | 12.37 | 10.79 | 5455.07
TS5500Exc | MW\23\009\A | MW | 23 | 9 | A | 1 Prestrip - Thick | 24.5651 | 12.052 | 12.052 | 2016-07-01 | 2016-07-03 09:25 | 54939.5971 | 54940 | [7 empty] | 0 | 0 | 3.3 | 10.46 | 5444.74
TS5500Shv | MW\20\012\D | MW | 20 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-07-01 03:31 | 2016-07-04 17:51 | 113115.2484 | [6 empty] | 113115 | 85730 | 4.44 | 0 | 0 | 5.59 | 5920
DRE1 | SC\26\005\D | SC | 26 | 5 | D | 6 DL | 100 | 0 | 100 | 2016-07-03 02:27 | 2016-07-11 12:26 | 724359.049 |  |  |  | 60886 | 724359 | 477931 |  |  | 0 | 45 | 0 | 6.09 | 5879.97
TS5500Exc | SC\26\003\D | SC | 26 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-07-03 09:25 | 2016-07-06 13:10 | 102546.5831 | [6 empty] | 102547 | 77751 | 4.86 | 0 | 0 | 6.33 | 5858
DRE2 | BW\20\008\D | BW | 20 | 8 | D | 6 DL | 100 | 100 | 100 | 2016-07-04 01:47 | 2016-07-09 15:42 | 462465.9907 |  |  |  | 20170 | 462466 | 333685 |  |  | 0 | 22.13 | 0 | 5.77 | 5907.74
TS5500Shv | MW\21\009\B | MW | 21 | 9 | B | 8 Coal Mining | 12.2 | 0 | 12.2 | 2016-07-04 17:51 | 2016-07-05 02:20 | 11132.2159 | [6 empty] | 11132 | 7735 | 0.48 | 0 | 0 | 21.05 | 4615
TS5500Shv | DT\24\001\B | DT | 24 | 1 | B | 1 Prestrip - Thick | 89.3187 | 83.8791 | 83.8791 | 2016-07-05 02:20 | 2016-08-01 | 742590.4675 | 742590 | [7 empty] | 0 | 0 | 36.88 | 11.34 | 5359.39
PH4100A | RS\01\003\D | RS | 1 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-07-06 06:16 | 2016-07-21 03:01 | 624675.3296 | 624675 | [7 empty] | 0 | 0 | 28.17 | 6 | 5887.03
TS5500Exc | SC\26\004\D | SC | 26 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-07-06 13:10 | 2016-07-08 22:46 | 77961.2214 | [6 empty] | 77961 | 58733 | 4.89 | 0 | 0 | 6.17 | 5872
TS Fleet 5 | BW\23\002\B | BW | 23 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-07-07 03:08 | 2016-07-20 11:20 | 645532.4699 | 645532 | [7 empty] | 0 | 0 | 26.26 | 11.4 | 5378.19
PH4100XPC#1 | DT\24\005\B | DT | 24 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-07-07 10:27 | 2016-07-21 22:56 | 872015.0784 | 872015 | [7 empty] | 0 | 0 | 51.92 | 11.48 | 5315.82
TS6060#1 | BW\22\007\B | BW | 22 | 7 | B | 8 Coal Mining | 100 | 0 | 49.5 | 2016-07-08 10:42 | 2016-07-09 15:48 | 42336.0746 | [6 empty] | 42336 | 30618 | 1.92 | 0 | 0 | 11.93 | 5367
TS5500Exc | SC\30\004\B | SC | 30 | 4 | B | 8 Coal Mining | 91.3 | 0 | 91.3 | 2016-07-08 22:46 | 2016-07-11 13:45 | 85240.4855 | [6 empty] | 85240 | 63076 | 3.29 | 0 | 0 | 9.04 | 5569
DRE2 | BW\20\007\D | BW | 20 | 7 | D | 6 DL | 100 | 100 | 100 | 2016-07-09 15:42 | 2016-07-15 09:14 | 474980.5559 |  |  |  | 20716 | 474981 | 342715 |  |  | 0 | 22.76 | 0 | 5.44 | 5935.64
TS6060#1 | BW\22\008\B | BW | 22 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-07-09 15:48 | 2016-07-12 03:20 | 86572.627 | [6 empty] | 86573 | 62246 | 3.89 | 0 | 0 | 13.45 | 5233
DRE1 | SC\26\006\D | SC | 26 | 6 | D | 6 DL | 100 | 0 | 100 | 2016-07-11 12:26 | 2016-07-19 22:59 | 726444.2355 |  |  |  | 61062 | 726444 | 479307 |  |  | 0 | 45 | 0 | 5.8 | 5904.06
TS5500Exc | SC\30\004\B | SC | 30 | 4 | B | 8 Coal Mining | 8.7 | 0 | 8.7 | 2016-07-11 13:45 | 2016-07-11 19:46 | 8149.3925 | [6 empty] | 8149 | 6030 | 0.31 | 0 | 0 | 9.04 | 5569
TS5500Exc | SC\26\005\D | SC | 26 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-07-11 19:46 | 2016-07-14 07:06 | 80322.5294 | [6 empty] | 80323 | 60416 | 5.03 | 0 | 0 | 6.09 | 5880
TS6060#1 | BW\22\009\B | BW | 22 | 9 | B | 8 Coal Mining | 55.1 | 0 | 55.1 | 2016-07-12 03:20 | 2016-07-13 11:40 | 47025.6709 | [6 empty] | 47026 | 33879 | 2.12 | 0 | 0 | 13.73 | 5197
TS6060#1 | BW\22\001\B | BW | 22 | 1 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-07-13 11:40 | 2016-07-16 01:38 | 90140.9521 | [6 empty] | 90141 | 65611 | 3.96 | 0 | 0 | 11.12 | 5389
TS5500Exc | SC\30\005\B | SC | 30 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-07-14 07:06 | 2016-07-15 22:18 | 53057.157 | [6 empty] | 53057 | 39177 | 3.23 | 0 | 0 | 9.24 | 5553
DRE2 | BW\20\006\D | BW | 20 | 6 | D | 6 DL | 100 | 100 | 100 | 2016-07-15 09:14 | 2016-07-21 12:47 | 509536.2373 |  |  |  | 22223 | 509536 | 367648 |  |  | 0 | 24.44 | 0 | 5.46 | 5934.28
TS5500Exc | MW\21\010\A | MW | 21 | 10 | A | 8 Coal Mining | 100 | 0 | 100 | 2016-07-15 22:18 | 2016-07-16 16:18 | 24354.7284 | [6 empty] | 24355 | 17563 | 1.12 | 0 | 0 | 13.47 | 5265
TS6060#1 | BW\22\010\B | BW | 22 | 10 | B | 8 Coal Mining | 59.7 | 0 | 59.7 | 2016-07-16 01:38 | 2016-07-17 12:17 | 50390.923 | [6 empty] | 50391 | 36795 | 2.3 | 0 | 0 | 11.83 | 5338
TS5500Exc | MW\22\003\A | MW | 22 | 3 | A | 8 Coal Mining | 80.4 | 0 | 80.4 | 2016-07-16 16:18 | 2016-07-18 16:40 | 65489.3702 | [6 empty] | 65489 | 48497 | 3.01 | 0 | 0 | 9.11 | 5508
TS6060#1 | DT\23\006\B | DT | 23 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-07-17 12:17 | 2016-07-18 13:41 | 36932.7577 | [6 empty] | 36933 | 27375 | 2.97 | 0 | 0 | 8.44 | 5579
TS6060#1 | BW\22\002\B | BW | 22 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-07-18 13:41 | 2016-07-21 00:03 | 84896.5844 | [6 empty] | 84897 | 61661 | 3.86 | 0 | 0 | 11.45 | 5360
TS5500Exc | MW\22\007\B | MW | 22 | 7 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2016-07-18 16:40 | 2016-07-19 12:31 | 26847.6574 | [6 empty] | 26848 | 19782 | 1.24 | 0 | 0 | 9.88 | 5530
TS5500Exc | MW\22\008\B | MW | 22 | 8 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2016-07-19 12:31 | 2016-07-20 10:29 | 29749.2266 | [6 empty] | 29749 | 21890 | 1.36 | 0 | 0 | 10.15 | 5496
DRE1 | SC\26\007\D | SC | 26 | 7 | D | 6 DL | 100 | 0 | 100 | 2016-07-19 22:59 | 2016-07-28 09:33 | 726423.9566 |  |  |  | 61060 | 726424 | 479293 |  |  | 0 | 45 | 0 | 5.6 | 5921.26
TS5500Exc | SC\26\006\D | SC | 26 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-07-20 10:29 | 2016-07-22 19:38 | 77362.1958 | [6 empty] | 77362 | 58656 | 4.89 | 0 | 0 | 5.8 | 5904
TS Fleet 5 | BW\23\003\X1 | BW | 23 | 3 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-07-20 11:20 | 2016-07-28 05:06 | 374502.0974 | 374502 | [7 empty] | 0 | 0 | 23.18 | 12.14 | 5303.59
TS6060#1 | BW\22\005\X1 | BW | 22 | 5 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2016-07-21 00:03 | 2016-07-21 13:25 | 19432.6423 | [6 empty] | 19433 | 14295 | 0.88 | 0 | 0 | 11.24 | 5401
PH4100A | RS\01\004\D | RS | 1 | 4 | D | 1 Prestrip - Thick | 100 | 64.59 | 64.59 | 2016-07-21 03:01 | 2016-08-01 | 457527.7459 | 457528 | [7 empty] | 0 | 0 | 18.16 | 6.26 | 5866.8
DRE2 | BW\20\005\D | BW | 20 | 5 | D | 6 DL | 100 | 100 | 100 | 2016-07-21 12:47 | 2016-07-27 11:05 | 491433.6732 |  |  |  | 21433 | 491434 | 354586 |  |  | 0 | 23.56 | 0 | 5.66 | 5917.42
TS6060#1 | BW\22\006\B | BW | 22 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-07-21 13:25 | 2016-07-23 22:42 | 83314.6109 | [6 empty] | 83315 | 60582 | 3.78 | 0 | 0 | 11.08 | 5430
PH4100XPC#1 | MW\21\010\B | MW | 21 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-07-21 22:56 | 2016-07-22 14:27 | 37627.5634 | 37628 | [7 empty] | 0 | 0 | 2.38 | 19.61 | 4767.68
PH4100XPC#1 | BW\22\005\X2 | BW | 22 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2016-07-22 14:27 | 2016-07-24 23:18 | 137867.246 | 137867 | [7 empty] | 0 | 0 | 8.52 | 0 | 0
TS5500Exc | MW\21\010\B | MW | 21 | 10 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2016-07-22 19:38 | 2016-07-24 04:01 | 43819.3754 | [6 empty] | 43819 | 30694 | 1.92 | 0 | 0 | 19.61 | 4768
TS6060#1 | DT\23\007\A | DT | 23 | 7 | A | 8 Coal Mining | 100 | 0 | 60.3 | 2016-07-23 22:42 | 2016-07-25 07:21 | 47495.6735 | [6 empty] | 47496 | 34989 | 2.3 | 0 | 0 | 9.93 | 5433
TS5500Exc | MW\22\009\A | MW | 22 | 9 | A | 8 Coal Mining | 24.9 | 0 | 24.9 | 2016-07-24 04:01 | 2016-07-24 11:29 | 10102.8624 | [6 empty] | 10103 | 7389 | 0.45 | 0 | 0 | 11.34 | 5399
TS5500Exc | MW\22\010\A | MW | 22 | 10 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2016-07-24 11:29 | 2016-07-25 03:23 | 21537.1213 | [6 empty] | 21537 | 15628 | 0.93 | 0 | 0 | 12.19 | 5355
PH4100XPC#1 | BW\22\005\B | BW | 22 | 5 | B | 1 Prestrip - Thick | 100 | 86.0949 | 86.0949 | 2016-07-24 23:18 | 2016-08-01 | 409126.9067 | 409127 | [7 empty] | 0 | 0 | 25.51 | 11 | 5433.84
TS5500Exc | MW\22\011\B | MW | 22 | 11 | B | 8 Coal Mining | 46 | 0 | 5.8 | 2016-07-25 03:23 | 2016-07-25 07:21 | 5374.1131 | [6 empty] | 5374 | 3787 | 0.24 | 0 | 0 | 18.83 | 4826
TS6060#1 | BW\23\006\B | BW | 23 | 6 | B | 1 Prestrip - Thick | 5.1411 | 5.1411 | 5.1411 | 2016-07-25 07:21 | 2016-07-26 22:26 | 42919.2739 | 42919 | [7 empty] | 0 | 0 | 2.71 | 10.79 | 5455.07
TS5500Exc | MW\23\012\A | MW | 23 | 12 | A | 1 Prestrip - Thick | 45.0762 | 24.6287 | 24.6287 | 2016-07-25 07:21 | 2016-08-01 | 153485.9539 | 153486 | [7 empty] | 0 | 0 | 9.74 | 10.88 | 5453.98
TS6060#1 | BW\23\008\B | BW | 23 | 8 | B | 1 Prestrip - Thick | 24.6015 | 15.3036 | 15.3036 | 2016-07-26 22:26 | 2016-08-01 | 134132.1736 | 134132 | [7 empty] | 0 | 0 | 7.29 | 12.45 | 5312.47
DRE2 | BW\20\004\D | BW | 20 | 4 | D | 6 DL | 100 | 76.4938 | 76.4938 | 2016-07-27 11:05 | 2016-08-01 | 376096.3599 |  |  |  | 16403 | 376096 | 271366 |  |  | 0 | 23.56 | 0 | 6.19 | 5871.63
TS Fleet 5 | BW\23\004\X1 | BW | 23 | 4 | X1 | 1 Prestrip - Thick | 100 | 43.0439 | 43.0439 | 2016-07-28 05:06 | 2016-08-01 | 183225.7577 | 183226 | [7 empty] | 0 | 0 | 11.45 | 10.86 | 5422.79
DRE1 | SC\27\013\D | SC | 27 | 13 | D | 6 DL | 100 | 0 | 42.1061 | 2016-07-28 09:33 | 2016-08-01 | 310013.2315 |  |  |  | 17177 | 310013 | 134674 |  |  | 0 | 40 | 0 | 7.44 | 5758.53
| EOP 31 : 2016\Jul | EOP 31 : 2016 | Jul | [6 empty] | 2016-08-01 | 2016-08-01 |  | 6006103 |  |  | 327453 | 5237555 | 3544479 | 1424700 | 1050584 | 69.69 | 0 | 324.64 | 8.95 | 5612.67
TS Fleet 5 | BW\23\004\X1 | BW | 23 | 4 | X1 | 1 Prestrip - Thick | 100 | 56.9561 | 56.9561 | 2016-08-01 | 2016-08-05 22:36 | 242446.4051 | 242446 | [7 empty] | 0 | 0 | 15.15 | 10.86 | 5422.79
DRE1 | SC\27\013\D | SC | 27 | 13 | D | 6 DL | 100 | 0 | 57.8939 | 2016-08-01 | 2016-08-05 22:51 | 426252.8483 |  |  |  | 23618 | 426253 | 185170 |  |  | 0 | 40 | 0 | 7.44 | 5758.53
PH4100A | RS\01\004\D | RS | 1 | 4 | D | 1 Prestrip - Thick | 100 | 35.41 | 35.41 | 2016-08-01 | 2016-08-06 21:11 | 250829.4783 | 250829 | [7 empty] | 0 | 0 | 9.96 | 6.26 | 5866.8
DRE2 | BW\20\004\D | BW | 20 | 4 | D | 6 DL | 100 | 23.5062 | 23.5062 | 2016-08-01 | 2016-08-02 09:27 | 115572.9844 |  |  |  | 5041 | 115573 | 83390 |  |  | 0 | 23.56 | 0 | 6.19 | 5871.63
TS5500Shv | DT\24\001\B | DT | 24 | 1 | B | 1 Prestrip - Thick | 89.3187 | 5.4396 | 5.4396 | 2016-08-01 | 2016-08-02 17:17 | 48157.6233 | 48158 | [7 empty] | 0 | 0 | 2.39 | 11.34 | 5359.39
PH4100XPC#1 | BW\22\005\B | BW | 22 | 5 | B | 1 Prestrip - Thick | 100 | 13.9051 | 13.9051 | 2016-08-01 | 2016-08-02 02:53 | 66077.7536 | 66078 | [7 empty] | 0 | 0 | 4.12 | 11 | 5433.84
TS6060#1 | BW\23\008\B | BW | 23 | 8 | B | 1 Prestrip - Thick | 24.6015 | 9.298 | 9.298 | 2016-08-01 | 2016-08-04 00:50 | 81494.4206 | 81494 | [7 empty] | 0 | 0 | 4.43 | 12.45 | 5312.47
TS5500Exc | MW\23\012\A | MW | 23 | 12 | A | 1 Prestrip - Thick | 45.0762 | 20.4475 | 20.4475 | 2016-08-01 | 2016-08-06 11:32 | 127428.3163 | 127428 | [7 empty] | 0 | 0 | 8.09 | 10.88 | 5453.98
PH4100XPC#1 | DT\24\006\A | DT | 24 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-08-02 02:53 | 2016-08-09 09:54 | 420858.4109 | 420858 | [7 empty] | 0 | 0 | 35.04 | 10.94 | 5367.71
DRE2 | BW\20\003\D | BW | 20 | 3 | D | 6 DL | 100 | 100 | 100 | 2016-08-02 09:27 | 2016-08-08 04:39 | 480683.4496 |  |  |  | 20964 | 480683 | 346829 |  |  | 0 | 22.98 | 0 | 6.9 | 5808.59
TS5500Shv | RS\01\003\D | RS | 1 | 3 | D | 7 PostStrip | 61.3434 | 0 | 61.3434 | 2016-08-02 17:17 | 2016-08-05 01:00 | 65060.6639 |  |  | 65061 | [5 empty] | 0 | 0 | 0 | 6 | 5887.03
TS6060#1 | DT\23\007\A | DT | 23 | 7 | A | 8 Coal Mining | 100 | 0 | 39.7 | 2016-08-04 00:50 | 2016-08-04 22:02 | 31249.0177 | [6 empty] | 31249 | 23020 | 1.51 | 0 | 0 | 9.93 | 5433
TS6060#1 | BW\22\003\X1 | BW | 22 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2016-08-04 22:02 | 2016-08-05 15:44 | 26101.5293 | [6 empty] | 26102 | 19004 | 1.18 | 0 | 0 | 12.68 | 5245
TS5500Shv | DT\23\007\B | DT | 23 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-08-05 01:00 | 2016-08-06 17:23 | 47183.4168 | 47183 | [7 empty] | 0 | 0 | 3.1 | 8.06 | 5625.8
TS6060#1 | BW\22\004\X1 | BW | 22 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2016-08-05 15:44 | 2016-08-06 10:10 | 27186.7581 | [6 empty] | 27187 | 19960 | 1.25 | 0 | 0 | 11.33 | 5375
TS Fleet 5 | BW\22\003\X2 | BW | 22 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2016-08-05 22:36 | 2016-08-09 04:42 | 159634.389 | 159634 | [7 empty] | 0 | 0 | 9.98 | 0 | 0
DRE1 | SC\27\012\D | SC | 27 | 12 | D | 6 DL | 100 | 0 | 100 | 2016-08-05 22:51 | 2016-08-13 07:08 | 632202.1119 |  |  |  | 48076 | 632202 | 432686 |  |  | 0 | 40 | 0 | 7.46 | 5757
TS6060#1 | BW\22\010\B | BW | 22 | 10 | B | 8 Coal Mining | 40.3 | 0 | 40.3 | 2016-08-06 10:10 | 2016-08-07 09:13 | 34000.898 | [6 empty] | 34001 | 24827 | 1.55 | 0 | 0 | 11.83 | 5338
TS5500Exc | SC\26\007\D | SC | 26 | 7 | D | 8 Coal Mining | 28.5 | 0 | 28.5 | 2016-08-06 11:32 | 2016-08-07 03:08 | 21413.33 | [6 empty] | 21413 | 16341 | 1.36 | 0 | 0 | 5.6 | 5921
TS5500Shv | RS\01\003\D | RS | 1 | 3 | D | 7 PostStrip | 38.6566 | 0 | 38.6566 | 2016-08-06 17:23 | 2016-08-08 04:29 | 40999.1751 |  |  | 40999 | [5 empty] | 0 | 0 | 0 | 6 | 5887.03
PH4100A | RS\01\005\D | RS | 1 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-08-06 21:11 | 2016-08-30 16:54 | 1019283.287 | 1019283 | [7 empty] | 0 | 0 | 32.85 | 6.29 | 5865.03
TS5500Exc | SC\27\013\D | SC | 27 | 13 | D | 7 PostStrip | 100 | 0 | 100 | 2016-08-07 03:08 | 2016-08-09 04:14 | 47307.5615 |  |  | 47308 | [5 empty] | 0 | 0 | 0 | 7.44 | 5758.53
TS6060#1 | BW\22\011\B | BW | 22 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-08-07 09:13 | 2016-08-10 01:19 | 94522.2883 | [6 empty] | 94522 | 68718 | 4.3 | 0 | 0 | 12.79 | 5255
TS5500Shv | MW\21\009\B | MW | 21 | 9 | B | 8 Coal Mining | 28 | 0 | 28 | 2016-08-08 04:29 | 2016-08-08 23:43 | 25547.0345 | [6 empty] | 25547 | 17750 | 1.1 | 0 | 0 | 21.05 | 4615
DRE2 | BW\20\002\D | BW | 20 | 2 | D | 6 DL | 100 | 100 | 100 | 2016-08-08 04:39 | 2016-08-13 13:18 | 444311.241 |  |  |  | 19378 | 444311 | 320586 |  |  | 0 | 21.25 | 0 | 6.42 | 5849.38
TS5500Shv | RS\01\004\D | RS | 1 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2016-08-08 23:43 | 2016-08-13 20:26 | 136320.373 |  |  | 136320 | [5 empty] | 0 | 0 | 0 | 6.26 | 5866.8
TS5500Exc | RS\01\003\D | RS | 1 | 3 | D | 8 Coal Mining | 26.1 | 0 | 26.1 | 2016-08-09 04:14 | 2016-08-09 18:41 | 19837.3391 | [6 empty] | 19837 | 14570 | 0.87 | 0 | 0 | 6 | 5887
TS Fleet 5 | BW\22\003\B | BW | 22 | 3 | B | 1 Prestrip - Thick | 42.1507 | 42.1507 | 42.1507 | 2016-08-09 04:42 | 2016-08-12 21:29 | 181467.2976 | 181467 | [7 empty] | 0 | 0 | 11.41 | 10.86 | 5413.31
PH4100XPC#1 | MW\21\009\D | MW | 21 | 9 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2016-08-09 09:54 | 2016-08-09 09:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | BW\22\004\X2 | BW | 22 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2016-08-09 09:54 | 2016-08-12 00:09 | 152979.958 | 152980 | [7 empty] | 0 | 0 | 9.58 | 0 | 0
TS5500Exc | BW\22\003\B | BW | 22 | 3 | B | 1 Prestrip - Thick | 100 | 22.1786 | 22.1786 | 2016-08-09 18:41 | 2016-08-13 21:46 | 95483.5272 | 95484 | [7 empty] | 0 | 0 | 6 | 10.86 | 5413.31
TS6060#1 | BW\22\003\B | BW | 22 | 3 | B | 1 Prestrip - Thick | 100 | 24.1404 | 24.1404 | 2016-08-10 01:19 | 2016-08-13 21:46 | 103929.2614 | 103929 | [7 empty] | 0 | 0 | 6.53 | 10.86 | 5413.31
PH4100XPC#1 | BW\22\004\B | BW | 22 | 4 | B | 1 Prestrip - Thick | 100 | 52.5617 | 52.5617 | 2016-08-12 00:09 | 2016-08-16 02:39 | 242061.8469 | 242062 | [7 empty] | 0 | 0 | 15.13 | 10.93 | 5425.74
TS Fleet 5 | BW\22\003\B | BW | 22 | 3 | B | 1 Prestrip - Thick | 34.2241 | 11.5303 | 11.5303 | 2016-08-12 21:29 | 2016-08-13 21:46 | 49640.499 | 49640 | [7 empty] | 0 | 0 | 3.12 | 10.86 | 5413.31
DRE1 | SC\27\011\D | SC | 27 | 11 | D | 6 DL | 100 | 0 | 100 | 2016-08-13 07:08 | 2016-08-20 15:33 | 632699.4601 |  |  |  | 48114 | 632699 | 433026 |  |  | 0 | 40 | 0 | 7.36 | 5766.67
DRE2 | BW\20\001\D | BW | 20 | 1 | D | 6 DL | 100 | 100 | 100 | 2016-08-13 13:18 | 2016-08-18 13:57 | 416634.9556 |  |  |  | 16045 | 416635 | 199649 |  |  | 0 | 21.39 | 0 | 5.96 | 5890.46
TS5500Shv | MW\22\003\A | MW | 22 | 3 | A | 8 Coal Mining | 19.6 | 0 | 19.6 | 2016-08-13 20:26 | 2016-08-14 08:26 | 15945.1391 | [6 empty] | 15945 | 11808 | 0.73 | 0 | 0 | 9.11 | 5508
TS6060#1 | BW\22\004\B | BW | 22 | 4 | B | 1 Prestrip - Thick | 100 | 12.9072 | 12.9072 | 2016-08-13 21:46 | 2016-08-16 02:39 | 59441.5473 | 59442 | [7 empty] | 0 | 0 | 3.71 | 10.93 | 5425.74
TS5500Exc | BW\22\004\B | BW | 22 | 4 | B | 1 Prestrip - Thick | 100 | 11.0633 | 11.0633 | 2016-08-13 21:46 | 2016-08-16 02:39 | 50949.8977 | 50950 | [7 empty] | 0 | 0 | 3.18 | 10.93 | 5425.74
TS Fleet 5 | BW\22\004\B | BW | 22 | 4 | B | 1 Prestrip - Thick | 29.8022 | 23.4677 | 23.4677 | 2016-08-13 21:46 | 2016-08-16 02:39 | 108075.5406 | 108076 | [7 empty] | 0 | 0 | 6.75 | 10.93 | 5425.74
TS5500Shv | MW\22\004\A | MW | 22 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2016-08-14 08:26 | 2016-08-16 09:37 | 65340.9298 | [6 empty] | 65341 | 48401 | 2.82 | 0 | 0 | 9.27 | 5523
TS Fleet 5 | BW\23\005\X1 | BW | 23 | 5 | X1 | 1 Prestrip - Thick | 71.056 | 71.056 | 71.056 | 2016-08-16 02:39 | 2016-08-21 04:10 | 248385.6535 | 248386 | [7 empty] | 0 | 0 | 15.48 | 10.47 | 5467.33
PH4100XPC#1 | MW\22\003\B | MW | 22 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-08-16 02:39 | 2016-08-16 22:03 | 47675.8393 | 47676 | [7 empty] | 0 | 0 | 2.96 | 8.17 | 5633.15
TS6060#1 | BW\22\005\B | BW | 22 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-08-16 02:39 | 2016-08-18 11:01 | 83136.135 | [6 empty] | 83136 | 60580 | 3.78 | 0 | 0 | 11 | 5434
TS5500Exc | RS\01\004\D | RS | 1 | 4 | D | 8 Coal Mining | 17 | 0 | 17 | 2016-08-16 02:39 | 2016-08-16 15:32 | 17689.0272 | [6 empty] | 17689 | 12807 | 0.64 | 0 | 0 | 6.26 | 5867
TS5500Shv | MW\22\005\B | MW | 22 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-08-16 09:37 | 2016-08-17 08:47 | 30790.423 | [6 empty] | 30790 | 22539 | 1.08 | 0 | 0 | 11.31 | 5424
TS5500Exc | SC\26\007\D | SC | 26 | 7 | D | 8 Coal Mining | 71.5 | 0 | 71.5 | 2016-08-16 15:32 | 2016-08-18 06:45 | 53809.7081 | [6 empty] | 53810 | 41062 | 3.42 | 0 | 0 | 5.6 | 5921
PH4100XPC#1 | MW\22\004\B | MW | 22 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-08-16 22:03 | 2016-08-17 16:26 | 45174.9734 | 45175 | [7 empty] | 0 | 0 | 2.73 | 8.84 | 5602.83
TS5500Shv | MW\22\003\B | MW | 22 | 3 | B | 8 Coal Mining | 45.9 | 0 | 45.9 | 2016-08-17 08:47 | 2016-08-18 06:56 | 29419.4375 | [6 empty] | 29419 | 21885 | 1.36 | 0 | 0 | 8.17 | 5633
PH4100XPC#1 | DT\24\007\A | DT | 24 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-08-17 16:26 | 2016-08-25 11:08 | 442127.0438 | 442127 | [7 empty] | 0 | 0 | 26.92 | 10.14 | 5424.72
TS5500Exc | MW\22\003\B | MW | 22 | 3 | B | 8 Coal Mining | 54.1 | 0 | 54.1 | 2016-08-18 06:45 | 2016-08-19 07:59 | 34638.6044 | [6 empty] | 34639 | 25768 | 1.6 | 0 | 0 | 8.17 | 5633
TS5500Shv | MW\21\010\B | MW | 21 | 10 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2016-08-18 06:56 | 2016-08-19 14:52 | 42420.8847 | [6 empty] | 42421 | 29714 | 1.86 | 0 | 0 | 19.61 | 4768
TS6060#1 | BW\20\011\D | BW | 20 | 11 | D | 8 Coal Mining | 52.1 | 0 | 52.1 | 2016-08-18 11:01 | 2016-08-20 00:10 | 54764.8969 | [6 empty] | 54765 | 41017 | 2.56 | 0 | 0 | 7.65 | 5742
DRE2 | DT\21\004\D | DT | 21 | 4 | D | 6 DL | 100 | 100 | 100 | 2016-08-18 13:57 | 2016-08-24 17:52 | 510806.0154 |  |  |  | 22278 | 510806 | 368564 |  |  | 0 | 24.44 | 0 | 5.68 | 5913.53
TS5500Exc | MW\22\004\B | MW | 22 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2016-08-19 07:59 | 2016-08-20 07:10 | 31821.4398 | [6 empty] | 31821 | 23597 | 1.46 | 0 | 0 | 8.84 | 5603
TS5500Shv | MW\22\004\B | MW | 22 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2016-08-19 14:52 | 2016-08-20 14:03 | 30805.8619 | [6 empty] | 30806 | 22844 | 1.41 | 0 | 0 | 8.84 | 5603
TS6060#1 | DT\23\007\B | DT | 23 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-08-20 00:10 | 2016-08-21 17:26 | 60862.3161 | [6 empty] | 60862 | 45310 | 2.98 | 0 | 0 | 8.06 | 5626
TS5500Exc | SC\27\012\D | SC | 27 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-08-20 07:10 | 2016-08-22 12:48 | 73594.9891 | [6 empty] | 73595 | 54828 | 4.57 | 0 | 0 | 7.46 | 5757
TS5500Shv | MW\22\007\B | MW | 22 | 7 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2016-08-20 14:03 | 2016-08-21 09:37 | 25990.8173 | [6 empty] | 25991 | 19151 | 1.2 | 0 | 0 | 9.88 | 5530
DRE1 | SC\27\010\D | SC | 27 | 10 | D | 6 DL | 100 | 0 | 100 | 2016-08-20 15:33 | 2016-08-28 00:29 | 634530.9989 |  |  |  | 48253 | 634531 | 434280 |  |  | 0 | 40 | 0 | 7.02 | 5796.73
TS Fleet 5 | BW\23\006\B | BW | 23 | 6 | B | 1 Prestrip - Thick | 3.8236 | 3.8236 | 3.8236 | 2016-08-21 04:10 | 2016-08-21 19:47 | 31920.2881 | 31920 | [7 empty] | 0 | 0 | 2.01 | 10.79 | 5455.07
TS5500Shv | MW\22\008\B | MW | 22 | 8 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2016-08-21 09:37 | 2016-08-22 07:17 | 28799.7832 | [6 empty] | 28800 | 21191 | 1.32 | 0 | 0 | 10.15 | 5496
TS6060#1 | BW\20\007\D | BW | 20 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-08-21 17:26 | 2016-08-24 15:26 | 103223.435 | [6 empty] | 103223 | 78492 | 4.91 | 0 | 0 | 5.44 | 5936
TS Fleet 5 | BW\23\006\B | BW | 23 | 6 | B | 1 Prestrip - Thick | 63.5995 | 59.7926 | 59.7926 | 2016-08-21 19:47 | 2016-09-01 | 499165.9271 | 499166 | [7 empty] | 0 | 0 | 31.46 | 10.79 | 5455.07
TS5500Shv | MW\22\009\A | MW | 22 | 9 | A | 8 Coal Mining | 51 | 0 | 51 | 2016-08-22 07:17 | 2016-08-22 22:53 | 20729.9259 | [6 empty] | 20730 | 15161 | 0.92 | 0 | 0 | 11.34 | 5399
TS5500Exc | SC\27\011\D | SC | 27 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-08-22 12:48 | 2016-08-24 20:38 | 76644.6026 | [6 empty] | 76645 | 57147 | 4.76 | 0 | 0 | 7.36 | 5767
TS5500Shv | DT\24\002\A2 | DT | 24 | 2 | A2 | 1 Prestrip - Thick | 65.9407 | 40.3834 | 40.3834 | 2016-08-22 22:53 | 2016-09-01 | 253082.6935 | 253083 | [7 empty] | 0 | 0 | 15.71 | 17.62 | 4939.31
TS6060#1 | BW\20\008\D | BW | 20 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-08-24 15:26 | 2016-08-27 15:37 | 106441.8345 | [6 empty] | 106442 | 80613 | 5.04 | 0 | 0 | 5.77 | 5908
DRE2 | DT\21\005\D | DT | 21 | 5 | D | 6 DL | 100 | 100 | 100 | 2016-08-24 17:52 | 2016-08-30 21:30 | 509880.0397 |  |  |  | 22238 | 509880 | 367896 |  |  | 0 | 24.94 | 0 | 5.48 | 5930.89
TS5500Exc | SC\27\013\D | SC | 27 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-08-24 20:38 | 2016-08-26 09:10 | 50132.6074 | [6 empty] | 50133 | 37348 | 4.55 | 0 | 0 | 7.44 | 5759
PH4100XPC#1 | MW\22\007\D | MW | 22 | 7 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2016-08-25 11:08 | 2016-08-25 11:08 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | MW\22\008\D | MW | 22 | 8 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2016-08-25 11:08 | 2016-08-25 11:08 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | MW\24\003\A | MW | 24 | 3 | A | 1 Prestrip - Thick | 100 | 70.5261 | 70.5261 | 2016-08-25 11:08 | 2016-09-01 | 390834.6068 | 390835 | [7 empty] | 0 | 0 | 24.04 | 9.83 | 5473.32
TS5500Exc | MW\22\011\B | MW | 22 | 11 | B | 8 Coal Mining | 46 | 0 | 40.2 | 2016-08-26 09:10 | 2016-08-27 12:23 | 37336.0433 | [6 empty] | 37336 | 26308 | 1.64 | 0 | 0 | 18.83 | 4826
TS5500Exc | MW\22\012\B | MW | 22 | 12 | B | 8 Coal Mining | 10 | 0 | 10 | 2016-08-27 12:23 | 2016-08-27 18:56 | 9005.9756 | [6 empty] | 9006 | 6489 | 0.4 | 0 | 0 | 15.2 | 5116
TS6060#1 | BW\20\006\D | BW | 20 | 6 | D | 8 Coal Mining | 100 | 0 | 32.3 | 2016-08-27 15:37 | 2016-08-28 14:49 | 34209.6331 | [6 empty] | 34210 | 25971 | 1.62 | 0 | 0 | 5.46 | 5934
TS5500Exc | MW\23\003\A | MW | 23 | 3 | A | 8 Coal Mining | 50.8 | 0 | 34.3 | 2016-08-27 18:56 | 2016-08-28 14:49 | 27287.3547 | [6 empty] | 27287 | 20180 | 1.27 | 0 | 0 | 9.44 | 5495
DRE1 | SC\27\009\D | SC | 27 | 9 | D | 6 DL | 100 | 0 | 53.361 | 2016-08-28 00:29 | 2016-09-01 | 342503.1808 |  |  |  | 26046 | 342503 | 234413 |  |  | 0 | 40 | 0 | 6.46 | 5846.3
TS6060#1 | BW\20\001\D | BW | 20 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2016-08-28 14:49 | 2016-08-31 01:20 | 65788.9664 |  |  | 65789 | [5 empty] | 0 | 0 | 0 | 5.96 | 5890.46
TS5500Exc | MW\23\012\A | MW | 23 | 12 | A | 1 Prestrip - Thick | 7.6769 | 7.6769 | 7.6769 | 2016-08-28 14:49 | 2016-08-30 16:12 | 47842.6233 | 47843 | [7 empty] | 0 | 0 | 3.04 | 10.88 | 5453.98
TS5500Exc | MW\25\003\A | MW | 25 | 3 | A | 1 Prestrip - Thick | 34.5821 | 4.9232 | 4.9232 | 2016-08-30 16:12 | 2016-09-01 | 30644.7764 | 30645 | [7 empty] | 0 | 0 | 2.03 | 10.16 | 5455.7
PH4100A | RS\01\006\D | RS | 1 | 6 | D | 1 Prestrip - Thick | 100 | 4.769 | 4.769 | 2016-08-30 16:54 | 2016-09-01 | 55250.0915 | 55250 | [7 empty] | 0 | 0 | 1.66 | 6.26 | 5894.22
DRE2 | DT\21\007\D | DT | 21 | 7 | D | 6 DL | 100 | 26.7737 | 26.7737 | 2016-08-30 21:30 | 2016-09-01 | 91478.1144 |  |  |  | 3990 | 91478 | 66005 |  |  | 0 | 24.37 | 0 | 5.44 | 5933.55
TS6060#1 | BW\23\008\B | BW | 23 | 8 | B | 1 Prestrip - Thick | 11.5305 | 2.8911 | 2.8911 | 2016-08-31 01:20 | 2016-09-01 | 25339.9888 | 25340 | [7 empty] | 0 | 0 | 1.38 | 12.45 | 5312.47
| EOP 32 : 2016\Aug | EOP 32 : 2016 | Aug | [6 empty] | 2016-09-01 | 2016-09-01 |  | 5624867 |  | 355477 | 304039 | 5237555 | 3472493 | 1424700 | 1054401 | 71.03 | 0 | 319.96 | 8.37 | 5661.12
TS Fleet 5 | BW\23\006\B | BW | 23 | 6 | B | 1 Prestrip - Thick | 63.5995 | 3.8069 | 3.8069 | 2016-09-01 | 2016-09-01 15:45 | 31780.7609 | 31781 | [7 empty] | 0 | 0 | 2 | 10.79 | 5455.07
DRE1 | SC\27\009\D | SC | 27 | 9 | D | 6 DL | 100 | 0 | 46.639 | 2016-09-01 | 2016-09-04 11:28 | 299357.2032 |  |  |  | 22765 | 299357 | 204883 |  |  | 0 | 40 | 0 | 6.46 | 5846.3
PH4100A | RS\01\006\D | RS | 1 | 6 | D | 1 Prestrip - Thick | 100 | 95.231 | 95.231 | 2016-09-01 | 2016-09-27 05:13 | 1103287.553 | 1103288 | [7 empty] | 0 | 0 | 33.24 | 6.26 | 5894.22
DRE2 | DT\21\007\D | DT | 21 | 7 | D | 6 DL | 100 | 73.2263 | 73.2263 | 2016-09-01 | 2016-09-04 00:26 | 250193.603 |  |  |  | 10912 | 250194 | 180523 |  |  | 0 | 24.37 | 0 | 5.44 | 5933.55
TS5500Shv | DT\24\002\A2 | DT | 24 | 2 | A2 | 1 Prestrip - Thick | 65.9407 | 25.5574 | 25.5574 | 2016-09-01 | 2016-09-06 19:18 | 160168.0152 | 160168 | [7 empty] | 0 | 0 | 9.94 | 17.62 | 4939.31
PH4100XPC#1 | MW\24\003\A | MW | 24 | 3 | A | 1 Prestrip - Thick | 100 | 29.4739 | 29.4739 | 2016-09-01 | 2016-09-03 18:25 | 163335.444 | 163335 | [7 empty] | 0 | 0 | 10.05 | 9.83 | 5473.32
TS6060#1 | BW\23\008\B | BW | 23 | 8 | B | 1 Prestrip - Thick | 11.5305 | 8.6394 | 8.6394 | 2016-09-01 | 2016-09-03 20:37 | 75722.2574 | 75722 | [7 empty] | 0 | 0 | 4.12 | 12.45 | 5312.47
TS5500Exc | MW\25\003\A | MW | 25 | 3 | A | 1 Prestrip - Thick | 34.5821 | 29.6589 | 29.6589 | 2016-09-01 | 2016-09-09 02:08 | 184612.8101 | 184613 | [7 empty] | 0 | 0 | 12.24 | 10.16 | 5455.7
TS Fleet 5 | BW\23\007\B | BW | 23 | 7 | B | 1 Prestrip - Thick | 91.7631 | 91.7631 | 91.7631 | 2016-09-01 15:45 | 2016-09-19 02:26 | 844053.312 | 844053 | [7 empty] | 0 | 0 | 47.18 | 11.53 | 5396.01
PH4100XPC#1 | MW\24\004\A | MW | 24 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-09-03 18:25 | 2016-09-08 01:40 | 247298.9519 | 247299 | [7 empty] | 0 | 0 | 15.46 | 9.23 | 5544.8
TS6060#1 | BW\20\006\D | BW | 20 | 6 | D | 8 Coal Mining | 100 | 0 | 67.7 | 2016-09-03 20:37 | 2016-09-05 21:51 | 71593.5117 | [6 empty] | 71594 | 54351 | 3.4 | 0 | 0 | 5.46 | 5934
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2016-09-04 00:26 | 2016-09-06 00:26
DRE1 | SC\27\003\D | SC | 27 | 3 | D | 6 DL | 100 | 0 | 100 | 2016-09-04 11:28 | 2016-09-15 20:12 | 978119.2666 |  |  |  | 54936 | 978119 | 425751 |  |  | 0 | 40 | 0 | 6.33 | 5857.97
TS6060#1 | BW\20\009\D | BW | 20 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-09-05 21:51 | 2016-09-08 16:43 | 97271.1716 | [6 empty] | 97271 | 73439 | 4.59 | 0 | 0 | 5.9 | 5894
DRE2 | MW\21\003\D | MW | 21 | 3 | D | 6 DL | 100 | 100 | 100 | 2016-09-06 00:26 | 2016-09-12 02:02 | 502790.141 |  |  |  | 21928 | 502790 | 362780 |  |  | 0 | 23.95 | 0 | 5.73 | 5908.04
TS5500Shv | DT\24\002\A2 | DT | 24 | 2 | A2 | 1 Prestrip - Thick | 34.0593 | 34.0593 | 34.0593 | 2016-09-06 19:18 | 2016-09-14 12:57 | 213449.6146 | 213450 | [7 empty] | 0 | 0 | 13.25 | 17.62 | 4939.31
PH4100XPC#1 | MW\24\005\A | MW | 24 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-09-08 01:40 | 2016-09-14 12:03 | 340848.0285 | 340848 | [7 empty] | 0 | 0 | 20.62 | 10.94 | 5408.46
TS6060#1 | BW\20\010\D | BW | 20 | 10 | D | 8 Coal Mining | 83.7 | 0 | 83.7 | 2016-09-08 16:43 | 2016-09-11 04:43 | 87260.4142 | [6 empty] | 87260 | 65563 | 4.1 | 0 | 0 | 6.71 | 5825
TS5500Exc | SC\27\010\D | SC | 27 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-09-09 02:08 | 2016-09-11 10:57 | 76894.8979 | [6 empty] | 76895 | 57607 | 4.8 | 0 | 0 | 7.02 | 5797
TS6060#1 | BW\22\003\B | BW | 22 | 3 | B | 8 Coal Mining | 89.7 | 0 | 89.7 | 2016-09-11 04:43 | 2016-09-13 07:56 | 74483.1758 | [6 empty] | 74483 | 54284 | 3.39 | 0 | 0 | 10.86 | 5413
TS5500Exc | SC\27\009\D | SC | 27 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-09-11 10:57 | 2016-09-13 20:02 | 77267.141 | [6 empty] | 77267 | 58303 | 4.86 | 0 | 0 | 6.46 | 5846
DRE2 | MW\21\004\D | MW | 21 | 4 | D | 6 DL | 100 | 100 | 100 | 2016-09-12 02:02 | 2016-09-17 08:09 | 435565.5747 |  |  |  | 18996 | 435566 | 314275 |  |  | 0 | 20.73 | 0 | 6.26 | 5861.44
TS6060#1 | BW\22\003\B | BW | 22 | 3 | B | 8 Coal Mining | 10.3 | 0 | 10.3 | 2016-09-13 07:56 | 2016-09-13 13:48 | 8537.1533 | [6 empty] | 8537 | 6222 | 0.39 | 0 | 0 | 10.86 | 5413
TS6060#1 | BW\20\005\D | BW | 20 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-09-13 13:48 | 2016-09-16 16:33 | 108714.9697 | [6 empty] | 108715 | 82266 | 5.14 | 0 | 0 | 5.66 | 5917
TS5500Exc | MW\23\003\A | MW | 23 | 3 | A | 8 Coal Mining | 50.8 | 0 | 16.5 | 2016-09-13 20:02 | 2016-09-14 05:42 | 13079.7379 | [6 empty] | 13080 | 9673 | 0.61 | 0 | 0 | 9.44 | 5495
TS5500Exc | MW\23\004\A | MW | 23 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2016-09-14 05:42 | 2016-09-15 12:44 | 42019.9669 | [6 empty] | 42020 | 31157 | 1.92 | 0 | 0 | 9.12 | 5546
PH4100XPC#1 | MW\24\006\B | MW | 24 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-09-14 12:03 | 2016-09-22 07:11 | 406883.8462 | 406884 | [7 empty] | 0 | 0 | 25.04 | 8.91 | 5654.67
TS5500Shv | RS\01\005\D | RS | 1 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2016-09-14 12:57 | 2016-09-21 05:04 | 184466.1759 |  |  | 184466 | [5 empty] | 0 | 0 | 0 | 6.29 | 5865.03
TS5500Exc | MW\23\005\A | MW | 23 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2016-09-15 12:44 | 2016-09-16 00:10 | 15479.0646 | [6 empty] | 15479 | 11398 | 0.69 | 0 | 0 | 10.59 | 5430
DRE1 | SC\27\004\D | SC | 27 | 4 | D | 6 DL | 100 | 0 | 100 | 2016-09-15 20:12 | 2016-09-23 02:34 | 625316.2175 |  |  |  | 47553 | 625316 | 427973 |  |  | 0 | 40 | 0 | 6.2 | 5868.94
TS5500Exc | SC\27\003\D | SC | 27 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2016-09-16 00:10 | 2016-09-19 00:25 | 68669.5849 |  |  | 68670 | [5 empty] | 0 | 0 | 0 | 6.33 | 5857.97
TS6060#1 | RS\01\003\D | RS | 1 | 3 | D | 8 Coal Mining | 73.9 | 0 | 73.9 | 2016-09-16 16:33 | 2016-09-18 07:09 | 56130.9431 | [6 empty] | 56131 | 41226 | 2.46 | 0 | 0 | 6 | 5887
DRE2 | MW\21\005\D | MW | 21 | 5 | D | 6 DL | 100 | 0 | 100 | 2016-09-17 08:09 | 2016-09-24 05:44 | 571836.9329 |  |  |  | 34150 | 571837 | 403675 |  |  | 0 | 26.66 | 0 | 6.59 | 5832.8
TS6060#1 | MW\21\004\D | MW | 21 | 4 | D | 8 Coal Mining | 100 | 0 | 64.8 | 2016-09-18 07:09 | 2016-09-20 00:43 | 60462.7298 | [6 empty] | 60463 | 45678 | 2.86 | 0 | 0 | 6.26 | 5861
TS5500Exc | MW\21\004\D | MW | 21 | 4 | D | 8 Coal Mining | 100 | 0 | 35.2 | 2016-09-19 00:25 | 2016-09-20 00:43 | 32883.6671 | [6 empty] | 32884 | 24843 | 1.55 | 0 | 0 | 6.26 | 5861
TS Fleet 5 | BW\23\007\B | BW | 23 | 7 | B | 1 Prestrip - Thick | 8.237 | 8.237 | 8.237 | 2016-09-19 02:26 | 2016-09-20 16:01 | 75764.9738 | 75765 | [7 empty] | 0 | 0 | 4.24 | 11.53 | 5396.01
TS5500Exc | SC\27\003\D | SC | 27 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-09-20 00:43 | 2016-09-22 17:01 | 87026.5921 | [6 empty] | 87027 | 65984 | 4.91 | 0 | 0 | 6.33 | 5858
TS6060#1 | BW\20\004\D | BW | 20 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-09-20 00:43 | 2016-09-23 06:07 | 112557.6056 | [6 empty] | 112558 | 84833 | 5.3 | 0 | 0 | 6.19 | 5872
TS Fleet 5 | BW\23\008\B | BW | 23 | 8 | B | 1 Prestrip - Thick | 63.868 | 57.0375 | 57.0375 | 2016-09-20 16:01 | 2016-10-01 | 499920.9533 | 499921 | [7 empty] | 0 | 0 | 27.17 | 12.45 | 5312.47
TS5500Shv | MW\21\003\D | MW | 21 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-09-21 05:04 | 2016-09-24 05:08 | 94423.3789 | [6 empty] | 94423 | 71682 | 4.48 | 0 | 0 | 5.73 | 5908
PH4100XPC#1 | MW\23\007\D | MW | 23 | 7 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2016-09-22 07:11 | 2016-09-22 07:11 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | MW\24\007\B | MW | 24 | 7 | B | 1 Prestrip - Thick | 100 | 99.6753 | 99.6753 | 2016-09-22 07:11 | 2016-10-01 | 460274.8753 | 460275 | [7 empty] | 0 | 0 | 28.64 | 9.78 | 5540.64
TS5500Exc | RS\01\005\D | RS | 1 | 5 | D | 8 Coal Mining | 34.7 | 0 | 34.7 | 2016-09-22 17:01 | 2016-09-24 08:28 | 53402.7073 | [6 empty] | 53403 | 38526 | 1.39 | 0 | 0 | 6.29 | 5865
DRE1 | SC\27\005\D | SC | 27 | 5 | D | 6 DL | 100 | 0 | 100 | 2016-09-23 02:34 | 2016-09-30 09:55 | 628820.6711 |  |  |  | 47819 | 628821 | 430372 |  |  | 0 | 40 | 0 | 6.08 | 5880.25
TS6060#1 | RS\01\004\D | RS | 1 | 4 | D | 8 Coal Mining | 83 | 0 | 83 | 2016-09-23 06:07 | 2016-09-25 17:19 | 86106.5164 | [6 empty] | 86107 | 62342 | 3.13 | 0 | 0 | 6.26 | 5867
TS5500Shv | MW\22\009\A | MW | 22 | 9 | A | 8 Coal Mining | 24.1 | 0 | 24.1 | 2016-09-24 05:08 | 2016-09-24 12:35 | 9780.4306 | [6 empty] | 9780 | 7153 | 0.43 | 0 | 0 | 11.34 | 5399
DRE2 | MW\21\006\D | MW | 21 | 6 | D | 6 DL | 100 | 100 | 100 | 2016-09-24 05:44 | 2016-09-30 07:22 | 502926.7295 |  |  |  | 21934 | 502927 | 362879 |  |  | 0 | 23.78 | 0 | 6.6 | 5832.24
TS5500Exc | SC\27\004\D | SC | 27 | 4 | D | 8 Coal Mining | 100 | 0 | 89.8 | 2016-09-24 08:28 | 2016-09-26 12:04 | 69857.2938 | [6 empty] | 69857 | 52628 | 4.39 | 0 | 0 | 6.2 | 5869
TS5500Shv | MW\22\010\A | MW | 22 | 10 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2016-09-24 12:35 | 2016-09-25 04:30 | 20849.7664 | [6 empty] | 20850 | 15129 | 0.9 | 0 | 0 | 12.19 | 5355
TS5500Shv | MW\22\011\B | MW | 22 | 11 | B | 8 Coal Mining | 44.5 | 0 | 44.5 | 2016-09-25 04:30 | 2016-09-26 12:03 | 41347.0662 | [6 empty] | 41347 | 29134 | 1.82 | 0 | 0 | 18.83 | 4826
TS6060#1 | BW\20\003\D | BW | 20 | 3 | D | 8 Coal Mining | 100 | 0 | 21.1 | 2016-09-25 17:19 | 2016-09-26 08:51 | 22602.3272 | [6 empty] | 22602 | 16941 | 1.06 | 0 | 0 | 6.9 | 5809
TS6060#1 | DT\21\004\D | DT | 21 | 4 | D | 8 Coal Mining | 100 | 0 | 4.7 | 2016-09-26 08:51 | 2016-09-26 12:04 | 4679.7839 | [6 empty] | 4680 | 3539 | 0.22 | 0 | 0 | 5.68 | 5914
TS5500Shv | DT\25\001\A | DT | 25 | 1 | A | 1 Prestrip - Thick | 24.2158 | 13.3753 | 13.3753 | 2016-09-26 12:03 | 2016-10-01 | 124076.1554 | 124076 | [7 empty] | 0 | 0 | 5.76 | 20.4 | 4719.49
TS6060#1 | BW\23\010\A2 | BW | 23 | 10 | A2 | 1 Prestrip - Thick | 24.6003 | 0 | 20.1457 | 2016-09-26 12:04 | 2016-10-01 | 118170.0159 | 118170 | [7 empty] | 0 | 0 | 8.28 | 0 | 0
TS5500Exc | MW\22\009\B | MW | 22 | 9 | B | 1 Prestrip - Thick | 75.4973 | 75.4973 | 75.4973 | 2016-09-26 12:04 | 2016-09-29 06:17 | 62926.9128 | 62927 | [7 empty] | 0 | 0 | 3.89 | 9.95 | 5529.76
PH4100A | RS\01\007\D | RS | 1 | 7 | D | 1 Prestrip - Thick | 100 | 12.8801 | 12.8801 | 2016-09-27 05:13 | 2016-10-01 | 159362.7657 | 159363 | [7 empty] | 0 | 0 | 4.31 | 6.74 | 5824.86
TS5500Exc | RS\01\006\D | RS | 1 | 6 | D | 7 PostStrip | 62.9276 | 0 | 20.3136 | 2016-09-29 06:17 | 2016-10-01 | 39640.2772 |  |  | 39640 | [5 empty] | 0 | 0 | 0 | 6.26 | 5894.22
DRE2 | MW\21\007\D | MW | 21 | 7 | D | 6 DL | 100 | 0 | 9.7383 | 2016-09-30 07:22 | 2016-10-01 | 57405.419 |  |  |  | 2504 | 57405 | 41420 |  |  | 0 | 28.17 | 0 | 6.09 | 5876.46
DRE1 | SC\27\006\D | SC | 27 | 6 | D | 6 DL | 100 | 0 | 8.0076 | 2016-09-30 09:55 | 2016-10-01 | 50504.6417 |  |  |  | 3841 | 50505 | 34566 |  |  | 0 | 40 | 0 | 5.84 | 5900.35
| EOP 33 : 2016\Sep | EOP 33 : 2016 | Sep | [6 empty] | 2016-10-01 | 2016-10-01 |  | 5271937 |  | 292776 | 287338 | 4902836 | 3189098 | 1424712 | 1063902 | 68.76 | 0 | 275.46 | 7.34 | 5765.51
TS Fleet 5 | BW\23\008\B | BW | 23 | 8 | B | 1 Prestrip - Thick | 63.868 | 6.8305 | 6.8305 | 2016-10-01 | 2016-10-02 07:26 | 59867.3887 | 59867 | [7 empty] | 0 | 0 | 3.25 | 12.45 | 5312.47
DRE1 | SC\27\006\D | SC | 27 | 6 | D | 6 DL | 100 | 0 | 91.9924 | 2016-10-01 | 2016-10-07 19:54 | 580201.5992 |  |  |  | 44122 | 580202 | 397096 |  |  | 0 | 40 | 0 | 5.84 | 5900.35
PH4100A | RS\01\007\D | RS | 1 | 7 | D | 1 Prestrip - Thick | 100 | 87.1199 | 87.1199 | 2016-10-01 | 2016-10-27 15:36 | 1077914.572 | 1077915 | [7 empty] | 0 | 0 | 29.15 | 6.74 | 5824.86
DRE2 | MW\21\007\D | MW | 21 | 7 | D | 6 DL | 100 | 0 | 90.2617 | 2016-10-01 | 2016-10-07 12:05 | 532073.5372 |  |  |  | 23206 | 532074 | 383909 |  |  | 0 | 28.17 | 0 | 6.09 | 5876.46
TS5500Shv | DT\25\001\A | DT | 25 | 1 | A | 1 Prestrip - Thick | 24.2158 | 10.8405 | 10.8405 | 2016-10-01 | 2016-10-04 20:37 | 100561.7504 | 100562 | [7 empty] | 0 | 0 | 4.67 | 20.4 | 4719.49
PH4100XPC#1 | MW\24\007\B | MW | 24 | 7 | B | 1 Prestrip - Thick | 100 | 0.32472 | 0.32472 | 2016-10-01 | 2016-10-01 00:42 | 1499.4536 | 1499 | [7 empty] | 0 | 0 | 0.09 | 9.78 | 5540.64
TS6060#1 | BW\23\010\A2 | BW | 23 | 10 | A2 | 1 Prestrip - Thick | 24.6003 | 0 | 4.4546 | 2016-10-01 | 2016-10-02 01:16 | 26129.4609 | 26129 | [7 empty] | 0 | 0 | 1.83 | 0 | 0
TS5500Exc | RS\01\006\D | RS | 1 | 6 | D | 7 PostStrip | 62.9276 | 0 | 42.614 | 2016-10-01 | 2016-10-04 20:38 | 83157.7541 |  |  | 83158 | [5 empty] | 0 | 0 | 0 | 6.26 | 5894.22
PH4100XPC#1 | MW\22\009\B | MW | 22 | 9 | B | 1 Prestrip - Thick | 100 | 24.5027 | 24.5027 | 2016-10-01 00:42 | 2016-10-01 09:28 | 20423.0018 | 20423 | [7 empty] | 0 | 0 | 1.26 | 9.95 | 5529.76
PH4100XPC#1 | MW\22\010\B | MW | 22 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-10-01 09:28 | 2016-10-02 02:58 | 40720.8816 | 40721 | [7 empty] | 0 | 0 | 2.5 | 9.06 | 5622.57
TS6060#1 | BW\20\003\D | BW | 20 | 3 | D | 8 Coal Mining | 100 | 0 | 78.9 | 2016-10-02 01:16 | 2016-10-04 14:39 | 84337.6513 | [6 empty] | 84338 | 63215 | 3.95 | 0 | 0 | 6.9 | 5809
PH4100XPC#1 | MW\24\008\A | MW | 24 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-10-02 02:58 | 2016-10-10 03:24 | 401676.2161 | 401676 | [7 empty] | 0 | 0 | 24.81 | 12.81 | 5167.81
TS Fleet 5 | BW\23\009\B | BW | 23 | 9 | B | 1 Prestrip - Thick | 97.3083 | 97.3083 | 97.3083 | 2016-10-02 07:26 | 2016-10-18 11:48 | 739446.6842 | 739447 | [7 empty] | 0 | 0 | 42.78 | 12.63 | 5286.29
TS6060#1 | BW\20\002\D | BW | 20 | 2 | D | 8 Coal Mining | 92.5 | 0 | 92.5 | 2016-10-04 14:39 | 2016-10-07 12:05 | 95371.2235 | [6 empty] | 95371 | 71771 | 4.48 | 0 | 0 | 6.42 | 5849
TS5500Shv | DT\25\001\A | DT | 25 | 1 | A | 1 Prestrip - Thick | 75.7842 | 75.7842 | 75.7842 | 2016-10-04 20:37 | 2016-10-31 20:10 | 703011.9178 | 703012 | [7 empty] | 0 | 0 | 32.66 | 20.4 | 4719.49
TS5500Exc | RS\01\006\D | RS | 1 | 6 | D | 7 PostStrip | 37.0724 | 0 | 37.0724 | 2016-10-04 20:38 | 2016-10-08 05:14 | 72343.6701 |  |  | 72344 | [5 empty] | 0 | 0 | 0 | 6.26 | 5894.22
TS6060#1 | BW\20\001\D | BW | 20 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-10-07 12:05 | 2016-10-10 01:04 | 83768.6976 | [6 empty] | 83769 | 63290 | 4.92 | 0 | 0 | 5.96 | 5890
DRE2 | DT\21\003\D | DT | 21 | 3 | D | 6 DL | 100 | 100 | 100 | 2016-10-07 12:05 | 2016-10-13 10:29 | 485383.5764 |  |  |  | 21169 | 485384 | 350221 |  |  | 0 | 23.22 | 0 | 6.18 | 5870.85
DRE1 | SC\27\007\D | SC | 27 | 7 | D | 6 DL | 100 | 0 | 100 | 2016-10-07 19:54 | 2016-10-15 06:17 | 631381.287 |  |  |  | 48014 | 631381 | 432124 |  |  | 0 | 40 | 0 | 5.7 | 5912.53
TS5500Exc | SC\27\004\D | SC | 27 | 4 | D | 8 Coal Mining | 100 | 0 | 10.2 | 2016-10-08 05:14 | 2016-10-08 11:26 | 7917.1947 | [6 empty] | 7917 | 5964 | 0.5 | 0 | 0 | 6.2 | 5869
TS5500Exc | MW\21\005\D | MW | 21 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-10-08 11:26 | 2016-10-11 13:06 | 94182.8288 | [6 empty] | 94183 | 70868 | 4.43 | 0 | 0 | 6.59 | 5833
TS6060#1 | BW\20\002\D | BW | 20 | 2 | D | 8 Coal Mining | 7.5 | 0 | 7.5 | 2016-10-10 01:04 | 2016-10-10 06:42 | 7724.4215 | [6 empty] | 7724 | 5813 | 0.36 | 0 | 0 | 6.42 | 5849
PH4100XPC#1 | MW\24\009\A | MW | 24 | 9 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-10-10 03:24 | 2016-10-20 08:24 | 519170.0952 | 519170 | [7 empty] | 0 | 0 | 31.25 | 10.31 | 5434.37
TS6060#1 | BW\20\010\D | BW | 20 | 10 | D | 8 Coal Mining | 16.3 | 0 | 16.3 | 2016-10-10 06:42 | 2016-10-10 19:02 | 16956.0095 | [6 empty] | 16956 | 12740 | 0.8 | 0 | 0 | 6.71 | 5825
TS6060#1 | BW\20\011\D | BW | 20 | 11 | D | 8 Coal Mining | 47.9 | 0 | 47.9 | 2016-10-10 19:02 | 2016-10-12 07:39 | 50289.8411 | [6 empty] | 50290 | 37665 | 2.35 | 0 | 0 | 7.65 | 5742
TS5500Exc | MW\21\006\D | MW | 21 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-10-11 13:06 | 2016-10-14 18:05 | 98418.9427 | [6 empty] | 98419 | 73827 | 4.61 | 0 | 0 | 6.6 | 5832
TS6060#1 | DT\21\004\D | DT | 21 | 4 | D | 8 Coal Mining | 100 | 0 | 95.3 | 2016-10-12 07:39 | 2016-10-15 04:57 | 95188.6899 | [6 empty] | 95189 | 71981 | 4.5 | 0 | 0 | 5.68 | 5914
DRE2 | DT\21\002\D | DT | 21 | 2 | D | 6 DL | 100 | 100 | 100 | 2016-10-13 10:29 | 2016-10-20 01:09 | 540818.4189 |  |  |  | 23587 | 540818 | 390219 |  |  | 0 | 21.19 | 0 | 7.07 | 5792.94
TS5500Exc | SC\27\005\D | SC | 27 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-10-14 18:05 | 2016-10-17 08:07 | 79298.0855 | [6 empty] | 79298 | 59646 | 4.97 | 0 | 0 | 6.08 | 5880
TS6060#1 | DT\21\005\D | DT | 21 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-10-15 04:57 | 2016-10-18 01:45 | 94500.7328 | [6 empty] | 94501 | 71688 | 4.64 | 0 | 0 | 5.48 | 5931
DRE1 | SC\27\008\D | SC | 27 | 8 | D | 6 DL | 100 | 0 | 100 | 2016-10-15 06:17 | 2016-10-23 12:10 | 700447.0356 |  |  |  | 48323 | 700447 | 434907 |  |  | 0 | 40 | 0 | 5.87 | 5897.73
TS5500Exc | MW\21\007\D | MW | 21 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-10-17 08:07 | 2016-10-20 11:23 | 96227.934 | [6 empty] | 96228 | 72411 | 4.53 | 0 | 0 | 6.09 | 5876
TS6060#1 | DT\21\007\D | DT | 21 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-10-18 01:45 | 2016-10-19 23:30 | 62849.9428 | [6 empty] | 62850 | 47752 | 4.5 | 0 | 0 | 5.44 | 5934
TS Fleet 5 | BW\23\009\B | BW | 23 | 9 | B | 1 Prestrip - Thick | 2.6917 | 2.6917 | 2.6917 | 2016-10-18 11:48 | 2016-10-18 22:33 | 20454.0512 | 20454 | [7 empty] | 0 | 0 | 1.18 | 12.63 | 5286.29
TS Fleet 5 | BW\23\010\A2 | BW | 23 | 10 | A2 | 1 Prestrip - Thick | 66.6025 | 0 | 66.6025 | 2016-10-18 22:33 | 2016-10-27 11:44 | 390674.4524 | 390674 | [7 empty] | 0 | 0 | 27.36 | 0 | 0
TS6060#1 | BW\22\004\B | BW | 22 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-10-19 23:30 | 2016-10-22 11:38 | 82595.6221 | [6 empty] | 82596 | 60206 | 3.76 | 0 | 0 | 10.93 | 5426
DRE2 | BW\21\011\D | BW | 21 | 11 | D | 6 DL | 100 | 100 | 100 | 2016-10-20 01:09 | 2016-10-25 12:08 | 446486.3201 |  |  |  | 19473 | 446486 | 322155 |  |  | 0 | 21.34 | 0 | 7.71 | 5737.02
PH4100XPC#1 | MW\23\010\A | MW | 23 | 10 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-10-20 08:24 | 2016-10-31 10:44 | 565804.8927 | 565805 | [7 empty] | 0 | 0 | 33.47 | 10.5 | 5478.88
TS5500Exc | SC\27\006\D | SC | 27 | 6 | D | 8 Coal Mining | 47.5 | 0 | 47.5 | 2016-10-20 11:23 | 2016-10-21 16:09 | 36772.8282 | [6 empty] | 36773 | 27859 | 2.32 | 0 | 0 | 5.84 | 5900
TS5500Exc | SC\27\006\D | SC | 27 | 6 | D | 8 Coal Mining | 52.5 | 0 | 52.5 | 2016-10-21 16:09 | 2016-10-22 23:58 | 40664.7926 | [6 empty] | 40665 | 30807 | 2.57 | 0 | 0 | 5.84 | 5900
TS6060#1 | RS\01\005\D | RS | 1 | 5 | D | 8 Coal Mining | 65.3 | 0 | 65.3 | 2016-10-22 11:38 | 2016-10-25 12:42 | 100352.6502 | [6 empty] | 100353 | 72397 | 2.61 | 0 | 0 | 6.29 | 5865
TS5500Exc | SC\27\007\D | SC | 27 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-10-22 23:58 | 2016-10-25 10:56 | 75399.9457 | [6 empty] | 75400 | 57399 | 4.78 | 0 | 0 | 5.7 | 5913
DRE1 | SC\28\013\D | SC | 28 | 13 | D | 6 DL | 100 | 0 | 79.1999 | 2016-10-23 12:10 | 2016-11-01 | 721506.8782 |  |  |  | 40087 | 721507 | 313559 |  |  | 0 | 40 | 0 | 7.47 | 5756.18
TS5500Exc | MW\23\006\B | MW | 23 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2016-10-25 10:56 | 2016-10-26 00:20 | 17126.3137 | [6 empty] | 17126 | 12616 | 0.77 | 0 | 0 | 10.2 | 5538
DRE2 | BW\21\010\D | BW | 21 | 10 | D | 6 DL | 100 | 100 | 100 | 2016-10-25 12:08 | 2016-10-31 00:57 | 452722.4636 |  |  |  | 19745 | 452722 | 326655 |  |  | 0 | 21.66 | 0 | 6.79 | 5818.45
TS6060#1 | BW\23\002\B | BW | 23 | 2 | B | 8 Coal Mining | 82.3 | 0 | 47.6 | 2016-10-25 12:42 | 2016-10-27 09:48 | 61966.8078 | [6 empty] | 61967 | 45025 | 1.83 | 0 | 0 | 11.4 | 5378
TS5500Exc | MW\23\008\B | MW | 23 | 8 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2016-10-26 00:20 | 2016-10-27 01:28 | 32118.973 | [6 empty] | 32119 | 23646 | 1.47 | 0 | 0 | 9.96 | 5506
TS5500Exc | SC\27\008\D | SC | 27 | 8 | D | 8 Coal Mining | 100 | 0 | 14.1 | 2016-10-27 01:28 | 2016-10-27 09:48 | 10669.871 | [6 empty] | 10670 | 8109 | 0.68 | 0 | 0 | 5.87 | 5898
TS6060#1 | BW\23\010\A2 | BW | 23 | 10 | A2 | 1 Prestrip - Thick | 8.7972 | 0 | 8.7972 | 2016-10-27 09:48 | 2016-10-29 11:42 | 51602.1734 | 51602 | [7 empty] | 0 | 0 | 3.61 | 0 | 0
TS5500Exc | MW\25\003\A | MW | 25 | 3 | A | 1 Prestrip - Thick | 65.4179 | 15.8972 | 15.8972 | 2016-10-27 09:48 | 2016-11-01 | 98952.678 | 98953 | [7 empty] | 0 | 0 | 6.56 | 10.16 | 5455.7
TS Fleet 5 | BW\23\011\A2 | BW | 23 | 11 | A2 | 1 Prestrip - Thick | 100 | 30.8663 | 30.8663 | 2016-10-27 11:44 | 2016-11-01 | 206133.4236 | 206133 | [7 empty] | 0 | 0 | 12.53 | 19.48 | 4707.71
PH4100A | RS\01\008\D | RS | 1 | 8 | D | 1 Prestrip - Thick | 100 | 10.7778 | 10.7778 | 2016-10-27 15:36 | 2016-11-01 | 175746.362 | 175746 | [7 empty] | 0 | 0 | 3.8 | 7.08 | 5786.41
TS6060#1 | BW\24\005\X1 | BW | 24 | 5 | X1 | 1 Prestrip - Thick | 26.8895 | 17.7341 | 17.7341 | 2016-10-29 11:42 | 2016-11-01 | 62983.9808 | 62984 | [7 empty] | 0 | 0 | 3.95 | 10.29 | 5483.03
DRE2 | BW\21\009\D | BW | 21 | 9 | D | 6 DL | 100 | 15.2587 | 15.2587 | 2016-10-31 00:57 | 2016-11-01 | 78514.0837 |  |  |  | 3424 | 78514 | 56651 |  |  | 0 | 24.53 | 0 | 5.95 | 5891.68
PH4100XPC#1 | MW\24\010\A | MW | 24 | 10 | A | 1 Prestrip - Thick | 100 | 4.5435 | 4.5435 | 2016-10-31 10:44 | 2016-11-01 | 28549.9604 | 28550 | [7 empty] | 0 | 0 | 1.7 | 10.24 | 5506.93
TS5500Shv | RS\01\007\D | RS | 1 | 7 | D | 7 PostStrip | 47.8758 | 0 | 1.9022 | 2016-10-31 20:10 | 2016-11-01 | 4169.6929 |  |  | 4170 | [5 empty] | 0 | 0 | 0 | 6.74 | 5824.86
| EOP 34 : 2016\Oct | EOP 34 : 2016 | Oct | [6 empty] | 2016-11-01 | 2016-11-01 |  | 5291323 |  | 159671 | 291149 | 5169535 | 3407495 | 1424700 | 1066695 | 70.33 | 0 | 268.43 | 7.36 | 5763.72
TS Fleet 5 | BW\23\011\A2 | BW | 23 | 11 | A2 | 1 Prestrip - Thick | 100 | 69.1337 | 69.1337 | 2016-11-01 | 2016-11-11 09:50 | 461693.6583 | 461694 | [7 empty] | 0 | 0 | 28.06 | 19.48 | 4707.71
DRE1 | SC\28\013\D | SC | 28 | 13 | D | 6 DL | 100 | 0 | 20.8001 | 2016-11-01 | 2016-11-03 06:14 | 189487.2366 |  |  |  | 10528 | 189487 | 82349 |  |  | 0 | 40 | 0 | 7.47 | 5756.18
PH4100A | RS\01\008\D | RS | 1 | 8 | D | 1 Prestrip - Thick | 100 | 71.2343 | 71.2343 | 2016-11-01 | 2016-12-01 | 1161570.505 | 1161571 | [7 empty] | 0 | 0 | 25.11 | 7.08 | 5786.41
DRE2 | BW\21\009\D | BW | 21 | 9 | D | 6 DL | 100 | 84.7413 | 84.7413 | 2016-11-01 | 2016-11-06 09:37 | 436038.7925 |  |  |  | 19017 | 436039 | 314617 |  |  | 0 | 24.53 | 0 | 5.95 | 5891.68
TS5500Shv | RS\01\007\D | RS | 1 | 7 | D | 7 PostStrip | 47.8758 | 0 | 45.9737 | 2016-11-01 | 2016-11-04 23:26 | 100778.0777 |  |  | 100778 | [5 empty] | 0 | 0 | 0 | 6.74 | 5824.86
PH4100XPC#1 | MW\24\010\A | MW | 24 | 10 | A | 1 Prestrip - Thick | 100 | 95.4565 | 95.4565 | 2016-11-01 | 2016-11-13 02:41 | 599816.8904 | 599817 | [7 empty] | 0 | 0 | 35.62 | 10.24 | 5506.93
TS6060#1 | BW\24\005\X1 | BW | 24 | 5 | X1 | 1 Prestrip - Thick | 26.8895 | 9.1554 | 9.1554 | 2016-11-01 | 2016-11-02 08:04 | 32516.2276 | 32516 | [7 empty] | 0 | 0 | 2.04 | 10.29 | 5483.03
TS5500Exc | MW\25\003\A | MW | 25 | 3 | A | 1 Prestrip - Thick | 65.4179 | 49.5207 | 49.5207 | 2016-11-01 | 2016-11-15 17:37 | 308243.0738 | 308243 | [7 empty] | 0 | 0 | 20.44 | 10.16 | 5455.7
TS6060#1 | BW\23\002\B | BW | 23 | 2 | B | 8 Coal Mining | 82.3 | 0 | 34.7 | 2016-11-02 08:04 | 2016-11-03 18:00 | 45250.1096 | [6 empty] | 45250 | 32879 | 1.34 | 0 | 0 | 11.4 | 5378
DRE1 | SC\28\012\D | SC | 28 | 12 | D | 6 DL | 100 | 0 | 100 | 2016-11-03 06:14 | 2016-11-10 18:52 | 630979.4416 |  |  |  | 47983 | 630979 | 431849 |  |  | 0 | 40 | 0 | 7.5 | 5753.14
TS6060#1 | RS\01\006\D | RS | 1 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-11-03 18:00 | 2016-11-07 23:48 | 135724.8686 | [6 empty] | 135725 | 98531 | 3.4 | 0 | 0 | 6.26 | 5894
TS5500Shv | RS\01\007\D | RS | 1 | 7 | D | 7 PostStrip | 10.4271 | 0 | 10.4271 | 2016-11-04 23:26 | 2016-11-05 21:04 | 22857.0648 |  |  | 22857 | [5 empty] | 0 | 0 | 0 | 6.74 | 5824.86
TS5500Shv | MW\22\009\B | MW | 22 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-11-05 21:04 | 2016-11-08 02:08 | 63729.8824 | [6 empty] | 63730 | 46957 | 2.92 | 0 | 0 | 9.95 | 5530
DRE2 | BW\21\008\D | BW | 21 | 8 | D | 6 DL | 100 | 100 | 100 | 2016-11-06 09:37 | 2016-11-12 04:03 | 465655.278 |  |  |  | 20309 | 465655 | 335986 |  |  | 0 | 22.22 | 0 | 5.63 | 5919.26
TS6060#1 | MW\22\010\B | MW | 22 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-11-07 23:48 | 2016-11-09 21:37 | 61079.8184 | [6 empty] | 61080 | 45187 | 2.81 | 0 | 0 | 9.06 | 5623
TS5500Shv | MW\22\011\B | MW | 22 | 11 | B | 8 Coal Mining | 9.5 | 0 | 9.5 | 2016-11-08 02:08 | 2016-11-08 09:30 | 8857.1333 | [6 empty] | 8857 | 6241 | 0.39 | 0 | 0 | 18.83 | 4826
TS5500Shv | MW\22\012\B | MW | 22 | 12 | B | 8 Coal Mining | 90 | 0 | 90 | 2016-11-08 09:30 | 2016-11-11 04:48 | 80837.4639 | [6 empty] | 80837 | 58245 | 3.56 | 0 | 0 | 15.2 | 5116
TS6060#1 | BW\23\002\B | BW | 23 | 2 | B | 8 Coal Mining | 17.7 | 0 | 17.7 | 2016-11-09 21:37 | 2016-11-10 14:53 | 23017.3017 | [6 empty] | 23017 | 16725 | 0.68 | 0 | 0 | 11.4 | 5378
TS6060#1 | BW\23\003\X1 | BW | 23 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2016-11-10 14:53 | 2016-11-11 08:24 | 23348.9195 | [6 empty] | 23349 | 17065 | 1.07 | 0 | 0 | 12.14 | 5304
DRE1 | SC\28\011\D | SC | 28 | 11 | D | 6 DL | 100 | 0 | 100 | 2016-11-10 18:52 | 2016-11-18 08:35 | 634767.1693 |  |  |  | 48271 | 634767 | 434441 |  |  | 0 | 40 | 0 | 7.41 | 5762.43
TS5500Shv | MW\23\003\A | MW | 23 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2016-11-11 04:48 | 2016-11-12 13:20 | 39078.7812 | [6 empty] | 39079 | 28900 | 1.81 | 0 | 0 | 9.44 | 5495
TS6060#1 | BW\23\004\X1 | BW | 23 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2016-11-11 08:24 | 2016-11-12 04:02 | 26171.114 | [6 empty] | 26171 | 19277 | 1.21 | 0 | 0 | 10.86 | 5423
TS Fleet 5 | BW\23\010\B | BW | 23 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-11-11 09:50 | 2016-11-12 16:05 | 55915.3048 | 55915 | [7 empty] | 0 | 0 | 3.51 | 12.11 | 5315.68
TS6060#1 | BW\23\005\X1 | BW | 23 | 5 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2016-11-12 04:02 | 2016-11-12 21:25 | 23183.7283 | [6 empty] | 23184 | 17132 | 1.05 | 0 | 0 | 10.47 | 5467
DRE2 | BW\21\007\D | BW | 21 | 7 | D | 6 DL | 100 | 100 | 100 | 2016-11-12 04:03 | 2016-11-17 19:52 | 456847.018 |  |  |  | 19925 | 456847 | 329631 |  |  | 0 | 21.84 | 0 | 5.35 | 5944.61
TS5500Shv | MW\23\004\A | MW | 23 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2016-11-12 13:20 | 2016-11-13 23:12 | 40678.9041 | [6 empty] | 40679 | 30162 | 1.86 | 0 | 0 | 9.12 | 5546
TS Fleet 5 | BW\23\003\X2 | BW | 23 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2016-11-12 16:05 | 2016-11-16 06:10 | 159081.591 | 159082 | [7 empty] | 0 | 0 | 10.03 | 0 | 0
TS6060#1 | DT\21\003\D | DT | 21 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-11-12 21:25 | 2016-11-16 02:30 | 102761.4246 | [6 empty] | 102761 | 77401 | 4.84 | 0 | 0 | 6.18 | 5871
PH4100XPC#1 | MW\22\009\D | MW | 22 | 9 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2016-11-13 02:41 | 2016-11-13 02:41 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | MW\22\010\D | MW | 22 | 10 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2016-11-13 02:41 | 2016-11-13 02:41 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | MW\23\003\B | MW | 23 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-11-13 02:41 | 2016-11-13 23:59 | 47521.1672 | 47521 | [7 empty] | 0 | 0 | 2.97 | 8.31 | 5627.57
TS5500Shv | MW\23\005\A | MW | 23 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2016-11-13 23:12 | 2016-11-14 11:40 | 14985.0519 | [6 empty] | 14985 | 11034 | 0.66 | 0 | 0 | 10.59 | 5430
PH4100XPC#1 | MW\23\004\B | MW | 23 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-11-13 23:59 | 2016-11-14 22:32 | 50295.5241 | 50296 | [7 empty] | 0 | 0 | 3.1 | 8.99 | 5596.25
TS5500Shv | MW\23\006\B | MW | 23 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2016-11-14 11:40 | 2016-11-15 01:28 | 16579.7292 | [6 empty] | 16580 | 12213 | 0.75 | 0 | 0 | 10.2 | 5538
PH4100XPC#1 | MW\23\005\B | MW | 23 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-11-14 22:32 | 2016-11-15 10:00 | 25616.6568 | 25617 | [7 empty] | 0 | 0 | 1.56 | 9.3 | 5600.27
TS5500Shv | MW\23\008\B | MW | 23 | 8 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2016-11-15 01:28 | 2016-11-16 03:21 | 31093.8994 | [6 empty] | 31094 | 22892 | 1.42 | 0 | 0 | 9.96 | 5506
PH4100XPC#1 | MW\23\006\D | MW | 23 | 6 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2016-11-15 10:00 | 2016-11-15 10:00 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | MW\23\011\A | MW | 23 | 11 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-11-15 10:00 | 2016-11-27 22:30 | 610318.3244 | 610318 | [7 empty] | 0 | 0 | 36.15 | 10.34 | 5501.16
TS5500Exc | RS\01\007\D | RS | 1 | 7 | D | 7 PostStrip | 33.0947 | 0 | 33.0947 | 2016-11-15 17:37 | 2016-11-19 04:54 | 72546.427 |  |  | 72546 | [5 empty] | 0 | 0 | 0 | 6.74 | 5824.86
TS6060#1 | BW\23\006\B | BW | 23 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-11-16 02:30 | 2016-11-18 17:08 | 83513.2503 | [6 empty] | 83513 | 60863 | 3.8 | 0 | 0 | 10.79 | 5455
TS5500Shv | MW\23\003\B | MW | 23 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-11-16 03:21 | 2016-11-18 08:51 | 64259.0245 | [6 empty] | 64259 | 47805 | 2.99 | 0 | 0 | 8.31 | 5628
TS Fleet 5 | BW\23\003\B | BW | 23 | 3 | B | 1 Prestrip - Thick | 18.9898 | 18.9898 | 18.9898 | 2016-11-16 06:10 | 2016-11-18 02:01 | 81047.5188 | 81048 | [7 empty] | 0 | 0 | 5.1 | 11.16 | 5401.05
DRE2 | BW\21\006\D | BW | 21 | 6 | D | 6 DL | 100 | 100 | 100 | 2016-11-17 19:52 | 2016-11-23 17:46 | 477311.077 |  |  |  | 20817 | 477311 | 344396 |  |  | 0 | 22.87 | 0 | 5.48 | 5933.56
TS Fleet 5 | BW\23\003\B | BW | 23 | 3 | B | 1 Prestrip - Thick | 81.0102 | 81.0102 | 81.0102 | 2016-11-18 02:01 | 2016-11-25 21:07 | 345747.4451 | 345747 | [7 empty] | 0 | 0 | 21.77 | 11.16 | 5401.05
DRE1 | SC\28\010\D | SC | 28 | 10 | D | 6 DL | 100 | 0 | 100 | 2016-11-18 08:35 | 2016-11-25 22:50 | 636590.0184 |  |  |  | 48410 | 636590 | 435689 |  |  | 0 | 40 | 0 | 7.09 | 5790.4
TS5500Shv | MW\23\004\B | MW | 23 | 4 | B | 8 Coal Mining | 56.3 | 0 | 56.3 | 2016-11-18 08:51 | 2016-11-19 14:53 | 36071.4249 | [6 empty] | 36071 | 26734 | 1.65 | 0 | 0 | 8.99 | 5596
TS6060#1 | BW\23\007\B | BW | 23 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2016-11-18 17:08 | 2016-11-21 07:43 | 83423.3859 | [6 empty] | 83423 | 60517 | 3.8 | 0 | 0 | 11.53 | 5396
TS5500Exc | RS\01\007\D | RS | 1 | 7 | D | 7 PostStrip | 8.6024 | 0 | 8.6024 | 2016-11-19 04:54 | 2016-11-20 02:32 | 18857.0785 |  |  | 18857 | [5 empty] | 0 | 0 | 0 | 6.74 | 5824.86
TS5500Shv | MW\23\005\B | MW | 23 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2016-11-19 14:53 | 2016-11-20 12:25 | 25865.0704 | [6 empty] | 25865 | 19138 | 1.17 | 0 | 0 | 9.3 | 5600
TS5500Exc | RS\01\007\D | RS | 1 | 7 | D | 8 Coal Mining | 18.6 | 0 | 18.6 | 2016-11-20 02:32 | 2016-11-21 05:28 | 33411.7156 | [6 empty] | 33412 | 24210 | 0.71 | 0 | 0 | 6.74 | 5825
TS5500Shv | MW\23\009\A | MW | 23 | 9 | A | 8 Coal Mining | 48 | 0 | 48 | 2016-11-20 12:25 | 2016-11-21 14:42 | 31571.7301 | [6 empty] | 31572 | 23204 | 1.44 | 0 | 0 | 10.46 | 5445
TS5500Exc | SC\27\008\D | SC | 27 | 8 | D | 8 Coal Mining | 100 | 0 | 85.9 | 2016-11-21 05:28 | 2016-11-23 09:52 | 65011.0877 | [6 empty] | 65011 | 49410 | 4.12 | 0 | 0 | 5.87 | 5898
TS6060#1 | DT\21\002\D | DT | 21 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-11-21 07:43 | 2016-11-25 04:51 | 124183.7442 | [6 empty] | 124184 | 93091 | 4.82 | 0 | 0 | 7.07 | 5793
TS5500Shv | DT\25\002\A | DT | 25 | 2 | A | 1 Prestrip - Thick | 43.9601 | 0 | 30.8795 | 2016-11-21 14:42 | 2016-12-01 | 237783.1755 | 237783 | [7 empty] | 0 | 0 | 14.52 | 0 | 0
TS5500Exc | MW\23\004\B | MW | 23 | 4 | B | 8 Coal Mining | 43.7 | 0 | 43.7 | 2016-11-23 09:52 | 2016-11-24 08:24 | 27957.0878 | [6 empty] | 27957 | 20720 | 1.28 | 0 | 0 | 8.99 | 5596
DRE2 | BW\21\005\D | BW | 21 | 5 | D | 6 DL | 100 | 100 | 100 | 2016-11-23 17:46 | 2016-11-29 15:54 | 478117.9551 |  |  |  | 20852 | 478118 | 344978 |  |  | 0 | 22.87 | 0 | 5.69 | 5914.58
TS5500Exc | MW\23\005\B | MW | 23 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2016-11-24 08:24 | 2016-11-25 05:56 | 26717.765 | [6 empty] | 26718 | 19768 | 1.21 | 0 | 0 | 9.3 | 5600
TS6060#1 | BW\21\011\D | BW | 21 | 11 | D | 8 Coal Mining | 87 | 0 | 51.2 | 2016-11-25 04:51 | 2016-11-26 21:09 | 53724.0271 | [6 empty] | 53724 | 40206 | 2.51 | 0 | 0 | 7.71 | 5737
TS5500Exc | MW\23\009\A | MW | 23 | 9 | A | 8 Coal Mining | 49.5 | 0 | 49.5 | 2016-11-25 05:56 | 2016-11-26 08:13 | 32612.5564 | [6 empty] | 32613 | 23968 | 1.49 | 0 | 0 | 10.46 | 5445
TS Fleet 5 | BW\23\004\X2 | BW | 23 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2016-11-25 21:07 | 2016-11-29 08:10 | 153479.667 | 153480 | [7 empty] | 0 | 0 | 9.69 | 0 | 0
DRE1 | SC\28\009\D | SC | 28 | 9 | D | 6 DL | 100 | 0 | 66.1418 | 2016-11-25 22:50 | 2016-12-01 | 423226.1341 |  |  |  | 32184 | 423226 | 289660 |  |  | 0 | 40 | 0 | 6.55 | 5838.19
TS5500Exc | SC\28\013\D | SC | 28 | 13 | D | 7 PostStrip | 100 | 0 | 100 | 2016-11-26 08:13 | 2016-11-29 04:39 | 59623.7984 |  |  | 59624 | [5 empty] | 0 | 0 | 0 | 7.47 | 5756.18
TS6060#1 | BW\23\005\X2 | BW | 23 | 5 | X2 | 1 Prestrip - Thick | 8.9856 | 0 | 8.9856 | 2016-11-26 21:09 | 2016-11-27 10:13 | 13274.7429 | 13275 | [7 empty] | 0 | 0 | 0.82 | 0 | 0
TS6060#1 | BW\24\006\B | BW | 24 | 6 | B | 1 Prestrip - Thick | 13.015 | 9.8285 | 9.8285 | 2016-11-27 10:13 | 2016-12-01 | 86284.4382 | 86284 | [7 empty] | 0 | 0 | 5.39 | 10.42 | 5487
PH4100XPC#1 | MW\23\004\D | MW | 23 | 4 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2016-11-27 22:30 | 2016-11-27 22:30 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | MW\24\011\A | MW | 24 | 11 | A | 1 Prestrip - Thick | 100 | 21.8752 | 21.8752 | 2016-11-27 22:30 | 2016-12-01 | 151496.7456 | 151497 | [7 empty] | 0 | 0 | 8.9 | 10.42 | 5500.57
TS5500Exc | MW\25\004\A | MW | 25 | 4 | A | 1 Prestrip - Thick | 36.3572 | 14.0926 | 14.0926 | 2016-11-29 04:39 | 2016-12-01 | 37784.4791 | 37784 | [7 empty] | 0 | 0 | 2.44 | 9.32 | 5543.19
TS Fleet 5 | BW\23\004\B | BW | 23 | 4 | B | 1 Prestrip - Thick | 100 | 16.1094 | 16.1094 | 2016-11-29 08:10 | 2016-12-01 | 73594.815 | 73595 | [7 empty] | 0 | 0 | 4.63 | 10.8 | 5447.19
DRE2 | BW\21\004\D | BW | 21 | 4 | D | 6 DL | 100 | 22.5167 | 22.5167 | 2016-11-29 15:54 | 2016-12-01 | 107929.8795 |  |  |  | 4707 | 107930 | 77875 |  |  | 0 | 22.93 | 0 | 6.19 | 5871.2
| EOP 35 : 2016\Nov | EOP 35 : 2016 | Nov | [6 empty] | 2016-12-01 | 2016-12-01 |  | 4693082 |  | 274662 | 293004 | 4936950 | 3421472 | 1424700 | 1050475 | 60.78 | 0 | 241.86 | 8.4 | 5666.78
TS Fleet 5 | BW\23\004\B | BW | 23 | 4 | B | 1 Prestrip - Thick | 100 | 83.8906 | 83.8906 | 2016-12-01 | 2016-12-11 13:28 | 383250.4467 | 383250 | [7 empty] | 0 | 0 | 24.13 | 10.8 | 5447.19
DRE1 | SC\28\009\D | SC | 28 | 9 | D | 6 DL | 100 | 0 | 33.8582 | 2016-12-01 | 2016-12-03 23:33 | 216651.108 |  |  |  | 16475 | 216651 | 148278 |  |  | 0 | 40 | 0 | 6.55 | 5838.19
PH4100A | RS\01\008\D | RS | 1 | 8 | D | 1 Prestrip - Thick | 100 | 17.9879 | 17.9879 | 2016-12-01 | 2016-12-10 04:05 | 293315.7846 | 293316 | [7 empty] | 0 | 0 | 6.34 | 7.08 | 5786.41
DRE2 | BW\21\004\D | BW | 21 | 4 | D | 6 DL | 100 | 77.4833 | 77.4833 | 2016-12-01 | 2016-12-06 07:24 | 371403.0208 |  |  |  | 16198 | 371403 | 267980 |  |  | 0 | 22.93 | 0 | 6.19 | 5871.2
TS5500Shv | DT\25\002\A | DT | 25 | 2 | A | 1 Prestrip - Thick | 43.9601 | 0 | 13.0806 | 2016-12-01 | 2016-12-05 20:38 | 100724.986 | 100725 | [7 empty] | 0 | 0 | 6.15 | 0 | 0
PH4100XPC#1 | MW\24\011\A | MW | 24 | 11 | A | 1 Prestrip - Thick | 100 | 78.1248 | 78.1248 | 2016-12-01 | 2016-12-14 05:45 | 541055.0267 | 541055 | [7 empty] | 0 | 0 | 31.77 | 10.42 | 5500.57
TS6060#1 | BW\24\006\B | BW | 24 | 6 | B | 1 Prestrip - Thick | 13.015 | 3.1865 | 3.1865 | 2016-12-01 | 2016-12-02 09:59 | 27974.8178 | 27975 | [7 empty] | 0 | 0 | 1.75 | 10.42 | 5487
TS5500Exc | MW\25\004\A | MW | 25 | 4 | A | 1 Prestrip - Thick | 36.3572 | 22.2646 | 22.2646 | 2016-12-01 | 2016-12-04 11:41 | 59694.7102 | 59695 | [7 empty] | 0 | 0 | 3.85 | 9.32 | 5543.19
TS6060#1 | BW\21\011\D | BW | 21 | 11 | D | 8 Coal Mining | 87 | 0 | 35.8 | 2016-12-02 09:59 | 2016-12-03 20:27 | 37599.5766 | [6 empty] | 37600 | 28139 | 1.76 | 0 | 0 | 7.71 | 5737
TS6060#1 | BW\21\011\D | BW | 21 | 11 | D | 8 Coal Mining | 13 | 0 | 13 | 2016-12-03 20:27 | 2016-12-04 08:59 | 13664.9248 | [6 empty] | 13665 | 10226 | 0.64 | 0 | 0 | 7.71 | 5737
DRE1 | SC\28\003\D | SC | 28 | 3 | D | 6 DL | 100 | 0 | 100 | 2016-12-03 23:33 | 2016-12-14 02:19 | 734946.3744 |  |  |  | 41278 | 734946 | 319904 |  |  | 0 | 40 | 0 | 6.32 | 5859.16
TS6060#1 | RS\01\007\D | RS | 1 | 7 | D | 8 Coal Mining | 81.4 | 0 | 81.4 | 2016-12-04 08:59 | 2016-12-09 22:51 | 146017.3121 | [6 empty] | 146017 | 105805 | 3.11 | 0 | 0 | 6.74 | 5825
TS5500Exc | SC\28\012\D | SC | 28 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-12-04 11:41 | 2016-12-07 12:13 | 73637.3878 | [6 empty] | 73637 | 54859 | 4.57 | 0 | 0 | 7.5 | 5753
TS5500Shv | DT\25\002\A | DT | 25 | 2 | A | 1 Prestrip - Thick | 56.0399 | 0 | 56.0399 | 2016-12-05 20:38 | 2016-12-26 16:21 | 431526.5113 | 431527 | [7 empty] | 0 | 0 | 26.35 | 0 | 0
DRE2 | BW\21\003\D | BW | 21 | 3 | D | 6 DL | 100 | 100 | 100 | 2016-12-06 07:24 | 2016-12-13 03:25 | 478189.3332 |  |  |  | 20855 | 478189 | 345030 |  |  | 0 | 22.89 | 0 | 7 | 5799.66
TS5500Exc | SC\28\011\D | SC | 28 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-12-07 12:13 | 2016-12-10 14:37 | 75530.8645 | [6 empty] | 75531 | 56361 | 4.7 | 0 | 0 | 7.41 | 5762
TS6060#1 | BW\21\009\D | BW | 21 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-12-09 22:51 | 2016-12-13 23:20 | 105247.3908 | [6 empty] | 105247 | 79519 | 4.97 | 0 | 0 | 5.95 | 5892
PH4100A | SC\32\005\D | SC | 32 | 5 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2016-12-10 04:05 | 2016-12-10 04:05 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\32\006\D | SC | 32 | 6 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2016-12-10 04:05 | 2016-12-10 04:05 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | RS\02\003\D | RS | 2 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2016-12-10 04:05 | 2016-12-21 06:20 | 361650.2235 | 361650 | [7 empty] | 0 | 0 | 19.57 | 6.05 | 5905.96
TS5500Exc | SC\28\013\D | SC | 28 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-12-10 14:37 | 2016-12-13 07:36 | 65976.3755 | [6 empty] | 65976 | 49230 | 4.62 | 0 | 0 | 7.47 | 5756
TS Fleet 5 | BW\23\005\X2 | BW | 23 | 5 | X2 | 1 Prestrip - Thick | 91.0144 | 0 | 91.0144 | 2016-12-11 13:28 | 2016-12-15 06:24 | 134458.1741 | 134458 | [7 empty] | 0 | 0 | 8.33 | 0 | 0
DRE2 | BW\21\002\D | BW | 21 | 2 | D | 6 DL | 100 | 100 | 100 | 2016-12-13 03:25 | 2016-12-19 12:26 | 446060.19 |  |  |  | 19454 | 446060 | 321848 |  |  | 0 | 21.3 | 0 | 6.63 | 5831.34
TS5500Exc | MW\23\009\A | MW | 23 | 9 | A | 8 Coal Mining | 2.5 | 0 | 2.5 | 2016-12-13 07:36 | 2016-12-13 09:14 | 1646.4 | [6 empty] | 1646 | 1210 | 0.08 | 0 | 0 | 10.46 | 5445
TS5500Exc | MW\23\010\A | MW | 23 | 10 | A | 8 Coal Mining | 100 | 0 | 100 | 2016-12-13 09:14 | 2016-12-16 13:09 | 77075.115 | [6 empty] | 77075 | 56426 | 3.51 | 0 | 0 | 10.5 | 5479
TS6060#1 | BW\21\010\D | BW | 21 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-12-13 23:20 | 2016-12-18 03:06 | 108836.6805 | [6 empty] | 108837 | 81837 | 5.12 | 0 | 0 | 6.79 | 5818
DRE1 | SC\28\004\D | SC | 28 | 4 | D | 6 DL | 100 | 0 | 100 | 2016-12-14 02:19 | 2016-12-22 18:49 | 631168.3718 |  |  |  | 47998 | 631168 | 431978 |  |  | 0 | 40 | 0 | 6.22 | 5867.75
PH4100XPC#1 | MW\23\012\A | MW | 23 | 12 | A | 1 Prestrip - Thick | 100 | 47.2469 | 47.2469 | 2016-12-14 05:45 | 2016-12-21 11:49 | 294441.8087 | 294442 | [7 empty] | 0 | 0 | 18.68 | 10.88 | 5453.98
TS Fleet 5 | BW\23\005\B | BW | 23 | 5 | B | 1 Prestrip - Thick | 59.3142 | 59.3142 | 59.3142 | 2016-12-15 06:24 | 2016-12-23 02:32 | 284469.452 | 284469 | [7 empty] | 0 | 0 | 17.8 | 10.89 | 5449.71
TS5500Exc | SC\28\010\D | SC | 28 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-12-16 13:09 | 2016-12-19 16:44 | 76734.273 | [6 empty] | 76734 | 57487 | 4.79 | 0 | 0 | 7.09 | 5790
TS6060#1 | BW\21\008\D | BW | 21 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-12-18 03:06 | 2016-12-22 01:22 | 102815.0719 | [6 empty] | 102815 | 77994 | 4.88 | 0 | 0 | 5.63 | 5919
DRE2 | BW\21\001\D | BW | 21 | 1 | D | 6 DL | 100 | 100 | 100 | 2016-12-19 12:26 | 2016-12-25 12:26 | 419824.0791 |  |  |  | 16146 | 419824 | 201131 |  |  | 0 | 21.46 | 0 | 6.15 | 5872.99
TS5500Exc | SC\28\009\D | SC | 28 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-12-19 16:44 | 2016-12-22 21:05 | 77516.1842 | [6 empty] | 77516 | 58444 | 4.87 | 0 | 0 | 6.55 | 5838
PH4100A | RS\02\004\D | RS | 2 | 4 | D | 1 Prestrip - Thick | 100 | 80.908 | 80.908 | 2016-12-21 06:20 | 2017-01-01 | 349338.844 | 349339 | [7 empty] | 0 | 0 | 17.36 | 6.23 | 5890.38
PH4100XPC#1 | MW\24\012\A | MW | 24 | 12 | A | 1 Prestrip - Thick | 100 | 75.3976 | 75.3976 | 2016-12-21 11:49 | 2017-01-01 | 430291.7216 | 430292 | [7 empty] | 0 | 0 | 33.28 | 11.05 | 5444.68
TS6060#1 | BW\23\003\B | BW | 23 | 3 | B | 8 Coal Mining | 31.6 | 0 | 31.6 | 2016-12-22 01:22 | 2016-12-23 01:09 | 25948.3163 | [6 empty] | 25948 | 18890 | 1.18 | 0 | 0 | 11.16 | 5401
DRE1 | SC\28\005\D | SC | 28 | 5 | D | 6 DL | 100 | 0 | 100 | 2016-12-22 18:49 | 2016-12-31 10:19 | 628177.0488 |  |  |  | 47770 | 628177 | 429931 |  |  | 0 | 40 | 0 | 6.07 | 5880.26
TS5500Exc | MW\23\011\A | MW | 23 | 11 | A | 8 Coal Mining | 23.9 | 0 | 23.9 | 2016-12-22 21:05 | 2016-12-23 15:58 | 19161.8047 | [6 empty] | 19162 | 14036 | 0.88 | 0 | 0 | 10.34 | 5501
TS6060#1 | BW\23\005\B | BW | 23 | 5 | B | 1 Prestrip - Thick | 34.7354 | 14.5915 | 14.5915 | 2016-12-23 01:09 | 2016-12-26 13:18 | 69980.6929 | 69981 | [7 empty] | 0 | 0 | 4.38 | 10.89 | 5449.71
TS Fleet 5 | BW\23\005\B | BW | 23 | 5 | B | 1 Prestrip - Thick | 27.0782 | 26.0942 | 26.0942 | 2016-12-23 02:32 | 2016-12-26 13:18 | 125147.3703 | 125147 | [7 empty] | 0 | 0 | 7.83 | 10.89 | 5449.71
TS5500Exc | MW\23\011\A | MW | 23 | 11 | A | 8 Coal Mining | 76.1 | 0 | 76.1 | 2016-12-23 15:58 | 2016-12-26 04:01 | 60957.1563 | [6 empty] | 60957 | 44652 | 2.79 | 0 | 0 | 10.34 | 5501
DRE2 | DT\22\004\D | DT | 22 | 4 | D | 6 DL | 100 | 87.7905 | 87.7905 | 2016-12-25 12:26 | 2017-01-01 | 453469.3769 |  |  |  | 19777 | 453469 | 327193 |  |  | 0 | 24.73 | 0 | 5.79 | 5904.22
TS5500Exc | MW\23\012\A | MW | 23 | 12 | A | 8 Coal Mining | 100 | 0 | 100 | 2016-12-26 04:01 | 2016-12-29 01:57 | 70995.546 | [6 empty] | 70996 | 52007 | 3.6 | 0 | 0 | 10.88 | 5454
TS Fleet 5 | BW\24\002\X1 | BW | 24 | 2 | X1 | 1 Prestrip - Thick | 100 | 38.0683 | 38.0683 | 2016-12-26 13:18 | 2017-01-01 | 197602.5568 | 197603 | [7 empty] | 0 | 0 | 11.97 | 11.45 | 5371.41
TS6060#1 | BW\21\005\D | BW | 21 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2016-12-26 13:18 | 2016-12-30 15:40 | 107300.9644 | [6 empty] | 107301 | 81198 | 5.07 | 0 | 0 | 5.69 | 5915
TS5500Shv | RS\01\008\D | RS | 1 | 8 | D | 7 PostStrip | 64.1223 | 0 | 40.5917 | 2016-12-26 16:21 | 2017-01-01 | 110283.9552 |  |  | 110284 | [5 empty] | 0 | 0 | 0 | 7.08 | 5786.41
TS5500Exc | SC\28\003\D | SC | 28 | 3 | D | 7 PostStrip | 100 | 0 | 96.7699 | 2016-12-29 01:57 | 2017-01-01 | 49930.7795 |  |  | 49931 | [5 empty] | 0 | 0 | 0 | 6.32 | 5859.16
TS6060#1 | BW\21\004\D | BW | 21 | 4 | D | 8 Coal Mining | 100 | 0 | 22.6 | 2016-12-30 15:40 | 2016-12-31 14:10 | 24535.391 | [6 empty] | 24535 | 18493 | 1.16 | 0 | 0 | 6.19 | 5871
DRE1 | SC\28\006\D | SC | 28 | 6 | D | 6 DL | 100 | 0 | 6.5722 | 2016-12-31 10:19 | 2017-01-01 | 41424.097 |  |  |  | 3150 | 41424 | 28351 |  |  | 0 | 40 | 0 | 5.91 | 5894.61
TS6060#1 | BW\23\003\B | BW | 23 | 3 | B | 8 Coal Mining | 68.4 | 0 | 13.1 | 2016-12-31 14:10 | 2017-01-01 | 10719.7748 | [6 empty] | 10720 | 7804 | 0.49 | 0 | 0 | 11.16 | 5401
| EOP 36 : 2016\Dec | EOP 36 : 2016 | Dec | [6 empty] | 2017-01-01 | 2017-01-01 |  | 4084923 |  | 160215 | 249102 | 4421313 | 2821625 | 1281917 | 954615 | 62.77 | 0 | 239.53 | 7.4 | 5763.52
TS Fleet 5 | BW\24\002\X1 | BW | 24 | 2 | X1 | 1 Prestrip - Thick | 100 | 61.9317 | 61.9317 | 2017-01-01 | 2017-01-08 17:10 | 321470.9951 | 321471 | [7 empty] | 0 | 0 | 19.47 | 11.45 | 5371.41
DRE1 | SC\28\006\D | SC | 28 | 6 | D | 6 DL | 100 | 0 | 93.4278 | 2017-01-01 | 2017-01-08 02:51 | 588873.0749 |  |  |  | 44781 | 588873 | 403031 |  |  | 0 | 40 | 0 | 5.91 | 5894.61
PH4100A | RS\02\004\D | RS | 2 | 4 | D | 1 Prestrip - Thick | 100 | 19.092 | 19.092 | 2017-01-01 | 2017-01-03 05:19 | 82433.8561 | 82434 | [7 empty] | 0 | 0 | 4.1 | 6.23 | 5890.38
DRE2 | DT\22\004\D | DT | 22 | 4 | D | 6 DL | 100 | 12.2095 | 12.2095 | 2017-01-01 | 2017-01-01 19:00 | 63066.5608 |  |  |  | 2751 | 63067 | 45505 |  |  | 0 | 24.73 | 0 | 5.79 | 5904.22
TS5500Shv | RS\01\008\D | RS | 1 | 8 | D | 7 PostStrip | 64.1223 | 0 | 23.5306 | 2017-01-01 | 2017-01-03 16:26 | 63930.4525 |  |  | 63930 | [5 empty] | 0 | 0 | 0 | 7.08 | 5786.41
PH4100XPC#1 | MW\24\012\A | MW | 24 | 12 | A | 1 Prestrip - Thick | 100 | 24.6024 | 24.6024 | 2017-01-01 | 2017-01-04 00:09 | 140405.164 | 140405 | [7 empty] | 0 | 0 | 10.86 | 11.05 | 5444.68
TS6060#1 | BW\23\003\B | BW | 23 | 3 | B | 8 Coal Mining | 68.4 | 0 | 55.3 | 2017-01-01 | 2017-01-02 12:17 | 45447.6396 | [6 empty] | 45448 | 33084 | 2.07 | 0 | 0 | 11.16 | 5401
TS5500Exc | SC\28\003\D | SC | 28 | 3 | D | 7 PostStrip | 100 | 0 | 3.2301 | 2017-01-01 | 2017-01-01 02:02 | 1666.673 |  |  | 1667 | [5 empty] | 0 | 0 | 0 | 6.32 | 5859.16
TS5500Exc | SC\28\003\D | SC | 28 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-01-01 02:02 | 2017-01-03 10:08 | 65397.58 | [6 empty] | 65398 | 49546 | 4.93 | 0 | 0 | 6.32 | 5859
DRE2 | DT\22\005\D | DT | 22 | 5 | D | 6 DL | 100 | 100 | 100 | 2017-01-01 19:00 | 2017-01-06 11:12 | 372418.012 |  |  |  | 22241 | 372418 | 262900 |  |  | 0 | 25.57 | 0 | 5.67 | 5914.69
TS6060#1 | BW\21\004\D | BW | 21 | 4 | D | 8 Coal Mining | 100 | 0 | 77.4 | 2017-01-02 12:17 | 2017-01-05 07:32 | 84227.6372 | [6 empty] | 84228 | 63483 | 3.97 | 0 | 0 | 6.19 | 5871
PH4100A | RS\02\005\D | RS | 2 | 5 | D | 1 Prestrip - Thick | 100 | 67.0441 | 67.0441 | 2017-01-03 05:19 | 2017-01-11 12:58 | 310761.4987 | 310761 | [7 empty] | 0 | 0 | 15.46 | 6.12 | 5899.78
TS5500Exc | SC\28\004\D | SC | 28 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-01-03 10:08 | 2017-01-06 04:43 | 77604.6843 | [6 empty] | 77605 | 58464 | 4.87 | 0 | 0 | 6.22 | 5868
TS5500Shv | RS\01\008\D | RS | 1 | 8 | D | 7 PostStrip | 35.8777 | 0 | 35.8777 | 2017-01-03 16:26 | 2017-01-07 18:42 | 97476.2997 |  |  | 97476 | [5 empty] | 0 | 0 | 0 | 7.08 | 5786.41
PH4100XPC#1 | MW\23\008\D | MW | 23 | 8 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-01-04 00:09 | 2017-01-04 00:09 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | MW\23\009\B | MW | 23 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-01-04 00:09 | 2017-01-05 18:52 | 89800.4578 | 89800 | [7 empty] | 0 | 0 | 5.61 | 9.54 | 5551.82
TS6060#1 | BW\21\006\D | BW | 21 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-01-05 07:32 | 2017-01-08 22:42 | 109165.5885 | [6 empty] | 109166 | 82872 | 5.18 | 0 | 0 | 5.48 | 5934
PH4100XPC#1 | MW\23\010\B | MW | 23 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-01-05 18:52 | 2017-01-06 20:08 | 53085.5383 | 53086 | [7 empty] | 0 | 0 | 3.31 | 8.64 | 5650.53
TS5500Exc | MW\23\009\B | MW | 23 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-01-06 04:43 | 2017-01-08 14:57 | 67882.0996 | [6 empty] | 67882 | 50076 | 3.13 | 0 | 0 | 9.54 | 5552
DRE2 | DT\22\006\D | DT | 22 | 6 | D | 6 DL | 100 | 100 | 100 | 2017-01-06 11:12 | 2017-01-09 19:21 | 266013.5157 |  |  |  | 15886 | 266014 | 187786 |  |  | 0 | 25.25 | 0 | 5.56 | 5923.99
PH4100XPC#1 | MW\23\011\B | MW | 23 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-01-06 20:08 | 2017-01-07 15:27 | 40619.0563 | 40619 | [7 empty] | 0 | 0 | 2.53 | 7.97 | 5706.21
PH4100XPC#1 | MW\23\012\B | MW | 23 | 12 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-01-07 15:27 | 2017-01-08 07:47 | 34301.1535 | 34301 | [7 empty] | 0 | 0 | 2.4 | 17.64 | 4917.87
TS5500Shv | MW\24\012\A | MW | 24 | 12 | A | 8 Coal Mining | 10.7 | 0 | 10.7 | 2017-01-07 18:42 | 2017-01-07 23:58 | 5946.9878 | [6 empty] | 5947 | 4352 | 0.38 | 0 | 0 | 11.05 | 5445
TS5500Shv | DT\22\004\D | DT | 22 | 4 | D | 8 Coal Mining | 21.5 | 0 | 21.5 | 2017-01-07 23:58 | 2017-01-08 19:02 | 21518.4126 | [6 empty] | 21518 | 16272 | 1.02 | 0 | 0 | 5.79 | 5904
DRE1 | SC\28\007\D | SC | 28 | 7 | D | 6 DL | 100 | 0 | 100 | 2017-01-08 02:51 | 2017-01-15 17:58 | 631110.1506 |  |  |  | 47993 | 631110 | 431939 |  |  | 0 | 40 | 0 | 5.81 | 5903.03
PH4100XPC#1 | RS\02\005\D | RS | 2 | 5 | D | 1 Prestrip - Thick | 100 | 32.9559 | 32.9559 | 2017-01-08 07:47 | 2017-01-11 12:58 | 152756.2928 | 152756 | [7 empty] | 0 | 0 | 7.6 | 6.12 | 5899.78
TS5500Exc | MW\23\012\B | MW | 23 | 12 | B | 8 Coal Mining | 100 | 0 | 54.4 | 2017-01-08 14:57 | 2017-01-10 02:26 | 41364.2311 | [6 empty] | 41364 | 29414 | 2.25 | 0 | 0 | 17.64 | 4918
TS Fleet 5 | BW\24\003\X1 | BW | 24 | 3 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-01-08 17:10 | 2017-01-19 03:31 | 434610.0552 | 434610 | [7 empty] | 0 | 0 | 26.5 | 11.72 | 5348.38
TS5500Shv | MW\24\003\A | MW | 24 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2017-01-08 19:02 | 2017-01-11 06:34 | 67176.7794 | [6 empty] | 67177 | 49563 | 3.1 | 0 | 0 | 9.83 | 5473
TS6060#1 | MW\23\012\B | MW | 23 | 12 | B | 8 Coal Mining | 100 | 0 | 45.6 | 2017-01-08 22:42 | 2017-01-10 02:26 | 34742.7144 | [6 empty] | 34743 | 24705 | 1.89 | 0 | 0 | 17.64 | 4918
DRE2 | DT\22\007\D | DT | 22 | 7 | D | 6 DL | 100 | 100 | 100 | 2017-01-09 19:21 | 2017-01-14 22:16 | 407925.2494 |  |  |  | 17791 | 407925 | 294332 |  |  | 0 | 24.79 | 0 | 5.56 | 5923.26
TS6060#1 | BW\21\003\D | BW | 21 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-01-10 02:26 | 2017-01-13 16:44 | 108078.9181 | [6 empty] | 108079 | 80945 | 5.06 | 0 | 0 | 7 | 5800
TS5500Exc | MW\23\010\B | MW | 23 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-01-10 02:26 | 2017-01-12 12:19 | 67453.3786 | [6 empty] | 67453 | 49941 | 3.12 | 0 | 0 | 8.64 | 5651
TS5500Shv | DT\22\005\D | DT | 22 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-01-11 06:34 | 2017-01-13 18:41 | 67835.2317 | [6 empty] | 67835 | 51378 | 4.67 | 0 | 0 | 5.67 | 5915
PH4100A | RS\02\006\D | RS | 2 | 6 | D | 1 Prestrip - Thick | 100 | 48.2288 | 48.2288 | 2017-01-11 12:58 | 2017-01-17 22:15 | 238156.2801 | 238156 | [7 empty] | 0 | 0 | 11.78 | 6.35 | 5879.57
PH4100XPC#1 | MW\24\003\B | MW | 24 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-01-11 12:58 | 2017-01-12 12:40 | 49814.4552 | 49814 | [7 empty] | 0 | 0 | 3.11 | 8.37 | 5626.49
TS5500Exc | RS\01\008\D | RS | 1 | 8 | D | 8 Coal Mining | 6.6 | 0 | 6.6 | 2017-01-12 12:19 | 2017-01-12 21:41 | 10934.8802 | [6 empty] | 10935 | 7926 | 0.18 | 0 | 0 | 7.08 | 5786
PH4100XPC#1 | MW\23\009\D | MW | 23 | 9 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-01-12 12:40 | 2017-01-12 12:40 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | MW\23\010\D | MW | 23 | 10 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-01-12 12:40 | 2017-01-12 12:40 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | RS\02\006\D | RS | 2 | 6 | D | 1 Prestrip - Thick | 100 | 51.7712 | 51.7712 | 2017-01-12 12:40 | 2017-01-17 22:15 | 255649.0679 | 255649 | [7 empty] | 0 | 0 | 12.65 | 6.35 | 5879.57
TS5500Exc | MW\23\011\B | MW | 23 | 11 | B | 8 Coal Mining | 67.3 | 0 | 67.3 | 2017-01-12 21:41 | 2017-01-14 10:06 | 42444.1913 | [6 empty] | 42444 | 31688 | 1.98 | 0 | 0 | 7.97 | 5706
TS6060#1 | MW\24\012\A | MW | 24 | 12 | A | 8 Coal Mining | 89.3 | 0 | 89.3 | 2017-01-13 16:44 | 2017-01-15 08:32 | 49840.9934 | [6 empty] | 49841 | 36473 | 3.21 | 0 | 0 | 11.05 | 5445
TS5500Shv | DT\22\006\D | DT | 22 | 6 | D | 8 Coal Mining | 53.2 | 0 | 53.2 | 2017-01-13 18:41 | 2017-01-14 17:35 | 25839.458 | [6 empty] | 25839 | 19586 | 2.44 | 0 | 0 | 5.56 | 5924
TS5500Exc | MW\24\003\B | MW | 24 | 3 | B | 8 Coal Mining | 91.6 | 0 | 91.6 | 2017-01-14 10:06 | 2017-01-16 12:59 | 59311.1421 | [6 empty] | 59311 | 44159 | 2.76 | 0 | 0 | 8.37 | 5626
TS5500Shv | MW\23\011\B | MW | 23 | 11 | B | 8 Coal Mining | 32.7 | 0 | 32.7 | 2017-01-14 17:35 | 2017-01-15 11:52 | 20620.1229 | [6 empty] | 20620 | 15395 | 0.96 | 0 | 0 | 7.97 | 5706
DRE2 | DT\22\003\D | DT | 22 | 3 | D | 6 DL | 100 | 100 | 100 | 2017-01-14 22:16 | 2017-01-20 23:49 | 483088.4045 |  |  |  | 21069 | 483088 | 348565 |  |  | 0 | 23.15 | 0 | 6.14 | 5873.83
TS6060#1 | MW\24\012\B | MW | 24 | 12 | B | 1 Prestrip - Thick | 49.0446 | 49.0446 | 49.0446 | 2017-01-15 08:32 | 2017-01-15 22:12 | 13050.2843 | 13050 | [7 empty] | 0 | 0 | 1.17 | 8.24 | 5683.44
TS5500Shv | MW\24\012\B | MW | 24 | 12 | B | 1 Prestrip - Thick | 50.9554 | 50.9554 | 50.9554 | 2017-01-15 11:52 | 2017-01-16 01:32 | 13558.737 | 13559 | [7 empty] | 0 | 0 | 1.21 | 8.24 | 5683.44
DRE1 | SC\28\008\D | SC | 28 | 8 | D | 6 DL | 100 | 0 | 100 | 2017-01-15 17:58 | 2017-01-24 04:32 | 698155.5336 |  |  |  | 48149 | 698156 | 433338 |  |  | 0 | 40 | 0 | 6.04 | 5883.45
TS6060#1 | BW\21\002\D | BW | 21 | 2 | D | 8 Coal Mining | 64.1 | 0 | 64.1 | 2017-01-15 22:12 | 2017-01-18 03:27 | 66691.5009 | [6 empty] | 66692 | 50069 | 3.13 | 0 | 0 | 6.63 | 5831
TS5500Shv | MW\24\012\B | MW | 24 | 12 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2017-01-16 01:32 | 2017-01-16 19:44 | 20544.1226 | [6 empty] | 20544 | 15361 | 1.4 | 0 | 0 | 8.24 | 5683
TS5500Exc | MW\24\004\A | MW | 24 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-01-16 12:59 | 2017-01-18 01:40 | 42747.9692 | [6 empty] | 42748 | 31682 | 1.97 | 0 | 0 | 9.23 | 5545
TS5500Shv | DT\22\007\D | DT | 22 | 7 | D | 8 Coal Mining | 70.2 | 0 | 70.2 | 2017-01-16 19:44 | 2017-01-18 17:48 | 51980.5226 | [6 empty] | 51981 | 39462 | 3.16 | 0 | 0 | 5.56 | 5923
PH4100A | RS\02\007\D | RS | 2 | 7 | D | 1 Prestrip - Thick | 100 | 44.0362 | 44.0362 | 2017-01-17 22:15 | 2017-01-23 22:13 | 223926.3607 | 223926 | [7 empty] | 0 | 0 | 10.98 | 6.5 | 5865.57
PH4100XPC#1 | MW\23\011\D | MW | 23 | 11 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-01-17 22:15 | 2017-01-17 22:15 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | RS\02\007\D | RS | 2 | 7 | D | 1 Prestrip - Thick | 100 | 55.9638 | 55.9638 | 2017-01-17 22:15 | 2017-01-23 22:13 | 284579.1807 | 284579 | [7 empty] | 0 | 0 | 13.95 | 6.5 | 5865.57
TS5500Exc | MW\24\005\A | MW | 24 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-01-18 01:40 | 2017-01-18 16:04 | 16786.2445 | [6 empty] | 16786 | 12338 | 0.75 | 0 | 0 | 10.94 | 5408
TS6060#1 | MW\24\012\B | MW | 24 | 12 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2017-01-18 03:27 | 2017-01-18 21:40 | 22801.7185 | [6 empty] | 22802 | 17049 | 1.55 | 0 | 0 | 8.24 | 5683
TS5500Exc | SC\28\005\D | SC | 28 | 5 | D | 8 Coal Mining | 9.9 | 0 | 9.9 | 2017-01-18 16:04 | 2017-01-18 22:40 | 7689.9321 | [6 empty] | 7690 | 5789 | 0.48 | 0 | 0 | 6.07 | 5880
TS5500Shv | MW\24\003\B | MW | 24 | 3 | B | 8 Coal Mining | 8.4 | 0 | 8.4 | 2017-01-18 17:48 | 2017-01-18 22:37 | 5437.7107 | [6 empty] | 5438 | 4049 | 0.25 | 0 | 0 | 8.37 | 5626
TS6060#1 | BW\23\004\B | BW | 23 | 4 | B | 8 Coal Mining | 100 | 0 | 51.2 | 2017-01-18 21:40 | 2017-01-20 07:20 | 42181.5536 | [6 empty] | 42182 | 30770 | 1.92 | 0 | 0 | 10.8 | 5447
TS5500Shv | MW\24\004\A | MW | 24 | 4 | A | 8 Coal Mining | 49.2 | 0 | 43.9 | 2017-01-18 22:37 | 2017-01-20 07:20 | 36918.5112 | [6 empty] | 36919 | 27362 | 1.7 | 0 | 0 | 9.23 | 5545
TS5500Exc | SC\28\005\D | SC | 28 | 5 | D | 8 Coal Mining | 90.1 | 0 | 48.9 | 2017-01-18 22:40 | 2017-01-20 07:20 | 38087.5436 | [6 empty] | 38088 | 28671 | 2.39 | 0 | 0 | 6.07 | 5880
TS Fleet 5 | BW\24\004\X1 | BW | 24 | 4 | X1 | 1 Prestrip - Thick | 61.5754 | 61.5754 | 61.5754 | 2017-01-19 03:31 | 2017-01-26 03:24 | 291449.9997 | 291450 | [7 empty] | 0 | 0 | 17.88 | 10.78 | 5436.07
TS5500Shv | DT\25\002\B | DT | 25 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-01-20 07:20 | 2017-01-23 08:40 | 72744.0414 | 72744 | [7 empty] | 0 | 0 | 3.71 | 11.46 | 5326.72
TS6060#1 | BW\21\001\D | BW | 21 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2017-01-20 07:20 | 2017-01-23 04:27 | 65985.5872 |  |  | 65986 | [5 empty] | 0 | 0 | 0 | 6.15 | 5872.99
TS5500Exc | MW\25\004\A | MW | 25 | 4 | A | 1 Prestrip - Thick | 63.6428 | 63.6428 | 63.6428 | 2017-01-20 07:20 | 2017-01-28 23:42 | 170635.9688 | 170636 | [7 empty] | 0 | 0 | 11.02 | 9.32 | 5543.19
DRE2 | DT\22\002\D | DT | 22 | 2 | D | 6 DL | 100 | 100 | 100 | 2017-01-20 23:49 | 2017-01-29 13:17 | 681918.9149 |  |  |  | 29741 | 681919 | 492028 |  |  | 0 | 21.44 | 0 | 6.72 | 5823.33
TS6060#1 | BW\24\006\B | BW | 24 | 6 | B | 1 Prestrip - Thick | 19.0054 | 19.0054 | 19.0054 | 2017-01-23 04:27 | 2017-01-30 13:01 | 166848.6675 | 166849 | [7 empty] | 0 | 0 | 10.41 | 10.42 | 5487
TS5500Shv | DT\25\004\B | DT | 25 | 4 | B | 1 Prestrip - Thick | 30.6925 | 29.3302 | 29.3302 | 2017-01-23 08:40 | 2017-02-01 | 206411.8105 | 206412 | [7 empty] | 0 | 0 | 12.15 | 10.8 | 5308.59
PH4100A | RS\02\008\D1 | RS | 2 | 8 | D1 | 1 Prestrip - Thick | 100 | 44.086 | 44.086 | 2017-01-23 22:13 | 2017-01-30 04:43 | 233460.814 | 233461 | [7 empty] | 0 | 0 | 11.87 | 7.21 | 5725.21
PH4100XPC#1 | MW\24\012\D | MW | 24 | 12 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-01-23 22:13 | 2017-01-23 22:13 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | RS\02\008\D1 | RS | 2 | 8 | D1 | 1 Prestrip - Thick | 100 | 55.914 | 55.914 | 2017-01-23 22:13 | 2017-01-30 04:43 | 296097.1639 | 296097 | [7 empty] | 0 | 0 | 15.06 | 7.21 | 5725.21
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 7d 00:00 |  | 7d 00:00 | 2017-01-24 04:32 | 2017-01-31 04:32
TS Fleet 5 | BW\24\004\X1 | BW | 24 | 4 | X1 | 1 Prestrip - Thick | 38.4246 | 38.4246 | 38.4246 | 2017-01-26 03:24 | 2017-01-30 12:10 | 181871.8116 | 181872 | [7 empty] | 0 | 0 | 11.16 | 10.78 | 5436.07
TS5500Exc | MW\25\005\A | MW | 25 | 5 | A | 1 Prestrip - Thick | 66.6059 | 17.4507 | 17.4507 | 2017-01-28 23:42 | 2017-02-01 | 59479.6654 | 59480 | [7 empty] | 0 | 0 | 3.59 | 10.05 | 5482.12
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2017-01-29 13:17 | 2017-01-31 13:17
PH4100A | RS\03\003\D | RS | 3 | 3 | D | 1 Prestrip - Thick | 100 | 39.9803 | 39.9803 | 2017-01-30 04:43 | 2017-02-01 | 67769.1724 | 67769 | [7 empty] | 0 | 0 | 7.89 | 6.19 | 5876.96
PH4100XPC#1 | RS\03\003\D | RS | 3 | 3 | D | 1 Prestrip - Thick | 100 | 51.0602 | 51.0602 | 2017-01-30 04:43 | 2017-02-01 | 86550.2076 | 86550 | [7 empty] | 0 | 0 | 10.08 | 6.19 | 5876.96
TS Fleet 5 | BW\24\005\X1 | BW | 24 | 5 | X1 | 1 Prestrip - Thick | 73.1105 | 17.508 | 17.508 | 2017-01-30 12:10 | 2017-02-01 | 62181.1384 | 62181 | [7 empty] | 0 | 0 | 3.9 | 10.29 | 5483.03
TS6060#1 | BW\24\008\B | BW | 24 | 8 | B | 1 Prestrip - Thick | 9.3346 | 3.4862 | 3.4862 | 2017-01-30 13:01 | 2017-02-01 | 33289.968 | 33290 | [7 empty] | 0 | 0 | 2 | 11.57 | 5382.18
DRE1 | RS\02\003\D | RS | 2 | 3 | D | 6 DL | 100 | 0 | 24.5487 | 2017-01-31 04:32 | 2017-02-01 | 67074.0409 |  |  |  | 2560 | 67074 | 61442 |  |  | 0 | 13.88 | 0 | 6.05 | 5905.96
DRE2 | BW\22\011\D | BW | 22 | 11 | D | 6 DL | 100 | 8.0033 | 8.0033 | 2017-01-31 13:17 | 2017-02-01 | 35523.7427 |  |  |  | 1549 | 35524 | 25632 |  |  | 0 | 21.25 | 0 | 7.15 | 5786.09
| EOP 37 : 2017\Jan | EOP 37 : 2017 | Jan | [6 empty] | 2017-02-01 | 2017-02-01 |  | 4667769 |  | 229059 | 254511 | 4295167 | 2986496 | 1424700 | 1061923 | 75.87 | 0 | 273.43 | 7.85 | 5717.04
TS Fleet 5 | BW\24\005\X1 | BW | 24 | 5 | X1 | 1 Prestrip - Thick | 73.1105 | 55.6025 | 55.6025 | 2017-02-01 | 2017-02-05 21:32 | 197476.9097 | 197477 | [7 empty] | 0 | 0 | 12.4 | 10.29 | 5483.03
DRE1 | RS\02\003\D | RS | 2 | 3 | D | 6 DL | 100 | 0 | 75.4513 | 2017-02-01 | 2017-02-03 10:14 | 206154.773 |  |  |  | 7869 | 206155 | 188844 |  |  | 0 | 13.88 | 0 | 6.05 | 5905.96
PH4100A | RS\03\003\D | RS | 3 | 3 | D | 1 Prestrip - Thick | 100 | 3.9346 | 3.9346 | 2017-02-01 | 2017-02-01 04:19 | 6669.316 | 6669 | [7 empty] | 0 | 0 | 0.78 | 6.19 | 5876.96
DRE2 | BW\22\011\D | BW | 22 | 11 | D | 6 DL | 100 | 91.9967 | 91.9967 | 2017-02-01 | 2017-02-05 23:47 | 408341.2731 |  |  |  | 17809 | 408341 | 294632 |  |  | 0 | 21.25 | 0 | 7.15 | 5786.09
TS5500Shv | DT\25\004\B | DT | 25 | 4 | B | 1 Prestrip - Thick | 30.6925 | 1.3622 | 1.3622 | 2017-02-01 | 2017-02-01 09:57 | 9586.7371 | 9587 | [7 empty] | 0 | 0 | 0.56 | 10.8 | 5308.59
PH4100XPC#1 | RS\03\003\D | RS | 3 | 3 | D | 1 Prestrip - Thick | 100 | 5.0249 | 5.0249 | 2017-02-01 | 2017-02-01 04:19 | 8517.5997 | 8518 | [7 empty] | 0 | 0 | 0.99 | 6.19 | 5876.96
TS6060#1 | BW\24\008\B | BW | 24 | 8 | B | 1 Prestrip - Thick | 9.3346 | 5.8485 | 5.8485 | 2017-02-01 | 2017-02-03 12:37 | 55848.1998 | 55848 | [7 empty] | 0 | 0 | 3.36 | 11.57 | 5382.18
TS5500Exc | MW\25\005\A | MW | 25 | 5 | A | 1 Prestrip - Thick | 66.6059 | 49.1552 | 49.1552 | 2017-02-01 | 2017-02-09 18:24 | 167542.0721 | 167542 | [7 empty] | 0 | 0 | 10.12 | 10.05 | 5482.12
PH4100XPC#1 | RS\03\004\D | RS | 3 | 4 | D | 1 Prestrip - Thick | 100 | 55.9641 | 55.9641 | 2017-02-01 04:19 | 2017-02-03 21:58 | 127779.3311 | 127779 | [7 empty] | 0 | 0 | 12.68 | 6.38 | 5860.4
PH4100A | RS\03\004\D | RS | 3 | 4 | D | 1 Prestrip - Thick | 100 | 44.0359 | 44.0359 | 2017-02-01 04:19 | 2017-02-03 21:58 | 100544.4055 | 100544 | [7 empty] | 0 | 0 | 9.98 | 6.38 | 5860.4
TS5500Shv | MW\24\004\A | MW | 24 | 4 | A | 8 Coal Mining | 49.2 | 0 | 5.3 | 2017-02-01 09:57 | 2017-02-01 14:02 | 4465.1611 | [6 empty] | 4465 | 3309 | 0.21 | 0 | 0 | 9.23 | 5545
TS5500Shv | MW\24\005\A | MW | 24 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-02-01 14:02 | 2017-02-02 04:55 | 16250.5133 | [6 empty] | 16251 | 11944 | 0.73 | 0 | 0 | 10.94 | 5408
TS5500Shv | MW\24\006\B | MW | 24 | 6 | B | 8 Coal Mining | 13 | 0 | 13 | 2017-02-02 04:55 | 2017-02-02 11:44 | 7444.5087 | [6 empty] | 7445 | 5521 | 0.34 | 0 | 0 | 8.91 | 5655
TS5500Shv | DT\25\004\B | DT | 25 | 4 | B | 1 Prestrip - Thick | 69.3075 | 69.3075 | 69.3075 | 2017-02-02 11:44 | 2017-02-23 13:58 | 487752.407 | 487752 | [7 empty] | 0 | 0 | 28.72 | 10.8 | 5308.59
DRE1 | RS\02\004\D | RS | 2 | 4 | D | 6 DL | 100 | 0 | 100 | 2017-02-03 10:14 | 2017-02-07 03:52 | 317288.3091 |  |  |  | 12110 | 317288 | 290646 |  |  | 0 | 14.84 | 0 | 6.23 | 5890.38
TS6060#1 | BW\23\004\B | BW | 23 | 4 | B | 8 Coal Mining | 100 | 0 | 48.8 | 2017-02-03 12:37 | 2017-02-04 21:45 | 40146.7344 | [6 empty] | 40147 | 29286 | 1.83 | 0 | 0 | 10.8 | 5447
PH4100A | RS\03\005\B | RS | 3 | 5 | B | 1 Prestrip - Thick | 100 | 57.6443 | 57.6443 | 2017-02-03 21:58 | 2017-02-08 15:09 | 169742.3784 | 169742 | [7 empty] | 0 | 0 | 16.68 | 16.32 | 4990.39
PH4100XPC#1 | MW\24\004\B | MW | 24 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-02-03 21:58 | 2017-02-05 02:06 | 58224.992 | 58225 | [7 empty] | 0 | 0 | 3.63 | 9.1 | 5588.12
TS6060#1 | BW\23\005\B | BW | 23 | 5 | B | 8 Coal Mining | 17.8 | 0 | 17.8 | 2017-02-04 21:45 | 2017-02-05 09:55 | 14758.4865 | [6 empty] | 14758 | 10759 | 0.67 | 0 | 0 | 10.89 | 5450
PH4100XPC#1 | MW\24\005\B | MW | 24 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-02-05 02:06 | 2017-02-05 20:40 | 38420.359 | 38420 | [7 empty] | 0 | 0 | 2.38 | 9.01 | 5633.06
TS6060#1 | BW\23\005\B | BW | 23 | 5 | B | 8 Coal Mining | 82.2 | 0 | 82.2 | 2017-02-05 09:55 | 2017-02-07 18:15 | 68278.2395 | [6 empty] | 68278 | 49774 | 3.11 | 0 | 0 | 10.89 | 5450
PH4100XPC#1 | RS\03\005\B | RS | 3 | 5 | B | 1 Prestrip - Thick | 100 | 42.3557 | 42.3557 | 2017-02-05 20:40 | 2017-02-08 15:09 | 124722.7092 | 124723 | [7 empty] | 0 | 0 | 12.26 | 16.32 | 4990.39
TS Fleet 5 | BW\24\006\B | BW | 24 | 6 | B | 1 Prestrip - Thick | 67.9796 | 67.9796 | 67.9796 | 2017-02-05 21:32 | 2017-02-20 16:46 | 596795.3331 | 596795 | [7 empty] | 0 | 0 | 37.25 | 10.42 | 5487
DRE2 | BW\22\010\D | BW | 22 | 10 | D | 6 DL | 100 | 100 | 100 | 2017-02-05 23:47 | 2017-02-11 10:40 | 446109.5359 |  |  |  | 19456 | 446110 | 321883 |  |  | 0 | 21.34 | 0 | 6.49 | 5844.55
DRE1 | RS\02\005\D | RS | 2 | 5 | D | 6 DL | 100 | 0 | 100 | 2017-02-07 03:52 | 2017-02-13 08:50 | 527277.2146 |  |  |  | 23592 | 527277 | 448245 |  |  | 0 | 23.17 | 0 | 6.12 | 5899.78
TS6060#1 | DT\22\004\D | DT | 22 | 4 | D | 8 Coal Mining | 78.5 | 0 | 78.5 | 2017-02-07 18:15 | 2017-02-10 11:10 | 78668.6621 | [6 empty] | 78669 | 59489 | 3.72 | 0 | 0 | 5.79 | 5904
PH4100XPC#1 | RS\03\006\B | RS | 3 | 6 | B | 1 Prestrip - Thick | 100 | 55.5386 | 55.5386 | 2017-02-08 15:09 | 2017-02-12 05:22 | 161215.1924 | 161215 | [7 empty] | 0 | 0 | 15.72 | 15.54 | 5053.21
PH4100A | RS\03\006\B | RS | 3 | 6 | B | 1 Prestrip - Thick | 100 | 44.4614 | 44.4614 | 2017-02-08 15:09 | 2017-02-12 05:22 | 129060.7686 | 129061 | [7 empty] | 0 | 0 | 12.59 | 15.54 | 5053.21
TS5500Exc | SC\28\005\D | SC | 28 | 5 | D | 8 Coal Mining | 90.1 | 0 | 41.2 | 2017-02-09 18:24 | 2017-02-10 22:51 | 32082.5813 | [6 empty] | 32083 | 24151 | 2.01 | 0 | 0 | 6.07 | 5880
TS6060#1 | RS\01\008\D | RS | 1 | 8 | D | 8 Coal Mining | 93.4 | 0 | 93.4 | 2017-02-10 11:10 | 2017-02-15 19:43 | 155808.5962 | [6 empty] | 155809 | 112930 | 2.58 | 0 | 0 | 7.08 | 5786
TS5500Exc | SC\28\006\D | SC | 28 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-02-10 22:51 | 2017-02-13 20:02 | 78046.8509 | [6 empty] | 78047 | 59033 | 4.92 | 0 | 0 | 5.91 | 5895
DRE2 | BW\22\009\D | BW | 22 | 9 | D | 6 DL | 100 | 100 | 100 | 2017-02-11 10:40 | 2017-02-17 20:58 | 525935.6566 |  |  |  | 31409 | 525936 | 371272 |  |  | 0 | 25.17 | 0 | 5.78 | 5907.46
PH4100A | RS\03\007\B | RS | 3 | 7 | B | 1 Prestrip - Thick | 100 | 44.4525 | 44.4525 | 2017-02-12 05:22 | 2017-02-15 22:29 | 133468.8367 | 133469 | [7 empty] | 0 | 0 | 13.06 | 16.91 | 4992.94
PH4100XPC#1 | RS\03\007\B | RS | 3 | 7 | B | 1 Prestrip - Thick | 100 | 55.5475 | 55.5475 | 2017-02-12 05:22 | 2017-02-15 22:29 | 166781.8458 | 166782 | [7 empty] | 0 | 0 | 16.33 | 16.91 | 4992.94
DRE1 | RS\02\006\D | RS | 2 | 6 | D | 6 DL | 100 | 0 | 100 | 2017-02-13 08:50 | 2017-02-19 07:52 | 506276.9164 |  |  |  | 22652 | 506277 | 430392 |  |  | 0 | 22.14 | 0 | 6.35 | 5879.57
TS5500Exc | SC\28\007\D | SC | 28 | 7 | D | 8 Coal Mining | 39.5 | 0 | 39.5 | 2017-02-13 20:02 | 2017-02-14 22:46 | 30151.6435 | [6 empty] | 30152 | 22898 | 1.91 | 0 | 0 | 5.81 | 5903
TS5500Exc | SC\28\007\D | SC | 28 | 7 | D | 8 Coal Mining | 60.5 | 0 | 60.5 | 2017-02-14 22:46 | 2017-02-16 15:38 | 46104.1714 | [6 empty] | 46104 | 35012 | 2.92 | 0 | 0 | 5.81 | 5903
TS6060#1 | DT\22\006\D | DT | 22 | 6 | D | 8 Coal Mining | 46.8 | 0 | 46.8 | 2017-02-15 19:43 | 2017-02-16 14:28 | 22718.8585 | [6 empty] | 22719 | 17220 | 2.15 | 0 | 0 | 5.56 | 5924
PH4100A | RS\03\008\B | RS | 3 | 8 | B | 1 Prestrip - Thick | 100 | 44.4498 | 44.4498 | 2017-02-15 22:29 | 2017-02-19 15:56 | 133965.0675 | 133965 | [7 empty] | 0 | 0 | 13.34 | 17.9 | 4943.38
PH4100XPC#1 | RS\03\008\B | RS | 3 | 8 | B | 1 Prestrip - Thick | 100 | 55.5502 | 55.5502 | 2017-02-15 22:29 | 2017-02-19 15:56 | 167420.2857 | 167420 | [7 empty] | 0 | 0 | 16.67 | 17.9 | 4943.38
TS6060#1 | BW\21\002\D | BW | 21 | 2 | D | 8 Coal Mining | 35.9 | 0 | 35.9 | 2017-02-16 14:28 | 2017-02-17 21:17 | 37353.8899 | [6 empty] | 37354 | 28043 | 1.75 | 0 | 0 | 6.63 | 5831
TS5500Exc | SC\28\008\D | SC | 28 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-02-16 15:38 | 2017-02-19 11:39 | 76706.8235 | [6 empty] | 76707 | 58159 | 4.85 | 0 | 0 | 6.04 | 5883
DRE2 | BW\22\008\D | BW | 22 | 8 | D | 6 DL | 100 | 100 | 100 | 2017-02-17 20:58 | 2017-02-23 20:31 | 489289.4826 |  |  |  | 21340 | 489289 | 353039 |  |  | 0 | 23.37 | 0 | 5.46 | 5935.15
TS6060#1 | BW\21\007\D | BW | 21 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-02-17 21:17 | 2017-02-21 11:57 | 105035.5219 | [6 empty] | 105036 | 79933 | 5 | 0 | 0 | 5.35 | 5945
DRE1 | RS\02\007\D | RS | 2 | 7 | D | 6 DL | 100 | 0 | 100 | 2017-02-19 07:52 | 2017-02-25 20:44 | 555310.9357 |  |  |  | 24846 | 555311 | 472076 |  |  | 0 | 24.08 | 0 | 6.5 | 5865.57
TS5500Exc | RS\02\005\D | RS | 2 | 5 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2017-02-19 11:39 | 2017-02-21 15:08 | 58084.5852 | [6 empty] | 58085 | 42007 | 2.1 | 0 | 0 | 6.12 | 5900
PH4100XPC#1 | BW\24\010\A | BW | 24 | 10 | A | 1 Prestrip - Thick | 100 | 0 | 68.302 | 2017-02-19 15:56 | 2017-03-01 | 485305.8918 | 485306 | [7 empty] | 0 | 0 | 32.31 | 0 | 0
PH4100A | RS\04\003\D | RS | 4 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-02-19 15:56 | 2017-02-24 05:26 | 169550.4569 | 169550 | [7 empty] | 0 | 0 | 19.58 | 6.21 | 5874.83
TS Fleet 5 | BW\24\007\B | BW | 24 | 7 | B | 1 Prestrip - Thick | 34.2467 | 34.0446 | 34.0446 | 2017-02-20 16:46 | 2017-03-01 | 334687.7572 | 334688 | [7 empty] | 0 | 0 | 20.65 | 11 | 5436.93
TS6060#1 | DT\22\007\D | DT | 22 | 7 | D | 8 Coal Mining | 29.8 | 0 | 29.8 | 2017-02-21 11:57 | 2017-02-22 06:11 | 22107.5677 | [6 empty] | 22108 | 16783 | 1.34 | 0 | 0 | 5.56 | 5923
TS5500Exc | MW\24\010\A | MW | 24 | 10 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-02-21 15:08 | 2017-02-23 01:17 | 38518.5394 | [6 empty] | 38519 | 28265 | 1.76 | 0 | 0 | 10.24 | 5507
TS6060#1 | BW\23\008\B | BW | 23 | 8 | B | 8 Coal Mining | 92.2 | 0 | 92.2 | 2017-02-22 06:11 | 2017-02-24 22:46 | 78265.4606 | [6 empty] | 78265 | 56597 | 3.57 | 0 | 0 | 12.45 | 5312
TS5500Exc | MW\24\011\A | MW | 24 | 11 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-02-23 01:17 | 2017-02-24 12:47 | 40050.775 | [6 empty] | 40051 | 29369 | 1.83 | 0 | 0 | 10.42 | 5501
TS5500Shv | MW\24\004\B | MW | 24 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-02-23 13:58 | 2017-02-26 00:47 | 64233.0872 | [6 empty] | 64233 | 47576 | 2.98 | 0 | 0 | 9.1 | 5588
DRE2 | BW\22\007\D | BW | 22 | 7 | D | 6 DL | 100 | 90.645 | 90.645 | 2017-02-23 20:31 | 2017-03-01 | 420903.2518 |  |  |  | 18357 | 420903 | 303696 |  |  | 0 | 22.2 | 0 | 5.26 | 5952.1
PH4100A | RS\04\004\B | RS | 4 | 4 | B | 1 Prestrip - Thick | 100 | 64.8314 | 64.8314 | 2017-02-24 05:26 | 2017-03-01 | 170664.0562 | 170664 | [7 empty] | 0 | 0 | 16.6 | 12.9 | 5282.18
TS5500Exc | RS\02\006\D | RS | 2 | 6 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2017-02-24 12:47 | 2017-02-26 17:12 | 59125.0824 | [6 empty] | 59125 | 42893 | 2.14 | 0 | 0 | 6.35 | 5880
TS6060#1 | RS\03\007\B | RS | 3 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-02-24 22:46 | 2017-02-26 20:09 | 55016.4952 | [6 empty] | 55016 | 37609 | 3.76 | 0 | 0 | 16.91 | 4993
DRE1 | RS\02\008\D1 | RS | 2 | 8 | D1 | 6 DL | 100 | 0 | 46.7325 | 2017-02-25 20:44 | 2017-03-01 | 266370.2511 |  |  |  | 10354 | 266370 | 152528 |  |  | 0 | 22.3 | 0 | 7.21 | 5725.21
TS5500Shv | MW\24\005\B | MW | 24 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-02-26 00:47 | 2017-02-28 09:27 | 61874.2543 | [6 empty] | 61874 | 45850 | 2.88 | 0 | 0 | 9.01 | 5633
TS5500Exc | DT\22\002\D | DT | 22 | 2 | D | 8 Coal Mining | 37.7 | 0 | 37.7 | 2017-02-26 17:12 | 2017-02-28 20:31 | 57875.7481 | [6 empty] | 57876 | 43418 | 1.8 | 0 | 0 | 6.72 | 5823
TS6060#1 | RS\03\008\B | RS | 3 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-02-26 20:09 | 2017-02-28 12:07 | 48428.7623 | [6 empty] | 48429 | 32870 | 3.85 | 0 | 0 | 17.9 | 4943
TS5500Shv | MW\24\006\B | MW | 24 | 6 | B | 8 Coal Mining | 87 | 0 | 23.7 | 2017-02-28 09:27 | 2017-02-28 21:55 | 13623.6351 | [6 empty] | 13624 | 10103 | 0.62 | 0 | 0 | 8.91 | 5655
TS6060#1 | DT\22\003\D | DT | 22 | 3 | D | 8 Coal Mining | 100 | 0 | 11.6 | 2017-02-28 12:07 | 2017-02-28 21:55 | 11885.8771 | [6 empty] | 11886 | 8960 | 0.56 | 0 | 0 | 6.14 | 5874
TS5500Exc | DT\24\001\B | DT | 24 | 1 | B | 8 Coal Mining | 30.2 | 0 | 2 | 2017-02-28 20:31 | 2017-02-28 21:55 | 1588.8877 | [6 empty] | 1589 | 1158 | 0.06 | 0 | 0 | 11.34 | 5359
TS5500Shv | DT\25\006\A | DT | 25 | 6 | A | 1 Prestrip - Thick | 61.3515 | 0.46215 | 0.46215 | 2017-02-28 21:55 | 2017-03-01 | 1983.0487 | 1983 | [7 empty] | 0 | 0 | 0.15 | 10.74 | 5388.23
TS6060#1 | BW\25\003\X1 | BW | 25 | 3 | X1 | 1 Prestrip - Thick | 29.8111 | 0.27646 | 0.27646 | 2017-02-28 21:55 | 2017-03-01 | 1898.5293 | 1899 | [7 empty] | 0 | 0 | 0.09 | 11.61 | 5365.98
TS5500Exc | MW\25\005\A | MW | 25 | 5 | A | 1 Prestrip - Thick | 20.4485 | 0.48363 | 0.48363 | 2017-02-28 21:55 | 2017-03-01 | 1648.4342 | 1648 | [7 empty] | 0 | 0 | 0.1 | 10.05 | 5482.12
| EOP 38 : 2017\Feb | EOP 38 : 2017 | Feb | [6 empty] | 2017-03-01 | 2017-03-01 |  | 4207273 |  |  | 209794 | 4669258 | 3627253 | 1424700 | 1050918 | 67.96 | 0 | 328.98 | 8.07 | 5711.13
TS Fleet 5 | BW\24\007\B | BW | 24 | 7 | B | 1 Prestrip - Thick | 34.2467 | 0.20212 | 0.20212 | 2017-03-01 | 2017-03-01 01:03 | 1987.05 | 1987 | [7 empty] | 0 | 0 | 0.12 | 11 | 5436.93
DRE1 | RS\02\008\D1 | RS | 2 | 8 | D1 | 6 DL | 100 | 0 | 53.2675 | 2017-03-01 | 2017-03-04 13:46 | 303618.8627 |  |  |  | 11802 | 303619 | 173857 |  |  | 0 | 22.3 | 0 | 7.21 | 5725.21
PH4100A | RS\04\004\B | RS | 4 | 4 | B | 1 Prestrip - Thick | 100 | 35.1686 | 35.1686 | 2017-03-01 | 2017-03-03 09:38 | 92578.6439 | 92579 | [7 empty] | 0 | 0 | 9.01 | 12.9 | 5282.18
DRE2 | BW\22\007\D | BW | 22 | 7 | D | 6 DL | 100 | 9.355 | 9.355 | 2017-03-01 | 2017-03-01 12:44 | 43439.1915 |  |  |  | 1895 | 43439 | 31343 |  |  | 0 | 22.2 | 0 | 5.26 | 5952.1
TS5500Shv | DT\25\006\A | DT | 25 | 6 | A | 1 Prestrip - Thick | 61.3515 | 60.8893 | 60.8893 | 2017-03-01 | 2017-03-11 04:15 | 261271.8678 | 261272 | [7 empty] | 0 | 0 | 20.09 | 10.74 | 5388.23
PH4100XPC#1 | BW\24\010\A | BW | 24 | 10 | A | 1 Prestrip - Thick | 100 | 0 | 31.698 | 2017-03-01 | 2017-03-05 00:27 | 225223.1581 | 225223 | [7 empty] | 0 | 0 | 15 | 0 | 0
TS6060#1 | BW\25\003\X1 | BW | 25 | 3 | X1 | 1 Prestrip - Thick | 29.8111 | 29.5346 | 29.5346 | 2017-03-01 | 2017-03-09 06:03 | 202823.7398 | 202824 | [7 empty] | 0 | 0 | 9.13 | 11.61 | 5365.98
TS5500Exc | MW\25\005\A | MW | 25 | 5 | A | 1 Prestrip - Thick | 20.4485 | 19.9648 | 19.9648 | 2017-03-01 | 2017-03-04 04:31 | 68048.8356 | 68049 | [7 empty] | 0 | 0 | 4.11 | 10.05 | 5482.12
TS Fleet 5 | BW\24\007\B | BW | 24 | 7 | B | 1 Prestrip - Thick | 65.7533 | 65.7533 | 65.7533 | 2017-03-01 01:03 | 2017-03-15 09:37 | 646412.4144 | 646412 | [7 empty] | 0 | 0 | 39.88 | 11 | 5436.93
DRE2 | BW\22\006\D | BW | 22 | 6 | D | 6 DL | 100 | 100 | 100 | 2017-03-01 12:44 | 2017-03-07 06:53 | 470899.3518 |  |  |  | 20538 | 470899 | 339770 |  |  | 0 | 22.51 | 0 | 5.48 | 5935.5
PH4100A | RS\04\005\B | RS | 4 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-03-03 09:38 | 2017-03-11 09:30 | 311182.592 | 311183 | [7 empty] | 0 | 0 | 30.66 | 14.52 | 5134.38
TS5500Exc | DT\24\001\B | DT | 24 | 1 | B | 8 Coal Mining | 30.2 | 0 | 28.2 | 2017-03-04 04:31 | 2017-03-04 22:30 | 22650.7441 | [6 empty] | 22651 | 16508 | 0.91 | 0 | 0 | 11.34 | 5359
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2017-03-04 13:46 | 2017-03-06 13:46
TS5500Exc | RS\02\008\D1 | RS | 2 | 8 | D1 | 7 PostStrip | 81.8809 | 0 | 81.8809 | 2017-03-04 22:30 | 2017-03-08 14:04 | 77436.7282 |  |  | 77437 | [5 empty] | 0 | 0 | 0 | 7.21 | 5725.21
PH4100XPC#1 | MW\24\004\D | MW | 24 | 4 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-03-05 00:27 | 2017-03-05 00:27 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | MW\24\005\D | MW | 24 | 5 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-03-05 00:27 | 2017-03-05 00:27 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | BW\24\009\A | BW | 24 | 9 | A | 1 Prestrip - Thick | 100 | 0 | 100 | 2017-03-05 00:27 | 2017-03-14 08:20 | 508930.0287 | 508930 | [7 empty] | 0 | 0 | 29.16 | 0 | 0
DRE1 | MW\21\008\D | MW | 21 | 8 | D | 6 DL | 100 | 100 | 100 | 2017-03-06 13:46 | 2017-03-13 03:16 | 557492.0493 |  |  |  | 33294 | 557492 | 393549 |  |  | 0 | 26.68 | 0 | 5.97 | 5887.22
DRE2 | BW\22\005\D | BW | 22 | 5 | D | 6 DL | 100 | 100 | 100 | 2017-03-07 06:53 | 2017-03-13 03:29 | 479213.3216 |  |  |  | 20900 | 479213 | 345769 |  |  | 0 | 22.91 | 0 | 5.64 | 5919.66
TS5500Exc | SC\29\006\B | SC | 29 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-03-08 14:04 | 2017-03-10 09:45 | 55015.3797 | [6 empty] | 55015 | 40606 | 3.4 | 0 | 0 | 9.26 | 5547
TS6060#1 | DT\22\003\D | DT | 22 | 3 | D | 8 Coal Mining | 100 | 0 | 88.4 | 2017-03-09 06:03 | 2017-03-12 00:50 | 90371.3431 | [6 empty] | 90371 | 68122 | 4.26 | 0 | 0 | 6.14 | 5874
TS5500Exc | SC\30\006\B | SC | 30 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-03-10 09:45 | 2017-03-12 03:13 | 52248.859 | [6 empty] | 52249 | 38551 | 3.21 | 0 | 0 | 9.34 | 5541
TS5500Shv | MW\24\006\B | MW | 24 | 6 | B | 8 Coal Mining | 87 | 0 | 63.3 | 2017-03-11 04:15 | 2017-03-12 10:03 | 36338.5467 | [6 empty] | 36339 | 26948 | 1.66 | 0 | 0 | 8.91 | 5655
PH4100A | RS\04\006\B | RS | 4 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-03-11 09:30 | 2017-03-19 18:01 | 326409.749 | 326410 | [7 empty] | 0 | 0 | 32.09 | 16.13 | 5000.39
TS6060#1 | BW\21\001\D | BW | 21 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-03-12 00:50 | 2017-03-14 14:05 | 82896.7715 | [6 empty] | 82897 | 62483 | 4.85 | 0 | 0 | 6.15 | 5873
TS5500Exc | RS\04\005\B | RS | 4 | 5 | B | 8 Coal Mining | 44.1 | 0 | 44.1 | 2017-03-12 03:13 | 2017-03-12 19:29 | 20474.7649 | [6 empty] | 20475 | 14322 | 1.43 | 0 | 0 | 14.52 | 5134
TS5500Shv | MW\24\007\B | MW | 24 | 7 | B | 8 Coal Mining | 8.1 | 0 | 8.1 | 2017-03-12 10:03 | 2017-03-12 14:07 | 4947.7049 | [6 empty] | 4948 | 3644 | 0.23 | 0 | 0 | 9.78 | 5541
TS5500Shv | MW\24\007\B | MW | 24 | 7 | B | 8 Coal Mining | 91.9 | 0 | 91.9 | 2017-03-12 14:07 | 2017-03-14 11:56 | 55875.5674 | [6 empty] | 55876 | 41156 | 2.56 | 0 | 0 | 9.78 | 5541
TS5500Exc | SC\29\007\B | SC | 29 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-03-12 19:29 | 2017-03-14 17:33 | 58029.17 | [6 empty] | 58029 | 42814 | 3.6 | 0 | 0 | 9.33 | 5536
DRE1 | MW\21\009\D | MW | 21 | 9 | D | 6 DL | 100 | 0 | 100 | 2017-03-13 03:16 | 2017-03-19 19:46 | 568151.8431 |  |  |  | 33930 | 568152 | 401074 |  |  | 0 | 27.17 | 0 | 6.25 | 5861.72
DRE2 | BW\22\004\D | BW | 22 | 4 | D | 6 DL | 100 | 100 | 100 | 2017-03-13 03:29 | 2017-03-19 00:39 | 481180.9939 |  |  |  | 20986 | 481181 | 347188 |  |  | 0 | 23 | 0 | 6.02 | 5885.17
PH4100XPC#1 | MW\24\006\D | MW | 24 | 6 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-03-14 08:20 | 2017-03-14 08:20 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | BW\24\011\B | BW | 24 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-03-14 08:20 | 2017-03-28 11:29 | 766280.1336 | 766280 | [7 empty] | 0 | 0 | 47.95 | 15.42 | 5045.19
TS5500Shv | MW\24\008\A | MW | 24 | 8 | A | 8 Coal Mining | 100 | 0 | 100 | 2017-03-14 11:56 | 2017-03-15 07:27 | 23806.9232 | [6 empty] | 23807 | 17306 | 1.05 | 0 | 0 | 12.81 | 5168
TS6060#1 | RS\03\005\B | RS | 3 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-03-14 14:05 | 2017-03-15 01:36 | 15585.5101 | [6 empty] | 15586 | 10785 | 1.04 | 0 | 0 | 16.32 | 4990
TS5500Exc | MW\21\008\D | MW | 21 | 8 | D | 8 Coal Mining | 46.9 | 0 | 46.9 | 2017-03-14 17:33 | 2017-03-16 04:48 | 44407.0012 | [6 empty] | 44407 | 33522 | 2.1 | 0 | 0 | 5.97 | 5887
TS6060#1 | RS\03\006\B | RS | 3 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-03-15 01:36 | 2017-03-16 04:49 | 36842.4259 | [6 empty] | 36842 | 25482 | 2.51 | 0 | 0 | 15.54 | 5053
TS5500Shv | MW\24\009\A | MW | 24 | 9 | A | 8 Coal Mining | 100 | 0 | 100 | 2017-03-15 07:27 | 2017-03-17 18:51 | 72414.7332 | [6 empty] | 72415 | 53270 | 3.35 | 0 | 0 | 10.31 | 5434
TS Fleet 5 | BW\24\008\B | BW | 24 | 8 | B | 1 Prestrip - Thick | 76.2985 | 76.2985 | 76.2985 | 2017-03-15 09:37 | 2017-03-31 14:00 | 728587.5856 | 728588 | [7 empty] | 0 | 0 | 43.87 | 11.57 | 5382.18
TS5500Exc | SC\30\007\B | SC | 30 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-03-16 04:48 | 2017-03-17 20:07 | 49525.8084 | [6 empty] | 49526 | 36502 | 3.05 | 0 | 0 | 9.51 | 5522
TS6060#1 | BW\22\009\D | BW | 22 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-03-16 04:49 | 2017-03-19 13:50 | 109657.1086 | [6 empty] | 109657 | 82979 | 5.19 | 0 | 0 | 5.78 | 5907
TS5500Shv | MW\24\010\A | MW | 24 | 10 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-03-17 18:51 | 2017-03-19 01:25 | 37289.2243 | [6 empty] | 37289 | 27363 | 1.71 | 0 | 0 | 10.24 | 5507
TS5500Exc | MW\24\009\B | MW | 24 | 9 | B | 1 Prestrip - Thick | 83.2573 | 83.2573 | 83.2573 | 2017-03-17 20:07 | 2017-03-21 04:01 | 70658.6156 | 70659 | [7 empty] | 0 | 0 | 4.44 | 9.65 | 5543.33
DRE2 | BW\22\003\D | BW | 22 | 3 | D | 6 DL | 100 | 100 | 100 | 2017-03-19 00:39 | 2017-03-24 19:22 | 472843.6126 |  |  |  | 20622 | 472844 | 341173 |  |  | 0 | 22.62 | 0 | 6.76 | 5820.71
TS5500Shv | MW\24\011\A | MW | 24 | 11 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-03-19 01:25 | 2017-03-20 09:13 | 38772.5587 | [6 empty] | 38773 | 28431 | 1.77 | 0 | 0 | 10.42 | 5501
TS6060#1 | RS\04\004\B | RS | 4 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-03-19 13:50 | 2017-03-20 07:23 | 23741.1796 | [6 empty] | 23741 | 16840 | 1.64 | 0 | 0 | 12.9 | 5282
PH4100A | RS\04\007\A | RS | 4 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-03-19 18:01 | 2017-03-27 04:58 | 288641.3839 | 288641 | [7 empty] | 0 | 0 | 28.34 | 15.72 | 5013.11
DRE1 | MW\21\010\D | MW | 21 | 10 | D | 6 DL | 100 | 100 | 100 | 2017-03-19 19:46 | 2017-03-26 07:28 | 551087.0582 |  |  |  | 32911 | 551087 | 389028 |  |  | 0 | 26.4 | 0 | 6.19 | 5866.68
TS6060#1 | RS\02\003\D | RS | 2 | 3 | D | 8 Coal Mining | 97.7 | 0 | 97.7 | 2017-03-20 07:23 | 2017-03-23 23:14 | 118902.5722 | [6 empty] | 118903 | 87469 | 4.32 | 0 | 0 | 6.05 | 5906
TS5500Shv | MW\25\003\A | MW | 25 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2017-03-20 09:13 | 2017-03-22 04:38 | 52943.1798 | [6 empty] | 52943 | 38991 | 2.44 | 0 | 0 | 10.16 | 5456
TS5500Exc | RS\04\006\B | RS | 4 | 6 | B | 8 Coal Mining | 65.4 | 0 | 65.4 | 2017-03-21 04:01 | 2017-03-22 08:59 | 36489.8025 | [6 empty] | 36490 | 25169 | 2.51 | 0 | 0 | 16.13 | 5000
TS5500Shv | DT\22\002\D | DT | 22 | 2 | D | 8 Coal Mining | 62.3 | 0 | 62.3 | 2017-03-22 04:38 | 2017-03-25 11:05 | 95648.816 | [6 empty] | 95649 | 71755 | 2.98 | 0 | 0 | 6.72 | 5823
TS5500Exc | MW\24\010\B | MW | 24 | 10 | B | 1 Prestrip - Thick | 28.3863 | 28.3863 | 28.3863 | 2017-03-22 08:59 | 2017-03-23 03:20 | 16220.8573 | 16221 | [7 empty] | 0 | 0 | 1.01 | 8.65 | 5661.89
TS5500Exc | MW\24\011\B | MW | 24 | 11 | B | 1 Prestrip - Thick | 28.3863 | 28.3863 | 28.3863 | 2017-03-23 03:20 | 2017-03-23 16:56 | 12030.2136 | 12030 | [7 empty] | 0 | 0 | 0.75 | 8.15 | 5700.73
TS5500Exc | MW\25\003\B | MW | 25 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-03-23 16:56 | 2017-03-26 07:38 | 55454.7984 | 55455 | [7 empty] | 0 | 0 | 3.46 | 8.28 | 5631.27
TS6060#1 | RS\02\003\D | RS | 2 | 3 | D | 8 Coal Mining | 2.3 | 0 | 2.3 | 2017-03-23 23:14 | 2017-03-24 01:19 | 2819.1189 | [6 empty] | 2819 | 2074 | 0.1 | 0 | 0 | 6.05 | 5906
TS6060#1 | RS\02\004\D | RS | 2 | 4 | D | 8 Coal Mining | 100 | 0 | 96 | 2017-03-24 01:19 | 2017-03-27 18:05 | 120139.8973 | [6 empty] | 120140 | 87431 | 4.37 | 0 | 0 | 6.23 | 5890
DRE2 | BW\22\002\D | BW | 22 | 2 | D | 6 DL | 100 | 100 | 100 | 2017-03-24 19:22 | 2017-03-30 07:55 | 451810.2504 |  |  |  | 19705 | 451810 | 325996 |  |  | 0 | 21.61 | 0 | 6.63 | 5831.89
TS5500Shv | DT\24\001\B | DT | 24 | 1 | B | 8 Coal Mining | 29.2 | 0 | 29.2 | 2017-03-25 11:05 | 2017-03-26 06:19 | 23466.0265 | [6 empty] | 23466 | 17103 | 0.94 | 0 | 0 | 11.34 | 5359
TS5500Shv | RS\02\008\D1 | RS | 2 | 8 | D1 | 7 PostStrip | 18.1191 | 0 | 18.1191 | 2017-03-26 06:19 | 2017-03-26 22:18 | 17135.6651 |  |  | 17136 | [5 empty] | 0 | 0 | 0 | 7.21 | 5725.21
DRE1 | MW\21\011\D | MW | 21 | 11 | D | 6 DL | 100 | 88.0005 | 88.0005 | 2017-03-26 07:28 | 2017-04-01 | 483281.3867 |  |  |  | 28862 | 483281 | 341162 |  |  | 0 | 26.31 | 0 | 5.71 | 5908.85
TS5500Exc | MW\21\009\D | MW | 21 | 9 | D | 8 Coal Mining | 50.8 | 0 | 47 | 2017-03-26 07:38 | 2017-03-27 18:05 | 43399.2622 | [6 empty] | 43399 | 32733 | 2.05 | 0 | 0 | 6.25 | 5862
TS5500Shv | DT\25\007\A | DT | 25 | 7 | A | 1 Prestrip - Thick | 25.0258 | 25.0258 | 25.0258 | 2017-03-26 22:18 | 2017-03-31 12:27 | 117392.026 | 117392 | [7 empty] | 0 | 0 | 7.34 | 10.19 | 5428.19
PH4100A | RS\04\008\A | RS | 4 | 8 | A | 1 Prestrip - Thick | 100 | 65.5132 | 65.5132 | 2017-03-27 04:58 | 2017-04-01 | 185588.5074 | 185589 | [7 empty] | 0 | 0 | 18.96 | 14.73 | 5116.6
TS6060#1 | BW\24\009\B | BW | 24 | 9 | B | 1 Prestrip - Thick | 27.1982 | 27.1982 | 27.1982 | 2017-03-27 18:05 | 2017-03-31 07:46 | 88401.3689 | 88401 | [7 empty] | 0 | 0 | 5.34 | 11.43 | 5382.03
TS5500Exc | MW\25\007\B | MW | 25 | 7 | B | 1 Prestrip - Thick | 22.3077 | 19.3688 | 19.3688 | 2017-03-27 18:05 | 2017-04-01 | 90653.5516 | 90654 | [7 empty] | 0 | 0 | 5.63 | 9.85 | 5536.77
PH4100XPC#1 | MW\24\007\D | MW | 24 | 7 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-03-28 11:29 | 2017-03-28 11:29 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | MW\24\008\B | MW | 24 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-03-28 11:29 | 2017-03-29 18:50 | 69937.0161 | 69937 | [7 empty] | 0 | 0 | 4.31 | 10.39 | 5458.02
PH4100XPC#1 | MW\24\009\B | MW | 24 | 9 | B | 1 Prestrip - Thick | 100 | 16.7427 | 16.7427 | 2017-03-29 18:50 | 2017-03-30 01:12 | 14209.1651 | 14209 | [7 empty] | 0 | 0 | 0.89 | 9.65 | 5543.33
PH4100XPC#1 | MW\24\010\B | MW | 24 | 10 | B | 1 Prestrip - Thick | 100 | 71.6137 | 71.6137 | 2017-03-30 01:12 | 2017-03-30 19:32 | 40922.3397 | 40922 | [7 empty] | 0 | 0 | 2.55 | 8.65 | 5661.89
DRE2 | BW\22\001\D | BW | 22 | 1 | D | 6 DL | 100 | 35.6524 | 35.6524 | 2017-03-30 07:55 | 2017-04-01 | 136611.6781 |  |  |  | 5240 | 136612 | 65418 |  |  | 0 | 21.61 | 0 | 6.35 | 5856.24
PH4100XPC#1 | MW\24\011\B | MW | 24 | 11 | B | 1 Prestrip - Thick | 100 | 71.6137 | 71.6137 | 2017-03-30 19:32 | 2017-03-31 09:08 | 30350.0905 | 30350 | [7 empty] | 0 | 0 | 1.89 | 8.15 | 5700.73
TS6060#1 | BW\25\003\X1 | BW | 25 | 3 | X1 | 1 Prestrip - Thick | 5.8847 | 2.42 | 2.42 | 2017-03-31 07:46 | 2017-04-01 | 16619.2372 | 16619 | [7 empty] | 0 | 0 | 0.75 | 11.61 | 5365.98
PH4100XPC#1 | BW\24\010\B | BW | 24 | 10 | B | 1 Prestrip - Thick | 100 | 58.4488 | 58.4488 | 2017-03-31 09:08 | 2017-04-01 | 33137.0399 | 33137 | [7 empty] | 0 | 0 | 2.07 | 12.52 | 5281.67
TS5500Shv | DT\25\007\A | DT | 25 | 7 | A | 1 Prestrip - Thick | 34.1713 | 2.6217 | 2.6217 | 2017-03-31 12:27 | 2017-04-01 | 12298.1473 | 12298 | [7 empty] | 0 | 0 | 0.77 | 10.19 | 5428.19
TS Fleet 5 | BW\24\008\B | BW | 24 | 8 | B | 1 Prestrip - Thick | 12.4563 | 1.9642 | 1.9642 | 2017-03-31 14:00 | 2017-04-01 | 18756.95 | 18757 | [7 empty] | 0 | 0 | 1.13 | 11.57 | 5382.18
| EOP 39 : 2017\Mar | EOP 39 : 2017 | Mar | [6 empty] | 2017-04-01 | 2017-04-01 |  | 5301007 |  | 94572 | 250684 | 4999630 | 3495326 | 1424700 | 1050360 | 69.21 | 0 | 370.7 | 8.65 | 5640.41
TS Fleet 5 | BW\24\008\B | BW | 24 | 8 | B | 1 Prestrip - Thick | 12.4563 | 10.492 | 10.492 | 2017-04-01 | 2017-04-03 03:07 | 100190.3213 | 100190 | [7 empty] | 0 | 0 | 6.03 | 11.57 | 5382.18
DRE1 | MW\21\011\D | MW | 21 | 11 | D | 6 DL | 100 | 11.9995 | 11.9995 | 2017-04-01 | 2017-04-01 18:37 | 65898.8455 |  |  |  | 3936 | 65899 | 46520 |  |  | 0 | 26.31 | 0 | 5.71 | 5908.85
PH4100A | RS\04\008\A | RS | 4 | 8 | A | 1 Prestrip - Thick | 100 | 34.4868 | 34.4868 | 2017-04-01 | 2017-04-03 09:13 | 97695.6742 | 97696 | [7 empty] | 0 | 0 | 9.98 | 14.73 | 5116.6
DRE2 | BW\22\001\D | BW | 22 | 1 | D | 6 DL | 100 | 64.3476 | 64.3476 | 2017-04-01 | 2017-04-04 00:20 | 246564.644 |  |  |  | 9458 | 246565 | 118070 |  |  | 0 | 21.61 | 0 | 6.35 | 5856.24
PH4100XPC#1 | BW\24\010\B | BW | 24 | 10 | B | 1 Prestrip - Thick | 100 | 41.5512 | 41.5512 | 2017-04-01 | 2017-04-01 09:58 | 23557.1091 | 23557 | [7 empty] | 0 | 0 | 1.47 | 12.52 | 5281.67
TS5500Shv | DT\25\007\A | DT | 25 | 7 | A | 1 Prestrip - Thick | 34.1713 | 31.5496 | 31.5496 | 2017-04-01 | 2017-04-06 12:54 | 147994.2599 | 147994 | [7 empty] | 0 | 0 | 9.26 | 10.19 | 5428.19
TS6060#1 | BW\25\003\X1 | BW | 25 | 3 | X1 | 1 Prestrip - Thick | 5.8847 | 3.4646 | 3.4646 | 2017-04-01 | 2017-04-01 22:14 | 23792.8336 | 23793 | [7 empty] | 0 | 0 | 1.07 | 11.61 | 5365.98
TS5500Exc | MW\25\007\B | MW | 25 | 7 | B | 1 Prestrip - Thick | 22.3077 | 2.9389 | 2.9389 | 2017-04-01 | 2017-04-01 14:47 | 13755.1221 | 13755 | [7 empty] | 0 | 0 | 0.85 | 9.85 | 5536.77
PH4100XPC#1 | BW\24\009\B | BW | 24 | 9 | B | 1 Prestrip - Thick | 100 | 72.8018 | 72.8018 | 2017-04-01 09:58 | 2017-04-05 14:13 | 236625.5631 | 236626 | [7 empty] | 0 | 0 | 14.3 | 11.43 | 5382.03
TS5500Exc | MW\24\008\B | MW | 24 | 8 | B | 8 Coal Mining | 16.6 | 0 | 16.6 | 2017-04-01 14:47 | 2017-04-01 22:50 | 10588.1177 | [6 empty] | 10588 | 7768 | 0.49 | 0 | 0 | 10.39 | 5458
DRE1 | MW\21\012\D | MW | 21 | 12 | D | 6 DL | 100 | 100 | 100 | 2017-04-01 18:37 | 2017-04-09 14:48 | 666124.2207 |  |  |  | 24016 | 666124 | 315451 |  |  | 0 | 25.73 | 0 | 5.58 | 5921
TS6060#1 | RS\02\004\D | RS | 2 | 4 | D | 8 Coal Mining | 100 | 0 | 4 | 2017-04-01 22:14 | 2017-04-02 01:48 | 5057.0493 | [6 empty] | 5057 | 3680 | 0.18 | 0 | 0 | 6.23 | 5890
TS5500Exc | MW\21\009\D | MW | 21 | 9 | D | 8 Coal Mining | 50.8 | 0 | 3.8 | 2017-04-01 22:50 | 2017-04-02 01:31 | 3518.9286 | [6 empty] | 3519 | 2654 | 0.17 | 0 | 0 | 6.25 | 5862
TS5500Exc | MW\24\009\B | MW | 24 | 9 | B | 8 Coal Mining | 23.6 | 0 | 23.6 | 2017-04-02 01:31 | 2017-04-02 13:22 | 15598.6751 | [6 empty] | 15599 | 11497 | 0.72 | 0 | 0 | 9.65 | 5543
TS6060#1 | RS\04\005\B | RS | 4 | 5 | B | 8 Coal Mining | 55.9 | 0 | 55.9 | 2017-04-02 01:48 | 2017-04-02 20:09 | 25939.9106 | [6 empty] | 25940 | 18144 | 1.81 | 0 | 0 | 14.52 | 5134
TS5500Exc | MW\21\011\D | MW | 21 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-04-02 13:22 | 2017-04-05 10:03 | 90393.4992 | [6 empty] | 90393 | 68506 | 4.28 | 0 | 0 | 5.71 | 5909
TS6060#1 | RS\02\005\D | RS | 2 | 5 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2017-04-02 20:09 | 2017-04-04 16:17 | 62410.0331 | [6 empty] | 62410 | 45135 | 2.26 | 0 | 0 | 6.12 | 5900
TS Fleet 5 | BW\25\003\X1 | BW | 25 | 3 | X1 | 1 Prestrip - Thick | 64.3042 | 64.3042 | 64.3042 | 2017-04-03 03:07 | 2017-04-12 12:25 | 441597.9977 | 441598 | [7 empty] | 0 | 0 | 19.88 | 11.61 | 5365.98
PH4100A | SC\29\013\D | SC | 29 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-04-03 09:13 | 2017-04-08 20:06 | 232758.1238 | 232758 | [7 empty] | 0 | 0 | 15.71 | 7.51 | 5753.54
DRE2 | MW\22\003\D | MW | 22 | 3 | D | 6 DL | 100 | 100 | 100 | 2017-04-04 00:20 | 2017-04-10 14:18 | 538444.4007 |  |  |  | 32156 | 538444 | 380103 |  |  | 0 | 25.73 | 0 | 5.84 | 5898.58
TS6060#1 | BW\22\006\D | BW | 22 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-04-04 16:17 | 2017-04-08 02:08 | 115728.1917 | [6 empty] | 115728 | 87848 | 5.49 | 0 | 0 | 5.48 | 5936
TS5500Exc | MW\24\009\B | MW | 24 | 9 | B | 8 Coal Mining | 33.3 | 0 | 33.3 | 2017-04-05 10:03 | 2017-04-06 02:48 | 22038.858 | [6 empty] | 22039 | 16244 | 1.02 | 0 | 0 | 9.65 | 5543
PH4100XPC#1 | BW\24\008\B | BW | 24 | 8 | B | 1 Prestrip - Thick | 100 | 1.9106 | 1.9106 | 2017-04-05 14:13 | 2017-04-05 21:55 | 18244.674 | 18245 | [7 empty] | 0 | 0 | 1.1 | 11.57 | 5382.18
PH4100XPC#1 | DT\25\006\A | DT | 25 | 6 | A | 1 Prestrip - Thick | 100 | 38.6485 | 38.6485 | 2017-04-05 21:55 | 2017-04-08 19:40 | 165838.2437 | 165838 | [7 empty] | 0 | 0 | 12.75 | 10.74 | 5388.23
TS5500Exc | MW\25\007\B | MW | 25 | 7 | B | 1 Prestrip - Thick | 39.3026 | 39.3026 | 39.3026 | 2017-04-06 02:48 | 2017-04-14 08:43 | 183951.3502 | 183951 | [7 empty] | 0 | 0 | 11.43 | 9.85 | 5536.77
TS5500Shv | MW\24\008\B | MW | 24 | 8 | B | 8 Coal Mining | 83.4 | 0 | 83.4 | 2017-04-06 12:54 | 2017-04-08 06:35 | 53096.6073 | [6 empty] | 53097 | 38952 | 2.43 | 0 | 0 | 10.39 | 5458
TS6060#1 | RS\04\006\B | RS | 4 | 6 | B | 8 Coal Mining | 34.6 | 0 | 34.6 | 2017-04-08 02:08 | 2017-04-08 15:46 | 19275.7518 | [6 empty] | 19276 | 13296 | 1.33 | 0 | 0 | 16.13 | 5000
TS5500Shv | MW\24\010\B | MW | 24 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-04-08 06:35 | 2017-04-10 08:29 | 63573.3654 | [6 empty] | 63573 | 47083 | 2.94 | 0 | 0 | 8.65 | 5662
TS6060#1 | RS\02\006\D | RS | 2 | 6 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2017-04-08 15:46 | 2017-04-10 12:42 | 63528.014 | [6 empty] | 63528 | 46087 | 2.3 | 0 | 0 | 6.35 | 5880
PH4100XPC#1 | MW\24\008\D | MW | 24 | 8 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-04-08 19:40 | 2017-04-08 19:40 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | DT\26\006\A | DT | 26 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-04-08 19:40 | 2017-04-16 09:49 | 444458.0032 | 444458 | [7 empty] | 0 | 0 | 30.37 | 11.02 | 5368.95
PH4100A | SC\30\013\D | SC | 30 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-04-08 20:06 | 2017-04-15 00:21 | 263668.1189 | 263668 | [7 empty] | 0 | 0 | 15.44 | 7.53 | 5751.26
DRE1 | RS\03\003\D | RS | 3 | 3 | D | 6 DL | 100 | 0 | 100 | 2017-04-09 14:48 | 2017-04-12 03:59 | 216594.3645 |  |  |  | 9691 | 216594 | 184129 |  |  | 0 | 22.17 | 0 | 6.19 | 5876.96
TS5500Shv | MW\24\011\B | MW | 24 | 11 | B | 8 Coal Mining | 54.6 | 0 | 54.6 | 2017-04-10 08:29 | 2017-04-11 11:16 | 34126.3722 | [6 empty] | 34126 | 25458 | 1.59 | 0 | 0 | 8.15 | 5701
TS6060#1 | BW\22\005\D | BW | 22 | 5 | D | 8 Coal Mining | 80.8 | 0 | 80.8 | 2017-04-10 12:42 | 2017-04-13 03:05 | 88230.355 | [6 empty] | 88230 | 66765 | 4.17 | 0 | 0 | 5.64 | 5920
DRE2 | MW\22\004\D | MW | 22 | 4 | D | 6 DL | 100 | 100 | 100 | 2017-04-10 14:18 | 2017-04-17 03:02 | 534245.3129 |  |  |  | 31905 | 534245 | 377139 |  |  | 0 | 25.48 | 0 | 6.32 | 5856.33
TS5500Shv | MW\21\008\D | MW | 21 | 8 | D | 8 Coal Mining | 53.1 | 0 | 53.1 | 2017-04-11 11:16 | 2017-04-13 02:43 | 50266.4286 | [6 empty] | 50266 | 37945 | 2.37 | 0 | 0 | 5.97 | 5887
DRE1 | RS\03\004\D | RS | 3 | 4 | D | 6 DL | 100 | 0 | 100 | 2017-04-12 03:59 | 2017-04-15 02:46 | 250521.5616 |  |  |  | 11209 | 250522 | 212971 |  |  | 0 | 21.96 | 0 | 6.38 | 5860.4
TS Fleet 5 | BW\25\004\X1 | BW | 25 | 4 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-04-12 12:25 | 2017-04-22 05:05 | 456035.5092 | 456036 | [7 empty] | 0 | 0 | 29.5 | 11.05 | 5419.51
TS5500Shv | MW\21\009\D | MW | 21 | 9 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-04-13 02:43 | 2017-04-14 14:23 | 45420.8017 | [6 empty] | 45421 | 34258 | 2.14 | 0 | 0 | 6.25 | 5862
TS6060#1 | RS\02\007\D | RS | 2 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-04-13 03:05 | 2017-04-15 13:03 | 81952.7519 | [6 empty] | 81953 | 59676 | 2.98 | 0 | 0 | 6.5 | 5866
TS5500Exc | MW\22\003\D | MW | 22 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-04-14 08:43 | 2017-04-15 21:11 | 47986.1044 | [6 empty] | 47986 | 36400 | 2.28 | 0 | 0 | 5.84 | 5899
TS5500Shv | MW\22\003\D | MW | 22 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-04-14 14:23 | 2017-04-16 02:50 | 46454.633 | [6 empty] | 46455 | 35238 | 2.2 | 0 | 0 | 5.84 | 5899
PH4100A | SC\29\012\D | SC | 29 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-04-15 00:21 | 2017-04-19 10:42 | 190919.8193 | 190920 | [7 empty] | 0 | 0 | 16.18 | 7.55 | 5749.29
DRE1 | RS\03\005\D | RS | 3 | 5 | D | 6 DL | 100 | 100 | 100 | 2017-04-15 02:46 | 2017-04-18 03:05 | 255986.5488 |  |  |  | 11454 | 255987 | 217617 |  |  | 0 | 22.91 | 0 | 6.29 | 5867.09
TS6060#1 | RS\02\008\D1 | RS | 2 | 8 | D1 | 8 Coal Mining | 100 | 0 | 100 | 2017-04-15 13:03 | 2017-04-17 11:25 | 65565.558 | [6 empty] | 65566 | 47745 | 2.64 | 0 | 0 | 7.21 | 5725
TS5500Exc | RS\03\003\D | RS | 3 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-04-15 21:11 | 2017-04-17 21:08 | 63108.2346 | [6 empty] | 63108 | 46233 | 4.5 | 0 | 0 | 6.19 | 5877
TS5500Shv | MW\21\010\D | MW | 21 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-04-16 02:50 | 2017-04-19 02:52 | 91758.0803 | [6 empty] | 91758 | 69262 | 4.33 | 0 | 0 | 6.19 | 5867
PH4100XPC#1 | MW\24\010\D | MW | 24 | 10 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-04-16 09:49 | 2017-04-16 09:49 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | DT\25\007\A | DT | 25 | 7 | A | 1 Prestrip - Thick | 100 | 40.8029 | 40.8029 | 2017-04-16 09:49 | 2017-04-19 18:50 | 191400.4624 | 191400 | [7 empty] | 0 | 0 | 11.97 | 10.19 | 5428.19
DRE2 | MW\22\005\D | MW | 22 | 5 | D | 6 DL | 100 | 100 | 100 | 2017-04-17 03:02 | 2017-04-23 12:08 | 521886.7917 |  |  |  | 22761 | 521887 | 376559 |  |  | 0 | 24.89 | 0 | 6.7 | 5822.53
TS6060#1 | RS\04\007\A | RS | 4 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2017-04-17 11:25 | 2017-04-18 15:51 | 40199.09 | [6 empty] | 40199 | 27629 | 2.75 | 0 | 0 | 15.72 | 5013
TS5500Exc | MW\22\004\D | MW | 22 | 4 | D | 8 Coal Mining | 18.7 | 0 | 18.7 | 2017-04-17 21:08 | 2017-04-18 10:22 | 17399.6286 | [6 empty] | 17400 | 13145 | 0.82 | 0 | 0 | 6.32 | 5856
DRE1 | RS\03\006\D | RS | 3 | 6 | D | 6 DL | 100 | 100 | 100 | 2017-04-18 03:05 | 2017-04-21 08:51 | 275306.8593 |  |  |  | 12318 | 275307 | 234042 |  |  | 0 | 24.63 | 0 | 6.53 | 5846.76
TS5500Exc | MW\21\012\D | MW | 21 | 12 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2017-04-18 10:22 | 2017-04-20 03:15 | 37786.348 |  |  | 37786 | [5 empty] | 0 | 0 | 0 | 5.58 | 5921
TS6060#1 | RS\04\008\A | RS | 4 | 8 | A | 8 Coal Mining | 100 | 0 | 100 | 2017-04-18 15:51 | 2017-04-19 21:53 | 42471.3626 | [6 empty] | 42471 | 29364 | 3.48 | 0 | 0 | 14.73 | 5117
TS5500Shv | MW\22\004\D | MW | 22 | 4 | D | 8 Coal Mining | 81.3 | 0 | 74.4 | 2017-04-19 02:52 | 2017-04-21 09:19 | 69366.7619 | [6 empty] | 69367 | 52404 | 3.27 | 0 | 0 | 6.32 | 5856
PH4100A | RS\04\007\B | RS | 4 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-04-19 10:42 | 2017-04-20 04:07 | 31545.7726 | 31546 | [7 empty] | 0 | 0 | 3.15 | 16.89 | 4990.33
PH4100XPC#1 | DT\26\007\A | DT | 26 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-04-19 18:50 | 2017-04-30 07:23 | 612530.9775 | 612531 | [7 empty] | 0 | 0 | 45.78 | 10.67 | 5396.47
TS6060#1 | MW\24\011\B | MW | 24 | 11 | B | 8 Coal Mining | 45.4 | 0 | 45.4 | 2017-04-19 21:53 | 2017-04-20 17:58 | 28392.1279 | [6 empty] | 28392 | 21180 | 1.32 | 0 | 0 | 8.15 | 5701
TS5500Exc | RS\03\004\D | RS | 3 | 4 | D | 8 Coal Mining | 100 | 0 | 63.7 | 2017-04-20 03:15 | 2017-04-21 09:19 | 39553.0187 | [6 empty] | 39553 | 28663 | 2.87 | 0 | 0 | 6.38 | 5860
PH4100A | RS\04\008\B | RS | 4 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-04-20 04:07 | 2017-04-20 18:38 | 26276.2894 | 26276 | [7 empty] | 0 | 0 | 3.13 | 17.49 | 4984.4
TS6060#1 | BW\22\002\D | BW | 22 | 2 | D | 8 Coal Mining | 100 | 0 | 20.3 | 2017-04-20 17:58 | 2017-04-21 09:19 | 21701.6888 | [6 empty] | 21702 | 16267 | 1.02 | 0 | 0 | 6.63 | 5832
PH4100A | SC\30\012\D | SC | 30 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-04-20 18:38 | 2017-04-25 23:21 | 225331.5462 | 225332 | [7 empty] | 0 | 0 | 19.19 | 7.58 | 5745.82
DRE1 | RS\03\007\D | RS | 3 | 7 | D | 6 DL | 100 | 100 | 100 | 2017-04-21 08:51 | 2017-04-24 22:40 | 303751.3539 |  |  |  | 15617 | 303751 | 244667 |  |  | 0 | 26.03 | 0 | 6.69 | 5829.7
TS5500Shv | DT\26\001\B | DT | 26 | 1 | B | 1 Prestrip - Thick | 25.5746 | 24.1409 | 24.1409 | 2017-04-21 09:19 | 2017-05-01 | 258501.6302 | 258502 | [7 empty] | 0 | 0 | 12.95 | 11.67 | 5333.24
TS6060#1 | BW\22\001\D | BW | 22 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2017-04-21 09:19 | 2017-04-23 16:40 | 59665.4263 |  |  | 59665 | [5 empty] | 0 | 0 | 0 | 6.35 | 5856.24
TS5500Exc | MW\25\008\A | MW | 25 | 8 | A | 1 Prestrip - Thick | 15.3823 | 15.3823 | 15.3823 | 2017-04-21 09:19 | 2017-04-24 00:28 | 58764.3282 | 58764 | [7 empty] | 0 | 0 | 3.63 | 11.58 | 5213.93
TS Fleet 5 | BW\25\005\X1 | BW | 25 | 5 | X1 | 1 Prestrip - Thick | 96.9575 | 96.9575 | 96.9575 | 2017-04-22 05:05 | 2017-04-29 19:57 | 358419.2218 | 358419 | [7 empty] | 0 | 0 | 22.11 | 10.76 | 5446.71
DRE2 | MW\22\006\D | MW | 22 | 6 | D | 6 DL | 100 | 0 | 90.7325 | 2017-04-23 12:08 | 2017-04-30 16:40 | 588109.7247 |  |  |  | 43961 | 588110 | 404622 |  |  | 0 | 30.66 | 0 | 6.83 | 5812.23
TS6060#1 | BW\25\006\B | BW | 25 | 6 | B | 1 Prestrip - Thick | 21.9053 | 20.3177 | 20.3177 | 2017-04-23 16:40 | 2017-05-01 | 187067.4043 | 187067 | [7 empty] | 0 | 0 | 11.63 | 10.38 | 5493.22
TS5500Exc | MW\25\008\A | MW | 25 | 8 | A | 1 Prestrip - Thick | 30.8857 | 30.8857 | 30.8857 | 2017-04-24 00:28 | 2017-04-29 07:17 | 117991.0832 | 117991 | [7 empty] | 0 | 0 | 7.29 | 11.58 | 5213.93
DRE1 | RS\03\008\D1 | RS | 3 | 8 | D1 | 6 DL | 100 | 100 | 100 | 2017-04-24 22:40 | 2017-04-27 23:42 | 258524.3465 |  |  |  | 9753 | 258524 | 147038 |  |  | 0 | 25.48 | 0 | 7.1 | 5713.76
PH4100A | SC\29\011\D | SC | 29 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-04-25 23:21 | 2017-04-30 00:53 | 174921.9924 | 174922 | [7 empty] | 0 | 0 | 14.76 | 7.45 | 5757.98
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2017-04-27 23:42 | 2017-04-29 23:42
TS5500Exc | MW\25\011\A | MW | 25 | 11 | A | 1 Prestrip - Thick | 4.408 | 3.046 | 3.046 | 2017-04-29 07:17 | 2017-05-01 | 37786.3994 | 37786 | [7 empty] | 0 | 0 | 1.44 | 10.75 | 5477.74
TS Fleet 5 | BW\25\005\X1 | BW | 25 | 5 | X1 | 1 Prestrip - Thick | 3.0425 | 3.0425 | 3.0425 | 2017-04-29 19:57 | 2017-04-30 01:41 | 11247.0998 | 11247 | [7 empty] | 0 | 0 | 0.69 | 10.76 | 5446.71
DRE1 | MW\22\006\D | MW | 22 | 6 | D | 6 DL | 100 | 0 | 9.2675 | 2017-04-29 23:42 | 2017-04-30 16:40 | 60069.8992 |  |  |  | 4490 | 60070 | 41328 |  |  | 0 | 30.66 | 0 | 6.83 | 5812.23
PH4100A | SC\30\011\D | SC | 30 | 11 | D | 1 Prestrip - Thick | 100 | 23.2666 | 23.2666 | 2017-04-30 00:53 | 2017-05-01 | 41602.3401 | 41602 | [7 empty] | 0 | 0 | 3.51 | 7.51 | 5752.87
TS Fleet 5 | BW\25\006\B | BW | 25 | 6 | B | 1 Prestrip - Thick | 68.3934 | 4.7474 | 4.7474 | 2017-04-30 01:41 | 2017-05-01 | 43709.8502 | 43710 | [7 empty] | 0 | 0 | 2.72 | 10.38 | 5493.22
PH4100XPC#1 | MW\24\011\D | MW | 24 | 11 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-04-30 07:23 | 2017-04-30 07:23 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | MW\26\003\A | MW | 26 | 3 | A | 1 Prestrip - Thick | 100 | 6.0716 | 6.0716 | 2017-04-30 07:23 | 2017-05-01 | 40869.8642 | 40870 | [7 empty] | 0 | 0 | 2.92 | 11.09 | 5390.78
DRE1 | MW\22\007\D | MW | 22 | 7 | D | 6 DL | 100 | 0 | 4.2568 | 2017-04-30 16:40 | 2017-05-01 | 25900.4 |  |  |  | 1130 | 25900 | 18688 |  |  | 0 | 29.03 | 0 | 6.33 | 5855.82
DRE2 | MW\22\007\D | MW | 22 | 7 | D | 6 DL | 100 | 0 | 4.0991 | 2017-04-30 16:40 | 2017-05-01 | 24941.1259 |  |  |  | 1088 | 24941 | 17996 |  |  | 0 | 29.03 | 0 | 6.33 | 5855.82
| EOP 40 : 2017\Apr | EOP 40 : 2017 | Apr | [6 empty] | 2017-05-01 | 2017-05-01 |  | 5459049 |  | 97452 | 244943 | 4832870 | 3336941 | 1424700 | 1054527 | 70.14 | 0 | 362.2 | 7.91 | 5712.8
TS Fleet 5 | BW\25\006\B | BW | 25 | 6 | B | 1 Prestrip - Thick | 68.3934 | 63.646 | 63.646 | 2017-05-01 | 2017-05-13 06:45 | 585995.2009 | 585995 | [7 empty] | 0 | 0 | 36.43 | 10.38 | 5493.22
PH4100A | SC\30\011\D | SC | 30 | 11 | D | 1 Prestrip - Thick | 100 | 76.7334 | 76.7334 | 2017-05-01 | 2017-05-04 03:10 | 137204.7476 | 137205 | [7 empty] | 0 | 0 | 11.58 | 7.51 | 5752.87
DRE2 | MW\22\007\D | MW | 22 | 7 | D | 6 DL | 100 | 0 | 91.644 | 2017-05-01 | 2017-05-07 19:35 | 557604.8528 |  |  |  | 24319 | 557605 | 402331 |  |  | 0 | 29.03 | 0 | 6.33 | 5855.82
TS5500Shv | DT\26\001\B | DT | 26 | 1 | B | 1 Prestrip - Thick | 25.5746 | 1.4337 | 1.4337 | 2017-05-01 | 2017-05-01 13:30 | 15352.3305 | 15352 | [7 empty] | 0 | 0 | 0.77 | 11.67 | 5333.24
PH4100XPC#1 | MW\26\003\A | MW | 26 | 3 | A | 1 Prestrip - Thick | 100 | 93.9284 | 93.9284 | 2017-05-01 | 2017-05-11 13:29 | 632257.2896 | 632257 | [7 empty] | 0 | 0 | 45.24 | 11.09 | 5390.78
TS6060#1 | BW\25\006\B | BW | 25 | 6 | B | 1 Prestrip - Thick | 21.9053 | 1.5876 | 1.5876 | 2017-05-01 | 2017-05-01 13:30 | 14616.9863 | 14617 | [7 empty] | 0 | 0 | 0.91 | 10.38 | 5493.22
TS5500Exc | MW\25\011\A | MW | 25 | 11 | A | 1 Prestrip - Thick | 4.408 | 1.3621 | 1.3621 | 2017-05-01 | 2017-05-01 17:57 | 16897.4065 | 16897 | [7 empty] | 0 | 0 | 0.64 | 10.75 | 5477.74
DRE1 | No Production | No Production | [7 empty] | 2017-05-01 | 2017-06-01
TS5500Shv | MW\22\004\D | MW | 22 | 4 | D | 8 Coal Mining | 81.3 | 0 | 6.9 | 2017-05-01 13:30 | 2017-05-01 18:30 | 6470.8078 | [6 empty] | 6471 | 4888 | 0.31 | 0 | 0 | 6.32 | 5856
TS6060#1 | BW\22\002\D | BW | 22 | 2 | D | 8 Coal Mining | 100 | 0 | 79.7 | 2017-05-01 13:30 | 2017-05-04 00:58 | 85297.9187 | [6 empty] | 85298 | 63935 | 4 | 0 | 0 | 6.63 | 5832
TS5500Exc | RS\04\007\B | RS | 4 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-05-01 17:57 | 2017-05-03 12:46 | 57153.5537 | [6 empty] | 57154 | 39072 | 3.91 | 0 | 0 | 16.89 | 4990
TS5500Shv | MW\24\009\B | MW | 24 | 9 | B | 8 Coal Mining | 22.8 | 0 | 22.8 | 2017-05-01 18:30 | 2017-05-02 06:12 | 15100.845 | [6 empty] | 15101 | 11130 | 0.7 | 0 | 0 | 9.65 | 5543
TS5500Shv | DT\26\001\B | DT | 26 | 1 | B | 1 Prestrip - Thick | 74.4254 | 74.4254 | 74.4254 | 2017-05-02 06:12 | 2017-05-31 11:21 | 796950.0774 | 796950 | [7 empty] | 0 | 0 | 39.92 | 11.67 | 5333.24
TS5500Exc | RS\04\008\B | RS | 4 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-05-03 12:46 | 2017-05-04 23:28 | 46318.74 | [6 empty] | 46319 | 31484 | 3.89 | 0 | 0 | 17.49 | 4984
TS6060#1 | BW\22\003\D | BW | 22 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-05-04 00:58 | 2017-05-07 04:15 | 107961.4447 | [6 empty] | 107961 | 80921 | 5.06 | 0 | 0 | 6.76 | 5821
PH4100A | SC\29\010\D | SC | 29 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-05-04 03:10 | 2017-05-08 16:18 | 198735.7324 | 198736 | [7 empty] | 0 | 0 | 16.76 | 7.18 | 5782.94
TS5500Exc | MW\22\005\D | MW | 22 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-05-04 23:28 | 2017-05-07 21:37 | 93645.6369 | [6 empty] | 93646 | 70406 | 4.4 | 0 | 0 | 6.7 | 5823
TS6060#1 | BW\22\004\D | BW | 22 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-05-07 04:15 | 2017-05-10 04:58 | 104281.1891 | [6 empty] | 104281 | 78601 | 4.91 | 0 | 0 | 6.02 | 5885
DRE2 | MW\22\008\D | MW | 22 | 8 | D | 6 DL | 100 | 0 | 100 | 2017-05-07 19:35 | 2017-05-15 01:15 | 591993.6346 |  |  |  | 35354 | 591994 | 417905 |  |  | 0 | 28.28 | 0 | 6.06 | 5879.16
TS5500Exc | MW\22\006\D | MW | 22 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-05-07 21:37 | 2017-05-10 22:54 | 97822.6392 | [6 empty] | 97823 | 73261 | 4.58 | 0 | 0 | 6.83 | 5812
PH4100A | SC\30\010\D | SC | 30 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-05-08 16:18 | 2017-05-13 12:06 | 212149.5888 | 212150 | [7 empty] | 0 | 0 | 18.07 | 7.27 | 5775.25
TS6060#1 | BW\22\005\D | BW | 22 | 5 | D | 8 Coal Mining | 19.2 | 0 | 19.2 | 2017-05-10 04:58 | 2017-05-10 19:34 | 20951.8427 | [6 empty] | 20952 | 15855 | 0.99 | 0 | 0 | 5.64 | 5920
TS6060#1 | BW\22\007\D | BW | 22 | 7 | D | 8 Coal Mining | 19.5 | 0 | 19.5 | 2017-05-10 19:34 | 2017-05-11 09:45 | 20340.7972 | [6 empty] | 20341 | 15480 | 0.97 | 0 | 0 | 5.26 | 5952
TS5500Exc | MW\22\007\D | MW | 22 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-05-10 22:54 | 2017-05-13 23:22 | 96710.9758 | [6 empty] | 96711 | 72659 | 4.54 | 0 | 0 | 6.33 | 5856
TS6060#1 | BW\25\006\B | BW | 25 | 6 | B | 1 Prestrip - Thick | 9.7012 | 9.7012 | 9.7012 | 2017-05-11 09:45 | 2017-05-14 20:17 | 89320.179 | 89320 | [7 empty] | 0 | 0 | 5.55 | 10.38 | 5493.22
PH4100XPC#1 | MW\26\004\A | MW | 26 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-05-11 13:29 | 2017-05-15 20:36 | 247202.8864 | 247203 | [7 empty] | 0 | 0 | 15.06 | 9.46 | 5535.38
TS Fleet 5 | BW\25\007\B | BW | 25 | 7 | B | 1 Prestrip - Thick | 69.61 | 69.61 | 69.61 | 2017-05-13 06:45 | 2017-05-28 16:00 | 734047.8491 | 734048 | [7 empty] | 0 | 0 | 49.24 | 10.65 | 5463.35
PH4100A | SC\29\009\D | SC | 29 | 9 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-05-13 12:06 | 2017-05-20 05:15 | 295543.7709 | 295544 | [7 empty] | 0 | 0 | 24.88 | 6.67 | 5827.82
TS5500Exc | RS\03\004\D | RS | 3 | 4 | D | 8 Coal Mining | 100 | 0 | 36.3 | 2017-05-13 23:22 | 2017-05-14 16:14 | 22515.9614 | [6 empty] | 22516 | 16317 | 1.63 | 0 | 0 | 6.38 | 5860
TS5500Exc | RS\03\005\D | RS | 3 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-05-14 16:14 | 2017-05-16 13:04 | 59850.5116 | [6 empty] | 59851 | 43164 | 4.32 | 0 | 0 | 6.29 | 5867
TS6060#1 | BW\22\001\D | BW | 22 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-05-14 20:17 | 2017-05-17 02:05 | 77153.2746 | [6 empty] | 77153 | 57922 | 4.93 | 0 | 0 | 6.35 | 5856
DRE2 | MW\22\009\D | MW | 22 | 9 | D | 6 DL | 100 | 0 | 100 | 2017-05-15 01:15 | 2017-05-22 09:56 | 602244.3973 |  |  |  | 35966 | 602244 | 425141 |  |  | 0 | 28.78 | 0 | 6.07 | 5878
PH4100XPC#1 | MW\25\005\A | MW | 25 | 5 | A | 1 Prestrip - Thick | 100 | 12.9456 | 12.9456 | 2017-05-15 20:36 | 2017-05-16 16:42 | 44124.2246 | 44124 | [7 empty] | 0 | 0 | 2.67 | 10.05 | 5482.12
TS5500Exc | MW\22\008\D | MW | 22 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-05-16 13:04 | 2017-05-19 11:36 | 94148.8215 | [6 empty] | 94149 | 71071 | 4.44 | 0 | 0 | 6.06 | 5879
PH4100XPC#1 | MW\26\005\A | MW | 26 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-05-16 16:42 | 2017-05-22 14:04 | 318317.2677 | 318317 | [7 empty] | 0 | 0 | 19.12 | 9.48 | 5526.37
TS6060#1 | BW\22\007\D | BW | 22 | 7 | D | 8 Coal Mining | 80.5 | 0 | 80.4 | 2017-05-17 02:05 | 2017-05-19 12:40 | 84013.5331 | [6 empty] | 84014 | 63935 | 4 | 0 | 0 | 5.26 | 5952
TS5500Exc | RS\03\006\D | RS | 3 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-05-19 11:36 | 2017-05-21 09:29 | 61239.6592 | [6 empty] | 61240 | 44342 | 4.43 | 0 | 0 | 6.53 | 5847
TS6060#1 | BW\23\008\B | BW | 23 | 8 | B | 8 Coal Mining | 7.8 | 0 | 7.8 | 2017-05-19 12:40 | 2017-05-19 17:16 | 6590.0745 | [6 empty] | 6590 | 4766 | 0.3 | 0 | 0 | 12.45 | 5312
TS6060#1 | BW\23\009\B | BW | 23 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-05-19 17:16 | 2017-05-22 04:07 | 84423.6943 | [6 empty] | 84424 | 61188 | 3.84 | 0 | 0 | 12.63 | 5286
PH4100A | SC\30\009\D | SC | 30 | 9 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-05-20 05:15 | 2017-05-28 06:54 | 357230.1878 | 357230 | [7 empty] | 0 | 0 | 30.56 | 6.81 | 5815.67
TS5500Exc | RS\03\007\D | RS | 3 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-05-21 09:29 | 2017-05-23 01:46 | 53786.3334 | [6 empty] | 53786 | 39102 | 3.9 | 0 | 0 | 6.69 | 5830
TS6060#1 | BW\23\010\B | BW | 23 | 10 | B | 8 Coal Mining | 100 | 0 | 93.7 | 2017-05-22 04:07 | 2017-05-24 13:07 | 81743.7799 | [6 empty] | 81744 | 59564 | 3.72 | 0 | 0 | 12.11 | 5316
DRE2 | MW\22\010\D | MW | 22 | 10 | D | 6 DL | 100 | 0 | 100 | 2017-05-22 09:56 | 2017-05-29 11:09 | 576777.543 |  |  |  | 34445 | 576778 | 407163 |  |  | 0 | 27.6 | 0 | 5.96 | 5886.97
PH4100XPC#1 | MW\25\006\B | MW | 25 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-05-22 14:04 | 2017-05-30 14:15 | 413624.5108 | 413625 | [7 empty] | 0 | 0 | 26.03 | 8.61 | 5690.84
TS5500Exc | MW\22\009\D | MW | 22 | 9 | D | 8 Coal Mining | 29.2 | 0 | 29.2 | 2017-05-23 01:46 | 2017-05-23 22:13 | 27278.4275 | [6 empty] | 27278 | 20608 | 1.29 | 0 | 0 | 6.07 | 5878
TS5500Exc | MW\22\009\D | MW | 22 | 9 | D | 8 Coal Mining | 70.8 | 0 | 21.3 | 2017-05-23 22:13 | 2017-05-24 13:07 | 19899.5382 | [6 empty] | 19900 | 15034 | 0.94 | 0 | 0 | 6.07 | 5878
TS6060#1 | MW\21\012\D | MW | 21 | 12 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2017-05-24 13:07 | 2017-05-26 05:26 | 44084.0727 |  |  | 44084 | [5 empty] | 0 | 0 | 0 | 5.58 | 5921
TS5500Exc | MW\25\011\A | MW | 25 | 11 | A | 1 Prestrip - Thick | 25.7932 | 13.5725 | 13.5725 | 2017-05-24 13:07 | 2017-06-01 | 168372.6767 | 168373 | [7 empty] | 0 | 0 | 6.4 | 10.75 | 5477.74
TS6060#1 | BW\25\009\A | BW | 25 | 9 | A | 1 Prestrip - Thick | 0.57053 | 0 | 0.57053 | 2017-05-26 05:26 | 2017-05-26 08:19 | 3125.055 | 3125 | [7 empty] | 0 | 0 | 0.19 | 0 | 0
TS6060#1 | BW\25\010\A | BW | 25 | 10 | A | 1 Prestrip - Thick | 26.6596 | 0 | 21.3021 | 2017-05-26 08:19 | 2017-06-01 | 145324.8845 | 145325 | [7 empty] | 0 | 0 | 8.77 | 0 | 0
PH4100A | SC\29\008\D | SC | 29 | 8 | D | 1 Prestrip - Thick | 100 | 34.2286 | 34.2286 | 2017-05-28 06:54 | 2017-06-01 | 165367.213 | 165367 | [7 empty] | 0 | 0 | 14.24 | 6.2 | 5869.37
TS Fleet 5 | BW\25\007\B | BW | 25 | 7 | B | 1 Prestrip - Thick | 30.39 | 15.0808 | 15.0808 | 2017-05-28 16:00 | 2017-06-01 | 159028.95 | 159029 | [7 empty] | 0 | 0 | 10.67 | 10.65 | 5463.35
DRE2 | MW\22\011\D | MW | 22 | 11 | D | 6 DL | 100 | 38.417 | 38.417 | 2017-05-29 11:09 | 2017-06-01 | 207377.9724 |  |  |  | 12385 | 207378 | 146394 |  |  | 0 | 25.82 | 0 | 5.79 | 5901.23
PH4100XPC#1 | MW\26\006\B | MW | 26 | 6 | B | 1 Prestrip - Thick | 100 | 17.3229 | 17.3229 | 2017-05-30 14:15 | 2017-06-01 | 72905.2273 | 72905 | [7 empty] | 0 | 0 | 4.57 | 8.78 | 5684.99
TS5500Shv | DT\26\002\B | DT | 26 | 2 | B | 1 Prestrip - Thick | 7.8561 | 2.3173 | 2.3173 | 2017-05-31 11:21 | 2017-06-01 | 14411.9291 | 14412 | [7 empty] | 0 | 0 | 0.66 | 11.59 | 5313.08
| EOP 41 : 2017\May | EOP 41 : 2017 | May | [6 empty] | 2017-06-01 | 2017-06-01 |  | 5838106 |  | 44084 | 142470 | 2535998 | 1798933 | 1424700 | 1054705 | 75.98 | 0 | 388.94 | 7.83 | 5722.6
TS Fleet 5 | BW\25\007\B | BW | 25 | 7 | B | 1 Prestrip - Thick | 30.39 | 15.3092 | 15.3092 | 2017-06-01 | 2017-06-04 09:12 | 161437.6879 | 161438 | [7 empty] | 0 | 0 | 10.83 | 10.65 | 5463.35
DRE1 | MW\22\011\D | MW | 22 | 11 | D | 6 DL | 100 | 25.2907 | 25.2907 | 2017-06-01 | 2017-06-03 09:28 | 136521.2981 |  |  |  | 8153 | 136521 | 96374 |  |  | 0 | 25.82 | 0 | 5.79 | 5901.23
PH4100A | SC\29\008\D | SC | 29 | 8 | D | 1 Prestrip - Thick | 100 | 65.7714 | 65.7714 | 2017-06-01 | 2017-06-08 03:11 | 317759.1964 | 317759 | [7 empty] | 0 | 0 | 27.36 | 6.2 | 5869.37
DRE2 | MW\22\011\D | MW | 22 | 11 | D | 6 DL | 100 | 36.2923 | 36.2923 | 2017-06-01 | 2017-06-03 09:28 | 195908.5584 |  |  |  | 11700 | 195909 | 138297 |  |  | 0 | 25.82 | 0 | 5.79 | 5901.23
TS5500Shv | DT\26\002\B | DT | 26 | 2 | B | 1 Prestrip - Thick | 7.8561 | 5.5388 | 5.5388 | 2017-06-01 | 2017-06-02 06:12 | 34448.2386 | 34448 | [7 empty] | 0 | 0 | 1.59 | 11.59 | 5313.08
PH4100XPC#1 | MW\26\006\B | MW | 26 | 6 | B | 1 Prestrip - Thick | 100 | 82.6771 | 82.6771 | 2017-06-01 | 2017-06-07 17:01 | 347954.3975 | 347954 | [7 empty] | 0 | 0 | 21.82 | 8.78 | 5684.99
TS6060#1 | BW\25\010\A | BW | 25 | 10 | A | 1 Prestrip - Thick | 26.6596 | 0 | 5.3575 | 2017-06-01 | 2017-06-02 10:07 | 36548.9838 | 36549 | [7 empty] | 0 | 0 | 2.2 | 0 | 0
TS5500Exc | MW\25\011\A | MW | 25 | 11 | A | 1 Prestrip - Thick | 25.7932 | 12.2208 | 12.2208 | 2017-06-01 | 2017-06-07 17:03 | 151603.9928 | 151604 | [7 empty] | 0 | 0 | 5.76 | 10.75 | 5477.74
TS5500Shv | DT\26\002\B | DT | 26 | 2 | B | 1 Prestrip - Thick | 92.1439 | 92.1439 | 92.1439 | 2017-06-02 06:12 | 2017-06-23 04:37 | 573078.454 | 573078 | [7 empty] | 0 | 0 | 26.4 | 11.59 | 5313.08
TS6060#1 | BW\22\007\D | BW | 22 | 7 | D | 8 Coal Mining | 80.5 | 0 | 0.1 | 2017-06-02 10:07 | 2017-06-02 10:11 | 92.0184 | [6 empty] | 92 | 70 | 0 | 0 | 0 | 5.26 | 5952
TS6060#1 | BW\22\008\D | BW | 22 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-06-02 10:11 | 2017-06-05 12:26 | 106500.5113 | [6 empty] | 106501 | 80917 | 5.06 | 0 | 0 | 5.46 | 5935
DRE2 | MW\22\012\D | MW | 22 | 12 | D | 6 DL | 100 | 58.9323 | 58.9323 | 2017-06-03 09:28 | 2017-06-07 06:05 | 315701.2254 |  |  |  | 11402 | 315701 | 149553 |  |  | 0 | 25.59 | 0 | 5.8 | 5900.94
DRE1 | MW\22\012\D | MW | 22 | 12 | D | 6 DL | 100 | 41.0677 | 41.0677 | 2017-06-03 09:28 | 2017-06-07 06:05 | 220000.2973 |  |  |  | 7946 | 220000 | 104218 |  |  | 0 | 25.59 | 0 | 5.8 | 5900.94
TS Fleet 5 | BW\25\008\B | BW | 25 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-06-04 09:12 | 2017-06-25 13:13 | 1009924.809 | 1009925 | [7 empty] | 0 | 0 | 63.49 | 10.77 | 5444.83
TS6060#1 | BW\22\010\D | BW | 22 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-06-05 12:26 | 2017-06-08 14:35 | 106345.1178 | [6 empty] | 106345 | 80092 | 5.01 | 0 | 0 | 6.49 | 5845
DRE2 | DT\23\004\D | DT | 23 | 4 | D | 6 DL | 100 | 100 | 100 | 2017-06-07 06:05 | 2017-06-13 18:54 | 534526.2827 |  |  |  | 23313 | 534526 | 385679 |  |  | 0 | 25.53 | 0 | 5.95 | 5890.6
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2017-06-07 06:05 | 2017-06-09 06:05
PH4100XPC#1 | MW\25\007\B | MW | 25 | 7 | B | 1 Prestrip - Thick | 100 | 38.3896 | 38.3896 | 2017-06-07 17:01 | 2017-06-11 03:32 | 179678.1446 | 179678 | [7 empty] | 0 | 0 | 11.16 | 9.85 | 5536.77
TS5500Exc | MW\22\009\D | MW | 22 | 9 | D | 8 Coal Mining | 70.8 | 0 | 49.5 | 2017-06-07 17:03 | 2017-06-09 03:41 | 46224.8911 | [6 empty] | 46225 | 34922 | 2.18 | 0 | 0 | 6.07 | 5878
PH4100A | SC\30\008\D | SC | 30 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-06-08 03:11 | 2017-06-19 15:26 | 515500.8855 | 515501 | [7 empty] | 0 | 0 | 43.3 | 6.36 | 5856.09
TS6060#1 | BW\22\011\D | BW | 22 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-06-08 14:35 | 2017-06-11 15:11 | 104121.454 | [6 empty] | 104121 | 78108 | 4.88 | 0 | 0 | 7.15 | 5786
TS5500Exc | MW\22\010\D | MW | 22 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-06-09 03:41 | 2017-06-12 00:14 | 91498.2894 | [6 empty] | 91498 | 69177 | 4.32 | 0 | 0 | 5.96 | 5887
DRE1 | RS\04\003\D | RS | 4 | 3 | D | 6 DL | 100 | 0 | 100 | 2017-06-09 06:05 | 2017-06-14 06:05 | 285042.258 |  |  |  | 14655 | 285042 | 229597 |  |  | 0 | 27.69 | 0 | 6.21 | 5874.83
PH4100XPC#1 | MW\26\007\A | MW | 26 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-06-11 03:32 | 2017-06-18 22:48 | 400740.8748 | 400741 | [7 empty] | 0 | 0 | 24.82 | 12.52 | 5187.11
TS6060#1 | BW\23\010\B | BW | 23 | 10 | B | 8 Coal Mining | 100 | 0 | 6.3 | 2017-06-11 15:11 | 2017-06-11 19:00 | 5473.5815 | [6 empty] | 5474 | 3988 | 0.25 | 0 | 0 | 12.11 | 5316
TS6060#1 | BW\23\011\A2 | BW | 23 | 11 | A2 | 8 Coal Mining | 100 | 0 | 100 | 2017-06-11 19:00 | 2017-06-12 12:04 | 24468.3841 | [6 empty] | 24468 | 17144 | 1.08 | 0 | 0 | 19.48 | 4708
TS5500Exc | MW\22\011\D | MW | 22 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-06-12 00:14 | 2017-06-14 19:14 | 89431.6144 | [6 empty] | 89432 | 67831 | 4.24 | 0 | 0 | 5.79 | 5901
TS6060#1 | BW\24\002\X1 | BW | 24 | 2 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2017-06-12 12:04 | 2017-06-13 03:50 | 22618.4614 | [6 empty] | 22618 | 16622 | 1 | 0 | 0 | 11.45 | 5371
TS6060#1 | BW\24\003\X1 | BW | 24 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2017-06-13 03:50 | 2017-06-13 19:30 | 22471.452 | [6 empty] | 22471 | 16469 | 1.01 | 0 | 0 | 11.72 | 5348
DRE2 | DT\23\005\D | DT | 23 | 5 | D | 6 DL | 100 | 100 | 100 | 2017-06-13 18:54 | 2017-06-19 13:22 | 471960.5379 |  |  |  | 28186 | 471961 | 333170 |  |  | 0 | 26.03 | 0 | 5.93 | 5891.54
TS6060#1 | BW\24\004\X1 | BW | 24 | 4 | X1 | 8 Coal Mining | 25.1 | 0 | 25.1 | 2017-06-13 19:30 | 2017-06-13 23:40 | 5982.5923 | [6 empty] | 5983 | 4410 | 0.27 | 0 | 0 | 10.78 | 5436
TS6060#1 | BW\24\002\B | BW | 24 | 2 | B | 1 Prestrip - Thick | 21.3174 | 21.3174 | 21.3174 | 2017-06-13 23:40 | 2017-06-18 14:26 | 121100.5052 | 121101 | [7 empty] | 0 | 0 | 7.69 | 11.38 | 5384.55
DRE1 | RS\04\004\D | RS | 4 | 4 | D | 6 DL | 100 | 100 | 100 | 2017-06-14 06:05 | 2017-06-19 01:58 | 275249.5718 |  |  |  | 12315 | 275250 | 233993 |  |  | 0 | 24.63 | 0 | 6.45 | 5853.71
TS5500Exc | MW\24\009\B | MW | 24 | 9 | B | 8 Coal Mining | 20.2 | 0 | 20.2 | 2017-06-14 19:14 | 2017-06-15 05:14 | 13348.6394 | [6 empty] | 13349 | 9839 | 0.62 | 0 | 0 | 9.65 | 5543
TS5500Exc | MW\25\003\B | MW | 25 | 3 | B | 8 Coal Mining | 85.3 | 0 | 85.3 | 2017-06-15 05:14 | 2017-06-16 22:12 | 54681.0022 | [6 empty] | 54681 | 40769 | 2.55 | 0 | 0 | 8.28 | 5631
TS5500Exc | MW\25\004\A | MW | 25 | 4 | A | 8 Coal Mining | 20.9 | 0 | 20.9 | 2017-06-16 22:12 | 2017-06-17 10:06 | 15883.8576 | [6 empty] | 15884 | 11768 | 0.76 | 0 | 0 | 9.32 | 5543
TS5500Exc | RS\04\003\D | RS | 4 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-06-17 10:06 | 2017-06-19 10:04 | 64038.2217 | [6 empty] | 64038 | 46879 | 4.53 | 0 | 0 | 6.21 | 5875
TS6060#1 | BW\24\002\B | BW | 24 | 2 | B | 1 Prestrip - Thick | 17.8836 | 17.8836 | 17.8836 | 2017-06-18 14:26 | 2017-06-22 11:21 | 101593.6021 | 101594 | [7 empty] | 0 | 0 | 6.45 | 11.38 | 5384.55
PH4100XPC#1 | MW\24\009\D | MW | 24 | 9 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-06-18 22:48 | 2017-06-18 22:48 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | BW\23\011\B | BW | 23 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-06-18 22:48 | 2017-06-19 22:23 | 56431.2777 | 56431 | [7 empty] | 0 | 0 | 3.55 | 14.26 | 5138.45
DRE1 | RS\04\005\D | RS | 4 | 5 | D | 6 DL | 100 | 100 | 100 | 2017-06-19 01:58 | 2017-06-23 19:18 | 269197.4021 |  |  |  | 12045 | 269197 | 228848 |  |  | 0 | 24.09 | 0 | 6.45 | 5852.73
TS5500Exc | RS\04\004\D | RS | 4 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-06-19 10:04 | 2017-06-21 08:16 | 61665.4638 | [6 empty] | 61665 | 44687 | 4.47 | 0 | 0 | 6.45 | 5854
DRE2 | DT\23\006\D | DT | 23 | 6 | D | 6 DL | 100 | 100 | 100 | 2017-06-19 13:22 | 2017-06-23 04:29 | 296931.6234 |  |  |  | 17733 | 296932 | 209612 |  |  | 0 | 25.49 | 0 | 5.84 | 5899.38
PH4100A | SC\29\007\D | SC | 29 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-06-19 15:26 | 2017-06-23 16:27 | 178049.0676 | 178049 | [7 empty] | 0 | 0 | 14.86 | 5.94 | 5891.82
PH4100XPC#1 | BW\24\003\B | BW | 24 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-06-19 22:23 | 2017-06-30 04:52 | 589805.2184 | 589805 | [7 empty] | 0 | 0 | 36.78 | 11.48 | 5381.52
TS5500Exc | MW\25\005\A | MW | 25 | 5 | A | 8 Coal Mining | 48 | 0 | 48 | 2017-06-21 08:16 | 2017-06-21 23:52 | 20812.8369 | [6 empty] | 20813 | 15368 | 0.95 | 0 | 0 | 10.05 | 5482
TS5500Exc | MW\25\007\B | MW | 25 | 7 | B | 8 Coal Mining | 2.6 | 0 | 2.6 | 2017-06-21 23:52 | 2017-06-22 01:06 | 1650.2583 | [6 empty] | 1650 | 1215 | 0.08 | 0 | 0 | 9.85 | 5537
TS5500Exc | MW\26\003\A | MW | 26 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2017-06-22 01:06 | 2017-06-22 23:39 | 30111.6083 | [6 empty] | 30112 | 22083 | 1.45 | 0 | 0 | 11.09 | 5391
TS6060#1 | MW\21\012\D | MW | 21 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-06-22 11:21 | 2017-06-25 05:02 | 94203.6693 | [6 empty] | 94204 | 71513 | 4.43 | 0 | 0 | 5.58 | 5921
TS5500Exc | MW\26\004\A | MW | 26 | 4 | A | 8 Coal Mining | 58.5 | 0 | 58.5 | 2017-06-22 23:39 | 2017-06-24 09:01 | 44530.1698 | [6 empty] | 44530 | 32949 | 2.07 | 0 | 0 | 9.46 | 5535
DRE2 | DT\23\007\D | DT | 23 | 7 | D | 6 DL | 100 | 100 | 100 | 2017-06-23 04:29 | 2017-06-28 23:12 | 472847.0701 |  |  |  | 28239 | 472847 | 333796 |  |  | 0 | 25.02 | 0 | 5.81 | 5901.83
TS5500Shv | MW\22\012\D | MW | 22 | 12 | D | 7 PostStrip | 100 | 0 | 100 | 2017-06-23 04:37 | 2017-06-25 15:00 | 66325.1197 |  |  | 66325 | [5 empty] | 0 | 0 | 0 | 5.8 | 5900.94
PH4100A | SC\30\007\D | SC | 30 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-06-23 16:27 | 2017-06-27 16:05 | 175489.6107 | 175490 | [7 empty] | 0 | 0 | 14.63 | 6.08 | 5879.67
DRE1 | RS\04\006\D | RS | 4 | 6 | D | 6 DL | 100 | 100 | 100 | 2017-06-23 19:18 | 2017-06-28 16:25 | 278179.5899 |  |  |  | 12447 | 278180 | 236484 |  |  | 0 | 24.89 | 0 | 6.61 | 5839.64
TS5500Exc | RS\04\005\D | RS | 4 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-06-24 09:01 | 2017-06-26 05:47 | 59759.782 | [6 empty] | 59760 | 43165 | 4.32 | 0 | 0 | 6.45 | 5853
TS6060#1 | BW\23\011\B | BW | 23 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-06-25 05:02 | 2017-06-27 22:10 | 93419.4467 | [6 empty] | 93419 | 67319 | 4.22 | 0 | 0 | 14.26 | 5138
TS Fleet 5 | BW\24\002\B | BW | 24 | 2 | B | 1 Prestrip - Thick | 7.8525 | 7.8525 | 7.8525 | 2017-06-25 13:13 | 2017-06-26 11:39 | 44608.5529 | 44609 | [7 empty] | 0 | 0 | 2.83 | 11.38 | 5384.55
TS5500Shv | MW\22\012\D | MW | 22 | 12 | D | 8 Coal Mining | 41.9 | 0 | 41.9 | 2017-06-25 15:00 | 2017-06-26 14:52 | 30847.0798 | [6 empty] | 30847 | 23416 | 1.8 | 0 | 0 | 5.8 | 5901
TS5500Exc | MW\22\012\D | MW | 22 | 12 | D | 8 Coal Mining | 30.7 | 0 | 30.7 | 2017-06-26 05:47 | 2017-06-26 22:44 | 22612.0103 | [6 empty] | 22612 | 17165 | 1.32 | 0 | 0 | 5.8 | 5901
TS Fleet 5 | BW\24\002\B | BW | 24 | 2 | B | 1 Prestrip - Thick | 9.4153 | 9.4153 | 9.4153 | 2017-06-26 11:39 | 2017-06-27 14:33 | 53486.523 | 53487 | [7 empty] | 0 | 0 | 3.4 | 11.38 | 5384.55
TS5500Shv | RS\03\008\D1 | RS | 3 | 8 | D1 | 7 PostStrip | 100 | 0 | 100 | 2017-06-26 14:52 | 2017-06-28 00:34 | 38273.8664 |  |  | 38274 | [5 empty] | 0 | 0 | 0 | 7.1 | 5713.76
TS5500Exc | MW\26\005\A | MW | 26 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-06-26 22:44 | 2017-06-27 22:31 | 31758.3729 | [6 empty] | 31758 | 23522 | 1.45 | 0 | 0 | 9.48 | 5526
TS Fleet 5 | BW\25\009\A | BW | 25 | 9 | A | 1 Prestrip - Thick | 99.4295 | 0 | 29.5578 | 2017-06-27 14:33 | 2017-07-01 | 161902.427 | 161902 | [7 empty] | 0 | 0 | 10.04 | 0 | 0
PH4100A | SC\29\006\D | SC | 29 | 6 | D | 1 Prestrip - Thick | 100 | 86.2239 | 86.2239 | 2017-06-27 16:05 | 2017-07-01 | 146659.1742 | 146659 | [7 empty] | 0 | 0 | 12.24 | 5.98 | 5888.61
TS6060#1 | BW\24\004\X1 | BW | 24 | 4 | X1 | 8 Coal Mining | 74.9 | 0 | 74.9 | 2017-06-27 22:10 | 2017-06-28 10:37 | 17866.2803 | [6 empty] | 17866 | 13171 | 0.81 | 0 | 0 | 10.78 | 5436
TS5500Exc | MW\26\006\B | MW | 26 | 6 | B | 8 Coal Mining | 4.6 | 0 | 4.6 | 2017-06-27 22:31 | 2017-06-28 00:18 | 2382.368 | [6 empty] | 2382 | 1768 | 0.11 | 0 | 0 | 8.78 | 5685
TS5500Exc | DT\23\004\D | DT | 23 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.4 | 2017-06-28 00:18 | 2017-06-29 14:29 | 50951.6924 | [6 empty] | 50952 | 38468 | 2.4 | 0 | 0 | 5.95 | 5891
TS5500Shv | MW\25\003\B | MW | 25 | 3 | B | 8 Coal Mining | 14.7 | 0 | 14.7 | 2017-06-28 00:34 | 2017-06-28 07:50 | 9399.3408 | [6 empty] | 9399 | 7008 | 0.44 | 0 | 0 | 8.28 | 5631
TS5500Shv | MW\25\004\A | MW | 25 | 4 | A | 8 Coal Mining | 54.7 | 0 | 52.2 | 2017-06-28 07:50 | 2017-06-29 14:29 | 39597.549 | [6 empty] | 39598 | 29337 | 1.9 | 0 | 0 | 9.32 | 5543
TS6060#1 | BW\24\005\X1 | BW | 24 | 5 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2017-06-28 10:37 | 2017-06-29 02:59 | 23467.9791 | [6 empty] | 23468 | 17363 | 1.09 | 0 | 0 | 10.29 | 5483
DRE1 | RS\04\007\D | RS | 4 | 7 | D | 6 DL | 100 | 44.4373 | 44.4373 | 2017-06-28 16:25 | 2017-07-01 | 132027.9829 |  |  |  | 6788 | 132028 | 106346 |  |  | 0 | 25.44 | 0 | 6.75 | 5827.73
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2017-06-28 23:12 | 2017-06-30 23:12
TS6060#1 | BW\24\006\B | BW | 24 | 6 | B | 8 Coal Mining | 100 | 0 | 19.8 | 2017-06-29 02:59 | 2017-06-29 14:29 | 16484.0044 | [6 empty] | 16484 | 12043 | 0.75 | 0 | 0 | 10.42 | 5487
TS5500Shv | DT\26\004\A | DT | 26 | 4 | A | 1 Prestrip - Thick | 20.0844 | 0 | 10.8101 | 2017-06-29 14:29 | 2017-07-01 | 38182.5191 | 38183 | [7 empty] | 0 | 0 | 2.33 | 0 | 0
TS6060#1 | BW\25\010\A | BW | 25 | 10 | A | 1 Prestrip - Thick | 5.7357 | 0 | 5.2619 | 2017-06-29 14:29 | 2017-07-01 | 35897.4019 | 35897 | [7 empty] | 0 | 0 | 2.17 | 0 | 0
TS5500Exc | MW\26\003\B | MW | 26 | 3 | B | 1 Prestrip - Thick | 100 | 66.372 | 66.372 | 2017-06-29 14:29 | 2017-07-01 | 31409.2494 | 31409 | [7 empty] | 0 | 0 | 1.98 | 8.22 | 5635.37
PH4100XPC#1 | BW\24\005\X2 | BW | 24 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 29.5316 | 2017-06-30 04:52 | 2017-07-01 | 45754.0425 | 45754 | [7 empty] | 0 | 0 | 2.87 | 0 | 0
DRE2 | MW\23\003\D | MW | 23 | 3 | D | 6 DL | 100 | 0.49947 | 0.49947 | 2017-06-30 23:12 | 2017-07-01 | 2703.9021 |  |  |  | 161 | 2704 | 1909 |  |  | 0 | 25.96 | 0 | 6.02 | 5883.43
| EOP 42 : 2017\Jun | EOP 42 : 2017 | Jun | [6 empty] | 2017-07-01 | 2017-07-01 |  | 5509045 |  | 104599 | 195082 | 3886798 | 2787876 | 1424700 | 1060561 | 71.82 | 0 | 360.55 | 7.81 | 5715.29
TS Fleet 5 | BW\25\009\A | BW | 25 | 9 | A | 1 Prestrip - Thick | 99.4295 | 0 | 69.8717 | 2017-07-01 | 2017-07-08 21:50 | 382721.5017 | 382722 | [7 empty] | 0 | 0 | 23.74 | 0 | 0
DRE1 | RS\04\007\D | RS | 4 | 7 | D | 6 DL | 100 | 55.5627 | 55.5627 | 2017-07-01 | 2017-07-02 22:01 | 165082.7301 |  |  |  | 8488 | 165083 | 132972 |  |  | 0 | 25.44 | 0 | 6.75 | 5827.73
PH4100A | SC\29\006\D | SC | 29 | 6 | D | 1 Prestrip - Thick | 100 | 13.7761 | 13.7761 | 2017-07-01 | 2017-07-01 12:35 | 23431.8828 | 23432 | [7 empty] | 0 | 0 | 1.96 | 5.98 | 5888.61
DRE2 | MW\23\003\D | MW | 23 | 3 | D | 6 DL | 100 | 99.5005 | 99.5005 | 2017-07-01 | 2017-07-07 11:58 | 538649.214 |  |  |  | 32168 | 538649 | 380247 |  |  | 0 | 25.96 | 0 | 6.02 | 5883.43
TS5500Shv | DT\26\004\A | DT | 26 | 4 | A | 1 Prestrip - Thick | 20.0844 | 0 | 9.2743 | 2017-07-01 | 2017-07-02 04:21 | 32757.8475 | 32758 | [7 empty] | 0 | 0 | 2 | 0 | 0
PH4100XPC#1 | BW\24\005\X2 | BW | 24 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 70.4684 | 2017-07-01 | 2017-07-02 21:01 | 109178.5895 | 109179 | [7 empty] | 0 | 0 | 6.84 | 0 | 0
TS6060#1 | BW\25\010\A | BW | 25 | 10 | A | 1 Prestrip - Thick | 5.7357 | 0 | 0.47372 | 2017-07-01 | 2017-07-01 02:58 | 3231.7501 | 3232 | [7 empty] | 0 | 0 | 0.19 | 0 | 0
TS5500Exc | MW\26\003\B | MW | 26 | 3 | B | 1 Prestrip - Thick | 100 | 33.628 | 33.628 | 2017-07-01 | 2017-07-01 16:44 | 15913.7697 | 15914 | [7 empty] | 0 | 0 | 1 | 8.22 | 5635.37
TS6060#1 | BW\24\003\B | BW | 24 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-07-01 02:58 | 2017-07-03 10:40 | 81001.237 | [6 empty] | 81001 | 58865 | 3.68 | 0 | 0 | 11.48 | 5382
PH4100A | SC\30\006\D | SC | 30 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-07-01 12:35 | 2017-07-05 06:15 | 166769.0863 | 166769 | [7 empty] | 0 | 0 | 13.9 | 6.04 | 5883.63
TS5500Exc | RS\03\008\D1 | RS | 3 | 8 | D1 | 8 Coal Mining | 100 | 0 | 100 | 2017-07-01 16:44 | 2017-07-02 12:39 | 26952.3447 | [6 empty] | 26952 | 19553 | 2.62 | 0 | 0 | 7.1 | 5714
TS5500Shv | MW\25\004\A | MW | 25 | 4 | A | 8 Coal Mining | 54.7 | 0 | 2.5 | 2017-07-02 04:21 | 2017-07-02 05:46 | 1871.5404 | [6 empty] | 1872 | 1387 | 0.09 | 0 | 0 | 9.32 | 5543
TS5500Shv | DT\26\004\A | DT | 26 | 4 | A | 1 Prestrip - Thick | 79.9156 | 0 | 79.9156 | 2017-07-02 05:46 | 2017-07-12 10:05 | 282270.275 | 282270 | [7 empty] | 0 | 0 | 17.23 | 0 | 0
TS5500Exc | RS\04\006\D | RS | 4 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-07-02 12:39 | 2017-07-04 09:59 | 61358.8351 | [6 empty] | 61359 | 44498 | 4.45 | 0 | 0 | 6.61 | 5840
PH4100XPC#1 | BW\24\004\X2 | BW | 24 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2017-07-02 21:01 | 2017-07-05 15:02 | 160137.447 | 160137 | [7 empty] | 0 | 0 | 9.94 | 0 | 0
DRE1 | RS\04\008\D1 | RS | 4 | 8 | D1 | 6 DL | 100 | 100 | 100 | 2017-07-02 22:01 | 2017-07-05 17:23 | 241598.8303 |  |  |  | 9111 | 241599 | 137399 |  |  | 0 | 25.51 | 0 | 6.96 | 5726.99
TS6060#1 | BW\24\006\B | BW | 24 | 6 | B | 8 Coal Mining | 100 | 0 | 80.2 | 2017-07-03 10:40 | 2017-07-05 08:31 | 66684.0074 | [6 empty] | 66684 | 48717 | 3.05 | 0 | 0 | 10.42 | 5487
TS5500Exc | RS\04\007\D | RS | 4 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-07-04 09:59 | 2017-07-06 07:46 | 61983.4557 | [6 empty] | 61983 | 45127 | 4.53 | 0 | 0 | 6.75 | 5828
PH4100A | SC\29\005\D | SC | 29 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-07-05 06:15 | 2017-07-08 06:18 | 134015.5917 | 134016 | [7 empty] | 0 | 0 | 11.14 | 6.08 | 5879.44
TS6060#1 | BW\24\007\B | BW | 24 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-07-05 08:31 | 2017-07-07 17:14 | 82492.4369 | [6 empty] | 82492 | 60068 | 3.77 | 0 | 0 | 11 | 5437
PH4100XPC#1 | BW\24\002\B | BW | 24 | 2 | B | 1 Prestrip - Thick | 100 | 43.5312 | 43.5312 | 2017-07-05 15:02 | 2017-07-09 21:01 | 247292.6401 | 247293 | [7 empty] | 0 | 0 | 15.71 | 11.38 | 5384.55
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 7d 00:00 |  | 7d 00:00 | 2017-07-05 17:23 | 2017-07-12 17:23
TS5500Exc | DT\23\004\D | DT | 23 | 4 | D | 8 Coal Mining | 50.8 | 0 | 0.4 | 2017-07-06 07:46 | 2017-07-06 08:04 | 392.3543 | [6 empty] | 392 | 296 | 0.02 | 0 | 0 | 5.95 | 5891
TS5500Exc | DT\23\005\D | DT | 23 | 5 | D | 8 Coal Mining | 12.4 | 0 | 12.4 | 2017-07-06 08:04 | 2017-07-06 15:55 | 10639.3752 | [6 empty] | 10639 | 8039 | 0.59 | 0 | 0 | 5.93 | 5892
TS5500Exc | DT\23\006\D | DT | 23 | 6 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-07-06 15:55 | 2017-07-07 12:21 | 27658.0166 | [6 empty] | 27658 | 20897 | 2.36 | 0 | 0 | 5.84 | 5899
DRE2 | MW\23\004\D | MW | 23 | 4 | D | 6 DL | 100 | 0 | 100 | 2017-07-07 11:58 | 2017-07-14 13:24 | 585110.6168 |  |  |  | 34943 | 585111 | 413046 |  |  | 0 | 27.89 | 0 | 6.4 | 5849.48
TS5500Exc | MW\23\003\D | MW | 23 | 3 | D | 8 Coal Mining | 52.8 | 0 | 52.8 | 2017-07-07 12:21 | 2017-07-09 01:32 | 50323.5121 | [6 empty] | 50324 | 38143 | 2.38 | 0 | 0 | 6.02 | 5883
TS6060#1 | BW\24\008\B | BW | 24 | 8 | B | 8 Coal Mining | 97.4 | 0 | 97.4 | 2017-07-07 17:14 | 2017-07-10 00:36 | 80532.8138 | [6 empty] | 80533 | 58541 | 3.68 | 0 | 0 | 11.57 | 5382
PH4100A | SC\30\005\D | SC | 30 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-07-08 06:18 | 2017-07-11 15:23 | 150821.6778 | 150822 | [7 empty] | 0 | 0 | 12.52 | 6.11 | 5877.84
TS Fleet 5 | BW\24\004\B | BW | 24 | 4 | B | 1 Prestrip - Thick | 59.7398 | 59.7398 | 59.7398 | 2017-07-08 21:50 | 2017-07-14 11:58 | 270418.7464 | 270419 | [7 empty] | 0 | 0 | 16.96 | 10.94 | 5442.77
TS5500Exc | DT\23\007\D | DT | 23 | 7 | D | 8 Coal Mining | 31.3 | 0 | 31.3 | 2017-07-09 01:32 | 2017-07-09 21:30 | 27026.5473 | [6 empty] | 27027 | 20469 | 1.43 | 0 | 0 | 5.81 | 5902
PH4100XPC#1 | BW\24\005\B | BW | 24 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-07-09 21:01 | 2017-07-18 01:13 | 475826.8494 | 475827 | [7 empty] | 0 | 0 | 29.79 | 10.64 | 5475.33
TS5500Exc | DT\23\007\D | DT | 23 | 7 | D | 8 Coal Mining | 19.5 | 0 | 19.5 | 2017-07-09 21:30 | 2017-07-10 09:55 | 16817.9315 | [6 empty] | 16818 | 12737 | 0.89 | 0 | 0 | 5.81 | 5902
TS6060#1 | BW\24\002\B | BW | 24 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-07-10 00:36 | 2017-07-12 07:11 | 79386.054 | [6 empty] | 79386 | 57707 | 3.77 | 0 | 0 | 11.38 | 5385
TS5500Exc | DT\24\001\B | DT | 24 | 1 | B | 8 Coal Mining | 20.6 | 0 | 20.6 | 2017-07-10 09:55 | 2017-07-10 22:09 | 16558.3645 | [6 empty] | 16558 | 12068 | 0.66 | 0 | 0 | 11.34 | 5359
TS5500Exc | DT\24\002\A2 | DT | 24 | 2 | A2 | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-07-10 22:09 | 2017-07-11 08:31 | 14020.9774 | [6 empty] | 14021 | 9884 | 0.56 | 0 | 0 | 17.62 | 4939
TS5500Exc | DT\24\004\B | DT | 24 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-07-11 08:31 | 2017-07-12 00:39 | 21844.656 | [6 empty] | 21845 | 15902 | 1 | 0 | 0 | 10.56 | 5337
PH4100A | SC\29\004\D | SC | 29 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-07-11 15:23 | 2017-07-13 17:45 | 93680.2591 | 93680 | [7 empty] | 0 | 0 | 7.71 | 6.22 | 5867.9
TS5500Exc | DT\24\005\B | DT | 24 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-07-12 00:39 | 2017-07-12 09:43 | 12270.2994 | [6 empty] | 12270 | 8934 | 0.52 | 0 | 0 | 11.48 | 5316
TS6060#1 | BW\25\003\X1 | BW | 25 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2017-07-12 07:11 | 2017-07-13 03:00 | 28820.1976 | [6 empty] | 28820 | 21142 | 0.93 | 0 | 0 | 11.61 | 5366
TS5500Exc | DT\24\006\A | DT | 24 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-07-12 09:43 | 2017-07-13 07:23 | 29340.844 | [6 empty] | 29341 | 21485 | 1.91 | 0 | 0 | 10.94 | 5368
TS5500Shv | MW\25\004\A | MW | 25 | 4 | A | 8 Coal Mining | 24.4 | 0 | 24.4 | 2017-07-12 10:05 | 2017-07-13 00:13 | 18511.3057 | [6 empty] | 18511 | 13715 | 0.89 | 0 | 0 | 9.32 | 5543
DRE1 | SC\29\013\D | SC | 29 | 13 | D | 6 DL | 100 | 0 | 100 | 2017-07-12 17:23 | 2017-07-25 07:13 | 1082421.571 |  |  |  | 60280 | 1082422 | 470570 |  |  | 0 | 40 | 0 | 7.51 | 5753.54
TS5500Shv | MW\25\005\A | MW | 25 | 5 | A | 8 Coal Mining | 52 | 0 | 52 | 2017-07-13 00:13 | 2017-07-13 17:27 | 22584.7621 | [6 empty] | 22585 | 16676 | 1.03 | 0 | 0 | 10.05 | 5482
TS6060#1 | BW\25\004\X1 | BW | 25 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2017-07-13 03:00 | 2017-07-13 17:16 | 20747.4255 | [6 empty] | 20747 | 15284 | 0.93 | 0 | 0 | 11.05 | 5420
TS5500Exc | MW\25\004\B | MW | 25 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-07-13 07:23 | 2017-07-15 17:39 | 55365.8029 | 55366 | [7 empty] | 0 | 0 | 3.55 | 9.18 | 5576.85
TS6060#1 | MW\22\012\D | MW | 22 | 12 | D | 8 Coal Mining | 27.4 | 0 | 27.4 | 2017-07-13 17:16 | 2017-07-14 07:08 | 20177.6367 | [6 empty] | 20178 | 15317 | 1.18 | 0 | 0 | 5.8 | 5901
TS5500Shv | MW\25\006\B | MW | 25 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-07-13 17:27 | 2017-07-15 17:34 | 63050.5001 | [6 empty] | 63051 | 46829 | 2.92 | 0 | 0 | 8.61 | 5691
PH4100A | SC\30\004\D | SC | 30 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-07-13 17:45 | 2017-07-17 14:53 | 173207.9963 | 173208 | [7 empty] | 0 | 0 | 11.38 | 6.22 | 5867.64
TS6060#1 | BW\25\005\X1 | BW | 25 | 5 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2017-07-14 07:08 | 2017-07-14 21:03 | 20223.6302 | [6 empty] | 20224 | 14927 | 0.91 | 0 | 0 | 10.76 | 5447
TS Fleet 5 | BW\25\003\B | BW | 25 | 3 | B | 1 Prestrip - Thick | 61.8183 | 61.8183 | 61.8183 | 2017-07-14 11:58 | 2017-07-24 23:12 | 506470.8019 | 506471 | [7 empty] | 0 | 0 | 22.64 | 11.29 | 5400.86
DRE2 | MW\23\005\D | MW | 23 | 5 | D | 6 DL | 100 | 100 | 100 | 2017-07-14 13:24 | 2017-07-21 08:27 | 563114.2088 |  |  |  | 33629 | 563114 | 397518 |  |  | 0 | 26.91 | 0 | 6.82 | 5812.2
TS6060#1 | BW\24\004\B | BW | 24 | 4 | B | 1 Prestrip - Thick | 29.2814 | 25.4348 | 25.4348 | 2017-07-14 21:03 | 2017-07-19 04:53 | 115133.4151 | 115133 | [7 empty] | 0 | 0 | 7.22 | 10.94 | 5442.77
TS5500Shv | MW\23\003\D | MW | 23 | 3 | D | 8 Coal Mining | 47.2 | 0 | 47.2 | 2017-07-15 17:34 | 2017-07-17 03:57 | 45067.5169 | [6 empty] | 45068 | 34159 | 2.14 | 0 | 0 | 6.02 | 5883
TS5500Exc | MW\23\004\D | MW | 23 | 4 | D | 8 Coal Mining | 39.2 | 0 | 39.2 | 2017-07-15 17:39 | 2017-07-16 20:55 | 36912.6187 | [6 empty] | 36913 | 27887 | 1.74 | 0 | 0 | 6.4 | 5849
TS5500Exc | MW\25\005\B | MW | 25 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-07-16 20:55 | 2017-07-19 05:11 | 53481.0792 | 53481 | [7 empty] | 0 | 0 | 3.32 | 9.1 | 5632.54
TS5500Shv | MW\25\007\B | MW | 25 | 7 | B | 8 Coal Mining | 97.4 | 0 | 97.4 | 2017-07-17 03:57 | 2017-07-19 02:58 | 61602.8508 | [6 empty] | 61603 | 45354 | 2.82 | 0 | 0 | 9.85 | 5537
PH4100A | SC\29\003\D | SC | 29 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-07-17 14:53 | 2017-07-19 05:01 | 70953.6837 | 70954 | [7 empty] | 0 | 0 | 10.29 | 6.3 | 5861.22
PH4100XPC#1 | BW\24\004\B | BW | 24 | 4 | B | 1 Prestrip - Thick | 100 | 14.8253 | 14.8253 | 2017-07-18 01:13 | 2017-07-19 04:53 | 67108.4438 | 67108 | [7 empty] | 0 | 0 | 4.21 | 10.94 | 5442.77
TS5500Shv | RS\04\008\D1 | RS | 4 | 8 | D1 | 7 PostStrip | 100 | 0 | 100 | 2017-07-19 02:58 | 2017-07-20 09:58 | 35709.3844 |  |  | 35709 | [5 empty] | 0 | 0 | 0 | 6.96 | 5726.99
PH4100XPC#1 | MW\25\008\A | MW | 25 | 8 | A | 1 Prestrip - Thick | 100 | 53.732 | 53.732 | 2017-07-19 04:53 | 2017-07-23 03:42 | 205269.9084 | 205270 | [7 empty] | 0 | 0 | 12.69 | 11.58 | 5213.93
TS6060#1 | BW\24\004\B | BW | 24 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-07-19 04:53 | 2017-07-21 13:09 | 81834.9845 | [6 empty] | 81835 | 59634 | 3.73 | 0 | 0 | 10.94 | 5443
PH4100A | SC\31\013\D | SC | 31 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-07-19 05:01 | 2017-07-23 09:00 | 183892.6383 | 183893 | [7 empty] | 0 | 0 | 15.78 | 7.6 | 5744.98
TS5500Exc | MW\25\004\B | MW | 25 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-07-19 05:11 | 2017-07-21 03:13 | 62295.256 | [6 empty] | 62295 | 46136 | 2.94 | 0 | 0 | 9.18 | 5577
TS5500Shv | MW\26\004\A | MW | 26 | 4 | A | 8 Coal Mining | 41.5 | 0 | 41.5 | 2017-07-20 09:58 | 2017-07-21 10:07 | 31640.1688 | [6 empty] | 31640 | 23412 | 1.47 | 0 | 0 | 9.46 | 5535
TS5500Exc | RS\04\008\D1 | RS | 4 | 8 | D1 | 8 Coal Mining | 100 | 0 | 100 | 2017-07-21 03:13 | 2017-07-21 19:39 | 22253.9975 | [6 empty] | 22254 | 16142 | 2.29 | 0 | 0 | 6.96 | 5727
DRE2 | MW\23\006\D | MW | 23 | 6 | D | 6 DL | 100 | 0 | 100 | 2017-07-21 08:27 | 2017-07-28 16:34 | 608194.8493 |  |  |  | 36322 | 608195 | 429342 |  |  | 0 | 29.09 | 0 | 7.09 | 5789.44
TS5500Shv | MW\23\004\D | MW | 23 | 4 | D | 8 Coal Mining | 60.8 | 0 | 54.7 | 2017-07-21 10:07 | 2017-07-23 01:24 | 51483.8956 | [6 empty] | 51484 | 38896 | 2.43 | 0 | 0 | 6.4 | 5849
TS6060#1 | BW\24\005\B | BW | 24 | 5 | B | 8 Coal Mining | 100 | 0 | 33.9 | 2017-07-21 13:09 | 2017-07-22 08:27 | 28068.4665 | [6 empty] | 28068 | 20485 | 1.28 | 0 | 0 | 10.64 | 5475
TS5500Exc | MW\23\005\D | MW | 23 | 5 | D | 8 Coal Mining | 100 | 0 | 43.2 | 2017-07-21 19:39 | 2017-07-23 01:24 | 40269.1836 | [6 empty] | 40269 | 30227 | 1.89 | 0 | 0 | 6.82 | 5812
TS6060#1 | BW\25\003\B | BW | 25 | 3 | B | 1 Prestrip - Thick | 8.4187 | 8.4187 | 8.4187 | 2017-07-22 08:27 | 2017-07-24 22:39 | 68973.2017 | 68973 | [7 empty] | 0 | 0 | 3.08 | 11.29 | 5400.86
TS5500Shv | DT\26\004\B | DT | 26 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-07-23 01:24 | 2017-07-25 01:01 | 54847.4684 | 54847 | [7 empty] | 0 | 0 | 3.34 | 9.91 | 5386.99
TS5500Exc | MW\26\004\B | MW | 26 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-07-23 01:24 | 2017-07-25 08:29 | 52358.0045 | 52358 | [7 empty] | 0 | 0 | 3.28 | 9.24 | 5568.59
PH4100XPC#1 | MW\26\008\A | MW | 26 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-07-23 03:42 | 2017-07-30 16:50 | 393512.8772 | 393513 | [7 empty] | 0 | 0 | 24.26 | 11.58 | 5209.72
PH4100A | SC\32\013\D | SC | 32 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-07-23 09:00 | 2017-07-26 15:57 | 145516.8744 | 145517 | [7 empty] | 0 | 0 | 12.66 | 7.64 | 5741.13
TS6060#1 | BW\25\004\X2 | BW | 25 | 4 | X2 | 1 Prestrip - Thick | 37.4985 | 0 | 37.4985 | 2017-07-24 22:39 | 2017-07-27 08:25 | 64057.3379 | 64057 | [7 empty] | 0 | 0 | 3.9 | 0 | 0
TS Fleet 5 | BW\25\003\B | BW | 25 | 3 | B | 1 Prestrip - Thick | 29.7631 | 29.7631 | 29.7631 | 2017-07-24 23:12 | 2017-07-30 00:09 | 243846.0859 | 243846 | [7 empty] | 0 | 0 | 10.9 | 11.29 | 5400.86
TS5500Shv | DT\26\005\B | DT | 26 | 5 | B | 1 Prestrip - Thick | 25.14 | 25.14 | 25.14 | 2017-07-25 01:01 | 2017-07-31 08:13 | 174777.034 | 174777 | [7 empty] | 0 | 0 | 7.68 | 12.6 | 5196.02
DRE1 | SC\29\012\D | SC | 29 | 12 | D | 6 DL | 100 | 0 | 91.1749 | 2017-07-25 07:13 | 2017-08-01 | 576591.2688 |  |  |  | 43847 | 576591 | 394625 |  |  | 0 | 40 | 0 | 7.55 | 5749.29
TS5500Exc | SC\29\013\D | SC | 29 | 13 | D | 7 PostStrip | 100 | 0 | 100 | 2017-07-25 08:29 | 2017-07-28 12:12 | 71952.0742 |  |  | 71952 | [5 empty] | 0 | 0 | 0 | 7.51 | 5753.54
PH4100A | SC\31\014\D | SC | 31 | 14 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-07-26 15:57 | 2017-07-30 11:15 | 165399.2967 | 165399 | [7 empty] | 0 | 0 | 21.25 | 7.46 | 5756.67
TS6060#1 | BW\25\005\X2 | BW | 25 | 5 | X2 | 1 Prestrip - Thick | 37.4985 | 0 | 37.4985 | 2017-07-27 08:25 | 2017-07-29 17:12 | 62951.3639 | 62951 | [7 empty] | 0 | 0 | 3.87 | 0 | 0
TS5500Exc | MW\27\003\B | MW | 27 | 3 | B | 1 Prestrip - Thick | 26.6427 | 10.4507 | 10.4507 | 2017-07-28 12:12 | 2017-08-01 | 79671.0911 | 79671 | [7 empty] | 0 | 0 | 5 | 8.34 | 5632.08
DRE2 | MW\23\007\D | MW | 23 | 7 | D | 6 DL | 100 | 0 | 44.9929 | 2017-07-28 16:34 | 2017-08-01 | 274297.9111 |  |  |  | 11963 | 274298 | 197915 |  |  | 0 | 29.47 | 0 | 6.64 | 5828.69
TS6060#1 | BW\25\009\B | BW | 25 | 9 | B | 1 Prestrip - Thick | 37.8223 | 18.0766 | 18.0766 | 2017-07-29 17:12 | 2017-08-01 | 60754.6431 | 60755 | [7 empty] | 0 | 0 | 3.9 | 11.77 | 5355.27
TS Fleet 5 | BW\25\004\X2 | BW | 25 | 4 | X2 | 1 Prestrip - Thick | 62.5015 | 0 | 56.459 | 2017-07-30 00:09 | 2017-08-01 | 96446.8641 | 96447 | [7 empty] | 0 | 0 | 5.87 | 0 | 0
PH4100A | SC\32\014\D | SC | 32 | 14 | D | 1 Prestrip - Thick | 100 | 41.5022 | 41.5022 | 2017-07-30 11:15 | 2017-08-01 | 66693.9586 | 66694 | [7 empty] | 0 | 0 | 7.47 | 7.49 | 5754.14
PH4100XPC#1 | MW\25\009\A | MW | 25 | 9 | A | 1 Prestrip - Thick | 100 | 11.9802 | 11.9802 | 2017-07-30 16:50 | 2017-08-01 | 69481.2079 | 69481 | [7 empty] | 0 | 0 | 4.21 | 10.33 | 5409.58
TS5500Shv | DT\26\005\B | DT | 26 | 5 | B | 1 Prestrip - Thick | 74.86 | 2.6215 | 2.6215 | 2017-07-31 08:13 | 2017-08-01 | 18225.2856 | 18225 | [7 empty] | 0 | 0 | 0.8 | 12.6 | 5196.02
| EOP 43 : 2017\Jul | EOP 43 : 2017 | Jul | [6 empty] | 2017-08-01 | 2017-08-01 |  | 5796864 |  | 107661 | 270752 | 4635061 | 2953633 | 1424700 | 1049538 | 73.47 | 0 | 383.18 | 8.46 | 5652.92
TS Fleet 5 | BW\25\004\X2 | BW | 25 | 4 | X2 | 1 Prestrip - Thick | 62.5015 | 0 | 6.0425 | 2017-08-01 | 2017-08-01 05:03 | 10322.199 | 10322 | [7 empty] | 0 | 0 | 0.63 | 0 | 0
DRE1 | SC\29\012\D | SC | 29 | 12 | D | 6 DL | 100 | 0 | 8.8251 | 2017-08-01 | 2017-08-01 15:33 | 55809.7266 |  |  |  | 4244 | 55810 | 38197 |  |  | 0 | 40 | 0 | 7.55 | 5749.29
PH4100A | SC\32\014\D | SC | 32 | 14 | D | 1 Prestrip - Thick | 100 | 58.4978 | 58.4978 | 2017-08-01 | 2017-08-03 03:06 | 94005.9691 | 94006 | [7 empty] | 0 | 0 | 10.52 | 7.49 | 5754.14
DRE2 | MW\23\007\D | MW | 23 | 7 | D | 6 DL | 100 | 0 | 55.0071 | 2017-08-01 | 2017-08-05 01:06 | 335348.5641 |  |  |  | 14626 | 335349 | 241965 |  |  | 0 | 29.47 | 0 | 6.64 | 5828.69
PH4100XPC#1 | MW\25\009\A | MW | 25 | 9 | A | 1 Prestrip - Thick | 100 | 88.0198 | 88.0198 | 2017-08-01 | 2017-08-10 09:52 | 510487.8752 | 510488 | [7 empty] | 0 | 0 | 30.95 | 10.33 | 5409.58
TS5500Shv | DT\26\005\B | DT | 26 | 5 | B | 1 Prestrip - Thick | 74.86 | 72.2385 | 72.2385 | 2017-08-01 | 2017-08-18 20:32 | 502213.6463 | 502214 | [7 empty] | 0 | 0 | 22.06 | 12.6 | 5196.02
TS6060#1 | BW\25\009\B | BW | 25 | 9 | B | 1 Prestrip - Thick | 37.8223 | 19.7457 | 19.7457 | 2017-08-01 | 2017-08-03 11:01 | 66364.4637 | 66364 | [7 empty] | 0 | 0 | 4.26 | 11.77 | 5355.27
TS5500Exc | MW\27\003\B | MW | 27 | 3 | B | 1 Prestrip - Thick | 26.6427 | 16.192 | 16.192 | 2017-08-01 | 2017-08-06 08:02 | 123440.2301 | 123440 | [7 empty] | 0 | 0 | 7.75 | 8.34 | 5632.08
TS Fleet 5 | BW\25\004\B | BW | 25 | 4 | B | 1 Prestrip - Thick | 70.2796 | 70.2796 | 70.2796 | 2017-08-01 05:03 | 2017-08-07 19:27 | 323775.3031 | 323775 | [7 empty] | 0 | 0 | 20.1 | 11.07 | 5438.29
DRE1 | SC\29\011\D | SC | 29 | 11 | D | 6 DL | 100 | 0 | 100 | 2017-08-01 15:33 | 2017-08-09 00:58 | 636221.3597 |  |  |  | 48382 | 636221 | 435437 |  |  | 0 | 40 | 0 | 7.45 | 5757.98
PH4100A | SC\31\010\D | SC | 31 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-08-03 03:06 | 2017-08-08 21:38 | 263821.4107 | 263821 | [7 empty] | 0 | 0 | 23.01 | 7.36 | 5767.44
TS6060#1 | BW\24\005\B | BW | 24 | 5 | B | 8 Coal Mining | 100 | 0 | 66.1 | 2017-08-03 11:01 | 2017-08-05 00:05 | 54646.6152 | [6 empty] | 54647 | 39881 | 2.5 | 0 | 0 | 10.64 | 5475
TS6060#1 | BW\24\008\B | BW | 24 | 8 | B | 8 Coal Mining | 2.6 | 0 | 2.6 | 2017-08-05 00:05 | 2017-08-05 01:34 | 2188.1589 | [6 empty] | 2188 | 1591 | 0.1 | 0 | 0 | 11.57 | 5382
DRE2 | MW\23\008\D | MW | 23 | 8 | D | 6 DL | 100 | 0 | 100 | 2017-08-05 01:06 | 2017-08-12 12:32 | 619653.2463 |  |  |  | 37006 | 619653 | 437430 |  |  | 0 | 29.54 | 0 | 6.2 | 5867.4
TS6060#1 | BW\24\009\B | BW | 24 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-08-05 01:34 | 2017-08-07 09:56 | 83114.4914 | [6 empty] | 83114 | 60598 | 3.85 | 0 | 0 | 11.43 | 5382
TS5500Exc | MW\25\008\A | MW | 25 | 8 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-08-06 08:02 | 2017-08-06 23:44 | 21529.5222 | [6 empty] | 21530 | 15764 | 0.96 | 0 | 0 | 11.58 | 5214
TS5500Exc | MW\23\005\D | MW | 23 | 5 | D | 8 Coal Mining | 100 | 0 | 56.8 | 2017-08-06 23:44 | 2017-08-08 14:21 | 53015.8582 | [6 empty] | 53016 | 39795 | 2.49 | 0 | 0 | 6.82 | 5812
TS6060#1 | BW\24\010\B | BW | 24 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-08-07 09:56 | 2017-08-09 20:31 | 86391.0053 | [6 empty] | 86391 | 62770 | 3.94 | 0 | 0 | 12.52 | 5282
TS Fleet 5 | BW\25\005\X2 | BW | 25 | 5 | X2 | 1 Prestrip - Thick | 62.5015 | 0 | 62.5015 | 2017-08-07 19:27 | 2017-08-09 22:47 | 104925.6551 | 104926 | [7 empty] | 0 | 0 | 6.45 | 0 | 0
TS5500Exc | MW\23\006\D | MW | 23 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-08-08 14:21 | 2017-08-11 13:01 | 96982.6308 | [6 empty] | 96983 | 72515 | 4.53 | 0 | 0 | 7.09 | 5789
PH4100A | SC\32\010\D | SC | 32 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-08-08 21:38 | 2017-08-15 00:45 | 283824.4111 | 283824 | [7 empty] | 0 | 0 | 24.8 | 7.46 | 5758.6
DRE1 | SC\29\010\D | SC | 29 | 10 | D | 6 DL | 100 | 0 | 100 | 2017-08-09 00:58 | 2017-08-16 10:00 | 634899.3559 |  |  |  | 48281 | 634899 | 434532 |  |  | 0 | 40 | 0 | 7.18 | 5782.94
TS6060#1 | BW\24\011\B | BW | 24 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-08-09 20:31 | 2017-08-12 11:35 | 93007.5122 | [6 empty] | 93008 | 66575 | 4.17 | 0 | 0 | 15.42 | 5045
TS Fleet 5 | BW\25\005\B | BW | 25 | 5 | B | 1 Prestrip - Thick | 64.7781 | 64.7781 | 64.7781 | 2017-08-09 22:47 | 2017-08-16 08:13 | 313643.8194 | 313644 | [7 empty] | 0 | 0 | 19.37 | 10.6 | 5483.49
PH4100XPC#1 | MW\26\009\A | MW | 26 | 9 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-08-10 09:52 | 2017-08-21 03:40 | 584067.9639 | 584068 | [7 empty] | 0 | 0 | 37.03 | 10.55 | 5389.48
TS5500Exc | SC\29\013\D | SC | 29 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-08-11 13:01 | 2017-08-14 00:48 | 82047.0912 | [6 empty] | 82047 | 61271 | 4.67 | 0 | 0 | 7.51 | 5754
TS6060#1 | BW\25\006\B | BW | 25 | 6 | B | 8 Coal Mining | 88.1 | 0 | 88.1 | 2017-08-12 11:35 | 2017-08-14 11:34 | 70748.766 | [6 empty] | 70749 | 51727 | 3.24 | 0 | 0 | 10.38 | 5493
DRE2 | MW\23\009\D | MW | 23 | 9 | D | 6 DL | 100 | 0 | 100 | 2017-08-12 12:32 | 2017-08-19 23:45 | 618953.9015 |  |  |  | 36964 | 618954 | 436937 |  |  | 0 | 29.63 | 0 | 5.86 | 5896.51
TS5500Exc | MW\23\007\D | MW | 23 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-08-14 00:48 | 2017-08-16 23:47 | 97410.2195 | [6 empty] | 97410 | 73069 | 4.57 | 0 | 0 | 6.64 | 5829
TS6060#1 | BW\25\004\B | BW | 25 | 4 | B | 1 Prestrip - Thick | 37.4985 | 29.7204 | 29.7204 | 2017-08-14 11:34 | 2017-08-19 13:22 | 136920.9458 | 136921 | [7 empty] | 0 | 0 | 8.5 | 11.07 | 5438.29
PH4100A | SC\31\011\D | SC | 31 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-08-15 00:45 | 2017-08-20 19:23 | 263263.3153 | 263263 | [7 empty] | 0 | 0 | 22.88 | 7.57 | 5748.06
TS Fleet 5 | BW\25\009\B | BW | 25 | 9 | B | 1 Prestrip - Thick | 66.683 | 62.1777 | 62.1777 | 2017-08-16 08:13 | 2017-08-20 14:28 | 208976.2898 | 208976 | [7 empty] | 0 | 0 | 13.43 | 11.77 | 5355.27
DRE1 | SC\29\009\D | SC | 29 | 9 | D | 6 DL | 100 | 0 | 100 | 2017-08-16 10:00 | 2017-08-24 12:27 | 697362.499 |  |  |  | 48088 | 697362 | 432796 |  |  | 0 | 40 | 0 | 6.67 | 5827.82
TS5500Exc | SC\29\012\D | SC | 29 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-08-16 23:47 | 2017-08-19 05:14 | 73361.748 | [6 empty] | 73362 | 54697 | 4.56 | 0 | 0 | 7.55 | 5749
TS5500Shv | MW\25\008\A | MW | 25 | 8 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-08-18 20:32 | 2017-08-19 12:14 | 20842.4098 | [6 empty] | 20842 | 15261 | 0.93 | 0 | 0 | 11.58 | 5214
TS5500Exc | MW\23\008\D | MW | 23 | 8 | D | 8 Coal Mining | 46.8 | 0 | 46.8 | 2017-08-19 05:14 | 2017-08-20 13:46 | 44644.2721 | [6 empty] | 44644 | 33675 | 2.1 | 0 | 0 | 6.2 | 5867
TS5500Shv | MW\23\004\D | MW | 23 | 4 | D | 8 Coal Mining | 60.8 | 0 | 6.2 | 2017-08-19 12:14 | 2017-08-19 16:35 | 5794.4244 | [6 empty] | 5794 | 4378 | 0.27 | 0 | 0 | 6.4 | 5849
TS6060#1 | BW\25\005\B | BW | 25 | 5 | B | 1 Prestrip - Thick | 8.9761 | 8.9761 | 8.9761 | 2017-08-19 13:22 | 2017-08-21 04:01 | 43460.5507 | 43461 | [7 empty] | 0 | 0 | 2.68 | 10.6 | 5483.49
TS5500Shv | MW\26\005\A | MW | 26 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-08-19 16:35 | 2017-08-20 15:44 | 30744.8078 | [6 empty] | 30745 | 22771 | 1.4 | 0 | 0 | 9.48 | 5526
DRE2 | MW\23\010\D | MW | 23 | 10 | D | 6 DL | 100 | 0 | 100 | 2017-08-19 23:45 | 2017-08-26 21:52 | 573644.5508 |  |  |  | 34258 | 573645 | 404952 |  |  | 0 | 27.46 | 0 | 5.69 | 5911.3
TS5500Exc | MW\25\008\B | MW | 25 | 8 | B | 1 Prestrip - Thick | 92.4572 | 92.4572 | 92.4572 | 2017-08-20 13:46 | 2017-08-24 00:55 | 80114.5024 | 80115 | [7 empty] | 0 | 0 | 4.96 | 11.01 | 5391.57
TS Fleet 5 | BW\25\010\A | BW | 25 | 10 | A | 1 Prestrip - Thick | 8.4903 | 0 | 8.4903 | 2017-08-20 14:28 | 2017-08-21 18:48 | 57921.4148 | 57921 | [7 empty] | 0 | 0 | 3.49 | 0 | 0
TS5500Shv | MW\26\006\B | MW | 26 | 6 | B | 8 Coal Mining | 4.5 | 0 | 4.5 | 2017-08-20 15:44 | 2017-08-20 17:28 | 2306.335 | [6 empty] | 2306 | 1712 | 0.11 | 0 | 0 | 8.78 | 5685
TS5500Shv | MW\23\008\D | MW | 23 | 8 | D | 8 Coal Mining | 53.2 | 0 | 53.2 | 2017-08-20 17:28 | 2017-08-22 07:36 | 50657.0308 | [6 empty] | 50657 | 38210 | 2.39 | 0 | 0 | 6.2 | 5867
PH4100A | SC\32\011\D | SC | 32 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-08-20 19:23 | 2017-08-25 05:36 | 204179.2503 | 204179 | [7 empty] | 0 | 0 | 17.39 | 7.61 | 5744.63
PH4100XPC#1 | MW\25\010\A | MW | 25 | 10 | A | 1 Prestrip - Thick | 100 | 86.9891 | 86.9891 | 2017-08-21 03:40 | 2017-09-01 | 594500.3334 | 594500 | [7 empty] | 0 | 0 | 36.69 | 10.13 | 5524.71
TS6060#1 | BW\25\005\B | BW | 25 | 5 | B | 1 Prestrip - Thick | 28.7687 | 26.2458 | 26.2458 | 2017-08-21 04:01 | 2017-08-25 21:04 | 127077.625 | 127078 | [7 empty] | 0 | 0 | 7.85 | 10.6 | 5483.49
TS Fleet 5 | BW\25\010\A | BW | 25 | 10 | A | 1 Prestrip - Thick | 59.1145 | 0 | 59.1145 | 2017-08-21 18:48 | 2017-08-30 00:06 | 403284.1474 | 403284 | [7 empty] | 0 | 0 | 24.33 | 0 | 0
TS5500Shv | MW\25\005\B | MW | 25 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-08-22 07:36 | 2017-08-23 05:55 | 29655.6849 | [6 empty] | 29656 | 21954 | 1.37 | 0 | 0 | 9.1 | 5633
TS5500Shv | MW\25\009\A | MW | 25 | 9 | A | 8 Coal Mining | 55.3 | 0 | 55.3 | 2017-08-23 05:55 | 2017-08-24 13:06 | 41429.1069 | [6 empty] | 41429 | 30482 | 1.9 | 0 | 0 | 10.33 | 5410
TS5500Exc | MW\25\008\B | MW | 25 | 8 | B | 1 Prestrip - Thick | 7.5428 | 7.5428 | 7.5428 | 2017-08-24 00:55 | 2017-08-24 07:42 | 6535.8321 | 6536 | [7 empty] | 0 | 0 | 0.4 | 11.01 | 5391.57
TS5500Exc | MW\25\005\B | MW | 25 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-08-24 07:42 | 2017-08-25 06:01 | 30633.3448 | [6 empty] | 30633 | 22678 | 1.41 | 0 | 0 | 9.1 | 5633
DRE1 | SC\29\003\D | SC | 29 | 3 | D | 6 DL | 100 | 0 | 100 | 2017-08-24 12:27 | 2017-08-30 05:25 | 491226.9426 |  |  |  | 27590 | 491227 | 213819 |  |  | 0 | 40 | 0 | 6.3 | 5861.22
TS5500Shv | MW\25\008\B | MW | 25 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-08-24 13:06 | 2017-08-26 12:56 | 63542.3089 | [6 empty] | 63542 | 46379 | 2.9 | 0 | 0 | 11.01 | 5392
PH4100A | SC\31\012\D | SC | 31 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-08-25 05:36 | 2017-08-29 13:39 | 197358.6909 | 197359 | [7 empty] | 0 | 0 | 16.88 | 7.62 | 5742.64
TS5500Exc | SC\29\011\D | SC | 29 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-08-25 06:01 | 2017-08-27 12:36 | 74908.4383 | [6 empty] | 74908 | 55896 | 4.66 | 0 | 0 | 7.45 | 5758
TS6060#1 | BW\25\003\B | BW | 25 | 3 | B | 8 Coal Mining | 100 | 0 | 99.7 | 2017-08-25 21:04 | 2017-08-28 23:35 | 109903.451 | [6 empty] | 109903 | 80008 | 3.61 | 0 | 0 | 11.29 | 5401
TS5500Shv | DT\27\001\B | DT | 27 | 1 | B | 1 Prestrip - Thick | 20.6828 | 19.1162 | 19.1162 | 2017-08-26 12:56 | 2017-09-01 | 153551.3755 | 153551 | [7 empty] | 0 | 0 | 7.14 | 12.55 | 5259.95
DRE2 | MW\23\011\D | MW | 23 | 11 | D | 6 DL | 100 | 0 | 72.6355 | 2017-08-26 21:52 | 2017-09-01 | 421766.5374 |  |  |  | 25188 | 421767 | 297737 |  |  | 0 | 27.76 | 0 | 5.88 | 5894.76
TS5500Exc | MW\25\009\A | MW | 25 | 9 | A | 8 Coal Mining | 44.7 | 0 | 44.7 | 2017-08-27 12:36 | 2017-08-28 13:01 | 33523.5737 | [6 empty] | 33524 | 24665 | 1.54 | 0 | 0 | 10.33 | 5410
TS5500Exc | MW\25\009\B | MW | 25 | 9 | B | 1 Prestrip - Thick | 100 | 97.2577 | 97.2577 | 2017-08-28 13:01 | 2017-09-01 | 79946.8635 | 79947 | [7 empty] | 0 | 0 | 5.01 | 9.95 | 5521.84
TS6060#1 | BW\25\011\A | BW | 25 | 11 | A | 1 Prestrip - Thick | 29.6447 | 13.421 | 13.421 | 2017-08-28 23:35 | 2017-09-01 | 80715.5881 | 80716 | [7 empty] | 0 | 0 | 5.04 | 20.4 | 4672.76
PH4100A | SC\32\012\D | SC | 32 | 12 | D | 1 Prestrip - Thick | 100 | 95.8536 | 95.8536 | 2017-08-29 13:39 | 2017-09-01 | 109486.6079 | 109487 | [7 empty] | 0 | 0 | 9.36 | 7.65 | 5739.94
TS Fleet 5 | BW\25\010\B | BW | 25 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-08-30 00:06 | 2017-08-31 11:22 | 72071.5173 | 72072 | [7 empty] | 0 | 0 | 4.46 | 13.86 | 5172.99
DRE1 | SC\29\004\D | SC | 29 | 4 | D | 6 DL | 100 | 0 | 23.8874 | 2017-08-30 05:25 | 2017-09-01 | 152668.7162 |  |  |  | 11610 | 152669 | 104488 |  |  | 0 | 40 | 0 | 6.22 | 5867.9
TS Fleet 5 | BW\25\011\A | BW | 25 | 11 | A | 1 Prestrip - Thick | 70.3553 | 4.2925 | 4.2925 | 2017-08-31 11:22 | 2017-09-01 | 25815.6542 | 25816 | [7 empty] | 0 | 0 | 1.61 | 20.4 | 4672.76
| EOP 44 : 2017\Aug | EOP 44 : 2017 | Aug | [6 empty] | 2017-09-01 | 2017-09-01 |  | 6026073 |  |  | 336238 | 5237555 | 3478289 | 1353029 | 998320 | 64.17 | 0 | 399.06 | 8.91 | 5613.15
TS Fleet 5 | BW\25\011\A | BW | 25 | 11 | A | 1 Prestrip - Thick | 70.3553 | 66.0628 | 66.0628 | 2017-09-01 | 2017-09-09 05:04 | 397310.3448 | 397310 | [7 empty] | 0 | 0 | 24.8 | 20.4 | 4672.76
DRE1 | SC\29\004\D | SC | 29 | 4 | D | 6 DL | 100 | 0 | 76.1126 | 2017-09-01 | 2017-09-06 15:38 | 486449.151 |  |  |  | 36992 | 486449 | 332931 |  |  | 0 | 40 | 0 | 6.22 | 5867.9
PH4100A | SC\32\012\D | SC | 32 | 12 | D | 1 Prestrip - Thick | 100 | 4.1464 | 4.1464 | 2017-09-01 | 2017-09-01 02:33 | 4736.1229 | 4736 | [7 empty] | 0 | 0 | 0.4 | 7.65 | 5739.94
DRE2 | MW\23\011\D | MW | 23 | 11 | D | 6 DL | 100 | 0 | 27.3645 | 2017-09-01 | 2017-09-03 20:07 | 158894.9386 |  |  |  | 9489 | 158895 | 112168 |  |  | 0 | 27.76 | 0 | 5.88 | 5894.76
PH4100XPC#1 | MW\25\010\A | MW | 25 | 10 | A | 1 Prestrip - Thick | 100 | 13.0109 | 13.0109 | 2017-09-01 | 2017-09-02 15:27 | 88918.9132 | 88919 | [7 empty] | 0 | 0 | 5.49 | 10.13 | 5524.71
TS5500Shv | DT\27\001\B | DT | 27 | 1 | B | 1 Prestrip - Thick | 20.6828 | 1.5667 | 1.5667 | 2017-09-01 | 2017-09-01 10:53 | 12584.4845 | 12584 | [7 empty] | 0 | 0 | 0.59 | 12.55 | 5259.95
TS6060#1 | BW\25\011\A | BW | 25 | 11 | A | 1 Prestrip - Thick | 29.6447 | 16.2238 | 16.2238 | 2017-09-01 | 2017-09-04 16:44 | 97571.8692 | 97572 | [7 empty] | 0 | 0 | 6.09 | 20.4 | 4672.76
TS5500Exc | MW\25\009\B | MW | 25 | 9 | B | 1 Prestrip - Thick | 100 | 2.7423 | 2.7423 | 2017-09-01 | 2017-09-01 02:22 | 2254.1631 | 2254 | [7 empty] | 0 | 0 | 0.14 | 9.95 | 5521.84
TS5500Exc | SC\29\003\D | SC | 29 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2017-09-01 02:22 | 2017-09-02 14:39 | 34486.95 |  |  | 34487 | [5 empty] | 0 | 0 | 0 | 6.3 | 5861.22
PH4100A | SC\31\008\D | SC | 31 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-09-01 02:33 | 2017-09-15 11:11 | 655472.5303 | 655473 | [7 empty] | 0 | 0 | 55.07 | 6.51 | 5842.97
TS5500Shv | DT\27\001\B | DT | 27 | 1 | B | 1 Prestrip - Thick | 79.3172 | 79.3172 | 79.3172 | 2017-09-01 10:53 | 2017-09-24 10:16 | 637118.424 | 637118 | [7 empty] | 0 | 0 | 29.63 | 12.55 | 5259.95
TS5500Exc | SC\29\003\D | SC | 29 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-09-02 14:39 | 2017-09-03 22:02 | 42473.5594 | [6 empty] | 42474 | 32128 | 4.9 | 0 | 0 | 6.3 | 5861
PH4100XPC#1 | MW\26\010\A | MW | 26 | 10 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-09-02 15:27 | 2017-09-16 00:54 | 723683.6649 | 723684 | [7 empty] | 0 | 0 | 44.48 | 10.34 | 5510.41
DRE2 | MW\23\012\D | MW | 23 | 12 | D | 6 DL | 100 | 100 | 100 | 2017-09-03 20:07 | 2017-09-11 10:20 | 424952.4206 |  |  |  | 15210 | 424952 | 200970 |  |  | 0 | 26.34 | 0 | 6.04 | 5879.92
TS5500Exc | MW\25\010\A | MW | 25 | 10 | A | 8 Coal Mining | 33.8 | 0 | 33.8 | 2017-09-03 22:02 | 2017-09-04 16:55 | 25570.1606 | [6 empty] | 25570 | 18806 | 1.17 | 0 | 0 | 10.13 | 5525
TS6060#1 | BW\25\003\B | BW | 25 | 3 | B | 8 Coal Mining | 100 | 0 | 0.3 | 2017-09-04 16:44 | 2017-09-04 16:59 | 377.1263 | [6 empty] | 377 | 275 | 0.01 | 0 | 0 | 11.29 | 5401
TS5500Exc | SC\29\009\D | SC | 29 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-09-04 16:55 | 2017-09-07 02:45 | 78277.7386 | [6 empty] | 78278 | 58924 | 4.91 | 0 | 0 | 6.67 | 5828
TS6060#1 | BW\25\004\B | BW | 25 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-09-04 16:59 | 2017-09-06 19:21 | 73243.2315 | [6 empty] | 73243 | 53359 | 3.34 | 0 | 0 | 11.07 | 5438
DRE1 | SC\29\005\D | SC | 29 | 5 | D | 6 DL | 100 | 0 | 100 | 2017-09-06 15:38 | 2017-09-14 00:01 | 632584.9484 |  |  |  | 48105 | 632585 | 432948 |  |  | 0 | 40 | 0 | 6.08 | 5879.44
TS6060#1 | BW\25\005\B | BW | 25 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-09-06 19:21 | 2017-09-08 21:17 | 72615.7455 | [6 empty] | 72616 | 53034 | 3.33 | 0 | 0 | 10.6 | 5483
TS5500Exc | SC\29\004\D | SC | 29 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-09-07 02:45 | 2017-09-09 12:19 | 77913.7949 | [6 empty] | 77914 | 58744 | 4.89 | 0 | 0 | 6.22 | 5868
TS6060#1 | BW\25\006\B | BW | 25 | 6 | B | 8 Coal Mining | 11.9 | 0 | 11.9 | 2017-09-08 21:17 | 2017-09-09 03:50 | 9533.7069 | [6 empty] | 9534 | 6970 | 0.44 | 0 | 0 | 10.38 | 5493
TS6060#1 | BW\25\007\B | BW | 25 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-09-09 03:50 | 2017-09-11 12:53 | 82983.4107 | [6 empty] | 82983 | 60598 | 3.78 | 0 | 0 | 10.65 | 5463
TS Fleet 5 | BW\26\003\X1 | BW | 26 | 3 | X1 | 1 Prestrip - Thick | 84.8894 | 84.8894 | 84.8894 | 2017-09-09 05:04 | 2017-09-16 10:45 | 350149.499 | 350149 | [7 empty] | 0 | 0 | 24.44 | 11.57 | 5371.29
TS5500Exc | SC\29\010\D | SC | 29 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-09-09 12:19 | 2017-09-11 21:18 | 77151.0536 | [6 empty] | 77151 | 57753 | 4.81 | 0 | 0 | 7.18 | 5783
DRE2 | DT\23\003\D | DT | 23 | 3 | D | 6 DL | 100 | 100 | 100 | 2017-09-11 10:20 | 2017-09-20 06:41 | 495251.5823 |  |  |  | 21600 | 495252 | 357341 |  |  | 0 | 23.64 | 0 | 6.1 | 5877.08
TS6060#1 | BW\25\008\B | BW | 25 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-09-11 12:53 | 2017-09-13 21:06 | 81766.3486 | [6 empty] | 81766 | 59751 | 3.73 | 0 | 0 | 10.77 | 5445
TS5500Exc | MW\23\009\D | MW | 23 | 9 | D | 8 Coal Mining | 33.8 | 0 | 33.8 | 2017-09-11 21:18 | 2017-09-12 20:40 | 31623.6639 | [6 empty] | 31624 | 23929 | 1.5 | 0 | 0 | 5.86 | 5897
TS5500Exc | MW\23\010\D | MW | 23 | 10 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-09-12 20:40 | 2017-09-14 07:21 | 46951.6772 | [6 empty] | 46952 | 35556 | 2.22 | 0 | 0 | 5.69 | 5911
TS6060#1 | BW\25\009\B | BW | 25 | 9 | B | 8 Coal Mining | 84.2 | 0 | 84.2 | 2017-09-13 21:06 | 2017-09-15 20:57 | 69576.9795 | [6 empty] | 69577 | 50646 | 3.17 | 0 | 0 | 11.77 | 5355
DRE1 | SC\29\006\D | SC | 29 | 6 | D | 6 DL | 100 | 0 | 100 | 2017-09-14 00:01 | 2017-09-21 07:48 | 630364.9712 |  |  |  | 47936 | 630365 | 431428 |  |  | 0 | 40 | 0 | 5.98 | 5888.61
TS5500Exc | SC\29\005\D | SC | 29 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-09-14 07:21 | 2017-09-16 17:09 | 78220.5807 | [6 empty] | 78221 | 58928 | 4.91 | 0 | 0 | 6.08 | 5879
PH4100A | SC\32\008\D | SC | 32 | 8 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-09-15 11:11 | 2017-09-15 11:11 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\31\009\D | SC | 31 | 9 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-09-15 11:11 | 2017-09-25 09:56 | 451484.91 | 451485 | [7 empty] | 0 | 0 | 39.8 | 6.96 | 5802.7
TS6060#1 | BW\25\009\B | BW | 25 | 9 | B | 8 Coal Mining | 15.8 | 0 | 15.8 | 2017-09-15 20:57 | 2017-09-16 05:54 | 13019.93 | [6 empty] | 13020 | 9477 | 0.59 | 0 | 0 | 11.77 | 5355
PH4100XPC#1 | MW\25\011\A | MW | 25 | 11 | A | 1 Prestrip - Thick | 100 | 65.4887 | 65.4887 | 2017-09-16 00:54 | 2017-10-01 | 812416.1441 | 812416 | [7 empty] | 0 | 0 | 30.86 | 10.75 | 5477.74
TS6060#1 | BW\25\010\B | BW | 25 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-09-16 05:54 | 2017-09-18 17:19 | 86422.3933 | [6 empty] | 86422 | 62330 | 3.85 | 0 | 0 | 13.86 | 5173
TS Fleet 5 | BW\26\004\X2 | BW | 26 | 4 | X2 | 1 Prestrip - Thick | 21.4346 | 0 | 21.4346 | 2017-09-16 10:45 | 2017-09-19 01:26 | 126368.8373 | 126369 | [7 empty] | 0 | 0 | 8.88 | 0 | 0
TS5500Exc | MW\23\011\D | MW | 23 | 11 | D | 8 Coal Mining | 9.2 | 0 | 9.2 | 2017-09-16 17:09 | 2017-09-16 23:25 | 8501.0787 | [6 empty] | 8501 | 6453 | 0.4 | 0 | 0 | 5.88 | 5895
TS5500Exc | MW\25\009\B | MW | 25 | 9 | B | 8 Coal Mining | 2.7 | 0 | 2.7 | 2017-09-16 23:25 | 2017-09-17 00:40 | 1694.6668 | [6 empty] | 1695 | 1246 | 0.08 | 0 | 0 | 9.95 | 5522
TS5500Exc | MW\25\009\B | MW | 25 | 9 | B | 8 Coal Mining | 48.1 | 0 | 48.1 | 2017-09-17 00:40 | 2017-09-17 23:13 | 30519.019 | [6 empty] | 30519 | 22438 | 1.4 | 0 | 0 | 9.95 | 5522
TS5500Exc | MW\25\010\A | MW | 25 | 10 | A | 8 Coal Mining | 17 | 0 | 17 | 2017-09-17 23:13 | 2017-09-18 08:42 | 12833.0703 | [6 empty] | 12833 | 9438 | 0.59 | 0 | 0 | 10.13 | 5525
TS5500Exc | MW\26\008\A | MW | 26 | 8 | A | 8 Coal Mining | 47.2 | 0 | 47.2 | 2017-09-18 08:42 | 2017-09-19 02:10 | 23632.7845 | [6 empty] | 23633 | 17305 | 1.08 | 0 | 0 | 11.58 | 5210
TS6060#1 | BW\25\011\A | BW | 25 | 11 | A | 8 Coal Mining | 100 | 0 | 100 | 2017-09-18 17:19 | 2017-09-19 07:43 | 20929.911 | [6 empty] | 20930 | 14573 | 0.91 | 0 | 0 | 20.4 | 4673
TS Fleet 5 | BW\26\004\X2 | BW | 26 | 4 | X2 | 1 Prestrip - Thick | 78.5654 | 0 | 78.5654 | 2017-09-19 01:26 | 2017-09-28 15:12 | 463185.7036 | 463186 | [7 empty] | 0 | 0 | 32.54 | 0 | 0
TS5500Exc | MW\26\009\A | MW | 26 | 9 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-09-19 02:10 | 2017-09-20 06:39 | 38556.7469 | [6 empty] | 38557 | 28348 | 1.77 | 0 | 0 | 10.55 | 5389
TS6060#1 | BW\25\011\B | BW | 25 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-09-19 07:43 | 2017-09-21 06:25 | 51791.535 | 51792 | [7 empty] | 0 | 0 | 3.22 | 17.84 | 4850.77
TS5500Exc | MW\26\010\A | MW | 26 | 10 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-09-20 06:39 | 2017-09-21 11:10 | 38597.634 | [6 empty] | 38598 | 28391 | 1.77 | 0 | 0 | 10.34 | 5510
DRE2 | DT\23\002\D | DT | 23 | 2 | D | 6 DL | 100 | 100 | 100 | 2017-09-20 06:41 | 2017-09-27 12:32 | 405436.5949 |  |  |  | 17682 | 405437 | 292536 |  |  | 0 | 21.86 | 0 | 6.22 | 5866.61
TS6060#1 | BW\25\011\B | BW | 25 | 11 | B | 8 Coal Mining | 100 | 0 | 10.9 | 2017-09-21 06:25 | 2017-09-21 13:37 | 10461.1277 | [6 empty] | 10461 | 7383 | 0.46 | 0 | 0 | 17.84 | 4851
DRE1 | SC\29\007\D | SC | 29 | 7 | D | 6 DL | 100 | 0 | 100 | 2017-09-21 07:48 | 2017-09-28 15:32 | 630215.1944 |  |  |  | 47925 | 630215 | 431326 |  |  | 0 | 40 | 0 | 5.94 | 5891.82
TS5500Exc | SC\29\006\D | SC | 29 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-09-21 11:10 | 2017-09-23 21:31 | 78988.3146 | [6 empty] | 78988 | 59650 | 4.97 | 0 | 0 | 5.98 | 5889
TS6060#1 | BW\26\003\X1 | BW | 26 | 3 | X1 | 1 Prestrip - Thick | 15.1106 | 15.1106 | 15.1106 | 2017-09-21 13:37 | 2017-09-23 22:00 | 62327.7506 | 62328 | [7 empty] | 0 | 0 | 4.35 | 11.57 | 5371.29
TS5500Exc | DT\23\003\D | DT | 23 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-09-23 21:31 | 2017-09-25 11:25 | 51294.2664 | [6 empty] | 51294 | 38665 | 2.42 | 0 | 0 | 6.1 | 5877
TS6060#1 | BW\26\003\X1 | BW | 26 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2017-09-23 22:00 | 2017-09-24 10:43 | 18491.6455 | [6 empty] | 18492 | 13560 | 1 | 0 | 0 | 11.57 | 5371
TS5500Shv | MW\25\010\A | MW | 25 | 10 | A | 8 Coal Mining | 32.8 | 0 | 32.8 | 2017-09-24 10:16 | 2017-09-25 05:09 | 24754.0917 | [6 empty] | 24754 | 18206 | 1.13 | 0 | 0 | 10.13 | 5525
TS6060#1 | MW\23\012\D | MW | 23 | 12 | D | 7 PostStrip | 100 | 0 | 100 | 2017-09-24 10:43 | 2017-09-26 08:24 | 50656.3599 |  |  | 50656 | [5 empty] | 0 | 0 | 0 | 6.04 | 5879.92
TS5500Shv | MW\23\009\D | MW | 23 | 9 | D | 8 Coal Mining | 66.2 | 0 | 66.2 | 2017-09-25 05:09 | 2017-09-27 04:24 | 61910.9674 | [6 empty] | 61911 | 46848 | 2.93 | 0 | 0 | 5.86 | 5897
PH4100A | SC\32\009\D | SC | 32 | 9 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-09-25 09:56 | 2017-09-25 09:56 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\31\004\B | SC | 31 | 4 | B | 1 Prestrip - Thick | 100 | 49.082 | 49.082 | 2017-09-25 09:56 | 2017-10-01 | 250038.6637 | 250039 | [7 empty] | 0 | 0 | 21.89 | 9.17 | 5559.61
TS5500Exc | MW\26\005\B | MW | 26 | 5 | B | 1 Prestrip - Thick | 1.8825 | 1.8825 | 1.8825 | 2017-09-25 11:25 | 2017-09-25 12:35 | 1110.9047 | 1111 | [7 empty] | 0 | 0 | 0.07 | 9.11 | 5635.28
TS5500Exc | MW\26\005\B | MW | 26 | 5 | B | 1 Prestrip - Thick | 98.1175 | 98.1175 | 98.1175 | 2017-09-25 12:35 | 2017-09-28 01:30 | 57899.9367 | 57900 | [7 empty] | 0 | 0 | 3.6 | 9.11 | 5635.28
TS6060#1 | BW\26\003\B | BW | 26 | 3 | B | 1 Prestrip - Thick | 44.3069 | 25.5532 | 25.5532 | 2017-09-26 08:24 | 2017-10-01 | 123736.8479 | 123737 | [7 empty] | 0 | 0 | 9.46 | 10.93 | 5434.52
TS5500Shv | MW\23\010\D | MW | 23 | 10 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-09-27 04:24 | 2017-09-28 15:05 | 45453.2194 | [6 empty] | 45453 | 34421 | 2.15 | 0 | 0 | 5.69 | 5911
DRE2 | DT\23\001\D | DT | 23 | 1 | D | 6 DL | 100 | 45.98 | 45.98 | 2017-09-27 12:32 | 2017-10-01 | 194648.4637 |  |  |  | 8489 | 194648 | 140445 |  |  | 0 | 21.63 | 0 | 6.49 | 5843.47
TS5500Exc | MW\23\012\D | MW | 23 | 12 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-09-28 01:30 | 2017-09-28 22:52 | 28926.6706 | [6 empty] | 28927 | 21959 | 2.22 | 0 | 0 | 6.04 | 5880
TS5500Shv | MW\23\011\D | MW | 23 | 11 | D | 8 Coal Mining | 90.8 | 0 | 48.9 | 2017-09-28 15:05 | 2017-09-30 01:36 | 45240.7934 | [6 empty] | 45241 | 34344 | 2.15 | 0 | 0 | 5.88 | 5895
TS Fleet 5 | BW\26\004\B | BW | 26 | 4 | B | 1 Prestrip - Thick | 100 | 25.194 | 25.194 | 2017-09-28 15:12 | 2017-10-01 | 114505.6152 | 114506 | [7 empty] | 0 | 0 | 7.19 | 10.79 | 5461.51
DRE1 | SC\29\008\D | SC | 29 | 8 | D | 6 DL | 100 | 0 | 32.9068 | 2017-09-28 15:32 | 2017-10-01 | 202503.735 |  |  |  | 15400 | 202504 | 138596 |  |  | 0 | 40 | 0 | 6.2 | 5869.37
TS5500Exc | SC\29\007\D | SC | 29 | 7 | D | 8 Coal Mining | 100 | 0 | 46.7 | 2017-09-28 22:52 | 2017-09-30 01:36 | 36192.8908 | [6 empty] | 36193 | 27419 | 2.28 | 0 | 0 | 5.94 | 5892
TS5500Shv | DT\27\002\B | DT | 27 | 2 | B | 1 Prestrip - Thick | 100 | 10.1622 | 10.1622 | 2017-09-30 01:36 | 2017-10-01 | 25838.0484 | 25838 | [7 empty] | 0 | 0 | 1.1 | 11.58 | 5313.59
TS5500Exc | MW\27\003\B | MW | 27 | 3 | B | 1 Prestrip - Thick | 69.843 | 2.7917 | 2.7917 | 2017-09-30 01:36 | 2017-10-01 | 21282.5519 | 21283 | [7 empty] | 0 | 0 | 1.34 | 8.34 | 5632.08
| EOP 45 : 2017\Sep | EOP 45 : 2017 | Sep | [6 empty] | 2017-10-01 | 2017-10-01 |  | 5531787 |  | 85143 | 268829 | 4261302 | 2870690 | 1524700 | 1131856 | 81.27 | 0 | 355.44 | 8.58 | 5654.01
TS Fleet 5 | BW\26\004\B | BW | 26 | 4 | B | 1 Prestrip - Thick | 100 | 74.806 | 74.806 | 2017-10-01 | 2017-10-08 10:33 | 339989.5323 | 339990 | [7 empty] | 0 | 0 | 21.36 | 10.79 | 5461.51
DRE1 | SC\29\008\D | SC | 29 | 8 | D | 6 DL | 100 | 0 | 67.0932 | 2017-10-01 | 2017-10-05 20:38 | 412882.5962 |  |  |  | 31398 | 412883 | 282581 |  |  | 0 | 40 | 0 | 6.2 | 5869.37
PH4100A | SC\31\004\B | SC | 31 | 4 | B | 1 Prestrip - Thick | 100 | 50.918 | 50.918 | 2017-10-01 | 2017-10-07 00:52 | 259392.1208 | 259392 | [7 empty] | 0 | 0 | 22.71 | 9.17 | 5559.61
DRE2 | DT\23\001\D | DT | 23 | 1 | D | 6 DL | 100 | 54.02 | 54.02 | 2017-10-01 | 2017-10-03 19:05 | 228684.342 |  |  |  | 9974 | 228684 | 165003 |  |  | 0 | 21.63 | 0 | 6.49 | 5843.47
PH4100XPC#1 | MW\25\011\A | MW | 25 | 11 | A | 1 Prestrip - Thick | 100 | 4.3101 | 4.3101 | 2017-10-01 | 2017-10-02 00:37 | 53468.1634 | 53468 | [7 empty] | 0 | 0 | 2.03 | 10.75 | 5477.74
TS5500Shv | DT\27\002\B | DT | 27 | 2 | B | 1 Prestrip - Thick | 100 | 89.8378 | 89.8378 | 2017-10-01 | 2017-10-09 17:31 | 228418.4275 | 228418 | [7 empty] | 0 | 0 | 9.69 | 11.58 | 5313.59
TS6060#1 | BW\26\003\B | BW | 26 | 3 | B | 1 Prestrip - Thick | 44.3069 | 18.7538 | 18.7538 | 2017-10-01 | 2017-10-04 14:43 | 90811.8122 | 90812 | [7 empty] | 0 | 0 | 6.94 | 10.93 | 5434.52
TS5500Exc | MW\27\003\B | MW | 27 | 3 | B | 1 Prestrip - Thick | 69.843 | 67.0513 | 67.0513 | 2017-10-01 | 2017-10-24 17:14 | 511167.7087 | 511168 | [7 empty] | 0 | 0 | 32.09 | 8.34 | 5632.08
PH4100XPC#1 | MW\26\011\A | MW | 26 | 11 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-10-02 00:37 | 2017-10-23 20:46 | 1137932.485 | 1137932 | [7 empty] | 0 | 0 | 50.59 | 11.08 | 5450.93
DRE2 | BW\23\011\D | BW | 23 | 11 | D | 6 DL | 100 | 100 | 100 | 2017-10-03 19:05 | 2017-10-09 02:45 | 435188.1568 |  |  |  | 18980 | 435188 | 314003 |  |  | 0 | 20.83 | 0 | 6.52 | 5840.83
TS6060#1 | BW\25\011\B | BW | 25 | 11 | B | 8 Coal Mining | 100 | 0 | 89.1 | 2017-10-04 14:43 | 2017-10-07 04:50 | 85335.9071 | [6 empty] | 85336 | 60227 | 3.76 | 0 | 0 | 17.84 | 4851
DRE1 | SC\30\013\D | SC | 30 | 13 | D | 6 DL | 100 | 0 | 100 | 2017-10-05 20:38 | 2017-10-20 12:45 | 1246392.803 |  |  |  | 69508 | 1246393 | 541964 |  |  | 0 | 40 | 0 | 7.53 | 5751.26
PH4100A | SC\32\005\B | SC | 32 | 5 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-10-07 00:52 | 2017-10-07 00:52 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\31\005\B | SC | 31 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-10-07 00:52 | 2017-10-18 22:17 | 530215.5054 | 530216 | [7 empty] | 0 | 0 | 44.75 | 9.33 | 5544.78
TS6060#1 | BW\26\003\B | BW | 26 | 3 | B | 1 Prestrip - Thick | 28.2478 | 25.4603 | 25.4603 | 2017-10-07 04:50 | 2017-10-12 02:34 | 123287.1891 | 123287 | [7 empty] | 0 | 0 | 9.42 | 10.93 | 5434.52
TS Fleet 5 | BW\26\003\B | BW | 26 | 3 | B | 1 Prestrip - Thick | 30.2327 | 30.2327 | 30.2327 | 2017-10-08 10:33 | 2017-10-11 15:27 | 146396.8685 | 146397 | [7 empty] | 0 | 0 | 11.19 | 10.93 | 5434.52
DRE2 | BW\23\010\D | BW | 23 | 10 | D | 6 DL | 100 | 100 | 100 | 2017-10-09 02:45 | 2017-10-14 14:13 | 448076.0031 |  |  |  | 19542 | 448076 | 323302 |  |  | 0 | 21.42 | 0 | 6.14 | 5874.3
TS5500Shv | MW\23\011\D | MW | 23 | 11 | D | 8 Coal Mining | 90.8 | 0 | 41.9 | 2017-10-09 17:31 | 2017-10-11 00:48 | 38713.1534 | [6 empty] | 38713 | 29388 | 1.84 | 0 | 0 | 5.88 | 5895
TS5500Shv | MW\23\012\D | MW | 23 | 12 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-10-11 00:48 | 2017-10-11 23:25 | 28003.479 | [6 empty] | 28003 | 21258 | 2.15 | 0 | 0 | 6.04 | 5880
TS Fleet 5 | BW\26\005\X1 | BW | 26 | 5 | X1 | 1 Prestrip - Thick | 88.0143 | 88.0143 | 88.0143 | 2017-10-11 15:27 | 2017-10-18 10:12 | 309895.4335 | 309895 | [7 empty] | 0 | 0 | 19.62 | 10.97 | 5429.69
TS5500Shv | MW\25\009\B | MW | 25 | 9 | B | 8 Coal Mining | 2.6 | 0 | 2.6 | 2017-10-11 23:25 | 2017-10-12 00:45 | 1640.5816 | [6 empty] | 1641 | 1206 | 0.08 | 0 | 0 | 9.95 | 5522
TS5500Shv | MW\25\009\B | MW | 25 | 9 | B | 8 Coal Mining | 46.6 | 0 | 46.6 | 2017-10-12 00:45 | 2017-10-13 00:37 | 29545.0077 | [6 empty] | 29545 | 21722 | 1.36 | 0 | 0 | 9.95 | 5522
TS6060#1 | BW\26\003\B | BW | 26 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-10-12 02:34 | 2017-10-14 01:06 | 63923.0209 | [6 empty] | 63923 | 46660 | 3.65 | 0 | 0 | 10.93 | 5435
TS5500Shv | MW\25\010\A | MW | 25 | 10 | A | 8 Coal Mining | 16.4 | 0 | 16.4 | 2017-10-13 00:37 | 2017-10-13 10:39 | 12423.5043 | [6 empty] | 12424 | 9137 | 0.57 | 0 | 0 | 10.13 | 5525
TS5500Shv | MW\25\011\A | MW | 25 | 11 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-10-13 10:39 | 2017-10-15 09:44 | 58268.1724 | [6 empty] | 58268 | 42735 | 1.76 | 0 | 0 | 10.75 | 5478
TS6060#1 | BW\26\004\B | BW | 26 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-10-14 01:06 | 2017-10-16 05:48 | 72386.5728 | [6 empty] | 72387 | 52831 | 3.29 | 0 | 0 | 10.79 | 5462
DRE2 | BW\23\009\D | BW | 23 | 9 | D | 6 DL | 100 | 100 | 100 | 2017-10-14 14:13 | 2017-10-20 20:01 | 510630.835 |  |  |  | 22270 | 510631 | 368437 |  |  | 0 | 24.49 | 0 | 5.59 | 5924.65
TS5500Shv | MW\26\006\B | MW | 26 | 6 | B | 8 Coal Mining | 90.9 | 0 | 90.9 | 2017-10-15 09:44 | 2017-10-16 23:26 | 46657.5714 | [6 empty] | 46658 | 34626 | 2.2 | 0 | 0 | 8.78 | 5685
TS6060#1 | BW\23\011\D | BW | 23 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-10-16 05:48 | 2017-10-19 08:27 | 102542.3127 | [6 empty] | 102542 | 77107 | 4.82 | 0 | 0 | 6.52 | 5841
TS5500Shv | MW\26\007\A | MW | 26 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2017-10-16 23:26 | 2017-10-17 20:40 | 26261.3467 | [6 empty] | 26261 | 19142 | 1.17 | 0 | 0 | 12.52 | 5187
TS5500Shv | MW\26\008\A | MW | 26 | 8 | A | 8 Coal Mining | 52.8 | 0 | 52.8 | 2017-10-17 20:40 | 2017-10-18 18:01 | 26427.0396 | [6 empty] | 26427 | 19351 | 1.21 | 0 | 0 | 11.58 | 5210
TS Fleet 5 | BW\26\006\B | BW | 26 | 6 | B | 1 Prestrip - Thick | 0.11022 | 0.11022 | 0.11022 | 2017-10-18 10:12 | 2017-10-18 10:45 | 1026.847 | 1027 | [7 empty] | 0 | 0 | 0.07 | 10.6 | 5475.9
TS Fleet 5 | BW\26\006\B | BW | 26 | 6 | B | 1 Prestrip - Thick | 66.0193 | 66.0193 | 66.0193 | 2017-10-18 10:45 | 2017-10-31 21:46 | 615042.3611 | 615042 | [7 empty] | 0 | 0 | 39.09 | 10.6 | 5475.9
TS5500Shv | MW\26\009\A | MW | 26 | 9 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-10-18 18:01 | 2017-10-20 00:10 | 37326.2125 | [6 empty] | 37326 | 27443 | 1.71 | 0 | 0 | 10.55 | 5389
PH4100A | SC\31\006\B | SC | 31 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-10-18 22:17 | 2017-10-31 20:37 | 579985.1274 | 579985 | [7 empty] | 0 | 0 | 47.6 | 9.86 | 5499.04
TS6060#1 | BW\26\005\X1 | BW | 26 | 5 | X1 | 1 Prestrip - Thick | 11.9857 | 11.9857 | 11.9857 | 2017-10-19 08:27 | 2017-10-21 00:47 | 42201.4161 | 42201 | [7 empty] | 0 | 0 | 2.67 | 10.97 | 5429.69
TS5500Shv | MW\26\010\A | MW | 26 | 10 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-10-20 00:10 | 2017-10-21 06:22 | 37365.7946 | [6 empty] | 37366 | 27485 | 1.71 | 0 | 0 | 10.34 | 5510
DRE1 | SC\30\012\D | SC | 30 | 12 | D | 6 DL | 100 | 0 | 100 | 2017-10-20 12:45 | 2017-10-27 22:00 | 627392.3381 |  |  |  | 47710 | 627392 | 429394 |  |  | 0 | 40 | 0 | 7.58 | 5745.82
DRE2 | BW\23\008\D | BW | 23 | 8 | D | 6 DL | 100 | 100 | 100 | 2017-10-20 20:01 | 2017-10-26 15:14 | 474549.0068 |  |  |  | 20697 | 474549 | 342403 |  |  | 0 | 22.78 | 0 | 5.26 | 5952.31
TS6060#1 | BW\23\010\D | BW | 23 | 10 | D | 8 Coal Mining | 33.1 | 0 | 33.1 | 2017-10-21 00:47 | 2017-10-22 01:59 | 34615.808 | [6 empty] | 34616 | 26112 | 1.63 | 0 | 0 | 6.14 | 5874
TS5500Shv | DT\23\001\D | DT | 23 | 1 | D | 8 Coal Mining | 89.6 | 0 | 89.6 | 2017-10-21 06:22 | 2017-10-24 02:39 | 84516.733 | [6 empty] | 84517 | 63404 | 4.26 | 0 | 0 | 6.49 | 5843
TS6060#1 | BW\26\006\B | BW | 26 | 6 | B | 1 Prestrip - Thick | 27.4476 | 26.4814 | 26.4814 | 2017-10-22 01:59 | 2017-11-01 | 246703.5095 | 246704 | [7 empty] | 0 | 0 | 15.68 | 10.6 | 5475.9
PH4100XPC#1 | BW\26\011\B | BW | 26 | 11 | B | 1 Prestrip - Thick | 100 | 61.057 | 61.057 | 2017-10-23 20:46 | 2017-11-01 | 461095.4485 | 461095 | [7 empty] | 0 | 0 | 31.59 | 20.14 | 4662.35
TS5500Shv | MW\26\011\A | MW | 26 | 11 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-10-24 02:39 | 2017-10-25 19:04 | 50012.2519 | [6 empty] | 50012 | 36657 | 1.73 | 0 | 0 | 11.08 | 5451
TS5500Exc | MW\25\011\A | MW | 25 | 11 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-10-24 17:14 | 2017-10-26 16:19 | 60189.1011 | [6 empty] | 60189 | 44144 | 1.82 | 0 | 0 | 10.75 | 5478
TS5500Shv | DT\23\002\D | DT | 23 | 2 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-10-25 19:04 | 2017-10-27 05:38 | 42771.6511 | [6 empty] | 42772 | 32188 | 2.29 | 0 | 0 | 6.22 | 5867
DRE2 | BW\23\007\D | BW | 23 | 7 | D | 6 DL | 100 | 97.0596 | 97.0596 | 2017-10-26 15:14 | 2017-11-01 | 438870.0564 |  |  |  | 19141 | 438870 | 316660 |  |  | 0 | 21.67 | 0 | 5.17 | 5959.5
TS5500Exc | MW\26\011\A | MW | 26 | 11 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-10-26 16:19 | 2017-10-28 08:43 | 51661.0074 | [6 empty] | 51661 | 37865 | 1.79 | 0 | 0 | 11.08 | 5451
TS5500Shv | DT\23\003\D | DT | 23 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-10-27 05:38 | 2017-10-28 21:45 | 49657.2153 | [6 empty] | 49657 | 37431 | 2.34 | 0 | 0 | 6.1 | 5877
DRE1 | SC\30\011\D | SC | 30 | 11 | D | 6 DL | 100 | 0 | 54.5477 | 2017-10-27 22:00 | 2017-11-01 | 346869.063 |  |  |  | 26378 | 346869 | 237401 |  |  | 0 | 40 | 0 | 7.51 | 5752.87
TS5500Exc | SC\29\007\D | SC | 29 | 7 | D | 8 Coal Mining | 100 | 0 | 53.3 | 2017-10-28 08:43 | 2017-10-29 17:02 | 41294.9278 | [6 empty] | 41295 | 31285 | 2.61 | 0 | 0 | 5.94 | 5892
TS5500Shv | DT\23\004\D | DT | 23 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-10-28 21:45 | 2017-10-30 13:55 | 49705.4069 | [6 empty] | 49705 | 37527 | 2.35 | 0 | 0 | 5.95 | 5891
TS5500Exc | DT\23\001\D | DT | 23 | 1 | D | 8 Coal Mining | 10.4 | 0 | 10.4 | 2017-10-29 17:02 | 2017-10-30 00:42 | 9815.1803 | [6 empty] | 9815 | 7363 | 0.5 | 0 | 0 | 6.49 | 5843
TS5500Exc | DT\23\002\D | DT | 23 | 2 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2017-10-30 00:42 | 2017-10-31 11:16 | 44181.7055 | [6 empty] | 44182 | 33249 | 2.37 | 0 | 0 | 6.22 | 5867
TS5500Shv | DT\23\005\D | DT | 23 | 5 | D | 8 Coal Mining | 75.5 | 0 | 49.3 | 2017-10-30 13:55 | 2017-11-01 | 42176.0051 | [6 empty] | 42176 | 31867 | 2.32 | 0 | 0 | 5.93 | 5892
TS5500Exc | SC\29\008\D | SC | 29 | 8 | D | 8 Coal Mining | 85.2 | 0 | 20.8 | 2017-10-31 11:16 | 2017-11-01 | 16270.3105 | [6 empty] | 16270 | 12306 | 1.03 | 0 | 0 | 6.2 | 5869
PH4100A | SC\32\006\B | SC | 32 | 6 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-10-31 20:37 | 2017-10-31 20:37 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\31\007\B | SC | 31 | 7 | B | 1 Prestrip - Thick | 100 | 1.1273 | 1.1273 | 2017-10-31 20:37 | 2017-11-01 | 6309.911 | 6310 | [7 empty] | 0 | 0 | 0.51 | 10.87 | 5414.3
TS Fleet 5 | BW\26\007\B | BW | 26 | 7 | B | 1 Prestrip - Thick | 72.4809 | 0.40296 | 0.40296 | 2017-10-31 21:46 | 2017-11-01 | 4224.9577 | 4225 | [7 empty] | 0 | 0 | 0.26 | 10.84 | 5448.52
| EOP 46 : 2017\Oct | EOP 46 : 2017 | Oct | [6 empty] | 2017-11-01 | 2017-11-01 |  | 5687565 |  |  | 285597 | 5169535 | 3321149 | 1243687 | 921716 | 58.3 | 0 | 367.87 | 8.73 | 5637.6
TS Fleet 5 | BW\26\007\B | BW | 26 | 7 | B | 1 Prestrip - Thick | 72.4809 | 72.078 | 72.078 | 2017-11-01 | 2017-11-18 00:56 | 755732.6812 | 755733 | [7 empty] | 0 | 0 | 46.8 | 10.84 | 5448.52
DRE1 | SC\30\011\D | SC | 30 | 11 | D | 6 DL | 100 | 0 | 45.4523 | 2017-11-01 | 2017-11-04 10:44 | 289031.2547 |  |  |  | 21980 | 289031 | 197816 |  |  | 0 | 40 | 0 | 7.51 | 5752.87
PH4100A | SC\31\007\B | SC | 31 | 7 | B | 1 Prestrip - Thick | 100 | 98.8727 | 98.8727 | 2017-11-01 | 2017-11-13 21:25 | 553422.593 | 553423 | [7 empty] | 0 | 0 | 44.67 | 10.87 | 5414.3
DRE2 | BW\23\007\D | BW | 23 | 7 | D | 6 DL | 100 | 2.9404 | 2.9404 | 2017-11-01 | 2017-11-01 03:57 | 13295.4026 |  |  |  | 580 | 13295 | 9593 |  |  | 0 | 21.67 | 0 | 5.17 | 5959.5
PH4100XPC#1 | BW\26\011\B | BW | 26 | 11 | B | 1 Prestrip - Thick | 100 | 38.943 | 38.943 | 2017-11-01 | 2017-11-06 09:55 | 294093.1035 | 294093 | [7 empty] | 0 | 0 | 20.15 | 20.14 | 4662.35
TS5500Shv | DT\23\005\D | DT | 23 | 5 | D | 8 Coal Mining | 75.5 | 0 | 26.2 | 2017-11-01 | 2017-11-01 18:36 | 22357.1037 | [6 empty] | 22357 | 16893 | 1.23 | 0 | 0 | 5.93 | 5892
TS6060#1 | BW\26\006\B | BW | 26 | 6 | B | 1 Prestrip - Thick | 27.4476 | 0.9662 | 0.9662 | 2017-11-01 | 2017-11-01 08:56 | 9001.1944 | 9001 | [7 empty] | 0 | 0 | 0.57 | 10.6 | 5475.9
TS5500Exc | SC\29\008\D | SC | 29 | 8 | D | 8 Coal Mining | 85.2 | 0 | 64.4 | 2017-11-01 | 2017-11-02 16:36 | 50390.2634 | [6 empty] | 50390 | 38114 | 3.18 | 0 | 0 | 6.2 | 5869
DRE2 | BW\23\006\D | BW | 23 | 6 | D | 6 DL | 100 | 100 | 100 | 2017-11-01 03:57 | 2017-11-07 01:49 | 477245.4811 |  |  |  | 20814 | 477245 | 344349 |  |  | 0 | 22.8 | 0 | 5.43 | 5939.05
TS6060#1 | BW\26\006\B | BW | 26 | 6 | B | 1 Prestrip - Thick | 6.4229 | 6.4229 | 6.4229 | 2017-11-01 08:56 | 2017-11-03 20:25 | 59836.4686 | 59836 | [7 empty] | 0 | 0 | 3.8 | 10.6 | 5475.9
TS5500Shv | DT\27\004\A | DT | 27 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-11-01 18:36 | 2017-11-02 06:41 | 12765.9218 | 12766 | [7 empty] | 0 | 0 | 1.12 | 20.99 | 4619.9
TS5500Shv | DT\27\005\B | DT | 27 | 5 | B | 1 Prestrip - Thick | 0.53618 | 0.53618 | 0.53618 | 2017-11-02 06:41 | 2017-11-02 08:29 | 1900.8998 | 1901 | [7 empty] | 0 | 0 | 0.08 | 10.71 | 5352.56
TS5500Shv | DT\27\005\B | DT | 27 | 5 | B | 1 Prestrip - Thick | 99.4638 | 99.4638 | 99.4638 | 2017-11-02 08:29 | 2017-11-16 05:24 | 352625.1779 | 352625 | [7 empty] | 0 | 0 | 14.41 | 10.71 | 5352.56
TS5500Exc | MW\25\010\B | MW | 25 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-11-02 16:36 | 2017-11-05 10:23 | 57301.325 | 57301 | [7 empty] | 0 | 0 | 3.57 | 8.68 | 5675.22
TS6060#1 | BW\23\008\D | BW | 23 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-11-03 20:25 | 2017-11-07 03:43 | 105723.7328 | [6 empty] | 105724 | 80391 | 5.02 | 0 | 0 | 5.26 | 5952
DRE1 | SC\30\010\D | SC | 30 | 10 | D | 6 DL | 100 | 0 | 100 | 2017-11-04 10:44 | 2017-11-11 22:34 | 628196.2544 |  |  |  | 47772 | 628196 | 429944 |  |  | 0 | 40 | 0 | 7.27 | 5775.25
TS5500Exc | MW\25\011\B | MW | 25 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-11-05 10:23 | 2017-11-08 11:05 | 63335.5745 | 63336 | [7 empty] | 0 | 0 | 2.63 | 8.37 | 5689.16
PH4100XPC#1 | BW\26\010\A | BW | 26 | 10 | A | 1 Prestrip - Thick | 100 | 0 | 100 | 2017-11-06 09:55 | 2017-11-18 17:34 | 689088.0059 | 689088 | [7 empty] | 0 | 0 | 43.78 | 0 | 0
DRE2 | BW\23\005\D | BW | 23 | 5 | D | 6 DL | 100 | 100 | 100 | 2017-11-07 01:49 | 2017-11-13 00:24 | 479579.8691 |  |  |  | 20916 | 479580 | 346033 |  |  | 0 | 22.94 | 0 | 5.58 | 5924.76
TS6060#1 | BW\23\007\D | BW | 23 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-11-07 03:43 | 2017-11-10 09:46 | 104063.1589 | [6 empty] | 104063 | 79194 | 4.95 | 0 | 0 | 5.17 | 5960
TS5500Exc | SC\30\013\D | SC | 30 | 13 | D | 7 PostStrip | 100 | 0 | 100 | 2017-11-08 11:05 | 2017-11-12 11:02 | 83603.6064 |  |  | 83604 | [5 empty] | 0 | 0 | 0 | 7.53 | 5751.26
TS6060#1 | BW\23\009\D | BW | 23 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-11-10 09:46 | 2017-11-13 20:57 | 110887.5079 | [6 empty] | 110888 | 84044 | 5.25 | 0 | 0 | 5.59 | 5925
DRE1 | SC\30\009\D | SC | 30 | 9 | D | 6 DL | 100 | 0 | 100 | 2017-11-11 22:34 | 2017-11-20 02:57 | 685985.3029 |  |  |  | 47223 | 685985 | 425009 |  |  | 0 | 40 | 0 | 6.81 | 5815.67
TS5500Exc | SC\29\008\D | SC | 29 | 8 | D | 8 Coal Mining | 14.8 | 0 | 14.8 | 2017-11-12 11:02 | 2017-11-12 20:24 | 11607.6144 | [6 empty] | 11608 | 8780 | 0.73 | 0 | 0 | 6.2 | 5869
TS5500Exc | SC\30\013\D | SC | 30 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-11-12 20:24 | 2017-11-16 02:30 | 96916.1786 | [6 empty] | 96916 | 72432 | 4.65 | 0 | 0 | 7.53 | 5751
DRE2 | BW\23\004\D | BW | 23 | 4 | D | 6 DL | 100 | 100 | 100 | 2017-11-13 00:24 | 2017-11-18 23:31 | 481438.011 |  |  |  | 20997 | 481438 | 347374 |  |  | 0 | 23.03 | 0 | 5.87 | 5898.18
TS6060#1 | BW\23\006\D | BW | 23 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-11-13 20:57 | 2017-11-17 11:31 | 115406.8576 | [6 empty] | 115407 | 87605 | 5.47 | 0 | 0 | 5.43 | 5939
PH4100A | SC\32\007\D | SC | 32 | 7 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-11-13 21:25 | 2017-11-13 21:25 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\33\005\B | SC | 33 | 5 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2017-11-13 21:25 | 2017-11-13 21:25 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\33\010\D | SC | 33 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-11-13 21:25 | 2017-11-17 14:27 | 156138.0579 | 156138 | [7 empty] | 0 | 0 | 12.76 | 7.56 | 5749.74
TS5500Exc | SC\30\012\D | SC | 30 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-11-16 02:30 | 2017-11-18 12:55 | 72472.9593 | [6 empty] | 72473 | 54076 | 4.51 | 0 | 0 | 7.58 | 5746
TS5500Shv | MW\25\010\B | MW | 25 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-11-16 05:24 | 2017-11-18 08:33 | 61432.6663 | [6 empty] | 61433 | 45552 | 2.84 | 0 | 0 | 8.68 | 5675
TS6060#1 | BW\23\010\D | BW | 23 | 10 | D | 8 Coal Mining | 66.9 | 0 | 66.9 | 2017-11-17 11:31 | 2017-11-19 15:53 | 69834.4958 | [6 empty] | 69834 | 52679 | 3.29 | 0 | 0 | 6.14 | 5874
PH4100A | SC\34\010\D | SC | 34 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-11-17 14:27 | 2017-11-20 20:22 | 134733.3469 | 134733 | [7 empty] | 0 | 0 | 10.89 | 7.64 | 5743.31
TS Fleet 5 | BW\26\007\B | BW | 26 | 7 | B | 1 Prestrip - Thick | 27.5191 | 27.5191 | 27.5191 | 2017-11-18 00:56 | 2017-11-24 13:04 | 288535.5095 | 288536 | [7 empty] | 0 | 0 | 17.87 | 10.84 | 5448.52
TS5500Shv | MW\25\011\B | MW | 25 | 11 | B | 8 Coal Mining | 51.9 | 0 | 51.9 | 2017-11-18 08:33 | 2017-11-20 00:43 | 48252.087 | [6 empty] | 48252 | 35968 | 1.51 | 0 | 0 | 8.37 | 5689
TS5500Exc | SC\31\004\B | SC | 31 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-11-18 12:55 | 2017-11-20 05:18 | 50109.4785 | [6 empty] | 50109 | 37032 | 3.29 | 0 | 0 | 9.17 | 5560
PH4100XPC#1 | BW\26\009\B | BW | 26 | 9 | B | 1 Prestrip - Thick | 100 | 76.62 | 76.62 | 2017-11-18 17:34 | 2017-12-01 | 662830.4341 | 662830 | [7 empty] | 0 | 0 | 43.59 | 12.89 | 5265.16
DRE2 | BW\23\003\D | BW | 23 | 3 | D | 6 DL | 100 | 100 | 100 | 2017-11-18 23:31 | 2017-11-24 20:56 | 475693.5761 |  |  |  | 20747 | 475694 | 343229 |  |  | 0 | 22.74 | 0 | 6.51 | 5842.35
TS6060#1 | BW\23\005\D | BW | 23 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-11-19 15:53 | 2017-11-23 02:49 | 110549.6392 | [6 empty] | 110550 | 83654 | 5.23 | 0 | 0 | 5.58 | 5925
TS5500Shv | MW\26\003\B | MW | 26 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-11-20 00:43 | 2017-11-22 05:27 | 63330.2241 | [6 empty] | 63330 | 47319 | 2.96 | 0 | 0 | 8.22 | 5635
DRE1 | SC\30\004\D | SC | 30 | 4 | D | 6 DL | 100 | 0 | 84.1207 | 2017-11-20 02:57 | 2017-12-01 | 911837.188 |  |  |  | 51213 | 911837 | 396900 |  |  | 0 | 40 | 0 | 6.22 | 5867.64
TS5500Exc | SC\31\005\B | SC | 31 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-11-20 05:18 | 2017-11-21 20:50 | 49061.668 | [6 empty] | 49062 | 36210 | 3.01 | 0 | 0 | 9.33 | 5545
PH4100A | SC\31\004\D | SC | 31 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-11-20 20:22 | 2017-11-23 04:57 | 96819.9456 | 96820 | [7 empty] | 0 | 0 | 12.55 | 6.18 | 5871.8
TS5500Exc | MW\25\011\B | MW | 25 | 11 | B | 8 Coal Mining | 48.1 | 0 | 48.1 | 2017-11-21 20:50 | 2017-11-23 08:51 | 44692.0907 | [6 empty] | 44692 | 33314 | 1.39 | 0 | 0 | 8.37 | 5689
TS5500Shv | MW\26\004\B | MW | 26 | 4 | B | 8 Coal Mining | 56.7 | 0 | 56.7 | 2017-11-22 05:27 | 2017-11-23 10:41 | 35124.1869 | [6 empty] | 35124 | 26029 | 1.64 | 0 | 0 | 9.24 | 5569
TS6060#1 | BW\26\005\X1 | BW | 26 | 5 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2017-11-23 02:49 | 2017-11-23 17:59 | 20236.819 | [6 empty] | 20237 | 14908 | 0.93 | 0 | 0 | 10.97 | 5430
PH4100A | SC\31\005\D | SC | 31 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-11-23 04:57 | 2017-11-27 02:20 | 159789.2379 | 159789 | [7 empty] | 0 | 0 | 13.31 | 6.12 | 5876.68
TS5500Exc | SC\30\011\D | SC | 30 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-11-23 08:51 | 2017-11-25 21:13 | 74904.1275 | [6 empty] | 74904 | 55892 | 4.66 | 0 | 0 | 7.51 | 5753
TS5500Shv | MW\26\005\B | MW | 26 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-11-23 10:41 | 2017-11-24 12:02 | 30441.8181 | [6 empty] | 30442 | 22540 | 1.4 | 0 | 0 | 9.11 | 5635
TS6060#1 | BW\26\006\B | BW | 26 | 6 | B | 8 Coal Mining | 78.9 | 0 | 78.9 | 2017-11-23 17:59 | 2017-11-25 17:08 | 62848.1899 | [6 empty] | 62848 | 45903 | 2.88 | 0 | 0 | 10.6 | 5476
TS5500Shv | DT\23\005\D | DT | 23 | 5 | D | 8 Coal Mining | 12.1 | 0 | 12.1 | 2017-11-24 12:02 | 2017-11-24 20:36 | 10299.8207 | [6 empty] | 10300 | 7782 | 0.57 | 0 | 0 | 5.93 | 5892
TS Fleet 5 | BW\26\005\X2 | BW | 26 | 5 | X2 | 1 Prestrip - Thick | 55.5337 | 0 | 55.5337 | 2017-11-24 13:04 | 2017-11-26 14:53 | 92044.5453 | 92045 | [7 empty] | 0 | 0 | 5.72 | 0 | 0
TS5500Shv | DT\23\006\D | DT | 23 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2017-11-24 20:36 | 2017-11-25 18:53 | 26775.3139 | [6 empty] | 26775 | 20230 | 2.28 | 0 | 0 | 5.84 | 5899
DRE2 | BW\23\002\D | BW | 23 | 2 | D | 6 DL | 100 | 77.5277 | 77.5277 | 2017-11-24 20:56 | 2017-12-01 | 494647.6601 |  |  |  | 18934 | 494648 | 236782 |  |  | 0 | 21.72 | 0 | 6.58 | 5836.42
TS6060#1 | BW\26\005\X2 | BW | 26 | 5 | X2 | 1 Prestrip - Thick | 44.4663 | 0 | 44.4663 | 2017-11-25 17:08 | 2017-11-28 17:39 | 73700.9307 | 73701 | [7 empty] | 0 | 0 | 4.58 | 0 | 0
TS5500Shv | DT\23\007\D | DT | 23 | 7 | D | 8 Coal Mining | 30.3 | 0 | 30.3 | 2017-11-25 18:53 | 2017-11-26 16:40 | 26163.9979 | [6 empty] | 26164 | 19815 | 1.38 | 0 | 0 | 5.81 | 5902
TS5500Exc | MW\26\004\B | MW | 26 | 4 | B | 8 Coal Mining | 43.3 | 0 | 43.3 | 2017-11-25 21:13 | 2017-11-26 18:49 | 26796.0333 | [6 empty] | 26796 | 19857 | 1.25 | 0 | 0 | 9.24 | 5569
TS Fleet 5 | BW\26\008\B | BW | 26 | 8 | B | 1 Prestrip - Thick | 15.3368 | 15.3368 | 15.3368 | 2017-11-26 14:53 | 2017-11-30 00:37 | 151042.7657 | 151043 | [7 empty] | 0 | 0 | 9.78 | 11.29 | 5403.92
TS5500Shv | DT\27\006\B | DT | 27 | 6 | B | 1 Prestrip - Thick | 20.7338 | 15.7738 | 15.7738 | 2017-11-26 16:40 | 2017-12-01 | 109564.2844 | 109564 | [7 empty] | 0 | 0 | 6.56 | 11.33 | 5370.04
TS5500Exc | MW\26\005\B | MW | 26 | 5 | B | 8 Coal Mining | 50.8 | 0 | 38.8 | 2017-11-26 18:49 | 2017-11-27 14:11 | 24021.9666 | [6 empty] | 24022 | 17787 | 1.11 | 0 | 0 | 9.11 | 5635
PH4100A | SC\32\018\D | SC | 32 | 18 | D | 1 Prestrip - Thick | 100 | 65.0143 | 65.0143 | 2017-11-27 02:20 | 2017-12-01 | 157479.7607 | 157480 | [7 empty] | 0 | 0 | 13.37 | 7.31 | 5768.95
TS5500Exc | MW\26\007\B | MW | 26 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-11-27 14:11 | 2017-11-30 20:24 | 68152.2149 | 68152 | [7 empty] | 0 | 0 | 4.26 | 9.92 | 5531.67
TS6060#1 | BW\26\005\B | BW | 26 | 5 | B | 1 Prestrip - Thick | 13.3044 | 11.4238 | 11.4238 | 2017-11-28 17:39 | 2017-12-01 | 55241.0758 | 55241 | [7 empty] | 0 | 0 | 3.45 | 10.77 | 5470.4
TS Fleet 5 | BW\26\005\B | BW | 26 | 5 | B | 1 Prestrip - Thick | 71.7087 | 8.9346 | 8.9346 | 2017-11-30 00:37 | 2017-12-01 | 43204.4983 | 43204 | [7 empty] | 0 | 0 | 2.7 | 10.77 | 5470.4
TS5500Exc | MW\26\008\B | MW | 26 | 8 | B | 1 Prestrip - Thick | 51.7339 | 3.2225 | 3.2225 | 2017-11-30 20:24 | 2017-12-01 | 3124.7143 | 3125 | [7 empty] | 0 | 0 | 0.2 | 11.32 | 5358.37
| EOP 47 : 2017\Nov | EOP 47 : 2017 | Nov | [6 empty] | 2017-12-01 | 2017-12-01 |  | 5101504 |  | 83604 | 271175 | 4936950 | 3077030 | 1524700 | 1143999 | 76.6 | 0 | 343.16 | 7.67 | 5736.38
TS Fleet 5 | BW\26\005\B | BW | 26 | 5 | B | 1 Prestrip - Thick | 71.7087 | 58.6142 | 58.6142 | 2017-12-01 | 2017-12-08 19:27 | 283435.9689 | 283436 | [7 empty] | 0 | 0 | 17.71 | 10.77 | 5470.4
DRE1 | SC\30\004\D | SC | 30 | 4 | D | 6 DL | 100 | 0 | 15.8793 | 2017-12-01 | 2017-12-03 08:51 | 172125.2476 |  |  |  | 9667 | 172125 | 74922 |  |  | 0 | 40 | 0 | 6.22 | 5867.64
PH4100A | SC\32\018\D | SC | 32 | 18 | D | 1 Prestrip - Thick | 100 | 34.9857 | 34.9857 | 2017-12-01 | 2017-12-03 13:00 | 84743.5799 | 84744 | [7 empty] | 0 | 0 | 7.19 | 7.31 | 5768.95
DRE2 | BW\23\002\D | BW | 23 | 2 | D | 6 DL | 100 | 22.4723 | 22.4723 | 2017-12-01 | 2017-12-03 01:10 | 143379.0142 |  |  |  | 5488 | 143379 | 68634 |  |  | 0 | 21.72 | 0 | 6.58 | 5836.42
PH4100XPC#1 | BW\26\009\B | BW | 26 | 9 | B | 1 Prestrip - Thick | 100 | 23.38 | 23.38 | 2017-12-01 | 2017-12-05 12:45 | 202257.8893 | 202258 | [7 empty] | 0 | 0 | 13.3 | 12.89 | 5265.16
TS5500Shv | DT\27\006\B | DT | 27 | 6 | B | 1 Prestrip - Thick | 20.7338 | 4.9601 | 4.9601 | 2017-12-01 | 2017-12-02 15:42 | 34452.4245 | 34452 | [7 empty] | 0 | 0 | 2.06 | 11.33 | 5370.04
TS6060#1 | BW\26\005\B | BW | 26 | 5 | B | 1 Prestrip - Thick | 13.3044 | 1.8806 | 1.8806 | 2017-12-01 | 2017-12-01 10:56 | 9093.7367 | 9094 | [7 empty] | 0 | 0 | 0.57 | 10.77 | 5470.4
TS5500Exc | MW\26\008\B | MW | 26 | 8 | B | 1 Prestrip - Thick | 51.7339 | 48.5114 | 48.5114 | 2017-12-01 | 2017-12-03 17:59 | 47039.422 | 47039 | [7 empty] | 0 | 0 | 2.94 | 11.32 | 5358.37
TS6060#1 | BW\26\005\B | BW | 26 | 5 | B | 1 Prestrip - Thick | 19.1468 | 19.1468 | 19.1468 | 2017-12-01 10:56 | 2017-12-06 02:16 | 92586.6434 | 92587 | [7 empty] | 0 | 0 | 5.79 | 10.77 | 5470.4
TS5500Shv | DT\27\006\B | DT | 27 | 6 | B | 1 Prestrip - Thick | 79.2662 | 79.2662 | 79.2662 | 2017-12-02 15:42 | 2017-12-29 02:17 | 550580.9149 | 550581 | [7 empty] | 0 | 0 | 32.94 | 11.33 | 5370.04
DRE2 | MW\24\003\D | MW | 24 | 3 | D | 6 DL | 100 | 100 | 100 | 2017-12-03 01:10 | 2017-12-10 19:17 | 542534.8087 |  |  |  | 32400 | 542535 | 382990 |  |  | 0 | 25.97 | 0 | 6.19 | 5868.44
DRE1 | SC\30\005\D | SC | 30 | 5 | D | 6 DL | 100 | 0 | 100 | 2017-12-03 08:51 | 2017-12-12 02:11 | 633724.1297 |  |  |  | 48192 | 633724 | 433728 |  |  | 0 | 40 | 0 | 6.11 | 5877.84
PH4100A | SC\33\018\D | SC | 33 | 18 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-12-03 13:00 | 2017-12-09 21:07 | 210462.8224 | 210463 | [7 empty] | 0 | 0 | 17.98 | 7.32 | 5768.66
TS5500Exc | MW\26\005\B | MW | 26 | 5 | B | 8 Coal Mining | 50.8 | 0 | 12 | 2017-12-03 17:59 | 2017-12-04 01:18 | 7423.428 | [6 empty] | 7423 | 5497 | 0.34 | 0 | 0 | 9.11 | 5635
TS5500Exc | MW\26\008\B | MW | 26 | 8 | B | 1 Prestrip - Thick | 48.2661 | 48.2661 | 48.2661 | 2017-12-04 01:18 | 2017-12-06 18:57 | 46801.4995 | 46801 | [7 empty] | 0 | 0 | 2.93 | 11.32 | 5358.37
PH4100XPC#1 | BW\26\008\B | BW | 26 | 8 | B | 1 Prestrip - Thick | 100 | 84.6632 | 84.6632 | 2017-12-05 12:45 | 2017-12-24 04:32 | 833795.4522 | 833795 | [7 empty] | 0 | 0 | 53.98 | 11.29 | 5403.92
TS6060#1 | BW\23\003\D | BW | 23 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-12-06 02:16 | 2017-12-10 03:48 | 106392.3004 | [6 empty] | 106392 | 79809 | 4.99 | 0 | 0 | 6.51 | 5842
TS5500Exc | SC\30\009\D | SC | 30 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-12-06 18:57 | 2017-12-10 00:41 | 78910.2581 | [6 empty] | 78910 | 59353 | 4.95 | 0 | 0 | 6.81 | 5816
TS Fleet 5 | BW\26\010\B | BW | 26 | 10 | B | 1 Prestrip - Thick | 50.0673 | 50.0673 | 50.0673 | 2017-12-08 19:27 | 2017-12-09 18:49 | 35320.0216 | 35320 | [7 empty] | 0 | 0 | 2.22 | 15.46 | 5042.19
TS Fleet 5 | BW\27\004\X2 | BW | 27 | 4 | X2 | 1 Prestrip - Thick | 58.6814 | 0 | 58.6814 | 2017-12-09 18:49 | 2017-12-22 11:54 | 461301.1495 | 461301 | [7 empty] | 0 | 0 | 22.78 | 0 | 0
PH4100A | SC\32\017\D | SC | 32 | 17 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-12-09 21:07 | 2017-12-15 20:12 | 198417.3629 | 198417 | [7 empty] | 0 | 0 | 16.98 | 7.36 | 5764.71
TS5500Exc | SC\30\010\D | SC | 30 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-12-10 00:41 | 2017-12-13 05:04 | 77535.6173 | [6 empty] | 77536 | 57996 | 4.84 | 0 | 0 | 7.27 | 5775
TS6060#1 | BW\23\004\D | BW | 23 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2017-12-10 03:48 | 2017-12-14 02:17 | 103062.3696 | [6 empty] | 103062 | 77745 | 4.86 | 0 | 0 | 5.87 | 5898
DRE2 | MW\24\004\D | MW | 24 | 4 | D | 6 DL | 100 | 0 | 100 | 2017-12-10 19:17 | 2017-12-19 05:12 | 588675.3027 |  |  |  | 35156 | 588675 | 415562 |  |  | 0 | 28.24 | 0 | 6.45 | 5844.82
DRE1 | SC\30\006\D | SC | 30 | 6 | D | 6 DL | 100 | 0 | 100 | 2017-12-12 02:11 | 2017-12-20 18:40 | 631186.2529 |  |  |  | 47999 | 631186 | 431991 |  |  | 0 | 40 | 0 | 6.04 | 5883.63
TS5500Exc | SC\31\006\B | SC | 31 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-12-13 05:04 | 2017-12-14 17:14 | 36732.469 | [6 empty] | 36732 | 27027 | 2.25 | 0 | 0 | 9.86 | 5499
TS6060#1 | BW\26\005\B | BW | 26 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-12-14 02:17 | 2017-12-16 16:08 | 67472.7738 | [6 empty] | 67473 | 49231 | 3.08 | 0 | 0 | 10.77 | 5470
TS5500Exc | MW\26\007\B | MW | 26 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-12-14 17:14 | 2017-12-17 07:04 | 62764.8865 | [6 empty] | 62765 | 46175 | 2.89 | 0 | 0 | 9.92 | 5532
PH4100A | SC\31\006\D | SC | 31 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-12-15 20:12 | 2017-12-20 19:03 | 168003.0715 | 168003 | [7 empty] | 0 | 0 | 13.99 | 6.1 | 5878.32
TS6060#1 | BW\26\006\B | BW | 26 | 6 | B | 8 Coal Mining | 21.1 | 0 | 21.1 | 2017-12-16 16:08 | 2017-12-17 07:34 | 16835.6145 | [6 empty] | 16836 | 12296 | 0.77 | 0 | 0 | 10.6 | 5476
TS5500Exc | MW\26\008\B | MW | 26 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-12-17 07:04 | 2017-12-19 21:54 | 63796.596 | [6 empty] | 63797 | 46431 | 2.9 | 0 | 0 | 11.32 | 5358
TS6060#1 | BW\26\007\B | BW | 26 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-12-17 07:34 | 2017-12-20 14:47 | 86407.42 | [6 empty] | 86407 | 63041 | 3.92 | 0 | 0 | 10.84 | 5449
DRE2 | MW\24\005\D | MW | 24 | 5 | D | 6 DL | 100 | 0 | 100 | 2017-12-19 05:12 | 2017-12-27 09:50 | 573221.7827 |  |  |  | 34233 | 573222 | 404653 |  |  | 0 | 27.46 | 0 | 6.83 | 5810.75
TS5500Exc | MW\24\004\D | MW | 24 | 4 | D | 8 Coal Mining | 100 | 0 | 57.6 | 2017-12-19 21:54 | 2017-12-22 03:25 | 54327.5935 | [6 empty] | 54328 | 41044 | 2.57 | 0 | 0 | 6.45 | 5845
TS6060#1 | MW\24\004\D | MW | 24 | 4 | D | 8 Coal Mining | 100 | 0 | 42.4 | 2017-12-20 14:47 | 2017-12-22 03:25 | 39961.3433 | [6 empty] | 39961 | 30190 | 1.89 | 0 | 0 | 6.45 | 5845
DRE1 | SC\30\007\D | SC | 30 | 7 | D | 6 DL | 100 | 0 | 100 | 2017-12-20 18:40 | 2017-12-29 11:01 | 630748.8511 |  |  |  | 47966 | 630749 | 431691 |  |  | 0 | 40 | 0 | 6.08 | 5879.67
PH4100A | SC\33\017\D | SC | 33 | 17 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-12-20 19:03 | 2017-12-27 10:51 | 220788.5258 | 220789 | [7 empty] | 0 | 0 | 18.82 | 7.34 | 5767.47
TS6060#1 | BW\26\009\B | BW | 26 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-12-22 03:25 | 2017-12-25 08:48 | 84397.7273 | [6 empty] | 84398 | 61043 | 3.81 | 0 | 0 | 12.89 | 5265
TS5500Exc | SC\30\004\D | SC | 30 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2017-12-22 03:25 | 2017-12-26 14:11 | 76100.3827 |  |  | 76100 | [5 empty] | 0 | 0 | 0 | 6.22 | 5867.64
TS Fleet 5 | BW\27\004\X2 | BW | 27 | 4 | X2 | 1 Prestrip - Thick | 41.3186 | 0 | 41.3186 | 2017-12-22 11:54 | 2017-12-31 10:43 | 324809.5983 | 324810 | [7 empty] | 0 | 0 | 16.04 | 0 | 0
PH4100XPC#1 | BW\26\010\B | BW | 26 | 10 | B | 1 Prestrip - Thick | 100 | 49.9327 | 49.9327 | 2017-12-24 04:32 | 2017-12-24 23:39 | 35225.1094 | 35225 | [7 empty] | 0 | 0 | 2.22 | 15.46 | 5042.19
PH4100XPC#1 | MW\26\011\B | MW | 26 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2017-12-24 23:39 | 2017-12-26 06:19 | 56527.0151 | 56527 | [7 empty] | 0 | 0 | 2.69 | 8.52 | 5680.26
TS6060#1 | BW\26\008\B | BW | 26 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-12-25 08:48 | 2017-12-28 14:28 | 84730.9258 | [6 empty] | 84731 | 61745 | 3.84 | 0 | 0 | 11.29 | 5404
PH4100XPC#1 | MW\27\011\X | MW | 27 | 11 | X | 1 Prestrip - Thick | 100 | 34.5656 | 34.5656 | 2017-12-26 06:19 | 2018-01-01 | 225723.2269 | 225723 | [7 empty] | 0 | 0 | 11.09 | 12.67 | 5150.07
TS5500Exc | MW\26\011\B | MW | 26 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-12-26 14:11 | 2017-12-29 20:45 | 79762.7394 | [6 empty] | 79763 | 59405 | 2.85 | 0 | 0 | 8.52 | 5680
DRE2 | MW\24\006\D | MW | 24 | 6 | D | 6 DL | 100 | 0 | 51.9437 | 2017-12-27 09:50 | 2018-01-01 | 321135.0916 |  |  |  | 19178 | 321135 | 226698 |  |  | 0 | 29.59 | 0 | 7.18 | 5781.35
PH4100A | SC\32\016\D | SC | 32 | 16 | D | 1 Prestrip - Thick | 100 | 77.8359 | 77.8359 | 2017-12-27 10:51 | 2018-01-01 | 151164.0317 | 151164 | [7 empty] | 0 | 0 | 12.95 | 7.39 | 5763.45
TS6060#1 | BW\26\010\B | BW | 26 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2017-12-28 14:28 | 2017-12-31 21:24 | 86091.8141 | [6 empty] | 86092 | 61545 | 3.86 | 0 | 0 | 15.46 | 5042
TS5500Shv | MW\24\003\D | MW | 24 | 3 | D | 8 Coal Mining | 100 | 0 | 71 | 2017-12-29 02:17 | 2018-01-01 | 68513.8997 | [6 empty] | 68514 | 51890 | 3.24 | 0 | 0 | 6.19 | 5868
DRE1 | SC\30\008\D | SC | 30 | 8 | D | 6 DL | 100 | 0 | 29.2682 | 2017-12-29 11:01 | 2018-01-01 | 184582.5187 |  |  |  | 14037 | 184583 | 126330 |  |  | 0 | 40 | 0 | 6.36 | 5856.09
TS5500Exc | SC\30\004\D | SC | 30 | 4 | D | 8 Coal Mining | 100 | 0 | 53.5 | 2017-12-29 20:45 | 2018-01-01 | 52017.5973 | [6 empty] | 52018 | 39251 | 2.63 | 0 | 0 | 6.22 | 5868
TS Fleet 5 | BW\27\004\B | BW | 27 | 4 | B | 1 Prestrip - Thick | 100 | 3.6934 | 3.6934 | 2017-12-31 10:43 | 2018-01-01 | 20061.2617 | 20061 | [7 empty] | 0 | 0 | 1.03 | 10.43 | 5487.09
TS6060#1 | BW\26\011\B | BW | 26 | 11 | B | 8 Coal Mining | 56.5 | 0 | 2.9 | 2017-12-31 21:24 | 2018-01-01 | 2829.945 | [6 empty] | 2830 | 1972 | 0.12 | 0 | 0 | 20.14 | 4662
| EOP 48 : 2017\Dec | EOP 48 : 2017 | Dec | [6 empty] | 2018-01-01 | 2018-01-01 |  | 4292591 |  | 76100 | 294317 | 4421313 | 2997199 | 1259967 | 932686 | 60.59 | 0 | 278.18 | 8.48 | 5661.67
TS Fleet 5 | BW\27\004\B | BW | 27 | 4 | B | 1 Prestrip - Thick | 100 | 96.3066 | 96.3066 | 2018-01-01 | 2018-01-13 13:19 | 523103.2089 | 523103 | [7 empty] | 0 | 0 | 26.76 | 10.43 | 5487.09
DRE1 | SC\30\008\D | SC | 30 | 8 | D | 6 DL | 100 | 0 | 70.7318 | 2018-01-01 | 2018-01-06 09:25 | 446075.7098 |  |  |  | 33922 | 446076 | 305299 |  |  | 0 | 40 | 0 | 6.36 | 5856.09
PH4100A | SC\32\016\D | SC | 32 | 16 | D | 1 Prestrip - Thick | 100 | 22.1641 | 22.1641 | 2018-01-01 | 2018-01-02 03:15 | 43044.489 | 43044 | [7 empty] | 0 | 0 | 3.69 | 7.39 | 5763.45
DRE2 | MW\24\006\D | MW | 24 | 6 | D | 6 DL | 100 | 0 | 48.0563 | 2018-01-01 | 2018-01-04 17:31 | 297101.5248 |  |  |  | 17743 | 297102 | 209732 |  |  | 0 | 29.59 | 0 | 7.18 | 5781.35
PH4100XPC#1 | MW\27\011\X | MW | 27 | 11 | X | 1 Prestrip - Thick | 100 | 65.4344 | 65.4344 | 2018-01-01 | 2018-01-10 12:33 | 427305.5654 | 427306 | [7 empty] | 0 | 0 | 20.99 | 12.67 | 5150.07
TS5500Shv | MW\24\003\D | MW | 24 | 3 | D | 8 Coal Mining | 100 | 0 | 29 | 2018-01-01 | 2018-01-02 00:51 | 28043.9163 | [6 empty] | 28044 | 21239 | 1.33 | 0 | 0 | 6.19 | 5868
TS6060#1 | BW\26\011\B | BW | 26 | 11 | B | 8 Coal Mining | 56.5 | 0 | 53.5 | 2018-01-01 | 2018-01-02 17:25 | 51889.4914 | [6 empty] | 51889 | 36160 | 2.27 | 0 | 0 | 20.14 | 4662
TS5500Exc | SC\30\004\D | SC | 30 | 4 | D | 8 Coal Mining | 100 | 0 | 46.5 | 2018-01-01 | 2018-01-02 14:51 | 45292.5799 | [6 empty] | 45293 | 34177 | 2.29 | 0 | 0 | 6.22 | 5868
TS5500Shv | MW\24\005\D | MW | 24 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-01-02 00:51 | 2018-01-03 17:07 | 45449.8682 | [6 empty] | 45450 | 34088 | 2.13 | 0 | 0 | 6.83 | 5811
PH4100A | SC\33\016\D | SC | 33 | 16 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-01-02 03:15 | 2018-01-08 22:22 | 256112.4197 | 256112 | [7 empty] | 0 | 0 | 20.11 | 7.23 | 5776.84
TS5500Exc | SC\30\005\D | SC | 30 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-01-02 14:51 | 2018-01-05 11:19 | 79795.8884 | [6 empty] | 79796 | 60116 | 5.01 | 0 | 0 | 6.11 | 5878
TS6060#1 | BW\26\011\B | BW | 26 | 11 | B | 8 Coal Mining | 43.5 | 0 | 43.5 | 2018-01-02 17:25 | 2018-01-04 03:06 | 42183.2147 | [6 empty] | 42183 | 29396 | 1.84 | 0 | 0 | 20.14 | 4662
TS5500Shv | DT\23\007\D | DT | 23 | 7 | D | 8 Coal Mining | 18.9 | 0 | 18.9 | 2018-01-03 17:07 | 2018-01-04 07:33 | 16281.189 | [6 empty] | 16281 | 12331 | 0.86 | 0 | 0 | 5.81 | 5902
TS6060#1 | BW\23\002\D | BW | 23 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2018-01-04 03:06 | 2018-01-08 10:24 | 98623.0751 |  |  | 98623 | [5 empty] | 0 | 0 | 0 | 6.58 | 5836.42
TS5500Shv | DT\24\001\B | DT | 24 | 1 | B | 8 Coal Mining | 20 | 0 | 20 | 2018-01-04 07:33 | 2018-01-04 21:45 | 16029.9061 | [6 empty] | 16030 | 11683 | 0.64 | 0 | 0 | 11.34 | 5359
DRE2 | MW\24\007\D | MW | 24 | 7 | D | 6 DL | 100 | 0 | 100 | 2018-01-04 17:31 | 2018-01-12 12:56 | 622014.7052 |  |  |  | 27128 | 622015 | 448805 |  |  | 0 | 29.72 | 0 | 6.85 | 5810.54
TS5500Shv | DT\24\002\A2 | DT | 24 | 2 | A2 | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-01-04 21:45 | 2018-01-05 09:47 | 13573.4994 | [6 empty] | 13573 | 9569 | 0.54 | 0 | 0 | 17.62 | 4939
TS5500Shv | DT\24\004\B | DT | 24 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-01-05 09:47 | 2018-01-06 04:32 | 21147.4861 | [6 empty] | 21147 | 15394 | 0.96 | 0 | 0 | 10.56 | 5337
TS5500Exc | SC\31\007\B | SC | 31 | 7 | B | 8 Coal Mining | 15.1 | 0 | 15.1 | 2018-01-05 11:19 | 2018-01-05 14:27 | 3658.0935 | [6 empty] | 3658 | 2677 | 0.22 | 0 | 0 | 10.87 | 5414
TS5500Exc | SC\31\007\B | SC | 31 | 7 | B | 8 Coal Mining | 84.9 | 0 | 84.9 | 2018-01-05 14:27 | 2018-01-06 08:04 | 20528.2554 | [6 empty] | 20528 | 15020 | 1.26 | 0 | 0 | 10.87 | 5414
TS5500Shv | DT\24\005\B | DT | 24 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-01-06 04:32 | 2018-01-06 15:03 | 11878.6941 | [6 empty] | 11879 | 8649 | 0.5 | 0 | 0 | 11.48 | 5316
TS5500Exc | MW\24\005\D | MW | 24 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-01-06 08:04 | 2018-01-08 00:20 | 46948.2156 | [6 empty] | 46948 | 35212 | 2.2 | 0 | 0 | 6.83 | 5811
DRE1 | SC\31\014\D | SC | 31 | 14 | D | 6 DL | 100 | 0 | 100 | 2018-01-06 09:25 | 2018-01-11 06:19 | 402867.0344 |  |  |  | 17477 | 402867 | 197400 |  |  | 0 | 31.73 | 0 | 7.46 | 5756.67
TS5500Shv | MW\24\006\D | MW | 24 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-01-06 15:03 | 2018-01-08 08:53 | 47198.6753 | [6 empty] | 47199 | 35262 | 2.2 | 0 | 0 | 7.18 | 5781
TS5500Exc | SC\30\006\D | SC | 30 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-01-08 00:20 | 2018-01-10 20:40 | 79643.6297 | [6 empty] | 79644 | 60097 | 5.01 | 0 | 0 | 6.04 | 5884
TS5500Shv | DT\24\006\A | DT | 24 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-01-08 08:53 | 2018-01-09 10:03 | 28404.4341 | [6 empty] | 28404 | 20799 | 1.85 | 0 | 0 | 10.94 | 5368
TS6060#1 | BW\23\002\D | BW | 23 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-01-08 10:24 | 2018-01-12 18:35 | 130484.0038 | [6 empty] | 130484 | 97726 | 4.98 | 0 | 0 | 6.58 | 5836
PH4100A | SC\31\007\D | SC | 31 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-01-08 22:22 | 2018-01-13 09:50 | 173233.1212 | 173233 | [7 empty] | 0 | 0 | 14.47 | 6.22 | 5868.2
TS5500Shv | DT\24\007\A | DT | 24 | 7 | A | 8 Coal Mining | 35.7 | 0 | 35.7 | 2018-01-09 10:03 | 2018-01-10 12:31 | 29853.9772 | [6 empty] | 29854 | 21977 | 1.36 | 0 | 0 | 10.14 | 5425
TS5500Shv | DT\24\006\B | DT | 24 | 6 | B | 1 Prestrip - Thick | 100 | 32.1232 | 32.1232 | 2018-01-10 12:31 | 2018-01-11 00:54 | 12285.3817 | 12285 | [7 empty] | 0 | 0 | 1.1 | 8.5 | 5572.38
PH4100XPC#1 | DT\24\006\B | DT | 24 | 6 | B | 1 Prestrip - Thick | 100 | 67.8768 | 67.8768 | 2018-01-10 12:33 | 2018-01-11 00:54 | 25959.226 | 25959 | [7 empty] | 0 | 0 | 2.33 | 8.5 | 5572.38
TS5500Exc | MW\27\011\X | MW | 27 | 11 | X | 8 Coal Mining | 24.3 | 0 | 24.3 | 2018-01-10 20:40 | 2018-01-11 03:05 | 7472.4522 | [6 empty] | 7472 | 5430 | 0.27 | 0 | 0 | 12.67 | 5150
PH4100XPC#1 | DT\24\002\B | DT | 24 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-01-11 00:54 | 2018-01-12 08:46 | 66997.2485 | 66997 | [7 empty] | 0 | 0 | 3.8 | 11.38 | 5336.92
TS5500Shv | MW\27\011\X | MW | 27 | 11 | X | 8 Coal Mining | 75.7 | 0 | 75.7 | 2018-01-11 00:54 | 2018-01-11 21:30 | 23252.2978 | [6 empty] | 23252 | 16896 | 0.85 | 0 | 0 | 12.67 | 5150
TS5500Exc | MW\24\006\D | MW | 24 | 6 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-01-11 03:05 | 2018-01-12 20:54 | 48754.6756 | [6 empty] | 48755 | 36424 | 2.28 | 0 | 0 | 7.18 | 5781
DRE1 | SC\31\013\D | SC | 31 | 13 | D | 6 DL | 100 | 0 | 100 | 2018-01-11 06:19 | 2018-01-18 19:38 | 624954.7303 |  |  |  | 47525 | 624955 | 427726 |  |  | 0 | 40 | 0 | 7.6 | 5744.98
TS5500Shv | DT\27\007\B | DT | 27 | 7 | B | 1 Prestrip - Thick | 26.1042 | 26.1042 | 26.1042 | 2018-01-11 21:30 | 2018-01-20 15:01 | 208318.2611 | 208318 | [7 empty] | 0 | 0 | 14.96 | 9.64 | 5518.42
PH4100XPC#1 | MW\26\010\B | MW | 26 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-01-12 08:46 | 2018-01-13 11:06 | 55354.0328 | 55354 | [7 empty] | 0 | 0 | 3.45 | 8.74 | 5674.27
DRE2 | DT\24\004\D | DT | 24 | 4 | D | 6 DL | 100 | 100 | 100 | 2018-01-12 12:56 | 2018-01-19 13:38 | 559923.6397 |  |  |  | 24420 | 559924 | 404004 |  |  | 0 | 26.74 | 0 | 6.1 | 5877.97
TS6060#1 | DT\24\006\B | DT | 24 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-01-12 18:35 | 2018-01-14 06:08 | 44522.9906 | [6 empty] | 44523 | 33003 | 3 | 0 | 0 | 8.5 | 5572
TS5500Exc | SC\30\007\D | SC | 30 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-01-12 20:54 | 2018-01-15 16:18 | 78553.1561 | [6 empty] | 78553 | 59368 | 4.95 | 0 | 0 | 6.08 | 5880
PH4100A | SC\32\015\D | SC | 32 | 15 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-01-13 09:50 | 2018-01-20 18:10 | 276773.3893 | 276773 | [7 empty] | 0 | 0 | 20.22 | 7.32 | 5768.61
PH4100XPC#1 | MW\27\010\A | MW | 27 | 10 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-01-13 11:06 | 2018-01-29 22:00 | 773534.8421 | 773535 | [7 empty] | 0 | 0 | 47.06 | 10.68 | 5478.85
TS Fleet 5 | BW\27\005\X1 | BW | 27 | 5 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-01-13 13:19 | 2018-01-21 16:36 | 338996.5737 | 338997 | [7 empty] | 0 | 0 | 21.73 | 11.25 | 5406.34
TS6060#1 | BW\27\004\B | BW | 27 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-01-14 06:08 | 2018-01-17 09:55 | 94906.3792 | [6 empty] | 94906 | 69415 | 3.55 | 0 | 0 | 10.43 | 5487
TS5500Exc | DT\24\002\B | DT | 24 | 2 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-01-15 16:18 | 2018-01-17 01:21 | 38519.1893 | [6 empty] | 38519 | 28010 | 1.6 | 0 | 0 | 11.38 | 5337
TS5500Exc | SC\30\008\D | SC | 30 | 8 | D | 8 Coal Mining | 38.8 | 0 | 38.8 | 2018-01-17 01:21 | 2018-01-18 03:48 | 30838.1743 | [6 empty] | 30838 | 23270 | 1.94 | 0 | 0 | 6.36 | 5856
TS6060#1 | BW\27\007\B | BW | 27 | 7 | B | 1 Prestrip - Thick | 21.1623 | 21.1623 | 21.1623 | 2018-01-17 09:55 | 2018-01-27 06:23 | 222940.66 | 222941 | [7 empty] | 0 | 0 | 12.96 | 11.46 | 5399.38
TS5500Exc | MW\27\003\B | MW | 27 | 3 | B | 1 Prestrip - Thick | 3.0043 | 3.0043 | 3.0043 | 2018-01-18 03:48 | 2018-01-19 07:46 | 22903.5248 | 22904 | [7 empty] | 0 | 0 | 1.44 | 8.34 | 5632.08
DRE1 | SC\31\012\D | SC | 31 | 12 | D | 6 DL | 100 | 0 | 100 | 2018-01-18 19:38 | 2018-01-26 09:17 | 626055.3154 |  |  |  | 47609 | 626055 | 428479 |  |  | 0 | 40 | 0 | 7.62 | 5742.64
TS5500Exc | SC\31\014\D | SC | 31 | 14 | D | 7 PostStrip | 100 | 0 | 100 | 2018-01-19 07:46 | 2018-01-21 02:17 | 34788.5727 |  |  | 34789 | [5 empty] | 0 | 0 | 0 | 7.46 | 5756.67
DRE2 | DT\24\005\D | DT | 24 | 5 | D | 6 DL | 100 | 100 | 100 | 2018-01-19 13:38 | 2018-01-26 00:14 | 513124.5047 |  |  |  | 22379 | 513125 | 370237 |  |  | 0 | 23.85 | 0 | 6.24 | 5865.52
TS5500Shv | MW\26\010\B | MW | 26 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-01-20 15:01 | 2018-01-22 21:09 | 61083.4835 | [6 empty] | 61083 | 45290 | 2.82 | 0 | 0 | 8.74 | 5674
PH4100A | RS\05\003\B | RS | 5 | 3 | B | 1 Prestrip - Thick | 100 | 0 | 100 | 2018-01-20 18:10 | 2018-01-26 00:40 | 193406.8405 | 193407 | [7 empty] | 0 | 0 | 26.96 | 0 | 0
TS5500Exc | DT\24\004\D | DT | 24 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-01-21 02:17 | 2018-01-22 22:40 | 51727.5081 | [6 empty] | 51728 | 39023 | 2.44 | 0 | 0 | 6.1 | 5878
TS Fleet 5 | BW\27\006\B | BW | 27 | 6 | B | 1 Prestrip - Thick | 18.0409 | 18.0409 | 18.0409 | 2018-01-21 16:36 | 2018-01-25 17:23 | 168029.3575 | 168029 | [7 empty] | 0 | 0 | 10.74 | 11.07 | 5437.68
TS5500Shv | DT\24\002\B | DT | 24 | 2 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-01-22 21:09 | 2018-01-24 06:12 | 37289.8535 | [6 empty] | 37290 | 27116 | 1.55 | 0 | 0 | 11.38 | 5337
TS5500Exc | SC\30\008\D | SC | 30 | 8 | D | 8 Coal Mining | 61.2 | 0 | 61.2 | 2018-01-22 22:40 | 2018-01-24 16:22 | 48610.9191 | [6 empty] | 48611 | 36680 | 3.06 | 0 | 0 | 6.36 | 5856
TS5500Shv | DT\24\004\D | DT | 24 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-01-24 06:12 | 2018-01-26 02:35 | 50076.6302 | [6 empty] | 50077 | 37778 | 2.36 | 0 | 0 | 6.1 | 5878
TS5500Exc | SC\31\013\D | SC | 31 | 13 | D | 8 Coal Mining | 23.4 | 0 | 23.4 | 2018-01-24 16:22 | 2018-01-25 07:13 | 17305.5984 | [6 empty] | 17306 | 12934 | 1.08 | 0 | 0 | 7.6 | 5745
TS5500Exc | DT\25\001\A | DT | 25 | 1 | A | 8 Coal Mining | 17.4 | 0 | 17.4 | 2018-01-25 07:13 | 2018-01-25 11:14 | 4684.3781 | [6 empty] | 4684 | 3254 | 0.16 | 0 | 0 | 20.4 | 4719
TS5500Exc | DT\25\002\B | DT | 25 | 2 | B | 8 Coal Mining | 50.8 | 0 | 32.9 | 2018-01-25 11:14 | 2018-01-26 11:57 | 28817.2958 | [6 empty] | 28817 | 20943 | 1.06 | 0 | 0 | 11.46 | 5327
TS Fleet 5 | BW\27\006\B | BW | 27 | 6 | B | 1 Prestrip - Thick | 81.9591 | 28.0718 | 28.0718 | 2018-01-25 17:23 | 2018-02-01 | 261454.86 | 261455 | [7 empty] | 0 | 0 | 16.71 | 11.07 | 5437.68
DRE2 | DT\24\006\D | DT | 24 | 6 | D | 6 DL | 100 | 100 | 100 | 2018-01-26 00:14 | 2018-01-30 07:02 | 341180.4566 |  |  |  | 20375 | 341180 | 240849 |  |  | 0 | 25.64 | 0 | 6.14 | 5873.45
PH4100A | RS\05\004\B | RS | 5 | 4 | B | 1 Prestrip - Thick | 100 | 75.6935 | 75.6935 | 2018-01-26 00:40 | 2018-02-01 | 217936.4244 | 217936 | [7 empty] | 0 | 0 | 21.54 | 13.32 | 5249.88
TS5500Shv | DT\27\007\B | DT | 27 | 7 | B | 1 Prestrip - Thick | 40.2624 | 17.618 | 17.618 | 2018-01-26 02:35 | 2018-02-01 | 140596.2231 | 140596 | [7 empty] | 0 | 0 | 10.09 | 9.64 | 5518.42
DRE1 | SC\31\011\D | SC | 31 | 11 | D | 6 DL | 100 | 0 | 75.6886 | 2018-01-26 09:17 | 2018-02-01 | 464280.4101 |  |  |  | 35306 | 464280 | 317758 |  |  | 0 | 40 | 0 | 7.57 | 5748.06
TS5500Exc | MW\27\004\A | MW | 27 | 4 | A | 1 Prestrip - Thick | 30.2216 | 20.6317 | 20.6317 | 2018-01-26 11:57 | 2018-02-01 | 108098.6017 | 108099 | [7 empty] | 0 | 0 | 6.37 | 9.71 | 5506.67
TS6060#1 | BW\27\008\B | BW | 27 | 8 | B | 1 Prestrip - Thick | 8.204 | 8.204 | 8.204 | 2018-01-27 06:23 | 2018-01-30 17:54 | 79432.3374 | 79432 | [7 empty] | 0 | 0 | 4.97 | 12.6 | 5300.27
PH4100XPC#1 | MW\26\009\B | MW | 26 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-01-29 22:00 | 2018-01-31 10:31 | 76753.6811 | 76754 | [7 empty] | 0 | 0 | 4.77 | 10.12 | 5506.94
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 1d 16:57 | 2018-01-30 07:02 | 2018-02-01
TS6060#1 | BW\27\008\B | BW | 27 | 8 | B | 1 Prestrip - Thick | 20.9076 | 2.9563 | 2.9563 | 2018-01-30 17:54 | 2018-02-01 | 28623.7797 | 28624 | [7 empty] | 0 | 0 | 1.79 | 12.6 | 5300.27
PH4100XPC#1 | MW\27\009\A | MW | 27 | 9 | A | 1 Prestrip - Thick | 100 | 4.2802 | 4.2802 | 2018-01-31 10:31 | 2018-02-01 | 26094.7538 | 26095 | [7 empty] | 0 | 0 | 1.63 | 10.87 | 5386.02
| EOP 49 : 2018\Jan | EOP 49 : 2018 | Jan | [6 empty] | 2018-02-01 | 2018-02-01 |  | 4727289 |  | 133412 | 293885 | 4897578 | 3350289 | 1424700 | 1056404 | 70.43 | 0 | 320.64 | 8.45 | 5658.51
TS Fleet 5 | BW\27\006\B | BW | 27 | 6 | B | 1 Prestrip - Thick | 81.9591 | 53.8873 | 53.8873 | 2018-02-01 | 2018-02-13 10:44 | 501894.2292 | 501894 | [7 empty] | 0 | 0 | 32.07 | 11.07 | 5437.68
DRE1 | SC\31\011\D | SC | 31 | 11 | D | 6 DL | 100 | 0 | 24.3114 | 2018-02-01 | 2018-02-02 18:07 | 149127.9424 |  |  |  | 11341 | 149128 | 102065 |  |  | 0 | 40 | 0 | 7.57 | 5748.06
PH4100A | RS\05\004\B | RS | 5 | 4 | B | 1 Prestrip - Thick | 100 | 24.3065 | 24.3065 | 2018-02-01 | 2018-02-02 22:44 | 69983.2351 | 69983 | [7 empty] | 0 | 0 | 6.92 | 13.32 | 5249.88
PH4100XPC#1 | MW\27\009\A | MW | 27 | 9 | A | 1 Prestrip - Thick | 100 | 95.7198 | 95.7198 | 2018-02-01 | 2018-02-13 17:52 | 583562.5667 | 583563 | [7 empty] | 0 | 0 | 36.52 | 10.87 | 5386.02
TS5500Shv | DT\27\007\B | DT | 27 | 7 | B | 1 Prestrip - Thick | 40.2624 | 22.6444 | 22.6444 | 2018-02-01 | 2018-02-08 19:48 | 180708.4107 | 180708 | [7 empty] | 0 | 0 | 12.97 | 9.64 | 5518.42
TS6060#1 | BW\27\008\B | BW | 27 | 8 | B | 1 Prestrip - Thick | 20.9076 | 17.9512 | 17.9512 | 2018-02-01 | 2018-02-08 20:49 | 173807.1226 | 173807 | [7 empty] | 0 | 0 | 10.88 | 12.6 | 5300.27
TS5500Exc | MW\27\004\A | MW | 27 | 4 | A | 1 Prestrip - Thick | 30.2216 | 9.5899 | 9.5899 | 2018-02-01 | 2018-02-03 15:25 | 50245.5241 | 50246 | [7 empty] | 0 | 0 | 2.96 | 9.71 | 5506.67
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 0d 07:03 | 2018-02-01 | 2018-02-01 07:02
DRE2 | MW\24\008\D | MW | 24 | 8 | D | 6 DL | 100 | 0 | 100 | 2018-02-01 07:02 | 2018-02-09 06:58 | 654211.1865 |  |  |  | 48902 | 654211 | 450101 |  |  | 0 | 31.17 | 0 | 6.43 | 5847.9
DRE1 | SC\31\010\D | SC | 31 | 10 | D | 6 DL | 100 | 0 | 100 | 2018-02-02 18:07 | 2018-02-09 22:48 | 611224.6754 |  |  |  | 46481 | 611225 | 418329 |  |  | 0 | 40 | 0 | 7.36 | 5767.44
PH4100A | RS\05\005\A | RS | 5 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-02-02 22:44 | 2018-02-11 09:52 | 305321.3919 | 305321 | [7 empty] | 0 | 0 | 30.19 | 14.38 | 5087.29
TS5500Exc | MW\26\009\B | MW | 26 | 9 | B | 8 Coal Mining | 50.6 | 0 | 50.6 | 2018-02-03 15:25 | 2018-02-04 19:46 | 31979.8085 | [6 empty] | 31980 | 23475 | 1.45 | 0 | 0 | 10.12 | 5507
TS5500Exc | SC\31\011\D | SC | 31 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-02-04 19:46 | 2018-02-07 14:16 | 75023.2749 | [6 empty] | 75023 | 55981 | 4.67 | 0 | 0 | 7.57 | 5748
TS5500Exc | SC\31\012\D | SC | 31 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-02-07 14:16 | 2018-02-10 06:16 | 72179.9263 | [6 empty] | 72180 | 53858 | 4.49 | 0 | 0 | 7.62 | 5743
TS5500Shv | MW\27\010\A | MW | 27 | 10 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-02-08 19:48 | 2018-02-11 17:15 | 75839.7612 | [6 empty] | 75840 | 55742 | 3.49 | 0 | 0 | 10.68 | 5479
TS6060#1 | BW\27\005\X1 | BW | 27 | 5 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2018-02-08 20:49 | 2018-02-09 12:53 | 19475.6593 | [6 empty] | 19476 | 14313 | 0.91 | 0 | 0 | 11.25 | 5406
DRE2 | MW\24\009\D | MW | 24 | 9 | D | 6 DL | 100 | 0 | 100 | 2018-02-09 06:58 | 2018-02-16 17:55 | 609972.8224 |  |  |  | 36428 | 609973 | 430597 |  |  | 0 | 29.26 | 0 | 5.85 | 5897.05
TS6060#1 | BW\27\005\X2 | BW | 27 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2018-02-09 12:53 | 2018-02-16 19:34 | 161398.787 | 161399 | [7 empty] | 0 | 0 | 10.12 | 0 | 0
DRE1 | SC\31\004\D | SC | 31 | 4 | D | 6 DL | 100 | 0 | 100 | 2018-02-09 22:48 | 2018-02-14 17:25 | 405691.1964 |  |  |  | 30851 | 405691 | 277659 |  |  | 0 | 40 | 0 | 6.18 | 5871.8
TS5500Exc | SC\31\010\D | SC | 31 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-02-10 06:16 | 2018-02-13 03:15 | 77816.3721 | [6 empty] | 77816 | 58206 | 4.85 | 0 | 0 | 7.36 | 5767
PH4100A | RS\05\006\A | RS | 5 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-02-11 09:52 | 2018-02-19 23:48 | 310508.7012 | 310509 | [7 empty] | 0 | 0 | 30.47 | 13.38 | 5158.42
TS5500Shv | MW\26\009\B | MW | 26 | 9 | B | 8 Coal Mining | 49.4 | 0 | 49.4 | 2018-02-11 17:15 | 2018-02-12 21:48 | 31165.5556 | [6 empty] | 31166 | 22877 | 1.41 | 0 | 0 | 10.12 | 5507
TS5500Shv | MW\24\007\D | MW | 24 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-02-12 21:48 | 2018-02-16 16:08 | 98648.4051 | [6 empty] | 98648 | 73940 | 4.62 | 0 | 0 | 6.85 | 5811
TS5500Exc | DT\25\002\B | DT | 25 | 2 | B | 8 Coal Mining | 50.8 | 0 | 17.9 | 2018-02-13 03:15 | 2018-02-13 17:06 | 15631.9798 | [6 empty] | 15632 | 11360 | 0.58 | 0 | 0 | 11.46 | 5327
TS Fleet 5 | BW\27\007\B | BW | 27 | 7 | B | 1 Prestrip - Thick | 27.1761 | 27.1761 | 27.1761 | 2018-02-13 10:44 | 2018-02-20 13:09 | 286295.0054 | 286295 | [7 empty] | 0 | 0 | 16.64 | 11.46 | 5399.38
TS5500Exc | DT\25\004\B | DT | 25 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-02-13 17:06 | 2018-02-14 11:04 | 20253.5603 | [6 empty] | 20254 | 14718 | 0.91 | 0 | 0 | 10.8 | 5309
PH4100XPC#1 | DT\28\004\A | DT | 28 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-02-13 17:52 | 2018-02-13 19:09 | 2679.5656 | 2680 | [7 empty] | 0 | 0 | 0.53 | 19.87 | 4710.47
PH4100XPC#1 | DT\28\005\B | DT | 28 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-02-13 19:09 | 2018-02-18 12:13 | 240636.2536 | 240636 | [7 empty] | 0 | 0 | 12.61 | 10.62 | 5365.18
TS5500Exc | DT\25\006\A | DT | 25 | 6 | A | 8 Coal Mining | 14.1 | 0 | 14.1 | 2018-02-14 11:04 | 2018-02-14 19:15 | 9236.7486 | [6 empty] | 9237 | 6771 | 0.49 | 0 | 0 | 10.74 | 5388
DRE1 | SC\31\005\D | SC | 31 | 5 | D | 6 DL | 100 | 0 | 100 | 2018-02-14 17:25 | 2018-02-22 03:50 | 631584.1071 |  |  |  | 48029 | 631584 | 432263 |  |  | 0 | 40 | 0 | 6.12 | 5876.68
TS5500Exc | SC\31\004\D | SC | 31 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-02-14 19:15 | 2018-02-16 14:51 | 49183.696 | [6 empty] | 49184 | 37114 | 4.96 | 0 | 0 | 6.18 | 5872
TS5500Exc | MW\27\004\A | MW | 27 | 4 | A | 1 Prestrip - Thick | 14.7382 | 14.7382 | 14.7382 | 2018-02-16 14:51 | 2018-02-20 16:19 | 77219.9725 | 77220 | [7 empty] | 0 | 0 | 4.55 | 9.71 | 5506.67
TS5500Shv | MW\24\008\D | MW | 24 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-02-16 16:08 | 2018-02-20 10:45 | 98963.7793 | [6 empty] | 98964 | 74474 | 4.66 | 0 | 0 | 6.43 | 5848
DRE2 | MW\24\010\D | MW | 24 | 10 | D | 6 DL | 100 | 0 | 100 | 2018-02-16 17:55 | 2018-02-23 21:48 | 585883.727 |  |  |  | 34989 | 585884 | 413591 |  |  | 0 | 28 | 0 | 5.56 | 5922.83
TS6060#1 | BW\27\005\B | BW | 27 | 5 | B | 1 Prestrip - Thick | 48.9049 | 46.7654 | 46.7654 | 2018-02-16 19:34 | 2018-02-26 19:09 | 221381.6617 | 221382 | [7 empty] | 0 | 0 | 13.95 | 10.93 | 5455
PH4100XPC#1 | DT\28\006\D | DT | 28 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-02-18 12:13 | 2018-02-27 00:15 | 435873.2488 | 435873 | [7 empty] | 0 | 0 | 21.03 | 7.16 | 5783.93
PH4100A | RS\05\007\A | RS | 5 | 7 | A | 1 Prestrip - Thick | 100 | 98.8976 | 98.8976 | 2018-02-19 23:48 | 2018-03-01 | 326165.04 | 326165 | [7 empty] | 0 | 0 | 31.83 | 14.97 | 5064.76
TS5500Shv | MW\24\009\D | MW | 24 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-02-20 10:45 | 2018-02-24 00:42 | 93840.8025 | [6 empty] | 93841 | 70952 | 4.43 | 0 | 0 | 5.85 | 5897
TS Fleet 5 | BW\27\005\B | BW | 27 | 5 | B | 1 Prestrip - Thick | 68.7292 | 53.2346 | 53.2346 | 2018-02-20 13:09 | 2018-02-26 19:09 | 252006.5533 | 252007 | [7 empty] | 0 | 0 | 15.87 | 10.93 | 5455
TS5500Exc | SC\31\013\D | SC | 31 | 13 | D | 8 Coal Mining | 76.6 | 0 | 76.6 | 2018-02-20 16:19 | 2018-02-22 18:27 | 56550.1713 | [6 empty] | 56550 | 42263 | 3.52 | 0 | 0 | 7.6 | 5745
DRE1 | SC\31\006\D | SC | 31 | 6 | D | 6 DL | 100 | 0 | 92.0118 | 2018-02-22 03:50 | 2018-03-01 | 581050.4788 |  |  |  | 44186 | 581050 | 397677 |  |  | 0 | 40 | 0 | 6.1 | 5878.32
TS5500Exc | SC\31\005\D | SC | 31 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-02-22 18:27 | 2018-02-25 17:22 | 79995.5271 | [6 empty] | 79996 | 60266 | 5.02 | 0 | 0 | 6.12 | 5877
DRE2 | MW\24\011\D | MW | 24 | 11 | D | 6 DL | 100 | 0 | 70.1242 | 2018-02-23 21:48 | 2018-03-01 | 416488.8592 |  |  |  | 24873 | 416489 | 294011 |  |  | 0 | 28.41 | 0 | 5.88 | 5894.47
TS5500Shv | MW\27\009\A | MW | 27 | 9 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-02-24 00:42 | 2018-02-26 21:50 | 75497.275 | [6 empty] | 75497 | 55442 | 3.48 | 0 | 0 | 10.87 | 5386
TS5500Exc | SC\31\014\D | SC | 31 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-02-25 17:22 | 2018-02-27 02:08 | 36968.8235 | [6 empty] | 36969 | 27673 | 4.59 | 0 | 0 | 7.46 | 5757
TS Fleet 5 | BW\27\007\B | BW | 27 | 7 | B | 1 Prestrip - Thick | 51.6615 | 8.4258 | 8.4258 | 2018-02-26 19:09 | 2018-03-01 | 88764.212 | 88764 | [7 empty] | 0 | 0 | 5.16 | 11.46 | 5399.38
TS6060#1 | BW\27\005\B | BW | 27 | 5 | B | 8 Coal Mining | 100 | 0 | 89.6 | 2018-02-26 19:09 | 2018-03-01 | 64037.0386 | [6 empty] | 64037 | 46715 | 2.91 | 0 | 0 | 10.93 | 5455
TS5500Shv | DT\24\005\D | DT | 24 | 5 | D | 8 Coal Mining | 2.1 | 0 | 2.1 | 2018-02-26 21:50 | 2018-02-26 23:52 | 2217.7246 | [6 empty] | 2218 | 1670 | 0.1 | 0 | 0 | 6.24 | 5866
TS5500Shv | DT\24\005\D | DT | 24 | 5 | D | 8 Coal Mining | 97.9 | 0 | 50.2 | 2018-02-26 23:52 | 2018-03-01 | 52560.5681 | [6 empty] | 52561 | 39589 | 2.41 | 0 | 0 | 6.24 | 5866
PH4100XPC#1 | DT\27\007\B | DT | 27 | 7 | B | 1 Prestrip - Thick | 100 | 12.9857 | 12.9857 | 2018-02-27 00:15 | 2018-03-01 | 103629.2951 | 103629 | [7 empty] | 0 | 0 | 7.44 | 9.64 | 5518.42
TS5500Exc | DT\25\006\A | DT | 25 | 6 | A | 8 Coal Mining | 36.7 | 0 | 36.7 | 2018-02-27 02:08 | 2018-02-27 23:23 | 23963.0645 | [6 empty] | 23963 | 17567 | 1.28 | 0 | 0 | 10.74 | 5388
TS5500Exc | DT\25\007\A | DT | 25 | 7 | A | 8 Coal Mining | 50.8 | 0 | 33.9 | 2018-02-27 23:23 | 2018-03-01 | 27757.1886 | [6 empty] | 27757 | 20411 | 1.28 | 0 | 0 | 10.19 | 5428
| EOP 50 : 2018\Feb | EOP 50 : 2018 | Feb | [6 empty] | 2018-03-01 | 2018-03-01 |  | 4372081 |  |  | 326081 | 4645235 | 3216292 | 1188787 | 885379 | 66.52 | 0 | 302.73 | 8.27 | 5672.06
TS Fleet 5 | BW\27\007\B | BW | 27 | 7 | B | 1 Prestrip - Thick | 51.6615 | 43.2357 | 43.2357 | 2018-03-01 | 2018-03-11 02:47 | 455479.1638 | 455479 | [7 empty] | 0 | 0 | 26.48 | 11.46 | 5399.38
DRE1 | SC\31\006\D | SC | 31 | 6 | D | 6 DL | 100 | 0 | 7.9882 | 2018-03-01 | 2018-03-01 14:15 | 50445.1786 |  |  |  | 3836 | 50445 | 34525 |  |  | 0 | 40 | 0 | 6.1 | 5878.32
PH4100A | RS\05\007\A | RS | 5 | 7 | A | 1 Prestrip - Thick | 100 | 1.1024 | 1.1024 | 2018-03-01 | 2018-03-01 02:01 | 3635.5764 | 3636 | [7 empty] | 0 | 0 | 0.35 | 14.97 | 5064.76
DRE2 | MW\24\011\D | MW | 24 | 11 | D | 6 DL | 100 | 0 | 29.8758 | 2018-03-01 | 2018-03-03 04:03 | 177441.6368 |  |  |  | 10597 | 177442 | 125261 |  |  | 0 | 28.41 | 0 | 5.88 | 5894.47
PH4100XPC#1 | DT\27\007\B | DT | 27 | 7 | B | 1 Prestrip - Thick | 100 | 20.6477 | 20.6477 | 2018-03-01 | 2018-03-07 03:13 | 164774.1736 | 164774 | [7 empty] | 0 | 0 | 11.83 | 9.64 | 5518.42
TS5500Shv | DT\24\005\D | DT | 24 | 5 | D | 8 Coal Mining | 97.9 | 0 | 47.7 | 2018-03-01 | 2018-03-02 16:57 | 49941.24 | [6 empty] | 49941 | 37616 | 2.29 | 0 | 0 | 6.24 | 5866
TS6060#1 | BW\27\005\B | BW | 27 | 5 | B | 8 Coal Mining | 100 | 0 | 10.4 | 2018-03-01 | 2018-03-01 05:29 | 7441.2285 | [6 empty] | 7441 | 5428 | 0.34 | 0 | 0 | 10.93 | 5455
TS5500Exc | DT\25\007\A | DT | 25 | 7 | A | 8 Coal Mining | 50.8 | 0 | 16.9 | 2018-03-01 | 2018-03-01 10:59 | 13855.1336 | [6 empty] | 13855 | 10188 | 0.64 | 0 | 0 | 10.19 | 5428
PH4100A | RS\05\008\A | RS | 5 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-03-01 02:01 | 2018-03-08 11:16 | 317967.6388 | 317968 | [7 empty] | 0 | 0 | 34.57 | 15.6 | 5051.35
TS6060#1 | BW\27\006\B | BW | 27 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-03-01 05:29 | 2018-03-03 16:27 | 79805.1655 | [6 empty] | 79805 | 58161 | 3.64 | 0 | 0 | 11.07 | 5438
TS5500Exc | DT\26\001\B | DT | 26 | 1 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-03-01 10:59 | 2018-03-03 01:35 | 48603.9954 | [6 empty] | 48604 | 35362 | 1.56 | 0 | 0 | 11.67 | 5333
DRE1 | SC\31\007\D | SC | 31 | 7 | D | 6 DL | 100 | 0 | 100 | 2018-03-01 14:15 | 2018-03-09 00:09 | 629748.5642 |  |  |  | 47890 | 629749 | 431007 |  |  | 0 | 40 | 0 | 6.22 | 5868.2
TS5500Shv | MW\24\010\D | MW | 24 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-03-02 16:57 | 2018-03-05 21:21 | 93164.5434 | [6 empty] | 93165 | 70610 | 4.41 | 0 | 0 | 5.56 | 5923
TS5500Exc | SC\31\006\D | SC | 31 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-03-03 01:35 | 2018-03-05 17:00 | 79884.6862 | [6 empty] | 79885 | 60231 | 5.02 | 0 | 0 | 6.1 | 5878
DRE2 | MW\24\012\D | MW | 24 | 12 | D | 6 DL | 100 | 0 | 100 | 2018-03-03 04:03 | 2018-03-07 02:51 | 323146.418 |  |  |  | 11311 | 323146 | 152188 |  |  | 0 | 28.4 | 0 | 6.14 | 5872.07
TS6060#1 | BW\27\009\B | BW | 27 | 9 | B | 1 Prestrip - Thick | 30.8534 | 30.8534 | 30.8534 | 2018-03-03 16:27 | 2018-03-14 12:43 | 266978.4528 | 266978 | [7 empty] | 0 | 0 | 17.1 | 13.96 | 5178.81
TS5500Exc | DT\26\002\B | DT | 26 | 2 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-03-05 17:00 | 2018-03-07 05:03 | 45419.8386 | [6 empty] | 45420 | 32965 | 1.49 | 0 | 0 | 11.59 | 5313
TS5500Shv | MW\24\011\D | MW | 24 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-03-05 21:21 | 2018-03-09 02:09 | 93647.0785 | [6 empty] | 93647 | 71091 | 4.44 | 0 | 0 | 5.88 | 5894
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2018-03-07 02:51 | 2018-03-09 02:51
PH4100XPC#1 | DT\28\007\D | DT | 28 | 7 | D | 1 Prestrip - Thick | 100 | 88.0146 | 88.0146 | 2018-03-07 03:13 | 2018-04-01 | 661478.8327 | 661479 | [7 empty] | 0 | 0 | 41.75 | 6.97 | 5800.59
TS5500Exc | DT\26\004\B | DT | 26 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-03-07 05:03 | 2018-03-08 07:25 | 33199.646 | [6 empty] | 33200 | 24254 | 1.51 | 0 | 0 | 9.91 | 5387
TS5500Exc | MW\27\008\A | MW | 27 | 8 | A | 1 Prestrip - Thick | 56.3964 | 56.3964 | 56.3964 | 2018-03-08 07:25 | 2018-03-19 22:13 | 248105.7683 | 248106 | [7 empty] | 0 | 0 | 15.15 | 11.39 | 5273.97
PH4100A | RS\06\003\A | RS | 6 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-03-08 11:16 | 2018-03-12 04:54 | 159668.765 | 159669 | [7 empty] | 0 | 0 | 23.59 | 12.46 | 5301.41
DRE1 | SC\31\008\D | SC | 31 | 8 | D | 6 DL | 100 | 0 | 100 | 2018-03-09 00:09 | 2018-03-16 09:59 | 629458.8472 |  |  |  | 47868 | 629459 | 430808 |  |  | 0 | 40 | 0 | 6.51 | 5842.97
TS5500Shv | MW\24\012\D | MW | 24 | 12 | D | 7 PostStrip | 100 | 0 | 100 | 2018-03-09 02:09 | 2018-03-10 10:45 | 34941.9118 |  |  | 34942 | [5 empty] | 0 | 0 | 0 | 6.14 | 5872.07
DRE2 | DT\24\003\D | DT | 24 | 3 | D | 6 DL | 100 | 100 | 100 | 2018-03-09 02:51 | 2018-03-15 11:57 | 521826.792 |  |  |  | 22759 | 521827 | 376516 |  |  | 0 | 24.9 | 0 | 6.08 | 5878.47
TS5500Shv | MW\24\012\D | MW | 24 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-03-10 10:45 | 2018-03-11 19:02 | 39381.0173 | [6 empty] | 39381 | 29871 | 4.43 | 0 | 0 | 6.14 | 5872
TS Fleet 5 | BW\27\008\B | BW | 27 | 8 | B | 1 Prestrip - Thick | 70.8885 | 70.8885 | 70.8885 | 2018-03-11 02:47 | 2018-03-26 08:39 | 686355.6143 | 686356 | [7 empty] | 0 | 0 | 42.97 | 12.6 | 5300.27
TS5500Shv | DT\24\006\D | DT | 24 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-03-11 19:02 | 2018-03-13 22:49 | 63132.5748 | [6 empty] | 63133 | 47550 | 4.72 | 0 | 0 | 6.14 | 5873
PH4100A | RS\06\004\A | RS | 6 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-03-12 04:54 | 2018-03-18 16:06 | 274891.7362 | 274892 | [7 empty] | 0 | 0 | 27.48 | 13.93 | 5156.71
TS5500Shv | DT\24\007\A | DT | 24 | 7 | A | 8 Coal Mining | 64.3 | 0 | 64.3 | 2018-03-13 22:49 | 2018-03-15 18:51 | 53706.9818 | [6 empty] | 53707 | 39536 | 2.45 | 0 | 0 | 10.14 | 5425
TS6060#1 | BW\27\007\B | BW | 27 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-03-14 12:43 | 2018-03-17 04:32 | 86356.5547 | [6 empty] | 86357 | 62830 | 3.93 | 0 | 0 | 11.46 | 5399
DRE2 | DT\24\002\D | DT | 24 | 2 | D | 6 DL | 100 | 100 | 100 | 2018-03-15 11:57 | 2018-03-21 12:48 | 493732.2657 |  |  |  | 21533 | 493732 | 356245 |  |  | 0 | 22.75 | 0 | 6.04 | 5882.06
TS5500Shv | DT\25\001\A | DT | 25 | 1 | A | 8 Coal Mining | 82.6 | 0 | 82.6 | 2018-03-15 18:51 | 2018-03-16 13:02 | 22165.3508 | [6 empty] | 22165 | 15395 | 0.75 | 0 | 0 | 20.4 | 4719
DRE1 | SC\31\009\D | SC | 31 | 9 | D | 6 DL | 100 | 0 | 100 | 2018-03-16 09:59 | 2018-03-24 06:16 | 666453.2068 |  |  |  | 45738 | 666453 | 411641 |  |  | 0 | 40 | 0 | 6.96 | 5802.7
TS5500Shv | DT\25\002\B | DT | 25 | 2 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-03-16 13:02 | 2018-03-18 00:19 | 43030.6817 | [6 empty] | 43031 | 31272 | 1.58 | 0 | 0 | 11.46 | 5327
TS6060#1 | BW\27\010\A | BW | 27 | 10 | A | 1 Prestrip - Thick | 24.1426 | 0 | 24.1426 | 2018-03-17 04:32 | 2018-03-24 15:30 | 180977.6413 | 180978 | [7 empty] | 0 | 0 | 11.18 | 0 | 0
TS5500Shv | DT\24\003\D | DT | 24 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-03-18 00:19 | 2018-03-19 16:45 | 49300.9156 | [6 empty] | 49301 | 37162 | 2.32 | 0 | 0 | 6.08 | 5878
PH4100A | RS\06\005\A | RS | 6 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-03-18 16:06 | 2018-03-26 04:20 | 322635.3753 | 322635 | [7 empty] | 0 | 0 | 31.91 | 13.54 | 5153.48
TS5500Shv | DT\25\004\B | DT | 25 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-03-19 16:45 | 2018-03-20 08:50 | 19607.1701 | [6 empty] | 19607 | 14249 | 0.88 | 0 | 0 | 10.8 | 5309
TS5500Exc | DT\24\003\D | DT | 24 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-03-19 22:13 | 2018-03-21 14:39 | 50926.2206 | [6 empty] | 50926 | 38387 | 2.4 | 0 | 0 | 6.08 | 5878
TS5500Shv | DT\25\006\A | DT | 25 | 6 | A | 8 Coal Mining | 13.7 | 0 | 13.7 | 2018-03-20 08:50 | 2018-03-20 16:10 | 8941.9588 | [6 empty] | 8942 | 6555 | 0.48 | 0 | 0 | 10.74 | 5388
TS5500Shv | DT\24\007\B | DT | 24 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-03-20 16:10 | 2018-03-22 18:12 | 53637.6715 | 53638 | [7 empty] | 0 | 0 | 3.35 | 8.16 | 5621.78
DRE2 | DT\24\001\D | DT | 24 | 1 | D | 6 DL | 100 | 100 | 100 | 2018-03-21 12:48 | 2018-03-27 13:14 | 492342.741 |  |  |  | 21473 | 492343 | 355242 |  |  | 0 | 21.66 | 0 | 6.25 | 5863.77
TS5500Exc | SC\31\007\D | SC | 31 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-03-21 14:39 | 2018-03-24 05:31 | 79186.9101 | [6 empty] | 79187 | 59704 | 4.98 | 0 | 0 | 6.22 | 5868
TS5500Shv | DT\25\001\B | DT | 25 | 1 | B | 1 Prestrip - Thick | 72.067 | 72.067 | 72.067 | 2018-03-22 18:12 | 2018-03-24 16:02 | 49128.6296 | 49129 | [7 empty] | 0 | 0 | 2.39 | 11.56 | 5343.53
TS5500Exc | SC\31\008\D | SC | 31 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-03-24 05:31 | 2018-03-26 20:40 | 79555.496 | [6 empty] | 79555 | 59934 | 5 | 0 | 0 | 6.51 | 5843
DRE1 | SC\32\014\D | SC | 32 | 14 | D | 6 DL | 100 | 0 | 100 | 2018-03-24 06:16 | 2018-03-29 20:33 | 475339.433 |  |  |  | 20910 | 475339 | 233541 |  |  | 0 | 32.92 | 0 | 7.49 | 5754.14
TS6060#1 | BW\27\010\A | BW | 27 | 10 | A | 1 Prestrip - Thick | 7.4104 | 0 | 7.4104 | 2018-03-24 15:30 | 2018-03-26 22:26 | 55549.5946 | 55550 | [7 empty] | 0 | 0 | 3.43 | 0 | 0
TS5500Shv | DT\28\001\D | DT | 28 | 1 | D | 1 Prestrip - Thick | 15.7474 | 15.7474 | 15.7474 | 2018-03-24 16:02 | 2018-03-28 03:08 | 89346.5756 | 89347 | [7 empty] | 0 | 0 | 3.45 | 6.01 | 5884.9
PH4100A | RS\06\006\A | RS | 6 | 6 | A | 1 Prestrip - Thick | 100 | 71.6075 | 71.6075 | 2018-03-26 04:20 | 2018-04-01 | 251863.6507 | 251864 | [7 empty] | 0 | 0 | 24.65 | 13.19 | 5167.92
TS Fleet 5 | BW\27\009\B | BW | 27 | 9 | B | 1 Prestrip - Thick | 16.6877 | 16.6877 | 16.6877 | 2018-03-26 08:39 | 2018-03-29 13:37 | 144401.0099 | 144401 | [7 empty] | 0 | 0 | 9.25 | 13.96 | 5178.81
TS5500Exc | SC\31\009\D | SC | 31 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-03-26 20:40 | 2018-03-29 11:47 | 79484.9084 | [6 empty] | 79485 | 59691 | 4.97 | 0 | 0 | 6.96 | 5803
TS6060#1 | BW\27\008\B | BW | 27 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-03-26 22:26 | 2018-03-29 13:56 | 85925.1656 | [6 empty] | 85925 | 62159 | 3.89 | 0 | 0 | 12.6 | 5300
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2018-03-27 13:14 | 2018-03-29 13:14
TS5500Shv | DT\28\001\D | DT | 28 | 1 | D | 1 Prestrip - Thick | 84.2526 | 17.5929 | 17.5929 | 2018-03-28 03:08 | 2018-04-01 | 99817.1663 | 99817 | [7 empty] | 0 | 0 | 3.85 | 6.01 | 5884.9
TS5500Exc | DT\24\001\D | DT | 24 | 1 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-03-29 11:47 | 2018-03-31 07:19 | 54833.4896 | [6 empty] | 54833 | 41167 | 2.38 | 0 | 0 | 6.25 | 5864
DRE2 | BW\24\011\D | BW | 24 | 11 | D | 6 DL | 100 | 47.2028 | 47.2028 | 2018-03-29 13:14 | 2018-04-01 | 200282.9465 |  |  |  | 8735 | 200283 | 144511 |  |  | 0 | 20.32 | 0 | 6.17 | 5871.59
TS Fleet 5 | BW\27\009\B | BW | 27 | 9 | B | 1 Prestrip - Thick | 52.4589 | 12.6553 | 12.6553 | 2018-03-29 13:37 | 2018-04-01 | 109508.212 | 109508 | [7 empty] | 0 | 0 | 7.01 | 13.96 | 5178.81
TS6060#1 | DT\24\007\B | DT | 24 | 7 | B | 8 Coal Mining | 100 | 0 | 97.8 | 2018-03-29 13:56 | 2018-03-31 13:22 | 64202.0483 | [6 empty] | 64202 | 47798 | 2.92 | 0 | 0 | 8.16 | 5622
DRE1 | SC\32\013\D | SC | 32 | 13 | D | 6 DL | 100 | 0 | 31.1174 | 2018-03-29 20:33 | 2018-04-01 | 182091.5702 |  |  |  | 12950 | 182092 | 130939 |  |  | 0 | 39.27 | 0 | 7.64 | 5741.13
TS5500Exc | SC\32\014\D | SC | 32 | 14 | D | 7 PostStrip | 100 | 0 | 33.3389 | 2018-03-31 07:19 | 2018-04-01 | 14754.7971 |  |  | 14755 | [5 empty] | 0 | 0 | 0 | 7.49 | 5754.14
TS6060#1 | BW\27\011\B | BW | 27 | 11 | B | 1 Prestrip - Thick | 28.7136 | 0 | 1.3114 | 2018-03-31 13:22 | 2018-04-01 | 10865.3689 | 10865 | [7 empty] | 0 | 0 | 0.66 | 0 | 0
| EOP 51 : 2018\Mar | EOP 51 : 2018 | Mar | [6 empty] | 2018-04-01 | 2018-04-01 |  | 4607067 |  | 49697 | 275599 | 4842310 | 3182423 | 1424700 | 1059166 | 73.42 | 0 | 342.4 | 8.38 | 5659.56
TS Fleet 5 | BW\27\009\B | BW | 27 | 9 | B | 1 Prestrip - Thick | 52.4589 | 39.8036 | 39.8036 | 2018-04-01 | 2018-04-08 07:43 | 344426.2785 | 344426 | [7 empty] | 0 | 0 | 22.05 | 13.96 | 5178.81
DRE1 | SC\32\013\D | SC | 32 | 13 | D | 6 DL | 100 | 0 | 68.8826 | 2018-04-01 | 2018-04-05 17:52 | 403084.5195 |  |  |  | 28667 | 403085 | 289851 |  |  | 0 | 39.27 | 0 | 7.64 | 5741.13
PH4100A | RS\06\006\A | RS | 6 | 6 | A | 1 Prestrip - Thick | 100 | 28.3925 | 28.3925 | 2018-04-01 | 2018-04-03 17:45 | 99864.2595 | 99864 | [7 empty] | 0 | 0 | 9.77 | 13.19 | 5167.92
DRE2 | BW\24\011\D | BW | 24 | 11 | D | 6 DL | 100 | 52.7972 | 52.7972 | 2018-04-01 | 2018-04-03 17:43 | 224020.1669 |  |  |  | 9770 | 224020 | 161638 |  |  | 0 | 20.32 | 0 | 6.17 | 5871.59
PH4100XPC#1 | DT\28\007\D | DT | 28 | 7 | D | 1 Prestrip - Thick | 100 | 11.9854 | 11.9854 | 2018-04-01 | 2018-04-02 12:44 | 90076.7398 | 90077 | [7 empty] | 0 | 0 | 5.69 | 6.97 | 5800.59
TS5500Shv | DT\28\001\D | DT | 28 | 1 | D | 1 Prestrip - Thick | 84.2526 | 66.6597 | 66.6597 | 2018-04-01 | 2018-04-15 00:44 | 378209.4981 | 378209 | [7 empty] | 0 | 0 | 14.6 | 6.01 | 5884.9
TS6060#1 | BW\27\011\B | BW | 27 | 11 | B | 1 Prestrip - Thick | 28.7136 | 0 | 27.4021 | 2018-04-01 | 2018-04-09 20:30 | 227034.0583 | 227034 | [7 empty] | 0 | 0 | 13.87 | 0 | 0
TS5500Exc | SC\32\014\D | SC | 32 | 14 | D | 7 PostStrip | 100 | 0 | 66.6611 | 2018-04-01 | 2018-04-02 07:55 | 29502.2331 |  |  | 29502 | [5 empty] | 0 | 0 | 0 | 7.49 | 5754.14
TS5500Exc | SC\32\014\D | SC | 32 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-04-02 07:55 | 2018-04-03 23:18 | 51825.2695 | [6 empty] | 51825 | 38793 | 4.54 | 0 | 0 | 7.49 | 5754
PH4100XPC#1 | DT\25\001\B | DT | 25 | 1 | B | 1 Prestrip - Thick | 100 | 27.933 | 27.933 | 2018-04-02 12:44 | 2018-04-02 20:48 | 19042.1813 | 19042 | [7 empty] | 0 | 0 | 0.93 | 11.56 | 5343.53
PH4100XPC#1 | MW\27\003\B | MW | 27 | 3 | B | 1 Prestrip - Thick | 100 | 0.50998 | 0.50998 | 2018-04-02 20:48 | 2018-04-02 22:22 | 3887.8703 | 3888 | [7 empty] | 0 | 0 | 0.24 | 8.34 | 5632.08
PH4100XPC#1 | MW\28\003\A | MW | 28 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-04-02 22:22 | 2018-04-14 13:22 | 690955.0255 | 690955 | [7 empty] | 0 | 0 | 42.63 | 11.93 | 5318.18
DRE2 | BW\24\010\D | BW | 24 | 10 | D | 6 DL | 100 | 100 | 100 | 2018-04-03 17:43 | 2018-04-09 02:17 | 438224.6332 |  |  |  | 19112 | 438225 | 316194 |  |  | 0 | 21.01 | 0 | 5.88 | 5897.88
PH4100A | RS\06\007\A | RS | 6 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-04-03 17:45 | 2018-04-14 02:27 | 378171.6474 | 378172 | [7 empty] | 0 | 0 | 36.83 | 15.07 | 5050.2
TS5500Exc | DT\24\002\D | DT | 24 | 2 | D | 8 Coal Mining | 30.1 | 0 | 30.1 | 2018-04-03 23:18 | 2018-04-04 22:45 | 30854.8355 | [6 empty] | 30855 | 23239 | 1.41 | 0 | 0 | 6.04 | 5882
TS5500Exc | DT\25\001\B | DT | 25 | 1 | B | 8 Coal Mining | 9.3 | 0 | 9.3 | 2018-04-04 22:45 | 2018-04-05 05:02 | 8269.278 | [6 empty] | 8269 | 6018 | 0.29 | 0 | 0 | 11.56 | 5344
TS5500Exc | DT\25\001\B | DT | 25 | 1 | B | 8 Coal Mining | 41.6 | 0 | 41.6 | 2018-04-05 05:02 | 2018-04-06 09:14 | 37119.7851 | [6 empty] | 37120 | 27013 | 1.32 | 0 | 0 | 11.56 | 5344
DRE1 | SC\32\012\D | SC | 32 | 12 | D | 6 DL | 100 | 0 | 100 | 2018-04-05 17:52 | 2018-04-13 05:11 | 634737.9691 |  |  |  | 48269 | 634738 | 434421 |  |  | 0 | 40 | 0 | 7.65 | 5739.94
TS5500Exc | SC\32\013\D | SC | 32 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-04-06 09:14 | 2018-04-08 16:53 | 73219.7507 | [6 empty] | 73220 | 54765 | 4.56 | 0 | 0 | 7.64 | 5741
TS Fleet 5 | BW\27\010\A | BW | 27 | 10 | A | 1 Prestrip - Thick | 68.447 | 0 | 68.447 | 2018-04-08 07:43 | 2018-04-19 05:30 | 513090.8733 | 513091 | [7 empty] | 0 | 0 | 31.69 | 0 | 0
TS5500Exc | MW\27\008\A | MW | 27 | 8 | A | 1 Prestrip - Thick | 0.9213 | 0.9213 | 0.9213 | 2018-04-08 16:53 | 2018-04-08 21:14 | 4053.0772 | 4053 | [7 empty] | 0 | 0 | 0.25 | 11.39 | 5273.97
TS5500Exc | DT\26\005\B | DT | 26 | 5 | B | 8 Coal Mining | 20 | 0 | 20 | 2018-04-08 21:14 | 2018-04-09 01:38 | 5795.069 | [6 empty] | 5795 | 4182 | 0.17 | 0 | 0 | 12.6 | 5196
TS5500Exc | DT\26\006\A | DT | 26 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-04-09 01:38 | 2018-04-09 20:18 | 24566.1004 | [6 empty] | 24566 | 17977 | 1.13 | 0 | 0 | 11.02 | 5369
DRE2 | BW\24\009\D | BW | 24 | 9 | D | 6 DL | 100 | 100 | 100 | 2018-04-09 02:17 | 2018-04-14 19:46 | 468656.8442 |  |  |  | 20440 | 468657 | 338152 |  |  | 0 | 22.54 | 0 | 5.35 | 5945.04
TS5500Exc | DT\26\007\A | DT | 26 | 7 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-04-09 20:18 | 2018-04-10 17:25 | 27778.9483 | [6 empty] | 27779 | 20375 | 1.33 | 0 | 0 | 10.67 | 5396
TS6060#1 | BW\27\009\B | BW | 27 | 9 | B | 8 Coal Mining | 69.9 | 0 | 69.9 | 2018-04-09 20:30 | 2018-04-11 14:55 | 59981.1746 | [6 empty] | 59981 | 43144 | 2.7 | 0 | 0 | 13.96 | 5179
TS5500Exc | DT\27\002\B | DT | 27 | 2 | B | 8 Coal Mining | 13.5 | 0 | 13.5 | 2018-04-10 17:25 | 2018-04-11 03:27 | 13201.8024 | [6 empty] | 13202 | 9587 | 0.39 | 0 | 0 | 11.58 | 5314
TS5500Exc | DT\27\004\A | DT | 27 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-04-11 03:27 | 2018-04-11 18:43 | 20099.9078 | [6 empty] | 20100 | 13922 | 1.73 | 0 | 0 | 20.99 | 4620
TS6060#1 | DT\24\007\B | DT | 24 | 7 | B | 8 Coal Mining | 100 | 0 | 2.2 | 2018-04-11 14:55 | 2018-04-11 15:57 | 1475.3977 | [6 empty] | 1475 | 1098 | 0.07 | 0 | 0 | 8.16 | 5622
TS6060#1 | BW\27\009\B | BW | 27 | 9 | B | 8 Coal Mining | 30.1 | 0 | 30.1 | 2018-04-11 15:57 | 2018-04-12 10:13 | 25810.4312 | [6 empty] | 25810 | 18565 | 1.16 | 0 | 0 | 13.96 | 5179
TS5500Exc | DT\27\005\B | DT | 27 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-04-11 18:43 | 2018-04-12 15:21 | 27156.6658 | [6 empty] | 27157 | 19803 | 0.76 | 0 | 0 | 10.71 | 5353
TS6060#1 | BW\24\011\D | BW | 24 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-04-12 10:13 | 2018-04-15 09:58 | 101454.9036 | [6 empty] | 101455 | 76412 | 4.78 | 0 | 0 | 6.17 | 5872
TS5500Exc | MW\27\009\B | MW | 27 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-04-12 15:21 | 2018-04-15 16:57 | 67999.9795 | 68000 | [7 empty] | 0 | 0 | 4.25 | 10.08 | 5507.46
DRE1 | SC\32\011\D | SC | 32 | 11 | D | 6 DL | 100 | 0 | 100 | 2018-04-13 05:11 | 2018-04-20 14:43 | 628372.9871 |  |  |  | 47785 | 628373 | 430065 |  |  | 0 | 40 | 0 | 7.61 | 5744.63
PH4100A | RS\06\008\A | RS | 6 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-04-14 02:27 | 2018-04-23 11:48 | 342913.0231 | 342913 | [7 empty] | 0 | 0 | 39.82 | 16.43 | 4983.39
PH4100XPC#1 | MW\27\004\A | MW | 27 | 4 | A | 1 Prestrip - Thick | 100 | 55.0402 | 55.0402 | 2018-04-14 13:22 | 2018-04-19 14:29 | 288379.1875 | 288379 | [7 empty] | 0 | 0 | 16.99 | 9.71 | 5506.67
DRE2 | DT\24\007\D | DT | 24 | 7 | D | 6 DL | 100 | 100 | 100 | 2018-04-14 19:46 | 2018-04-21 05:31 | 524084.4965 |  |  |  | 31299 | 524084 | 369966 |  |  | 0 | 25.23 | 0 | 6.05 | 5880.48
TS5500Shv | MW\27\003\B | MW | 27 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-04-15 00:44 | 2018-04-17 00:21 | 60663.3958 | [6 empty] | 60663 | 45276 | 2.82 | 0 | 0 | 8.34 | 5632
TS6060#1 | BW\28\005\X2 | BW | 28 | 5 | X2 | 1 Prestrip - Thick | 28.246 | 0 | 28.246 | 2018-04-15 09:58 | 2018-04-25 16:12 | 264112.1447 | 264112 | [7 empty] | 0 | 0 | 10.06 | 0 | 0
TS5500Exc | MW\28\003\A | MW | 28 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-04-15 16:57 | 2018-04-16 03:30 | 13884.4267 | [6 empty] | 13884 | 10116 | 0.61 | 0 | 0 | 11.93 | 5318
TS5500Exc | SC\32\012\D | SC | 32 | 12 | D | 8 Coal Mining | 59.7 | 0 | 59.7 | 2018-04-16 03:30 | 2018-04-17 12:20 | 43208.6705 | [6 empty] | 43209 | 32266 | 2.69 | 0 | 0 | 7.65 | 5740
TS5500Shv | MW\28\003\A | MW | 28 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-04-17 00:21 | 2018-04-17 10:54 | 13441.3067 | [6 empty] | 13441 | 9794 | 0.59 | 0 | 0 | 11.93 | 5318
TS5500Shv | DT\24\001\D | DT | 24 | 1 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-04-17 10:54 | 2018-04-19 04:34 | 53083.4846 | [6 empty] | 53083 | 39853 | 2.31 | 0 | 0 | 6.25 | 5864
TS5500Exc | SC\32\012\D | SC | 32 | 12 | D | 8 Coal Mining | 40.3 | 0 | 40.3 | 2018-04-17 12:20 | 2018-04-18 10:31 | 29196.3375 | [6 empty] | 29196 | 21802 | 1.82 | 0 | 0 | 7.65 | 5740
TS5500Exc | MW\27\010\B | MW | 27 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-04-18 10:31 | 2018-04-20 18:27 | 51679.8589 | 51680 | [7 empty] | 0 | 0 | 3.23 | 8.88 | 5653.41
TS5500Shv | DT\24\002\D | DT | 24 | 2 | D | 8 Coal Mining | 69.9 | 0 | 69.9 | 2018-04-19 04:34 | 2018-04-21 12:51 | 71699.7771 | [6 empty] | 71700 | 54001 | 3.28 | 0 | 0 | 6.04 | 5882
TS Fleet 5 | BW\27\010\B | BW | 27 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-04-19 05:30 | 2018-04-20 20:38 | 76696.7595 | 76697 | [7 empty] | 0 | 0 | 4.78 | 16.29 | 4971.59
PH4100XPC#1 | MW\28\004\A | MW | 28 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-04-19 14:29 | 2018-04-29 00:08 | 543807.4671 | 543807 | [7 empty] | 0 | 0 | 34.62 | 9.99 | 5473.99
DRE1 | SC\32\010\D | SC | 32 | 10 | D | 6 DL | 100 | 0 | 100 | 2018-04-20 14:43 | 2018-04-27 18:55 | 609542.1717 |  |  |  | 46353 | 609542 | 417177 |  |  | 0 | 40 | 0 | 7.46 | 5758.6
TS5500Exc | MW\27\004\A | MW | 27 | 4 | A | 8 Coal Mining | 100 | 0 | 65.9 | 2018-04-20 18:27 | 2018-04-22 09:53 | 51894.569 | [6 empty] | 51895 | 38329 | 2.37 | 0 | 0 | 9.71 | 5507
TS Fleet 5 | BW\27\011\B | BW | 27 | 11 | B | 1 Prestrip - Thick | 39.984 | 0 | 39.984 | 2018-04-20 20:38 | 2018-04-27 21:39 | 331277.8767 | 331278 | [7 empty] | 0 | 0 | 20.23 | 0 | 0
DRE2 | BW\24\008\D | BW | 24 | 8 | D | 6 DL | 100 | 100 | 100 | 2018-04-21 05:31 | 2018-04-26 15:57 | 444541.2138 |  |  |  | 19388 | 444541 | 320752 |  |  | 0 | 21.32 | 0 | 5.06 | 5968.74
TS5500Shv | MW\27\004\A | MW | 27 | 4 | A | 8 Coal Mining | 92.7 | 0 | 34.1 | 2018-04-21 12:51 | 2018-04-22 09:53 | 26800.2032 | [6 empty] | 26800 | 19794 | 1.22 | 0 | 0 | 9.71 | 5507
TS5500Shv | DT\24\007\D | DT | 24 | 7 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-04-22 09:53 | 2018-04-23 23:07 | 47446.8761 | [6 empty] | 47447 | 35848 | 2.26 | 0 | 0 | 6.05 | 5880
TS5500Exc | DT\24\007\D | DT | 24 | 7 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-04-22 09:53 | 2018-04-23 23:07 | 49011.0589 | [6 empty] | 49011 | 37030 | 2.33 | 0 | 0 | 6.05 | 5880
PH4100A | SC\32\020\D | SC | 32 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-04-23 11:48 | 2018-04-24 17:20 | 46591.554 | 46592 | [7 empty] | 0 | 0 | 3.72 | 7.16 | 5783.99
TS5500Shv | DT\25\001\B | DT | 25 | 1 | B | 8 Coal Mining | 9 | 0 | 9 | 2018-04-23 23:07 | 2018-04-24 05:24 | 8005.3649 | [6 empty] | 8005 | 5826 | 0.28 | 0 | 0 | 11.56 | 5344
TS5500Exc | MW\27\004\B | MW | 27 | 4 | B | 1 Prestrip - Thick | 3.6832 | 3.6832 | 3.6832 | 2018-04-23 23:07 | 2018-04-24 01:17 | 1996.2806 | 1996 | [7 empty] | 0 | 0 | 0.12 | 9.09 | 5583.28
TS5500Exc | MW\27\004\B | MW | 27 | 4 | B | 1 Prestrip - Thick | 96.3168 | 96.3168 | 96.3168 | 2018-04-24 01:17 | 2018-04-26 09:47 | 52203.119 | 52203 | [7 empty] | 0 | 0 | 3.23 | 9.09 | 5583.28
TS5500Shv | DT\28\002\B | DT | 28 | 2 | B | 1 Prestrip - Thick | 3.0749 | 3.0749 | 3.0749 | 2018-04-24 05:24 | 2018-04-24 07:34 | 2421.4093 | 2421 | [7 empty] | 0 | 0 | 0.14 | 11.99 | 5282.63
TS5500Shv | DT\28\002\B | DT | 28 | 2 | B | 1 Prestrip - Thick | 96.9251 | 96.9251 | 96.9251 | 2018-04-24 07:34 | 2018-04-27 03:40 | 76325.9126 | 76326 | [7 empty] | 0 | 0 | 4.55 | 11.99 | 5282.63
PH4100A | SC\33\011\D | SC | 33 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-04-24 17:20 | 2018-04-27 13:32 | 109526.2115 | 109526 | [7 empty] | 0 | 0 | 9.04 | 7.63 | 5742.77
TS6060#1 | BW\27\010\B | BW | 27 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-04-25 16:12 | 2018-04-28 06:15 | 87757.7474 | [6 empty] | 87758 | 62473 | 3.91 | 0 | 0 | 16.29 | 4972
TS5500Exc | SC\32\011\D | SC | 32 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-04-26 09:47 | 2018-04-28 18:50 | 75075.0023 | [6 empty] | 75075 | 56020 | 4.68 | 0 | 0 | 7.61 | 5745
DRE2 | BW\24\007\D | BW | 24 | 7 | D | 6 DL | 100 | 81.5989 | 81.5989 | 2018-04-26 15:57 | 2018-05-01 | 354664.6454 |  |  |  | 15468 | 354665 | 255903 |  |  | 0 | 20.82 | 0 | 5.1 | 5966
TS5500Shv | MW\27\004\B | MW | 27 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-04-27 03:40 | 2018-04-29 05:23 | 63336.0601 | [6 empty] | 63336 | 46973 | 2.92 | 0 | 0 | 9.09 | 5583
PH4100A | SC\33\012\D | SC | 33 | 12 | D | 1 Prestrip - Thick | 100 | 93.9448 | 93.9448 | 2018-04-27 13:32 | 2018-05-01 | 129771.9592 | 129772 | [7 empty] | 0 | 0 | 11.12 | 7.67 | 5738.37
DRE1 | SC\32\005\D | SC | 32 | 5 | D | 6 DL | 100 | 0 | 0 | 2018-04-27 18:55 | 2018-04-27 18:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE1 | SC\32\006\D | SC | 32 | 6 | D | 6 DL | 100 | 0 | 0 | 2018-04-27 18:55 | 2018-04-27 18:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE1 | SC\32\007\D | SC | 32 | 7 | D | 6 DL | 100 | 0 | 0 | 2018-04-27 18:55 | 2018-04-27 18:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE1 | SC\32\008\D | SC | 32 | 8 | D | 6 DL | 100 | 0 | 0 | 2018-04-27 18:55 | 2018-04-27 18:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE1 | SC\32\009\D | SC | 32 | 9 | D | 6 DL | 100 | 0 | 0 | 2018-04-27 18:55 | 2018-04-27 18:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE1 | SC\32\015\D | SC | 32 | 15 | D | 6 DL | 100 | 0 | 49.926 | 2018-04-27 18:55 | 2018-05-01 | 272846.3526 |  |  |  | 15572 | 272846 | 206887 |  |  | 0 | 32.14 | 0 | 7.32 | 5768.61
TS Fleet 5 | BW\27\011\B | BW | 27 | 11 | B | 1 Prestrip - Thick | 31.3025 | 0 | 17.5864 | 2018-04-27 21:39 | 2018-05-01 | 145708.212 | 145708 | [7 empty] | 0 | 0 | 8.9 | 0 | 0
TS6060#1 | BW\28\005\X2 | BW | 28 | 5 | X2 | 1 Prestrip - Thick | 2.5231 | 0 | 2.5231 | 2018-04-28 06:15 | 2018-04-29 04:15 | 23592.1465 | 23592 | [7 empty] | 0 | 0 | 0.9 | 0 | 0
TS5500Exc | SC\32\010\D | SC | 32 | 10 | D | 8 Coal Mining | 100 | 0 | 89.8 | 2018-04-28 18:50 | 2018-05-01 | 69961.1347 | [6 empty] | 69961 | 52330 | 4.36 | 0 | 0 | 7.46 | 5759
PH4100XPC#1 | MW\27\005\A | MW | 27 | 5 | A | 1 Prestrip - Thick | 100 | 35.3063 | 35.3063 | 2018-04-29 00:08 | 2018-05-01 | 108439.9556 | 108440 | [7 empty] | 0 | 0 | 6.73 | 9.45 | 5521.99
TS6060#1 | BW\24\009\D | BW | 24 | 9 | D | 8 Coal Mining | 100 | 0 | 57.7 | 2018-04-29 04:15 | 2018-05-01 | 61849.3084 | [6 empty] | 61849 | 46953 | 2.94 | 0 | 0 | 5.35 | 5945
TS5500Shv | MW\28\004\A | MW | 28 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-04-29 05:23 | 2018-04-30 11:59 | 38983.8737 | [6 empty] | 38984 | 28718 | 1.77 | 0 | 0 | 9.99 | 5474
TS5500Shv | DT\25\001\B | DT | 25 | 1 | B | 8 Coal Mining | 40.2 | 0 | 17.1 | 2018-04-30 11:59 | 2018-05-01 | 15298.3957 | [6 empty] | 15298 | 11133 | 0.54 | 0 | 0 | 11.56 | 5344
| EOP 52 : 2018\Apr | EOP 52 : 2018 | Apr | [6 empty] | 2018-05-01 | 2018-05-01 |  | 5412255 |  | 29502 | 302123 | 5002776 | 3541006 | 1389206 | 1029429 | 70.07 | 0 | 360.99 | 8.69 | 5635.15
TS Fleet 5 | BW\27\011\B | BW | 27 | 11 | B | 1 Prestrip - Thick | 31.3025 | 0 | 13.716 | 2018-05-01 | 2018-05-03 09:09 | 113641.088 | 113641 | [7 empty] | 0 | 0 | 6.94 | 0 | 0
DRE1 | SC\32\015\D | SC | 32 | 15 | D | 6 DL | 100 | 0 | 50.074 | 2018-05-01 | 2018-05-04 05:18 | 273655.4309 |  |  |  | 15618 | 273655 | 207501 |  |  | 0 | 32.14 | 0 | 7.32 | 5768.61
PH4100A | SC\33\012\D | SC | 33 | 12 | D | 1 Prestrip - Thick | 100 | 6.0552 | 6.0552 | 2018-05-01 | 2018-05-01 04:35 | 8364.4114 | 8364 | [7 empty] | 0 | 0 | 0.72 | 7.67 | 5738.37
DRE2 | BW\24\007\D | BW | 24 | 7 | D | 6 DL | 100 | 18.4011 | 18.4011 | 2018-05-01 | 2018-05-01 23:27 | 79979.3534 |  |  |  | 3488 | 79979 | 57708 |  |  | 0 | 20.82 | 0 | 5.1 | 5966
PH4100XPC#1 | MW\27\005\A | MW | 27 | 5 | A | 1 Prestrip - Thick | 100 | 64.6937 | 64.6937 | 2018-05-01 | 2018-05-04 14:30 | 198700.856 | 198701 | [7 empty] | 0 | 0 | 12.34 | 9.45 | 5521.99
TS5500Shv | DT\25\001\B | DT | 25 | 1 | B | 8 Coal Mining | 40.2 | 0 | 23.1 | 2018-05-01 | 2018-05-01 15:58 | 20636.7153 | [6 empty] | 20637 | 15018 | 0.73 | 0 | 0 | 11.56 | 5344
TS6060#1 | BW\24\009\D | BW | 24 | 9 | D | 8 Coal Mining | 100 | 0 | 42.3 | 2018-05-01 | 2018-05-02 07:36 | 45321.3978 | [6 empty] | 45321 | 34406 | 2.15 | 0 | 0 | 5.35 | 5945
TS5500Exc | SC\32\010\D | SC | 32 | 10 | D | 8 Coal Mining | 100 | 0 | 10.2 | 2018-05-01 | 2018-05-01 05:57 | 7952.8257 | [6 empty] | 7953 | 5949 | 0.5 | 0 | 0 | 7.46 | 5759
PH4100A | SC\33\013\D | SC | 33 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-05-01 04:35 | 2018-05-04 17:32 | 153530.1172 | 153530 | [7 empty] | 0 | 0 | 13.2 | 7.67 | 5738.06
TS5500Exc | MW\28\004\A | MW | 28 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-05-01 05:57 | 2018-05-02 12:07 | 40269.0564 | [6 empty] | 40269 | 29665 | 1.83 | 0 | 0 | 9.99 | 5474
TS5500Shv | DT\25\006\A | DT | 25 | 6 | A | 8 Coal Mining | 35.5 | 0 | 35.5 | 2018-05-01 15:58 | 2018-05-02 09:55 | 23198.2859 | [6 empty] | 23198 | 17007 | 1.24 | 0 | 0 | 10.74 | 5388
DRE2 | BW\24\006\D | BW | 24 | 6 | D | 6 DL | 100 | 100 | 100 | 2018-05-01 23:27 | 2018-05-07 21:44 | 484964.6497 |  |  |  | 21151 | 484965 | 349918 |  |  | 0 | 23.18 | 0 | 5.36 | 5944.67
TS6060#1 | BW\24\008\D | BW | 24 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-05-02 07:36 | 2018-05-05 07:18 | 102842.7265 | [6 empty] | 102843 | 78266 | 4.89 | 0 | 0 | 5.06 | 5969
TS5500Shv | DT\25\007\A | DT | 25 | 7 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-05-02 09:55 | 2018-05-03 17:05 | 40284.2694 | [6 empty] | 40284 | 29623 | 1.85 | 0 | 0 | 10.19 | 5428
TS5500Exc | MW\27\011\A | MW | 27 | 11 | A | 1 Prestrip - Thick | 42.3301 | 42.3301 | 42.3301 | 2018-05-02 12:07 | 2018-05-09 13:10 | 158437.2319 | 158437 | [7 empty] | 0 | 0 | 8.36 | 11.51 | 5413.05
TS Fleet 5 | BW\28\005\X2 | BW | 28 | 5 | X2 | 1 Prestrip - Thick | 69.2309 | 0 | 69.2309 | 2018-05-03 09:09 | 2018-05-16 22:47 | 647338.1723 | 647338 | [7 empty] | 0 | 0 | 24.66 | 0 | 0
TS5500Shv | DT\26\001\B | DT | 26 | 1 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-05-03 17:05 | 2018-05-05 05:30 | 47052.804 | [6 empty] | 47053 | 34233 | 1.51 | 0 | 0 | 11.67 | 5333
DRE1 | SC\32\016\D | SC | 32 | 16 | D | 6 DL | 100 | 0 | 100 | 2018-05-04 05:18 | 2018-05-11 01:14 | 580266.5355 |  |  |  | 41267 | 580267 | 417260 |  |  | 0 | 38.55 | 0 | 7.39 | 5763.45
PH4100XPC#1 | DT\25\006\B | DT | 25 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-05-04 14:30 | 2018-05-05 10:18 | 47376.5402 | 47377 | [7 empty] | 0 | 0 | 3.45 | 8.58 | 5570.9
PH4100A | SC\33\014\D | SC | 33 | 14 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-05-04 17:32 | 2018-05-09 12:56 | 206374.7844 | 206375 | [7 empty] | 0 | 0 | 18.56 | 7.52 | 5751.01
TS5500Shv | DT\26\002\B | DT | 26 | 2 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-05-05 05:30 | 2018-05-06 15:32 | 43970.2693 | [6 empty] | 43970 | 31913 | 1.44 | 0 | 0 | 11.59 | 5313
TS6060#1 | BW\24\007\D | BW | 24 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-05-05 07:18 | 2018-05-08 07:31 | 103578.2548 | [6 empty] | 103578 | 78825 | 4.93 | 0 | 0 | 5.1 | 5966
PH4100XPC#1 | DT\25\007\B | DT | 25 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-05-05 10:18 | 2018-05-06 10:43 | 58397.3461 | 58397 | [7 empty] | 0 | 0 | 3.64 | 8.24 | 5620.5
PH4100XPC#1 | MW\28\005\A | MW | 28 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-05-06 10:43 | 2018-05-11 16:59 | 294134.1327 | 294134 | [7 empty] | 0 | 0 | 18.51 | 9.53 | 5507.69
TS5500Shv | DT\25\006\B | DT | 25 | 6 | B | 8 Coal Mining | 98.5 | 0 | 98.5 | 2018-05-06 15:32 | 2018-05-08 09:29 | 54209.4327 | [6 empty] | 54209 | 40182 | 2.94 | 0 | 0 | 8.58 | 5571
DRE2 | BW\24\005\D | BW | 24 | 5 | D | 6 DL | 100 | 100 | 100 | 2018-05-07 21:44 | 2018-05-13 18:33 | 479962.6556 |  |  |  | 20933 | 479963 | 346309 |  |  | 0 | 22.95 | 0 | 5.51 | 5930.51
TS6060#1 | BW\24\010\D | BW | 24 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-05-08 07:31 | 2018-05-11 08:46 | 105055.462 | [6 empty] | 105055 | 79374 | 4.96 | 0 | 0 | 5.88 | 5898
TS5500Shv | DT\25\007\B | DT | 25 | 7 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-05-08 09:29 | 2018-05-09 09:51 | 31498.2753 | [6 empty] | 31498 | 23450 | 1.46 | 0 | 0 | 8.24 | 5621
TS5500Shv | DT\26\004\B | DT | 26 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-05-09 09:51 | 2018-05-10 10:44 | 32140.0828 | [6 empty] | 32140 | 23480 | 1.46 | 0 | 0 | 9.91 | 5387
PH4100A | SC\33\019\D | SC | 33 | 19 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-05-09 12:56 | 2018-05-14 11:21 | 213428.3072 | 213428 | [7 empty] | 0 | 0 | 18.26 | 7.24 | 5774.38
TS5500Exc | MW\27\005\A | MW | 27 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-05-09 13:10 | 2018-05-10 14:52 | 34297.3029 | [6 empty] | 34297 | 25399 | 1.58 | 0 | 0 | 9.45 | 5522
TS5500Shv | DT\26\005\B | DT | 26 | 5 | B | 8 Coal Mining | 60.7 | 0 | 60.7 | 2018-05-10 10:44 | 2018-05-11 00:20 | 17589.3187 | [6 empty] | 17589 | 12693 | 0.53 | 0 | 0 | 12.6 | 5196
TS5500Exc | DT\25\006\B | DT | 25 | 6 | B | 8 Coal Mining | 1.5 | 0 | 1.5 | 2018-05-10 14:52 | 2018-05-10 15:28 | 807.6445 | [6 empty] | 808 | 599 | 0.04 | 0 | 0 | 8.58 | 5571
TS5500Exc | DT\25\007\B | DT | 25 | 7 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-05-10 15:28 | 2018-05-11 15:51 | 32536.68 | [6 empty] | 32537 | 24223 | 1.51 | 0 | 0 | 8.24 | 5621
TS5500Shv | DT\29\001\D | DT | 29 | 1 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-05-11 00:20 | 2018-05-19 16:24 | 237076.6553 | 237077 | [7 empty] | 0 | 0 | 16.13 | 6.06 | 5880.2
DRE1 | SC\32\017\D | SC | 32 | 17 | D | 6 DL | 100 | 0 | 100 | 2018-05-11 01:14 | 2018-05-18 10:00 | 625680.6866 |  |  |  | 47580 | 625681 | 428223 |  |  | 0 | 40 | 0 | 7.36 | 5764.71
TS6060#1 | BW\24\006\D | BW | 24 | 6 | D | 8 Coal Mining | 73.9 | 0 | 73.9 | 2018-05-11 08:46 | 2018-05-13 17:30 | 81352.8505 | [6 empty] | 81353 | 61758 | 3.86 | 0 | 0 | 5.36 | 5945
TS5500Exc | SC\32\015\D | SC | 32 | 15 | D | 8 Coal Mining | 25.1 | 0 | 25.1 | 2018-05-11 15:51 | 2018-05-12 05:28 | 18169.1864 | [6 empty] | 18169 | 13600 | 1.13 | 0 | 0 | 7.32 | 5769
PH4100XPC#1 | MW\27\006\B | MW | 27 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-05-11 16:59 | 2018-05-20 02:32 | 438841.9115 | 438842 | [7 empty] | 0 | 0 | 26.95 | 9.18 | 5641.34
TS5500Exc | MW\28\005\A | MW | 28 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-05-12 05:28 | 2018-05-13 07:21 | 34562.4587 | [6 empty] | 34562 | 25567 | 1.59 | 0 | 0 | 9.53 | 5508
TS5500Exc | SC\32\015\D | SC | 32 | 15 | D | 8 Coal Mining | 74.9 | 0 | 74.9 | 2018-05-13 07:21 | 2018-05-14 23:58 | 54221.8696 | [6 empty] | 54222 | 40587 | 3.38 | 0 | 0 | 7.32 | 5769
TS6060#1 | BW\28\006\B | BW | 28 | 6 | B | 1 Prestrip - Thick | 36.6429 | 36.6429 | 36.6429 | 2018-05-13 17:30 | 2018-05-27 09:18 | 354228.8821 | 354229 | [7 empty] | 0 | 0 | 22.19 | 11.56 | 5397.54
DRE2 | BW\24\004\D | BW | 24 | 4 | D | 6 DL | 100 | 100 | 100 | 2018-05-13 18:33 | 2018-05-19 15:18 | 479784.3701 |  |  |  | 20925 | 479784 | 346181 |  |  | 0 | 22.95 | 0 | 5.78 | 5905.69
PH4100A | SC\33\020\D | SC | 33 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-05-14 11:21 | 2018-05-18 03:26 | 158854.8838 | 158855 | [7 empty] | 0 | 0 | 13.65 | 7.31 | 5770.2
TS5500Exc | SC\32\016\D | SC | 32 | 16 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-05-14 23:58 | 2018-05-17 07:25 | 73992.7847 | [6 empty] | 73993 | 55255 | 4.6 | 0 | 0 | 7.39 | 5763
TS Fleet 5 | BW\28\005\B | BW | 28 | 5 | B | 1 Prestrip - Thick | 62.07 | 62.07 | 62.07 | 2018-05-16 22:47 | 2018-05-26 18:21 | 468312.5277 | 468313 | [7 empty] | 0 | 0 | 17.89 | 10.62 | 5475.83
TS5500Exc | MW\27\011\A | MW | 27 | 11 | A | 1 Prestrip - Thick | 57.6699 | 57.6699 | 57.6699 | 2018-05-17 07:25 | 2018-05-26 21:43 | 215852.4884 | 215852 | [7 empty] | 0 | 0 | 11.39 | 11.51 | 5413.05
PH4100A | SC\33\021\D | SC | 33 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-05-18 03:26 | 2018-05-20 14:57 | 107863.0904 | 107863 | [7 empty] | 0 | 0 | 8.57 | 7.25 | 5776.5
DRE1 | SC\32\018\D | SC | 32 | 18 | D | 6 DL | 100 | 0 | 100 | 2018-05-18 10:00 | 2018-05-25 19:38 | 628762.07 |  |  |  | 47815 | 628762 | 430331 |  |  | 0 | 40 | 0 | 7.31 | 5768.95
DRE2 | BW\24\003\D | BW | 24 | 3 | D | 6 DL | 100 | 100 | 100 | 2018-05-19 15:18 | 2018-05-25 11:52 | 479127.7106 |  |  |  | 20896 | 479128 | 345707 |  |  | 0 | 22.91 | 0 | 6.3 | 5860.39
TS5500Shv | DT\30\001\D | DT | 30 | 1 | D | 1 Prestrip - Thick | 57.8277 | 57.8277 | 57.8277 | 2018-05-19 16:24 | 2018-05-24 20:59 | 141908.2663 | 141908 | [7 empty] | 0 | 0 | 11.83 | 6.14 | 5873.3
PH4100XPC#1 | MW\28\006\A | MW | 28 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-05-20 02:32 | 2018-05-27 03:22 | 361072.2253 | 361072 | [7 empty] | 0 | 0 | 22.04 | 12.21 | 5288.61
PH4100A | SC\34\011\D | SC | 34 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-05-20 14:57 | 2018-05-23 11:33 | 125966.877 | 125967 | [7 empty] | 0 | 0 | 10.67 | 7.65 | 5740.97
PH4100A | SC\34\012\D | SC | 34 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-05-23 11:33 | 2018-05-26 09:54 | 127877.1772 | 127877 | [7 empty] | 0 | 0 | 11.01 | 7.67 | 5738.78
TS5500Shv | DT\30\001\D | DT | 30 | 1 | D | 1 Prestrip - Thick | 42.1723 | 42.1723 | 42.1723 | 2018-05-24 20:59 | 2018-05-28 15:49 | 103490.2977 | 103490 | [7 empty] | 0 | 0 | 8.63 | 6.14 | 5873.3
DRE2 | BW\24\002\D | BW | 24 | 2 | D | 6 DL | 100 | 100 | 100 | 2018-05-25 11:52 | 2018-05-29 18:12 | 348833.3574 |  |  |  | 13240 | 348833 | 166733 |  |  | 0 | 22.2 | 0 | 6.47 | 5845.43
DRE1 | SC\32\019\D | SC | 32 | 19 | D | 6 DL | 100 | 80.9458 | 80.9458 | 2018-05-25 19:38 | 2018-06-01 | 525172.077 |  |  |  | 39937 | 525172 | 359433 |  |  | 0 | 41.42 | 0 | 7.3 | 5770.88
PH4100A | SC\34\013\D | SC | 34 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-05-26 09:54 | 2018-05-30 03:25 | 161229.1795 | 161229 | [7 empty] | 0 | 0 | 13.81 | 7.7 | 5735.38
TS Fleet 5 | BW\28\005\B | BW | 28 | 5 | B | 1 Prestrip - Thick | 32.5014 | 32.5014 | 32.5014 | 2018-05-26 18:21 | 2018-05-31 21:42 | 245220.1869 | 245220 | [7 empty] | 0 | 0 | 9.37 | 10.62 | 5475.83
TS5500Exc | MW\27\006\B | MW | 27 | 6 | B | 8 Coal Mining | 24.9 | 0 | 24.9 | 2018-05-26 21:43 | 2018-05-27 06:03 | 11122.8949 | [6 empty] | 11123 | 8236 | 0.51 | 0 | 0 | 9.18 | 5641
PH4100XPC#1 | MW\27\007\A | MW | 27 | 7 | A | 1 Prestrip - Thick | 100 | 61.0841 | 61.0841 | 2018-05-27 03:22 | 2018-06-01 | 249664.0136 | 249664 | [7 empty] | 0 | 0 | 15.36 | 10.95 | 5341.52
TS5500Exc | SC\32\017\D | SC | 32 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-05-27 06:03 | 2018-05-29 11:48 | 71725.0978 | [6 empty] | 71725 | 53433 | 4.45 | 0 | 0 | 7.36 | 5765
TS6060#1 | BW\28\005\B | BW | 28 | 5 | B | 1 Prestrip - Thick | 5.4286 | 5.4286 | 5.4286 | 2018-05-27 09:18 | 2018-05-28 22:46 | 40958.3849 | 40958 | [7 empty] | 0 | 0 | 1.56 | 10.62 | 5475.83
TS5500Shv | MW\28\006\A | MW | 28 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-05-28 15:49 | 2018-05-29 08:51 | 21999.7806 | [6 empty] | 22000 | 16066 | 0.96 | 0 | 0 | 12.21 | 5289
TS6060#1 | BW\28\007\B | BW | 28 | 7 | B | 1 Prestrip - Thick | 0.49618 | 0.49618 | 0.49618 | 2018-05-28 22:46 | 2018-05-29 03:35 | 5221.6082 | 5222 | [7 empty] | 0 | 0 | 0.31 | 11.9 | 5365.43
TS6060#1 | BW\28\007\B | BW | 28 | 7 | B | 1 Prestrip - Thick | 35.6943 | 7.0372 | 7.0372 | 2018-05-29 03:35 | 2018-06-01 | 74057.2355 | 74057 | [7 empty] | 0 | 0 | 4.46 | 11.9 | 5365.43
TS5500Shv | DT\26\005\B | DT | 26 | 5 | B | 8 Coal Mining | 19.3 | 0 | 19.3 | 2018-05-29 08:51 | 2018-05-29 13:11 | 5610.12 | [6 empty] | 5610 | 4048 | 0.17 | 0 | 0 | 12.6 | 5196
TS5500Exc | SC\32\018\D | SC | 32 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-05-29 11:48 | 2018-05-31 16:33 | 70422.7415 | [6 empty] | 70423 | 52378 | 4.37 | 0 | 0 | 7.31 | 5769
TS5500Shv | DT\26\006\A | DT | 26 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-05-29 13:11 | 2018-05-30 07:36 | 23782.0759 | [6 empty] | 23782 | 17403 | 1.09 | 0 | 0 | 11.02 | 5369
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2018-05-29 18:12 | 2018-05-31 18:12
PH4100A | SC\34\014\D | SC | 34 | 14 | D | 1 Prestrip - Thick | 100 | 31.1041 | 31.1041 | 2018-05-30 03:25 | 2018-06-01 | 79677.8963 | 79678 | [7 empty] | 0 | 0 | 5.82 | 7.56 | 5747.58
TS5500Shv | DT\26\007\A | DT | 26 | 7 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-05-30 07:36 | 2018-05-31 04:24 | 26892.3862 | [6 empty] | 26892 | 19724 | 1.29 | 0 | 0 | 10.67 | 5396
TS5500Shv | DT\27\002\B | DT | 27 | 2 | B | 8 Coal Mining | 86.5 | 0 | 25.9 | 2018-05-31 04:24 | 2018-06-01 | 25312.0454 | [6 empty] | 25312 | 18382 | 0.75 | 0 | 0 | 11.58 | 5314
TS5500Exc | MW\28\003\B | MW | 28 | 3 | B | 1 Prestrip - Thick | 100 | 13.3779 | 13.3779 | 2018-05-31 16:33 | 2018-06-01 | 6973.0812 | 6973 | [7 empty] | 0 | 0 | 0.43 | 8.34 | 5641.22
DRE2 | DT\25\004\D | DT | 25 | 4 | D | 6 DL | 100 | 3.6372 | 3.6372 | 2018-05-31 18:12 | 2018-06-01 | 19733.5034 |  |  |  | 861 | 19734 | 14238 |  |  | 0 | 26 | 0 | 6.25 | 5864.13
TS Fleet 5 | BW\28\006\B | BW | 28 | 6 | B | 1 Prestrip - Thick | 63.3571 | 0.47171 | 0.47171 | 2018-05-31 21:42 | 2018-06-01 | 4560.0251 | 4560 | [7 empty] | 0 | 0 | 0.29 | 11.56 | 5397.54
| EOP 53 : 2018\May | EOP 53 : 2018 | May | [6 empty] | 2018-06-01 | 2018-06-01 |  | 5808630 |  |  | 293712 | 5005922 | 3469543 | 1302407 | 970740 | 63.73 | 0 | 361 | 7.78 | 5711.08
TS Fleet 5 | BW\28\006\B | BW | 28 | 6 | B | 1 Prestrip - Thick | 63.3571 | 62.8854 | 62.8854 | 2018-06-01 | 2018-06-13 17:47 | 607916.7231 | 607917 | [7 empty] | 0 | 0 | 38.08 | 11.56 | 5397.54
DRE1 | SC\32\019\D | SC | 32 | 19 | D | 6 DL | 100 | 19.0542 | 19.0542 | 2018-06-01 | 2018-06-02 10:55 | 123622.8404 |  |  |  | 9401 | 123623 | 84609 |  |  | 0 | 41.42 | 0 | 7.3 | 5770.88
PH4100A | SC\34\014\D | SC | 34 | 14 | D | 1 Prestrip - Thick | 100 | 68.8959 | 68.8959 | 2018-06-01 | 2018-06-05 02:44 | 176487.5721 | 176488 | [7 empty] | 0 | 0 | 12.89 | 7.56 | 5747.58
DRE2 | DT\25\004\D | DT | 25 | 4 | D | 6 DL | 100 | 96.3628 | 96.3628 | 2018-06-01 | 2018-06-07 09:22 | 522810.3391 |  |  |  | 22802 | 522810 | 377225 |  |  | 0 | 26 | 0 | 6.25 | 5864.13
PH4100XPC#1 | MW\27\007\A | MW | 27 | 7 | A | 1 Prestrip - Thick | 100 | 38.9159 | 38.9159 | 2018-06-01 | 2018-06-04 02:18 | 159057.8657 | 159058 | [7 empty] | 0 | 0 | 9.79 | 10.95 | 5341.52
TS5500Shv | DT\27\002\B | DT | 27 | 2 | B | 8 Coal Mining | 86.5 | 0 | 60.5 | 2018-06-01 | 2018-06-02 21:43 | 59078.1246 | [6 empty] | 59078 | 42904 | 1.75 | 0 | 0 | 11.58 | 5314
TS6060#1 | BW\28\007\B | BW | 28 | 7 | B | 1 Prestrip - Thick | 35.6943 | 28.6571 | 28.6571 | 2018-06-01 | 2018-06-12 14:33 | 301576.3323 | 301576 | [7 empty] | 0 | 0 | 18.16 | 11.9 | 5365.43
TS5500Exc | MW\28\003\B | MW | 28 | 3 | B | 1 Prestrip - Thick | 100 | 86.6221 | 86.6221 | 2018-06-01 | 2018-06-03 00:10 | 45150.7125 | 45151 | [7 empty] | 0 | 0 | 2.8 | 8.34 | 5641.22
DRE1 | SC\32\020\D | SC | 32 | 20 | D | 6 DL | 100 | 0 | 100 | 2018-06-02 10:55 | 2018-06-13 10:13 | 931981.436 |  |  |  | 46584 | 931981 | 424426 |  |  | 0 | 38.35 | 0 | 7.16 | 5783.99
TS5500Shv | DT\27\004\A | DT | 27 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-06-02 21:43 | 2018-06-03 12:46 | 19458.4214 | [6 empty] | 19458 | 13477 | 1.68 | 0 | 0 | 20.99 | 4620
TS5500Exc | SC\32\019\D | SC | 32 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-06-03 00:10 | 2018-06-05 07:35 | 73970.4611 | [6 empty] | 73970 | 54977 | 4.59 | 0 | 0 | 7.3 | 5771
TS5500Shv | DT\27\005\B | DT | 27 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-06-03 12:46 | 2018-06-04 09:07 | 26289.9637 | [6 empty] | 26290 | 19171 | 0.74 | 0 | 0 | 10.71 | 5353
PH4100XPC#1 | DT\26\006\B | DT | 26 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-06-04 02:18 | 2018-06-04 19:57 | 42232.7327 | 42233 | [7 empty] | 0 | 0 | 2.61 | 9.02 | 5543.86
TS5500Shv | MW\27\007\A | MW | 27 | 7 | A | 8 Coal Mining | 64.2 | 0 | 64.2 | 2018-06-04 09:07 | 2018-06-05 17:15 | 41521.499 | [6 empty] | 41521 | 30533 | 1.88 | 0 | 0 | 10.95 | 5342
PH4100XPC#1 | DT\26\007\B | DT | 26 | 7 | B | 1 Prestrip - Thick | 100 | 96.9476 | 96.9476 | 2018-06-04 19:57 | 2018-06-05 18:46 | 54596.736 | 54597 | [7 empty] | 0 | 0 | 3.45 | 8.31 | 5619.8
PH4100A | SC\33\015\D | SC | 33 | 15 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-06-05 02:44 | 2018-06-10 01:22 | 211241.4291 | 211241 | [7 empty] | 0 | 0 | 22.02 | 7.17 | 5781.03
TS5500Exc | MW\27\007\A | MW | 27 | 7 | A | 8 Coal Mining | 35.8 | 0 | 35.8 | 2018-06-05 07:35 | 2018-06-06 00:55 | 23132.0133 | [6 empty] | 23132 | 17010 | 1.05 | 0 | 0 | 10.95 | 5342
TS5500Shv | DT\26\007\B | DT | 26 | 7 | B | 1 Prestrip - Thick | 32.1917 | 3.0524 | 3.0524 | 2018-06-05 17:15 | 2018-06-05 18:46 | 1719.001 | 1719 | [7 empty] | 0 | 0 | 0.11 | 8.31 | 5619.8
PH4100XPC#1 | DT\27\004\B | DT | 27 | 4 | B | 1 Prestrip - Thick | 100 | 67.8083 | 67.8083 | 2018-06-05 18:46 | 2018-06-06 15:47 | 50322.976 | 50323 | [7 empty] | 0 | 0 | 3.14 | 9.92 | 5395.36
TS5500Shv | DT\27\004\B | DT | 27 | 4 | B | 1 Prestrip - Thick | 32.1917 | 32.1917 | 32.1917 | 2018-06-05 18:46 | 2018-06-06 15:47 | 23890.5766 | 23891 | [7 empty] | 0 | 0 | 1.49 | 9.92 | 5395.36
TS5500Exc | MW\27\007\B | MW | 27 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-06-06 00:55 | 2018-06-09 03:35 | 69975.6045 | 69976 | [7 empty] | 0 | 0 | 4.37 | 9.86 | 5534.27
TS5500Shv | GG\01\004\D | GG | 1 | 4 | D | 1 Prestrip - Thick | 44.9878 | 44.9878 | 44.9878 | 2018-06-06 15:47 | 2018-06-12 22:51 | 170583.7948 | 170584 | [7 empty] | 0 | 0 | 8.6 | 5.31 | 5908.31
PH4100XPC#1 | MW\28\007\A | MW | 28 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-06-06 15:47 | 2018-06-15 01:04 | 432403.208 | 432403 | [7 empty] | 0 | 0 | 26.81 | 10.78 | 5384.22
DRE2 | DT\25\005\D | DT | 25 | 5 | D | 6 DL | 100 | 100 | 100 | 2018-06-07 09:22 | 2018-06-14 05:12 | 558406.8178 |  |  |  | 24354 | 558407 | 402909 |  |  | 0 | 22.38 | 0 | 6.5 | 5843.05
TS5500Exc | DT\25\004\D | DT | 25 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-06-09 03:35 | 2018-06-10 18:17 | 51669.5139 | [6 empty] | 51670 | 38917 | 2.43 | 0 | 0 | 6.25 | 5864
PH4100A | SC\35\022\D | SC | 35 | 22 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-06-10 01:22 | 2018-06-13 00:03 | 127735.4678 | 127735 | [7 empty] | 0 | 0 | 10.28 | 7.35 | 5768.23
TS5500Exc | MW\27\007\B | MW | 27 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-06-10 18:17 | 2018-06-12 16:03 | 61071.0548 | [6 empty] | 61071 | 44921 | 2.82 | 0 | 0 | 9.86 | 5534
TS6060#1 | BW\28\005\B | BW | 28 | 5 | B | 8 Coal Mining | 4 | 0 | 4 | 2018-06-12 14:33 | 2018-06-12 18:08 | 5154.202 | [6 empty] | 5154 | 3768 | 0.14 | 0 | 0 | 10.62 | 5476
TS5500Exc | MW\28\004\B | MW | 28 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-06-12 16:03 | 2018-06-15 05:08 | 57248.7726 | 57249 | [7 empty] | 0 | 0 | 3.54 | 8.9 | 5602.35
TS6060#1 | BW\24\003\D | BW | 24 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-06-12 18:08 | 2018-06-15 19:33 | 105294.2678 | [6 empty] | 105294 | 79049 | 4.94 | 0 | 0 | 6.3 | 5860
TS5500Shv | DT\25\004\D | DT | 25 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-06-12 22:51 | 2018-06-14 13:34 | 50020.4869 | [6 empty] | 50020 | 37675 | 2.35 | 0 | 0 | 6.25 | 5864
PH4100A | SC\34\021\D | SC | 34 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-06-13 00:03 | 2018-06-15 05:18 | 96614.3712 | 96614 | [7 empty] | 0 | 0 | 7.78 | 7.34 | 5769.01
DRE1 | SC\33\014\D | SC | 33 | 14 | D | 6 DL | 100 | 0 | 100 | 2018-06-13 10:13 | 2018-06-18 13:39 | 436923.7128 |  |  |  | 24937 | 436924 | 331300 |  |  | 0 | 31.55 | 0 | 7.52 | 5751.01
TS Fleet 5 | BW\28\007\B | BW | 28 | 7 | B | 1 Prestrip - Thick | 49.1564 | 49.1564 | 49.1564 | 2018-06-13 17:47 | 2018-06-24 14:00 | 517303.0649 | 517303 | [7 empty] | 0 | 0 | 31.15 | 11.9 | 5365.43
DRE2 | DT\25\006\D | DT | 25 | 6 | D | 6 DL | 100 | 100 | 100 | 2018-06-14 05:12 | 2018-06-19 09:16 | 422915.4004 |  |  |  | 25257 | 422915 | 298548 |  |  | 0 | 25.28 | 0 | 6.4 | 5850.76
TS5500Shv | DT\25\005\D | DT | 25 | 5 | D | 8 Coal Mining | 45 | 0 | 45 | 2018-06-14 13:34 | 2018-06-16 08:53 | 55993.925 | [6 empty] | 55994 | 42042 | 2.2 | 0 | 0 | 6.5 | 5843
PH4100XPC#1 | MW\27\008\A | MW | 27 | 8 | A | 1 Prestrip - Thick | 100 | 42.6823 | 42.6823 | 2018-06-15 01:04 | 2018-06-18 15:49 | 187772.8044 | 187773 | [7 empty] | 0 | 0 | 11.47 | 11.39 | 5273.97
TS5500Exc | MW\28\007\A | MW | 28 | 7 | A | 8 Coal Mining | 46.9 | 0 | 46.9 | 2018-06-15 05:08 | 2018-06-16 06:36 | 33996.4126 | [6 empty] | 33996 | 25027 | 1.56 | 0 | 0 | 10.78 | 5384
PH4100A | SC\35\021\D | SC | 35 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-06-15 05:18 | 2018-06-18 15:37 | 148428.7832 | 148429 | [7 empty] | 0 | 0 | 12.76 | 7.31 | 5770.29
TS6060#1 | BW\24\004\D | BW | 24 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-06-15 19:33 | 2018-06-18 19:44 | 103524.6253 | [6 empty] | 103525 | 78155 | 4.88 | 0 | 0 | 5.78 | 5906
TS5500Exc | DT\25\005\D | DT | 25 | 5 | D | 8 Coal Mining | 46.4 | 0 | 46.4 | 2018-06-16 06:36 | 2018-06-18 01:56 | 57839.8786 | [6 empty] | 57840 | 43428 | 2.27 | 0 | 0 | 6.5 | 5843
TS5500Shv | MW\28\007\A | MW | 28 | 7 | A | 8 Coal Mining | 53.1 | 0 | 53.1 | 2018-06-16 08:53 | 2018-06-17 14:42 | 38511.713 | [6 empty] | 38512 | 28351 | 1.76 | 0 | 0 | 10.78 | 5384
TS5500Shv | GG\01\004\D | GG | 1 | 4 | D | 1 Prestrip - Thick | 55.0122 | 55.0122 | 55.0122 | 2018-06-17 14:42 | 2018-06-25 07:25 | 208594.4711 | 208594 | [7 empty] | 0 | 0 | 10.51 | 5.31 | 5908.31
TS5500Exc | SC\32\020\D | SC | 32 | 20 | D | 7 PostStrip | 84.1605 | 0 | 84.1605 | 2018-06-18 01:56 | 2018-06-19 19:46 | 39211.6853 |  |  | 39212 | [5 empty] | 0 | 0 | 0 | 7.16 | 5783.99
DRE1 | SC\33\013\D | SC | 33 | 13 | D | 6 DL | 100 | 0 | 100 | 2018-06-18 13:39 | 2018-06-25 03:07 | 557423.228 |  |  |  | 39643 | 557423 | 400834 |  |  | 0 | 37.01 | 0 | 7.67 | 5738.06
PH4100A | SC\34\020\D | SC | 34 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-06-18 15:37 | 2018-06-22 03:49 | 151865.3567 | 151865 | [7 empty] | 0 | 0 | 13.04 | 7.31 | 5769.52
PH4100XPC#1 | MW\28\008\A | MW | 28 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-06-18 15:49 | 2018-06-27 23:05 | 486613.0884 | 486613 | [7 empty] | 0 | 0 | 29.82 | 11.26 | 5331.88
TS6060#1 | BW\24\005\D | BW | 24 | 5 | D | 8 Coal Mining | 14.8 | 0 | 14.8 | 2018-06-18 19:44 | 2018-06-19 06:50 | 15912.7885 | [6 empty] | 15913 | 12042 | 0.75 | 0 | 0 | 5.51 | 5931
TS6060#1 | BW\24\002\D | BW | 24 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2018-06-19 06:50 | 2018-06-21 06:40 | 52304.444 |  |  | 52304 | [5 empty] | 0 | 0 | 0 | 6.47 | 5845.43
DRE2 | DT\25\007\D | DT | 25 | 7 | D | 6 DL | 100 | 100 | 100 | 2018-06-19 09:16 | 2018-06-25 20:31 | 529154.3591 |  |  |  | 31601 | 529154 | 373545 |  |  | 0 | 25.31 | 0 | 6.29 | 5859.49
TS5500Exc | SC\32\020\D | SC | 32 | 20 | D | 7 PostStrip | 15.8395 | 0 | 15.8395 | 2018-06-19 19:46 | 2018-06-20 03:39 | 7379.8687 |  |  | 7380 | [5 empty] | 0 | 0 | 0 | 7.16 | 5783.99
TS5500Exc | SC\32\020\D | SC | 32 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-06-20 03:39 | 2018-06-22 13:08 | 76734.2985 | [6 empty] | 76734 | 57033 | 4.75 | 0 | 0 | 7.16 | 5784
TS6060#1 | BW\28\008\B | BW | 28 | 8 | B | 1 Prestrip - Thick | 19.9402 | 19.9402 | 19.9402 | 2018-06-21 06:40 | 2018-06-28 07:11 | 184031.2735 | 184031 | [7 empty] | 0 | 0 | 11.85 | 13.11 | 5261.64
PH4100A | SC\35\020\D | SC | 35 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-06-22 03:49 | 2018-06-26 08:59 | 182301.3454 | 182301 | [7 empty] | 0 | 0 | 15.54 | 7.13 | 5785.74
TS5500Exc | SC\33\014\D | SC | 33 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-06-22 13:08 | 2018-06-24 13:44 | 64883 | [6 empty] | 64883 | 48606 | 4.49 | 0 | 0 | 7.52 | 5751
TS5500Exc | MW\28\006\B | MW | 28 | 6 | B | 1 Prestrip - Thick | 3.9122 | 3.9122 | 3.9122 | 2018-06-24 13:44 | 2018-06-24 16:51 | 2915.4808 | 2915 | [7 empty] | 0 | 0 | 0.18 | 8.68 | 5668.89
TS Fleet 5 | BW\28\007\B | BW | 28 | 7 | B | 1 Prestrip - Thick | 14.6531 | 14.6531 | 14.6531 | 2018-06-24 14:00 | 2018-06-27 19:34 | 154203.4479 | 154203 | [7 empty] | 0 | 0 | 9.29 | 11.9 | 5365.43
TS5500Exc | MW\28\006\B | MW | 28 | 6 | B | 1 Prestrip - Thick | 96.0878 | 96.0878 | 96.0878 | 2018-06-24 16:51 | 2018-06-27 21:15 | 71607.5363 | 71608 | [7 empty] | 0 | 0 | 4.43 | 8.68 | 5668.89
DRE1 | SC\33\012\D | SC | 33 | 12 | D | 6 DL | 100 | 0 | 79.133 | 2018-06-25 03:07 | 2018-07-01 | 498632.7827 |  |  |  | 37919 | 498633 | 341270 |  |  | 0 | 40 | 0 | 7.67 | 5738.37
TS5500Shv | MW\27\008\A | MW | 27 | 8 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-06-25 07:25 | 2018-06-27 07:50 | 62574.9149 | [6 empty] | 62575 | 45881 | 2.87 | 0 | 0 | 11.39 | 5274
DRE2 | DT\25\003\D | DT | 25 | 3 | D | 6 DL | 100 | 78.4881 | 78.4881 | 2018-06-25 20:31 | 2018-07-01 | 420905.0837 |  |  |  | 25137 | 420905 | 297129 |  |  | 0 | 25.68 | 0 | 6.15 | 5872.94
PH4100A | SC\34\019\D | SC | 34 | 19 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-06-26 08:59 | 2018-06-30 19:12 | 191401.4803 | 191401 | [7 empty] | 0 | 0 | 16.34 | 7.18 | 5780.25
TS5500Shv | GG\01\004\D | GG | 1 | 4 | D | 7 PostStrip | 100 | 0 | 73.2027 | 2018-06-27 07:50 | 2018-07-01 | 100141.8837 |  |  | 100142 | [5 empty] | 0 | 0 | 0 | 5.31 | 5908.31
TS Fleet 5 | BW\28\008\B | BW | 28 | 8 | B | 1 Prestrip - Thick | 78.9848 | 16.6589 | 16.4627 | 2018-06-27 19:34 | 2018-07-01 | 151936.7641 | 151937 | [7 empty] | 0 | 0 | 9.79 | 13.11 | 5261.64
TS5500Exc | MW\27\008\B | MW | 27 | 8 | B | 1 Prestrip - Thick | 100 | 74.854 | 74.854 | 2018-06-27 21:15 | 2018-07-01 | 70043.512 | 70044 | [7 empty] | 0 | 0 | 4.38 | 11.02 | 5389.94
PH4100XPC#1 | MW\28\009\A | MW | 28 | 9 | A | 1 Prestrip - Thick | 100 | 24.2874 | 24.2874 | 2018-06-27 23:05 | 2018-07-01 | 161236.8365 | 161237 | [7 empty] | 0 | 0 | 9.93 | 11.18 | 5381.52
TS6060#1 | BW\28\008\B | BW | 28 | 8 | B | 1 Prestrip - Thick | 1.075 | 0 | 1.075 | 2018-06-28 07:11 | 2018-06-28 16:16 | 9921.6497 | 9922 | [7 empty] | 0 | 0 | 0.64 | 13.11 | 5261.64
TS6060#1 | BW\24\002\D | BW | 24 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-06-28 16:16 | 2018-06-30 15:52 | 68258.6163 | [6 empty] | 68259 | 51122 | 4.93 | 0 | 0 | 6.47 | 5845
TS6060#1 | BW\24\005\D | BW | 24 | 5 | D | 8 Coal Mining | 85.2 | 0 | 10.8 | 2018-06-30 15:52 | 2018-07-01 | 11662.2453 | [6 empty] | 11662 | 8825 | 0.55 | 0 | 0 | 5.51 | 5931
PH4100A | SC\35\019\D | SC | 35 | 19 | D | 1 Prestrip - Thick | 100 | 4.0535 | 4.0535 | 2018-06-30 19:12 | 2018-07-01 | 8593.3363 | 8593 | [7 empty] | 0 | 0 | 0.72 | 7.23 | 5776.8
| EOP 54 : 2018\Jun | EOP 54 : 2018 | Jun | [6 empty] | 2018-07-01 | 2018-07-01 |  | 5517524 |  | 199038 | 287634 | 5002776 | 3331793 | 1106552 | 822915 | 55.39 | 0 | 367.78 | 8.01 | 5686.9
TS Fleet 5 | BW\28\008\B | BW | 28 | 8 | B | 1 Prestrip - Thick | 78.9848 | 63.4009 | 62.5221 | 2018-07-01 | 2018-07-12 22:13 | 577026.9599 | 577027 | [7 empty] | 0 | 0 | 37.16 | 13.11 | 5261.64
DRE1 | SC\33\012\D | SC | 33 | 12 | D | 6 DL | 100 | 0 | 20.867 | 2018-07-01 | 2018-07-02 12:39 | 131486.81 |  |  |  | 9999 | 131487 | 89991 |  |  | 0 | 40 | 0 | 7.67 | 5738.37
PH4100A | SC\35\019\D | SC | 35 | 19 | D | 1 Prestrip - Thick | 100 | 95.9465 | 95.9465 | 2018-07-01 | 2018-07-05 15:46 | 203403.8593 | 203404 | [7 empty] | 0 | 0 | 17.03 | 7.23 | 5776.8
DRE2 | DT\25\003\D | DT | 25 | 3 | D | 6 DL | 100 | 21.5119 | 21.5119 | 2018-07-01 | 2018-07-02 09:24 | 115360.7057 |  |  |  | 6889 | 115361 | 81436 |  |  | 0 | 25.68 | 0 | 6.15 | 5872.94
PH4100XPC#1 | MW\28\009\A | MW | 28 | 9 | A | 1 Prestrip - Thick | 100 | 75.7126 | 75.7126 | 2018-07-01 | 2018-07-10 08:14 | 502634.7368 | 502635 | [7 empty] | 0 | 0 | 30.96 | 11.18 | 5381.52
TS5500Shv | GG\01\004\D | GG | 1 | 4 | D | 7 PostStrip | 100 | 0 | 26.7973 | 2018-07-01 | 2018-07-02 07:49 | 36658.8982 |  |  | 36659 | [5 empty] | 0 | 0 | 0 | 5.31 | 5908.31
TS6060#1 | BW\24\005\D | BW | 24 | 5 | D | 8 Coal Mining | 85.2 | 0 | 74.4 | 2018-07-01 | 2018-07-03 07:12 | 80293.5647 | [6 empty] | 80294 | 60760 | 3.8 | 0 | 0 | 5.51 | 5931
TS5500Exc | MW\27\008\B | MW | 27 | 8 | B | 1 Prestrip - Thick | 100 | 25.146 | 25.146 | 2018-07-01 | 2018-07-02 00:45 | 23529.9662 | 23530 | [7 empty] | 0 | 0 | 1.47 | 11.02 | 5389.94
TS5500Exc | MW\28\008\A | MW | 28 | 8 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-07-02 00:45 | 2018-07-03 04:04 | 36969.3767 | [6 empty] | 36969 | 27137 | 1.69 | 0 | 0 | 11.26 | 5332
TS5500Shv | MW\28\008\A | MW | 28 | 8 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-07-02 07:49 | 2018-07-03 11:08 | 35789.503 | [6 empty] | 35790 | 26271 | 1.64 | 0 | 0 | 11.26 | 5332
DRE2 | DT\25\002\D | DT | 25 | 2 | D | 6 DL | 100 | 100 | 100 | 2018-07-02 09:24 | 2018-07-09 10:30 | 583993.7802 |  |  |  | 25470 | 583994 | 421371 |  |  | 0 | 23.54 | 0 | 5.96 | 5889.37
DRE1 | SC\33\011\D | SC | 33 | 11 | D | 6 DL | 100 | 0 | 100 | 2018-07-02 12:39 | 2018-07-10 04:11 | 658203.5715 |  |  |  | 50054 | 658204 | 450482 |  |  | 0 | 40 | 0 | 7.63 | 5742.77
TS5500Exc | DT\25\007\D | DT | 25 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-07-03 04:04 | 2018-07-06 04:24 | 97910.6437 | [6 empty] | 97911 | 73740 | 4.61 | 0 | 0 | 6.29 | 5859
TS6060#1 | BW\24\006\D | BW | 24 | 6 | D | 8 Coal Mining | 26.1 | 0 | 26.1 | 2018-07-03 07:12 | 2018-07-04 02:56 | 28710.4097 | [6 empty] | 28710 | 21795 | 1.36 | 0 | 0 | 5.36 | 5945
TS5500Shv | MW\27\008\B | MW | 27 | 8 | B | 8 Coal Mining | 31.2 | 0 | 31.2 | 2018-07-03 11:08 | 2018-07-04 02:22 | 19976.4538 | [6 empty] | 19976 | 14571 | 0.91 | 0 | 0 | 11.02 | 5390
TS5500Shv | GG\01\004\D | GG | 1 | 4 | D | 8 Coal Mining | 44.8 | 0 | 44.8 | 2018-07-04 02:22 | 2018-07-05 17:49 | 51687.4186 | [6 empty] | 51687 | 39073 | 1.72 | 0 | 0 | 5.31 | 5908
TS6060#1 | BW\28\005\B | BW | 28 | 5 | B | 8 Coal Mining | 96 | 0 | 96 | 2018-07-04 02:56 | 2018-07-07 16:04 | 123807.3317 | [6 empty] | 123807 | 90503 | 3.44 | 0 | 0 | 10.62 | 5476
PH4100A | SC\34\018\D | SC | 34 | 18 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-07-05 15:46 | 2018-07-10 20:17 | 226314.9838 | 226315 | [7 empty] | 0 | 0 | 19.18 | 7.27 | 5772.78
TS5500Shv | GG\01\005\D | GG | 1 | 5 | D | 1 Prestrip - Thick | 91.5305 | 91.5305 | 91.5305 | 2018-07-05 17:49 | 2018-07-17 22:27 | 333196.3495 | 333196 | [7 empty] | 0 | 0 | 24.72 | 5.47 | 5893.82
TS5500Exc | SC\33\013\D | SC | 33 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-07-06 04:24 | 2018-07-08 10:11 | 72808.6486 | [6 empty] | 72809 | 54457 | 4.54 | 0 | 0 | 7.67 | 5738
TS6060#1 | BW\28\006\B | BW | 28 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-07-07 16:04 | 2018-07-09 23:22 | 80439.7166 | [6 empty] | 80440 | 58480 | 3.66 | 0 | 0 | 11.56 | 5398
TS5500Exc | MW\27\008\B | MW | 27 | 8 | B | 8 Coal Mining | 68.8 | 0 | 68.8 | 2018-07-08 10:11 | 2018-07-09 18:42 | 44020.6943 | [6 empty] | 44021 | 32108 | 2 | 0 | 0 | 11.02 | 5390
DRE2 | DT\25\001\D | DT | 25 | 1 | D | 6 DL | 100 | 100 | 100 | 2018-07-09 10:30 | 2018-07-16 03:17 | 555256.3794 |  |  |  | 24217 | 555256 | 400636 |  |  | 0 | 21.51 | 0 | 6.12 | 5874.48
TS5500Exc | SC\33\012\D | SC | 33 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-07-09 18:42 | 2018-07-12 00:32 | 72870.838 | [6 empty] | 72871 | 54417 | 4.53 | 0 | 0 | 7.67 | 5738
TS6060#1 | BW\28\007\B | BW | 28 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-07-09 23:22 | 2018-07-12 10:06 | 85412.869 | [6 empty] | 85413 | 61995 | 3.88 | 0 | 0 | 11.9 | 5365
DRE1 | SC\33\010\D | SC | 33 | 10 | D | 6 DL | 100 | 0 | 100 | 2018-07-10 04:11 | 2018-07-17 19:48 | 658486.5083 |  |  |  | 50075 | 658487 | 450675 |  |  | 0 | 40 | 0 | 7.56 | 5749.74
PH4100XPC#1 | MW\28\010\A | MW | 28 | 10 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-07-10 08:14 | 2018-07-25 10:32 | 822677.7246 | 822678 | [7 empty] | 0 | 0 | 50.36 | 11 | 5448.22
PH4100A | SC\35\018\D | SC | 35 | 18 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-07-10 20:17 | 2018-07-16 03:44 | 231565.5972 | 231566 | [7 empty] | 0 | 0 | 19.22 | 7.25 | 5774.51
TS5500Exc | MW\28\009\A | MW | 28 | 9 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2018-07-12 00:32 | 2018-07-13 05:07 | 38689.6655 | [6 empty] | 38690 | 28380 | 1.78 | 0 | 0 | 11.18 | 5382
TS6060#1 | GG\01\004\D | GG | 1 | 4 | D | 8 Coal Mining | 55.2 | 0 | 55.2 | 2018-07-12 10:06 | 2018-07-14 05:49 | 63580.7196 | [6 empty] | 63581 | 48063 | 2.12 | 0 | 0 | 5.31 | 5908
TS Fleet 5 | BW\28\009\X2 | BW | 28 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2018-07-12 22:13 | 2018-07-21 02:36 | 395912.6587 | 395913 | [7 empty] | 0 | 0 | 24.05 | 0 | 0
TS5500Exc | DT\25\002\D | DT | 25 | 2 | D | 8 Coal Mining | 57.4 | 0 | 57.4 | 2018-07-13 05:07 | 2018-07-15 07:49 | 68627.1834 | [6 empty] | 68627 | 51689 | 2.74 | 0 | 0 | 5.96 | 5889
TS6060#1 | BW\28\008\B | BW | 28 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-07-14 05:49 | 2018-07-16 16:12 | 84904.8035 | [6 empty] | 84905 | 61243 | 3.83 | 0 | 0 | 13.11 | 5262
TS5500Exc | SC\33\011\D | SC | 33 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-07-15 07:49 | 2018-07-17 15:34 | 75453.441 | [6 empty] | 75453 | 56347 | 4.69 | 0 | 0 | 7.63 | 5743
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2018-07-16 03:17 | 2018-07-18 03:17
PH4100A | SC\34\017\D | SC | 34 | 17 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-07-16 03:44 | 2018-07-21 16:39 | 241177.2087 | 241177 | [7 empty] | 0 | 0 | 20.38 | 7.29 | 5770.94
TS6060#1 | BW\28\010\B | BW | 28 | 10 | B | 1 Prestrip - Thick | 34.4232 | 34.4232 | 34.4232 | 2018-07-16 16:12 | 2018-07-28 01:07 | 297709.2172 | 297709 | [7 empty] | 0 | 0 | 17.14 | 16.77 | 4929.66
TS5500Exc | DT\25\001\D | DT | 25 | 1 | D | 8 Coal Mining | 26.3 | 0 | 26.3 | 2018-07-17 15:34 | 2018-07-18 14:57 | 31653.3607 | [6 empty] | 31653 | 23782 | 1.21 | 0 | 0 | 6.12 | 5874
DRE1 | SC\33\015\D | SC | 33 | 15 | D | 6 DL | 100 | 0 | 100 | 2018-07-17 19:48 | 2018-07-21 23:38 | 358023.6813 |  |  |  | 16814 | 358024 | 263412 |  |  | 0 | 28.87 | 0 | 7.17 | 5781.03
TS5500Shv | MW\28\009\A | MW | 28 | 9 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-07-17 22:27 | 2018-07-19 03:02 | 37454.8889 | [6 empty] | 37455 | 27474 | 1.72 | 0 | 0 | 11.18 | 5382
DRE2 | BW\25\011\D | BW | 25 | 11 | D | 6 DL | 100 | 100 | 100 | 2018-07-18 03:17 | 2018-07-23 04:22 | 418148.9038 |  |  |  | 18237 | 418149 | 301709 |  |  | 0 | 19.99 | 0 | 5.99 | 5887.13
TS5500Exc | SC\33\010\D | SC | 33 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-07-18 14:57 | 2018-07-21 00:43 | 78191.297 | [6 empty] | 78191 | 58440 | 4.87 | 0 | 0 | 7.56 | 5750
TS5500Shv | DT\25\002\D | DT | 25 | 2 | D | 8 Coal Mining | 12.3 | 0 | 12.3 | 2018-07-19 03:02 | 2018-07-19 14:17 | 14749.5356 | [6 empty] | 14750 | 11109 | 0.59 | 0 | 0 | 5.96 | 5889
TS5500Shv | GG\01\005\D | GG | 1 | 5 | D | 1 Prestrip - Thick | 8.4695 | 8.4695 | 8.4695 | 2018-07-19 14:17 | 2018-07-20 17:22 | 30831.3135 | 30831 | [7 empty] | 0 | 0 | 2.29 | 5.47 | 5893.82
TS5500Shv | GG\01\005\D | GG | 1 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2018-07-20 17:22 | 2018-07-23 17:57 | 83625.6419 |  |  | 83626 | [5 empty] | 0 | 0 | 0 | 5.47 | 5893.82
TS5500Exc | MW\28\003\B | MW | 28 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-07-21 00:43 | 2018-07-23 00:47 | 65070.4532 | [6 empty] | 65070 | 48484 | 3.03 | 0 | 0 | 8.34 | 5641
TS Fleet 5 | BW\28\009\B | BW | 28 | 9 | B | 1 Prestrip - Thick | 19.4779 | 19.4779 | 19.4779 | 2018-07-21 02:36 | 2018-07-23 02:11 | 95920.1694 | 95920 | [7 empty] | 0 | 0 | 5.95 | 14.45 | 5139.84
PH4100A | SC\35\017\D | SC | 35 | 17 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-07-21 16:39 | 2018-07-26 20:09 | 224082.4199 | 224082 | [7 empty] | 0 | 0 | 18.71 | 7.06 | 5790.97
DRE1 | SC\33\016\D | SC | 33 | 16 | D | 6 DL | 100 | 0 | 100 | 2018-07-21 23:38 | 2018-07-28 01:52 | 524428.6839 |  |  |  | 29931 | 524429 | 397651 |  |  | 0 | 33.1 | 0 | 7.23 | 5776.84
TS5500Exc | SC\33\015\D | SC | 33 | 15 | D | 8 Coal Mining | 100 | 0 | 60.4 | 2018-07-23 00:47 | 2018-07-23 22:36 | 29532.1639 | [6 empty] | 29532 | 22123 | 2.63 | 0 | 0 | 7.17 | 5781
TS Fleet 5 | BW\28\009\B | BW | 28 | 9 | B | 1 Prestrip - Thick | 73.5513 | 73.5513 | 73.5513 | 2018-07-23 02:11 | 2018-07-30 13:51 | 362208.1259 | 362208 | [7 empty] | 0 | 0 | 22.45 | 14.45 | 5139.84
DRE2 | BW\25\010\D | BW | 25 | 10 | D | 6 DL | 100 | 100 | 100 | 2018-07-23 04:22 | 2018-07-28 09:36 | 432472.4619 |  |  |  | 18862 | 432472 | 312044 |  |  | 0 | 20.64 | 0 | 5.68 | 5916.75
TS5500Shv | MW\27\009\B | MW | 27 | 9 | B | 8 Coal Mining | 100 | 0 | 9.6 | 2018-07-23 17:57 | 2018-07-23 22:36 | 6095.0194 | [6 empty] | 6095 | 4474 | 0.28 | 0 | 0 | 10.08 | 5507
TS5500Shv | GG\02\003\D | GG | 2 | 3 | D | 1 Prestrip - Thick | 56.9286 | 44.5288 | 44.5288 | 2018-07-23 22:36 | 2018-08-01 | 222060.0096 | 222060 | [7 empty] | 0 | 0 | 11.64 | 5.22 | 5923.58
TS5500Exc | MW\28\007\B | MW | 28 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-07-23 22:36 | 2018-07-27 06:28 | 75901.2227 | 75901 | [7 empty] | 0 | 0 | 4.74 | 9.76 | 5540.27
PH4100XPC#1 | MW\28\011\X | MW | 28 | 11 | X | 1 Prestrip - Thick | 100 | 54.8796 | 54.8796 | 2018-07-25 10:32 | 2018-08-01 | 343403.8411 | 343404 | [7 empty] | 0 | 0 | 18.6 | 12.53 | 5161.34
PH4100A | SC\34\016\D | SC | 34 | 16 | D | 1 Prestrip - Thick | 100 | 65.5592 | 65.5592 | 2018-07-26 20:09 | 2018-08-01 | 224235.3411 | 224235 | [7 empty] | 0 | 0 | 13.23 | 7.1 | 5787.82
TS5500Exc | MW\28\008\B | MW | 28 | 8 | B | 1 Prestrip - Thick | 46.0952 | 46.0952 | 46.0952 | 2018-07-27 06:28 | 2018-07-29 02:54 | 42225.5083 | 42226 | [7 empty] | 0 | 0 | 2.64 | 10.71 | 5421.94
TS6060#1 | BW\28\009\B | BW | 28 | 9 | B | 1 Prestrip - Thick | 6.9708 | 6.9708 | 6.9708 | 2018-07-28 01:07 | 2018-07-29 08:05 | 34328.2991 | 34328 | [7 empty] | 0 | 0 | 2.13 | 14.45 | 5139.84
DRE1 | SC\33\017\D | SC | 33 | 17 | D | 6 DL | 100 | 0 | 59.3147 | 2018-07-28 01:52 | 2018-08-01 | 337559.345 |  |  |  | 24007 | 337559 | 242733 |  |  | 0 | 37.71 | 0 | 7.34 | 5767.47
DRE2 | BW\25\009\D | BW | 25 | 9 | D | 6 DL | 100 | 68.0846 | 68.0846 | 2018-07-28 09:36 | 2018-08-01 | 298368.9689 |  |  |  | 13013 | 298369 | 215283 |  |  | 0 | 20.98 | 0 | 5.09 | 5966.9
TS5500Exc | MW\28\008\B | MW | 28 | 8 | B | 1 Prestrip - Thick | 53.9048 | 53.9048 | 53.9048 | 2018-07-29 02:54 | 2018-07-31 06:51 | 49379.5092 | 49380 | [7 empty] | 0 | 0 | 3.09 | 10.71 | 5421.94
TS6060#1 | BW\28\010\B | BW | 28 | 10 | B | 1 Prestrip - Thick | 2.7159 | 0 | 2.7159 | 2018-07-29 08:05 | 2018-07-30 05:37 | 23488.366 | 23488 | [7 empty] | 0 | 0 | 1.35 | 16.77 | 4929.66
TS6060#1 | BW\29\006\B | BW | 29 | 6 | B | 1 Prestrip - Thick | 32.1769 | 7.832 | 7.832 | 2018-07-30 05:37 | 2018-08-01 | 46443.4649 | 46443 | [7 empty] | 0 | 0 | 4.64 | 11.9 | 5370.13
TS Fleet 5 | BW\28\010\B | BW | 28 | 10 | B | 1 Prestrip - Thick | 47.8786 | 8.3032 | 7.9593 | 2018-07-30 13:51 | 2018-08-01 | 68836.0861 | 68836 | [7 empty] | 0 | 0 | 3.96 | 16.77 | 4929.66
TS5500Exc | MW\28\009\B | MW | 28 | 9 | B | 1 Prestrip - Thick | 100 | 25.6124 | 25.6124 | 2018-07-31 06:51 | 2018-08-01 | 16288.4941 | 16288 | [7 empty] | 0 | 0 | 1.02 | 10.01 | 5509.51
| EOP 55 : 2018\Jul | EOP 55 : 2018 | Jul | [6 empty] | 2018-08-01 | 2018-08-01 |  | 5714781 |  | 120285 | 287566 | 5071790 | 3627423 | 1424700 | 1056916 | 67.26 | 0 | 378.11 | 8.22 | 5678.64
TS Fleet 5 | BW\28\010\B | BW | 28 | 10 | B | 1 Prestrip - Thick | 47.8786 | 41.6439 | 39.9192 | 2018-08-01 | 2018-08-08 00:54 | 345241.837 | 345242 | [7 empty] | 0 | 0 | 19.88 | 16.77 | 4929.66
DRE1 | SC\33\017\D | SC | 33 | 17 | D | 6 DL | 100 | 0 | 40.6853 | 2018-08-01 | 2018-08-03 16:33 | 231540.0517 |  |  |  | 16467 | 231540 | 166497 |  |  | 0 | 37.71 | 0 | 7.34 | 5767.47
PH4100A | SC\34\016\D | SC | 34 | 16 | D | 1 Prestrip - Thick | 100 | 34.4408 | 34.4408 | 2018-08-01 | 2018-08-03 16:12 | 117799.5032 | 117800 | [7 empty] | 0 | 0 | 6.95 | 7.1 | 5787.82
DRE2 | BW\25\009\D | BW | 25 | 9 | D | 6 DL | 100 | 31.9154 | 31.9154 | 2018-08-01 | 2018-08-02 16:29 | 139863.541 |  |  |  | 6100 | 139864 | 100916 |  |  | 0 | 20.98 | 0 | 5.09 | 5966.9
PH4100XPC#1 | MW\28\011\X | MW | 28 | 11 | X | 1 Prestrip - Thick | 100 | 45.1204 | 45.1204 | 2018-08-01 | 2018-08-06 07:45 | 282336.8721 | 282337 | [7 empty] | 0 | 0 | 15.29 | 12.53 | 5161.34
TS5500Shv | GG\02\003\D | GG | 2 | 3 | D | 1 Prestrip - Thick | 56.9286 | 12.3998 | 12.3998 | 2018-08-01 | 2018-08-03 05:06 | 61836.4456 | 61836 | [7 empty] | 0 | 0 | 3.24 | 5.22 | 5923.58
TS6060#1 | BW\29\006\B | BW | 29 | 6 | B | 1 Prestrip - Thick | 32.1769 | 24.3449 | 24.3449 | 2018-08-01 | 2018-08-06 09:55 | 144363.218 | 144363 | [7 empty] | 0 | 0 | 14.41 | 11.9 | 5370.13
TS5500Exc | MW\28\009\B | MW | 28 | 9 | B | 1 Prestrip - Thick | 100 | 74.3876 | 74.3876 | 2018-08-01 | 2018-08-03 01:05 | 47307.5707 | 47308 | [7 empty] | 0 | 0 | 2.96 | 10.01 | 5509.51
DRE2 | BW\25\008\D | BW | 25 | 8 | D | 6 DL | 100 | 100 | 100 | 2018-08-02 16:29 | 2018-08-07 19:11 | 423685.0577 |  |  |  | 18478 | 423685 | 305703 |  |  | 0 | 20.28 | 0 | 4.89 | 5984.09
TS5500Exc | MW\28\010\A | MW | 28 | 10 | A | 8 Coal Mining | 3.7 | 0 | 3.7 | 2018-08-03 01:05 | 2018-08-03 03:10 | 2845.5208 | [6 empty] | 2846 | 2089 | 0.13 | 0 | 0 | 11 | 5448
TS5500Exc | SC\33\015\D | SC | 33 | 15 | D | 8 Coal Mining | 100 | 0 | 39.6 | 2018-08-03 03:10 | 2018-08-03 17:17 | 19387.2246 | [6 empty] | 19387 | 14523 | 1.73 | 0 | 0 | 7.17 | 5781
TS5500Shv | MW\27\005\A | MW | 27 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-08-03 05:06 | 2018-08-04 06:06 | 33202.7081 | [6 empty] | 33203 | 24588 | 1.53 | 0 | 0 | 9.45 | 5522
PH4100A | SC\34\015\D | SC | 34 | 15 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-08-03 16:12 | 2018-08-09 21:04 | 273423.3287 | 273423 | [7 empty] | 0 | 0 | 18.64 | 7.03 | 5792.85
DRE1 | SC\33\018\D | SC | 33 | 18 | D | 6 DL | 100 | 0 | 100 | 2018-08-03 16:33 | 2018-08-10 14:21 | 594607.0852 |  |  |  | 42287 | 594607 | 427572 |  |  | 0 | 39.46 | 0 | 7.32 | 5768.66
TS5500Exc | SC\33\016\D | SC | 33 | 16 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-08-03 17:17 | 2018-08-05 21:30 | 71669.4552 | [6 empty] | 71669 | 53647 | 4.47 | 0 | 0 | 7.23 | 5777
TS5500Shv | MW\28\005\A | MW | 28 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2018-08-04 06:06 | 2018-08-05 07:17 | 33459.4015 | [6 empty] | 33459 | 24751 | 1.54 | 0 | 0 | 9.53 | 5508
TS5500Shv | MW\27\006\B | MW | 27 | 6 | B | 8 Coal Mining | 75.1 | 0 | 75.1 | 2018-08-05 07:17 | 2018-08-06 08:34 | 33591.7503 | [6 empty] | 33592 | 24873 | 1.54 | 0 | 0 | 9.18 | 5641
TS5500Exc | MW\27\005\B | MW | 27 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-08-05 21:30 | 2018-08-08 17:09 | 65173.7909 | 65174 | [7 empty] | 0 | 0 | 4.06 | 9.04 | 5632.72
PH4100XPC#1 | BW\28\011\B | BW | 28 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-08-06 07:45 | 2018-08-18 23:46 | 755188.3485 | 755188 | [7 empty] | 0 | 0 | 45 | 10.99 | 5366.16
TS5500Shv | MW\28\010\A | MW | 28 | 10 | A | 8 Coal Mining | 96.3 | 0 | 96.3 | 2018-08-06 08:34 | 2018-08-08 15:44 | 73299.8792 | [6 empty] | 73300 | 53815 | 3.37 | 0 | 0 | 11 | 5448
TS6060#1 | BW\25\011\D | BW | 25 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-08-06 09:55 | 2018-08-09 06:06 | 100549.0097 | [6 empty] | 100549 | 75791 | 4.74 | 0 | 0 | 5.99 | 5887
DRE2 | BW\25\007\D | BW | 25 | 7 | D | 6 DL | 100 | 100 | 100 | 2018-08-07 19:11 | 2018-08-12 22:11 | 424788.5414 |  |  |  | 18526 | 424789 | 306499 |  |  | 0 | 20.32 | 0 | 5.03 | 5972.16
TS Fleet 5 | BW\29\005\X2 | BW | 29 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2018-08-08 00:54 | 2018-08-16 09:33 | 410130.3394 | 410130 | [7 empty] | 0 | 0 | 34.78 | 0 | 0
TS5500Shv | MW\27\009\B | MW | 27 | 9 | B | 8 Coal Mining | 100 | 0 | 90.4 | 2018-08-08 15:44 | 2018-08-10 10:43 | 57094.3657 | [6 empty] | 57094 | 41912 | 2.61 | 0 | 0 | 10.08 | 5507
TS5500Exc | SC\33\017\D | SC | 33 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-08-08 17:09 | 2018-08-10 22:24 | 73090.2349 | [6 empty] | 73090 | 54581 | 4.55 | 0 | 0 | 7.34 | 5767
TS6060#1 | BW\25\010\D | BW | 25 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-08-09 06:06 | 2018-08-12 09:28 | 111138.4714 | [6 empty] | 111138 | 84166 | 5.26 | 0 | 0 | 5.68 | 5917
PH4100A | SC\35\015\D | SC | 35 | 15 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-08-09 21:04 | 2018-08-14 04:52 | 191793.9117 | 191794 | [7 empty] | 0 | 0 | 14.33 | 7.02 | 5793.39
TS5500Shv | MW\27\005\B | MW | 27 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-08-10 10:43 | 2018-08-12 09:49 | 62594.4959 | [6 empty] | 62594 | 46353 | 2.9 | 0 | 0 | 9.04 | 5633
DRE1 | SC\33\019\D | SC | 33 | 19 | D | 6 DL | 100 | 0 | 100 | 2018-08-10 14:21 | 2018-08-17 20:39 | 625042.8527 |  |  |  | 47532 | 625043 | 427786 |  |  | 0 | 40 | 0 | 7.24 | 5774.38
TS5500Exc | MW\28\005\B | MW | 28 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-08-10 22:24 | 2018-08-14 03:03 | 73863.0257 | 73863 | [7 empty] | 0 | 0 | 4.6 | 8.95 | 5631.06
TS6060#1 | BW\28\009\B | BW | 28 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-08-12 09:28 | 2018-08-14 20:06 | 86472.2837 | [6 empty] | 86472 | 62007 | 3.87 | 0 | 0 | 14.45 | 5140
TS5500Shv | MW\27\010\B | MW | 27 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-08-12 09:49 | 2018-08-14 07:41 | 60941.9579 | [6 empty] | 60942 | 45186 | 2.82 | 0 | 0 | 8.88 | 5653
DRE2 | BW\25\006\D | BW | 25 | 6 | D | 6 DL | 100 | 100 | 100 | 2018-08-12 22:11 | 2018-08-18 17:38 | 481603.039 |  |  |  | 21004 | 481603 | 347493 |  |  | 0 | 23.06 | 0 | 5.27 | 5951.01
TS5500Exc | SC\33\018\D | SC | 33 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-08-14 03:03 | 2018-08-16 07:00 | 71286.1526 | [6 empty] | 71286 | 53105 | 4.43 | 0 | 0 | 7.32 | 5769
PH4100A | SC\35\010\D | SC | 35 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-08-14 04:52 | 2018-08-18 11:33 | 193916.1102 | 193916 | [7 empty] | 0 | 0 | 16.14 | 7.67 | 5739.79
TS5500Shv | MW\28\011\X | MW | 28 | 11 | X | 8 Coal Mining | 100 | 0 | 100 | 2018-08-14 07:41 | 2018-08-15 06:42 | 30575.4507 | [6 empty] | 30575 | 22249 | 1.33 | 0 | 0 | 12.53 | 5161
TS6060#1 | BW\25\009\D | BW | 25 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-08-14 20:06 | 2018-08-17 18:58 | 104481.5657 | [6 empty] | 104482 | 79448 | 4.97 | 0 | 0 | 5.09 | 5967
TS5500Shv | MW\27\011\A | MW | 27 | 11 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-08-15 06:42 | 2018-08-17 23:45 | 86422.2528 | [6 empty] | 86422 | 63256 | 3.47 | 0 | 0 | 11.51 | 5413
TS5500Exc | MW\28\004\B | MW | 28 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-08-16 07:00 | 2018-08-18 05:51 | 64296.3484 | [6 empty] | 64296 | 47691 | 2.97 | 0 | 0 | 8.9 | 5602
TS Fleet 5 | BW\29\005\B | BW | 29 | 5 | B | 1 Prestrip - Thick | 54.5941 | 54.5941 | 54.5941 | 2018-08-16 09:33 | 2018-08-20 05:49 | 188583.6116 | 188584 | [7 empty] | 0 | 0 | 16.06 | 10.86 | 5454.98
TS6060#1 | BW\25\008\D | BW | 25 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-08-17 18:58 | 2018-08-20 16:18 | 102242.9018 | [6 empty] | 102243 | 77873 | 4.87 | 0 | 0 | 4.89 | 5984
DRE1 | SC\33\020\D | SC | 33 | 20 | D | 6 DL | 100 | 0 | 100 | 2018-08-17 20:39 | 2018-08-25 03:13 | 626074.6278 |  |  |  | 47610 | 626075 | 428492 |  |  | 0 | 40 | 0 | 7.31 | 5770.2
TS5500Shv | GG\02\003\D | GG | 2 | 3 | D | 1 Prestrip - Thick | 43.0714 | 43.0714 | 43.0714 | 2018-08-17 23:45 | 2018-08-25 16:15 | 214792.3133 | 214792 | [7 empty] | 0 | 0 | 11.26 | 5.22 | 5923.58
TS5500Exc | MW\27\011\B | MW | 27 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-08-18 05:51 | 2018-08-20 08:31 | 48824.4801 | 48824 | [7 empty] | 0 | 0 | 2.7 | 8.65 | 5666.5
PH4100A | SC\36\010\D | SC | 36 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-08-18 11:33 | 2018-08-23 18:23 | 239139.6578 | 239140 | [7 empty] | 0 | 0 | 20.17 | 7.71 | 5736.49
DRE2 | BW\25\005\D | BW | 25 | 5 | D | 6 DL | 100 | 100 | 100 | 2018-08-18 17:38 | 2018-08-24 12:39 | 480090.6129 |  |  |  | 20938 | 480091 | 346402 |  |  | 0 | 22.97 | 0 | 5.41 | 5937.8
PH4100XPC#1 | BW\28\010\B | BW | 28 | 10 | B | 1 Prestrip - Thick | 100 | 15.6297 | 14.9824 | 2018-08-18 23:46 | 2018-08-21 02:39 | 129575.0268 | 129575 | [7 empty] | 0 | 0 | 7.46 | 16.77 | 4929.66
TS Fleet 5 | BW\29\005\B | BW | 29 | 5 | B | 1 Prestrip - Thick | 45.4059 | 45.4059 | 45.4059 | 2018-08-20 05:49 | 2018-08-23 10:33 | 156845.0656 | 156845 | [7 empty] | 0 | 0 | 13.36 | 10.86 | 5454.98
TS5500Exc | SC\33\019\D | SC | 33 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-08-20 08:31 | 2018-08-22 11:12 | 69564.456 | [6 empty] | 69564 | 51739 | 4.31 | 0 | 0 | 7.24 | 5774
TS6060#1 | BW\25\007\D | BW | 25 | 7 | D | 8 Coal Mining | 79.3 | 0 | 68.2 | 2018-08-20 16:18 | 2018-08-22 15:51 | 70119.7612 | [6 empty] | 70120 | 53363 | 3.34 | 0 | 0 | 5.03 | 5972
PH4100XPC#1 | RS\07\008\A | RS | 7 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-08-21 02:39 | 2018-08-28 02:55 | 389233.5207 | 389234 | [7 empty] | 0 | 0 | 47.97 | 16.98 | 4936.49
TS5500Exc | MW\27\011\B | MW | 27 | 11 | B | 8 Coal Mining | 100 | 0 | 9.5 | 2018-08-22 11:12 | 2018-08-22 15:51 | 6374.3518 | [6 empty] | 6374 | 4743 | 0.26 | 0 | 0 | 8.65 | 5667
TS6060#1 | BW\29\007\B | BW | 29 | 7 | B | 1 Prestrip - Thick | 12.4809 | 12.4809 | 12.4809 | 2018-08-22 15:51 | 2018-08-25 15:59 | 80359.5344 | 80360 | [7 empty] | 0 | 0 | 8.01 | 12.36 | 5331.8
TS5500Exc | MW\28\010\B | MW | 28 | 10 | B | 1 Prestrip - Thick | 89.2462 | 89.2462 | 89.2462 | 2018-08-22 15:51 | 2018-08-24 12:17 | 42811.9943 | 42812 | [7 empty] | 0 | 0 | 2.68 | 9 | 5633.49
TS Fleet 5 | BW\29\006\B | BW | 29 | 6 | B | 1 Prestrip - Thick | 67.8231 | 67.8231 | 67.8231 | 2018-08-23 10:33 | 2018-08-31 15:18 | 402186.0664 | 402186 | [7 empty] | 0 | 0 | 40.15 | 11.9 | 5370.13
PH4100A | SC\35\011\D | SC | 35 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-08-23 18:23 | 2018-08-26 19:21 | 137088.4026 | 137088 | [7 empty] | 0 | 0 | 11.71 | 7.67 | 5739.73
TS5500Exc | MW\28\010\B | MW | 28 | 10 | B | 1 Prestrip - Thick | 10.7538 | 10.7538 | 10.7538 | 2018-08-24 12:17 | 2018-08-24 17:38 | 5158.6545 | 5159 | [7 empty] | 0 | 0 | 0.32 | 9 | 5633.49
DRE2 | BW\25\004\D | BW | 25 | 4 | D | 6 DL | 100 | 100 | 100 | 2018-08-24 12:39 | 2018-08-30 07:08 | 478212.3758 |  |  |  | 20856 | 478212 | 345046 |  |  | 0 | 22.86 | 0 | 5.69 | 5913.04
TS5500Exc | MW\28\011\A | MW | 28 | 11 | A | 1 Prestrip - Thick | 16.6388 | 16.6388 | 16.6388 | 2018-08-24 17:38 | 2018-08-27 00:41 | 53046.3729 | 53046 | [7 empty] | 0 | 0 | 3.29 | 11.9 | 5377.22
DRE1 | SC\33\021\D | SC | 33 | 21 | D | 6 DL | 100 | 0 | 66.8768 | 2018-08-25 03:13 | 2018-09-01 | 590923.9826 |  |  |  | 31046 | 590924 | 271412 |  |  | 0 | 39.64 | 0 | 7.25 | 5776.5
TS6060#1 | BW\29\007\B | BW | 29 | 7 | B | 1 Prestrip - Thick | 24.4008 | 24.4008 | 24.4008 | 2018-08-25 15:59 | 2018-08-31 13:01 | 157107.4071 | 157107 | [7 empty] | 0 | 0 | 15.66 | 12.36 | 5331.8
TS5500Shv | GG\02\003\D | GG | 2 | 3 | D | 7 PostStrip | 70.6765 | 0 | 70.6765 | 2018-08-25 16:15 | 2018-08-28 16:25 | 84292.1514 |  |  | 84292 | [5 empty] | 0 | 0 | 0 | 5.22 | 5923.58
PH4100A | SC\36\011\D | SC | 36 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-08-26 19:21 | 2018-08-29 22:48 | 141483.6883 | 141484 | [7 empty] | 0 | 0 | 12.15 | 7.67 | 5739.95
TS5500Exc | MW\29\001\D | MW | 29 | 1 | D | 1 Prestrip - Thick | 17.32 | 17.32 | 17.32 | 2018-08-27 00:41 | 2018-08-27 13:27 | 12296.8297 | 12297 | [7 empty] | 0 | 0 | 1.13 | 7.35 | 5766.84
TS5500Exc | MW\29\001\D | MW | 29 | 1 | D | 1 Prestrip - Thick | 12.4456 | 12.4456 | 12.4456 | 2018-08-27 13:27 | 2018-08-27 22:37 | 8836.1481 | 8836 | [7 empty] | 0 | 0 | 0.81 | 7.35 | 5766.84
TS5500Exc | MW\29\005\A | MW | 29 | 5 | A | 1 Prestrip - Thick | 27.8673 | 27.8673 | 27.8673 | 2018-08-27 22:37 | 2018-08-29 23:32 | 47223.1163 | 47223 | [7 empty] | 0 | 0 | 4.9 | 9.68 | 5490.3
PH4100XPC#1 | RS\08\008\X | RS | 8 | 8 | X | 1 Prestrip - Thick | 100 | 81.2562 | 81.2562 | 2018-08-28 02:55 | 2018-09-01 | 210531.7464 | 210532 | [7 empty] | 0 | 0 | 25.78 | 14.34 | 4997.25
TS5500Shv | GG\02\004\D | GG | 2 | 4 | D | 1 Prestrip - Thick | 15.5512 | 15.2954 | 15.2954 | 2018-08-28 16:25 | 2018-09-01 | 91628.7862 | 91629 | [7 empty] | 0 | 0 | 5.3 | 5.36 | 5912.38
PH4100A | SC\35\012\D | SC | 35 | 12 | D | 1 Prestrip - Thick | 100 | 79.6079 | 79.6079 | 2018-08-29 22:48 | 2018-09-01 | 91759.77 | 91760 | [7 empty] | 0 | 0 | 7.93 | 7.64 | 5741.21
TS5500Exc | MW\29\006\A | MW | 29 | 6 | A | 1 Prestrip - Thick | 7.3315 | 7.3315 | 7.3315 | 2018-08-29 23:32 | 2018-08-30 16:18 | 16261.6912 | 16262 | [7 empty] | 0 | 0 | 1.6 | 10.63 | 5414.51
DRE2 | BW\25\003\D | BW | 25 | 3 | D | 6 DL | 100 | 23.5602 | 23.5602 | 2018-08-30 07:08 | 2018-09-01 | 141123.6324 |  |  |  | 5294 | 141124 | 67313 |  |  | 0 | 22.91 | 0 | 6.12 | 5875.67
TS5500Exc | MW\29\006\A | MW | 29 | 6 | A | 1 Prestrip - Thick | 23.9913 | 13.8613 | 13.8613 | 2018-08-30 16:18 | 2018-09-01 | 30745.2891 | 30745 | [7 empty] | 0 | 0 | 3.02 | 10.63 | 5414.51
TS6060#1 | GG\02\003\D | GG | 2 | 3 | D | 7 PostStrip | 29.3235 | 0 | 10.342 | 2018-08-31 13:01 | 2018-09-01 | 12334.3489 |  |  | 12334 | [5 empty] | 0 | 0 | 0 | 5.22 | 5923.58
TS Fleet 5 | BW\29\007\B | BW | 29 | 7 | B | 1 Prestrip - Thick | 63.1184 | 2.7567 | 2.7567 | 2018-08-31 15:18 | 2018-09-01 | 17749.0801 | 17749 | [7 empty] | 0 | 0 | 1.77 | 12.36 | 5331.8
| EOP 56 : 2018\Aug | EOP 56 : 2018 | Aug | [6 empty] | 2018-09-01 | 2018-09-01 |  | 5875643 |  | 96627 | 296140 | 5237555 | 3541132 | 1424700 | 1061750 | 71 | 0 | 465.47 | 7.88 | 5714.45
TS Fleet 5 | BW\29\007\B | BW | 29 | 7 | B | 1 Prestrip - Thick | 63.1184 | 60.3617 | 60.3617 | 2018-09-01 | 2018-09-09 00:46 | 388646.466 | 388646 | [7 empty] | 0 | 0 | 38.75 | 12.36 | 5331.8
DRE1 | SC\33\021\D | SC | 33 | 21 | D | 6 DL | 100 | 0 | 33.1232 | 2018-09-01 | 2018-09-04 09:36 | 292677.5303 |  |  |  | 15377 | 292678 | 134427 |  |  | 0 | 39.64 | 0 | 7.25 | 5776.5
PH4100A | SC\35\012\D | SC | 35 | 12 | D | 1 Prestrip - Thick | 100 | 20.3921 | 20.3921 | 2018-09-01 | 2018-09-01 12:46 | 23504.8688 | 23505 | [7 empty] | 0 | 0 | 2.03 | 7.64 | 5741.21
DRE2 | BW\25\003\D | BW | 25 | 3 | D | 6 DL | 100 | 76.4398 | 76.4398 | 2018-09-01 | 2018-09-06 12:34 | 457867.6861 |  |  |  | 17175 | 457868 | 218394 |  |  | 0 | 22.91 | 0 | 6.12 | 5875.67
PH4100XPC#1 | RS\08\008\X | RS | 8 | 8 | X | 1 Prestrip - Thick | 100 | 18.7438 | 18.7438 | 2018-09-01 | 2018-09-01 21:45 | 48564.4693 | 48564 | [7 empty] | 0 | 0 | 5.95 | 14.34 | 4997.25
TS5500Shv | GG\02\004\D | GG | 2 | 4 | D | 1 Prestrip - Thick | 15.5512 | 0.25584 | 0.25584 | 2018-09-01 | 2018-09-01 01:20 | 1532.6357 | 1533 | [7 empty] | 0 | 0 | 0.09 | 5.36 | 5912.38
TS6060#1 | GG\02\003\D | GG | 2 | 3 | D | 7 PostStrip | 29.3235 | 0 | 18.9815 | 2018-09-01 | 2018-09-01 20:25 | 22638.2406 |  |  | 22638 | [5 empty] | 0 | 0 | 0 | 5.22 | 5923.58
TS5500Exc | MW\29\006\A | MW | 29 | 6 | A | 1 Prestrip - Thick | 23.9913 | 10.13 | 10.13 | 2018-09-01 | 2018-09-01 23:28 | 22468.8442 | 22469 | [7 empty] | 0 | 0 | 2.21 | 10.63 | 5414.51
TS5500Shv | RS\07\008\A | RS | 7 | 8 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-09-01 01:20 | 2018-09-02 05:03 | 36300.7333 | [6 empty] | 36301 | 24874 | 3.59 | 0 | 0 | 16.98 | 4936
PH4100A | SC\36\012\D | SC | 36 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-09-01 12:46 | 2018-09-03 19:44 | 101079.1717 | 101079 | [7 empty] | 0 | 0 | 8.79 | 7.6 | 5744.66
TS6060#1 | BW\28\010\B | BW | 28 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-09-01 20:25 | 2018-09-04 09:41 | 89124.1212 | [6 empty] | 89124 | 63269 | 3.95 | 0 | 0 | 16.77 | 4930
PH4100XPC#1 | RS\07\007\A | RS | 7 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-09-01 21:45 | 2018-09-10 00:57 | 445552.8704 | 445553 | [7 empty] | 0 | 0 | 43.1 | 15.43 | 5016.27
TS5500Exc | SC\33\020\D | SC | 33 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-09-01 23:28 | 2018-09-04 05:44 | 73456.5185 | [6 empty] | 73457 | 54553 | 4.55 | 0 | 0 | 7.31 | 5770
TS5500Shv | RS\07\008\B | RS | 7 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-09-02 05:03 | 2018-09-02 22:08 | 19683.204 | 19683 | [7 empty] | 0 | 0 | 2.85 | 16.94 | 5017.09
TS5500Shv | RS\07\008\B | RS | 7 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-09-02 22:08 | 2018-09-04 02:43 | 37462.9665 | [6 empty] | 37463 | 25551 | 3.87 | 0 | 0 | 16.94 | 5017
PH4100A | SC\35\013\D | SC | 35 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-09-03 19:44 | 2018-09-07 17:34 | 171017.9626 | 171018 | [7 empty] | 0 | 0 | 14.66 | 7.73 | 5733.31
TS5500Shv | RS\08\008\X | RS | 8 | 8 | X | 8 Coal Mining | 100 | 0 | 100 | 2018-09-04 02:43 | 2018-09-04 13:58 | 14739.1792 | [6 empty] | 14739 | 10174 | 1.31 | 0 | 0 | 14.34 | 4997
TS5500Exc | MW\27\011\B | MW | 27 | 11 | B | 8 Coal Mining | 100 | 0 | 90.5 | 2018-09-04 05:44 | 2018-09-06 02:36 | 60716.3115 | [6 empty] | 60716 | 45179 | 2.52 | 0 | 0 | 8.65 | 5667
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 7d 00:00 |  | 7d 00:00 | 2018-09-04 09:36 | 2018-09-11 09:36
TS6060#1 | BW\25\007\D | BW | 25 | 7 | D | 8 Coal Mining | 79.3 | 0 | 11.2 | 2018-09-04 09:41 | 2018-09-04 17:34 | 11468.2901 | [6 empty] | 11468 | 8728 | 0.55 | 0 | 0 | 5.03 | 5972
TS5500Shv | RS\08\008\A | RS | 8 | 8 | A | 1 Prestrip - Thick | 100 | 99.8639 | 99.8639 | 2018-09-04 13:58 | 2018-09-10 01:02 | 150984.0224 | 150984 | [7 empty] | 0 | 0 | 22.82 | 17.46 | 4894.06
TS6060#1 | BW\28\011\B | BW | 28 | 11 | B | 8 Coal Mining | 49.4 | 0 | 49.4 | 2018-09-04 17:34 | 2018-09-05 14:37 | 30604.3646 | [6 empty] | 30604 | 22430 | 1.39 | 0 | 0 | 10.99 | 5366
TS6060#1 | BW\25\004\D | BW | 25 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-09-05 14:37 | 2018-09-08 10:52 | 99275.4834 | [6 empty] | 99275 | 74951 | 4.68 | 0 | 0 | 5.69 | 5913
TS5500Exc | MW\28\005\B | MW | 28 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-09-06 02:36 | 2018-09-08 01:48 | 63890.6115 | [6 empty] | 63891 | 47355 | 2.96 | 0 | 0 | 8.95 | 5631
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2018-09-06 12:34 | 2018-09-08 12:34
PH4100A | SC\36\013\D | SC | 36 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-09-07 17:34 | 2018-09-11 14:52 | 169908.7197 | 169909 | [7 empty] | 0 | 0 | 14.52 | 7.74 | 5732.71
TS5500Exc | MW\28\006\B | MW | 28 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-09-08 01:48 | 2018-09-10 02:11 | 65492.3619 | [6 empty] | 65492 | 48586 | 3.04 | 0 | 0 | 8.68 | 5669
TS6060#1 | BW\25\005\D | BW | 25 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-09-08 10:52 | 2018-09-11 07:26 | 99702.591 | [6 empty] | 99703 | 75454 | 4.72 | 0 | 0 | 5.41 | 5938
DRE2 | DT\26\004\D | DT | 26 | 4 | D | 6 DL | 100 | 100 | 100 | 2018-09-08 12:34 | 2018-09-14 22:45 | 532465.3136 |  |  |  | 23223 | 532465 | 384192 |  |  | 0 | 25.48 | 0 | 6.46 | 5845.7
TS Fleet 5 | BW\29\008\B | BW | 29 | 8 | B | 1 Prestrip - Thick | 74.6771 | 74.6771 | 74.6771 | 2018-09-09 00:46 | 2018-09-17 11:56 | 409573.322 | 409573 | [7 empty] | 0 | 0 | 42.51 | 13.39 | 5245.8
PH4100XPC#1 | RS\08\008\A | RS | 8 | 8 | A | 1 Prestrip - Thick | 100 | 0.13609 | 0.13609 | 2018-09-10 00:57 | 2018-09-10 01:02 | 205.7543 | 206 | [7 empty] | 0 | 0 | 0.03 | 17.46 | 4894.06
TS5500Shv | RS\08\008\A | RS | 8 | 8 | A | 8 Coal Mining | 29.7 | 0 | 29.7 | 2018-09-10 01:02 | 2018-09-10 08:35 | 9890.1277 | [6 empty] | 9890 | 6765 | 1.05 | 0 | 0 | 17.46 | 4894
PH4100XPC#1 | RS\08\007\X | RS | 8 | 7 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-09-10 01:02 | 2018-09-15 12:28 | 290827.6088 | 290828 | [7 empty] | 0 | 0 | 28.57 | 12.31 | 5177.77
TS5500Exc | SC\33\021\D | SC | 33 | 21 | D | 7 PostStrip | 100 | 0 | 100 | 2018-09-10 02:11 | 2018-09-12 21:03 | 63545.3597 |  |  | 63545 | [5 empty] | 0 | 0 | 0 | 7.25 | 5776.5
TS5500Shv | RS\07\007\A | RS | 7 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-09-10 08:35 | 2018-09-11 23:58 | 51608.4957 | [6 empty] | 51608 | 35534 | 3.57 | 0 | 0 | 15.43 | 5016
TS6060#1 | BW\25\006\D | BW | 25 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-09-11 07:26 | 2018-09-14 06:42 | 103665.6769 | [6 empty] | 103666 | 78702 | 4.92 | 0 | 0 | 5.27 | 5951
DRE1 | MW\25\003\D | MW | 25 | 3 | D | 6 DL | 100 | 100 | 100 | 2018-09-11 09:36 | 2018-09-17 16:53 | 542534.6763 |  |  |  | 32400 | 542535 | 382990 |  |  | 0 | 25.95 | 0 | 6.34 | 5855.81
PH4100A | SC\35\014\D | SC | 35 | 14 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-09-11 14:52 | 2018-09-18 16:22 | 306999.4907 | 306999 | [7 empty] | 0 | 0 | 18.89 | 7.59 | 5744.59
TS5500Shv | GG\02\004\D | GG | 2 | 4 | D | 1 Prestrip - Thick | 84.4488 | 84.4488 | 84.4488 | 2018-09-11 23:58 | 2018-09-30 13:25 | 505901.5553 | 505902 | [7 empty] | 0 | 0 | 29.26 | 5.36 | 5912.38
TS5500Exc | SC\33\021\D | SC | 33 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-09-12 21:03 | 2018-09-15 05:56 | 77015.088 | [6 empty] | 77015 | 57153 | 4.76 | 0 | 0 | 7.25 | 5777
TS6060#1 | BW\25\007\D | BW | 25 | 7 | D | 8 Coal Mining | 20.7 | 0 | 20.7 | 2018-09-14 06:42 | 2018-09-14 21:19 | 21260.2108 | [6 empty] | 21260 | 16180 | 1.01 | 0 | 0 | 5.03 | 5972
TS6060#1 | BW\28\011\B | BW | 28 | 11 | B | 8 Coal Mining | 50.6 | 0 | 50.6 | 2018-09-14 21:19 | 2018-09-15 18:54 | 31390.6526 | [6 empty] | 31391 | 23006 | 1.43 | 0 | 0 | 10.99 | 5366
DRE2 | DT\26\005\D | DT | 26 | 5 | D | 6 DL | 100 | 100 | 100 | 2018-09-14 22:45 | 2018-09-23 05:33 | 686490.7026 |  |  |  | 29940 | 686491 | 495326 |  |  | 0 | 23.88 | 0 | 6.7 | 5824.43
TS5500Exc | DT\26\004\D | DT | 26 | 4 | D | 8 Coal Mining | 72.7 | 0 | 72.7 | 2018-09-15 05:56 | 2018-09-17 12:24 | 73712.8447 | [6 empty] | 73713 | 55387 | 3.46 | 0 | 0 | 6.46 | 5846
PH4100XPC#1 | RS\07\007\B | RS | 7 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-09-15 12:28 | 2018-09-16 00:31 | 29237.2433 | 29237 | [7 empty] | 0 | 0 | 2.94 | 16.85 | 4962.29
TS6060#1 | BW\29\005\B | BW | 29 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-09-15 18:54 | 2018-09-17 11:17 | 58716.49 | [6 empty] | 58716 | 42877 | 3.67 | 0 | 0 | 10.86 | 5455
PH4100XPC#1 | RS\07\006\A | RS | 7 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-09-16 00:31 | 2018-09-23 05:42 | 393099.5247 | 393100 | [7 empty] | 0 | 0 | 38.48 | 13.26 | 5155.52
TS6060#1 | RS\07\007\B | RS | 7 | 7 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2018-09-17 11:17 | 2018-09-18 07:57 | 30069.8143 | [6 empty] | 30070 | 20569 | 2.06 | 0 | 0 | 16.85 | 4962
TS Fleet 5 | BW\29\008\B | BW | 29 | 8 | B | 1 Prestrip - Thick | 25.3229 | 25.3229 | 25.3229 | 2018-09-17 11:56 | 2018-09-20 08:50 | 138885.9001 | 138886 | [7 empty] | 0 | 0 | 14.41 | 13.39 | 5245.8
TS5500Exc | DT\26\004\D | DT | 26 | 4 | D | 8 Coal Mining | 27.3 | 0 | 27.3 | 2018-09-17 12:24 | 2018-09-18 08:48 | 27621.9598 | [6 empty] | 27622 | 20755 | 1.3 | 0 | 0 | 6.46 | 5846
DRE1 | MW\25\004\D | MW | 25 | 4 | D | 6 DL | 100 | 100 | 100 | 2018-09-17 16:53 | 2018-09-24 01:52 | 548619.8642 |  |  |  | 32764 | 548620 | 387286 |  |  | 0 | 26.52 | 0 | 6.39 | 5850.12
TS6060#1 | BW\29\006\B | BW | 29 | 6 | B | 8 Coal Mining | 21.4 | 0 | 21.4 | 2018-09-18 07:57 | 2018-09-18 15:32 | 11022.5196 | [6 empty] | 11023 | 8002 | 0.8 | 0 | 0 | 11.9 | 5370
TS5500Exc | MW\25\003\D | MW | 25 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-09-18 08:48 | 2018-09-21 08:29 | 97037.8119 | [6 empty] | 97038 | 73434 | 4.59 | 0 | 0 | 6.34 | 5856
TS6060#1 | BW\25\003\D | BW | 25 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2018-09-18 15:32 | 2018-09-21 21:07 | 86021.1516 |  |  | 86021 | [5 empty] | 0 | 0 | 0 | 6.12 | 5875.67
PH4100A | SC\36\014\D | SC | 36 | 14 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-09-18 16:22 | 2018-09-23 07:28 | 201658.9863 | 201659 | [7 empty] | 0 | 0 | 17.08 | 7.7 | 5735
TS Fleet 5 | BW\29\009\X2 | BW | 29 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2018-09-20 08:50 | 2018-09-25 04:51 | 233898.8916 | 233899 | [7 empty] | 0 | 0 | 23.8 | 0 | 0
TS5500Exc | MW\28\007\B | MW | 28 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-09-21 08:29 | 2018-09-23 06:04 | 61687.173 | [6 empty] | 61687 | 45376 | 2.84 | 0 | 0 | 9.76 | 5540
TS6060#1 | BW\29\010\A | BW | 29 | 10 | A | 1 Prestrip - Thick | 6.9418 | 0 | 6.9418 | 2018-09-21 21:07 | 2018-09-23 04:58 | 34836.8193 | 34837 | [7 empty] | 0 | 0 | 3.22 | 0 | 0
TS6060#1 | BW\29\010\A | BW | 29 | 10 | A | 1 Prestrip - Thick | 29.0155 | 0 | 29.0155 | 2018-09-23 04:58 | 2018-09-28 18:07 | 145611.3699 | 145611 | [7 empty] | 0 | 0 | 13.46 | 0 | 0
DRE2 | DT\27\001\B | DT | 27 | 1 | B | 6 DL | 100 | 0 | 100 | 2018-09-23 05:33 | 2018-09-26 02:24 | 237791.4827 |  |  |  |  | 237791 | 237791 |  |  | 0 | 10.96 | 0 | 12.55 | 5259.95
PH4100XPC#1 | RS\08\006\A | RS | 8 | 6 | A | 1 Prestrip - Thick | 100 | 98.1193 | 98.1193 | 2018-09-23 05:42 | 2018-10-01 | 425549.4382 | 425549 | [7 empty] | 0 | 0 | 41.82 | 13.57 | 5125.94
TS5500Exc | MW\28\008\B | MW | 28 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-09-23 06:04 | 2018-09-25 05:18 | 63941.4991 | [6 empty] | 63941 | 46740 | 2.92 | 0 | 0 | 10.71 | 5422
PH4100A | SC\36\015\D | SC | 36 | 15 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-09-23 07:28 | 2018-09-26 11:04 | 136765.2325 | 136765 | [7 empty] | 0 | 0 | 19.88 | 7.38 | 5761.25
DRE1 | MW\25\005\D | MW | 25 | 5 | D | 6 DL | 100 | 100 | 100 | 2018-09-24 01:52 | 2018-09-30 16:17 | 568132.461 |  |  |  | 33929 | 568132 | 401060 |  |  | 0 | 27.19 | 0 | 6.52 | 5837.25
TS Fleet 5 | BW\29\009\B | BW | 29 | 9 | B | 1 Prestrip - Thick | 59.3609 | 59.3609 | 59.3609 | 2018-09-25 04:51 | 2018-09-29 01:25 | 186609.7777 | 186610 | [7 empty] | 0 | 0 | 18.67 | 14.63 | 5131.11
TS5500Exc | BW\29\009\B | BW | 29 | 9 | B | 1 Prestrip - Thick | 100 | 32.5638 | 32.5638 | 2018-09-25 05:18 | 2018-09-29 17:01 | 102369.1712 | 102369 | [7 empty] | 0 | 0 | 10.24 | 14.63 | 5131.11
DRE2 | DT\26\003\D | DT | 26 | 3 | D | 6 DL | 100 | 79.0535 | 79.0535 | 2018-09-26 02:24 | 2018-10-01 | 406103.2151 |  |  |  | 17712 | 406103 | 293017 |  |  | 0 | 24.63 | 0 | 6.3 | 5860.13
PH4100A | SC\35\016\D | SC | 35 | 16 | D | 1 Prestrip - Thick | 100 | 79.3978 | 79.3978 | 2018-09-26 11:04 | 2018-10-01 | 198715.2609 | 198715 | [7 empty] | 0 | 0 | 11.9 | 6.73 | 5819.17
TS6060#1 | BW\29\009\B | BW | 29 | 9 | B | 1 Prestrip - Thick | 100 | 8.0753 | 8.0753 | 2018-09-28 18:07 | 2018-09-29 17:01 | 25385.8784 | 25386 | [7 empty] | 0 | 0 | 2.54 | 14.63 | 5131.11
TS Fleet 5 | BW\29\010\A | BW | 29 | 10 | A | 1 Prestrip - Thick | 64.0427 | 0 | 18.7123 | 2018-09-29 01:25 | 2018-10-01 | 93905.6426 | 93906 | [7 empty] | 0 | 0 | 8.68 | 0 | 0
TS6060#1 | DT\26\005\D | DT | 26 | 5 | D | 8 Coal Mining | 100 | 0 | 8.8 | 2018-09-29 17:01 | 2018-09-30 01:30 | 12340.6997 | [6 empty] | 12341 | 9251 | 0.42 | 0 | 0 | 6.7 | 5824
TS5500Exc | MW\25\004\D | MW | 25 | 4 | D | 8 Coal Mining | 100 | 0 | 12.3 | 2018-09-29 17:01 | 2018-09-30 01:30 | 11485.4037 | [6 empty] | 11485 | 8684 | 0.54 | 0 | 0 | 6.39 | 5850
TS6060#1 | BW\30\006\B | BW | 30 | 6 | B | 1 Prestrip - Thick | 6.7973 | 4.1937 | 4.1937 | 2018-09-30 01:30 | 2018-10-01 | 24678.4546 | 24678 | [7 empty] | 0 | 0 | 2.43 | 12.05 | 5357.59
TS5500Exc | MW\29\009\A | MW | 29 | 9 | A | 1 Prestrip - Thick | 29.4605 | 4.9825 | 4.9825 | 2018-09-30 01:30 | 2018-10-01 | 21482.1994 | 21482 | [7 empty] | 0 | 0 | 2.15 | 11.53 | 5360.76
TS5500Shv | GG\02\004\D | GG | 2 | 4 | D | 7 PostStrip | 47.1844 | 0 | 11.927 | 2018-09-30 13:25 | 2018-10-01 | 12173.7033 |  |  | 12174 | [5 empty] | 0 | 0 | 0 | 5.36 | 5912.38
DRE1 | MW\25\006\D | MW | 25 | 6 | D | 6 DL | 100 | 4.4316 | 4.4316 | 2018-09-30 16:17 | 2018-10-01 | 27659.2681 |  |  |  | 1652 | 27659 | 19525 |  |  | 0 | 29.9 | 0 | 6.85 | 5809.45
| EOP 57 : 2018\Sep | EOP 57 : 2018 | Sep | [6 empty] | 2018-10-01 | 2018-10-01 |  | 5449141 |  | 184378 | 204172 | 4300342 | 2954009 | 1424700 | 1049515 | 76.46 | 0 | 506.71 | 8.89 | 5625.01
TS Fleet 5 | BW\29\010\A | BW | 29 | 10 | A | 1 Prestrip - Thick | 64.0427 | 0 | 45.3305 | 2018-10-01 | 2018-10-05 23:28 | 227486.5674 | 227487 | [7 empty] | 0 | 0 | 21.03 | 0 | 0
DRE1 | MW\25\006\D | MW | 25 | 6 | D | 6 DL | 100 | 95.5684 | 95.5684 | 2018-10-01 | 2018-10-08 00:30 | 596479.0409 |  |  |  | 35622 | 596479 | 421071 |  |  | 0 | 29.9 | 0 | 6.85 | 5809.45
PH4100A | SC\35\016\D | SC | 35 | 16 | D | 1 Prestrip - Thick | 100 | 20.6022 | 20.6022 | 2018-10-01 | 2018-10-02 05:26 | 51562.8226 | 51563 | [7 empty] | 0 | 0 | 3.09 | 6.73 | 5819.17
DRE2 | DT\26\003\D | DT | 26 | 3 | D | 6 DL | 100 | 20.9465 | 20.9465 | 2018-10-01 | 2018-10-02 07:34 | 107603.6612 |  |  |  | 4693 | 107604 | 77640 |  |  | 0 | 24.63 | 0 | 6.3 | 5860.13
PH4100XPC#1 | RS\08\006\A | RS | 8 | 6 | A | 1 Prestrip - Thick | 100 | 1.8807 | 1.8807 | 2018-10-01 | 2018-10-01 03:43 | 8156.7534 | 8157 | [7 empty] | 0 | 0 | 0.8 | 13.57 | 5125.94
TS5500Shv | GG\02\004\D | GG | 2 | 4 | D | 7 PostStrip | 47.1844 | 0 | 35.2573 | 2018-10-01 | 2018-10-02 09:04 | 35986.4623 |  |  | 35986 | [5 empty] | 0 | 0 | 0 | 5.36 | 5912.38
TS6060#1 | BW\30\006\B | BW | 30 | 6 | B | 1 Prestrip - Thick | 6.7973 | 2.6036 | 2.6036 | 2018-10-01 | 2018-10-01 14:47 | 15320.9833 | 15321 | [7 empty] | 0 | 0 | 1.51 | 12.05 | 5357.59
TS5500Exc | MW\29\009\A | MW | 29 | 9 | A | 1 Prestrip - Thick | 29.4605 | 24.478 | 24.478 | 2018-10-01 | 2018-10-05 21:00 | 105538.1256 | 105538 | [7 empty] | 0 | 0 | 10.54 | 11.53 | 5360.76
PH4100XPC#1 | RS\07\005\A | RS | 7 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-10-01 03:43 | 2018-10-07 20:30 | 344549.2177 | 344549 | [7 empty] | 0 | 0 | 33.93 | 13.47 | 5161.58
TS6060#1 | RS\08\006\A | RS | 8 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-10-01 14:47 | 2018-10-03 04:14 | 51457.8547 | [6 empty] | 51458 | 35683 | 3.56 | 0 | 0 | 13.57 | 5126
PH4100A | SC\36\016\D | SC | 36 | 16 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-10-02 05:26 | 2018-10-06 18:31 | 191798.9521 | 191799 | [7 empty] | 0 | 0 | 11.33 | 6.96 | 5798.81
DRE2 | DT\26\002\D | DT | 26 | 2 | D | 6 DL | 100 | 100 | 100 | 2018-10-02 07:34 | 2018-10-10 06:17 | 650125.0388 |  |  |  | 28354 | 650125 | 469087 |  |  | 0 | 23.28 | 0 | 5.94 | 5891.71
TS5500Shv | RS\07\006\A | RS | 7 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-10-02 09:04 | 2018-10-04 02:43 | 51546.2441 | [6 empty] | 51546 | 35817 | 3.58 | 0 | 0 | 13.26 | 5156
TS6060#1 | DT\26\005\D | DT | 26 | 5 | D | 8 Coal Mining | 100 | 0 | 91.2 | 2018-10-03 04:14 | 2018-10-07 00:50 | 127195.9944 | [6 empty] | 127196 | 95346 | 4.36 | 0 | 0 | 6.7 | 5824
TS5500Shv | RS\07\006\B | RS | 7 | 6 | B | 1 Prestrip - Thick | 38.5648 | 38.5648 | 38.5648 | 2018-10-04 02:43 | 2018-10-04 13:56 | 12194.777 | 12195 | [7 empty] | 0 | 0 | 1.22 | 16.62 | 4936.56
TS5500Shv | RS\07\007\B | RS | 7 | 7 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2018-10-04 13:56 | 2018-10-05 11:49 | 27092.605 | [6 empty] | 27093 | 18533 | 1.86 | 0 | 0 | 16.85 | 4962
TS5500Shv | RS\08\007\X | RS | 8 | 7 | X | 8 Coal Mining | 100 | 0 | 100 | 2018-10-05 11:49 | 2018-10-06 00:13 | 15352.1024 | [6 empty] | 15352 | 10789 | 1.07 | 0 | 0 | 12.31 | 5178
TS5500Exc | DT\26\003\D | DT | 26 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-10-05 21:00 | 2018-10-09 03:56 | 100919.0783 | [6 empty] | 100919 | 75950 | 4.75 | 0 | 0 | 6.3 | 5860
TS Fleet 5 | BW\29\010\B | BW | 29 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-10-05 23:28 | 2018-10-07 03:33 | 53475.5143 | 53476 | [7 empty] | 0 | 0 | 5.33 | 16.99 | 4912.85
TS5500Shv | RS\08\007\A | RS | 8 | 7 | A | 1 Prestrip - Thick | 70.4036 | 51.7297 | 51.7297 | 2018-10-06 00:13 | 2018-10-10 06:54 | 111709.131 | 111709 | [7 empty] | 0 | 0 | 11.12 | 15.86 | 4980.49
PH4100A | RS\07\006\B | RS | 7 | 6 | B | 1 Prestrip - Thick | 100 | 61.4352 | 61.4352 | 2018-10-06 18:31 | 2018-10-07 05:24 | 19426.7735 | 19427 | [7 empty] | 0 | 0 | 1.94 | 16.62 | 4936.56
TS6060#1 | DT\27\001\B | DT | 27 | 1 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-10-07 00:50 | 2018-10-08 22:27 | 62650.251 | [6 empty] | 62650 | 45376 | 1.82 | 0 | 0 | 12.55 | 5260
TS Fleet 5 | BW\29\011\B | BW | 29 | 11 | B | 1 Prestrip - Thick | 91.3563 | 91.3563 | 91.3563 | 2018-10-07 03:33 | 2018-10-16 19:02 | 440737.7063 | 440738 | [7 empty] | 0 | 0 | 47.94 | 11.1 | 5354.09
PH4100A | SC\36\023\D | SC | 36 | 23 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-10-07 05:24 | 2018-10-11 06:31 | 169884.2329 | 169884 | [7 empty] | 0 | 0 | 13.57 | 7.2 | 5781.5
PH4100XPC#1 | RS\08\006\B | RS | 8 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-10-07 20:30 | 2018-10-08 10:07 | 31732.8373 | 31733 | [7 empty] | 0 | 0 | 3.17 | 17.01 | 4896.59
DRE1 | MW\25\007\D | MW | 25 | 7 | D | 6 DL | 100 | 100 | 100 | 2018-10-08 00:30 | 2018-10-15 13:10 | 639520.6231 |  |  |  | 38193 | 639521 | 451455 |  |  | 0 | 30.59 | 0 | 6.86 | 5809.64
PH4100XPC#1 | RS\08\007\A | RS | 8 | 7 | A | 1 Prestrip - Thick | 100 | 48.2703 | 48.2703 | 2018-10-08 10:07 | 2018-10-10 06:54 | 104238.4726 | 104238 | [7 empty] | 0 | 0 | 10.38 | 15.86 | 4980.49
TS6060#1 | RS\07\006\B | RS | 7 | 6 | B | 8 Coal Mining | 6.6 | 0 | 6.6 | 2018-10-08 22:27 | 2018-10-09 01:16 | 3866.4373 | [6 empty] | 3866 | 2657 | 0.27 | 0 | 0 | 16.62 | 4937
TS6060#1 | BW\25\003\D | BW | 25 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-10-09 01:16 | 2018-10-12 09:47 | 110603.1526 | [6 empty] | 110603 | 83102 | 4.86 | 0 | 0 | 6.12 | 5876
TS5500Exc | MW\25\004\D | MW | 25 | 4 | D | 8 Coal Mining | 100 | 0 | 87.7 | 2018-10-09 03:56 | 2018-10-11 20:12 | 82163.386 | [6 empty] | 82163 | 62122 | 3.88 | 0 | 0 | 6.39 | 5850
DRE2 | DT\26\001\D | DT | 26 | 1 | D | 6 DL | 100 | 100 | 100 | 2018-10-10 06:17 | 2018-10-17 12:48 | 594833.1443 |  |  |  | 25943 | 594833 | 429192 |  |  | 0 | 20.55 | 0 | 6.01 | 5883.16
TS5500Shv | RS\07\006\B | RS | 7 | 6 | B | 8 Coal Mining | 93.4 | 0 | 93.4 | 2018-10-10 06:54 | 2018-10-12 02:49 | 54354.9804 | [6 empty] | 54355 | 37346 | 3.73 | 0 | 0 | 16.62 | 4937
PH4100XPC#1 | RS\08\005\A | RS | 8 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-10-10 06:54 | 2018-10-17 13:58 | 378117.642 | 378118 | [7 empty] | 0 | 0 | 36.96 | 13.8 | 5141.95
PH4100A | SC\36\022\D | SC | 36 | 22 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-10-11 06:31 | 2018-10-14 20:21 | 150488.0981 | 150488 | [7 empty] | 0 | 0 | 12.91 | 7.27 | 5774.56
TS5500Exc | MW\25\005\D | MW | 25 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-10-11 20:12 | 2018-10-14 17:47 | 88943.8002 | [6 empty] | 88944 | 66863 | 4.18 | 0 | 0 | 6.52 | 5837
TS5500Shv | RS\07\005\A | RS | 7 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-10-12 02:49 | 2018-10-13 18:58 | 49698.8941 | [6 empty] | 49699 | 34683 | 3.47 | 0 | 0 | 13.47 | 5162
TS6060#1 | RS\08\007\A | RS | 8 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-10-12 09:47 | 2018-10-13 22:44 | 50758.5378 | [6 empty] | 50759 | 34889 | 3.5 | 0 | 0 | 15.86 | 4980
TS5500Shv | RS\07\005\B | RS | 7 | 5 | B | 1 Prestrip - Thick | 79.2008 | 79.2008 | 79.2008 | 2018-10-13 18:58 | 2018-10-14 18:20 | 25415.2445 | 25415 | [7 empty] | 0 | 0 | 2.54 | 17.93 | 4858.37
TS6060#1 | BW\29\006\B | BW | 29 | 6 | B | 8 Coal Mining | 78.6 | 0 | 78.6 | 2018-10-13 22:44 | 2018-10-15 04:08 | 40388.0143 | [6 empty] | 40388 | 29319 | 2.93 | 0 | 0 | 11.9 | 5370
TS5500Exc | MW\25\006\D | MW | 25 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-10-14 17:47 | 2018-10-17 19:35 | 94337.4542 | [6 empty] | 94337 | 70588 | 4.41 | 0 | 0 | 6.85 | 5809
TS5500Shv | RS\08\007\B | RS | 8 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-10-14 18:20 | 2018-10-15 18:16 | 26036.4797 | 26036 | [7 empty] | 0 | 0 | 2.61 | 16.99 | 4942.2
PH4100A | RS\07\005\B | RS | 7 | 5 | B | 1 Prestrip - Thick | 100 | 20.7992 | 20.7992 | 2018-10-14 20:21 | 2018-10-15 00:05 | 6674.3772 | 6674 | [7 empty] | 0 | 0 | 0.67 | 17.93 | 4858.37
PH4100A | SC\36\021\D | SC | 36 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-10-15 00:05 | 2018-10-18 22:16 | 165222.2569 | 165222 | [7 empty] | 0 | 0 | 14.1 | 7.14 | 5785.71
TS6060#1 | BW\29\007\B | BW | 29 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-10-15 04:08 | 2018-10-16 18:49 | 53134.0797 | [6 empty] | 53134 | 38440 | 3.84 | 0 | 0 | 12.36 | 5332
DRE1 | MW\25\008\D | MW | 25 | 8 | D | 6 DL | 100 | 100 | 100 | 2018-10-15 13:10 | 2018-10-23 06:11 | 654860.1843 |  |  |  | 48951 | 654860 | 450547 |  |  | 0 | 31.29 | 0 | 6.77 | 5819.08
TS5500Shv | GG\03\002\D | GG | 3 | 2 | D | 1 Prestrip - Thick | 10.693 | 10.693 | 10.693 | 2018-10-15 18:16 | 2018-10-18 13:20 | 72841.3094 | 72841 | [7 empty] | 0 | 0 | 4.06 | 5.36 | 5914.56
TS6060#1 | BW\29\008\B | BW | 29 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-10-16 18:49 | 2018-10-18 09:03 | 52507.715 | [6 empty] | 52508 | 37784 | 3.78 | 0 | 0 | 13.39 | 5246
TS Fleet 5 | BW\29\011\B | BW | 29 | 11 | B | 1 Prestrip - Thick | 8.6437 | 8.6437 | 8.6437 | 2018-10-16 19:02 | 2018-10-17 16:56 | 41700.2854 | 41700 | [7 empty] | 0 | 0 | 4.54 | 11.1 | 5354.09
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2018-10-17 12:48 | 2018-10-19 12:48
PH4100XPC#1 | RS\07\004\A | RS | 7 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-10-17 13:58 | 2018-10-23 14:24 | 303693.1237 | 303693 | [7 empty] | 0 | 0 | 29.92 | 12.93 | 5237.13
TS Fleet 5 | BW\30\005\X2 | BW | 30 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2018-10-17 16:56 | 2018-10-24 01:43 | 290885.1782 | 290885 | [7 empty] | 0 | 0 | 34.27 | 0 | 0
TS5500Exc | DT\25\001\D | DT | 25 | 1 | D | 8 Coal Mining | 20 | 0 | 20 | 2018-10-17 19:35 | 2018-10-18 14:26 | 24097.6818 | [6 empty] | 24098 | 18105 | 0.92 | 0 | 0 | 6.12 | 5874
TS6060#1 | RS\08\005\A | RS | 8 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-10-18 09:03 | 2018-10-19 22:28 | 51400.3566 | [6 empty] | 51400 | 35801 | 3.57 | 0 | 0 | 13.8 | 5142
TS5500Shv | GG\03\002\D | GG | 3 | 2 | D | 1 Prestrip - Thick | 88.2141 | 51.4425 | 51.4425 | 2018-10-18 13:20 | 2018-11-01 | 350428.1628 | 350428 | [7 empty] | 0 | 0 | 19.52 | 5.36 | 5914.56
TS5500Exc | MW\25\007\D | MW | 25 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-10-18 14:26 | 2018-10-21 19:32 | 98570.2308 | [6 empty] | 98570 | 73823 | 4.61 | 0 | 0 | 6.86 | 5810
PH4100A | SC\36\020\D | SC | 36 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-10-18 22:16 | 2018-10-23 14:02 | 195781.4531 | 195781 | [7 empty] | 0 | 0 | 16.52 | 7.22 | 5777.18
DRE2 | BW\26\011\D | BW | 26 | 11 | D | 6 DL | 100 | 100 | 100 | 2018-10-19 12:48 | 2018-10-24 17:24 | 424700.6618 |  |  |  | 18523 | 424701 | 306436 |  |  | 0 | 20.29 | 0 | 5.84 | 5899.44
TS6060#1 | BW\29\009\B | BW | 29 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-10-19 22:28 | 2018-10-21 13:31 | 53624.9958 | [6 empty] | 53625 | 38384 | 3.84 | 0 | 0 | 14.63 | 5131
TS6060#1 | BW\29\010\B | BW | 29 | 10 | B | 8 Coal Mining | 25.6 | 0 | 25.6 | 2018-10-21 13:31 | 2018-10-22 00:02 | 14445.4333 | [6 empty] | 14445 | 10238 | 1.02 | 0 | 0 | 16.99 | 4913
TS5500Exc | MW\28\009\B | MW | 28 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-10-21 19:32 | 2018-10-23 20:50 | 63026.0191 | [6 empty] | 63026 | 46300 | 2.89 | 0 | 0 | 10.01 | 5510
TS6060#1 | GG\02\004\D | GG | 2 | 4 | D | 7 PostStrip | 52.8156 | 0 | 52.8156 | 2018-10-22 00:02 | 2018-10-24 03:30 | 53907.9031 |  |  | 53908 | [5 empty] | 0 | 0 | 0 | 5.36 | 5912.38
DRE1 | MW\25\009\D | MW | 25 | 9 | D | 6 DL | 100 | 100 | 100 | 2018-10-23 06:11 | 2018-10-30 08:42 | 603586.2218 |  |  |  | 36047 | 603586 | 426088 |  |  | 0 | 28.92 | 0 | 6.05 | 5879.46
PH4100A | SC\36\019\D | SC | 36 | 19 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-10-23 14:02 | 2018-10-28 20:55 | 221963.0416 | 221963 | [7 empty] | 0 | 0 | 18.57 | 7.25 | 5774.5
PH4100XPC#1 | RS\08\005\B | RS | 8 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-10-23 14:24 | 2018-10-24 04:57 | 33865.6222 | 33866 | [7 empty] | 0 | 0 | 3.38 | 18.7 | 4797.13
TS5500Exc | MW\25\008\D | MW | 25 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-10-23 20:50 | 2018-10-27 04:41 | 102079.1999 | [6 empty] | 102079 | 76458 | 4.78 | 0 | 0 | 6.77 | 5819
TS Fleet 5 | BW\30\005\B | BW | 30 | 5 | B | 1 Prestrip - Thick | 64.5204 | 63.3726 | 63.3726 | 2018-10-24 01:43 | 2018-10-27 11:38 | 155970.1182 | 155970 | [7 empty] | 0 | 0 | 19.07 | 11.13 | 5431.41
TS6060#1 | BW\30\005\B | BW | 30 | 5 | B | 1 Prestrip - Thick | 100 | 34.0926 | 34.0926 | 2018-10-24 03:30 | 2018-10-27 11:38 | 83907.2251 | 83907 | [7 empty] | 0 | 0 | 10.26 | 11.13 | 5431.41
PH4100XPC#1 | RS\08\004\A | RS | 8 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-10-24 04:57 | 2018-10-30 23:59 | 346755.2768 | 346755 | [7 empty] | 0 | 0 | 34.2 | 12.76 | 5256.85
DRE2 | BW\26\010\D | BW | 26 | 10 | D | 6 DL | 100 | 100 | 100 | 2018-10-24 17:24 | 2018-10-30 00:23 | 432860.0399 |  |  |  | 18878 | 432860 | 312323 |  |  | 0 | 20.72 | 0 | 5.53 | 5930.08
TS5500Exc | BW\30\005\B | BW | 30 | 5 | B | 1 Prestrip - Thick | 100 | 2.5348 | 2.5348 | 2018-10-27 04:41 | 2018-10-27 11:38 | 6238.6138 | 6239 | [7 empty] | 0 | 0 | 0.76 | 11.13 | 5431.41
TS Fleet 5 | BW\30\006\B | BW | 30 | 6 | B | 1 Prestrip - Thick | 65.233 | 35.0612 | 35.0612 | 2018-10-27 11:38 | 2018-11-01 | 206320.6302 | 206321 | [7 empty] | 0 | 0 | 20.28 | 12.05 | 5357.59
TS6060#1 | BW\30\006\B | BW | 30 | 6 | B | 1 Prestrip - Thick | 27.9696 | 19.0813 | 19.0813 | 2018-10-27 11:38 | 2018-11-01 | 112285.5001 | 112286 | [7 empty] | 0 | 0 | 11.04 | 12.05 | 5357.59
TS5500Exc | MW\28\010\B | MW | 28 | 10 | B | 8 Coal Mining | 100 | 0 | 0.8 | 2018-10-27 11:38 | 2018-10-27 12:01 | 485.5013 | [6 empty] | 486 | 360 | 0.02 | 0 | 0 | 9 | 5633
TS5500Exc | MW\29\010\X | MW | 29 | 10 | X | 1 Prestrip - Thick | 23.97 | 23.97 | 23.97 | 2018-10-27 12:01 | 2018-10-31 02:51 | 78449.3578 | 78449 | [7 empty] | 0 | 0 | 7.59 | 12.32 | 5195.07
PH4100A | SC\36\018\D | SC | 36 | 18 | D | 1 Prestrip - Thick | 100 | 59.9091 | 59.9091 | 2018-10-28 20:55 | 2018-11-01 | 131032.4925 | 131032 | [7 empty] | 0 | 0 | 10.9 | 7.02 | 5793.77
DRE2 | BW\26\009\D | BW | 26 | 9 | D | 6 DL | 100 | 37.5151 | 37.5151 | 2018-10-30 00:23 | 2018-11-01 | 162263.0541 |  |  |  | 7077 | 162263 | 117078 |  |  | 0 | 20.68 | 0 | 4.96 | 5978.91
DRE1 | MW\25\010\D | MW | 25 | 10 | D | 6 DL | 100 | 23.0143 | 23.0143 | 2018-10-30 08:42 | 2018-11-01 | 139090.7299 |  |  |  | 8307 | 139091 | 98188 |  |  | 0 | 28.88 | 0 | 5.54 | 5924.76
PH4100XPC#1 | RS\07\003\A | RS | 7 | 3 | A | 1 Prestrip - Thick | 100 | 28.7063 | 28.7063 | 2018-10-30 23:59 | 2018-11-01 | 50991.9725 | 50992 | [7 empty] | 0 | 0 | 7.64 | 11.44 | 5382.91
TS5500Exc | MW\29\010\X | MW | 29 | 10 | X | 1 Prestrip - Thick | 7.9603 | 5.8351 | 5.8351 | 2018-10-31 02:51 | 2018-11-01 | 19097.1129 | 19097 | [7 empty] | 0 | 0 | 1.85 | 12.32 | 5195.07
| EOP 58 : 2018\Oct | EOP 58 : 2018 | Oct | [6 empty] | 2018-11-01 | 2018-11-01 |  | 5341973 |  | 89894 | 270586 | 5005922 | 3559106 | 1524700 | 1114756 | 81.51 | 0 | 501.03 | 9.33 | 5581.71
TS Fleet 5 | BW\30\006\B | BW | 30 | 6 | B | 1 Prestrip - Thick | 65.233 | 30.1718 | 30.1718 | 2018-11-01 | 2018-11-05 00:04 | 177548.2695 | 177548 | [7 empty] | 0 | 0 | 17.45 | 12.05 | 5357.59
DRE1 | MW\25\010\D | MW | 25 | 10 | D | 6 DL | 100 | 76.9857 | 76.9857 | 2018-11-01 | 2018-11-06 13:11 | 465275.8175 |  |  |  | 27787 | 465276 | 328451 |  |  | 0 | 28.88 | 0 | 5.54 | 5924.76
PH4100A | SC\36\018\D | SC | 36 | 18 | D | 1 Prestrip - Thick | 100 | 40.0909 | 40.0909 | 2018-11-01 | 2018-11-03 04:25 | 87686.3273 | 87686 | [7 empty] | 0 | 0 | 7.29 | 7.02 | 5793.77
DRE2 | BW\26\009\D | BW | 26 | 9 | D | 6 DL | 100 | 62.4849 | 62.4849 | 2018-11-01 | 2018-11-04 08:20 | 270263.8699 |  |  |  | 11787 | 270264 | 195005 |  |  | 0 | 20.68 | 0 | 4.96 | 5978.91
PH4100XPC#1 | RS\07\003\A | RS | 7 | 3 | A | 1 Prestrip - Thick | 100 | 71.2937 | 71.2937 | 2018-11-01 | 2018-11-03 14:12 | 126641.5883 | 126642 | [7 empty] | 0 | 0 | 18.96 | 11.44 | 5382.91
TS5500Shv | GG\03\002\D | GG | 3 | 2 | D | 1 Prestrip - Thick | 88.2141 | 36.7716 | 36.7716 | 2018-11-01 | 2018-11-10 21:37 | 250489.6435 | 250490 | [7 empty] | 0 | 0 | 13.96 | 5.36 | 5914.56
TS6060#1 | BW\30\006\B | BW | 30 | 6 | B | 1 Prestrip - Thick | 27.9696 | 8.8883 | 8.8883 | 2018-11-01 | 2018-11-03 04:00 | 52304.0966 | 52304 | [7 empty] | 0 | 0 | 5.14 | 12.05 | 5357.59
TS5500Exc | MW\29\010\X | MW | 29 | 10 | X | 1 Prestrip - Thick | 7.9603 | 2.1252 | 2.1252 | 2018-11-01 | 2018-11-01 07:55 | 6955.4811 | 6955 | [7 empty] | 0 | 0 | 0.67 | 12.32 | 5195.07
TS5500Exc | MW\28\010\B | MW | 28 | 10 | B | 8 Coal Mining | 100 | 0 | 99.2 | 2018-11-01 07:55 | 2018-11-03 08:49 | 60657.1704 | [6 empty] | 60657 | 44943 | 2.81 | 0 | 0 | 9 | 5633
TS6060#1 | RS\08\004\A | RS | 8 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-11-03 04:00 | 2018-11-04 17:51 | 50454.9251 | [6 empty] | 50455 | 35568 | 3.56 | 0 | 0 | 12.76 | 5257
PH4100A | SC\36\017\D | SC | 36 | 17 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-11-03 04:25 | 2018-11-09 15:16 | 262146.3108 | 262146 | [7 empty] | 0 | 0 | 13.53 | 6.63 | 5829.26
TS5500Exc | DT\25\001\D | DT | 25 | 1 | D | 8 Coal Mining | 53.6 | 0 | 53.6 | 2018-11-03 08:49 | 2018-11-05 12:48 | 64518.4681 | [6 empty] | 64518 | 48474 | 2.46 | 0 | 0 | 6.12 | 5874
PH4100XPC#1 | RS\08\003\A | RS | 8 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-11-03 14:12 | 2018-11-07 19:25 | 206053.4169 | 206053 | [7 empty] | 0 | 0 | 30.36 | 11.33 | 5396.29
DRE2 | BW\26\008\D | BW | 26 | 8 | D | 6 DL | 100 | 100 | 100 | 2018-11-04 08:20 | 2018-11-09 15:40 | 428304.6228 |  |  |  | 18680 | 428305 | 309036 |  |  | 0 | 20.45 | 0 | 4.8 | 5991.6
TS6060#1 | BW\26\010\D | BW | 26 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-11-04 17:51 | 2018-11-08 07:01 | 113550.8235 | [6 empty] | 113551 | 86059 | 5.38 | 0 | 0 | 5.53 | 5930
TS Fleet 5 | BW\30\007\B | BW | 30 | 7 | B | 1 Prestrip - Thick | 79.4944 | 79.4944 | 79.4944 | 2018-11-05 00:04 | 2018-11-16 06:30 | 499750.6999 | 499751 | [7 empty] | 0 | 0 | 52.25 | 12.66 | 5310.5
TS5500Exc | MW\25\009\D | MW | 25 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-11-05 12:48 | 2018-11-08 17:00 | 94535.2248 | [6 empty] | 94535 | 71248 | 4.45 | 0 | 0 | 6.05 | 5879
DRE1 | MW\25\011\D | MW | 25 | 11 | D | 6 DL | 100 | 100 | 100 | 2018-11-06 13:11 | 2018-11-17 16:20 | 933150.2714 |  |  |  | 32551 | 933150 | 439189 |  |  | 0 | 28.75 | 0 | 5.91 | 5892.32
PH4100XPC#1 | RS\08\004\B | RS | 8 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-11-07 19:25 | 2018-11-08 12:27 | 38029.3881 | 38029 | [7 empty] | 0 | 0 | 3.81 | 16.05 | 5034.65
TS6060#1 | RS\08\003\A | RS | 8 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-11-08 07:01 | 2018-11-09 10:33 | 36719.8362 | [6 empty] | 36720 | 26194 | 3.61 | 0 | 0 | 11.33 | 5396
PH4100XPC#1 | BW\30\011\B | BW | 30 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-11-08 12:27 | 2018-11-17 04:08 | 474910.2221 | 474910 | [7 empty] | 0 | 0 | 52.56 | 11.38 | 5329.58
TS5500Exc | DT\25\002\D | DT | 25 | 2 | D | 8 Coal Mining | 30.2 | 0 | 30.2 | 2018-11-08 17:00 | 2018-11-09 22:07 | 36130.8213 | [6 empty] | 36131 | 27213 | 1.44 | 0 | 0 | 5.96 | 5889
TS6060#1 | BW\26\009\D | BW | 26 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-11-09 10:33 | 2018-11-12 18:11 | 106168.0496 | [6 empty] | 106168 | 80794 | 5.05 | 0 | 0 | 4.96 | 5979
PH4100A | RS\08\003\B | RS | 8 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-11-09 15:16 | 2018-11-10 06:00 | 25213.289 | 25213 | [7 empty] | 0 | 0 | 3.38 | 16.51 | 5005.55
DRE2 | BW\26\007\D | BW | 26 | 7 | D | 6 DL | 100 | 100 | 100 | 2018-11-09 15:40 | 2018-11-15 01:33 | 436870.994 |  |  |  | 19053 | 436871 | 315217 |  |  | 0 | 20.85 | 0 | 5.01 | 5973.57
TS5500Exc | DT\25\003\D | DT | 25 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-11-09 22:07 | 2018-11-13 06:42 | 99982.4427 | [6 empty] | 99982 | 75303 | 4.71 | 0 | 0 | 6.15 | 5873
PH4100A | RS\09\003\A | RS | 9 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-11-10 06:00 | 2018-11-15 19:56 | 217684.0896 | 217684 | [7 empty] | 0 | 0 | 31.55 | 11.28 | 5403.97
TS5500Shv | RS\07\004\A | RS | 7 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-11-10 21:37 | 2018-11-12 14:24 | 48978.2125 | [6 empty] | 48978 | 34508 | 3.49 | 0 | 0 | 12.93 | 5237
TS5500Shv | RS\07\003\A | RS | 7 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-11-12 14:24 | 2018-11-13 20:18 | 35930.8501 | [6 empty] | 35931 | 25627 | 3.57 | 0 | 0 | 11.44 | 5383
TS6060#1 | BW\26\011\D | BW | 26 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-11-12 18:11 | 2018-11-15 20:46 | 99421.1866 | [6 empty] | 99421 | 75061 | 4.69 | 0 | 0 | 5.84 | 5899
TS5500Exc | MW\25\010\D | MW | 25 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-11-13 06:42 | 2018-11-16 10:26 | 93970.7883 | [6 empty] | 93971 | 71165 | 4.45 | 0 | 0 | 5.54 | 5925
TS5500Shv | RS\07\003\B | RS | 7 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-11-13 20:18 | 2018-11-14 19:42 | 24704.4638 | 24704 | [7 empty] | 0 | 0 | 3.36 | 15.65 | 5073.79
TS5500Shv | RS\07\003\B | RS | 7 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-11-14 19:42 | 2018-11-16 09:14 | 45075.1478 | [6 empty] | 45075 | 31489 | 3.85 | 0 | 0 | 15.65 | 5074
DRE2 | BW\26\006\D | BW | 26 | 6 | D | 6 DL | 100 | 100 | 100 | 2018-11-15 01:33 | 2018-11-20 19:12 | 463046.2891 |  |  |  | 20195 | 463046 | 334104 |  |  | 0 | 22.18 | 0 | 5.24 | 5952.1
PH4100A | RS\07\004\B | RS | 7 | 4 | B | 1 Prestrip - Thick | 100 | 85.8343 | 85.8343 | 2018-11-15 19:56 | 2018-11-16 14:05 | 31062.8586 | 31063 | [7 empty] | 0 | 0 | 3.11 | 15.48 | 5078.59
TS6060#1 | BW\26\008\D | BW | 26 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-11-15 20:46 | 2018-11-19 01:19 | 102061.3153 | [6 empty] | 102061 | 77735 | 4.86 | 0 | 0 | 4.8 | 5992
TS Fleet 5 | BW\30\007\B | BW | 30 | 7 | B | 1 Prestrip - Thick | 20.5056 | 20.5056 | 20.5056 | 2018-11-16 06:30 | 2018-11-19 04:15 | 128910.9044 | 128911 | [7 empty] | 0 | 0 | 13.48 | 12.66 | 5310.5
TS5500Shv | RS\07\004\B | RS | 7 | 4 | B | 1 Prestrip - Thick | 100 | 14.1657 | 14.1657 | 2018-11-16 09:14 | 2018-11-16 14:05 | 5126.4769 | 5126 | [7 empty] | 0 | 0 | 0.51 | 15.48 | 5078.59
TS5500Exc | DT\25\005\D | DT | 25 | 5 | D | 8 Coal Mining | 8.6 | 0 | 8.6 | 2018-11-16 10:26 | 2018-11-16 19:04 | 10712.1374 | [6 empty] | 10712 | 8043 | 0.42 | 0 | 0 | 6.5 | 5843
PH4100A | RS\09\004\A | RS | 9 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-11-16 14:05 | 2018-11-26 09:25 | 384079.619 | 384080 | [7 empty] | 0 | 0 | 37.81 | 12.61 | 5279.32
TS5500Shv | RS\08\003\B | RS | 8 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-11-16 14:05 | 2018-11-18 05:02 | 46792.0025 | [6 empty] | 46792 | 32475 | 3.92 | 0 | 0 | 16.51 | 5006
TS5500Exc | DT\25\006\D | DT | 25 | 6 | D | 8 Coal Mining | 86.6 | 0 | 86.6 | 2018-11-16 19:04 | 2018-11-19 02:06 | 68296.3736 | [6 empty] | 68296 | 51274 | 4.05 | 0 | 0 | 6.4 | 5851
PH4100XPC#1 | BW\30\010\B | BW | 30 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-11-17 04:08 | 2018-11-27 03:32 | 548326.6431 | 548327 | [7 empty] | 0 | 0 | 58.73 | 17.09 | 4905.66
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2018-11-17 16:20 | 2018-11-19 16:20
TS5500Shv | RS\07\004\B | RS | 7 | 4 | B | 8 Coal Mining | 75.6 | 0 | 75.6 | 2018-11-18 05:02 | 2018-11-19 17:01 | 43214.2783 | [6 empty] | 43214 | 30211 | 3.03 | 0 | 0 | 15.48 | 5079
TS6060#1 | BW\26\007\D | BW | 26 | 7 | D | 8 Coal Mining | 77.5 | 0 | 77.5 | 2018-11-19 01:19 | 2018-11-21 12:25 | 78798.6251 | [6 empty] | 78799 | 59921 | 3.74 | 0 | 0 | 5.01 | 5974
TS5500Exc | DT\25\006\D | DT | 25 | 6 | D | 8 Coal Mining | 13.4 | 0 | 13.4 | 2018-11-19 02:06 | 2018-11-19 10:36 | 10543.0483 | [6 empty] | 10543 | 7915 | 0.63 | 0 | 0 | 6.4 | 5851
TS Fleet 5 | BW\30\008\B | BW | 30 | 8 | B | 1 Prestrip - Thick | 25.585 | 25.585 | 25.585 | 2018-11-19 04:15 | 2018-11-22 06:32 | 137262.2728 | 137262 | [7 empty] | 0 | 0 | 14.11 | 13.5 | 5242.02
TS5500Exc | DT\26\001\D | DT | 26 | 1 | D | 8 Coal Mining | 100 | 0 | 91.4 | 2018-11-19 10:36 | 2018-11-23 09:38 | 117914.858 | [6 empty] | 117915 | 88653 | 4.01 | 0 | 0 | 6.01 | 5883
DRE1 | RS\05\003\D | RS | 5 | 3 | D | 6 DL | 100 | 100 | 100 | 2018-11-19 16:20 | 2018-11-23 01:50 | 284728.6355 |  |  |  | 12740 | 284729 | 242051 |  |  | 0 | 24.52 | 0 | 6.23 | 5873.83
TS5500Shv | GG\03\003\B | GG | 3 | 3 | B | 1 Prestrip - Thick | 3.9473 | 3.9473 | 3.9473 | 2018-11-19 17:01 | 2018-11-20 17:43 | 25792.7529 | 25793 | [7 empty] | 0 | 0 | 0.97 | 11.84 | 5385.2
TS5500Shv | GG\03\003\B | GG | 3 | 3 | B | 1 Prestrip - Thick | 14.7659 | 14.7659 | 14.7659 | 2018-11-20 17:43 | 2018-11-24 14:09 | 96484.9488 | 96485 | [7 empty] | 0 | 0 | 3.63 | 11.84 | 5385.2
DRE2 | BW\26\005\D | BW | 26 | 5 | D | 6 DL | 100 | 100 | 100 | 2018-11-20 19:12 | 2018-11-26 15:34 | 472173.5877 |  |  |  | 20593 | 472174 | 340689 |  |  | 0 | 22.59 | 0 | 5.35 | 5939.82
TS6060#1 | BW\29\010\B | BW | 29 | 10 | B | 8 Coal Mining | 74.4 | 0 | 74.4 | 2018-11-21 12:25 | 2018-11-22 19:53 | 41938.2509 | [6 empty] | 41938 | 29722 | 2.97 | 0 | 0 | 16.99 | 4913
TS Fleet 5 | MW\28\011\A | MW | 28 | 11 | A | 1 Prestrip - Thick | 83.3612 | 83.3612 | 83.3612 | 2018-11-22 06:32 | 2018-11-28 06:20 | 265764.2186 | 265764 | [7 empty] | 0 | 0 | 16.46 | 11.9 | 5377.22
TS6060#1 | BW\29\011\B | BW | 29 | 11 | B | 8 Coal Mining | 100 | 0 | 51.7 | 2018-11-22 19:53 | 2018-11-23 09:38 | 18335.1639 | [6 empty] | 18335 | 13430 | 1.35 | 0 | 0 | 11.1 | 5354
DRE1 | SC\34\014\D | SC | 34 | 14 | D | 6 DL | 100 | 0 | 100 | 2018-11-23 01:50 | 2018-11-29 08:41 | 526914.8189 |  |  |  | 30073 | 526915 | 399536 |  |  | 0 | 30.9 | 0 | 7.56 | 5747.58
TS6060#1 | RS\09\005\A | RS | 9 | 5 | A | 1 Prestrip - Thick | 6.0319 | 6.0319 | 6.0319 | 2018-11-23 09:38 | 2018-11-24 10:42 | 24749.6601 | 24750 | [7 empty] | 0 | 0 | 2.41 | 14.29 | 5113.17
TS5500Exc | MW\25\011\D | MW | 25 | 11 | D | 7 PostStrip | 23.5061 | 0 | 23.5061 | 2018-11-23 09:38 | 2018-11-24 12:26 | 23348.6541 |  |  | 23349 | [5 empty] | 0 | 0 | 0 | 5.91 | 5892.32
TS6060#1 | RS\09\005\A | RS | 9 | 5 | A | 1 Prestrip - Thick | 2.6205 | 2.6205 | 2.6205 | 2018-11-24 10:42 | 2018-11-24 21:35 | 10752.1227 | 10752 | [7 empty] | 0 | 0 | 1.05 | 14.29 | 5113.17
TS5500Exc | MW\30\001\D | MW | 30 | 1 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-11-24 12:26 | 2018-11-26 01:24 | 32206.8949 | 32207 | [7 empty] | 0 | 0 | 3.89 | 7.49 | 5754.98
TS5500Shv | MW\25\011\D | MW | 25 | 11 | D | 7 PostStrip | 76.4939 | 0 | 76.4939 | 2018-11-24 14:09 | 2018-11-27 14:06 | 75981.6206 |  |  | 75982 | [5 empty] | 0 | 0 | 0 | 5.91 | 5892.32
TS6060#1 | RS\09\007\X | RS | 9 | 7 | X | 1 Prestrip - Thick | 1.5907 | 1.5907 | 1.5907 | 2018-11-24 21:35 | 2018-11-25 02:45 | 5055.5485 | 5056 | [7 empty] | 0 | 0 | 0.5 | 11.88 | 5211.62
TS6060#1 | RS\09\008\X | RS | 9 | 8 | X | 1 Prestrip - Thick | 37.431 | 37.431 | 37.431 | 2018-11-25 02:45 | 2018-11-29 06:15 | 98092.869 | 98093 | [7 empty] | 0 | 0 | 13.54 | 14.12 | 5014.33
TS5500Exc | MW\30\002\D | MW | 30 | 2 | D | 1 Prestrip - Thick | 45.3763 | 28.6786 | 28.6786 | 2018-11-26 01:24 | 2018-12-01 | 103326.6371 | 103327 | [7 empty] | 0 | 0 | 10.43 | 7.27 | 5774.22
PH4100A | RS\09\005\A | RS | 9 | 5 | A | 1 Prestrip - Thick | 100 | 44.3784 | 44.3784 | 2018-11-26 09:25 | 2018-12-01 | 182089.9184 | 182090 | [7 empty] | 0 | 0 | 17.76 | 14.29 | 5113.17
DRE2 | BW\26\004\D | BW | 26 | 4 | D | 6 DL | 100 | 73.1735 | 73.1735 | 2018-11-26 15:34 | 2018-12-01 | 351240.6365 |  |  |  | 15319 | 351241 | 253432 |  |  | 0 | 22.93 | 0 | 5.64 | 5915.61
PH4100XPC#1 | BW\30\009\X2 | BW | 30 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 92.0854 | 2018-11-27 03:32 | 2018-12-01 | 209251.1443 | 209251 | [7 empty] | 0 | 0 | 21.96 | 0 | 0
TS5500Shv | GG\03\005\B | GG | 3 | 5 | B | 1 Prestrip - Thick | 8.9883 | 0 | 8.9883 | 2018-11-27 14:06 | 2018-11-30 17:17 | 79248.9576 | 79249 | [7 empty] | 0 | 0 | 3.02 | 0 | 0
TS Fleet 5 | MW\29\001\D | MW | 29 | 1 | D | 1 Prestrip - Thick | 70.2344 | 70.2344 | 70.2344 | 2018-11-28 06:20 | 2018-11-29 09:19 | 49865.0572 | 49865 | [7 empty] | 0 | 0 | 4.58 | 7.35 | 5766.84
TS6060#1 | RS\10\003\A | RS | 10 | 3 | A | 1 Prestrip - Thick | 37.473 | 17.4411 | 17.4411 | 2018-11-29 06:15 | 2018-12-01 | 40926.4874 | 40926 | [7 empty] | 0 | 0 | 5.97 | 11.27 | 5409.55
DRE1 | SC\34\013\D | SC | 34 | 13 | D | 6 DL | 100 | 0 | 24.896 | 2018-11-29 08:41 | 2018-12-01 | 137310.4567 |  |  |  | 9765 | 137310 | 98738 |  |  | 0 | 36.51 | 0 | 7.7 | 5735.38
TS Fleet 5 | MW\29\002\D | MW | 29 | 2 | D | 1 Prestrip - Thick | 100 | 17.85 | 17.85 | 2018-11-29 09:19 | 2018-12-01 | 71458.5776 | 71459 | [7 empty] | 0 | 0 | 7.21 | 7.14 | 5785.41
TS5500Shv | GG\03\005\B | GG | 3 | 5 | B | 1 Prestrip - Thick | 18.7066 | 0 | 0.80283 | 2018-11-30 17:17 | 2018-12-01 | 7078.5217 | 7079 | [7 empty] | 0 | 0 | 0.27 | 0 | 0
| EOP 59 : 2018\Nov | EOP 59 : 2018 | Nov | [6 empty] | 2018-12-01 | 2018-12-01 |  | 4987030 |  | 99330 | 218542 | 4769280 | 3255447 | 1524700 | 1133028 | 82.5 | 0 | 495.69 | 8.22 | 5689.85
TS Fleet 5 | MW\29\002\D | MW | 29 | 2 | D | 1 Prestrip - Thick | 100 | 82.15 | 82.15 | 2018-12-01 | 2018-12-10 01:30 | 328868.5323 | 328869 | [7 empty] | 0 | 0 | 33.2 | 7.14 | 5785.41
DRE1 | SC\34\013\D | SC | 34 | 13 | D | 6 DL | 100 | 0 | 75.104 | 2018-12-01 | 2018-12-06 16:49 | 414225.3794 |  |  |  | 29459 | 414225 | 297863 |  |  | 0 | 36.51 | 0 | 7.7 | 5735.38
PH4100A | RS\09\005\A | RS | 9 | 5 | A | 1 Prestrip - Thick | 100 | 46.9692 | 46.9692 | 2018-12-01 | 2018-12-06 21:40 | 192719.9136 | 192720 | [7 empty] | 0 | 0 | 18.79 | 14.29 | 5113.17
DRE2 | BW\26\004\D | BW | 26 | 4 | D | 6 DL | 100 | 26.8265 | 26.8265 | 2018-12-01 | 2018-12-02 20:10 | 128769.9125 |  |  |  | 5616 | 128770 | 92912 |  |  | 0 | 22.93 | 0 | 5.64 | 5915.61
PH4100XPC#1 | BW\30\009\X2 | BW | 30 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 7.9146 | 2018-12-01 | 2018-12-01 09:37 | 17984.8001 | 17985 | [7 empty] | 0 | 0 | 1.89 | 0 | 0
TS5500Shv | GG\03\005\B | GG | 3 | 5 | B | 1 Prestrip - Thick | 18.7066 | 0 | 17.9037 | 2018-12-01 | 2018-12-08 15:00 | 157856.2653 | 157856 | [7 empty] | 0 | 0 | 6.02 | 0 | 0
TS6060#1 | RS\10\003\A | RS | 10 | 3 | A | 1 Prestrip - Thick | 37.473 | 20.0319 | 20.0319 | 2018-12-01 | 2018-12-03 10:35 | 47005.9181 | 47006 | [7 empty] | 0 | 0 | 6.86 | 11.27 | 5409.55
TS5500Exc | MW\30\002\D | MW | 30 | 2 | D | 1 Prestrip - Thick | 45.3763 | 16.6977 | 16.6977 | 2018-12-01 | 2018-12-04 12:23 | 60160.3481 | 60160 | [7 empty] | 0 | 0 | 6.07 | 7.27 | 5774.22
PH4100XPC#1 | BW\30\008\B | BW | 30 | 8 | B | 1 Prestrip - Thick | 100 | 74.415 | 74.415 | 2018-12-01 09:37 | 2018-12-10 10:15 | 399233.6912 | 399234 | [7 empty] | 0 | 0 | 41.03 | 13.5 | 5242.02
DRE2 | BW\26\003\D | BW | 26 | 3 | D | 6 DL | 100 | 100 | 100 | 2018-12-02 20:10 | 2018-12-06 19:51 | 278951.9168 |  |  |  | 10434 | 278952 | 132986 |  |  | 0 | 23.1 | 0 | 5.92 | 5893.49
TS6060#1 | BW\29\011\B | BW | 29 | 11 | B | 8 Coal Mining | 100 | 0 | 48.3 | 2018-12-03 10:35 | 2018-12-04 02:16 | 17108.1309 | [6 empty] | 17108 | 12531 | 1.26 | 0 | 0 | 11.1 | 5354
TS6060#1 | BW\30\005\B | BW | 30 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-12-04 02:16 | 2018-12-05 14:49 | 39871.6738 | [6 empty] | 39872 | 29068 | 3.61 | 0 | 0 | 11.13 | 5431
TS5500Exc | MW\28\011\A | MW | 28 | 11 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-12-04 12:23 | 2018-12-07 12:35 | 73294.2156 | [6 empty] | 73294 | 53589 | 3.47 | 0 | 0 | 11.9 | 5377
TS6060#1 | BW\30\006\B | BW | 30 | 6 | B | 8 Coal Mining | 47.5 | 0 | 47.5 | 2018-12-05 14:49 | 2018-12-06 13:16 | 24476.1221 | [6 empty] | 24476 | 17751 | 1.78 | 0 | 0 | 12.05 | 5358
TS6060#1 | RS\05\003\D | RS | 5 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-12-06 13:16 | 2018-12-09 00:52 | 65021.2866 | [6 empty] | 65021 | 47601 | 4.57 | 0 | 0 | 6.23 | 5874
DRE1 | SC\34\012\D | SC | 34 | 12 | D | 6 DL | 100 | 0 | 100 | 2018-12-06 16:49 | 2018-12-15 08:21 | 628284.2247 |  |  |  | 47778 | 628284 | 430004 |  |  | 0 | 40 | 0 | 7.67 | 5738.78
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2018-12-06 19:51 | 2018-12-08 19:51
PH4100A | RS\09\006\A | RS | 9 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-12-06 21:40 | 2018-12-21 07:17 | 472908.7462 | 472909 | [7 empty] | 0 | 0 | 46.54 | 13.86 | 5104.35
TS5500Exc | DT\26\001\D | DT | 26 | 1 | D | 8 Coal Mining | 100 | 0 | 8.6 | 2018-12-07 12:35 | 2018-12-07 23:33 | 11141.1906 | [6 empty] | 11141 | 8376 | 0.38 | 0 | 0 | 6.01 | 5883
TS5500Exc | DT\26\002\D | DT | 26 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-12-07 23:33 | 2018-12-13 15:21 | 137855.2036 | [6 empty] | 137855 | 103919 | 4.89 | 0 | 0 | 5.94 | 5892
TS5500Shv | RS\07\004\B | RS | 7 | 4 | B | 8 Coal Mining | 24.4 | 0 | 24.4 | 2018-12-08 15:00 | 2018-12-09 05:10 | 13918.5047 | [6 empty] | 13919 | 9730 | 0.98 | 0 | 0 | 15.48 | 5079
DRE2 | DT\27\005\D | DT | 27 | 5 | D | 6 DL | 100 | 100 | 100 | 2018-12-08 19:51 | 2018-12-20 07:25 | 803328.1909 |  |  |  | 35036 | 803328 | 579628 |  |  | 0 | 24.82 | 0 | 6.86 | 5810.64
TS6060#1 | RS\09\003\A | RS | 9 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2018-12-09 00:52 | 2018-12-10 11:09 | 37393.6721 | [6 empty] | 37394 | 26654 | 3.64 | 0 | 0 | 11.28 | 5404
TS5500Shv | RS\07\005\B | RS | 7 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-12-09 05:10 | 2018-12-11 16:53 | 58682.5967 | [6 empty] | 58683 | 40360 | 4.03 | 0 | 0 | 17.93 | 4858
TS Fleet 5 | BW\30\009\B | BW | 30 | 9 | B | 1 Prestrip - Thick | 50.0673 | 47.3706 | 47.3706 | 2018-12-10 01:30 | 2018-12-14 04:16 | 149328.2226 | 149328 | [7 empty] | 0 | 0 | 15.02 | 14.7 | 5130.36
PH4100XPC#1 | BW\30\009\B | BW | 30 | 9 | B | 1 Prestrip - Thick | 100 | 52.6294 | 52.6294 | 2018-12-10 10:15 | 2018-12-14 04:16 | 165905.7559 | 165906 | [7 empty] | 0 | 0 | 16.69 | 14.7 | 5130.36
TS6060#1 | BW\26\004\D | BW | 26 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-12-10 11:09 | 2018-12-14 01:59 | 94716.6979 | [6 empty] | 94717 | 71455 | 4.47 | 0 | 0 | 5.64 | 5916
TS5500Shv | RS\08\005\B | RS | 8 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-12-11 16:53 | 2018-12-14 05:52 | 59942.7841 | [6 empty] | 59943 | 41035 | 4.1 | 0 | 0 | 18.7 | 4797
TS5500Exc | SC\34\014\D | SC | 34 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-12-13 15:21 | 2018-12-16 20:54 | 78730.6953 | [6 empty] | 78731 | 58979 | 4.43 | 0 | 0 | 7.56 | 5748
TS6060#1 | BW\26\005\D | BW | 26 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-12-14 01:59 | 2018-12-17 12:51 | 90390.3184 | [6 empty] | 90390 | 68414 | 4.28 | 0 | 0 | 5.35 | 5940
PH4100XPC#1 | GG\03\002\D | GG | 3 | 2 | D | 1 Prestrip - Thick | 100 | 1.0929 | 1.0929 | 2018-12-14 04:16 | 2018-12-14 08:18 | 7444.6278 | 7445 | [7 empty] | 0 | 0 | 0.41 | 5.36 | 5914.56
TS Fleet 5 | MW\28\011\B | MW | 28 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-12-14 04:16 | 2018-12-15 06:37 | 39860.5657 | 39861 | [7 empty] | 0 | 0 | 2.61 | 8.77 | 5652.77
TS5500Shv | RS\08\004\B | RS | 8 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-12-14 05:52 | 2018-12-16 17:02 | 58146.6322 | [6 empty] | 58147 | 40470 | 4.05 | 0 | 0 | 16.05 | 5035
PH4100XPC#1 | GG\03\003\B | GG | 3 | 3 | B | 1 Prestrip - Thick | 100 | 81.2869 | 81.2869 | 2018-12-14 08:18 | 2018-12-26 14:47 | 531154.3522 | 531154 | [7 empty] | 0 | 0 | 19.96 | 11.84 | 5385.2
TS Fleet 5 | MW\29\003\A | MW | 29 | 3 | A | 1 Prestrip - Thick | 47 | 47 | 47 | 2018-12-15 06:37 | 2018-12-20 15:43 | 195180.8224 | 195181 | [7 empty] | 0 | 0 | 19.24 | 10.8 | 5404.36
DRE1 | SC\34\011\D | SC | 34 | 11 | D | 6 DL | 100 | 0 | 100 | 2018-12-15 08:21 | 2018-12-24 03:20 | 638732.6544 |  |  |  | 48573 | 638733 | 437155 |  |  | 0 | 40 | 0 | 7.65 | 5740.97
TS5500Shv | GG\03\002\D | GG | 3 | 2 | D | 7 PostStrip | 50.9554 | 0 | 50.9554 | 2018-12-16 17:02 | 2018-12-19 06:30 | 53111.3887 |  |  | 53111 | [5 empty] | 0 | 0 | 0 | 5.36 | 5914.56
TS5500Exc | MW\28\011\B | MW | 28 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-12-16 20:54 | 2018-12-19 04:15 | 56190.6281 | [6 empty] | 56191 | 41778 | 2.76 | 0 | 0 | 8.77 | 5653
TS6060#1 | GG\03\002\D | GG | 3 | 2 | D | 7 PostStrip | 49.0446 | 0 | 49.0446 | 2018-12-17 12:51 | 2018-12-20 02:19 | 51119.7116 |  |  | 51120 | [5 empty] | 0 | 0 | 0 | 5.36 | 5914.56
TS5500Exc | SC\34\013\D | SC | 34 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-12-19 04:15 | 2018-12-22 03:46 | 72614.7185 | [6 empty] | 72615 | 54355 | 4.53 | 0 | 0 | 7.7 | 5735
TS5500Shv | RS\08\006\B | RS | 8 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-12-19 06:30 | 2018-12-21 18:22 | 58838.9827 | [6 empty] | 58839 | 40328 | 4.03 | 0 | 0 | 17.01 | 4897
TS6060#1 | BW\26\006\D | BW | 26 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-12-20 02:19 | 2018-12-23 20:32 | 98408.4137 | [6 empty] | 98408 | 74655 | 4.67 | 0 | 0 | 5.24 | 5952
DRE2 | DT\27\003\D | DT | 27 | 3 | D | 6 DL | 100 | 100 | 100 | 2018-12-20 07:25 | 2018-12-27 12:11 | 503685.0352 |  |  |  | 21967 | 503685 | 363426 |  |  | 0 | 24.09 | 0 | 6.48 | 5843.49
TS Fleet 5 | MW\29\003\A | MW | 29 | 3 | A | 1 Prestrip - Thick | 53 | 53 | 53 | 2018-12-20 15:43 | 2018-12-26 17:17 | 220097.6252 | 220098 | [7 empty] | 0 | 0 | 21.69 | 10.8 | 5404.36
PH4100A | RS\09\003\B | RS | 9 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2018-12-21 07:17 | 2018-12-22 00:33 | 24392.5001 | 24393 | [7 empty] | 0 | 0 | 3.25 | 17.13 | 4955.6
TS5500Shv | RS\08\008\A | RS | 8 | 8 | A | 8 Coal Mining | 70.3 | 0 | 70.3 | 2018-12-21 18:22 | 2018-12-22 18:10 | 23379.3693 | [6 empty] | 23379 | 15992 | 2.48 | 0 | 0 | 17.46 | 4894
PH4100A | RS\09\007\X | RS | 9 | 7 | X | 1 Prestrip - Thick | 100 | 98.4093 | 98.4093 | 2018-12-22 00:33 | 2018-12-31 16:54 | 312759.3751 | 312759 | [7 empty] | 0 | 0 | 31.02 | 11.88 | 5211.62
TS5500Exc | DT\26\006\B | DT | 26 | 6 | B | 8 Coal Mining | 47.7 | 0 | 47.7 | 2018-12-22 03:46 | 2018-12-23 02:42 | 23277.399 | [6 empty] | 23277 | 17225 | 1.06 | 0 | 0 | 9.02 | 5544
TS5500Shv | RS\08\007\B | RS | 8 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-12-22 18:10 | 2018-12-25 03:14 | 56085.1085 | [6 empty] | 56085 | 38370 | 3.85 | 0 | 0 | 16.99 | 4942
TS5500Exc | SC\34\012\D | SC | 34 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2018-12-23 02:42 | 2018-12-26 02:51 | 73242.5345 | [6 empty] | 73243 | 54695 | 4.56 | 0 | 0 | 7.67 | 5739
TS6060#1 | RS\09\004\A | RS | 9 | 4 | A | 8 Coal Mining | 69.9 | 0 | 69.9 | 2018-12-23 20:32 | 2018-12-25 04:56 | 35343.6049 | [6 empty] | 35344 | 24913 | 2.49 | 0 | 0 | 12.61 | 5279
DRE1 | SC\34\010\D | SC | 34 | 10 | D | 6 DL | 100 | 0 | 62.7841 | 2018-12-24 03:20 | 2019-01-01 | 571124.7415 |  |  |  | 31906 | 571125 | 248404 |  |  | 0 | 40 | 0 | 7.64 | 5743.31
TS5500Shv | RS\08\008\B | RS | 8 | 8 | B | 1 Prestrip - Thick | 86.5954 | 86.5954 | 86.5954 | 2018-12-25 03:14 | 2018-12-25 19:56 | 14428.5034 | 14429 | [7 empty] | 0 | 0 | 2.25 | 17.15 | 4986.43
TS6060#1 | BW\26\007\D | BW | 26 | 7 | D | 8 Coal Mining | 22.5 | 0 | 22.5 | 2018-12-25 04:56 | 2018-12-26 01:51 | 22818.033 | [6 empty] | 22818 | 17352 | 1.08 | 0 | 0 | 5.01 | 5974
TS5500Shv | RS\09\003\B | RS | 9 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2018-12-25 19:56 | 2018-12-27 21:11 | 48399.7924 | [6 empty] | 48400 | 33396 | 4.01 | 0 | 0 | 17.13 | 4956
TS6060#1 | BW\30\006\B | BW | 30 | 6 | B | 8 Coal Mining | 52.5 | 0 | 52.5 | 2018-12-26 01:51 | 2018-12-27 02:41 | 27088.1983 | [6 empty] | 27088 | 19645 | 1.97 | 0 | 0 | 12.05 | 5358
TS5500Exc | MW\25\011\D | MW | 25 | 11 | D | 8 Coal Mining | 100 | 0 | 44.2 | 2018-12-26 02:51 | 2018-12-28 04:43 | 50624.3244 | [6 empty] | 50624 | 38369 | 1.96 | 0 | 0 | 5.91 | 5892
PH4100XPC#1 | RS\08\008\B | RS | 8 | 8 | B | 1 Prestrip - Thick | 100 | 13.4046 | 13.4046 | 2018-12-26 14:47 | 2018-12-26 15:59 | 2233.4746 | 2233 | [7 empty] | 0 | 0 | 0.35 | 17.15 | 4986.43
PH4100XPC#1 | GG\03\004\B | GG | 3 | 4 | B | 1 Prestrip - Thick | 100 | 26.3781 | 26.3781 | 2018-12-26 15:59 | 2019-01-01 | 221968.165 | 221968 | [7 empty] | 0 | 0 | 7.61 | 10.33 | 5496.77
TS Fleet 5 | MW\29\004\A | MW | 29 | 4 | A | 1 Prestrip - Thick | 100 | 64.0899 | 64.0899 | 2018-12-26 17:17 | 2019-01-01 | 191592.2318 | 191592 | [7 empty] | 0 | 0 | 19.47 | 10.19 | 5452.68
TS6060#1 | BW\30\007\B | BW | 30 | 7 | B | 8 Coal Mining | 19.4 | 0 | 19.4 | 2018-12-27 02:41 | 2018-12-27 12:07 | 10290.0485 | [6 empty] | 10290 | 7429 | 0.74 | 0 | 0 | 12.66 | 5311
TS6060#1 | BW\26\003\D | BW | 26 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2018-12-27 12:07 | 2018-12-29 11:47 | 39628.5749 |  |  | 39629 | [5 empty] | 0 | 0 | 0 | 5.92 | 5893.49
DRE2 | DT\27\002\D | DT | 27 | 2 | D | 6 DL | 100 | 43.3952 | 43.3952 | 2018-12-27 12:11 | 2019-01-01 | 314278.9446 |  |  |  | 13707 | 314279 | 226763 |  |  | 0 | 23.26 | 0 | 5.99 | 5887.36
TS5500Shv | RS\08\008\B | RS | 8 | 8 | B | 8 Coal Mining | 100 | 0 | 21.5 | 2018-12-27 21:11 | 2018-12-28 04:43 | 7409.1196 | [6 empty] | 7409 | 5051 | 0.83 | 0 | 0 | 17.15 | 4986
TS5500Shv | GG\05\002\X1 | GG | 5 | 2 | X1 | 1 Prestrip - Thick | 6.1211 | 0 | 6.1211 | 2018-12-28 04:43 | 2018-12-31 07:59 | 65106.9767 | 65107 | [7 empty] | 0 | 0 | 2.46 | 0 | 0
TS5500Exc | MW\30\002\D | MW | 30 | 2 | D | 1 Prestrip - Thick | 54.6237 | 18.06 | 18.06 | 2018-12-28 04:43 | 2019-01-01 | 65068.5654 | 65069 | [7 empty] | 0 | 0 | 6.57 | 7.27 | 5774.22
TS6060#1 | RS\10\004\A | RS | 10 | 4 | A | 1 Prestrip - Thick | 5.3502 | 5.3502 | 5.3502 | 2018-12-29 11:47 | 2018-12-30 15:32 | 22355.4941 | 22355 | [7 empty] | 0 | 0 | 2.2 | 12.57 | 5293.38
TS6060#1 | RS\10\004\A | RS | 10 | 4 | A | 1 Prestrip - Thick | 31.7479 | 6.2539 | 6.2539 | 2018-12-30 15:32 | 2019-01-01 | 26131.3837 | 26131 | [7 empty] | 0 | 0 | 2.57 | 12.57 | 5293.38
TS5500Shv | RS\56\001\D | RS | 56 | 1 | D | 1 Prestrip - Thick | 21.9712 | 15.8787 | 15.8787 | 2018-12-31 07:59 | 2019-01-01 | 13797.6154 | 13798 | [7 empty] | 0 | 0 | 1.62 | 7.68 | 5744.79
PH4100A | RS\09\008\X | RS | 9 | 8 | X | 1 Prestrip - Thick | 100 | 3.6718 | 3.6718 | 2018-12-31 16:54 | 2019-01-01 | 9622.4949 | 9622 | [7 empty] | 0 | 0 | 1.33 | 14.12 | 5014.33
| EOP 60 : 2018\Dec | EOP 60 : 2018 | Dec | [6 empty] | 2019-01-01 | 2019-01-01 |  | 3955167 |  | 143860 | 244476 | 4281381 | 2809141 | 1524700 | 1113484 | 90.94 | 0 | 336.73 | 9.51 | 5576.16
TS Fleet 5 | MW\29\004\A | MW | 29 | 4 | A | 1 Prestrip - Thick | 100 | 35.9101 | 35.9101 | 2019-01-01 | 2019-01-03 13:50 | 107350.7302 | 107351 | [7 empty] | 0 | 0 | 10.91 | 10.19 | 5452.68
DRE1 | SC\34\010\D | SC | 34 | 10 | D | 6 DL | 100 | 0 | 37.2159 | 2019-01-01 | 2019-01-05 02:13 | 338539.6971 |  |  |  | 18913 | 338540 | 147244 |  |  | 0 | 40 | 0 | 7.64 | 5743.31
PH4100A | RS\09\008\X | RS | 9 | 8 | X | 1 Prestrip - Thick | 100 | 58.8972 | 58.8972 | 2019-01-01 | 2019-01-05 03:42 | 154347.6444 | 154348 | [7 empty] | 0 | 0 | 21.31 | 14.12 | 5014.33
DRE2 | DT\27\002\D | DT | 27 | 2 | D | 6 DL | 100 | 56.6048 | 56.6048 | 2019-01-01 | 2019-01-06 03:31 | 409946.1492 |  |  |  | 17879 | 409946 | 295790 |  |  | 0 | 23.26 | 0 | 5.99 | 5887.36
PH4100XPC#1 | GG\03\004\B | GG | 3 | 4 | B | 1 Prestrip - Thick | 100 | 73.6219 | 73.6219 | 2019-01-01 | 2019-01-14 01:17 | 619519.6621 | 619520 | [7 empty] | 0 | 0 | 21.23 | 10.33 | 5496.77
TS5500Shv | RS\56\001\D | RS | 56 | 1 | D | 1 Prestrip - Thick | 21.9712 | 6.0925 | 6.0925 | 2019-01-01 | 2019-01-01 05:20 | 5294.0242 | 5294 | [7 empty] | 0 | 0 | 0.62 | 7.68 | 5744.79
TS6060#1 | RS\10\004\A | RS | 10 | 4 | A | 1 Prestrip - Thick | 31.7479 | 25.494 | 25.494 | 2019-01-01 | 2019-01-05 19:13 | 106525.2838 | 106525 | [7 empty] | 0 | 0 | 10.49 | 12.57 | 5293.38
TS5500Exc | MW\30\002\D | MW | 30 | 2 | D | 1 Prestrip - Thick | 54.6237 | 36.5637 | 36.5637 | 2019-01-01 | 2019-01-07 04:56 | 131735.9084 | 131736 | [7 empty] | 0 | 0 | 13.3 | 7.27 | 5774.22
TS5500Shv | RS\08\008\B | RS | 8 | 8 | B | 8 Coal Mining | 100 | 0 | 78.5 | 2019-01-01 05:20 | 2019-01-02 05:17 | 27012.4521 | [6 empty] | 27012 | 18415 | 3.01 | 0 | 0 | 17.15 | 4986
TS5500Shv | RS\09\004\A | RS | 9 | 4 | A | 8 Coal Mining | 30.1 | 0 | 30.1 | 2019-01-02 05:17 | 2019-01-02 18:46 | 15220.5234 | [6 empty] | 15221 | 10729 | 1.07 | 0 | 0 | 12.61 | 5279
TS5500Shv | RS\09\005\A | RS | 9 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-01-02 18:46 | 2019-01-04 16:22 | 51446.2994 | [6 empty] | 51446 | 35749 | 3.56 | 0 | 0 | 14.29 | 5113
TS Fleet 5 | MW\29\005\A | MW | 29 | 5 | A | 1 Prestrip - Thick | 72.1327 | 72.1327 | 72.1327 | 2019-01-03 13:50 | 2019-01-06 12:14 | 122234.2286 | 122234 | [7 empty] | 0 | 0 | 12.69 | 9.68 | 5490.3
TS5500Shv | RS\09\005\B | RS | 9 | 5 | B | 1 Prestrip - Thick | 100 | 92.862 | 92.862 | 2019-01-04 16:22 | 2019-01-06 02:05 | 33450.1631 | 33450 | [7 empty] | 0 | 0 | 3.34 | 18.99 | 4776.61
DRE1 | SC\34\015\D | SC | 34 | 15 | D | 6 DL | 100 | 0 | 100 | 2019-01-05 02:13 | 2019-01-12 14:08 | 620063.2338 |  |  |  | 33049 | 620063 | 439078 |  |  | 0 | 31.73 | 0 | 7.03 | 5792.85
PH4100A | RS\09\004\B | RS | 9 | 4 | B | 1 Prestrip - Thick | 100 | 86.9464 | 86.9464 | 2019-01-05 03:42 | 2019-01-06 00:29 | 33509.3962 | 33509 | [7 empty] | 0 | 0 | 3.35 | 16.74 | 4981.81
TS6060#1 | RS\09\004\B | RS | 9 | 4 | B | 1 Prestrip - Thick | 100 | 13.0535 | 13.0535 | 2019-01-05 19:13 | 2019-01-06 00:29 | 5030.8734 | 5031 | [7 empty] | 0 | 0 | 0.5 | 16.74 | 4981.81
PH4100A | RS\09\005\B | RS | 9 | 5 | B | 1 Prestrip - Thick | 100 | 7.138 | 7.138 | 2019-01-06 00:29 | 2019-01-06 02:05 | 2571.2208 | 2571 | [7 empty] | 0 | 0 | 0.26 | 18.99 | 4776.61
TS6060#1 | BW\26\003\D | BW | 26 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-01-06 00:29 | 2019-01-07 16:39 | 50293.8019 | [6 empty] | 50294 | 37819 | 4.83 | 0 | 0 | 5.92 | 5893
PH4100A | RS\10\003\A | RS | 10 | 3 | A | 1 Prestrip - Thick | 100 | 62.527 | 62.527 | 2019-01-06 02:05 | 2019-01-10 01:33 | 146722.9034 | 146723 | [7 empty] | 0 | 0 | 21.41 | 11.27 | 5409.55
TS5500Shv | RS\09\004\B | RS | 9 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-01-06 02:05 | 2019-01-08 06:28 | 59118.1353 | [6 empty] | 59118 | 40912 | 4.09 | 0 | 0 | 16.74 | 4982
DRE2 | DT\27\001\D | DT | 27 | 1 | D | 6 DL | 100 | 100 | 100 | 2019-01-06 03:31 | 2019-01-13 18:41 | 607929.4907 |  |  |  | 26514 | 607929 | 438642 |  |  | 0 | 19.04 | 0 | 5.99 | 5884.72
TS Fleet 5 | MW\29\006\A | MW | 29 | 6 | A | 1 Prestrip - Thick | 68.6772 | 68.6772 | 68.6772 | 2019-01-06 12:14 | 2019-01-10 03:59 | 152330.0471 | 152330 | [7 empty] | 0 | 0 | 14.99 | 10.63 | 5414.51
TS5500Exc | MW\29\003\A | MW | 29 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-01-07 04:56 | 2019-01-08 08:26 | 34631.9041 | [6 empty] | 34632 | 25368 | 2.52 | 0 | 0 | 10.8 | 5404
TS6060#1 | BW\30\007\B | BW | 30 | 7 | B | 8 Coal Mining | 80.6 | 0 | 80.6 | 2019-01-07 16:39 | 2019-01-09 02:41 | 42632.7923 | [6 empty] | 42633 | 30778 | 3.08 | 0 | 0 | 12.66 | 5311
TS5500Shv | RS\09\005\B | RS | 9 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-01-08 06:28 | 2019-01-10 11:53 | 60277.6644 | [6 empty] | 60278 | 41152 | 4.11 | 0 | 0 | 18.99 | 4777
TS5500Exc | MW\29\003\B | MW | 29 | 3 | B | 1 Prestrip - Thick | 6.1379 | 6.1379 | 6.1379 | 2019-01-08 08:26 | 2019-01-08 10:54 | 2195.117 | 2195 | [7 empty] | 0 | 0 | 0.22 | 8.4 | 5644.55
TS5500Exc | MW\25\011\D | MW | 25 | 11 | D | 8 Coal Mining | 100 | 0 | 55.8 | 2019-01-08 10:54 | 2019-01-10 13:36 | 63858.9045 | [6 empty] | 63859 | 48399 | 2.47 | 0 | 0 | 5.91 | 5892
TS6060#1 | BW\30\008\B | BW | 30 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-01-09 02:41 | 2019-01-10 20:19 | 52144.914 | [6 empty] | 52145 | 37479 | 3.75 | 0 | 0 | 13.5 | 5242
PH4100A | RS\10\004\A | RS | 10 | 4 | A | 1 Prestrip - Thick | 100 | 62.9019 | 62.9019 | 2019-01-10 01:33 | 2019-01-17 03:43 | 262831.8436 | 262832 | [7 empty] | 0 | 0 | 25.87 | 12.57 | 5293.38
TS Fleet 5 | MW\29\003\B | MW | 29 | 3 | B | 1 Prestrip - Thick | 93.8621 | 93.8621 | 93.8621 | 2019-01-10 03:59 | 2019-01-10 23:20 | 33568.3054 | 33568 | [7 empty] | 0 | 0 | 3.36 | 8.4 | 5644.55
TS5500Shv | RS\09\006\A | RS | 9 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-01-10 11:53 | 2019-01-12 09:29 | 51442.608 | [6 empty] | 51443 | 35602 | 3.56 | 0 | 0 | 13.86 | 5104
TS5500Exc | SC\34\011\D | SC | 34 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-01-10 13:36 | 2019-01-13 01:46 | 75777.234 | [6 empty] | 75777 | 56589 | 4.72 | 0 | 0 | 7.65 | 5741
TS6060#1 | BW\30\009\B | BW | 30 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-01-10 20:19 | 2019-01-12 14:38 | 52993.9676 | [6 empty] | 52994 | 37896 | 3.79 | 0 | 0 | 14.7 | 5130
TS Fleet 5 | MW\29\007\A | MW | 29 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-01-10 23:20 | 2019-01-17 19:27 | 284928.5532 | 284929 | [7 empty] | 0 | 0 | 28.18 | 10.71 | 5404.38
TS5500Shv | RS\09\006\B | RS | 9 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-01-12 09:29 | 2019-01-13 17:23 | 31648.2788 | 31648 | [7 empty] | 0 | 0 | 3.16 | 18.4 | 4784.07
DRE1 | SC\34\016\D | SC | 34 | 16 | D | 6 DL | 100 | 0 | 100 | 2019-01-12 14:08 | 2019-01-20 18:52 | 678089.4603 |  |  |  | 38701 | 678089 | 514165 |  |  | 0 | 32.17 | 0 | 7.1 | 5787.82
TS6060#1 | BW\30\010\B | BW | 30 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-01-12 14:38 | 2019-01-14 11:02 | 55605.814 | [6 empty] | 55606 | 39384 | 3.99 | 0 | 0 | 17.09 | 4906
TS5500Exc | MW\29\003\B | MW | 29 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-01-13 01:46 | 2019-01-14 10:33 | 41291.6969 | [6 empty] | 41292 | 30725 | 3.08 | 0 | 0 | 8.4 | 5645
TS5500Shv | RS\09\006\B | RS | 9 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-01-13 17:23 | 2019-01-15 22:38 | 60088.0287 | [6 empty] | 60088 | 40880 | 4.08 | 0 | 0 | 18.4 | 4784
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2019-01-13 18:41 | 2019-01-15 18:41
PH4100XPC#1 | GG\03\005\B | GG | 3 | 5 | B | 1 Prestrip - Thick | 100 | 0 | 72.3052 | 2019-01-14 01:17 | 2019-01-26 07:39 | 637510.7185 | 637511 | [7 empty] | 0 | 0 | 24.33 | 0 | 0
TS5500Exc | MW\29\004\A | MW | 29 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-01-14 10:33 | 2019-01-16 01:36 | 49184.041 | [6 empty] | 49184 | 36183 | 3.61 | 0 | 0 | 10.19 | 5453
TS6060#1 | BW\30\011\B | BW | 30 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-01-14 11:02 | 2019-01-15 10:52 | 29844.7665 | [6 empty] | 29845 | 21827 | 2.19 | 0 | 0 | 11.38 | 5330
TS6060#1 | GG\01\005\D | GG | 1 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-01-15 10:52 | 2019-01-17 17:13 | 68062.2039 | [6 empty] | 68062 | 51450 | 3.83 | 0 | 0 | 5.47 | 5894
DRE2 | BW\27\011\D | BW | 27 | 11 | D | 6 DL | 100 | 100 | 100 | 2019-01-15 18:41 | 2019-01-21 03:15 | 426709.4219 |  |  |  | 18610 | 426709 | 307885 |  |  | 0 | 20.43 | 0 | 5.83 | 5900.09
TS5500Shv | RS\09\007\X | RS | 9 | 7 | X | 8 Coal Mining | 100 | 0 | 100 | 2019-01-15 22:38 | 2019-01-16 15:35 | 19132.8074 | [6 empty] | 19133 | 13493 | 1.36 | 0 | 0 | 11.88 | 5212
TS5500Exc | MW\29\005\A | MW | 29 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-01-16 01:36 | 2019-01-17 13:31 | 45244.1211 | [6 empty] | 45244 | 33437 | 3.35 | 0 | 0 | 9.68 | 5490
TS5500Shv | RS\09\008\X | RS | 9 | 8 | X | 8 Coal Mining | 100 | 0 | 100 | 2019-01-16 15:35 | 2019-01-17 02:30 | 12307.1981 | [6 empty] | 12307 | 8511 | 1.23 | 0 | 0 | 14.12 | 5014
TS5500Shv | RS\09\007\A | RS | 9 | 7 | A | 1 Prestrip - Thick | 68.3559 | 38.4297 | 38.4297 | 2019-01-17 02:30 | 2019-01-20 17:17 | 86090.6321 | 86091 | [7 empty] | 0 | 0 | 8.59 | 16.05 | 4964.9
PH4100A | RS\09\007\A | RS | 9 | 7 | A | 1 Prestrip - Thick | 100 | 61.5703 | 61.5703 | 2019-01-17 03:43 | 2019-01-20 17:17 | 137930.2389 | 137930 | [7 empty] | 0 | 0 | 13.77 | 16.05 | 4964.9
TS5500Exc | MW\29\006\A | MW | 29 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-01-17 13:31 | 2019-01-18 13:13 | 29847.8636 | [6 empty] | 29848 | 21988 | 2.19 | 0 | 0 | 10.63 | 5415
TS6060#1 | GG\02\005\D | GG | 2 | 5 | D | 1 Prestrip - Thick | 100 | 41.8939 | 41.8939 | 2019-01-17 17:13 | 2019-01-26 06:46 | 193726.5688 | 193727 | [7 empty] | 0 | 0 | 14.3 | 5.46 | 5893.01
TS Fleet 5 | MW\29\004\B | MW | 29 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-01-17 19:27 | 2019-01-18 16:00 | 35659.5403 | 35660 | [7 empty] | 0 | 0 | 3.55 | 8.8 | 5614.81
TS5500Exc | GG\02\005\D | GG | 2 | 5 | D | 1 Prestrip - Thick | 100 | 35.5082 | 35.5082 | 2019-01-18 13:13 | 2019-01-26 06:46 | 164197.7144 | 164198 | [7 empty] | 0 | 0 | 12.12 | 5.46 | 5893.01
TS Fleet 5 | MW\29\005\B | MW | 29 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-01-18 16:00 | 2019-01-19 18:10 | 45431.0483 | 45431 | [7 empty] | 0 | 0 | 4.53 | 8.89 | 5627.28
TS Fleet 5 | MW\29\006\B | MW | 29 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-01-19 18:10 | 2019-01-20 22:47 | 49686.2022 | 49686 | [7 empty] | 0 | 0 | 4.98 | 8.75 | 5651.2
PH4100A | RS\09\008\A | RS | 9 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-01-20 17:17 | 2019-01-24 04:49 | 134654.9617 | 134655 | [7 empty] | 0 | 0 | 22.86 | 17.81 | 4861.78
TS5500Shv | MW\29\004\B | MW | 29 | 4 | B | 8 Coal Mining | 77.3 | 0 | 77.3 | 2019-01-20 17:17 | 2019-01-21 21:13 | 31522.0327 | [6 empty] | 31522 | 23383 | 2.33 | 0 | 0 | 8.8 | 5615
DRE1 | SC\34\017\D | SC | 34 | 17 | D | 6 DL | 100 | 0 | 100 | 2019-01-20 18:52 | 2019-01-27 14:21 | 563444.9622 |  |  |  | 40071 | 563445 | 405164 |  |  | 0 | 37.07 | 0 | 7.29 | 5770.94
TS Fleet 5 | MW\29\008\A | MW | 29 | 8 | A | 1 Prestrip - Thick | 40.0165 | 40.0165 | 40.0165 | 2019-01-20 22:47 | 2019-01-24 02:54 | 132121.4876 | 132121 | [7 empty] | 0 | 0 | 12.89 | 11.21 | 5355.71
DRE2 | BW\27\010\D | BW | 27 | 10 | D | 6 DL | 100 | 100 | 100 | 2019-01-21 03:15 | 2019-01-26 13:55 | 433684.0164 |  |  |  | 18914 | 433684 | 312918 |  |  | 0 | 20.75 | 0 | 5.57 | 5925.6
TS5500Shv | GG\02\005\D | GG | 2 | 5 | D | 1 Prestrip - Thick | 49.4658 | 22.5979 | 22.5979 | 2019-01-21 21:13 | 2019-01-26 06:46 | 104497.3809 | 104497 | [7 empty] | 0 | 0 | 7.72 | 5.46 | 5893.01
TS Fleet 5 | MW\29\008\A | MW | 29 | 8 | A | 1 Prestrip - Thick | 59.9835 | 59.9835 | 59.9835 | 2019-01-24 02:54 | 2019-01-28 20:59 | 198046.4351 | 198046 | [7 empty] | 0 | 0 | 19.32 | 11.21 | 5355.71
PH4100A | RS\10\006\X | RS | 10 | 6 | X | 1 Prestrip - Thick | 100 | 92.9397 | 92.9397 | 2019-01-24 04:49 | 2019-02-01 | 286734.3831 | 286734 | [7 empty] | 0 | 0 | 28.19 | 11.44 | 5247.94
TS6060#1 | GG\02\003\D | GG | 2 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-01-26 06:46 | 2019-01-29 19:40 | 106311.0458 | [6 empty] | 106311 | 80302 | 4.35 | 0 | 0 | 5.22 | 5924
TS5500Exc | MW\29\007\A | MW | 29 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-01-26 06:46 | 2019-01-27 19:07 | 45769.6647 | [6 empty] | 45770 | 33721 | 3.36 | 0 | 0 | 10.71 | 5404
TS5500Shv | RS\09\007\A | RS | 9 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-01-26 06:46 | 2019-01-28 03:42 | 50691.8925 | [6 empty] | 50692 | 34830 | 3.48 | 0 | 0 | 16.05 | 4965
PH4100XPC#1 | GG\04\002\B | GG | 4 | 2 | B | 1 Prestrip - Thick | 100 | 28.7217 | 28.7217 | 2019-01-26 07:39 | 2019-02-01 | 294899.939 | 294900 | [7 empty] | 0 | 0 | 11.23 | 15.51 | 5104.38
DRE2 | BW\27\009\D | BW | 27 | 9 | D | 6 DL | 100 | 100 | 100 | 2019-01-26 13:55 | 2019-01-31 23:07 | 428768.2366 |  |  |  | 18700 | 428768 | 309371 |  |  | 0 | 20.52 | 0 | 5.1 | 5966.44
DRE1 | SC\34\018\D | SC | 34 | 18 | D | 6 DL | 100 | 0 | 62.3969 | 2019-01-27 14:21 | 2019-02-01 | 364095.8466 |  |  |  | 25894 | 364096 | 261815 |  |  | 0 | 38.47 | 0 | 7.27 | 5772.78
TS5500Exc | SC\34\010\D | SC | 34 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2019-01-27 19:07 | 2019-01-30 16:54 | 61719.0363 |  |  | 61719 | [5 empty] | 0 | 0 | 0 | 7.64 | 5743.31
TS5500Shv | RS\09\008\A | RS | 9 | 8 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-01-28 03:42 | 2019-01-29 05:32 | 29162.5059 | [6 empty] | 29163 | 19931 | 3.48 | 0 | 0 | 17.81 | 4862
TS Fleet 5 | MW\29\007\B | MW | 29 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-01-28 20:59 | 2019-01-30 02:44 | 51651.0458 | 51651 | [7 empty] | 0 | 0 | 5.16 | 9.68 | 5541.54
TS5500Shv | RS\09\008\B | RS | 9 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-01-29 05:32 | 2019-01-29 19:18 | 13648.0647 | 13648 | [7 empty] | 0 | 0 | 2.39 | 17.44 | 4948.09
TS5500Shv | RS\09\008\B | RS | 9 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-01-29 19:18 | 2019-01-30 22:08 | 30286.2771 | [6 empty] | 30286 | 20629 | 3.8 | 0 | 0 | 17.44 | 4948
TS6060#1 | GG\02\004\D | GG | 2 | 4 | D | 8 Coal Mining | 100 | 0 | 46.7 | 2019-01-29 19:40 | 2019-01-31 15:33 | 54965.5775 | [6 empty] | 54966 | 41550 | 2.08 | 0 | 0 | 5.36 | 5912
TS Fleet 5 | MW\29\009\A | MW | 29 | 9 | A | 1 Prestrip - Thick | 70.5395 | 18.2246 | 18.2246 | 2019-01-30 02:44 | 2019-02-01 | 78576.3761 | 78576 | [7 empty] | 0 | 0 | 7.85 | 11.53 | 5360.76
TS5500Exc | SC\34\010\D | SC | 34 | 10 | D | 8 Coal Mining | 10.3 | 0 | 10.3 | 2019-01-30 16:54 | 2019-01-30 23:19 | 8077.1221 | [6 empty] | 8077 | 6042 | 0.5 | 0 | 0 | 7.64 | 5743
TS5500Shv | GG\02\005\D | GG | 2 | 5 | D | 7 PostStrip | 100 | 0 | 31.9982 | 2019-01-30 22:08 | 2019-02-01 | 25645.8478 |  |  | 25646 | [5 empty] | 0 | 0 | 0 | 5.46 | 5893.01
TS5500Exc | SC\34\010\D | SC | 34 | 10 | D | 8 Coal Mining | 89.7 | 0 | 26.1 | 2019-01-30 23:19 | 2019-01-31 15:33 | 20454.1398 | [6 empty] | 20454 | 15300 | 1.27 | 0 | 0 | 7.64 | 5743
TS6060#1 | RS\10\007\X | RS | 10 | 7 | X | 1 Prestrip - Thick | 26.7847 | 2.21 | 2.21 | 2019-01-31 15:33 | 2019-02-01 | 7794.4728 | 7794 | [7 empty] | 0 | 0 | 0.77 | 11.5 | 5240.61
TS5500Exc | MW\30\003\A | MW | 30 | 3 | A | 1 Prestrip - Thick | 25.8558 | 1.8649 | 1.8649 | 2019-01-31 15:33 | 2019-02-01 | 7470.2955 | 7470 | [7 empty] | 0 | 0 | 0.74 | 10.67 | 5415.51
DRE2 | BW\27\008\D | BW | 27 | 8 | D | 6 DL | 100 | 0.67422 | 0.67422 | 2019-01-31 23:07 | 2019-02-01 | 2917.0851 |  |  |  | 127 | 2917 | 2105 |  |  | 0 | 20.7 | 0 | 4.94 | 5979.46
| EOP 61 : 2019\Jan | EOP 61 : 2019 | Jan | [6 empty] | 2019-02-01 | 2019-02-01 |  | 4896122 |  | 87365 | 257372 | 4874188 | 3434176 | 1424700 | 1030452 | 98.12 | 0 | 400.48 | 10.18 | 5503.74
TS Fleet 5 | MW\29\009\A | MW | 29 | 9 | A | 1 Prestrip - Thick | 70.5395 | 52.3149 | 52.3149 | 2019-02-01 | 2019-02-06 14:15 | 225558.4488 | 225558 | [7 empty] | 0 | 0 | 22.53 | 11.53 | 5360.76
DRE1 | SC\34\018\D | SC | 34 | 18 | D | 6 DL | 100 | 0 | 37.6031 | 2019-02-01 | 2019-02-03 13:59 | 219420.4281 |  |  |  | 15605 | 219420 | 157782 |  |  | 0 | 38.47 | 0 | 7.27 | 5772.78
PH4100A | RS\10\006\X | RS | 10 | 6 | X | 1 Prestrip - Thick | 100 | 7.0603 | 7.0603 | 2019-02-01 | 2019-02-01 14:26 | 21782.0576 | 21782 | [7 empty] | 0 | 0 | 2.14 | 11.44 | 5247.94
DRE2 | BW\27\008\D | BW | 27 | 8 | D | 6 DL | 100 | 99.3258 | 99.3258 | 2019-02-01 | 2019-02-06 06:04 | 429744.9611 |  |  |  | 18743 | 429745 | 310076 |  |  | 0 | 20.7 | 0 | 4.94 | 5979.46
PH4100XPC#1 | GG\04\002\B | GG | 4 | 2 | B | 1 Prestrip - Thick | 100 | 71.2783 | 71.2783 | 2019-02-01 | 2019-02-15 07:37 | 731850.079 | 731850 | [7 empty] | 0 | 0 | 27.88 | 15.51 | 5104.38
TS5500Shv | GG\02\005\D | GG | 2 | 5 | D | 7 PostStrip | 100 | 0 | 68.0018 | 2019-02-01 | 2019-02-03 08:46 | 54501.8262 |  |  | 54502 | [5 empty] | 0 | 0 | 0 | 5.46 | 5893.01
TS6060#1 | RS\10\007\X | RS | 10 | 7 | X | 1 Prestrip - Thick | 26.7847 | 24.5748 | 24.5748 | 2019-02-01 | 2019-02-05 01:01 | 86673.3424 | 86673 | [7 empty] | 0 | 0 | 8.6 | 11.5 | 5240.61
TS5500Exc | MW\30\003\A | MW | 30 | 3 | A | 1 Prestrip - Thick | 25.8558 | 23.9909 | 23.9909 | 2019-02-01 | 2019-02-05 12:38 | 96102.2046 | 96102 | [7 empty] | 0 | 0 | 9.55 | 10.67 | 5415.51
PH4100A | RS\09\007\B | RS | 9 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-02-01 14:26 | 2019-02-02 06:20 | 25225.4942 | 25225 | [7 empty] | 0 | 0 | 2.52 | 18.18 | 4841.49
PH4100A | RS\10\007\X | RS | 10 | 7 | X | 1 Prestrip - Thick | 100 | 73.2153 | 73.2153 | 2019-02-02 06:20 | 2019-02-09 08:30 | 258224.8533 | 258225 | [7 empty] | 0 | 0 | 25.62 | 11.5 | 5240.61
TS5500Shv | RS\09\007\B | RS | 9 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-02-03 08:46 | 2019-02-05 12:48 | 56824.5131 | [6 empty] | 56825 | 38651 | 3.86 | 0 | 0 | 18.18 | 4841
DRE1 | SC\34\019\D | SC | 34 | 19 | D | 6 DL | 100 | 0 | 100 | 2019-02-03 13:59 | 2019-02-10 23:18 | 627665.1061 |  |  |  | 47731 | 627665 | 429581 |  |  | 0 | 40 | 0 | 7.18 | 5780.25
TS6060#1 | GG\02\004\D | GG | 2 | 4 | D | 8 Coal Mining | 100 | 0 | 53.3 | 2019-02-05 01:01 | 2019-02-07 04:48 | 62760.1063 | [6 empty] | 62760 | 47442 | 2.37 | 0 | 0 | 5.36 | 5912
TS5500Exc | SC\34\010\D | SC | 34 | 10 | D | 8 Coal Mining | 89.7 | 0 | 63.5 | 2019-02-05 12:38 | 2019-02-07 04:04 | 49687.5094 | [6 empty] | 49688 | 37166 | 3.1 | 0 | 0 | 7.64 | 5743
TS5500Shv | MW\29\007\B | MW | 29 | 7 | B | 8 Coal Mining | 22.4 | 0 | 22.4 | 2019-02-05 12:48 | 2019-02-05 20:48 | 8737.7527 | [6 empty] | 8738 | 6433 | 0.64 | 0 | 0 | 9.68 | 5542
TS5500Shv | MW\29\008\A | MW | 29 | 8 | A | 8 Coal Mining | 46.4 | 0 | 46.4 | 2019-02-05 20:48 | 2019-02-06 17:12 | 22279.4979 | [6 empty] | 22279 | 16366 | 1.65 | 0 | 0 | 11.21 | 5356
DRE2 | BW\27\007\D | BW | 27 | 7 | D | 6 DL | 100 | 100 | 100 | 2019-02-06 06:04 | 2019-02-11 16:00 | 442907.1985 |  |  |  | 19317 | 442907 | 319573 |  |  | 0 | 21.18 | 0 | 5.12 | 5963.54
TS Fleet 5 | MW\29\010\X | MW | 29 | 10 | X | 1 Prestrip - Thick | 68.0697 | 68.0697 | 68.0697 | 2019-02-06 14:15 | 2019-02-12 02:52 | 222779.8441 | 222780 | [7 empty] | 0 | 0 | 21.55 | 12.32 | 5195.07
TS5500Shv | MW\29\009\A | MW | 29 | 9 | A | 8 Coal Mining | 46.4 | 0 | 46.4 | 2019-02-06 17:12 | 2019-02-07 13:24 | 22044.0423 | [6 empty] | 22044 | 16154 | 1.63 | 0 | 0 | 11.53 | 5361
TS5500Exc | SC\34\015\D | SC | 34 | 15 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-02-07 04:04 | 2019-02-09 15:09 | 74409.4283 | [6 empty] | 74409 | 55784 | 4.25 | 0 | 0 | 7.03 | 5793
TS6060#1 | GG\03\002\D | GG | 3 | 2 | D | 8 Coal Mining | 45.7 | 0 | 45.7 | 2019-02-07 04:48 | 2019-02-08 23:56 | 52272.735 | [6 empty] | 52273 | 39452 | 2.09 | 0 | 0 | 5.36 | 5915
TS5500Shv | GG\02\005\D | GG | 2 | 5 | D | 8 Coal Mining | 25.1 | 0 | 25.1 | 2019-02-07 13:24 | 2019-02-08 06:57 | 19171.7704 | [6 empty] | 19172 | 14492 | 0.93 | 0 | 0 | 5.46 | 5893
TS5500Shv | GG\02\005\D | GG | 2 | 5 | D | 8 Coal Mining | 74.9 | 0 | 74.9 | 2019-02-08 06:57 | 2019-02-10 11:24 | 57276.4358 | [6 empty] | 57276 | 43296 | 2.79 | 0 | 0 | 5.46 | 5893
TS6060#1 | BW\27\009\D | BW | 27 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-02-08 23:56 | 2019-02-12 15:11 | 105736.2339 | [6 empty] | 105736 | 80400 | 5.03 | 0 | 0 | 5.1 | 5966
PH4100A | RS\10\008\X | RS | 10 | 8 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-02-09 08:30 | 2019-02-15 15:49 | 231350.3499 | 231350 | [7 empty] | 0 | 0 | 38.29 | 13.6 | 5057.69
TS5500Exc | SC\34\016\D | SC | 34 | 16 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-02-09 15:09 | 2019-02-12 17:53 | 94142.5824 | [6 empty] | 94143 | 70524 | 4.39 | 0 | 0 | 7.1 | 5788
TS5500Shv | GG\03\002\D | GG | 3 | 2 | D | 8 Coal Mining | 54.3 | 0 | 54.3 | 2019-02-10 11:24 | 2019-02-12 20:19 | 62152.3839 | [6 empty] | 62152 | 46908 | 2.49 | 0 | 0 | 5.36 | 5915
DRE1 | SC\34\020\D | SC | 34 | 20 | D | 6 DL | 100 | 0 | 100 | 2019-02-10 23:18 | 2019-02-17 18:35 | 577963.1 |  |  |  | 41104 | 577963 | 415604 |  |  | 0 | 38.31 | 0 | 7.31 | 5769.52
DRE2 | BW\27\006\D | BW | 27 | 6 | D | 6 DL | 100 | 100 | 100 | 2019-02-11 16:00 | 2019-02-17 04:38 | 452088.1485 |  |  |  | 19717 | 452088 | 326197 |  |  | 0 | 21.63 | 0 | 5.35 | 5942.17
TS Fleet 5 | MW\29\011\X | MW | 29 | 11 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-02-12 02:52 | 2019-02-21 05:17 | 366960.0666 | 366960 | [7 empty] | 0 | 0 | 35.42 | 12.46 | 5169.82
TS6060#1 | BW\27\010\D | BW | 27 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-02-12 15:11 | 2019-02-16 09:26 | 109386.4818 | [6 empty] | 109386 | 83040 | 5.19 | 0 | 0 | 5.57 | 5926
TS5500Exc | SC\34\017\D | SC | 34 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-02-12 17:53 | 2019-02-15 03:05 | 72032.2008 | [6 empty] | 72032 | 53833 | 4.49 | 0 | 0 | 7.29 | 5771
TS5500Shv | MW\29\010\X | MW | 29 | 10 | X | 8 Coal Mining | 46.4 | 0 | 46.4 | 2019-02-12 20:19 | 2019-02-13 04:02 | 8431.0332 | [6 empty] | 8431 | 6145 | 0.61 | 0 | 0 | 12.32 | 5195
TS5500Shv | DT\27\002\D | DT | 27 | 2 | D | 8 Coal Mining | 20.6 | 0 | 20.6 | 2019-02-13 04:02 | 2019-02-14 09:04 | 31694.1964 | [6 empty] | 31694 | 23911 | 1.01 | 0 | 0 | 5.99 | 5887
TS5500Shv | DT\28\002\B | DT | 28 | 2 | B | 8 Coal Mining | 41 | 0 | 41 | 2019-02-14 09:04 | 2019-02-15 05:18 | 22109.869 | [6 empty] | 22110 | 16028 | 0.87 | 0 | 0 | 11.99 | 5283
TS5500Exc | MW\29\004\B | MW | 29 | 4 | B | 8 Coal Mining | 22.7 | 0 | 22.7 | 2019-02-15 03:05 | 2019-02-15 10:26 | 9263.8075 | [6 empty] | 9264 | 6872 | 0.68 | 0 | 0 | 8.8 | 5615
TS5500Shv | DT\28\004\A | DT | 28 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2019-02-15 05:18 | 2019-02-15 10:02 | 5153.3206 | [6 empty] | 5153 | 3591 | 1.83 | 0 | 0 | 19.87 | 4710
PH4100XPC#1 | GG\03\005\D | GG | 3 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-02-15 07:37 | 2019-02-18 03:26 | 140338.854 | 140339 | [7 empty] | 0 | 0 | 11.63 | 5.59 | 5892.04
TS5500Shv | DT\28\005\B | DT | 28 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2019-02-15 10:02 | 2019-02-16 06:02 | 21839.6282 | [6 empty] | 21840 | 15944 | 0.76 | 0 | 0 | 10.62 | 5365
TS5500Exc | GG\04\002\B | GG | 4 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-02-15 10:26 | 2019-02-17 09:35 | 59402.2577 | [6 empty] | 59402 | 42272 | 1.75 | 0 | 0 | 15.51 | 5104
PH4100A | MW\31\002\D | MW | 31 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-02-15 15:49 | 2019-02-23 07:19 | 301478.3996 | 301478 | [7 empty] | 0 | 0 | 30.58 | 7.4 | 5763.68
TS5500Shv | RS\05\004\B | RS | 5 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2019-02-16 06:02 | 2019-02-17 06:10 | 26355.6615 | [6 empty] | 26356 | 18652 | 1.87 | 0 | 0 | 13.32 | 5250
TS6060#1 | BW\27\008\D | BW | 27 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-02-16 09:26 | 2019-02-19 20:58 | 101250.3791 | [6 empty] | 101250 | 77056 | 4.82 | 0 | 0 | 4.94 | 5979
DRE2 | BW\27\005\D | BW | 27 | 5 | D | 6 DL | 100 | 100 | 100 | 2019-02-17 04:38 | 2019-02-22 21:45 | 467378.2192 |  |  |  | 20384 | 467378 | 337229 |  |  | 0 | 22.35 | 0 | 5.49 | 5927.86
TS5500Shv | RS\05\005\A | RS | 5 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-02-17 06:10 | 2019-02-17 23:05 | 18480.4592 | [6 empty] | 18480 | 12828 | 1.27 | 0 | 0 | 14.38 | 5087
TS5500Exc | MW\29\005\B | MW | 29 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-02-17 09:35 | 2019-02-18 17:39 | 40374.5636 | [6 empty] | 40375 | 29926 | 2.97 | 0 | 0 | 8.89 | 5627
DRE1 | SC\34\021\D | SC | 34 | 21 | D | 6 DL | 100 | 0 | 100 | 2019-02-17 18:35 | 2019-02-27 23:14 | 866016.9381 |  |  |  | 45612 | 866017 | 397928 |  |  | 0 | 39.35 | 0 | 7.34 | 5769.01
TS5500Shv | RS\05\006\A | RS | 5 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-02-17 23:05 | 2019-02-19 17:35 | 46403.4385 | [6 empty] | 46403 | 32268 | 3.21 | 0 | 0 | 13.38 | 5158
PH4100XPC#1 | RS\05\005\B | RS | 5 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-02-18 03:26 | 2019-02-18 16:07 | 26248.9163 | 26249 | [7 empty] | 0 | 0 | 2.61 | 15.58 | 5049.42
PH4100XPC#1 | GG\04\002\D | GG | 4 | 2 | D | 1 Prestrip - Thick | 100 | 73.9025 | 73.9025 | 2019-02-18 16:07 | 2019-02-23 04:23 | 224059.5282 | 224060 | [7 empty] | 0 | 0 | 15 | 5.42 | 5909.49
TS5500Exc | MW\29\006\B | MW | 29 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-02-18 17:39 | 2019-02-20 02:10 | 40963.7277 | [6 empty] | 40964 | 30367 | 3.04 | 0 | 0 | 8.75 | 5651
TS5500Shv | GG\03\005\D | GG | 3 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2019-02-19 17:35 | 2019-02-24 07:47 | 105796.8121 |  |  | 105797 | [5 empty] | 0 | 0 | 0 | 5.59 | 5892.04
TS6060#1 | BW\27\007\D | BW | 27 | 7 | D | 8 Coal Mining | 100 | 0 | 63.4 | 2019-02-19 20:58 | 2019-02-22 01:49 | 64045.745 | [6 empty] | 64046 | 48664 | 3.04 | 0 | 0 | 5.12 | 5964
TS5500Exc | SC\34\018\D | SC | 34 | 18 | D | 8 Coal Mining | 100 | 0 | 84.5 | 2019-02-20 02:10 | 2019-02-22 01:49 | 60018.2386 | [6 empty] | 60018 | 44711 | 3.73 | 0 | 0 | 7.27 | 5773
TS Fleet 5 | GG\04\002\D | GG | 4 | 2 | D | 1 Prestrip - Thick | 45.3048 | 26.0975 | 26.0975 | 2019-02-21 05:17 | 2019-02-23 04:23 | 79123.0612 | 79123 | [7 empty] | 0 | 0 | 5.3 | 5.42 | 5909.49
TS6060#1 | RS\11\005\X | RS | 11 | 5 | X | 1 Prestrip - Thick | 47.2554 | 47.2554 | 47.2554 | 2019-02-22 01:49 | 2019-02-28 13:03 | 137917.1836 | 137917 | [7 empty] | 0 | 0 | 13.55 | 13.11 | 5151.24
TS5500Exc | MW\30\003\A | MW | 30 | 3 | A | 1 Prestrip - Thick | 74.1442 | 36.6985 | 36.6985 | 2019-02-22 01:49 | 2019-03-01 | 147006.3372 | 147006 | [7 empty] | 0 | 0 | 14.61 | 10.67 | 5415.51
DRE2 | BW\27\004\D | BW | 27 | 4 | D | 6 DL | 100 | 96.1817 | 96.1817 | 2019-02-22 21:45 | 2019-03-01 | 498460.6727 |  |  |  | 18624 | 498461 | 237586 |  |  | 0 | 23.17 | 0 | 5.72 | 5909.47
TS Fleet 5 | GG\05\002\X1 | GG | 5 | 2 | X1 | 1 Prestrip - Thick | 36.189 | 0 | 22.0505 | 2019-02-23 04:23 | 2019-03-01 | 234538.5793 | 234539 | [7 empty] | 0 | 0 | 8.87 | 0 | 0
PH4100XPC#1 | RS\05\006\B | RS | 5 | 6 | B | 1 Prestrip - Thick | 100 | 65.1142 | 65.1142 | 2019-02-23 04:23 | 2019-02-23 14:06 | 20117.0544 | 20117 | [7 empty] | 0 | 0 | 2.01 | 16.23 | 4985.73
PH4100A | RS\05\006\B | RS | 5 | 6 | B | 1 Prestrip - Thick | 100 | 34.8858 | 34.8858 | 2019-02-23 07:19 | 2019-02-23 14:06 | 10777.9655 | 10778 | [7 empty] | 0 | 0 | 1.08 | 16.23 | 4985.73
PH4100A | RS\10\005\A | RS | 10 | 5 | A | 1 Prestrip - Thick | 100 | 43.3097 | 43.3097 | 2019-02-23 14:06 | 2019-03-01 | 199250.9019 | 199251 | [7 empty] | 0 | 0 | 19.42 | 14.54 | 5103.98
PH4100XPC#1 | GG\04\005\B | GG | 4 | 5 | B | 1 Prestrip - Thick | 100 | 27.3333 | 27.3333 | 2019-02-23 14:06 | 2019-03-01 | 278316.4018 | 278316 | [7 empty] | 0 | 0 | 15.05 | 11.33 | 5396.94
TS5500Shv | GG\04\002\D | GG | 4 | 2 | D | 7 PostStrip | 50.9554 | 0 | 50.9554 | 2019-02-24 07:47 | 2019-02-26 12:24 | 50509.8165 |  |  | 50510 | [5 empty] | 0 | 0 | 0 | 5.42 | 5909.49
TS5500Shv | RS\57\001\D | RS | 57 | 1 | D | 1 Prestrip - Thick | 21.9806 | 21.9806 | 21.9806 | 2019-02-26 12:24 | 2019-02-27 04:25 | 15344.0828 | 15344 | [7 empty] | 0 | 0 | 1.68 | 7.79 | 5735.19
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 19:35 |  | 1d 19:35 | 2019-02-27 04:25 | 2019-03-01
DRE1 | SC\35\014\D | SC | 35 | 14 | D | 6 DL | 100 | 0 | 13.9982 | 2019-02-27 23:14 | 2019-03-01 | 87612.8277 |  |  |  | 5000 | 87613 | 66433 |  |  | 0 | 30.92 | 0 | 7.59 | 5744.59
TS6060#1 | GG\04\002\D | GG | 4 | 2 | D | 7 PostStrip | 49.0446 | 0 | 10.2009 | 2019-02-28 13:03 | 2019-03-01 | 10111.6556 |  |  | 10112 | [5 empty] | 0 | 0 | 0 | 5.42 | 5909.49
| EOP 62 : 2019\Feb | EOP 62 : 2019 | Feb | [6 empty] | 2019-03-01 | 2019-03-01 |  | 4081024 |  | 220920 | 251836 | 4669258 | 2997986 | 1424700 | 1059176 | 76.36 | 0 | 335.47 | 7.88 | 5707.42
TS Fleet 5 | GG\05\002\X1 | GG | 5 | 2 | X1 | 1 Prestrip - Thick | 36.189 | 0 | 14.1385 | 2019-03-01 | 2019-03-04 08:09 | 150383.6546 | 150384 | [7 empty] | 0 | 0 | 5.69 | 0 | 0
DRE1 | SC\35\014\D | SC | 35 | 14 | D | 6 DL | 100 | 0 | 86.0018 | 2019-03-01 | 2019-03-07 08:04 | 538275.5834 |  |  |  | 30721 | 538276 | 408150 |  |  | 0 | 30.92 | 0 | 7.59 | 5744.59
PH4100A | RS\10\005\A | RS | 10 | 5 | A | 1 Prestrip - Thick | 100 | 56.6903 | 56.6903 | 2019-03-01 | 2019-03-07 13:41 | 260809.7072 | 260810 | [7 empty] | 0 | 0 | 25.42 | 14.54 | 5103.98
DRE2 | BW\27\004\D | BW | 27 | 4 | D | 6 DL | 100 | 3.8183 | 3.8183 | 2019-03-01 | 2019-03-01 05:43 | 19788.0796 |  |  |  | 739 | 19788 | 9432 |  |  | 0 | 23.17 | 0 | 5.72 | 5909.47
PH4100XPC#1 | GG\04\005\B | GG | 4 | 5 | B | 1 Prestrip - Thick | 100 | 72.6667 | 72.6667 | 2019-03-01 | 2019-03-14 08:17 | 739915.7859 | 739916 | [7 empty] | 0 | 0 | 40 | 11.33 | 5396.94
TS5500Shv | MW\29\011\X | MW | 29 | 11 | X | 8 Coal Mining | 46.4 | 0 | 46.4 | 2019-03-01 | 2019-03-01 06:05 | 7421.0008 | [6 empty] | 7421 | 5404 | 0.6 | 0 | 0 | 12.46 | 5170
TS6060#1 | GG\04\002\D | GG | 4 | 2 | D | 7 PostStrip | 49.0446 | 0 | 38.8437 | 2019-03-01 | 2019-03-02 13:19 | 38504.0428 |  |  | 38504 | [5 empty] | 0 | 0 | 0 | 5.42 | 5909.49
TS5500Exc | MW\30\003\A | MW | 30 | 3 | A | 1 Prestrip - Thick | 74.1442 | 37.4457 | 37.4457 | 2019-03-01 | 2019-03-08 01:33 | 149999.2383 | 149999 | [7 empty] | 0 | 0 | 14.91 | 10.67 | 5415.51
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2019-03-01 05:43 | 2019-03-03 05:43
TS5500Shv | GG\03\005\D | GG | 3 | 5 | D | 8 Coal Mining | 22.8 | 0 | 22.8 | 2019-03-01 06:05 | 2019-03-02 05:03 | 28022.2677 | [6 empty] | 28022 | 21182 | 1.01 | 0 | 0 | 5.59 | 5892
TS5500Shv | RS\05\007\A | RS | 5 | 7 | A | 8 Coal Mining | 54.9 | 0 | 54.9 | 2019-03-02 05:03 | 2019-03-03 04:44 | 28866.9266 | [6 empty] | 28867 | 19912 | 1.99 | 0 | 0 | 14.97 | 5065
TS6060#1 | BW\27\007\D | BW | 27 | 7 | D | 8 Coal Mining | 100 | 0 | 36.6 | 2019-03-02 13:19 | 2019-03-03 16:36 | 36931.9659 | [6 empty] | 36932 | 28062 | 1.75 | 0 | 0 | 5.12 | 5964
TS5500Shv | GG\04\002\D | GG | 4 | 2 | D | 8 Coal Mining | 36.2 | 0 | 36.2 | 2019-03-03 04:44 | 2019-03-04 17:00 | 44231.2426 | [6 empty] | 44231 | 33382 | 1.67 | 0 | 0 | 5.42 | 5909
DRE2 | DT\28\006\D | DT | 28 | 6 | D | 6 DL | 100 | 0 | 100 | 2019-03-03 05:43 | 2019-03-13 05:03 | 826530.0771 |  |  |  | 61783 | 826530 | 568657 |  |  | 0 | 30 | 0 | 7.16 | 5783.93
TS6060#1 | BW\27\011\D | BW | 27 | 11 | D | 8 Coal Mining | 68.3 | 0 | 68.3 | 2019-03-03 16:36 | 2019-03-05 18:19 | 67288.8628 | [6 empty] | 67289 | 50925 | 3.18 | 0 | 0 | 5.83 | 5900
TS Fleet 5 | GG\05\003\X1 | GG | 5 | 3 | X1 | 1 Prestrip - Thick | 45.2998 | 45.2998 | 45.2998 | 2019-03-04 08:09 | 2019-03-09 15:02 | 238033.9148 | 238034 | [7 empty] | 0 | 0 | 11.2 | 9.4 | 5487.25
TS5500Shv | RS\05\005\B | RS | 5 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2019-03-04 17:00 | 2019-03-05 15:09 | 27011.9349 | [6 empty] | 27012 | 18806 | 1.88 | 0 | 0 | 15.58 | 5049
TS5500Shv | RS\05\008\A | RS | 5 | 8 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2019-03-05 15:09 | 2019-03-06 08:06 | 20654.7191 | [6 empty] | 20655 | 14226 | 1.8 | 0 | 0 | 15.6 | 5051
TS6060#1 | BW\27\005\D | BW | 27 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-03-05 18:19 | 2019-03-08 14:09 | 91813.1418 | [6 empty] | 91813 | 69378 | 4.34 | 0 | 0 | 5.49 | 5928
TS5500Shv | RS\06\003\A | RS | 6 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2019-03-06 08:06 | 2019-03-06 14:06 | 7322.9925 | [6 empty] | 7323 | 5204 | 0.74 | 0 | 0 | 12.46 | 5301
TS5500Shv | RS\06\004\A | RS | 6 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2019-03-06 14:06 | 2019-03-06 22:54 | 10726.609 | [6 empty] | 10727 | 7524 | 0.74 | 0 | 0 | 13.93 | 5157
TS5500Shv | RS\06\005\A | RS | 6 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2019-03-06 22:54 | 2019-03-07 14:01 | 18427.7833 | [6 empty] | 18428 | 12854 | 1.28 | 0 | 0 | 13.54 | 5153
DRE1 | SC\35\013\D | SC | 35 | 13 | D | 6 DL | 100 | 0 | 100 | 2019-03-07 08:04 | 2019-03-13 13:54 | 530416.5327 |  |  |  | 37722 | 530417 | 381414 |  |  | 0 | 35.18 | 0 | 7.73 | 5733.31
PH4100A | MW\32\002\D | MW | 32 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-03-07 13:41 | 2019-03-13 07:29 | 243695.0632 | 243695 | [7 empty] | 0 | 0 | 24.88 | 7.52 | 5753.21
TS5500Shv | RS\06\006\A | RS | 6 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2019-03-07 14:01 | 2019-03-08 10:49 | 25364.9546 | [6 empty] | 25365 | 17651 | 1.76 | 0 | 0 | 13.19 | 5168
TS5500Exc | SC\34\018\D | SC | 34 | 18 | D | 8 Coal Mining | 100 | 0 | 15.5 | 2019-03-08 01:33 | 2019-03-08 10:19 | 11047.2913 | [6 empty] | 11047 | 8230 | 0.69 | 0 | 0 | 7.27 | 5773
TS5500Exc | MW\29\007\B | MW | 29 | 7 | B | 8 Coal Mining | 77.6 | 0 | 77.6 | 2019-03-08 10:19 | 2019-03-09 10:20 | 30248.7294 | [6 empty] | 30249 | 22269 | 2.23 | 0 | 0 | 9.68 | 5542
TS5500Shv | MW\30\003\A | MW | 30 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-03-08 10:49 | 2019-03-09 19:17 | 39604.5742 | [6 empty] | 39605 | 29013 | 2.9 | 0 | 0 | 10.67 | 5416
TS6060#1 | BW\27\006\D | BW | 27 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-03-08 14:09 | 2019-03-11 13:59 | 97201.5826 | [6 empty] | 97202 | 73623 | 4.6 | 0 | 0 | 5.35 | 5942
TS5500Exc | MW\29\008\A | MW | 29 | 8 | A | 8 Coal Mining | 53.6 | 0 | 53.6 | 2019-03-09 10:20 | 2019-03-10 06:44 | 25698.952 | [6 empty] | 25699 | 18878 | 1.91 | 0 | 0 | 11.21 | 5356
TS Fleet 5 | GG\05\004\X1 | GG | 5 | 4 | X1 | 1 Prestrip - Thick | 45.356 | 45.356 | 45.356 | 2019-03-09 15:02 | 2019-03-15 10:36 | 261826.4051 | 261826 | [7 empty] | 0 | 0 | 11.92 | 10.82 | 5357.93
TS5500Shv | RS\06\008\A | RS | 6 | 8 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2019-03-09 19:17 | 2019-03-10 11:09 | 19348.2636 | [6 empty] | 19348 | 13283 | 1.79 | 0 | 0 | 16.43 | 4983
TS5500Exc | MW\29\009\A | MW | 29 | 9 | A | 8 Coal Mining | 53.6 | 0 | 53.6 | 2019-03-10 06:44 | 2019-03-11 02:56 | 25427.3587 | [6 empty] | 25427 | 18634 | 1.88 | 0 | 0 | 11.53 | 5361
TS5500Shv | RS\10\008\X | RS | 10 | 8 | X | 8 Coal Mining | 100 | 0 | 100 | 2019-03-10 11:09 | 2019-03-10 19:09 | 9741.8563 | [6 empty] | 9742 | 6765 | 1.16 | 0 | 0 | 13.6 | 5058
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 09:55 |  | 2d 09:55 | 2019-03-10 19:09 | 2019-03-13 05:03
TS5500Exc | MW\29\010\X | MW | 29 | 10 | X | 8 Coal Mining | 53.6 | 0 | 53.6 | 2019-03-11 02:56 | 2019-03-11 10:39 | 9725.027 | [6 empty] | 9725 | 7088 | 0.7 | 0 | 0 | 12.32 | 5195
TS5500Exc | MW\29\010\A | MW | 29 | 10 | A | 1 Prestrip - Thick | 100 | 46.9599 | 46.9599 | 2019-03-11 10:39 | 2019-03-15 18:59 | 92277.0336 | 92277 | [7 empty] | 0 | 0 | 9.22 | 11.23 | 5424.11
TS6060#1 | MW\29\010\A | MW | 29 | 10 | A | 1 Prestrip - Thick | 100 | 53.0401 | 53.0401 | 2019-03-11 13:59 | 2019-03-15 18:59 | 104224.9023 | 104225 | [7 empty] | 0 | 0 | 10.42 | 11.23 | 5424.11
DRE2 | DT\28\007\D | DT | 28 | 7 | D | 6 DL | 100 | 0 | 100 | 2019-03-13 05:03 | 2019-03-20 18:40 | 627158.4054 |  |  |  | 46880 | 627158 | 431488 |  |  | 0 | 30 | 0 | 6.97 | 5800.59
TS5500Shv | DT\28\006\D | DT | 28 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2019-03-13 05:03 | 2019-03-15 08:45 | 63028.087 | [6 empty] | 63028 | 47018 | 2.29 | 0 | 0 | 7.16 | 5784
PH4100A | MW\31\003\A | MW | 31 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-03-13 07:29 | 2019-03-22 07:30 | 388263.5465 | 388264 | [7 empty] | 0 | 0 | 40.67 | 10.82 | 5405.53
DRE1 | SC\35\012\D | SC | 35 | 12 | D | 6 DL | 100 | 0 | 100 | 2019-03-13 13:54 | 2019-03-20 23:11 | 627509.0051 |  |  |  | 47719 | 627509 | 429474 |  |  | 0 | 40 | 0 | 7.64 | 5741.21
PH4100XPC#1 | GG\04\006\B | GG | 4 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-03-14 08:17 | 2019-03-16 13:32 | 120485.1327 | 120485 | [7 empty] | 0 | 0 | 32.76 | 10.42 | 5469.27
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 10:15 |  | 0d 10:15 | 2019-03-15 08:45 | 2019-03-15 18:59
TS Fleet 5 | MW\29\008\B | MW | 29 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-03-15 10:36 | 2019-03-16 16:14 | 55599.4575 | 55599 | [7 empty] | 0 | 0 | 5.6 | 10.51 | 5438.93
TS5500Shv | MW\29\010\A | MW | 29 | 10 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-03-15 18:59 | 2019-03-17 10:09 | 47753.0289 | [6 empty] | 47753 | 35047 | 3.51 | 0 | 0 | 11.23 | 5424
TS5500Exc | MW\29\011\X | MW | 29 | 11 | X | 8 Coal Mining | 53.6 | 0 | 53.6 | 2019-03-15 18:59 | 2019-03-16 01:47 | 8559.9749 | [6 empty] | 8560 | 6233 | 0.69 | 0 | 0 | 12.46 | 5170
TS6060#1 | BW\27\011\D | BW | 27 | 11 | D | 8 Coal Mining | 31.7 | 0 | 31.7 | 2019-03-15 18:59 | 2019-03-16 18:03 | 31213.1155 | [6 empty] | 31213 | 23622 | 1.48 | 0 | 0 | 5.83 | 5900
TS5500Exc | DT\26\006\B | DT | 26 | 6 | B | 8 Coal Mining | 45.3 | 0 | 45.3 | 2019-03-16 01:47 | 2019-03-16 19:20 | 22114.251 | [6 empty] | 22114 | 16364 | 1.01 | 0 | 0 | 9.02 | 5544
PH4100XPC#1 | GG\05\002\X1 | GG | 5 | 2 | X1 | 1 Prestrip - Thick | 100 | 0 | 57.6899 | 2019-03-16 13:32 | 2019-03-27 17:31 | 613615.685 | 613616 | [7 empty] | 0 | 0 | 23.21 | 0 | 0
TS Fleet 5 | MW\29\009\B | MW | 29 | 9 | B | 1 Prestrip - Thick | 100 | 72.9144 | 72.9144 | 2019-03-16 16:14 | 2019-03-17 06:51 | 27419.8646 | 27420 | [7 empty] | 0 | 0 | 2.76 | 9.92 | 5512.02
TS6060#1 | GG\03\003\B | GG | 3 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-03-16 18:03 | 2019-03-18 01:02 | 41925.535 | [6 empty] | 41926 | 30406 | 1.21 | 0 | 0 | 11.84 | 5385
TS5500Exc | MW\29\009\B | MW | 29 | 9 | B | 1 Prestrip - Thick | 38.1833 | 27.0856 | 27.0856 | 2019-03-16 19:20 | 2019-03-17 06:51 | 10185.6779 | 10186 | [7 empty] | 0 | 0 | 1.03 | 9.92 | 5512.02
TS Fleet 5 | MW\29\011\A | MW | 29 | 11 | A | 1 Prestrip - Thick | 85.9531 | 85.9531 | 85.9531 | 2019-03-17 06:51 | 2019-03-20 13:10 | 146909.3 | 146909 | [7 empty] | 0 | 0 | 16.88 | 12.11 | 5354.8
TS5500Exc | SC\34\019\D | SC | 34 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-03-17 06:51 | 2019-03-19 15:00 | 70712.5029 | [6 empty] | 70713 | 52594 | 4.38 | 0 | 0 | 7.18 | 5780
TS5500Shv | MW\29\008\B | MW | 29 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-03-17 10:09 | 2019-03-18 18:35 | 39551.0307 | [6 empty] | 39551 | 28952 | 2.91 | 0 | 0 | 10.51 | 5439
TS6060#1 | GG\03\004\B | GG | 3 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-03-18 01:02 | 2019-03-21 12:52 | 113459.884 | [6 empty] | 113460 | 83095 | 3.42 | 0 | 0 | 10.33 | 5497
TS5500Shv | MW\29\009\B | MW | 29 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-03-18 18:35 | 2019-03-20 02:50 | 39323.8557 | [6 empty] | 39324 | 28910 | 2.91 | 0 | 0 | 9.92 | 5512
TS5500Exc | SC\34\020\D | SC | 34 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-03-19 15:00 | 2019-03-22 01:22 | 73516.1922 | [6 empty] | 73516 | 54552 | 4.55 | 0 | 0 | 7.31 | 5770
TS5500Shv | GG\04\003\B | GG | 4 | 3 | B | 1 Prestrip - Thick | 4.7305 | 4.7305 | 4.7305 | 2019-03-20 02:50 | 2019-03-21 16:42 | 40242.1877 | 40242 | [7 empty] | 0 | 0 | 1.79 | 9.39 | 5587.32
TS Fleet 5 | GG\03\003\D | GG | 3 | 3 | D | 1 Prestrip - Thick | 91.307 | 91.307 | 91.307 | 2019-03-20 13:10 | 2019-03-25 16:32 | 231427.7834 | 231428 | [7 empty] | 0 | 0 | 15.94 | 5.22 | 5924.23
DRE2 | DT\28\003\D | DT | 28 | 3 | D | 6 DL | 100 | 100 | 100 | 2019-03-20 18:40 | 2019-03-25 08:37 | 379740.0326 |  |  |  | 16562 | 379740 | 273995 |  |  | 0 | 24.2 | 0 | 6.66 | 5825.88
DRE1 | SC\35\011\D | SC | 35 | 11 | D | 6 DL | 100 | 0 | 100 | 2019-03-20 23:11 | 2019-03-28 09:46 | 632111.6234 |  |  |  | 48069 | 632112 | 432624 |  |  | 0 | 40 | 0 | 7.67 | 5739.73
TS6060#1 | GG\03\005\D | GG | 3 | 5 | D | 8 Coal Mining | 25.3 | 0 | 25.3 | 2019-03-21 12:52 | 2019-03-22 11:51 | 31101.6378 | [6 empty] | 31102 | 23510 | 1.13 | 0 | 0 | 5.59 | 5892
TS5500Shv | GG\04\004\B | GG | 4 | 4 | B | 1 Prestrip - Thick | 11.6061 | 11.6061 | 11.6061 | 2019-03-21 16:42 | 2019-03-25 21:51 | 106791.4163 | 106791 | [7 empty] | 0 | 0 | 5.17 | 10.22 | 5505.47
TS5500Exc | DT\26\006\B | DT | 26 | 6 | B | 8 Coal Mining | 7 | 0 | 7 | 2019-03-22 01:22 | 2019-03-22 04:03 | 3391.3872 | [6 empty] | 3391 | 2510 | 0.16 | 0 | 0 | 9.02 | 5544
TS5500Exc | DT\26\007\B | DT | 26 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-03-22 04:03 | 2019-03-24 06:39 | 63727.4782 | [6 empty] | 63727 | 47477 | 2.97 | 0 | 0 | 8.31 | 5620
PH4100A | MW\32\003\A | MW | 32 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-03-22 07:30 | 2019-03-31 08:57 | 390569.9838 | 390570 | [7 empty] | 0 | 0 | 40.42 | 11.1 | 5386.55
TS6060#1 | GG\04\005\B | GG | 4 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-03-22 11:51 | 2019-03-24 05:58 | 57011.5694 | [6 empty] | 57012 | 41559 | 1.92 | 0 | 0 | 11.33 | 5397
TS6060#1 | GG\04\006\B | GG | 4 | 6 | B | 8 Coal Mining | 51.3 | 0 | 51.3 | 2019-03-24 05:58 | 2019-03-24 11:08 | 6991.0727 | [6 empty] | 6991 | 5122 | 1.82 | 0 | 0 | 10.42 | 5469
TS5500Exc | DT\27\001\D | DT | 27 | 1 | D | 8 Coal Mining | 100 | 0 | 20.5 | 2019-03-24 06:39 | 2019-03-25 05:49 | 29191.3603 | [6 empty] | 29191 | 22018 | 0.9 | 0 | 0 | 5.99 | 5885
TS6060#1 | BW\27\004\D | BW | 27 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2019-03-24 11:08 | 2019-03-27 10:11 | 73318.4936 |  |  | 73318 | [5 empty] | 0 | 0 | 0 | 5.72 | 5909.47
TS5500Exc | SC\34\021\D | SC | 34 | 21 | D | 7 PostStrip | 100 | 0 | 100 | 2019-03-25 05:49 | 2019-03-28 05:21 | 63263.8158 |  |  | 63264 | [5 empty] | 0 | 0 | 0 | 7.34 | 5769.01
DRE2 | DT\26\006\D | DT | 26 | 6 | D | 6 DL | 100 | 100 | 100 | 2019-03-25 08:37 | 2019-03-31 11:39 | 507744.4079 |  |  |  | 30323 | 507744 | 358431 |  |  | 0 | 25.02 | 0 | 6.64 | 5829.56
TS Fleet 5 | GG\03\003\D | GG | 3 | 3 | D | 1 Prestrip - Thick | 8.693 | 8.693 | 8.693 | 2019-03-25 16:32 | 2019-03-26 04:16 | 22033.2751 | 22033 | [7 empty] | 0 | 0 | 1.52 | 5.22 | 5924.23
TS5500Shv | GG\04\004\B | GG | 4 | 4 | B | 1 Prestrip - Thick | 9.1957 | 9.1957 | 9.1957 | 2019-03-25 21:51 | 2019-03-29 06:00 | 84612.8027 | 84613 | [7 empty] | 0 | 0 | 4.09 | 10.22 | 5505.47
TS Fleet 5 | GG\04\003\B | GG | 4 | 3 | B | 1 Prestrip - Thick | 43.5454 | 30.8112 | 30.8112 | 2019-03-26 04:16 | 2019-04-01 | 262110.345 | 262110 | [7 empty] | 0 | 0 | 11.66 | 9.39 | 5587.32
TS6060#1 | RS\11\005\X | RS | 11 | 5 | X | 1 Prestrip - Thick | 52.7446 | 37.324 | 37.324 | 2019-03-27 10:11 | 2019-04-01 | 108932.0678 | 108932 | [7 empty] | 0 | 0 | 10.7 | 13.11 | 5151.24
PH4100XPC#1 | GG\03\004\D | GG | 3 | 4 | D | 1 Prestrip - Thick | 100 | 74.378 | 74.378 | 2019-03-27 17:31 | 2019-04-01 | 228624.3889 | 228624 | [7 empty] | 0 | 0 | 15.15 | 5.36 | 5910.75
TS5500Exc | MW\30\003\B | MW | 30 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-03-28 05:21 | 2019-03-29 21:14 | 35273.7449 | 35274 | [7 empty] | 0 | 0 | 3.53 | 8.48 | 5647.68
DRE1 | SC\35\010\D | SC | 35 | 10 | D | 6 DL | 100 | 0 | 35.023 | 2019-03-28 09:46 | 2019-04-01 | 305224.0554 |  |  |  | 17143 | 305224 | 132857 |  |  | 0 | 40 | 0 | 7.67 | 5739.79
TS5500Shv | GG\05\002\B | GG | 5 | 2 | B | 1 Prestrip - Thick | 31.3267 | 31.3267 | 31.3267 | 2019-03-29 06:00 | 2019-03-31 08:15 | 53872.5269 | 53873 | [7 empty] | 0 | 0 | 2.42 | 11.34 | 5441.06
TS5500Exc | MW\30\004\A | MW | 30 | 4 | A | 1 Prestrip - Thick | 54.2241 | 17.3466 | 17.3466 | 2019-03-29 21:14 | 2019-04-01 | 44887.8473 | 44888 | [7 empty] | 0 | 0 | 4.69 | 10.23 | 5447.78
TS5500Shv | GG\05\002\B | GG | 5 | 2 | B | 1 Prestrip - Thick | 0.37041 | 0.37041 | 0.37041 | 2019-03-31 08:15 | 2019-03-31 08:50 | 636.9935 | 637 | [7 empty] | 0 | 0 | 0.03 | 11.34 | 5441.06
TS5500Shv | GG\03\003\D | GG | 3 | 3 | D | 7 PostStrip | 100 | 0 | 15.968 | 2019-03-31 08:50 | 2019-04-01 | 16242.383 |  |  | 16242 | [5 empty] | 0 | 0 | 0 | 5.22 | 5924.23
PH4100A | MW\31\004\A | MW | 31 | 4 | A | 1 Prestrip - Thick | 100 | 12.617 | 12.617 | 2019-03-31 08:57 | 2019-04-01 | 25960.9871 | 25961 | [7 empty] | 0 | 0 | 2.75 | 10.16 | 5451.93
DRE2 | DT\26\007\D | DT | 26 | 7 | D | 6 DL | 100 | 7.971 | 7.971 | 2019-03-31 11:39 | 2019-04-01 | 42640.1975 |  |  |  | 2546 | 42640 | 30101 |  |  | 0 | 25.58 | 0 | 6.53 | 5838.51
| EOP 63 : 2019\Mar | EOP 63 : 2019 | Mar | [6 empty] | 2019-04-01 | 2019-04-01 |  | 5239621 |  | 191329 | 340208 | 5037138 | 3456622 | 1424700 | 1051283 | 77.82 | 0 | 396.4 | 8.34 | 5663.49
TS Fleet 5 | GG\04\003\B | GG | 4 | 3 | B | 1 Prestrip - Thick | 43.5454 | 12.7342 | 12.7342 | 2019-04-01 | 2019-04-03 07:16 | 108329.526 | 108330 | [7 empty] | 0 | 0 | 4.82 | 9.39 | 5587.32
DRE1 | SC\35\010\D | SC | 35 | 10 | D | 6 DL | 100 | 0 | 64.977 | 2019-04-01 | 2019-04-07 15:58 | 566271.4809 |  |  |  | 31805 | 566271 | 246484 |  |  | 0 | 40 | 0 | 7.67 | 5739.79
PH4100A | MW\31\004\A | MW | 31 | 4 | A | 1 Prestrip - Thick | 100 | 87.383 | 87.383 | 2019-04-01 | 2019-04-05 02:29 | 179800.8169 | 179801 | [7 empty] | 0 | 0 | 19.06 | 10.16 | 5451.93
DRE2 | DT\26\007\D | DT | 26 | 7 | D | 6 DL | 100 | 92.029 | 92.029 | 2019-04-01 | 2019-04-07 00:25 | 492301.035 |  |  |  | 29400 | 492301 | 347529 |  |  | 0 | 25.58 | 0 | 6.53 | 5838.51
PH4100XPC#1 | GG\03\004\D | GG | 3 | 4 | D | 1 Prestrip - Thick | 100 | 25.622 | 25.622 | 2019-04-01 | 2019-04-02 09:21 | 78757.3602 | 78757 | [7 empty] | 0 | 0 | 5.22 | 5.36 | 5910.75
TS5500Shv | GG\03\003\D | GG | 3 | 3 | D | 7 PostStrip | 100 | 0 | 84.032 | 2019-04-01 | 2019-04-04 04:19 | 85475.9054 |  |  | 85476 | [5 empty] | 0 | 0 | 0 | 5.22 | 5924.23
TS6060#1 | RS\11\005\X | RS | 11 | 5 | X | 1 Prestrip - Thick | 52.7446 | 15.4206 | 15.4206 | 2019-04-01 | 2019-04-02 19:25 | 45005.7124 | 45006 | [7 empty] | 0 | 0 | 4.42 | 13.11 | 5151.24
TS5500Exc | MW\30\004\A | MW | 30 | 4 | A | 1 Prestrip - Thick | 54.2241 | 36.8775 | 36.8775 | 2019-04-01 | 2019-04-05 11:53 | 95427.6366 | 95428 | [7 empty] | 0 | 0 | 9.97 | 10.23 | 5447.78
PH4100XPC#1 | GG\04\003\B | GG | 4 | 3 | B | 1 Prestrip - Thick | 100 | 51.7241 | 51.7241 | 2019-04-02 09:21 | 2019-04-10 06:49 | 440015.6931 | 440016 | [7 empty] | 0 | 0 | 19.57 | 9.39 | 5587.32
TS6060#1 | DT\26\006\D | DT | 26 | 6 | D | 8 Coal Mining | 46.5 | 0 | 46.5 | 2019-04-02 19:25 | 2019-04-04 02:44 | 44280.5261 | [6 empty] | 44281 | 33164 | 2.16 | 0 | 0 | 6.64 | 5830
TS Fleet 5 | GG\04\004\B | GG | 4 | 4 | B | 1 Prestrip - Thick | 26.9788 | 26.9788 | 26.9788 | 2019-04-03 07:16 | 2019-04-08 13:55 | 248240.686 | 248241 | [7 empty] | 0 | 0 | 12.01 | 10.22 | 5505.47
TS6060#1 | GG\03\004\D | GG | 3 | 4 | D | 7 PostStrip | 36.7131 | 0 | 36.7131 | 2019-04-04 02:44 | 2019-04-05 12:48 | 36725.6524 |  |  | 36726 | [5 empty] | 0 | 0 | 0 | 5.36 | 5910.75
TS5500Shv | DT\26\006\D | DT | 26 | 6 | D | 8 Coal Mining | 53.5 | 0 | 53.5 | 2019-04-04 04:19 | 2019-04-05 20:17 | 50936.4061 | [6 empty] | 50936 | 38149 | 2.48 | 0 | 0 | 6.64 | 5830
PH4100A | MW\32\004\A | MW | 32 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-04-05 02:29 | 2019-04-08 23:51 | 169665.2372 | 169665 | [7 empty] | 0 | 0 | 17.93 | 10.12 | 5453.59
TS5500Exc | DT\27\001\D | DT | 27 | 1 | D | 8 Coal Mining | 100 | 0 | 79.5 | 2019-04-05 11:53 | 2019-04-09 05:37 | 113031.8896 | [6 empty] | 113032 | 85255 | 3.48 | 0 | 0 | 5.99 | 5885
TS6060#1 | BW\27\004\D | BW | 27 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-04-05 12:48 | 2019-04-08 03:57 | 89295.3547 | [6 empty] | 89295 | 67309 | 4.62 | 0 | 0 | 5.72 | 5909
TS5500Shv | GG\03\004\D | GG | 3 | 4 | D | 7 PostStrip | 63.2869 | 0 | 63.2869 | 2019-04-05 20:17 | 2019-04-08 04:49 | 63308.4539 |  |  | 63308 | [5 empty] | 0 | 0 | 0 | 5.36 | 5910.75
DRE2 | DT\28\001\D | DT | 28 | 1 | D | 6 DL | 100 | 0 | 100 | 2019-04-07 00:25 | 2019-04-19 15:35 | 1033384.573 |  |  |  | 77245 | 1033385 | 710974 |  |  | 0 | 30 | 0 | 6.01 | 5884.9
DRE1 | SC\35\015\D | SC | 35 | 15 | D | 6 DL | 100 | 0 | 100 | 2019-04-07 15:58 | 2019-04-15 14:36 | 674764.8774 |  |  |  | 44290 | 674765 | 447820 |  |  | 0 | 36.01 | 0 | 7.02 | 5793.39
TS6060#1 | DT\26\007\D | DT | 26 | 7 | D | 8 Coal Mining | 3.8 | 0 | 3.8 | 2019-04-08 03:57 | 2019-04-08 06:37 | 3785.6034 | [6 empty] | 3786 | 2844 | 0.18 | 0 | 0 | 6.53 | 5839
TS5500Shv | DT\26\007\D | DT | 26 | 7 | D | 8 Coal Mining | 96.2 | 0 | 96.2 | 2019-04-08 04:49 | 2019-04-11 07:18 | 94893.3649 | [6 empty] | 94893 | 71297 | 4.46 | 0 | 0 | 6.53 | 5839
TS6060#1 | GG\03\003\D | GG | 3 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-04-08 06:37 | 2019-04-11 17:08 | 116666.5493 | [6 empty] | 116667 | 88120 | 4.41 | 0 | 0 | 5.22 | 5924
TS Fleet 5 | MW\29\010\B | MW | 29 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-04-08 13:55 | 2019-04-09 04:16 | 28114.376 | 28114 | [7 empty] | 0 | 0 | 2.81 | 9.03 | 5620.8
PH4100A | MW\31\005\A | MW | 31 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-04-08 23:51 | 2019-04-12 07:37 | 141907.4788 | 141907 | [7 empty] | 0 | 0 | 14.92 | 10.25 | 5438.91
TS Fleet 5 | MW\29\011\A | MW | 29 | 11 | A | 1 Prestrip - Thick | 14.0469 | 14.0469 | 14.0469 | 2019-04-09 04:16 | 2019-04-09 16:31 | 24008.6471 | 24009 | [7 empty] | 0 | 0 | 2.76 | 12.11 | 5354.8
TS5500Exc | MW\29\010\B | MW | 29 | 10 | B | 8 Coal Mining | 71.8 | 0 | 71.8 | 2019-04-09 05:37 | 2019-04-10 03:29 | 27531.4301 | [6 empty] | 27531 | 20399 | 2.04 | 0 | 0 | 9.03 | 5621
TS Fleet 5 | GG\05\002\B | GG | 5 | 2 | B | 1 Prestrip - Thick | 30.5461 | 30.5461 | 30.5461 | 2019-04-09 16:31 | 2019-04-10 19:19 | 52530.2023 | 52530 | [7 empty] | 0 | 0 | 2.36 | 11.34 | 5441.06
TS5500Exc | MW\29\011\A | MW | 29 | 11 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2019-04-10 03:29 | 2019-04-10 19:24 | 20061.6137 | [6 empty] | 20062 | 14662 | 1.77 | 0 | 0 | 12.11 | 5355
PH4100XPC#1 | GG\04\004\B | GG | 4 | 4 | B | 1 Prestrip - Thick | 100 | 52.2195 | 52.2195 | 2019-04-10 06:49 | 2019-04-19 00:16 | 480489.1779 | 480489 | [7 empty] | 0 | 0 | 23.24 | 10.22 | 5505.47
TS Fleet 5 | GG\05\005\B | GG | 5 | 5 | B | 1 Prestrip - Thick | 3.7223 | 3.7223 | 3.7223 | 2019-04-10 19:19 | 2019-04-11 17:52 | 44198.5961 | 44199 | [7 empty] | 0 | 0 | 1.94 | 10.67 | 5432.09
TS5500Exc | GG\03\005\D | GG | 3 | 5 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2019-04-10 19:24 | 2019-04-12 21:56 | 63649.7112 | [6 empty] | 63650 | 48112 | 2.31 | 0 | 0 | 5.59 | 5892
TS5500Shv | MW\29\010\B | MW | 29 | 10 | B | 8 Coal Mining | 28.2 | 0 | 28.2 | 2019-04-11 07:18 | 2019-04-11 15:47 | 10809.1565 | [6 empty] | 10809 | 8009 | 0.8 | 0 | 0 | 9.03 | 5621
TS5500Shv | MW\29\011\A | MW | 29 | 11 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2019-04-11 15:47 | 2019-04-12 07:02 | 19421.3495 | [6 empty] | 19421 | 14194 | 1.72 | 0 | 0 | 12.11 | 5355
TS6060#1 | GG\03\004\D | GG | 3 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-04-11 17:08 | 2019-04-15 01:52 | 114155.4255 | [6 empty] | 114155 | 86293 | 4.32 | 0 | 0 | 5.36 | 5911
TS Fleet 5 | GG\05\005\B | GG | 5 | 5 | B | 1 Prestrip - Thick | 39.0888 | 39.0888 | 39.0888 | 2019-04-11 17:52 | 2019-04-21 14:40 | 464137.4026 | 464137 | [7 empty] | 0 | 0 | 20.39 | 10.67 | 5432.09
TS5500Shv | MW\31\003\A | MW | 31 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-04-12 07:02 | 2019-04-13 10:49 | 35393.3069 | [6 empty] | 35393 | 25912 | 2.66 | 0 | 0 | 10.82 | 5406
PH4100A | MW\32\005\A | MW | 32 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-04-12 07:37 | 2019-04-15 22:52 | 155265.3565 | 155265 | [7 empty] | 0 | 0 | 16.37 | 10.75 | 5398.21
TS5500Exc | DT\27\002\D | DT | 27 | 2 | D | 8 Coal Mining | 38.8 | 0 | 38.8 | 2019-04-12 21:56 | 2019-04-14 21:14 | 59566.8154 | [6 empty] | 59567 | 44939 | 1.9 | 0 | 0 | 5.99 | 5887
TS5500Shv | MW\31\004\A | MW | 31 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-04-13 10:49 | 2019-04-15 01:41 | 49520.6859 | [6 empty] | 49521 | 36423 | 3.64 | 0 | 0 | 10.16 | 5452
TS5500Exc | SC\34\021\D | SC | 34 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-04-14 21:14 | 2019-04-17 10:48 | 77557.7899 | [6 empty] | 77558 | 57465 | 4.79 | 0 | 0 | 7.34 | 5769
TS5500Shv | MW\32\003\A | MW | 32 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-04-15 01:41 | 2019-04-15 21:12 | 24873.9524 | [6 empty] | 24874 | 18175 | 1.9 | 0 | 0 | 11.1 | 5387
TS6060#1 | GG\04\002\D | GG | 4 | 2 | D | 8 Coal Mining | 63.8 | 0 | 63.8 | 2019-04-15 01:52 | 2019-04-17 09:07 | 78116.1552 | [6 empty] | 78116 | 58955 | 2.95 | 0 | 0 | 5.42 | 5909
DRE1 | SC\35\016\D | SC | 35 | 16 | D | 6 DL | 100 | 0 | 100 | 2019-04-15 14:36 | 2019-04-25 10:35 | 835324.6538 |  |  |  | 59407 | 835325 | 600668 |  |  | 0 | 38.92 | 0 | 6.73 | 5819.17
TS5500Shv | MW\32\004\A | MW | 32 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-04-15 21:12 | 2019-04-17 10:43 | 47790.3045 | [6 empty] | 47790 | 35151 | 3.49 | 0 | 0 | 10.12 | 5454
PH4100A | MW\31\006\A | MW | 31 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-04-15 22:52 | 2019-04-21 13:50 | 230139.5678 | 230140 | [7 empty] | 0 | 0 | 22.7 | 10.51 | 5427.04
TS6060#1 | GG\04\003\B | GG | 4 | 3 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2019-04-17 09:07 | 2019-04-18 21:15 | 51106.8959 | [6 empty] | 51107 | 37525 | 1.87 | 0 | 0 | 9.39 | 5587
TS5500Shv | MW\31\005\A | MW | 31 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-04-17 10:43 | 2019-04-18 19:32 | 41811.2711 | [6 empty] | 41811 | 30814 | 3.14 | 0 | 0 | 10.25 | 5439
TS5500Exc | SC\35\011\D | SC | 35 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-04-17 10:48 | 2019-04-19 23:15 | 76131.9227 | [6 empty] | 76132 | 56854 | 4.74 | 0 | 0 | 7.67 | 5740
TS5500Shv | GG\04\003\B | GG | 4 | 3 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2019-04-18 19:32 | 2019-04-20 07:41 | 46046.8072 | [6 empty] | 46047 | 33810 | 1.68 | 0 | 0 | 9.39 | 5587
TS6060#1 | RS\11\006\X | RS | 11 | 6 | X | 1 Prestrip - Thick | 54.4403 | 54.4403 | 54.4403 | 2019-04-18 21:15 | 2019-04-26 07:44 | 185802.5561 | 185803 | [7 empty] | 0 | 0 | 18.42 | 11.27 | 5260.22
PH4100XPC#1 | GG\04\005\D | GG | 4 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-04-19 00:16 | 2019-04-23 15:22 | 262273.5708 | 262274 | [7 empty] | 0 | 0 | 17.95 | 5.61 | 5890.85
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2019-04-19 15:35 | 2019-04-21 15:35
TS5500Exc | SC\35\012\D | SC | 35 | 12 | D | 8 Coal Mining | 100 | 0 | 53.4 | 2019-04-19 23:15 | 2019-04-21 06:26 | 39281.4608 | [6 empty] | 39281 | 29334 | 2.44 | 0 | 0 | 7.64 | 5741
TS5500Shv | MW\32\005\A | MW | 32 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-04-20 07:41 | 2019-04-21 06:12 | 28695.7765 | [6 empty] | 28696 | 21110 | 2.17 | 0 | 0 | 10.75 | 5398
TS5500Shv | GG\04\004\B | GG | 4 | 4 | B | 8 Coal Mining | 32.2 | 0 | 0.3 | 2019-04-21 06:12 | 2019-04-21 06:26 | 288.475 | [6 empty] | 288 | 211 | 0.01 | 0 | 0 | 10.22 | 5505
TS5500Shv | GG\04\003\D | GG | 4 | 3 | D | 1 Prestrip - Thick | 22.5904 | 22.5904 | 22.5904 | 2019-04-21 06:26 | 2019-04-23 21:26 | 70561.1793 | 70561 | [7 empty] | 0 | 0 | 4.66 | 5.31 | 5916.48
TS5500Exc | SC\35\010\D | SC | 35 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2019-04-21 06:26 | 2019-04-24 03:37 | 61187.1238 |  |  | 61187 | [5 empty] | 0 | 0 | 0 | 7.67 | 5739.79
PH4100A | MW\32\006\A | MW | 32 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-04-21 13:50 | 2019-04-27 03:27 | 227945.9175 | 227946 | [7 empty] | 0 | 0 | 22.94 | 10.39 | 5436.99
TS Fleet 5 | MW\29\011\B | MW | 29 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-04-21 14:40 | 2019-04-22 01:08 | 20519.6655 | 20520 | [7 empty] | 0 | 0 | 2.52 | 8.81 | 5642.1
DRE2 | BW\28\011\D | BW | 28 | 11 | D | 6 DL | 100 | 100 | 100 | 2019-04-21 15:35 | 2019-04-27 03:11 | 448522.2859 |  |  |  | 19562 | 448522 | 323624 |  |  | 0 | 21.43 | 0 | 5.83 | 5899.88
TS Fleet 5 | GG\04\003\D | GG | 4 | 3 | D | 1 Prestrip - Thick | 30.9873 | 30.9873 | 30.9873 | 2019-04-22 01:08 | 2019-04-24 02:31 | 96789.1012 | 96789 | [7 empty] | 0 | 0 | 6.39 | 5.31 | 5916.48
PH4100XPC#1 | GG\04\003\D | GG | 4 | 3 | D | 1 Prestrip - Thick | 100 | 46.4223 | 46.4223 | 2019-04-23 15:22 | 2019-04-26 04:48 | 145000.4745 | 145000 | [7 empty] | 0 | 0 | 9.58 | 5.31 | 5916.48
TS5500Shv | GG\04\005\D | GG | 4 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2019-04-23 21:26 | 2019-04-27 15:51 | 101260.3635 |  |  | 101260 | [5 empty] | 0 | 0 | 0 | 5.61 | 5890.85
TS Fleet 5 | GG\06\002\X1 | GG | 6 | 2 | X1 | 1 Prestrip - Thick | 42.6833 | 0 | 17.2414 | 2019-04-24 02:31 | 2019-05-01 | 324331.7973 | 324332 | [7 empty] | 0 | 0 | 12.53 | 0 | 0
TS5500Exc | MW\30\004\A | MW | 30 | 4 | A | 1 Prestrip - Thick | 45.7759 | 45.7759 | 45.7759 | 2019-04-24 03:37 | 2019-04-29 17:33 | 118454.0718 | 118454 | [7 empty] | 0 | 0 | 12.38 | 10.23 | 5447.78
DRE1 | SC\35\017\D | SC | 35 | 17 | D | 6 DL | 100 | 0 | 92.6096 | 2019-04-25 10:35 | 2019-05-01 | 472222.9879 |  |  |  | 26951 | 472223 | 358066 |  |  | 0 | 34.17 | 0 | 7.06 | 5790.97
PH4100XPC#1 | GG\05\002\B | GG | 5 | 2 | B | 1 Prestrip - Thick | 100 | 37.7568 | 37.7568 | 2019-04-26 04:48 | 2019-04-27 08:18 | 64930.3925 | 64930 | [7 empty] | 0 | 0 | 2.91 | 11.34 | 5441.06
TS6060#1 | RS\11\006\X | RS | 11 | 6 | X | 1 Prestrip - Thick | 45.5597 | 34.2378 | 34.2378 | 2019-04-26 07:44 | 2019-05-01 | 116852.2835 | 116852 | [7 empty] | 0 | 0 | 11.58 | 11.27 | 5260.22
DRE2 | BW\28\010\D | BW | 28 | 10 | D | 6 DL | 100 | 73.2761 | 73.2761 | 2019-04-27 03:11 | 2019-05-01 | 316371.3063 |  |  |  | 13798 | 316371 | 228273 |  |  | 0 | 20.65 | 0 | 5.62 | 5920.18
PH4100A | MW\31\007\A | MW | 31 | 7 | A | 1 Prestrip - Thick | 100 | 55.0232 | 55.0232 | 2019-04-27 03:27 | 2019-05-01 | 157961.8236 | 157962 | [7 empty] | 0 | 0 | 15.44 | 10.32 | 5453.14
PH4100XPC#1 | GG\05\003\X1 | GG | 5 | 3 | X1 | 1 Prestrip - Thick | 100 | 38.4815 | 38.4815 | 2019-04-27 08:18 | 2019-05-01 | 202206.2988 | 202206 | [7 empty] | 0 | 0 | 9.51 | 9.4 | 5487.25
TS5500Shv | GG\04\003\D | GG | 4 | 3 | D | 7 PostStrip | 100 | 0 | 89.8496 | 2019-04-27 15:51 | 2019-05-01 | 89766.9714 |  |  | 89767 | [5 empty] | 0 | 0 | 0 | 5.31 | 5916.48
TS5500Exc | MW\30\005\A | MW | 30 | 5 | A | 1 Prestrip - Thick | 65.1722 | 17.517 | 17.517 | 2019-04-29 17:33 | 2019-05-01 | 26974.9845 | 26975 | [7 empty] | 0 | 0 | 2.84 | 9.9 | 5469.37
| EOP 64 : 2019\Apr | EOP 64 : 2019 | Apr | [6 empty] | 2019-05-01 | 2019-05-01 |  | 5006638 |  | 437724 | 302458 | 4839163 | 3263437 | 1424700 | 1064487 | 72.11 | 0 | 350.15 | 7.3 | 5750.89
TS Fleet 5 | GG\06\002\X1 | GG | 6 | 2 | X1 | 1 Prestrip - Thick | 42.6833 | 0 | 25.4418 | 2019-05-01 | 2019-05-11 00:44 | 478590.9538 | 478591 | [7 empty] | 0 | 0 | 18.49 | 0 | 0
DRE1 | SC\35\017\D | SC | 35 | 17 | D | 6 DL | 100 | 0 | 7.3904 | 2019-05-01 | 2019-05-01 14:59 | 37684.024 |  |  |  | 2151 | 37684 | 28574 |  |  | 0 | 34.17 | 0 | 7.06 | 5790.97
PH4100A | MW\31\007\A | MW | 31 | 7 | A | 1 Prestrip - Thick | 100 | 44.9768 | 44.9768 | 2019-05-01 | 2019-05-04 02:37 | 129120.5058 | 129121 | [7 empty] | 0 | 0 | 12.62 | 10.32 | 5453.14
DRE2 | BW\28\010\D | BW | 28 | 10 | D | 6 DL | 100 | 26.7239 | 26.7239 | 2019-05-01 | 2019-05-02 09:51 | 115381.3078 |  |  |  | 5032 | 115381 | 83252 |  |  | 0 | 20.65 | 0 | 5.62 | 5920.18
PH4100XPC#1 | GG\05\003\X1 | GG | 5 | 3 | X1 | 1 Prestrip - Thick | 100 | 16.2187 | 16.2187 | 2019-05-01 | 2019-05-02 12:27 | 85223.18 | 85223 | [7 empty] | 0 | 0 | 4.01 | 9.4 | 5487.25
TS5500Shv | GG\04\003\D | GG | 4 | 3 | D | 7 PostStrip | 100 | 0 | 10.1504 | 2019-05-01 | 2019-05-01 08:55 | 10141.0741 |  |  | 10141 | [5 empty] | 0 | 0 | 0 | 5.31 | 5916.48
TS6060#1 | RS\11\006\X | RS | 11 | 6 | X | 1 Prestrip - Thick | 45.5597 | 11.3219 | 11.3219 | 2019-05-01 | 2019-05-02 12:35 | 38641.1728 | 38641 | [7 empty] | 0 | 0 | 3.83 | 11.27 | 5260.22
TS5500Exc | MW\30\005\A | MW | 30 | 5 | A | 1 Prestrip - Thick | 65.1722 | 47.6552 | 47.6552 | 2019-05-01 | 2019-05-04 10:49 | 73385.9599 | 73386 | [7 empty] | 0 | 0 | 7.72 | 9.9 | 5469.37
TS5500Shv | MW\29\011\B | MW | 29 | 11 | B | 8 Coal Mining | 54 | 0 | 54 | 2019-05-01 08:55 | 2019-05-01 21:29 | 16229.0587 | [6 empty] | 16229 | 12067 | 1.5 | 0 | 0 | 8.81 | 5642
DRE1 | SC\35\018\D | SC | 35 | 18 | D | 6 DL | 100 | 0 | 100 | 2019-05-01 14:59 | 2019-05-11 09:12 | 589081.1906 |  |  |  | 41894 | 589081 | 423598 |  |  | 0 | 38.05 | 0 | 7.25 | 5774.51
TS5500Shv | GG\04\004\B | GG | 4 | 4 | B | 8 Coal Mining | 32.2 | 0 | 32 | 2019-05-01 21:29 | 2019-05-02 22:07 | 31841.8619 | [6 empty] | 31842 | 23313 | 1.17 | 0 | 0 | 10.22 | 5505
DRE2 | BW\28\009\D | BW | 28 | 9 | D | 6 DL | 100 | 100 | 100 | 2019-05-02 09:51 | 2019-05-07 15:21 | 427788.2414 |  |  |  | 18657 | 427788 | 308664 |  |  | 0 | 20.46 | 0 | 5.24 | 5953.17
PH4100XPC#1 | GG\05\004\X1 | GG | 5 | 4 | X1 | 1 Prestrip - Thick | 100 | 54.644 | 54.644 | 2019-05-02 12:27 | 2019-05-08 03:42 | 315442.6081 | 315443 | [7 empty] | 0 | 0 | 14.36 | 10.82 | 5357.93
TS6060#1 | GG\04\004\B | GG | 4 | 4 | B | 8 Coal Mining | 67.8 | 0 | 67.8 | 2019-05-02 12:35 | 2019-05-04 11:40 | 67510.3016 | [6 empty] | 67510 | 49427 | 2.47 | 0 | 0 | 10.22 | 5505
TS5500Shv | GG\04\005\D | GG | 4 | 5 | D | 8 Coal Mining | 26.9 | 0 | 26.9 | 2019-05-02 22:07 | 2019-05-03 22:34 | 31590.6778 | [6 empty] | 31591 | 23881 | 1.19 | 0 | 0 | 5.61 | 5891
TS5500Shv | MW\31\006\A | MW | 31 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-05-03 22:34 | 2019-05-05 06:44 | 41574.8718 | [6 empty] | 41575 | 30665 | 3.01 | 0 | 0 | 10.51 | 5427
PH4100A | MW\32\007\A | MW | 32 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-05-04 02:37 | 2019-05-10 19:14 | 278193.4476 | 278193 | [7 empty] | 0 | 0 | 27.53 | 10.15 | 5473.97
TS5500Exc | MW\29\011\B | MW | 29 | 11 | B | 8 Coal Mining | 46 | 0 | 46 | 2019-05-04 10:49 | 2019-05-04 21:49 | 13846.5808 | [6 empty] | 13847 | 10295 | 1.28 | 0 | 0 | 8.81 | 5642
TS6060#1 | GG\04\005\D | GG | 4 | 5 | D | 8 Coal Mining | 29.8 | 0 | 29.8 | 2019-05-04 11:40 | 2019-05-05 12:06 | 35062.1808 | [6 empty] | 35062 | 26505 | 1.33 | 0 | 0 | 5.61 | 5891
TS5500Exc | SC\35\012\D | SC | 35 | 12 | D | 8 Coal Mining | 100 | 0 | 46.6 | 2019-05-04 21:49 | 2019-05-06 01:04 | 34337.9643 | [6 empty] | 34338 | 25642 | 2.14 | 0 | 0 | 7.64 | 5741
TS5500Shv | MW\32\006\A | MW | 32 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-05-05 06:44 | 2019-05-06 15:24 | 42209.8761 | [6 empty] | 42210 | 31151 | 3.09 | 0 | 0 | 10.39 | 5437
TS6060#1 | BW\28\011\D | BW | 28 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-05-05 12:06 | 2019-05-08 07:59 | 97356.5295 | [6 empty] | 97357 | 73919 | 4.62 | 0 | 0 | 5.83 | 5900
TS5500Exc | SC\35\013\D | SC | 35 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-05-06 01:04 | 2019-05-08 10:53 | 72816.3324 | [6 empty] | 72816 | 54506 | 4.54 | 0 | 0 | 7.73 | 5733
TS5500Shv | GG\04\003\D | GG | 4 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-05-06 15:24 | 2019-05-10 10:05 | 117172.168 | [6 empty] | 117172 | 88432 | 4.42 | 0 | 0 | 5.31 | 5916
DRE2 | BW\28\008\D | BW | 28 | 8 | D | 6 DL | 100 | 100 | 100 | 2019-05-07 15:21 | 2019-05-12 21:39 | 430528.3128 |  |  |  | 18777 | 430528 | 310641 |  |  | 0 | 20.59 | 0 | 5.09 | 5965.78
PH4100XPC#1 | GG\04\004\D | GG | 4 | 4 | D | 1 Prestrip - Thick | 100 | 79.4755 | 79.4755 | 2019-05-08 03:42 | 2019-05-12 07:52 | 239694.9405 | 239695 | [7 empty] | 0 | 0 | 15.96 | 5.42 | 5905.01
TS6060#1 | BW\28\010\D | BW | 28 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-05-08 07:59 | 2019-05-11 08:30 | 104002.9944 | [6 empty] | 104003 | 79021 | 4.94 | 0 | 0 | 5.62 | 5920
TS5500Exc | SC\35\014\D | SC | 35 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-05-08 10:53 | 2019-05-11 11:50 | 91898.3368 | [6 empty] | 91898 | 68842 | 4.36 | 0 | 0 | 7.59 | 5745
TS5500Shv | MW\31\007\A | MW | 31 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-05-10 10:05 | 2019-05-11 22:02 | 46448.936 | [6 empty] | 46449 | 34304 | 3.31 | 0 | 0 | 10.32 | 5453
PH4100A | MW\31\008\A | MW | 31 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-05-10 19:14 | 2019-05-19 21:26 | 382509.6382 | 382510 | [7 empty] | 0 | 0 | 36.92 | 11.14 | 5384.52
TS Fleet 5 | GG\04\004\D | GG | 4 | 4 | D | 1 Prestrip - Thick | 44.7216 | 20.5245 | 20.5245 | 2019-05-11 00:44 | 2019-05-12 07:52 | 61901.0692 | 61901 | [7 empty] | 0 | 0 | 4.12 | 5.42 | 5905.01
TS6060#1 | BW\28\009\D | BW | 28 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-05-11 08:30 | 2019-05-14 07:34 | 101918.1401 | [6 empty] | 101918 | 77439 | 4.84 | 0 | 0 | 5.24 | 5953
DRE1 | SC\35\019\D | SC | 35 | 19 | D | 6 DL | 100 | 0 | 100 | 2019-05-11 09:12 | 2019-05-21 07:29 | 599281.4706 |  |  |  | 42620 | 599281 | 430933 |  |  | 0 | 38.99 | 0 | 7.23 | 5776.8
TS5500Exc | SC\35\010\D | SC | 35 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-05-11 11:50 | 2019-05-14 01:45 | 77982.8156 | [6 empty] | 77983 | 58330 | 4.86 | 0 | 0 | 7.67 | 5740
TS5500Shv | MW\32\007\A | MW | 32 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-05-11 22:02 | 2019-05-13 08:36 | 44681.7514 | [6 empty] | 44682 | 33027 | 3.28 | 0 | 0 | 10.15 | 5474
TS Fleet 5 | GG\06\005\X2 | GG | 6 | 5 | X2 | 1 Prestrip - Thick | 42.8179 | 0 | 42.8179 | 2019-05-12 07:52 | 2019-05-22 15:58 | 493234.3633 | 493234 | [7 empty] | 0 | 0 | 19.34 | 0 | 0
PH4100XPC#1 | GG\05\005\B | GG | 5 | 5 | B | 1 Prestrip - Thick | 100 | 57.1889 | 57.1889 | 2019-05-12 07:52 | 2019-05-23 17:50 | 679056.008 | 679056 | [7 empty] | 0 | 0 | 29.83 | 10.67 | 5432.09
DRE2 | BW\28\007\D | BW | 28 | 7 | D | 6 DL | 100 | 100 | 100 | 2019-05-12 21:39 | 2019-05-18 06:51 | 440367.2563 |  |  |  | 19206 | 440367 | 317740 |  |  | 0 | 21.06 | 0 | 5.25 | 5952.26
TS5500Shv | GG\04\004\D | GG | 4 | 4 | D | 7 PostStrip | 29.4422 | 0 | 29.4422 | 2019-05-13 08:36 | 2019-05-14 10:31 | 29436.3091 |  |  | 29436 | [5 empty] | 0 | 0 | 0 | 5.42 | 5905.01
TS5500Exc | SC\35\015\D | SC | 35 | 15 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-05-14 01:45 | 2019-05-16 13:54 | 75766.0326 | [6 empty] | 75766 | 56801 | 4.2 | 0 | 0 | 7.02 | 5793
TS6060#1 | GG\04\005\D | GG | 4 | 5 | D | 8 Coal Mining | 19.4 | 0 | 19.4 | 2019-05-14 07:34 | 2019-05-14 23:28 | 22796.2097 | [6 empty] | 22796 | 17233 | 0.86 | 0 | 0 | 5.61 | 5891
TS5500Shv | GG\04\004\D | GG | 4 | 4 | D | 7 PostStrip | 70.5578 | 0 | 70.5578 | 2019-05-14 10:31 | 2019-05-17 00:37 | 70543.6322 |  |  | 70544 | [5 empty] | 0 | 0 | 0 | 5.42 | 5905.01
TS6060#1 | GG\04\006\B | GG | 4 | 6 | B | 8 Coal Mining | 25.6 | 0 | 25.6 | 2019-05-14 23:28 | 2019-05-15 01:54 | 3494.2259 | [6 empty] | 3494 | 2560 | 0.91 | 0 | 0 | 10.42 | 5469
TS6060#1 | GG\05\002\B | GG | 5 | 2 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2019-05-15 01:54 | 2019-05-16 02:25 | 35173.183 | [6 empty] | 35173 | 25558 | 1.21 | 0 | 0 | 11.34 | 5441
TS6060#1 | BW\28\008\D | BW | 28 | 8 | D | 8 Coal Mining | 100 | 0 | 93.5 | 2019-05-16 02:25 | 2019-05-18 20:11 | 94313.9111 | [6 empty] | 94314 | 71662 | 4.48 | 0 | 0 | 5.09 | 5966
TS5500Exc | SC\35\016\D | SC | 35 | 16 | D | 8 Coal Mining | 100 | 0 | 91 | 2019-05-16 13:54 | 2019-05-18 20:11 | 68375.3394 | [6 empty] | 68375 | 51262 | 3.95 | 0 | 0 | 6.73 | 5819
TS5500Shv | GG\04\004\D | GG | 4 | 4 | D | 8 Coal Mining | 67.8 | 0 | 49.6 | 2019-05-17 00:37 | 2019-05-18 20:11 | 56299.7203 | [6 empty] | 56300 | 42525 | 2.13 | 0 | 0 | 5.42 | 5905
DRE2 | BW\28\006\D | BW | 28 | 6 | D | 6 DL | 100 | 100 | 100 | 2019-05-18 06:51 | 2019-05-23 17:52 | 446593.2004 |  |  |  | 19477 | 446593 | 322232 |  |  | 0 | 21.37 | 0 | 5.48 | 5930.68
TS6060#1 | RS\11\007\X | RS | 11 | 7 | X | 1 Prestrip - Thick | 40.0899 | 40.0899 | 40.0899 | 2019-05-18 20:11 | 2019-05-28 03:15 | 236720.8389 | 236721 | [7 empty] | 0 | 0 | 15.65 | 11.6 | 5227.04
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 13d 03:48 |  | 13d 03:48 | 2019-05-18 20:11 | 2019-06-01
TS5500Exc | MW\30\005\A | MW | 30 | 5 | A | 1 Prestrip - Thick | 34.8278 | 34.8278 | 34.8278 | 2019-05-18 20:11 | 2019-05-21 08:43 | 53632.5035 | 53633 | [7 empty] | 0 | 0 | 5.64 | 9.9 | 5469.37
PH4100A | MW\32\008\A | MW | 32 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-05-19 21:26 | 2019-05-28 20:08 | 377288.0182 | 377288 | [7 empty] | 0 | 0 | 37.31 | 11.33 | 5379.59
DRE1 | SC\35\020\D | SC | 35 | 20 | D | 6 DL | 100 | 0 | 100 | 2019-05-21 07:29 | 2019-05-31 17:39 | 629182.1812 |  |  |  | 47847 | 629182 | 430619 |  |  | 0 | 40 | 0 | 7.13 | 5785.74
TS5500Exc | MW\30\006\A | MW | 30 | 6 | A | 1 Prestrip - Thick | 38.5513 | 38.5513 | 38.5513 | 2019-05-21 08:43 | 2019-05-25 13:05 | 89346.3628 | 89346 | [7 empty] | 0 | 0 | 8.77 | 10.71 | 5409.75
TS Fleet 5 | MW\30\011\X | MW | 30 | 11 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-05-22 15:58 | 2019-05-29 20:08 | 342238.0455 | 342238 | [7 empty] | 0 | 0 | 36.94 | 12.4 | 5176.86
PH4100XPC#1 | GG\06\002\X1 | GG | 6 | 2 | X1 | 1 Prestrip - Thick | 100 | 0 | 26.1417 | 2019-05-23 17:50 | 2019-06-01 | 491756.0954 | 491756 | [7 empty] | 0 | 0 | 19 | 0 | 0
DRE2 | BW\28\005\D | BW | 28 | 5 | D | 6 DL | 100 | 92.6484 | 92.6484 | 2019-05-23 17:52 | 2019-06-01 | 675340.0813 |  |  |  | 25480 | 675340 | 322456 |  |  | 0 | 22.56 | 0 | 5.69 | 5912.06
TS5500Exc | MW\30\006\A | MW | 30 | 6 | A | 1 Prestrip - Thick | 61.4487 | 59.5037 | 59.5037 | 2019-05-25 13:05 | 2019-06-01 | 137905.5726 | 137906 | [7 empty] | 0 | 0 | 13.54 | 10.71 | 5409.75
TS6060#1 | RS\11\007\X | RS | 11 | 7 | X | 1 Prestrip - Thick | 59.9101 | 16.669 | 16.669 | 2019-05-28 03:15 | 2019-06-01 | 98426.0392 | 98426 | [7 empty] | 0 | 0 | 6.51 | 11.6 | 5227.04
PH4100A | MW\31\009\A | MW | 31 | 9 | A | 1 Prestrip - Thick | 100 | 28.8109 | 28.8109 | 2019-05-28 20:08 | 2019-06-01 | 133127.6244 | 133128 | [7 empty] | 0 | 0 | 13.16 | 12.04 | 5326.87
TS Fleet 5 | MW\31\003\B | MW | 31 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-05-29 20:08 | 2019-05-30 11:42 | 30968.1348 | 30968 | [7 empty] | 0 | 0 | 3.13 | 8.57 | 5650.68
TS Fleet 5 | MW\31\004\B | MW | 31 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-05-30 11:42 | 2019-05-31 03:59 | 32348.1946 | 32348 | [7 empty] | 0 | 0 | 3.22 | 8.72 | 5629.49
TS Fleet 5 | MW\31\005\B | MW | 31 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-05-31 03:59 | 2019-05-31 22:12 | 36243.6704 | 36244 | [7 empty] | 0 | 0 | 3.62 | 8.85 | 5614.58
DRE1 | SC\35\021\D | SC | 35 | 21 | D | 6 DL | 100 | 0 | 2.8391 | 2019-05-31 17:39 | 2019-06-01 | 15968.3336 |  |  |  | 1136 | 15968 | 11483 |  |  | 0 | 37.3 | 0 | 7.31 | 5770.29
TS Fleet 5 | MW\31\006\B | MW | 31 | 6 | B | 1 Prestrip - Thick | 100 | 6.8156 | 6.8156 | 2019-05-31 22:12 | 2019-06-01 | 3547.5683 | 3548 | [7 empty] | 0 | 0 | 0.35 | 8.82 | 5623.97
| EOP 65 : 2019\May | EOP 65 : 2019 | May | [6 empty] | 2019-06-01 | 2019-06-01 |  | 5318543 |  | 110121 | 242277 | 4407196 | 2990191 | 1424700 | 1068365 | 74.06 | 0 | 361.57 | 7.2 | 5762.92
TS Fleet 5 | MW\31\006\B | MW | 31 | 6 | B | 1 Prestrip - Thick | 100 | 93.1844 | 93.1844 | 2019-06-01 | 2019-06-02 00:23 | 48502.9065 | 48503 | [7 empty] | 0 | 0 | 4.8 | 8.82 | 5623.97
DRE1 | SC\35\021\D | SC | 35 | 21 | D | 6 DL | 100 | 0 | 97.1609 | 2019-06-01 | 2019-06-07 10:23 | 546474.0117 |  |  |  | 38864 | 546474 | 392960 |  |  | 0 | 37.3 | 0 | 7.31 | 5770.29
PH4100A | MW\31\009\A | MW | 31 | 9 | A | 1 Prestrip - Thick | 100 | 71.189 | 71.189 | 2019-06-01 | 2019-06-08 19:26 | 328945.3851 | 328945 | [7 empty] | 0 | 0 | 32.51 | 12.04 | 5326.87
PH4100XPC#1 | GG\06\002\X1 | GG | 6 | 2 | X1 | 1 Prestrip - Thick | 100 | 0 | 31.175 | 2019-06-01 | 2019-06-10 20:18 | 586439.5461 | 586440 | [7 empty] | 0 | 0 | 22.66 | 0 | 0
TS5500Shv | GG\04\004\D | GG | 4 | 4 | D | 8 Coal Mining | 67.8 | 0 | 18.2 | 2019-06-01 | 2019-06-01 15:59 | 20669.8154 | [6 empty] | 20670 | 15612 | 0.78 | 0 | 0 | 5.42 | 5905
TS6060#1 | RS\11\007\X | RS | 11 | 7 | X | 1 Prestrip - Thick | 59.9101 | 43.2412 | 43.2412 | 2019-06-01 | 2019-06-11 00:35 | 255328.3989 | 255328 | [7 empty] | 0 | 0 | 16.88 | 11.6 | 5227.04
TS5500Exc | MW\30\006\A | MW | 30 | 6 | A | 1 Prestrip - Thick | 61.4487 | 1.9449 | 1.9449 | 2019-06-01 | 2019-06-01 05:03 | 4507.5785 | 4508 | [7 empty] | 0 | 0 | 0.44 | 10.71 | 5409.75
DRE2 | No Production | No Production | [7 empty] | 2019-06-01 | 2019-07-01
TS5500Exc | SC\35\016\D | SC | 35 | 16 | D | 8 Coal Mining | 100 | 0 | 9 | 2019-06-01 05:03 | 2019-06-01 10:27 | 6793.1927 | [6 empty] | 6793 | 5093 | 0.39 | 0 | 0 | 6.73 | 5819
TS5500Exc | SC\35\017\D | SC | 35 | 17 | D | 8 Coal Mining | 50.4 | 0 | 50.4 | 2019-06-01 10:27 | 2019-06-02 14:26 | 35253.0861 | [6 empty] | 35253 | 26408 | 2.2 | 0 | 0 | 7.06 | 5791
TS5500Shv | GG\04\005\D | GG | 4 | 5 | D | 8 Coal Mining | 23.9 | 0 | 23.9 | 2019-06-01 15:59 | 2019-06-02 13:43 | 28080.0689 | [6 empty] | 28080 | 21227 | 1.06 | 0 | 0 | 5.61 | 5891
TS Fleet 5 | MW\31\007\B | MW | 31 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-06-02 00:23 | 2019-06-03 10:11 | 67187.5862 | 67188 | [7 empty] | 0 | 0 | 6.58 | 9.55 | 5539.47
TS5500Shv | GG\04\006\B | GG | 4 | 6 | B | 8 Coal Mining | 23.1 | 0 | 23.1 | 2019-06-02 13:43 | 2019-06-02 16:09 | 3148.2629 | [6 empty] | 3148 | 2307 | 0.82 | 0 | 0 | 10.42 | 5469
TS5500Exc | SC\35\017\D | SC | 35 | 17 | D | 8 Coal Mining | 49.6 | 0 | 49.6 | 2019-06-02 14:26 | 2019-06-03 17:56 | 34630.8376 | [6 empty] | 34631 | 25942 | 2.16 | 0 | 0 | 7.06 | 5791
TS5500Shv | GG\05\002\B | GG | 5 | 2 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2019-06-02 16:09 | 2019-06-03 16:41 | 31690.6896 | [6 empty] | 31691 | 23027 | 1.09 | 0 | 0 | 11.34 | 5441
TS Fleet 5 | GG\05\006\B | GG | 5 | 6 | B | 1 Prestrip - Thick | 43.8817 | 43.8817 | 43.8817 | 2019-06-03 10:11 | 2019-06-07 16:45 | 203907.0315 | 203907 | [7 empty] | 0 | 0 | 20.09 | 10.27 | 5455.44
TS5500Shv | GG\05\003\X1 | GG | 5 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2019-06-03 16:41 | 2019-06-04 20:36 | 36079.8908 | [6 empty] | 36080 | 26847 | 1.31 | 0 | 0 | 9.4 | 5487
TS5500Exc | SC\35\018\D | SC | 35 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-06-03 17:56 | 2019-06-06 02:22 | 71086.4971 | [6 empty] | 71086 | 53125 | 4.43 | 0 | 0 | 7.25 | 5775
TS5500Shv | GG\05\004\X1 | GG | 5 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2019-06-04 20:36 | 2019-06-06 00:56 | 36620.0331 | [6 empty] | 36620 | 26999 | 1.32 | 0 | 0 | 10.82 | 5358
TS5500Shv | GG\05\005\B | GG | 5 | 5 | B | 8 Coal Mining | 59 | 0 | 59 | 2019-06-06 00:56 | 2019-06-07 14:35 | 48634.1318 | [6 empty] | 48634 | 35593 | 1.76 | 0 | 0 | 10.67 | 5432
TS5500Exc | SC\35\019\D | SC | 35 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-06-06 02:22 | 2019-06-08 11:20 | 71751.2066 | [6 empty] | 71751 | 53452 | 4.45 | 0 | 0 | 7.23 | 5777
DRE1 | SC\35\022\D | SC | 35 | 22 | D | 6 DL | 100 | 0 | 100 | 2019-06-07 10:23 | 2019-06-16 18:14 | 792378.8363 |  |  |  | 42305 | 792379 | 364910 |  |  | 0 | 36.8 | 0 | 7.35 | 5768.23
TS5500Shv | GG\04\006\D | GG | 4 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-06-07 14:35 | 2019-06-10 13:25 | 80477.8913 | 80478 | [7 empty] | 0 | 0 | 15.29 | 5.66 | 5888.42
TS Fleet 5 | GG\05\002\D | GG | 5 | 2 | D | 1 Prestrip - Thick | 46.887 | 46.887 | 46.887 | 2019-06-07 16:45 | 2019-06-09 23:03 | 107939.8463 | 107940 | [7 empty] | 0 | 0 | 8.72 | 5.51 | 5901.42
TS5500Exc | SC\35\020\D | SC | 35 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-06-08 11:20 | 2019-06-10 21:12 | 72890.9792 | [6 empty] | 72891 | 54216 | 4.52 | 0 | 0 | 7.13 | 5786
PH4100A | MW\32\009\A | MW | 32 | 9 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-06-08 19:26 | 2019-06-19 20:25 | 465552.5997 | 465553 | [7 empty] | 0 | 0 | 46.08 | 12.16 | 5319.82
TS Fleet 5 | GG\05\002\D | GG | 5 | 2 | D | 1 Prestrip - Thick | 12.7508 | 12.7508 | 12.7508 | 2019-06-09 23:03 | 2019-06-10 13:49 | 29354.0461 | 29354 | [7 empty] | 0 | 0 | 2.37 | 5.51 | 5901.42
TS5500Shv | GG\04\006\D | GG | 4 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2019-06-10 13:25 | 2019-06-11 23:51 | 39104.9255 |  |  | 39105 | [5 empty] | 0 | 0 | 0 | 5.66 | 5888.42
TS Fleet 5 | GG\05\003\X2 | GG | 5 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2019-06-10 13:49 | 2019-06-14 23:46 | 210614.543 | 210615 | [7 empty] | 0 | 0 | 10.38 | 0 | 0
PH4100XPC#1 | GG\05\004\B | GG | 5 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-06-10 20:18 | 2019-06-20 06:39 | 541655.9952 | 541656 | [7 empty] | 0 | 0 | 26.71 | 9.9 | 5524.05
TS5500Exc | MW\31\009\A | MW | 31 | 9 | A | 8 Coal Mining | 75.6 | 0 | 75.6 | 2019-06-10 21:12 | 2019-06-12 01:51 | 36092.9808 | [6 empty] | 36093 | 26405 | 2.66 | 0 | 0 | 12.04 | 5327
TS6060#1 | GG\04\004\D | GG | 4 | 4 | D | 8 Coal Mining | 32.2 | 0 | 32.2 | 2019-06-11 00:35 | 2019-06-12 02:03 | 36511.7959 | [6 empty] | 36512 | 27578 | 1.38 | 0 | 0 | 5.42 | 5905
TS5500Shv | GG\05\002\D | GG | 5 | 2 | D | 1 Prestrip - Thick | 40.3621 | 40.3621 | 40.3621 | 2019-06-11 23:51 | 2019-06-15 09:38 | 92918.7549 | 92919 | [7 empty] | 0 | 0 | 7.51 | 5.51 | 5901.42
TS5500Exc | DT\27\002\D | DT | 27 | 2 | D | 8 Coal Mining | 40.6 | 0 | 40.6 | 2019-06-12 01:51 | 2019-06-14 03:26 | 62454.3136 | [6 empty] | 62454 | 47118 | 1.99 | 0 | 0 | 5.99 | 5887
TS6060#1 | BW\28\008\D | BW | 28 | 8 | D | 8 Coal Mining | 100 | 0 | 6.5 | 2019-06-12 02:03 | 2019-06-12 06:38 | 6580.3022 | [6 empty] | 6580 | 5000 | 0.31 | 0 | 0 | 5.09 | 5966
TS6060#1 | GG\05\005\B | GG | 5 | 5 | B | 8 Coal Mining | 41 | 0 | 41 | 2019-06-12 06:38 | 2019-06-13 06:11 | 33773.2551 | [6 empty] | 33773 | 24717 | 1.22 | 0 | 0 | 10.67 | 5432
TS6060#1 | BW\28\006\D | BW | 28 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-06-13 06:11 | 2019-06-16 02:49 | 98435.4727 | [6 empty] | 98435 | 74437 | 4.65 | 0 | 0 | 5.48 | 5931
TS5500Exc | DT\27\003\D | DT | 27 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-06-14 03:26 | 2019-06-17 10:01 | 98983.6772 | [6 empty] | 98984 | 74371 | 4.65 | 0 | 0 | 6.48 | 5843
TS Fleet 5 | GG\05\003\B | GG | 5 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-06-14 23:46 | 2019-06-21 03:30 | 293696.4309 | 293696 | [7 empty] | 0 | 0 | 14.62 | 9.24 | 5604.71
TS5500Shv | GG\05\002\D | GG | 5 | 2 | D | 7 PostStrip | 15.3978 | 0 | 15.3978 | 2019-06-15 09:38 | 2019-06-15 21:07 | 13031.9947 |  |  | 13032 | [5 empty] | 0 | 0 | 0 | 5.51 | 5901.42
TS5500Shv | GG\05\002\D | GG | 5 | 2 | D | 7 PostStrip | 84.6022 | 0 | 84.6022 | 2019-06-15 21:07 | 2019-06-18 12:08 | 71603.2569 |  |  | 71603 | [5 empty] | 0 | 0 | 0 | 5.51 | 5901.42
TS6060#1 | BW\28\007\D | BW | 28 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-06-16 02:49 | 2019-06-19 01:17 | 101070.1276 | [6 empty] | 101070 | 76672 | 4.79 | 0 | 0 | 5.25 | 5952
DRE1 | SC\36\015\D | SC | 36 | 15 | D | 6 DL | 100 | 0 | 100 | 2019-06-16 18:14 | 2019-06-19 19:09 | 258082.9773 |  |  |  | 14730 | 258083 | 195693 |  |  | 0 | 30.16 | 0 | 7.38 | 5761.25
TS5500Exc | SC\35\021\D | SC | 35 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-06-17 10:01 | 2019-06-19 21:45 | 75240.8876 | [6 empty] | 75241 | 55790 | 4.65 | 0 | 0 | 7.31 | 5770
TS5500Shv | MW\30\003\B | MW | 30 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-06-18 12:08 | 2019-06-19 20:31 | 41835.1178 | [6 empty] | 41835 | 31086 | 3.11 | 0 | 0 | 8.48 | 5648
TS6060#1 | RS\12\003\A | RS | 12 | 3 | A | 1 Prestrip - Thick | 57.9892 | 57.9892 | 57.9892 | 2019-06-19 01:17 | 2019-06-25 08:34 | 160395.5785 | 160396 | [7 empty] | 0 | 0 | 23.64 | 11.45 | 5405.99
DRE1 | SC\36\014\D | SC | 36 | 14 | D | 6 DL | 100 | 0 | 100 | 2019-06-19 19:09 | 2019-06-25 06:41 | 465604.612 |  |  |  | 26573 | 465605 | 353047 |  |  | 0 | 31.58 | 0 | 7.7 | 5735
PH4100A | MW\31\010\X | MW | 31 | 10 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-06-19 20:25 | 2019-06-28 04:07 | 348267.9591 | 348268 | [7 empty] | 0 | 0 | 33.46 | 12.23 | 5209.78
TS5500Shv | MW\30\004\A | MW | 30 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-06-19 20:31 | 2019-06-21 10:52 | 49555.5421 | [6 empty] | 49556 | 36455 | 3.64 | 0 | 0 | 10.23 | 5448
TS5500Exc | MW\32\009\A | MW | 32 | 9 | A | 8 Coal Mining | 51.3 | 0 | 51.3 | 2019-06-19 21:45 | 2019-06-20 17:13 | 24520.1748 | [6 empty] | 24520 | 17929 | 1.8 | 0 | 0 | 12.16 | 5320
PH4100XPC#1 | GG\05\005\D | GG | 5 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-06-20 06:39 | 2019-06-26 06:30 | 344190.1578 | 344190 | [7 empty] | 0 | 0 | 22.18 | 5.69 | 5884.1
TS5500Exc | SC\36\015\D | SC | 36 | 15 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-06-20 17:13 | 2019-06-21 20:50 | 34784.1779 | [6 empty] | 34784 | 26056 | 4.14 | 0 | 0 | 7.38 | 5761
TS Fleet 5 | GG\06\002\B | GG | 6 | 2 | B | 1 Prestrip - Thick | 44.3854 | 44.3854 | 44.3854 | 2019-06-21 03:30 | 2019-06-23 14:14 | 116787.0774 | 116787 | [7 empty] | 0 | 0 | 4.62 | 10.56 | 5506.04
TS5500Shv | MW\31\008\A | MW | 31 | 8 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-06-21 10:52 | 2019-06-22 23:13 | 46965.936 | [6 empty] | 46966 | 34529 | 3.45 | 0 | 0 | 11.14 | 5385
TS5500Exc | MW\30\004\B | MW | 30 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-06-21 20:50 | 2019-06-23 10:51 | 33619.9932 | 33620 | [7 empty] | 0 | 0 | 3.35 | 8.76 | 5621.53
TS5500Shv | MW\32\008\A | MW | 32 | 8 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-06-22 23:13 | 2019-06-24 11:22 | 46718.6766 | [6 empty] | 46719 | 34314 | 3.43 | 0 | 0 | 11.33 | 5380
TS5500Exc | MW\30\004\B | MW | 30 | 4 | B | 8 Coal Mining | 72.2 | 0 | 72.2 | 2019-06-23 10:51 | 2019-06-24 10:37 | 29929.0341 | [6 empty] | 29929 | 22187 | 2.2 | 0 | 0 | 8.76 | 5622
TS Fleet 5 | GG\06\003\X1 | GG | 6 | 3 | X1 | 1 Prestrip - Thick | 44.5713 | 44.5713 | 44.5713 | 2019-06-23 14:14 | 2019-06-30 00:48 | 307251.1504 | 307251 | [7 empty] | 0 | 0 | 14.8 | 8.84 | 5533.52
TS5500Exc | MW\30\005\A | MW | 30 | 5 | A | 8 Coal Mining | 49 | 0 | 49 | 2019-06-24 10:37 | 2019-06-25 04:51 | 22975.8356 | [6 empty] | 22976 | 16962 | 1.69 | 0 | 0 | 9.9 | 5469
TS5500Shv | MW\31\009\A | MW | 31 | 9 | A | 8 Coal Mining | 24.4 | 0 | 24.4 | 2019-06-24 11:22 | 2019-06-24 20:24 | 11664.9173 | [6 empty] | 11665 | 8534 | 0.86 | 0 | 0 | 12.04 | 5327
TS5500Shv | GG\04\006\D | GG | 4 | 6 | D | 8 Coal Mining | 100 | 0 | 68.4 | 2019-06-24 20:24 | 2019-06-25 20:50 | 31575.7831 | [6 empty] | 31576 | 23872 | 3.11 | 0 | 0 | 5.66 | 5888
TS5500Exc | MW\32\009\A | MW | 32 | 9 | A | 8 Coal Mining | 16.3 | 0 | 16.3 | 2019-06-25 04:51 | 2019-06-25 11:02 | 7797.7194 | [6 empty] | 7798 | 5702 | 0.57 | 0 | 0 | 12.16 | 5320
DRE1 | SC\36\013\D | SC | 36 | 13 | D | 6 DL | 100 | 0 | 99.0481 | 2019-06-25 06:41 | 2019-07-01 | 486043.5627 |  |  |  | 27740 | 486044 | 368545 |  |  | 0 | 33.47 | 0 | 7.74 | 5732.71
TS6060#1 | GG\05\003\B | GG | 5 | 3 | B | 8 Coal Mining | 15.5 | 0 | 15.5 | 2019-06-25 08:34 | 2019-06-25 19:19 | 15414.7654 | [6 empty] | 15415 | 11321 | 0.57 | 0 | 0 | 9.24 | 5605
TS5500Exc | DT\27\004\B | DT | 27 | 4 | B | 8 Coal Mining | 100 | 0 | 18.5 | 2019-06-25 11:02 | 2019-06-25 20:50 | 12329.6508 | [6 empty] | 12330 | 9016 | 0.56 | 0 | 0 | 9.92 | 5395
TS6060#1 | GG\05\004\B | GG | 5 | 4 | B | 8 Coal Mining | 52.6 | 0 | 2.2 | 2019-06-25 19:19 | 2019-06-25 20:50 | 2161.1647 | [6 empty] | 2161 | 1584 | 0.08 | 0 | 0 | 9.9 | 5524
TS5500Shv | GG\07\002\X1 | GG | 7 | 2 | X1 | 1 Prestrip - Thick | 8.5855 | 0 | 6.2081 | 2019-06-25 20:50 | 2019-07-01 | 140221.1306 | 140221 | [7 empty] | 0 | 0 | 4.47 | 0 | 0
TS6060#1 | RS\12\003\A | RS | 12 | 3 | A | 1 Prestrip - Thick | 42.0108 | 42.0108 | 42.0108 | 2019-06-25 20:50 | 2019-06-30 10:26 | 116200.0516 | 116200 | [7 empty] | 0 | 0 | 17.13 | 11.45 | 5405.99
TS5500Exc | SC\35\022\D | SC | 35 | 22 | D | 7 PostStrip | 100 | 0 | 100 | 2019-06-25 20:50 | 2019-06-28 19:53 | 62839.9369 |  |  | 62840 | [5 empty] | 0 | 0 | 0 | 7.35 | 5768.23
PH4100XPC#1 | GG\05\006\B | GG | 5 | 6 | B | 1 Prestrip - Thick | 100 | 56.1183 | 56.1183 | 2019-06-26 06:30 | 2019-06-30 17:16 | 260767.7027 | 260768 | [7 empty] | 0 | 0 | 25.69 | 10.27 | 5455.44
PH4100A | MW\32\010\X | MW | 32 | 10 | X | 1 Prestrip - Thick | 100 | 19.4358 | 19.4358 | 2019-06-28 04:07 | 2019-07-01 | 119399.3258 | 119399 | [7 empty] | 0 | 0 | 7.09 | 12.24 | 5207.93
TS5500Exc | MW\30\007\A | MW | 30 | 7 | A | 1 Prestrip - Thick | 33.2158 | 15.7321 | 15.7321 | 2019-06-28 19:53 | 2019-07-01 | 46378.704 | 46379 | [7 empty] | 0 | 0 | 4.55 | 10.65 | 5418.49
TS Fleet 5 | GG\06\004\X1 | GG | 6 | 4 | X1 | 1 Prestrip - Thick | 23.7207 | 6.1106 | 6.1106 | 2019-06-30 00:48 | 2019-07-01 | 46119.3818 | 46119 | [7 empty] | 0 | 0 | 2.16 | 10.3 | 5402.85
TS6060#1 | RS\12\004\X | RS | 12 | 4 | X | 1 Prestrip - Thick | 78.1106 | 4.7986 | 4.7986 | 2019-06-30 10:26 | 2019-07-01 | 14162.7179 | 14163 | [7 empty] | 0 | 0 | 1.39 | 14.05 | 5098.57
PH4100XPC#1 | GG\06\002\B | GG | 6 | 2 | B | 1 Prestrip - Thick | 100 | 6.1116 | 6.1116 | 2019-06-30 17:16 | 2019-07-01 | 16080.8137 | 16081 | [7 empty] | 0 | 0 | 0.64 | 10.56 | 5506.04
| EOP 66 : 2019\Jun | EOP 66 : 2019 | Jun | [6 empty] | 2019-07-01 | 2019-07-01 |  | 5386870 |  | 186580 | 150212 | 2548584 | 1675155 | 1424700 | 1061484 | 81.8 | 0 | 400.82 | 8.02 | 5688.27
TS Fleet 5 | GG\06\004\X1 | GG | 6 | 4 | X1 | 1 Prestrip - Thick | 23.7207 | 17.61 | 17.61 | 2019-07-01 | 2019-07-03 17:55 | 132910.2176 | 132910 | [7 empty] | 0 | 0 | 6.22 | 10.3 | 5402.85
DRE1 | SC\36\013\D | SC | 36 | 13 | D | 6 DL | 100 | 0 | 0.95189 | 2019-07-01 | 2019-07-01 01:18 | 4671.0765 |  |  |  | 267 | 4671 | 3542 |  |  | 0 | 33.47 | 0 | 7.74 | 5732.71
PH4100A | MW\32\010\X | MW | 32 | 10 | X | 1 Prestrip - Thick | 100 | 80.5642 | 80.5642 | 2019-07-01 | 2019-07-12 13:36 | 494926.6537 | 494927 | [7 empty] | 0 | 0 | 29.4 | 12.24 | 5207.93
DRE2 | BW\28\005\D | BW | 28 | 5 | D | 6 DL | 100 | 7.3516 | 7.3516 | 2019-07-01 | 2019-07-02 00:53 | 53588.1715 |  |  |  | 2022 | 53588 | 25587 |  |  | 0 | 22.56 | 0 | 5.69 | 5912.06
PH4100XPC#1 | GG\06\002\B | GG | 6 | 2 | B | 1 Prestrip - Thick | 100 | 49.503 | 49.503 | 2019-07-01 | 2019-07-03 05:42 | 130252.2968 | 130252 | [7 empty] | 0 | 0 | 5.15 | 10.56 | 5506.04
TS5500Shv | GG\07\002\X1 | GG | 7 | 2 | X1 | 1 Prestrip - Thick | 8.5855 | 0 | 2.3773 | 2019-07-01 | 2019-07-02 22:30 | 53696.3073 | 53696 | [7 empty] | 0 | 0 | 1.71 | 0 | 0
TS6060#1 | RS\12\004\X | RS | 12 | 4 | X | 1 Prestrip - Thick | 78.1106 | 73.312 | 73.312 | 2019-07-01 | 2019-07-09 12:19 | 216374.2938 | 216374 | [7 empty] | 0 | 0 | 21.3 | 14.05 | 5098.57
TS5500Exc | MW\30\007\A | MW | 30 | 7 | A | 1 Prestrip - Thick | 33.2158 | 17.4837 | 17.4837 | 2019-07-01 | 2019-07-03 09:54 | 51542.5832 | 51543 | [7 empty] | 0 | 0 | 5.06 | 10.65 | 5418.49
DRE1 | SC\36\012\D | SC | 36 | 12 | D | 6 DL | 100 | 0 | 100 | 2019-07-01 01:18 | 2019-07-08 07:55 | 626273.0153 |  |  |  | 47625 | 626273 | 428628 |  |  | 0 | 40 | 0 | 7.6 | 5744.66
DRE2 | BW\29\008\D | BW | 29 | 8 | D | 6 DL | 100 | 100 | 100 | 2019-07-02 00:53 | 2019-07-06 11:03 | 228552.117 |  |  |  | 10226 | 228552 | 194295 |  |  | 0 | 20.46 | 0 | 5.29 | 5948.37
TS5500Shv | GG\05\005\D | GG | 5 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2019-07-02 22:30 | 2019-07-06 13:28 | 100189.3721 |  |  | 100189 | [5 empty] | 0 | 0 | 0 | 5.69 | 5884.1
PH4100XPC#1 | GG\06\003\X1 | GG | 6 | 3 | X1 | 1 Prestrip - Thick | 100 | 55.4287 | 55.4287 | 2019-07-03 05:42 | 2019-07-09 20:27 | 382095.6996 | 382096 | [7 empty] | 0 | 0 | 18.41 | 8.84 | 5533.52
TS5500Exc | MW\31\010\X | MW | 31 | 10 | X | 8 Coal Mining | 49 | 0 | 49 | 2019-07-03 09:54 | 2019-07-03 17:11 | 9175.3756 | [6 empty] | 9175 | 6692 | 0.66 | 0 | 0 | 12.23 | 5210
TS5500Exc | DT\27\004\B | DT | 27 | 4 | B | 8 Coal Mining | 100 | 0 | 81.5 | 2019-07-03 17:11 | 2019-07-05 12:25 | 54442.3466 | [6 empty] | 54442 | 39809 | 2.49 | 0 | 0 | 9.92 | 5395
TS Fleet 5 | GG\06\004\X1 | GG | 6 | 4 | X1 | 1 Prestrip - Thick | 20.2805 | 20.2805 | 20.2805 | 2019-07-03 17:55 | 2019-07-06 21:51 | 153065.1129 | 153065 | [7 empty] | 0 | 0 | 7.17 | 10.3 | 5402.85
TS5500Exc | SC\36\014\D | SC | 36 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-07-05 12:25 | 2019-07-07 20:02 | 70062.8257 | [6 empty] | 70063 | 52485 | 4.38 | 0 | 0 | 7.7 | 5735
DRE2 | DT\27\004\D | DT | 27 | 4 | D | 6 DL | 100 | 100 | 100 | 2019-07-06 11:03 | 2019-07-16 15:51 | 527024.0935 |  |  |  | 22985 | 527024 | 380266 |  |  | 0 | 25.19 | 0 | 6.75 | 5820.5
TS5500Shv | GG\04\006\D | GG | 4 | 6 | D | 8 Coal Mining | 100 | 0 | 31.6 | 2019-07-06 13:28 | 2019-07-07 00:37 | 14608.244 | [6 empty] | 14608 | 11044 | 1.44 | 0 | 0 | 5.66 | 5888
TS Fleet 5 | GG\07\002\X1 | GG | 7 | 2 | X1 | 1 Prestrip - Thick | 59.7193 | 0 | 53.7453 | 2019-07-06 21:51 | 2019-08-01 | 1213928.669 | 1213929 | [7 empty] | 0 | 0 | 38.66 | 0 | 0
TS5500Shv | GG\05\002\D | GG | 5 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-07-07 00:37 | 2019-07-10 06:23 | 101897.5907 | [6 empty] | 101898 | 76842 | 4.59 | 0 | 0 | 5.51 | 5901
TS5500Exc | DT\27\005\D | DT | 27 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-07-07 20:02 | 2019-07-12 23:07 | 155028.2185 | [6 empty] | 155028 | 116021 | 4.72 | 0 | 0 | 6.86 | 5811
DRE1 | SC\36\011\D | SC | 36 | 11 | D | 6 DL | 100 | 0 | 100 | 2019-07-08 07:55 | 2019-07-15 15:06 | 628217.9486 |  |  |  | 47773 | 628218 | 429959 |  |  | 0 | 40 | 0 | 7.67 | 5739.95
TS6060#1 | GG\05\004\B | GG | 5 | 4 | B | 8 Coal Mining | 52.6 | 0 | 50.4 | 2019-07-09 12:19 | 2019-07-10 23:01 | 50465.8 | [6 empty] | 50466 | 36993 | 1.85 | 0 | 0 | 9.9 | 5524
PH4100XPC#1 | GG\06\004\X1 | GG | 6 | 4 | X1 | 1 Prestrip - Thick | 100 | 55.9989 | 55.9989 | 2019-07-09 20:27 | 2019-07-17 03:46 | 422646.3106 | 422646 | [7 empty] | 0 | 0 | 19.79 | 10.3 | 5402.85
TS5500Shv | GG\05\003\B | GG | 5 | 3 | B | 8 Coal Mining | 84.5 | 0 | 84.5 | 2019-07-10 06:23 | 2019-07-12 22:36 | 84147.5628 | [6 empty] | 84148 | 61800 | 3.09 | 0 | 0 | 9.24 | 5605
TS6060#1 | GG\05\005\D | GG | 5 | 5 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2019-07-10 23:01 | 2019-07-12 17:33 | 61861.7878 | [6 empty] | 61862 | 46727 | 2.34 | 0 | 0 | 5.69 | 5884
PH4100A | MW\31\011\X | MW | 31 | 11 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-07-12 13:36 | 2019-07-19 17:11 | 307112.3386 | 307112 | [7 empty] | 0 | 0 | 37.65 | 12.35 | 5184.4
TS6060#1 | GG\05\006\B | GG | 5 | 6 | B | 8 Coal Mining | 16.6 | 0 | 16.6 | 2019-07-12 17:33 | 2019-07-12 23:10 | 8162.4435 | [6 empty] | 8162 | 5987 | 0.63 | 0 | 0 | 10.27 | 5455
TS5500Shv | GG\05\004\B | GG | 5 | 4 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2019-07-12 22:36 | 2019-07-14 10:47 | 47416.3742 | [6 empty] | 47416 | 34758 | 1.74 | 0 | 0 | 9.9 | 5524
TS5500Exc | SC\36\013\D | SC | 36 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-07-12 23:07 | 2019-07-15 09:27 | 73476.3403 | [6 empty] | 73476 | 55000 | 4.58 | 0 | 0 | 7.74 | 5733
TS6060#1 | GG\05\006\B | GG | 5 | 6 | B | 8 Coal Mining | 43.8 | 0 | 43.8 | 2019-07-12 23:10 | 2019-07-13 13:57 | 21506.4037 | [6 empty] | 21506 | 15774 | 1.67 | 0 | 0 | 10.27 | 5455
TS6060#1 | GG\06\002\B | GG | 6 | 2 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2019-07-13 13:57 | 2019-07-15 02:39 | 53385.6016 | [6 empty] | 53386 | 38924 | 1.56 | 0 | 0 | 10.56 | 5506
TS5500Shv | GG\05\005\D | GG | 5 | 5 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2019-07-14 10:47 | 2019-07-16 05:19 | 55736.8583 | [6 empty] | 55737 | 42100 | 2.11 | 0 | 0 | 5.69 | 5884
TS6060#1 | GG\06\003\X1 | GG | 6 | 3 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2019-07-15 02:39 | 2019-07-15 17:14 | 21198.6315 | [6 empty] | 21199 | 15820 | 0.78 | 0 | 0 | 8.84 | 5534
TS5500Exc | MW\32\010\X | MW | 32 | 10 | X | 8 Coal Mining | 39.1 | 0 | 39.1 | 2019-07-15 09:27 | 2019-07-15 18:18 | 11149.1949 | [6 empty] | 11149 | 8132 | 0.51 | 0 | 0 | 12.24 | 5208
DRE1 | SC\36\010\D | SC | 36 | 10 | D | 6 DL | 100 | 0 | 100 | 2019-07-15 15:06 | 2019-07-25 13:55 | 856454.6172 |  |  |  | 48128 | 856455 | 372822 |  |  | 0 | 40 | 0 | 7.71 | 5736.49
TS6060#1 | BW\28\005\D | BW | 28 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2019-07-15 17:14 | 2019-07-19 17:41 | 106951.894 |  |  | 106952 | [5 empty] | 0 | 0 | 0 | 5.69 | 5912.06
TS5500Exc | DT\27\006\B | DT | 27 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-07-15 18:18 | 2019-07-16 13:10 | 23778.0974 | [6 empty] | 23778 | 17392 | 0.97 | 0 | 0 | 11.33 | 5370
TS5500Shv | MW\32\009\A | MW | 32 | 9 | A | 8 Coal Mining | 15.4 | 0 | 15.4 | 2019-07-16 05:19 | 2019-07-16 10:56 | 7354.2808 | [6 empty] | 7354 | 5378 | 0.54 | 0 | 0 | 12.16 | 5320
TS5500Shv | GG\05\003\D | GG | 5 | 3 | D | 1 Prestrip - Thick | 29.9589 | 29.9589 | 29.9589 | 2019-07-16 10:56 | 2019-07-19 17:43 | 90757.6438 | 90758 | [7 empty] | 0 | 0 | 6.04 | 5.46 | 5903.71
TS5500Exc | DT\27\007\B | DT | 27 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-07-16 13:10 | 2019-07-17 14:52 | 32357.2401 | [6 empty] | 32357 | 23930 | 1.56 | 0 | 0 | 9.64 | 5518
DRE2 | DT\27\006\D | DT | 27 | 6 | D | 6 DL | 100 | 100 | 100 | 2019-07-16 15:51 | 2019-07-27 17:32 | 571943.1514 |  |  |  | 24944 | 571943 | 412676 |  |  | 0 | 24 | 0 | 6.89 | 5807.42
PH4100XPC#1 | GG\05\003\D | GG | 5 | 3 | D | 1 Prestrip - Thick | 100 | 60.9827 | 60.9827 | 2019-07-17 03:46 | 2019-07-20 07:56 | 184741.1736 | 184741 | [7 empty] | 0 | 0 | 12.29 | 5.46 | 5903.71
TS5500Exc | SC\36\012\D | SC | 36 | 12 | D | 8 Coal Mining | 66.7 | 0 | 66.7 | 2019-07-17 14:52 | 2019-07-19 06:05 | 49396.6565 | [6 empty] | 49397 | 36858 | 3.07 | 0 | 0 | 7.6 | 5745
TS5500Exc | SC\35\022\D | SC | 35 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-07-19 06:05 | 2019-07-21 20:01 | 78016.3935 | [6 empty] | 78016 | 57760 | 4.81 | 0 | 0 | 7.35 | 5768
PH4100A | GG\05\003\D | GG | 5 | 3 | D | 1 Prestrip - Thick | 100 | 9.0583 | 9.0583 | 2019-07-19 17:11 | 2019-07-20 07:56 | 27441.3609 | 27441 | [7 empty] | 0 | 0 | 1.83 | 5.46 | 5903.71
TS6060#1 | GG\06\004\X1 | GG | 6 | 4 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2019-07-19 17:41 | 2019-07-20 07:04 | 19463.1959 | [6 empty] | 19463 | 14394 | 0.71 | 0 | 0 | 10.3 | 5403
TS5500Shv | MW\30\004\B | MW | 30 | 4 | B | 8 Coal Mining | 27.8 | 0 | 27.8 | 2019-07-19 17:43 | 2019-07-20 02:29 | 11498.7257 | [6 empty] | 11499 | 8524 | 0.85 | 0 | 0 | 8.76 | 5622
TS5500Shv | MW\30\005\A | MW | 30 | 5 | A | 8 Coal Mining | 51 | 0 | 51 | 2019-07-20 02:29 | 2019-07-20 20:43 | 23902.4571 | [6 empty] | 23902 | 17646 | 1.76 | 0 | 0 | 9.9 | 5469
TS6060#1 | BW\28\005\D | BW | 28 | 5 | D | 8 Coal Mining | 10.8 | 0 | 10.8 | 2019-07-20 07:04 | 2019-07-20 16:45 | 14076.1989 | [6 empty] | 14076 | 10619 | 0.5 | 0 | 0 | 5.69 | 5912
PH4100A | GG\05\004\D | GG | 5 | 4 | D | 1 Prestrip - Thick | 100 | 43.4052 | 43.4052 | 2019-07-20 07:56 | 2019-07-23 05:33 | 129468.9824 | 129469 | [7 empty] | 0 | 0 | 8.65 | 5.54 | 5895.24
PH4100XPC#1 | GG\05\004\D | GG | 5 | 4 | D | 1 Prestrip - Thick | 100 | 56.5948 | 56.5948 | 2019-07-20 07:56 | 2019-07-23 05:33 | 168810.8474 | 168811 | [7 empty] | 0 | 0 | 11.27 | 5.54 | 5895.24
TS6060#1 | RS\12\004\X | RS | 12 | 4 | X | 1 Prestrip - Thick | 21.8894 | 21.8894 | 21.8894 | 2019-07-20 16:45 | 2019-07-23 05:45 | 64604.8266 | 64605 | [7 empty] | 0 | 0 | 6.36 | 14.05 | 5098.57
TS5500Shv | GG\05\003\D | GG | 5 | 3 | D | 7 PostStrip | 81.1577 | 0 | 81.1577 | 2019-07-20 20:43 | 2019-07-23 19:08 | 81104.3347 |  |  | 81104 | [5 empty] | 0 | 0 | 0 | 5.46 | 5903.71
TS5500Exc | MW\30\005\B | MW | 30 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-07-21 20:01 | 2019-07-23 18:18 | 40931.1114 | 40931 | [7 empty] | 0 | 0 | 4.06 | 8.87 | 5620.72
PH4100XPC#1 | GG\06\005\X2 | GG | 6 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 32.3588 | 2019-07-23 05:33 | 2019-07-29 12:34 | 372752.7329 | 372753 | [7 empty] | 0 | 0 | 14.61 | 0 | 0
PH4100A | GG\06\005\X2 | GG | 6 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 24.8233 | 2019-07-23 05:33 | 2019-07-29 12:34 | 285948.3132 | 285948 | [7 empty] | 0 | 0 | 11.21 | 0 | 0
TS6060#1 | BW\28\005\D | BW | 28 | 5 | D | 8 Coal Mining | 89.2 | 0 | 89.2 | 2019-07-23 05:45 | 2019-07-26 13:27 | 115910.7162 | [6 empty] | 115911 | 87442 | 4.11 | 0 | 0 | 5.69 | 5912
TS5500Exc | SC\36\011\D | SC | 36 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-07-23 18:18 | 2019-07-26 06:49 | 76229.0865 | [6 empty] | 76229 | 56927 | 4.75 | 0 | 0 | 7.67 | 5740
TS5500Shv | GG\05\003\D | GG | 5 | 3 | D | 7 PostStrip | 18.8423 | 0 | 18.8423 | 2019-07-23 19:08 | 2019-07-24 11:28 | 18829.8944 |  |  | 18830 | [5 empty] | 0 | 0 | 0 | 5.46 | 5903.71
TS5500Shv | GG\05\004\D | GG | 5 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2019-07-24 11:28 | 2019-07-28 02:16 | 99979.7947 |  |  | 99980 | [5 empty] | 0 | 0 | 0 | 5.54 | 5895.24
DRE1 | SC\36\016\D | SC | 36 | 16 | D | 6 DL | 100 | 0 | 60.301 | 2019-07-25 13:55 | 2019-08-01 | 552571.9424 |  |  |  | 37068 | 552572 | 374797 |  |  | 0 | 39.26 | 0 | 6.96 | 5798.81
TS5500Exc | SC\36\010\D | SC | 36 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2019-07-26 06:49 | 2019-07-29 03:02 | 60326.2038 |  |  | 60326 | [5 empty] | 0 | 0 | 0 | 7.71 | 5736.49
TS6060#1 | GG\05\003\D | GG | 5 | 3 | D | 8 Coal Mining | 73.4 | 0 | 56.7 | 2019-07-26 13:27 | 2019-07-28 11:28 | 66927.9031 | [6 empty] | 66928 | 50512 | 2.53 | 0 | 0 | 5.46 | 5904
DRE2 | DT\27\007\D | DT | 27 | 7 | D | 6 DL | 100 | 40.7378 | 40.7378 | 2019-07-27 17:32 | 2019-08-01 | 220575.6666 |  |  |  | 13173 | 220576 | 155710 |  |  | 0 | 25.9 | 0 | 6.76 | 5818.89
TS5500Shv | MW\31\010\X | MW | 31 | 10 | X | 8 Coal Mining | 51 | 0 | 51 | 2019-07-28 02:16 | 2019-07-28 09:33 | 9545.421 | [6 empty] | 9545 | 6962 | 0.69 | 0 | 0 | 12.23 | 5210
TS5500Shv | MW\32\009\A | MW | 32 | 9 | A | 8 Coal Mining | 17 | 0 | 5.3 | 2019-07-28 09:33 | 2019-07-28 11:28 | 2522.0276 | [6 empty] | 2522 | 1844 | 0.18 | 0 | 0 | 12.16 | 5320
TS5500Shv | GG\07\002\X1 | GG | 7 | 2 | X1 | 1 Prestrip - Thick | 11.6377 | 0 | 4.3204 | 2019-07-28 11:28 | 2019-08-01 | 97583.4549 | 97583 | [7 empty] | 0 | 0 | 3.11 | 0 | 0
TS6060#1 | RS\12\005\X | RS | 12 | 5 | X | 1 Prestrip - Thick | 42.0452 | 27.563 | 27.563 | 2019-07-28 11:28 | 2019-08-01 | 90578.3559 | 90578 | [7 empty] | 0 | 0 | 8.96 | 12.94 | 5161.48
TS5500Exc | MW\30\007\A | MW | 30 | 7 | A | 1 Prestrip - Thick | 66.7842 | 20.8211 | 20.8211 | 2019-07-29 03:02 | 2019-08-01 | 61381.2232 | 61381 | [7 empty] | 0 | 0 | 6.02 | 10.65 | 5418.49
PH4100A | GG\06\005\B | GG | 6 | 5 | B | 1 Prestrip - Thick | 100 | 43.3133 | 43.3133 | 2019-07-29 12:34 | 2019-08-01 | 110522.5248 | 110523 | [7 empty] | 0 | 0 | 5.4 | 10.84 | 5401.4
PH4100XPC#1 | GG\06\005\B | GG | 6 | 5 | B | 1 Prestrip - Thick | 100 | 56.4749 | 56.4749 | 2019-07-29 12:34 | 2019-08-01 | 144107.1114 | 144107 | [7 empty] | 0 | 0 | 7.04 | 10.84 | 5401.4
| EOP 67 : 2019\Jul | EOP 67 : 2019 | Jul | [6 empty] | 2019-08-01 | 2019-08-01 |  | 5428180 |  | 467381 | 254211 | 4269872 | 2778282 | 1424700 | 1061098 | 66.16 | 0 | 297.37 | 7.41 | 5740.04
TS Fleet 5 | GG\07\002\X1 | GG | 7 | 2 | X1 | 1 Prestrip - Thick | 59.7193 | 0 | 5.974 | 2019-08-01 | 2019-08-03 18:00 | 134932.9798 | 134933 | [7 empty] | 0 | 0 | 4.3 | 0 | 0
DRE1 | SC\36\016\D | SC | 36 | 16 | D | 6 DL | 100 | 0 | 39.699 | 2019-08-01 | 2019-08-05 05:26 | 363784.1531 |  |  |  | 24404 | 363784 | 246747 |  |  | 0 | 39.26 | 0 | 6.96 | 5798.81
PH4100A | GG\06\005\B | GG | 6 | 5 | B | 1 Prestrip - Thick | 100 | 0.091952 | 0.091952 | 2019-08-01 | 2019-08-01 00:07 | 234.633 | 235 | [7 empty] | 0 | 0 | 0.01 | 10.84 | 5401.4
DRE2 | DT\27\007\D | DT | 27 | 7 | D | 6 DL | 100 | 59.2622 | 59.2622 | 2019-08-01 | 2019-08-04 20:54 | 320876.1176 |  |  |  | 19163 | 320876 | 226515 |  |  | 0 | 25.9 | 0 | 6.76 | 5818.89
PH4100XPC#1 | GG\06\005\B | GG | 6 | 5 | B | 1 Prestrip - Thick | 100 | 0.11989 | 0.11989 | 2019-08-01 | 2019-08-01 00:07 | 305.9311 | 306 | [7 empty] | 0 | 0 | 0.01 | 10.84 | 5401.4
TS5500Shv | GG\07\002\X1 | GG | 7 | 2 | X1 | 1 Prestrip - Thick | 11.6377 | 0 | 7.3173 | 2019-08-01 | 2019-08-06 21:11 | 165273.1468 | 165273 | [7 empty] | 0 | 0 | 5.26 | 0 | 0
TS6060#1 | RS\12\005\X | RS | 12 | 5 | X | 1 Prestrip - Thick | 42.0452 | 14.4822 | 14.4822 | 2019-08-01 | 2019-08-02 19:48 | 47592.0034 | 47592 | [7 empty] | 0 | 0 | 4.71 | 12.94 | 5161.48
TS5500Exc | MW\30\007\A | MW | 30 | 7 | A | 1 Prestrip - Thick | 66.7842 | 45.9632 | 45.9632 | 2019-08-01 | 2019-08-07 08:14 | 135501.0999 | 135501 | [7 empty] | 0 | 0 | 13.3 | 10.65 | 5418.49
PH4100A | SC\37\010\D | SC | 37 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-08-01 00:07 | 2019-08-07 09:04 | 287418.4965 | 287418 | [7 empty] | 0 | 0 | 24.24 | 7.76 | 5732.36
PH4100XPC#1 | GG\08\007\X2 | GG | 8 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2019-08-01 00:07 | 2019-08-07 00:26 | 357804.1789 | 357804 | [7 empty] | 0 | 0 | 39.11 | 0 | 0
TS6060#1 | GG\05\003\D | GG | 5 | 3 | D | 8 Coal Mining | 73.4 | 0 | 16.7 | 2019-08-02 19:48 | 2019-08-03 09:07 | 19651.1688 | [6 empty] | 19651 | 14831 | 0.74 | 0 | 0 | 5.46 | 5904
TS6060#1 | GG\05\004\D | GG | 5 | 4 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2019-08-03 09:07 | 2019-08-05 01:59 | 60256.2438 | [6 empty] | 60256 | 45477 | 2.27 | 0 | 0 | 5.54 | 5895
TS Fleet 5 | GG\07\002\X1 | GG | 7 | 2 | X1 | 1 Prestrip - Thick | 20.0575 | 0 | 20.0575 | 2019-08-03 18:00 | 2019-08-12 23:39 | 453033.5014 | 453034 | [7 empty] | 0 | 0 | 14.43 | 0 | 0
DRE2 | BW\29\007\D | BW | 29 | 7 | D | 6 DL | 100 | 100 | 100 | 2019-08-04 20:54 | 2019-08-07 16:47 | 234407.6433 |  |  |  | 10488 | 234408 | 199273 |  |  | 0 | 20.98 | 0 | 5.43 | 5936.43
TS6060#1 | GG\06\005\B | GG | 6 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-08-05 01:59 | 2019-08-07 22:21 | 100820.5066 | [6 empty] | 100821 | 73722 | 3.68 | 0 | 0 | 10.84 | 5401
DRE1 | SC\36\017\D | SC | 36 | 17 | D | 6 DL | 100 | 0 | 100 | 2019-08-05 05:26 | 2019-08-17 07:15 | 1039359.785 |  |  |  | 79039 | 1039360 | 711349 |  |  | 0 | 40 | 0 | 6.63 | 5829.26
TS5500Shv | MW\32\009\A | MW | 32 | 9 | A | 8 Coal Mining | 17 | 0 | 11.7 | 2019-08-06 21:11 | 2019-08-07 01:23 | 5590.1759 | [6 empty] | 5590 | 4088 | 0.41 | 0 | 0 | 12.16 | 5320
PH4100XPC#1 | GG\08\007\B | GG | 8 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-08-07 00:26 | 2019-08-10 12:19 | 206114.5863 | 206115 | [7 empty] | 0 | 0 | 21.35 | 10.64 | 5386.66
TS5500Shv | GG\05\003\D | GG | 5 | 3 | D | 8 Coal Mining | 26.6 | 0 | 26.6 | 2019-08-07 01:23 | 2019-08-08 01:03 | 31428.7595 | [6 empty] | 31429 | 23720 | 1.19 | 0 | 0 | 5.46 | 5904
TS5500Exc | SC\36\010\D | SC | 36 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-08-07 08:14 | 2019-08-09 21:43 | 77448.6627 | [6 empty] | 77449 | 57976 | 4.84 | 0 | 0 | 7.71 | 5736
PH4100A | SC\37\011\D | SC | 37 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-08-07 09:04 | 2019-08-10 17:42 | 150939.6802 | 150940 | [7 empty] | 0 | 0 | 12.89 | 7.64 | 5741.8
DRE2 | BW\29\006\D | BW | 29 | 6 | D | 6 DL | 100 | 100 | 100 | 2019-08-07 16:47 | 2019-08-10 13:23 | 236883.4774 |  |  |  | 10599 | 236883 | 201377 |  |  | 0 | 21.2 | 0 | 5.67 | 5915.14
TS6060#1 | BW\29\008\D | BW | 29 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-08-07 22:21 | 2019-08-09 17:06 | 63034.2496 | [6 empty] | 63034 | 47818 | 4.78 | 0 | 0 | 5.29 | 5948
TS5500Shv | GG\05\004\D | GG | 5 | 4 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2019-08-08 01:03 | 2019-08-09 17:55 | 54290.2791 | [6 empty] | 54290 | 40974 | 2.05 | 0 | 0 | 5.54 | 5895
TS6060#1 | BW\29\007\D | BW | 29 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-08-09 17:06 | 2019-08-11 12:07 | 63422.8597 | [6 empty] | 63423 | 47997 | 4.8 | 0 | 0 | 5.43 | 5936
TS5500Shv | GG\05\006\B | GG | 5 | 6 | B | 8 Coal Mining | 39.5 | 0 | 39.5 | 2019-08-09 17:55 | 2019-08-10 08:30 | 19377.0568 | [6 empty] | 19377 | 14213 | 1.51 | 0 | 0 | 10.27 | 5455
TS5500Exc | SC\36\012\D | SC | 36 | 12 | D | 8 Coal Mining | 33.3 | 0 | 33.3 | 2019-08-09 21:43 | 2019-08-10 17:17 | 24643.9831 | [6 empty] | 24644 | 18389 | 1.53 | 0 | 0 | 7.6 | 5745
TS5500Shv | GG\06\002\B | GG | 6 | 2 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2019-08-10 08:30 | 2019-08-11 20:42 | 48099.8985 | [6 empty] | 48100 | 35070 | 1.41 | 0 | 0 | 10.56 | 5506
PH4100XPC#1 | GG\05\006\D | GG | 5 | 6 | D | 1 Prestrip - Thick | 100 | 59.5728 | 59.5728 | 2019-08-10 12:19 | 2019-08-12 11:07 | 115010.3593 | 115010 | [7 empty] | 0 | 0 | 10.82 | 5.73 | 5883.88
DRE2 | BW\29\005\D | BW | 29 | 5 | D | 6 DL | 100 | 100 | 100 | 2019-08-10 13:23 | 2019-08-13 09:13 | 234282.2949 |  |  |  | 7712 | 234282 | 141809 |  |  | 0 | 22.28 | 0 | 5.85 | 5898.75
TS5500Exc | SC\36\016\D | SC | 36 | 16 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-08-10 17:17 | 2019-08-13 23:05 | 97994.6563 | [6 empty] | 97995 | 73407 | 4.22 | 0 | 0 | 6.96 | 5799
PH4100A | GG\05\006\D | GG | 5 | 6 | D | 1 Prestrip - Thick | 100 | 40.4272 | 40.4272 | 2019-08-10 17:42 | 2019-08-12 11:07 | 78047.9912 | 78048 | [7 empty] | 0 | 0 | 7.34 | 5.73 | 5883.88
TS6060#1 | BW\29\006\D | BW | 29 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-08-11 12:07 | 2019-08-13 06:34 | 62615.1295 | [6 empty] | 62615 | 47273 | 4.73 | 0 | 0 | 5.67 | 5915
TS5500Shv | GG\06\003\X1 | GG | 6 | 3 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2019-08-11 20:42 | 2019-08-12 11:04 | 19099.7571 | [6 empty] | 19100 | 14253 | 0.7 | 0 | 0 | 8.84 | 5534
TS5500Shv | GG\06\004\X1 | GG | 6 | 4 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2019-08-12 11:04 | 2019-08-13 00:16 | 17536.1468 | [6 empty] | 17536 | 12969 | 0.64 | 0 | 0 | 10.3 | 5403
PH4100XPC#1 | GG\06\005\D | GG | 6 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-08-12 11:07 | 2019-08-18 09:23 | 349646.4784 | 349646 | [7 empty] | 0 | 0 | 22.49 | 5.84 | 5872.84
PH4100A | GG\06\002\D | GG | 6 | 2 | D | 1 Prestrip - Thick | 100 | 78.5919 | 78.5919 | 2019-08-12 11:07 | 2019-08-17 03:26 | 211692.3726 | 211692 | [7 empty] | 0 | 0 | 15.85 | 5.66 | 5888.11
TS Fleet 5 | GG\06\002\D | GG | 6 | 2 | D | 1 Prestrip - Thick | 21.4081 | 21.4081 | 21.4081 | 2019-08-12 23:39 | 2019-08-14 03:51 | 57664.1454 | 57664 | [7 empty] | 0 | 0 | 4.32 | 5.66 | 5888.11
TS5500Shv | GG\05\006\D | GG | 5 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2019-08-13 00:16 | 2019-08-15 15:05 | 73367.1945 |  |  | 73367 | [5 empty] | 0 | 0 | 0 | 5.73 | 5883.88
TS6060#1 | GG\08\007\B | GG | 8 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-08-13 06:34 | 2019-08-14 17:11 | 51030.3503 | [6 empty] | 51030 | 37342 | 3.78 | 0 | 0 | 10.64 | 5387
DRE2 | BW\29\009\D | BW | 29 | 9 | D | 6 DL | 100 | 100 | 100 | 2019-08-13 09:13 | 2019-08-16 03:30 | 228884.8527 |  |  |  | 10241 | 228885 | 194578 |  |  | 0 | 20.47 | 0 | 5.39 | 5938.71
TS5500Exc | DT\27\004\D | DT | 27 | 4 | D | 8 Coal Mining | 85.8 | 0 | 85.8 | 2019-08-13 23:05 | 2019-08-16 19:56 | 86720.1822 | [6 empty] | 86720 | 64952 | 4.06 | 0 | 0 | 6.75 | 5821
TS Fleet 5 | GG\06\003\X2 | GG | 6 | 3 | X2 | 1 Prestrip - Thick | 30.1324 | 0 | 30.1324 | 2019-08-14 03:51 | 2019-08-15 13:20 | 68437.0517 | 68437 | [7 empty] | 0 | 0 | 3.37 | 0 | 0
TS6060#1 | GG\08\007\D | GG | 8 | 7 | D | 1 Prestrip - Thick | 33.0588 | 33.0588 | 33.0588 | 2019-08-14 17:11 | 2019-08-17 11:09 | 74171.8372 | 74172 | [7 empty] | 0 | 0 | 6.62 | 6.21 | 5842.87
TS Fleet 5 | GG\06\006\B | GG | 6 | 6 | B | 1 Prestrip - Thick | 26.4256 | 26.4256 | 26.4256 | 2019-08-15 13:20 | 2019-08-20 03:54 | 225992.0819 | 225992 | [7 empty] | 0 | 0 | 16.63 | 10.55 | 5403.77
TS5500Shv | MW\32\010\X | MW | 32 | 10 | X | 8 Coal Mining | 60.9 | 0 | 60.9 | 2019-08-15 15:05 | 2019-08-16 04:09 | 17363.2549 | [6 empty] | 17363 | 12665 | 0.8 | 0 | 0 | 12.24 | 5208
DRE2 | BW\29\010\D | BW | 29 | 10 | D | 6 DL | 100 | 100 | 100 | 2019-08-16 03:30 | 2019-08-18 22:03 | 229851.4099 |  |  |  | 10284 | 229851 | 195399 |  |  | 0 | 20.57 | 0 | 5.68 | 5913.92
TS5500Shv | DT\27\004\D | DT | 27 | 4 | D | 8 Coal Mining | 5.2 | 0 | 5.2 | 2019-08-16 04:09 | 2019-08-16 08:05 | 5217.93 | [6 empty] | 5218 | 3908 | 0.24 | 0 | 0 | 6.75 | 5821
TS5500Shv | GG\06\006\B | GG | 6 | 6 | B | 1 Prestrip - Thick | 5.0933 | 5.0933 | 5.0933 | 2019-08-16 08:05 | 2019-08-17 21:17 | 43558.0472 | 43558 | [7 empty] | 0 | 0 | 3.21 | 10.55 | 5403.77
TS5500Exc | DT\27\004\D | DT | 27 | 4 | D | 8 Coal Mining | 9 | 0 | 9 | 2019-08-16 19:56 | 2019-08-17 03:10 | 9115.1037 | [6 empty] | 9115 | 6827 | 0.43 | 0 | 0 | 6.75 | 5821
TS5500Exc | DT\27\006\D | DT | 27 | 6 | D | 8 Coal Mining | 29.7 | 0 | 29.7 | 2019-08-17 03:10 | 2019-08-18 05:42 | 33407.2526 | [6 empty] | 33407 | 24961 | 1.38 | 0 | 0 | 6.89 | 5807
PH4100A | GG\06\003\X2 | GG | 6 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 69.8676 | 2019-08-17 03:26 | 2019-08-20 15:37 | 158683.8123 | 158684 | [7 empty] | 0 | 0 | 7.82 | 0 | 0
DRE1 | SC\36\018\D | SC | 36 | 18 | D | 6 DL | 100 | 0 | 100 | 2019-08-17 07:15 | 2019-08-24 00:04 | 576750.3479 |  |  |  | 41017 | 576750 | 414732 |  |  | 0 | 37.3 | 0 | 7.02 | 5793.77
TS6060#1 | GG\05\006\D | GG | 5 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-08-17 11:09 | 2019-08-20 00:39 | 90689.3457 | [6 empty] | 90689 | 68502 | 4.71 | 0 | 0 | 5.73 | 5884
TS5500Shv | GG\06\002\D | GG | 6 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2019-08-17 21:17 | 2019-08-21 01:19 | 88810.6583 |  |  | 88811 | [5 empty] | 0 | 0 | 0 | 5.66 | 5888.11
TS5500Exc | SC\36\017\D | SC | 36 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-08-18 05:42 | 2019-08-21 15:06 | 102538.1569 | [6 empty] | 102538 | 76875 | 4.44 | 0 | 0 | 6.63 | 5829
PH4100XPC#1 | GG\06\004\X2 | GG | 6 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2019-08-18 09:23 | 2019-08-22 10:47 | 239374.614 | 239375 | [7 empty] | 0 | 0 | 11.81 | 0 | 0
DRE2 | BW\29\011\D | BW | 29 | 11 | D | 6 DL | 100 | 100 | 100 | 2019-08-18 22:03 | 2019-08-21 20:21 | 242768.2922 |  |  |  | 10862 | 242768 | 206380 |  |  | 0 | 21.72 | 0 | 5.85 | 5898.16
TS6060#1 | BW\29\005\D | BW | 29 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2019-08-20 00:39 | 2019-08-21 15:09 | 43276.4892 |  |  | 43276 | [5 empty] | 0 | 0 | 0 | 5.85 | 5898.75
TS Fleet 5 | GG\06\006\B | GG | 6 | 6 | B | 1 Prestrip - Thick | 3.0564 | 3.0564 | 3.0564 | 2019-08-20 03:54 | 2019-08-20 16:41 | 26138.3508 | 26138 | [7 empty] | 0 | 0 | 1.92 | 10.55 | 5403.77
PH4100A | GG\06\003\B | GG | 6 | 3 | B | 1 Prestrip - Thick | 100 | 63.754 | 63.754 | 2019-08-20 15:37 | 2019-08-25 00:12 | 197124.9452 | 197125 | [7 empty] | 0 | 0 | 9.8 | 9.09 | 5618.98
TS Fleet 5 | GG\06\003\B | GG | 6 | 3 | B | 1 Prestrip - Thick | 30.1324 | 30.1324 | 30.1324 | 2019-08-20 16:41 | 2019-08-22 14:16 | 93168.3458 | 93168 | [7 empty] | 0 | 0 | 4.63 | 9.09 | 5618.98
TS5500Shv | GG\06\002\D | GG | 6 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-08-21 01:19 | 2019-08-24 08:01 | 104570.1971 | [6 empty] | 104570 | 78796 | 4.59 | 0 | 0 | 5.66 | 5888
TS5500Exc | MW\30\008\A | MW | 30 | 8 | A | 1 Prestrip - Thick | 23.549 | 23.549 | 23.549 | 2019-08-21 15:06 | 2019-08-25 14:15 | 84588.9551 | 84589 | [7 empty] | 0 | 0 | 8.19 | 11.21 | 5367.89
TS6060#1 | RS\12\005\X | RS | 12 | 5 | X | 1 Prestrip - Thick | 57.9548 | 57.9548 | 57.9548 | 2019-08-21 15:09 | 2019-08-28 22:26 | 190453.1346 | 190453 | [7 empty] | 0 | 0 | 18.84 | 12.94 | 5161.48
DRE2 | DT\29\001\D | DT | 29 | 1 | D | 6 DL | 100 | 0 | 100 | 2019-08-21 20:21 | 2019-08-28 11:50 | 550791.366 |  |  |  | 31435 | 550791 | 417640 |  |  | 0 | 30 | 0 | 6.06 | 5880.2
PH4100XPC#1 | GG\06\004\B | GG | 6 | 4 | B | 1 Prestrip - Thick | 100 | 69.3481 | 69.3481 | 2019-08-22 10:47 | 2019-08-26 10:08 | 234291.7102 | 234292 | [7 empty] | 0 | 0 | 11.59 | 9.53 | 5547.67
TS Fleet 5 | GG\07\002\B | GG | 7 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-08-22 14:16 | 2019-08-28 02:34 | 270418.0667 | 270418 | [7 empty] | 0 | 0 | 9.53 | 10.14 | 5536.18
DRE1 | SC\36\019\D | SC | 36 | 19 | D | 6 DL | 100 | 0 | 100 | 2019-08-24 00:04 | 2019-08-31 10:15 | 639036.8705 |  |  |  | 48596 | 639037 | 437364 |  |  | 0 | 40 | 0 | 7.25 | 5774.5
TS5500Shv | GG\06\003\B | GG | 6 | 3 | B | 1 Prestrip - Thick | 15.0711 | 6.1136 | 6.1136 | 2019-08-24 08:01 | 2019-08-25 00:12 | 18902.8923 | 18903 | [7 empty] | 0 | 0 | 0.94 | 9.09 | 5618.98
PH4100A | GG\06\004\B | GG | 6 | 4 | B | 1 Prestrip - Thick | 100 | 18.9245 | 18.9245 | 2019-08-25 00:12 | 2019-08-26 10:08 | 63936.2001 | 63936 | [7 empty] | 0 | 0 | 3.16 | 9.53 | 5547.67
TS5500Shv | GG\06\004\B | GG | 6 | 4 | B | 1 Prestrip - Thick | 17.9896 | 11.7274 | 11.7274 | 2019-08-25 00:12 | 2019-08-26 10:08 | 39620.905 | 39621 | [7 empty] | 0 | 0 | 1.96 | 9.53 | 5547.67
TS5500Exc | SC\36\018\D | SC | 36 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-08-25 14:15 | 2019-08-27 21:14 | 69271.5766 | [6 empty] | 69272 | 51892 | 4.33 | 0 | 0 | 7.02 | 5794
TS5500Shv | GG\06\005\D | GG | 6 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2019-08-26 10:08 | 2019-08-29 23:43 | 99969.3944 |  |  | 99969 | [5 empty] | 0 | 0 | 0 | 5.84 | 5872.84
PH4100A | GG\06\006\B | GG | 6 | 6 | B | 1 Prestrip - Thick | 100 | 28.1296 | 28.1296 | 2019-08-26 10:08 | 2019-08-31 14:05 | 240564.6402 | 240565 | [7 empty] | 0 | 0 | 17.7 | 10.55 | 5403.77
PH4100XPC#1 | GG\06\006\B | GG | 6 | 6 | B | 1 Prestrip - Thick | 100 | 36.7097 | 36.7097 | 2019-08-26 10:08 | 2019-08-31 14:05 | 313941.4181 | 313941 | [7 empty] | 0 | 0 | 23.1 | 10.55 | 5403.77
TS5500Exc | GG\06\004\B | GG | 6 | 4 | B | 8 Coal Mining | 100 | 0 | 57.3 | 2019-08-27 21:14 | 2019-08-29 19:33 | 58334.395 | [6 empty] | 58334 | 42855 | 2.14 | 0 | 0 | 9.53 | 5548
TS Fleet 5 | GG\07\003\X1 | GG | 7 | 3 | X1 | 1 Prestrip - Thick | 71.9023 | 21.0726 | 21.0726 | 2019-08-28 02:34 | 2019-09-01 | 190951.4765 | 190951 | [7 empty] | 0 | 0 | 9.31 | 8.83 | 5532.5
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2019-08-28 11:50 | 2019-08-30 11:50
TS6060#1 | GG\06\004\B | GG | 6 | 4 | B | 8 Coal Mining | 100 | 0 | 30.6 | 2019-08-28 22:26 | 2019-08-29 19:33 | 31132.7209 | [6 empty] | 31133 | 22871 | 1.14 | 0 | 0 | 9.53 | 5548
TS6060#1 | RS\12\006\X | RS | 12 | 6 | X | 1 Prestrip - Thick | 44.7881 | 15.035 | 15.035 | 2019-08-29 19:33 | 2019-09-01 | 57108.0798 | 57108 | [7 empty] | 0 | 0 | 5.65 | 11.06 | 5276.49
TS5500Exc | MW\30\008\A | MW | 30 | 8 | A | 1 Prestrip - Thick | 76.451 | 12.9793 | 12.9793 | 2019-08-29 19:33 | 2019-09-01 | 46622.3935 | 46622 | [7 empty] | 0 | 0 | 4.51 | 11.21 | 5367.89
TS5500Shv | GG\06\006\B | GG | 6 | 6 | B | 1 Prestrip - Thick | 0.5853 | 0.5853 | 0.5853 | 2019-08-29 23:43 | 2019-08-30 03:59 | 5005.4965 | 5005 | [7 empty] | 0 | 0 | 0.37 | 10.55 | 5403.77
TS5500Shv | GG\09\006\X2 | GG | 9 | 6 | X2 | 1 Prestrip - Thick | 1.0934 | 0 | 1.0934 | 2019-08-30 03:59 | 2019-08-30 10:00 | 7032.6021 | 7033 | [7 empty] | 0 | 0 | 0.59 | 0 | 0
TS5500Shv | GG\09\007\X1 | GG | 9 | 7 | X1 | 1 Prestrip - Thick | 20.5557 | 10.2332 | 10.2332 | 2019-08-30 10:00 | 2019-09-01 | 44156.1522 | 44156 | [7 empty] | 0 | 0 | 4.3 | 11.07 | 5384.11
DRE2 | MW\26\003\D | MW | 26 | 3 | D | 6 DL | 100 | 22.8442 | 22.8442 | 2019-08-30 11:50 | 2019-09-01 | 124855.746 |  |  |  | 7456 | 124856 | 88139 |  |  | 0 | 26.11 | 0 | 6.48 | 5843.05
DRE1 | SC\36\020\D | SC | 36 | 20 | D | 6 DL | 100 | 0 | 7.7604 | 2019-08-31 10:15 | 2019-09-01 | 49257.4433 |  |  |  | 3746 | 49257 | 33712 |  |  | 0 | 40 | 0 | 7.22 | 5777.18
PH4100A | SC\37\012\D | SC | 37 | 12 | D | 1 Prestrip - Thick | 100 | 17.7829 | 17.7829 | 2019-08-31 14:05 | 2019-09-01 | 18430.4209 | 18430 | [7 empty] | 0 | 0 | 1.6 | 7.56 | 5748.56
PH4100XPC#1 | GG\08\007\D | GG | 8 | 7 | D | 1 Prestrip - Thick | 100 | 10.8507 | 10.8507 | 2019-08-31 14:05 | 2019-09-01 | 24344.9056 | 24345 | [7 empty] | 0 | 0 | 2.17 | 6.21 | 5842.87
| EOP 68 : 2019\Aug | EOP 68 : 2019 | Aug | [6 empty] | 2019-09-01 | 2019-09-01 |  | 5728230 |  | 305424 | 315042 | 5071790 | 3715014 | 1424700 | 1064623 | 71.52 | 0 | 389.74 | 7.18 | 5763.99
TS Fleet 5 | GG\07\003\X1 | GG | 7 | 3 | X1 | 1 Prestrip - Thick | 71.9023 | 50.8296 | 50.8296 | 2019-09-01 | 2019-09-10 12:28 | 460596.9554 | 460597 | [7 empty] | 0 | 0 | 22.45 | 8.83 | 5532.5
DRE1 | SC\36\020\D | SC | 36 | 20 | D | 6 DL | 100 | 0 | 92.2396 | 2019-09-01 | 2019-09-07 19:15 | 585472.1929 |  |  |  | 44523 | 585472 | 400703 |  |  | 0 | 40 | 0 | 7.22 | 5777.18
PH4100A | SC\37\012\D | SC | 37 | 12 | D | 1 Prestrip - Thick | 100 | 82.2171 | 82.2171 | 2019-09-01 | 2019-09-02 22:24 | 85210.5715 | 85211 | [7 empty] | 0 | 0 | 7.4 | 7.56 | 5748.56
DRE2 | MW\26\003\D | MW | 26 | 3 | D | 6 DL | 100 | 77.1558 | 77.1558 | 2019-09-01 | 2019-09-06 02:06 | 421696.6202 |  |  |  | 25184 | 421697 | 297687 |  |  | 0 | 26.11 | 0 | 6.48 | 5843.05
PH4100XPC#1 | GG\08\007\D | GG | 8 | 7 | D | 1 Prestrip - Thick | 100 | 56.0905 | 56.0905 | 2019-09-01 | 2019-09-03 03:53 | 125846.4262 | 125846 | [7 empty] | 0 | 0 | 11.24 | 6.21 | 5842.87
TS5500Shv | GG\09\007\X1 | GG | 9 | 7 | X1 | 1 Prestrip - Thick | 20.5557 | 10.3225 | 10.3225 | 2019-09-01 | 2019-09-02 14:50 | 44541.1491 | 44541 | [7 empty] | 0 | 0 | 4.34 | 11.07 | 5384.11
TS6060#1 | RS\12\006\X | RS | 12 | 6 | X | 1 Prestrip - Thick | 44.7881 | 29.753 | 29.753 | 2019-09-01 | 2019-09-05 09:13 | 113011.7938 | 113012 | [7 empty] | 0 | 0 | 11.18 | 11.06 | 5276.49
TS5500Exc | MW\30\008\A | MW | 30 | 8 | A | 1 Prestrip - Thick | 76.451 | 63.4717 | 63.4717 | 2019-09-01 | 2019-09-11 16:26 | 227993.1454 | 227993 | [7 empty] | 0 | 0 | 22.07 | 11.21 | 5367.89
TS5500Shv | MW\30\005\B | MW | 30 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-09-02 14:50 | 2019-09-03 21:33 | 40248.3406 | [6 empty] | 40248 | 29809 | 2.95 | 0 | 0 | 8.87 | 5621
PH4100A | SC\37\013\D | SC | 37 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-09-02 22:24 | 2019-09-06 13:18 | 158390.8487 | 158391 | [7 empty] | 0 | 0 | 13.45 | 7.72 | 5733.89
PH4100XPC#1 | GG\07\005\X1 | GG | 7 | 5 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-09-03 03:53 | 2019-09-21 16:56 | 1081270.725 | 1081271 | [7 empty] | 0 | 0 | 49.68 | 12.17 | 5241.03
TS5500Shv | MW\31\011\X | MW | 31 | 11 | X | 8 Coal Mining | 100 | 0 | 100 | 2019-09-03 21:33 | 2019-09-04 06:42 | 11976.4322 | [6 empty] | 11976 | 8728 | 1.24 | 0 | 0 | 12.35 | 5184
TS5500Shv | GG\06\003\B | GG | 6 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-09-04 06:42 | 2019-09-07 12:25 | 101842.3428 | [6 empty] | 101842 | 74820 | 3.74 | 0 | 0 | 9.09 | 5619
TS6060#1 | GG\08\007\D | GG | 8 | 7 | D | 7 PostStrip | 100 | 0 | 100 | 2019-09-05 09:13 | 2019-09-08 04:29 | 74595.135 |  |  | 74595 | [5 empty] | 0 | 0 | 0 | 6.21 | 5842.87
DRE2 | MW\26\004\D | MW | 26 | 4 | D | 6 DL | 100 | 100 | 100 | 2019-09-06 02:06 | 2019-09-12 02:25 | 498362.6697 |  |  |  | 21735 | 498363 | 359586 |  |  | 0 | 23.8 | 0 | 6.32 | 5856.08
PH4100A | SC\37\014\D | SC | 37 | 14 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-09-06 13:18 | 2019-09-10 23:48 | 193431.6335 | 193432 | [7 empty] | 0 | 0 | 16.34 | 7.69 | 5735.25
TS5500Shv | GG\06\004\B | GG | 6 | 4 | B | 8 Coal Mining | 60.1 | 0 | 12.2 | 2019-09-07 12:25 | 2019-09-07 21:52 | 12386.1014 | [6 empty] | 12386 | 9099 | 0.45 | 0 | 0 | 9.53 | 5548
DRE1 | SC\36\021\D | SC | 36 | 21 | D | 6 DL | 100 | 0 | 100 | 2019-09-07 19:15 | 2019-09-15 02:51 | 629777.8146 |  |  |  | 47892 | 629778 | 431027 |  |  | 0 | 40 | 0 | 7.14 | 5785.71
TS5500Shv | MW\30\006\A | MW | 30 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-09-07 21:52 | 2019-09-09 01:25 | 36105.3297 | [6 empty] | 36105 | 26585 | 2.63 | 0 | 0 | 10.71 | 5410
TS6060#1 | GG\06\005\D | GG | 6 | 5 | D | 8 Coal Mining | 100 | 0 | 68.2 | 2019-09-08 04:29 | 2019-09-10 13:42 | 83219.027 | [6 empty] | 83219 | 62759 | 3.14 | 0 | 0 | 5.84 | 5873
TS5500Shv | GG\06\005\D | GG | 6 | 5 | D | 8 Coal Mining | 31.8 | 0 | 31.8 | 2019-09-09 01:25 | 2019-09-10 07:05 | 38874.1898 | [6 empty] | 38874 | 29317 | 1.47 | 0 | 0 | 5.84 | 5873
TS5500Shv | MW\26\003\D | MW | 26 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-09-10 07:05 | 2019-09-13 09:11 | 97092.8793 | [6 empty] | 97093 | 73417 | 4.59 | 0 | 0 | 6.48 | 5843
TS Fleet 5 | GG\07\003\X1 | GG | 7 | 3 | X1 | 1 Prestrip - Thick | 28.0977 | 28.0977 | 28.0977 | 2019-09-10 12:28 | 2019-09-15 18:45 | 254610.0291 | 254610 | [7 empty] | 0 | 0 | 12.41 | 8.83 | 5532.5
TS6060#1 | GG\06\006\B | GG | 6 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-09-10 13:42 | 2019-09-13 00:07 | 84949.1553 | [6 empty] | 84949 | 62239 | 3.83 | 0 | 0 | 10.55 | 5404
PH4100A | GG\06\003\D | GG | 6 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-09-10 23:48 | 2019-09-17 14:46 | 295707.3279 | 295707 | [7 empty] | 0 | 0 | 19.79 | 5.62 | 5890.17
TS5500Exc | MW\30\006\B | MW | 30 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-09-11 16:26 | 2019-09-14 00:05 | 49207.7381 | 49208 | [7 empty] | 0 | 0 | 4.89 | 8.79 | 5637.14
DRE2 | MW\26\005\D | MW | 26 | 5 | D | 6 DL | 100 | 100 | 100 | 2019-09-12 02:25 | 2019-09-19 03:29 | 583879.6893 |  |  |  | 34870 | 583880 | 412177 |  |  | 0 | 27.88 | 0 | 6.2 | 5865.86
TS6060#1 | MW\26\004\D | MW | 26 | 4 | D | 8 Coal Mining | 100 | 0 | 70.9 | 2019-09-13 00:07 | 2019-09-14 21:39 | 66242.5402 | [6 empty] | 66243 | 50166 | 3.14 | 0 | 0 | 6.32 | 5856
TS5500Shv | MW\30\007\A | MW | 30 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2019-09-13 09:11 | 2019-09-14 20:48 | 46670.067 | [6 empty] | 46670 | 34415 | 3.38 | 0 | 0 | 10.65 | 5418
TS5500Exc | MW\26\004\D | MW | 26 | 4 | D | 8 Coal Mining | 100 | 0 | 29.1 | 2019-09-14 00:05 | 2019-09-14 21:39 | 27181.6866 | [6 empty] | 27182 | 20585 | 1.29 | 0 | 0 | 6.32 | 5856
TS5500Shv | MW\30\006\B | MW | 30 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-09-14 20:48 | 2019-09-16 03:54 | 40758.1026 | [6 empty] | 40758 | 30191 | 3.01 | 0 | 0 | 8.79 | 5637
TS6060#1 | GG\08\007\D | GG | 8 | 7 | D | 8 Coal Mining | 5.1 | 0 | 5.1 | 2019-09-14 21:39 | 2019-09-15 01:04 | 4959.5777 | [6 empty] | 4960 | 3731 | 0.25 | 0 | 0 | 6.21 | 5843
TS5500Exc | SC\36\019\D | SC | 36 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-09-14 21:39 | 2019-09-17 05:31 | 70369.8655 | [6 empty] | 70370 | 52589 | 4.38 | 0 | 0 | 7.25 | 5775
TS6060#1 | DT\29\001\D | DT | 29 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-09-15 01:04 | 2019-09-17 15:28 | 90762.1715 | [6 empty] | 90762 | 68688 | 4.7 | 0 | 0 | 6.06 | 5880
DRE1 | SC\36\022\D | SC | 36 | 22 | D | 6 DL | 100 | 0 | 100 | 2019-09-15 02:51 | 2019-09-21 09:32 | 540396.922 |  |  |  | 38432 | 540397 | 388590 |  |  | 0 | 35.78 | 0 | 7.27 | 5774.56
TS Fleet 5 | GG\07\004\X1 | GG | 7 | 4 | X1 | 1 Prestrip - Thick | 100 | 77.4243 | 77.4243 | 2019-09-15 18:45 | 2019-10-01 | 736313.0155 | 736313 | [7 empty] | 0 | 0 | 36.61 | 9.93 | 5430.64
TS5500Shv | GG\07\002\B | GG | 7 | 2 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2019-09-16 03:54 | 2019-09-18 | 57784.2371 | [6 empty] | 57784 | 42251 | 1.49 | 0 | 0 | 10.14 | 5536
TS5500Exc | SC\36\020\D | SC | 36 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-09-17 05:31 | 2019-09-19 15:07 | 72538.6044 | [6 empty] | 72539 | 54083 | 4.51 | 0 | 0 | 7.22 | 5777
PH4100A | GG\06\004\D | GG | 6 | 4 | D | 1 Prestrip - Thick | 100 | 78.3702 | 78.3702 | 2019-09-17 14:46 | 2019-09-22 19:18 | 231615.2037 | 231615 | [7 empty] | 0 | 0 | 15.5 | 5.7 | 5881.72
TS6060#1 | GG\08\007\D | GG | 8 | 7 | D | 8 Coal Mining | 94.9 | 0 | 94.9 | 2019-09-17 15:28 | 2019-09-20 06:51 | 92174.8312 | [6 empty] | 92175 | 69349 | 4.58 | 0 | 0 | 6.21 | 5843
TS5500Shv | GG\06\003\D | GG | 6 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2019-09-18 | 2019-09-21 14:45 | 99954.1969 |  |  | 99954 | [5 empty] | 0 | 0 | 0 | 5.62 | 5890.17
DRE2 | MW\26\006\D | MW | 26 | 6 | D | 6 DL | 100 | 100 | 100 | 2019-09-19 03:29 | 2019-09-26 16:43 | 625897.0921 |  |  |  | 37379 | 625897 | 441838 |  |  | 0 | 29.97 | 0 | 6.5 | 5839.64
TS5500Exc | MW\30\007\B | MW | 30 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-09-19 15:07 | 2019-09-22 06:21 | 55930.1288 | 55930 | [7 empty] | 0 | 0 | 5.55 | 9.62 | 5540.46
TS6060#1 | BW\29\005\D | BW | 29 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-09-20 06:51 | 2019-09-21 20:18 | 54461.0643 | [6 empty] | 54461 | 41018 | 4.77 | 0 | 0 | 5.85 | 5899
DRE1 | SC\36\023\D | SC | 36 | 23 | D | 6 DL | 100 | 0 | 100 | 2019-09-21 09:32 | 2019-09-29 02:08 | 661994.7278 |  |  |  | 29232 | 661995 | 325487 |  |  | 0 | 32.66 | 0 | 7.2 | 5781.5
TS5500Shv | GG\06\003\D | GG | 6 | 3 | D | 8 Coal Mining | 100 | 0 | 88 | 2019-09-21 14:45 | 2019-09-24 22:43 | 104783.2716 | [6 empty] | 104783 | 78956 | 3.95 | 0 | 0 | 5.62 | 5890
PH4100XPC#1 | GG\06\004\D | GG | 6 | 4 | D | 1 Prestrip - Thick | 100 | 21.6298 | 21.6298 | 2019-09-21 16:56 | 2019-09-22 19:18 | 63924.7972 | 63925 | [7 empty] | 0 | 0 | 4.28 | 5.7 | 5881.72
TS6060#1 | BW\29\009\D | BW | 29 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-09-21 20:18 | 2019-09-23 14:40 | 61629.7318 | [6 empty] | 61630 | 46754 | 4.68 | 0 | 0 | 5.39 | 5939
TS5500Exc | SC\36\021\D | SC | 36 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-09-22 06:21 | 2019-09-24 17:46 | 74828.1065 | [6 empty] | 74828 | 55703 | 4.64 | 0 | 0 | 7.14 | 5786
PH4100A | GG\06\006\D | GG | 6 | 6 | D | 1 Prestrip - Thick | 100 | 43.4052 | 43.4052 | 2019-09-22 19:18 | 2019-09-26 01:25 | 145295.8946 | 145296 | [7 empty] | 0 | 0 | 9.02 | 5.83 | 5875.26
PH4100XPC#1 | GG\06\006\D | GG | 6 | 6 | D | 1 Prestrip - Thick | 100 | 56.5948 | 56.5948 | 2019-09-22 19:18 | 2019-09-26 01:25 | 189447.0987 | 189447 | [7 empty] | 0 | 0 | 11.76 | 5.83 | 5875.26
TS6060#1 | BW\29\010\D | BW | 29 | 10 | D | 8 Coal Mining | 100 | 0 | 75.2 | 2019-09-23 14:40 | 2019-09-24 22:43 | 46614.3171 | [6 empty] | 46614 | 35420 | 3.54 | 0 | 0 | 5.68 | 5914
TS5500Exc | SC\36\022\D | SC | 36 | 22 | D | 8 Coal Mining | 100 | 0 | 8.1 | 2019-09-24 17:46 | 2019-09-24 22:43 | 6248.0271 | [6 empty] | 6248 | 4640 | 0.39 | 0 | 0 | 7.27 | 5775
TS5500Shv | GG\06\004\D | GG | 6 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2019-09-24 22:43 | 2019-09-28 13:30 | 99970.9423 |  |  | 99971 | [5 empty] | 0 | 0 | 0 | 5.7 | 5881.72
TS6060#1 | RS\12\006\X | RS | 12 | 6 | X | 1 Prestrip - Thick | 55.2119 | 41.0793 | 41.0793 | 2019-09-24 22:43 | 2019-10-01 | 156032.6661 | 156033 | [7 empty] | 0 | 0 | 15.44 | 11.06 | 5276.49
TS5500Exc | MW\30\009\A | MW | 30 | 9 | A | 1 Prestrip - Thick | 11.5986 | 11.5986 | 11.5986 | 2019-09-24 22:43 | 2019-09-27 08:55 | 51713.7242 | 51714 | [7 empty] | 0 | 0 | 5.17 | 11.81 | 5341.92
PH4100A | SC\37\015\D | SC | 37 | 15 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-09-26 01:25 | 2019-09-29 22:37 | 168974.6577 | 168975 | [7 empty] | 0 | 0 | 18.37 | 7.39 | 5760.01
PH4100XPC#1 | GG\07\006\B | GG | 7 | 6 | B | 1 Prestrip - Thick | 100 | 20.2513 | 20.2513 | 2019-09-26 01:25 | 2019-10-01 | 299635.9329 | 299636 | [7 empty] | 0 | 0 | 13.76 | 10.81 | 5368.44
DRE2 | MW\26\007\D | MW | 26 | 7 | D | 6 DL | 100 | 54.3392 | 54.3392 | 2019-09-26 16:43 | 2019-10-01 | 356647.9287 |  |  |  | 21299 | 356648 | 251768 |  |  | 0 | 31.42 | 0 | 6.84 | 5810.7
TS5500Exc | MW\30\009\A | MW | 30 | 9 | A | 1 Prestrip - Thick | 88.4014 | 17.3579 | 17.3579 | 2019-09-27 08:55 | 2019-10-01 | 77392.4598 | 77392 | [7 empty] | 0 | 0 | 7.74 | 11.81 | 5341.92
TS5500Shv | GG\06\006\D | GG | 6 | 6 | D | 7 PostStrip | 100 | 0 | 63.5007 | 2019-09-28 13:30 | 2019-10-01 | 67381.1714 |  |  | 67381 | [5 empty] | 0 | 0 | 0 | 5.83 | 5875.26
DRE1 | SC\37\010\D | SC | 37 | 10 | D | 6 DL | 100 | 0 | 19.2204 | 2019-09-29 02:08 | 2019-10-01 | 164476.3426 |  |  |  | 9232 | 164476 | 71586 |  |  | 0 | 40 | 0 | 7.76 | 5732.36
PH4100A | SC\37\016\D | SC | 37 | 16 | D | 1 Prestrip - Thick | 100 | 29.6854 | 29.6854 | 2019-09-29 22:37 | 2019-10-01 | 46530.1152 | 46530 | [7 empty] | 0 | 0 | 3.61 | 7.04 | 5791.46
| EOP 69 : 2019\Sep | EOP 69 : 2019 | Sep | [6 empty] | 2019-10-01 | 2019-10-01 |  | 5312624 |  | 341901 | 309777 | 5068602 | 3380449 | 1424700 | 1065311 | 76.72 | 0 | 342.05 | 7.09 | 5771.65
TS Fleet 5 | GG\07\004\X1 | GG | 7 | 4 | X1 | 1 Prestrip - Thick | 100 | 22.5757 | 22.5757 | 2019-10-01 | 2019-10-05 16:45 | 214697.2281 | 214697 | [7 empty] | 0 | 0 | 10.68 | 9.93 | 5430.64
DRE1 | SC\37\010\D | SC | 37 | 10 | D | 6 DL | 100 | 0 | 80.7796 | 2019-10-01 | 2019-10-09 03:17 | 691263.3726 |  |  |  | 38801 | 691263 | 300864 |  |  | 0 | 40 | 0 | 7.76 | 5732.36
PH4100A | SC\37\016\D | SC | 37 | 16 | D | 1 Prestrip - Thick | 100 | 70.3146 | 70.3146 | 2019-10-01 | 2019-10-03 14:37 | 110214.1553 | 110214 | [7 empty] | 0 | 0 | 8.56 | 7.04 | 5791.46
DRE2 | MW\26\007\D | MW | 26 | 7 | D | 6 DL | 100 | 45.6608 | 45.6608 | 2019-10-01 | 2019-10-04 15:55 | 299688.8121 |  |  |  | 17898 | 299689 | 211559 |  |  | 0 | 31.42 | 0 | 6.84 | 5810.7
PH4100XPC#1 | GG\07\006\B | GG | 7 | 6 | B | 1 Prestrip - Thick | 100 | 79.7487 | 79.7487 | 2019-10-01 | 2019-10-21 06:24 | 1179954.872 | 1179955 | [7 empty] | 0 | 0 | 54.19 | 10.81 | 5368.44
TS5500Shv | GG\06\006\D | GG | 6 | 6 | D | 7 PostStrip | 100 | 0 | 36.4993 | 2019-10-01 | 2019-10-02 11:35 | 38729.7961 |  |  | 38730 | [5 empty] | 0 | 0 | 0 | 5.83 | 5875.26
TS6060#1 | RS\12\006\X | RS | 12 | 6 | X | 1 Prestrip - Thick | 55.2119 | 14.1327 | 14.1327 | 2019-10-01 | 2019-10-03 04:55 | 53680.5196 | 53681 | [7 empty] | 0 | 0 | 5.31 | 11.06 | 5276.49
TS5500Exc | MW\30\009\A | MW | 30 | 9 | A | 1 Prestrip - Thick | 88.4014 | 71.0435 | 71.0435 | 2019-10-01 | 2019-10-15 20:24 | 316756.7147 | 316757 | [7 empty] | 0 | 0 | 31.67 | 11.81 | 5341.92
TS5500Shv | GG\06\003\D | GG | 6 | 3 | D | 8 Coal Mining | 100 | 0 | 12 | 2019-10-02 11:35 | 2019-10-02 23:11 | 14354.3158 | [6 empty] | 14354 | 10816 | 0.54 | 0 | 0 | 5.62 | 5890
TS5500Shv | GG\06\004\D | GG | 6 | 4 | D | 8 Coal Mining | 3.9 | 0 | 3.9 | 2019-10-02 23:11 | 2019-10-03 02:48 | 4468.5304 | [6 empty] | 4469 | 3370 | 0.17 | 0 | 0 | 5.7 | 5882
TS5500Shv | GG\06\004\D | GG | 6 | 4 | D | 8 Coal Mining | 96.1 | 0 | 96.1 | 2019-10-03 02:48 | 2019-10-06 20:52 | 111477.1048 | [6 empty] | 111477 | 84068 | 4.2 | 0 | 0 | 5.7 | 5882
TS6060#1 | BW\29\010\D | BW | 29 | 10 | D | 8 Coal Mining | 100 | 0 | 24.8 | 2019-10-03 04:55 | 2019-10-03 16:06 | 15374.5276 | [6 empty] | 15375 | 11682 | 1.17 | 0 | 0 | 5.68 | 5914
PH4100A | SC\37\017\D | SC | 37 | 17 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-10-03 14:37 | 2019-10-07 02:28 | 148124.719 | 148125 | [7 empty] | 0 | 0 | 10.66 | 6.76 | 5817.84
TS6060#1 | BW\29\011\D | BW | 29 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-10-03 16:06 | 2019-10-05 12:07 | 60456.9376 | [6 empty] | 60457 | 45940 | 4.59 | 0 | 0 | 5.85 | 5898
DRE2 | MW\26\008\D | MW | 26 | 8 | D | 6 DL | 100 | 100 | 100 | 2019-10-04 15:55 | 2019-10-12 18:12 | 662268.5853 |  |  |  | 49505 | 662269 | 455644 |  |  | 0 | 31.58 | 0 | 7.04 | 5794.8
TS6060#1 | GG\06\006\D | GG | 6 | 6 | D | 8 Coal Mining | 54 | 0 | 54 | 2019-10-05 12:07 | 2019-10-07 16:45 | 72289.6753 | [6 empty] | 72290 | 54605 | 2.55 | 0 | 0 | 5.83 | 5875
TS Fleet 5 | GG\08\002\X1 | GG | 8 | 2 | X1 | 1 Prestrip - Thick | 20.8215 | 0 | 20.8215 | 2019-10-05 16:45 | 2019-10-19 10:02 | 626949.1766 | 626949 | [7 empty] | 0 | 0 | 16.15 | 0 | 0
TS5500Shv | GG\06\006\D | GG | 6 | 6 | D | 8 Coal Mining | 46 | 0 | 46 | 2019-10-06 20:52 | 2019-10-08 22:35 | 61522.303 | [6 empty] | 61522 | 46472 | 2.17 | 0 | 0 | 5.83 | 5875
PH4100A | SC\37\018\D | SC | 37 | 18 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-10-07 02:28 | 2019-10-13 00:59 | 252536.5887 | 252537 | [7 empty] | 0 | 0 | 14 | 6.67 | 5825.68
TS6060#1 | GG\07\002\B | GG | 7 | 2 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2019-10-07 16:45 | 2019-10-09 15:26 | 64134.1532 | [6 empty] | 64134 | 46894 | 1.65 | 0 | 0 | 10.14 | 5536
TS5500Shv | MW\26\005\D | MW | 26 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-10-08 22:35 | 2019-10-11 23:35 | 90337.7253 | [6 empty] | 90338 | 68078 | 4.25 | 0 | 0 | 6.2 | 5866
DRE1 | SC\37\011\D | SC | 37 | 11 | D | 6 DL | 100 | 0 | 100 | 2019-10-09 03:17 | 2019-10-16 13:27 | 630647.4994 |  |  |  | 47958 | 630647 | 431622 |  |  | 0 | 40 | 0 | 7.64 | 5741.8
TS6060#1 | GG\07\003\X1 | GG | 7 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2019-10-09 15:26 | 2019-10-10 19:47 | 38934.9516 | [6 empty] | 38935 | 29073 | 1.47 | 0 | 0 | 8.83 | 5533
TS6060#1 | GG\07\005\X1 | GG | 7 | 5 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2019-10-10 19:47 | 2019-10-11 17:01 | 29172.8986 | [6 empty] | 29173 | 21359 | 1.03 | 0 | 0 | 12.17 | 5241
TS6060#1 | GG\07\004\X1 | GG | 7 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2019-10-11 17:01 | 2019-10-12 19:57 | 36993.1145 | [6 empty] | 36993 | 27443 | 1.37 | 0 | 0 | 9.93 | 5431
TS5500Shv | GG\07\002\D | GG | 7 | 2 | D | 1 Prestrip - Thick | 55.6963 | 55.6963 | 55.6963 | 2019-10-11 23:35 | 2019-10-18 23:17 | 182461.2828 | 182461 | [7 empty] | 0 | 0 | 10.97 | 5.8 | 5876.04
DRE2 | MW\26\009\D | MW | 26 | 9 | D | 6 DL | 100 | 100 | 100 | 2019-10-12 18:12 | 2019-10-20 06:14 | 613636.0699 |  |  |  | 36647 | 613636 | 433183 |  |  | 0 | 29.3 | 0 | 6.23 | 5864.49
TS6060#1 | RS\12\007\X | RS | 12 | 7 | X | 1 Prestrip - Thick | 47.79 | 47.79 | 47.79 | 2019-10-12 19:57 | 2019-10-24 10:41 | 283968.4294 | 283968 | [7 empty] | 0 | 0 | 20.03 | 11 | 5276.88
PH4100A | SC\37\019\D | SC | 37 | 19 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-10-13 00:59 | 2019-10-17 17:35 | 197043.4302 | 197043 | [7 empty] | 0 | 0 | 16.49 | 7.12 | 5784.77
TS5500Exc | SC\36\022\D | SC | 36 | 22 | D | 8 Coal Mining | 100 | 0 | 91.9 | 2019-10-15 20:24 | 2019-10-18 04:26 | 70565.2771 | [6 empty] | 70565 | 52407 | 4.37 | 0 | 0 | 7.27 | 5775
DRE1 | SC\37\012\D | SC | 37 | 12 | D | 6 DL | 100 | 0 | 100 | 2019-10-16 13:27 | 2019-10-23 10:14 | 583283.6041 |  |  |  | 41482 | 583284 | 419430 |  |  | 0 | 38.67 | 0 | 7.56 | 5748.56
PH4100A | SC\37\020\D | SC | 37 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-10-17 17:35 | 2019-10-23 00:24 | 222293.1695 | 222293 | [7 empty] | 0 | 0 | 18.73 | 7.3 | 5769.7
TS5500Exc | MW\26\008\D | MW | 26 | 8 | D | 8 Coal Mining | 46.4 | 0 | 46.4 | 2019-10-18 04:26 | 2019-10-19 17:55 | 47221.3352 | [6 empty] | 47221 | 35228 | 2.2 | 0 | 0 | 7.04 | 5795
TS5500Shv | GG\07\002\D | GG | 7 | 2 | D | 1 Prestrip - Thick | 31.2325 | 26.5851 | 26.5851 | 2019-10-18 23:17 | 2019-10-22 07:20 | 87092.9911 | 87093 | [7 empty] | 0 | 0 | 5.24 | 5.8 | 5876.04
TS Fleet 5 | GG\07\005\X2 | GG | 7 | 5 | X2 | 1 Prestrip - Thick | 5.0996 | 0 | 5.0996 | 2019-10-19 10:02 | 2019-10-19 15:24 | 10212.7963 | 10213 | [7 empty] | 0 | 0 | 0.49 | 0 | 0
TS Fleet 5 | GG\07\004\X2 | GG | 7 | 4 | X2 | 1 Prestrip - Thick | 46.1185 | 0 | 46.1185 | 2019-10-19 15:24 | 2019-10-22 03:51 | 115108.7128 | 115109 | [7 empty] | 0 | 0 | 5.76 | 0 | 0
TS5500Exc | MW\30\007\B | MW | 30 | 7 | B | 8 Coal Mining | 50.4 | 0 | 50.4 | 2019-10-19 17:55 | 2019-10-20 09:42 | 19886.1642 | [6 empty] | 19886 | 14641 | 1.47 | 0 | 0 | 9.62 | 5540
DRE2 | MW\26\010\D | MW | 26 | 10 | D | 6 DL | 100 | 100 | 100 | 2019-10-20 06:14 | 2019-10-27 22:15 | 627238.2551 |  |  |  | 37459 | 627238 | 442785 |  |  | 0 | 29.98 | 0 | 5.53 | 5925.97
TS5500Exc | MW\30\008\A | MW | 30 | 8 | A | 8 Coal Mining | 50.4 | 0 | 50.4 | 2019-10-20 09:42 | 2019-10-21 04:39 | 23869.1347 | [6 empty] | 23869 | 17532 | 1.77 | 0 | 0 | 11.21 | 5368
TS5500Exc | SC\37\010\D | SC | 37 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2019-10-21 04:39 | 2019-10-24 00:20 | 59848.445 |  |  | 59848 | [5 empty] | 0 | 0 | 0 | 7.76 | 5732.36
PH4100XPC#1 | GG\07\002\D | GG | 7 | 2 | D | 1 Prestrip - Thick | 100 | 17.7186 | 17.7186 | 2019-10-21 06:24 | 2019-10-22 07:20 | 58046.2648 | 58046 | [7 empty] | 0 | 0 | 3.49 | 5.8 | 5876.04
TS Fleet 5 | GG\08\002\X1 | GG | 8 | 2 | X1 | 1 Prestrip - Thick | 45.6649 | 0 | 14.9319 | 2019-10-22 03:51 | 2019-11-01 | 449608.0861 | 449608 | [7 empty] | 0 | 0 | 11.58 | 0 | 0
TS5500Shv | GG\07\006\B | GG | 7 | 6 | B | 8 Coal Mining | 0.3 | 0 | 0.3 | 2019-10-22 07:20 | 2019-10-22 07:39 | 394.8596 | [6 empty] | 395 | 289 | 0.01 | 0 | 0 | 10.81 | 5368
PH4100XPC#1 | GG\07\003\X2 | GG | 7 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2019-10-22 07:20 | 2019-10-26 15:36 | 242761.339 | 242761 | [7 empty] | 0 | 0 | 12.27 | 0 | 0
TS5500Shv | GG\07\002\D | GG | 7 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2019-10-22 07:39 | 2019-10-26 14:04 | 111437.9434 |  |  | 111438 | [5 empty] | 0 | 0 | 0 | 5.8 | 5876.04
PH4100A | SC\37\021\D | SC | 37 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-10-23 00:24 | 2019-10-27 06:47 | 179545.0482 | 179545 | [7 empty] | 0 | 0 | 15.35 | 7.25 | 5775.41
DRE1 | SC\37\013\D | SC | 37 | 13 | D | 6 DL | 100 | 0 | 100 | 2019-10-23 10:14 | 2019-10-29 04:09 | 488203.013 |  |  |  | 27863 | 488203 | 370182 |  |  | 0 | 33.04 | 0 | 7.72 | 5733.89
TS5500Exc | SC\37\010\D | SC | 37 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-10-24 00:20 | 2019-10-26 13:28 | 77015.019 | [6 empty] | 77015 | 57697 | 4.81 | 0 | 0 | 7.76 | 5732
TS6060#1 | GG\07\006\B | GG | 7 | 6 | B | 8 Coal Mining | 0.4 | 0 | 0.4 | 2019-10-24 10:41 | 2019-10-24 11:01 | 438.2508 | [6 empty] | 438 | 321 | 0.01 | 0 | 0 | 10.81 | 5368
TS6060#1 | GG\07\006\B | GG | 7 | 6 | B | 8 Coal Mining | 99.3 | 0 | 99.3 | 2019-10-24 11:01 | 2019-10-28 00:43 | 117723.0944 | [6 empty] | 117723 | 86119 | 3.74 | 0 | 0 | 10.81 | 5368
TS5500Exc | MW\26\009\D | MW | 26 | 9 | D | 8 Coal Mining | 62.6 | 0 | 62.6 | 2019-10-26 13:28 | 2019-10-28 13:15 | 60174.2069 | [6 empty] | 60174 | 45208 | 2.83 | 0 | 0 | 6.23 | 5864
TS5500Shv | MW\26\006\D | MW | 26 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-10-26 14:04 | 2019-10-29 17:46 | 93669.6668 | [6 empty] | 93670 | 70256 | 4.39 | 0 | 0 | 6.5 | 5840
PH4100XPC#1 | GG\07\003\B | GG | 7 | 3 | B | 1 Prestrip - Thick | 100 | 99.7876 | 99.7876 | 2019-10-26 15:36 | 2019-11-01 | 298918.2104 | 298918 | [7 empty] | 0 | 0 | 15.06 | 8.87 | 5634.95
PH4100A | SC\37\022\D | SC | 37 | 22 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-10-27 06:47 | 2019-10-30 20:13 | 149979.7645 | 149980 | [7 empty] | 0 | 0 | 12.85 | 7.16 | 5784.1
DRE2 | MW\26\011\D | MW | 26 | 11 | D | 6 DL | 100 | 41.035 | 41.035 | 2019-10-27 22:15 | 2019-11-01 | 333166.6776 |  |  |  | 11546 | 333167 | 156611 |  |  | 0 | 29.44 | 0 | 5.84 | 5898.41
TS6060#1 | GG\07\002\D | GG | 7 | 2 | D | 8 Coal Mining | 100 | 0 | 98.9 | 2019-10-28 00:43 | 2019-11-01 | 130873.9975 | [6 empty] | 130874 | 98540 | 4.54 | 0 | 0 | 5.8 | 5876
TS5500Exc | SC\37\011\D | SC | 37 | 11 | D | 8 Coal Mining | 62 | 0 | 62 | 2019-10-28 13:15 | 2019-10-30 02:47 | 47276.5203 | [6 empty] | 47277 | 35306 | 2.94 | 0 | 0 | 7.64 | 5742
DRE1 | SC\37\014\D | SC | 37 | 14 | D | 6 DL | 100 | 0 | 51.2865 | 2019-10-29 04:09 | 2019-11-01 | 240139.3109 |  |  |  | 13705 | 240139 | 182087 |  |  | 0 | 31.67 | 0 | 7.69 | 5735.25
TS5500Shv | MW\26\007\D | MW | 26 | 7 | D | 8 Coal Mining | 100 | 0 | 69.9 | 2019-10-29 17:46 | 2019-11-01 | 67116.104 | [6 empty] | 67116 | 50222 | 3.14 | 0 | 0 | 6.84 | 5811
TS5500Exc | SC\36\023\D | SC | 36 | 23 | D | 7 PostStrip | 39.9147 | 0 | 39.9147 | 2019-10-30 02:47 | 2019-10-31 07:09 | 25097.3322 |  |  | 25097 | [5 empty] | 0 | 0 | 0 | 7.2 | 5781.5
PH4100A | SC\37\023\D | SC | 37 | 23 | D | 1 Prestrip - Thick | 100 | 31.6746 | 31.6746 | 2019-10-30 20:13 | 2019-11-01 | 48669.0389 | 48669 | [7 empty] | 0 | 0 | 4.16 | 7.22 | 5778.8
TS5500Exc | SC\36\023\D | SC | 36 | 23 | D | 7 PostStrip | 60.0853 | 0 | 23.6838 | 2019-10-31 07:09 | 2019-11-01 | 14891.7363 |  |  | 14892 | [5 empty] | 0 | 0 | 0 | 7.2 | 5781.5
| EOP 70 : 2019\Oct | EOP 70 : 2019 | Oct | [6 empty] | 2019-11-01 | 2019-11-01 |  | 5428623 |  | 250005 | 322863 | 5169535 | 3403965 | 1355740 | 1013565 | 61.38 | 0 | 303.69 | 7.29 | 5754.95
TS Fleet 5 | GG\08\002\X1 | GG | 8 | 2 | X1 | 1 Prestrip - Thick | 45.6649 | 0 | 30.733 | 2019-11-01 | 2019-11-21 20:45 | 925391.9139 | 925392 | [7 empty] | 0 | 0 | 23.84 | 0 | 0
DRE1 | SC\37\014\D | SC | 37 | 14 | D | 6 DL | 100 | 0 | 48.7135 | 2019-11-01 | 2019-11-03 17:17 | 228091.4741 |  |  |  | 13018 | 228091 | 172952 |  |  | 0 | 31.67 | 0 | 7.69 | 5735.25
PH4100A | SC\37\023\D | SC | 37 | 23 | D | 1 Prestrip - Thick | 100 | 68.3254 | 68.3254 | 2019-11-01 | 2019-11-03 14:31 | 104983.98 | 104984 | [7 empty] | 0 | 0 | 8.98 | 7.22 | 5778.8
DRE2 | MW\26\011\D | MW | 26 | 11 | D | 6 DL | 100 | 58.965 | 58.965 | 2019-11-01 | 2019-11-06 22:19 | 478741.9753 |  |  |  | 16591 | 478742 | 225041 |  |  | 0 | 29.44 | 0 | 5.84 | 5898.41
PH4100XPC#1 | GG\07\003\B | GG | 7 | 3 | B | 1 Prestrip - Thick | 100 | 0.21245 | 0.21245 | 2019-11-01 | 2019-11-01 00:17 | 636.3907 | 636 | [7 empty] | 0 | 0 | 0.03 | 8.87 | 5634.95
TS5500Shv | MW\26\007\D | MW | 26 | 7 | D | 8 Coal Mining | 100 | 0 | 30.1 | 2019-11-01 | 2019-11-02 | 28836.575 | [6 empty] | 28837 | 21578 | 1.35 | 0 | 0 | 6.84 | 5811
TS6060#1 | GG\07\002\D | GG | 7 | 2 | D | 8 Coal Mining | 100 | 0 | 1.1 | 2019-11-01 | 2019-11-01 01:03 | 1411.501 | [6 empty] | 1412 | 1063 | 0.05 | 0 | 0 | 5.8 | 5876
TS5500Exc | SC\36\023\D | SC | 36 | 23 | D | 7 PostStrip | 60.0853 | 0 | 36.4016 | 2019-11-01 | 2019-11-02 01:52 | 22888.3582 |  |  | 22888 | [5 empty] | 0 | 0 | 0 | 7.2 | 5781.5
PH4100XPC#1 | GG\07\004\X2 | GG | 7 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.8815 | 2019-11-01 00:17 | 2019-11-03 12:33 | 134484.8562 | 134485 | [7 empty] | 0 | 0 | 6.74 | 0 | 0
TS6060#1 | RS\12\007\X | RS | 12 | 7 | X | 1 Prestrip - Thick | 52.21 | 52.21 | 52.21 | 2019-11-01 01:03 | 2019-11-14 02:48 | 310232.0926 | 310232 | [7 empty] | 0 | 0 | 21.88 | 11 | 5276.88
TS5500Shv | MW\26\008\D | MW | 26 | 8 | D | 8 Coal Mining | 53.6 | 0 | 53.6 | 2019-11-02 | 2019-11-03 21:25 | 54561.6855 | [6 empty] | 54562 | 40705 | 2.54 | 0 | 0 | 7.04 | 5795
TS5500Exc | SC\36\023\D | SC | 36 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-11-02 01:52 | 2019-11-04 15:47 | 77992.2754 | [6 empty] | 77992 | 57924 | 4.83 | 0 | 0 | 7.2 | 5782
PH4100XPC#1 | GG\07\004\B | GG | 7 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-11-03 12:33 | 2019-11-09 17:16 | 331810.4671 | 331810 | [7 empty] | 0 | 0 | 16.52 | 9.41 | 5551.97
PH4100A | SC\37\024\D | SC | 37 | 24 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-11-03 14:31 | 2019-11-08 18:26 | 206832.1487 | 206832 | [7 empty] | 0 | 0 | 16.41 | 7.04 | 5794.8
DRE1 | SC\37\015\D | SC | 37 | 15 | D | 6 DL | 100 | 0 | 100 | 2019-11-03 17:17 | 2019-11-07 23:30 | 357043.8776 |  |  |  | 20378 | 357044 | 270730 |  |  | 0 | 31.17 | 0 | 7.39 | 5760.01
TS5500Shv | MW\30\007\B | MW | 30 | 7 | B | 8 Coal Mining | 49.6 | 0 | 49.6 | 2019-11-03 21:25 | 2019-11-04 13:41 | 19538.8352 | [6 empty] | 19539 | 14385 | 1.44 | 0 | 0 | 9.62 | 5540
TS5500Shv | MW\30\008\A | MW | 30 | 8 | A | 8 Coal Mining | 49.6 | 0 | 49.6 | 2019-11-04 13:41 | 2019-11-05 09:13 | 23452.2396 | [6 empty] | 23452 | 17226 | 1.74 | 0 | 0 | 11.21 | 5368
TS5500Exc | SC\37\011\D | SC | 37 | 11 | D | 8 Coal Mining | 38 | 0 | 38 | 2019-11-04 15:47 | 2019-11-05 14:45 | 28922.6384 | [6 empty] | 28923 | 21599 | 1.8 | 0 | 0 | 7.64 | 5742
TS5500Shv | GG\07\003\B | GG | 7 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2019-11-05 09:13 | 2019-11-08 23:21 | 103463.437 | [6 empty] | 103463 | 76125 | 3.8 | 0 | 0 | 8.87 | 5635
TS5500Exc | SC\37\012\D | SC | 37 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-11-05 14:45 | 2019-11-08 01:56 | 74548.8028 | [6 empty] | 74549 | 55583 | 4.63 | 0 | 0 | 7.56 | 5749
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2019-11-06 22:19 | 2019-11-08 22:19
DRE1 | SC\37\016\D | SC | 37 | 16 | D | 6 DL | 100 | 0 | 100 | 2019-11-07 23:30 | 2019-11-16 03:03 | 683046.9791 |  |  |  | 44879 | 683047 | 453775 |  |  | 0 | 37.78 | 0 | 7.04 | 5791.46
TS5500Exc | DT\27\007\D | DT | 27 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-11-08 01:56 | 2019-11-11 08:58 | 99548.8885 | [6 empty] | 99549 | 74618 | 4.66 | 0 | 0 | 6.76 | 5819
PH4100A | SC\38\010\D | SC | 38 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-11-08 18:26 | 2019-11-16 10:27 | 313463.9218 | 313464 | [7 empty] | 0 | 0 | 26.6 | 7.79 | 5729.7
DRE2 | MW\27\003\D | MW | 27 | 3 | D | 6 DL | 100 | 100 | 100 | 2019-11-08 22:19 | 2019-11-15 20:43 | 559743.2108 |  |  |  | 33428 | 559743 | 395138 |  |  | 0 | 26.75 | 0 | 6.59 | 5833.24
TS5500Shv | DT\27\006\D | DT | 27 | 6 | D | 8 Coal Mining | 70.3 | 0 | 70.3 | 2019-11-08 23:21 | 2019-11-11 17:15 | 79167.2671 | [6 empty] | 79167 | 59152 | 3.27 | 0 | 0 | 6.89 | 5807
PH4100XPC#1 | GG\07\003\D | GG | 7 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-11-09 17:16 | 2019-11-15 03:55 | 291515.1521 | 291515 | [7 empty] | 0 | 0 | 19.58 | 5.79 | 5875.81
TS5500Exc | SC\37\013\D | SC | 37 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-11-11 08:58 | 2019-11-13 19:23 | 73579.0327 | [6 empty] | 73579 | 55034 | 4.59 | 0 | 0 | 7.72 | 5734
TS5500Shv | MW\26\009\D | MW | 26 | 9 | D | 8 Coal Mining | 37.4 | 0 | 37.4 | 2019-11-11 17:15 | 2019-11-12 23:09 | 35912.3208 | [6 empty] | 35912 | 26980 | 1.69 | 0 | 0 | 6.23 | 5864
TS5500Shv | GG\07\004\B | GG | 7 | 4 | B | 8 Coal Mining | 44.7 | 0 | 44.7 | 2019-11-12 23:09 | 2019-11-14 13:49 | 46450.7951 | [6 empty] | 46451 | 34130 | 1.7 | 0 | 0 | 9.41 | 5552
TS5500Exc | DT\28\001\D | DT | 28 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-11-13 19:23 | 2019-11-19 04:41 | 162870.528 | [6 empty] | 162871 | 123157 | 4.63 | 0 | 0 | 6.01 | 5885
TS6060#1 | GG\07\004\B | GG | 7 | 4 | B | 8 Coal Mining | 55.3 | 0 | 55.3 | 2019-11-14 02:48 | 2019-11-15 21:54 | 57459.2385 | [6 empty] | 57459 | 42219 | 2.11 | 0 | 0 | 9.41 | 5552
TS5500Shv | MW\26\010\D | MW | 26 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-11-14 13:49 | 2019-11-17 20:40 | 94702.8251 | [6 empty] | 94703 | 71721 | 4.48 | 0 | 0 | 5.53 | 5926
PH4100XPC#1 | GG\07\005\X2 | GG | 7 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 94.9004 | 2019-11-15 03:55 | 2019-11-18 17:06 | 190052.8527 | 190053 | [7 empty] | 0 | 0 | 9.19 | 0 | 0
DRE2 | MW\27\004\D | MW | 27 | 4 | D | 6 DL | 100 | 100 | 100 | 2019-11-15 20:43 | 2019-11-22 10:33 | 530910.8746 |  |  |  | 31706 | 530911 | 374785 |  |  | 0 | 25.31 | 0 | 6.29 | 5858.47
TS6060#1 | RS\13\003\A | RS | 13 | 3 | A | 1 Prestrip - Thick | 52.0779 | 52.0779 | 52.0779 | 2019-11-15 21:54 | 2019-11-22 07:47 | 152122.0305 | 152122 | [7 empty] | 0 | 0 | 22.54 | 11.55 | 5402.68
DRE1 | SC\37\017\D | SC | 37 | 17 | D | 6 DL | 100 | 0 | 100 | 2019-11-16 03:03 | 2019-11-25 01:45 | 750025.8066 |  |  |  | 57036 | 750026 | 513326 |  |  | 0 | 40 | 0 | 6.76 | 5817.84
PH4100A | SC\39\010\D | SC | 39 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-11-16 10:27 | 2019-11-23 22:30 | 306837.1203 | 306837 | [7 empty] | 0 | 0 | 25.82 | 7.77 | 5731.33
TS5500Shv | GG\07\003\D | GG | 7 | 3 | D | 7 PostStrip | 30.8758 | 0 | 30.8758 | 2019-11-17 20:40 | 2019-11-19 01:54 | 30875.0536 |  |  | 30875 | [5 empty] | 0 | 0 | 0 | 5.79 | 5875.81
PH4100XPC#1 | GG\07\004\D | GG | 7 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-11-18 17:06 | 2019-11-24 03:32 | 290998.3289 | 290998 | [7 empty] | 0 | 0 | 19.55 | 5.87 | 5867.29
TS5500Shv | GG\07\003\D | GG | 7 | 3 | D | 7 PostStrip | 69.1242 | 0 | 69.1242 | 2019-11-19 01:54 | 2019-11-21 19:21 | 69122.3954 |  |  | 69122 | [5 empty] | 0 | 0 | 0 | 5.79 | 5875.81
TS5500Exc | SC\37\014\D | SC | 37 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-11-19 04:41 | 2019-11-21 11:58 | 69622.6833 | [6 empty] | 69623 | 52155 | 4.35 | 0 | 0 | 7.69 | 5735
TS5500Exc | SC\37\015\D | SC | 37 | 15 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-11-21 11:58 | 2019-11-23 01:40 | 47493.7278 | [6 empty] | 47494 | 35576 | 4.07 | 0 | 0 | 7.39 | 5760
TS5500Shv | GG\07\003\D | GG | 7 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-11-21 19:21 | 2019-11-25 23:20 | 120088.3933 | [6 empty] | 120088 | 90417 | 4.52 | 0 | 0 | 5.79 | 5876
TS Fleet 5 | GG\07\005\B | GG | 7 | 5 | B | 1 Prestrip - Thick | 44.2524 | 44.2524 | 44.2524 | 2019-11-21 20:45 | 2019-11-25 04:53 | 148101.4494 | 148101 | [7 empty] | 0 | 0 | 7.29 | 10.85 | 5383.94
TS6060#1 | RS\13\003\A | RS | 13 | 3 | A | 1 Prestrip - Thick | 47.9221 | 47.9221 | 47.9221 | 2019-11-22 07:47 | 2019-11-28 05:23 | 139982.8959 | 139983 | [7 empty] | 0 | 0 | 20.74 | 11.55 | 5402.68
DRE2 | MW\27\005\D | MW | 27 | 5 | D | 6 DL | 100 | 100 | 100 | 2019-11-22 10:33 | 2019-11-29 15:16 | 580962.7892 |  |  |  | 34695 | 580963 | 410118 |  |  | 0 | 27.84 | 0 | 6.07 | 5877.24
TS5500Exc | MW\27\003\D | MW | 27 | 3 | D | 8 Coal Mining | 44.9 | 0 | 44.9 | 2019-11-23 01:40 | 2019-11-24 12:24 | 43750.3562 | [6 empty] | 43750 | 33029 | 2.06 | 0 | 0 | 6.59 | 5833
PH4100A | SC\38\011\D | SC | 38 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-11-23 22:30 | 2019-11-28 05:54 | 175470.3962 | 175470 | [7 empty] | 0 | 0 | 14.93 | 7.62 | 5744
PH4100XPC#1 | GG\07\005\B | GG | 7 | 5 | B | 1 Prestrip - Thick | 100 | 55.7476 | 55.7476 | 2019-11-24 03:32 | 2019-11-27 15:09 | 186572.804 | 186573 | [7 empty] | 0 | 0 | 9.19 | 10.85 | 5383.94
TS5500Exc | DT\28\002\B | DT | 28 | 2 | B | 8 Coal Mining | 42.9 | 0 | 42.9 | 2019-11-24 12:24 | 2019-11-25 06:48 | 23184.8076 | [6 empty] | 23185 | 16808 | 0.92 | 0 | 0 | 11.99 | 5283
DRE1 | SC\37\018\D | SC | 37 | 18 | D | 6 DL | 100 | 0 | 51.2987 | 2019-11-25 01:45 | 2019-12-01 | 496841.8627 |  |  |  | 37783 | 496842 | 340044 |  |  | 0 | 40 | 0 | 6.67 | 5825.68
TS Fleet 5 | GG\07\006\D | GG | 7 | 6 | D | 1 Prestrip - Thick | 46.1185 | 46.1185 | 46.1185 | 2019-11-25 04:53 | 2019-11-29 19:01 | 203506.9019 | 203507 | [7 empty] | 0 | 0 | 9.56 | 6 | 5859.98
TS5500Exc | MW\30\008\B | MW | 30 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-11-25 06:48 | 2019-11-27 20:58 | 54973.7561 | 54974 | [7 empty] | 0 | 0 | 5.54 | 10.37 | 5448.4
TS5500Shv | MW\26\011\D | MW | 26 | 11 | D | 7 PostStrip | 100 | 0 | 100 | 2019-11-25 23:20 | 2019-11-29 06:43 | 83840.3887 |  |  | 83840 | [5 empty] | 0 | 0 | 0 | 5.84 | 5898.41
PH4100XPC#1 | GG\07\006\D | GG | 7 | 6 | D | 1 Prestrip - Thick | 100 | 40.8778 | 40.8778 | 2019-11-27 15:09 | 2019-12-01 | 180381.6285 | 180382 | [7 empty] | 0 | 0 | 8.47 | 6 | 5859.98
TS5500Exc | SC\37\016\D | SC | 37 | 16 | D | 8 Coal Mining | 100 | 0 | 46.2 | 2019-11-27 20:58 | 2019-11-28 23:43 | 33695.6851 | [6 empty] | 33696 | 25241 | 1.92 | 0 | 0 | 7.04 | 5791
TS6060#1 | GG\07\005\B | GG | 7 | 5 | B | 8 Coal Mining | 100 | 0 | 24.1 | 2019-11-28 05:23 | 2019-11-28 23:43 | 24445.4609 | [6 empty] | 24445 | 17865 | 0.9 | 0 | 0 | 10.85 | 5384
PH4100A | SC\39\011\D | SC | 39 | 11 | D | 1 Prestrip - Thick | 100 | 56.3313 | 56.3313 | 2019-11-28 05:54 | 2019-12-01 | 112271.8737 | 112272 | [7 empty] | 0 | 0 | 9.54 | 7.6 | 5745.81
TS6060#1 | RS\13\004\X | RS | 13 | 4 | X | 1 Prestrip - Thick | 100 | 14.5999 | 14.5999 | 2019-11-28 23:43 | 2019-12-01 | 47094.21 | 47094 | [7 empty] | 0 | 0 | 4.66 | 13.73 | 5110.72
TS5500Exc | MW\30\010\X | MW | 30 | 10 | X | 1 Prestrip - Thick | 100 | 12.5347 | 12.5347 | 2019-11-28 23:43 | 2019-12-01 | 42950.1677 | 42950 | [7 empty] | 0 | 0 | 4.11 | 12.27 | 5202.71
TS5500Shv | GG\07\004\D | GG | 7 | 4 | D | 7 PostStrip | 100 | 0 | 43.5832 | 2019-11-29 06:43 | 2019-12-01 | 43581.614 |  |  | 43582 | [5 empty] | 0 | 0 | 0 | 5.87 | 5867.29
DRE2 | MW\27\006\D | MW | 27 | 6 | D | 6 DL | 100 | 18.0904 | 18.0904 | 2019-11-29 15:16 | 2019-12-01 | 110081.1501 |  |  |  | 6574 | 110081 | 77709 |  |  | 0 | 29.16 | 0 | 6.32 | 5855.57
TS Fleet 5 | GG\08\002\X1 | GG | 8 | 2 | X1 | 1 Prestrip - Thick | 33.5136 | 0 | 1.7788 | 2019-11-29 19:01 | 2019-12-01 | 53559.7349 | 53560 | [7 empty] | 0 | 0 | 1.38 | 0 | 0
| EOP 71 : 2019\Nov | EOP 71 : 2019 | Nov | [6 empty] | 2019-12-01 | 2019-12-01 |  | 4904227 |  | 250308 | 296088 | 4775490 | 3233618 | 1424700 | 1064289 | 68.06 | 0 | 313.07 | 7.21 | 5766.46
TS Fleet 5 | GG\08\002\X1 | GG | 8 | 2 | X1 | 1 Prestrip - Thick | 33.5136 | 0 | 31.7349 | 2019-12-01 | 2019-12-27 07:58 | 955558.3491 | 955558 | [7 empty] | 0 | 0 | 24.62 | 0 | 0
DRE1 | SC\37\018\D | SC | 37 | 18 | D | 6 DL | 100 | 0 | 48.7013 | 2019-12-01 | 2019-12-07 11:48 | 471685.1223 |  |  |  | 35870 | 471685 | 322826 |  |  | 0 | 40 | 0 | 6.67 | 5825.68
PH4100A | SC\39\011\D | SC | 39 | 11 | D | 1 Prestrip - Thick | 100 | 43.6687 | 43.6687 | 2019-12-01 | 2019-12-03 14:01 | 87034.4004 | 87034 | [7 empty] | 0 | 0 | 7.39 | 7.6 | 5745.81
DRE2 | MW\27\006\D | MW | 27 | 6 | D | 6 DL | 100 | 81.9096 | 81.9096 | 2019-12-01 | 2019-12-08 02:58 | 498424.7906 |  |  |  | 29766 | 498425 | 351852 |  |  | 0 | 29.16 | 0 | 6.32 | 5855.57
PH4100XPC#1 | GG\07\006\D | GG | 7 | 6 | D | 1 Prestrip - Thick | 100 | 13.0037 | 13.0037 | 2019-12-01 | 2019-12-02 07:07 | 57381.4023 | 57381 | [7 empty] | 0 | 0 | 2.7 | 6 | 5859.98
TS5500Shv | GG\07\004\D | GG | 7 | 4 | D | 7 PostStrip | 100 | 0 | 56.4168 | 2019-12-01 | 2019-12-03 17:17 | 56414.7019 |  |  | 56415 | [5 empty] | 0 | 0 | 0 | 5.87 | 5867.29
TS6060#1 | RS\13\004\X | RS | 13 | 4 | X | 1 Prestrip - Thick | 100 | 85.4001 | 85.4001 | 2019-12-01 | 2019-12-15 09:08 | 275472.1154 | 275472 | [7 empty] | 0 | 0 | 27.25 | 13.73 | 5110.72
TS5500Exc | MW\30\010\X | MW | 30 | 10 | X | 1 Prestrip - Thick | 100 | 87.4653 | 87.4653 | 2019-12-01 | 2019-12-15 00:51 | 299699.041 | 299699 | [7 empty] | 0 | 0 | 28.65 | 12.27 | 5202.71
PH4100XPC#1 | GG\08\006\B | GG | 8 | 6 | B | 1 Prestrip - Thick | 100 | 85.1873 | 85.1873 | 2019-12-02 07:07 | 2020-01-01 | 1355939.684 | 1355940 | [7 empty] | 0 | 0 | 56.81 | 11.16 | 5331.22
PH4100A | SC\38\012\D | SC | 38 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-12-03 14:01 | 2019-12-06 20:53 | 109952.6499 | 109953 | [7 empty] | 0 | 0 | 9.45 | 7.52 | 5751.92
TS5500Shv | GG\07\006\D | GG | 7 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2019-12-03 17:17 | 2019-12-10 11:40 | 140290.7046 |  |  | 140291 | [5 empty] | 0 | 0 | 0 | 6 | 5859.98
PH4100A | SC\39\012\D | SC | 39 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-12-06 20:53 | 2019-12-09 18:10 | 96804.3587 | 96804 | [7 empty] | 0 | 0 | 8.33 | 7.49 | 5754.39
DRE1 | SC\37\019\D | SC | 37 | 19 | D | 6 DL | 100 | 0 | 100 | 2019-12-07 11:48 | 2019-12-16 07:15 | 640134.0488 |  |  |  | 48679 | 640134 | 438115 |  |  | 0 | 40 | 0 | 7.12 | 5784.77
DRE2 | MW\27\007\D | MW | 27 | 7 | D | 6 DL | 100 | 100 | 100 | 2019-12-08 02:58 | 2019-12-17 11:57 | 655900.5356 |  |  |  | 39171 | 655901 | 463018 |  |  | 0 | 31.41 | 0 | 6.69 | 5824.19
PH4100A | SC\38\013\D | SC | 38 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-12-09 18:10 | 2019-12-14 00:49 | 142475.0933 | 142475 | [7 empty] | 0 | 0 | 12.08 | 7.67 | 5738.05
TS5500Shv | MW\26\011\D | MW | 26 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-12-10 11:40 | 2019-12-14 13:32 | 96197.711 | [6 empty] | 96198 | 72851 | 4.42 | 0 | 0 | 5.84 | 5898
PH4100A | SC\39\013\D | SC | 39 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-12-14 00:49 | 2019-12-17 22:08 | 129828.7602 | 129829 | [7 empty] | 0 | 0 | 10.94 | 7.59 | 5744.61
TS5500Shv | MW\27\003\D | MW | 27 | 3 | D | 8 Coal Mining | 55.1 | 0 | 55.1 | 2019-12-14 13:32 | 2019-12-16 20:06 | 53627.431 | [6 empty] | 53627 | 40485 | 2.53 | 0 | 0 | 6.59 | 5833
TS5500Exc | SC\37\016\D | SC | 37 | 16 | D | 8 Coal Mining | 100 | 0 | 53.8 | 2019-12-15 00:51 | 2019-12-16 07:59 | 39210.7853 | [6 empty] | 39211 | 29372 | 2.24 | 0 | 0 | 7.04 | 5791
TS6060#1 | GG\07\005\B | GG | 7 | 5 | B | 8 Coal Mining | 100 | 0 | 75.9 | 2019-12-15 09:08 | 2019-12-18 07:45 | 77033.0289 | [6 empty] | 77033 | 56297 | 2.83 | 0 | 0 | 10.85 | 5384
DRE1 | SC\37\020\D | SC | 37 | 20 | D | 6 DL | 100 | 0 | 100 | 2019-12-16 07:15 | 2019-12-25 00:46 | 634296.8065 |  |  |  | 48235 | 634297 | 434119 |  |  | 0 | 40 | 0 | 7.3 | 5769.7
TS5500Exc | SC\37\017\D | SC | 37 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-12-16 07:59 | 2019-12-18 21:40 | 77708.2884 | [6 empty] | 77708 | 58213 | 4.42 | 0 | 0 | 6.76 | 5818
TS5500Shv | MW\27\004\D | MW | 27 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-12-16 20:06 | 2019-12-20 19:32 | 93788.1695 | [6 empty] | 93788 | 71026 | 4.44 | 0 | 0 | 6.29 | 5858
DRE2 | MW\27\008\D | MW | 27 | 8 | D | 6 DL | 100 | 100 | 100 | 2019-12-17 11:57 | 2019-12-27 02:41 | 672617.9659 |  |  |  | 50278 | 672618 | 462764 |  |  | 0 | 32.04 | 0 | 6.84 | 5812.22
PH4100A | SC\38\014\D | SC | 38 | 14 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-12-17 22:08 | 2019-12-23 04:36 | 174934.2018 | 174934 | [7 empty] | 0 | 0 | 14.73 | 7.66 | 5737.49
TS6060#1 | GG\07\006\D | GG | 7 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-12-18 07:45 | 2019-12-25 02:30 | 177522.3016 | [6 empty] | 177522 | 133880 | 4.73 | 0 | 0 | 6 | 5860
TS5500Exc | SC\37\018\D | SC | 37 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-12-18 21:40 | 2019-12-22 08:09 | 103877.9045 | [6 empty] | 103878 | 77880 | 4.51 | 0 | 0 | 6.67 | 5826
TS5500Shv | MW\27\005\D | MW | 27 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2019-12-20 19:32 | 2019-12-24 16:57 | 91802.5832 | [6 empty] | 91803 | 69296 | 4.33 | 0 | 0 | 6.07 | 5877
TS5500Exc | MW\27\006\D | MW | 27 | 6 | D | 8 Coal Mining | 44.8 | 0 | 44.8 | 2019-12-22 08:09 | 2019-12-23 17:25 | 41911.0077 | [6 empty] | 41911 | 31510 | 1.97 | 0 | 0 | 6.32 | 5856
PH4100A | SC\39\014\D | SC | 39 | 14 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2019-12-23 04:36 | 2019-12-27 20:37 | 155432.8925 | 155433 | [7 empty] | 0 | 0 | 12.98 | 7.63 | 5739.85
TS5500Exc | MW\27\007\D | MW | 27 | 7 | D | 8 Coal Mining | 56.2 | 0 | 56.2 | 2019-12-23 17:25 | 2019-12-25 12:03 | 53699.7668 | [6 empty] | 53700 | 40215 | 2.51 | 0 | 0 | 6.69 | 5824
TS5500Shv | MW\27\006\D | MW | 27 | 6 | D | 8 Coal Mining | 55.2 | 0 | 55.2 | 2019-12-24 16:57 | 2019-12-26 21:24 | 51559.005 | [6 empty] | 51559 | 38764 | 2.42 | 0 | 0 | 6.32 | 5856
DRE1 | SC\37\021\D | SC | 37 | 21 | D | 6 DL | 100 | 0 | 80.6405 | 2019-12-25 00:46 | 2020-01-01 | 506251.0224 |  |  |  | 38498 | 506251 | 346484 |  |  | 0 | 40 | 0 | 7.25 | 5775.41
TS6060#1 | GG\07\004\D | GG | 7 | 4 | D | 8 Coal Mining | 90.1 | 0 | 90.1 | 2019-12-25 02:30 | 2019-12-29 03:17 | 105578.8408 | [6 empty] | 105579 | 79492 | 3.97 | 0 | 0 | 5.87 | 5867
TS5500Exc | MW\30\008\B | MW | 30 | 8 | B | 8 Coal Mining | 56.2 | 0 | 56.2 | 2019-12-25 12:03 | 2019-12-26 05:30 | 21988.5492 | [6 empty] | 21989 | 16118 | 1.62 | 0 | 0 | 10.37 | 5448
TS5500Exc | SC\37\019\D | SC | 37 | 19 | D | 8 Coal Mining | 9.3 | 0 | 9.3 | 2019-12-26 05:30 | 2019-12-26 10:36 | 6419.5171 | [6 empty] | 6420 | 4809 | 0.4 | 0 | 0 | 7.12 | 5785
TS5500Exc | SC\37\019\D | SC | 37 | 19 | D | 8 Coal Mining | 90.7 | 0 | 90.7 | 2019-12-26 10:36 | 2019-12-28 12:09 | 62418.7135 | [6 empty] | 62419 | 46758 | 3.9 | 0 | 0 | 7.12 | 5785
TS5500Shv | MW\27\007\D | MW | 27 | 7 | D | 8 Coal Mining | 43.8 | 0 | 18.2 | 2019-12-26 21:24 | 2019-12-27 15:08 | 17414.3258 | [6 empty] | 17414 | 13041 | 0.82 | 0 | 0 | 6.69 | 5824
DRE2 | MW\27\009\D | MW | 27 | 9 | D | 6 DL | 100 | 52.3387 | 52.3387 | 2019-12-27 02:41 | 2020-01-01 | 342002.7079 |  |  |  | 25565 | 342003 | 235300 |  |  | 0 | 31.09 | 0 | 6.15 | 5872.58
TS Fleet 5 | GG\07\005\D | GG | 7 | 5 | D | 1 Prestrip - Thick | 46.1185 | 46.1185 | 46.1185 | 2019-12-27 07:58 | 2019-12-31 13:30 | 153499.1185 | 153499 | [7 empty] | 0 | 0 | 10 | 6 | 5858.42
TS5500Shv | MW\30\008\B | MW | 30 | 8 | B | 8 Coal Mining | 43.8 | 0 | 43.8 | 2019-12-27 15:08 | 2019-12-28 08:35 | 17156.5149 | [6 empty] | 17157 | 12576 | 1.27 | 0 | 0 | 10.37 | 5448
PH4100A | SC\38\015\D | SC | 38 | 15 | D | 1 Prestrip - Thick | 100 | 69.0354 | 69.0354 | 2019-12-27 20:37 | 2020-01-01 | 137195.5107 | 137196 | [7 empty] | 0 | 0 | 11.79 | 7.39 | 5759.32
TS5500Shv | MW\30\009\A | MW | 30 | 9 | A | 8 Coal Mining | 10.5 | 0 | 10.5 | 2019-12-28 08:35 | 2019-12-28 13:41 | 5008.8135 | [6 empty] | 5009 | 3666 | 0.37 | 0 | 0 | 11.81 | 5342
TS5500Exc | DT\28\002\B | DT | 28 | 2 | B | 8 Coal Mining | 16.1 | 0 | 16.1 | 2019-12-28 12:09 | 2019-12-28 19:03 | 8686.7825 | [6 empty] | 8687 | 6297 | 0.34 | 0 | 0 | 11.99 | 5283
TS5500Shv | MW\30\009\A | MW | 30 | 9 | A | 8 Coal Mining | 89.5 | 0 | 89.5 | 2019-12-28 13:41 | 2019-12-30 09:00 | 42568.1233 | [6 empty] | 42568 | 31154 | 3.15 | 0 | 0 | 11.81 | 5342
TS5500Exc | DT\28\003\D | DT | 28 | 3 | D | 8 Coal Mining | 51.9 | 0 | 51.9 | 2019-12-28 19:03 | 2019-12-29 23:47 | 36186.4355 | [6 empty] | 36186 | 27141 | 2.26 | 0 | 0 | 6.66 | 5826
TS6060#1 | GG\07\004\D | GG | 7 | 4 | D | 8 Coal Mining | 9.9 | 0 | 9.9 | 2019-12-29 03:17 | 2019-12-29 13:52 | 11546.0963 | [6 empty] | 11546 | 8693 | 0.43 | 0 | 0 | 5.87 | 5867
TS6060#1 | RS\13\005\X | RS | 13 | 5 | X | 1 Prestrip - Thick | 100 | 12.734 | 12.734 | 2019-12-29 13:52 | 2020-01-01 | 46894.6395 | 46895 | [7 empty] | 0 | 0 | 4.64 | 12.72 | 5172.82
TS5500Exc | DT\28\004\A | DT | 28 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2019-12-29 23:47 | 2019-12-30 04:00 | 5323.2103 | [6 empty] | 5323 | 3710 | 1.89 | 0 | 0 | 19.87 | 4710
TS5500Exc | DT\28\005\B | DT | 28 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2019-12-30 04:00 | 2019-12-30 21:55 | 22559.6159 | [6 empty] | 22560 | 16470 | 0.79 | 0 | 0 | 10.62 | 5365
TS5500Shv | DT\28\003\D | DT | 28 | 3 | D | 8 Coal Mining | 48.1 | 0 | 48.1 | 2019-12-30 09:00 | 2019-12-31 19:03 | 33474.7339 | [6 empty] | 33475 | 25107 | 2.09 | 0 | 0 | 6.66 | 5826
TS5500Exc | DT\28\006\D | DT | 28 | 6 | D | 8 Coal Mining | 50.8 | 0 | 25.6 | 2019-12-30 21:55 | 2020-01-01 | 32843.4991 | [6 empty] | 32843 | 24501 | 1.19 | 0 | 0 | 7.16 | 5784
TS Fleet 5 | GG\08\002\B | GG | 8 | 2 | B | 1 Prestrip - Thick | 100 | 4.7652 | 4.7652 | 2019-12-31 13:30 | 2020-01-01 | 15870.5323 | 15871 | [7 empty] | 0 | 0 | 0.47 | 10.19 | 5521.99
TS5500Shv | DT\28\007\D | DT | 28 | 7 | D | 8 Coal Mining | 100 | 0 | 4.8 | 2019-12-31 19:03 | 2020-01-01 | 4853.3891 | [6 empty] | 4853 | 3629 | 0.23 | 0 | 0 | 6.97 | 5801
| EOP 72 : 2019\Dec | EOP 72 : 2019 | Dec | [6 empty] | 2020-01-01 | 2020-01-01 |  | 4193973 |  | 196705 | 316062 | 4421313 | 3054478 | 1391965 | 1042952 | 66.08 | 0 | 242.83 | 7.19 | 5765.75
TS Fleet 5 | GG\08\002\B | GG | 8 | 2 | B | 1 Prestrip - Thick | 100 | 95.2348 | 95.2348 | 2020-01-01 | 2020-01-08 01:04 | 317180.2979 | 317180 | [7 empty] | 0 | 0 | 9.45 | 10.19 | 5521.99
DRE1 | SC\37\021\D | SC | 37 | 21 | D | 6 DL | 100 | 0 | 19.3595 | 2020-01-01 | 2020-01-02 10:47 | 121536.3449 |  |  |  | 9242 | 121536 | 83181 |  |  | 0 | 40 | 0 | 7.25 | 5775.41
PH4100A | SC\38\015\D | SC | 38 | 15 | D | 1 Prestrip - Thick | 100 | 30.9646 | 30.9646 | 2020-01-01 | 2020-01-02 13:55 | 61536.6422 | 61537 | [7 empty] | 0 | 0 | 5.29 | 7.39 | 5759.32
DRE2 | MW\27\009\D | MW | 27 | 9 | D | 6 DL | 100 | 47.6613 | 47.6613 | 2020-01-01 | 2020-01-04 20:35 | 311439.2588 |  |  |  | 23280 | 311439 | 214272 |  |  | 0 | 31.09 | 0 | 6.15 | 5872.58
PH4100XPC#1 | GG\08\006\B | GG | 8 | 6 | B | 1 Prestrip - Thick | 100 | 14.8127 | 14.8127 | 2020-01-01 | 2020-01-05 04:56 | 235776.2487 | 235776 | [7 empty] | 0 | 0 | 9.88 | 11.16 | 5331.22
TS5500Shv | DT\28\007\D | DT | 28 | 7 | D | 8 Coal Mining | 100 | 0 | 38.8 | 2020-01-01 | 2020-01-02 07:56 | 38955.1749 | [6 empty] | 38955 | 29130 | 1.82 | 0 | 0 | 6.97 | 5801
TS6060#1 | RS\13\005\X | RS | 13 | 5 | X | 1 Prestrip - Thick | 100 | 87.266 | 87.266 | 2020-01-01 | 2020-01-14 09:02 | 321369.2803 | 321369 | [7 empty] | 0 | 0 | 31.79 | 12.72 | 5172.82
TS5500Exc | DT\28\006\D | DT | 28 | 6 | D | 8 Coal Mining | 50.8 | 0 | 25.2 | 2020-01-01 | 2020-01-02 01:36 | 32262.4369 | [6 empty] | 32262 | 24067 | 1.17 | 0 | 0 | 7.16 | 5784
TS5500Exc | SC\37\020\D | SC | 37 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-01-02 01:36 | 2020-01-04 09:07 | 69914.7652 | [6 empty] | 69915 | 52290 | 4.36 | 0 | 0 | 7.3 | 5770
TS5500Shv | MW\27\007\D | MW | 27 | 7 | D | 8 Coal Mining | 43.8 | 0 | 25.6 | 2020-01-02 07:56 | 2020-01-03 04:01 | 24484.7936 | [6 empty] | 24485 | 18336 | 1.15 | 0 | 0 | 6.69 | 5824
DRE1 | SC\37\022\D | SC | 37 | 22 | D | 6 DL | 100 | 0 | 100 | 2020-01-02 10:47 | 2020-01-09 14:46 | 600730.9974 |  |  |  | 42723 | 600731 | 431976 |  |  | 0 | 39.71 | 0 | 7.16 | 5784.1
PH4100A | DT\28\004\B | DT | 28 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-01-02 13:55 | 2020-01-03 20:07 | 50185.8446 | 50186 | [7 empty] | 0 | 0 | 4.24 | 9.96 | 5399.58
TS5500Shv | MW\27\008\D | MW | 27 | 8 | D | 8 Coal Mining | 58.1 | 0 | 58.1 | 2020-01-03 04:01 | 2020-01-05 04:33 | 59184.0489 | [6 empty] | 59184 | 44223 | 2.76 | 0 | 0 | 6.84 | 5812
PH4100A | SC\39\015\D | SC | 39 | 15 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-01-03 20:07 | 2020-01-09 18:28 | 231268.9865 | 231269 | [7 empty] | 0 | 0 | 16.13 | 7.39 | 5758.94
TS5500Exc | DT\28\004\B | DT | 28 | 4 | B | 8 Coal Mining | 83.4 | 0 | 83.4 | 2020-01-04 09:07 | 2020-01-05 18:03 | 41494.6394 | [6 empty] | 41495 | 30339 | 2.52 | 0 | 0 | 9.96 | 5400
DRE2 | DT\28\005\D | DT | 28 | 5 | D | 6 DL | 100 | 100 | 100 | 2020-01-04 20:35 | 2020-01-13 04:05 | 671062.2673 |  |  |  | 40076 | 671062 | 473721 |  |  | 0 | 25.24 | 0 | 6.99 | 5799.72
TS5500Shv | DT\28\007\D | DT | 28 | 7 | D | 8 Coal Mining | 100 | 0 | 56.3 | 2020-01-05 04:33 | 2020-01-07 02:52 | 56474.4103 | [6 empty] | 56474 | 42231 | 2.64 | 0 | 0 | 6.97 | 5801
PH4100XPC#1 | GG\07\005\D | GG | 7 | 5 | D | 1 Prestrip - Thick | 100 | 53.8815 | 53.8815 | 2020-01-05 04:56 | 2020-01-08 12:09 | 179337.4834 | 179337 | [7 empty] | 0 | 0 | 11.68 | 6 | 5858.42
TS5500Exc | MW\27\009\D | MW | 27 | 9 | D | 8 Coal Mining | 67.5 | 0 | 67.5 | 2020-01-05 18:03 | 2020-01-07 23:09 | 66871.1873 | [6 empty] | 66871 | 50283 | 3.14 | 0 | 0 | 6.15 | 5873
TS5500Shv | MW\27\009\D | MW | 27 | 9 | D | 8 Coal Mining | 32.5 | 0 | 32.5 | 2020-01-07 02:52 | 2020-01-08 05:13 | 32137.4692 | [6 empty] | 32137 | 24165 | 1.51 | 0 | 0 | 6.15 | 5873
TS5500Exc | RS\05\004\B | RS | 5 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-01-07 23:09 | 2020-01-08 20:45 | 27224.5294 | [6 empty] | 27225 | 19267 | 1.93 | 0 | 0 | 13.32 | 5250
TS Fleet 5 | GG\08\003\X1 | GG | 8 | 3 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-01-08 01:04 | 2020-02-02 02:02 | 1127423.938 | 1127424 | [7 empty] | 0 | 0 | 52.78 | 9.03 | 5508.19
TS5500Shv | DT\28\004\B | DT | 28 | 4 | B | 8 Coal Mining | 16.6 | 0 | 16.6 | 2020-01-08 05:13 | 2020-01-08 12:00 | 8275.0669 | [6 empty] | 8275 | 6050 | 0.5 | 0 | 0 | 9.96 | 5400
TS5500Shv | GG\08\002\B | GG | 8 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-01-08 12:00 | 2020-01-14 01:46 | 163106.8491 | [6 empty] | 163107 | 119428 | 3.77 | 0 | 0 | 10.19 | 5522
PH4100XPC#1 | GG\08\005\X1 | GG | 8 | 5 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-01-08 12:09 | 2020-01-29 22:44 | 1193383.408 | 1193383 | [7 empty] | 0 | 0 | 76.71 | 11.27 | 5311.57
TS5500Exc | SC\37\021\D | SC | 37 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-01-08 20:45 | 2020-01-11 06:51 | 73171.7712 | [6 empty] | 73172 | 54598 | 4.55 | 0 | 0 | 7.25 | 5775
DRE1 | RS\05\004\D | RS | 5 | 4 | D | 6 DL | 100 | 100 | 100 | 2020-01-09 14:46 | 2020-01-13 04:00 | 297724.9154 |  |  |  | 15307 | 297725 | 239813 |  |  | 0 | 25.51 | 0 | 6.59 | 5841.65
PH4100A | SC\38\016\D | SC | 38 | 16 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-01-09 18:28 | 2020-01-14 09:46 | 185425.198 | 185425 | [7 empty] | 0 | 0 | 14.17 | 7.07 | 5788.19
TS5500Exc | RS\05\007\A | RS | 5 | 7 | A | 8 Coal Mining | 45.1 | 0 | 45.1 | 2020-01-11 06:51 | 2020-01-12 01:38 | 23669.7396 | [6 empty] | 23670 | 16327 | 1.63 | 0 | 0 | 14.97 | 5065
TS5500Exc | RS\05\005\B | RS | 5 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-01-12 01:38 | 2020-01-12 23:47 | 27902.4383 | [6 empty] | 27902 | 19426 | 1.94 | 0 | 0 | 15.58 | 5049
TS5500Exc | RS\05\006\B | RS | 5 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-01-12 23:47 | 2020-01-14 20:38 | 56476.1205 | [6 empty] | 56476 | 38933 | 3.89 | 0 | 0 | 16.23 | 4986
DRE1 | RS\05\005\D | RS | 5 | 5 | D | 6 DL | 100 | 100 | 100 | 2020-01-13 04:00 | 2020-01-16 09:14 | 269795.6383 |  |  |  | 12071 | 269796 | 229356 |  |  | 0 | 24.14 | 0 | 6.64 | 5836.19
DRE2 | DT\28\004\D | DT | 28 | 4 | D | 6 DL | 100 | 100 | 100 | 2020-01-13 04:05 | 2020-01-18 02:47 | 399316.2077 |  |  |  | 17416 | 399316 | 288120 |  |  | 0 | 25.44 | 0 | 7.03 | 5796.03
TS5500Shv | GG\07\005\D | GG | 7 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2020-01-14 01:46 | 2020-01-17 22:50 | 99775.2282 |  |  | 99775 | [5 empty] | 0 | 0 | 0 | 6 | 5858.42
TS6060#1 | GG\08\006\B | GG | 8 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-01-14 09:02 | 2020-01-17 11:40 | 101009.9753 | [6 empty] | 101010 | 73731 | 3.69 | 0 | 0 | 11.16 | 5331
PH4100A | RS\05\007\B | RS | 5 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-01-14 09:46 | 2020-01-15 04:57 | 31883.5492 | 31884 | [7 empty] | 0 | 0 | 3.19 | 16.86 | 4985.61
TS5500Exc | DT\28\005\D | DT | 28 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-01-14 20:38 | 2020-01-17 00:32 | 65376.861 | [6 empty] | 65377 | 48890 | 2.42 | 0 | 0 | 6.99 | 5800
PH4100A | SC\39\016\D | SC | 39 | 16 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-01-15 04:57 | 2020-01-18 09:14 | 126404.4104 | 126404 | [7 empty] | 0 | 0 | 9.9 | 7.09 | 5784.42
DRE1 | RS\05\006\D | RS | 5 | 6 | D | 6 DL | 100 | 100 | 100 | 2020-01-16 09:14 | 2020-01-19 20:47 | 291886.3705 |  |  |  | 15007 | 291886 | 235110 |  |  | 0 | 25.01 | 0 | 6.7 | 5831.88
TS5500Exc | SC\37\022\D | SC | 37 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-01-17 00:32 | 2020-01-19 12:35 | 75632.5121 | [6 empty] | 75633 | 56347 | 4.7 | 0 | 0 | 7.16 | 5784
TS6060#1 | GG\08\006\D | GG | 8 | 6 | D | 1 Prestrip - Thick | 47.4111 | 47.4111 | 47.4111 | 2020-01-17 11:40 | 2020-01-23 12:30 | 149440.6314 | 149441 | [7 empty] | 0 | 0 | 9.84 | 6.21 | 5841.03
TS5500Shv | GG\07\005\D | GG | 7 | 5 | D | 8 Coal Mining | 8.1 | 0 | 8.1 | 2020-01-17 22:50 | 2020-01-18 07:01 | 9966.36 | [6 empty] | 9966 | 7504 | 0.38 | 0 | 0 | 6 | 5858
DRE2 | DT\28\002\D | DT | 28 | 2 | D | 6 DL | 100 | 100 | 100 | 2020-01-18 02:47 | 2020-01-25 14:06 | 603146.6942 |  |  |  | 26305 | 603147 | 435191 |  |  | 0 | 23.73 | 0 | 6.07 | 5880.36
TS5500Shv | DT\28\005\D | DT | 28 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-01-18 07:01 | 2020-01-20 10:55 | 63290.3654 | [6 empty] | 63290 | 47329 | 2.34 | 0 | 0 | 6.99 | 5800
PH4100A | SC\38\017\D | SC | 38 | 17 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-01-18 09:14 | 2020-01-23 13:35 | 206200.3088 | 206200 | [7 empty] | 0 | 0 | 14.74 | 6.84 | 5809.99
TS5500Exc | DT\28\004\D | DT | 28 | 4 | D | 8 Coal Mining | 74.3 | 0 | 74.3 | 2020-01-19 12:35 | 2020-01-21 09:32 | 56622.0617 | [6 empty] | 56622 | 42309 | 3.53 | 0 | 0 | 7.03 | 5796
DRE1 | SC\37\023\D | SC | 37 | 23 | D | 6 DL | 100 | 0 | 100 | 2020-01-19 20:47 | 2020-01-25 23:01 | 510783.0042 |  |  |  | 29152 | 510783 | 387304 |  |  | 0 | 34.79 | 0 | 7.22 | 5778.8
TS5500Shv | DT\28\004\D | DT | 28 | 4 | D | 8 Coal Mining | 25.7 | 0 | 25.7 | 2020-01-20 10:55 | 2020-01-21 02:59 | 19600.5251 | [6 empty] | 19601 | 14646 | 1.22 | 0 | 0 | 7.03 | 5796
TS5500Shv | RS\05\004\D | RS | 5 | 4 | D | 8 Coal Mining | 22.1 | 0 | 22.1 | 2020-01-21 02:59 | 2020-01-21 14:10 | 13624.5398 | [6 empty] | 13625 | 9873 | 0.99 | 0 | 0 | 6.59 | 5842
TS5500Exc | RS\05\004\D | RS | 5 | 4 | D | 8 Coal Mining | 22.8 | 0 | 22.8 | 2020-01-21 09:32 | 2020-01-21 20:42 | 14073.7004 | [6 empty] | 14074 | 10199 | 1.02 | 0 | 0 | 6.59 | 5842
TS5500Shv | RS\05\007\B | RS | 5 | 7 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-01-21 14:10 | 2020-01-22 13:23 | 28313.779 | [6 empty] | 28314 | 19356 | 1.94 | 0 | 0 | 16.86 | 4986
TS5500Exc | RS\05\007\B | RS | 5 | 7 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-01-21 20:42 | 2020-01-22 19:55 | 29247.2003 | [6 empty] | 29247 | 19994 | 2 | 0 | 0 | 16.86 | 4986
TS5500Shv | RS\05\005\D | RS | 5 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-01-22 13:23 | 2020-01-23 13:37 | 29548.5669 | [6 empty] | 29549 | 21377 | 2.14 | 0 | 0 | 6.64 | 5836
TS5500Exc | RS\05\005\D | RS | 5 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-01-22 19:55 | 2020-01-23 20:09 | 30522.6955 | [6 empty] | 30523 | 22082 | 2.21 | 0 | 0 | 6.64 | 5836
TS6060#1 | GG\07\005\D | GG | 7 | 5 | D | 8 Coal Mining | 91.9 | 0 | 91.9 | 2020-01-23 12:30 | 2020-01-26 23:35 | 112449.1977 | [6 empty] | 112449 | 84667 | 4.23 | 0 | 0 | 6 | 5858
PH4100A | SC\39\017\D | SC | 39 | 17 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-01-23 13:35 | 2020-01-30 16:10 | 289716.5726 | 289717 | [7 empty] | 0 | 0 | 24.55 | 6.9 | 5802.84
TS5500Shv | RS\05\006\D | RS | 5 | 6 | D | 8 Coal Mining | 17.7 | 0 | 17.7 | 2020-01-23 13:37 | 2020-01-23 22:33 | 10899.0167 | [6 empty] | 10899 | 7910 | 0.79 | 0 | 0 | 6.7 | 5832
TS5500Exc | RS\05\008\A | RS | 5 | 8 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-01-23 20:09 | 2020-01-24 13:05 | 21335.6439 | [6 empty] | 21336 | 14695 | 1.85 | 0 | 0 | 15.6 | 5051
TS5500Shv | RS\11\007\X | RS | 11 | 7 | X | 8 Coal Mining | 36.6 | 0 | 36.6 | 2020-01-23 22:33 | 2020-01-24 06:33 | 9759.3449 | [6 empty] | 9759 | 6895 | 0.47 | 0 | 0 | 11.6 | 5227
TS5500Shv | RS\12\003\A | RS | 12 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-01-24 06:33 | 2020-01-24 22:23 | 19295.3764 | [6 empty] | 19295 | 13685 | 1.82 | 0 | 0 | 11.45 | 5406
TS5500Exc | RS\05\006\D | RS | 5 | 6 | D | 8 Coal Mining | 82.3 | 0 | 82.3 | 2020-01-24 13:05 | 2020-01-26 05:18 | 50644.2955 | [6 empty] | 50644 | 36757 | 3.68 | 0 | 0 | 6.7 | 5832
TS5500Shv | RS\12\004\X | RS | 12 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2020-01-24 22:23 | 2020-01-25 11:55 | 16502.7251 | [6 empty] | 16503 | 11489 | 1.14 | 0 | 0 | 14.05 | 5099
TS5500Shv | RS\12\005\X | RS | 12 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2020-01-25 11:55 | 2020-01-26 03:57 | 19553.2513 | [6 empty] | 19553 | 13693 | 1.37 | 0 | 0 | 12.94 | 5161
DRE2 | MW\27\010\D | MW | 27 | 10 | D | 6 DL | 100 | 100 | 100 | 2020-01-25 14:06 | 2020-02-02 13:24 | 643522.3973 |  |  |  | 48103 | 643522 | 442747 |  |  | 0 | 30.68 | 0 | 5.54 | 5924.87
DRE1 | RS\05\007\D | RS | 5 | 7 | D | 6 DL | 100 | 100 | 100 | 2020-01-25 23:01 | 2020-01-29 12:05 | 297179.3189 |  |  |  | 15279 | 297179 | 239373 |  |  | 0 | 25.46 | 0 | 6.77 | 5826.39
TS5500Shv | DT\28\002\D | DT | 28 | 2 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-01-26 03:57 | 2020-01-28 05:37 | 60566.8793 | [6 empty] | 60567 | 45728 | 2.37 | 0 | 0 | 6.07 | 5880
TS5500Exc | DT\28\002\D | DT | 28 | 2 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-01-26 05:18 | 2020-01-28 06:58 | 62563.5896 | [6 empty] | 62564 | 47236 | 2.44 | 0 | 0 | 6.07 | 5880
TS6060#1 | RS\05\004\D | RS | 5 | 4 | D | 8 Coal Mining | 55.1 | 0 | 55.1 | 2020-01-26 23:35 | 2020-01-28 00:40 | 33942.4903 | [6 empty] | 33942 | 24597 | 2.46 | 0 | 0 | 6.59 | 5842
TS6060#1 | RS\12\004\A | RS | 12 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-01-28 00:40 | 2020-02-05 06:06 | 203713.5966 | 203714 | [7 empty] | 0 | 0 | 20.33 | 13.15 | 5264.62
TS5500Shv | RS\12\006\X | RS | 12 | 6 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-01-28 05:37 | 2020-01-28 14:04 | 10300.1261 | [6 empty] | 10300 | 7315 | 0.73 | 0 | 0 | 11.06 | 5276
TS5500Exc | RS\06\003\A | RS | 6 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-01-28 06:58 | 2020-01-28 12:58 | 7564.4099 | [6 empty] | 7564 | 5376 | 0.76 | 0 | 0 | 12.46 | 5301
TS5500Exc | RS\06\004\A | RS | 6 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-01-28 12:58 | 2020-01-28 21:46 | 11080.2334 | [6 empty] | 11080 | 7772 | 0.77 | 0 | 0 | 13.93 | 5157
TS5500Shv | RS\12\007\X | RS | 12 | 7 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-01-28 14:04 | 2020-01-28 23:55 | 12010.1778 | [6 empty] | 12010 | 8530 | 0.62 | 0 | 0 | 11 | 5277
TS5500Exc | RS\06\005\A | RS | 6 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-01-28 21:46 | 2020-01-29 12:53 | 19035.2926 | [6 empty] | 19035 | 13278 | 1.32 | 0 | 0 | 13.54 | 5153
TS5500Shv | RS\13\003\A | RS | 13 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-01-28 23:55 | 2020-01-29 15:54 | 19492.2492 | [6 empty] | 19492 | 13787 | 1.81 | 0 | 0 | 11.55 | 5403
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 7d 00:00 |  | 7d 00:00 | 2020-01-29 12:05 | 2020-02-05 12:05
TS5500Exc | RS\05\007\D | RS | 5 | 7 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-01-29 12:53 | 2020-01-30 14:06 | 31768.4651 | [6 empty] | 31768 | 23130 | 2.31 | 0 | 0 | 6.77 | 5826
TS5500Shv | RS\05\007\D | RS | 5 | 7 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-01-29 15:54 | 2020-01-30 17:07 | 30754.578 | [6 empty] | 30755 | 22392 | 2.24 | 0 | 0 | 6.77 | 5826
PH4100XPC#1 | RS\05\008\B | RS | 5 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-01-29 22:44 | 2020-01-30 09:41 | 24776.8404 | 24777 | [7 empty] | 0 | 0 | 3.14 | 17.08 | 5022.3
PH4100XPC#1 | RS\06\005\B | RS | 6 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-01-30 09:41 | 2020-01-30 23:24 | 31040.4775 | 31040 | [7 empty] | 0 | 0 | 3.1 | 16.82 | 4948.25
TS5500Exc | RS\05\008\B | RS | 5 | 8 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-01-30 14:06 | 2020-01-31 07:35 | 22025.0609 | [6 empty] | 22025 | 14995 | 1.97 | 0 | 0 | 17.08 | 5022
PH4100A | RS\06\003\B | RS | 6 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-01-30 16:10 | 2020-01-31 03:54 | 19499.0016 | 19499 | [7 empty] | 0 | 0 | 2.66 | 14.29 | 5182.15
TS5500Shv | GG\08\005\X1 | GG | 8 | 5 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-01-30 17:07 | 2020-01-31 19:17 | 31895.2754 | [6 empty] | 31895 | 23499 | 1.18 | 0 | 0 | 11.27 | 5312
PH4100XPC#1 | RS\06\004\B | RS | 6 | 4 | B | 1 Prestrip - Thick | 100 | 70.6602 | 70.6602 | 2020-01-30 23:24 | 2020-01-31 09:45 | 23440.8749 | 23441 | [7 empty] | 0 | 0 | 2.35 | 14.61 | 5147.36
PH4100A | RS\06\004\B | RS | 6 | 4 | B | 1 Prestrip - Thick | 100 | 29.3398 | 29.3398 | 2020-01-31 03:54 | 2020-01-31 09:45 | 9733.2244 | 9733 | [7 empty] | 0 | 0 | 0.97 | 14.61 | 5147.36
TS5500Exc | RS\06\003\B | RS | 6 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-01-31 07:35 | 2020-02-01 01:14 | 22223.1249 | [6 empty] | 22223 | 15659 | 1.94 | 0 | 0 | 14.29 | 5182
PH4100A | RS\10\008\A | RS | 10 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-01-31 09:45 | 2020-02-03 04:31 | 110922.3705 | 110922 | [7 empty] | 0 | 0 | 22.77 | 18 | 4842.43
PH4100XPC#1 | GG\08\002\D | GG | 8 | 2 | D | 1 Prestrip - Thick | 100 | 65.7181 | 65.7181 | 2020-01-31 09:45 | 2020-02-04 22:27 | 246025.42 | 246025 | [7 empty] | 0 | 0 | 12.78 | 5.93 | 5864.32
TS5500Shv | RS\05\008\B | RS | 5 | 8 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-01-31 19:17 | 2020-02-01 12:46 | 21322.1334 | [6 empty] | 21322 | 14517 | 1.91 | 0 | 0 | 17.08 | 5022
TS5500Exc | RS\06\006\A | RS | 6 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-02-01 01:14 | 2020-02-01 22:02 | 26201.1619 | [6 empty] | 26201 | 18233 | 1.82 | 0 | 0 | 13.19 | 5168
TS5500Shv | RS\06\003\B | RS | 6 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-02-01 12:46 | 2020-02-02 06:24 | 21513.8762 | [6 empty] | 21514 | 15159 | 1.88 | 0 | 0 | 14.29 | 5182
TS5500Exc | RS\06\004\B | RS | 6 | 4 | B | 8 Coal Mining | 8.7 | 0 | 8.7 | 2020-02-01 22:02 | 2020-02-02 01:54 | 4869.3242 | [6 empty] | 4869 | 3423 | 0.34 | 0 | 0 | 14.61 | 5147
TS5500Exc | RS\06\007\A | RS | 6 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-02-02 01:54 | 2020-02-03 19:36 | 52533.8962 | [6 empty] | 52534 | 36220 | 3.62 | 0 | 0 | 15.07 | 5050
TS Fleet 5 | GG\08\002\D | GG | 8 | 2 | D | 1 Prestrip - Thick | 37.3166 | 34.2819 | 34.2819 | 2020-02-02 02:02 | 2020-02-04 22:27 | 128339.0903 | 128339 | [7 empty] | 0 | 0 | 6.67 | 5.93 | 5864.32
TS5500Shv | RS\06\005\B | RS | 6 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-02-02 06:24 | 2020-02-04 04:59 | 56801.872 | [6 empty] | 56802 | 39292 | 3.93 | 0 | 0 | 16.82 | 4948
DRE2 | RS\06\003\D | RS | 6 | 3 | D | 6 DL | 100 | 100 | 100 | 2020-02-02 13:24 | 2020-02-06 04:00 | 291264.1277 |  |  |  | 13032 | 291264 | 247607 |  |  | 0 | 24.93 | 0 | 6.23 | 5873.98
PH4100A | RS\05\008\D1 | RS | 5 | 8 | D1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-02-03 04:31 | 2020-02-03 12:38 | 13482.6481 | 13483 | [7 empty] | 0 | 0 | 2.03 | 6.63 | 5727.38
PH4100A | RS\06\006\B | RS | 6 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-02-03 12:38 | 2020-02-04 07:27 | 31285.185 | 31285 | [7 empty] | 0 | 0 | 3.12 | 16.38 | 4965.41
TS5500Exc | MW\27\010\D | MW | 27 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-02-03 19:36 | 2020-02-06 23:12 | 95227.9015 | [6 empty] | 95228 | 72119 | 4.51 | 0 | 0 | 5.54 | 5925
TS5500Shv | GG\08\003\X1 | GG | 8 | 3 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2020-02-04 04:59 | 2020-02-04 19:45 | 17995.7043 | [6 empty] | 17996 | 13422 | 0.67 | 0 | 0 | 9.03 | 5508
PH4100A | RS\06\007\B | RS | 6 | 7 | B | 1 Prestrip - Thick | 100 | 87.633 | 87.633 | 2020-02-04 07:27 | 2020-02-05 00:09 | 27742.401 | 27742 | [7 empty] | 0 | 0 | 2.78 | 16.84 | 4976.3
TS5500Shv | RS\06\006\B | RS | 6 | 6 | B | 8 Coal Mining | 9.4 | 0 | 9.4 | 2020-02-04 19:45 | 2020-02-05 00:09 | 5371.7332 | [6 empty] | 5372 | 3698 | 0.37 | 0 | 0 | 16.38 | 4965
TS Fleet 5 | GG\09\002\X1 | GG | 9 | 2 | X1 | 1 Prestrip - Thick | 45.3511 | 0 | 45.3511 | 2020-02-04 22:27 | 2020-02-06 21:57 | 89114.6673 | 89115 | [7 empty] | 0 | 0 | 6.04 | 0 | 0
PH4100XPC#1 | RS\06\007\B | RS | 6 | 7 | B | 1 Prestrip - Thick | 100 | 12.367 | 12.367 | 2020-02-04 22:27 | 2020-02-05 00:11 | 3915.0812 | 3915 | [7 empty] | 0 | 0 | 0.39 | 16.84 | 4976.3
PH4100A | SC\39\018\D | SC | 39 | 18 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-02-05 00:09 | 2020-02-07 15:23 | 106477.2393 | 106477 | [7 empty] | 0 | 0 | 9.71 | 6.88 | 5802.84
TS5500Shv | GG\08\002\D | GG | 8 | 2 | D | 7 PostStrip | 89.0036 | 0 | 89.0036 | 2020-02-05 00:09 | 2020-02-09 11:44 | 115320.1905 |  |  | 115320 | [5 empty] | 0 | 0 | 0 | 5.93 | 5864.32
PH4100XPC#1 | GG\08\005\X2 | GG | 8 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2020-02-05 00:11 | 2020-02-08 23:22 | 215463.769 | 215464 | [7 empty] | 0 | 0 | 10.77 | 0 | 0
TS6060#1 | RS\06\004\B | RS | 6 | 4 | B | 8 Coal Mining | 91.3 | 0 | 91.3 | 2020-02-05 06:06 | 2020-02-06 19:54 | 51150.3178 | [6 empty] | 51150 | 35959 | 3.61 | 0 | 0 | 14.61 | 5147
DRE1 | RS\05\008\D1 | RS | 5 | 8 | D1 | 6 DL | 100 | 0 | 100 | 2020-02-05 12:05 | 2020-02-07 08:46 | 156078.68 |  |  |  |  | 156079 | 156079 |  |  | 0 | 23.52 | 0 | 6.63 | 5727.38
DRE2 | RS\06\005\D | RS | 6 | 5 | D | 6 DL | 100 | 100 | 100 | 2020-02-06 04:00 | 2020-02-09 12:20 | 270241.7008 |  |  |  | 12091 | 270242 | 229736 |  |  | 0 | 24.18 | 0 | 6.84 | 5818.87
TS6060#1 | GG\08\002\D | GG | 8 | 2 | D | 7 PostStrip | 10.9964 | 0 | 10.9964 | 2020-02-06 19:54 | 2020-02-07 09:42 | 14247.858 |  |  | 14248 | [5 empty] | 0 | 0 | 0 | 5.93 | 5864.32
TS Fleet 5 | GG\09\006\X2 | GG | 9 | 6 | X2 | 1 Prestrip - Thick | 43.5674 | 0 | 43.5674 | 2020-02-06 21:57 | 2020-02-13 03:19 | 280223.9192 | 280224 | [7 empty] | 0 | 0 | 23.42 | 0 | 0
TS5500Exc | RS\06\003\D | RS | 6 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-02-06 23:12 | 2020-02-09 02:51 | 65047.1528 | [6 empty] | 65047 | 47656 | 4.55 | 0 | 0 | 6.23 | 5874
DRE1 | SC\37\024\D | SC | 37 | 24 | D | 6 DL | 100 | 0 | 100 | 2020-02-07 08:46 | 2020-02-13 23:48 | 555537.7238 |  |  |  | 22756 | 555538 | 293692 |  |  | 0 | 29.58 | 0 | 7.04 | 5794.8
TS6060#1 | GG\08\003\X1 | GG | 8 | 3 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2020-02-07 09:42 | 2020-02-08 00:28 | 19973.2542 | [6 empty] | 19973 | 14897 | 0.74 | 0 | 0 | 9.03 | 5508
PH4100A | SC\38\018\D | SC | 38 | 18 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-02-07 15:23 | 2020-02-16 07:57 | 348712.0327 | 348712 | [7 empty] | 0 | 0 | 22.72 | 6.76 | 5817.56
TS6060#1 | RS\11\003\A | RS | 11 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-02-08 00:28 | 2020-02-18 16:40 | 255698.3937 | 255698 | [7 empty] | 0 | 0 | 37.47 | 11.32 | 5411.46
PH4100XPC#1 | GG\08\003\X2 | GG | 8 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2020-02-08 23:22 | 2020-02-13 18:41 | 261013.611 | 261014 | [7 empty] | 0 | 0 | 13.1 | 0 | 0
TS5500Exc | RS\05\008\D1 | RS | 5 | 8 | D1 | 8 Coal Mining | 100 | 0 | 100 | 2020-02-09 02:51 | 2020-02-09 12:05 | 11637.8175 | [6 empty] | 11638 | 8389 | 1.3 | 0 | 0 | 6.63 | 5727
TS5500Shv | GG\08\002\D | GG | 8 | 2 | D | 8 Coal Mining | 36.1 | 0 | 36.1 | 2020-02-09 11:44 | 2020-02-11 09:40 | 56020.3726 | [6 empty] | 56020 | 42112 | 1.65 | 0 | 0 | 5.93 | 5864
TS5500Exc | RS\06\006\B | RS | 6 | 6 | B | 8 Coal Mining | 90.6 | 0 | 90.6 | 2020-02-09 12:05 | 2020-02-11 05:18 | 51911.0925 | [6 empty] | 51911 | 35741 | 3.57 | 0 | 0 | 16.38 | 4965
DRE2 | RS\06\004\D | RS | 6 | 4 | D | 6 DL | 100 | 100 | 100 | 2020-02-09 12:20 | 2020-02-13 03:50 | 294304.4869 |  |  |  | 15131 | 294304 | 237058 |  |  | 0 | 25.22 | 0 | 6.74 | 5828.54
TS5500Exc | RS\06\005\D | RS | 6 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-02-11 05:18 | 2020-02-13 05:18 | 60472.4615 | [6 empty] | 60472 | 43818 | 4.38 | 0 | 0 | 6.84 | 5819
TS5500Shv | RS\05\008\D | RS | 5 | 8 | D | 7 PostStrip | 100 | 100 | 100 | 2020-02-11 09:40 | 2020-02-11 18:35 | 9564.7339 |  |  | 9565 | [5 empty] | 0 | 0 | 0 | 6.52 | 5819.83
TS5500Shv | RS\05\008\D | RS | 5 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-02-11 18:35 | 2020-02-12 08:40 | 17164.3599 | [6 empty] | 17164 | 12447 | 1.93 | 0 | 0 | 6.52 | 5820
TS5500Shv | RS\06\007\B | RS | 6 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-02-12 08:40 | 2020-02-14 08:05 | 57828.8187 | [6 empty] | 57829 | 39544 | 3.96 | 0 | 0 | 16.84 | 4976
TS Fleet 5 | GG\09\005\X2 | GG | 9 | 5 | X2 | 1 Prestrip - Thick | 44.3074 | 0 | 44.3074 | 2020-02-13 03:19 | 2020-02-20 08:35 | 325046.0269 | 325046 | [7 empty] | 0 | 0 | 41.27 | 0 | 0
DRE2 | RS\06\006\D | RS | 6 | 6 | D | 6 DL | 100 | 100 | 100 | 2020-02-13 03:50 | 2020-02-16 18:59 | 293171.0227 |  |  |  | 15073 | 293171 | 236145 |  |  | 0 | 25.12 | 0 | 6.77 | 5826.06
TS5500Exc | SC\37\023\D | SC | 37 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-02-13 05:18 | 2020-02-15 18:31 | 77105.539 | [6 empty] | 77106 | 57401 | 4.78 | 0 | 0 | 7.22 | 5779
PH4100XPC#1 | GG\08\003\B | GG | 8 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-02-13 18:41 | 2020-02-18 15:13 | 263795.6437 | 263796 | [7 empty] | 0 | 0 | 13.22 | 9.07 | 5612.07
DRE1 | SC\38\010\D | SC | 38 | 10 | D | 6 DL | 100 | 0 | 100 | 2020-02-13 23:48 | 2020-02-24 03:15 | 850373.8838 |  |  |  | 47683 | 850374 | 370059 |  |  | 0 | 40 | 0 | 7.79 | 5729.7
TS5500Shv | RS\06\004\D | RS | 6 | 4 | D | 8 Coal Mining | 98.9 | 0 | 98.9 | 2020-02-14 08:05 | 2020-02-16 10:22 | 61306.223 | [6 empty] | 61306 | 44462 | 4.45 | 0 | 0 | 6.74 | 5829
TS5500Exc | RS\06\004\D | RS | 6 | 4 | D | 8 Coal Mining | 1.1 | 0 | 1.1 | 2020-02-15 18:31 | 2020-02-15 19:03 | 658.3642 | [6 empty] | 658 | 477 | 0.05 | 0 | 0 | 6.74 | 5829
TS5500Exc | RS\06\008\A | RS | 6 | 8 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-02-15 19:03 | 2020-02-16 10:55 | 19986.1185 | [6 empty] | 19986 | 13721 | 1.85 | 0 | 0 | 16.43 | 4983
PH4100A | SC\39\019\D | SC | 39 | 19 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-02-16 07:57 | 2020-02-20 17:28 | 175217.7951 | 175218 | [7 empty] | 0 | 0 | 11.86 | 6.8 | 5814.6
TS5500Shv | RS\13\004\X | RS | 13 | 4 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-02-16 10:22 | 2020-02-16 19:03 | 10588.6393 | [6 empty] | 10589 | 7379 | 0.74 | 0 | 0 | 13.73 | 5111
TS5500Exc | RS\10\003\A | RS | 10 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-02-16 10:55 | 2020-02-17 17:11 | 38134.6628 | [6 empty] | 38135 | 27157 | 3.68 | 0 | 0 | 11.27 | 5410
DRE2 | RS\06\007\D | RS | 6 | 7 | D | 6 DL | 100 | 100 | 100 | 2020-02-16 18:59 | 2020-02-20 11:30 | 297721.1556 |  |  |  | 15307 | 297721 | 239810 |  |  | 0 | 25.51 | 0 | 6.8 | 5823.32
TS5500Shv | RS\06\006\D | RS | 6 | 6 | D | 8 Coal Mining | 1.6 | 0 | 1.6 | 2020-02-16 19:03 | 2020-02-16 19:51 | 979.7067 | [6 empty] | 980 | 712 | 0.07 | 0 | 0 | 6.77 | 5826
TS5500Shv | RS\13\005\X | RS | 13 | 5 | X | 8 Coal Mining | 66.4 | 0 | 66.4 | 2020-02-16 19:51 | 2020-02-17 06:21 | 12795.1908 | [6 empty] | 12795 | 8966 | 0.9 | 0 | 0 | 12.72 | 5173
TS5500Shv | GG\09\011\X1 | GG | 9 | 11 | X1 | 1 Prestrip - Thick | 15.519 | 15.519 | 15.519 | 2020-02-17 06:21 | 2020-02-19 01:51 | 46558.0289 | 46558 | [7 empty] | 0 | 0 | 4.93 | 12.68 | 5289.17
TS5500Exc | RS\06\006\D | RS | 6 | 6 | D | 8 Coal Mining | 98.4 | 0 | 98.4 | 2020-02-17 17:11 | 2020-02-19 17:25 | 60747.2681 | [6 empty] | 60747 | 44124 | 4.41 | 0 | 0 | 6.77 | 5826
PH4100XPC#1 | RS\06\008\B | RS | 6 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-02-18 15:13 | 2020-02-19 01:12 | 22589.8926 | 22590 | [7 empty] | 0 | 0 | 3.05 | 16.81 | 5038.53
TS6060#1 | GG\08\002\D | GG | 8 | 2 | D | 8 Coal Mining | 63.9 | 0 | 63.9 | 2020-02-18 16:40 | 2020-02-21 18:01 | 99264.5208 | [6 empty] | 99265 | 74621 | 2.92 | 0 | 0 | 5.93 | 5864
PH4100XPC#1 | GG\08\005\B | GG | 8 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-02-19 01:12 | 2020-02-25 10:41 | 347393.9745 | 347394 | [7 empty] | 0 | 0 | 17.28 | 10.93 | 5364.97
TS5500Shv | GG\08\003\B | GG | 8 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-02-19 01:51 | 2020-02-22 16:04 | 105133.9867 | [6 empty] | 105134 | 77336 | 3.86 | 0 | 0 | 9.07 | 5612
TS5500Exc | RS\10\004\A | RS | 10 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-02-19 17:25 | 2020-02-21 09:40 | 50694.5439 | [6 empty] | 50695 | 35690 | 3.57 | 0 | 0 | 12.57 | 5293
TS Fleet 5 | GG\09\003\X1 | GG | 9 | 3 | X1 | 1 Prestrip - Thick | 45.6471 | 45.6471 | 45.6471 | 2020-02-20 08:35 | 2020-02-26 17:01 | 285956.0217 | 285956 | [7 empty] | 0 | 0 | 26.83 | 9.31 | 5472.37
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2020-02-20 11:30 | 2020-02-22 11:30
PH4100A | RS\10\003\B | RS | 10 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-02-20 17:28 | 2020-02-21 07:12 | 22839.086 | 22839 | [7 empty] | 0 | 0 | 3.02 | 18.11 | 4878.09
PH4100A | SC\38\019\D | SC | 38 | 19 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-02-21 07:12 | 2020-02-25 14:01 | 169512.2848 | 169512 | [7 empty] | 0 | 0 | 14.42 | 6.75 | 5818.63
TS5500Exc | RS\10\005\A | RS | 10 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-02-21 09:40 | 2020-02-23 02:31 | 51471.456 | [6 empty] | 51471 | 35692 | 3.56 | 0 | 0 | 14.54 | 5104
TS6060#1 | RS\11\004\A | RS | 11 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-02-21 18:01 | 2020-03-12 04:44 | 467764.4184 | 467764 | [7 empty] | 0 | 0 | 46.01 | 12.47 | 5310.43
DRE2 | MW\27\011\D | MW | 27 | 11 | D | 6 DL | 100 | 100 | 100 | 2020-02-22 11:30 | 2020-03-02 06:16 | 709011.4708 |  |  |  | 33192 | 709011 | 323274 |  |  | 0 | 30.8 | 0 | 5.78 | 5903.73
TS5500Shv | RS\06\008\B | RS | 6 | 8 | B | 8 Coal Mining | 87.7 | 0 | 87.7 | 2020-02-22 16:04 | 2020-02-23 21:10 | 35485.2966 | [6 empty] | 35485 | 24195 | 3.41 | 0 | 0 | 16.81 | 5039
TS5500Exc | RS\06\008\B | RS | 6 | 8 | B | 8 Coal Mining | 12.3 | 0 | 12.3 | 2020-02-23 02:31 | 2020-02-23 06:27 | 4954.4211 | [6 empty] | 4954 | 3378 | 0.48 | 0 | 0 | 16.81 | 5039
TS5500Exc | RS\10\003\B | RS | 10 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-02-23 06:27 | 2020-02-24 02:36 | 25364.6042 | [6 empty] | 25365 | 17369 | 2.07 | 0 | 0 | 18.11 | 4878
TS5500Shv | RS\10\003\B | RS | 10 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-02-23 21:10 | 2020-02-24 17:18 | 24555.0956 | [6 empty] | 24555 | 16815 | 2.01 | 0 | 0 | 18.11 | 4878
TS5500Exc | RS\10\006\X | RS | 10 | 6 | X | 8 Coal Mining | 100 | 0 | 100 | 2020-02-24 02:36 | 2020-02-24 17:48 | 19156.3854 | [6 empty] | 19156 | 13574 | 1.36 | 0 | 0 | 11.44 | 5248
DRE1 | SC\38\011\D | SC | 38 | 11 | D | 6 DL | 100 | 0 | 100 | 2020-02-24 03:15 | 2020-03-02 15:53 | 630986.561 |  |  |  | 47984 | 630987 | 431854 |  |  | 0 | 40 | 0 | 7.62 | 5744
TS5500Shv | RS\11\003\A | RS | 11 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-02-24 17:18 | 2020-02-25 08:58 | 19106.9412 | [6 empty] | 19107 | 13584 | 1.82 | 0 | 0 | 11.32 | 5411
TS5500Exc | RS\10\007\X | RS | 10 | 7 | X | 8 Coal Mining | 100 | 0 | 100 | 2020-02-24 17:48 | 2020-02-25 09:09 | 19323.7749 | [6 empty] | 19324 | 13666 | 1.37 | 0 | 0 | 11.5 | 5241
TS5500Shv | GG\09\013\X2 | GG | 9 | 13 | X2 | 1 Prestrip - Thick | 11.6404 | 0 | 11.6404 | 2020-02-25 08:58 | 2020-02-26 05:04 | 21524.8528 | 21525 | [7 empty] | 0 | 0 | 4.07 | 0 | 0
TS5500Exc | SC\38\010\D | SC | 38 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2020-02-25 09:09 | 2020-02-28 03:57 | 59085.4831 |  |  | 59085 | [5 empty] | 0 | 0 | 0 | 7.79 | 5729.7
PH4100XPC#1 | GG\08\003\D | GG | 8 | 3 | D | 1 Prestrip - Thick | 100 | 65.2009 | 65.2009 | 2020-02-25 10:41 | 2020-02-28 23:54 | 192891.6282 | 192892 | [7 empty] | 0 | 0 | 12.9 | 5.95 | 5862.29
PH4100A | RS\10\004\B | RS | 10 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-02-25 14:01 | 2020-02-26 13:10 | 38461.4346 | 38461 | [7 empty] | 0 | 0 | 3.84 | 17.66 | 4911.88
TS5500Shv | GG\09\018\X2 | GG | 9 | 18 | X2 | 1 Prestrip - Thick | 15.5909 | 0 | 15.5909 | 2020-02-26 05:04 | 2020-02-27 08:32 | 29411.4866 | 29411 | [7 empty] | 0 | 0 | 5.39 | 0 | 0
PH4100A | RS\10\005\B | RS | 10 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-02-26 13:10 | 2020-02-27 11:37 | 37298.4035 | 37298 | [7 empty] | 0 | 0 | 3.72 | 19.52 | 4738.3
TS Fleet 5 | GG\08\003\D | GG | 8 | 3 | D | 1 Prestrip - Thick | 45.3511 | 34.7991 | 34.7991 | 2020-02-26 17:01 | 2020-02-28 23:54 | 102950.5724 | 102951 | [7 empty] | 0 | 0 | 6.88 | 5.95 | 5862.29
TS5500Shv | RS\10\004\B | RS | 10 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-02-27 08:32 | 2020-02-28 08:43 | 29477.83 | [6 empty] | 29478 | 20270 | 2.03 | 0 | 0 | 17.66 | 4912
PH4100A | RS\10\006\A | RS | 10 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-02-27 11:37 | 2020-03-03 13:24 | 202362.1447 | 202362 | [7 empty] | 0 | 0 | 20.13 | 14.15 | 5087.83
TS5500Exc | RS\10\004\B | RS | 10 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-02-28 03:57 | 2020-02-29 04:08 | 30449.6266 | [6 empty] | 30450 | 20938 | 2.09 | 0 | 0 | 17.66 | 4912
TS5500Shv | GG\09\020\B | GG | 9 | 20 | B | 1 Prestrip - Thick | 11.4007 | 11.4007 | 11.4007 | 2020-02-28 08:43 | 2020-03-01 06:03 | 48688.8635 | 48689 | [7 empty] | 0 | 0 | 5.19 | 12.44 | 5334.28
PH4100XPC#1 | GG\08\006\D | GG | 8 | 6 | D | 1 Prestrip - Thick | 100 | 52.5889 | 52.5889 | 2020-02-28 23:54 | 2020-03-03 01:08 | 165760.9102 | 165761 | [7 empty] | 0 | 0 | 10.92 | 6.21 | 5841.03
TS Fleet 5 | GG\09\007\X1 | GG | 9 | 7 | X1 | 1 Prestrip - Thick | 25.8286 | 25.8286 | 25.8286 | 2020-02-28 23:54 | 2020-03-02 11:18 | 111449.6369 | 111450 | [7 empty] | 0 | 0 | 10.85 | 11.07 | 5384.11
TS5500Exc | RS\10\005\B | RS | 10 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-02-29 04:08 | 2020-03-02 04:19 | 60690.2748 | [6 empty] | 60690 | 41265 | 4.12 | 0 | 0 | 19.52 | 4738
TS5500Shv | GG\08\003\D | GG | 8 | 3 | D | 7 PostStrip | 63.2664 | 0 | 63.2664 | 2020-03-01 06:03 | 2020-03-03 17:07 | 63310.3703 |  |  | 63310 | [5 empty] | 0 | 0 | 0 | 5.95 | 5862.29
TS5500Exc | SC\38\010\D | SC | 38 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-03-02 04:19 | 2020-03-04 18:01 | 77734.7042 | [6 empty] | 77735 | 58237 | 4.85 | 0 | 0 | 7.79 | 5730
DRE2 | RS\06\008\D | RS | 6 | 8 | D | 6 DL | 100 | 100 | 100 | 2020-03-02 06:16 | 2020-03-04 22:14 | 215170.2085 |  |  |  | 8041 | 215170 | 122116 |  |  | 0 | 26.22 | 0 | 6.84 | 5815.92
TS Fleet 5 | GG\09\008\X1 | GG | 9 | 8 | X1 | 1 Prestrip - Thick | 32.603 | 32.603 | 32.603 | 2020-03-02 11:18 | 2020-03-05 03:22 | 120168.3761 | 120168 | [7 empty] | 0 | 0 | 11.87 | 11.4 | 5385.08
DRE1 | SC\38\012\D | SC | 38 | 12 | D | 6 DL | 100 | 0 | 100 | 2020-03-02 15:53 | 2020-03-09 14:06 | 580576.2848 |  |  |  | 41290 | 580576 | 417483 |  |  | 0 | 38.16 | 0 | 7.52 | 5751.92
PH4100XPC#1 | GG\08\004\X1 | GG | 8 | 4 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-03-03 01:08 | 2020-03-22 19:06 | 1086638.192 | 1086638 | [7 empty] | 0 | 0 | 58.79 | 9.69 | 5441.88
PH4100A | RS\10\007\A | RS | 10 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-03-03 13:24 | 2020-03-09 01:57 | 220235.4207 | 220235 | [7 empty] | 0 | 0 | 22.03 | 16.15 | 4958.31
TS5500Shv | GG\08\006\D | GG | 8 | 6 | D | 7 PostStrip | 27.1662 | 0 | 27.1662 | 2020-03-03 17:07 | 2020-03-04 18:27 | 27162.6897 |  |  | 27163 | [5 empty] | 0 | 0 | 0 | 6.21 | 5841.03
TS5500Exc | RS\06\007\D | RS | 6 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-03-04 18:01 | 2020-03-06 19:42 | 62573.0662 | [6 empty] | 62573 | 45594 | 4.56 | 0 | 0 | 6.8 | 5823
TS5500Shv | MW\27\011\D | MW | 27 | 11 | D | 7 PostStrip | 100 | 0 | 100 | 2020-03-04 18:27 | 2020-03-07 10:53 | 69069.1705 |  |  | 69069 | [5 empty] | 0 | 0 | 0 | 5.78 | 5903.73
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 4d 00:00 |  | 4d 00:00 | 2020-03-04 22:14 | 2020-03-08 22:14
TS Fleet 5 | GG\09\009\X1 | GG | 9 | 9 | X1 | 1 Prestrip - Thick | 32.5011 | 32.5011 | 32.5011 | 2020-03-05 03:22 | 2020-03-07 15:25 | 112660.4572 | 112660 | [7 empty] | 0 | 0 | 11.05 | 11.41 | 5382.6
TS5500Exc | SC\38\011\D | SC | 38 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-03-06 19:42 | 2020-03-09 08:15 | 76272.7631 | [6 empty] | 76273 | 56960 | 4.75 | 0 | 0 | 7.62 | 5744
TS5500Shv | RS\06\008\D | RS | 6 | 8 | D | 7 PostStrip | 100 | 0 | 100 | 2020-03-07 10:53 | 2020-03-08 15:29 | 30670.062 |  |  | 30670 | [5 empty] | 0 | 0 | 0 | 6.84 | 5815.92
TS Fleet 5 | GG\09\010\B | GG | 9 | 10 | B | 1 Prestrip - Thick | 32.1675 | 32.1675 | 32.1675 | 2020-03-07 15:25 | 2020-03-11 09:07 | 168293.7043 | 168294 | [7 empty] | 0 | 0 | 17.82 | 10.55 | 5461.04
TS5500Shv | RS\06\008\D | RS | 6 | 8 | D | 8 Coal Mining | 7.8 | 0 | 7.8 | 2020-03-08 15:29 | 2020-03-08 17:32 | 2492.6767 | [6 empty] | 2493 | 1817 | 0.31 | 0 | 0 | 6.84 | 5816
TS5500Shv | RS\10\006\A | RS | 10 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-03-08 17:32 | 2020-03-09 14:15 | 25265.8714 | [6 empty] | 25266 | 17464 | 1.75 | 0 | 0 | 14.15 | 5088
DRE2 | MW\28\003\D | MW | 28 | 3 | D | 6 DL | 100 | 100 | 100 | 2020-03-08 22:14 | 2020-03-15 21:44 | 563396.394 |  |  |  | 33646 | 563396 | 397717 |  |  | 0 | 26.97 | 0 | 6.67 | 5826.9
PH4100A | SC\39\020\D | SC | 39 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-03-09 01:57 | 2020-03-13 13:06 | 176352.8447 | 176353 | [7 empty] | 0 | 0 | 15.09 | 6.83 | 5812.04
TS5500Exc | MW\27\011\D | MW | 27 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-03-09 08:15 | 2020-03-11 22:51 | 78851.9094 | [6 empty] | 78852 | 59716 | 4.42 | 0 | 0 | 5.78 | 5904
DRE1 | SC\38\013\D | SC | 38 | 13 | D | 6 DL | 100 | 0 | 100 | 2020-03-09 14:06 | 2020-03-15 14:12 | 503360.5635 |  |  |  | 28728 | 503361 | 381676 |  |  | 0 | 33.95 | 0 | 7.67 | 5738.05
TS5500Shv | RS\10\007\A | RS | 10 | 7 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-03-09 14:15 | 2020-03-10 10:40 | 24896.403 | [6 empty] | 24896 | 17104 | 1.71 | 0 | 0 | 16.15 | 4958
TS5500Shv | MW\30\010\X | MW | 30 | 10 | X | 8 Coal Mining | 100 | 0 | 100 | 2020-03-10 10:40 | 2020-03-11 01:57 | 18629.4235 | [6 empty] | 18629 | 13578 | 1.36 | 0 | 0 | 12.27 | 5203
TS5500Shv | GG\09\024\B | GG | 9 | 24 | B | 1 Prestrip - Thick | 5.1763 | 5.1763 | 5.1763 | 2020-03-11 01:57 | 2020-03-11 16:23 | 15481.6 | 15482 | [7 empty] | 0 | 0 | 1.75 | 11.68 | 5303.53
TS Fleet 5 | GG\09\011\X1 | GG | 9 | 11 | X1 | 1 Prestrip - Thick | 27.235 | 27.235 | 27.235 | 2020-03-11 09:07 | 2020-03-13 04:40 | 81706.6105 | 81707 | [7 empty] | 0 | 0 | 8.65 | 12.68 | 5289.17
TS5500Shv | GG\09\025\D | GG | 9 | 25 | D | 1 Prestrip - Thick | 15.3378 | 15.3378 | 15.3378 | 2020-03-11 16:23 | 2020-03-12 08:07 | 16919.0742 | 16919 | [7 empty] | 0 | 0 | 2.12 | 5.97 | 5861.67
TS5500Exc | RS\06\008\D | RS | 6 | 8 | D | 8 Coal Mining | 92.2 | 0 | 92.2 | 2020-03-11 22:51 | 2020-03-12 22:22 | 29625.5352 | [6 empty] | 29626 | 21600 | 3.63 | 0 | 0 | 6.84 | 5816
TS6060#1 | GG\08\006\D | GG | 8 | 6 | D | 7 PostStrip | 72.8338 | 0 | 72.8338 | 2020-03-12 04:44 | 2020-03-15 03:19 | 72824.3875 |  |  | 72824 | [5 empty] | 0 | 0 | 0 | 6.21 | 5841.03
TS5500Shv | RS\11\004\A | RS | 11 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-03-12 08:07 | 2020-03-13 04:36 | 24975.9724 | [6 empty] | 24976 | 17571 | 1.76 | 0 | 0 | 12.47 | 5310
TS5500Exc | RS\10\006\A | RS | 10 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-03-12 22:22 | 2020-03-13 19:06 | 26098.8122 | [6 empty] | 26099 | 18040 | 1.8 | 0 | 0 | 14.15 | 5088
TS5500Shv | MW\30\011\X | MW | 30 | 11 | X | 8 Coal Mining | 100 | 0 | 100 | 2020-03-13 04:36 | 2020-03-13 15:57 | 13832.2745 | [6 empty] | 13832 | 10080 | 1.26 | 0 | 0 | 12.4 | 5177
TS Fleet 5 | GG\09\012\X2 | GG | 9 | 12 | X2 | 1 Prestrip - Thick | 31.8758 | 0 | 31.8758 | 2020-03-13 04:40 | 2020-03-15 22:17 | 123080.5998 | 123081 | [7 empty] | 0 | 0 | 13.4 | 0 | 0
PH4100A | SC\38\020\D | SC | 38 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-03-13 13:06 | 2020-03-18 13:34 | 196783.1218 | 196783 | [7 empty] | 0 | 0 | 16.54 | 7.23 | 5775.15
TS5500Shv | MW\31\003\B | MW | 31 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-03-13 15:57 | 2020-03-15 02:24 | 42005.53 | [6 empty] | 42006 | 31168 | 3.12 | 0 | 0 | 8.57 | 5651
TS5500Exc | RS\10\007\A | RS | 10 | 7 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-03-13 19:06 | 2020-03-14 15:31 | 25717.1635 | [6 empty] | 25717 | 17668 | 1.76 | 0 | 0 | 16.15 | 4958
TS5500Exc | SC\38\012\D | SC | 38 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-03-14 15:31 | 2020-03-17 02:54 | 74805.7364 | [6 empty] | 74806 | 55775 | 4.65 | 0 | 0 | 7.52 | 5752
TS5500Shv | MW\31\004\B | MW | 31 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-03-15 02:24 | 2020-03-15 19:31 | 20868.6191 | [6 empty] | 20869 | 15462 | 1.53 | 0 | 0 | 8.72 | 5629
TS6060#1 | GG\08\006\D | GG | 8 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-03-15 03:19 | 2020-03-18 23:25 | 124641.2651 | [6 empty] | 124641 | 93698 | 4.68 | 0 | 0 | 6.21 | 5841
DRE1 | SC\38\014\D | SC | 38 | 14 | D | 6 DL | 100 | 0 | 100 | 2020-03-15 14:12 | 2020-03-21 08:58 | 484769.4615 |  |  |  | 27667 | 484769 | 367579 |  |  | 0 | 32.62 | 0 | 7.66 | 5737.49
TS5500Shv | MW\31\005\B | MW | 31 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-03-15 19:31 | 2020-03-16 11:37 | 19645.6842 | [6 empty] | 19646 | 14538 | 1.44 | 0 | 0 | 8.85 | 5615
DRE2 | MW\28\004\D | MW | 28 | 4 | D | 6 DL | 100 | 100 | 100 | 2020-03-15 21:44 | 2020-03-22 19:22 | 557174.717 |  |  |  | 33275 | 557175 | 393325 |  |  | 0 | 26.6 | 0 | 6.29 | 5858.8
TS Fleet 5 | GG\09\013\X2 | GG | 9 | 13 | X2 | 1 Prestrip - Thick | 28.6344 | 0 | 28.6344 | 2020-03-15 22:17 | 2020-03-17 02:30 | 52949.3131 | 52949 | [7 empty] | 0 | 0 | 10.02 | 0 | 0
TS5500Shv | MW\28\003\D | MW | 28 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-03-16 11:37 | 2020-03-18 03:13 | 48281.7285 | [6 empty] | 48282 | 36421 | 2.28 | 0 | 0 | 6.67 | 5827
TS Fleet 5 | GG\09\018\X2 | GG | 9 | 18 | X2 | 1 Prestrip - Thick | 27.3516 | 0 | 27.3516 | 2020-03-17 02:30 | 2020-03-18 06:01 | 51597.4771 | 51597 | [7 empty] | 0 | 0 | 9.45 | 0 | 0
TS5500Exc | MW\28\003\D | MW | 28 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-03-17 02:54 | 2020-03-18 18:30 | 49873.4338 | [6 empty] | 49873 | 37622 | 2.35 | 0 | 0 | 6.67 | 5827
TS5500Shv | MW\31\006\B | MW | 31 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-03-18 03:13 | 2020-03-19 12:49 | 40964.6771 | [6 empty] | 40965 | 30322 | 3.01 | 0 | 0 | 8.82 | 5624
TS Fleet 5 | GG\09\019\B | GG | 9 | 19 | B | 1 Prestrip - Thick | 31.8015 | 31.8015 | 31.8015 | 2020-03-18 06:01 | 2020-03-20 21:27 | 119024.8119 | 119025 | [7 empty] | 0 | 0 | 11.83 | 11.67 | 5390.36
PH4100A | RS\10\006\B | RS | 10 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-03-18 13:34 | 2020-03-19 08:17 | 31100.7518 | 31101 | [7 empty] | 0 | 0 | 3.11 | 10 | 5453.81
TS5500Exc | RS\11\003\A | RS | 11 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-03-18 18:30 | 2020-03-19 10:10 | 19736.8404 | [6 empty] | 19737 | 14032 | 1.88 | 0 | 0 | 11.32 | 5411
TS6060#1 | GG\08\005\B | GG | 8 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-03-18 23:25 | 2020-03-22 02:23 | 101464.4417 | [6 empty] | 101464 | 74123 | 3.71 | 0 | 0 | 10.93 | 5365
PH4100A | RS\10\007\B | RS | 10 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-03-19 08:17 | 2020-03-19 23:38 | 25511.6696 | 25512 | [7 empty] | 0 | 0 | 2.55 | 20.48 | 4655.79
TS5500Exc | RS\10\008\A | RS | 10 | 8 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-03-19 10:10 | 2020-03-20 05:15 | 24045.8992 | [6 empty] | 24046 | 16429 | 3.47 | 0 | 0 | 18 | 4842
TS5500Shv | RS\10\006\B | RS | 10 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-03-19 12:49 | 2020-03-20 22:33 | 41147.8275 | [6 empty] | 41148 | 29114 | 2.91 | 0 | 0 | 10 | 5454
PH4100A | SC\39\021\D | SC | 39 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-03-19 23:38 | 2020-03-25 05:26 | 205657.9829 | 205658 | [7 empty] | 0 | 0 | 17.41 | 7.33 | 5766.54
TS5500Exc | RS\10\007\B | RS | 10 | 7 | B | 8 Coal Mining | 46 | 0 | 46 | 2020-03-20 05:15 | 2020-03-21 02:49 | 27164.886 | [6 empty] | 27165 | 18266 | 1.83 | 0 | 0 | 20.48 | 4656
TS Fleet 5 | GG\09\020\B | GG | 9 | 20 | B | 1 Prestrip - Thick | 28.2488 | 28.2488 | 28.2488 | 2020-03-20 21:27 | 2020-03-23 13:46 | 120642.1829 | 120642 | [7 empty] | 0 | 0 | 12.85 | 12.44 | 5334.28
TS5500Shv | RS\10\007\B | RS | 10 | 7 | B | 8 Coal Mining | 54 | 0 | 54 | 2020-03-20 22:33 | 2020-03-22 00:42 | 31874.7774 | [6 empty] | 31875 | 21433 | 2.14 | 0 | 0 | 20.48 | 4656
TS5500Exc | RS\11\005\X | RS | 11 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2020-03-21 02:49 | 2020-03-21 18:10 | 19330.9385 | [6 empty] | 19331 | 13534 | 1.36 | 0 | 0 | 13.11 | 5151
DRE1 | SC\38\015\D | SC | 38 | 15 | D | 6 DL | 100 | 0 | 100 | 2020-03-21 08:58 | 2020-03-26 21:11 | 461819.9061 |  |  |  | 26357 | 461820 | 350177 |  |  | 0 | 31.83 | 0 | 7.39 | 5759.32
TS5500Exc | SC\38\013\D | SC | 38 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-03-21 18:10 | 2020-03-24 03:48 | 72604.212 | [6 empty] | 72604 | 54261 | 4.52 | 0 | 0 | 7.67 | 5738
TS5500Shv | MW\31\007\B | MW | 31 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-03-22 00:42 | 2020-03-23 09:38 | 40165.0007 | [6 empty] | 40165 | 29575 | 2.95 | 0 | 0 | 9.55 | 5539
TS6060#1 | GG\08\003\D | GG | 8 | 3 | D | 7 PostStrip | 36.7336 | 0 | 36.7336 | 2020-03-22 02:23 | 2020-03-23 14:01 | 36759.0838 |  |  | 36759 | [5 empty] | 0 | 0 | 0 | 5.95 | 5862.29
PH4100XPC#1 | GG\08\005\D | GG | 8 | 5 | D | 1 Prestrip - Thick | 100 | 60.7983 | 60.7983 | 2020-03-22 19:06 | 2020-03-26 07:10 | 190288.9762 | 190289 | [7 empty] | 0 | 0 | 12.56 | 6.17 | 5843.14
DRE2 | MW\28\005\D | MW | 28 | 5 | D | 6 DL | 100 | 100 | 100 | 2020-03-22 19:22 | 2020-03-29 20:58 | 570470.2127 |  |  |  | 34069 | 570470 | 402711 |  |  | 0 | 27.34 | 0 | 6.05 | 5879.29
TS5500Shv | GG\08\004\X1 | GG | 8 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-03-23 09:38 | 2020-03-24 16:54 | 38128.9714 | [6 empty] | 38129 | 28341 | 1.43 | 0 | 0 | 9.69 | 5442
TS Fleet 5 | GG\08\005\D | GG | 8 | 5 | D | 1 Prestrip - Thick | 45.3511 | 39.2017 | 39.2017 | 2020-03-23 13:46 | 2020-03-26 07:10 | 122694.955 | 122695 | [7 empty] | 0 | 0 | 8.1 | 6.17 | 5843.14
TS6060#1 | GG\08\003\D | GG | 8 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-03-23 14:01 | 2020-03-27 06:42 | 120030.2702 | [6 empty] | 120030 | 90229 | 4.51 | 0 | 0 | 5.95 | 5862
TS5500Exc | MW\28\004\D | MW | 28 | 4 | D | 8 Coal Mining | 19 | 0 | 19 | 2020-03-24 03:48 | 2020-03-24 18:05 | 17976.4022 | [6 empty] | 17976 | 13603 | 0.85 | 0 | 0 | 6.29 | 5859
TS5500Shv | MW\28\004\D | MW | 28 | 4 | D | 8 Coal Mining | 81 | 0 | 81 | 2020-03-24 16:54 | 2020-03-27 07:56 | 76860.764 | [6 empty] | 76861 | 58162 | 3.64 | 0 | 0 | 6.29 | 5859
TS5500Exc | RS\11\006\X | RS | 11 | 6 | X | 8 Coal Mining | 100 | 0 | 100 | 2020-03-24 18:05 | 2020-03-25 11:38 | 22115.1478 | [6 empty] | 22115 | 15685 | 1.57 | 0 | 0 | 11.27 | 5260
PH4100A | RS\10\008\B | RS | 10 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-03-25 05:26 | 2020-03-25 12:22 | 11510.1331 | 11510 | [7 empty] | 0 | 0 | 2.45 | 18.4 | 4858.4
TS5500Exc | RS\11\007\X | RS | 11 | 7 | X | 8 Coal Mining | 63.4 | 0 | 63.4 | 2020-03-25 11:38 | 2020-03-26 01:03 | 16902.3159 | [6 empty] | 16902 | 11942 | 0.81 | 0 | 0 | 11.6 | 5227
PH4100A | SC\38\021\D | SC | 38 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-03-25 12:22 | 2020-03-30 22:50 | 213110.5465 | 213111 | [7 empty] | 0 | 0 | 18.02 | 7.36 | 5764.71
TS5500Exc | RS\10\008\B | RS | 10 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-03-26 01:03 | 2020-03-26 20:45 | 24811.9739 | [6 empty] | 24812 | 16833 | 3.79 | 0 | 0 | 18.4 | 4858
TS Fleet 5 | GG\08\004\X2 | GG | 8 | 4 | X2 | 1 Prestrip - Thick | 45.3511 | 0 | 45.3193 | 2020-03-26 07:10 | 2020-03-28 18:30 | 111294.973 | 111295 | [7 empty] | 0 | 0 | 5.63 | 0 | 0
PH4100XPC#1 | GG\08\004\X2 | GG | 8 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.6807 | 2020-03-26 07:10 | 2020-03-28 18:30 | 134284.86 | 134285 | [7 empty] | 0 | 0 | 6.79 | 0 | 0
TS5500Exc | RS\12\003\A | RS | 12 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-03-26 20:45 | 2020-03-27 12:35 | 19931.4878 | [6 empty] | 19931 | 14136 | 1.88 | 0 | 0 | 11.45 | 5406
DRE1 | SC\38\016\D | SC | 38 | 16 | D | 6 DL | 100 | 0 | 100 | 2020-03-26 21:11 | 2020-04-05 00:58 | 767736.5318 |  |  |  | 53440 | 767737 | 480960 |  |  | 0 | 40 | 0 | 7.07 | 5788.19
TS6060#1 | RS\11\003\B | RS | 11 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-03-27 06:42 | 2020-03-28 03:25 | 21377.9194 | 21378 | [7 empty] | 0 | 0 | 2.8 | 19.41 | 4776.16
TS5500Shv | GG\08\005\D | GG | 8 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2020-03-27 07:56 | 2020-03-31 05:09 | 99935.171 |  |  | 99935 | [5 empty] | 0 | 0 | 0 | 6.17 | 5843.14
TS5500Exc | SC\38\014\D | SC | 38 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-03-27 12:35 | 2020-03-29 18:56 | 68459.0143 | [6 empty] | 68459 | 51283 | 4.27 | 0 | 0 | 7.66 | 5737
TS6060#1 | RS\11\005\A | RS | 11 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-03-28 03:25 | 2020-04-05 10:51 | 205771.9543 | 205772 | [7 empty] | 0 | 0 | 20.52 | 14.62 | 5105.82
TS Fleet 5 | GG\08\004\B | GG | 8 | 4 | B | 1 Prestrip - Thick | 45.3511 | 45.3193 | 45.3193 | 2020-03-28 18:30 | 2020-03-31 21:39 | 140983.5209 | 140984 | [7 empty] | 0 | 0 | 7.04 | 10.01 | 5493.29
PH4100XPC#1 | GG\08\004\B | GG | 8 | 4 | B | 1 Prestrip - Thick | 100 | 54.6807 | 54.6807 | 2020-03-28 18:30 | 2020-03-31 21:39 | 170106.087 | 170106 | [7 empty] | 0 | 0 | 8.49 | 10.01 | 5493.29
TS5500Exc | RS\12\006\X | RS | 12 | 6 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-03-29 18:56 | 2020-03-30 03:22 | 10639.6907 | [6 empty] | 10640 | 7557 | 0.76 | 0 | 0 | 11.06 | 5276
DRE2 | MW\28\006\D | MW | 28 | 6 | D | 6 DL | 100 | 100 | 100 | 2020-03-29 20:58 | 2020-04-06 10:31 | 610708.4094 |  |  |  | 36472 | 610708 | 431116 |  |  | 0 | 29.24 | 0 | 6.22 | 5864.88
TS5500Exc | MW\28\005\D | MW | 28 | 5 | D | 8 Coal Mining | 34.2 | 0 | 34.2 | 2020-03-30 03:22 | 2020-03-31 04:23 | 31506.4859 | [6 empty] | 31506 | 23802 | 1.49 | 0 | 0 | 6.05 | 5879
PH4100A | SC\39\022\D | SC | 39 | 22 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-03-30 22:50 | 2020-04-04 21:38 | 194373.9097 | 194374 | [7 empty] | 0 | 0 | 16.49 | 7.41 | 5760.69
TS5500Exc | RS\12\007\X | RS | 12 | 7 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-03-31 04:23 | 2020-03-31 14:14 | 12406.1177 | [6 empty] | 12406 | 8811 | 0.64 | 0 | 0 | 11 | 5277
TS5500Shv | GG\08\005\D | GG | 8 | 5 | D | 8 Coal Mining | 58.7 | 0 | 58.7 | 2020-03-31 05:09 | 2020-04-02 15:19 | 70922.3228 | [6 empty] | 70922 | 53315 | 2.67 | 0 | 0 | 6.17 | 5843
TS5500Exc | RS\13\003\A | RS | 13 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-03-31 14:14 | 2020-04-01 06:13 | 20134.8508 | [6 empty] | 20135 | 14242 | 1.87 | 0 | 0 | 11.55 | 5403
TS Fleet 5 | GG\09\004\X1 | GG | 9 | 4 | X1 | 1 Prestrip - Thick | 44.9506 | 44.9506 | 44.9506 | 2020-03-31 21:39 | 2020-04-06 18:02 | 263376.6483 | 263377 | [7 empty] | 0 | 0 | 25.51 | 9.99 | 5410.61
PH4100XPC#1 | GG\09\002\X1 | GG | 9 | 2 | X1 | 1 Prestrip - Thick | 100 | 0 | 54.6489 | 2020-03-31 21:39 | 2020-04-02 21:05 | 107384.5766 | 107385 | [7 empty] | 0 | 0 | 7.28 | 0 | 0
TS5500Exc | RS\13\004\X | RS | 13 | 4 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-04-01 06:13 | 2020-04-01 14:54 | 10937.7153 | [6 empty] | 10938 | 7622 | 0.77 | 0 | 0 | 13.73 | 5111
TS5500Exc | RS\11\004\A | RS | 11 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-04-01 14:54 | 2020-04-02 11:23 | 25799.3561 | [6 empty] | 25799 | 18151 | 1.81 | 0 | 0 | 12.47 | 5310
TS5500Exc | SC\38\015\D | SC | 38 | 15 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-04-02 11:23 | 2020-04-04 11:03 | 60042.427 | [6 empty] | 60042 | 44975 | 4.02 | 0 | 0 | 7.39 | 5759
TS5500Shv | GG\08\004\B | GG | 8 | 4 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2020-04-02 15:19 | 2020-04-04 07:48 | 49359.5485 | [6 empty] | 49360 | 36175 | 1.81 | 0 | 0 | 10.01 | 5493
PH4100XPC#1 | GG\09\002\B | GG | 9 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-02 21:05 | 2020-04-05 13:17 | 145328.2854 | 145328 | [7 empty] | 0 | 0 | 10.06 | 9.78 | 5546.26
TS5500Shv | MW\28\005\D | MW | 28 | 5 | D | 8 Coal Mining | 65.8 | 0 | 65.8 | 2020-04-04 07:48 | 2020-04-06 09:35 | 60719.1355 | [6 empty] | 60719 | 45871 | 2.87 | 0 | 0 | 6.05 | 5879
TS5500Exc | RS\13\005\X | RS | 13 | 5 | X | 8 Coal Mining | 33.6 | 0 | 33.6 | 2020-04-04 11:03 | 2020-04-04 16:12 | 6482.586 | [6 empty] | 6483 | 4543 | 0.46 | 0 | 0 | 12.72 | 5173
TS5500Exc | SC\37\024\D | SC | 37 | 24 | D | 7 PostStrip | 100 | 0 | 100 | 2020-04-04 16:12 | 2020-04-07 15:13 | 62811.8264 |  |  | 62812 | [5 empty] | 0 | 0 | 0 | 7.04 | 5794.8
PH4100A | SC\38\022\D | SC | 38 | 22 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-04 21:38 | 2020-04-08 19:25 | 153158.5751 | 153159 | [7 empty] | 0 | 0 | 13.13 | 7.27 | 5773.6
DRE1 | SC\38\017\D | SC | 38 | 17 | D | 6 DL | 100 | 0 | 100 | 2020-04-05 00:58 | 2020-04-13 23:31 | 749461.9242 |  |  |  | 56993 | 749462 | 512940 |  |  | 0 | 40 | 0 | 6.84 | 5809.99
TS6060#1 | GG\08\004\B | GG | 8 | 4 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2020-04-05 10:51 | 2020-04-07 03:19 | 54783.6748 | [6 empty] | 54784 | 40151 | 2.01 | 0 | 0 | 10.01 | 5493
PH4100XPC#1 | GG\09\003\X1 | GG | 9 | 3 | X1 | 1 Prestrip - Thick | 100 | 54.3529 | 54.3529 | 2020-04-05 13:17 | 2020-04-11 21:31 | 340493.5611 | 340494 | [7 empty] | 0 | 0 | 31.95 | 9.31 | 5472.37
TS5500Shv | RS\11\003\B | RS | 11 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-04-06 09:35 | 2020-04-08 03:55 | 51606.6834 | [6 empty] | 51607 | 35031 | 4.14 | 0 | 0 | 19.41 | 4776
DRE2 | MW\28\007\D | MW | 28 | 7 | D | 6 DL | 100 | 100 | 100 | 2020-04-06 10:31 | 2020-04-14 12:24 | 652183.6291 |  |  |  | 38949 | 652184 | 460394 |  |  | 0 | 31.23 | 0 | 6.5 | 5841.04
TS Fleet 5 | GG\09\021\B | GG | 9 | 21 | B | 1 Prestrip - Thick | 32.3641 | 32.3641 | 32.3641 | 2020-04-06 18:02 | 2020-04-09 03:25 | 107633.9983 | 107634 | [7 empty] | 0 | 0 | 11.06 | 13.23 | 5271.29
TS6060#1 | GG\09\002\B | GG | 9 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-04-07 03:19 | 2020-04-09 11:09 | 75545.0165 | [6 empty] | 75545 | 55495 | 3.89 | 0 | 0 | 9.78 | 5546
TS5500Exc | SC\37\024\D | SC | 37 | 24 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-04-07 15:13 | 2020-04-10 04:58 | 77763.2641 | [6 empty] | 77763 | 57891 | 4.83 | 0 | 0 | 7.04 | 5795
TS5500Shv | MW\28\006\D | MW | 28 | 6 | D | 8 Coal Mining | 77.5 | 0 | 77.5 | 2020-04-08 03:55 | 2020-04-10 15:16 | 72375.6003 | [6 empty] | 72376 | 54502 | 3.41 | 0 | 0 | 6.22 | 5865
PH4100A | SC\39\023\D | SC | 39 | 23 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-08 19:25 | 2020-04-12 08:19 | 138760.4953 | 138760 | [7 empty] | 0 | 0 | 11.92 | 7.31 | 5770.82
TS Fleet 5 | GG\08\004\D | GG | 8 | 4 | D | 1 Prestrip - Thick | 45.3511 | 45.3511 | 45.3511 | 2020-04-09 03:25 | 2020-04-12 02:21 | 133088.0407 | 133088 | [7 empty] | 0 | 0 | 8.92 | 6.03 | 5853.93
TS6060#1 | GG\08\005\D | GG | 8 | 5 | D | 8 Coal Mining | 41.3 | 0 | 41.3 | 2020-04-09 11:09 | 2020-04-10 23:57 | 49806.5849 | [6 empty] | 49807 | 37441 | 1.87 | 0 | 0 | 6.17 | 5843
TS5500Exc | MW\28\006\D | MW | 28 | 6 | D | 8 Coal Mining | 22.5 | 0 | 22.5 | 2020-04-10 04:58 | 2020-04-10 21:39 | 21025.6411 | [6 empty] | 21026 | 15833 | 0.99 | 0 | 0 | 6.22 | 5865
TS5500Shv | RS\11\005\A | RS | 11 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-04-10 15:16 | 2020-04-12 09:30 | 51508.5775 | [6 empty] | 51509 | 35666 | 3.56 | 0 | 0 | 14.62 | 5106
TS5500Exc | SC\38\016\D | SC | 38 | 16 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-04-10 21:39 | 2020-04-13 07:13 | 72501.8274 | [6 empty] | 72502 | 54310 | 4.16 | 0 | 0 | 7.07 | 5788
TS6060#1 | RS\11\004\B | RS | 11 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-10 23:57 | 2020-04-12 13:09 | 38383.5264 | 38384 | [7 empty] | 0 | 0 | 3.84 | 18.56 | 4843.23
PH4100XPC#1 | GG\08\004\D | GG | 8 | 4 | D | 1 Prestrip - Thick | 100 | 54.6489 | 54.6489 | 2020-04-11 21:31 | 2020-04-14 20:22 | 160373.1836 | 160373 | [7 empty] | 0 | 0 | 10.75 | 6.03 | 5853.93
TS Fleet 5 | GG\09\022\X2 | GG | 9 | 22 | X2 | 1 Prestrip - Thick | 31.9063 | 0 | 31.9063 | 2020-04-12 02:21 | 2020-04-13 17:13 | 72913.21 | 72913 | [7 empty] | 0 | 0 | 7.59 | 0 | 0
PH4100A | SC\38\023\D | SC | 38 | 23 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-12 08:19 | 2020-04-15 18:13 | 133948.396 | 133948 | [7 empty] | 0 | 0 | 11.5 | 7.18 | 5782.33
TS5500Shv | GG\09\003\X1 | GG | 9 | 3 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2020-04-12 09:30 | 2020-04-12 16:32 | 8563.482 | [6 empty] | 8563 | 6384 | 0.64 | 0 | 0 | 9.31 | 5472
TS6060#1 | GG\09\003\X1 | GG | 9 | 3 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2020-04-12 13:09 | 2020-04-12 20:10 | 9504.5239 | [6 empty] | 9505 | 7086 | 0.71 | 0 | 0 | 9.31 | 5472
TS5500Shv | RS\11\004\B | RS | 11 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-04-12 16:32 | 2020-04-14 18:17 | 60676.5987 | [6 empty] | 60677 | 41467 | 4.14 | 0 | 0 | 18.56 | 4843
TS6060#1 | RS\11\005\B | RS | 11 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-12 20:10 | 2020-04-14 08:04 | 37041.617 | 37042 | [7 empty] | 0 | 0 | 3.7 | 9.45 | 5549.11
TS5500Exc | MW\30\009\B | MW | 30 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-13 07:13 | 2020-04-15 00:03 | 36116.5528 | 36117 | [7 empty] | 0 | 0 | 3.64 | 9.84 | 5514.1
TS Fleet 5 | GG\09\003\X2 | GG | 9 | 3 | X2 | 1 Prestrip - Thick | 32.3667 | 0 | 32.3667 | 2020-04-13 17:13 | 2020-04-14 16:38 | 43937.5782 | 43938 | [7 empty] | 0 | 0 | 4.45 | 0 | 0
DRE1 | SC\38\018\D | SC | 38 | 18 | D | 6 DL | 100 | 0 | 100 | 2020-04-13 23:31 | 2020-04-23 17:25 | 817017.1568 |  |  |  | 62131 | 817017 | 559175 |  |  | 0 | 40 | 0 | 6.76 | 5817.56
TS6060#1 | RS\11\006\A | RS | 11 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-14 08:04 | 2020-04-22 15:11 | 205455.2229 | 205455 | [7 empty] | 0 | 0 | 20.57 | 14.64 | 5056.31
DRE2 | MW\28\008\D | MW | 28 | 8 | D | 6 DL | 100 | 100 | 100 | 2020-04-14 12:24 | 2020-04-22 22:26 | 679546.7882 |  |  |  | 50796 | 679547 | 467532 |  |  | 0 | 32.38 | 0 | 6.54 | 5838.63
TS Fleet 5 | GG\09\023\B | GG | 9 | 23 | B | 1 Prestrip - Thick | 31.7398 | 31.7398 | 31.7398 | 2020-04-14 16:38 | 2020-04-17 03:43 | 110826.2416 | 110826 | [7 empty] | 0 | 0 | 11.51 | 16.97 | 4919.18
TS5500Shv | MW\28\007\D | MW | 28 | 7 | D | 8 Coal Mining | 25 | 0 | 25 | 2020-04-14 18:17 | 2020-04-15 14:00 | 24038.2632 | [6 empty] | 24038 | 18045 | 1.13 | 0 | 0 | 6.5 | 5841
PH4100XPC#1 | GG\09\003\X2 | GG | 9 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 67.6333 | 2020-04-14 20:22 | 2020-04-16 12:56 | 91811.5748 | 91812 | [7 empty] | 0 | 0 | 9.29 | 0 | 0
TS5500Exc | MW\28\007\D | MW | 28 | 7 | D | 8 Coal Mining | 75 | 0 | 75 | 2020-04-15 00:03 | 2020-04-17 09:14 | 72039.4618 | [6 empty] | 72039 | 54079 | 3.38 | 0 | 0 | 6.5 | 5841
TS5500Shv | GG\08\004\D | GG | 8 | 4 | D | 7 PostStrip | 97.5594 | 0 | 97.5594 | 2020-04-15 14:00 | 2020-04-19 09:03 | 97610.4569 |  |  | 97610 | [5 empty] | 0 | 0 | 0 | 6.03 | 5853.93
PH4100A | SC\39\024\D | SC | 39 | 24 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-15 18:13 | 2020-04-18 18:18 | 118028.0892 | 118028 | [7 empty] | 0 | 0 | 10.18 | 7.27 | 5774.74
PH4100XPC#1 | GG\09\003\B | GG | 9 | 3 | B | 1 Prestrip - Thick | 100 | 67.6333 | 67.6333 | 2020-04-16 12:56 | 2020-04-18 01:01 | 81672.4928 | 81672 | [7 empty] | 0 | 0 | 8.22 | 9.43 | 5572.64
TS Fleet 5 | GG\09\003\B | GG | 9 | 3 | B | 1 Prestrip - Thick | 32.3667 | 32.3667 | 32.3667 | 2020-04-17 03:43 | 2020-04-18 00:33 | 39085.3936 | 39085 | [7 empty] | 0 | 0 | 3.93 | 9.43 | 5572.64
TS5500Exc | RS\11\005\B | RS | 11 | 5 | B | 8 Coal Mining | 69.1 | 0 | 69.1 | 2020-04-17 09:14 | 2020-04-18 07:47 | 28403.3826 | [6 empty] | 28403 | 20295 | 2.02 | 0 | 0 | 9.45 | 5549
TS Fleet 5 | GG\09\024\B | GG | 9 | 24 | B | 1 Prestrip - Thick | 30.0446 | 30.0446 | 30.0446 | 2020-04-18 00:33 | 2020-04-20 00:27 | 89858.6846 | 89859 | [7 empty] | 0 | 0 | 10.16 | 11.68 | 5303.53
PH4100XPC#1 | GG\09\004\X1 | GG | 9 | 4 | X1 | 1 Prestrip - Thick | 100 | 55.0494 | 55.0494 | 2020-04-18 01:01 | 2020-04-23 21:14 | 322547.6135 | 322548 | [7 empty] | 0 | 0 | 31.24 | 9.99 | 5410.61
TS5500Exc | MW\30\009\B | MW | 30 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-04-18 07:47 | 2020-04-19 15:03 | 39384.3438 | [6 empty] | 39384 | 28997 | 2.92 | 0 | 0 | 9.84 | 5514
PH4100A | SC\38\024\D | SC | 38 | 24 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-18 18:18 | 2020-04-22 16:18 | 153244.1477 | 153244 | [7 empty] | 0 | 0 | 13.06 | 7.18 | 5782.48
TS5500Shv | GG\09\003\B | GG | 9 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-04-19 09:03 | 2020-04-21 04:22 | 52821.4501 | [6 empty] | 52821 | 38823 | 3.88 | 0 | 0 | 9.43 | 5573
TS5500Exc | SC\38\017\D | SC | 38 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-04-19 15:03 | 2020-04-22 03:12 | 75748.1254 | [6 empty] | 75748 | 56744 | 4.41 | 0 | 0 | 6.84 | 5810
TS Fleet 5 | GG\09\025\D | GG | 9 | 25 | D | 1 Prestrip - Thick | 26.8124 | 26.8124 | 26.8124 | 2020-04-20 00:27 | 2020-04-20 16:13 | 29576.7313 | 29577 | [7 empty] | 0 | 0 | 3.7 | 5.97 | 5861.67
TS Fleet 5 | MW\30\010\A | MW | 30 | 10 | A | 1 Prestrip - Thick | 58.7859 | 58.7859 | 58.7859 | 2020-04-20 16:13 | 2020-04-23 05:59 | 115886.4778 | 115886 | [7 empty] | 0 | 0 | 11.57 | 11.43 | 5404.09
TS5500Shv | RS\11\005\B | RS | 11 | 5 | B | 8 Coal Mining | 30.9 | 0 | 30.9 | 2020-04-21 04:22 | 2020-04-21 14:47 | 12691.065 | [6 empty] | 12691 | 9068 | 0.9 | 0 | 0 | 9.45 | 5549
TS5500Shv | GG\10\003\X1 | GG | 10 | 3 | X1 | 1 Prestrip - Thick | 19.5885 | 19.5885 | 19.5885 | 2020-04-21 14:47 | 2020-04-26 22:14 | 135899.1194 | 135899 | [7 empty] | 0 | 0 | 12.73 | 9.52 | 5445.21
TS5500Exc | MW\30\010\A | MW | 30 | 10 | A | 1 Prestrip - Thick | 41.2141 | 41.2141 | 41.2141 | 2020-04-22 03:12 | 2020-04-25 23:04 | 81246.561 | 81247 | [7 empty] | 0 | 0 | 8.11 | 11.43 | 5404.09
TS6060#1 | GG\08\004\D | GG | 8 | 4 | D | 7 PostStrip | 100 | 0 | 2.4406 | 2020-04-22 15:11 | 2020-04-22 17:33 | 2441.8389 |  |  | 2442 | [5 empty] | 0 | 0 | 0 | 6.03 | 5853.93
PH4100A | SC\39\025\D | SC | 39 | 25 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-22 16:18 | 2020-04-26 15:57 | 155900.5666 | 155901 | [7 empty] | 0 | 0 | 13.31 | 7.2 | 5781.22
TS6060#1 | GG\08\004\D | GG | 8 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-04-22 17:33 | 2020-04-26 08:56 | 118253.4899 | [6 empty] | 118253 | 88894 | 4.44 | 0 | 0 | 6.03 | 5854
DRE2 | MW\28\009\D | MW | 28 | 9 | D | 6 DL | 100 | 100 | 100 | 2020-04-22 22:26 | 2020-05-01 06:40 | 673530.3171 |  |  |  | 50346 | 673530 | 463392 |  |  | 0 | 32.1 | 0 | 6 | 5885.72
TS Fleet 5 | MW\30\011\A | MW | 30 | 11 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-23 05:59 | 2020-04-26 13:34 | 149289.5653 | 149290 | [7 empty] | 0 | 0 | 19.55 | 12.21 | 5342.55
DRE1 | SC\38\019\D | SC | 38 | 19 | D | 6 DL | 100 | 0 | 100 | 2020-04-23 17:25 | 2020-05-01 06:12 | 631500.9443 |  |  |  | 48023 | 631501 | 432206 |  |  | 0 | 40 | 0 | 6.75 | 5818.63
PH4100XPC#1 | GG\09\005\X2 | GG | 9 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 55.6926 | 2020-04-23 21:14 | 2020-05-01 02:16 | 408570.2729 | 408570 | [7 empty] | 0 | 0 | 51.88 | 0 | 0
TS5500Exc | SC\38\018\D | SC | 38 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-04-25 23:04 | 2020-04-28 18:42 | 85192.8642 | [6 empty] | 85193 | 63820 | 4.5 | 0 | 0 | 6.76 | 5818
TS6060#1 | MW\30\010\A | MW | 30 | 10 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-04-26 08:56 | 2020-04-27 20:20 | 47918.7296 | [6 empty] | 47919 | 35146 | 3.52 | 0 | 0 | 11.43 | 5404
TS Fleet 5 | MW\31\008\B | MW | 31 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-26 13:34 | 2020-04-27 18:59 | 55187.5179 | 55188 | [7 empty] | 0 | 0 | 5.52 | 10.24 | 5457.64
PH4100A | SC\38\025\D | SC | 38 | 25 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-26 15:57 | 2020-05-02 15:24 | 231872.4904 | 231872 | [7 empty] | 0 | 0 | 18.24 | 6.91 | 5806.24
TS5500Shv | GG\09\004\X1 | GG | 9 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-04-26 22:14 | 2020-04-27 11:19 | 15951.7797 | [6 empty] | 15952 | 11851 | 1.22 | 0 | 0 | 9.99 | 5411
TS5500Shv | MW\28\008\D | MW | 28 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-04-27 11:19 | 2020-04-30 22:58 | 101993.4874 | [6 empty] | 101993 | 76454 | 4.78 | 0 | 0 | 6.54 | 5839
TS Fleet 5 | GG\09\004\X2 | GG | 9 | 4 | X2 | 1 Prestrip - Thick | 45.3511 | 0 | 45.3511 | 2020-04-27 18:59 | 2020-04-28 23:06 | 52753.0872 | 52753 | [7 empty] | 0 | 0 | 5.38 | 0 | 0
TS6060#1 | RS\11\007\A | RS | 11 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-27 20:20 | 2020-05-10 01:36 | 302592.811 | 302593 | [7 empty] | 0 | 0 | 21.89 | 16.82 | 4913.23
TS5500Exc | RS\12\004\A | RS | 12 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-04-28 18:42 | 2020-04-30 11:29 | 51377.7253 | [6 empty] | 51378 | 35994 | 3.6 | 0 | 0 | 13.15 | 5265
TS Fleet 5 | MW\30\010\B | MW | 30 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-28 23:06 | 2020-04-29 13:23 | 26790.0103 | 26790 | [7 empty] | 0 | 0 | 2.68 | 9.05 | 5611.79
TS Fleet 5 | MW\31\009\B | MW | 31 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-29 13:23 | 2020-04-30 07:58 | 34848.3219 | 34848 | [7 empty] | 0 | 0 | 3.51 | 9.76 | 5516.5
TS Fleet 5 | MW\31\010\A | MW | 31 | 10 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-04-30 07:58 | 2020-05-04 17:19 | 197635.0504 | 197635 | [7 empty] | 0 | 0 | 19.65 | 11.57 | 5388.54
TS5500Exc | MW\30\010\B | MW | 30 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-04-30 11:29 | 2020-05-01 18:00 | 38428.6398 | [6 empty] | 38429 | 28474 | 2.85 | 0 | 0 | 9.05 | 5612
TS5500Shv | RS\11\006\A | RS | 11 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-04-30 22:58 | 2020-05-02 17:06 | 51386.4309 | [6 empty] | 51386 | 35408 | 3.54 | 0 | 0 | 14.64 | 5056
PH4100XPC#1 | GG\09\004\X2 | GG | 9 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.6489 | 2020-05-01 02:16 | 2020-05-02 06:21 | 63568.3003 | 63568 | [7 empty] | 0 | 0 | 6.48 | 0 | 0
DRE1 | SC\38\020\D | SC | 38 | 20 | D | 6 DL | 100 | 0 | 100 | 2020-05-01 06:12 | 2020-05-08 20:40 | 637425.5408 |  |  |  | 48473 | 637426 | 436261 |  |  | 0 | 40 | 0 | 7.23 | 5775.15
DRE2 | MW\28\010\D | MW | 28 | 10 | D | 6 DL | 100 | 100 | 100 | 2020-05-01 06:40 | 2020-05-09 06:45 | 646140.2692 |  |  |  | 48299 | 646140 | 444548 |  |  | 0 | 30.82 | 0 | 5.56 | 5923.44
TS5500Exc | SC\38\019\D | SC | 38 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-05-01 18:00 | 2020-05-04 03:18 | 72174.8989 | [6 empty] | 72175 | 54112 | 4.51 | 0 | 0 | 6.75 | 5819
PH4100XPC#1 | GG\09\004\B | GG | 9 | 4 | B | 1 Prestrip - Thick | 100 | 95.4286 | 95.4286 | 2020-05-02 06:21 | 2020-05-04 20:56 | 141631.3155 | 141631 | [7 empty] | 0 | 0 | 14.15 | 10.51 | 5444.87
PH4100A | SC\39\026\D | SC | 39 | 26 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-02 15:24 | 2020-05-08 19:45 | 239608.5278 | 239609 | [7 empty] | 0 | 0 | 18.78 | 6.91 | 5806.8
TS5500Shv | MW\28\009\D | MW | 28 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-05-02 17:06 | 2020-05-06 03:21 | 100294.8363 | [6 empty] | 100295 | 75599 | 4.72 | 0 | 0 | 6 | 5886
TS5500Exc | MW\31\004\B | MW | 31 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-05-04 03:18 | 2020-05-04 20:24 | 21556.5956 | [6 empty] | 21557 | 15972 | 1.59 | 0 | 0 | 8.72 | 5629
TS Fleet 5 | GG\09\004\B | GG | 9 | 4 | B | 1 Prestrip - Thick | 45.3511 | 4.5714 | 4.5714 | 2020-05-04 17:19 | 2020-05-04 20:56 | 6784.7183 | 6785 | [7 empty] | 0 | 0 | 0.68 | 10.51 | 5444.87
TS5500Exc | MW\31\005\B | MW | 31 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-05-04 20:24 | 2020-05-05 12:31 | 20293.3441 | [6 empty] | 20293 | 15018 | 1.49 | 0 | 0 | 8.85 | 5615
TS Fleet 5 | MW\31\011\A | MW | 31 | 11 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-04 20:56 | 2020-05-07 17:34 | 128780.9057 | 128781 | [7 empty] | 0 | 0 | 19.47 | 12.24 | 5335.46
PH4100XPC#1 | GG\09\006\X2 | GG | 9 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 46.381 | 2020-05-04 20:56 | 2020-05-10 05:35 | 298320.6058 | 298321 | [7 empty] | 0 | 0 | 24.93 | 0 | 0
TS5500Exc | MW\30\011\A | MW | 30 | 11 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-05-05 12:31 | 2020-05-06 02:25 | 17512.5572 | [6 empty] | 17513 | 12805 | 1.78 | 0 | 0 | 12.21 | 5343
TS5500Exc | MW\31\008\B | MW | 31 | 8 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-05-06 02:25 | 2020-05-06 18:07 | 19778.9753 | [6 empty] | 19779 | 14508 | 1.46 | 0 | 0 | 10.24 | 5458
TS5500Shv | GG\09\004\B | GG | 9 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-05-06 03:21 | 2020-05-07 22:01 | 52032.9831 | [6 empty] | 52033 | 38068 | 3.8 | 0 | 0 | 10.51 | 5445
TS5500Exc | MW\31\009\B | MW | 31 | 9 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-05-06 18:07 | 2020-05-07 10:03 | 20065.7694 | [6 empty] | 20066 | 14785 | 1.49 | 0 | 0 | 9.76 | 5517
TS5500Exc | MW\31\010\A | MW | 31 | 10 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-05-07 10:03 | 2020-05-08 05:29 | 24468.0321 | [6 empty] | 24468 | 17940 | 1.79 | 0 | 0 | 11.57 | 5389
TS Fleet 5 | MW\32\003\B | MW | 32 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-07 17:34 | 2020-05-08 05:25 | 22201.1229 | 22201 | [7 empty] | 0 | 0 | 2.27 | 8.83 | 5640.6
TS5500Shv | MW\30\011\A | MW | 30 | 11 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-05-07 22:01 | 2020-05-08 11:56 | 16953.6458 | [6 empty] | 16954 | 12397 | 1.72 | 0 | 0 | 12.21 | 5343
TS Fleet 5 | MW\32\004\B | MW | 32 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-08 05:25 | 2020-05-08 22:33 | 32166.6505 | 32167 | [7 empty] | 0 | 0 | 3.2 | 8.67 | 5637.75
TS5500Exc | MW\32\003\B | MW | 32 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-05-08 05:29 | 2020-05-08 20:27 | 18856.0327 | [6 empty] | 18856 | 13958 | 1.4 | 0 | 0 | 8.83 | 5641
TS5500Shv | MW\31\008\B | MW | 31 | 8 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-05-08 11:56 | 2020-05-09 03:38 | 19147.7314 | [6 empty] | 19148 | 14045 | 1.41 | 0 | 0 | 10.24 | 5458
PH4100A | GG\09\006\X2 | GG | 9 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 8.9582 | 2020-05-08 19:45 | 2020-05-10 05:35 | 57618.5525 | 57619 | [7 empty] | 0 | 0 | 4.82 | 0 | 0
TS5500Exc | MW\33\009\A | MW | 33 | 9 | A | 1 Prestrip - Thick | 7.337 | 7.337 | 7.337 | 2020-05-08 20:27 | 2020-05-10 10:56 | 34186.1602 | 34186 | [7 empty] | 0 | 0 | 3.4 | 12.21 | 5316.34
DRE1 | SC\38\021\D | SC | 38 | 21 | D | 6 DL | 100 | 0 | 100 | 2020-05-08 20:40 | 2020-05-16 09:47 | 632637.9829 |  |  |  | 48109 | 632638 | 432984 |  |  | 0 | 40 | 0 | 7.36 | 5764.71
TS Fleet 5 | MW\30\011\B | MW | 30 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-08 22:33 | 2020-05-09 07:58 | 17655.7173 | 17656 | [7 empty] | 0 | 0 | 2.49 | 8.84 | 5633.89
TS5500Shv | MW\31\009\B | MW | 31 | 9 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-05-09 03:38 | 2020-05-09 19:34 | 19425.3725 | [6 empty] | 19425 | 14313 | 1.44 | 0 | 0 | 9.76 | 5517
DRE2 | MW\28\011\D | MW | 28 | 11 | D | 6 DL | 100 | 100 | 100 | 2020-05-09 06:45 | 2020-05-16 12:15 | 583594.7788 |  |  |  | 27159 | 583595 | 265829 |  |  | 0 | 31.54 | 0 | 5.73 | 5908.1
TS Fleet 5 | MW\32\005\B | MW | 32 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-09 07:58 | 2020-05-10 00:06 | 30256.5949 | 30257 | [7 empty] | 0 | 0 | 3.04 | 8.83 | 5608.03
TS5500Shv | MW\28\010\D | MW | 28 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-05-09 19:34 | 2020-05-13 02:07 | 95796.4638 | [6 empty] | 95796 | 72551 | 4.53 | 0 | 0 | 5.56 | 5923
TS Fleet 5 | MW\32\006\B | MW | 32 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-10 00:06 | 2020-05-11 04:44 | 53739.0429 | 53739 | [7 empty] | 0 | 0 | 5.35 | 8.84 | 5611.85
TS6060#1 | RS\11\006\B | RS | 11 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-10 01:36 | 2020-05-11 07:16 | 30599.5565 | 30600 | [7 empty] | 0 | 0 | 3.06 | 9.85 | 5476.69
PH4100A | GG\09\006\B | GG | 9 | 6 | B | 1 Prestrip - Thick | 100 | 42.3325 | 42.3325 | 2020-05-10 05:35 | 2020-05-10 06:07 | 901.2264 | 901 | [7 empty] | 0 | 0 | 0.09 | 11.35 | 5313.3
PH4100XPC#1 | GG\09\006\B | GG | 9 | 6 | B | 1 Prestrip - Thick | 100 | 57.6675 | 57.6675 | 2020-05-10 05:35 | 2020-05-10 06:07 | 1227.6985 | 1228 | [7 empty] | 0 | 0 | 0.12 | 11.35 | 5313.3
PH4100A | GG\09\007\X1 | GG | 9 | 7 | X1 | 1 Prestrip - Thick | 100 | 22.7447 | 22.7447 | 2020-05-10 06:07 | 2020-05-12 17:27 | 98142.7794 | 98143 | [7 empty] | 0 | 0 | 9.56 | 11.07 | 5384.11
PH4100XPC#1 | GG\09\007\X1 | GG | 9 | 7 | X1 | 1 Prestrip - Thick | 100 | 30.871 | 30.871 | 2020-05-10 06:07 | 2020-05-12 17:27 | 133207.4669 | 133207 | [7 empty] | 0 | 0 | 12.97 | 11.07 | 5384.11
TS5500Exc | SC\38\020\D | SC | 38 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-05-10 10:56 | 2020-05-12 17:14 | 68408.5964 | [6 empty] | 68409 | 51286 | 4.27 | 0 | 0 | 7.23 | 5775
TS Fleet 5 | MW\32\007\B | MW | 32 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-11 04:44 | 2020-05-12 20:39 | 74860.5835 | 74861 | [7 empty] | 0 | 0 | 7.46 | 9.49 | 5537.51
TS6060#1 | RS\12\003\B | RS | 12 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-11 07:16 | 2020-05-12 02:54 | 20260.5962 | 20261 | [7 empty] | 0 | 0 | 2.63 | 21.03 | 4647.56
TS6060#1 | RS\12\005\A | RS | 12 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-12 02:54 | 2020-05-20 07:44 | 203087.6927 | 203088 | [7 empty] | 0 | 0 | 20.32 | 14.83 | 5091.67
TS5500Exc | RS\12\003\B | RS | 12 | 3 | B | 8 Coal Mining | 42.6 | 0 | 42.6 | 2020-05-12 17:14 | 2020-05-13 11:12 | 22625.005 | [6 empty] | 22625 | 15211 | 1.78 | 0 | 0 | 21.03 | 4648
PH4100XPC#1 | GG\09\008\X1 | GG | 9 | 8 | X1 | 1 Prestrip - Thick | 100 | 38.7775 | 38.7775 | 2020-05-12 17:27 | 2020-05-15 09:26 | 142926.5384 | 142927 | [7 empty] | 0 | 0 | 14.12 | 11.4 | 5385.08
PH4100A | GG\09\008\X1 | GG | 9 | 8 | X1 | 1 Prestrip - Thick | 100 | 28.6195 | 28.6195 | 2020-05-12 17:27 | 2020-05-15 09:26 | 105485.9988 | 105486 | [7 empty] | 0 | 0 | 10.42 | 11.4 | 5385.08
TS Fleet 5 | MW\32\008\B | MW | 32 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-12 20:39 | 2020-05-14 01:23 | 53920.7705 | 53921 | [7 empty] | 0 | 0 | 5.39 | 10.11 | 5465.62
TS5500Shv | GG\09\007\X1 | GG | 9 | 7 | X1 | 8 Coal Mining | 8 | 0 | 8 | 2020-05-13 02:07 | 2020-05-13 03:14 | 1352.9076 | [6 empty] | 1353 | 998 | 0.1 | 0 | 0 | 11.07 | 5384
TS5500Shv | RS\11\007\A | RS | 11 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-05-13 03:14 | 2020-05-15 12:14 | 69504.1021 | [6 empty] | 69504 | 47644 | 3.48 | 0 | 0 | 16.82 | 4913
TS5500Exc | MW\30\011\B | MW | 30 | 11 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-05-13 11:12 | 2020-05-13 21:47 | 13334.8909 | [6 empty] | 13335 | 9915 | 1.42 | 0 | 0 | 8.84 | 5634
TS5500Exc | MW\32\004\B | MW | 32 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-05-13 21:47 | 2020-05-14 15:20 | 22114.4776 | [6 empty] | 22114 | 16376 | 1.63 | 0 | 0 | 8.67 | 5638
TS Fleet 5 | MW\32\009\B | MW | 32 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-14 01:23 | 2020-05-14 19:33 | 34068.7229 | 34069 | [7 empty] | 0 | 0 | 3.41 | 9.68 | 5518.64
TS5500Exc | MW\32\005\B | MW | 32 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-05-14 15:20 | 2020-05-15 07:11 | 19956.9298 | [6 empty] | 19957 | 14767 | 1.46 | 0 | 0 | 8.83 | 5608
TS Fleet 5 | MW\32\010\A | MW | 32 | 10 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-14 19:33 | 2020-05-21 12:30 | 301957.0938 | 301957 | [7 empty] | 0 | 0 | 19.49 | 11.67 | 5376.32
TS5500Exc | MW\32\006\B | MW | 32 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-05-15 07:11 | 2020-05-15 23:50 | 20961.9865 | [6 empty] | 20962 | 15506 | 1.54 | 0 | 0 | 8.84 | 5612
PH4100A | GG\09\009\X1 | GG | 9 | 9 | X1 | 1 Prestrip - Thick | 100 | 28.6515 | 28.6515 | 2020-05-15 09:26 | 2020-05-17 21:24 | 99316.1459 | 99316 | [7 empty] | 0 | 0 | 9.74 | 11.41 | 5382.6
PH4100XPC#1 | GG\09\009\X1 | GG | 9 | 9 | X1 | 1 Prestrip - Thick | 100 | 38.8474 | 38.8474 | 2020-05-15 09:26 | 2020-05-17 21:24 | 134659.0623 | 134659 | [7 empty] | 0 | 0 | 13.21 | 11.41 | 5382.6
TS5500Shv | GG\09\008\X1 | GG | 9 | 8 | X1 | 8 Coal Mining | 20 | 0 | 20 | 2020-05-15 12:14 | 2020-05-15 14:09 | 2351.9223 | [6 empty] | 2352 | 1734 | 0.17 | 0 | 0 | 11.4 | 5385
TS5500Shv | RS\11\006\B | RS | 11 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-05-15 14:09 | 2020-05-16 23:37 | 40810.4123 | [6 empty] | 40810 | 28914 | 2.89 | 0 | 0 | 9.85 | 5477
TS5500Exc | MW\32\007\B | MW | 32 | 7 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-05-15 23:50 | 2020-05-16 16:14 | 20667.5407 | [6 empty] | 20668 | 15231 | 1.52 | 0 | 0 | 9.49 | 5538
DRE1 | SC\38\022\D | SC | 38 | 22 | D | 6 DL | 100 | 0 | 100 | 2020-05-16 09:47 | 2020-05-23 13:13 | 598819.2359 |  |  |  | 42587 | 598819 | 430601 |  |  | 0 | 39.63 | 0 | 7.27 | 5773.6
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 4d 00:00 |  | 4d 00:00 | 2020-05-16 12:15 | 2020-05-20 12:15
TS5500Exc | SC\38\021\D | SC | 38 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-05-16 16:14 | 2020-05-18 23:48 | 69996.5636 | [6 empty] | 69997 | 52393 | 4.37 | 0 | 0 | 7.36 | 5765
TS5500Shv | RS\12\003\B | RS | 12 | 3 | B | 8 Coal Mining | 57.4 | 0 | 57.4 | 2020-05-16 23:37 | 2020-05-18 00:40 | 30535.505 | [6 empty] | 30536 | 20529 | 2.4 | 0 | 0 | 21.03 | 4648
PH4100XPC#1 | GG\09\010\B | GG | 9 | 10 | B | 1 Prestrip - Thick | 100 | 39.1018 | 39.1018 | 2020-05-17 21:24 | 2020-05-21 15:00 | 204572.5591 | 204573 | [7 empty] | 0 | 0 | 21.66 | 10.55 | 5461.04
PH4100A | GG\09\010\B | GG | 9 | 10 | B | 1 Prestrip - Thick | 100 | 28.7307 | 28.7307 | 2020-05-17 21:24 | 2020-05-21 15:00 | 150312.9632 | 150313 | [7 empty] | 0 | 0 | 15.92 | 10.55 | 5461.04
TS5500Shv | GG\09\009\X1 | GG | 9 | 9 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-05-18 00:40 | 2020-05-18 12:48 | 14805.8267 | [6 empty] | 14806 | 10894 | 1.08 | 0 | 0 | 11.41 | 5383
TS5500Shv | GG\09\009\B | GG | 9 | 9 | B | 1 Prestrip - Thick | 53.6124 | 53.6124 | 53.6124 | 2020-05-18 12:48 | 2020-05-22 04:28 | 93976.6616 | 93977 | [7 empty] | 0 | 0 | 9.34 | 10.71 | 5443.73
TS5500Exc | MW\32\008\B | MW | 32 | 8 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-05-18 23:48 | 2020-05-19 15:28 | 19737.4775 | [6 empty] | 19737 | 14498 | 1.45 | 0 | 0 | 10.11 | 5466
TS5500Exc | MW\32\009\B | MW | 32 | 9 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-05-19 15:28 | 2020-05-20 07:27 | 20125.9208 | [6 empty] | 20126 | 14840 | 1.49 | 0 | 0 | 9.68 | 5519
TS5500Exc | MW\33\010\X | MW | 33 | 10 | X | 1 Prestrip - Thick | 15.8322 | 15.8322 | 15.8322 | 2020-05-20 07:27 | 2020-05-24 15:08 | 92116.8159 | 92117 | [7 empty] | 0 | 0 | 5.94 | 12.21 | 5215.7
TS6060#1 | GG\09\007\X1 | GG | 9 | 7 | X1 | 8 Coal Mining | 92 | 0 | 92 | 2020-05-20 07:44 | 2020-05-20 19:17 | 15645.8496 | [6 empty] | 15646 | 11541 | 1.13 | 0 | 0 | 11.07 | 5384
DRE2 | MW\29\001\D | MW | 29 | 1 | D | 6 DL | 100 | 0 | 100 | 2020-05-20 12:15 | 2020-05-26 18:21 | 504926.5885 |  |  |  | 35909 | 504927 | 363084 |  |  | 0 | 35 | 0 | 7.35 | 5766.84
TS6060#1 | GG\09\008\X1 | GG | 9 | 8 | X1 | 8 Coal Mining | 80 | 0 | 80 | 2020-05-20 19:17 | 2020-05-21 02:15 | 9432.0132 | [6 empty] | 9432 | 6955 | 0.7 | 0 | 0 | 11.4 | 5385
TS6060#1 | MW\28\011\D | MW | 28 | 11 | D | 7 PostStrip | 48.0635 | 0 | 48.0635 | 2020-05-21 02:15 | 2020-05-22 03:58 | 26531.4005 |  |  | 26531 | [5 empty] | 0 | 0 | 0 | 5.73 | 5908.1
TS Fleet 5 | GG\09\007\X2 | GG | 9 | 7 | X2 | 1 Prestrip - Thick | 32.3667 | 0 | 32.3667 | 2020-05-21 12:30 | 2020-05-22 05:38 | 32137.6434 | 32138 | [7 empty] | 0 | 0 | 3.16 | 0 | 0
PH4100A | GG\09\007\X2 | GG | 9 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 28.6308 | 2020-05-21 15:00 | 2020-05-22 08:06 | 28428.1694 | 28428 | [7 empty] | 0 | 0 | 2.8 | 0 | 0
PH4100XPC#1 | GG\09\007\X2 | GG | 9 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 39.0024 | 2020-05-21 15:00 | 2020-05-22 08:06 | 38726.3662 | 38726 | [7 empty] | 0 | 0 | 3.81 | 0 | 0
TS6060#1 | RS\11\007\B | RS | 11 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-22 03:58 | 2020-05-23 14:33 | 35678.4073 | 35678 | [7 empty] | 0 | 0 | 2.61 | 10.16 | 5486.23
TS5500Shv | MW\28\011\D | MW | 28 | 11 | D | 7 PostStrip | 51.9365 | 0 | 51.9365 | 2020-05-22 04:28 | 2020-05-23 07:13 | 28669.2718 |  |  | 28669 | [5 empty] | 0 | 0 | 0 | 5.73 | 5908.1
TS Fleet 5 | GG\09\009\B | GG | 9 | 9 | B | 1 Prestrip - Thick | 15.9806 | 15.9806 | 15.9806 | 2020-05-22 05:38 | 2020-05-22 20:34 | 28012.2094 | 28012 | [7 empty] | 0 | 0 | 2.78 | 10.71 | 5443.73
PH4100XPC#1 | GG\09\007\B | GG | 9 | 7 | B | 1 Prestrip - Thick | 100 | 57.6675 | 57.6675 | 2020-05-22 08:06 | 2020-05-22 17:16 | 20743.2598 | 20743 | [7 empty] | 0 | 0 | 2.03 | 10.8 | 5395.5
PH4100A | GG\09\007\B | GG | 9 | 7 | B | 1 Prestrip - Thick | 100 | 42.3325 | 42.3325 | 2020-05-22 08:06 | 2020-05-22 17:16 | 15227.1686 | 15227 | [7 empty] | 0 | 0 | 1.49 | 10.8 | 5395.5
PH4100A | GG\09\008\X2 | GG | 9 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 30.4774 | 2020-05-22 17:16 | 2020-05-23 10:59 | 29440.601 | 29441 | [7 empty] | 0 | 0 | 2.97 | 0 | 0
PH4100XPC#1 | GG\09\008\X2 | GG | 9 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 41.5179 | 2020-05-22 17:16 | 2020-05-23 10:59 | 40105.5545 | 40106 | [7 empty] | 0 | 0 | 4.05 | 0 | 0
TS Fleet 5 | GG\09\008\X2 | GG | 9 | 8 | X2 | 1 Prestrip - Thick | 32.3667 | 0 | 28.0048 | 2020-05-22 20:34 | 2020-05-23 10:59 | 27052.1345 | 27052 | [7 empty] | 0 | 0 | 2.73 | 0 | 0
TS5500Shv | MW\28\011\D | MW | 28 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-05-23 07:13 | 2020-05-25 10:43 | 62801.0709 | [6 empty] | 62801 | 47598 | 4.43 | 0 | 0 | 5.73 | 5908
TS Fleet 5 | GG\09\008\B | GG | 9 | 8 | B | 1 Prestrip - Thick | 32.3667 | 32.3386 | 32.3386 | 2020-05-23 10:59 | 2020-05-23 22:15 | 21118.0786 | 21118 | [7 empty] | 0 | 0 | 2.14 | 10.72 | 5439.13
PH4100A | GG\09\008\B | GG | 9 | 8 | B | 1 Prestrip - Thick | 100 | 28.6427 | 28.6427 | 2020-05-23 10:59 | 2020-05-23 22:15 | 18704.5839 | 18705 | [7 empty] | 0 | 0 | 1.89 | 10.72 | 5439.13
PH4100XPC#1 | GG\09\008\B | GG | 9 | 8 | B | 1 Prestrip - Thick | 100 | 39.0187 | 39.0187 | 2020-05-23 10:59 | 2020-05-23 22:15 | 25480.3802 | 25480 | [7 empty] | 0 | 0 | 2.58 | 10.72 | 5439.13
DRE1 | SC\38\023\D | SC | 38 | 23 | D | 6 DL | 100 | 0 | 100 | 2020-05-23 13:13 | 2020-05-30 13:09 | 586634.5572 |  |  |  | 41720 | 586635 | 421839 |  |  | 0 | 38.75 | 0 | 7.18 | 5782.33
TS6060#1 | RS\12\004\B | RS | 12 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-23 14:33 | 2020-05-25 02:35 | 37173.6443 | 37174 | [7 empty] | 0 | 0 | 3.71 | 19.49 | 4772.36
TS Fleet 5 | MW\33\002\D | MW | 33 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-23 22:15 | 2020-05-27 04:01 | 145894.7745 | 145895 | [7 empty] | 0 | 0 | 12.71 | 7.67 | 5740.06
PH4100A | GG\09\009\B | GG | 9 | 9 | B | 1 Prestrip - Thick | 100 | 12.872 | 12.872 | 2020-05-23 22:15 | 2020-05-24 11:49 | 22563.2122 | 22563 | [7 empty] | 0 | 0 | 2.24 | 10.71 | 5443.73
PH4100XPC#1 | GG\09\009\B | GG | 9 | 9 | B | 1 Prestrip - Thick | 100 | 17.5349 | 17.5349 | 2020-05-23 22:15 | 2020-05-24 11:49 | 30736.8091 | 30737 | [7 empty] | 0 | 0 | 3.06 | 10.71 | 5443.73
PH4100A | GG\09\011\X1 | GG | 9 | 11 | X1 | 1 Prestrip - Thick | 100 | 24.2548 | 24.2548 | 2020-05-24 11:49 | 2020-05-26 07:19 | 72765.9907 | 72766 | [7 empty] | 0 | 0 | 7.7 | 12.68 | 5289.17
PH4100XPC#1 | GG\09\011\X1 | GG | 9 | 11 | X1 | 1 Prestrip - Thick | 100 | 32.9911 | 32.9911 | 2020-05-24 11:49 | 2020-05-26 07:19 | 98975.4246 | 98975 | [7 empty] | 0 | 0 | 10.47 | 12.68 | 5289.17
TS5500Exc | RS\11\007\B | RS | 11 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-05-24 15:08 | 2020-05-26 09:02 | 52770.4581 | [6 empty] | 52770 | 37270 | 2.73 | 0 | 0 | 10.16 | 5486
TS6060#1 | RS\12\006\A | RS | 12 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-25 02:35 | 2020-06-02 07:21 | 203036.3377 | 203036 | [7 empty] | 0 | 0 | 20.33 | 15.3 | 5011.18
TS5500Shv | MW\30\011\B | MW | 30 | 11 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-05-25 10:43 | 2020-05-25 21:18 | 12909.3093 | [6 empty] | 12909 | 9599 | 1.37 | 0 | 0 | 8.84 | 5634
TS5500Shv | MW\31\010\A | MW | 31 | 10 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-05-25 21:18 | 2020-05-26 16:44 | 23687.1374 | [6 empty] | 23687 | 17367 | 1.73 | 0 | 0 | 11.57 | 5389
PH4100A | GG\09\012\X2 | GG | 9 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 28.8413 | 2020-05-26 07:19 | 2020-05-29 00:51 | 111363.9563 | 111364 | [7 empty] | 0 | 0 | 12.13 | 0 | 0
PH4100XPC#1 | GG\09\012\X2 | GG | 9 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 39.2829 | 2020-05-26 07:19 | 2020-05-29 00:51 | 151681.4753 | 151681 | [7 empty] | 0 | 0 | 16.52 | 0 | 0
TS5500Exc | SC\38\022\D | SC | 38 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-05-26 09:02 | 2020-05-28 19:42 | 73902.4616 | [6 empty] | 73902 | 55232 | 4.6 | 0 | 0 | 7.27 | 5774
TS5500Shv | MW\31\011\A | MW | 31 | 11 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-05-26 16:44 | 2020-05-27 16:55 | 29496.3152 | [6 empty] | 29496 | 21567 | 3.5 | 0 | 0 | 12.24 | 5335
DRE2 | MW\29\002\D | MW | 29 | 2 | D | 6 DL | 100 | 0 | 100 | 2020-05-26 18:21 | 2020-06-01 05:45 | 441983.7871 |  |  |  | 31433 | 441984 | 317823 |  |  | 0 | 35 | 0 | 7.14 | 5785.41
TS Fleet 5 | MW\31\010\B | MW | 31 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-27 04:01 | 2020-05-27 17:54 | 26042.0426 | 26042 | [7 empty] | 0 | 0 | 2.6 | 9.07 | 5602.97
TS5500Shv | MW\32\003\B | MW | 32 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-05-27 16:55 | 2020-05-28 07:53 | 18254.2444 | [6 empty] | 18254 | 13513 | 1.36 | 0 | 0 | 8.83 | 5641
TS Fleet 5 | MW\31\011\B | MW | 31 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-27 17:54 | 2020-05-28 01:55 | 15041.6911 | 15042 | [7 empty] | 0 | 0 | 2.5 | 8.86 | 5625.68
TS Fleet 5 | MW\33\003\A | MW | 33 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-05-28 01:55 | 2020-06-04 18:49 | 346874.1074 | 346874 | [7 empty] | 0 | 0 | 34.65 | 11.58 | 5336.68
TS5500Shv | MW\31\010\B | MW | 31 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-05-28 07:53 | 2020-05-29 15:28 | 38514.2392 | [6 empty] | 38514 | 28559 | 2.86 | 0 | 0 | 9.07 | 5603
TS5500Exc | MW\29\001\D | MW | 29 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-05-28 19:42 | 2020-05-31 03:40 | 70502.0544 | [6 empty] | 70502 | 52511 | 4.66 | 0 | 0 | 7.35 | 5767
PH4100A | GG\09\012\B | GG | 9 | 12 | B | 1 Prestrip - Thick | 100 | 42.3325 | 42.3325 | 2020-05-29 00:51 | 2020-05-30 03:53 | 44926.9718 | 44927 | [7 empty] | 0 | 0 | 4.5 | 10.09 | 5517.08
PH4100XPC#1 | GG\09\012\B | GG | 9 | 12 | B | 1 Prestrip - Thick | 100 | 57.6675 | 57.6675 | 2020-05-29 00:51 | 2020-05-30 03:53 | 61201.9134 | 61202 | [7 empty] | 0 | 0 | 6.14 | 10.09 | 5517.08
TS5500Shv | MW\31\011\B | MW | 31 | 11 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-05-29 15:28 | 2020-05-30 00:31 | 11024.7746 | [6 empty] | 11025 | 8192 | 1.38 | 0 | 0 | 8.86 | 5626
TS5500Shv | MW\32\004\B | MW | 32 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-05-30 00:31 | 2020-05-30 18:04 | 21408.6964 | [6 empty] | 21409 | 15853 | 1.58 | 0 | 0 | 8.67 | 5638
PH4100A | GG\09\013\X2 | GG | 9 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 25.2966 | 2020-05-30 03:53 | 2020-05-31 08:04 | 46777.2646 | 46777 | [7 empty] | 0 | 0 | 8.85 | 0 | 0
PH4100XPC#1 | GG\09\013\X2 | GG | 9 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 34.4287 | 2020-05-30 03:53 | 2020-05-31 08:04 | 63663.9306 | 63664 | [7 empty] | 0 | 0 | 12.05 | 0 | 0
DRE1 | SC\38\024\D | SC | 38 | 24 | D | 6 DL | 100 | 0 | 100 | 2020-05-30 13:09 | 2020-06-05 15:32 | 511303.3641 |  |  |  | 29182 | 511303 | 387698 |  |  | 0 | 34.71 | 0 | 7.18 | 5782.48
TS5500Shv | MW\32\005\B | MW | 32 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-05-30 18:04 | 2020-05-31 09:55 | 19320.0065 | [6 empty] | 19320 | 14296 | 1.42 | 0 | 0 | 8.83 | 5608
TS5500Exc | SC\38\023\D | SC | 38 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-05-31 03:40 | 2020-06-02 15:56 | 75903.9005 | [6 empty] | 75904 | 56594 | 4.71 | 0 | 0 | 7.18 | 5782
PH4100A | GG\09\013\B | GG | 9 | 13 | B | 1 Prestrip - Thick | 100 | 35.7322 | 35.7322 | 2020-05-31 08:04 | 2020-05-31 21:46 | 22765.8311 | 22766 | [7 empty] | 0 | 0 | 4.74 | 10.69 | 5467.67
PH4100XPC#1 | GG\09\013\B | GG | 9 | 13 | B | 1 Prestrip - Thick | 100 | 48.6763 | 48.6763 | 2020-05-31 08:04 | 2020-05-31 21:46 | 31012.8274 | 31013 | [7 empty] | 0 | 0 | 6.46 | 10.69 | 5467.67
TS5500Shv | GG\09\013\B | GG | 9 | 13 | B | 1 Prestrip - Thick | 15.5915 | 15.5915 | 15.5915 | 2020-05-31 09:55 | 2020-05-31 19:11 | 9933.7247 | 9934 | [7 empty] | 0 | 0 | 2.07 | 10.69 | 5467.67
TS5500Shv | MW\32\006\B | MW | 32 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-05-31 19:11 | 2020-06-01 11:49 | 20292.987 | [6 empty] | 20293 | 15011 | 1.5 | 0 | 0 | 8.84 | 5612
PH4100XPC#1 | GG\09\018\X2 | GG | 9 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 32.891 | 2020-05-31 21:46 | 2020-06-02 01:15 | 62047.3395 | 62047 | [7 empty] | 0 | 0 | 11.36 | 0 | 0
PH4100A | GG\09\018\X2 | GG | 9 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 24.1666 | 2020-05-31 21:46 | 2020-06-02 01:15 | 45589.1389 | 45589 | [7 empty] | 0 | 0 | 8.35 | 0 | 0
DRE2 | MW\29\003\D | MW | 29 | 3 | D | 6 DL | 100 | 100 | 100 | 2020-06-01 05:45 | 2020-06-05 02:39 | 312519.717 |  |  |  | 16068 | 312520 | 251730 |  |  | 0 | 26.81 | 0 | 6.73 | 5821.47
TS5500Shv | MW\29\002\D | MW | 29 | 2 | D | 8 Coal Mining | 48.8 | 0 | 48.8 | 2020-06-01 11:49 | 2020-06-02 12:59 | 30680.9118 | [6 empty] | 30681 | 22906 | 2.29 | 0 | 0 | 7.14 | 5785
PH4100A | GG\09\018\B | GG | 9 | 18 | B | 1 Prestrip - Thick | 100 | 39.6225 | 39.6225 | 2020-06-02 01:15 | 2020-06-02 16:54 | 26027.3259 | 26027 | [7 empty] | 0 | 0 | 5.21 | 11.11 | 5433.13
PH4100XPC#1 | GG\09\018\B | GG | 9 | 18 | B | 1 Prestrip - Thick | 100 | 53.9759 | 53.9759 | 2020-06-02 01:15 | 2020-06-02 16:54 | 35455.8093 | 35456 | [7 empty] | 0 | 0 | 7.1 | 11.11 | 5433.13
TS6060#1 | GG\09\011\X1 | GG | 9 | 11 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-06-02 07:21 | 2020-06-02 15:50 | 11477.1275 | [6 empty] | 11477 | 8368 | 0.87 | 0 | 0 | 12.68 | 5289
TS5500Shv | GG\09\018\B | GG | 9 | 18 | B | 1 Prestrip - Thick | 15.5915 | 6.4016 | 6.4016 | 2020-06-02 12:59 | 2020-06-02 16:54 | 4205.1026 | 4205 | [7 empty] | 0 | 0 | 0.84 | 11.11 | 5433.13
TS6060#1 | RS\12\007\A | RS | 12 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-02 15:50 | 2020-06-13 17:56 | 274567.6778 | 274568 | [7 empty] | 0 | 0 | 21.44 | 16.89 | 4902.71
TS5500Exc | MW\29\002\D | MW | 29 | 2 | D | 8 Coal Mining | 51.2 | 0 | 51.2 | 2020-06-02 15:56 | 2020-06-03 17:32 | 32239.684 | [6 empty] | 32240 | 24070 | 2.41 | 0 | 0 | 7.14 | 5785
TS5500Shv | MW\32\007\B | MW | 32 | 7 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-02 16:54 | 2020-06-03 09:19 | 20007.9383 | [6 empty] | 20008 | 14745 | 1.47 | 0 | 0 | 9.49 | 5538
PH4100A | GG\09\011\X2 | GG | 9 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 42.3325 | 2020-06-02 16:54 | 2020-06-03 15:48 | 38049.1524 | 38049 | [7 empty] | 0 | 0 | 3.83 | 0 | 0
PH4100XPC#1 | GG\09\011\X2 | GG | 9 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 57.6675 | 2020-06-02 16:54 | 2020-06-03 15:48 | 51832.5816 | 51833 | [7 empty] | 0 | 0 | 5.21 | 0 | 0
TS5500Shv | MW\32\008\B | MW | 32 | 8 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-03 09:19 | 2020-06-04 00:59 | 19107.558 | [6 empty] | 19108 | 14035 | 1.4 | 0 | 0 | 10.11 | 5466
PH4100A | GG\09\011\B | GG | 9 | 11 | B | 1 Prestrip - Thick | 100 | 42.2338 | 42.2338 | 2020-06-03 15:48 | 2020-06-04 18:57 | 45099.6354 | 45100 | [7 empty] | 0 | 0 | 4.52 | 10.09 | 5509.83
PH4100XPC#1 | GG\09\011\B | GG | 9 | 11 | B | 1 Prestrip - Thick | 100 | 57.5331 | 57.5331 | 2020-06-03 15:48 | 2020-06-04 18:57 | 61437.1248 | 61437 | [7 empty] | 0 | 0 | 6.16 | 10.09 | 5509.83
TS5500Exc | RS\12\004\B | RS | 12 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-06-03 17:32 | 2020-06-05 18:30 | 61685.4492 | [6 empty] | 61685 | 41906 | 4.18 | 0 | 0 | 19.49 | 4772
TS5500Shv | MW\32\009\B | MW | 32 | 9 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-04 00:59 | 2020-06-04 16:58 | 19483.6042 | [6 empty] | 19484 | 14366 | 1.44 | 0 | 0 | 9.68 | 5519
TS5500Shv | RS\12\005\A | RS | 12 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-04 16:58 | 2020-06-05 13:47 | 25392.9908 | [6 empty] | 25393 | 17547 | 1.75 | 0 | 0 | 14.83 | 5092
TS Fleet 5 | GG\09\011\B | GG | 9 | 11 | B | 1 Prestrip - Thick | 32.3667 | 0.23312 | 0.23312 | 2020-06-04 18:49 | 2020-06-04 18:57 | 248.9443 | 249 | [7 empty] | 0 | 0 | 0.02 | 10.09 | 5509.83
PH4100A | GG\09\019\B | GG | 9 | 19 | B | 1 Prestrip - Thick | 100 | 28.8609 | 28.8609 | 2020-06-04 18:57 | 2020-06-07 10:19 | 108019.1213 | 108019 | [7 empty] | 0 | 0 | 10.74 | 11.67 | 5390.36
PH4100XPC#1 | GG\09\019\B | GG | 9 | 19 | B | 1 Prestrip - Thick | 100 | 39.3376 | 39.3376 | 2020-06-04 18:57 | 2020-06-07 10:19 | 147230.7531 | 147231 | [7 empty] | 0 | 0 | 14.64 | 11.67 | 5390.36
TS Fleet 5 | MW\33\004\A | MW | 33 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-04 18:57 | 2020-06-08 01:58 | 148233.5125 | 148234 | [7 empty] | 0 | 0 | 15.72 | 10.33 | 5424.66
DRE2 | MW\29\004\D | MW | 29 | 4 | D | 6 DL | 100 | 100 | 100 | 2020-06-05 02:39 | 2020-06-09 00:52 | 316868.5859 |  |  |  | 16291 | 316869 | 255233 |  |  | 0 | 27.09 | 0 | 6.3 | 5858.89
TS5500Shv | MW\29\003\D | MW | 29 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-05 13:47 | 2020-06-06 14:45 | 30431.3344 | [6 empty] | 30431 | 22919 | 2.29 | 0 | 0 | 6.73 | 5821
DRE1 | SC\38\025\D | SC | 38 | 25 | D | 6 DL | 100 | 0 | 100 | 2020-06-05 15:32 | 2020-06-11 22:12 | 526338.3902 |  |  |  | 21774 | 526338 | 278839 |  |  | 0 | 28.11 | 0 | 6.91 | 5806.24
TS5500Exc | MW\29\003\D | MW | 29 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-06-05 18:30 | 2020-06-06 19:27 | 31434.5652 | [6 empty] | 31435 | 23675 | 2.37 | 0 | 0 | 6.73 | 5821
TS5500Shv | RS\12\006\A | RS | 12 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-06 14:45 | 2020-06-07 11:29 | 25300.2051 | [6 empty] | 25300 | 17367 | 1.74 | 0 | 0 | 15.3 | 5011
TS5500Exc | SC\38\024\D | SC | 38 | 24 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-06-06 19:27 | 2020-06-09 08:42 | 77146.468 | [6 empty] | 77146 | 57522 | 4.79 | 0 | 0 | 7.18 | 5782
PH4100A | GG\09\020\B | GG | 9 | 20 | B | 1 Prestrip - Thick | 100 | 25.5412 | 25.5412 | 2020-06-07 10:19 | 2020-06-10 02:32 | 109078.8673 | 109079 | [7 empty] | 0 | 0 | 11.62 | 12.44 | 5334.28
PH4100XPC#1 | GG\09\020\B | GG | 9 | 20 | B | 1 Prestrip - Thick | 100 | 34.8093 | 34.8093 | 2020-06-07 10:19 | 2020-06-10 02:32 | 148660.2169 | 148660 | [7 empty] | 0 | 0 | 15.83 | 12.44 | 5334.28
TS5500Shv | MW\32\010\A | MW | 32 | 10 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-07 11:29 | 2020-06-08 16:27 | 35307.6756 | [6 empty] | 35308 | 25898 | 1.72 | 0 | 0 | 11.67 | 5376
TS Fleet 5 | MW\33\005\B | MW | 33 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-08 01:58 | 2020-06-12 01:44 | 179675.8403 | 179676 | [7 empty] | 0 | 0 | 19.66 | 8.99 | 5587.83
TS5500Shv | MW\33\003\A | MW | 33 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-08 16:27 | 2020-06-09 00:59 | 10406.3891 | [6 empty] | 10406 | 7578 | 0.76 | 0 | 0 | 11.58 | 5337
DRE2 | MW\29\005\D | MW | 29 | 5 | D | 6 DL | 100 | 100 | 100 | 2020-06-09 00:52 | 2020-06-13 00:11 | 320642.4062 |  |  |  | 16485 | 320642 | 258272 |  |  | 0 | 27.39 | 0 | 6.03 | 5881.53
TS5500Shv | MW\29\004\D | MW | 29 | 4 | D | 8 Coal Mining | 42.7 | 0 | 42.7 | 2020-06-09 00:59 | 2020-06-09 21:57 | 25573.6203 | [6 empty] | 25574 | 19352 | 1.94 | 0 | 0 | 6.3 | 5859
TS5500Exc | MW\29\004\D | MW | 29 | 4 | D | 8 Coal Mining | 57.3 | 0 | 57.3 | 2020-06-09 08:42 | 2020-06-10 11:57 | 34317.0887 | [6 empty] | 34317 | 25969 | 2.6 | 0 | 0 | 6.3 | 5859
TS5500Shv | MW\33\004\A | MW | 33 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-09 21:57 | 2020-06-10 14:47 | 20524.9362 | [6 empty] | 20525 | 15056 | 1.51 | 0 | 0 | 10.33 | 5425
PH4100A | GG\09\021\B | GG | 9 | 21 | B | 1 Prestrip - Thick | 100 | 28.6383 | 28.6383 | 2020-06-10 02:32 | 2020-06-12 11:50 | 95242.8354 | 95243 | [7 empty] | 0 | 0 | 9.78 | 13.23 | 5271.29
PH4100XPC#1 | GG\09\021\B | GG | 9 | 21 | B | 1 Prestrip - Thick | 100 | 38.9976 | 38.9976 | 2020-06-10 02:32 | 2020-06-12 11:50 | 129695.1583 | 129695 | [7 empty] | 0 | 0 | 13.32 | 13.23 | 5271.29
TS5500Exc | MW\31\011\B | MW | 31 | 11 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-06-10 11:57 | 2020-06-10 20:59 | 11388.2287 | [6 empty] | 11388 | 8462 | 1.43 | 0 | 0 | 8.86 | 5626
TS5500Shv | GG\10\011\X2 | GG | 10 | 11 | X2 | 1 Prestrip - Thick | 4.3183 | 0 | 4.3183 | 2020-06-10 14:47 | 2020-06-11 07:29 | 17911.2889 | 17911 | [7 empty] | 0 | 0 | 2.13 | 0 | 0
TS5500Exc | RS\12\005\A | RS | 12 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-06-10 20:59 | 2020-06-11 17:49 | 26230.1224 | [6 empty] | 26230 | 18126 | 1.81 | 0 | 0 | 14.83 | 5092
TS5500Shv | GG\10\013\X2 | GG | 10 | 13 | X2 | 1 Prestrip - Thick | 32.1434 | 0 | 32.1434 | 2020-06-11 07:29 | 2020-06-13 23:55 | 68901.1364 | 68901 | [7 empty] | 0 | 0 | 11.07 | 0 | 0
TS5500Exc | RS\12\006\A | RS | 12 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-06-11 17:49 | 2020-06-12 14:34 | 26134.2778 | [6 empty] | 26134 | 17940 | 1.79 | 0 | 0 | 15.3 | 5011
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 7d 00:00 |  | 7d 00:00 | 2020-06-11 22:12 | 2020-06-18 22:12
TS Fleet 5 | MW\33\006\A | MW | 33 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-12 01:44 | 2020-06-17 02:15 | 226089.8272 | 226090 | [7 empty] | 0 | 0 | 22.88 | 10.45 | 5429.1
PH4100A | GG\09\022\X2 | GG | 9 | 22 | X2 | 1 Prestrip - Thick | 100 | 0 | 28.8527 | 2020-06-12 11:50 | 2020-06-14 02:39 | 65935.0077 | 65935 | [7 empty] | 0 | 0 | 6.87 | 0 | 0
PH4100XPC#1 | GG\09\022\X2 | GG | 9 | 22 | X2 | 1 Prestrip - Thick | 100 | 0 | 39.241 | 2020-06-12 11:50 | 2020-06-14 02:39 | 89674.6223 | 89675 | [7 empty] | 0 | 0 | 9.34 | 0 | 0
TS5500Exc | MW\32\010\A | MW | 32 | 10 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-06-12 14:34 | 2020-06-13 19:31 | 36471.6649 | [6 empty] | 36472 | 26752 | 1.78 | 0 | 0 | 11.67 | 5376
DRE2 | MW\29\006\D | MW | 29 | 6 | D | 6 DL | 100 | 100 | 100 | 2020-06-13 00:11 | 2020-06-17 04:19 | 336852.71 |  |  |  | 17319 | 336853 | 271330 |  |  | 0 | 28.89 | 0 | 6.13 | 5872.92
TS6060#1 | RS\13\003\B | RS | 13 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-13 17:56 | 2020-06-14 12:45 | 19400.9028 | 19401 | [7 empty] | 0 | 0 | 2.49 | 8.63 | 5653.5
TS5500Exc | RS\12\007\A | RS | 12 | 7 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-06-13 19:31 | 2020-06-14 21:29 | 32713.978 | [6 empty] | 32714 | 22401 | 1.77 | 0 | 0 | 16.89 | 4903
TS5500Shv | MW\29\005\D | MW | 29 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-06-13 23:55 | 2020-06-15 23:38 | 58187.2519 | [6 empty] | 58187 | 43994 | 4.4 | 0 | 0 | 6.03 | 5882
PH4100A | GG\09\022\B | GG | 9 | 22 | B | 1 Prestrip - Thick | 100 | 42.3325 | 42.3325 | 2020-06-14 02:39 | 2020-06-15 09:26 | 51146.1213 | 51146 | [7 empty] | 0 | 0 | 5.15 | 14.42 | 5157.61
PH4100XPC#1 | GG\09\022\B | GG | 9 | 22 | B | 1 Prestrip - Thick | 100 | 57.6675 | 57.6675 | 2020-06-14 02:39 | 2020-06-15 09:26 | 69673.97 | 69674 | [7 empty] | 0 | 0 | 7.01 | 14.42 | 5157.61
TS6060#1 | RS\13\004\A | RS | 13 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-14 12:45 | 2020-06-22 17:46 | 203287.2022 | 203287 | [7 empty] | 0 | 0 | 20.35 | 13.49 | 5237.4
TS5500Exc | RS\13\003\B | RS | 13 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-06-14 21:29 | 2020-06-15 11:10 | 17239.9583 | [6 empty] | 17240 | 12313 | 1.55 | 0 | 0 | 8.63 | 5654
PH4100XPC#1 | GG\09\023\B | GG | 9 | 23 | B | 1 Prestrip - Thick | 100 | 39.3595 | 39.3595 | 2020-06-15 09:26 | 2020-06-17 20:26 | 137432.0031 | 137432 | [7 empty] | 0 | 0 | 14.27 | 16.97 | 4919.18
PH4100A | GG\09\023\B | GG | 9 | 23 | B | 1 Prestrip - Thick | 100 | 28.9007 | 28.9007 | 2020-06-15 09:26 | 2020-06-17 20:26 | 100912.9092 | 100913 | [7 empty] | 0 | 0 | 10.48 | 16.97 | 4919.18
TS5500Exc | SC\38\025\D | SC | 38 | 25 | D | 7 PostStrip | 100 | 0 | 100 | 2020-06-15 11:10 | 2020-06-18 09:36 | 62284.3873 |  |  | 62284 | [5 empty] | 0 | 0 | 0 | 6.91 | 5806.24
TS5500Shv | RS\12\007\A | RS | 12 | 7 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-15 23:38 | 2020-06-17 01:37 | 31669.9149 | [6 empty] | 31670 | 21686 | 1.71 | 0 | 0 | 16.89 | 4903
TS5500Shv | RS\13\003\B | RS | 13 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-17 01:37 | 2020-06-17 15:18 | 16689.7468 | [6 empty] | 16690 | 11920 | 1.5 | 0 | 0 | 8.63 | 5654
TS Fleet 5 | MW\32\010\B | MW | 32 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-17 02:15 | 2020-06-17 22:54 | 38721.7622 | 38722 | [7 empty] | 0 | 0 | 2.59 | 9 | 5603.59
DRE2 | MW\29\007\D | MW | 29 | 7 | D | 6 DL | 100 | 100 | 100 | 2020-06-17 04:19 | 2020-06-21 20:42 | 377993.3026 |  |  |  | 21573 | 377993 | 286615 |  |  | 0 | 30.86 | 0 | 6.34 | 5854.36
TS5500Shv | MW\29\006\D | MW | 29 | 6 | D | 8 Coal Mining | 42.5 | 0 | 42.5 | 2020-06-17 15:18 | 2020-06-18 11:36 | 24752.0102 | [6 empty] | 24752 | 18654 | 1.87 | 0 | 0 | 6.13 | 5873
PH4100A | GG\09\024\B | GG | 9 | 24 | B | 1 Prestrip - Thick | 100 | 27.4306 | 27.4306 | 2020-06-17 20:26 | 2020-06-19 20:16 | 82040.5655 | 82041 | [7 empty] | 0 | 0 | 9.27 | 11.68 | 5303.53
PH4100XPC#1 | GG\09\024\B | GG | 9 | 24 | B | 1 Prestrip - Thick | 100 | 37.3485 | 37.3485 | 2020-06-17 20:26 | 2020-06-19 20:16 | 111703.5055 | 111704 | [7 empty] | 0 | 0 | 12.62 | 11.68 | 5303.53
TS Fleet 5 | MW\33\007\A | MW | 33 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-17 22:54 | 2020-06-24 05:28 | 282478.2533 | 282478 | [7 empty] | 0 | 0 | 27.99 | 10.41 | 5452.83
TS5500Exc | MW\29\006\D | MW | 29 | 6 | D | 8 Coal Mining | 57.5 | 0 | 57.5 | 2020-06-18 09:36 | 2020-06-19 12:13 | 33528.8482 | [6 empty] | 33529 | 25269 | 2.53 | 0 | 0 | 6.13 | 5873
TS5500Shv | MW\32\010\B | MW | 32 | 10 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-18 11:36 | 2020-06-19 10:40 | 28124.1152 | [6 empty] | 28124 | 20870 | 1.41 | 0 | 0 | 9 | 5604
DRE1 | MW\30\001\D | MW | 30 | 1 | D | 6 DL | 100 | 0 | 100 | 2020-06-18 22:12 | 2020-06-23 15:51 | 396961.2835 |  |  |  | 28231 | 396961 | 285448 |  |  | 0 | 35 | 0 | 7.49 | 5754.98
TS5500Shv | MW\33\005\B | MW | 33 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-19 10:40 | 2020-06-20 01:05 | 17583.5126 | [6 empty] | 17584 | 12993 | 1.3 | 0 | 0 | 8.99 | 5588
TS5500Exc | SC\38\025\D | SC | 38 | 25 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-06-19 12:13 | 2020-06-22 01:50 | 77611.192 | [6 empty] | 77611 | 57960 | 4.83 | 0 | 0 | 6.91 | 5806
PH4100XPC#1 | GG\09\025\D | GG | 9 | 25 | D | 1 Prestrip - Thick | 100 | 33.3681 | 33.3681 | 2020-06-19 20:16 | 2020-06-20 12:01 | 36808.2666 | 36808 | [7 empty] | 0 | 0 | 4.61 | 5.97 | 5861.67
PH4100A | GG\09\025\D | GG | 9 | 25 | D | 1 Prestrip - Thick | 100 | 24.4817 | 24.4817 | 2020-06-19 20:16 | 2020-06-20 12:01 | 27005.6516 | 27006 | [7 empty] | 0 | 0 | 3.38 | 5.97 | 5861.67
TS5500Shv | MW\33\006\A | MW | 33 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-20 01:05 | 2020-06-20 18:17 | 20983.8047 | [6 empty] | 20984 | 15470 | 1.56 | 0 | 0 | 10.45 | 5429
PH4100A | GG\11\002\X1 | GG | 11 | 2 | X1 | 1 Prestrip - Thick | 100 | 0 | 100 | 2020-06-20 12:01 | 2020-06-22 23:56 | 99559.5853 | 99560 | [7 empty] | 0 | 0 | 8.27 | 0 | 0
PH4100XPC#1 | GG\10\002\X1 | GG | 10 | 2 | X1 | 1 Prestrip - Thick | 100 | 0 | 100 | 2020-06-20 12:01 | 2020-06-22 15:52 | 117361.6277 | 117362 | [7 empty] | 0 | 0 | 8.8 | 0 | 0
TS5500Shv | GG\10\018\X2 | GG | 10 | 18 | X2 | 1 Prestrip - Thick | 6.3648 | 0 | 6.3648 | 2020-06-20 18:17 | 2020-06-21 06:52 | 13473.4698 | 13473 | [7 empty] | 0 | 0 | 2.13 | 0 | 0
TS5500Shv | GG\10\022\X2 | GG | 10 | 22 | X2 | 1 Prestrip - Thick | 31.6277 | 0 | 31.6277 | 2020-06-21 06:52 | 2020-06-24 01:42 | 71577.37 | 71577 | [7 empty] | 0 | 0 | 7.56 | 0 | 0
DRE2 | MW\29\008\D | MW | 29 | 8 | D | 6 DL | 100 | 100 | 100 | 2020-06-21 20:42 | 2020-06-26 17:18 | 392237.9376 |  |  |  | 22386 | 392238 | 297416 |  |  | 0 | 32.05 | 0 | 6.34 | 5856.55
TS5500Exc | MW\29\007\D | MW | 29 | 7 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-06-22 01:50 | 2020-06-23 01:58 | 30393.1958 | [6 empty] | 30393 | 22852 | 2.29 | 0 | 0 | 6.34 | 5854
PH4100XPC#1 | GG\10\002\B | GG | 10 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-22 15:52 | 2020-06-24 21:52 | 122238.5943 | 122239 | [7 empty] | 0 | 0 | 9.27 | 9.89 | 5531.69
TS6060#1 | RS\12\005\B | RS | 12 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-22 17:46 | 2020-06-24 04:26 | 35777.2536 | 35777 | [7 empty] | 0 | 0 | 3.57 | 9.4 | 5556.37
PH4100A | GG\11\002\B | GG | 11 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-22 23:56 | 2020-06-25 12:54 | 101290.9617 | 101291 | [7 empty] | 0 | 0 | 8.49 | 10.08 | 5512.1
TS5500Exc | MW\32\010\B | MW | 32 | 10 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-06-23 01:58 | 2020-06-24 01:02 | 29051.2838 | [6 empty] | 29051 | 21558 | 1.45 | 0 | 0 | 9 | 5604
DRE1 | MW\30\002\D | MW | 30 | 2 | D | 6 DL | 100 | 0 | 100 | 2020-06-23 15:51 | 2020-06-28 22:31 | 442500.3562 |  |  |  | 31470 | 442500 | 318195 |  |  | 0 | 35 | 0 | 7.27 | 5774.22
TS5500Exc | MW\30\001\D | MW | 30 | 1 | D | 8 Coal Mining | 21.7 | 0 | 21.7 | 2020-06-24 01:02 | 2020-06-24 10:35 | 12040.4346 | [6 empty] | 12040 | 8961 | 1.01 | 0 | 0 | 7.49 | 5755
TS5500Shv | MW\29\007\D | MW | 29 | 7 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-24 01:42 | 2020-06-25 01:49 | 29423.2002 | [6 empty] | 29423 | 22123 | 2.21 | 0 | 0 | 6.34 | 5854
TS6060#1 | RS\12\006\B | RS | 12 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-24 04:26 | 2020-06-25 09:41 | 30177.7688 | 30178 | [7 empty] | 0 | 0 | 3.02 | 9.7 | 5498.51
TS Fleet 5 | MW\33\008\A | MW | 33 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-24 05:28 | 2020-07-02 14:57 | 377965.1742 | 377965 | [7 empty] | 0 | 0 | 37.81 | 11.64 | 5357.04
TS5500Exc | RS\12\005\B | RS | 12 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-06-24 10:35 | 2020-06-25 03:09 | 20862.032 | [6 empty] | 20862 | 14896 | 1.49 | 0 | 0 | 9.4 | 5556
PH4100XPC#1 | GG\10\003\X1 | GG | 10 | 3 | X1 | 1 Prestrip - Thick | 100 | 80.4115 | 80.4115 | 2020-06-24 21:52 | 2020-07-05 06:50 | 557871.4864 | 557871 | [7 empty] | 0 | 0 | 52.26 | 9.52 | 5445.21
TS5500Shv | GG\10\002\B | GG | 10 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-06-25 01:49 | 2020-06-27 11:19 | 70108.8223 | [6 empty] | 70109 | 51515 | 3.96 | 0 | 0 | 9.89 | 5532
TS5500Exc | MW\33\003\A | MW | 33 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-06-25 03:09 | 2020-06-25 11:41 | 10749.4569 | [6 empty] | 10749 | 7828 | 0.79 | 0 | 0 | 11.58 | 5337
TS6060#1 | RS\12\007\B | RS | 12 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-25 09:41 | 2020-06-26 18:25 | 33764.1977 | 33764 | [7 empty] | 0 | 0 | 2.67 | 9.91 | 5505.43
TS5500Exc | RS\12\006\B | RS | 12 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-06-25 11:41 | 2020-06-26 19:48 | 40466.5523 | [6 empty] | 40467 | 28709 | 2.87 | 0 | 0 | 9.7 | 5499
PH4100A | GG\11\003\X1 | GG | 11 | 3 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-25 12:54 | 2020-07-14 15:22 | 758122.3565 | 758122 | [7 empty] | 0 | 0 | 70.93 | 9.73 | 5417.68
DRE2 | MW\29\009\D | MW | 29 | 9 | D | 6 DL | 100 | 100 | 100 | 2020-06-26 17:18 | 2020-07-01 12:19 | 386865.9614 |  |  |  | 22080 | 386866 | 293343 |  |  | 0 | 31.6 | 0 | 5.9 | 5894.41
TS6060#1 | RS\13\005\A | RS | 13 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-06-26 18:25 | 2020-07-04 19:32 | 199265.6069 | 199266 | [7 empty] | 0 | 0 | 19.95 | 15.22 | 5060.91
TS5500Exc | MW\29\008\D | MW | 29 | 8 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-06-26 19:48 | 2020-06-27 21:20 | 32155.4147 | [6 empty] | 32155 | 24161 | 2.42 | 0 | 0 | 6.34 | 5857
TS5500Shv | GG\11\002\B | GG | 11 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-06-27 11:19 | 2020-06-29 16:25 | 64745.8574 | [6 empty] | 64746 | 47564 | 4.04 | 0 | 0 | 10.08 | 5512
TS5500Exc | RS\12\007\B | RS | 12 | 7 | B | 8 Coal Mining | 65.7 | 0 | 65.7 | 2020-06-27 21:20 | 2020-06-28 22:37 | 31843.3994 | [6 empty] | 31843 | 22536 | 1.79 | 0 | 0 | 9.91 | 5505
DRE1 | MW\30\003\D | MW | 30 | 3 | D | 6 DL | 100 | 100 | 100 | 2020-06-28 22:31 | 2020-07-02 15:18 | 310110.3296 |  |  |  | 15944 | 310110 | 249789 |  |  | 0 | 26.59 | 0 | 6.8 | 5815.16
TS5500Exc | MW\30\002\D | MW | 30 | 2 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-06-28 22:37 | 2020-06-30 00:11 | 32195.1619 | [6 empty] | 32195 | 24037 | 2.4 | 0 | 0 | 7.27 | 5774
TS5500Shv | MW\29\008\D | MW | 29 | 8 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-06-29 16:25 | 2020-06-30 17:56 | 31129.1781 | [6 empty] | 31129 | 23390 | 2.34 | 0 | 0 | 6.34 | 5857
TS5500Exc | MW\33\004\A | MW | 33 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-06-30 00:11 | 2020-06-30 17:00 | 21201.5825 | [6 empty] | 21202 | 15552 | 1.56 | 0 | 0 | 10.33 | 5425
TS5500Exc | MW\33\005\B | MW | 33 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-06-30 17:00 | 2020-07-01 07:26 | 18163.1889 | [6 empty] | 18163 | 13421 | 1.34 | 0 | 0 | 8.99 | 5588
TS5500Shv | RS\13\004\A | RS | 13 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-06-30 17:56 | 2020-07-02 12:45 | 52203.2386 | [6 empty] | 52203 | 36448 | 3.65 | 0 | 0 | 13.49 | 5237
TS5500Exc | MW\33\006\A | MW | 33 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-01 07:26 | 2020-07-02 00:38 | 21675.5785 | [6 empty] | 21676 | 15980 | 1.61 | 0 | 0 | 10.45 | 5429
DRE2 | MW\29\010\D | MW | 29 | 10 | D | 6 DL | 100 | 100 | 100 | 2020-07-01 12:19 | 2020-07-06 04:54 | 378688.4952 |  |  |  | 21613 | 378688 | 287143 |  |  | 0 | 30.89 | 0 | 5.55 | 5924.23
TS5500Exc | MW\33\006\B | MW | 33 | 6 | B | 1 Prestrip - Thick | 100 | 95.1621 | 95.1621 | 2020-07-02 00:38 | 2020-07-04 09:26 | 50227.1525 | 50227 | [7 empty] | 0 | 0 | 5.02 | 8.84 | 5603.91
TS5500Shv | MW\29\009\D | MW | 29 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-07-02 12:45 | 2020-07-04 15:51 | 62307.8456 | [6 empty] | 62308 | 47003 | 4.7 | 0 | 0 | 5.9 | 5894
TS Fleet 5 | MW\33\003\B | MW | 33 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-07-02 14:57 | 2020-07-03 00:59 | 18816.1975 | 18816 | [7 empty] | 0 | 0 | 1.9 | 9.24 | 5609.19
DRE1 | MW\30\004\D | MW | 30 | 4 | D | 6 DL | 100 | 100 | 100 | 2020-07-02 15:18 | 2020-07-06 13:11 | 327928.2858 |  |  |  | 16860 | 327928 | 264141 |  |  | 0 | 27.98 | 0 | 6.31 | 5857.59
TS Fleet 5 | MW\33\004\B | MW | 33 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-07-03 00:59 | 2020-07-03 18:22 | 32618.0572 | 32618 | [7 empty] | 0 | 0 | 3.26 | 8.75 | 5627.61
TS Fleet 5 | MW\33\006\B | MW | 33 | 6 | B | 1 Prestrip - Thick | 4.8379 | 4.8379 | 4.8379 | 2020-07-03 18:22 | 2020-07-03 19:43 | 2553.4869 | 2553 | [7 empty] | 0 | 0 | 0.26 | 8.84 | 5603.91
TS Fleet 5 | MW\33\009\A | MW | 33 | 9 | A | 1 Prestrip - Thick | 92.663 | 92.663 | 92.663 | 2020-07-03 19:43 | 2020-07-13 09:52 | 431753.2313 | 431753 | [7 empty] | 0 | 0 | 42.96 | 12.21 | 5316.34
TS5500Exc | MW\30\003\D | MW | 30 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-04 09:26 | 2020-07-05 10:32 | 31629.6567 | [6 empty] | 31630 | 23803 | 2.38 | 0 | 0 | 6.8 | 5815
TS5500Shv | MW\30\001\D | MW | 30 | 1 | D | 8 Coal Mining | 78.3 | 0 | 78.3 | 2020-07-04 15:51 | 2020-07-06 03:35 | 43573.4551 | [6 empty] | 43573 | 32429 | 3.66 | 0 | 0 | 7.49 | 5755
TS6060#1 | RS\13\004\B | RS | 13 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-07-04 19:32 | 2020-07-06 03:52 | 33366.9169 | 33367 | [7 empty] | 0 | 0 | 3.33 | 9.26 | 5597.5
PH4100XPC#1 | GG\10\004\X1 | GG | 10 | 4 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-07-05 06:50 | 2020-07-16 11:13 | 616079.4787 | 616079 | [7 empty] | 0 | 0 | 58.53 | 10.09 | 5395.53
TS5500Exc | MW\33\003\B | MW | 33 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-05 10:32 | 2020-07-05 22:56 | 15610.2818 | [6 empty] | 15610 | 11520 | 1.16 | 0 | 0 | 9.24 | 5609
TS5500Exc | MW\33\004\B | MW | 33 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-05 22:56 | 2020-07-06 16:22 | 21967.8188 | [6 empty] | 21968 | 16243 | 1.62 | 0 | 0 | 8.75 | 5628
TS5500Shv | MW\30\002\D | MW | 30 | 2 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-06 03:35 | 2020-07-07 05:09 | 31167.6567 | [6 empty] | 31168 | 23270 | 2.33 | 0 | 0 | 7.27 | 5774
TS6060#1 | GG\10\003\X1 | GG | 10 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-07-06 03:52 | 2020-07-06 16:49 | 17521.323 | [6 empty] | 17521 | 13048 | 1.32 | 0 | 0 | 9.52 | 5445
DRE2 | MW\29\011\D | MW | 29 | 11 | D | 6 DL | 100 | 100 | 100 | 2020-07-06 04:54 | 2020-07-09 09:23 | 257301.2783 |  |  |  | 10423 | 257301 | 135704 |  |  | 0 | 31.48 | 0 | 5.67 | 5913.41
DRE1 | MW\30\005\D | MW | 30 | 5 | D | 6 DL | 100 | 100 | 100 | 2020-07-06 13:11 | 2020-07-10 14:24 | 339588.8887 |  |  |  | 17460 | 339589 | 273533 |  |  | 0 | 28.89 | 0 | 5.97 | 5886.27
TS5500Exc | MW\29\010\D | MW | 29 | 10 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-06 16:22 | 2020-07-07 16:37 | 30542.1365 | [6 empty] | 30542 | 23150 | 2.31 | 0 | 0 | 5.55 | 5924
TS6060#1 | RS\13\006\X | RS | 13 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-07-06 16:49 | 2020-07-24 01:53 | 418190.4723 | 418190 | [7 empty] | 0 | 0 | 41.19 | 10.97 | 5288.5
TS5500Shv | MW\29\010\D | MW | 29 | 10 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-07 05:09 | 2020-07-08 05:23 | 29567.3874 | [6 empty] | 29567 | 22411 | 2.24 | 0 | 0 | 5.55 | 5924
TS5500Exc | MW\30\004\D | MW | 30 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-07 16:37 | 2020-07-08 16:57 | 30653.3067 | [6 empty] | 30653 | 23178 | 2.32 | 0 | 0 | 6.31 | 5858
TS5500Shv | RS\12\005\B | RS | 12 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-08 05:23 | 2020-07-08 21:57 | 20196.2225 | [6 empty] | 20196 | 14421 | 1.44 | 0 | 0 | 9.4 | 5556
TS5500Exc | RS\13\004\B | RS | 13 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-08 16:57 | 2020-07-09 09:58 | 21434.8595 | [6 empty] | 21435 | 15319 | 1.53 | 0 | 0 | 9.26 | 5598
TS5500Shv | MW\30\003\D | MW | 30 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-08 21:57 | 2020-07-09 23:04 | 30620.1996 | [6 empty] | 30620 | 23043 | 2.3 | 0 | 0 | 6.8 | 5815
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2020-07-09 09:23 | 2020-07-11 09:23
TS5500Exc | RS\13\005\A | RS | 13 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-09 09:58 | 2020-07-10 06:52 | 26317.9087 | [6 empty] | 26318 | 18128 | 1.81 | 0 | 0 | 15.22 | 5061
TS5500Shv | MW\29\011\D | MW | 29 | 11 | D | 7 PostStrip | 100 | 0 | 100 | 2020-07-09 23:04 | 2020-07-11 00:48 | 27594.8509 |  |  | 27595 | [5 empty] | 0 | 0 | 0 | 5.67 | 5913.41
TS5500Exc | MW\33\006\B | MW | 33 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-10 06:52 | 2020-07-10 23:38 | 21112.8821 | [6 empty] | 21113 | 15607 | 1.56 | 0 | 0 | 8.84 | 5604
DRE1 | MW\30\006\D | MW | 30 | 6 | D | 6 DL | 100 | 100 | 100 | 2020-07-10 14:24 | 2020-07-14 15:48 | 340271.5839 |  |  |  | 17495 | 340272 | 274083 |  |  | 0 | 29.11 | 0 | 6.01 | 5882.51
TS5500Exc | MW\30\005\D | MW | 30 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-10 23:38 | 2020-07-11 23:08 | 29599.022 | [6 empty] | 29599 | 22397 | 2.24 | 0 | 0 | 5.97 | 5886
TS5500Shv | MW\29\011\D | MW | 29 | 11 | D | 8 Coal Mining | 61.8 | 0 | 61.8 | 2020-07-11 00:48 | 2020-07-11 16:42 | 19372.7497 | [6 empty] | 19373 | 14695 | 2.75 | 0 | 0 | 5.67 | 5913
DRE2 | RS\07\003\D | RS | 7 | 3 | D | 6 DL | 100 | 100 | 100 | 2020-07-11 09:23 | 2020-07-14 22:12 | 285283.8296 |  |  |  | 12764 | 285284 | 242523 |  |  | 0 | 24.26 | 0 | 6.21 | 5875.2
TS5500Shv | RS\12\007\B | RS | 12 | 7 | B | 8 Coal Mining | 34.3 | 0 | 34.3 | 2020-07-11 16:42 | 2020-07-12 06:21 | 16656.2019 | [6 empty] | 16656 | 11788 | 0.93 | 0 | 0 | 9.91 | 5505
TS5500Exc | MW\29\011\D | MW | 29 | 11 | D | 8 Coal Mining | 38.2 | 0 | 38.2 | 2020-07-11 23:08 | 2020-07-12 08:38 | 11968.8092 | [6 empty] | 11969 | 9079 | 1.7 | 0 | 0 | 5.67 | 5913
TS5500Shv | MW\30\004\D | MW | 30 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-12 06:21 | 2020-07-13 06:41 | 29675.0096 | [6 empty] | 29675 | 22438 | 2.24 | 0 | 0 | 6.31 | 5858
TS5500Exc | MW\33\008\A | MW | 33 | 8 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-12 08:38 | 2020-07-13 03:22 | 23611.7578 | [6 empty] | 23612 | 17319 | 1.74 | 0 | 0 | 11.64 | 5357
TS5500Exc | MW\34\006\A | MW | 34 | 6 | A | 1 Prestrip - Thick | 6.7917 | 6.7917 | 6.7917 | 2020-07-13 03:22 | 2020-07-13 20:40 | 15387.64 | 15388 | [7 empty] | 0 | 0 | 1.58 | 10.8 | 5399.89
TS5500Shv | MW\33\003\B | MW | 33 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-13 06:41 | 2020-07-13 19:05 | 15112.0813 | [6 empty] | 15112 | 11153 | 1.13 | 0 | 0 | 9.24 | 5609
TS Fleet 5 | MW\33\010\X | MW | 33 | 10 | X | 1 Prestrip - Thick | 84.1678 | 84.1678 | 84.1678 | 2020-07-13 09:52 | 2020-07-24 06:55 | 489716.9036 | 489717 | [7 empty] | 0 | 0 | 31.6 | 12.21 | 5215.7
TS5500Shv | RS\13\004\B | RS | 13 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-13 19:05 | 2020-07-14 12:06 | 20750.7682 | [6 empty] | 20751 | 14830 | 1.48 | 0 | 0 | 9.26 | 5598
TS5500Exc | MW\33\009\A | MW | 33 | 9 | A | 8 Coal Mining | 86.9 | 0 | 86.9 | 2020-07-13 20:40 | 2020-07-15 05:25 | 41244.1101 | [6 empty] | 41244 | 30155 | 3.02 | 0 | 0 | 12.21 | 5316
TS5500Shv | MW\30\005\D | MW | 30 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-14 12:06 | 2020-07-15 11:36 | 28654.3724 | [6 empty] | 28654 | 21683 | 2.17 | 0 | 0 | 5.97 | 5886
PH4100A | GG\10\003\X2 | GG | 10 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 72.1707 | 2020-07-14 15:22 | 2020-07-17 04:32 | 101648.8028 | 101649 | [7 empty] | 0 | 0 | 10.29 | 0 | 0
DRE1 | MW\30\007\D | MW | 30 | 7 | D | 6 DL | 100 | 100 | 100 | 2020-07-14 15:48 | 2020-07-19 02:54 | 374091.7892 |  |  |  | 21351 | 374092 | 283657 |  |  | 0 | 30.54 | 0 | 6.23 | 5864.25
DRE2 | RS\07\004\D | RS | 7 | 4 | D | 6 DL | 100 | 100 | 100 | 2020-07-14 22:12 | 2020-07-18 08:30 | 276838.8796 |  |  |  | 12387 | 276839 | 235344 |  |  | 0 | 24.77 | 0 | 6.86 | 5817.95
TS5500Exc | RS\07\003\D | RS | 7 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-15 05:25 | 2020-07-16 07:25 | 32767.884 | [6 empty] | 32768 | 24042 | 2.28 | 0 | 0 | 6.21 | 5875
TS5500Shv | RS\07\003\D | RS | 7 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-15 11:36 | 2020-07-16 13:37 | 31722.1005 | [6 empty] | 31722 | 23275 | 2.21 | 0 | 0 | 6.21 | 5875
TS5500Exc | MW\30\006\D | MW | 30 | 6 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-16 07:25 | 2020-07-17 06:44 | 29368.4702 | [6 empty] | 29368 | 22169 | 2.22 | 0 | 0 | 6.01 | 5883
PH4100XPC#1 | GG\10\003\X2 | GG | 10 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 27.8293 | 2020-07-16 11:13 | 2020-07-17 04:32 | 39196.1972 | 39196 | [7 empty] | 0 | 0 | 3.97 | 0 | 0
TS5500Shv | GG\10\004\X1 | GG | 10 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-07-16 13:37 | 2020-07-17 02:39 | 15910.0735 | [6 empty] | 15910 | 11814 | 1.18 | 0 | 0 | 10.09 | 5396
TS5500Shv | MW\33\004\B | MW | 33 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-17 02:39 | 2020-07-17 20:06 | 21266.7182 | [6 empty] | 21267 | 15725 | 1.57 | 0 | 0 | 8.75 | 5628
PH4100XPC#1 | GG\10\003\B | GG | 10 | 3 | B | 1 Prestrip - Thick | 100 | 57.6675 | 57.6675 | 2020-07-17 04:32 | 2020-07-18 09:26 | 65385.6201 | 65386 | [7 empty] | 0 | 0 | 6.6 | 9.68 | 5545.63
PH4100A | GG\10\003\B | GG | 10 | 3 | B | 1 Prestrip - Thick | 100 | 42.3325 | 42.3325 | 2020-07-17 04:32 | 2020-07-18 09:26 | 47998.1384 | 47998 | [7 empty] | 0 | 0 | 4.84 | 9.68 | 5545.63
TS5500Exc | MW\34\009\A | MW | 34 | 9 | A | 1 Prestrip - Thick | 10.9007 | 10.9007 | 10.9007 | 2020-07-17 06:44 | 2020-07-19 15:46 | 50664.982 | 50665 | [7 empty] | 0 | 0 | 5.02 | 12.24 | 5314.89
TS5500Shv | RS\13\005\A | RS | 13 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-17 20:06 | 2020-07-18 17:00 | 25477.9755 | [6 empty] | 25478 | 17549 | 1.75 | 0 | 0 | 15.22 | 5061
DRE2 | RS\07\005\D | RS | 7 | 5 | D | 6 DL | 100 | 100 | 100 | 2020-07-18 08:30 | 2020-07-21 16:59 | 270727.0316 |  |  |  | 12113 | 270727 | 230148 |  |  | 0 | 24.22 | 0 | 7 | 5805.43
PH4100XPC#1 | GG\10\004\X2 | GG | 10 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2020-07-18 09:26 | 2020-07-20 12:07 | 114724.845 | 114725 | [7 empty] | 0 | 0 | 11.58 | 0 | 0
PH4100A | GG\11\004\X1 | GG | 11 | 4 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-07-18 09:26 | 2020-08-03 17:17 | 661610.7486 | 661611 | [7 empty] | 0 | 0 | 62.44 | 9.92 | 5401
TS5500Shv | RS\07\004\D | RS | 7 | 4 | D | 8 Coal Mining | 35.7 | 0 | 35.7 | 2020-07-18 17:00 | 2020-07-19 11:14 | 22233.7144 | [6 empty] | 22234 | 16138 | 1.61 | 0 | 0 | 6.86 | 5818
DRE1 | MW\30\008\D | MW | 30 | 8 | D | 6 DL | 100 | 100 | 100 | 2020-07-19 02:54 | 2020-07-23 16:44 | 383649.9443 |  |  |  | 21896 | 383650 | 290905 |  |  | 0 | 31.36 | 0 | 6.25 | 5864.22
TS5500Shv | MW\30\006\D | MW | 30 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-19 11:14 | 2020-07-20 10:32 | 28431.1786 | [6 empty] | 28431 | 21461 | 2.15 | 0 | 0 | 6.01 | 5883
TS5500Exc | RS\07\004\D | RS | 7 | 4 | D | 8 Coal Mining | 64.3 | 0 | 64.3 | 2020-07-19 15:46 | 2020-07-20 23:38 | 40122.3806 | [6 empty] | 40122 | 29122 | 2.91 | 0 | 0 | 6.86 | 5818
TS5500Shv | MW\30\007\D | MW | 30 | 7 | D | 8 Coal Mining | 32.8 | 0 | 32.8 | 2020-07-20 10:32 | 2020-07-21 02:36 | 19575.848 | [6 empty] | 19576 | 14730 | 1.47 | 0 | 0 | 6.23 | 5864
PH4100XPC#1 | GG\10\004\B | GG | 10 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-07-20 12:07 | 2020-07-23 03:34 | 143620.5478 | 143621 | [7 empty] | 0 | 0 | 14.38 | 10.78 | 5419.09
TS5500Exc | MW\30\007\D | MW | 30 | 7 | D | 8 Coal Mining | 67.2 | 0 | 67.2 | 2020-07-20 23:38 | 2020-07-22 07:27 | 40090.4659 | [6 empty] | 40090 | 30167 | 3.02 | 0 | 0 | 6.23 | 5864
TS5500Shv | MW\33\006\B | MW | 33 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-21 02:36 | 2020-07-21 19:21 | 20439.0667 | [6 empty] | 20439 | 15109 | 1.51 | 0 | 0 | 8.84 | 5604
DRE2 | RS\07\006\D | RS | 7 | 6 | D | 6 DL | 100 | 100 | 100 | 2020-07-21 16:59 | 2020-07-25 08:30 | 294380.097 |  |  |  | 15135 | 294380 | 237119 |  |  | 0 | 25.22 | 0 | 6.82 | 5821.82
TS5500Shv | RS\07\005\D | RS | 7 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-21 19:21 | 2020-07-22 19:56 | 29970.595 | [6 empty] | 29971 | 21734 | 2.17 | 0 | 0 | 7 | 5805
TS5500Exc | RS\07\005\D | RS | 7 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-22 07:27 | 2020-07-23 08:02 | 30958.6366 | [6 empty] | 30959 | 22451 | 2.24 | 0 | 0 | 7 | 5805
TS5500Shv | MW\33\007\A | MW | 33 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-07-22 19:56 | 2020-07-24 09:13 | 45459.6758 | [6 empty] | 45460 | 33543 | 3.39 | 0 | 0 | 10.41 | 5453
PH4100XPC#1 | GG\10\005\X2 | GG | 10 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2020-07-23 03:34 | 2020-08-05 11:14 | 758681.776 | 758682 | [7 empty] | 0 | 0 | 72.47 | 0 | 0
TS5500Exc | MW\34\010\X | MW | 34 | 10 | X | 1 Prestrip - Thick | 15.0599 | 15.0599 | 15.0599 | 2020-07-23 08:02 | 2020-07-27 05:06 | 82699.5938 | 82700 | [7 empty] | 0 | 0 | 5.71 | 12.18 | 5223.28
DRE1 | MW\30\009\D | MW | 30 | 9 | D | 6 DL | 100 | 100 | 100 | 2020-07-23 16:44 | 2020-07-28 04:45 | 377323.5012 |  |  |  | 21535 | 377324 | 286108 |  |  | 0 | 30.83 | 0 | 5.86 | 5898.09
TS6060#1 | GG\10\003\B | GG | 10 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-07-24 01:53 | 2020-07-25 16:53 | 52781.809 | [6 empty] | 52782 | 38777 | 3.89 | 0 | 0 | 9.68 | 5546
TS Fleet 5 | MW\34\002\D | MW | 34 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-07-24 06:55 | 2020-07-25 22:07 | 73559.5967 | 73560 | [7 empty] | 0 | 0 | 8.23 | 7.49 | 5755.68
TS5500Shv | MW\30\008\D | MW | 30 | 8 | D | 8 Coal Mining | 22.4 | 0 | 22.4 | 2020-07-24 09:13 | 2020-07-24 20:42 | 14005.9422 | [6 empty] | 14006 | 10532 | 1.05 | 0 | 0 | 6.25 | 5864
TS5500Shv | RS\13\006\X | RS | 13 | 6 | X | 8 Coal Mining | 10.4 | 0 | 10.4 | 2020-07-24 20:42 | 2020-07-24 22:23 | 2056.9141 | [6 empty] | 2057 | 1461 | 0.15 | 0 | 0 | 10.97 | 5289
TS5500Shv | MW\33\008\A | MW | 33 | 8 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-24 22:23 | 2020-07-25 17:08 | 22858.191 | [6 empty] | 22858 | 16767 | 1.69 | 0 | 0 | 11.64 | 5357
DRE2 | RS\07\007\D | RS | 7 | 7 | D | 6 DL | 100 | 100 | 100 | 2020-07-25 08:30 | 2020-07-29 00:36 | 296345.4397 |  |  |  | 15236 | 296345 | 238702 |  |  | 0 | 25.4 | 0 | 6.87 | 5817.59
TS6060#1 | GG\10\004\B | GG | 10 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-07-25 16:53 | 2020-07-27 07:17 | 51987.2735 | [6 empty] | 51987 | 37994 | 3.8 | 0 | 0 | 10.78 | 5419
TS5500Shv | MW\33\009\A | MW | 33 | 9 | A | 8 Coal Mining | 13.1 | 0 | 13.1 | 2020-07-25 17:08 | 2020-07-25 22:14 | 6218.319 | [6 empty] | 6218 | 4546 | 0.46 | 0 | 0 | 12.21 | 5316
TS Fleet 5 | MW\33\007\B | MW | 33 | 7 | B | 1 Prestrip - Thick | 50.8847 | 50.8847 | 50.8847 | 2020-07-25 22:07 | 2020-07-26 17:49 | 36935.3875 | 36935 | [7 empty] | 0 | 0 | 3.71 | 9.47 | 5533.12
TS5500Shv | GG\11\011\X2 | GG | 11 | 11 | X2 | 1 Prestrip - Thick | 28.3361 | 0 | 28.3361 | 2020-07-25 22:14 | 2020-07-30 19:31 | 125942.1908 | 125942 | [7 empty] | 0 | 0 | 16.46 | 0 | 0
TS Fleet 5 | MW\34\003\A | MW | 34 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-07-26 17:49 | 2020-08-02 06:05 | 293156.672 | 293157 | [7 empty] | 0 | 0 | 28.84 | 11.87 | 5286.09
TS5500Exc | RS\07\006\D | RS | 7 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-07-27 05:06 | 2020-07-29 06:16 | 61914.4345 | [6 empty] | 61914 | 45042 | 4.5 | 0 | 0 | 6.82 | 5822
TS6060#1 | GG\11\003\X1 | GG | 11 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-07-27 07:17 | 2020-07-27 19:52 | 17027.5337 | [6 empty] | 17028 | 12666 | 1.27 | 0 | 0 | 9.73 | 5418
TS6060#1 | RS\13\005\B | RS | 13 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-07-27 19:52 | 2020-07-29 05:09 | 34336.4899 | 34336 | [7 empty] | 0 | 0 | 3.43 | 9.36 | 5560.44
DRE1 | MW\30\010\D | MW | 30 | 10 | D | 6 DL | 100 | 100 | 100 | 2020-07-28 04:45 | 2020-08-01 17:03 | 378335.7527 |  |  |  | 21593 | 378336 | 286875 |  |  | 0 | 30.86 | 0 | 5.53 | 5926.3
DRE2 | RS\07\008\D | RS | 7 | 8 | D | 6 DL | 100 | 100 | 100 | 2020-07-29 00:36 | 2020-07-31 08:48 | 189062.2573 |  |  |  | 7149 | 189062 | 107587 |  |  | 0 | 25.31 | 0 | 6.93 | 5810.37
TS6060#1 | RS\13\007\X | RS | 13 | 7 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-07-29 05:09 | 2020-08-22 20:05 | 595231.5551 | 595232 | [7 empty] | 0 | 0 | 45.07 | 10.41 | 5325.9
TS5500Exc | MW\30\008\D | MW | 30 | 8 | D | 8 Coal Mining | 77.6 | 0 | 77.6 | 2020-07-29 06:16 | 2020-07-30 20:51 | 48600.0987 | [6 empty] | 48600 | 36545 | 3.65 | 0 | 0 | 6.25 | 5864
TS5500Shv | RS\07\007\D | RS | 7 | 7 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-07-30 19:31 | 2020-07-31 20:40 | 30655.8733 | [6 empty] | 30656 | 22337 | 2.23 | 0 | 0 | 6.87 | 5818
TS5500Exc | RS\07\007\D | RS | 7 | 7 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-30 20:51 | 2020-07-31 21:59 | 31666.5065 | [6 empty] | 31667 | 23074 | 2.31 | 0 | 0 | 6.87 | 5818
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2020-07-31 08:48 | 2020-08-02 08:48
TS5500Shv | RS\07\008\D | RS | 7 | 8 | D | 7 PostStrip | 100 | 0 | 100 | 2020-07-31 20:40 | 2020-08-01 23:00 | 28242.897 |  |  | 28243 | [5 empty] | 0 | 0 | 0 | 6.93 | 5810.37
TS5500Exc | RS\13\005\B | RS | 13 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-07-31 21:59 | 2020-08-01 14:29 | 20789.9629 | [6 empty] | 20790 | 14844 | 1.48 | 0 | 0 | 9.36 | 5560
TS5500Exc | MW\30\009\D | MW | 30 | 9 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-08-01 14:29 | 2020-08-02 15:23 | 31346.7009 | [6 empty] | 31347 | 23665 | 2.37 | 0 | 0 | 5.86 | 5898
DRE1 | MW\30\011\D | MW | 30 | 11 | D | 6 DL | 100 | 100 | 100 | 2020-08-01 17:03 | 2020-08-04 04:04 | 206153.7711 |  |  |  | 8365 | 206154 | 108767 |  |  | 0 | 31.28 | 0 | 5.61 | 5918.8
TS5500Shv | RS\07\008\D | RS | 7 | 8 | D | 8 Coal Mining | 22.7 | 0 | 22.7 | 2020-08-01 23:00 | 2020-08-02 05:15 | 7615.6521 | [6 empty] | 7616 | 5556 | 1.02 | 0 | 0 | 6.93 | 5810
TS5500Shv | RS\13\005\B | RS | 13 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-08-02 05:15 | 2020-08-02 21:45 | 20126.4534 | [6 empty] | 20126 | 14371 | 1.44 | 0 | 0 | 9.36 | 5560
TS Fleet 5 | MW\34\004\A | MW | 34 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-08-02 06:05 | 2020-08-05 07:09 | 137070.9556 | 137071 | [7 empty] | 0 | 0 | 14.45 | 10.71 | 5370.43
DRE2 | BW\30\008\D | BW | 30 | 8 | D | 6 DL | 100 | 100 | 100 | 2020-08-02 08:48 | 2020-08-05 04:21 | 227229.4917 |  |  |  | 10167 | 227229 | 193170 |  |  | 0 | 20.34 | 0 | 5.47 | 5932.17
TS5500Exc | RS\07\008\D | RS | 7 | 8 | D | 8 Coal Mining | 77.3 | 0 | 77.3 | 2020-08-02 15:23 | 2020-08-03 12:00 | 25970.4691 | [6 empty] | 25970 | 18946 | 3.48 | 0 | 0 | 6.93 | 5810
TS5500Shv | MW\30\009\D | MW | 30 | 9 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-08-02 21:45 | 2020-08-03 22:39 | 30346.2743 | [6 empty] | 30346 | 22910 | 2.29 | 0 | 0 | 5.86 | 5898
TS5500Exc | RS\13\006\X | RS | 13 | 6 | X | 8 Coal Mining | 89.6 | 0 | 89.6 | 2020-08-03 12:00 | 2020-08-04 02:03 | 17713.8671 | [6 empty] | 17714 | 12581 | 1.26 | 0 | 0 | 10.97 | 5289
PH4100A | GG\11\005\X2 | GG | 11 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2020-08-03 17:17 | 2020-08-22 19:02 | 788149.3512 | 788149 | [7 empty] | 0 | 0 | 56.77 | 0 | 0
TS5500Shv | GG\11\004\X1 | GG | 11 | 4 | X1 | 8 Coal Mining | 84.9 | 0 | 84.9 | 2020-08-03 22:39 | 2020-08-04 10:36 | 14582.8234 | [6 empty] | 14583 | 10849 | 1.09 | 0 | 0 | 9.92 | 5401
TS5500Exc | MW\33\007\B | MW | 33 | 7 | B | 1 Prestrip - Thick | 49.1153 | 49.1153 | 49.1153 | 2020-08-04 02:03 | 2020-08-05 18:22 | 35650.9941 | 35651 | [7 empty] | 0 | 0 | 3.58 | 9.47 | 5533.12
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2020-08-04 04:04 | 2020-08-06 04:04
TS5500Shv | MW\30\010\D | MW | 30 | 10 | D | 8 Coal Mining | 29.5 | 0 | 29.5 | 2020-08-04 10:36 | 2020-08-05 01:10 | 17766.4849 | [6 empty] | 17766 | 13477 | 1.35 | 0 | 0 | 5.53 | 5926
TS5500Shv | MW\30\011\D | MW | 30 | 11 | D | 7 PostStrip | 54.7945 | 0 | 54.7945 | 2020-08-05 01:10 | 2020-08-05 12:34 | 12211.6801 |  |  | 12212 | [5 empty] | 0 | 0 | 0 | 5.61 | 5918.8
DRE2 | BW\30\007\D | BW | 30 | 7 | D | 6 DL | 100 | 100 | 100 | 2020-08-05 04:21 | 2020-08-08 01:53 | 233879.5619 |  |  |  | 10464 | 233880 | 198824 |  |  | 0 | 20.93 | 0 | 5.6 | 5921.63
TS Fleet 5 | MW\34\005\B | MW | 34 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-08-05 07:09 | 2020-08-09 01:29 | 169478.8228 | 169479 | [7 empty] | 0 | 0 | 17.95 | 9.18 | 5565.56
PH4100XPC#1 | GG\10\006\X1 | GG | 10 | 6 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-08-05 11:14 | 2020-08-15 02:43 | 532660.545 | 532661 | [7 empty] | 0 | 0 | 42.74 | 11.82 | 5290.9
TS5500Shv | GG\11\003\X2 | GG | 11 | 3 | X2 | 1 Prestrip - Thick | 0.67785 | 0 | 0.67785 | 2020-08-05 12:34 | 2020-08-05 13:13 | 703.4288 | 703 | [7 empty] | 0 | 0 | 0.07 | 0 | 0
TS5500Shv | MW\34\003\A | MW | 34 | 3 | A | 8 Coal Mining | 54.8 | 0 | 54.8 | 2020-08-05 13:13 | 2020-08-05 22:20 | 11105.2459 | [6 empty] | 11105 | 8058 | 0.81 | 0 | 0 | 11.87 | 5286
TS5500Exc | MW\33\007\B | MW | 33 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-08-05 18:22 | 2020-08-07 02:39 | 40651.1218 | [6 empty] | 40651 | 29958 | 3 | 0 | 0 | 9.47 | 5533
TS5500Shv | MW\34\004\A | MW | 34 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-08-05 22:20 | 2020-08-06 13:17 | 18232.25 | [6 empty] | 18232 | 13320 | 1.34 | 0 | 0 | 10.71 | 5370
DRE1 | RS\08\003\D | RS | 8 | 3 | D | 6 DL | 100 | 100 | 100 | 2020-08-06 04:04 | 2020-08-09 13:51 | 285652.3356 |  |  |  | 12781 | 285652 | 242836 |  |  | 0 | 24.13 | 0 | 6.21 | 5874.93
TS5500Shv | GG\11\012\B | GG | 11 | 12 | B | 1 Prestrip - Thick | 31.5271 | 31.5271 | 31.5271 | 2020-08-06 13:17 | 2020-08-13 11:54 | 178980.5792 | 178981 | [7 empty] | 0 | 0 | 20.74 | 10.16 | 5506.24
TS5500Exc | MW\30\010\D | MW | 30 | 10 | D | 8 Coal Mining | 70.5 | 0 | 70.5 | 2020-08-07 02:39 | 2020-08-08 12:20 | 42448.2511 | [6 empty] | 42448 | 32200 | 3.22 | 0 | 0 | 5.53 | 5926
DRE2 | BW\30\006\D | BW | 30 | 6 | D | 6 DL | 100 | 100 | 100 | 2020-08-08 01:53 | 2020-08-11 00:08 | 236284.9833 |  |  |  | 10572 | 236285 | 200869 |  |  | 0 | 21.15 | 0 | 5.83 | 5901.08
TS5500Exc | MW\30\011\D | MW | 30 | 11 | D | 7 PostStrip | 45.2055 | 0 | 45.2055 | 2020-08-08 12:20 | 2020-08-08 23:44 | 10074.6361 |  |  | 10075 | [5 empty] | 0 | 0 | 0 | 5.61 | 5918.8
TS5500Exc | MW\30\011\D | MW | 30 | 11 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-08-08 23:44 | 2020-08-09 09:55 | 12822.443 | [6 empty] | 12822 | 9734 | 2.28 | 0 | 0 | 5.61 | 5919
TS Fleet 5 | MW\34\006\A | MW | 34 | 6 | A | 1 Prestrip - Thick | 93.2083 | 93.2083 | 93.2083 | 2020-08-09 01:29 | 2020-08-13 18:03 | 211177.9027 | 211178 | [7 empty] | 0 | 0 | 21.62 | 10.8 | 5399.89
TS5500Exc | MW\33\008\B | MW | 33 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-08-09 09:55 | 2020-08-11 20:08 | 51486.701 | 51487 | [7 empty] | 0 | 0 | 5.17 | 10.06 | 5464.53
DRE1 | RS\08\004\D | RS | 8 | 4 | D | 6 DL | 100 | 100 | 100 | 2020-08-09 13:51 | 2020-08-12 19:41 | 271858.2422 |  |  |  | 12164 | 271858 | 231110 |  |  | 0 | 24.33 | 0 | 6.94 | 5811.31
DRE2 | BW\30\005\D | BW | 30 | 5 | D | 6 DL | 100 | 100 | 100 | 2020-08-11 00:08 | 2020-08-12 16:13 | 134828.1736 |  |  |  | 4451 | 134828 | 81636 |  |  | 0 | 22.1 | 0 | 5.99 | 5887.61
TS5500Exc | MW\33\008\B | MW | 33 | 8 | B | 8 Coal Mining | 87.6 | 0 | 87.6 | 2020-08-11 20:08 | 2020-08-12 23:00 | 33841.1591 | [6 empty] | 33841 | 24876 | 2.49 | 0 | 0 | 10.06 | 5465
DRE2 | BW\30\009\D | BW | 30 | 9 | D | 6 DL | 100 | 100 | 100 | 2020-08-12 16:13 | 2020-08-15 12:27 | 229522.9102 |  |  |  | 10269 | 229523 | 195120 |  |  | 0 | 20.54 | 0 | 5.54 | 5925.61
DRE1 | RS\08\005\D | RS | 8 | 5 | D | 6 DL | 100 | 100 | 100 | 2020-08-12 19:41 | 2020-08-16 01:27 | 271690.178 |  |  |  | 12156 | 271690 | 230967 |  |  | 0 | 24.31 | 0 | 7.06 | 5800.42
TS5500Exc | MW\33\009\B | MW | 33 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-08-12 23:00 | 2020-08-14 12:54 | 33516.1649 | 33516 | [7 empty] | 0 | 0 | 3.36 | 9.62 | 5518.8
TS5500Shv | MW\30\011\D | MW | 30 | 11 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-08-13 11:54 | 2020-08-13 22:05 | 12413.2162 | [6 empty] | 12413 | 9424 | 2.2 | 0 | 0 | 5.61 | 5919
TS Fleet 5 | MW\34\007\A | MW | 34 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-08-13 18:03 | 2020-08-20 00:59 | 283142.243 | 283142 | [7 empty] | 0 | 0 | 27.93 | 10.77 | 5422.92
TS5500Shv | MW\33\008\B | MW | 33 | 8 | B | 8 Coal Mining | 12.4 | 0 | 12.4 | 2020-08-13 22:05 | 2020-08-14 02:02 | 4811.3322 | [6 empty] | 4811 | 3537 | 0.35 | 0 | 0 | 10.06 | 5465
TS5500Shv | RS\08\003\D | RS | 8 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-08-14 02:02 | 2020-08-16 06:45 | 64298.5251 | [6 empty] | 64299 | 47213 | 4.45 | 0 | 0 | 6.21 | 5875
TS5500Exc | MW\33\009\B | MW | 33 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-08-14 12:54 | 2020-08-15 20:21 | 39615.7964 | [6 empty] | 39616 | 29232 | 2.93 | 0 | 0 | 9.62 | 5519
PH4100XPC#1 | GG\10\007\X1 | GG | 10 | 7 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-08-15 02:43 | 2020-08-23 10:29 | 448731.5764 | 448732 | [7 empty] | 0 | 0 | 43.63 | 10.83 | 5407.42
DRE2 | BW\30\010\D | BW | 30 | 10 | D | 6 DL | 100 | 100 | 100 | 2020-08-15 12:27 | 2020-08-18 08:44 | 229711.869 |  |  |  | 10278 | 229712 | 195281 |  |  | 0 | 20.55 | 0 | 5.75 | 5907.38
TS5500Exc | RS\08\004\D | RS | 8 | 4 | D | 8 Coal Mining | 60.8 | 0 | 60.8 | 2020-08-15 20:21 | 2020-08-17 02:31 | 38015.5019 | [6 empty] | 38016 | 27614 | 2.76 | 0 | 0 | 6.94 | 5811
DRE1 | RS\08\006\D | RS | 8 | 6 | D | 6 DL | 100 | 100 | 100 | 2020-08-16 01:27 | 2020-08-19 13:55 | 295015.5196 |  |  |  | 15168 | 295016 | 237630 |  |  | 0 | 25.28 | 0 | 6.86 | 5818.02
TS5500Shv | GG\10\006\X1 | GG | 10 | 6 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-08-16 06:45 | 2020-08-16 18:23 | 14170.9188 | [6 empty] | 14171 | 10414 | 1 | 0 | 0 | 11.82 | 5291
TS5500Shv | RS\08\004\D | RS | 8 | 4 | D | 8 Coal Mining | 39.2 | 0 | 39.2 | 2020-08-16 18:23 | 2020-08-17 14:30 | 24539.1615 | [6 empty] | 24539 | 17825 | 1.78 | 0 | 0 | 6.94 | 5811
TS5500Exc | RS\08\005\D | RS | 8 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-08-17 02:31 | 2020-08-18 03:17 | 31181.3065 | [6 empty] | 31181 | 22630 | 2.26 | 0 | 0 | 7.06 | 5800
TS5500Shv | RS\08\005\D | RS | 8 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-08-17 14:30 | 2020-08-18 15:15 | 30186.1584 | [6 empty] | 30186 | 21908 | 2.19 | 0 | 0 | 7.06 | 5800
TS5500Exc | MW\33\010\X | MW | 33 | 10 | X | 8 Coal Mining | 100 | 0 | 100 | 2020-08-18 03:17 | 2020-08-19 00:26 | 26640.0271 | [6 empty] | 26640 | 19431 | 1.32 | 0 | 0 | 12.21 | 5216
DRE2 | BW\30\011\D | BW | 30 | 11 | D | 6 DL | 100 | 100 | 100 | 2020-08-18 08:44 | 2020-08-21 09:30 | 244755.4152 |  |  |  | 10951 | 244755 | 208069 |  |  | 0 | 21.88 | 0 | 5.88 | 5895.63
TS5500Shv | MW\34\005\B | MW | 34 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-08-18 15:15 | 2020-08-19 04:43 | 16418.2303 | [6 empty] | 16418 | 12108 | 1.22 | 0 | 0 | 9.18 | 5566
TS5500Exc | MW\33\010\A | MW | 33 | 10 | A | 1 Prestrip - Thick | 11.1417 | 11.1417 | 11.1417 | 2020-08-19 00:26 | 2020-08-20 11:39 | 31143.0971 | 31143 | [7 empty] | 0 | 0 | 2.16 | 11.39 | 5396.07
TS5500Shv | MW\34\006\A | MW | 34 | 6 | A | 8 Coal Mining | 7.4 | 0 | 7.4 | 2020-08-19 04:43 | 2020-08-19 07:05 | 2882.6589 | [6 empty] | 2883 | 2120 | 0.21 | 0 | 0 | 10.8 | 5400
TS5500Shv | GG\11\013\X2 | GG | 11 | 13 | X2 | 1 Prestrip - Thick | 31.941 | 0 | 31.941 | 2020-08-19 07:05 | 2020-08-22 08:39 | 78594.0052 | 78594 | [7 empty] | 0 | 0 | 12.4 | 0 | 0
DRE1 | RS\08\007\D | RS | 8 | 7 | D | 6 DL | 100 | 100 | 100 | 2020-08-19 13:55 | 2020-08-23 01:27 | 291813.5264 |  |  |  | 15003 | 291814 | 235051 |  |  | 0 | 25.02 | 0 | 6.97 | 5807.91
TS Fleet 5 | MW\33\010\A | MW | 33 | 10 | A | 1 Prestrip - Thick | 88.8583 | 88.8583 | 88.8583 | 2020-08-20 00:59 | 2020-08-25 13:23 | 248376.3666 | 248376 | [7 empty] | 0 | 0 | 17.26 | 11.39 | 5396.07
TS5500Exc | MW\34\003\A | MW | 34 | 3 | A | 8 Coal Mining | 45.2 | 0 | 45.2 | 2020-08-20 11:39 | 2020-08-20 18:54 | 9147.8867 | [6 empty] | 9148 | 6637 | 0.66 | 0 | 0 | 11.87 | 5286
TS5500Exc | MW\34\004\A | MW | 34 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-08-20 18:54 | 2020-08-21 09:51 | 18833.3131 | [6 empty] | 18833 | 13759 | 1.39 | 0 | 0 | 10.71 | 5370
DRE2 | DT\30\001\D | DT | 30 | 1 | D | 6 DL | 100 | 0 | 100 | 2020-08-21 09:30 | 2020-08-26 22:35 | 447689.8441 |  |  |  | 25551 | 447690 | 339463 |  |  | 0 | 30 | 0 | 6.14 | 5873.3
TS5500Exc | MW\34\005\B | MW | 34 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-08-21 09:51 | 2020-08-21 23:19 | 16959.4907 | [6 empty] | 16959 | 12507 | 1.26 | 0 | 0 | 9.18 | 5566
TS5500Exc | MW\34\006\A | MW | 34 | 6 | A | 8 Coal Mining | 92.6 | 0 | 92.6 | 2020-08-21 23:19 | 2020-08-23 03:49 | 35896.4272 | [6 empty] | 35896 | 26399 | 2.65 | 0 | 0 | 10.8 | 5400
TS5500Shv | RS\08\006\D | RS | 8 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-08-22 08:39 | 2020-08-24 11:31 | 62030.3054 | [6 empty] | 62030 | 45162 | 4.52 | 0 | 0 | 6.86 | 5818
PH4100A | GG\10\006\X2 | GG | 10 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 57.4031 | 2020-08-22 19:02 | 2020-08-24 04:59 | 56432.4038 | 56432 | [7 empty] | 0 | 0 | 5.48 | 0 | 0
TS6060#1 | GG\11\004\X1 | GG | 11 | 4 | X1 | 8 Coal Mining | 100 | 0 | 15.1 | 2020-08-22 20:05 | 2020-08-22 22:00 | 2593.8695 | [6 empty] | 2594 | 1930 | 0.19 | 0 | 0 | 9.92 | 5401
TS6060#1 | BW\30\006\D | BW | 30 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-08-22 22:00 | 2020-08-24 21:06 | 63748.4338 | [6 empty] | 63748 | 48051 | 4.81 | 0 | 0 | 5.83 | 5901
DRE1 | RS\08\008\D | RS | 8 | 8 | D | 6 DL | 100 | 100 | 100 | 2020-08-23 01:27 | 2020-08-25 02:29 | 171298.5101 |  |  |  | 6435 | 171299 | 97331 |  |  | 0 | 25.82 | 0 | 7.01 | 5803.31
TS5500Exc | RS\08\007\D | RS | 8 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-08-23 03:49 | 2020-08-25 04:17 | 61045.0244 | [6 empty] | 61045 | 44476 | 4.45 | 0 | 0 | 6.97 | 5808
PH4100XPC#1 | GG\10\006\X2 | GG | 10 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 42.5969 | 2020-08-23 10:29 | 2020-08-24 04:59 | 41876.6302 | 41877 | [7 empty] | 0 | 0 | 4.06 | 0 | 0
PH4100XPC#1 | GG\10\008\X1 | GG | 10 | 8 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-08-24 04:59 | 2020-08-31 18:20 | 404059.3453 | 404059 | [7 empty] | 0 | 0 | 39 | 10.33 | 5472.63
PH4100A | GG\11\005\B | GG | 11 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-08-24 04:59 | 2020-08-24 06:43 | 2872.254 | 2872 | [7 empty] | 0 | 0 | 0.29 | 11.88 | 5282.96
PH4100A | GG\11\006\X1 | GG | 11 | 6 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-08-24 06:43 | 2020-09-06 20:35 | 543186.3898 | 543186 | [7 empty] | 0 | 0 | 47.84 | 10.87 | 5362.24
TS5500Shv | GG\10\007\X1 | GG | 10 | 7 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-08-24 11:31 | 2020-08-25 01:08 | 16608.1648 | [6 empty] | 16608 | 12275 | 1.21 | 0 | 0 | 10.83 | 5407
TS6060#1 | BW\30\007\D | BW | 30 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-08-24 21:06 | 2020-08-26 20:10 | 63704.8134 | [6 empty] | 63705 | 48133 | 4.81 | 0 | 0 | 5.6 | 5922
TS5500Shv | GG\10\007\X2 | GG | 10 | 7 | X2 | 1 Prestrip - Thick | 81.1329 | 0 | 81.1329 | 2020-08-25 01:08 | 2020-08-28 04:35 | 80886.5413 | 80887 | [7 empty] | 0 | 0 | 7.98 | 0 | 0
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2020-08-25 02:29 | 2020-08-27 02:29
TS5500Exc | RS\13\007\X | RS | 13 | 7 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-08-25 04:17 | 2020-08-25 13:15 | 11302.6938 | [6 empty] | 11303 | 8068 | 0.63 | 0 | 0 | 10.41 | 5326
TS5500Exc | MW\34\006\B | MW | 34 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-08-25 13:15 | 2020-08-27 22:38 | 50736.5292 | 50737 | [7 empty] | 0 | 0 | 5.09 | 8.83 | 5597.74
TS Fleet 5 | MW\34\003\B | MW | 34 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-08-25 13:23 | 2020-08-25 23:39 | 19257.8156 | 19258 | [7 empty] | 0 | 0 | 1.94 | 9.55 | 5563.48
TS Fleet 5 | MW\34\004\B | MW | 34 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-08-25 23:39 | 2020-08-26 17:21 | 33224.0441 | 33224 | [7 empty] | 0 | 0 | 3.34 | 8.96 | 5594.63
TS Fleet 5 | MW\34\008\A | MW | 34 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-08-26 17:21 | 2020-09-03 23:58 | 372586.1606 | 372586 | [7 empty] | 0 | 0 | 37.36 | 11.95 | 5333.63
TS6060#1 | MW\33\010\A | MW | 33 | 10 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-08-26 20:10 | 2020-08-28 20:54 | 65937.4225 | [6 empty] | 65937 | 48422 | 3.46 | 0 | 0 | 11.39 | 5396
DRE2 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 10d 00:00 |  | 10d 00:00 | 2020-08-26 22:35 | 2020-09-05 22:35
DRE1 | RS\09\003\D | RS | 9 | 3 | D | 6 DL | 100 | 100 | 100 | 2020-08-27 02:29 | 2020-08-30 14:02 | 291808.6579 |  |  |  | 13056 | 291809 | 248070 |  |  | 0 | 24.49 | 0 | 6.23 | 5872.94
TS5500Exc | DT\30\001\D | DT | 30 | 1 | D | 8 Coal Mining | 64.1 | 0 | 64.1 | 2020-08-27 22:38 | 2020-08-29 11:35 | 46551.8152 | [6 empty] | 46552 | 35258 | 3 | 0 | 0 | 6.14 | 5873
TS5500Shv | DT\30\001\D | DT | 30 | 1 | D | 8 Coal Mining | 35.9 | 0 | 35.9 | 2020-08-28 04:35 | 2020-08-29 01:59 | 26095.7507 | [6 empty] | 26096 | 19765 | 1.68 | 0 | 0 | 6.14 | 5873
TS6060#1 | BW\30\008\D | BW | 30 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-08-28 20:54 | 2020-08-30 19:31 | 63109.6797 | [6 empty] | 63110 | 47760 | 4.78 | 0 | 0 | 5.47 | 5932
TS5500Shv | RS\08\008\D | RS | 8 | 8 | D | 7 PostStrip | 100 | 0 | 100 | 2020-08-29 01:59 | 2020-08-30 01:14 | 24925.13 |  |  | 24925 | [5 empty] | 0 | 0 | 0 | 7.01 | 5803.31
TS5500Exc | MW\33\010\B | MW | 33 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-08-29 11:35 | 2020-08-31 04:57 | 36585.7455 | 36586 | [7 empty] | 0 | 0 | 2.64 | 8.98 | 5599.94
TS5500Shv | RS\08\008\D | RS | 8 | 8 | D | 8 Coal Mining | 13.5 | 0 | 13.5 | 2020-08-30 01:14 | 2020-08-30 04:34 | 4059.6919 | [6 empty] | 4060 | 2959 | 0.6 | 0 | 0 | 7.01 | 5803
TS5500Shv | RS\13\007\X | RS | 13 | 7 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-08-30 04:34 | 2020-08-30 13:32 | 10941.9695 | [6 empty] | 10942 | 7810 | 0.61 | 0 | 0 | 10.41 | 5326
TS5500Shv | MW\34\003\B | MW | 34 | 3 | B | 8 Coal Mining | 66.3 | 0 | 66.3 | 2020-08-30 13:32 | 2020-08-31 05:04 | 18934.741 | [6 empty] | 18935 | 13943 | 1.4 | 0 | 0 | 9.55 | 5563
DRE1 | RS\09\004\D | RS | 9 | 4 | D | 6 DL | 100 | 100 | 100 | 2020-08-30 14:02 | 2020-09-02 19:29 | 270582.3319 |  |  |  | 12107 | 270582 | 230025 |  |  | 0 | 24.21 | 0 | 6.93 | 5812.29
TS6060#1 | BW\30\009\D | BW | 30 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-08-30 19:31 | 2020-09-01 16:03 | 60258.3285 | [6 empty] | 60258 | 45642 | 4.56 | 0 | 0 | 5.54 | 5926
TS5500Exc | RS\08\008\D | RS | 8 | 8 | D | 8 Coal Mining | 86.5 | 0 | 86.5 | 2020-08-31 04:57 | 2020-09-01 01:35 | 25984.1847 | [6 empty] | 25984 | 18939 | 3.81 | 0 | 0 | 7.01 | 5803
TS5500Shv | RS\09\003\D | RS | 9 | 3 | D | 8 Coal Mining | 36.8 | 0 | 36.8 | 2020-08-31 05:04 | 2020-09-01 00:39 | 23885.3799 | [6 empty] | 23885 | 17538 | 1.64 | 0 | 0 | 6.23 | 5873
PH4100XPC#1 | GG\10\007\X2 | GG | 10 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 18.8671 | 2020-08-31 18:20 | 2020-09-01 02:39 | 18809.8377 | 18810 | [7 empty] | 0 | 0 | 1.86 | 0 | 0
TS5500Shv | GG\10\008\X1 | GG | 10 | 8 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-09-01 00:39 | 2020-09-01 13:17 | 15395.5605 | [6 empty] | 15396 | 11417 | 1.13 | 0 | 0 | 10.33 | 5473
TS5500Exc | RS\09\003\D | RS | 9 | 3 | D | 8 Coal Mining | 63.2 | 0 | 63.2 | 2020-09-01 01:35 | 2020-09-02 10:06 | 40972.3766 | [6 empty] | 40972 | 30085 | 2.82 | 0 | 0 | 6.23 | 5873
PH4100XPC#1 | GG\10\009\X1 | GG | 10 | 9 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-01 02:39 | 2020-09-08 03:48 | 377078.1203 | 377078 | [7 empty] | 0 | 0 | 36.67 | 11.15 | 5408.22
TS5500Shv | MW\34\004\B | MW | 34 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-09-01 13:17 | 2020-09-02 06:21 | 20806.1867 | [6 empty] | 20806 | 15360 | 1.54 | 0 | 0 | 8.96 | 5595
TS6060#1 | BW\30\010\D | BW | 30 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-09-01 16:03 | 2020-09-03 12:49 | 60581.0882 | [6 empty] | 60581 | 46034 | 4.6 | 0 | 0 | 5.75 | 5907
TS5500Shv | MW\34\006\B | MW | 34 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-09-02 06:21 | 2020-09-02 23:11 | 20531.8772 | [6 empty] | 20532 | 15178 | 1.52 | 0 | 0 | 8.83 | 5598
TS5500Exc | MW\33\010\B | MW | 33 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-09-02 10:06 | 2020-09-04 04:26 | 53322.1821 | [6 empty] | 53322 | 39571 | 2.88 | 0 | 0 | 8.98 | 5600
DRE1 | RS\09\005\D | RS | 9 | 5 | D | 6 DL | 100 | 100 | 100 | 2020-09-02 19:29 | 2020-09-06 01:58 | 274110.2316 |  |  |  | 12264 | 274110 | 233024 |  |  | 0 | 24.53 | 0 | 7.06 | 5800.07
TS5500Shv | MW\34\007\A | MW | 34 | 7 | A | 8 Coal Mining | 51 | 0 | 51 | 2020-09-02 23:11 | 2020-09-03 18:28 | 23507.6671 | [6 empty] | 23508 | 17307 | 1.75 | 0 | 0 | 10.77 | 5423
TS6060#1 | BW\30\011\D | BW | 30 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-09-03 12:49 | 2020-09-05 09:38 | 60671.3049 | [6 empty] | 60671 | 46139 | 4.61 | 0 | 0 | 5.88 | 5896
TS5500Shv | GG\11\018\X2 | GG | 11 | 18 | X2 | 1 Prestrip - Thick | 32.1671 | 0 | 32.1671 | 2020-09-03 18:28 | 2020-09-06 15:49 | 74217.8921 | 74218 | [7 empty] | 0 | 0 | 9.95 | 0 | 0
TS Fleet 5 | MW\34\009\A | MW | 34 | 9 | A | 1 Prestrip - Thick | 89.0993 | 89.0993 | 89.0993 | 2020-09-03 23:58 | 2020-09-13 04:42 | 414119.9004 | 414120 | [7 empty] | 0 | 0 | 41.04 | 12.24 | 5314.89
TS5500Exc | RS\09\004\D | RS | 9 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-09-04 04:26 | 2020-09-06 06:05 | 62526.8392 | [6 empty] | 62527 | 45419 | 4.54 | 0 | 0 | 6.93 | 5812
TS6060#1 | BW\30\005\D | BW | 30 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2020-09-05 09:38 | 2020-09-06 10:02 | 25177.763 |  |  | 25178 | [5 empty] | 0 | 0 | 0 | 5.99 | 5887.61
DRE2 | GG\09\012\B | GG | 9 | 12 | B | 6 DL | 100 | 0 | 100 | 2020-09-05 22:35 | 2020-09-08 10:17 | 200810.1743 |  |  |  |  | 200810 | 167342 |  |  | 0 | 16.78 | 0 | 10.09 | 5517.08
DRE1 | RS\09\006\D | RS | 9 | 6 | D | 6 DL | 100 | 100 | 100 | 2020-09-06 01:58 | 2020-09-09 14:31 | 295362.6023 |  |  |  | 15186 | 295363 | 237910 |  |  | 0 | 25.31 | 0 | 6.92 | 5812.59
TS5500Exc | RS\09\005\D | RS | 9 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-09-06 06:05 | 2020-09-08 07:03 | 61684.7407 | [6 empty] | 61685 | 44805 | 4.48 | 0 | 0 | 7.06 | 5800
TS6060#1 | BW\30\005\D | BW | 30 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-09-06 10:02 | 2020-09-07 09:40 | 31967.8288 | [6 empty] | 31968 | 24057 | 4.84 | 0 | 0 | 5.99 | 5888
TS5500Shv | MW\34\008\A | MW | 34 | 8 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-09-06 15:49 | 2020-09-08 06:02 | 46621.1173 | [6 empty] | 46621 | 34127 | 3.44 | 0 | 0 | 11.95 | 5334
PH4100A | GG\11\007\X1 | GG | 11 | 7 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-06 20:35 | 2020-09-18 16:46 | 470006.5205 | 470007 | [7 empty] | 0 | 0 | 46.04 | 10.75 | 5414.73
TS6060#1 | RS\13\006\A | RS | 13 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-07 09:40 | 2020-09-15 12:09 | 200683.6784 | 200684 | [7 empty] | 0 | 0 | 20.09 | 15.93 | 4966.71
PH4100XPC#1 | GG\10\008\X2 | GG | 10 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2020-09-08 03:48 | 2020-09-09 23:29 | 98877.175 | 98877 | [7 empty] | 0 | 0 | 9.87 | 0 | 0
TS5500Shv | GG\11\006\X1 | GG | 11 | 6 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-09-08 06:02 | 2020-09-08 20:25 | 17525.9723 | [6 empty] | 17526 | 12953 | 1.28 | 0 | 0 | 10.87 | 5362
TS5500Exc | MW\34\003\B | MW | 34 | 3 | B | 8 Coal Mining | 33.7 | 0 | 33.7 | 2020-09-08 07:03 | 2020-09-08 14:41 | 9622.3983 | [6 empty] | 9622 | 7086 | 0.71 | 0 | 0 | 9.55 | 5563
DRE2 | GG\09\011\B | GG | 9 | 11 | B | 6 DL | 100 | 0 | 100 | 2020-09-08 10:17 | 2020-09-11 02:35 | 216289.2262 |  |  |  |  | 216289 | 166376 |  |  | 0 | 16.69 | 0 | 10.09 | 5509.83
TS5500Exc | MW\34\004\B | MW | 34 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-09-08 14:41 | 2020-09-09 07:45 | 21492.105 | [6 empty] | 21492 | 15866 | 1.59 | 0 | 0 | 8.96 | 5595
TS5500Shv | GG\10\009\X1 | GG | 10 | 9 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-09-08 20:25 | 2020-09-09 08:47 | 15091.6168 | [6 empty] | 15092 | 11123 | 1.1 | 0 | 0 | 11.15 | 5408
TS5500Exc | MW\34\006\B | MW | 34 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-09-09 07:45 | 2020-09-10 00:36 | 21208.7522 | [6 empty] | 21209 | 15678 | 1.57 | 0 | 0 | 8.83 | 5598
TS5500Shv | GG\10\009\X2 | GG | 10 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 43.0101 | 2020-09-09 08:47 | 2020-09-11 00:14 | 42286.3613 | 42286 | [7 empty] | 0 | 0 | 4.2 | 0 | 0
DRE1 | RS\09\007\D | RS | 9 | 7 | D | 6 DL | 100 | 100 | 100 | 2020-09-09 14:31 | 2020-09-12 21:39 | 276435.3254 |  |  |  | 12368 | 276435 | 235001 |  |  | 0 | 24.74 | 0 | 7.11 | 5795.34
PH4100XPC#1 | GG\10\009\X2 | GG | 10 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 56.9899 | 2020-09-09 23:29 | 2020-09-11 00:14 | 56030.9477 | 56031 | [7 empty] | 0 | 0 | 5.57 | 0 | 0
TS5500Exc | RS\09\006\D | RS | 9 | 6 | D | 8 Coal Mining | 99.4 | 0 | 99.4 | 2020-09-10 00:36 | 2020-09-12 01:29 | 61588.6078 | [6 empty] | 61589 | 44875 | 4.49 | 0 | 0 | 6.92 | 5813
TS5500Shv | GG\09\012\B | GG | 9 | 12 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-09-11 00:14 | 2020-09-12 16:43 | 49369.3745 | [6 empty] | 49369 | 36217 | 3.63 | 0 | 0 | 10.09 | 5517
PH4100XPC#1 | GG\10\011\X2 | GG | 10 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 95.6817 | 2020-09-11 00:14 | 2020-09-18 04:28 | 396866.3282 | 396866 | [7 empty] | 0 | 0 | 47.24 | 0 | 0
DRE2 | GG\09\010\B | GG | 9 | 10 | B | 6 DL | 100 | 0 | 100 | 2020-09-11 02:35 | 2020-09-13 12:30 | 194820.9582 |  |  |  |  | 194821 | 162351 |  |  | 0 | 17.09 | 0 | 10.55 | 5461.04
TS5500Exc | MW\34\007\A | MW | 34 | 7 | A | 8 Coal Mining | 49 | 0 | 49 | 2020-09-12 01:29 | 2020-09-12 19:24 | 22558.4635 | [6 empty] | 22558 | 16608 | 1.68 | 0 | 0 | 10.77 | 5423
TS5500Shv | GG\09\011\B | GG | 9 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-09-12 16:43 | 2020-09-14 09:48 | 50096.6382 | [6 empty] | 50097 | 36751 | 3.68 | 0 | 0 | 10.09 | 5510
TS5500Exc | MW\34\007\B | MW | 34 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-12 19:24 | 2020-09-16 00:35 | 68269.1803 | 68269 | [7 empty] | 0 | 0 | 6.87 | 9.46 | 5527.99
DRE1 | RS\09\008\D | RS | 9 | 8 | D | 6 DL | 100 | 100 | 100 | 2020-09-12 21:39 | 2020-09-14 16:14 | 148764.1414 |  |  |  | 5615 | 148764 | 84620 |  |  | 0 | 25.45 | 0 | 7.12 | 5791.48
TS Fleet 5 | MW\34\010\X | MW | 34 | 10 | X | 1 Prestrip - Thick | 84.9401 | 84.9401 | 84.9401 | 2020-09-13 04:42 | 2020-09-23 13:21 | 466439.5642 | 466440 | [7 empty] | 0 | 0 | 32.22 | 12.18 | 5223.28
DRE2 | GG\09\009\B | GG | 9 | 9 | B | 6 DL | 100 | 0 | 100 | 2020-09-13 12:30 | 2020-09-16 05:34 | 218859.8772 |  |  |  |  | 218860 | 182383 |  |  | 0 | 18.13 | 0 | 10.71 | 5443.73
TS5500Shv | GG\09\010\B | GG | 9 | 10 | B | 8 Coal Mining | 69.4 | 0 | 69.4 | 2020-09-14 09:48 | 2020-09-15 14:20 | 34779.3154 | [6 empty] | 34779 | 25441 | 2.55 | 0 | 0 | 10.55 | 5461
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2020-09-14 16:14 | 2020-09-16 16:14
TS6060#1 | GG\09\010\B | GG | 9 | 10 | B | 8 Coal Mining | 100 | 0 | 30.6 | 2020-09-15 12:09 | 2020-09-15 23:28 | 15301.5126 | [6 empty] | 15302 | 11193 | 1.12 | 0 | 0 | 10.55 | 5461
TS5500Shv | RS\09\006\D | RS | 9 | 6 | D | 8 Coal Mining | 0.6 | 0 | 0.6 | 2020-09-15 14:20 | 2020-09-15 14:36 | 340.8378 | [6 empty] | 341 | 248 | 0.02 | 0 | 0 | 6.92 | 5813
TS5500Shv | RS\13\006\A | RS | 13 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-09-15 14:36 | 2020-09-16 11:22 | 25306.9537 | [6 empty] | 25307 | 17316 | 1.73 | 0 | 0 | 15.93 | 4967
TS6060#1 | RS\13\007\A | RS | 13 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-15 23:28 | 2020-09-25 23:07 | 247271.5079 | 247272 | [7 empty] | 0 | 0 | 21 | 16.85 | 4900.95
TS5500Exc | RS\13\006\A | RS | 13 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-09-16 00:35 | 2020-09-16 21:21 | 26141.2488 | [6 empty] | 26141 | 17887 | 1.79 | 0 | 0 | 15.93 | 4967
DRE2 | GG\09\008\B | GG | 9 | 8 | B | 6 DL | 100 | 0 | 100 | 2020-09-16 05:34 | 2020-09-18 23:59 | 223404.2067 |  |  |  |  | 223404 | 186170 |  |  | 0 | 18.82 | 0 | 10.72 | 5439.13
TS5500Shv | GG\09\009\B | GG | 9 | 9 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2020-09-16 11:22 | 2020-09-17 07:27 | 24502.8607 | [6 empty] | 24503 | 17887 | 1.79 | 0 | 0 | 10.71 | 5444
DRE1 | MW\31\001\D | MW | 31 | 1 | D | 6 DL | 100 | 100 | 100 | 2020-09-16 16:14 | 2020-09-20 04:34 | 294576.1267 |  |  |  | 20950 | 294576 | 211825 |  |  | 0 | 35.71 | 0 | 7.61 | 5744.81
TS5500Exc | RS\09\007\D | RS | 9 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-09-16 21:21 | 2020-09-18 20:55 | 59929.6944 | [6 empty] | 59930 | 43592 | 4.36 | 0 | 0 | 7.11 | 5795
TS5500Shv | RS\09\008\D | RS | 9 | 8 | D | 7 PostStrip | 62.311 | 0 | 62.311 | 2020-09-17 07:27 | 2020-09-17 20:17 | 13748.2044 |  |  | 13748 | [5 empty] | 0 | 0 | 0 | 7.12 | 5791.48
TS5500Shv | GG\11\019\B | GG | 11 | 19 | B | 1 Prestrip - Thick | 4.8988 | 4.8988 | 4.8988 | 2020-09-17 20:17 | 2020-09-18 12:21 | 17242.0474 | 17242 | [7 empty] | 0 | 0 | 1.68 | 11.44 | 5409.49
PH4100XPC#1 | GG\10\010\B | GG | 10 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-18 04:28 | 2020-09-28 05:41 | 553417.1818 | 553417 | [7 empty] | 0 | 0 | 60.06 | 10.27 | 5483.01
TS5500Shv | GG\12\002\X1 | GG | 12 | 2 | X1 | 1 Prestrip - Thick | 31.9822 | 31.9822 | 31.9822 | 2020-09-18 12:21 | 2020-10-01 12:12 | 333351.9001 | 333352 | [7 empty] | 0 | 0 | 26.07 | 11.05 | 5302.72
PH4100A | GG\11\008\X1 | GG | 11 | 8 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-18 16:46 | 2020-09-29 14:55 | 431962.5157 | 431963 | [7 empty] | 0 | 0 | 40.95 | 9.99 | 5502.6
TS5500Exc | RS\09\008\D | RS | 9 | 8 | D | 7 PostStrip | 37.689 | 0 | 37.689 | 2020-09-18 20:55 | 2020-09-19 06:19 | 8315.6506 |  |  | 8316 | [5 empty] | 0 | 0 | 0 | 7.12 | 5791.48
DRE2 | GG\09\007\B | GG | 9 | 7 | B | 6 DL | 100 | 0 | 100 | 2020-09-18 23:59 | 2020-09-21 23:10 | 239408.7304 |  |  |  |  | 239409 | 199507 |  |  | 0 | 19.52 | 0 | 10.8 | 5395.5
TS5500Exc | RS\09\008\D | RS | 9 | 8 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-09-19 06:19 | 2020-09-19 16:48 | 13201.3831 | [6 empty] | 13201 | 9612 | 2.19 | 0 | 0 | 7.12 | 5791
TS5500Exc | MW\34\007\B | MW | 34 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-09-19 16:48 | 2020-09-21 00:59 | 40528.5388 | [6 empty] | 40529 | 29867 | 2.99 | 0 | 0 | 9.46 | 5528
DRE1 | MW\31\002\D | MW | 31 | 2 | D | 6 DL | 100 | 0 | 100 | 2020-09-20 04:34 | 2020-09-25 10:50 | 441061.9717 |  |  |  | 31368 | 441062 | 317160 |  |  | 0 | 35 | 0 | 7.4 | 5763.68
TS5500Exc | MW\31\001\D | MW | 31 | 1 | D | 8 Coal Mining | 16.6 | 0 | 16.6 | 2020-09-21 00:59 | 2020-09-21 06:20 | 6753.4693 | [6 empty] | 6753 | 5026 | 0.78 | 0 | 0 | 7.61 | 5745
TS5500Exc | MW\34\008\B | MW | 34 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-21 06:20 | 2020-09-23 14:00 | 49231.4905 | 49231 | [7 empty] | 0 | 0 | 4.94 | 10.02 | 5461.78
DRE2 | GG\09\006\B | GG | 9 | 6 | B | 6 DL | 100 | 0 | 100 | 2020-09-21 23:10 | 2020-09-24 17:02 | 221567.6207 |  |  |  |  | 221568 | 192667 |  |  | 0 | 19 | 0 | 11.35 | 5313.3
TS Fleet 5 | MW\35\002\D | MW | 35 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-23 13:21 | 2020-09-24 05:46 | 30806.6501 | 30807 | [7 empty] | 0 | 0 | 4.84 | 7.05 | 5793.95
TS5500Exc | MW\34\008\B | MW | 34 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-09-23 14:00 | 2020-09-24 20:38 | 38571.8436 | [6 empty] | 38572 | 28353 | 2.84 | 0 | 0 | 10.02 | 5462
TS Fleet 5 | MW\35\003\A | MW | 35 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-24 05:46 | 2020-09-29 14:45 | 241963.996 | 241964 | [7 empty] | 0 | 0 | 23.65 | 12.08 | 5241.7
DRE2 | GG\09\005\B | GG | 9 | 5 | B | 6 DL | 100 | 100 | 100 | 2020-09-24 17:02 | 2020-09-27 02:47 | 194282.3508 |  |  |  |  | 194282 | 168941 |  |  | 0 | 16.89 | 0 | 11.35 | 5327.53
TS5500Exc | MW\34\009\A | MW | 34 | 9 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-09-24 20:38 | 2020-09-26 10:08 | 47234.0108 | [6 empty] | 47234 | 34535 | 3.46 | 0 | 0 | 12.24 | 5315
DRE1 | MW\31\003\D | MW | 31 | 3 | D | 6 DL | 100 | 100 | 100 | 2020-09-25 10:50 | 2020-09-29 03:28 | 309603.4275 |  |  |  | 15918 | 309603 | 249381 |  |  | 0 | 26.52 | 0 | 6.89 | 5807.77
TS6060#1 | GG\09\009\B | GG | 9 | 9 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2020-09-25 23:07 | 2020-09-26 19:13 | 27195.4827 | [6 empty] | 27195 | 19853 | 1.99 | 0 | 0 | 10.71 | 5444
TS5500Exc | RS\13\007\A | RS | 13 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-09-26 10:08 | 2020-09-28 09:05 | 59137.9187 | [6 empty] | 59138 | 40482 | 3.47 | 0 | 0 | 16.85 | 4901
TS6060#1 | GG\09\006\B | GG | 9 | 6 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2020-09-26 19:13 | 2020-09-27 14:45 | 26435.7503 | [6 empty] | 26436 | 19278 | 1.92 | 0 | 0 | 11.35 | 5313
DRE2 | GG\09\013\B | GG | 9 | 13 | B | 6 DL | 100 | 0 | 100 | 2020-09-27 02:47 | 2020-09-28 08:42 | 100645.9321 |  |  |  |  | 100646 | 83872 |  |  | 0 | 17.46 | 0 | 10.69 | 5467.67
TS6060#1 | GG\09\005\B | GG | 9 | 5 | B | 8 Coal Mining | 58.6 | 0 | 58.6 | 2020-09-27 14:45 | 2020-09-28 12:46 | 29808.3187 | [6 empty] | 29808 | 21728 | 2.17 | 0 | 0 | 11.35 | 5328
PH4100XPC#1 | GG\10\009\B | GG | 10 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-28 05:41 | 2020-09-29 14:22 | 73975.5577 | 73976 | [7 empty] | 0 | 0 | 7.38 | 10.42 | 5470.88
DRE2 | GG\09\018\B | GG | 9 | 18 | B | 6 DL | 100 | 0 | 100 | 2020-09-28 08:42 | 2020-09-29 16:45 | 107773.3152 |  |  |  |  | 107773 | 89811 |  |  | 0 | 17.99 | 0 | 11.11 | 5433.13
TS5500Exc | MW\34\009\B | MW | 34 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-28 09:05 | 2020-09-29 22:30 | 33099.4205 | 33099 | [7 empty] | 0 | 0 | 3.32 | 9.57 | 5518.49
TS6060#1 | GG\09\013\B | GG | 9 | 13 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2020-09-28 12:46 | 2020-09-28 21:31 | 11843.2641 | [6 empty] | 11843 | 8661 | 1.84 | 0 | 0 | 10.69 | 5468
TS6060#1 | RS\13\006\B | RS | 13 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-28 21:31 | 2020-09-30 02:22 | 29767.751 | 29768 | [7 empty] | 0 | 0 | 2.98 | 9.57 | 5518.9
DRE1 | MW\31\004\D | MW | 31 | 4 | D | 6 DL | 100 | 100 | 100 | 2020-09-29 03:28 | 2020-10-03 04:34 | 339155.9585 |  |  |  | 17437 | 339156 | 273185 |  |  | 0 | 28.98 | 0 | 6.34 | 5855.69
PH4100XPC#1 | GG\10\011\B | GG | 10 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-29 14:22 | 2020-10-01 13:50 | 107446.1017 | 107446 | [7 empty] | 0 | 0 | 10.75 | 9.95 | 5518.67
TS Fleet 5 | MW\35\004\A | MW | 35 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-29 14:45 | 2020-10-02 11:48 | 129561.9932 | 129562 | [7 empty] | 0 | 0 | 13.78 | 10.97 | 5324.01
PH4100A | GG\11\009\X1 | GG | 11 | 9 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-29 14:55 | 2020-10-09 21:51 | 406361.1186 | 406361 | [7 empty] | 0 | 0 | 38.77 | 11.04 | 5419.18
DRE2 | GG\09\019\B | GG | 9 | 19 | B | 6 DL | 100 | 0 | 100 | 2020-09-29 16:45 | 2020-10-02 12:46 | 228803.3766 |  |  |  |  | 228803 | 190669 |  |  | 0 | 18.81 | 0 | 11.67 | 5390.36
TS5500Exc | MW\31\003\D | MW | 31 | 3 | D | 8 Coal Mining | 50.5 | 0 | 50.5 | 2020-09-29 22:30 | 2020-09-30 23:44 | 31782.8444 | [6 empty] | 31783 | 23900 | 2.39 | 0 | 0 | 6.89 | 5808
TS6060#1 | GG\09\018\B | GG | 9 | 18 | B | 8 Coal Mining | 26.4 | 0 | 26.4 | 2020-09-30 02:22 | 2020-09-30 06:55 | 6167.8422 | [6 empty] | 6168 | 4500 | 0.92 | 0 | 0 | 11.11 | 5433
TS6060#1 | RS\13\007\B | RS | 13 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-09-30 06:55 | 2020-10-01 13:25 | 31469.8581 | 31470 | [7 empty] | 0 | 0 | 2.71 | 9.67 | 5526.83
TS5500Exc | RS\13\006\B | RS | 13 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-09-30 23:44 | 2020-10-02 07:35 | 40118.795 | [6 empty] | 40119 | 28501 | 2.85 | 0 | 0 | 9.57 | 5519
TS5500Shv | GG\11\007\X1 | GG | 11 | 7 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-10-01 12:12 | 2020-10-02 01:35 | 16329.8936 | [6 empty] | 16330 | 12077 | 1.2 | 0 | 0 | 10.75 | 5415
TS6060#1 | RS\14\003\X | RS | 14 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-10-01 13:25 | 2020-10-08 00:12 | 152110.6789 | 152111 | [7 empty] | 0 | 0 | 23.87 | 13.52 | 5111.78
PH4100XPC#1 | GG\10\012\B | GG | 10 | 12 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-10-01 13:50 | 2020-10-11 05:35 | 535071.7632 | 535072 | [7 empty] | 0 | 0 | 59.47 | 10.1 | 5512.99
TS5500Shv | GG\11\008\X1 | GG | 11 | 8 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-10-02 01:35 | 2020-10-02 15:19 | 16734.7311 | [6 empty] | 16735 | 12440 | 1.21 | 0 | 0 | 9.99 | 5503
TS5500Exc | RS\13\007\B | RS | 13 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-10-02 07:35 | 2020-10-03 18:48 | 44343.1397 | [6 empty] | 44343 | 31448 | 2.71 | 0 | 0 | 9.67 | 5527
TS Fleet 5 | MW\35\005\B | MW | 35 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-10-02 11:48 | 2020-10-06 06:12 | 169591.6039 | 169592 | [7 empty] | 0 | 0 | 17.72 | 9.5 | 5533.23
DRE2 | GG\09\020\B | GG | 9 | 20 | B | 6 DL | 100 | 0 | 100 | 2020-10-02 12:46 | 2020-10-05 05:23 | 217360.4135 |  |  |  |  | 217360 | 181134 |  |  | 0 | 19.16 | 0 | 12.44 | 5334.28
TS5500Shv | GG\11\008\X2 | GG | 11 | 8 | X2 | 1 Prestrip - Thick | 32.1389 | 0 | 32.1389 | 2020-10-02 15:19 | 2020-10-03 21:28 | 32331.0382 | 32331 | [7 empty] | 0 | 0 | 3.16 | 0 | 0
DRE1 | MW\31\005\D | MW | 31 | 5 | D | 6 DL | 100 | 100 | 100 | 2020-10-03 04:34 | 2020-10-07 17:24 | 380199.3261 |  |  |  | 21699 | 380199 | 288288 |  |  | 0 | 30.79 | 0 | 5.92 | 5891.49
TS5500Exc | MW\31\004\D | MW | 31 | 4 | D | 8 Coal Mining | 65.2 | 0 | 65.2 | 2020-10-03 18:48 | 2020-10-05 02:15 | 39624.8884 | [6 empty] | 39625 | 29962 | 3 | 0 | 0 | 6.34 | 5856
TS5500Shv | GG\09\008\B | GG | 9 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-10-03 21:28 | 2020-10-05 17:38 | 53843.9803 | [6 empty] | 53844 | 39239 | 3.93 | 0 | 0 | 10.72 | 5439
TS5500Exc | MW\34\009\B | MW | 34 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-10-05 02:15 | 2020-10-06 09:40 | 39564.5299 | [6 empty] | 39565 | 29215 | 2.93 | 0 | 0 | 9.57 | 5518
DRE2 | GG\09\021\B | GG | 9 | 21 | B | 6 DL | 100 | 0 | 100 | 2020-10-05 05:23 | 2020-10-08 02:52 | 233699.9564 |  |  |  |  | 233700 | 194750 |  |  | 0 | 19.83 | 0 | 13.23 | 5271.29
TS5500Shv | RS\09\008\D | RS | 9 | 8 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-10-05 17:38 | 2020-10-06 04:07 | 12780.0623 | [6 empty] | 12780 | 9305 | 2.12 | 0 | 0 | 7.12 | 5791
TS5500Shv | GG\09\007\B | GG | 9 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-10-06 04:07 | 2020-10-07 23:32 | 52952.3787 | [6 empty] | 52952 | 38642 | 3.86 | 0 | 0 | 10.8 | 5396
TS Fleet 5 | MW\35\006\A | MW | 35 | 6 | A | 1 Prestrip - Thick | 90.106 | 90.106 | 90.106 | 2020-10-06 06:12 | 2020-10-10 22:02 | 209781.1226 | 209781 | [7 empty] | 0 | 0 | 21.46 | 11.25 | 5364.12
TS5500Exc | MW\34\010\X | MW | 34 | 10 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-10-06 09:40 | 2020-10-06 19:41 | 12614.348 | [6 empty] | 12614 | 9201 | 0.67 | 0 | 0 | 12.18 | 5223
TS5500Exc | MW\35\004\A | MW | 35 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-10-06 19:41 | 2020-10-07 08:44 | 16452.3557 | [6 empty] | 16452 | 11979 | 1.22 | 0 | 0 | 10.97 | 5324
TS5500Exc | MW\35\005\B | MW | 35 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-10-07 08:44 | 2020-10-07 20:18 | 14559.0983 | [6 empty] | 14559 | 10715 | 1.1 | 0 | 0 | 9.5 | 5533
DRE1 | MW\31\006\D | MW | 31 | 6 | D | 6 DL | 100 | 100 | 100 | 2020-10-07 17:24 | 2020-10-11 21:07 | 348288.6204 |  |  |  | 17907 | 348289 | 280541 |  |  | 0 | 29.78 | 0 | 5.9 | 5892.59
TS5500Exc | MW\31\005\D | MW | 31 | 5 | D | 8 Coal Mining | 29.3 | 0 | 29.3 | 2020-10-07 20:18 | 2020-10-08 09:53 | 17121.3598 | [6 empty] | 17121 | 12956 | 1.3 | 0 | 0 | 5.92 | 5891
TS5500Shv | GG\10\007\B | GG | 10 | 7 | B | 1 Prestrip - Thick | 87.7228 | 87.7228 | 87.7228 | 2020-10-07 23:32 | 2020-10-09 10:27 | 37428.4663 | 37428 | [7 empty] | 0 | 0 | 3.77 | 10.9 | 5394.11
TS6060#1 | RS\14\004\X | RS | 14 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-10-08 00:12 | 2020-10-22 09:03 | 342926.2767 | 342926 | [7 empty] | 0 | 0 | 33.96 | 13.35 | 5126.24
DRE2 | GG\09\022\B | GG | 9 | 22 | B | 6 DL | 100 | 0 | 100 | 2020-10-08 02:52 | 2020-10-10 23:28 | 230770.3179 |  |  |  |  | 230770 | 192309 |  |  | 0 | 19.35 | 0 | 14.42 | 5157.61
TS5500Exc | RS\14\003\X | RS | 14 | 3 | X | 8 Coal Mining | 61.7 | 0 | 61.7 | 2020-10-08 09:53 | 2020-10-08 16:29 | 8306.3056 | [6 empty] | 8306 | 5795 | 0.89 | 0 | 0 | 13.52 | 5112
TS5500Exc | MW\35\006\A | MW | 35 | 6 | A | 1 Prestrip - Thick | 9.894 | 9.894 | 9.894 | 2020-10-08 16:29 | 2020-10-09 18:22 | 23034.9023 | 23035 | [7 empty] | 0 | 0 | 2.36 | 11.25 | 5364.12
TS5500Shv | MW\31\001\D | MW | 31 | 1 | D | 8 Coal Mining | 83.4 | 0 | 83.4 | 2020-10-09 10:27 | 2020-10-10 14:16 | 33917.9642 | [6 empty] | 33918 | 25243 | 3.92 | 0 | 0 | 7.61 | 5745
TS5500Exc | MW\35\007\A | MW | 35 | 7 | A | 1 Prestrip - Thick | 3.5952 | 3.5952 | 3.5952 | 2020-10-09 18:22 | 2020-10-10 05:57 | 10297.1541 | 10297 | [7 empty] | 0 | 0 | 1.02 | 11.14 | 5392.5
PH4100A | GG\10\007\B | GG | 10 | 7 | B | 1 Prestrip - Thick | 100 | 12.2772 | 12.2772 | 2020-10-09 21:51 | 2020-10-10 01:00 | 5238.2624 | 5238 | [7 empty] | 0 | 0 | 0.53 | 10.9 | 5394.11
PH4100A | GG\10\008\B | GG | 10 | 8 | B | 1 Prestrip - Thick | 100 | 86.6817 | 86.6817 | 2020-10-10 01:00 | 2020-10-11 09:13 | 53539.4281 | 53539 | [7 empty] | 0 | 0 | 5.41 | 10.59 | 5455.13
TS5500Exc | MW\35\008\A | MW | 35 | 8 | A | 1 Prestrip - Thick | 32.0998 | 32.0998 | 32.0998 | 2020-10-10 05:57 | 2020-10-15 21:16 | 120161.0012 | 120161 | [7 empty] | 0 | 0 | 11.99 | 12.26 | 5310.77
TS5500Shv | GG\11\009\X1 | GG | 11 | 9 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2020-10-10 14:16 | 2020-10-11 03:12 | 15779.3677 | [6 empty] | 15779 | 11630 | 1.15 | 0 | 0 | 11.04 | 5419
TS Fleet 5 | MW\35\007\A | MW | 35 | 7 | A | 1 Prestrip - Thick | 96.4048 | 96.4048 | 96.4048 | 2020-10-10 22:02 | 2020-10-17 01:13 | 276114.7763 | 276115 | [7 empty] | 0 | 0 | 27.4 | 11.14 | 5392.5
DRE2 | GG\09\023\B | GG | 9 | 23 | B | 6 DL | 100 | 0 | 100 | 2020-10-10 23:28 | 2020-10-13 18:32 | 225615.0995 |  |  |  |  | 225615 | 188013 |  |  | 0 | 19.36 | 0 | 16.97 | 4919.18
TS5500Shv | GG\11\009\X2 | GG | 11 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2020-10-11 03:12 | 2020-10-14 22:13 | 97562.204 | 97562 | [7 empty] | 0 | 0 | 9.64 | 0 | 0
PH4100XPC#1 | GG\10\008\B | GG | 10 | 8 | B | 1 Prestrip - Thick | 100 | 13.3183 | 13.3183 | 2020-10-11 05:35 | 2020-10-11 09:13 | 8226.144 | 8226 | [7 empty] | 0 | 0 | 0.83 | 10.59 | 5455.13
PH4100A | GG\11\025\D | GG | 11 | 25 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-10-11 09:13 | 2020-10-15 07:35 | 164150.0421 | 164150 | [7 empty] | 0 | 0 | 26.54 | 6.08 | 5852.43
PH4100XPC#1 | GG\10\013\X2 | GG | 10 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 67.8566 | 2020-10-11 09:13 | 2020-10-14 01:39 | 145454.5725 | 145455 | [7 empty] | 0 | 0 | 23.37 | 0 | 0
DRE1 | MW\31\007\D | MW | 31 | 7 | D | 6 DL | 100 | 100 | 100 | 2020-10-11 21:07 | 2020-10-16 07:23 | 371199.7299 |  |  |  | 21185 | 371200 | 281464 |  |  | 0 | 30.28 | 0 | 6.12 | 5874.2
DRE2 | GG\09\024\B | GG | 9 | 24 | B | 6 DL | 100 | 0 | 100 | 2020-10-13 18:32 | 2020-10-16 03:40 | 192179.521 |  |  |  |  | 192180 | 160150 |  |  | 0 | 17.92 | 0 | 11.68 | 5303.53
PH4100XPC#1 | GG\10\018\X2 | GG | 10 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 93.6352 | 2020-10-14 01:39 | 2020-10-17 17:24 | 198213.4075 | 198213 | [7 empty] | 0 | 0 | 31.39 | 0 | 0
TS5500Shv | GG\09\005\B | GG | 9 | 5 | B | 8 Coal Mining | 41.4 | 0 | 41.4 | 2020-10-14 22:13 | 2020-10-15 15:31 | 21092.3708 | [6 empty] | 21092 | 15375 | 1.54 | 0 | 0 | 11.35 | 5328
PH4100A | GG\12\025\D | GG | 12 | 25 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-10-15 07:35 | 2020-10-18 14:53 | 138785.4256 | 138785 | [7 empty] | 0 | 0 | 23.98 | 6.13 | 5847.73
TS5500Shv | GG\09\006\B | GG | 9 | 6 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2020-10-15 15:31 | 2020-10-16 11:03 | 23818.3493 | [6 empty] | 23818 | 17369 | 1.73 | 0 | 0 | 11.35 | 5313
TS5500Exc | MW\31\006\D | MW | 31 | 6 | D | 8 Coal Mining | 24.3 | 0 | 24.3 | 2020-10-15 21:16 | 2020-10-16 08:20 | 13946.8855 | [6 empty] | 13947 | 10536 | 1.05 | 0 | 0 | 5.9 | 5893
DRE2 | GG\09\025\D | GG | 9 | 25 | D | 6 DL | 100 | 0 | 100 | 2020-10-16 03:40 | 2020-10-21 11:17 | 429279.3867 |  |  |  | 32645 | 429279 | 293803 |  |  | 0 | 40 | 0 | 5.97 | 5861.67
DRE1 | MW\31\008\D | MW | 31 | 8 | D | 6 DL | 100 | 100 | 100 | 2020-10-16 07:23 | 2020-10-20 19:00 | 375927.1853 |  |  |  | 21455 | 375927 | 285049 |  |  | 0 | 30.72 | 0 | 6.16 | 5871.78
TS5500Exc | MW\31\007\D | MW | 31 | 7 | D | 8 Coal Mining | 80.2 | 0 | 80.2 | 2020-10-16 08:20 | 2020-10-17 22:10 | 47654.1915 | [6 empty] | 47654 | 35916 | 3.59 | 0 | 0 | 6.12 | 5874
TS5500Shv | GG\09\013\B | GG | 9 | 13 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2020-10-16 11:03 | 2020-10-16 19:48 | 10670.6637 | [6 empty] | 10671 | 7803 | 1.66 | 0 | 0 | 10.69 | 5468
TS5500Shv | GG\09\018\B | GG | 9 | 18 | B | 8 Coal Mining | 73.6 | 0 | 73.6 | 2020-10-16 19:48 | 2020-10-17 09:55 | 17229.5671 | [6 empty] | 17230 | 12571 | 2.58 | 0 | 0 | 11.11 | 5433
TS Fleet 5 | MW\35\008\A | MW | 35 | 8 | A | 1 Prestrip - Thick | 67.9002 | 67.9002 | 67.9002 | 2020-10-17 01:13 | 2020-10-22 16:42 | 254174.1134 | 254174 | [7 empty] | 0 | 0 | 25.36 | 12.26 | 5310.77
TS5500Shv | MW\31\002\D | MW | 31 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-10-17 09:55 | 2020-10-19 14:35 | 64210.648 | [6 empty] | 64211 | 47904 | 4.79 | 0 | 0 | 7.4 | 5764
PH4100XPC#1 | GG\10\006\B | GG | 10 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-10-17 17:24 | 2020-10-17 18:09 | 1681.4937 | 1681 | [7 empty] | 0 | 0 | 0.17 | 11.52 | 5303.8
PH4100XPC#1 | GG\10\013\B | GG | 10 | 13 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-10-17 18:09 | 2020-10-19 03:49 | 76220.9177 | 76221 | [7 empty] | 0 | 0 | 13.65 | 10.72 | 5463.28
TS5500Exc | MW\35\006\A | MW | 35 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-10-17 22:10 | 2020-10-18 22:40 | 30855.6763 | [6 empty] | 30856 | 22623 | 2.29 | 0 | 0 | 11.25 | 5364
PH4100A | GG\10\005\B | GG | 10 | 5 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2020-10-18 14:53 | 2020-10-18 14:53 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | GG\11\024\B | GG | 11 | 24 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-10-18 14:53 | 2020-10-26 10:20 | 323618.3943 | 323618 | [7 empty] | 0 | 0 | 34.57 | 0 | 0
TS5500Exc | GG\09\021\B | GG | 9 | 21 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-10-18 22:40 | 2020-10-20 15:43 | 51708.9554 | [6 empty] | 51709 | 37196 | 3.72 | 0 | 0 | 13.23 | 5271
PH4100XPC#1 | GG\10\018\B | GG | 10 | 18 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-10-19 03:49 | 2020-10-20 14:22 | 78206.9059 | 78207 | [7 empty] | 0 | 0 | 13.54 | 11.2 | 5424.33
TS5500Shv | GG\09\019\B | GG | 9 | 19 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-10-19 14:35 | 2020-10-21 08:50 | 51521.3368 | [6 empty] | 51521 | 37456 | 3.74 | 0 | 0 | 11.67 | 5390
PH4100XPC#1 | GG\10\022\X2 | GG | 10 | 22 | X2 | 1 Prestrip - Thick | 100 | 0 | 68.3723 | 2020-10-20 14:22 | 2020-10-23 09:12 | 154735.1567 | 154735 | [7 empty] | 0 | 0 | 16.33 | 0 | 0
TS5500Exc | MW\27\008\D | MW | 27 | 8 | D | 8 Coal Mining | 41.9 | 0 | 41.9 | 2020-10-20 15:43 | 2020-10-22 01:37 | 42687.9259 | [6 empty] | 42688 | 31897 | 1.99 | 0 | 0 | 6.84 | 5812
DRE1 | MW\31\009\D | MW | 31 | 9 | D | 6 DL | 100 | 100 | 100 | 2020-10-20 19:00 | 2020-10-25 04:15 | 367660.7115 |  |  |  | 20983 | 367661 | 278781 |  |  | 0 | 30.05 | 0 | 5.81 | 5901.69
TS5500Shv | MW\31\003\D | MW | 31 | 3 | D | 8 Coal Mining | 49.5 | 0 | 49.5 | 2020-10-21 08:50 | 2020-10-22 10:24 | 31170.7396 | [6 empty] | 31171 | 23440 | 2.34 | 0 | 0 | 6.89 | 5808
DRE2 | GG\10\012\B | GG | 10 | 12 | B | 6 DL | 100 | 0 | 100 | 2020-10-21 11:17 | 2020-10-23 17:01 | 180732.8211 |  |  |  |  | 180733 | 150611 |  |  | 0 | 16.65 | 0 | 10.1 | 5512.99
TS5500Exc | MW\31\008\D | MW | 31 | 8 | D | 8 Coal Mining | 28 | 0 | 28 | 2020-10-22 01:37 | 2020-10-22 15:21 | 17302.3 | [6 empty] | 17302 | 13031 | 1.3 | 0 | 0 | 6.16 | 5872
TS6060#1 | GG\09\025\D | GG | 9 | 25 | D | 8 Coal Mining | 15.9 | 0 | 15.9 | 2020-10-22 09:03 | 2020-10-22 14:53 | 7901.459 | [6 empty] | 7901 | 5993 | 0.74 | 0 | 0 | 5.97 | 5862
TS5500Shv | GG\09\020\B | GG | 9 | 20 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-10-22 10:24 | 2020-10-24 05:19 | 52339.5718 | [6 empty] | 52340 | 37840 | 3.78 | 0 | 0 | 12.44 | 5334
TS6060#1 | RS\14\005\X | RS | 14 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-10-22 14:53 | 2020-11-08 09:48 | 404640.7896 | 404641 | [7 empty] | 0 | 0 | 40.03 | 12.5 | 5182.8
TS5500Exc | MW\35\006\B | MW | 35 | 6 | B | 1 Prestrip - Thick | 100 | 88.561 | 88.561 | 2020-10-22 15:21 | 2020-10-24 15:15 | 42366.4205 | 42366 | [7 empty] | 0 | 0 | 4.26 | 8.83 | 5591.3
TS Fleet 5 | MW\35\006\B | MW | 35 | 6 | B | 1 Prestrip - Thick | 11.439 | 11.439 | 11.439 | 2020-10-22 16:42 | 2020-10-22 19:37 | 5472.278 | 5472 | [7 empty] | 0 | 0 | 0.55 | 8.83 | 5591.3
TS Fleet 5 | MW\35\009\A | MW | 35 | 9 | A | 1 Prestrip - Thick | 70.4571 | 70.4571 | 70.4571 | 2020-10-22 19:37 | 2020-10-30 04:48 | 332381.2816 | 332381 | [7 empty] | 0 | 0 | 32.89 | 12.23 | 5315.77
PH4100XPC#1 | GG\10\019\B | GG | 10 | 19 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-10-23 09:12 | 2020-10-29 22:51 | 364942.7876 | 364943 | [7 empty] | 0 | 0 | 36.25 | 11.58 | 5398.05
DRE2 | GG\10\011\B | GG | 10 | 11 | B | 6 DL | 100 | 0 | 100 | 2020-10-23 17:01 | 2020-10-26 09:36 | 217217.0905 |  |  |  |  | 217217 | 167090 |  |  | 0 | 16.72 | 0 | 9.95 | 5518.67
TS5500Shv | MW\31\004\D | MW | 31 | 4 | D | 8 Coal Mining | 34.8 | 0 | 34.8 | 2020-10-24 05:19 | 2020-10-24 22:41 | 21165.9163 | [6 empty] | 21166 | 16005 | 1.6 | 0 | 0 | 6.34 | 5856
TS5500Exc | MW\35\006\B | MW | 35 | 6 | B | 8 Coal Mining | 22.9 | 0 | 22.9 | 2020-10-24 15:15 | 2020-10-24 22:51 | 9579.8927 | [6 empty] | 9580 | 7077 | 0.71 | 0 | 0 | 8.83 | 5591
TS5500Shv | RS\14\003\X | RS | 14 | 3 | X | 8 Coal Mining | 38.3 | 0 | 38.3 | 2020-10-24 22:41 | 2020-10-25 02:54 | 5154.467 | [6 empty] | 5154 | 3596 | 0.55 | 0 | 0 | 13.52 | 5112
TS5500Exc | MW\35\009\A | MW | 35 | 9 | A | 1 Prestrip - Thick | 29.5429 | 29.5429 | 29.5429 | 2020-10-24 22:51 | 2020-10-31 11:46 | 139368.7917 | 139369 | [7 empty] | 0 | 0 | 13.79 | 12.23 | 5315.77
TS5500Shv | GG\09\022\B | GG | 9 | 22 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-10-25 02:54 | 2020-10-26 21:54 | 52427.018 | [6 empty] | 52427 | 37544 | 3.75 | 0 | 0 | 14.42 | 5158
DRE1 | MW\31\010\D | MW | 31 | 10 | D | 6 DL | 100 | 100 | 100 | 2020-10-25 04:15 | 2020-10-29 15:44 | 375447.5316 |  |  |  | 21428 | 375448 | 284685 |  |  | 0 | 30.63 | 0 | 5.51 | 5928.37
DRE2 | GG\10\010\B | GG | 10 | 10 | B | 6 DL | 100 | 0 | 100 | 2020-10-26 09:36 | 2020-10-28 18:40 | 191977.4354 |  |  |  |  | 191977 | 159981 |  |  | 0 | 17.27 | 0 | 10.27 | 5483.01
PH4100A | GG\12\024\B | GG | 12 | 24 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-10-26 10:20 | 2020-11-01 17:56 | 261912.6754 | 261913 | [7 empty] | 0 | 0 | 27.47 | 0 | 0
TS5500Shv | MW\31\005\D | MW | 31 | 5 | D | 8 Coal Mining | 70.7 | 0 | 70.7 | 2020-10-26 21:54 | 2020-10-28 07:42 | 41219.9302 | [6 empty] | 41220 | 31191 | 3.12 | 0 | 0 | 5.92 | 5891
TS5500Shv | GG\09\023\B | GG | 9 | 23 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-10-28 07:42 | 2020-10-30 06:22 | 56903.8636 | [6 empty] | 56904 | 40367 | 4.03 | 0 | 0 | 16.97 | 4919
DRE2 | GG\10\009\B | GG | 10 | 9 | B | 6 DL | 100 | 0 | 100 | 2020-10-28 18:40 | 2020-10-31 12:22 | 220991.3904 |  |  |  |  | 220991 | 184159 |  |  | 0 | 18.37 | 0 | 10.42 | 5470.88
DRE1 | MW\31\011\D | MW | 31 | 11 | D | 6 DL | 100 | 100 | 100 | 2020-10-29 15:44 | 2020-10-31 12:11 | 155259.9576 |  |  |  | 6315 | 155260 | 81956 |  |  | 0 | 31 | 0 | 5.55 | 5923.97
PH4100XPC#1 | GG\10\020\B | GG | 10 | 20 | B | 1 Prestrip - Thick | 100 | 80.4818 | 80.4818 | 2020-10-29 22:51 | 2020-11-04 13:49 | 313422.8451 | 313423 | [7 empty] | 0 | 0 | 34.02 | 12.55 | 5328.86
TS Fleet 5 | MW\35\010\X | MW | 35 | 10 | X | 1 Prestrip - Thick | 67.886 | 67.886 | 67.886 | 2020-10-30 04:48 | 2020-11-06 23:20 | 349948.691 | 349949 | [7 empty] | 0 | 0 | 26.33 | 12.16 | 5230.42
TS5500Shv | MW\31\006\D | MW | 31 | 6 | D | 8 Coal Mining | 75.7 | 0 | 75.7 | 2020-10-30 06:22 | 2020-10-31 17:57 | 43391.6244 | [6 empty] | 43392 | 32780 | 3.28 | 0 | 0 | 5.9 | 5893
TS5500Exc | MW\31\010\D | MW | 31 | 10 | D | 8 Coal Mining | 62.4 | 0 | 62.4 | 2020-10-31 11:46 | 2020-11-01 17:36 | 37581.8136 | [6 empty] | 37582 | 28532 | 2.85 | 0 | 0 | 5.51 | 5928
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2020-10-31 12:11 | 2020-11-02 12:11
DRE2 | GG\10\008\B | GG | 10 | 8 | B | 6 DL | 100 | 0 | 100 | 2020-10-31 12:22 | 2020-11-03 07:54 | 227164.7867 |  |  |  |  | 227165 | 189304 |  |  | 0 | 19.12 | 0 | 10.59 | 5455.13
TS5500Shv | GG\09\024\B | GG | 9 | 24 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-10-31 17:57 | 2020-11-01 15:03 | 25734.4117 | [6 empty] | 25734 | 18804 | 1.87 | 0 | 0 | 11.68 | 5304
TS5500Shv | GG\10\020\B | GG | 10 | 20 | B | 1 Prestrip - Thick | 20.9367 | 19.5182 | 19.5182 | 2020-11-01 15:03 | 2020-11-04 13:49 | 76010.2422 | 76010 | [7 empty] | 0 | 0 | 8.25 | 12.55 | 5328.86
TS5500Exc | MW\35\010\X | MW | 35 | 10 | X | 1 Prestrip - Thick | 32.114 | 32.114 | 32.114 | 2020-11-01 17:36 | 2020-11-09 11:54 | 165545.5909 | 165546 | [7 empty] | 0 | 0 | 12.45 | 12.16 | 5230.42
PH4100A | GG\11\023\B | GG | 11 | 23 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-01 17:56 | 2020-11-09 05:00 | 306474.545 | 306475 | [7 empty] | 0 | 0 | 31.62 | 19.94 | 4700.33
DRE1 | RS\10\003\D | RS | 10 | 3 | D | 6 DL | 100 | 100 | 100 | 2020-11-02 12:11 | 2020-11-06 00:43 | 295336.7933 |  |  |  | 13214 | 295337 | 251069 |  |  | 0 | 24.63 | 0 | 6.27 | 5869.42
DRE2 | GG\10\007\B | GG | 10 | 7 | B | 6 DL | 100 | 0 | 100 | 2020-11-03 07:54 | 2020-11-06 05:17 | 233365.1777 |  |  |  |  | 233365 | 194471 |  |  | 0 | 19.6 | 0 | 10.9 | 5394.11
PH4100XPC#1 | GG\10\021\B | GG | 10 | 21 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-04 13:49 | 2020-11-10 18:08 | 336793.0727 | 336793 | [7 empty] | 0 | 0 | 35.32 | 13.38 | 5266.13
TS5500Shv | MW\31\007\D | MW | 31 | 7 | D | 8 Coal Mining | 19.8 | 0 | 19.8 | 2020-11-04 13:49 | 2020-11-04 23:29 | 11781.64 | [6 empty] | 11782 | 8880 | 0.89 | 0 | 0 | 6.12 | 5874
TS5500Shv | GG\09\025\D | GG | 9 | 25 | D | 8 Coal Mining | 84.1 | 0 | 84.1 | 2020-11-04 23:29 | 2020-11-06 09:46 | 41819.7578 | [6 empty] | 41820 | 31717 | 3.92 | 0 | 0 | 5.97 | 5862
DRE1 | RS\10\004\D | RS | 10 | 4 | D | 6 DL | 100 | 100 | 100 | 2020-11-06 00:43 | 2020-11-09 06:29 | 271600.0577 |  |  |  | 12152 | 271600 | 230890 |  |  | 0 | 24.31 | 0 | 6.88 | 5816.13
DRE2 | GG\10\006\B | GG | 10 | 6 | B | 6 DL | 100 | 0 | 100 | 2020-11-06 05:17 | 2020-11-09 02:55 | 234237.0608 |  |  |  |  | 234237 | 195198 |  |  | 0 | 19.5 | 0 | 11.52 | 5303.8
TS5500Shv | GG\10\012\B | GG | 10 | 12 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2020-11-06 09:46 | 2020-11-07 04:31 | 22866.4548 | [6 empty] | 22866 | 16773 | 1.68 | 0 | 0 | 10.1 | 5513
TS Fleet 5 | MW\36\003\A | MW | 36 | 3 | A | 1 Prestrip - Thick | 67.9892 | 67.9892 | 67.9892 | 2020-11-06 23:20 | 2020-11-08 09:08 | 63416.7358 | 63417 | [7 empty] | 0 | 0 | 6.54 | 12.09 | 5212.82
TS5500Shv | RS\14\004\X | RS | 14 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2020-11-07 04:31 | 2020-11-07 21:45 | 21011.6131 | [6 empty] | 21012 | 14670 | 1.47 | 0 | 0 | 13.35 | 5126
TS5500Shv | MW\31\008\D | MW | 31 | 8 | D | 8 Coal Mining | 72 | 0 | 72 | 2020-11-07 21:45 | 2020-11-09 10:17 | 44547.6086 | [6 empty] | 44548 | 33551 | 3.36 | 0 | 0 | 6.16 | 5872
TS Fleet 5 | MW\36\004\A | MW | 36 | 4 | A | 1 Prestrip - Thick | 1.9812 | 1.9812 | 1.9812 | 2020-11-08 09:08 | 2020-11-08 10:22 | 2303.911 | 2304 | [7 empty] | 0 | 0 | 0.25 | 11.33 | 5267.6
TS6060#1 | GG\10\012\B | GG | 10 | 12 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2020-11-08 09:48 | 2020-11-09 04:33 | 25379.252 | [6 empty] | 25379 | 18616 | 1.86 | 0 | 0 | 10.1 | 5513
TS Fleet 5 | MW\36\004\A | MW | 36 | 4 | A | 1 Prestrip - Thick | 66.0017 | 66.0017 | 66.0017 | 2020-11-08 10:22 | 2020-11-10 03:17 | 76750.6718 | 76751 | [7 empty] | 0 | 0 | 8.42 | 11.33 | 5267.6
DRE2 | GG\10\005\B | GG | 10 | 5 | B | 6 DL | 100 | 0 | 100 | 2020-11-09 02:55 | 2020-11-11 11:36 | 190700.3375 |  |  |  |  | 190700 | 165826 |  |  | 0 | 16.57 | 0 | 11.66 | 5301.1
TS6060#1 | RS\14\003\A | RS | 14 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-09 04:33 | 2020-11-14 23:56 | 143806.5076 | 143807 | [7 empty] | 0 | 0 | 20.4 | 11.66 | 5395.77
PH4100A | GG\12\023\B | GG | 12 | 23 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-09 05:00 | 2020-11-16 19:25 | 312195.9002 | 312196 | [7 empty] | 0 | 0 | 32.24 | 11.97 | 5333.75
DRE1 | RS\10\005\D | RS | 10 | 5 | D | 6 DL | 100 | 100 | 100 | 2020-11-09 06:29 | 2020-11-12 13:40 | 276627.3624 |  |  |  | 12377 | 276627 | 235164 |  |  | 0 | 24.75 | 0 | 7.04 | 5801.87
TS5500Shv | MW\34\010\X | MW | 34 | 10 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-11-09 10:17 | 2020-11-09 20:18 | 12211.7625 | [6 empty] | 12212 | 8907 | 0.65 | 0 | 0 | 12.18 | 5223
TS5500Exc | RS\10\003\D | RS | 10 | 3 | D | 8 Coal Mining | 48.7 | 0 | 48.7 | 2020-11-09 11:54 | 2020-11-10 13:11 | 31835.6178 | [6 empty] | 31836 | 23358 | 2.17 | 0 | 0 | 6.27 | 5869
TS5500Shv | GG\10\011\B | GG | 10 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-11-09 20:18 | 2020-11-11 13:06 | 49754.2285 | [6 empty] | 49754 | 36540 | 3.66 | 0 | 0 | 9.95 | 5519
TS Fleet 5 | MW\34\010\A | MW | 34 | 10 | A | 1 Prestrip - Thick | 47.433 | 47.433 | 47.433 | 2020-11-10 03:17 | 2020-11-12 20:29 | 122328.2592 | 122328 | [7 empty] | 0 | 0 | 9.18 | 11.13 | 5413.78
TS5500Exc | MW\34\010\A | MW | 34 | 10 | A | 1 Prestrip - Thick | 60.3302 | 52.567 | 52.567 | 2020-11-10 13:11 | 2020-11-16 22:28 | 135568.4694 | 135568 | [7 empty] | 0 | 0 | 10.17 | 11.13 | 5413.78
PH4100XPC#1 | GG\10\022\B | GG | 10 | 22 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-10 18:08 | 2020-11-12 23:37 | 121052.0065 | 121052 | [7 empty] | 0 | 0 | 12.18 | 14.51 | 5157.38
DRE2 | GG\09\012\D | GG | 9 | 12 | D | 6 DL | 100 | 100 | 100 | 2020-11-11 11:36 | 2020-11-17 15:53 | 498781.5721 |  |  |  | 11613 | 498782 | 220648 |  |  | 0 | 23.22 | 0 | 6.07 | 5855.43
TS5500Shv | GG\10\010\B | GG | 10 | 10 | B | 8 Coal Mining | 92 | 0 | 92 | 2020-11-11 13:06 | 2020-11-13 02:51 | 46019.8139 | [6 empty] | 46020 | 33720 | 3.38 | 0 | 0 | 10.27 | 5483
DRE1 | RS\10\006\D | RS | 10 | 6 | D | 6 DL | 100 | 100 | 100 | 2020-11-12 13:40 | 2020-11-16 06:27 | 310106.9936 |  |  |  | 15944 | 310107 | 249786 |  |  | 0 | 26.57 | 0 | 7.05 | 5801.38
TS Fleet 5 | MW\36\005\B | MW | 36 | 5 | B | 1 Prestrip - Thick | 67.9173 | 67.9173 | 67.9173 | 2020-11-12 20:29 | 2020-11-15 11:00 | 117284.5952 | 117285 | [7 empty] | 0 | 0 | 12.2 | 10.12 | 5477.33
PH4100XPC#1 | GG\10\023\B | GG | 10 | 23 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-12 23:37 | 2020-11-18 21:05 | 329456.1803 | 329456 | [7 empty] | 0 | 0 | 34 | 18.3 | 4819.38
TS5500Shv | MW\31\009\D | MW | 31 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-11-13 02:51 | 2020-11-15 04:54 | 61040.0736 | [6 empty] | 61040 | 46118 | 4.61 | 0 | 0 | 5.81 | 5902
TS6060#1 | GG\10\010\B | GG | 10 | 10 | B | 8 Coal Mining | 8 | 0 | 8 | 2020-11-14 23:56 | 2020-11-15 02:52 | 3986.5935 | [6 empty] | 3987 | 2921 | 0.29 | 0 | 0 | 10.27 | 5483
TS6060#1 | RS\14\004\A | RS | 14 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-15 02:52 | 2020-11-23 06:10 | 201501.3895 | 201501 | [7 empty] | 0 | 0 | 20.12 | 13.59 | 5223.53
TS5500Shv | MW\35\003\A | MW | 35 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-11-15 04:54 | 2020-11-15 21:03 | 19688.9319 | [6 empty] | 19689 | 14247 | 1.42 | 0 | 0 | 12.08 | 5242
TS Fleet 5 | MW\36\006\A | MW | 36 | 6 | A | 1 Prestrip - Thick | 67.8568 | 67.8568 | 67.8568 | 2020-11-15 11:00 | 2020-11-18 23:19 | 158162.2135 | 158162 | [7 empty] | 0 | 0 | 16.48 | 12.06 | 5301.21
TS5500Shv | GG\10\009\B | GG | 10 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-11-15 21:03 | 2020-11-17 15:31 | 51777.7993 | [6 empty] | 51778 | 37842 | 3.79 | 0 | 0 | 10.42 | 5471
DRE1 | RS\10\007\D | RS | 10 | 7 | D | 6 DL | 100 | 100 | 100 | 2020-11-16 06:27 | 2020-11-19 13:25 | 275878.0578 |  |  |  | 12344 | 275878 | 234527 |  |  | 0 | 24.69 | 0 | 7.27 | 5781.83
PH4100A | GG\11\022\B | GG | 11 | 22 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-16 19:25 | 2020-11-25 05:16 | 339068.1779 | 339068 | [7 empty] | 0 | 0 | 35.07 | 14.61 | 5160.87
TS5500Exc | MW\34\010\A | MW | 34 | 10 | A | 8 Coal Mining | 83.2 | 0 | 83.2 | 2020-11-16 22:28 | 2020-11-18 14:17 | 50147.7563 | [6 empty] | 50148 | 36897 | 2.86 | 0 | 0 | 11.13 | 5414
TS5500Shv | MW\31\010\D | MW | 31 | 10 | D | 8 Coal Mining | 37.6 | 0 | 37.6 | 2020-11-17 15:31 | 2020-11-18 10:04 | 22626.7064 | [6 empty] | 22627 | 17178 | 1.72 | 0 | 0 | 5.51 | 5928
DRE2 | GG\09\011\D | GG | 9 | 11 | D | 6 DL | 100 | 100 | 100 | 2020-11-17 15:53 | 2020-11-24 00:31 | 513438.3181 |  |  |  | 9319 | 513438 | 223660 |  |  | 0 | 23.31 | 0 | 5.99 | 5862.74
TS5500Shv | MW\31\011\D | MW | 31 | 11 | D | 7 PostStrip | 100 | 0 | 100 | 2020-11-18 10:04 | 2020-11-19 01:54 | 16973.2164 |  |  | 16973 | [5 empty] | 0 | 0 | 0 | 5.55 | 5923.97
TS5500Exc | RS\14\003\A | RS | 14 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-11-18 14:17 | 2020-11-19 21:21 | 39126.6376 | [6 empty] | 39127 | 27602 | 3.59 | 0 | 0 | 11.66 | 5396
PH4100XPC#1 | GG\10\024\B | GG | 10 | 24 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-18 21:05 | 2020-11-24 10:13 | 312312.747 | 312313 | [7 empty] | 0 | 0 | 34.62 | 11.87 | 5290.72
TS Fleet 5 | MW\35\003\B | MW | 35 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-18 23:19 | 2020-11-19 09:47 | 19635.2366 | 19635 | [7 empty] | 0 | 0 | 1.97 | 9.82 | 5520.32
TS5500Shv | MW\31\011\D | MW | 31 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-11-19 01:54 | 2020-11-19 17:34 | 19099.7127 | [6 empty] | 19100 | 14512 | 4.52 | 0 | 0 | 5.55 | 5924
TS Fleet 5 | MW\36\007\A | MW | 36 | 7 | A | 1 Prestrip - Thick | 67.9243 | 67.9243 | 67.9243 | 2020-11-19 09:47 | 2020-11-23 22:08 | 203276.5138 | 203277 | [7 empty] | 0 | 0 | 20.31 | 11.52 | 5361.25
DRE1 | RS\10\008\D | RS | 10 | 8 | D | 6 DL | 100 | 100 | 100 | 2020-11-19 13:25 | 2020-11-20 23:29 | 118953.7888 |  |  |  | 4495 | 118954 | 67681 |  |  | 0 | 25.36 | 0 | 7.28 | 5774.87
TS5500Shv | MW\34\010\A | MW | 34 | 10 | A | 8 Coal Mining | 16.8 | 0 | 16.8 | 2020-11-19 17:34 | 2020-11-20 01:53 | 10140.5496 | [6 empty] | 10141 | 7461 | 0.58 | 0 | 0 | 11.13 | 5414
TS5500Exc | MW\35\003\B | MW | 35 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-11-19 21:21 | 2020-11-20 08:19 | 13826.9586 | [6 empty] | 13827 | 10162 | 1.02 | 0 | 0 | 9.82 | 5520
TS5500Shv | MW\35\003\B | MW | 35 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-11-20 01:53 | 2020-11-20 12:51 | 13385.6727 | [6 empty] | 13386 | 9837 | 0.99 | 0 | 0 | 9.82 | 5520
TS5500Exc | RS\10\004\D | RS | 10 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-11-20 08:19 | 2020-11-21 09:25 | 31607.067 | [6 empty] | 31607 | 22977 | 2.3 | 0 | 0 | 6.88 | 5816
TS5500Shv | MW\35\004\A | MW | 35 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-11-20 12:51 | 2020-11-21 01:55 | 15927.2805 | [6 empty] | 15927 | 11597 | 1.18 | 0 | 0 | 10.97 | 5324
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2020-11-20 23:29 | 2020-11-22 23:29
TS5500Shv | GG\10\007\B | GG | 10 | 7 | B | 8 Coal Mining | 52.5 | 0 | 52.5 | 2020-11-21 01:55 | 2020-11-22 00:35 | 27634.9949 | [6 empty] | 27635 | 20156 | 2.01 | 0 | 0 | 10.9 | 5394
TS5500Exc | RS\10\005\D | RS | 10 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-11-21 09:25 | 2020-11-23 10:38 | 61991.3247 | [6 empty] | 61991 | 45029 | 4.5 | 0 | 0 | 7.04 | 5802
TS5500Shv | GG\10\006\B | GG | 10 | 6 | B | 8 Coal Mining | 45.5 | 0 | 45.5 | 2020-11-22 00:35 | 2020-11-22 19:28 | 23036.8971 | [6 empty] | 23037 | 16781 | 1.68 | 0 | 0 | 11.52 | 5304
TS5500Shv | GG\10\005\B | GG | 10 | 5 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2020-11-22 19:28 | 2020-11-23 15:16 | 24142.9838 | [6 empty] | 24143 | 17574 | 1.76 | 0 | 0 | 11.66 | 5301
DRE1 | MW\32\001\D | MW | 32 | 1 | D | 6 DL | 100 | 100 | 100 | 2020-11-22 23:29 | 2020-11-24 21:10 | 159590.4271 |  |  |  | 9108 | 159590 | 121010 |  |  | 0 | 31.41 | 0 | 7.73 | 5733.89
TS6060#1 | GG\10\007\B | GG | 10 | 7 | B | 8 Coal Mining | 47.5 | 0 | 47.5 | 2020-11-23 06:10 | 2020-11-24 00:36 | 24962.2606 | [6 empty] | 24962 | 18206 | 1.82 | 0 | 0 | 10.9 | 5394
TS5500Exc | RS\14\004\A | RS | 14 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2020-11-23 10:38 | 2020-11-25 03:31 | 51508.4602 | [6 empty] | 51508 | 35899 | 3.58 | 0 | 0 | 13.59 | 5224
TS5500Shv | RS\10\003\D | RS | 10 | 3 | D | 8 Coal Mining | 51.3 | 0 | 51.3 | 2020-11-23 15:16 | 2020-11-24 18:45 | 33504.2798 | [6 empty] | 33504 | 24582 | 2.29 | 0 | 0 | 6.27 | 5869
TS Fleet 5 | MW\34\010\B | MW | 34 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-23 22:08 | 2020-11-24 16:29 | 34428.1553 | 34428 | [7 empty] | 0 | 0 | 2.69 | 8.96 | 5596.33
DRE2 | GG\09\010\D | GG | 9 | 10 | D | 6 DL | 100 | 100 | 100 | 2020-11-24 00:31 | 2020-11-30 02:40 | 491578.2828 |  |  |  | 11445 | 491578 | 217462 |  |  | 0 | 22.91 | 0 | 6.18 | 5846.36
TS6060#1 | GG\10\008\B | GG | 10 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-11-24 00:36 | 2020-11-25 16:11 | 53565.0326 | [6 empty] | 53565 | 39033 | 3.91 | 0 | 0 | 10.59 | 5455
PH4100XPC#1 | GG\10\025\D | GG | 10 | 25 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-24 10:13 | 2020-11-27 04:46 | 156795.2121 | 156795 | [7 empty] | 0 | 0 | 23.24 | 6.03 | 5856.89
TS Fleet 5 | MW\35\004\B | MW | 35 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-24 16:29 | 2020-11-25 09:45 | 32399.729 | 32400 | [7 empty] | 0 | 0 | 3.27 | 9.15 | 5562.31
TS5500Shv | MW\34\010\B | MW | 34 | 10 | B | 8 Coal Mining | 59.7 | 0 | 59.7 | 2020-11-24 18:45 | 2020-11-25 18:59 | 29548.2733 | [6 empty] | 29548 | 21945 | 1.73 | 0 | 0 | 8.96 | 5596
DRE1 | MW\32\002\D | MW | 32 | 2 | D | 6 DL | 100 | 0 | 100 | 2020-11-24 21:10 | 2020-11-30 02:54 | 439210.3548 |  |  |  | 31236 | 439210 | 315829 |  |  | 0 | 35 | 0 | 7.52 | 5753.21
TS5500Exc | MW\34\010\B | MW | 34 | 10 | B | 8 Coal Mining | 40.3 | 0 | 40.3 | 2020-11-25 03:31 | 2020-11-25 19:21 | 19941.7933 | [6 empty] | 19942 | 14811 | 1.17 | 0 | 0 | 8.96 | 5596
PH4100A | GG\12\022\B | GG | 12 | 22 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-25 05:16 | 2020-12-03 08:24 | 328145.5888 | 328146 | [7 empty] | 0 | 0 | 33.8 | 14.9 | 5149.01
TS Fleet 5 | MW\36\008\A | MW | 36 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-25 09:45 | 2020-12-03 22:36 | 384286.9024 | 384287 | [7 empty] | 0 | 0 | 38.64 | 12.56 | 5288.41
TS6060#1 | GG\10\006\B | GG | 10 | 6 | B | 8 Coal Mining | 54.5 | 0 | 54.5 | 2020-11-25 16:11 | 2020-11-26 12:32 | 27544.7458 | [6 empty] | 27545 | 20065 | 2.01 | 0 | 0 | 11.52 | 5304
TS5500Shv | MW\35\004\B | MW | 35 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-11-25 18:59 | 2020-11-26 11:47 | 20493.9369 | [6 empty] | 20494 | 15107 | 1.53 | 0 | 0 | 9.15 | 5562
TS5500Exc | MW\35\004\B | MW | 35 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-11-25 19:21 | 2020-11-26 12:10 | 21169.5612 | [6 empty] | 21170 | 15605 | 1.58 | 0 | 0 | 9.15 | 5562
TS5500Shv | MW\35\005\B | MW | 35 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-11-26 11:47 | 2020-11-26 23:21 | 14094.4462 | [6 empty] | 14094 | 10373 | 1.06 | 0 | 0 | 9.5 | 5533
TS5500Exc | RS\10\008\D | RS | 10 | 8 | D | 7 PostStrip | 100 | 0 | 100 | 2020-11-26 12:10 | 2020-11-27 08:12 | 17721.715 |  |  | 17722 | [5 empty] | 0 | 0 | 0 | 7.28 | 5774.87
TS6060#1 | GG\10\005\B | GG | 10 | 5 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2020-11-26 12:32 | 2020-11-27 08:20 | 26796.0589 | [6 empty] | 26796 | 19505 | 1.95 | 0 | 0 | 11.66 | 5301
TS5500Shv | RS\10\004\D | RS | 10 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-11-26 23:21 | 2020-11-28 00:26 | 30598.3308 | [6 empty] | 30598 | 22243 | 2.22 | 0 | 0 | 6.88 | 5816
PH4100XPC#1 | GG\11\003\X2 | GG | 11 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 99.3221 | 2020-11-27 04:46 | 2020-11-29 02:19 | 103069.5525 | 103070 | [7 empty] | 0 | 0 | 10.42 | 0 | 0
TS5500Exc | MW\36\003\A | MW | 36 | 3 | A | 1 Prestrip - Thick | 32.0108 | 32.0108 | 32.0108 | 2020-11-27 08:12 | 2020-11-28 17:57 | 29858.0198 | 29858 | [7 empty] | 0 | 0 | 3.08 | 12.09 | 5212.82
TS6060#1 | RS\14\003\B | RS | 14 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-27 08:20 | 2020-11-28 02:56 | 19190.7694 | 19191 | [7 empty] | 0 | 0 | 2.44 | 8.68 | 5652.42
TS5500Shv | GG\09\012\D | GG | 9 | 12 | D | 8 Coal Mining | 83.1 | 0 | 83.1 | 2020-11-28 00:26 | 2020-11-29 20:27 | 53663.4743 | [6 empty] | 53663 | 40311 | 4.03 | 0 | 0 | 6.07 | 5855
TS6060#1 | RS\14\004\B | RS | 14 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-28 02:56 | 2020-11-29 07:44 | 29719.8433 | 29720 | [7 empty] | 0 | 0 | 2.96 | 9.18 | 5599.94
TS5500Exc | RS\14\003\B | RS | 14 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-11-28 17:57 | 2020-11-29 07:46 | 17394.1694 | [6 empty] | 17394 | 12406 | 1.55 | 0 | 0 | 8.68 | 5652
PH4100XPC#1 | GG\11\003\B | GG | 11 | 3 | B | 1 Prestrip - Thick | 100 | 80.2823 | 80.2823 | 2020-11-29 02:19 | 2020-11-30 15:59 | 85271.7345 | 85272 | [7 empty] | 0 | 0 | 8.6 | 9.91 | 5520.8
TS6060#1 | RS\14\006\X | RS | 14 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-11-29 07:44 | 2020-12-18 04:57 | 456099.944 | 456100 | [7 empty] | 0 | 0 | 44.85 | 11.01 | 5292.35
TS5500Exc | RS\14\004\B | RS | 14 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-11-29 07:46 | 2020-11-30 00:50 | 21493.391 | [6 empty] | 21493 | 15361 | 1.53 | 0 | 0 | 9.18 | 5600
TS5500Shv | GG\11\003\B | GG | 11 | 3 | B | 1 Prestrip - Thick | 32.1389 | 19.7177 | 19.7177 | 2020-11-29 20:27 | 2020-11-30 15:59 | 20943.1428 | 20943 | [7 empty] | 0 | 0 | 2.11 | 9.91 | 5520.8
TS5500Exc | MW\36\004\A | MW | 36 | 4 | A | 1 Prestrip - Thick | 32.017 | 32.017 | 32.017 | 2020-11-30 00:50 | 2020-12-01 18:55 | 37231.3001 | 37231 | [7 empty] | 0 | 0 | 4.09 | 11.33 | 5267.6
DRE2 | GG\09\009\D | GG | 9 | 9 | D | 6 DL | 100 | 100 | 100 | 2020-11-30 02:40 | 2020-12-05 22:13 | 469395.5245 |  |  |  | 10929 | 469396 | 207649 |  |  | 0 | 21.87 | 0 | 6.48 | 5819.95
DRE1 | MW\32\003\D | MW | 32 | 3 | D | 6 DL | 100 | 100 | 100 | 2020-11-30 02:54 | 2020-12-03 19:47 | 310492.1957 |  |  |  | 15964 | 310492 | 250097 |  |  | 0 | 26.6 | 0 | 6.98 | 5800.27
TS5500Shv | GG\11\003\B | GG | 11 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-11-30 15:59 | 2020-12-02 11:17 | 52792.2792 | [6 empty] | 52792 | 38769 | 3.88 | 0 | 0 | 9.91 | 5521
PH4100XPC#1 | GG\11\004\X2 | GG | 11 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2020-11-30 15:59 | 2020-12-02 20:28 | 118784.874 | 118785 | [7 empty] | 0 | 0 | 11.99 | 0 | 0
TS5500Exc | MW\36\005\B | MW | 36 | 5 | B | 1 Prestrip - Thick | 32.0827 | 32.0827 | 32.0827 | 2020-12-01 18:55 | 2020-12-04 09:21 | 55402.7757 | 55403 | [7 empty] | 0 | 0 | 5.76 | 10.12 | 5477.33
TS5500Shv | RS\14\003\B | RS | 14 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-12-02 11:17 | 2020-12-03 01:05 | 16839.0363 | [6 empty] | 16839 | 12010 | 1.5 | 0 | 0 | 8.68 | 5652
PH4100XPC#1 | GG\11\004\B | GG | 11 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-12-02 20:28 | 2020-12-05 09:32 | 138249.9779 | 138250 | [7 empty] | 0 | 0 | 13.89 | 10.96 | 5400.71
TS5500Shv | RS\14\004\B | RS | 14 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-12-03 01:05 | 2020-12-03 18:09 | 20807.4317 | [6 empty] | 20807 | 14870 | 1.48 | 0 | 0 | 9.18 | 5600
PH4100A | GG\11\021\B | GG | 11 | 21 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-12-03 08:24 | 2020-12-11 14:58 | 333086.5217 | 333087 | [7 empty] | 0 | 0 | 35.92 | 13.6 | 5257.37
TS5500Shv | GG\12\003\X1 | GG | 12 | 3 | X1 | 1 Prestrip - Thick | 10.2415 | 10.2415 | 10.2415 | 2020-12-03 18:09 | 2020-12-07 00:48 | 84009.1887 | 84009 | [7 empty] | 0 | 0 | 8.05 | 9.94 | 5390.87
DRE1 | MW\32\004\D | MW | 32 | 4 | D | 6 DL | 100 | 100 | 100 | 2020-12-03 19:47 | 2020-12-07 23:02 | 346656.7338 |  |  |  | 17823 | 346657 | 279227 |  |  | 0 | 29.64 | 0 | 6.36 | 5853.7
TS Fleet 5 | MW\36\009\A | MW | 36 | 9 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-12-03 22:36 | 2020-12-14 17:19 | 485346.9082 | 485347 | [7 empty] | 0 | 0 | 47.95 | 12.21 | 5317.78
TS5500Exc | MW\36\006\A | MW | 36 | 6 | A | 1 Prestrip - Thick | 32.1432 | 32.1432 | 32.1432 | 2020-12-04 09:21 | 2020-12-07 21:33 | 74920.0054 | 74920 | [7 empty] | 0 | 0 | 7.8 | 12.06 | 5301.21
PH4100XPC#1 | GG\11\006\X2 | GG | 11 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2020-12-05 09:32 | 2020-12-07 07:33 | 104138.579 | 104139 | [7 empty] | 0 | 0 | 10.18 | 0 | 0
DRE2 | GG\09\008\D | GG | 9 | 8 | D | 6 DL | 100 | 100 | 100 | 2020-12-05 22:13 | 2020-12-11 13:18 | 454407.7485 |  |  |  | 10580 | 454408 | 201019 |  |  | 0 | 21.18 | 0 | 6.61 | 5808.13
TS5500Shv | GG\11\004\B | GG | 11 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2020-12-07 00:48 | 2020-12-08 19:18 | 51839.6539 | [6 empty] | 51840 | 37851 | 3.79 | 0 | 0 | 10.96 | 5401
PH4100XPC#1 | GG\11\006\B | GG | 11 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-12-07 07:33 | 2020-12-07 10:02 | 5622.5299 | 5623 | [7 empty] | 0 | 0 | 0.56 | 11.61 | 5302.51
PH4100XPC#1 | GG\11\007\X2 | GG | 11 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2020-12-07 10:02 | 2020-12-09 05:31 | 98419.477 | 98419 | [7 empty] | 0 | 0 | 9.8 | 0 | 0
TS5500Exc | MW\36\007\A | MW | 36 | 7 | A | 1 Prestrip - Thick | 11.4291 | 11.4291 | 11.4291 | 2020-12-07 21:33 | 2020-12-09 12:03 | 34203.8317 | 34204 | [7 empty] | 0 | 0 | 3.42 | 11.52 | 5361.25
DRE1 | MW\32\005\D | MW | 32 | 5 | D | 6 DL | 100 | 100 | 100 | 2020-12-07 23:02 | 2020-12-12 17:11 | 398751.5332 |  |  |  | 22758 | 398752 | 302355 |  |  | 0 | 32.4 | 0 | 5.86 | 5896.55
TS5500Shv | GG\12\003\X1 | GG | 12 | 3 | X1 | 1 Prestrip - Thick | 21.9553 | 21.9553 | 21.9553 | 2020-12-08 19:18 | 2020-12-15 19:55 | 180096.1412 | 180096 | [7 empty] | 0 | 0 | 17.26 | 9.94 | 5390.87
PH4100XPC#1 | GG\11\007\B | GG | 11 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-12-09 05:31 | 2020-12-10 00:59 | 44075.7604 | 44076 | [7 empty] | 0 | 0 | 4.5 | 10.83 | 5403.76
TS5500Exc | MW\36\007\A | MW | 36 | 7 | A | 1 Prestrip - Thick | 20.6466 | 20.6466 | 20.6466 | 2020-12-09 12:03 | 2020-12-12 09:35 | 61788.8413 | 61789 | [7 empty] | 0 | 0 | 6.17 | 11.52 | 5361.25
PH4100XPC#1 | GG\11\008\X2 | GG | 11 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 67.8611 | 2020-12-10 00:59 | 2020-12-11 07:08 | 68266.7458 | 68267 | [7 empty] | 0 | 0 | 6.68 | 0 | 0
PH4100XPC#1 | GG\11\008\B | GG | 11 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-12-11 07:08 | 2020-12-12 10:01 | 60818.8811 | 60819 | [7 empty] | 0 | 0 | 6.12 | 10.45 | 5470.37
DRE2 | GG\09\007\D | GG | 9 | 7 | D | 6 DL | 100 | 100 | 100 | 2020-12-11 13:18 | 2020-12-17 00:05 | 439946.879 |  |  |  | 10243 | 439947 | 194621 |  |  | 0 | 20.48 | 0 | 6.4 | 5826.54
PH4100A | GG\12\021\B | GG | 12 | 21 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-12-11 14:58 | 2020-12-19 09:19 | 314233.3235 | 314233 | [7 empty] | 0 | 0 | 34.02 | 13.91 | 5241.6
TS5500Exc | MW\32\001\D | MW | 32 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-12-12 09:35 | 2020-12-13 05:56 | 25636.2143 | [6 empty] | 25636 | 19080 | 4.74 | 0 | 0 | 7.73 | 5734
PH4100XPC#1 | GG\11\009\B | GG | 11 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-12-12 10:01 | 2020-12-13 18:14 | 72946.4043 | 72946 | [7 empty] | 0 | 0 | 7.28 | 10.1 | 5498.61
DRE1 | MW\32\006\D | MW | 32 | 6 | D | 6 DL | 100 | 100 | 100 | 2020-12-12 17:11 | 2020-12-17 03:21 | 370855.937 |  |  |  | 21166 | 370856 | 281203 |  |  | 0 | 30.2 | 0 | 5.78 | 5902.57
TS5500Exc | MW\32\002\D | MW | 32 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2020-12-13 05:56 | 2020-12-15 09:33 | 65018.6603 | [6 empty] | 65019 | 48509 | 4.85 | 0 | 0 | 7.52 | 5753
PH4100XPC#1 | GG\11\010\B | GG | 11 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-12-13 18:14 | 2020-12-24 04:38 | 575679.0162 | 575679 | [7 empty] | 0 | 0 | 60.21 | 9.95 | 5508.56
TS Fleet 5 | MW\36\010\X | MW | 36 | 10 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-12-14 17:19 | 2020-12-25 08:27 | 478635.9067 | 478636 | [7 empty] | 0 | 0 | 39.36 | 12.15 | 5235.57
TS5500Exc | MW\32\003\D | MW | 32 | 3 | D | 8 Coal Mining | 77 | 0 | 77 | 2020-12-15 09:33 | 2020-12-17 00:42 | 49301.4339 | [6 empty] | 49301 | 37045 | 3.7 | 0 | 0 | 6.98 | 5800
TS5500Shv | MW\32\003\D | MW | 32 | 3 | D | 8 Coal Mining | 23 | 0 | 23 | 2020-12-15 19:55 | 2020-12-16 07:57 | 14688.3407 | [6 empty] | 14688 | 11037 | 1.1 | 0 | 0 | 6.98 | 5800
TS5500Shv | MW\32\004\D | MW | 32 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-12-16 07:57 | 2020-12-17 08:47 | 30270.4434 | [6 empty] | 30270 | 22871 | 2.29 | 0 | 0 | 6.36 | 5854
DRE2 | GG\09\006\D | GG | 9 | 6 | D | 6 DL | 100 | 100 | 100 | 2020-12-17 00:05 | 2020-12-22 07:09 | 427379.0736 |  |  |  | 10336 | 427379 | 196377 |  |  | 0 | 20.67 | 0 | 6.34 | 5829.48
TS5500Exc | MW\32\004\D | MW | 32 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-12-17 00:42 | 2020-12-18 01:31 | 31268.3701 | [6 empty] | 31268 | 23625 | 2.36 | 0 | 0 | 6.36 | 5854
DRE1 | MW\32\007\D | MW | 32 | 7 | D | 6 DL | 100 | 100 | 100 | 2020-12-17 03:21 | 2020-12-21 13:20 | 370212.6138 |  |  |  | 21129 | 370213 | 280716 |  |  | 0 | 30.19 | 0 | 6 | 5884.1
TS5500Shv | MW\32\005\D | MW | 32 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-12-17 08:47 | 2020-12-18 08:18 | 28676.6438 | [6 empty] | 28677 | 21717 | 2.17 | 0 | 0 | 5.86 | 5897
TS5500Exc | MW\32\005\D | MW | 32 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-12-18 01:31 | 2020-12-19 01:02 | 29622.0277 | [6 empty] | 29622 | 22433 | 2.24 | 0 | 0 | 5.86 | 5897
TS6060#1 | RS\14\007\X | RS | 14 | 7 | X | 1 Prestrip - Thick | 21.077 | 21.077 | 21.077 | 2020-12-18 04:57 | 2020-12-23 08:50 | 125187.7763 | 125188 | [7 empty] | 0 | 0 | 10.28 | 9.96 | 5365.22
TS5500Shv | MW\32\006\D | MW | 32 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2020-12-18 08:18 | 2020-12-19 07:15 | 27989.4233 | [6 empty] | 27989 | 21178 | 2.12 | 0 | 0 | 5.78 | 5903
TS5500Exc | MW\32\006\D | MW | 32 | 6 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2020-12-19 01:02 | 2020-12-19 23:59 | 28912.1515 | [6 empty] | 28912 | 21877 | 2.19 | 0 | 0 | 5.78 | 5903
TS5500Shv | MW\35\007\A | MW | 35 | 7 | A | 8 Coal Mining | 10.1 | 0 | 10.1 | 2020-12-19 07:15 | 2020-12-19 11:05 | 4675.8099 | [6 empty] | 4676 | 3435 | 0.35 | 0 | 0 | 11.14 | 5393
PH4100A | GG\11\020\B | GG | 11 | 20 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-12-19 09:19 | 2020-12-28 08:34 | 368977.7739 | 368978 | [7 empty] | 0 | 0 | 41.12 | 12.72 | 5319.77
TS5500Shv | MW\35\008\A | MW | 35 | 8 | A | 8 Coal Mining | 49.2 | 0 | 41.3 | 2020-12-19 11:05 | 2020-12-20 02:55 | 19304.329 | [6 empty] | 19304 | 14103 | 1.42 | 0 | 0 | 12.26 | 5311
TS5500Exc | MW\35\006\B | MW | 35 | 6 | B | 8 Coal Mining | 77.1 | 0 | 8.8 | 2020-12-19 23:59 | 2020-12-20 02:55 | 3687.3524 | [6 empty] | 3687 | 2724 | 0.27 | 0 | 0 | 8.83 | 5591
TS5500Shv | GG\12\006\X1 | GG | 12 | 6 | X1 | 1 Prestrip - Thick | 14.0894 | 14.0894 | 14.0894 | 2020-12-20 02:55 | 2020-12-23 04:33 | 78857.8344 | 78858 | [7 empty] | 0 | 0 | 7.65 | 10.7 | 5373.89
TS5500Exc | MW\37\009\A | MW | 37 | 9 | A | 1 Prestrip - Thick | 13.2132 | 13.2132 | 13.2132 | 2020-12-20 02:55 | 2020-12-23 03:51 | 64766.5882 | 64767 | [7 empty] | 0 | 0 | 6.38 | 12.19 | 5319.51
DRE1 | MW\32\008\D | MW | 32 | 8 | D | 6 DL | 100 | 100 | 100 | 2020-12-21 13:20 | 2020-12-25 23:29 | 370794.1581 |  |  |  | 21162 | 370794 | 281157 |  |  | 0 | 30.23 | 0 | 6.07 | 5879.55
DRE2 | GG\09\005\D | GG | 9 | 5 | D | 6 DL | 100 | 100 | 100 | 2020-12-22 07:09 | 2020-12-27 13:07 | 423763.347 |  |  |  | 10248 | 423763 | 194716 |  |  | 0 | 20.49 | 0 | 6.28 | 5833.77
TS5500Exc | MW\37\010\X | MW | 37 | 10 | X | 1 Prestrip - Thick | 6.5257 | 6.5257 | 6.5257 | 2020-12-23 03:51 | 2020-12-24 12:04 | 28631.0985 | 28631 | [7 empty] | 0 | 0 | 2.58 | 12.16 | 5239.56
TS5500Shv | GG\12\008\X1 | GG | 12 | 8 | X1 | 1 Prestrip - Thick | 31.2701 | 31.2701 | 31.2701 | 2020-12-23 04:33 | 2020-12-28 15:38 | 139516.6365 | 139517 | [7 empty] | 0 | 0 | 13.49 | 10 | 5501.84
TS6060#1 | RS\14\007\X | RS | 14 | 7 | X | 1 Prestrip - Thick | 32.3837 | 32.3837 | 32.3837 | 2020-12-23 08:50 | 2020-12-31 07:10 | 192344.152 | 192344 | [7 empty] | 0 | 0 | 15.79 | 9.96 | 5365.22
PH4100XPC#1 | GG\11\011\X2 | GG | 11 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 71.6639 | 2020-12-24 04:38 | 2020-12-29 20:14 | 318515.8776 | 318516 | [7 empty] | 0 | 0 | 41.62 | 0 | 0
TS5500Exc | MW\38\006\B | MW | 38 | 6 | B | 1 Prestrip - Thick | 6.361 | 6.361 | 6.361 | 2020-12-24 12:04 | 2020-12-25 06:19 | 16235.4699 | 16235 | [7 empty] | 0 | 0 | 1.72 | 8.57 | 5604.97
TS5500Exc | MW\38\007\A | MW | 38 | 7 | A | 1 Prestrip - Thick | 26.0155 | 26.0155 | 26.0155 | 2020-12-25 06:19 | 2020-12-28 21:16 | 77219.1841 | 77219 | [7 empty] | 0 | 0 | 7.83 | 12.19 | 5306.29
TS Fleet 5 | MW\37\003\A | MW | 37 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-12-25 08:27 | 2020-12-26 11:21 | 50462.8908 | 50463 | [7 empty] | 0 | 0 | 4.37 | 13.26 | 5110.68
DRE1 | MW\32\009\D | MW | 32 | 9 | D | 6 DL | 100 | 100 | 100 | 2020-12-25 23:29 | 2020-12-30 01:25 | 342125.3601 |  |  |  | 17590 | 342125 | 275577 |  |  | 0 | 29.36 | 0 | 5.77 | 5905.47
TS Fleet 5 | MW\37\004\A | MW | 37 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2020-12-26 11:21 | 2020-12-28 18:37 | 103695.0112 | 103695 | [7 empty] | 0 | 0 | 11.55 | 12.7 | 5148.82
DRE2 | GG\09\004\D | GG | 9 | 4 | D | 6 DL | 100 | 84.1061 | 84.1061 | 2020-12-27 13:07 | 2021-01-01 | 359475.6232 |  |  |  | 6694 | 359476 | 160659 |  |  | 0 | 19.89 | 0 | 6.14 | 5844.89
PH4100A | GG\12\020\B | GG | 12 | 20 | B | 1 Prestrip - Thick | 100 | 40.5716 | 40.5716 | 2020-12-28 08:34 | 2021-01-01 | 151016.1224 | 151016 | [7 empty] | 0 | 0 | 17.03 | 12.9 | 5309.85
TS5500Shv | GG\12\010\B | GG | 12 | 10 | B | 1 Prestrip - Thick | 14.9444 | 14.6109 | 14.6109 | 2020-12-28 15:38 | 2021-01-01 | 85987.8378 | 85988 | [7 empty] | 0 | 0 | 8.27 | 9.59 | 5536.41
TS Fleet 5 | MW\37\005\B | MW | 37 | 5 | B | 1 Prestrip - Thick | 100 | 81.6696 | 81.6696 | 2020-12-28 18:37 | 2021-01-01 | 145144.9168 | 145145 | [7 empty] | 0 | 0 | 15.2 | 10.73 | 5427.18
TS5500Exc | MW\38\009\A | MW | 38 | 9 | A | 1 Prestrip - Thick | 3.9054 | 3.9054 | 3.9054 | 2020-12-28 21:16 | 2020-12-29 19:06 | 19382.5041 | 19383 | [7 empty] | 0 | 0 | 1.91 | 12.16 | 5321.7
TS5500Exc | MW\39\005\D | MW | 39 | 5 | D | 1 Prestrip - Thick | 10.0978 | 10.0978 | 10.0978 | 2020-12-29 19:06 | 2020-12-30 04:22 | 8202.2062 | 8202 | [7 empty] | 0 | 0 | 1.07 | 6.06 | 5879.94
PH4100XPC#1 | GG\11\011\B | GG | 11 | 11 | B | 1 Prestrip - Thick | 100 | 76.7683 | 76.7683 | 2020-12-29 20:14 | 2020-12-31 07:21 | 79485.3523 | 79485 | [7 empty] | 0 | 0 | 7.96 | 9.86 | 5524.15
DRE1 | MW\32\010\D | MW | 32 | 10 | D | 6 DL | 100 | 29.7623 | 29.7623 | 2020-12-30 01:25 | 2021-01-01 | 162674.7154 |  |  |  | 6659 | 162675 | 85987 |  |  | 0 | 30.27 | 0 | 5.48 | 5930.28
TS5500Exc | GG\11\011\B | GG | 11 | 11 | B | 1 Prestrip - Thick | 100 | 23.0545 | 23.0545 | 2020-12-30 04:22 | 2020-12-31 07:21 | 23870.469 | 23870 | [7 empty] | 0 | 0 | 2.39 | 9.86 | 5524.15
TS6060#1 | GG\11\011\B | GG | 11 | 11 | B | 1 Prestrip - Thick | 100 | 0.17717 | 0.17717 | 2020-12-31 07:10 | 2020-12-31 07:21 | 183.4369 | 183 | [7 empty] | 0 | 0 | 0.02 | 9.86 | 5524.15
PH4100XPC#1 | GG\11\012\B | GG | 11 | 12 | B | 1 Prestrip - Thick | 100 | 6.8386 | 6.8386 | 2020-12-31 07:21 | 2021-01-01 | 38822.9831 | 38823 | [7 empty] | 0 | 0 | 4.5 | 10.16 | 5506.24
TS6060#1 | RS\15\006\X | RS | 15 | 6 | X | 1 Prestrip - Thick | 26.2637 | 3.4933 | 3.4933 | 2020-12-31 07:21 | 2021-01-01 | 16800.605 | 16801 | [7 empty] | 0 | 0 | 1.66 | 11.12 | 5290.59
TS5500Exc | MW\39\006\B | MW | 39 | 6 | B | 1 Prestrip - Thick | 32.0813 | 6.1169 | 6.1169 | 2020-12-31 07:21 | 2021-01-01 | 14805.569 | 14806 | [7 empty] | 0 | 0 | 1.57 | 8.65 | 5600.13
| EOP 73 : 2020 | EOP 73 : 2020 | [7 empty] | 2021-01-01 | 2021-01-01 |  | 62846731 |  | 1163059 | 2815126 | 56281230 | 40389486 | 17096400 | 12535708 | 1157.03 | 0 | 5911.8 | 9.07 | 5601.29
TS Fleet 5 | MW\37\005\B | MW | 37 | 5 | B | 1 Prestrip - Thick | 100 | 18.3304 | 18.3304 | 2021-01-01 | 2021-01-01 16:37 | 32577.263 | 32577 | [7 empty] | 0 | 0 | 3.41 | 10.73 | 5427.18
DRE1 | MW\32\010\D | MW | 32 | 10 | D | 6 DL | 100 | 70.2377 | 70.2377 | 2021-01-01 | 2021-01-05 13:54 | 383905.6606 |  |  |  | 15714 | 383906 | 202925 |  |  | 0 | 30.27 | 0 | 5.48 | 5930.28
PH4100A | GG\12\020\B | GG | 12 | 20 | B | 1 Prestrip - Thick | 100 | 59.4284 | 59.4284 | 2021-01-01 | 2021-01-06 02:33 | 221205.2028 | 221205 | [7 empty] | 0 | 0 | 24.95 | 12.9 | 5309.85
DRE2 | GG\09\004\D | GG | 9 | 4 | D | 6 DL | 100 | 15.8939 | 15.8939 | 2021-01-01 | 2021-01-01 20:11 | 67931.6107 |  |  |  | 1265 | 67932 | 30360 |  |  | 0 | 19.89 | 0 | 6.14 | 5844.89
PH4100XPC#1 | GG\11\012\B | GG | 11 | 12 | B | 1 Prestrip - Thick | 100 | 61.6343 | 61.6343 | 2021-01-01 | 2021-01-07 05:58 | 349900.6347 | 349901 | [7 empty] | 0 | 0 | 40.54 | 10.16 | 5506.24
TS6060#1 | RS\15\006\X | RS | 15 | 6 | X | 1 Prestrip - Thick | 26.2637 | 22.7703 | 22.7703 | 2021-01-01 | 2021-01-05 12:28 | 109510.6498 | 109511 | [7 empty] | 0 | 0 | 10.82 | 11.12 | 5290.59
TS5500Shv | GG\12\010\B | GG | 12 | 10 | B | 1 Prestrip - Thick | 14.9444 | 0.33348 | 0.33348 | 2021-01-01 | 2021-01-01 01:50 | 1962.6206 | 1963 | [7 empty] | 0 | 0 | 0.19 | 9.59 | 5536.41
TS5500Exc | MW\39\006\B | MW | 39 | 6 | B | 1 Prestrip - Thick | 32.0813 | 25.9644 | 25.9644 | 2021-01-01 | 2021-01-03 22:38 | 62845.6712 | 62846 | [7 empty] | 0 | 0 | 6.68 | 8.65 | 5600.13
TS5500Shv | MW\32\007\D | MW | 32 | 7 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-01 01:50 | 2021-01-02 01:32 | 28911.7139 | [6 empty] | 28912 | 21807 | 2.18 | 0 | 0 | 6 | 5884
TS Fleet 5 | MW\37\006\A | MW | 37 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-01 16:37 | 2021-01-06 11:35 | 225334.1618 | 225334 | [7 empty] | 0 | 0 | 23.9 | 13.11 | 5220.73
DRE2 | GG\09\003\D | GG | 9 | 3 | D | 6 DL | 100 | 100 | 100 | 2021-01-01 20:11 | 2021-01-04 10:07 | 208341.7138 |  |  |  | 7952 | 208342 | 190847 |  |  | 0 | 19.88 | 0 | 6.04 | 5853.96
TS5500Shv | MW\32\008\D | MW | 32 | 8 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-02 01:32 | 2021-01-03 02:16 | 30152.6002 | [6 empty] | 30153 | 22727 | 2.27 | 0 | 0 | 6.07 | 5880
TS5500Shv | MW\32\009\D | MW | 32 | 9 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-03 02:16 | 2021-01-04 02:38 | 29720.4103 | [6 empty] | 29720 | 22473 | 2.25 | 0 | 0 | 5.77 | 5905
TS5500Exc | MW\32\007\D | MW | 32 | 7 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-03 22:38 | 2021-01-04 22:20 | 29864.8474 | [6 empty] | 29865 | 22526 | 2.25 | 0 | 0 | 6 | 5884
TS5500Shv | MW\35\008\A | MW | 35 | 8 | A | 8 Coal Mining | 49.2 | 0 | 7.9 | 2021-01-04 02:38 | 2021-01-04 05:40 | 3687.301 | [6 empty] | 3687 | 2694 | 0.27 | 0 | 0 | 12.26 | 5311
TS5500Shv | MW\36\004\A | MW | 36 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-04 05:40 | 2021-01-04 16:15 | 12903.7735 | [6 empty] | 12904 | 9355 | 0.97 | 0 | 0 | 11.33 | 5268
DRE2 | GG\09\002\D | GG | 9 | 2 | D | 6 DL | 100 | 100 | 100 | 2021-01-04 10:07 | 2021-01-07 14:56 | 258344.4337 |  |  |  | 9010 | 258344 | 157359 |  |  | 0 | 19.13 | 0 | 6.03 | 5855.29
TS5500Shv | MW\36\005\B | MW | 36 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-04 16:15 | 2021-01-05 01:05 | 10783.1811 | [6 empty] | 10783 | 7906 | 0.8 | 0 | 0 | 10.12 | 5477
TS5500Exc | MW\32\008\D | MW | 32 | 8 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-04 22:20 | 2021-01-05 23:04 | 31146.642 | [6 empty] | 31147 | 23476 | 2.35 | 0 | 0 | 6.07 | 5880
TS5500Shv | MW\36\006\A | MW | 36 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-05 01:05 | 2021-01-05 09:52 | 10714.8683 | [6 empty] | 10715 | 7819 | 0.8 | 0 | 0 | 12.06 | 5301
TS5500Shv | MW\36\007\A | MW | 36 | 7 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-05 09:52 | 2021-01-06 04:44 | 23006.4648 | [6 empty] | 23006 | 16860 | 1.71 | 0 | 0 | 11.52 | 5361
TS6060#1 | GG\09\004\D | GG | 9 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-01-05 12:28 | 2021-01-07 08:38 | 59777.8301 | [6 empty] | 59778 | 44901 | 4.49 | 0 | 0 | 6.14 | 5845
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2021-01-05 13:54 | 2021-01-07 13:54
TS5500Exc | MW\32\009\D | MW | 32 | 9 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-05 23:04 | 2021-01-06 23:26 | 30700.2041 | [6 empty] | 30700 | 23214 | 2.32 | 0 | 0 | 5.77 | 5905
PH4100A | GG\11\019\B | GG | 11 | 19 | B | 1 Prestrip - Thick | 100 | 95.1012 | 95.1012 | 2021-01-06 02:33 | 2021-01-13 23:48 | 334721.1233 | 334721 | [7 empty] | 0 | 0 | 32.56 | 11.44 | 5409.49
TS5500Shv | MW\32\010\D | MW | 32 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2021-01-06 04:44 | 2021-01-08 14:12 | 61590.3908 |  |  | 61590 | [5 empty] | 0 | 0 | 0 | 5.48 | 5930.28
TS Fleet 5 | MW\37\007\A | MW | 37 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-06 11:35 | 2021-01-12 20:36 | 299916.4722 | 299916 | [7 empty] | 0 | 0 | 30.05 | 11.89 | 5331.05
TS5500Exc | MW\35\006\B | MW | 35 | 6 | B | 8 Coal Mining | 77.1 | 0 | 68.3 | 2021-01-06 23:26 | 2021-01-07 22:09 | 28610.2189 | [6 empty] | 28610 | 21135 | 2.12 | 0 | 0 | 8.83 | 5591
PH4100XPC#1 | GG\11\013\X2 | GG | 11 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 68.059 | 2021-01-07 05:58 | 2021-01-10 07:32 | 167465.8315 | 167466 | [7 empty] | 0 | 0 | 26.42 | 0 | 0
TS6060#1 | GG\09\005\D | GG | 9 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-01-07 08:38 | 2021-01-09 05:22 | 60538.5851 | [6 empty] | 60539 | 45437 | 4.54 | 0 | 0 | 6.28 | 5834
DRE1 | RS\11\003\D | RS | 11 | 3 | D | 6 DL | 100 | 100 | 100 | 2021-01-07 13:54 | 2021-01-11 03:01 | 297326.0303 |  |  |  | 13303 | 297326 | 252760 |  |  | 0 | 24.64 | 0 | 6.32 | 5865.53
DRE2 | GG\10\013\B | GG | 10 | 13 | B | 6 DL | 100 | 0 | 100 | 2021-01-07 14:56 | 2021-01-09 01:13 | 115316.0693 |  |  |  |  | 115316 | 96097 |  |  | 0 | 17.21 | 0 | 10.72 | 5463.28
TS5500Exc | MW\35\007\A | MW | 35 | 7 | A | 8 Coal Mining | 89.9 | 0 | 89.9 | 2021-01-07 22:09 | 2021-01-09 07:16 | 41709.0323 | [6 empty] | 41709 | 30637 | 3.1 | 0 | 0 | 11.14 | 5393
TS5500Shv | GG\09\002\D | GG | 9 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2021-01-08 14:12 | 2021-01-10 21:07 | 58873.7413 |  |  | 58874 | [5 empty] | 0 | 0 | 0 | 6.03 | 5855.29
DRE2 | GG\10\018\B | GG | 10 | 18 | B | 6 DL | 100 | 0 | 100 | 2021-01-09 01:13 | 2021-01-10 13:58 | 123669.5036 |  |  |  |  | 123670 | 103058 |  |  | 0 | 17.84 | 0 | 11.2 | 5424.33
TS6060#1 | MW\32\010\D | MW | 32 | 10 | D | 8 Coal Mining | 100 | 0 | 53.5 | 2021-01-09 05:22 | 2021-01-10 10:10 | 38980.7478 | [6 empty] | 38981 | 29617 | 2.44 | 0 | 0 | 5.48 | 5930
TS5500Exc | MW\32\010\D | MW | 32 | 10 | D | 8 Coal Mining | 100 | 0 | 46.5 | 2021-01-09 07:16 | 2021-01-10 10:10 | 33881.6297 | [6 empty] | 33882 | 25743 | 2.12 | 0 | 0 | 5.48 | 5930
PH4100XPC#1 | GG\11\013\B | GG | 11 | 13 | B | 1 Prestrip - Thick | 100 | 78.9441 | 78.9441 | 2021-01-10 07:32 | 2021-01-11 14:37 | 70378.2422 | 70378 | [7 empty] | 0 | 0 | 11.06 | 10.78 | 5456.73
TS5500Exc | MW\35\008\A | MW | 35 | 8 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-10 10:10 | 2021-01-11 05:01 | 23749.5958 | [6 empty] | 23750 | 17350 | 1.75 | 0 | 0 | 12.26 | 5311
TS6060#1 | GG\09\003\D | GG | 9 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-01-10 10:10 | 2021-01-12 06:42 | 60274.8177 | [6 empty] | 60275 | 45274 | 4.53 | 0 | 0 | 6.04 | 5854
DRE2 | GG\10\019\B | GG | 10 | 19 | B | 6 DL | 100 | 0 | 100 | 2021-01-10 13:58 | 2021-01-13 09:12 | 226146.8732 |  |  |  |  | 226147 | 188456 |  |  | 0 | 18.57 | 0 | 11.58 | 5398.05
TS5500Shv | GG\11\013\B | GG | 11 | 13 | B | 1 Prestrip - Thick | 32.1389 | 21.0559 | 21.0559 | 2021-01-10 21:07 | 2021-01-11 14:37 | 18771.2193 | 18771 | [7 empty] | 0 | 0 | 2.95 | 10.78 | 5456.73
DRE1 | RS\11\004\D | RS | 11 | 4 | D | 6 DL | 100 | 100 | 100 | 2021-01-11 03:01 | 2021-01-14 09:05 | 272735.445 |  |  |  | 12203 | 272735 | 231856 |  |  | 0 | 24.41 | 0 | 6.85 | 5818.59
TS5500Exc | MW\35\009\A | MW | 35 | 9 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-01-11 05:01 | 2021-01-12 18:24 | 47086.0921 | [6 empty] | 47086 | 34409 | 3.45 | 0 | 0 | 12.23 | 5316
PH4100XPC#1 | GG\11\018\X2 | GG | 11 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 67.8329 | 2021-01-11 14:37 | 2021-01-14 11:58 | 156508.5265 | 156509 | [7 empty] | 0 | 0 | 20.99 | 0 | 0
TS5500Shv | MW\36\008\A | MW | 36 | 8 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-11 14:37 | 2021-01-12 09:31 | 23048.4551 | [6 empty] | 23048 | 16806 | 1.69 | 0 | 0 | 12.56 | 5288
TS6060#1 | GG\09\006\D | GG | 9 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-01-12 06:42 | 2021-01-14 04:48 | 62397.8146 | [6 empty] | 62398 | 46833 | 4.68 | 0 | 0 | 6.34 | 5829
TS5500Shv | MW\36\009\A | MW | 36 | 9 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-12 09:31 | 2021-01-13 04:25 | 23034.3796 | [6 empty] | 23034 | 16837 | 1.69 | 0 | 0 | 12.21 | 5318
TS5500Exc | MW\35\010\X | MW | 35 | 10 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-01-12 18:24 | 2021-01-13 12:37 | 22938.5982 | [6 empty] | 22939 | 16739 | 1.33 | 0 | 0 | 12.16 | 5230
TS Fleet 5 | MW\35\007\B | MW | 35 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-12 20:36 | 2021-01-14 04:59 | 63464.28 | 63464 | [7 empty] | 0 | 0 | 6.39 | 9.44 | 5522.9
TS5500Shv | GG\09\011\D | GG | 9 | 11 | D | 8 Coal Mining | 32.8 | 0 | 32.8 | 2021-01-13 04:25 | 2021-01-13 21:53 | 21297.3875 | [6 empty] | 21297 | 15998 | 1.6 | 0 | 0 | 5.99 | 5863
DRE2 | GG\10\020\B | GG | 10 | 20 | B | 6 DL | 100 | 0 | 100 | 2021-01-13 09:12 | 2021-01-16 00:38 | 213354.4602 |  |  |  |  | 213354 | 177795 |  |  | 0 | 19.15 | 0 | 12.55 | 5328.86
TS5500Exc | MW\36\003\A | MW | 36 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-01-13 12:37 | 2021-01-14 04:35 | 20113.2473 | [6 empty] | 20113 | 14523 | 1.44 | 0 | 0 | 12.09 | 5213
TS5500Shv | GG\09\012\D | GG | 9 | 12 | D | 8 Coal Mining | 8 | 0 | 8 | 2021-01-13 21:53 | 2021-01-14 02:07 | 5162.5445 | [6 empty] | 5163 | 3878 | 0.39 | 0 | 0 | 6.07 | 5855
PH4100A | GG\12\019\B | GG | 12 | 19 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-13 23:48 | 2021-01-22 05:34 | 347694.3356 | 347694 | [7 empty] | 0 | 0 | 31.83 | 11.29 | 5421.5
TS5500Shv | GG\10\013\B | GG | 10 | 13 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-01-14 02:07 | 2021-01-14 11:54 | 11941.7648 | [6 empty] | 11942 | 8733 | 1.6 | 0 | 0 | 10.72 | 5463
TS5500Exc | MW\36\004\A | MW | 36 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-14 04:35 | 2021-01-14 15:10 | 13329.1726 | [6 empty] | 13329 | 9664 | 1 | 0 | 0 | 11.33 | 5268
TS6060#1 | GG\09\007\D | GG | 9 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-01-14 04:48 | 2021-01-16 04:39 | 64753.1771 | [6 empty] | 64753 | 48563 | 4.86 | 0 | 0 | 6.4 | 5827
TS Fleet 5 | MW\35\008\B | MW | 35 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-14 04:59 | 2021-01-15 04:58 | 47022.4541 | 47022 | [7 empty] | 0 | 0 | 4.72 | 9.99 | 5458.69
DRE1 | RS\11\005\D | RS | 11 | 5 | D | 6 DL | 100 | 100 | 100 | 2021-01-14 09:05 | 2021-01-18 00:30 | 305348.6793 |  |  |  | 15699 | 305349 | 245954 |  |  | 0 | 26.16 | 0 | 7.03 | 5802.88
TS5500Shv | MW\35\007\B | MW | 35 | 7 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-14 11:54 | 2021-01-15 04:12 | 19869.267 | [6 empty] | 19869 | 14642 | 1.47 | 0 | 0 | 9.44 | 5523
PH4100XPC#1 | GG\11\018\B | GG | 11 | 18 | B | 1 Prestrip - Thick | 100 | 80.9109 | 80.9109 | 2021-01-14 11:58 | 2021-01-15 20:19 | 73201.0461 | 73201 | [7 empty] | 0 | 0 | 11.16 | 11.17 | 5425.17
TS5500Exc | MW\36\005\B | MW | 36 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-14 15:10 | 2021-01-15 | 11138.6706 | [6 empty] | 11139 | 8166 | 0.83 | 0 | 0 | 10.12 | 5477
TS5500Exc | MW\36\006\A | MW | 36 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-15 | 2021-01-15 08:48 | 11068.1057 | [6 empty] | 11068 | 8076 | 0.82 | 0 | 0 | 12.06 | 5301
TS5500Shv | GG\11\018\B | GG | 11 | 18 | B | 1 Prestrip - Thick | 32.1389 | 19.0891 | 19.0891 | 2021-01-15 04:12 | 2021-01-15 20:19 | 17270.098 | 17270 | [7 empty] | 0 | 0 | 2.63 | 11.17 | 5425.17
TS Fleet 5 | MW\35\009\B | MW | 35 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-15 04:58 | 2021-01-15 21:44 | 32863.4529 | 32863 | [7 empty] | 0 | 0 | 3.29 | 9.51 | 5518.04
TS5500Exc | MW\36\007\A | MW | 36 | 7 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-15 08:48 | 2021-01-16 03:40 | 23764.9197 | [6 empty] | 23765 | 17416 | 1.77 | 0 | 0 | 11.52 | 5361
TS5500Shv | MW\35\008\B | MW | 35 | 8 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-15 20:19 | 2021-01-16 11:50 | 18925.8811 | [6 empty] | 18926 | 13921 | 1.39 | 0 | 0 | 9.99 | 5459
PH4100XPC#1 | GG\12\002\X1 | GG | 12 | 2 | X1 | 1 Prestrip - Thick | 100 | 68.0178 | 68.0178 | 2021-01-15 20:19 | 2021-01-28 20:10 | 708952.5587 | 708953 | [7 empty] | 0 | 0 | 55.45 | 11.05 | 5302.72
TS Fleet 5 | MW\35\010\A | MW | 35 | 10 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-15 21:44 | 2021-01-20 22:20 | 236382.7233 | 236383 | [7 empty] | 0 | 0 | 19.27 | 10.9 | 5429.03
DRE2 | GG\10\021\B | GG | 10 | 21 | B | 6 DL | 100 | 0 | 100 | 2021-01-16 00:38 | 2021-01-18 21:07 | 230357.5966 |  |  |  |  | 230358 | 191965 |  |  | 0 | 19.96 | 0 | 13.38 | 5266.13
TS5500Exc | MW\36\008\A | MW | 36 | 8 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-16 03:40 | 2021-01-16 22:34 | 23808.2943 | [6 empty] | 23808 | 17360 | 1.75 | 0 | 0 | 12.56 | 5288
TS6060#1 | GG\09\002\D | GG | 9 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-01-16 04:39 | 2021-01-18 08:52 | 70662.8096 | [6 empty] | 70663 | 53077 | 4.55 | 0 | 0 | 6.03 | 5855
TS5500Shv | MW\35\009\B | MW | 35 | 9 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-16 11:50 | 2021-01-17 03:45 | 19418.5727 | [6 empty] | 19419 | 14349 | 1.44 | 0 | 0 | 9.51 | 5518
TS5500Exc | MW\36\009\A | MW | 36 | 9 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-16 22:34 | 2021-01-17 17:27 | 23793.7547 | [6 empty] | 23794 | 17393 | 1.74 | 0 | 0 | 12.21 | 5318
TS5500Shv | GG\10\018\B | GG | 10 | 18 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-01-17 03:45 | 2021-01-17 13:57 | 12438.4243 | [6 empty] | 12438 | 9072 | 1.6 | 0 | 0 | 11.2 | 5424
TS5500Shv | GG\10\019\B | GG | 10 | 19 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-01-17 13:57 | 2021-01-18 10:04 | 24528.9767 | [6 empty] | 24529 | 17836 | 1.78 | 0 | 0 | 11.58 | 5398
TS5500Exc | MW\35\007\B | MW | 35 | 7 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-17 17:27 | 2021-01-18 09:45 | 20524.2978 | [6 empty] | 20524 | 15125 | 1.51 | 0 | 0 | 9.44 | 5523
DRE1 | RS\11\006\D | RS | 11 | 6 | D | 6 DL | 100 | 100 | 100 | 2021-01-18 00:30 | 2021-01-21 17:32 | 310975.6033 |  |  |  | 15988 | 310976 | 250486 |  |  | 0 | 26.65 | 0 | 7.22 | 5786.65
TS6060#1 | GG\09\008\D | GG | 9 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-01-18 08:52 | 2021-01-20 08:53 | 64994.6326 | [6 empty] | 64995 | 48552 | 4.86 | 0 | 0 | 6.61 | 5808
TS5500Exc | MW\35\008\B | MW | 35 | 8 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-18 09:45 | 2021-01-19 01:16 | 19549.8112 | [6 empty] | 19550 | 14380 | 1.44 | 0 | 0 | 9.99 | 5459
TS5500Shv | GG\10\020\B | GG | 10 | 20 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-01-18 10:04 | 2021-01-19 06:26 | 24832.7225 | [6 empty] | 24833 | 17928 | 1.79 | 0 | 0 | 12.55 | 5329
DRE2 | GG\10\022\B | GG | 10 | 22 | B | 6 DL | 100 | 0 | 100 | 2021-01-18 21:07 | 2021-01-21 17:39 | 230562.005 |  |  |  |  | 230562 | 192135 |  |  | 0 | 19.34 | 0 | 14.51 | 5157.38
TS5500Exc | MW\35\009\B | MW | 35 | 9 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-19 01:16 | 2021-01-19 17:11 | 20058.7454 | [6 empty] | 20059 | 14822 | 1.48 | 0 | 0 | 9.51 | 5518
TS5500Shv | GG\10\021\B | GG | 10 | 21 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-01-19 06:26 | 2021-01-20 02:26 | 24379.2242 | [6 empty] | 24379 | 17504 | 1.75 | 0 | 0 | 13.38 | 5266
TS5500Exc | RS\10\006\D | RS | 10 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-01-19 17:11 | 2021-01-21 18:17 | 61847.1137 | [6 empty] | 61847 | 45028 | 4.5 | 0 | 0 | 7.05 | 5801
TS5500Shv | MW\36\010\X | MW | 36 | 10 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-20 02:26 | 2021-01-20 10:51 | 10273.079 | [6 empty] | 10273 | 7493 | 0.65 | 0 | 0 | 12.15 | 5236
TS6060#1 | GG\09\009\D | GG | 9 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-01-20 08:53 | 2021-01-22 08:48 | 64843.1539 | [6 empty] | 64843 | 48477 | 4.85 | 0 | 0 | 6.48 | 5820
TS5500Shv | MW\37\004\A | MW | 37 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-20 10:51 | 2021-01-20 16:34 | 6960.1042 | [6 empty] | 6960 | 5006 | 0.54 | 0 | 0 | 12.7 | 5149
TS5500Shv | MW\37\005\B | MW | 37 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-20 16:34 | 2021-01-20 23:23 | 8309.5377 | [6 empty] | 8310 | 6074 | 0.62 | 0 | 0 | 10.73 | 5427
TS Fleet 5 | MW\36\003\B | MW | 36 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-20 22:20 | 2021-01-21 09:09 | 21181.2971 | 21181 | [7 empty] | 0 | 0 | 2.11 | 9.99 | 5485.43
TS5500Shv | MW\35\010\A | MW | 35 | 10 | A | 8 Coal Mining | 38.8 | 0 | 38.8 | 2021-01-20 23:23 | 2021-01-21 16:47 | 21231.9197 | [6 empty] | 21232 | 15640 | 1.32 | 0 | 0 | 10.9 | 5429
TS Fleet 5 | MW\36\004\B | MW | 36 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-21 09:09 | 2021-01-22 00:19 | 29728.0802 | 29728 | [7 empty] | 0 | 0 | 3.02 | 9.39 | 5525.33
TS5500Shv | MW\36\003\B | MW | 36 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-21 16:47 | 2021-01-22 03:47 | 13415.8138 | [6 empty] | 13416 | 9845 | 0.98 | 0 | 0 | 9.99 | 5485
DRE1 | RS\11\007\D | RS | 11 | 7 | D | 6 DL | 100 | 100 | 100 | 2021-01-21 17:32 | 2021-01-26 23:07 | 438676.0168 |  |  |  | 16393 | 438676 | 248959 |  |  | 0 | 26.22 | 0 | 7.44 | 5765.08
DRE2 | GG\10\023\B | GG | 10 | 23 | B | 6 DL | 100 | 0 | 100 | 2021-01-21 17:39 | 2021-01-24 12:29 | 224807.1896 |  |  |  |  | 224807 | 187339 |  |  | 0 | 19.16 | 0 | 18.3 | 4819.38
TS5500Exc | RS\10\007\D | RS | 10 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-01-21 18:17 | 2021-01-23 17:46 | 59799.9295 | [6 empty] | 59800 | 43463 | 4.35 | 0 | 0 | 7.27 | 5782
TS Fleet 5 | MW\36\006\B | MW | 36 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-22 00:19 | 2021-01-22 23:20 | 45105.411 | 45105 | [7 empty] | 0 | 0 | 4.53 | 8.83 | 5584.58
TS5500Shv | GG\10\022\B | GG | 10 | 22 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-01-22 03:47 | 2021-01-22 23:58 | 24594.9711 | [6 empty] | 24595 | 17583 | 1.76 | 0 | 0 | 14.51 | 5157
PH4100A | GG\12\018\X2 | GG | 12 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2021-01-22 05:34 | 2021-01-28 04:54 | 248023.1633 | 248023 | [7 empty] | 0 | 0 | 30.37 | 0 | 0
TS6060#1 | GG\09\010\D | GG | 9 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-01-22 08:48 | 2021-01-24 09:09 | 65443.9291 | [6 empty] | 65444 | 49043 | 4.9 | 0 | 0 | 6.18 | 5846
TS Fleet 5 | MW\36\007\B | MW | 36 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-22 23:20 | 2021-01-24 04:49 | 57793.3177 | 57793 | [7 empty] | 0 | 0 | 5.83 | 9.43 | 5517.71
TS5500Shv | MW\36\004\B | MW | 36 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-22 23:58 | 2021-01-23 15:53 | 19412.5292 | [6 empty] | 19413 | 14283 | 1.45 | 0 | 0 | 9.39 | 5525
TS5500Shv | MW\36\006\B | MW | 36 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-23 15:53 | 2021-01-24 08:48 | 20636.2533 | [6 empty] | 20636 | 15233 | 1.52 | 0 | 0 | 8.83 | 5585
TS5500Exc | RS\10\008\D | RS | 10 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-01-23 17:46 | 2021-01-24 10:18 | 20829.1878 | [6 empty] | 20829 | 15134 | 4.29 | 0 | 0 | 7.28 | 5775
TS Fleet 5 | MW\36\008\B | MW | 36 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-24 04:49 | 2021-01-25 03:44 | 44914.1643 | 44914 | [7 empty] | 0 | 0 | 4.51 | 9.96 | 5454.82
TS5500Shv | MW\36\007\B | MW | 36 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-01-24 08:48 | 2021-01-25 17:48 | 40229.7631 | [6 empty] | 40230 | 29645 | 2.97 | 0 | 0 | 9.43 | 5518
TS6060#1 | GG\09\011\D | GG | 9 | 11 | D | 8 Coal Mining | 67.2 | 0 | 67.2 | 2021-01-24 09:09 | 2021-01-25 17:23 | 43616.6972 | [6 empty] | 43617 | 32764 | 3.28 | 0 | 0 | 5.99 | 5863
TS5500Exc | MW\35\010\A | MW | 35 | 10 | A | 8 Coal Mining | 61.2 | 0 | 61.2 | 2021-01-24 10:18 | 2021-01-25 12:56 | 33549.5483 | [6 empty] | 33550 | 24713 | 2.09 | 0 | 0 | 10.9 | 5429
DRE2 | GG\10\024\B | GG | 10 | 24 | B | 6 DL | 100 | 0 | 100 | 2021-01-24 12:29 | 2021-01-27 00:22 | 201406.192 |  |  |  |  | 201406 | 167838 |  |  | 0 | 18.43 | 0 | 11.87 | 5290.72
TS Fleet 5 | MW\36\009\B | MW | 36 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-25 03:44 | 2021-01-25 20:26 | 32748.726 | 32749 | [7 empty] | 0 | 0 | 3.28 | 9.47 | 5517.6
TS5500Exc | MW\36\003\B | MW | 36 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-25 12:56 | 2021-01-25 23:56 | 13858.0934 | [6 empty] | 13858 | 10170 | 1.02 | 0 | 0 | 9.99 | 5485
TS6060#1 | GG\09\012\D | GG | 9 | 12 | D | 8 Coal Mining | 8.9 | 0 | 8.9 | 2021-01-25 17:23 | 2021-01-25 21:37 | 5729.857 | [6 empty] | 5730 | 4304 | 0.43 | 0 | 0 | 6.07 | 5855
TS5500Shv | MW\36\008\B | MW | 36 | 8 | B | 8 Coal Mining | 78.3 | 0 | 78.3 | 2021-01-25 17:48 | 2021-01-26 18:27 | 30055.3361 | [6 empty] | 30055 | 22124 | 2.22 | 0 | 0 | 9.96 | 5455
TS Fleet 5 | MW\35\010\B | MW | 35 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-25 20:26 | 2021-01-26 12:51 | 32163.171 | 32163 | [7 empty] | 0 | 0 | 2.74 | 8.94 | 5592.85
TS6060#1 | GG\10\013\B | GG | 10 | 13 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-01-25 21:37 | 2021-01-26 07:24 | 13254.0467 | [6 empty] | 13254 | 9692 | 1.77 | 0 | 0 | 10.72 | 5463
TS5500Exc | MW\36\004\B | MW | 36 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-25 23:56 | 2021-01-26 15:52 | 20052.5027 | [6 empty] | 20053 | 14754 | 1.5 | 0 | 0 | 9.39 | 5525
TS6060#1 | GG\10\018\B | GG | 10 | 18 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-01-26 07:24 | 2021-01-26 17:36 | 13805.2841 | [6 empty] | 13805 | 10069 | 1.78 | 0 | 0 | 11.2 | 5424
TS Fleet 5 | MW\37\008\A | MW | 37 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-26 12:51 | 2021-02-03 16:10 | 382814.0813 | 382814 | [7 empty] | 0 | 0 | 38.23 | 12.83 | 5266.72
TS5500Exc | MW\36\006\B | MW | 36 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-26 15:52 | 2021-01-27 08:47 | 21316.5693 | [6 empty] | 21317 | 15736 | 1.57 | 0 | 0 | 8.83 | 5585
TS6060#1 | GG\10\019\B | GG | 10 | 19 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-01-26 17:36 | 2021-01-27 13:43 | 27224.4686 | [6 empty] | 27224 | 19796 | 1.98 | 0 | 0 | 11.58 | 5398
TS5500Shv | MW\35\010\B | MW | 35 | 10 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-26 18:27 | 2021-01-27 12:51 | 22451.9904 | [6 empty] | 22452 | 16676 | 1.43 | 0 | 0 | 8.94 | 5593
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2021-01-26 23:07 | 2021-01-28 23:07
DRE2 | GG\09\013\D | GG | 9 | 13 | D | 6 DL | 100 | 100 | 100 | 2021-01-27 00:22 | 2021-01-29 14:16 | 208226.9839 |  |  |  | 4848 | 208227 | 92114 |  |  | 0 | 22.54 | 0 | 6.25 | 5839.95
TS5500Exc | MW\35\010\B | MW | 35 | 10 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-27 08:47 | 2021-01-28 03:12 | 23192.1659 | [6 empty] | 23192 | 17225 | 1.48 | 0 | 0 | 8.94 | 5593
TS5500Shv | MW\36\009\B | MW | 36 | 9 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-27 12:51 | 2021-01-28 04:44 | 19358.1355 | [6 empty] | 19358 | 14315 | 1.43 | 0 | 0 | 9.47 | 5518
TS6060#1 | GG\10\020\B | GG | 10 | 20 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-01-27 13:43 | 2021-01-28 10:05 | 27561.5931 | [6 empty] | 27562 | 19899 | 1.99 | 0 | 0 | 12.55 | 5329
TS5500Exc | RS\11\003\D | RS | 11 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-01-28 03:12 | 2021-01-30 07:26 | 65796.4725 | [6 empty] | 65796 | 48200 | 4.46 | 0 | 0 | 6.32 | 5866
TS5500Shv | RS\11\007\D | RS | 11 | 7 | D | 7 PostStrip | 100 | 0 | 100 | 2021-01-28 04:44 | 2021-01-30 15:03 | 62511.1622 |  |  | 62511 | [5 empty] | 0 | 0 | 0 | 7.44 | 5765.08
PH4100A | GG\12\018\B | GG | 12 | 18 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-01-28 04:54 | 2021-01-30 16:14 | 102991.2175 | 102991 | [7 empty] | 0 | 0 | 14.04 | 11.02 | 5435.31
TS6060#1 | GG\10\021\B | GG | 10 | 21 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-01-28 10:05 | 2021-01-29 06:05 | 27058.2599 | [6 empty] | 27058 | 19428 | 1.94 | 0 | 0 | 13.38 | 5266
PH4100XPC#1 | GG\12\003\X1 | GG | 12 | 3 | X1 | 1 Prestrip - Thick | 100 | 67.8032 | 67.8032 | 2021-01-28 20:10 | 2021-02-08 03:25 | 556180.2881 | 556180 | [7 empty] | 0 | 0 | 53.31 | 9.94 | 5390.87
DRE1 | MW\33\002\D | MW | 33 | 2 | D | 6 DL | 100 | 0 | 100 | 2021-01-28 23:07 | 2021-02-04 04:07 | 520462.5769 |  |  |  | 37014 | 520463 | 374256 |  |  | 0 | 35 | 0 | 7.67 | 5740.06
TS6060#1 | GG\10\022\B | GG | 10 | 22 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-01-29 06:05 | 2021-01-30 02:15 | 27297.7152 | [6 empty] | 27298 | 19515 | 1.95 | 0 | 0 | 14.51 | 5157
DRE2 | GG\09\018\D | GG | 9 | 18 | D | 6 DL | 100 | 100 | 100 | 2021-01-29 14:16 | 2021-02-01 05:12 | 211679.0584 |  |  |  | 4928 | 211679 | 93641 |  |  | 0 | 22.01 | 0 | 6.26 | 5838.75
TS6060#1 | GG\10\023\B | GG | 10 | 23 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-01-30 02:15 | 2021-01-31 20:57 | 57788.7832 | [6 empty] | 57789 | 40688 | 4.05 | 0 | 0 | 18.3 | 4819
TS5500Exc | MW\36\008\B | MW | 36 | 8 | B | 8 Coal Mining | 21.7 | 0 | 21.7 | 2021-01-30 07:26 | 2021-01-30 14:02 | 8311.8647 | [6 empty] | 8312 | 6118 | 0.61 | 0 | 0 | 9.96 | 5455
TS5500Exc | MW\36\009\B | MW | 36 | 9 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-01-30 14:02 | 2021-01-31 05:54 | 19996.3158 | [6 empty] | 19996 | 14787 | 1.48 | 0 | 0 | 9.47 | 5518
TS5500Shv | GG\09\013\D | GG | 9 | 13 | D | 8 Coal Mining | 63 | 0 | 63 | 2021-01-30 15:03 | 2021-01-31 05:11 | 17246.5806 | [6 empty] | 17247 | 12935 | 3.05 | 0 | 0 | 6.25 | 5840
PH4100A | RS\14\007\X | RS | 14 | 7 | X | 1 Prestrip - Thick | 100 | 46.5393 | 46.5393 | 2021-01-30 16:14 | 2021-02-06 11:54 | 276421.8043 | 276422 | [7 empty] | 0 | 0 | 22.69 | 9.96 | 5365.22
TS5500Shv | RS\11\006\D | RS | 11 | 6 | D | 8 Coal Mining | 21.1 | 0 | 21.1 | 2021-01-31 05:11 | 2021-01-31 15:52 | 13018.9331 | [6 empty] | 13019 | 9456 | 0.95 | 0 | 0 | 7.22 | 5787
TS5500Exc | RS\11\004\D | RS | 11 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-01-31 05:54 | 2021-02-02 07:06 | 61960.4894 | [6 empty] | 61960 | 45006 | 4.5 | 0 | 0 | 6.85 | 5819
TS5500Shv | RS\11\007\D | RS | 11 | 7 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-01-31 15:52 | 2021-02-01 22:08 | 36906.6588 | [6 empty] | 36907 | 26776 | 2.15 | 0 | 0 | 7.44 | 5765
TS6060#1 | GG\10\024\B | GG | 10 | 24 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-01-31 20:57 | 2021-02-01 14:26 | 23670.9893 | [6 empty] | 23671 | 17272 | 1.76 | 0 | 0 | 11.87 | 5291
DRE2 | GG\09\019\D | GG | 9 | 19 | D | 6 DL | 100 | 100 | 100 | 2021-02-01 05:12 | 2021-02-06 20:35 | 455427.7408 |  |  |  | 10604 | 455428 | 201470 |  |  | 0 | 21.19 | 0 | 6.09 | 5853.3
TS6060#1 | GG\12\002\X1 | GG | 12 | 2 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2021-02-01 14:26 | 2021-02-02 00:05 | 13061.0698 | [6 empty] | 13061 | 9642 | 0.86 | 0 | 0 | 11.05 | 5303
TS5500Shv | GG\09\018\D | GG | 9 | 18 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-02-01 22:08 | 2021-02-02 09:11 | 13487.0182 | [6 empty] | 13487 | 10115 | 2.29 | 0 | 0 | 6.26 | 5839
TS6060#1 | GG\09\013\D | GG | 9 | 13 | D | 8 Coal Mining | 37 | 0 | 37 | 2021-02-02 00:05 | 2021-02-02 07:34 | 10111.0166 | [6 empty] | 10111 | 7583 | 1.79 | 0 | 0 | 6.25 | 5840
TS5500Exc | RS\11\005\D | RS | 11 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-02-02 07:06 | 2021-02-04 08:26 | 62155.7848 | [6 empty] | 62156 | 45149 | 4.52 | 0 | 0 | 7.03 | 5803
TS6060#1 | GG\09\018\D | GG | 9 | 18 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-02-02 07:34 | 2021-02-02 18:37 | 14969.1082 | [6 empty] | 14969 | 11227 | 2.54 | 0 | 0 | 6.26 | 5839
TS5500Shv | MW\37\006\A | MW | 37 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-02-02 09:11 | 2021-02-02 15:09 | 7266.0753 | [6 empty] | 7266 | 5273 | 0.54 | 0 | 0 | 13.11 | 5221
TS5500Shv | MW\37\007\A | MW | 37 | 7 | A | 8 Coal Mining | 39.7 | 0 | 39.7 | 2021-02-02 15:09 | 2021-02-03 06:36 | 18848.9093 | [6 empty] | 18849 | 13782 | 1.39 | 0 | 0 | 11.89 | 5331
TS6060#1 | RS\15\007\X | RS | 15 | 7 | X | 1 Prestrip - Thick | 30.7283 | 30.7283 | 30.7283 | 2021-02-02 18:37 | 2021-02-10 03:28 | 178999.8396 | 179000 | [7 empty] | 0 | 0 | 16.06 | 9.76 | 5384.18
TS5500Shv | GG\12\011\B | GG | 12 | 11 | B | 1 Prestrip - Thick | 26.819 | 26.819 | 26.819 | 2021-02-03 06:36 | 2021-02-09 13:48 | 162353.4718 | 162353 | [7 empty] | 0 | 0 | 18.53 | 9.82 | 5525.76
TS Fleet 5 | MW\37\009\A | MW | 37 | 9 | A | 1 Prestrip - Thick | 86.7868 | 86.7868 | 86.7868 | 2021-02-03 16:10 | 2021-02-12 17:12 | 425399.8927 | 425400 | [7 empty] | 0 | 0 | 41.89 | 12.19 | 5319.51
DRE1 | MW\33\003\D | MW | 33 | 3 | D | 6 DL | 100 | 100 | 100 | 2021-02-04 04:07 | 2021-02-07 20:22 | 308290.5829 |  |  |  | 15850 | 308291 | 248323 |  |  | 0 | 26.41 | 0 | 7.07 | 5792.88
TS5500Exc | RS\11\006\D | RS | 11 | 6 | D | 8 Coal Mining | 78.9 | 0 | 78.9 | 2021-02-04 08:26 | 2021-02-05 23:09 | 48753.9558 | [6 empty] | 48754 | 35413 | 3.54 | 0 | 0 | 7.22 | 5787
TS5500Exc | RS\11\007\D | RS | 11 | 7 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-02-05 23:09 | 2021-02-07 05:25 | 38123.3618 | [6 empty] | 38123 | 27658 | 2.22 | 0 | 0 | 7.44 | 5765
PH4100A | RS\15\003\X | RS | 15 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-02-06 11:54 | 2021-02-10 13:57 | 160805.3831 | 160805 | [7 empty] | 0 | 0 | 25.67 | 13.28 | 5121.14
DRE2 | GG\09\020\D | GG | 9 | 20 | D | 6 DL | 100 | 100 | 100 | 2021-02-06 20:35 | 2021-02-12 09:39 | 447598.1773 |  |  |  | 10421 | 447598 | 198006 |  |  | 0 | 20.84 | 0 | 5.88 | 5872
TS5500Exc | RS\14\005\X | RS | 14 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-02-07 05:25 | 2021-02-07 20:21 | 18810.2205 | [6 empty] | 18810 | 13191 | 1.32 | 0 | 0 | 12.5 | 5183
TS5500Exc | RS\14\006\X | RS | 14 | 6 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-02-07 20:21 | 2021-02-08 11:08 | 18620.6381 | [6 empty] | 18621 | 13215 | 1.32 | 0 | 0 | 11.01 | 5292
DRE1 | MW\33\004\D | MW | 33 | 4 | D | 6 DL | 100 | 100 | 100 | 2021-02-07 20:22 | 2021-02-12 00:25 | 349510.2812 |  |  |  | 17970 | 349510 | 281525 |  |  | 0 | 29.93 | 0 | 6.4 | 5851.09
PH4100XPC#1 | GG\12\002\X2 | GG | 12 | 2 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2021-02-08 03:25 | 2021-02-09 20:18 | 92557.1027 | 92557 | [7 empty] | 0 | 0 | 8.51 | 0 | 0
TS5500Exc | GG\12\003\X1 | GG | 12 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2021-02-08 11:08 | 2021-02-09 00:08 | 16379.709 | [6 empty] | 16380 | 12178 | 1.23 | 0 | 0 | 9.94 | 5391
TS5500Exc | MW\33\002\D | MW | 33 | 2 | D | 8 Coal Mining | 69.7 | 0 | 69.7 | 2021-02-09 00:08 | 2021-02-10 18:09 | 52932.847 | [6 empty] | 52933 | 39461 | 3.4 | 0 | 0 | 7.67 | 5740
TS5500Shv | GG\09\019\D | GG | 9 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-02-09 13:48 | 2021-02-11 18:42 | 64509.8812 | [6 empty] | 64510 | 48497 | 4.85 | 0 | 0 | 6.09 | 5853
PH4100XPC#1 | GG\12\002\B | GG | 12 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-02-09 20:18 | 2021-02-11 11:23 | 88471.6254 | 88472 | [7 empty] | 0 | 0 | 8.42 | 10.24 | 5497.02
TS6060#1 | RS\14\005\A | RS | 14 | 5 | A | 1 Prestrip - Thick | 27.3316 | 27.3316 | 27.3316 | 2021-02-10 03:28 | 2021-02-12 07:20 | 53518.2501 | 53518 | [7 empty] | 0 | 0 | 5.36 | 15.82 | 5012.03
PH4100A | RS\14\005\A | RS | 14 | 5 | A | 1 Prestrip - Thick | 100 | 72.6684 | 72.6684 | 2021-02-10 13:57 | 2021-02-13 23:55 | 142292.4549 | 142292 | [7 empty] | 0 | 0 | 14.25 | 15.82 | 5012.03
TS5500Exc | MW\36\010\X | MW | 36 | 10 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-02-10 18:09 | 2021-02-11 02:35 | 10611.752 | [6 empty] | 10612 | 7740 | 0.67 | 0 | 0 | 12.15 | 5236
TS5500Exc | RS\14\007\X | RS | 14 | 7 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-02-11 02:35 | 2021-02-11 18:29 | 20036.6037 | [6 empty] | 20037 | 14353 | 1.22 | 0 | 0 | 9.96 | 5365
PH4100XPC#1 | GG\12\003\X2 | GG | 12 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2021-02-11 11:23 | 2021-02-13 08:31 | 102134.6761 | 102135 | [7 empty] | 0 | 0 | 10.31 | 0 | 0
TS5500Exc | RS\14\007\A | RS | 14 | 7 | A | 1 Prestrip - Thick | 100 | 48.912 | 48.912 | 2021-02-11 18:29 | 2021-02-16 21:07 | 108456.2898 | 108456 | [7 empty] | 0 | 0 | 10.05 | 16.74 | 4906.4
TS5500Shv | GG\12\002\B | GG | 12 | 2 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-02-11 18:42 | 2021-02-12 17:13 | 27448.2285 | [6 empty] | 27448 | 20159 | 1.95 | 0 | 0 | 10.24 | 5497
DRE1 | MW\33\005\D | MW | 33 | 5 | D | 6 DL | 100 | 100 | 100 | 2021-02-12 00:25 | 2021-02-16 20:53 | 406825.2319 |  |  |  | 23219 | 406825 | 308477 |  |  | 0 | 33.04 | 0 | 5.82 | 5900.02
TS6060#1 | RS\14\007\A | RS | 14 | 7 | A | 1 Prestrip - Thick | 100 | 51.088 | 51.088 | 2021-02-12 07:20 | 2021-02-16 21:07 | 113281.3769 | 113281 | [7 empty] | 0 | 0 | 10.5 | 16.74 | 4906.4
DRE2 | GG\09\021\D | GG | 9 | 21 | D | 6 DL | 100 | 100 | 100 | 2021-02-12 09:39 | 2021-02-17 18:23 | 432990.3244 |  |  |  | 10081 | 432990 | 191544 |  |  | 0 | 20.17 | 0 | 5.79 | 5879.06
TS Fleet 5 | MW\36\010\A | MW | 36 | 10 | A | 1 Prestrip - Thick | 97.4887 | 97.4887 | 97.4887 | 2021-02-12 17:12 | 2021-02-17 04:05 | 209497.1485 | 209497 | [7 empty] | 0 | 0 | 18.7 | 10.74 | 5439.06
TS5500Shv | MW\33\002\D | MW | 33 | 2 | D | 8 Coal Mining | 30.3 | 0 | 30.3 | 2021-02-12 17:13 | 2021-02-13 12:03 | 22969.8764 | [6 empty] | 22970 | 17124 | 1.47 | 0 | 0 | 7.67 | 5740
PH4100XPC#1 | GG\12\003\B | GG | 12 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-02-13 08:31 | 2021-02-15 04:25 | 99379.6165 | 99380 | [7 empty] | 0 | 0 | 10.01 | 10.12 | 5499.21
TS5500Shv | MW\33\003\D | MW | 33 | 3 | D | 8 Coal Mining | 46.6 | 0 | 46.6 | 2021-02-13 12:03 | 2021-02-14 12:41 | 30039.266 | [6 empty] | 30039 | 22554 | 2.26 | 0 | 0 | 7.07 | 5793
PH4100A | RS\14\006\A | RS | 14 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-02-13 23:55 | 2021-02-18 18:10 | 198347.9584 | 198348 | [7 empty] | 0 | 0 | 19.86 | 16.55 | 4921
TS5500Shv | GG\09\020\D | GG | 9 | 20 | D | 8 Coal Mining | 36.2 | 0 | 36.2 | 2021-02-14 12:41 | 2021-02-15 07:37 | 23098.8528 | [6 empty] | 23099 | 17393 | 1.74 | 0 | 0 | 5.88 | 5872
PH4100XPC#1 | GG\12\004\X1 | GG | 12 | 4 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-02-15 04:25 | 2021-02-28 09:01 | 728805.2969 | 728805 | [7 empty] | 0 | 0 | 70.71 | 9.83 | 5400.26
TS5500Shv | GG\12\003\B | GG | 12 | 3 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-02-15 07:37 | 2021-02-16 04:10 | 25045.8876 | [6 empty] | 25046 | 18385 | 1.84 | 0 | 0 | 10.12 | 5499
TS5500Shv | MW\33\004\D | MW | 33 | 4 | D | 8 Coal Mining | 20.9 | 0 | 20.9 | 2021-02-16 04:10 | 2021-02-16 14:49 | 12996.3057 | [6 empty] | 12996 | 9812 | 0.98 | 0 | 0 | 6.4 | 5851
TS5500Shv | RS\14\005\A | RS | 14 | 5 | A | 8 Coal Mining | 20.3 | 0 | 20.3 | 2021-02-16 14:49 | 2021-02-16 23:30 | 10578.0443 | [6 empty] | 10578 | 7253 | 0.73 | 0 | 0 | 15.82 | 5012
DRE1 | MW\33\006\D | MW | 33 | 6 | D | 6 DL | 100 | 100 | 100 | 2021-02-16 20:53 | 2021-02-21 07:13 | 371428.4026 |  |  |  | 21199 | 371428 | 281638 |  |  | 0 | 30.26 | 0 | 5.69 | 5910.78
TS5500Exc | MW\37\003\A | MW | 37 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-02-16 21:07 | 2021-02-17 09:30 | 15586.086 | [6 empty] | 15586 | 11181 | 0.92 | 0 | 0 | 13.26 | 5111
TS6060#1 | GG\12\002\B | GG | 12 | 2 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-02-16 21:07 | 2021-02-17 19:38 | 30464.5174 | [6 empty] | 30465 | 22375 | 2.16 | 0 | 0 | 10.24 | 5497
TS5500Shv | MW\33\005\D | MW | 33 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-02-16 23:30 | 2021-02-17 22:59 | 28644.9238 | [6 empty] | 28645 | 21693 | 2.17 | 0 | 0 | 5.82 | 5900
TS Fleet 5 | MW\37\010\X | MW | 37 | 10 | X | 1 Prestrip - Thick | 93.4743 | 93.4743 | 93.4743 | 2021-02-17 04:05 | 2021-02-25 21:20 | 410109.552 | 410110 | [7 empty] | 0 | 0 | 37 | 12.16 | 5239.56
TS5500Exc | RS\15\003\X | RS | 15 | 3 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-02-17 09:30 | 2021-02-17 20:46 | 14190.8566 | [6 empty] | 14191 | 9908 | 1.54 | 0 | 0 | 13.28 | 5121
DRE2 | GG\09\022\D | GG | 9 | 22 | D | 6 DL | 100 | 100 | 100 | 2021-02-17 18:23 | 2021-02-23 06:12 | 443423.8112 |  |  |  | 10324 | 443424 | 196160 |  |  | 0 | 20.65 | 0 | 5.82 | 5872.52
TS6060#1 | GG\12\003\B | GG | 12 | 3 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-02-17 19:38 | 2021-02-18 16:10 | 27798.183 | [6 empty] | 27798 | 20406 | 2.04 | 0 | 0 | 10.12 | 5499
TS5500Exc | MW\33\003\D | MW | 33 | 3 | D | 8 Coal Mining | 53.4 | 0 | 53.4 | 2021-02-17 20:46 | 2021-02-19 00:06 | 34441.5572 | [6 empty] | 34442 | 25859 | 2.59 | 0 | 0 | 7.07 | 5793
TS5500Shv | GG\09\021\D | GG | 9 | 21 | D | 8 Coal Mining | 33.7 | 0 | 33.7 | 2021-02-17 22:59 | 2021-02-18 16:28 | 21318.8209 | [6 empty] | 21319 | 16078 | 1.61 | 0 | 0 | 5.79 | 5879
TS6060#1 | GG\09\020\D | GG | 9 | 20 | D | 8 Coal Mining | 63.8 | 0 | 63.8 | 2021-02-18 16:10 | 2021-02-19 22:16 | 40733.115 | [6 empty] | 40733 | 30671 | 3.07 | 0 | 0 | 5.88 | 5872
TS5500Shv | MW\37\008\A | MW | 37 | 8 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-02-18 16:28 | 2021-02-19 11:24 | 23093.5189 | [6 empty] | 23094 | 16809 | 1.69 | 0 | 0 | 12.83 | 5267
PH4100A | RS\15\003\A | RS | 15 | 3 | A | 1 Prestrip - Thick | 100 | 88.7935 | 88.7935 | 2021-02-18 18:10 | 2021-02-21 21:14 | 130301.6088 | 130302 | [7 empty] | 0 | 0 | 18.44 | 12.06 | 5362.45
TS5500Exc | MW\36\010\A | MW | 36 | 10 | A | 1 Prestrip - Thick | 2.5113 | 2.5113 | 2.5113 | 2021-02-19 00:06 | 2021-02-19 06:12 | 5396.6093 | 5397 | [7 empty] | 0 | 0 | 0.48 | 10.74 | 5439.06
TS5500Exc | MW\36\010\A | MW | 36 | 10 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-02-19 06:12 | 2021-02-20 21:24 | 49357.1129 | [6 empty] | 49357 | 36400 | 3.38 | 0 | 0 | 10.74 | 5439
TS5500Shv | RS\14\006\A | RS | 14 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-02-19 11:24 | 2021-02-20 08:11 | 25329.0569 | [6 empty] | 25329 | 17273 | 1.73 | 0 | 0 | 16.55 | 4921
TS6060#1 | GG\09\021\D | GG | 9 | 21 | D | 8 Coal Mining | 66.3 | 0 | 66.3 | 2021-02-19 22:16 | 2021-02-21 05:17 | 41983.317 | [6 empty] | 41983 | 31663 | 3.17 | 0 | 0 | 5.79 | 5879
TS5500Shv | MW\37\009\A | MW | 37 | 9 | A | 8 Coal Mining | 9.2 | 0 | 9.2 | 2021-02-20 08:11 | 2021-02-20 11:41 | 4281.0311 | [6 empty] | 4281 | 3130 | 0.31 | 0 | 0 | 12.19 | 5320
TS5500Shv | GG\12\012\B | GG | 12 | 12 | B | 1 Prestrip - Thick | 12.1038 | 12.1038 | 12.1038 | 2021-02-20 11:41 | 2021-02-23 04:09 | 69262.7352 | 69263 | [7 empty] | 0 | 0 | 7.2 | 10.26 | 5496.37
TS5500Exc | MW\33\004\D | MW | 33 | 4 | D | 8 Coal Mining | 79.1 | 0 | 79.1 | 2021-02-20 21:24 | 2021-02-22 12:24 | 49143.4332 | [6 empty] | 49143 | 37102 | 3.71 | 0 | 0 | 6.4 | 5851
TS6060#1 | RS\15\003\A | RS | 15 | 3 | A | 1 Prestrip - Thick | 37.2787 | 11.2065 | 11.2065 | 2021-02-21 05:17 | 2021-02-21 21:14 | 16445.106 | 16445 | [7 empty] | 0 | 0 | 2.33 | 12.06 | 5362.45
DRE1 | MW\33\007\D | MW | 33 | 7 | D | 6 DL | 100 | 100 | 100 | 2021-02-21 07:13 | 2021-02-25 16:56 | 369273.7296 |  |  |  | 21076 | 369274 | 280004 |  |  | 0 | 30.13 | 0 | 5.89 | 5893.45
PH4100A | RS\15\004\X | RS | 15 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-02-21 21:14 | 2021-03-02 22:10 | 360277.3587 | 360277 | [7 empty] | 0 | 0 | 35.59 | 13 | 5140.33
TS6060#1 | RS\16\004\X | RS | 16 | 4 | X | 1 Prestrip - Thick | 35.8965 | 35.8965 | 35.8965 | 2021-02-21 21:14 | 2021-02-27 12:07 | 135025.4354 | 135025 | [7 empty] | 0 | 0 | 13.34 | 12.77 | 5149.41
TS5500Exc | MW\37\004\A | MW | 37 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-02-22 12:24 | 2021-02-22 18:07 | 7189.5581 | [6 empty] | 7190 | 5171 | 0.56 | 0 | 0 | 12.7 | 5149
TS5500Exc | RS\14\005\A | RS | 14 | 5 | A | 8 Coal Mining | 79.7 | 0 | 79.7 | 2021-02-22 18:07 | 2021-02-24 03:04 | 41514.5307 | [6 empty] | 41515 | 28467 | 2.85 | 0 | 0 | 15.82 | 5012
TS5500Shv | MW\33\006\D | MW | 33 | 6 | D | 8 Coal Mining | 44.2 | 0 | 44.2 | 2021-02-23 04:09 | 2021-02-24 00:42 | 25061.6254 | [6 empty] | 25062 | 18978 | 1.9 | 0 | 0 | 5.69 | 5911
DRE2 | GG\09\023\D | GG | 9 | 23 | D | 6 DL | 100 | 100 | 100 | 2021-02-23 06:12 | 2021-02-28 18:11 | 443975.5285 |  |  |  | 10337 | 443976 | 196404 |  |  | 0 | 20.64 | 0 | 5.83 | 5860.82
TS5500Shv | GG\09\022\D | GG | 9 | 22 | D | 8 Coal Mining | 29.1 | 0 | 29.1 | 2021-02-24 00:42 | 2021-02-24 14:43 | 17102.7326 | [6 empty] | 17103 | 12919 | 1.29 | 0 | 0 | 5.82 | 5873
TS5500Exc | MW\33\005\D | MW | 33 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-02-24 03:04 | 2021-02-25 02:34 | 29589.262 | [6 empty] | 29589 | 22408 | 2.24 | 0 | 0 | 5.82 | 5900
TS5500Shv | GG\12\013\B | GG | 12 | 13 | B | 1 Prestrip - Thick | 12.4806 | 12.4806 | 12.4806 | 2021-02-24 14:43 | 2021-02-26 12:04 | 48523.1707 | 48523 | [7 empty] | 0 | 0 | 7.1 | 10.85 | 5449.6
TS5500Exc | RS\14\006\A | RS | 14 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-02-25 02:34 | 2021-02-25 23:20 | 26164.0808 | [6 empty] | 26164 | 17842 | 1.78 | 0 | 0 | 16.55 | 4921
DRE1 | MW\33\008\D | MW | 33 | 8 | D | 6 DL | 100 | 100 | 100 | 2021-02-25 16:56 | 2021-03-02 02:19 | 368128.9814 |  |  |  | 21010 | 368129 | 279136 |  |  | 0 | 30.03 | 0 | 5.97 | 5888.2
TS Fleet 5 | MW\37\003\B | MW | 37 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-02-25 21:20 | 2021-02-26 09:05 | 23041.1031 | 23041 | [7 empty] | 0 | 0 | 1.85 | 10.72 | 5411.78
TS5500Exc | RS\14\006\B | RS | 14 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-02-25 23:20 | 2021-02-27 08:34 | 29386.9432 | 29387 | [7 empty] | 0 | 0 | 2.94 | 9.43 | 5537.69
TS Fleet 5 | MW\37\004\B | MW | 37 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-02-26 09:05 | 2021-02-26 21:43 | 24765.2026 | 24765 | [7 empty] | 0 | 0 | 2.54 | 9.82 | 5477.74
TS5500Shv | MW\37\003\B | MW | 37 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-02-26 12:04 | 2021-02-26 22:42 | 12962.7098 | [6 empty] | 12963 | 9470 | 0.76 | 0 | 0 | 10.72 | 5412
TS Fleet 5 | MW\36\010\B | MW | 36 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-02-26 21:43 | 2021-02-27 12:54 | 29743.5954 | 29744 | [7 empty] | 0 | 0 | 2.79 | 8.91 | 5591.28
TS5500Shv | MW\37\004\B | MW | 37 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-02-26 22:42 | 2021-02-27 12:08 | 16388.2463 | [6 empty] | 16388 | 12033 | 1.22 | 0 | 0 | 9.82 | 5478
TS5500Exc | MW\37\003\B | MW | 37 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-02-27 08:34 | 2021-02-27 19:12 | 13390.0519 | [6 empty] | 13390 | 9782 | 0.79 | 0 | 0 | 10.72 | 5412
TS6060#1 | GG\09\022\D | GG | 9 | 22 | D | 8 Coal Mining | 70.9 | 0 | 70.9 | 2021-02-27 12:07 | 2021-02-28 18:56 | 41719.6196 | [6 empty] | 41720 | 31514 | 3.15 | 0 | 0 | 5.82 | 5873
TS5500Shv | RS\14\006\B | RS | 14 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-02-27 12:08 | 2021-02-28 04:11 | 19568.5327 | [6 empty] | 19569 | 13921 | 1.39 | 0 | 0 | 9.43 | 5538
TS Fleet 5 | MW\38\003\B | MW | 38 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-02-27 12:54 | 2021-03-03 02:50 | 168430.5468 | 168431 | [7 empty] | 0 | 0 | 15.56 | 10.48 | 5427.87
TS5500Exc | MW\36\010\B | MW | 36 | 10 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-02-27 19:12 | 2021-02-28 12:00 | 21170.9083 | [6 empty] | 21171 | 15736 | 1.49 | 0 | 0 | 8.91 | 5591
TS5500Shv | MW\36\010\B | MW | 36 | 10 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-02-28 04:11 | 2021-02-28 21:00 | 20495.241 | [6 empty] | 20495 | 15234 | 1.44 | 0 | 0 | 8.91 | 5591
PH4100XPC#1 | GG\12\005\X2 | GG | 12 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2021-02-28 09:01 | 2021-03-15 00:55 | 810729.5375 | 810730 | [7 empty] | 0 | 0 | 62.9 | 0 | 0
TS5500Exc | MW\37\005\B | MW | 37 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-02-28 12:00 | 2021-02-28 18:49 | 8583.4785 | [6 empty] | 8583 | 6274 | 0.64 | 0 | 0 | 10.73 | 5427
DRE2 | GG\09\024\D | GG | 9 | 24 | D | 6 DL | 100 | 100 | 100 | 2021-02-28 18:11 | 2021-03-06 15:18 | 474676.5958 |  |  |  | 11052 | 474677 | 209985 |  |  | 0 | 22.08 | 0 | 6.02 | 5854.58
TS5500Exc | MW\37\004\B | MW | 37 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-02-28 18:49 | 2021-03-01 08:15 | 16928.5181 | [6 empty] | 16929 | 12430 | 1.26 | 0 | 0 | 9.82 | 5478
TS6060#1 | GG\12\004\X1 | GG | 12 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2021-02-28 18:56 | 2021-03-01 08:19 | 18118.0184 | [6 empty] | 18118 | 13488 | 1.37 | 0 | 0 | 9.83 | 5400
TS5500Shv | GG\09\023\D | GG | 9 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-02-28 21:00 | 2021-03-02 13:28 | 49354.5121 | [6 empty] | 49355 | 37406 | 3.68 | 0 | 0 | 5.83 | 5861
TS5500Exc | RS\14\007\A | RS | 14 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-03-01 08:15 | 2021-03-03 03:09 | 54021.9593 | [6 empty] | 54022 | 36991 | 3.47 | 0 | 0 | 16.74 | 4906
TS6060#1 | RS\16\007\X | RS | 16 | 7 | X | 1 Prestrip - Thick | 32.3515 | 32.3515 | 32.3515 | 2021-03-01 08:19 | 2021-03-08 19:09 | 181144.3538 | 181144 | [7 empty] | 0 | 0 | 17.69 | 9.83 | 5378.32
DRE1 | MW\33\009\D | MW | 33 | 9 | D | 6 DL | 100 | 100 | 100 | 2021-03-02 02:19 | 2021-03-06 03:00 | 337700.3504 |  |  |  | 17362 | 337700 | 272012 |  |  | 0 | 28.96 | 0 | 5.7 | 5911.44
TS5500Shv | MW\33\007\D | MW | 33 | 7 | D | 8 Coal Mining | 37.8 | 0 | 37.8 | 2021-03-02 13:28 | 2021-03-03 07:32 | 22038.0568 | [6 empty] | 22038 | 16649 | 1.66 | 0 | 0 | 5.89 | 5893
PH4100A | RS\14\005\B | RS | 14 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-03-02 22:10 | 2021-03-03 17:10 | 32983.4564 | 32983 | [7 empty] | 0 | 0 | 3.3 | 9.33 | 5562.44
TS Fleet 5 | MW\38\004\B | MW | 38 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-03-03 02:50 | 2021-03-05 18:45 | 125287.1059 | 125287 | [7 empty] | 0 | 0 | 13.8 | 10.67 | 5404.28
TS5500Exc | RS\15\004\X | RS | 15 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-03-03 03:09 | 2021-03-03 17:54 | 18578.2179 | [6 empty] | 18578 | 12983 | 1.29 | 0 | 0 | 13 | 5140
TS5500Shv | MW\38\003\B | MW | 38 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-03-03 07:32 | 2021-03-03 18:35 | 13469.1756 | [6 empty] | 13469 | 9860 | 0.89 | 0 | 0 | 10.48 | 5428
PH4100A | RS\14\007\B | RS | 14 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-03-03 17:10 | 2021-03-04 09:56 | 29112.8383 | 29113 | [7 empty] | 0 | 0 | 2.74 | 9.45 | 5549.33
TS5500Exc | MW\33\006\D | MW | 33 | 6 | D | 8 Coal Mining | 55.8 | 0 | 55.8 | 2021-03-03 17:54 | 2021-03-04 19:02 | 31658.6586 | [6 empty] | 31659 | 23974 | 2.4 | 0 | 0 | 5.69 | 5911
TS5500Shv | RS\14\005\B | RS | 14 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-03-03 18:35 | 2021-03-05 04:02 | 40781.7721 | [6 empty] | 40782 | 29118 | 2.91 | 0 | 0 | 9.33 | 5562
PH4100A | RS\15\004\A | RS | 15 | 4 | A | 1 Prestrip - Thick | 100 | 96.273 | 96.273 | 2021-03-04 09:56 | 2021-03-09 02:29 | 195378.957 | 195379 | [7 empty] | 0 | 0 | 19.45 | 14.12 | 5175.36
TS5500Exc | RS\14\007\B | RS | 14 | 7 | B | 8 Coal Mining | 100 | 0 | 71.4 | 2021-03-04 19:02 | 2021-03-05 17:55 | 28826.223 | [6 empty] | 28826 | 20486 | 1.93 | 0 | 0 | 9.45 | 5549
TS5500Shv | RS\14\007\B | RS | 14 | 7 | B | 8 Coal Mining | 28.6 | 0 | 28.6 | 2021-03-05 04:02 | 2021-03-05 13:29 | 11531.6359 | [6 empty] | 11532 | 8195 | 0.77 | 0 | 0 | 9.45 | 5549
TS5500Shv | GG\13\002\X1 | GG | 13 | 2 | X1 | 1 Prestrip - Thick | 18.0069 | 18.0069 | 18.0069 | 2021-03-05 13:29 | 2021-03-12 07:46 | 173434.3624 | 173434 | [7 empty] | 0 | 0 | 15.36 | 10.65 | 5323.37
TS5500Exc | RS\14\006\B | RS | 14 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-03-05 17:55 | 2021-03-06 09:58 | 20213.6492 | [6 empty] | 20214 | 14379 | 1.44 | 0 | 0 | 9.43 | 5538
TS Fleet 5 | MW\38\005\D | MW | 38 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-03-05 18:45 | 2021-03-08 13:07 | 130068.9623 | 130069 | [7 empty] | 0 | 0 | 13.5 | 6.15 | 5872.06
DRE1 | MW\33\010\D | MW | 33 | 10 | D | 6 DL | 100 | 100 | 100 | 2021-03-06 03:00 | 2021-03-11 16:14 | 465442.2044 |  |  |  | 16739 | 465442 | 261812 |  |  | 0 | 29.77 | 0 | 5.42 | 5935.62
TS5500Exc | MW\37\006\A | MW | 37 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-03-06 09:58 | 2021-03-06 15:55 | 7505.6162 | [6 empty] | 7506 | 5447 | 0.56 | 0 | 0 | 13.11 | 5221
DRE2 | GG\11\011\B | GG | 11 | 11 | B | 6 DL | 100 | 0 | 100 | 2021-03-06 15:18 | 2021-03-09 08:06 | 217975.2308 |  |  |  |  | 217975 | 167673 |  |  | 0 | 16.79 | 0 | 9.86 | 5524.15
TS5500Exc | RS\15\003\A | RS | 15 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-03-06 15:55 | 2021-03-07 21:38 | 37422.2904 | [6 empty] | 37422 | 26301 | 3.39 | 0 | 0 | 12.06 | 5362
TS5500Exc | MW\33\007\D | MW | 33 | 7 | D | 8 Coal Mining | 62.2 | 0 | 62.2 | 2021-03-07 21:38 | 2021-03-09 02:28 | 36323.8797 | [6 empty] | 36324 | 27442 | 2.74 | 0 | 0 | 5.89 | 5893
TS Fleet 5 | MW\38\006\B | MW | 38 | 6 | B | 1 Prestrip - Thick | 93.639 | 93.639 | 93.639 | 2021-03-08 13:07 | 2021-03-13 15:03 | 239000.8577 | 239001 | [7 empty] | 0 | 0 | 25.28 | 8.57 | 5604.97
TS6060#1 | RS\15\004\A | RS | 15 | 4 | A | 1 Prestrip - Thick | 37.2787 | 3.727 | 3.727 | 2021-03-08 19:09 | 2021-03-09 02:29 | 7563.6075 | 7564 | [7 empty] | 0 | 0 | 0.75 | 14.12 | 5175.36
TS5500Exc | MW\37\006\B | MW | 37 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-03-09 02:28 | 2021-03-10 20:29 | 37155.3168 | 37155 | [7 empty] | 0 | 0 | 3.75 | 8.72 | 5592.17
PH4100A | RS\15\003\B | RS | 15 | 3 | B | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2021-03-09 02:29 | 2021-03-09 09:19 | 11876.0389 | 11876 | [7 empty] | 0 | 0 | 1.5 | 8.69 | 5651.07
TS6060#1 | RS\15\003\B | RS | 15 | 3 | B | 1 Prestrip - Thick | 37.2787 | 37.2787 | 37.2787 | 2021-03-09 02:29 | 2021-03-09 09:19 | 7058.5812 | 7059 | [7 empty] | 0 | 0 | 0.89 | 8.69 | 5651.07
DRE2 | GG\11\010\B | GG | 11 | 10 | B | 6 DL | 100 | 0 | 100 | 2021-03-09 08:06 | 2021-03-11 20:04 | 201703.845 |  |  |  |  | 201704 | 168087 |  |  | 0 | 17.49 | 0 | 9.95 | 5508.56
PH4100A | RS\15\005\X | RS | 15 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-03-09 09:19 | 2021-03-20 00:26 | 428671.7486 | 428672 | [7 empty] | 0 | 0 | 42.53 | 12.42 | 5185.89
TS6060#1 | GG\09\024\D | GG | 9 | 24 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-03-09 09:19 | 2021-03-11 04:02 | 57798.0957 | [6 empty] | 57798 | 43905 | 4.41 | 0 | 0 | 6.02 | 5855
TS5500Exc | RS\15\003\B | RS | 15 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-03-10 20:29 | 2021-03-11 10:16 | 17363.2745 | [6 empty] | 17363 | 12374 | 1.53 | 0 | 0 | 8.69 | 5651
TS6060#1 | GG\11\011\B | GG | 11 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-03-11 04:02 | 2021-03-12 16:33 | 49430.2491 | [6 empty] | 49430 | 36312 | 3.64 | 0 | 0 | 9.86 | 5524
TS5500Exc | RS\15\004\A | RS | 15 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-03-11 10:16 | 2021-03-12 05:53 | 24704.913 | [6 empty] | 24705 | 17150 | 1.71 | 0 | 0 | 14.12 | 5175
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2021-03-11 16:14 | 2021-03-13 16:14
DRE2 | GG\11\009\B | GG | 11 | 9 | B | 6 DL | 100 | 0 | 100 | 2021-03-11 20:04 | 2021-03-14 14:45 | 224274.4683 |  |  |  |  | 224274 | 186895 |  |  | 0 | 18.65 | 0 | 10.1 | 5498.61
TS5500Exc | MW\37\006\B | MW | 37 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-03-12 05:53 | 2021-03-13 15:04 | 41803.4689 | [6 empty] | 41803 | 30880 | 3.08 | 0 | 0 | 8.72 | 5592
TS5500Shv | RS\15\003\B | RS | 15 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-03-12 07:46 | 2021-03-12 21:33 | 16809.1275 | [6 empty] | 16809 | 11979 | 1.48 | 0 | 0 | 8.69 | 5651
TS6060#1 | GG\11\010\B | GG | 11 | 10 | B | 8 Coal Mining | 51.4 | 0 | 51.4 | 2021-03-12 16:33 | 2021-03-13 11:33 | 25716.9293 | [6 empty] | 25717 | 18889 | 1.89 | 0 | 0 | 9.95 | 5509
TS5500Shv | RS\15\004\A | RS | 15 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-03-12 21:33 | 2021-03-13 17:10 | 23916.4583 | [6 empty] | 23916 | 16603 | 1.65 | 0 | 0 | 14.12 | 5175
TS6060#1 | MW\33\010\D | MW | 33 | 10 | D | 7 PostStrip | 48.4203 | 0 | 48.4203 | 2021-03-13 11:33 | 2021-03-14 13:57 | 27230.7677 |  |  | 27231 | [5 empty] | 0 | 0 | 0 | 5.42 | 5935.62
TS Fleet 5 | MW\38\007\A | MW | 38 | 7 | A | 1 Prestrip - Thick | 73.9845 | 73.9845 | 73.9845 | 2021-03-13 15:03 | 2021-03-18 07:05 | 219600.9124 | 219601 | [7 empty] | 0 | 0 | 22.27 | 12.19 | 5306.29
TS5500Exc | MW\33\008\D | MW | 33 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-03-13 15:04 | 2021-03-15 15:40 | 61222.2316 | [6 empty] | 61222 | 46219 | 4.62 | 0 | 0 | 5.97 | 5888
DRE1 | RS\12\003\D | RS | 12 | 3 | D | 6 DL | 100 | 100 | 100 | 2021-03-13 16:14 | 2021-03-17 05:57 | 299403.7247 |  |  |  | 13396 | 299404 | 254527 |  |  | 0 | 24.66 | 0 | 6.35 | 5862.79
TS5500Shv | MW\33\009\D | MW | 33 | 9 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-03-13 17:10 | 2021-03-14 17:25 | 29562.2886 | [6 empty] | 29562 | 22389 | 2.24 | 0 | 0 | 5.7 | 5911
TS6060#1 | RS\15\004\B | RS | 15 | 4 | B | 1 Prestrip - Thick | 37.2787 | 37.2787 | 37.2787 | 2021-03-14 13:57 | 2021-03-15 00:01 | 10389.3116 | 10389 | [7 empty] | 0 | 0 | 1.03 | 9.1 | 5601.25
DRE2 | GG\11\008\B | GG | 11 | 8 | B | 6 DL | 100 | 0 | 100 | 2021-03-14 14:45 | 2021-03-17 11:46 | 232156.9377 |  |  |  |  | 232157 | 193464 |  |  | 0 | 19.46 | 0 | 10.45 | 5470.37
TS5500Shv | GG\11\010\B | GG | 11 | 10 | B | 8 Coal Mining | 48.6 | 0 | 48.6 | 2021-03-14 17:25 | 2021-03-15 13:21 | 24307.8977 | [6 empty] | 24308 | 17854 | 1.79 | 0 | 0 | 9.95 | 5509
TS6060#1 | GG\11\009\B | GG | 11 | 9 | B | 8 Coal Mining | 62.8 | 0 | 62.8 | 2021-03-15 00:01 | 2021-03-16 00:07 | 32616.0369 | [6 empty] | 32616 | 23881 | 2.39 | 0 | 0 | 10.1 | 5499
PH4100XPC#1 | GG\12\004\X2 | GG | 12 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2021-03-15 00:55 | 2021-03-17 07:33 | 123660.855 | 123661 | [7 empty] | 0 | 0 | 12.53 | 0 | 0
TS5500Shv | GG\11\009\B | GG | 11 | 9 | B | 8 Coal Mining | 37.2 | 0 | 37.2 | 2021-03-15 13:21 | 2021-03-16 05:11 | 19308.0201 | [6 empty] | 19308 | 14137 | 1.42 | 0 | 0 | 10.1 | 5499
TS5500Exc | MW\37\007\A | MW | 37 | 7 | A | 8 Coal Mining | 60.3 | 0 | 60.3 | 2021-03-15 15:40 | 2021-03-16 14:24 | 28625.4136 | [6 empty] | 28625 | 20931 | 2.12 | 0 | 0 | 11.89 | 5331
TS6060#1 | RS\17\003\X | RS | 17 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-03-16 00:07 | 2021-03-23 17:25 | 184236.4782 | 184236 | [7 empty] | 0 | 0 | 29.5 | 12.86 | 5138.82
TS5500Shv | MW\33\010\D | MW | 33 | 10 | D | 7 PostStrip | 51.5797 | 0 | 51.5797 | 2021-03-16 05:11 | 2021-03-17 08:14 | 29007.557 |  |  | 29008 | [5 empty] | 0 | 0 | 0 | 5.42 | 5935.62
TS5500Exc | MW\33\009\D | MW | 33 | 9 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-03-16 14:24 | 2021-03-17 14:38 | 30536.8695 | [6 empty] | 30537 | 23127 | 2.31 | 0 | 0 | 5.7 | 5911
DRE1 | RS\12\004\D | RS | 12 | 4 | D | 6 DL | 100 | 100 | 100 | 2021-03-17 05:57 | 2021-03-20 12:23 | 273966.189 |  |  |  | 12258 | 273966 | 232902 |  |  | 0 | 24.52 | 0 | 6.84 | 5819.38
PH4100XPC#1 | GG\12\004\B | GG | 12 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-03-17 07:33 | 2021-03-19 17:49 | 131888.3679 | 131888 | [7 empty] | 0 | 0 | 13.3 | 11.06 | 5389.07
TS5500Shv | MW\33\010\D | MW | 33 | 10 | D | 8 Coal Mining | 60.1 | 0 | 60.1 | 2021-03-17 08:14 | 2021-03-18 16:52 | 39794.5463 | [6 empty] | 39795 | 30260 | 2.73 | 0 | 0 | 5.42 | 5936
DRE2 | GG\11\007\B | GG | 11 | 7 | B | 6 DL | 100 | 0 | 100 | 2021-03-17 11:46 | 2021-03-20 09:26 | 234329.8281 |  |  |  |  | 234330 | 195275 |  |  | 0 | 19.95 | 0 | 10.83 | 5403.76
TS5500Exc | MW\37\008\A | MW | 37 | 8 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-03-17 14:38 | 2021-03-18 09:35 | 23854.8437 | [6 empty] | 23855 | 17363 | 1.75 | 0 | 0 | 12.83 | 5267
TS Fleet 5 | MW\37\007\B | MW | 37 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-03-18 07:05 | 2021-03-19 09:36 | 51951.8588 | 51952 | [7 empty] | 0 | 0 | 5.23 | 9.43 | 5513.14
TS5500Exc | MW\33\010\D | MW | 33 | 10 | D | 8 Coal Mining | 39.9 | 0 | 39.9 | 2021-03-18 09:35 | 2021-03-19 06:32 | 26391.4093 | [6 empty] | 26391 | 20068 | 1.81 | 0 | 0 | 5.42 | 5936
TS5500Shv | RS\12\003\D | RS | 12 | 3 | D | 8 Coal Mining | 65.8 | 0 | 65.8 | 2021-03-18 16:52 | 2021-03-20 04:40 | 43650.5707 | [6 empty] | 43651 | 31927 | 2.93 | 0 | 0 | 6.35 | 5863
TS5500Exc | RS\12\003\D | RS | 12 | 3 | D | 8 Coal Mining | 34.2 | 0 | 34.2 | 2021-03-19 06:32 | 2021-03-20 00:33 | 22708.5345 | [6 empty] | 22709 | 16609 | 1.53 | 0 | 0 | 6.35 | 5863
TS Fleet 5 | MW\37\008\B | MW | 37 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-03-19 09:36 | 2021-03-20 07:33 | 43015.263 | 43015 | [7 empty] | 0 | 0 | 4.32 | 10 | 5445.45
PH4100XPC#1 | GG\12\005\B | GG | 12 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-03-19 17:49 | 2021-03-19 18:26 | 1390.7751 | 1391 | [7 empty] | 0 | 0 | 0.14 | 11.98 | 5277.75
PH4100XPC#1 | GG\12\006\X1 | GG | 12 | 6 | X1 | 1 Prestrip - Thick | 100 | 85.9106 | 85.9106 | 2021-03-19 18:26 | 2021-03-28 15:17 | 480838.5267 | 480839 | [7 empty] | 0 | 0 | 46.62 | 10.7 | 5373.89
PH4100A | RS\15\004\B | RS | 15 | 4 | B | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2021-03-20 00:26 | 2021-03-20 10:31 | 17479.9814 | 17480 | [7 empty] | 0 | 0 | 1.74 | 9.1 | 5601.25
TS5500Exc | RS\15\005\X | RS | 15 | 5 | X | 8 Coal Mining | 65.1 | 0 | 65.1 | 2021-03-20 00:33 | 2021-03-20 09:58 | 11851.3819 | [6 empty] | 11851 | 8309 | 0.83 | 0 | 0 | 12.42 | 5186
TS5500Shv | GG\12\004\B | GG | 12 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-03-20 04:40 | 2021-03-21 22:56 | 51526.8449 | [6 empty] | 51527 | 37626 | 3.77 | 0 | 0 | 11.06 | 5389
TS Fleet 5 | MW\38\008\A | MW | 38 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-03-20 07:33 | 2021-03-28 13:03 | 387126.564 | 387127 | [7 empty] | 0 | 0 | 38.49 | 13.08 | 5246.07
DRE2 | GG\11\006\B | GG | 11 | 6 | B | 6 DL | 100 | 0 | 100 | 2021-03-20 09:26 | 2021-03-23 08:04 | 237620.3087 |  |  |  |  | 237620 | 198017 |  |  | 0 | 19.75 | 0 | 11.61 | 5302.51
TS5500Exc | MW\37\007\B | MW | 37 | 7 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-03-20 09:58 | 2021-03-21 02:07 | 20337.3389 | [6 empty] | 20337 | 14986 | 1.5 | 0 | 0 | 9.43 | 5513
PH4100A | RS\15\006\X | RS | 15 | 6 | X | 1 Prestrip - Thick | 100 | 73.7363 | 73.7363 | 2021-03-20 10:31 | 2021-03-29 04:46 | 354624.218 | 354624 | [7 empty] | 0 | 0 | 35.02 | 11.12 | 5290.59
DRE1 | RS\12\005\D | RS | 12 | 5 | D | 6 DL | 100 | 100 | 100 | 2021-03-20 12:23 | 2021-03-24 04:25 | 307538.7207 |  |  |  | 15812 | 307539 | 247718 |  |  | 0 | 26.35 | 0 | 7.06 | 5800.92
TS5500Exc | RS\15\004\B | RS | 15 | 4 | B | 8 Coal Mining | 80.2 | 0 | 80.2 | 2021-03-21 02:07 | 2021-03-22 04:53 | 33718.0849 | [6 empty] | 33718 | 24096 | 2.4 | 0 | 0 | 9.1 | 5601
TS5500Shv | RS\15\005\X | RS | 15 | 5 | X | 8 Coal Mining | 34.9 | 0 | 34.9 | 2021-03-21 22:56 | 2021-03-22 04:08 | 6359.5896 | [6 empty] | 6360 | 4459 | 0.45 | 0 | 0 | 12.42 | 5186
TS5500Shv | RS\15\004\B | RS | 15 | 4 | B | 8 Coal Mining | 19.8 | 0 | 19.8 | 2021-03-22 04:08 | 2021-03-22 10:59 | 8334.0781 | [6 empty] | 8334 | 5956 | 0.59 | 0 | 0 | 9.1 | 5601
TS5500Exc | MW\37\008\B | MW | 37 | 8 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-03-22 04:53 | 2021-03-22 20:20 | 19462.6449 | [6 empty] | 19463 | 14326 | 1.43 | 0 | 0 | 10 | 5445
TS5500Shv | MW\37\007\B | MW | 37 | 7 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-03-22 10:59 | 2021-03-23 03:07 | 19688.2749 | [6 empty] | 19688 | 14508 | 1.45 | 0 | 0 | 9.43 | 5513
TS5500Exc | MW\37\009\A | MW | 37 | 9 | A | 8 Coal Mining | 90.8 | 0 | 90.8 | 2021-03-22 20:20 | 2021-03-24 05:55 | 42293.4252 | [6 empty] | 42293 | 30925 | 3.1 | 0 | 0 | 12.19 | 5320
TS5500Shv | MW\37\008\B | MW | 37 | 8 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-03-23 03:07 | 2021-03-23 18:34 | 18841.4967 | [6 empty] | 18841 | 13869 | 1.39 | 0 | 0 | 10 | 5445
DRE2 | GG\11\005\B | GG | 11 | 5 | B | 6 DL | 100 | 0 | 100 | 2021-03-23 08:04 | 2021-03-25 14:50 | 184223.5985 |  |  |  |  | 184224 | 160194 |  |  | 0 | 16 | 0 | 11.88 | 5282.96
TS6060#1 | RS\15\005\A | RS | 15 | 5 | A | 1 Prestrip - Thick | 37.2787 | 37.2787 | 37.2787 | 2021-03-23 17:25 | 2021-03-26 15:20 | 72137.909 | 72138 | [7 empty] | 0 | 0 | 7.21 | 16.6 | 4947.12
TS5500Shv | GG\11\007\B | GG | 11 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-03-23 18:34 | 2021-03-25 13:13 | 52008.7147 | [6 empty] | 52009 | 37938 | 3.8 | 0 | 0 | 10.83 | 5404
DRE1 | RS\12\006\D | RS | 12 | 6 | D | 6 DL | 100 | 100 | 100 | 2021-03-24 04:25 | 2021-03-27 21:36 | 311515.5099 |  |  |  | 16016 | 311516 | 250921 |  |  | 0 | 26.7 | 0 | 7.37 | 5773
TS5500Exc | RS\12\005\D | RS | 12 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-03-24 05:55 | 2021-03-25 06:57 | 31542.6184 | [6 empty] | 31543 | 22912 | 2.29 | 0 | 0 | 7.06 | 5801
TS5500Exc | MW\37\009\B | MW | 37 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-03-25 06:57 | 2021-03-26 19:56 | 32705.6303 | 32706 | [7 empty] | 0 | 0 | 3.27 | 9.44 | 5517.37
TS5500Shv | GG\11\006\B | GG | 11 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-03-25 13:13 | 2021-03-27 07:04 | 51028.7959 | [6 empty] | 51029 | 37133 | 3.72 | 0 | 0 | 11.61 | 5303
DRE2 | GG\10\011\D | GG | 10 | 11 | D | 6 DL | 100 | 100 | 100 | 2021-03-25 14:50 | 2021-03-31 23:20 | 512988.7801 |  |  |  | 9311 | 512989 | 223459 |  |  | 0 | 23.28 | 0 | 6.02 | 5860.02
TS6060#1 | GG\11\008\B | GG | 11 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-03-26 15:20 | 2021-03-28 06:44 | 53336.3448 | [6 empty] | 53336 | 38894 | 3.89 | 0 | 0 | 10.45 | 5470
TS5500Exc | MW\37\009\B | MW | 37 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-03-26 19:56 | 2021-03-28 03:05 | 39241.3079 | [6 empty] | 39241 | 29017 | 2.9 | 0 | 0 | 9.44 | 5517
TS5500Shv | GG\11\005\B | GG | 11 | 5 | B | 8 Coal Mining | 49.8 | 0 | 49.8 | 2021-03-27 07:04 | 2021-03-28 03:53 | 25387.0214 | [6 empty] | 25387 | 18464 | 1.85 | 0 | 0 | 11.88 | 5283
DRE1 | RS\12\007\D | RS | 12 | 7 | D | 6 DL | 100 | 100 | 100 | 2021-03-27 21:36 | 2021-04-01 18:08 | 407071.3353 |  |  |  | 15169 | 407071 | 230873 |  |  | 0 | 26.45 | 0 | 7.64 | 5747.95
TS5500Exc | RS\12\006\D | RS | 12 | 6 | D | 8 Coal Mining | 77.7 | 0 | 77.7 | 2021-03-28 03:05 | 2021-03-29 17:06 | 47882.9468 | [6 empty] | 47883 | 34726 | 3.47 | 0 | 0 | 7.37 | 5773
TS5500Shv | RS\12\004\D | RS | 12 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-03-28 03:53 | 2021-03-30 06:23 | 61575.0251 | [6 empty] | 61575 | 44725 | 4.47 | 0 | 0 | 6.84 | 5819
TS6060#1 | GG\11\005\B | GG | 11 | 5 | B | 8 Coal Mining | 50.2 | 0 | 50.2 | 2021-03-28 06:44 | 2021-03-29 01:40 | 25620.6615 | [6 empty] | 25621 | 18634 | 1.86 | 0 | 0 | 11.88 | 5283
TS Fleet 5 | MW\38\009\A | MW | 38 | 9 | A | 1 Prestrip - Thick | 96.0946 | 96.0946 | 96.0946 | 2021-03-28 13:03 | 2021-04-07 16:23 | 476913.3494 | 476913 | [7 empty] | 0 | 0 | 46.88 | 12.16 | 5321.7
PH4100XPC#1 | GG\12\007\X1 | GG | 12 | 7 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-03-28 15:17 | 2021-04-06 23:51 | 503659.5299 | 503660 | [7 empty] | 0 | 0 | 48.89 | 10.75 | 5412.99
TS6060#1 | GG\12\006\X1 | GG | 12 | 6 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-03-29 01:40 | 2021-03-29 08:28 | 9204.0231 | [6 empty] | 9204 | 6817 | 0.67 | 0 | 0 | 10.7 | 5374
PH4100A | RS\15\005\A | RS | 15 | 5 | A | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2021-03-29 04:46 | 2021-04-01 02:41 | 121371.7872 | 121372 | [7 empty] | 0 | 0 | 12.13 | 16.6 | 4947.12
TS6060#1 | RS\17\004\X | RS | 17 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-03-29 08:28 | 2021-04-14 16:05 | 392977.1116 | 392977 | [7 empty] | 0 | 0 | 38.98 | 12.74 | 5150.17
TS5500Exc | RS\15\006\X | RS | 15 | 6 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-03-29 17:06 | 2021-03-30 00:19 | 9083.1377 | [6 empty] | 9083 | 6437 | 0.64 | 0 | 0 | 11.12 | 5291
TS5500Exc | MW\37\010\X | MW | 37 | 10 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-03-30 00:19 | 2021-03-30 15:04 | 18590.1677 | [6 empty] | 18590 | 13560 | 1.29 | 0 | 0 | 12.16 | 5240
TS5500Shv | RS\15\006\X | RS | 15 | 6 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-03-30 06:23 | 2021-03-30 13:36 | 8793.2503 | [6 empty] | 8793 | 6232 | 0.62 | 0 | 0 | 11.12 | 5291
TS5500Shv | GG\12\006\X1 | GG | 12 | 6 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-03-30 13:36 | 2021-03-30 20:24 | 8292.7337 | [6 empty] | 8293 | 6142 | 0.6 | 0 | 0 | 10.7 | 5374
TS5500Exc | MW\38\003\B | MW | 38 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-03-30 15:04 | 2021-03-31 02:07 | 13913.2143 | [6 empty] | 13913 | 10185 | 0.92 | 0 | 0 | 10.48 | 5428
TS5500Shv | RS\12\005\D | RS | 12 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-03-30 20:24 | 2021-03-31 21:26 | 30535.9391 | [6 empty] | 30536 | 22180 | 2.22 | 0 | 0 | 7.06 | 5801
TS5500Exc | MW\38\004\B | MW | 38 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-03-31 02:07 | 2021-03-31 11:22 | 11643.8011 | [6 empty] | 11644 | 8512 | 0.88 | 0 | 0 | 10.67 | 5404
TS5500Exc | MW\38\006\B | MW | 38 | 6 | B | 8 Coal Mining | 92.3 | 0 | 92.3 | 2021-03-31 11:22 | 2021-04-01 17:00 | 37343.5048 | [6 empty] | 37344 | 27601 | 2.78 | 0 | 0 | 8.57 | 5605
TS5500Shv | RS\12\006\D | RS | 12 | 6 | D | 8 Coal Mining | 22.3 | 0 | 22.3 | 2021-03-31 21:26 | 2021-04-01 08:42 | 13728.2249 | [6 empty] | 13728 | 9956 | 1 | 0 | 0 | 7.37 | 5773
DRE2 | GG\10\010\D | GG | 10 | 10 | D | 6 DL | 100 | 100 | 100 | 2021-03-31 23:20 | 2021-04-07 00:21 | 487775.6731 |  |  |  | 11357 | 487776 | 215780 |  |  | 0 | 22.73 | 0 | 6.15 | 5848.66
PH4100A | RS\15\006\A | RS | 15 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-01 02:41 | 2021-04-05 19:45 | 196295.8063 | 196296 | [7 empty] | 0 | 0 | 19.63 | 17.3 | 4865.08
TS5500Shv | RS\15\005\A | RS | 15 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-04-01 08:42 | 2021-04-02 05:43 | 25627.4335 | [6 empty] | 25627 | 17486 | 1.75 | 0 | 0 | 16.6 | 4947
TS5500Exc | RS\15\005\A | RS | 15 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-04-01 17:00 | 2021-04-02 14:01 | 26472.294 | [6 empty] | 26472 | 18062 | 1.81 | 0 | 0 | 16.6 | 4947
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2021-04-01 18:08 | 2021-04-03 18:08
TS5500Shv | GG\10\011\D | GG | 10 | 11 | D | 8 Coal Mining | 23.9 | 0 | 23.9 | 2021-04-02 05:43 | 2021-04-02 18:25 | 15480.552 | [6 empty] | 15481 | 11619 | 1.16 | 0 | 0 | 6.02 | 5860
TS5500Exc | RS\12\007\D | RS | 12 | 7 | D | 7 PostStrip | 98.6355 | 0 | 98.6355 | 2021-04-02 14:01 | 2021-04-05 05:59 | 56560.8685 |  |  | 56561 | [5 empty] | 0 | 0 | 0 | 7.64 | 5747.95
TS5500Shv | RS\12\007\D | RS | 12 | 7 | D | 7 PostStrip | 1.3645 | 0 | 1.3645 | 2021-04-02 18:25 | 2021-04-02 19:08 | 782.4524 |  |  | 782 | [5 empty] | 0 | 0 | 0 | 7.64 | 5747.95
TS5500Shv | MW\38\004\B | MW | 38 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-04-02 19:08 | 2021-04-03 04:23 | 11272.1905 | [6 empty] | 11272 | 8241 | 0.85 | 0 | 0 | 10.67 | 5404
TS5500Shv | MW\38\006\B | MW | 38 | 6 | B | 8 Coal Mining | 7.7 | 0 | 7.7 | 2021-04-03 04:23 | 2021-04-03 06:57 | 3119.899 | [6 empty] | 3120 | 2306 | 0.23 | 0 | 0 | 8.57 | 5605
TS5500Shv | MW\38\007\A | MW | 38 | 7 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-04-03 06:57 | 2021-04-04 02:24 | 23717.0175 | [6 empty] | 23717 | 17310 | 1.74 | 0 | 0 | 12.19 | 5306
DRE1 | MW\34\002\D | MW | 34 | 2 | D | 6 DL | 100 | 0 | 100 | 2021-04-03 18:08 | 2021-04-08 15:45 | 410848.334 |  |  |  | 29219 | 410848 | 295434 |  |  | 0 | 35 | 0 | 7.49 | 5755.68
TS5500Shv | RS\17\003\X | RS | 17 | 3 | X | 8 Coal Mining | 79.4 | 0 | 79.4 | 2021-04-04 02:24 | 2021-04-04 09:52 | 9105.6097 | [6 empty] | 9106 | 6368 | 0.97 | 0 | 0 | 12.86 | 5139
TS5500Shv | GG\13\006\X1 | GG | 13 | 6 | X1 | 1 Prestrip - Thick | 32.1634 | 32.1634 | 32.1634 | 2021-04-04 09:52 | 2021-04-11 16:26 | 186789.3028 | 186789 | [7 empty] | 0 | 0 | 18.34 | 10.69 | 5371.03
TS5500Exc | RS\12\007\D | RS | 12 | 7 | D | 8 Coal Mining | 78.3 | 0 | 78.3 | 2021-04-05 05:59 | 2021-04-07 01:00 | 54196.5649 | [6 empty] | 54197 | 39259 | 3.43 | 0 | 0 | 7.64 | 5748
PH4100A | RS\15\005\B | RS | 15 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-05 19:45 | 2021-04-06 14:02 | 31754.9333 | 31755 | [7 empty] | 0 | 0 | 3.17 | 9.28 | 5564.26
PH4100A | RS\15\007\X | RS | 15 | 7 | X | 1 Prestrip - Thick | 100 | 69.2717 | 69.2717 | 2021-04-06 14:02 | 2021-04-16 12:28 | 403525.0125 | 403525 | [7 empty] | 0 | 0 | 36.2 | 9.76 | 5384.18
PH4100XPC#1 | GG\12\006\X2 | GG | 12 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2021-04-06 23:51 | 2021-04-08 21:15 | 102765.647 | 102766 | [7 empty] | 0 | 0 | 10.06 | 0 | 0
DRE2 | GG\10\009\D | GG | 10 | 9 | D | 6 DL | 100 | 100 | 100 | 2021-04-07 00:21 | 2021-04-12 18:21 | 464182.2097 |  |  |  | 10808 | 464182 | 205343 |  |  | 0 | 21.63 | 0 | 6.42 | 5824.67
TS5500Exc | RS\15\006\A | RS | 15 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-04-07 01:00 | 2021-04-07 21:47 | 26166.9604 | [6 empty] | 26167 | 17770 | 1.78 | 0 | 0 | 17.3 | 4865
TS Fleet 5 | MW\37\010\A | MW | 37 | 10 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-07 16:23 | 2021-04-11 19:14 | 193744.587 | 193745 | [7 empty] | 0 | 0 | 19.11 | 10.68 | 5443.59
TS5500Exc | RS\15\005\B | RS | 15 | 5 | B | 8 Coal Mining | 75 | 0 | 75 | 2021-04-07 21:47 | 2021-04-08 21:56 | 30431.0597 | [6 empty] | 30431 | 21727 | 2.17 | 0 | 0 | 9.28 | 5564
DRE1 | MW\34\003\D | MW | 34 | 3 | D | 6 DL | 100 | 100 | 100 | 2021-04-08 15:45 | 2021-04-12 06:27 | 302826.6224 |  |  |  | 15569 | 302827 | 243922 |  |  | 0 | 25.97 | 0 | 7 | 5798.81
PH4100XPC#1 | GG\12\006\B | GG | 12 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-08 21:15 | 2021-04-09 03:19 | 13705.7191 | 13706 | [7 empty] | 0 | 0 | 1.37 | 11.48 | 5317.01
TS5500Exc | MW\34\002\D | MW | 34 | 2 | D | 8 Coal Mining | 68.6 | 0 | 68.6 | 2021-04-08 21:56 | 2021-04-10 06:23 | 40873.7431 | [6 empty] | 40874 | 30543 | 3.32 | 0 | 0 | 7.49 | 5756
PH4100XPC#1 | GG\12\008\X1 | GG | 12 | 8 | X1 | 1 Prestrip - Thick | 100 | 68.7299 | 68.7299 | 2021-04-09 03:19 | 2021-04-14 20:36 | 306649.201 | 306649 | [7 empty] | 0 | 0 | 29.66 | 10 | 5501.84
TS5500Exc | MW\38\007\A | MW | 38 | 7 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-04-10 06:23 | 2021-04-11 01:50 | 24498.8972 | [6 empty] | 24499 | 17880 | 1.79 | 0 | 0 | 12.19 | 5306
TS5500Exc | MW\38\007\B | MW | 38 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-11 01:50 | 2021-04-13 08:05 | 47972.8152 | 47973 | [7 empty] | 0 | 0 | 4.8 | 9.43 | 5509.2
TS5500Shv | GG\12\007\X1 | GG | 12 | 7 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2021-04-11 16:26 | 2021-04-12 05:51 | 16374.6012 | [6 empty] | 16375 | 12110 | 1.2 | 0 | 0 | 10.75 | 5413
TS Fleet 5 | MW\38\010\X | MW | 38 | 10 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-11 19:14 | 2021-04-20 07:08 | 399651.9812 | 399652 | [7 empty] | 0 | 0 | 39.11 | 12.16 | 5242.47
TS5500Shv | RS\15\006\A | RS | 15 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-04-12 05:51 | 2021-04-13 02:38 | 25331.8446 | [6 empty] | 25332 | 17203 | 1.72 | 0 | 0 | 17.3 | 4865
DRE1 | MW\34\004\D | MW | 34 | 4 | D | 6 DL | 100 | 100 | 100 | 2021-04-12 06:27 | 2021-04-16 09:31 | 346084.047 |  |  |  | 17794 | 346084 | 278765 |  |  | 0 | 29.71 | 0 | 6.49 | 5842.46
DRE2 | GG\10\008\D | GG | 10 | 8 | D | 6 DL | 100 | 100 | 100 | 2021-04-12 18:21 | 2021-04-18 07:31 | 447956.8361 |  |  |  | 10430 | 447957 | 198165 |  |  | 0 | 20.88 | 0 | 6.64 | 5805.14
TS5500Shv | RS\15\005\B | RS | 15 | 5 | B | 8 Coal Mining | 25 | 0 | 25 | 2021-04-13 02:38 | 2021-04-13 10:57 | 10151.8356 | [6 empty] | 10152 | 7248 | 0.72 | 0 | 0 | 9.28 | 5564
TS5500Exc | MW\37\010\A | MW | 37 | 10 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-04-13 08:05 | 2021-04-14 01:53 | 22415.3248 | [6 empty] | 22415 | 16537 | 1.7 | 0 | 0 | 10.68 | 5444
TS5500Shv | GG\10\010\D | GG | 10 | 10 | D | 8 Coal Mining | 57.6 | 0 | 57.6 | 2021-04-13 10:57 | 2021-04-14 17:39 | 37437.6536 | [6 empty] | 37438 | 28055 | 2.81 | 0 | 0 | 6.15 | 5849
TS5500Exc | MW\34\003\D | MW | 34 | 3 | D | 8 Coal Mining | 83.5 | 0 | 83.5 | 2021-04-14 01:53 | 2021-04-15 20:05 | 53161.8536 | [6 empty] | 53162 | 39913 | 3.99 | 0 | 0 | 7 | 5799
TS6060#1 | RS\15\006\B | RS | 15 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-14 16:05 | 2021-04-15 20:00 | 28819.6904 | 28820 | [7 empty] | 0 | 0 | 2.88 | 9.32 | 5553.48
TS5500Shv | RS\12\007\D | RS | 12 | 7 | D | 8 Coal Mining | 21.7 | 0 | 21.7 | 2021-04-14 17:39 | 2021-04-15 05:59 | 15029.2337 | [6 empty] | 15029 | 10887 | 0.95 | 0 | 0 | 7.64 | 5748
PH4100XPC#1 | GG\12\007\X2 | GG | 12 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2021-04-14 20:36 | 2021-04-16 16:07 | 98532.178 | 98532 | [7 empty] | 0 | 0 | 9.79 | 0 | 0
TS5500Shv | GG\10\009\D | GG | 10 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-04-15 05:59 | 2021-04-17 10:38 | 64200.1178 | [6 empty] | 64200 | 47996 | 4.8 | 0 | 0 | 6.42 | 5825
TS6060#1 | GG\12\008\X1 | GG | 12 | 8 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2021-04-15 20:00 | 2021-04-16 08:18 | 16633.2403 | [6 empty] | 16633 | 12356 | 1.22 | 0 | 0 | 10 | 5502
TS5500Exc | RS\15\006\B | RS | 15 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-04-15 20:05 | 2021-04-17 03:24 | 39450.4106 | [6 empty] | 39450 | 28082 | 2.81 | 0 | 0 | 9.32 | 5553
TS6060#1 | GG\10\011\D | GG | 10 | 11 | D | 8 Coal Mining | 76.1 | 0 | 76.1 | 2021-04-16 08:18 | 2021-04-17 20:45 | 49332.6419 | [6 empty] | 49333 | 37028 | 3.7 | 0 | 0 | 6.02 | 5860
DRE1 | MW\34\005\D | MW | 34 | 5 | D | 6 DL | 100 | 100 | 100 | 2021-04-16 09:31 | 2021-04-21 04:14 | 400717.3659 |  |  |  | 22870 | 400717 | 303846 |  |  | 0 | 32.76 | 0 | 5.9 | 5893.22
PH4100A | RS\16\003\X | RS | 16 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-16 12:28 | 2021-04-20 21:31 | 173300.0218 | 173300 | [7 empty] | 0 | 0 | 27.79 | 13.06 | 5130.33
PH4100XPC#1 | GG\12\007\B | GG | 12 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-16 16:07 | 2021-04-17 12:30 | 46105.742 | 46106 | [7 empty] | 0 | 0 | 4.7 | 10.67 | 5418.76
TS5500Exc | RS\15\007\X | RS | 15 | 7 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-04-17 03:24 | 2021-04-17 10:36 | 9062.6906 | [6 empty] | 9063 | 6501 | 0.6 | 0 | 0 | 9.76 | 5384
TS5500Exc | MW\34\004\D | MW | 34 | 4 | D | 8 Coal Mining | 38.1 | 0 | 38.1 | 2021-04-17 10:36 | 2021-04-18 05:22 | 23644.5654 | [6 empty] | 23645 | 17808 | 1.78 | 0 | 0 | 6.49 | 5842
TS5500Shv | RS\15\007\X | RS | 15 | 7 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-04-17 10:38 | 2021-04-17 17:49 | 8773.4558 | [6 empty] | 8773 | 6294 | 0.58 | 0 | 0 | 9.76 | 5384
PH4100XPC#1 | GG\12\008\X2 | GG | 12 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2021-04-17 12:30 | 2021-04-19 08:00 | 98473.284 | 98473 | [7 empty] | 0 | 0 | 9.71 | 0 | 0
TS5500Shv | MW\34\002\D | MW | 34 | 2 | D | 8 Coal Mining | 31.4 | 0 | 31.4 | 2021-04-17 17:49 | 2021-04-18 09:10 | 18709.9517 | [6 empty] | 18710 | 13981 | 1.52 | 0 | 0 | 7.49 | 5756
TS6060#1 | RS\15\007\A | RS | 15 | 7 | A | 1 Prestrip - Thick | 15.0776 | 15.0776 | 15.0776 | 2021-04-17 20:45 | 2021-04-19 01:38 | 29805.3375 | 29805 | [7 empty] | 0 | 0 | 3.03 | 16.51 | 4921.75
TS5500Exc | MW\38\007\B | MW | 38 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-04-18 05:22 | 2021-04-19 13:00 | 39846.3411 | [6 empty] | 39846 | 29360 | 2.94 | 0 | 0 | 9.43 | 5509
DRE2 | GG\10\007\D | GG | 10 | 7 | D | 6 DL | 100 | 100 | 100 | 2021-04-18 07:31 | 2021-04-23 17:44 | 438010.2572 |  |  |  | 10198 | 438010 | 193765 |  |  | 0 | 20.4 | 0 | 6.48 | 5818.9
TS5500Shv | MW\37\010\A | MW | 37 | 10 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-04-18 09:10 | 2021-04-19 02:58 | 21699.9421 | [6 empty] | 21700 | 16009 | 1.65 | 0 | 0 | 10.68 | 5444
TS6060#1 | GG\10\010\D | GG | 10 | 10 | D | 8 Coal Mining | 42.4 | 0 | 42.4 | 2021-04-19 01:38 | 2021-04-19 22:02 | 27605.6653 | [6 empty] | 27606 | 20687 | 2.07 | 0 | 0 | 6.15 | 5849
TS5500Shv | MW\34\003\D | MW | 34 | 3 | D | 8 Coal Mining | 16.5 | 0 | 16.5 | 2021-04-19 02:58 | 2021-04-19 11:33 | 10473.576 | [6 empty] | 10474 | 7863 | 0.79 | 0 | 0 | 7 | 5799
PH4100XPC#1 | GG\12\008\B | GG | 12 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-19 08:00 | 2021-04-20 09:55 | 58689.6327 | 58690 | [7 empty] | 0 | 0 | 5.86 | 10.38 | 5479.08
TS5500Shv | GG\10\008\D | GG | 10 | 8 | D | 8 Coal Mining | 38.4 | 0 | 38.4 | 2021-04-19 11:33 | 2021-04-20 07:42 | 24568.0798 | [6 empty] | 24568 | 18338 | 1.83 | 0 | 0 | 6.64 | 5805
TS5500Exc | MW\37\010\B | MW | 37 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-19 13:00 | 2021-04-20 19:50 | 27273.4823 | 27273 | [7 empty] | 0 | 0 | 2.84 | 8.86 | 5594.82
TS6060#1 | GG\10\008\D | GG | 10 | 8 | D | 8 Coal Mining | 61.6 | 0 | 61.6 | 2021-04-19 22:02 | 2021-04-21 03:08 | 39394.6122 | [6 empty] | 39395 | 29405 | 2.94 | 0 | 0 | 6.64 | 5805
TS Fleet 5 | MW\39\003\B | MW | 39 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-20 07:08 | 2021-04-23 20:05 | 166495.1663 | 166495 | [7 empty] | 0 | 0 | 14.23 | 10.78 | 5401.62
TS5500Shv | MW\34\004\D | MW | 34 | 4 | D | 8 Coal Mining | 61.9 | 0 | 61.9 | 2021-04-20 07:42 | 2021-04-21 15:15 | 38462.7207 | [6 empty] | 38463 | 28968 | 2.9 | 0 | 0 | 6.49 | 5842
PH4100XPC#1 | GG\12\009\X1 | GG | 12 | 9 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-20 09:55 | 2021-04-28 08:11 | 425162.7163 | 425163 | [7 empty] | 0 | 0 | 40.54 | 11.1 | 5414.29
TS5500Exc | MW\37\010\B | MW | 37 | 10 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-04-20 19:50 | 2021-04-21 11:01 | 19127.5549 | [6 empty] | 19128 | 14218 | 1.5 | 0 | 0 | 8.86 | 5595
PH4100A | RS\15\007\A | RS | 15 | 7 | A | 1 Prestrip - Thick | 100 | 84.9224 | 84.9224 | 2021-04-20 21:31 | 2021-04-24 22:13 | 167873.7032 | 167874 | [7 empty] | 0 | 0 | 17.08 | 16.51 | 4921.75
TS6060#1 | RS\18\003\X | RS | 18 | 3 | X | 1 Prestrip - Thick | 25.1398 | 25.1398 | 25.1398 | 2021-04-21 03:08 | 2021-04-23 03:26 | 48066.6613 | 48067 | [7 empty] | 0 | 0 | 7.77 | 12.72 | 5145.27
DRE1 | MW\34\006\D | MW | 34 | 6 | D | 6 DL | 100 | 100 | 100 | 2021-04-21 04:14 | 2021-04-25 14:47 | 372155.5425 |  |  |  | 21240 | 372156 | 282189 |  |  | 0 | 30.31 | 0 | 5.68 | 5911.56
TS5500Exc | RS\16\003\X | RS | 16 | 3 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-04-21 11:01 | 2021-04-21 21:11 | 12796.4405 | [6 empty] | 12796 | 8940 | 1.37 | 0 | 0 | 13.06 | 5130
TS5500Shv | MW\37\010\B | MW | 37 | 10 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-04-21 15:15 | 2021-04-22 06:26 | 18517.101 | [6 empty] | 18517 | 13764 | 1.45 | 0 | 0 | 8.86 | 5595
TS5500Exc | MW\34\005\D | MW | 34 | 5 | D | 8 Coal Mining | 15 | 0 | 15 | 2021-04-21 21:11 | 2021-04-22 04:13 | 8860.4431 | [6 empty] | 8860 | 6705 | 0.67 | 0 | 0 | 5.9 | 5893
TS5500Exc | MW\38\008\A | MW | 38 | 8 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-04-22 04:13 | 2021-04-23 17:31 | 46991.4149 | [6 empty] | 46991 | 34147 | 3.43 | 0 | 0 | 13.08 | 5246
TS5500Shv | MW\34\005\D | MW | 34 | 5 | D | 8 Coal Mining | 85 | 0 | 85 | 2021-04-22 06:26 | 2021-04-23 23:37 | 50229.8371 | [6 empty] | 50230 | 38009 | 3.8 | 0 | 0 | 5.9 | 5893
TS6060#1 | RS\16\003\A | RS | 16 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-23 03:26 | 2021-04-29 03:26 | 148586.3174 | 148586 | [7 empty] | 0 | 0 | 20.87 | 12.54 | 5320.77
TS5500Exc | MW\38\008\B | MW | 38 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-23 17:31 | 2021-04-25 16:18 | 41365.5298 | 41366 | [7 empty] | 0 | 0 | 4.15 | 10.06 | 5434.93
DRE2 | GG\10\006\D | GG | 10 | 6 | D | 6 DL | 100 | 100 | 100 | 2021-04-23 17:44 | 2021-04-29 04:31 | 439916.0154 |  |  |  | 10243 | 439916 | 194608 |  |  | 0 | 20.5 | 0 | 6.41 | 5824.16
TS Fleet 5 | MW\39\004\D | MW | 39 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-23 20:05 | 2021-04-25 06:58 | 68373.8955 | 68374 | [7 empty] | 0 | 0 | 7.24 | 6.63 | 5830.51
TS5500Shv | GG\10\007\D | GG | 10 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-04-23 23:37 | 2021-04-26 04:24 | 64363.6895 | [6 empty] | 64364 | 48194 | 4.82 | 0 | 0 | 6.48 | 5819
PH4100A | RS\16\004\X | RS | 16 | 4 | X | 1 Prestrip - Thick | 100 | 64.1035 | 64.1035 | 2021-04-24 22:13 | 2021-04-30 22:48 | 241127.1809 | 241127 | [7 empty] | 0 | 0 | 23.83 | 12.77 | 5149.41
TS Fleet 5 | MW\39\005\D | MW | 39 | 5 | D | 1 Prestrip - Thick | 89.9022 | 89.9022 | 89.9022 | 2021-04-25 06:58 | 2021-04-26 20:13 | 73025.4526 | 73025 | [7 empty] | 0 | 0 | 9.5 | 6.06 | 5879.94
DRE1 | MW\34\007\D | MW | 34 | 7 | D | 6 DL | 100 | 100 | 100 | 2021-04-25 14:47 | 2021-04-30 00:08 | 368015.6576 |  |  |  | 21004 | 368016 | 279050 |  |  | 0 | 30.02 | 0 | 5.8 | 5901.38
TS5500Exc | RS\15\007\A | RS | 15 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-04-25 16:18 | 2021-04-27 07:02 | 48798.9246 | [6 empty] | 48799 | 33460 | 3.45 | 0 | 0 | 16.51 | 4922
TS5500Shv | MW\34\006\D | MW | 34 | 6 | D | 8 Coal Mining | 27.7 | 0 | 27.7 | 2021-04-26 04:24 | 2021-04-26 17:21 | 15781.0279 | [6 empty] | 15781 | 11950 | 1.2 | 0 | 0 | 5.68 | 5912
TS5500Shv | MW\38\010\X | MW | 38 | 10 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-04-26 17:21 | 2021-04-27 06:29 | 16024.0177 | [6 empty] | 16024 | 11688 | 1.25 | 0 | 0 | 12.16 | 5242
TS Fleet 5 | MW\39\006\B | MW | 39 | 6 | B | 1 Prestrip - Thick | 67.9187 | 67.9187 | 67.9187 | 2021-04-26 20:13 | 2021-04-30 08:06 | 164394.2801 | 164394 | [7 empty] | 0 | 0 | 17.46 | 8.65 | 5600.13
TS5500Shv | MW\39\003\B | MW | 39 | 3 | B | 8 Coal Mining | 34.7 | 0 | 34.7 | 2021-04-27 06:29 | 2021-04-27 14:33 | 9842.6876 | [6 empty] | 9843 | 7193 | 0.58 | 0 | 0 | 10.78 | 5402
TS5500Exc | MW\34\006\D | MW | 34 | 6 | D | 8 Coal Mining | 72.3 | 0 | 72.3 | 2021-04-27 07:02 | 2021-04-28 15:40 | 41102.4886 | [6 empty] | 41102 | 31126 | 3.11 | 0 | 0 | 5.68 | 5912
TS5500Shv | RS\17\004\X | RS | 17 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-04-27 14:33 | 2021-04-28 02:31 | 14587.279 | [6 empty] | 14587 | 10196 | 1.02 | 0 | 0 | 12.74 | 5150
TS5500Shv | GG\13\011\B | GG | 13 | 11 | B | 1 Prestrip - Thick | 19.6755 | 19.6755 | 19.6755 | 2021-04-28 02:31 | 2021-05-02 18:21 | 120116.4505 | 120116 | [7 empty] | 0 | 0 | 11.7 | 9.82 | 5525.72
PH4100XPC#1 | GG\12\010\B | GG | 12 | 10 | B | 1 Prestrip - Thick | 100 | 85.0556 | 85.0556 | 2021-04-28 08:11 | 2021-05-07 09:40 | 500567.9964 | 500568 | [7 empty] | 0 | 0 | 48.16 | 9.59 | 5536.41
TS5500Exc | MW\38\008\B | MW | 38 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-04-28 15:40 | 2021-04-29 22:03 | 38270.7899 | [6 empty] | 38271 | 28170 | 2.82 | 0 | 0 | 10.06 | 5435
TS6060#1 | GG\12\009\X1 | GG | 12 | 9 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2021-04-29 03:26 | 2021-04-29 15:34 | 16406.8201 | [6 empty] | 16407 | 12089 | 1.19 | 0 | 0 | 11.1 | 5414
DRE2 | GG\10\005\D | GG | 10 | 5 | D | 6 DL | 100 | 100 | 100 | 2021-04-29 04:31 | 2021-05-04 10:55 | 425174.8497 |  |  |  | 10282 | 425175 | 195365 |  |  | 0 | 20.56 | 0 | 6.34 | 5828.39
TS6060#1 | RS\17\004\A | RS | 17 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-29 15:34 | 2021-05-07 23:30 | 206288.0343 | 206288 | [7 empty] | 0 | 0 | 20.55 | 15.94 | 5021.09
TS5500Exc | RS\16\003\A | RS | 16 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-04-29 22:03 | 2021-04-30 12:17 | 17925.7753 | [6 empty] | 17926 | 12551 | 1.61 | 0 | 0 | 12.54 | 5321
DRE1 | MW\34\008\D | MW | 34 | 8 | D | 6 DL | 100 | 100 | 100 | 2021-04-30 00:08 | 2021-05-04 04:03 | 349041.7503 |  |  |  | 17946 | 349042 | 281148 |  |  | 0 | 29.93 | 0 | 5.85 | 5898.3
TS Fleet 5 | MW\38\010\A | MW | 38 | 10 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-30 08:06 | 2021-05-03 23:52 | 172030.5594 | 172031 | [7 empty] | 0 | 0 | 19.04 | 10.63 | 5446.48
TS5500Exc | MW\34\007\D | MW | 34 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-04-30 12:17 | 2021-05-02 10:47 | 58579.3612 | [6 empty] | 58579 | 44291 | 4.43 | 0 | 0 | 5.8 | 5901
PH4100A | RS\15\007\B | RS | 15 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-04-30 22:48 | 2021-05-01 14:00 | 26386.7365 | 26387 | [7 empty] | 0 | 0 | 2.73 | 9.26 | 5571.23
PH4100A | RS\16\005\X | RS | 16 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-05-01 14:00 | 2021-05-12 16:25 | 448802.6693 | 448803 | [7 empty] | 0 | 0 | 44.42 | 12.52 | 5179.97
TS5500Exc | RS\15\007\B | RS | 15 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-05-02 10:47 | 2021-05-03 15:53 | 36653.9432 | [6 empty] | 36654 | 26103 | 2.71 | 0 | 0 | 9.26 | 5571
TS5500Shv | RS\16\004\X | RS | 16 | 4 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-05-02 18:21 | 2021-05-03 00:52 | 7948.6429 | [6 empty] | 7949 | 5558 | 0.55 | 0 | 0 | 12.77 | 5149
TS5500Shv | RS\16\003\A | RS | 16 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-05-03 00:52 | 2021-05-03 15:06 | 17353.6761 | [6 empty] | 17354 | 12151 | 1.56 | 0 | 0 | 12.54 | 5321
TS5500Shv | GG\10\006\D | GG | 10 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-05-03 15:06 | 2021-05-05 18:31 | 62711.7962 | [6 empty] | 62712 | 47032 | 4.7 | 0 | 0 | 6.41 | 5824
TS5500Exc | RS\16\004\X | RS | 16 | 4 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-05-03 15:53 | 2021-05-03 22:25 | 8210.686 | [6 empty] | 8211 | 5742 | 0.57 | 0 | 0 | 12.77 | 5149
TS5500Exc | MW\38\009\A | MW | 38 | 9 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-05-03 22:25 | 2021-05-05 11:12 | 46337.9001 | [6 empty] | 46338 | 33871 | 3.39 | 0 | 0 | 12.16 | 5322
TS Fleet 5 | MW\39\007\A | MW | 39 | 7 | A | 1 Prestrip - Thick | 88.7694 | 88.7694 | 88.7694 | 2021-05-03 23:52 | 2021-05-09 09:13 | 253527.7129 | 253528 | [7 empty] | 0 | 0 | 26.19 | 12.44 | 5285.18
DRE1 | MW\34\009\D | MW | 34 | 9 | D | 6 DL | 100 | 100 | 100 | 2021-05-04 04:03 | 2021-05-08 04:02 | 335258.9805 |  |  |  | 17237 | 335259 | 270046 |  |  | 0 | 28.76 | 0 | 5.61 | 5919.52
DRE2 | GG\10\004\D | GG | 10 | 4 | D | 6 DL | 100 | 100 | 100 | 2021-05-04 10:55 | 2021-05-07 05:31 | 224031.4979 |  |  |  | 10024 | 224031 | 190452 |  |  | 0 | 20.04 | 0 | 6.21 | 5839.64
TS5500Exc | MW\34\008\D | MW | 34 | 8 | D | 8 Coal Mining | 43.3 | 0 | 43.3 | 2021-05-05 11:12 | 2021-05-06 08:21 | 26635.3362 | [6 empty] | 26635 | 20125 | 2.01 | 0 | 0 | 5.85 | 5898
TS5500Shv | MW\34\008\D | MW | 34 | 8 | D | 8 Coal Mining | 56.7 | 0 | 56.7 | 2021-05-05 18:31 | 2021-05-06 23:05 | 34817.5426 | [6 empty] | 34818 | 26307 | 2.63 | 0 | 0 | 5.85 | 5898
TS5500Exc | MW\38\009\B | MW | 38 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-05-06 08:21 | 2021-05-07 21:17 | 32675.5119 | 32676 | [7 empty] | 0 | 0 | 3.27 | 9.42 | 5516.76
TS5500Shv | MW\38\010\A | MW | 38 | 10 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-05-06 23:05 | 2021-05-07 14:45 | 19110.595 | [6 empty] | 19111 | 14103 | 1.63 | 0 | 0 | 10.63 | 5446
DRE2 | GG\10\003\D | GG | 10 | 3 | D | 6 DL | 100 | 100 | 100 | 2021-05-07 05:31 | 2021-05-09 19:04 | 207055.0851 |  |  |  | 7903 | 207055 | 189669 |  |  | 0 | 19.77 | 0 | 6.1 | 5849.61
PH4100XPC#1 | GG\12\009\X2 | GG | 12 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2021-05-07 09:40 | 2021-05-09 04:11 | 96249.843 | 96250 | [7 empty] | 0 | 0 | 9.44 | 0 | 0
TS5500Shv | GG\13\012\B | GG | 13 | 12 | B | 1 Prestrip - Thick | 8.3693 | 8.3693 | 8.3693 | 2021-05-07 14:45 | 2021-05-09 08:46 | 45090.1713 | 45090 | [7 empty] | 0 | 0 | 3.76 | 10.39 | 5484.73
TS5500Exc | MW\38\009\B | MW | 38 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-05-07 21:17 | 2021-05-09 04:19 | 39082.3227 | [6 empty] | 39082 | 28920 | 2.89 | 0 | 0 | 9.42 | 5517
TS6060#1 | RS\16\004\A | RS | 16 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-05-07 23:30 | 2021-05-16 06:15 | 205080.995 | 205081 | [7 empty] | 0 | 0 | 20.41 | 14.89 | 5108.83
DRE1 | MW\34\010\D | MW | 34 | 10 | D | 6 DL | 100 | 100 | 100 | 2021-05-08 04:02 | 2021-05-13 02:03 | 412270.3119 |  |  |  | 14900 | 412270 | 232167 |  |  | 0 | 29.26 | 0 | 5.35 | 5942.1
PH4100XPC#1 | GG\12\009\B | GG | 12 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-05-09 04:11 | 2021-05-10 12:01 | 72046.8141 | 72047 | [7 empty] | 0 | 0 | 7.11 | 9.82 | 5522.31
TS5500Exc | MW\34\009\D | MW | 34 | 9 | D | 8 Coal Mining | 73.2 | 0 | 73.2 | 2021-05-09 04:19 | 2021-05-10 15:14 | 43990.4484 | [6 empty] | 43990 | 33343 | 3.33 | 0 | 0 | 5.61 | 5920
TS5500Shv | MW\34\009\D | MW | 34 | 9 | D | 8 Coal Mining | 26.8 | 0 | 26.8 | 2021-05-09 08:46 | 2021-05-09 21:58 | 16096.6931 | [6 empty] | 16097 | 12201 | 1.22 | 0 | 0 | 5.61 | 5920
TS Fleet 5 | MW\39\008\A | MW | 39 | 8 | A | 1 Prestrip - Thick | 90.7227 | 90.7227 | 90.7227 | 2021-05-09 09:13 | 2021-05-16 22:26 | 355165.7828 | 355166 | [7 empty] | 0 | 0 | 35.17 | 13.28 | 5229.48
DRE2 | GG\10\002\D | GG | 10 | 2 | D | 6 DL | 100 | 100 | 100 | 2021-05-09 19:04 | 2021-05-15 20:00 | 487527.929 |  |  |  | 8043 | 487528 | 140363 |  |  | 0 | 19.09 | 0 | 6.1 | 5849.82
TS5500Shv | GG\10\003\D | GG | 10 | 3 | D | 8 Coal Mining | 32.2 | 0 | 32.2 | 2021-05-09 21:58 | 2021-05-10 13:58 | 19517.3197 | [6 empty] | 19517 | 14648 | 1.46 | 0 | 0 | 6.1 | 5850
PH4100XPC#1 | GG\12\011\B | GG | 12 | 11 | B | 1 Prestrip - Thick | 100 | 73.181 | 73.181 | 2021-05-10 12:01 | 2021-05-18 09:24 | 443013.1606 | 443013 | [7 empty] | 0 | 0 | 50.56 | 9.82 | 5525.76
TS5500Shv | RS\17\004\A | RS | 17 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-05-10 13:58 | 2021-05-11 06:42 | 20394.6807 | [6 empty] | 20395 | 13988 | 1.39 | 0 | 0 | 15.94 | 5021
TS5500Exc | MW\39\003\B | MW | 39 | 3 | B | 8 Coal Mining | 65.3 | 0 | 65.3 | 2021-05-10 15:14 | 2021-05-11 05:57 | 18531.7767 | [6 empty] | 18532 | 13543 | 1.1 | 0 | 0 | 10.78 | 5402
TS5500Exc | RS\17\003\X | RS | 17 | 3 | X | 8 Coal Mining | 20.6 | 0 | 20.6 | 2021-05-11 05:57 | 2021-05-11 07:49 | 2355.4256 | [6 empty] | 2355 | 1647 | 0.25 | 0 | 0 | 12.86 | 5139
TS5500Shv | GG\13\013\B | GG | 13 | 13 | B | 1 Prestrip - Thick | 15.4956 | 15.4956 | 15.4956 | 2021-05-11 06:42 | 2021-05-13 21:24 | 67106.3422 | 67106 | [7 empty] | 0 | 0 | 8.55 | 10.91 | 5443.1
TS5500Exc | MW\38\010\A | MW | 38 | 10 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-05-11 07:49 | 2021-05-11 23:30 | 19740.6146 | [6 empty] | 19741 | 14568 | 1.69 | 0 | 0 | 10.63 | 5446
TS5500Exc | MW\39\006\B | MW | 39 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-05-11 23:30 | 2021-05-13 03:04 | 34729.1099 | [6 empty] | 34729 | 25658 | 2.59 | 0 | 0 | 8.65 | 5600
PH4100A | RS\16\003\B | RS | 16 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-05-12 16:25 | 2021-05-13 03:09 | 18634.5465 | 18635 | [7 empty] | 0 | 0 | 2.34 | 8.69 | 5648.98
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2021-05-13 02:03 | 2021-05-15 02:03
TS5500Exc | RS\16\005\X | RS | 16 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-05-13 03:04 | 2021-05-13 17:11 | 17783.815 | [6 empty] | 17784 | 12445 | 1.24 | 0 | 0 | 12.52 | 5180
PH4100A | RS\16\006\X | RS | 16 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-05-13 03:09 | 2021-05-25 12:07 | 502342.2226 | 502342 | [7 empty] | 0 | 0 | 49.7 | 11.28 | 5283.19
TS5500Exc | RS\16\003\B | RS | 16 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-05-13 17:11 | 2021-05-14 20:04 | 33852.6697 | [6 empty] | 33853 | 24123 | 2.97 | 0 | 0 | 8.69 | 5649
TS5500Shv | MW\34\010\D | MW | 34 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2021-05-13 21:24 | 2021-05-15 20:54 | 50925.5946 |  |  | 50926 | [5 empty] | 0 | 0 | 0 | 5.35 | 5942.1
TS5500Exc | MW\39\007\A | MW | 39 | 7 | A | 1 Prestrip - Thick | 11.2306 | 11.2306 | 11.2306 | 2021-05-14 20:04 | 2021-05-16 08:10 | 32074.8815 | 32075 | [7 empty] | 0 | 0 | 3.31 | 12.44 | 5285.18
DRE1 | RS\13\003\D | RS | 13 | 3 | D | 6 DL | 100 | 100 | 100 | 2021-05-15 02:03 | 2021-05-19 00:41 | 330522.8802 |  |  |  | 16993 | 330523 | 266231 |  |  | 0 | 25.96 | 0 | 6.37 | 5861.11
DRE2 | GG\11\012\B | GG | 11 | 12 | B | 6 DL | 100 | 0 | 100 | 2021-05-15 20:00 | 2021-05-17 23:30 | 173198.4925 |  |  |  |  | 173198 | 144332 |  |  | 0 | 16.63 | 0 | 10.16 | 5506.24
TS5500Shv | GG\10\002\D | GG | 10 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2021-05-15 20:54 | 2021-05-17 22:02 | 52663.2264 |  |  | 52663 | [5 empty] | 0 | 0 | 0 | 6.1 | 5849.82
TS6060#1 | MW\34\010\D | MW | 34 | 10 | D | 8 Coal Mining | 100 | 0 | 53.9 | 2021-05-16 06:15 | 2021-05-17 05:58 | 32094.0326 | [6 empty] | 32094 | 24424 | 2.44 | 0 | 0 | 5.35 | 5942
TS5500Exc | MW\34\010\D | MW | 34 | 10 | D | 8 Coal Mining | 100 | 0 | 46.1 | 2021-05-16 08:10 | 2021-05-17 05:58 | 27449.8294 | [6 empty] | 27450 | 20890 | 2.08 | 0 | 0 | 5.35 | 5942
TS Fleet 5 | MW\38\010\B | MW | 38 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-05-16 22:26 | 2021-05-17 10:57 | 24556.1347 | 24556 | [7 empty] | 0 | 0 | 2.88 | 8.82 | 5598.86
TS6060#1 | RS\16\005\A | RS | 16 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-05-17 05:58 | 2021-05-25 00:36 | 192560.9286 | 192561 | [7 empty] | 0 | 0 | 19.19 | 17.49 | 4873.05
TS5500Exc | RS\16\004\A | RS | 16 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-05-17 05:58 | 2021-05-18 17:31 | 44769.6253 | [6 empty] | 44770 | 30916 | 3.08 | 0 | 0 | 14.89 | 5109
TS Fleet 5 | MW\39\009\A | MW | 39 | 9 | A | 1 Prestrip - Thick | 94.0411 | 94.0411 | 94.0411 | 2021-05-17 10:57 | 2021-05-27 11:49 | 472095.6954 | 472096 | [7 empty] | 0 | 0 | 46.68 | 12.12 | 5324.72
TS5500Shv | MW\38\010\B | MW | 38 | 10 | B | 8 Coal Mining | 50.1 | 0 | 50.1 | 2021-05-17 22:02 | 2021-05-18 11:46 | 16752.2488 | [6 empty] | 16752 | 12462 | 1.48 | 0 | 0 | 8.82 | 5599
DRE2 | GG\11\013\B | GG | 11 | 13 | B | 6 DL | 100 | 0 | 100 | 2021-05-17 23:30 | 2021-05-19 14:00 | 129545.5728 |  |  |  |  | 129546 | 107955 |  |  | 0 | 16.97 | 0 | 10.78 | 5456.73
PH4100XPC#1 | GG\12\012\B | GG | 12 | 12 | B | 1 Prestrip - Thick | 100 | 87.8962 | 87.8962 | 2021-05-18 09:24 | 2021-05-27 07:41 | 502976.6294 | 502977 | [7 empty] | 0 | 0 | 52.26 | 10.26 | 5496.37
TS5500Shv | GG\11\012\B | GG | 11 | 12 | B | 8 Coal Mining | 27.1 | 0 | 27.1 | 2021-05-18 11:46 | 2021-05-18 22:20 | 12889.7371 | [6 empty] | 12890 | 9452 | 0.95 | 0 | 0 | 10.16 | 5506
TS5500Exc | MW\38\010\B | MW | 38 | 10 | B | 8 Coal Mining | 49.9 | 0 | 49.9 | 2021-05-18 17:31 | 2021-05-19 06:45 | 16681.0069 | [6 empty] | 16681 | 12409 | 1.47 | 0 | 0 | 8.82 | 5599
TS5500Shv | MW\39\007\A | MW | 39 | 7 | A | 8 Coal Mining | 27.2 | 0 | 27.2 | 2021-05-18 22:20 | 2021-05-19 08:58 | 12962.4221 | [6 empty] | 12962 | 9438 | 0.94 | 0 | 0 | 12.44 | 5285
DRE1 | RS\13\004\D | RS | 13 | 4 | D | 6 DL | 100 | 100 | 100 | 2021-05-19 00:41 | 2021-05-22 15:23 | 302885.7795 |  |  |  | 15573 | 302886 | 243970 |  |  | 0 | 25.95 | 0 | 6.85 | 5819.05
TS5500Exc | RS\13\003\D | RS | 13 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-05-19 06:45 | 2021-05-21 11:53 | 66916.34 | [6 empty] | 66916 | 48868 | 4.46 | 0 | 0 | 6.37 | 5861
TS5500Shv | GG\13\019\B | GG | 13 | 19 | B | 1 Prestrip - Thick | 27.012 | 27.012 | 27.012 | 2021-05-19 08:58 | 2021-05-23 02:02 | 95423.5488 | 95424 | [7 empty] | 0 | 0 | 9.06 | 11.21 | 5428.63
DRE2 | GG\11\018\B | GG | 11 | 18 | B | 6 DL | 100 | 0 | 100 | 2021-05-19 14:00 | 2021-05-21 07:17 | 138819.3462 |  |  |  |  | 138819 | 115683 |  |  | 0 | 17.64 | 0 | 11.17 | 5425.17
DRE2 | GG\11\019\B | GG | 11 | 19 | B | 6 DL | 100 | 0 | 100 | 2021-05-21 07:17 | 2021-05-24 02:48 | 227113.0727 |  |  |  |  | 227113 | 189261 |  |  | 0 | 18.26 | 0 | 11.44 | 5409.49
TS5500Exc | MW\39\007\A | MW | 39 | 7 | A | 8 Coal Mining | 72.8 | 0 | 72.8 | 2021-05-21 11:53 | 2021-05-22 15:28 | 34752.1334 | [6 empty] | 34752 | 25304 | 2.52 | 0 | 0 | 12.44 | 5285
DRE1 | RS\13\005\D | RS | 13 | 5 | D | 6 DL | 100 | 100 | 100 | 2021-05-22 15:23 | 2021-05-26 07:58 | 309430.6792 |  |  |  | 15909 | 309431 | 249242 |  |  | 0 | 26.52 | 0 | 7.08 | 5798.79
TS5500Exc | RS\13\004\D | RS | 13 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-05-22 15:28 | 2021-05-24 16:35 | 61859.7763 | [6 empty] | 61860 | 44898 | 4.49 | 0 | 0 | 6.85 | 5819
TS5500Shv | GG\11\013\B | GG | 11 | 13 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-05-23 02:02 | 2021-05-23 12:46 | 13083.7563 | [6 empty] | 13084 | 9567 | 1.53 | 0 | 0 | 10.78 | 5457
TS5500Shv | GG\11\018\B | GG | 11 | 18 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-05-23 12:46 | 2021-05-24 00:14 | 13987.6191 | [6 empty] | 13988 | 10206 | 1.58 | 0 | 0 | 11.17 | 5425
TS5500Shv | GG\13\021\B | GG | 13 | 21 | B | 1 Prestrip - Thick | 30.645 | 30.645 | 30.645 | 2021-05-24 00:14 | 2021-05-27 16:46 | 95043.7913 | 95044 | [7 empty] | 0 | 0 | 9.94 | 14.27 | 5221.57
DRE2 | GG\11\020\B | GG | 11 | 20 | B | 6 DL | 100 | 0 | 100 | 2021-05-24 02:48 | 2021-05-26 16:34 | 207800.1743 |  |  |  |  | 207800 | 173167 |  |  | 0 | 19.14 | 0 | 12.72 | 5319.77
TS5500Exc | MW\39\007\B | MW | 39 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-05-24 16:35 | 2021-05-26 22:13 | 47440.8663 | 47441 | [7 empty] | 0 | 0 | 4.73 | 9.43 | 5505.51
TS6060#1 | GG\10\005\D | GG | 10 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-05-25 00:36 | 2021-05-26 21:32 | 60818.1266 | [6 empty] | 60818 | 45647 | 4.56 | 0 | 0 | 6.34 | 5828
PH4100A | RS\16\004\B | RS | 16 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-05-25 12:07 | 2021-05-26 03:32 | 26758.2101 | 26758 | [7 empty] | 0 | 0 | 2.66 | 9.05 | 5601.51
PH4100A | RS\16\007\X | RS | 16 | 7 | X | 1 Prestrip - Thick | 100 | 67.6485 | 67.6485 | 2021-05-26 03:32 | 2021-06-04 11:07 | 378782.1041 | 378782 | [7 empty] | 0 | 0 | 37 | 9.83 | 5378.32
DRE1 | RS\13\006\D | RS | 13 | 6 | D | 6 DL | 100 | 100 | 100 | 2021-05-26 07:58 | 2021-05-30 01:15 | 311896.2955 |  |  |  | 16036 | 311896 | 251228 |  |  | 0 | 26.73 | 0 | 7.5 | 5761.4
DRE2 | GG\11\021\B | GG | 11 | 21 | B | 6 DL | 100 | 0 | 100 | 2021-05-26 16:34 | 2021-05-29 17:09 | 244152.8223 |  |  |  |  | 244153 | 187810 |  |  | 0 | 20.07 | 0 | 13.6 | 5257.37
TS6060#1 | GG\10\004\D | GG | 10 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-05-26 21:32 | 2021-05-28 18:02 | 60234.5741 | [6 empty] | 60235 | 45208 | 4.52 | 0 | 0 | 6.21 | 5840
TS5500Exc | RS\16\004\B | RS | 16 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-05-26 22:13 | 2021-05-28 07:08 | 41464.1736 | [6 empty] | 41464 | 29629 | 2.95 | 0 | 0 | 9.05 | 5602
PH4100XPC#1 | GG\12\013\B | GG | 12 | 13 | B | 1 Prestrip - Thick | 100 | 87.5194 | 87.5194 | 2021-05-27 07:41 | 2021-06-02 12:15 | 340266.799 | 340267 | [7 empty] | 0 | 0 | 49.8 | 10.85 | 5449.6
TS Fleet 5 | MW\39\010\X | MW | 39 | 10 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-05-27 11:49 | 2021-06-04 02:00 | 357077.5204 | 357078 | [7 empty] | 0 | 0 | 39.35 | 12.17 | 5244.19
TS5500Shv | RS\16\005\A | RS | 16 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-05-27 16:46 | 2021-05-28 13:31 | 25303.3522 | [6 empty] | 25303 | 17163 | 1.71 | 0 | 0 | 17.49 | 4873
TS5500Exc | RS\16\005\A | RS | 16 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-05-28 07:08 | 2021-05-29 03:53 | 26137.5286 | [6 empty] | 26138 | 17728 | 1.77 | 0 | 0 | 17.49 | 4873
TS5500Shv | RS\16\006\X | RS | 16 | 6 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-05-28 13:31 | 2021-05-28 20:31 | 8539.5376 | [6 empty] | 8540 | 6039 | 0.6 | 0 | 0 | 11.28 | 5283
TS6060#1 | GG\10\003\D | GG | 10 | 3 | D | 8 Coal Mining | 67.8 | 0 | 67.8 | 2021-05-28 18:02 | 2021-05-30 00:24 | 41085.9341 | [6 empty] | 41086 | 30836 | 3.08 | 0 | 0 | 6.1 | 5850
TS5500Shv | GG\11\020\B | GG | 11 | 20 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-05-28 20:31 | 2021-05-30 15:37 | 52559.2073 | [6 empty] | 52559 | 37897 | 3.79 | 0 | 0 | 12.72 | 5320
TS5500Exc | RS\16\006\X | RS | 16 | 6 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-05-29 03:53 | 2021-05-29 10:53 | 8821.0609 | [6 empty] | 8821 | 6238 | 0.62 | 0 | 0 | 11.28 | 5283
TS5500Exc | RS\13\005\D | RS | 13 | 5 | D | 8 Coal Mining | 64 | 0 | 64 | 2021-05-29 10:53 | 2021-05-30 18:18 | 39570.4091 | [6 empty] | 39570 | 28742 | 2.87 | 0 | 0 | 7.08 | 5799
DRE2 | GG\11\022\B | GG | 11 | 22 | B | 6 DL | 100 | 0 | 100 | 2021-05-29 17:09 | 2021-06-01 12:32 | 226666.1654 |  |  |  |  | 226666 | 188888 |  |  | 0 | 19.37 | 0 | 14.61 | 5160.87
TS6060#1 | RS\16\005\B | RS | 16 | 5 | B | 1 Prestrip - Thick | 37.2787 | 37.2787 | 37.2787 | 2021-05-30 00:24 | 2021-05-30 11:15 | 11200.5738 | 11201 | [7 empty] | 0 | 0 | 1.11 | 9.26 | 5564.37
DRE1 | RS\13\007\D | RS | 13 | 7 | D | 6 DL | 100 | 100 | 100 | 2021-05-30 01:15 | 2021-06-03 12:32 | 374727.8827 |  |  |  | 13926 | 374728 | 212396 |  |  | 0 | 26.68 | 0 | 7.85 | 5729.35
TS6060#1 | RS\16\006\A | RS | 16 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-05-30 11:15 | 2021-06-07 08:04 | 194820.2053 | 194820 | [7 empty] | 0 | 0 | 19.42 | 17.85 | 4822.98
TS5500Shv | GG\11\021\B | GG | 11 | 21 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-05-30 15:37 | 2021-06-01 09:45 | 51371.8212 | [6 empty] | 51372 | 36805 | 3.68 | 0 | 0 | 13.6 | 5257
TS5500Exc | RS\13\006\D | RS | 13 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-05-30 18:18 | 2021-06-01 19:02 | 61385.0262 | [6 empty] | 61385 | 44482 | 4.45 | 0 | 0 | 7.5 | 5761
TS5500Shv | RS\13\005\D | RS | 13 | 5 | D | 8 Coal Mining | 36 | 0 | 36 | 2021-06-01 09:45 | 2021-06-02 04:02 | 22291.5851 | [6 empty] | 22292 | 16192 | 1.62 | 0 | 0 | 7.08 | 5799
DRE2 | GG\11\023\B | GG | 11 | 23 | B | 6 DL | 100 | 0 | 100 | 2021-06-01 12:32 | 2021-06-04 06:38 | 222315.0188 |  |  |  |  | 222315 | 185263 |  |  | 0 | 18.93 | 0 | 19.94 | 4700.33
TS5500Exc | MW\39\007\B | MW | 39 | 7 | B | 8 Coal Mining | 51.9 | 0 | 51.9 | 2021-06-01 19:02 | 2021-06-02 11:22 | 20572.8401 | [6 empty] | 20573 | 15169 | 1.52 | 0 | 0 | 9.43 | 5506
TS5500Shv | GG\11\022\B | GG | 11 | 22 | B | 8 Coal Mining | 58.5 | 0 | 58.5 | 2021-06-02 04:02 | 2021-06-03 04:44 | 30111.666 | [6 empty] | 30112 | 21485 | 2.15 | 0 | 0 | 14.61 | 5161
TS5500Exc | MW\39\008\A | MW | 39 | 8 | A | 1 Prestrip - Thick | 9.2773 | 9.2773 | 9.2773 | 2021-06-02 11:22 | 2021-06-04 04:18 | 36319.1575 | 36319 | [7 empty] | 0 | 0 | 3.6 | 13.28 | 5229.48
PH4100XPC#1 | GG\13\002\X1 | GG | 13 | 2 | X1 | 1 Prestrip - Thick | 100 | 81.9931 | 81.9931 | 2021-06-02 12:15 | 2021-06-17 01:21 | 789721.7866 | 789722 | [7 empty] | 0 | 0 | 69.93 | 10.65 | 5323.37
TS5500Shv | MW\39\007\B | MW | 39 | 7 | B | 8 Coal Mining | 48.1 | 0 | 48.1 | 2021-06-03 04:44 | 2021-06-03 20:21 | 19041.4039 | [6 empty] | 19041 | 14040 | 1.4 | 0 | 0 | 9.43 | 5506
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2021-06-03 12:32 | 2021-06-05 12:32
TS5500Shv | RS\13\007\D | RS | 13 | 7 | D | 7 PostStrip | 100 | 0 | 100 | 2021-06-03 20:21 | 2021-06-05 21:02 | 52198.2716 |  |  | 52198 | [5 empty] | 0 | 0 | 0 | 7.85 | 5729.35
TS Fleet 5 | MW\40\003\B | MW | 40 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-04 02:00 | 2021-06-06 06:37 | 103137.2661 | 103137 | [7 empty] | 0 | 0 | 7.59 | 12.07 | 5295.42
TS5500Exc | MW\39\008\A | MW | 39 | 8 | A | 8 Coal Mining | 92.5 | 0 | 92.5 | 2021-06-04 04:18 | 2021-06-05 14:48 | 43456.7282 | [6 empty] | 43457 | 31535 | 3.17 | 0 | 0 | 13.28 | 5229
DRE2 | GG\11\024\B | GG | 11 | 24 | B | 6 DL | 100 | 0 | 100 | 2021-06-04 06:38 | 2021-06-07 13:37 | 265708.1995 |  |  |  |  | 265708 | 204391 |  |  | 0 | 21.63 | 0 | 0 | 0
PH4100A | RS\16\005\B | RS | 16 | 5 | B | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2021-06-04 11:07 | 2021-06-04 21:58 | 18844.9275 | 18845 | [7 empty] | 0 | 0 | 1.88 | 9.26 | 5564.37
PH4100A | RS\17\007\X | RS | 17 | 7 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-04 21:58 | 2021-06-17 17:57 | 522307.5149 | 522308 | [7 empty] | 0 | 0 | 56.72 | 10.02 | 5361.12
DRE1 | MW\35\002\D | MW | 35 | 2 | D | 6 DL | 100 | 0 | 100 | 2021-06-05 12:32 | 2021-06-09 02:39 | 300837.7859 |  |  |  | 21395 | 300838 | 216327 |  |  | 0 | 35 | 0 | 7.05 | 5793.95
TS5500Exc | RS\16\005\B | RS | 16 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-06-05 14:48 | 2021-06-06 22:32 | 39978.011 | [6 empty] | 39978 | 28540 | 2.84 | 0 | 0 | 9.26 | 5564
TS5500Shv | RS\16\007\X | RS | 16 | 7 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-06-05 21:02 | 2021-06-06 03:30 | 7884.1223 | [6 empty] | 7884 | 5652 | 0.57 | 0 | 0 | 9.83 | 5378
TS5500Shv | GG\11\023\B | GG | 11 | 23 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-06-06 03:30 | 2021-06-08 03:44 | 58822.3151 | [6 empty] | 58822 | 41019 | 4.09 | 0 | 0 | 19.94 | 4700
TS Fleet 5 | MW\40\004\D | MW | 40 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-06 06:37 | 2021-06-06 14:29 | 15391.0027 | 15391 | [7 empty] | 0 | 0 | 2.12 | 6.5 | 5842.15
TS Fleet 5 | MW\40\005\D | MW | 40 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-06 14:29 | 2021-06-08 19:10 | 103288.7273 | 103289 | [7 empty] | 0 | 0 | 10.68 | 5.97 | 5887.96
TS5500Exc | RS\16\007\X | RS | 16 | 7 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-06-06 22:32 | 2021-06-07 05:00 | 8144.0385 | [6 empty] | 8144 | 5838 | 0.59 | 0 | 0 | 9.83 | 5378
TS5500Exc | RS\13\007\D | RS | 13 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-06-07 05:00 | 2021-06-09 07:08 | 63136.477 | [6 empty] | 63136 | 45663 | 4.39 | 0 | 0 | 7.85 | 5729
TS6060#1 | RS\16\007\A | RS | 16 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-07 08:04 | 2021-06-14 10:03 | 175383.3624 | 175383 | [7 empty] | 0 | 0 | 19.67 | 16.33 | 4936.4
DRE2 | GG\10\012\D | GG | 10 | 12 | D | 6 DL | 100 | 100 | 100 | 2021-06-07 13:37 | 2021-06-13 18:44 | 501556.7307 |  |  |  | 11678 | 501557 | 221876 |  |  | 0 | 23.35 | 0 | 6.19 | 5844.67
TS5500Shv | RS\16\006\A | RS | 16 | 6 | A | 8 Coal Mining | 23.9 | 0 | 23.9 | 2021-06-08 03:44 | 2021-06-08 13:45 | 12212.8095 | [6 empty] | 12213 | 8261 | 0.82 | 0 | 0 | 17.85 | 4823
TS5500Shv | MW\39\008\A | MW | 39 | 8 | A | 8 Coal Mining | 7.5 | 0 | 7.5 | 2021-06-08 13:45 | 2021-06-08 16:38 | 3515.6891 | [6 empty] | 3516 | 2551 | 0.26 | 0 | 0 | 13.28 | 5229
TS5500Shv | MW\39\010\X | MW | 39 | 10 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-06-08 16:38 | 2021-06-08 21:54 | 6417.3107 | [6 empty] | 6417 | 4681 | 0.56 | 0 | 0 | 12.17 | 5244
TS Fleet 5 | MW\40\006\B | MW | 40 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-08 19:10 | 2021-06-13 19:49 | 236451.95 | 236452 | [7 empty] | 0 | 0 | 24.12 | 8.92 | 5577.88
TS5500Shv | GG\13\022\B | GG | 13 | 22 | B | 1 Prestrip - Thick | 4.7955 | 4.7955 | 4.7955 | 2021-06-08 21:54 | 2021-06-09 12:02 | 15152.4575 | 15152 | [7 empty] | 0 | 0 | 1.53 | 15.51 | 5110.96
DRE1 | MW\35\003\D | MW | 35 | 3 | D | 6 DL | 100 | 100 | 100 | 2021-06-09 02:39 | 2021-06-12 15:29 | 296316.7872 |  |  |  | 15235 | 296317 | 238678 |  |  | 0 | 25.44 | 0 | 6.83 | 5812.89
TS5500Exc | MW\35\002\D | MW | 35 | 2 | D | 8 Coal Mining | 100 | 0 | 57.9 | 2021-06-09 07:08 | 2021-06-10 02:49 | 24795.2873 | [6 empty] | 24795 | 18601 | 2.74 | 0 | 0 | 7.05 | 5794
TS5500Shv | MW\35\002\D | MW | 35 | 2 | D | 8 Coal Mining | 78.4 | 0 | 42.1 | 2021-06-09 12:02 | 2021-06-10 02:49 | 18030.4341 | [6 empty] | 18030 | 13526 | 1.99 | 0 | 0 | 7.05 | 5794
TS5500Shv | GG\14\002\X1 | GG | 14 | 2 | X1 | 1 Prestrip - Thick | 28.8321 | 28.8321 | 28.8321 | 2021-06-10 02:49 | 2021-06-20 10:20 | 264434.1077 | 264434 | [7 empty] | 0 | 0 | 25.38 | 10.23 | 5347.54
TS5500Exc | RS\16\006\A | RS | 16 | 6 | A | 8 Coal Mining | 76.1 | 0 | 76.1 | 2021-06-10 02:49 | 2021-06-11 09:38 | 38827.3372 | [6 empty] | 38827 | 26265 | 2.62 | 0 | 0 | 17.85 | 4823
TS5500Exc | MW\39\008\B | MW | 39 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-11 09:38 | 2021-06-13 06:33 | 39713.0173 | 39713 | [7 empty] | 0 | 0 | 3.99 | 10.11 | 5424.29
DRE1 | MW\35\004\D | MW | 35 | 4 | D | 6 DL | 100 | 100 | 100 | 2021-06-12 15:29 | 2021-06-16 16:41 | 339508.1081 |  |  |  | 17455 | 339508 | 273468 |  |  | 0 | 29.17 | 0 | 6.61 | 5831.94
TS5500Exc | MW\35\003\D | MW | 35 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-06-13 06:33 | 2021-06-14 07:41 | 31661.9829 | [6 empty] | 31662 | 23770 | 2.38 | 0 | 0 | 6.83 | 5813
DRE2 | GG\10\013\D | GG | 10 | 13 | D | 6 DL | 100 | 100 | 100 | 2021-06-13 18:44 | 2021-06-16 20:40 | 248697.3681 |  |  |  | 5790 | 248697 | 110017 |  |  | 0 | 22.79 | 0 | 6.41 | 5825.8
TS Fleet 5 | MW\40\007\A | MW | 40 | 7 | A | 1 Prestrip - Thick | 97.7296 | 97.7296 | 97.7296 | 2021-06-13 19:49 | 2021-06-19 09:43 | 262468.1601 | 262468 | [7 empty] | 0 | 0 | 27.18 | 12.69 | 5265.75
TS5500Exc | MW\39\008\B | MW | 39 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-06-14 07:41 | 2021-06-15 13:58 | 38144.624 | [6 empty] | 38145 | 28077 | 2.81 | 0 | 0 | 10.11 | 5424
TS6060#1 | GG\10\002\D | GG | 10 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-06-14 10:03 | 2021-06-16 08:52 | 63373.9541 | [6 empty] | 63374 | 47564 | 4.56 | 0 | 0 | 6.1 | 5850
TS5500Exc | RS\16\007\A | RS | 16 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-06-15 13:58 | 2021-06-17 00:23 | 43364.4074 | [6 empty] | 43364 | 29767 | 3.39 | 0 | 0 | 16.33 | 4936
TS6060#1 | GG\11\012\B | GG | 11 | 12 | B | 8 Coal Mining | 72.9 | 0 | 72.9 | 2021-06-16 08:52 | 2021-06-17 10:27 | 34619.5209 | [6 empty] | 34620 | 25387 | 2.54 | 0 | 0 | 10.16 | 5506
DRE1 | MW\35\005\D | MW | 35 | 5 | D | 6 DL | 100 | 100 | 100 | 2021-06-16 16:41 | 2021-06-21 08:50 | 391804.3097 |  |  |  | 22361 | 391804 | 297088 |  |  | 0 | 32.07 | 0 | 6 | 5884.26
DRE2 | GG\10\018\D | GG | 10 | 18 | D | 6 DL | 100 | 100 | 100 | 2021-06-16 20:40 | 2021-06-19 23:04 | 250273.4407 |  |  |  | 5827 | 250273 | 110715 |  |  | 0 | 22.16 | 0 | 6.42 | 5824.68
TS5500Exc | MW\35\004\D | MW | 35 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-06-17 00:23 | 2021-06-18 01:19 | 31403.2112 | [6 empty] | 31403 | 23594 | 2.36 | 0 | 0 | 6.61 | 5832
PH4100XPC#1 | GG\13\003\X1 | GG | 13 | 3 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-17 01:21 | 2021-07-03 12:28 | 891267.4535 | 891267 | [7 empty] | 0 | 0 | 82.69 | 10.03 | 5375.76
TS6060#1 | GG\13\002\X1 | GG | 13 | 2 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-06-17 10:27 | 2021-06-17 15:15 | 6501.778 | [6 empty] | 6502 | 4809 | 0.53 | 0 | 0 | 10.65 | 5323
TS6060#1 | GG\11\013\B | GG | 11 | 13 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-06-17 15:15 | 2021-06-18 01:59 | 14521.5318 | [6 empty] | 14522 | 10618 | 1.7 | 0 | 0 | 10.78 | 5457
PH4100A | RS\16\006\B | RS | 16 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-17 17:57 | 2021-06-18 09:43 | 27358.9191 | 27359 | [7 empty] | 0 | 0 | 2.72 | 9.24 | 5564.01
TS5500Exc | RS\17\007\X | RS | 17 | 7 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-06-18 01:19 | 2021-06-18 07:09 | 7347.7251 | [6 empty] | 7348 | 5256 | 0.59 | 0 | 0 | 10.02 | 5361
TS6060#1 | GG\11\018\B | GG | 11 | 18 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-06-18 01:59 | 2021-06-18 13:27 | 15524.7201 | [6 empty] | 15525 | 11327 | 1.76 | 0 | 0 | 11.17 | 5425
TS5500Exc | MW\39\009\A | MW | 39 | 9 | A | 1 Prestrip - Thick | 5.9589 | 5.9589 | 5.9589 | 2021-06-18 07:09 | 2021-06-19 16:51 | 29914.4766 | 29914 | [7 empty] | 0 | 0 | 2.96 | 12.12 | 5324.72
PH4100A | RS\16\007\B | RS | 16 | 7 | B | 1 Prestrip - Thick | 100 | 73.0994 | 73.0994 | 2021-06-18 09:43 | 2021-06-18 19:32 | 17059.8618 | 17060 | [7 empty] | 0 | 0 | 1.95 | 9.13 | 5585.48
TS6060#1 | RS\16\007\B | RS | 16 | 7 | B | 1 Prestrip - Thick | 37.2787 | 26.9006 | 26.9006 | 2021-06-18 13:27 | 2021-06-18 19:32 | 6278.0284 | 6278 | [7 empty] | 0 | 0 | 0.72 | 9.13 | 5585.48
PH4100A | RS\18\007\X | RS | 18 | 7 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-18 19:32 | 2021-06-30 13:39 | 478892.4841 | 478892 | [7 empty] | 0 | 0 | 58.38 | 10.28 | 5338.39
TS6060#1 | GG\11\019\B | GG | 11 | 19 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-06-18 19:32 | 2021-06-20 10:11 | 52302.5971 | [6 empty] | 52303 | 38052 | 3.8 | 0 | 0 | 11.44 | 5409
TS Fleet 5 | MW\40\008\A | MW | 40 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-19 09:43 | 2021-06-27 18:53 | 394276.4991 | 394276 | [7 empty] | 0 | 0 | 39.6 | 13.45 | 5215.86
TS5500Exc | RS\16\006\B | RS | 16 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-06-19 16:51 | 2021-06-20 23:45 | 38921.807 | [6 empty] | 38922 | 27742 | 2.76 | 0 | 0 | 9.24 | 5564
DRE2 | GG\10\019\D | GG | 10 | 19 | D | 6 DL | 100 | 100 | 100 | 2021-06-19 23:04 | 2021-06-25 16:04 | 460815.839 |  |  |  | 10729 | 460816 | 203853 |  |  | 0 | 21.43 | 0 | 6.25 | 5839.86
TS6060#1 | GG\11\022\B | GG | 11 | 22 | B | 8 Coal Mining | 41.5 | 0 | 41.5 | 2021-06-20 10:11 | 2021-06-21 01:57 | 21348.68 | [6 empty] | 21349 | 15232 | 1.52 | 0 | 0 | 14.61 | 5161
TS5500Shv | GG\13\002\X1 | GG | 13 | 2 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-06-20 10:20 | 2021-06-20 15:08 | 5858.0376 | [6 empty] | 5858 | 4333 | 0.47 | 0 | 0 | 10.65 | 5323
TS5500Shv | RS\17\007\X | RS | 17 | 7 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-06-20 15:08 | 2021-06-20 20:58 | 7113.2232 | [6 empty] | 7113 | 5088 | 0.57 | 0 | 0 | 10.02 | 5361
TS5500Shv | GG\13\002\X2 | GG | 13 | 2 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2021-06-20 20:58 | 2021-06-23 17:28 | 73427.7767 | 73428 | [7 empty] | 0 | 0 | 8.38 | 0 | 0
TS5500Exc | RS\16\007\B | RS | 16 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-06-20 23:45 | 2021-06-22 02:13 | 33335.6848 | [6 empty] | 33336 | 23774 | 2.72 | 0 | 0 | 9.13 | 5585
TS6060#1 | GG\10\013\D | GG | 10 | 13 | D | 8 Coal Mining | 18 | 0 | 18 | 2021-06-21 01:57 | 2021-06-21 06:16 | 5839.6612 | [6 empty] | 5840 | 4373 | 0.87 | 0 | 0 | 6.41 | 5826
TS6060#1 | GG\10\018\D | GG | 10 | 18 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-06-21 06:16 | 2021-06-21 19:15 | 17572.3341 | [6 empty] | 17572 | 13169 | 2.54 | 0 | 0 | 6.42 | 5825
DRE1 | MW\35\006\D | MW | 35 | 6 | D | 6 DL | 100 | 100 | 100 | 2021-06-21 08:50 | 2021-06-25 18:52 | 370343.8036 |  |  |  | 21137 | 370344 | 280815 |  |  | 0 | 30.22 | 0 | 5.68 | 5911.27
TS6060#1 | RS\17\003\A | RS | 17 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-21 19:15 | 2021-06-27 20:25 | 149774.2957 | 149774 | [7 empty] | 0 | 0 | 20.87 | 12.94 | 5285.58
TS5500Exc | MW\35\005\D | MW | 35 | 5 | D | 8 Coal Mining | 72.5 | 0 | 72.5 | 2021-06-22 02:13 | 2021-06-23 12:35 | 43287.5596 | [6 empty] | 43288 | 32678 | 3.27 | 0 | 0 | 6 | 5884
TS5500Exc | MW\39\009\A | MW | 39 | 9 | A | 8 Coal Mining | 71.4 | 0 | 71.4 | 2021-06-23 12:35 | 2021-06-24 14:43 | 32911.937 | [6 empty] | 32912 | 24067 | 2.41 | 0 | 0 | 12.12 | 5325
TS5500Shv | GG\13\002\B | GG | 13 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-23 17:28 | 2021-06-26 10:27 | 69657.9119 | 69658 | [7 empty] | 0 | 0 | 8.1 | 10.36 | 5485.54
TS5500Exc | RS\17\004\A | RS | 17 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-06-24 14:43 | 2021-06-25 07:27 | 21067.0328 | [6 empty] | 21067 | 14449 | 1.44 | 0 | 0 | 15.94 | 5021
TS5500Exc | MW\39\010\X | MW | 39 | 10 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-06-25 07:27 | 2021-06-25 12:42 | 6628.8703 | [6 empty] | 6629 | 4835 | 0.58 | 0 | 0 | 12.17 | 5244
TS5500Exc | MW\39\010\A | MW | 39 | 10 | A | 1 Prestrip - Thick | 47.5301 | 47.5301 | 47.5301 | 2021-06-25 12:42 | 2021-06-28 22:21 | 72199.1932 | 72199 | [7 empty] | 0 | 0 | 9.08 | 10.62 | 5447.21
DRE2 | GG\10\020\D | GG | 10 | 20 | D | 6 DL | 100 | 100 | 100 | 2021-06-25 16:04 | 2021-07-01 05:13 | 447880.0497 |  |  |  | 10428 | 447880 | 198131 |  |  | 0 | 20.85 | 0 | 6.04 | 5857.23
DRE1 | MW\35\007\D | MW | 35 | 7 | D | 6 DL | 100 | 100 | 100 | 2021-06-25 18:52 | 2021-06-29 22:48 | 349069.7439 |  |  |  | 17947 | 349070 | 281170 |  |  | 0 | 29.93 | 0 | 5.72 | 5909.02
TS5500Shv | GG\13\002\B | GG | 13 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-06-26 10:27 | 2021-06-28 00:33 | 46450.8722 | [6 empty] | 46451 | 34111 | 4.02 | 0 | 0 | 10.36 | 5486
TS Fleet 5 | MW\39\010\A | MW | 39 | 10 | A | 1 Prestrip - Thick | 62.2553 | 52.4699 | 52.4699 | 2021-06-27 18:53 | 2021-06-29 11:33 | 79702.7146 | 79703 | [7 empty] | 0 | 0 | 10.02 | 10.62 | 5447.21
TS6060#1 | GG\10\019\D | GG | 10 | 19 | D | 8 Coal Mining | 35.5 | 0 | 35.5 | 2021-06-27 20:25 | 2021-06-28 13:24 | 22998.4721 | [6 empty] | 22998 | 17262 | 1.73 | 0 | 0 | 6.25 | 5840
TS5500Shv | GG\10\012\D | GG | 10 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-06-28 00:33 | 2021-06-30 05:37 | 64715.3985 | [6 empty] | 64715 | 48536 | 4.85 | 0 | 0 | 6.19 | 5845
TS6060#1 | RS\17\004\B | RS | 17 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-28 13:24 | 2021-06-29 13:57 | 25316.3692 | 25316 | [7 empty] | 0 | 0 | 2.52 | 9.03 | 5599.98
TS5500Exc | RS\17\003\A | RS | 17 | 3 | A | 8 Coal Mining | 52.1 | 0 | 52.1 | 2021-06-28 22:21 | 2021-06-29 12:22 | 17657.4947 | [6 empty] | 17657 | 12320 | 1.57 | 0 | 0 | 12.94 | 5286
TS Fleet 5 | MW\40\009\A | MW | 40 | 9 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-29 11:33 | 2021-07-10 06:12 | 506948.3872 | 506948 | [7 empty] | 0 | 0 | 50.16 | 12.16 | 5321.66
TS5500Exc | MW\35\006\D | MW | 35 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-06-29 12:22 | 2021-07-01 09:53 | 57345.9886 | [6 empty] | 57346 | 43427 | 4.34 | 0 | 0 | 5.68 | 5911
TS6060#1 | RS\19\003\X | RS | 19 | 3 | X | 1 Prestrip - Thick | 37.5302 | 37.5302 | 37.5302 | 2021-06-29 13:57 | 2021-07-02 14:12 | 72142.053 | 72142 | [7 empty] | 0 | 0 | 11.97 | 12.66 | 5149.43
DRE1 | MW\35\008\D | MW | 35 | 8 | D | 6 DL | 100 | 100 | 100 | 2021-06-29 22:48 | 2021-07-04 02:22 | 347856.152 |  |  |  | 17885 | 347856 | 280193 |  |  | 0 | 29.83 | 0 | 5.74 | 5908.46
TS5500Shv | MW\35\003\D | MW | 35 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-06-30 05:37 | 2021-07-01 06:45 | 30651.494 | [6 empty] | 30651 | 23012 | 2.3 | 0 | 0 | 6.83 | 5813
PH4100A | RS\17\007\A | RS | 17 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-06-30 13:39 | 2021-07-04 05:28 | 152422.8946 | 152423 | [7 empty] | 0 | 0 | 19.3 | 16.66 | 4914.87
DRE2 | GG\10\021\D | GG | 10 | 21 | D | 6 DL | 100 | 100 | 100 | 2021-07-01 05:13 | 2021-07-06 13:08 | 430300.2775 |  |  |  | 10019 | 430300 | 190354 |  |  | 0 | 20.04 | 0 | 5.97 | 5862.95
TS5500Shv | RS\18\007\X | RS | 18 | 7 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-07-01 06:45 | 2021-07-01 11:56 | 6319.5187 | [6 empty] | 6320 | 4511 | 0.58 | 0 | 0 | 10.28 | 5338
TS5500Exc | RS\18\007\X | RS | 18 | 7 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-07-01 09:53 | 2021-07-01 15:04 | 6527.8545 | [6 empty] | 6528 | 4659 | 0.59 | 0 | 0 | 10.28 | 5338
TS5500Shv | GG\10\013\D | GG | 10 | 13 | D | 8 Coal Mining | 82 | 0 | 82 | 2021-07-01 11:56 | 2021-07-02 09:41 | 26521.625 | [6 empty] | 26522 | 19859 | 3.96 | 0 | 0 | 6.41 | 5826
TS5500Exc | MW\35\007\D | MW | 35 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-07-01 15:04 | 2021-07-03 13:50 | 58909.2713 | [6 empty] | 58909 | 44577 | 4.46 | 0 | 0 | 5.72 | 5909
TS5500Shv | GG\10\018\D | GG | 10 | 18 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-07-02 09:41 | 2021-07-02 22:40 | 15832.4991 | [6 empty] | 15832 | 11865 | 2.28 | 0 | 0 | 6.42 | 5825
TS6060#1 | GG\10\020\D | GG | 10 | 20 | D | 8 Coal Mining | 93.4 | 0 | 93.4 | 2021-07-02 14:12 | 2021-07-04 10:21 | 59761.1539 | [6 empty] | 59761 | 44927 | 4.49 | 0 | 0 | 6.04 | 5857
TS5500Shv | MW\35\004\D | MW | 35 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-07-02 22:40 | 2021-07-03 23:36 | 30400.981 | [6 empty] | 30401 | 22841 | 2.28 | 0 | 0 | 6.61 | 5832
PH4100XPC#1 | GG\13\004\X1 | GG | 13 | 4 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-03 12:28 | 2021-07-17 23:47 | 801358.6895 | 801359 | [7 empty] | 0 | 0 | 77.89 | 9.72 | 5400.87
TS5500Exc | MW\39\010\A | MW | 39 | 10 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-07-03 13:50 | 2021-07-04 03:24 | 17078.1579 | [6 empty] | 17078 | 12605 | 1.68 | 0 | 0 | 10.62 | 5447
TS5500Shv | GG\13\003\X1 | GG | 13 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2021-07-03 23:36 | 2021-07-04 12:44 | 16015.9387 | [6 empty] | 16016 | 11899 | 1.23 | 0 | 0 | 10.03 | 5376
DRE1 | MW\35\009\D | MW | 35 | 9 | D | 6 DL | 100 | 100 | 100 | 2021-07-04 02:22 | 2021-07-08 01:49 | 333416.232 |  |  |  | 17142 | 333416 | 268561 |  |  | 0 | 28.59 | 0 | 5.51 | 5927.63
TS5500Exc | MW\35\008\D | MW | 35 | 8 | D | 8 Coal Mining | 52.3 | 0 | 52.3 | 2021-07-04 03:24 | 2021-07-05 05:01 | 32263.2807 | [6 empty] | 32263 | 24416 | 2.44 | 0 | 0 | 5.74 | 5908
PH4100A | RS\17\006\X | RS | 17 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-04 05:28 | 2021-07-17 02:04 | 522913.7086 | 522914 | [7 empty] | 0 | 0 | 51.87 | 11.52 | 5265.77
TS6060#1 | RS\19\004\X | RS | 19 | 4 | X | 1 Prestrip - Thick | 66.5556 | 66.5556 | 66.5556 | 2021-07-04 10:21 | 2021-07-16 10:52 | 290188.5983 | 290189 | [7 empty] | 0 | 0 | 28.83 | 12.79 | 5148.94
TS5500Shv | GG\13\003\X2 | GG | 13 | 3 | X2 | 1 Prestrip - Thick | 92.1587 | 0 | 92.1587 | 2021-07-04 12:44 | 2021-07-07 16:20 | 81050.9846 | 81051 | [7 empty] | 0 | 0 | 8.38 | 0 | 0
TS5500Exc | RS\17\007\A | RS | 17 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-07-05 05:01 | 2021-07-06 11:18 | 38154.7274 | [6 empty] | 38155 | 26130 | 3.36 | 0 | 0 | 16.66 | 4915
TS5500Exc | RS\17\004\B | RS | 17 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-07-06 11:18 | 2021-07-07 03:42 | 20647.2111 | [6 empty] | 20647 | 14752 | 1.47 | 0 | 0 | 9.03 | 5600
DRE2 | GG\10\022\D | GG | 10 | 22 | D | 6 DL | 100 | 100 | 100 | 2021-07-06 13:08 | 2021-07-12 01:01 | 443652.7792 |  |  |  | 10330 | 443653 | 196261 |  |  | 0 | 20.66 | 0 | 5.96 | 5859.18
TS5500Exc | MW\40\006\B | MW | 40 | 6 | B | 8 Coal Mining | 23.5 | 0 | 23.5 | 2021-07-07 03:42 | 2021-07-07 08:56 | 6592.3173 | [6 empty] | 6592 | 4861 | 0.49 | 0 | 0 | 8.92 | 5578
TS5500Exc | MW\40\007\A | MW | 40 | 7 | A | 1 Prestrip - Thick | 2.2704 | 2.2704 | 2.2704 | 2021-07-07 08:56 | 2021-07-07 15:47 | 6097.5693 | 6098 | [7 empty] | 0 | 0 | 0.63 | 12.69 | 5265.75
TS5500Exc | MW\40\007\A | MW | 40 | 7 | A | 8 Coal Mining | 75 | 0 | 75 | 2021-07-07 15:47 | 2021-07-08 17:40 | 32582.9705 | [6 empty] | 32583 | 23694 | 2.36 | 0 | 0 | 12.69 | 5266
TS5500Shv | GG\10\019\D | GG | 10 | 19 | D | 8 Coal Mining | 64.5 | 0 | 64.5 | 2021-07-07 16:20 | 2021-07-09 02:33 | 41719.5857 | [6 empty] | 41720 | 31314 | 3.13 | 0 | 0 | 6.25 | 5840
DRE1 | MW\35\010\D | MW | 35 | 10 | D | 6 DL | 100 | 100 | 100 | 2021-07-08 01:49 | 2021-07-12 09:09 | 360952.4932 |  |  |  | 13112 | 360952 | 203510 |  |  | 0 | 28.75 | 0 | 5.27 | 5948.32
TS5500Exc | MW\35\009\D | MW | 35 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-07-08 17:40 | 2021-07-10 17:21 | 60071.8378 | [6 empty] | 60072 | 45606 | 4.56 | 0 | 0 | 5.51 | 5928
TS5500Shv | MW\35\005\D | MW | 35 | 5 | D | 8 Coal Mining | 27.5 | 0 | 27.5 | 2021-07-09 02:33 | 2021-07-09 16:03 | 16452.4552 | [6 empty] | 16452 | 12420 | 1.24 | 0 | 0 | 6 | 5884
TS5500Shv | RS\17\003\A | RS | 17 | 3 | A | 8 Coal Mining | 47.9 | 0 | 47.9 | 2021-07-09 16:03 | 2021-07-10 05:22 | 16239.1353 | [6 empty] | 16239 | 11331 | 1.44 | 0 | 0 | 12.94 | 5286
TS5500Shv | MW\39\009\A | MW | 39 | 9 | A | 8 Coal Mining | 28.6 | 0 | 28.6 | 2021-07-10 05:22 | 2021-07-10 16:09 | 13163.4958 | [6 empty] | 13163 | 9626 | 0.96 | 0 | 0 | 12.12 | 5325
TS Fleet 5 | MW\40\010\X | MW | 40 | 10 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-10 06:12 | 2021-07-17 04:58 | 326877.7584 | 326878 | [7 empty] | 0 | 0 | 39.82 | 12.16 | 5246.71
TS5500Shv | GG\10\020\D | GG | 10 | 20 | D | 8 Coal Mining | 6.6 | 0 | 6.6 | 2021-07-10 16:09 | 2021-07-10 19:37 | 4214.7982 | [6 empty] | 4215 | 3169 | 0.32 | 0 | 0 | 6.04 | 5857
TS5500Exc | MW\39\009\B | MW | 39 | 9 | B | 1 Prestrip - Thick | 69.9393 | 69.9393 | 69.9393 | 2021-07-10 17:21 | 2021-07-11 19:10 | 22830.413 | 22830 | [7 empty] | 0 | 0 | 2.29 | 9.39 | 5516.4
TS5500Shv | GG\10\021\D | GG | 10 | 21 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-07-10 19:37 | 2021-07-11 20:15 | 30042.2374 | [6 empty] | 30042 | 22603 | 2.26 | 0 | 0 | 5.97 | 5863
TS5500Exc | MW\40\008\A | MW | 40 | 8 | A | 8 Coal Mining | 59.5 | 0 | 59.5 | 2021-07-11 19:10 | 2021-07-12 17:25 | 28025.7883 | [6 empty] | 28026 | 20312 | 2.04 | 0 | 0 | 13.45 | 5216
TS5500Shv | MW\35\008\D | MW | 35 | 8 | D | 8 Coal Mining | 47.7 | 0 | 47.7 | 2021-07-11 20:15 | 2021-07-12 20:21 | 29376.9129 | [6 empty] | 29377 | 22232 | 2.22 | 0 | 0 | 5.74 | 5908
DRE2 | GG\10\023\D | GG | 10 | 23 | D | 6 DL | 100 | 100 | 100 | 2021-07-12 01:01 | 2021-07-17 14:10 | 447867.2156 |  |  |  | 10428 | 447867 | 198125 |  |  | 0 | 20.84 | 0 | 5.89 | 5852.64
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2021-07-12 09:09 | 2021-07-14 09:09
TS5500Exc | MW\40\009\A | MW | 40 | 9 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-07-12 17:25 | 2021-07-14 05:45 | 45778.23 | [6 empty] | 45778 | 33452 | 3.35 | 0 | 0 | 12.16 | 5322
TS5500Shv | GG\10\022\D | GG | 10 | 22 | D | 8 Coal Mining | 77.1 | 0 | 77.1 | 2021-07-12 20:21 | 2021-07-14 08:55 | 44599.3517 | [6 empty] | 44599 | 33635 | 3.36 | 0 | 0 | 5.96 | 5859
TS5500Exc | MW\40\009\B | MW | 40 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-14 05:45 | 2021-07-15 18:35 | 32562.4003 | 32562 | [7 empty] | 0 | 0 | 3.26 | 9.4 | 5514.22
TS5500Shv | MW\35\010\D | MW | 35 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2021-07-14 08:55 | 2021-07-16 03:28 | 45612.3933 |  |  | 45612 | [5 empty] | 0 | 0 | 0 | 5.27 | 5948.32
DRE1 | RS\14\003\D | RS | 14 | 3 | D | 6 DL | 100 | 100 | 100 | 2021-07-14 09:09 | 2021-07-18 09:51 | 337790.8088 |  |  |  | 17367 | 337791 | 272085 |  |  | 0 | 26.37 | 0 | 6.38 | 5859.91
TS5500Exc | MW\40\009\B | MW | 40 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-07-15 18:35 | 2021-07-17 01:08 | 38484.3042 | [6 empty] | 38484 | 28496 | 2.86 | 0 | 0 | 9.4 | 5514
TS5500Shv | MW\35\010\D | MW | 35 | 10 | D | 8 Coal Mining | 52.1 | 0 | 52.1 | 2021-07-16 03:28 | 2021-07-17 02:05 | 27588.1776 | [6 empty] | 27588 | 21029 | 2.35 | 0 | 0 | 5.27 | 5948
TS6060#1 | GG\10\021\D | GG | 10 | 21 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-07-16 10:52 | 2021-07-17 11:30 | 33343.5822 | [6 empty] | 33344 | 25087 | 2.51 | 0 | 0 | 5.97 | 5863
TS5500Exc | MW\35\010\D | MW | 35 | 10 | D | 8 Coal Mining | 47.9 | 0 | 47.9 | 2021-07-17 01:08 | 2021-07-17 21:14 | 25332.7461 | [6 empty] | 25333 | 19310 | 2.15 | 0 | 0 | 5.27 | 5948
PH4100A | RS\17\003\B | RS | 17 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-17 02:04 | 2021-07-17 12:47 | 18603.7029 | 18604 | [7 empty] | 0 | 0 | 2.32 | 8.71 | 5646.04
TS5500Shv | MW\39\010\A | MW | 39 | 10 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-07-17 02:05 | 2021-07-17 15:39 | 16533.1103 | [6 empty] | 16533 | 12203 | 1.62 | 0 | 0 | 10.62 | 5447
TS Fleet 5 | MW\39\009\B | MW | 39 | 9 | B | 1 Prestrip - Thick | 30.0607 | 30.0607 | 30.0607 | 2021-07-17 04:58 | 2021-07-17 09:59 | 9812.7743 | 9813 | [7 empty] | 0 | 0 | 0.98 | 9.39 | 5516.4
TS Fleet 5 | MW\41\003\B | MW | 41 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-17 09:59 | 2021-07-21 00:16 | 169107.8082 | 169108 | [7 empty] | 0 | 0 | 16.61 | 11.69 | 5324.39
TS6060#1 | MW\39\009\B | MW | 39 | 9 | B | 8 Coal Mining | 100 | 0 | 58.9 | 2021-07-17 11:30 | 2021-07-18 04:29 | 22987.1063 | [6 empty] | 22987 | 17010 | 1.7 | 0 | 0 | 9.39 | 5516
PH4100A | RS\18\006\X | RS | 18 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-17 12:47 | 2021-07-30 18:35 | 539141.0548 | 539141 | [7 empty] | 0 | 0 | 53.68 | 11.74 | 5247.01
DRE2 | GG\10\024\D | GG | 10 | 24 | D | 6 DL | 100 | 100 | 100 | 2021-07-17 14:10 | 2021-07-23 07:17 | 461201.9411 |  |  |  | 10738 | 461202 | 204024 |  |  | 0 | 21.57 | 0 | 6.04 | 5852.1
TS5500Shv | MW\39\009\B | MW | 39 | 9 | B | 8 Coal Mining | 17.8 | 0 | 17.8 | 2021-07-17 15:39 | 2021-07-17 21:20 | 6931.9614 | [6 empty] | 6932 | 5129 | 0.51 | 0 | 0 | 9.39 | 5516
TS5500Exc | MW\39\009\B | MW | 39 | 9 | B | 8 Coal Mining | 100 | 0 | 23.4 | 2021-07-17 21:14 | 2021-07-18 04:29 | 9119.2398 | [6 empty] | 9119 | 6748 | 0.68 | 0 | 0 | 9.39 | 5516
TS5500Shv | RS\17\004\B | RS | 17 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-07-17 21:20 | 2021-07-18 13:44 | 19988.2576 | [6 empty] | 19988 | 14281 | 1.42 | 0 | 0 | 9.03 | 5600
PH4100XPC#1 | GG\13\003\X2 | GG | 13 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 7.8412 | 2021-07-17 23:47 | 2021-07-18 02:50 | 6896.1555 | 6896 | [7 empty] | 0 | 0 | 0.71 | 0 | 0
PH4100XPC#1 | GG\13\003\B | GG | 13 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-18 02:50 | 2021-07-19 19:30 | 92083.5947 | 92084 | [7 empty] | 0 | 0 | 9.35 | 10.29 | 5481.05
TS6060#1 | GG\13\004\X1 | GG | 13 | 4 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-07-18 04:29 | 2021-07-18 12:09 | 10371.1956 | [6 empty] | 10371 | 7728 | 0.77 | 0 | 0 | 9.72 | 5401
TS5500Exc | RS\17\006\X | RS | 17 | 6 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-07-18 04:29 | 2021-07-18 17:57 | 16956.855 | [6 empty] | 16957 | 11967 | 1.19 | 0 | 0 | 11.52 | 5266
DRE1 | RS\14\004\D | RS | 14 | 4 | D | 6 DL | 100 | 100 | 100 | 2021-07-18 09:51 | 2021-07-22 01:40 | 306740.1371 |  |  |  | 15771 | 306740 | 247074 |  |  | 0 | 26.28 | 0 | 6.84 | 5819.71
TS6060#1 | GG\10\022\D | GG | 10 | 22 | D | 8 Coal Mining | 22.9 | 0 | 22.9 | 2021-07-18 12:09 | 2021-07-18 21:57 | 13279.3487 | [6 empty] | 13279 | 10015 | 1 | 0 | 0 | 5.96 | 5859
TS5500Shv | GG\13\004\X1 | GG | 13 | 4 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-07-18 13:44 | 2021-07-18 21:23 | 9344.3446 | [6 empty] | 9344 | 6963 | 0.7 | 0 | 0 | 9.72 | 5401
TS5500Exc | RS\17\003\B | RS | 17 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-07-18 17:57 | 2021-07-19 20:31 | 33468.4903 | [6 empty] | 33468 | 23847 | 2.91 | 0 | 0 | 8.71 | 5646
TS5500Shv | GG\13\004\X2 | GG | 13 | 4 | X2 | 1 Prestrip - Thick | 60.1829 | 0 | 44.5912 | 2021-07-18 21:23 | 2021-07-21 03:08 | 57621.4028 | 57621 | [7 empty] | 0 | 0 | 5.82 | 0 | 0
TS6060#1 | RS\17\006\A | RS | 17 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-18 21:57 | 2021-07-26 16:34 | 192545.9564 | 192546 | [7 empty] | 0 | 0 | 19.18 | 18.47 | 4774.93
PH4100XPC#1 | GG\13\004\X2 | GG | 13 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 55.4088 | 2021-07-19 19:30 | 2021-07-21 03:08 | 71600.0262 | 71600 | [7 empty] | 0 | 0 | 7.23 | 0 | 0
TS5500Exc | MW\39\010\B | MW | 39 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-19 20:31 | 2021-07-20 20:53 | 21559.3981 | 21559 | [7 empty] | 0 | 0 | 2.92 | 8.77 | 5603.49
TS5500Exc | MW\39\010\B | MW | 39 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-07-20 20:53 | 2021-07-21 20:00 | 29099.5301 | [6 empty] | 29100 | 21647 | 2.97 | 0 | 0 | 8.77 | 5603
TS Fleet 5 | MW\41\004\D | MW | 41 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-21 00:16 | 2021-07-21 21:07 | 40888.0636 | 40888 | [7 empty] | 0 | 0 | 4.4 | 6.38 | 5852.68
PH4100XPC#1 | GG\13\004\B | GG | 13 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-21 03:08 | 2021-07-23 10:04 | 124330.2931 | 124330 | [7 empty] | 0 | 0 | 12.57 | 11.09 | 5383.04
TS5500Shv | GG\13\003\B | GG | 13 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-07-21 03:08 | 2021-07-22 22:19 | 52658.7151 | [6 empty] | 52659 | 38633 | 3.87 | 0 | 0 | 10.29 | 5481
TS5500Exc | RS\14\003\D | RS | 14 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-07-21 20:00 | 2021-07-24 01:20 | 67187.8308 | [6 empty] | 67188 | 48990 | 4.44 | 0 | 0 | 6.38 | 5860
TS Fleet 5 | MW\41\005\D | MW | 41 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-21 21:07 | 2021-07-23 14:27 | 81019.548 | 81020 | [7 empty] | 0 | 0 | 8.2 | 5.89 | 5894.71
DRE1 | RS\14\005\D | RS | 14 | 5 | D | 6 DL | 100 | 100 | 100 | 2021-07-22 01:40 | 2021-07-25 18:43 | 311033.9609 |  |  |  | 15991 | 311034 | 250533 |  |  | 0 | 26.65 | 0 | 7.09 | 5797.87
TS5500Shv | MW\40\006\B | MW | 40 | 6 | B | 8 Coal Mining | 76.5 | 0 | 76.5 | 2021-07-22 22:19 | 2021-07-23 15:55 | 21452.1573 | [6 empty] | 21452 | 15817 | 1.59 | 0 | 0 | 8.92 | 5578
DRE2 | GG\10\025\D | GG | 10 | 25 | D | 6 DL | 100 | 0 | 100 | 2021-07-23 07:17 | 2021-07-27 18:10 | 359543.609 |  |  |  | 27342 | 359544 | 246075 |  |  | 0 | 40 | 0 | 6.03 | 5856.89
PH4100XPC#1 | GG\13\005\X1 | GG | 13 | 5 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-23 10:04 | 2021-08-05 10:22 | 713074.8766 | 713075 | [7 empty] | 0 | 0 | 63.25 | 10.05 | 5387.53
TS Fleet 5 | MW\41\006\B | MW | 41 | 6 | B | 1 Prestrip - Thick | 81.0846 | 81.0846 | 81.0846 | 2021-07-23 14:27 | 2021-07-27 07:52 | 175254.5319 | 175255 | [7 empty] | 0 | 0 | 17.84 | 9.12 | 5558.68
TS5500Shv | GG\13\004\B | GG | 13 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-07-23 15:55 | 2021-07-25 09:52 | 51157.6851 | [6 empty] | 51158 | 37368 | 3.74 | 0 | 0 | 11.09 | 5383
TS5500Exc | RS\14\004\D | RS | 14 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-07-24 01:20 | 2021-07-26 02:17 | 61661.5819 | [6 empty] | 61662 | 44823 | 4.48 | 0 | 0 | 6.84 | 5820
TS5500Shv | GG\10\024\D | GG | 10 | 24 | D | 8 Coal Mining | 78.9 | 0 | 78.9 | 2021-07-25 09:52 | 2021-07-26 22:57 | 45213.3011 | [6 empty] | 45213 | 34346 | 3.45 | 0 | 0 | 6.04 | 5852
DRE1 | RS\14\006\D | RS | 14 | 6 | D | 6 DL | 100 | 100 | 100 | 2021-07-25 18:43 | 2021-07-29 12:06 | 312259.7747 |  |  |  | 16054 | 312260 | 251520 |  |  | 0 | 26.76 | 0 | 7.6 | 5752.45
TS5500Exc | RS\14\005\D | RS | 14 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-07-26 02:17 | 2021-07-27 03:06 | 31247.1487 | [6 empty] | 31247 | 22731 | 2.27 | 0 | 0 | 7.09 | 5798
TS6060#1 | GG\10\023\D | GG | 10 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-07-26 16:34 | 2021-07-28 03:06 | 46734.502 | [6 empty] | 46735 | 35415 | 3.54 | 0 | 0 | 5.89 | 5853
TS5500Shv | RS\17\006\A | RS | 17 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-07-26 22:57 | 2021-07-27 19:14 | 24742.3057 | [6 empty] | 24742 | 16660 | 1.66 | 0 | 0 | 18.47 | 4775
TS5500Exc | RS\17\006\A | RS | 17 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-07-27 03:06 | 2021-07-27 23:23 | 25557.9861 | [6 empty] | 25558 | 17209 | 1.71 | 0 | 0 | 18.47 | 4775
TS Fleet 5 | MW\41\007\A | MW | 41 | 7 | A | 1 Prestrip - Thick | 74.897 | 74.897 | 74.897 | 2021-07-27 07:52 | 2021-07-31 09:06 | 190572.4608 | 190572 | [7 empty] | 0 | 0 | 19.38 | 12.85 | 5254.62
DRE2 | GG\12\012\B | GG | 12 | 12 | B | 6 DL | 100 | 0 | 100 | 2021-07-27 18:10 | 2021-07-30 03:59 | 194456.6144 |  |  |  |  | 194457 | 162047 |  |  | 0 | 16.75 | 0 | 10.26 | 5496.37
TS5500Shv | GG\10\025\D | GG | 10 | 25 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-07-27 19:14 | 2021-07-28 11:36 | 19942.8465 | [6 empty] | 19943 | 15137 | 2.21 | 0 | 0 | 6.03 | 5857
TS5500Exc | MW\40\010\X | MW | 40 | 10 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-07-27 23:23 | 2021-07-28 03:38 | 5349.4881 | [6 empty] | 5349 | 3899 | 0.51 | 0 | 0 | 12.16 | 5247
TS6060#1 | GG\10\024\D | GG | 10 | 24 | D | 8 Coal Mining | 21.1 | 0 | 21.1 | 2021-07-28 03:06 | 2021-07-28 12:02 | 12081.5568 | [6 empty] | 12082 | 9178 | 0.92 | 0 | 0 | 6.04 | 5852
TS5500Exc | MW\41\006\B | MW | 41 | 6 | B | 1 Prestrip - Thick | 18.9154 | 18.9154 | 18.9154 | 2021-07-28 03:38 | 2021-07-30 01:36 | 40883.4373 | 40883 | [7 empty] | 0 | 0 | 4.16 | 9.12 | 5558.68
TS5500Shv | MW\40\007\A | MW | 40 | 7 | A | 8 Coal Mining | 25 | 0 | 25 | 2021-07-28 11:36 | 2021-07-28 20:29 | 10848.5537 | [6 empty] | 10849 | 7889 | 0.79 | 0 | 0 | 12.69 | 5266
TS6060#1 | GG\10\025\D | GG | 10 | 25 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-07-28 12:02 | 2021-07-29 04:23 | 22134.3681 | [6 empty] | 22134 | 16801 | 2.45 | 0 | 0 | 6.03 | 5857
TS5500Shv | RS\14\005\D | RS | 14 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-07-28 20:29 | 2021-07-29 21:18 | 30249.8993 | [6 empty] | 30250 | 22006 | 2.2 | 0 | 0 | 7.09 | 5798
TS6060#1 | RS\17\006\B | RS | 17 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-29 04:23 | 2021-07-30 05:43 | 26134.6322 | 26135 | [7 empty] | 0 | 0 | 2.6 | 9.19 | 5569.26
DRE1 | RS\14\007\D | RS | 14 | 7 | D | 6 DL | 100 | 100 | 100 | 2021-07-29 12:06 | 2021-08-02 14:01 | 342026.067 |  |  |  | 12679 | 342026 | 193748 |  |  | 0 | 26.89 | 0 | 8.06 | 5710.35
TS5500Shv | RS\14\006\D | RS | 14 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-07-29 21:18 | 2021-07-30 21:58 | 30080.0641 | [6 empty] | 30080 | 21780 | 2.18 | 0 | 0 | 7.6 | 5752
TS5500Exc | RS\14\006\D | RS | 14 | 6 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-07-30 01:36 | 2021-07-31 02:16 | 31071.7146 | [6 empty] | 31072 | 22498 | 2.25 | 0 | 0 | 7.6 | 5752
DRE2 | GG\12\011\B | GG | 12 | 11 | B | 6 DL | 100 | 0 | 100 | 2021-07-30 03:59 | 2021-08-01 13:24 | 193160.5824 |  |  |  |  | 193161 | 148585 |  |  | 0 | 16.87 | 0 | 9.82 | 5525.76
TS6060#1 | GG\12\012\B | GG | 12 | 12 | B | 8 Coal Mining | 38.3 | 0 | 38.3 | 2021-07-30 05:43 | 2021-07-30 19:03 | 18057.8003 | [6 empty] | 18058 | 13236 | 1.33 | 0 | 0 | 10.26 | 5496
PH4100A | RS\17\005\X | RS | 17 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-30 18:35 | 2021-08-11 06:11 | 465562.8997 | 465563 | [7 empty] | 0 | 0 | 46.16 | 12.68 | 5171.2
TS6060#1 | RS\17\007\B | RS | 17 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-30 19:03 | 2021-07-31 14:57 | 20522.712 | 20523 | [7 empty] | 0 | 0 | 2.65 | 9.08 | 5588.63
TS5500Shv | GG\12\012\B | GG | 12 | 12 | B | 8 Coal Mining | 61.7 | 0 | 61.7 | 2021-07-30 21:58 | 2021-07-31 21:48 | 29064.2481 | [6 empty] | 29064 | 21303 | 2.14 | 0 | 0 | 10.26 | 5496
TS5500Exc | RS\18\006\X | RS | 18 | 6 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-07-31 02:16 | 2021-07-31 15:36 | 16802.2409 | [6 empty] | 16802 | 11833 | 1.18 | 0 | 0 | 11.74 | 5247
TS Fleet 5 | MW\41\008\A | MW | 41 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-07-31 09:06 | 2021-08-08 18:35 | 394889.1011 | 394889 | [7 empty] | 0 | 0 | 39.21 | 13.52 | 5210.99
TS6060#1 | RS\19\005\X | RS | 19 | 5 | X | 1 Prestrip - Thick | 99.1883 | 99.1883 | 99.1883 | 2021-07-31 14:57 | 2021-08-21 06:17 | 501373.5836 | 501374 | [7 empty] | 0 | 0 | 49.83 | 12.94 | 5155.65
TS5500Exc | RS\17\006\B | RS | 17 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-07-31 15:36 | 2021-08-01 07:05 | 19489.3996 | [6 empty] | 19489 | 13890 | 1.38 | 0 | 0 | 9.19 | 5569
TS5500Shv | RS\17\006\B | RS | 17 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-07-31 21:48 | 2021-08-01 13:16 | 18867.3975 | [6 empty] | 18867 | 13446 | 1.34 | 0 | 0 | 9.19 | 5569
TS5500Exc | RS\17\007\B | RS | 17 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-08-01 07:05 | 2021-08-02 06:25 | 29406.0516 | [6 empty] | 29406 | 20986 | 2.72 | 0 | 0 | 9.08 | 5589
TS5500Shv | MW\40\008\A | MW | 40 | 8 | A | 8 Coal Mining | 40.5 | 0 | 40.5 | 2021-08-01 13:16 | 2021-08-02 04:55 | 19066.7169 | [6 empty] | 19067 | 13818 | 1.39 | 0 | 0 | 13.45 | 5216
DRE2 | GG\12\010\B | GG | 12 | 10 | B | 6 DL | 100 | 0 | 100 | 2021-08-01 13:24 | 2021-08-04 07:35 | 222623.9034 |  |  |  |  | 222624 | 185520 |  |  | 0 | 17.76 | 0 | 9.59 | 5536.41
TS5500Shv | GG\12\011\B | GG | 12 | 11 | B | 8 Coal Mining | 49.6 | 0 | 49.6 | 2021-08-02 04:55 | 2021-08-03 00:53 | 24363.1269 | [6 empty] | 24363 | 17900 | 1.79 | 0 | 0 | 9.82 | 5526
TS5500Exc | MW\40\007\B | MW | 40 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-08-02 06:25 | 2021-08-04 15:40 | 50627.993 | 50628 | [7 empty] | 0 | 0 | 5.04 | 9.43 | 5502.19
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2021-08-02 14:01 | 2021-08-04 14:01
TS5500Shv | RS\14\007\D | RS | 14 | 7 | D | 7 PostStrip | 100 | 0 | 100 | 2021-08-03 00:53 | 2021-08-04 20:52 | 47148.287 |  |  | 47148 | [5 empty] | 0 | 0 | 0 | 8.06 | 5710.35
DRE2 | GG\12\009\B | GG | 12 | 9 | B | 6 DL | 100 | 0 | 100 | 2021-08-04 07:35 | 2021-08-07 03:59 | 230099.2071 |  |  |  |  | 230099 | 191749 |  |  | 0 | 18.94 | 0 | 9.82 | 5522.31
DRE1 | MW\36\002\D | MW | 36 | 2 | D | 6 DL | 100 | 100 | 100 | 2021-08-04 14:01 | 2021-08-06 15:57 | 174387.4875 |  |  |  | 9953 | 174387 | 132230 |  |  | 0 | 32.63 | 0 | 6.58 | 5833.85
TS5500Exc | MW\40\007\B | MW | 40 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-08-04 15:40 | 2021-08-05 22:55 | 39370.5776 | [6 empty] | 39371 | 29028 | 2.9 | 0 | 0 | 9.43 | 5502
TS5500Shv | GG\12\010\B | GG | 12 | 10 | B | 8 Coal Mining | 50.7 | 0 | 50.7 | 2021-08-04 20:52 | 2021-08-05 17:45 | 25452.5846 | [6 empty] | 25453 | 18736 | 1.88 | 0 | 0 | 9.59 | 5536
PH4100XPC#1 | GG\13\006\X1 | GG | 13 | 6 | X1 | 1 Prestrip - Thick | 100 | 67.8366 | 67.8366 | 2021-08-05 10:22 | 2021-08-12 17:01 | 393962.3812 | 393962 | [7 empty] | 0 | 0 | 38.67 | 10.69 | 5371.03
TS5500Shv | GG\13\005\X1 | GG | 13 | 5 | X1 | 8 Coal Mining | 4.3 | 0 | 4.3 | 2021-08-05 17:45 | 2021-08-05 18:27 | 854.8223 | [6 empty] | 855 | 636 | 0.06 | 0 | 0 | 10.05 | 5388
TS5500Shv | MW\40\010\X | MW | 40 | 10 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-08-05 18:27 | 2021-08-05 22:41 | 5178.7597 | [6 empty] | 5179 | 3775 | 0.49 | 0 | 0 | 12.16 | 5247
TS5500Shv | MW\41\006\B | MW | 41 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-08-05 22:41 | 2021-08-06 09:41 | 13409.1905 | [6 empty] | 13409 | 9879 | 1.02 | 0 | 0 | 9.12 | 5559
TS5500Exc | RS\14\007\D | RS | 14 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-08-05 22:55 | 2021-08-07 20:15 | 57094.5566 | [6 empty] | 57095 | 41229 | 4.39 | 0 | 0 | 8.06 | 5710
TS5500Shv | GG\14\004\X1 | GG | 14 | 4 | X1 | 1 Prestrip - Thick | 1.9068 | 1.9068 | 1.9068 | 2021-08-06 09:41 | 2021-08-07 00:43 | 16115.493 | 16115 | [7 empty] | 0 | 0 | 1.57 | 9.73 | 5391.96
DRE1 | MW\36\003\D | MW | 36 | 3 | D | 6 DL | 100 | 100 | 100 | 2021-08-06 15:57 | 2021-08-12 19:31 | 515490.8642 |  |  |  | 12467 | 515491 | 236864 |  |  | 0 | 24.96 | 0 | 6.66 | 5827.58
TS5500Shv | MW\36\002\D | MW | 36 | 2 | D | 8 Coal Mining | 70.1 | 0 | 70.1 | 2021-08-07 00:43 | 2021-08-07 15:56 | 18558.306 | [6 empty] | 18558 | 13976 | 3.19 | 0 | 0 | 6.58 | 5834
DRE2 | GG\12\008\B | GG | 12 | 8 | B | 6 DL | 100 | 0 | 100 | 2021-08-07 03:59 | 2021-08-10 02:33 | 237360.8022 |  |  |  |  | 237361 | 197801 |  |  | 0 | 19.76 | 0 | 10.38 | 5479.08
TS5500Shv | GG\12\009\B | GG | 12 | 9 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-08-07 15:56 | 2021-08-08 12:13 | 24728.7137 | [6 empty] | 24729 | 18129 | 1.81 | 0 | 0 | 9.82 | 5522
TS5500Exc | MW\36\002\D | MW | 36 | 2 | D | 8 Coal Mining | 29.9 | 0 | 29.9 | 2021-08-07 20:15 | 2021-08-08 02:32 | 7907.7818 | [6 empty] | 7908 | 5955 | 1.36 | 0 | 0 | 6.58 | 5834
TS5500Exc | MW\40\010\A | MW | 40 | 10 | A | 1 Prestrip - Thick | 27.9617 | 27.9617 | 27.9617 | 2021-08-08 02:32 | 2021-08-09 23:27 | 39721.6576 | 39722 | [7 empty] | 0 | 0 | 5.53 | 10.88 | 5426.34
TS5500Shv | GG\14\005\X1 | GG | 14 | 5 | X1 | 1 Prestrip - Thick | 32.0535 | 32.0535 | 32.0535 | 2021-08-08 12:13 | 2021-08-17 12:37 | 231899.8177 | 231900 | [7 empty] | 0 | 0 | 21.28 | 9.97 | 5386.23
TS Fleet 5 | MW\40\008\B | MW | 40 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-08-08 18:35 | 2021-08-09 13:59 | 38039.4917 | 38039 | [7 empty] | 0 | 0 | 3.82 | 10.16 | 5415.62
TS Fleet 5 | MW\40\010\A | MW | 40 | 10 | A | 1 Prestrip - Thick | 74.1748 | 72.0383 | 72.0383 | 2021-08-09 13:59 | 2021-08-11 18:12 | 102335.6249 | 102336 | [7 empty] | 0 | 0 | 14.26 | 10.88 | 5426.34
TS5500Exc | MW\41\006\B | MW | 41 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-08-09 23:27 | 2021-08-10 10:26 | 13851.2518 | [6 empty] | 13851 | 10205 | 1.05 | 0 | 0 | 9.12 | 5559
DRE2 | GG\12\007\B | GG | 12 | 7 | B | 6 DL | 100 | 0 | 100 | 2021-08-10 02:33 | 2021-08-13 06:49 | 256518.2893 |  |  |  |  | 256518 | 197322 |  |  | 0 | 20.11 | 0 | 10.67 | 5418.76
TS5500Exc | MW\41\007\A | MW | 41 | 7 | A | 1 Prestrip - Thick | 25.103 | 25.103 | 25.103 | 2021-08-10 10:26 | 2021-08-13 10:21 | 63873.6602 | 63874 | [7 empty] | 0 | 0 | 6.5 | 12.85 | 5254.62
PH4100A | RS\18\006\A | RS | 18 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-08-11 06:11 | 2021-08-15 19:20 | 189471.0171 | 189471 | [7 empty] | 0 | 0 | 18.92 | 19.22 | 4718.9
TS Fleet 5 | MW\41\009\A | MW | 41 | 9 | A | 1 Prestrip - Thick | 94.5642 | 94.5642 | 94.5642 | 2021-08-11 18:12 | 2021-08-21 22:49 | 479462.4153 | 479462 | [7 empty] | 0 | 0 | 47.48 | 12.34 | 5307.73
PH4100XPC#1 | GG\13\007\X1 | GG | 13 | 7 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-08-12 17:01 | 2021-08-22 16:04 | 535757.3003 | 535757 | [7 empty] | 0 | 0 | 51.46 | 10.76 | 5409.07
DRE1 | MW\36\004\D | MW | 36 | 4 | D | 6 DL | 100 | 100 | 100 | 2021-08-12 19:31 | 2021-08-16 18:24 | 331468.8347 |  |  |  | 17042 | 331469 | 266993 |  |  | 0 | 28.48 | 0 | 6.73 | 5821.51
DRE2 | GG\12\006\B | GG | 12 | 6 | B | 6 DL | 100 | 0 | 100 | 2021-08-13 06:49 | 2021-08-16 06:13 | 240162.6679 |  |  |  |  | 240163 | 200136 |  |  | 0 | 19.94 | 0 | 11.48 | 5317.01
TS5500Exc | RS\17\005\X | RS | 17 | 5 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-08-13 10:21 | 2021-08-13 17:21 | 8822.2898 | [6 empty] | 8822 | 6161 | 0.61 | 0 | 0 | 12.68 | 5171
TS5500Exc | MW\36\003\D | MW | 36 | 3 | D | 8 Coal Mining | 72.3 | 0 | 72.3 | 2021-08-13 17:21 | 2021-08-15 04:26 | 44195.0923 | [6 empty] | 44195 | 33205 | 3.32 | 0 | 0 | 6.66 | 5828
TS5500Exc | MW\40\010\A | MW | 40 | 10 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-08-15 04:26 | 2021-08-16 04:02 | 29716.5896 | [6 empty] | 29717 | 21908 | 3.27 | 0 | 0 | 10.88 | 5426
PH4100A | RS\18\005\X | RS | 18 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-08-15 19:20 | 2021-08-27 20:07 | 488298.1935 | 488298 | [7 empty] | 0 | 0 | 48.56 | 12.85 | 5161.58
TS5500Exc | RS\18\006\A | RS | 18 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-08-16 04:02 | 2021-08-17 00:11 | 25393.3362 | [6 empty] | 25393 | 17019 | 1.7 | 0 | 0 | 19.22 | 4719
DRE2 | GG\12\005\B | GG | 12 | 5 | B | 6 DL | 100 | 0 | 100 | 2021-08-16 06:13 | 2021-08-18 13:00 | 184322.6551 |  |  |  |  | 184323 | 160281 |  |  | 0 | 16 | 0 | 11.98 | 5277.75
DRE1 | MW\36\005\D | MW | 36 | 5 | D | 6 DL | 100 | 100 | 100 | 2021-08-16 18:24 | 2021-08-21 07:42 | 381803.4496 |  |  |  | 21791 | 381803 | 289504 |  |  | 0 | 31.25 | 0 | 6.11 | 5874.91
TS5500Exc | MW\36\004\D | MW | 36 | 4 | D | 8 Coal Mining | 53.2 | 0 | 53.2 | 2021-08-17 00:11 | 2021-08-18 02:13 | 32788.8585 | [6 empty] | 32789 | 24576 | 2.46 | 0 | 0 | 6.73 | 5822
TS5500Shv | RS\17\005\X | RS | 17 | 5 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-08-17 12:37 | 2021-08-17 19:38 | 8540.7274 | [6 empty] | 8541 | 5964 | 0.6 | 0 | 0 | 12.68 | 5171
TS5500Shv | RS\18\006\A | RS | 18 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-08-17 19:38 | 2021-08-18 15:47 | 24582.9105 | [6 empty] | 24583 | 16476 | 1.64 | 0 | 0 | 19.22 | 4719
TS5500Exc | MW\40\010\B | MW | 40 | 10 | B | 1 Prestrip - Thick | 72.2565 | 72.2565 | 72.2565 | 2021-08-18 02:13 | 2021-08-18 17:53 | 13845.9952 | 13846 | [7 empty] | 0 | 0 | 2.12 | 8.8 | 5600.72
DRE2 | GG\11\012\D | GG | 11 | 12 | D | 6 DL | 100 | 100 | 100 | 2021-08-18 13:00 | 2021-08-24 18:08 | 501602.5872 |  |  |  | 11679 | 501603 | 221896 |  |  | 0 | 23.37 | 0 | 6.3 | 5834.92
TS5500Shv | GG\12\008\B | GG | 12 | 8 | B | 8 Coal Mining | 36.8 | 0 | 36.8 | 2021-08-18 15:47 | 2021-08-19 07:54 | 19640.7759 | [6 empty] | 19641 | 14318 | 1.43 | 0 | 0 | 10.38 | 5479
TS5500Exc | MW\41\007\A | MW | 41 | 7 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-08-18 17:53 | 2021-08-19 10:01 | 20329.4322 | [6 empty] | 20329 | 14768 | 1.49 | 0 | 0 | 12.85 | 5255
TS5500Shv | GG\12\007\B | GG | 12 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-08-19 07:54 | 2021-08-21 02:20 | 51758.6534 | [6 empty] | 51759 | 37774 | 3.78 | 0 | 0 | 10.67 | 5419
TS5500Exc | MW\41\008\A | MW | 41 | 8 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-08-19 10:01 | 2021-08-20 23:32 | 47267.9646 | [6 empty] | 47268 | 34246 | 3.41 | 0 | 0 | 13.52 | 5211
TS5500Exc | MW\41\008\B | MW | 41 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-08-20 23:32 | 2021-08-22 17:48 | 37372.3215 | 37372 | [7 empty] | 0 | 0 | 3.74 | 10.14 | 5420.69
TS5500Shv | GG\12\006\B | GG | 12 | 6 | B | 8 Coal Mining | 57.9 | 0 | 57.9 | 2021-08-21 02:20 | 2021-08-22 02:33 | 29521.2216 | [6 empty] | 29521 | 21495 | 2.15 | 0 | 0 | 11.48 | 5317
TS6060#1 | GG\13\005\X1 | GG | 13 | 5 | X1 | 8 Coal Mining | 95.7 | 0 | 95.7 | 2021-08-21 06:17 | 2021-08-21 20:29 | 19209.1761 | [6 empty] | 19209 | 14290 | 1.38 | 0 | 0 | 10.05 | 5388
DRE1 | MW\36\006\D | MW | 36 | 6 | D | 6 DL | 100 | 100 | 100 | 2021-08-21 07:42 | 2021-08-25 11:46 | 349511.1903 |  |  |  | 17970 | 349511 | 281526 |  |  | 0 | 29.98 | 0 | 5.69 | 5910.74
TS6060#1 | GG\13\006\X1 | GG | 13 | 6 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2021-08-21 20:29 | 2021-08-22 08:52 | 16767.8243 | [6 empty] | 16768 | 12422 | 1.23 | 0 | 0 | 10.69 | 5371
TS Fleet 5 | MW\40\010\B | MW | 40 | 10 | B | 1 Prestrip - Thick | 27.7435 | 27.7435 | 27.7435 | 2021-08-21 22:49 | 2021-08-22 01:32 | 5316.2987 | 5316 | [7 empty] | 0 | 0 | 0.81 | 8.8 | 5600.72
TS Fleet 5 | MW\41\010\A | MW | 41 | 10 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-08-22 01:32 | 2021-08-30 10:02 | 392992.208 | 392992 | [7 empty] | 0 | 0 | 60.24 | 11.25 | 5397.43
TS5500Shv | MW\36\003\D | MW | 36 | 3 | D | 8 Coal Mining | 27.7 | 0 | 27.7 | 2021-08-22 02:33 | 2021-08-22 16:26 | 16928.2419 | [6 empty] | 16928 | 12719 | 1.27 | 0 | 0 | 6.66 | 5828
TS6060#1 | RS\17\005\A | RS | 17 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-08-22 08:52 | 2021-08-30 02:09 | 191179.2346 | 191179 | [7 empty] | 0 | 0 | 19.07 | 18.59 | 4781.98
PH4100XPC#1 | GG\13\005\X2 | GG | 13 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2021-08-22 16:04 | 2021-08-24 17:55 | 112814.782 | 112815 | [7 empty] | 0 | 0 | 11.04 | 0 | 0
TS5500Shv | GG\13\006\X2 | GG | 13 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 69.3673 | 2021-08-22 16:26 | 2021-08-25 09:09 | 69387.2087 | 69387 | [7 empty] | 0 | 0 | 6.84 | 0 | 0
TS5500Exc | MW\36\005\D | MW | 36 | 5 | D | 8 Coal Mining | 96.6 | 0 | 96.6 | 2021-08-22 17:48 | 2021-08-24 15:55 | 58092.1142 | [6 empty] | 58092 | 43784 | 4.38 | 0 | 0 | 6.11 | 5875
TS5500Exc | MW\40\010\B | MW | 40 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-08-24 15:55 | 2021-08-25 11:20 | 24462.0154 | [6 empty] | 24462 | 18205 | 2.84 | 0 | 0 | 8.8 | 5601
PH4100XPC#1 | GG\13\005\B | GG | 13 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-08-24 17:55 | 2021-08-24 19:37 | 3872.1673 | 3872 | [7 empty] | 0 | 0 | 0.39 | 11.96 | 5283.95
DRE2 | GG\11\011\D | GG | 11 | 11 | D | 6 DL | 100 | 100 | 100 | 2021-08-24 18:08 | 2021-08-31 02:12 | 511534.6185 |  |  |  | 9284 | 511535 | 222809 |  |  | 0 | 23.21 | 0 | 6.06 | 5856.47
PH4100XPC#1 | GG\13\006\X2 | GG | 13 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 30.6327 | 2021-08-24 19:37 | 2021-08-25 09:09 | 30641.5053 | 30642 | [7 empty] | 0 | 0 | 3.02 | 0 | 0
PH4100XPC#1 | GG\13\006\B | GG | 13 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-08-25 09:09 | 2021-08-25 19:34 | 23549.5356 | 23550 | [7 empty] | 0 | 0 | 2.35 | 11.13 | 5348.89
TS5500Shv | GG\12\005\B | GG | 12 | 5 | B | 8 Coal Mining | 93.2 | 0 | 93.2 | 2021-08-25 09:09 | 2021-08-27 00:14 | 47647.5629 | [6 empty] | 47648 | 34643 | 3.46 | 0 | 0 | 11.98 | 5278
TS5500Exc | MW\41\008\B | MW | 41 | 8 | B | 8 Coal Mining | 66.3 | 0 | 66.3 | 2021-08-25 11:20 | 2021-08-26 07:13 | 25039.4316 | [6 empty] | 25039 | 18429 | 1.84 | 0 | 0 | 10.14 | 5421
DRE1 | MW\36\007\D | MW | 36 | 7 | D | 6 DL | 100 | 100 | 100 | 2021-08-25 11:46 | 2021-08-29 15:25 | 348112.8164 |  |  |  | 17898 | 348113 | 280399 |  |  | 0 | 29.84 | 0 | 5.63 | 5916.68
PH4100XPC#1 | GG\13\008\X1 | GG | 13 | 8 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-08-25 19:34 | 2021-09-03 10:41 | 462911.856 | 462912 | [7 empty] | 0 | 0 | 45.39 | 10.27 | 5477.74
TS5500Exc | MW\36\006\D | MW | 36 | 6 | D | 8 Coal Mining | 69.9 | 0 | 69.9 | 2021-08-26 07:13 | 2021-08-27 15:23 | 40507.1018 | [6 empty] | 40507 | 30651 | 3.07 | 0 | 0 | 5.69 | 5911
TS5500Shv | MW\40\008\B | MW | 40 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-08-27 00:14 | 2021-08-28 07:26 | 38039.3262 | [6 empty] | 38039 | 27999 | 2.8 | 0 | 0 | 10.16 | 5416
TS5500Exc | MW\41\009\A | MW | 41 | 9 | A | 1 Prestrip - Thick | 5.4358 | 5.4358 | 5.4358 | 2021-08-27 15:23 | 2021-08-28 22:26 | 27560.6169 | 27561 | [7 empty] | 0 | 0 | 2.73 | 12.34 | 5307.73
PH4100A | RS\18\004\X | RS | 18 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-08-27 20:07 | 2021-09-07 03:26 | 414534.8598 | 414535 | [7 empty] | 0 | 0 | 41.21 | 12.78 | 5148.77
TS5500Shv | RS\18\005\X | RS | 18 | 5 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-08-28 07:26 | 2021-08-28 14:20 | 8430.1709 | [6 empty] | 8430 | 5875 | 0.59 | 0 | 0 | 12.85 | 5162
TS5500Shv | MW\36\004\D | MW | 36 | 4 | D | 8 Coal Mining | 46.8 | 0 | 46.8 | 2021-08-28 14:20 | 2021-08-29 13:58 | 28812.5082 | [6 empty] | 28813 | 21596 | 2.16 | 0 | 0 | 6.73 | 5822
TS5500Exc | RS\18\005\X | RS | 18 | 5 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-08-28 22:26 | 2021-08-29 05:21 | 8708.0886 | [6 empty] | 8708 | 6068 | 0.6 | 0 | 0 | 12.85 | 5162
TS5500Exc | MW\41\009\A | MW | 41 | 9 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-08-29 05:21 | 2021-08-30 17:44 | 45836.8624 | [6 empty] | 45837 | 33468 | 3.33 | 0 | 0 | 12.34 | 5308
TS5500Shv | MW\36\005\D | MW | 36 | 5 | D | 8 Coal Mining | 3.4 | 0 | 3.4 | 2021-08-29 13:58 | 2021-08-29 15:38 | 2031.3539 | [6 empty] | 2031 | 1531 | 0.15 | 0 | 0 | 6.11 | 5875
DRE1 | MW\36\008\D | MW | 36 | 8 | D | 6 DL | 100 | 100 | 100 | 2021-08-29 15:25 | 2021-09-02 18:40 | 346667.7739 |  |  |  | 17824 | 346668 | 279235 |  |  | 0 | 29.73 | 0 | 5.62 | 5918.62
TS5500Shv | GG\11\012\D | GG | 11 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-08-29 15:38 | 2021-08-31 20:28 | 64416.0355 | [6 empty] | 64416 | 48273 | 4.83 | 0 | 0 | 6.3 | 5835
TS6060#1 | GG\13\007\X1 | GG | 13 | 7 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2021-08-30 02:09 | 2021-08-30 14:20 | 16482.3278 | [6 empty] | 16482 | 12189 | 1.2 | 0 | 0 | 10.76 | 5409
TS Fleet 5 | MW\42\003\B | MW | 42 | 3 | B | 1 Prestrip - Thick | 93.3261 | 93.3261 | 93.3261 | 2021-08-30 10:02 | 2021-09-02 13:36 | 148090.3809 | 148090 | [7 empty] | 0 | 0 | 15.15 | 12.72 | 5246.55
TS6060#1 | GG\12\011\B | GG | 12 | 11 | B | 8 Coal Mining | 50.4 | 0 | 50.4 | 2021-08-30 14:20 | 2021-08-31 08:38 | 24765.3813 | [6 empty] | 24765 | 18196 | 1.82 | 0 | 0 | 9.82 | 5526
TS5500Exc | RS\17\005\A | RS | 17 | 5 | A | 8 Coal Mining | 64.2 | 0 | 64.2 | 2021-08-30 17:44 | 2021-08-31 19:29 | 32427.4899 | [6 empty] | 32427 | 21820 | 2.17 | 0 | 0 | 18.59 | 4782
DRE2 | GG\11\010\D | GG | 11 | 10 | D | 6 DL | 100 | 100 | 100 | 2021-08-31 02:12 | 2021-09-06 01:46 | 482947.4336 |  |  |  | 11244 | 482947 | 213644 |  |  | 0 | 22.51 | 0 | 6.11 | 5851.93
TS6060#1 | GG\12\010\B | GG | 12 | 10 | B | 8 Coal Mining | 49.3 | 0 | 49.3 | 2021-08-31 08:38 | 2021-09-01 02:54 | 24725.0819 | [6 empty] | 24725 | 18200 | 1.82 | 0 | 0 | 9.59 | 5536
TS5500Exc | MW\36\007\D | MW | 36 | 7 | D | 8 Coal Mining | 47.3 | 0 | 47.3 | 2021-08-31 19:29 | 2021-09-01 17:43 | 28012.3256 | [6 empty] | 28012 | 21215 | 2.12 | 0 | 0 | 5.63 | 5917
TS5500Shv | GG\13\007\X2 | GG | 13 | 7 | X2 | 1 Prestrip - Thick | 95.6407 | 0 | 77.7914 | 2021-08-31 20:28 | 2021-09-03 20:25 | 77132.6557 | 77133 | [7 empty] | 0 | 0 | 7.61 | 0 | 0
TS6060#1 | RS\18\005\A | RS | 18 | 5 | A | 1 Prestrip - Thick | 59.7186 | 59.7186 | 59.7186 | 2021-09-01 02:54 | 2021-09-05 16:51 | 113442.2875 | 113442 | [7 empty] | 0 | 0 | 11.3 | 19.79 | 4682.76
TS5500Exc | MW\41\009\B | MW | 41 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-01 17:43 | 2021-09-03 06:46 | 32769.7154 | 32770 | [7 empty] | 0 | 0 | 3.27 | 9.47 | 5509.31
TS Fleet 5 | MW\42\004\D | MW | 42 | 4 | D | 1 Prestrip - Thick | 68.0474 | 68.0474 | 68.0474 | 2021-09-02 13:36 | 2021-09-02 20:20 | 13190.6745 | 13191 | [7 empty] | 0 | 0 | 1.53 | 6.4 | 5850.39
DRE1 | MW\36\009\D | MW | 36 | 9 | D | 6 DL | 100 | 100 | 100 | 2021-09-02 18:40 | 2021-09-06 17:44 | 332064.82 |  |  |  | 17073 | 332065 | 267473 |  |  | 0 | 28.47 | 0 | 5.42 | 5935.91
TS Fleet 5 | MW\42\005\B | MW | 42 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-02 20:20 | 2021-09-08 01:21 | 245055.9412 | 245056 | [7 empty] | 0 | 0 | 16.66 | 11.84 | 5332.21
TS5500Exc | MW\36\008\D | MW | 36 | 8 | D | 8 Coal Mining | 37.2 | 0 | 37.2 | 2021-09-03 06:46 | 2021-09-04 01:03 | 23016.183 | [6 empty] | 23016 | 17432 | 1.74 | 0 | 0 | 5.62 | 5919
PH4100XPC#1 | GG\13\007\X2 | GG | 13 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 22.2086 | 2021-09-03 10:41 | 2021-09-03 20:25 | 22020.4903 | 22020 | [7 empty] | 0 | 0 | 2.17 | 0 | 0
TS5500Shv | GG\13\008\X1 | GG | 13 | 8 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-09-03 20:25 | 2021-09-04 02:50 | 7838.0467 | [6 empty] | 7838 | 5811 | 0.58 | 0 | 0 | 10.27 | 5478
PH4100XPC#1 | GG\13\007\B | GG | 13 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-03 20:25 | 2021-09-04 18:15 | 49441.2643 | 49441 | [7 empty] | 0 | 0 | 5.02 | 10.52 | 5432.58
TS5500Exc | MW\41\009\B | MW | 41 | 9 | B | 8 Coal Mining | 96.3 | 0 | 96.3 | 2021-09-04 01:03 | 2021-09-05 05:24 | 35723.8974 | [6 empty] | 35724 | 26424 | 2.64 | 0 | 0 | 9.47 | 5509
TS5500Shv | RS\17\005\A | RS | 17 | 5 | A | 8 Coal Mining | 35.8 | 0 | 35.8 | 2021-09-04 02:50 | 2021-09-04 17:41 | 18092.0347 | [6 empty] | 18092 | 12174 | 1.21 | 0 | 0 | 18.59 | 4782
TS5500Shv | MW\36\006\D | MW | 36 | 6 | D | 8 Coal Mining | 30.1 | 0 | 30.1 | 2021-09-04 17:41 | 2021-09-05 07:57 | 17402.9572 | [6 empty] | 17403 | 13168 | 1.32 | 0 | 0 | 5.69 | 5911
PH4100XPC#1 | GG\13\009\X1 | GG | 13 | 9 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-04 18:15 | 2021-09-12 21:49 | 438214.1946 | 438214 | [7 empty] | 0 | 0 | 42.82 | 11.24 | 5403.47
TS5500Exc | MW\41\010\A | MW | 41 | 10 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-09-05 05:24 | 2021-09-05 15:36 | 12831.1886 | [6 empty] | 12831 | 9434 | 1.66 | 0 | 0 | 11.25 | 5397
TS5500Shv | GG\11\011\D | GG | 11 | 11 | D | 8 Coal Mining | 73.7 | 0 | 73.7 | 2021-09-05 07:57 | 2021-09-06 22:52 | 47448.3441 | [6 empty] | 47448 | 35586 | 3.56 | 0 | 0 | 6.06 | 5856
TS5500Exc | MW\42\003\B | MW | 42 | 3 | B | 1 Prestrip - Thick | 6.6739 | 6.6739 | 6.6739 | 2021-09-05 15:36 | 2021-09-06 03:34 | 10590.1937 | 10590 | [7 empty] | 0 | 0 | 1.08 | 12.72 | 5246.55
TS6060#1 | GG\13\008\X1 | GG | 13 | 8 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-09-05 16:51 | 2021-09-05 23:16 | 8699.3706 | [6 empty] | 8699 | 6449 | 0.64 | 0 | 0 | 10.27 | 5478
TS6060#1 | RS\17\005\B | RS | 17 | 5 | B | 1 Prestrip - Thick | 57.5179 | 57.5179 | 57.5179 | 2021-09-05 23:16 | 2021-09-06 14:46 | 15987.3173 | 15987 | [7 empty] | 0 | 0 | 1.59 | 9.27 | 5561.7
DRE2 | GG\11\009\D | GG | 11 | 9 | D | 6 DL | 100 | 100 | 100 | 2021-09-06 01:46 | 2021-09-11 17:58 | 458095.1056 |  |  |  | 10666 | 458095 | 202650 |  |  | 0 | 21.35 | 0 | 6.38 | 5827.3
TS5500Exc | MW\42\004\D | MW | 42 | 4 | D | 1 Prestrip - Thick | 31.9526 | 31.9526 | 31.9526 | 2021-09-06 03:34 | 2021-09-06 10:34 | 6193.8585 | 6194 | [7 empty] | 0 | 0 | 0.72 | 6.4 | 5850.39
TS5500Exc | MW\42\006\B | MW | 42 | 6 | B | 1 Prestrip - Thick | 19.3352 | 19.3352 | 19.3352 | 2021-09-06 10:34 | 2021-09-08 14:40 | 46312.1405 | 46312 | [7 empty] | 0 | 0 | 4.42 | 9.67 | 5509.49
TS6060#1 | GG\12\008\B | GG | 12 | 8 | B | 8 Coal Mining | 63.2 | 0 | 63.2 | 2021-09-06 14:46 | 2021-09-07 15:41 | 33710.1917 | [6 empty] | 33710 | 24574 | 2.45 | 0 | 0 | 10.38 | 5479
DRE1 | MW\36\010\D | MW | 36 | 10 | D | 6 DL | 100 | 100 | 100 | 2021-09-06 17:44 | 2021-09-10 10:58 | 311733.3497 |  |  |  | 11383 | 311733 | 175973 |  |  | 0 | 28.24 | 0 | 5.2 | 5954.45
TS5500Shv | GG\13\008\X2 | GG | 13 | 8 | X2 | 1 Prestrip - Thick | 6.811 | 0 | 6.811 | 2021-09-06 22:52 | 2021-09-07 04:57 | 6532.36 | 6532 | [7 empty] | 0 | 0 | 0.65 | 0 | 0
PH4100A | RS\17\005\B | RS | 17 | 5 | B | 1 Prestrip - Thick | 100 | 42.4821 | 42.4821 | 2021-09-07 03:26 | 2021-09-07 10:14 | 11808.0373 | 11808 | [7 empty] | 0 | 0 | 1.18 | 9.27 | 5561.7
TS5500Shv | RS\18\004\X | RS | 18 | 4 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-09-07 04:57 | 2021-09-07 10:45 | 7077.3536 | [6 empty] | 7077 | 4941 | 0.49 | 0 | 0 | 12.78 | 5149
PH4100A | RS\18\003\X | RS | 18 | 3 | X | 1 Prestrip - Thick | 100 | 74.8602 | 74.8602 | 2021-09-07 10:14 | 2021-09-11 00:43 | 143130.8873 | 143131 | [7 empty] | 0 | 0 | 23.12 | 12.72 | 5145.27
TS5500Shv | RS\17\005\B | RS | 17 | 5 | B | 8 Coal Mining | 17.4 | 0 | 17.4 | 2021-09-07 10:45 | 2021-09-07 16:18 | 6763.3938 | [6 empty] | 6763 | 4827 | 0.48 | 0 | 0 | 9.27 | 5562
TS6060#1 | GG\12\009\B | GG | 12 | 9 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-09-07 15:41 | 2021-09-08 11:57 | 27446.1548 | [6 empty] | 27446 | 20121 | 2.01 | 0 | 0 | 9.82 | 5522
TS5500Shv | MW\36\007\D | MW | 36 | 7 | D | 8 Coal Mining | 52.7 | 0 | 52.7 | 2021-09-07 16:18 | 2021-09-08 17:57 | 31269.3484 | [6 empty] | 31269 | 23681 | 2.37 | 0 | 0 | 5.63 | 5917
TS Fleet 5 | MW\42\006\B | MW | 42 | 6 | B | 1 Prestrip - Thick | 80.6648 | 80.6648 | 80.6648 | 2021-09-08 01:21 | 2021-09-12 03:56 | 193210.2294 | 193210 | [7 empty] | 0 | 0 | 18.45 | 9.67 | 5509.49
TS6060#1 | GG\12\006\B | GG | 12 | 6 | B | 8 Coal Mining | 42.1 | 0 | 42.1 | 2021-09-08 11:57 | 2021-09-09 03:48 | 21433.9215 | [6 empty] | 21434 | 15606 | 1.56 | 0 | 0 | 11.48 | 5317
TS5500Exc | RS\17\005\B | RS | 17 | 5 | B | 8 Coal Mining | 82.6 | 0 | 82.6 | 2021-09-08 14:40 | 2021-09-09 16:12 | 32152.6698 | [6 empty] | 32153 | 22949 | 2.28 | 0 | 0 | 9.27 | 5562
TS5500Shv | GG\11\010\D | GG | 11 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-09-08 17:57 | 2021-09-10 23:03 | 64746.4956 | [6 empty] | 64746 | 48482 | 4.85 | 0 | 0 | 6.11 | 5852
TS6060#1 | GG\12\005\B | GG | 12 | 5 | B | 8 Coal Mining | 6.8 | 0 | 6.8 | 2021-09-09 03:48 | 2021-09-09 06:23 | 3495.4329 | [6 empty] | 3495 | 2541 | 0.25 | 0 | 0 | 11.98 | 5278
TS6060#1 | GG\11\011\D | GG | 11 | 11 | D | 8 Coal Mining | 26.3 | 0 | 26.3 | 2021-09-09 06:23 | 2021-09-09 18:55 | 16972.6582 | [6 empty] | 16973 | 12729 | 1.27 | 0 | 0 | 6.06 | 5856
TS5500Exc | RS\18\004\X | RS | 18 | 4 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-09-09 16:12 | 2021-09-09 22:00 | 7310.6729 | [6 empty] | 7311 | 5104 | 0.51 | 0 | 0 | 12.78 | 5149
TS6060#1 | RS\19\006\X | RS | 19 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-09 18:55 | 2021-10-02 17:12 | 558334.977 | 558335 | [7 empty] | 0 | 0 | 55.71 | 11.9 | 5232.79
TS5500Exc | MW\36\009\D | MW | 36 | 9 | D | 8 Coal Mining | 41.3 | 0 | 41.3 | 2021-09-09 22:00 | 2021-09-10 17:44 | 24850.5607 | [6 empty] | 24851 | 18881 | 1.89 | 0 | 0 | 5.42 | 5936
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2021-09-10 10:58 | 2021-09-12 10:58
TS5500Exc | MW\36\010\D | MW | 36 | 10 | D | 7 PostStrip | 38.1412 | 0 | 38.1412 | 2021-09-10 17:44 | 2021-09-11 11:07 | 15371.5576 |  |  | 15372 | [5 empty] | 0 | 0 | 0 | 5.2 | 5954.45
TS5500Shv | MW\36\008\D | MW | 36 | 8 | D | 8 Coal Mining | 62.8 | 0 | 62.8 | 2021-09-10 23:03 | 2021-09-12 06:54 | 38850.4482 | [6 empty] | 38850 | 29425 | 2.94 | 0 | 0 | 5.62 | 5919
PH4100A | RS\18\007\A | RS | 18 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-11 00:43 | 2021-09-14 04:14 | 131092.027 | 131092 | [7 empty] | 0 | 0 | 19.02 | 17.37 | 4864.77
TS5500Exc | RS\18\003\X | RS | 18 | 3 | X | 8 Coal Mining | 74.4 | 0 | 74.4 | 2021-09-11 11:07 | 2021-09-11 17:16 | 7756.7748 | [6 empty] | 7757 | 5424 | 0.83 | 0 | 0 | 12.72 | 5145
TS5500Exc | MW\42\008\A | MW | 42 | 8 | A | 1 Prestrip - Thick | 0.53714 | 0.53714 | 0.53714 | 2021-09-11 17:16 | 2021-09-11 19:36 | 2061.5157 | 2062 | [7 empty] | 0 | 0 | 0.21 | 13.55 | 5208.73
DRE2 | GG\11\008\D | GG | 11 | 8 | D | 6 DL | 100 | 100 | 100 | 2021-09-11 17:58 | 2021-09-17 04:56 | 440535.4586 |  |  |  | 10257 | 440535 | 194882 |  |  | 0 | 20.54 | 0 | 6.64 | 5803.51
TS5500Exc | MW\42\009\A | MW | 42 | 9 | A | 1 Prestrip - Thick | 18.1914 | 18.1914 | 18.1914 | 2021-09-11 19:36 | 2021-09-18 08:08 | 138893.3582 | 138893 | [7 empty] | 0 | 0 | 9.58 | 12.19 | 5320.96
TS Fleet 5 | MW\42\007\A | MW | 42 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-12 03:56 | 2021-09-17 09:03 | 245229.9839 | 245230 | [7 empty] | 0 | 0 | 24.72 | 12.81 | 5259.05
TS5500Shv | RS\18\003\X | RS | 18 | 3 | X | 8 Coal Mining | 25.6 | 0 | 25.6 | 2021-09-12 06:54 | 2021-09-12 09:06 | 2671.8963 | [6 empty] | 2672 | 1868 | 0.29 | 0 | 0 | 12.72 | 5145
TS5500Shv | MW\36\009\D | MW | 36 | 9 | D | 8 Coal Mining | 58.7 | 0 | 58.7 | 2021-09-12 09:06 | 2021-09-13 14:02 | 35280.6026 | [6 empty] | 35281 | 26806 | 2.68 | 0 | 0 | 5.42 | 5936
DRE1 | RS\15\003\D | RS | 15 | 3 | D | 6 DL | 100 | 100 | 100 | 2021-09-12 10:58 | 2021-09-16 14:26 | 347423.1546 |  |  |  | 17862 | 347423 | 279844 |  |  | 0 | 26.96 | 0 | 6.38 | 5859.77
PH4100XPC#1 | GG\13\008\X2 | GG | 13 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 93.189 | 2021-09-12 21:49 | 2021-09-14 13:19 | 89376.14 | 89376 | [7 empty] | 0 | 0 | 8.92 | 0 | 0
TS5500Shv | GG\13\009\X1 | GG | 13 | 9 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-09-13 14:02 | 2021-09-13 20:28 | 7852.2979 | [6 empty] | 7852 | 5775 | 0.58 | 0 | 0 | 11.24 | 5403
TS5500Shv | MW\41\007\A | MW | 41 | 7 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-09-13 20:28 | 2021-09-14 12:36 | 19680.6205 | [6 empty] | 19681 | 14297 | 1.44 | 0 | 0 | 12.85 | 5255
PH4100A | RS\18\006\B | RS | 18 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-14 04:14 | 2021-09-14 19:17 | 26148.9641 | 26149 | [7 empty] | 0 | 0 | 2.61 | 9.18 | 5569.92
TS5500Shv | GG\11\009\D | GG | 11 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-09-14 12:36 | 2021-09-16 16:53 | 63743.8178 | [6 empty] | 63744 | 47655 | 4.77 | 0 | 0 | 6.38 | 5827
PH4100XPC#1 | GG\13\008\B | GG | 13 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-14 13:19 | 2021-09-15 15:03 | 58263.781 | 58264 | [7 empty] | 0 | 0 | 5.83 | 10.37 | 5481.45
PH4100A | RS\18\005\A | RS | 18 | 5 | A | 1 Prestrip - Thick | 100 | 40.2814 | 40.2814 | 2021-09-14 19:17 | 2021-09-16 15:22 | 76518.954 | 76519 | [7 empty] | 0 | 0 | 7.63 | 19.79 | 4682.76
PH4100XPC#1 | GG\13\010\B | GG | 13 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-15 15:03 | 2021-09-26 06:15 | 586555.7843 | 586556 | [7 empty] | 0 | 0 | 54.5 | 9.34 | 5557.32
DRE1 | RS\15\004\D | RS | 15 | 4 | D | 6 DL | 100 | 100 | 100 | 2021-09-16 14:26 | 2021-09-20 08:12 | 313575.6007 |  |  |  | 16122 | 313576 | 252580 |  |  | 0 | 26.86 | 0 | 6.81 | 5822.03
PH4100A | RS\18\004\A | RS | 18 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-16 15:22 | 2021-09-21 14:25 | 206664.9942 | 206665 | [7 empty] | 0 | 0 | 20.6 | 16.97 | 4935.33
TS5500Shv | RS\18\005\A | RS | 18 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-09-16 16:53 | 2021-09-17 13:02 | 24561.7983 | [6 empty] | 24562 | 16383 | 1.63 | 0 | 0 | 19.79 | 4683
DRE2 | GG\11\007\D | GG | 11 | 7 | D | 6 DL | 100 | 100 | 100 | 2021-09-17 04:56 | 2021-09-22 12:50 | 430265.6494 |  |  |  | 10018 | 430266 | 190339 |  |  | 0 | 20.05 | 0 | 6.53 | 5814.22
TS Fleet 5 | MW\42\008\A | MW | 42 | 8 | A | 1 Prestrip - Thick | 99.4629 | 99.4629 | 99.4629 | 2021-09-17 09:03 | 2021-09-25 11:49 | 381734.2768 | 381734 | [7 empty] | 0 | 0 | 38.27 | 13.55 | 5208.73
TS5500Shv | MW\36\010\D | MW | 36 | 10 | D | 7 PostStrip | 61.8588 | 0 | 61.8588 | 2021-09-17 13:02 | 2021-09-18 12:17 | 24930.1041 |  |  | 24930 | [5 empty] | 0 | 0 | 0 | 5.2 | 5954.45
TS5500Exc | RS\18\005\A | RS | 18 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-09-18 08:08 | 2021-09-19 04:16 | 25371.5279 | [6 empty] | 25372 | 16923 | 1.69 | 0 | 0 | 19.79 | 4683
TS5500Shv | MW\36\010\D | MW | 36 | 10 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-09-18 12:17 | 2021-09-19 07:00 | 22832.3373 | [6 empty] | 22832 | 17418 | 2.2 | 0 | 0 | 5.2 | 5954
TS5500Exc | RS\18\006\B | RS | 18 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-09-19 04:16 | 2021-09-20 10:15 | 37775.3724 | [6 empty] | 37775 | 26938 | 2.69 | 0 | 0 | 9.18 | 5570
TS5500Shv | GG\11\008\D | GG | 11 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-09-19 07:00 | 2021-09-21 10:39 | 62967.3515 | [6 empty] | 62967 | 46962 | 4.7 | 0 | 0 | 6.64 | 5804
DRE1 | RS\15\005\D | RS | 15 | 5 | D | 6 DL | 100 | 100 | 100 | 2021-09-20 08:12 | 2021-09-24 01:37 | 312380.4596 |  |  |  | 16061 | 312380 | 251618 |  |  | 0 | 26.77 | 0 | 7.09 | 5797.96
TS5500Exc | RS\18\007\A | RS | 18 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-09-20 10:15 | 2021-09-21 12:43 | 33323.9303 | [6 empty] | 33324 | 22724 | 3.36 | 0 | 0 | 17.37 | 4865
TS5500Shv | RS\15\003\D | RS | 15 | 3 | D | 8 Coal Mining | 35.9 | 0 | 35.9 | 2021-09-21 10:39 | 2021-09-22 06:26 | 24132.9747 | [6 empty] | 24133 | 17569 | 1.58 | 0 | 0 | 6.38 | 5860
TS5500Exc | MW\36\010\D | MW | 36 | 10 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-09-21 12:43 | 2021-09-22 07:26 | 23585.0517 | [6 empty] | 23585 | 17992 | 2.28 | 0 | 0 | 5.2 | 5954
PH4100A | RS\18\005\B | RS | 18 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-21 14:25 | 2021-09-22 05:21 | 25931.2573 | 25931 | [7 empty] | 0 | 0 | 2.58 | 9.28 | 5557.72
PH4100A | RS\18\007\B | RS | 18 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-22 05:21 | 2021-09-22 15:48 | 18123.5232 | 18124 | [7 empty] | 0 | 0 | 2.69 | 9.07 | 5588.15
TS5500Shv | RS\18\004\A | RS | 18 | 4 | A | 8 Coal Mining | 70.9 | 0 | 70.9 | 2021-09-22 06:26 | 2021-09-23 05:42 | 28364.1787 | [6 empty] | 28364 | 19309 | 1.92 | 0 | 0 | 16.97 | 4935
TS5500Exc | RS\18\004\A | RS | 18 | 4 | A | 8 Coal Mining | 29.1 | 0 | 29.1 | 2021-09-22 07:26 | 2021-09-22 16:42 | 11664.9415 | [6 empty] | 11665 | 7941 | 0.79 | 0 | 0 | 16.97 | 4935
DRE2 | GG\11\006\D | GG | 11 | 6 | D | 6 DL | 100 | 100 | 100 | 2021-09-22 12:50 | 2021-09-27 22:01 | 434515.5891 |  |  |  | 10117 | 434516 | 192219 |  |  | 0 | 20.25 | 0 | 6.46 | 5820.27
PH4100A | RS\18\003\A | RS | 18 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-22 15:48 | 2021-09-26 05:29 | 148759.6319 | 148760 | [7 empty] | 0 | 0 | 20.78 | 13.29 | 5254.84
TS5500Exc | RS\18\005\B | RS | 18 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-09-22 16:42 | 2021-09-23 22:49 | 37936.3024 | [6 empty] | 37936 | 27053 | 2.69 | 0 | 0 | 9.28 | 5558
TS5500Shv | RS\18\007\B | RS | 18 | 7 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-09-23 05:42 | 2021-09-23 15:55 | 12462.3518 | [6 empty] | 12462 | 8893 | 1.32 | 0 | 0 | 9.07 | 5588
TS5500Shv | GG\11\007\D | GG | 11 | 7 | D | 8 Coal Mining | 3.8 | 0 | 3.8 | 2021-09-23 15:55 | 2021-09-23 17:54 | 2416.0118 | [6 empty] | 2416 | 1806 | 0.18 | 0 | 0 | 6.53 | 5814
TS5500Shv | RS\15\004\D | RS | 15 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-09-23 17:54 | 2021-09-24 18:38 | 30167.8956 | [6 empty] | 30168 | 21963 | 2.2 | 0 | 0 | 6.81 | 5822
TS5500Exc | RS\18\007\B | RS | 18 | 7 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-09-23 22:49 | 2021-09-24 09:02 | 12873.1985 | [6 empty] | 12873 | 9187 | 1.37 | 0 | 0 | 9.07 | 5588
DRE1 | RS\15\006\D | RS | 15 | 6 | D | 6 DL | 100 | 100 | 100 | 2021-09-24 01:37 | 2021-09-27 19:04 | 312439.6031 |  |  |  | 16064 | 312440 | 251665 |  |  | 0 | 26.77 | 0 | 7.66 | 5747.53
TS5500Exc | MW\41\007\B | MW | 41 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-24 09:02 | 2021-09-26 20:37 | 52691.6613 | 52692 | [7 empty] | 0 | 0 | 5.29 | 9.5 | 5496.43
TS5500Shv | MW\41\008\B | MW | 41 | 8 | B | 8 Coal Mining | 33.7 | 0 | 33.7 | 2021-09-24 18:38 | 2021-09-25 05:04 | 12709.8987 | [6 empty] | 12710 | 9355 | 0.94 | 0 | 0 | 10.14 | 5421
TS5500Shv | RS\15\005\D | RS | 15 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-09-25 05:04 | 2021-09-26 05:44 | 30094.6494 | [6 empty] | 30095 | 21910 | 2.19 | 0 | 0 | 7.09 | 5798
TS Fleet 5 | MW\42\009\A | MW | 42 | 9 | A | 1 Prestrip - Thick | 81.8086 | 81.8086 | 81.8086 | 2021-09-25 11:49 | 2021-10-08 18:30 | 624617.2366 | 624617 | [7 empty] | 0 | 0 | 43.09 | 12.19 | 5320.96
PH4100A | RS\18\004\B | RS | 18 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-26 05:29 | 2021-09-26 19:13 | 23847.0474 | 23847 | [7 empty] | 0 | 0 | 2.38 | 9.04 | 5597.32
TS5500Shv | RS\18\003\A | RS | 18 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-09-26 05:44 | 2021-09-27 08:51 | 33060.7165 | [6 empty] | 33061 | 23001 | 2.93 | 0 | 0 | 13.29 | 5255
PH4100XPC#1 | GG\13\011\B | GG | 13 | 11 | B | 1 Prestrip - Thick | 100 | 80.3245 | 80.3245 | 2021-09-26 06:15 | 2021-10-04 23:06 | 490369.7072 | 490370 | [7 empty] | 0 | 0 | 47.76 | 9.82 | 5525.72
PH4100A | RS\19\003\X | RS | 19 | 3 | X | 1 Prestrip - Thick | 100 | 62.4698 | 62.4698 | 2021-09-26 19:13 | 2021-09-29 19:29 | 120082.1288 | 120082 | [7 empty] | 0 | 0 | 19.92 | 12.66 | 5149.43
TS5500Exc | RS\18\004\B | RS | 18 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-09-26 20:37 | 2021-09-28 04:08 | 39707.0142 | [6 empty] | 39707 | 28345 | 2.82 | 0 | 0 | 9.04 | 5597
TS5500Shv | MW\41\009\B | MW | 41 | 9 | B | 8 Coal Mining | 3.7 | 0 | 3.7 | 2021-09-27 08:51 | 2021-09-27 09:59 | 1373.9808 | [6 empty] | 1374 | 1016 | 0.1 | 0 | 0 | 9.47 | 5509
TS5500Shv | MW\41\010\A | MW | 41 | 10 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-09-27 09:59 | 2021-09-27 20:10 | 12421.6825 | [6 empty] | 12422 | 9133 | 1.61 | 0 | 0 | 11.25 | 5397
DRE1 | RS\15\007\D | RS | 15 | 7 | D | 6 DL | 100 | 100 | 100 | 2021-09-27 19:04 | 2021-10-01 11:41 | 309569.5462 |  |  |  | 11449 | 309570 | 175270 |  |  | 0 | 27.09 | 0 | 8.28 | 5690.99
TS5500Shv | MW\42\005\B | MW | 42 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-09-27 20:10 | 2021-09-28 12:20 | 19714.276 | [6 empty] | 19714 | 14326 | 0.96 | 0 | 0 | 11.84 | 5332
DRE2 | GG\11\005\D | GG | 11 | 5 | D | 6 DL | 100 | 100 | 100 | 2021-09-27 22:01 | 2021-10-03 04:39 | 425945.0541 |  |  |  | 10301 | 425945 | 195718 |  |  | 0 | 20.6 | 0 | 6.4 | 5823.41
TS5500Exc | MW\41\007\B | MW | 41 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-09-28 04:08 | 2021-09-29 11:14 | 39173.4603 | [6 empty] | 39173 | 28861 | 2.89 | 0 | 0 | 9.5 | 5496
TS5500Shv | GG\11\006\D | GG | 11 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-09-28 12:20 | 2021-09-30 16:03 | 63058.906 | [6 empty] | 63059 | 47255 | 4.72 | 0 | 0 | 6.46 | 5820
TS5500Exc | RS\15\003\D | RS | 15 | 3 | D | 8 Coal Mining | 64.1 | 0 | 64.1 | 2021-09-29 11:14 | 2021-09-30 21:31 | 43170.5085 | [6 empty] | 43171 | 31428 | 2.83 | 0 | 0 | 6.38 | 5860
PH4100A | RS\18\003\B | RS | 18 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-29 19:29 | 2021-09-30 06:15 | 18698.7902 | 18699 | [7 empty] | 0 | 0 | 2.33 | 8.74 | 5642.53
PH4100A | RS\20\003\X | RS | 20 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-09-30 06:15 | 2021-10-05 04:31 | 197424.1428 | 197424 | [7 empty] | 0 | 0 | 33.8 | 12.61 | 5153.69
TS5500Shv | RS\18\003\B | RS | 18 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-09-30 16:03 | 2021-10-01 05:16 | 16127.8106 | [6 empty] | 16128 | 11490 | 1.41 | 0 | 0 | 8.74 | 5643
TS5500Exc | RS\18\003\B | RS | 18 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-09-30 21:31 | 2021-10-01 10:44 | 16659.4966 | [6 empty] | 16659 | 11869 | 1.45 | 0 | 0 | 8.74 | 5643
TS5500Shv | RS\19\003\X | RS | 19 | 3 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-10-01 05:16 | 2021-10-01 09:26 | 5078.0834 | [6 empty] | 5078 | 3551 | 0.55 | 0 | 0 | 12.66 | 5149
TS5500Shv | MW\42\008\A | MW | 42 | 8 | A | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-10-01 09:26 | 2021-10-02 03:46 | 22358.9057 | [6 empty] | 22359 | 16197 | 1.62 | 0 | 0 | 13.55 | 5209
TS5500Exc | RS\19\003\X | RS | 19 | 3 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-10-01 10:44 | 2021-10-01 14:54 | 5245.4927 | [6 empty] | 5245 | 3668 | 0.57 | 0 | 0 | 12.66 | 5149
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2021-10-01 11:41 | 2021-10-03 11:41
TS5500Exc | RS\15\004\D | RS | 15 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-10-01 14:54 | 2021-10-02 15:39 | 31162.4416 | [6 empty] | 31162 | 22687 | 2.27 | 0 | 0 | 6.81 | 5822
TS5500Shv | RS\15\007\D | RS | 15 | 7 | D | 7 PostStrip | 43.7618 | 0 | 43.7618 | 2021-10-02 03:46 | 2021-10-02 21:02 | 18497.902 |  |  | 18498 | [5 empty] | 0 | 0 | 0 | 8.28 | 5690.99
TS5500Exc | RS\15\005\D | RS | 15 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-10-02 15:39 | 2021-10-03 16:19 | 31086.7807 | [6 empty] | 31087 | 22632 | 2.26 | 0 | 0 | 7.09 | 5798
TS6060#1 | GG\13\009\X1 | GG | 13 | 9 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-10-02 17:12 | 2021-10-02 23:39 | 8715.1878 | [6 empty] | 8715 | 6410 | 0.64 | 0 | 0 | 11.24 | 5403
TS5500Shv | GG\14\006\X1 | GG | 14 | 6 | X1 | 1 Prestrip - Thick | 32.1901 | 32.1901 | 32.1901 | 2021-10-02 21:02 | 2021-10-10 13:02 | 196725.5865 | 196726 | [7 empty] | 0 | 0 | 19.27 | 10.72 | 5364.16
TS6060#1 | GG\11\007\D | GG | 11 | 7 | D | 8 Coal Mining | 96.2 | 0 | 96.2 | 2021-10-02 23:39 | 2021-10-04 20:53 | 61221.3849 | [6 empty] | 61221 | 45769 | 4.58 | 0 | 0 | 6.53 | 5814
DRE2 | GG\11\004\D | GG | 11 | 4 | D | 6 DL | 100 | 100 | 100 | 2021-10-03 04:39 | 2021-10-05 23:38 | 225318.0573 |  |  |  | 10081 | 225318 | 191546 |  |  | 0 | 20.16 | 0 | 6.27 | 5834.87
DRE1 | MW\37\003\D | MW | 37 | 3 | D | 6 DL | 100 | 100 | 100 | 2021-10-03 11:41 | 2021-10-10 05:22 | 564756.9627 |  |  |  | 13658 | 564757 | 259501 |  |  | 0 | 22.77 | 0 | 6.42 | 5847.92
TS5500Exc | RS\15\006\D | RS | 15 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-10-03 16:19 | 2021-10-05 16:39 | 60875.3139 | [6 empty] | 60875 | 44077 | 4.41 | 0 | 0 | 7.66 | 5748
TS6060#1 | RS\19\007\X | RS | 19 | 7 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-10-04 20:53 | 2021-10-22 16:09 | 433696.7903 | 433697 | [7 empty] | 0 | 0 | 59.99 | 10.65 | 5308.97
PH4100XPC#1 | GG\13\009\X2 | GG | 13 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2021-10-04 23:06 | 2021-10-06 15:44 | 91969.277 | 91969 | [7 empty] | 0 | 0 | 9.17 | 0 | 0
PH4100A | RS\19\003\A | RS | 19 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-10-05 04:31 | 2021-10-08 15:52 | 144687.9743 | 144688 | [7 empty] | 0 | 0 | 20.47 | 13.55 | 5231.83
TS5500Exc | RS\20\003\X | RS | 20 | 3 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-10-05 16:39 | 2021-10-06 01:10 | 10716.746 | [6 empty] | 10717 | 7494 | 1.18 | 0 | 0 | 12.61 | 5154
DRE2 | GG\11\003\D | GG | 11 | 3 | D | 6 DL | 100 | 100 | 100 | 2021-10-05 23:38 | 2021-10-11 04:38 | 420513.6134 |  |  |  | 7831 | 420514 | 187939 |  |  | 0 | 19.59 | 0 | 6.14 | 5845.86
TS5500Exc | RS\15\007\D | RS | 15 | 7 | D | 7 PostStrip | 56.2382 | 0 | 56.2382 | 2021-10-06 01:10 | 2021-10-07 04:02 | 23771.5965 |  |  | 23772 | [5 empty] | 0 | 0 | 0 | 8.28 | 5690.99
PH4100XPC#1 | GG\13\009\B | GG | 13 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-10-06 15:44 | 2021-10-07 23:18 | 71441.4422 | 71441 | [7 empty] | 0 | 0 | 7.11 | 9.69 | 5533.77
TS5500Exc | RS\15\007\D | RS | 15 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-10-07 04:02 | 2021-10-08 20:42 | 51224.6092 | [6 empty] | 51225 | 36932 | 4.39 | 0 | 0 | 8.28 | 5691
PH4100XPC#1 | GG\13\012\B | GG | 13 | 12 | B | 1 Prestrip - Thick | 100 | 91.6307 | 91.6307 | 2021-10-07 23:18 | 2021-10-16 19:07 | 493666.2832 | 493666 | [7 empty] | 0 | 0 | 41.13 | 10.39 | 5484.73
PH4100A | RS\20\003\A | RS | 20 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-10-08 15:52 | 2021-10-12 00:36 | 140155.886 | 140156 | [7 empty] | 0 | 0 | 20.07 | 13.66 | 5219.63
TS Fleet 5 | SC\57\001\D | SC | 57 | 1 | D | 1 Prestrip - Thick | 80.451 | 80.451 | 80.451 | 2021-10-08 18:30 | 2021-10-31 13:13 | 1071592.837 | 1071593 | [7 empty] | 0 | 0 | 19.51 | 5.91 | 5889.86
TS5500Exc | RS\19\003\A | RS | 19 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-10-08 20:42 | 2021-10-09 23:08 | 33292.4743 | [6 empty] | 33292 | 23105 | 2.98 | 0 | 0 | 13.55 | 5232
TS5500Exc | MW\41\010\B | MW | 41 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-10-09 23:08 | 2021-10-10 17:45 | 16462.0994 | 16462 | [7 empty] | 0 | 0 | 2.96 | 8.96 | 5587.08
DRE1 | MW\37\004\D | MW | 37 | 4 | D | 6 DL | 100 | 100 | 100 | 2021-10-10 05:22 | 2021-10-14 03:06 | 327422.6873 |  |  |  | 16834 | 327423 | 263734 |  |  | 0 | 28.08 | 0 | 6.83 | 5812.12
TS5500Shv | GG\11\005\D | GG | 11 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-10-10 13:02 | 2021-10-12 15:12 | 61161.435 | [6 empty] | 61161 | 45868 | 4.59 | 0 | 0 | 6.4 | 5823
TS5500Exc | MW\41\010\B | MW | 41 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-10-10 17:45 | 2021-10-11 09:17 | 19559.9341 | [6 empty] | 19560 | 14539 | 2.66 | 0 | 0 | 8.96 | 5587
DRE2 | GG\11\002\D | GG | 11 | 2 | D | 6 DL | 100 | 100 | 100 | 2021-10-11 04:38 | 2021-10-16 10:41 | 423964.6373 |  |  |  | 7022 | 423965 | 122112 |  |  | 0 | 18.91 | 0 | 6.15 | 5845.92
TS5500Exc | MW\37\003\D | MW | 37 | 3 | D | 8 Coal Mining | 48 | 0 | 48 | 2021-10-11 09:17 | 2021-10-12 12:54 | 34786.5034 | [6 empty] | 34787 | 26156 | 2.19 | 0 | 0 | 6.42 | 5848
PH4100A | RS\19\003\B | RS | 19 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-10-12 00:36 | 2021-10-12 11:27 | 18829.3161 | 18829 | [7 empty] | 0 | 0 | 2.38 | 8.77 | 5638.73
PH4100A | RS\19\004\X | RS | 19 | 4 | X | 1 Prestrip - Thick | 100 | 33.4444 | 33.4444 | 2021-10-12 11:27 | 2021-10-16 02:20 | 145820.9716 | 145821 | [7 empty] | 0 | 0 | 14.49 | 12.79 | 5148.94
TS5500Exc | RS\20\003\A | RS | 20 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-10-12 12:54 | 2021-10-13 16:33 | 34840.6262 | [6 empty] | 34841 | 24162 | 3.15 | 0 | 0 | 13.66 | 5220
TS5500Shv | RS\19\003\B | RS | 19 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-10-12 15:12 | 2021-10-13 17:23 | 31936.5505 | [6 empty] | 31937 | 22750 | 2.82 | 0 | 0 | 8.77 | 5639
TS5500Exc | RS\19\006\X | RS | 19 | 6 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-10-13 16:33 | 2021-10-14 05:50 | 16727.0713 | [6 empty] | 16727 | 11763 | 1.18 | 0 | 0 | 11.9 | 5233
TS5500Shv | GG\11\004\D | GG | 11 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-10-13 17:23 | 2021-10-15 19:07 | 60641.5287 | [6 empty] | 60642 | 45477 | 4.55 | 0 | 0 | 6.27 | 5835
DRE1 | MW\37\005\D | MW | 37 | 5 | D | 6 DL | 100 | 100 | 100 | 2021-10-14 03:06 | 2021-10-18 12:17 | 367419.2133 |  |  |  | 20970 | 367419 | 278598 |  |  | 0 | 30.07 | 0 | 6.2 | 5867.04
TS5500Exc | MW\37\004\D | MW | 37 | 4 | D | 8 Coal Mining | 47.3 | 0 | 47.3 | 2021-10-14 05:50 | 2021-10-15 05:00 | 29185.2154 | [6 empty] | 29185 | 21823 | 2.18 | 0 | 0 | 6.83 | 5812
TS5500Exc | MW\42\006\B | MW | 42 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-10-15 05:00 | 2021-10-16 01:35 | 25913.1845 | [6 empty] | 25913 | 19058 | 1.88 | 0 | 0 | 9.67 | 5509
TS5500Shv | GG\11\003\D | GG | 11 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-10-15 19:07 | 2021-10-17 20:59 | 60802.2492 | [6 empty] | 60802 | 45598 | 4.56 | 0 | 0 | 6.14 | 5846
TS5500Exc | MW\42\007\A | MW | 42 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-10-16 01:35 | 2021-10-17 09:27 | 40139.1746 | [6 empty] | 40139 | 29166 | 2.94 | 0 | 0 | 12.81 | 5259
PH4100A | RS\19\006\A | RS | 19 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-10-16 02:20 | 2021-10-20 13:43 | 186412.0293 | 186412 | [7 empty] | 0 | 0 | 18.67 | 19.69 | 4687.42
DRE2 | GG\12\013\B | GG | 12 | 13 | B | 6 DL | 100 | 0 | 100 | 2021-10-16 10:41 | 2021-10-18 03:39 | 137817.8441 |  |  |  |  | 137818 | 114848 |  |  | 0 | 16.72 | 0 | 10.85 | 5449.6
PH4100XPC#1 | GG\13\013\B | GG | 13 | 13 | B | 1 Prestrip - Thick | 100 | 84.5044 | 84.5044 | 2021-10-16 19:07 | 2021-10-23 09:47 | 365960.4583 | 365960 | [7 empty] | 0 | 0 | 46.6 | 10.91 | 5443.1
TS5500Exc | RS\19\004\X | RS | 19 | 4 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-10-17 09:27 | 2021-10-17 15:30 | 7629.8698 | [6 empty] | 7630 | 5325 | 0.53 | 0 | 0 | 12.79 | 5149
TS5500Exc | MW\42\007\B | MW | 42 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-10-17 15:30 | 2021-10-20 01:39 | 51428.4007 | 51428 | [7 empty] | 0 | 0 | 5.17 | 9.61 | 5489
TS5500Shv | RS\19\004\X | RS | 19 | 4 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-10-17 20:59 | 2021-10-18 03:02 | 7386.3633 | [6 empty] | 7386 | 5155 | 0.51 | 0 | 0 | 12.79 | 5149
TS5500Shv | MW\37\003\D | MW | 37 | 3 | D | 8 Coal Mining | 52 | 0 | 52 | 2021-10-18 03:02 | 2021-10-19 09:54 | 37643.4215 | [6 empty] | 37643 | 28304 | 2.36 | 0 | 0 | 6.42 | 5848
DRE2 | GG\12\018\B | GG | 12 | 18 | B | 6 DL | 100 | 0 | 100 | 2021-10-18 03:39 | 2021-10-20 01:02 | 152634.0661 |  |  |  |  | 152634 | 127195 |  |  | 0 | 17.34 | 0 | 11.02 | 5435.31
DRE1 | MW\37\006\D | MW | 37 | 6 | D | 6 DL | 100 | 100 | 100 | 2021-10-18 12:17 | 2021-10-22 15:49 | 347688.2312 |  |  |  | 17876 | 347688 | 280057 |  |  | 0 | 29.82 | 0 | 5.7 | 5910.51
TS5500Shv | GG\11\002\D | GG | 11 | 2 | D | 7 PostStrip | 92.8777 | 0 | 92.8777 | 2021-10-19 09:54 | 2021-10-21 02:08 | 43114.5037 |  |  | 43115 | [5 empty] | 0 | 0 | 0 | 6.15 | 5845.92
DRE2 | GG\12\019\B | GG | 12 | 19 | B | 6 DL | 100 | 0 | 100 | 2021-10-20 01:02 | 2021-10-22 23:29 | 237014.3467 |  |  |  |  | 237014 | 197512 |  |  | 0 | 17.93 | 0 | 11.29 | 5421.5
TS5500Exc | MW\37\005\D | MW | 37 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-10-20 01:39 | 2021-10-22 01:39 | 60463.5819 | [6 empty] | 60464 | 45499 | 4.55 | 0 | 0 | 6.2 | 5867
PH4100A | RS\19\004\A | RS | 19 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-10-20 13:43 | 2021-10-25 12:17 | 205847.6392 | 205848 | [7 empty] | 0 | 0 | 20.52 | 17.21 | 4912.81
TS5500Shv | MW\37\004\D | MW | 37 | 4 | D | 8 Coal Mining | 52.7 | 0 | 52.7 | 2021-10-21 02:08 | 2021-10-22 04:50 | 32571.3059 | [6 empty] | 32571 | 24355 | 2.44 | 0 | 0 | 6.83 | 5812
TS5500Exc | RS\19\006\A | RS | 19 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-10-22 01:39 | 2021-10-23 17:15 | 49866.9195 | [6 empty] | 49867 | 33354 | 3.34 | 0 | 0 | 19.69 | 4687
TS5500Shv | GG\12\018\B | GG | 12 | 18 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-10-22 04:50 | 2021-10-23 08:14 | 33400.1358 | [6 empty] | 33400 | 24379 | 3.37 | 0 | 0 | 11.02 | 5435
DRE1 | MW\37\007\D | MW | 37 | 7 | D | 6 DL | 100 | 100 | 100 | 2021-10-22 15:49 | 2021-10-26 19:16 | 347358.645 |  |  |  | 17859 | 347359 | 279792 |  |  | 0 | 29.77 | 0 | 5.56 | 5923.17
TS6060#1 | GG\11\002\D | GG | 11 | 2 | D | 7 PostStrip | 7.1223 | 0 | 7.1223 | 2021-10-22 16:09 | 2021-10-22 19:22 | 3306.205 |  |  | 3306 | [5 empty] | 0 | 0 | 0 | 6.15 | 5845.92
TS6060#1 | GG\11\002\D | GG | 11 | 2 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-10-22 19:22 | 2021-10-23 17:21 | 29773.2387 | [6 empty] | 29773 | 22328 | 2.43 | 0 | 0 | 6.15 | 5846
DRE2 | GG\12\020\B | GG | 12 | 20 | B | 6 DL | 100 | 0 | 100 | 2021-10-22 23:29 | 2021-10-25 12:33 | 205420.9825 |  |  |  |  | 205421 | 171184 |  |  | 0 | 19.15 | 0 | 12.9 | 5309.85
TS5500Shv | GG\11\002\D | GG | 11 | 2 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-10-23 08:14 | 2021-10-24 06:14 | 26825.3933 | [6 empty] | 26825 | 20118 | 2.19 | 0 | 0 | 6.15 | 5846
PH4100XPC#1 | GG\13\018\X2 | GG | 13 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2021-10-23 09:47 | 2021-10-28 06:42 | 262660.0735 | 262660 | [7 empty] | 0 | 0 | 30.13 | 0 | 0
TS5500Exc | MW\37\006\D | MW | 37 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-10-23 17:15 | 2021-10-25 15:37 | 58406.5438 | [6 empty] | 58407 | 44160 | 4.42 | 0 | 0 | 5.7 | 5911
TS6060#1 | GG\12\013\B | GG | 12 | 13 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-10-23 17:21 | 2021-10-24 15:26 | 29869.9503 | [6 empty] | 29870 | 21823 | 3.1 | 0 | 0 | 10.85 | 5450
TS5500Shv | GG\12\019\B | GG | 12 | 19 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-10-24 06:14 | 2021-10-26 01:32 | 52808.4594 | [6 empty] | 52808 | 38436 | 3.83 | 0 | 0 | 11.29 | 5422
TS6060#1 | RS\20\007\X | RS | 20 | 7 | X | 1 Prestrip - Thick | 37.3978 | 37.3978 | 37.3978 | 2021-10-24 15:26 | 2021-10-30 12:43 | 143509.1342 | 143509 | [7 empty] | 0 | 0 | 22.95 | 11.16 | 5271.93
PH4100A | RS\19\006\B | RS | 19 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-10-25 12:17 | 2021-10-26 03:42 | 26742.878 | 26743 | [7 empty] | 0 | 0 | 2.68 | 9.15 | 5571.7
DRE2 | GG\12\021\B | GG | 12 | 21 | B | 6 DL | 100 | 0 | 100 | 2021-10-25 12:33 | 2021-10-28 13:16 | 244549.3511 |  |  |  |  | 244549 | 188115 |  |  | 0 | 20.17 | 0 | 13.91 | 5241.6
TS5500Exc | RS\19\004\A | RS | 19 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-10-25 15:37 | 2021-10-27 00:58 | 42018.8201 | [6 empty] | 42019 | 28526 | 2.84 | 0 | 0 | 17.21 | 4913
TS5500Shv | MW\42\007\B | MW | 42 | 7 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-10-26 01:32 | 2021-10-26 17:19 | 19243.8531 | [6 empty] | 19244 | 14178 | 1.42 | 0 | 0 | 9.61 | 5489
PH4100A | RS\20\003\B | RS | 20 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-10-26 03:42 | 2021-10-26 14:40 | 19059.2765 | 19059 | [7 empty] | 0 | 0 | 2.44 | 8.78 | 5635.16
PH4100A | RS\20\004\X | RS | 20 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-10-26 14:40 | 2021-11-06 21:25 | 455192.3428 | 455192 | [7 empty] | 0 | 0 | 45.15 | 12.77 | 5151.22
TS5500Shv | GG\12\020\B | GG | 12 | 20 | B | 8 Coal Mining | 29.1 | 0 | 29.1 | 2021-10-26 17:19 | 2021-10-27 05:55 | 15368.9174 | [6 empty] | 15369 | 11067 | 1.11 | 0 | 0 | 12.9 | 5310
DRE1 | MW\37\008\D | MW | 37 | 8 | D | 6 DL | 100 | 100 | 100 | 2021-10-26 19:16 | 2021-10-30 22:09 | 345453.3417 |  |  |  | 17761 | 345453 | 278257 |  |  | 0 | 29.62 | 0 | 5.53 | 5926.93
TS5500Exc | RS\20\003\B | RS | 20 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-10-27 00:58 | 2021-10-28 01:46 | 31226.4901 | [6 empty] | 31226 | 22243 | 2.79 | 0 | 0 | 8.78 | 5635
TS5500Shv | MW\37\007\D | MW | 37 | 7 | D | 8 Coal Mining | 39.8 | 0 | 39.8 | 2021-10-27 05:55 | 2021-10-28 01:27 | 23810.3093 | [6 empty] | 23810 | 18033 | 1.8 | 0 | 0 | 5.56 | 5923
TS5500Shv | MW\42\009\A | MW | 42 | 9 | A | 8 Coal Mining | 41.7 | 0 | 41.7 | 2021-10-28 01:27 | 2021-10-28 22:53 | 26150.2712 | [6 empty] | 26150 | 19103 | 1.38 | 0 | 0 | 12.19 | 5321
TS5500Exc | MW\37\007\D | MW | 37 | 7 | D | 8 Coal Mining | 60.2 | 0 | 60.2 | 2021-10-28 01:46 | 2021-10-29 06:18 | 35953.0858 | [6 empty] | 35953 | 27229 | 2.72 | 0 | 0 | 5.56 | 5923
PH4100XPC#1 | GG\13\018\B | GG | 13 | 18 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-10-28 06:42 | 2021-10-30 08:36 | 112960.6716 | 112961 | [7 empty] | 0 | 0 | 13.47 | 10.84 | 5448.61
DRE2 | GG\12\022\B | GG | 12 | 22 | B | 6 DL | 100 | 0 | 100 | 2021-10-28 13:16 | 2021-10-31 09:16 | 228785.4465 |  |  |  |  | 228785 | 190655 |  |  | 0 | 19.46 | 0 | 14.9 | 5149.01
TS5500Shv | GG\14\007\X1 | GG | 14 | 7 | X1 | 1 Prestrip - Thick | 9.9895 | 9.9895 | 9.9895 | 2021-10-28 22:53 | 2021-10-31 03:06 | 55678.0587 | 55678 | [7 empty] | 0 | 0 | 5.36 | 10.79 | 5403.27
TS5500Exc | MW\42\007\B | MW | 42 | 7 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-10-29 06:18 | 2021-10-29 22:05 | 19878.2659 | [6 empty] | 19878 | 14645 | 1.47 | 0 | 0 | 9.61 | 5489
TS5500Exc | RS\19\007\X | RS | 19 | 7 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-10-29 22:05 | 2021-10-30 07:02 | 11257.1671 | [6 empty] | 11257 | 8007 | 1.17 | 0 | 0 | 10.65 | 5309
TS5500Exc | MW\42\008\A | MW | 42 | 8 | A | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-10-30 07:02 | 2021-10-31 02:42 | 24785.7037 | [6 empty] | 24786 | 17955 | 1.79 | 0 | 0 | 13.55 | 5209
PH4100XPC#1 | GG\13\019\B | GG | 13 | 19 | B | 1 Prestrip - Thick | 100 | 72.988 | 72.988 | 2021-10-30 08:36 | 2021-11-04 01:49 | 257839.854 | 257840 | [7 empty] | 0 | 0 | 24.49 | 11.21 | 5428.63
TS6060#1 | GG\12\020\B | GG | 12 | 20 | B | 8 Coal Mining | 70.9 | 0 | 70.9 | 2021-10-30 12:43 | 2021-10-31 16:26 | 37495.4471 | [6 empty] | 37495 | 26999 | 2.7 | 0 | 0 | 12.9 | 5310
DRE1 | MW\37\009\D | MW | 37 | 9 | D | 6 DL | 100 | 100 | 100 | 2021-10-30 22:09 | 2021-11-03 20:54 | 330967.0625 |  |  |  | 17016 | 330967 | 266589 |  |  | 0 | 28.38 | 0 | 5.35 | 5941.88
TS5500Exc | MW\37\008\D | MW | 37 | 8 | D | 8 Coal Mining | 100 | 0 | 43 | 2021-10-31 02:42 | 2021-10-31 23:52 | 26655.1026 | [6 empty] | 26655 | 20221 | 2.02 | 0 | 0 | 5.53 | 5927
TS5500Shv | MW\37\008\D | MW | 37 | 8 | D | 8 Coal Mining | 93.5 | 0 | 40.8 | 2021-10-31 03:06 | 2021-10-31 23:52 | 25312.2351 | [6 empty] | 25312 | 19202 | 1.92 | 0 | 0 | 5.53 | 5927
DRE2 | GG\12\023\B | GG | 12 | 23 | B | 6 DL | 100 | 0 | 100 | 2021-10-31 09:16 | 2021-11-02 22:09 | 204793.756 |  |  |  |  | 204794 | 170661 |  |  | 0 | 17.46 | 0 | 11.97 | 5333.75
TS Fleet 5 | SC\57\001\D | SC | 57 | 1 | D | 1 Prestrip - Thick | 19.549 | 19.549 | 19.549 | 2021-10-31 13:13 | 2021-11-06 02:05 | 260388.9831 | 260389 | [7 empty] | 0 | 0 | 4.74 | 5.91 | 5889.86
TS6060#1 | MW\37\008\D | MW | 37 | 8 | D | 8 Coal Mining | 100 | 0 | 16.2 | 2021-10-31 16:26 | 2021-10-31 23:52 | 10064.1772 | [6 empty] | 10064 | 7635 | 0.76 | 0 | 0 | 5.53 | 5927
TS6060#1 | GG\12\021\B | GG | 12 | 21 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-10-31 23:52 | 2021-11-02 13:57 | 51552.1733 | [6 empty] | 51552 | 36838 | 3.69 | 0 | 0 | 13.91 | 5242
TS5500Exc | RS\19\006\B | RS | 19 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-10-31 23:52 | 2021-11-02 05:25 | 37233.2565 | [6 empty] | 37233 | 26550 | 2.66 | 0 | 0 | 9.15 | 5572
TS5500Shv | GG\12\022\B | GG | 12 | 22 | B | 8 Coal Mining | 41.8 | 0 | 41.8 | 2021-10-31 23:52 | 2021-11-01 17:31 | 21519.4618 | [6 empty] | 21519 | 15315 | 1.53 | 0 | 0 | 14.9 | 5149
TS5500Shv | GG\14\007\X1 | GG | 14 | 7 | X1 | 1 Prestrip - Thick | 22.25 | 22.25 | 22.25 | 2021-11-01 17:31 | 2021-11-06 13:49 | 124014.3581 | 124014 | [7 empty] | 0 | 0 | 11.93 | 10.79 | 5403.27
TS5500Exc | MW\42\008\B | MW | 42 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-11-02 05:25 | 2021-11-03 23:10 | 36918.2759 | 36918 | [7 empty] | 0 | 0 | 3.68 | 10.11 | 5429.11
TS6060#1 | GG\12\022\B | GG | 12 | 22 | B | 8 Coal Mining | 58.2 | 0 | 58.2 | 2021-11-02 13:57 | 2021-11-03 12:07 | 29990.7774 | [6 empty] | 29991 | 21343 | 2.14 | 0 | 0 | 14.9 | 5149
DRE2 | GG\12\024\B | GG | 12 | 24 | B | 6 DL | 100 | 0 | 100 | 2021-11-02 22:09 | 2021-11-06 19:39 | 314465.6555 |  |  |  |  | 314466 | 241897 |  |  | 0 | 25.09 | 0 | 0 | 0
TS6060#1 | GG\12\023\B | GG | 12 | 23 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-11-03 12:07 | 2021-11-04 03:21 | 20618.4845 | [6 empty] | 20618 | 14962 | 1.5 | 0 | 0 | 11.97 | 5334
DRE1 | MW\37\010\D | MW | 37 | 10 | D | 6 DL | 100 | 100 | 100 | 2021-11-03 20:54 | 2021-11-07 00:46 | 264986.5297 |  |  |  | 9723 | 264987 | 149754 |  |  | 0 | 27.79 | 0 | 5.16 | 5958.02
TS5500Exc | MW\37\009\D | MW | 37 | 9 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-11-03 23:10 | 2021-11-04 23:26 | 30566.552 | [6 empty] | 30567 | 23262 | 2.33 | 0 | 0 | 5.35 | 5942
PH4100XPC#1 | GG\13\020\B | GG | 13 | 20 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-11-04 01:49 | 2021-11-10 15:28 | 374125.2724 | 374125 | [7 empty] | 0 | 0 | 42.04 | 13.09 | 5299.15
TS6060#1 | RS\19\007\A | RS | 19 | 7 | A | 1 Prestrip - Thick | 1.91 | 1.91 | 1.91 | 2021-11-04 03:21 | 2021-11-04 05:24 | 2115.7247 | 2116 | [7 empty] | 0 | 0 | 0.36 | 18.22 | 4803.99
TS6060#1 | RS\21\003\X | RS | 21 | 3 | X | 1 Prestrip - Thick | 29.895 | 29.895 | 29.895 | 2021-11-04 05:24 | 2021-11-06 17:01 | 59927.4119 | 59927 | [7 empty] | 0 | 0 | 10.65 | 12.56 | 5158.59
TS5500Exc | MW\42\008\B | MW | 42 | 8 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-11-04 23:26 | 2021-11-05 14:38 | 19136.6813 | [6 empty] | 19137 | 14084 | 1.4 | 0 | 0 | 10.11 | 5429
TS5500Exc | MW\42\009\A | MW | 42 | 9 | A | 8 Coal Mining | 58.3 | 0 | 58.3 | 2021-11-05 14:38 | 2021-11-06 19:39 | 36564.878 | [6 empty] | 36565 | 26712 | 1.93 | 0 | 0 | 12.19 | 5321
TS Fleet 5 | SC\57\002\D | SC | 57 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-11-06 02:05 | 2021-11-22 13:49 | 775651.4252 | 775651 | [7 empty] | 0 | 0 | 20.2 | 6.28 | 5858.91
TS5500Shv | MW\37\009\D | MW | 37 | 9 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-11-06 13:49 | 2021-11-07 14:05 | 29591.0238 | [6 empty] | 29591 | 22520 | 2.25 | 0 | 0 | 5.35 | 5942
TS6060#1 | RS\21\004\X | RS | 21 | 4 | X | 1 Prestrip - Thick | 57.6233 | 57.6233 | 57.6233 | 2021-11-06 17:01 | 2021-11-17 17:16 | 266570.6711 | 266571 | [7 empty] | 0 | 0 | 26.51 | 12.71 | 5157.09
DRE2 | GG\11\013\D | GG | 11 | 13 | D | 6 DL | 100 | 100 | 100 | 2021-11-06 19:39 | 2021-11-10 09:51 | 289984.9868 |  |  |  | 6752 | 289985 | 128282 |  |  | 0 | 23.03 | 0 | 6.57 | 5811.72
TS5500Exc | MW\42\009\B | MW | 42 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-11-06 19:39 | 2021-11-08 21:28 | 44056.328 | 44056 | [7 empty] | 0 | 0 | 3.2 | 9.38 | 5527.14
PH4100A | RS\19\004\B | RS | 19 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-11-06 21:25 | 2021-11-07 11:00 | 23568.8569 | 23569 | [7 empty] | 0 | 0 | 2.35 | 9.03 | 5595.16
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2021-11-07 00:46 | 2021-11-09 00:46
PH4100A | RS\19\007\A | RS | 19 | 7 | A | 1 Prestrip - Thick | 100 | 98.09 | 98.09 | 2021-11-07 11:00 | 2021-11-10 01:35 | 108655.2729 | 108655 | [7 empty] | 0 | 0 | 18.4 | 18.22 | 4803.99
TS5500Shv | RS\19\004\B | RS | 19 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-11-07 14:05 | 2021-11-08 05:50 | 19205.8012 | [6 empty] | 19206 | 13699 | 1.37 | 0 | 0 | 9.03 | 5595
TS5500Shv | RS\20\004\X | RS | 20 | 4 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-11-08 05:50 | 2021-11-08 12:13 | 7778.7865 | [6 empty] | 7779 | 5426 | 0.54 | 0 | 0 | 12.77 | 5151
TS5500Shv | GG\12\023\B | GG | 12 | 23 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-11-08 12:13 | 2021-11-09 03:27 | 18577.0504 | [6 empty] | 18577 | 13480 | 1.35 | 0 | 0 | 11.97 | 5334
TS5500Exc | RS\19\004\B | RS | 19 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-11-08 21:28 | 2021-11-09 13:13 | 19838.9595 | [6 empty] | 19839 | 14151 | 1.41 | 0 | 0 | 9.03 | 5595
DRE1 | RS\16\003\D | RS | 16 | 3 | D | 6 DL | 100 | 100 | 100 | 2021-11-09 00:46 | 2021-11-13 07:21 | 358331.0192 |  |  |  | 18423 | 358331 | 288630 |  |  | 0 | 27.65 | 0 | 6.35 | 5862.01
TS5500Shv | MW\37\010\D | MW | 37 | 10 | D | 7 PostStrip | 50.9554 | 0 | 50.9554 | 2021-11-09 03:27 | 2021-11-09 20:05 | 17828.3795 |  |  | 17828 | [5 empty] | 0 | 0 | 0 | 5.16 | 5958.02
TS5500Exc | RS\20\004\X | RS | 20 | 4 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-11-09 13:13 | 2021-11-09 19:36 | 8035.23 | [6 empty] | 8035 | 5605 | 0.56 | 0 | 0 | 12.77 | 5151
TS5500Exc | MW\42\009\B | MW | 42 | 9 | B | 8 Coal Mining | 94.4 | 0 | 94.4 | 2021-11-09 19:36 | 2021-11-11 08:52 | 46944.6487 | [6 empty] | 46945 | 34744 | 2.54 | 0 | 0 | 9.38 | 5527
TS5500Shv | MW\42\008\B | MW | 42 | 8 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-11-09 20:05 | 2021-11-10 11:16 | 18525.9361 | [6 empty] | 18526 | 13635 | 1.36 | 0 | 0 | 10.11 | 5429
PH4100A | RS\20\004\A | RS | 20 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-11-10 01:35 | 2021-11-14 23:06 | 204012.3678 | 204012 | [7 empty] | 0 | 0 | 20.32 | 17.17 | 4912.33
DRE2 | GG\11\018\D | GG | 11 | 18 | D | 6 DL | 100 | 100 | 100 | 2021-11-10 09:51 | 2021-11-14 00:08 | 290209.7602 |  |  |  | 6757 | 290210 | 128382 |  |  | 0 | 22.36 | 0 | 6.58 | 5810.5
TS5500Shv | GG\11\013\D | GG | 11 | 13 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-11-10 11:16 | 2021-11-11 01:47 | 17703.4856 | [6 empty] | 17703 | 13246 | 2.29 | 0 | 0 | 6.57 | 5812
PH4100XPC#1 | GG\13\021\B | GG | 13 | 21 | B | 1 Prestrip - Thick | 100 | 69.355 | 69.355 | 2021-11-10 15:28 | 2021-11-14 12:39 | 215101.0561 | 215101 | [7 empty] | 0 | 0 | 22.5 | 14.27 | 5221.57
TS5500Shv | MW\42\009\B | MW | 42 | 9 | B | 8 Coal Mining | 5.6 | 0 | 5.6 | 2021-11-11 01:47 | 2021-11-11 04:04 | 2774.6748 | [6 empty] | 2775 | 2054 | 0.15 | 0 | 0 | 9.38 | 5527
TS5500Shv | GG\14\010\B | GG | 14 | 10 | B | 1 Prestrip - Thick | 26.4369 | 26.4369 | 26.4369 | 2021-11-11 04:04 | 2021-11-17 10:06 | 160824.7273 | 160825 | [7 empty] | 0 | 0 | 16.3 | 9.3 | 5561.57
TS5500Exc | RS\19\007\A | RS | 19 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-11-11 08:52 | 2021-11-12 07:34 | 28588.1765 | [6 empty] | 28588 | 19403 | 3.35 | 0 | 0 | 18.22 | 4804
TS5500Exc | MW\43\002\D | MW | 43 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-11-12 07:34 | 2021-11-13 07:55 | 21539.8804 | 21540 | [7 empty] | 0 | 0 | 3.72 | 6.5 | 5842.35
DRE1 | RS\16\004\D | RS | 16 | 4 | D | 6 DL | 100 | 100 | 100 | 2021-11-13 07:21 | 2021-11-17 03:43 | 322672.1442 |  |  |  | 16590 | 322672 | 259907 |  |  | 0 | 27.64 | 0 | 6.78 | 5824.75
TS5500Exc | RS\16\003\D | RS | 16 | 3 | D | 8 Coal Mining | 58.7 | 0 | 58.7 | 2021-11-13 07:55 | 2021-11-14 15:20 | 39564.162 | [6 empty] | 39564 | 28801 | 2.58 | 0 | 0 | 6.35 | 5862
DRE2 | GG\11\019\D | GG | 11 | 19 | D | 6 DL | 100 | 100 | 100 | 2021-11-14 00:08 | 2021-11-19 19:06 | 467490.5569 |  |  |  | 10885 | 467491 | 206806 |  |  | 0 | 21.74 | 0 | 6.4 | 5826.76
PH4100XPC#1 | GG\13\022\B | GG | 13 | 22 | B | 1 Prestrip - Thick | 100 | 95.2045 | 95.2045 | 2021-11-14 12:39 | 2021-11-19 23:56 | 300821.1927 | 300821 | [7 empty] | 0 | 0 | 30.43 | 15.51 | 5110.96
TS5500Exc | MW\43\003\D | MW | 43 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-11-14 15:20 | 2021-11-24 15:17 | 212301.5367 | 212302 | [7 empty] | 0 | 0 | 21.67 | 6.54 | 5838.27
PH4100A | RS\19\007\B | RS | 19 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-11-14 23:06 | 2021-11-15 08:13 | 15832.2418 | 15832 | [7 empty] | 0 | 0 | 2.75 | 9.07 | 5586.54
PH4100A | RS\19\005\X | RS | 19 | 5 | X | 1 Prestrip - Thick | 100 | 0.81169 | 0.81169 | 2021-11-15 08:13 | 2021-11-15 10:39 | 4102.8996 | 4103 | [7 empty] | 0 | 0 | 0.41 | 12.94 | 5155.65
PH4100A | RS\20\005\X | RS | 20 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-11-15 10:39 | 2021-11-28 05:27 | 519894.3605 | 519894 | [7 empty] | 0 | 0 | 51.75 | 12.91 | 5158
DRE1 | RS\16\005\D | RS | 16 | 5 | D | 6 DL | 100 | 100 | 100 | 2021-11-17 03:43 | 2021-11-20 22:21 | 316586.4526 |  |  |  | 16277 | 316586 | 255005 |  |  | 0 | 27.12 | 0 | 7.08 | 5798.48
TS5500Shv | RS\19\005\X | RS | 19 | 5 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-11-17 10:06 | 2021-11-17 16:58 | 8360.5365 | [6 empty] | 8361 | 5818 | 0.58 | 0 | 0 | 12.94 | 5156
TS5500Shv | GG\11\018\D | GG | 11 | 18 | D | 8 Coal Mining | 96.6 | 0 | 96.6 | 2021-11-17 16:58 | 2021-11-18 23:23 | 37102.9987 | [6 empty] | 37103 | 27761 | 4.65 | 0 | 0 | 6.58 | 5811
TS6060#1 | GG\11\013\D | GG | 11 | 13 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-11-17 17:16 | 2021-11-18 07:47 | 19648.9235 | [6 empty] | 19649 | 14701 | 2.54 | 0 | 0 | 6.57 | 5812
TS6060#1 | MW\37\010\D | MW | 37 | 10 | D | 7 PostStrip | 49.0446 | 0 | 49.0446 | 2021-11-18 07:47 | 2021-11-19 00:25 | 17159.8153 |  |  | 17160 | [5 empty] | 0 | 0 | 0 | 5.16 | 5958.02
TS5500Shv | RS\19\007\B | RS | 19 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-11-18 23:23 | 2021-11-19 16:54 | 21356.4052 | [6 empty] | 21356 | 15250 | 2.66 | 0 | 0 | 9.07 | 5587
TS6060#1 | GG\11\018\D | GG | 11 | 18 | D | 8 Coal Mining | 3.4 | 0 | 3.4 | 2021-11-19 00:25 | 2021-11-19 01:23 | 1306.8785 | [6 empty] | 1307 | 978 | 0.16 | 0 | 0 | 6.58 | 5811
TS6060#1 | RS\21\005\X | RS | 21 | 5 | X | 1 Prestrip - Thick | 54.2476 | 54.2476 | 54.2476 | 2021-11-19 01:23 | 2021-11-30 22:12 | 288887.9738 | 288888 | [7 empty] | 0 | 0 | 28.79 | 12.83 | 5163.72
TS5500Shv | MW\37\010\D | MW | 37 | 10 | D | 8 Coal Mining | 72.6 | 0 | 72.6 | 2021-11-19 16:54 | 2021-11-20 16:44 | 29065.2309 | [6 empty] | 29065 | 22190 | 3.24 | 0 | 0 | 5.16 | 5958
DRE2 | GG\11\020\D | GG | 11 | 20 | D | 6 DL | 100 | 100 | 100 | 2021-11-19 19:06 | 2021-11-25 08:17 | 447951.1802 |  |  |  | 10430 | 447951 | 198162 |  |  | 0 | 20.86 | 0 | 6.21 | 5843.31
PH4100XPC#1 | GG\13\023\B | GG | 13 | 23 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-11-19 23:56 | 2021-11-25 13:33 | 311588.5037 | 311589 | [7 empty] | 0 | 0 | 32.7 | 12.21 | 5326.75
TS5500Shv | GG\11\019\D | GG | 11 | 19 | D | 8 Coal Mining | 79.2 | 0 | 79.2 | 2021-11-20 16:44 | 2021-11-22 10:57 | 51479.3949 | [6 empty] | 51479 | 38578 | 3.86 | 0 | 0 | 6.4 | 5827
DRE1 | RS\16\006\D | RS | 16 | 6 | D | 6 DL | 100 | 100 | 100 | 2021-11-20 22:21 | 2021-11-24 16:45 | 315756.8358 |  |  |  | 16234 | 315757 | 254337 |  |  | 0 | 27.05 | 0 | 7.67 | 5746.68
TS5500Shv | RS\16\003\D | RS | 16 | 3 | D | 8 Coal Mining | 41.3 | 0 | 41.3 | 2021-11-22 10:57 | 2021-11-23 09:47 | 27848.3051 | [6 empty] | 27848 | 20273 | 1.82 | 0 | 0 | 6.35 | 5862
TS Fleet 5 | SC\58\001\D | SC | 58 | 1 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-11-22 13:49 | 2021-12-10 21:51 | 862470.5664 | 862471 | [7 empty] | 0 | 0 | 21.34 | 6.22 | 5867.84
TS5500Shv | RS\16\004\D | RS | 16 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-11-23 09:47 | 2021-11-24 10:25 | 30034.9742 | [6 empty] | 30035 | 21900 | 2.19 | 0 | 0 | 6.78 | 5825
TS5500Shv | RS\16\005\D | RS | 16 | 5 | D | 8 Coal Mining | 25.2 | 0 | 25.2 | 2021-11-24 10:25 | 2021-11-24 23:00 | 15337.1483 | [6 empty] | 15337 | 11174 | 1.12 | 0 | 0 | 7.08 | 5798
TS5500Exc | RS\19\005\X | RS | 19 | 5 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-11-24 15:17 | 2021-11-24 22:09 | 8636.1586 | [6 empty] | 8636 | 6010 | 0.6 | 0 | 0 | 12.94 | 5156
DRE1 | RS\16\007\D | RS | 16 | 7 | D | 6 DL | 100 | 100 | 100 | 2021-11-24 16:45 | 2021-11-28 01:40 | 282681.7661 |  |  |  | 10383 | 282682 | 159793 |  |  | 0 | 27.7 | 0 | 8.46 | 5674.85
TS5500Exc | RS\20\004\A | RS | 20 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-11-24 22:09 | 2021-11-26 10:07 | 45311.6262 | [6 empty] | 45312 | 30721 | 3.06 | 0 | 0 | 17.17 | 4912
TS5500Shv | RS\16\006\D | RS | 16 | 6 | D | 8 Coal Mining | 4.6 | 0 | 4.6 | 2021-11-24 23:00 | 2021-11-25 01:18 | 2800.3259 | [6 empty] | 2800 | 2028 | 0.2 | 0 | 0 | 7.67 | 5747
TS5500Shv | GG\14\012\B | GG | 14 | 12 | B | 1 Prestrip - Thick | 28.9598 | 28.9598 | 28.9598 | 2021-11-25 01:18 | 2021-11-30 19:47 | 148195.5784 | 148196 | [7 empty] | 0 | 0 | 12.94 | 10.36 | 5485.76
DRE2 | GG\11\021\D | GG | 11 | 21 | D | 6 DL | 100 | 100 | 100 | 2021-11-25 08:17 | 2021-11-30 15:29 | 427869.6932 |  |  |  | 7968 | 427870 | 191227 |  |  | 0 | 19.93 | 0 | 6.15 | 5847.78
PH4100XPC#1 | GG\13\024\B | GG | 13 | 24 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-11-25 13:33 | 2021-11-30 03:46 | 259711.4163 | 259711 | [7 empty] | 0 | 0 | 39.95 | 0 | 0
TS5500Exc | MW\37\010\D | MW | 37 | 10 | D | 8 Coal Mining | 27.4 | 0 | 27.4 | 2021-11-26 10:07 | 2021-11-26 18:48 | 10943.5617 | [6 empty] | 10944 | 8355 | 1.22 | 0 | 0 | 5.16 | 5958
TS5500Exc | RS\16\004\D | RS | 16 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2021-11-26 18:48 | 2021-11-27 19:26 | 31025.1382 | [6 empty] | 31025 | 22622 | 2.26 | 0 | 0 | 6.78 | 5825
TS5500Exc | RS\16\005\D | RS | 16 | 5 | D | 8 Coal Mining | 74.8 | 0 | 74.8 | 2021-11-27 19:26 | 2021-11-29 07:34 | 45506.7783 | [6 empty] | 45507 | 33155 | 3.32 | 0 | 0 | 7.08 | 5798
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2021-11-28 01:40 | 2021-11-30 01:40
PH4100A | RS\19\005\A | RS | 19 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-11-28 05:27 | 2021-12-02 18:36 | 189504.6953 | 189505 | [7 empty] | 0 | 0 | 18.89 | 20.34 | 4635.19
TS5500Exc | RS\20\005\X | RS | 20 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2021-11-29 07:34 | 2021-11-29 20:51 | 16735.837 | [6 empty] | 16736 | 11649 | 1.16 | 0 | 0 | 12.91 | 5158
TS5500Exc | RS\16\006\D | RS | 16 | 6 | D | 8 Coal Mining | 41.7 | 0 | 41.7 | 2021-11-29 20:51 | 2021-11-30 16:55 | 25272.7961 | [6 empty] | 25273 | 18298 | 1.83 | 0 | 0 | 7.67 | 5747
DRE1 | MW\38\003\D | MW | 38 | 3 | D | 6 DL | 100 | 100 | 100 | 2021-11-30 01:40 | 2021-12-03 11:23 | 285444.653 |  |  |  | 14676 | 285445 | 229921 |  |  | 0 | 25.02 | 0 | 6.42 | 5848.79
PH4100XPC#1 | GG\14\002\X1 | GG | 14 | 2 | X1 | 1 Prestrip - Thick | 100 | 71.1679 | 71.1679 | 2021-11-30 03:46 | 2021-12-12 05:33 | 652717.0969 | 652717 | [7 empty] | 0 | 0 | 62.65 | 10.23 | 5347.54
DRE2 | GG\11\022\D | GG | 11 | 22 | D | 6 DL | 100 | 100 | 100 | 2021-11-30 15:29 | 2021-12-06 03:11 | 443030.0818 |  |  |  | 10315 | 443030 | 195985 |  |  | 0 | 20.63 | 0 | 6.1 | 5846.35
TS5500Exc | RS\16\007\D | RS | 16 | 7 | D | 7 PostStrip | 100 | 0 | 100 | 2021-11-30 16:55 | 2021-12-02 11:18 | 37490.2755 |  |  | 37490 | [5 empty] | 0 | 0 | 0 | 8.46 | 5674.85
TS5500Shv | GG\11\020\D | GG | 11 | 20 | D | 8 Coal Mining | 44.7 | 0 | 44.7 | 2021-11-30 19:47 | 2021-12-01 19:20 | 28717.286 | [6 empty] | 28717 | 21538 | 2.15 | 0 | 0 | 6.21 | 5843
TS6060#1 | GG\11\019\D | GG | 11 | 19 | D | 8 Coal Mining | 20.8 | 0 | 20.8 | 2021-11-30 22:12 | 2021-12-01 08:10 | 13495.8551 | [6 empty] | 13496 | 10114 | 1.01 | 0 | 0 | 6.4 | 5827
TS6060#1 | GG\11\020\D | GG | 11 | 20 | D | 8 Coal Mining | 55.3 | 0 | 55.3 | 2021-12-01 08:10 | 2021-12-02 10:24 | 35511.4361 | [6 empty] | 35511 | 26633 | 2.66 | 0 | 0 | 6.21 | 5843
TS5500Shv | GG\11\021\D | GG | 11 | 21 | D | 8 Coal Mining | 38.5 | 0 | 38.5 | 2021-12-01 19:20 | 2021-12-02 15:24 | 24466.2176 | [6 empty] | 24466 | 18364 | 1.84 | 0 | 0 | 6.15 | 5848
TS6060#1 | RS\21\005\X | RS | 21 | 5 | X | 1 Prestrip - Thick | 0.18433 | 0.18433 | 0.18433 | 2021-12-02 10:24 | 2021-12-02 11:22 | 981.6101 | 982 | [7 empty] | 0 | 0 | 0.1 | 12.83 | 5163.72
TS5500Exc | MW\43\005\B | MW | 43 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-12-02 11:18 | 2021-12-10 16:23 | 174374.6192 | 174375 | [7 empty] | 0 | 0 | 17.57 | 11.32 | 5366.38
TS6060#1 | GG\11\021\D | GG | 11 | 21 | D | 8 Coal Mining | 61.5 | 0 | 61.5 | 2021-12-02 11:22 | 2021-12-03 16:12 | 39023.1157 | [6 empty] | 39023 | 29290 | 2.93 | 0 | 0 | 6.15 | 5848
TS5500Shv | RS\16\007\D | RS | 16 | 7 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2021-12-02 15:24 | 2021-12-03 09:44 | 22351.9344 | [6 empty] | 22352 | 16102 | 2.16 | 0 | 0 | 8.46 | 5675
PH4100A | RS\20\004\B | RS | 20 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-12-02 18:36 | 2021-12-03 08:23 | 23919.404 | 23919 | [7 empty] | 0 | 0 | 2.38 | 9.03 | 5593.02
PH4100A | RS\20\005\A | RS | 20 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-12-03 08:23 | 2021-12-07 21:21 | 189171.8415 | 189172 | [7 empty] | 0 | 0 | 18.89 | 20.34 | 4636.02
TS5500Shv | RS\19\005\A | RS | 19 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-12-03 09:44 | 2021-12-05 02:49 | 50111.4683 | [6 empty] | 50111 | 33257 | 3.32 | 0 | 0 | 20.34 | 4635
DRE1 | MW\38\004\D | MW | 38 | 4 | D | 6 DL | 100 | 100 | 100 | 2021-12-03 11:23 | 2021-12-07 08:07 | 323936.0695 |  |  |  | 16655 | 323936 | 260925 |  |  | 0 | 27.77 | 0 | 6.76 | 5818.77
TS6060#1 | RS\21\006\X | RS | 21 | 6 | X | 1 Prestrip - Thick | 20.9469 | 20.9469 | 20.9469 | 2021-12-03 16:12 | 2021-12-11 15:48 | 194715.6254 | 194716 | [7 empty] | 0 | 0 | 12.71 | 12 | 5219.63
TS5500Shv | RS\20\004\B | RS | 20 | 4 | B | 8 Coal Mining | 64.6 | 0 | 64.6 | 2021-12-05 02:49 | 2021-12-05 23:18 | 24962.5966 | [6 empty] | 24963 | 17804 | 1.77 | 0 | 0 | 9.03 | 5593
TS5500Shv | MW\38\003\D | MW | 38 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-12-05 23:18 | 2021-12-08 00:27 | 59947.8981 | [6 empty] | 59948 | 45078 | 4.68 | 0 | 0 | 6.42 | 5849
DRE2 | GG\11\023\D | GG | 11 | 23 | D | 6 DL | 100 | 100 | 100 | 2021-12-06 03:11 | 2021-12-11 17:52 | 453039.1476 |  |  |  | 10548 | 453039 | 200413 |  |  | 0 | 21.07 | 0 | 6.03 | 5846.72
DRE1 | MW\38\005\D | MW | 38 | 5 | D | 6 DL | 100 | 0 | 100 | 2021-12-07 08:07 | 2021-12-12 13:08 | 436671.7311 |  |  |  | 31055 | 436672 | 314003 |  |  | 0 | 35 | 0 | 6.15 | 5872.06
PH4100A | RS\19\005\B | RS | 19 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-12-07 21:21 | 2021-12-08 11:59 | 25390.91 | 25391 | [7 empty] | 0 | 0 | 2.53 | 9.27 | 5555.57
TS5500Shv | MW\38\004\D | MW | 38 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-12-08 00:27 | 2021-12-10 03:23 | 62104.4533 | [6 empty] | 62104 | 46476 | 4.65 | 0 | 0 | 6.76 | 5819
PH4100A | RS\20\006\X | RS | 20 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-12-08 11:59 | 2021-12-22 16:48 | 579221.0828 | 579221 | [7 empty] | 0 | 0 | 57.71 | 12.01 | 5223
TS5500Shv | GG\14\024\D | GG | 14 | 24 | D | 1 Prestrip - Thick | 5.7672 | 5.7672 | 5.7672 | 2021-12-10 03:23 | 2021-12-10 15:31 | 13030.7644 | 13031 | [7 empty] | 0 | 0 | 2.39 | 6.28 | 5835.84
TS5500Shv | GG\15\003\X1 | GG | 15 | 3 | X1 | 1 Prestrip - Thick | 32.2064 | 32.2064 | 32.2064 | 2021-12-10 15:31 | 2021-12-31 03:48 | 525724.2077 | 525724 | [7 empty] | 0 | 0 | 28.4 | 10.04 | 5360.15
TS5500Exc | RS\19\005\B | RS | 19 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-12-10 16:23 | 2021-12-11 22:10 | 37517.5324 | [6 empty] | 37518 | 26734 | 2.66 | 0 | 0 | 9.27 | 5556
TS Fleet 5 | SC\58\002\D | SC | 58 | 2 | D | 1 Prestrip - Thick | 100 | 94.1597 | 94.1597 | 2021-12-10 21:51 | 2022-01-01 | 992034.9345 | 992035 | [7 empty] | 0 | 0 | 22.73 | 6.26 | 5864.51
TS6060#1 | GG\11\022\D | GG | 11 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-12-11 15:48 | 2021-12-13 10:04 | 57186.6326 | [6 empty] | 57187 | 43024 | 4.29 | 0 | 0 | 6.1 | 5846
DRE2 | GG\11\024\D | GG | 11 | 24 | D | 6 DL | 100 | 100 | 100 | 2021-12-11 17:52 | 2021-12-16 13:46 | 389834.9058 |  |  |  | 7259 | 389835 | 174228 |  |  | 0 | 18.37 | 0 | 6.1 | 5848.91
TS5500Exc | RS\20\005\A | RS | 20 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2021-12-11 22:10 | 2021-12-13 14:03 | 50226.2059 | [6 empty] | 50226 | 33321 | 3.33 | 0 | 0 | 20.34 | 4636
PH4100XPC#1 | GG\14\003\X1 | GG | 14 | 3 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-12-12 05:33 | 2021-12-30 05:39 | 973713.2327 | 973713 | [7 empty] | 0 | 0 | 87.75 | 9.94 | 5375.41
DRE1 | MW\38\006\D | MW | 38 | 6 | D | 6 DL | 100 | 100 | 100 | 2021-12-12 13:08 | 2021-12-16 16:25 | 346830.5805 |  |  |  | 17832 | 346831 | 279367 |  |  | 0 | 29.76 | 0 | 5.68 | 5912.54
TS6060#1 | GG\14\002\X1 | GG | 14 | 2 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-12-13 10:04 | 2021-12-13 15:27 | 7288.7598 | [6 empty] | 7289 | 5406 | 0.63 | 0 | 0 | 10.23 | 5348
TS5500Exc | RS\20\004\B | RS | 20 | 4 | B | 8 Coal Mining | 35.4 | 0 | 35.4 | 2021-12-13 14:03 | 2021-12-14 00:55 | 13697.6985 | [6 empty] | 13698 | 9770 | 0.97 | 0 | 0 | 9.03 | 5593
TS6060#1 | GG\11\023\D | GG | 11 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-12-13 15:27 | 2021-12-15 05:39 | 51695.5433 | [6 empty] | 51696 | 39111 | 3.92 | 0 | 0 | 6.03 | 5847
TS5500Exc | SC\57\001\D | SC | 57 | 1 | D | 7 PostStrip | 12.2754 | 0 | 12.2754 | 2021-12-14 00:55 | 2021-12-16 01:27 | 42917.4742 |  |  | 42917 | [5 empty] | 0 | 0 | 0 | 5.91 | 5889.86
TS6060#1 | RS\23\003\X | RS | 23 | 3 | X | 1 Prestrip - Thick | 37.4237 | 37.4237 | 37.4237 | 2021-12-15 05:39 | 2021-12-18 08:09 | 75421.8775 | 75422 | [7 empty] | 0 | 0 | 14.35 | 12.44 | 5172.75
TS5500Exc | SC\57\001\D | SC | 57 | 1 | D | 7 PostStrip | 87.7246 | 0 | 87.7246 | 2021-12-16 01:27 | 2021-12-30 12:15 | 306704.8799 |  |  | 306705 | [5 empty] | 0 | 0 | 0 | 5.91 | 5889.86
DRE2 | GG\11\025\D | GG | 11 | 25 | D | 6 DL | 100 | 0 | 100 | 2021-12-16 13:46 | 2021-12-20 15:35 | 329061.282 |  |  |  | 25024 | 329061 | 225213 |  |  | 0 | 40 | 0 | 6.08 | 5852.43
DRE1 | MW\38\007\D | MW | 38 | 7 | D | 6 DL | 100 | 100 | 100 | 2021-12-16 16:25 | 2021-12-20 19:40 | 346697.2823 |  |  |  | 17825 | 346697 | 279259 |  |  | 0 | 29.71 | 0 | 5.53 | 5926.46
TS6060#1 | GG\11\024\D | GG | 11 | 24 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-12-18 08:09 | 2021-12-20 04:01 | 59366.9657 | [6 empty] | 59367 | 45061 | 4.52 | 0 | 0 | 6.1 | 5849
TS6060#1 | RS\23\004\X | RS | 23 | 4 | X | 1 Prestrip - Thick | 49.1844 | 49.1844 | 49.1844 | 2021-12-20 04:01 | 2021-12-29 11:53 | 226451.6752 | 226452 | [7 empty] | 0 | 0 | 22.68 | 12.56 | 5173.59
DRE2 | GG\13\012\B | GG | 13 | 12 | B | 6 DL | 100 | 0 | 100 | 2021-12-20 15:35 | 2021-12-23 16:39 | 245759.1432 |  |  |  |  | 245759 | 204799 |  |  | 0 | 16.97 | 0 | 10.39 | 5484.73
DRE1 | MW\38\008\D | MW | 38 | 8 | D | 6 DL | 100 | 100 | 100 | 2021-12-20 19:40 | 2021-12-24 22:12 | 344191.0507 |  |  |  | 17696 | 344191 | 277240 |  |  | 0 | 29.52 | 0 | 5.47 | 5932.34
PH4100A | RS\20\005\B | RS | 20 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2021-12-22 16:48 | 2021-12-23 07:36 | 25689.3604 | 25689 | [7 empty] | 0 | 0 | 2.57 | 9.23 | 5558.62
PH4100A | RS\20\007\X | RS | 20 | 7 | X | 1 Prestrip - Thick | 100 | 62.6022 | 62.6022 | 2021-12-23 07:36 | 2021-12-29 04:54 | 240227.9233 | 240228 | [7 empty] | 0 | 0 | 38.42 | 11.16 | 5271.93
DRE2 | GG\13\011\B | GG | 13 | 11 | B | 6 DL | 100 | 0 | 100 | 2021-12-23 16:39 | 2021-12-26 12:27 | 228098.9889 |  |  |  |  | 228099 | 175461 |  |  | 0 | 17 | 0 | 9.82 | 5525.72
DRE1 | MW\38\009\D | MW | 38 | 9 | D | 6 DL | 100 | 100 | 100 | 2021-12-24 22:12 | 2021-12-28 20:39 | 329939.1301 |  |  |  | 16963 | 329939 | 265761 |  |  | 0 | 28.29 | 0 | 5.31 | 5945.45
DRE2 | GG\13\010\B | GG | 13 | 10 | B | 6 DL | 100 | 0 | 100 | 2021-12-26 12:27 | 2021-12-29 10:08 | 234391.2911 |  |  |  |  | 234391 | 195326 |  |  | 0 | 18.06 | 0 | 9.34 | 5557.32
DRE1 | MW\38\010\D | MW | 38 | 10 | D | 6 DL | 100 | 100 | 100 | 2021-12-28 20:39 | 2021-12-31 11:42 | 220192.1618 |  |  |  | 8111 | 220192 | 124551 |  |  | 0 | 27.44 | 0 | 5.14 | 5959.78
PH4100A | RS\21\003\X | RS | 21 | 3 | X | 1 Prestrip - Thick | 100 | 56.136 | 56.136 | 2021-12-29 04:54 | 2022-01-01 | 112530.0301 | 112530 | [7 empty] | 0 | 0 | 20 | 12.56 | 5158.59
DRE2 | GG\13\009\B | GG | 13 | 9 | B | 6 DL | 100 | 0 | 90.1578 | 2021-12-29 10:08 | 2022-01-01 | 208057.6747 |  |  |  |  | 208058 | 173381 |  |  | 0 | 19.13 | 0 | 9.69 | 5533.77
TS6060#1 | GG\11\025\D | GG | 11 | 25 | D | 8 Coal Mining | 100 | 0 | 100 | 2021-12-29 11:53 | 2021-12-30 16:49 | 39151.2323 | [6 empty] | 39151 | 29693 | 4.66 | 0 | 0 | 6.08 | 5852
PH4100XPC#1 | GG\14\004\X1 | GG | 14 | 4 | X1 | 1 Prestrip - Thick | 100 | 11.5752 | 11.5752 | 2021-12-30 05:39 | 2022-01-01 | 97827.0365 | 97827 | [7 empty] | 0 | 0 | 9.54 | 9.73 | 5391.96
TS5500Exc | RS\20\005\B | RS | 20 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2021-12-30 12:15 | 2021-12-31 17:46 | 37190.5708 | [6 empty] | 37191 | 26500 | 2.65 | 0 | 0 | 9.23 | 5559
TS6060#1 | GG\14\003\X1 | GG | 14 | 3 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2021-12-30 16:49 | 2021-12-31 00:13 | 10008.0497 | [6 empty] | 10008 | 7443 | 0.7 | 0 | 0 | 9.94 | 5375
TS6060#1 | GG\13\010\B | GG | 13 | 10 | B | 8 Coal Mining | 100 | 0 | 63.9 | 2021-12-31 00:13 | 2022-01-01 | 32185.5237 | [6 empty] | 32186 | 23734 | 2.37 | 0 | 0 | 9.34 | 5557
TS5500Shv | GG\14\002\X1 | GG | 14 | 2 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2021-12-31 03:48 | 2021-12-31 09:11 | 6567.1004 | [6 empty] | 6567 | 4870 | 0.57 | 0 | 0 | 10.23 | 5348
TS5500Shv | GG\14\002\X2 | GG | 14 | 2 | X2 | 1 Prestrip - Thick | 91.9052 | 0 | 24.4139 | 2021-12-31 09:11 | 2022-01-01 | 15877.0885 | 15877 | [7 empty] | 0 | 0 | 1.97 | 0 | 0
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 0d 12:18 | 2021-12-31 11:42 | 2022-01-01
TS5500Exc | RS\20\006\X | RS | 20 | 6 | X | 8 Coal Mining | 100 | 0 | 46.9 | 2021-12-31 17:46 | 2022-01-01 | 7835.0976 | [6 empty] | 7835 | 5502 | 0.55 | 0 | 0 | 12.01 | 5223
| EOP 74 : 2021 | EOP 74 : 2021 | [7 empty] | 2022-01-01 | 2022-01-01 |  | 63837824 |  | 1096197 | 1929678 | 58011226 | 38241877 | 17006007 | 12463241 | 1294.23 | 0 | 6232.96 | 9.03 | 5596.94
TS Fleet 5 | SC\58\002\D | SC | 58 | 2 | D | 1 Prestrip - Thick | 100 | 5.8403 | 5.8403 | 2022-01-01 | 2022-01-02 07:23 | 61531.4121 | 61531 | [7 empty] | 0 | 0 | 1.41 | 6.26 | 5864.51
PH4100A | RS\21\003\X | RS | 21 | 3 | X | 1 Prestrip - Thick | 100 | 13.9691 | 13.9691 | 2022-01-01 | 2022-01-01 16:41 | 28002.3432 | 28002 | [7 empty] | 0 | 0 | 4.98 | 12.56 | 5158.59
DRE2 | GG\13\009\B | GG | 13 | 9 | B | 6 DL | 100 | 0 | 9.8422 | 2022-01-01 | 2022-01-01 06:56 | 22712.9042 |  |  |  |  | 22713 | 18927 |  |  | 0 | 19.13 | 0 | 9.69 | 5533.77
PH4100XPC#1 | GG\14\004\X1 | GG | 14 | 4 | X1 | 1 Prestrip - Thick | 100 | 86.518 | 86.518 | 2022-01-01 | 2022-01-14 04:29 | 731202.2636 | 731202 | [7 empty] | 0 | 0 | 71.33 | 9.73 | 5391.96
TS6060#1 | GG\13\010\B | GG | 13 | 10 | B | 8 Coal Mining | 100 | 0 | 36.1 | 2022-01-01 | 2022-01-01 13:27 | 18207.4162 | [6 empty] | 18207 | 13426 | 1.34 | 0 | 0 | 9.34 | 5557
TS5500Shv | GG\14\002\X2 | GG | 14 | 2 | X2 | 1 Prestrip - Thick | 91.9052 | 0 | 67.4914 | 2022-01-01 | 2022-01-02 16:56 | 43891.7238 | 43892 | [7 empty] | 0 | 0 | 5.46 | 0 | 0
TS5500Exc | RS\20\006\X | RS | 20 | 6 | X | 8 Coal Mining | 100 | 0 | 53.1 | 2022-01-01 | 2022-01-01 07:02 | 8868.3712 | [6 empty] | 8868 | 6228 | 0.62 | 0 | 0 | 12.01 | 5223
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 1d 11:42 | 2022-01-01 | 2022-01-02 11:42
DRE2 | GG\13\008\B | GG | 13 | 8 | B | 6 DL | 100 | 0 | 100 | 2022-01-01 06:56 | 2022-01-04 07:39 | 238100.9721 |  |  |  |  | 238101 | 198417 |  |  | 0 | 19.84 | 0 | 10.37 | 5481.45
TS5500Exc | RS\20\007\X | RS | 20 | 7 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-01-01 07:02 | 2022-01-01 10:56 | 4910.0858 | [6 empty] | 4910 | 3477 | 0.59 | 0 | 0 | 11.16 | 5272
TS5500Exc | SC\57\001\D | SC | 57 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-01-01 10:56 | 2022-01-09 16:15 | 248537.4315 | [6 empty] | 248537 | 187982 | 4.07 | 0 | 0 | 5.91 | 5890
TS6060#1 | RS\20\006\A | RS | 20 | 6 | A | 1 Prestrip - Thick | 37.2787 | 37.2787 | 37.2787 | 2022-01-01 13:27 | 2022-01-04 07:53 | 68552.2363 | 68552 | [7 empty] | 0 | 0 | 6.87 | 19.98 | 4669.07
PH4100A | RS\20\006\A | RS | 20 | 6 | A | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2022-01-01 16:41 | 2022-01-04 11:08 | 115338.905 | 115339 | [7 empty] | 0 | 0 | 11.55 | 19.98 | 4669.07
TS Fleet 5 | SC\59\001\D | SC | 59 | 1 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-01-02 07:23 | 2022-01-21 10:33 | 899960.2447 | 899960 | [7 empty] | 0 | 0 | 22.68 | 6.12 | 5876.54
DRE1 | RS\17\003\D | RS | 17 | 3 | D | 6 DL | 100 | 100 | 100 | 2022-01-02 11:42 | 2022-01-07 10:32 | 370840.6483 |  |  |  | 19066 | 370841 | 298706 |  |  | 0 | 28.48 | 0 | 6.31 | 5866.01
TS5500Shv | GG\14\003\X1 | GG | 14 | 3 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-01-02 16:56 | 2022-01-03 00:20 | 9017.1537 | [6 empty] | 9017 | 6706 | 0.63 | 0 | 0 | 9.94 | 5375
TS5500Shv | RS\20\007\X | RS | 20 | 7 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-01-03 00:20 | 2022-01-03 04:14 | 4753.381 | [6 empty] | 4753 | 3366 | 0.57 | 0 | 0 | 11.16 | 5272
TS5500Shv | RS\21\003\X | RS | 21 | 3 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-01-03 04:14 | 2022-01-03 08:38 | 5371.4485 | [6 empty] | 5371 | 3756 | 0.6 | 0 | 0 | 12.56 | 5159
TS5500Shv | GG\14\003\X2 | GG | 14 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2022-01-03 08:38 | 2022-01-06 21:27 | 90915.2277 | 90915 | [7 empty] | 0 | 0 | 8.76 | 0 | 0
DRE2 | GG\13\007\B | GG | 13 | 7 | B | 6 DL | 100 | 0 | 100 | 2022-01-04 07:39 | 2022-01-07 14:23 | 257740.8996 |  |  |  |  | 257741 | 198262 |  |  | 0 | 20.11 | 0 | 10.52 | 5432.58
TS6060#1 | GG\13\009\B | GG | 13 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-01-04 07:53 | 2022-01-05 22:19 | 52022.5535 | [6 empty] | 52023 | 38179 | 3.82 | 0 | 0 | 9.69 | 5534
PH4100A | RS\20\007\A | RS | 20 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-01-04 11:08 | 2022-01-06 15:33 | 91009.9837 | 91010 | [7 empty] | 0 | 0 | 18.5 | 19.01 | 4748.13
TS6060#1 | GG\13\008\B | GG | 13 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-01-05 22:19 | 2022-01-07 13:37 | 53183.8138 | [6 empty] | 53184 | 38794 | 3.88 | 0 | 0 | 10.37 | 5481
PH4100A | RS\22\003\X | RS | 22 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-01-06 15:33 | 2022-01-11 17:16 | 205084.3046 | 205084 | [7 empty] | 0 | 0 | 37.52 | 12.5 | 5164.48
TS5500Shv | RS\20\006\A | RS | 20 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-01-06 21:27 | 2022-01-08 14:20 | 49869.3719 | [6 empty] | 49869 | 33327 | 3.34 | 0 | 0 | 19.98 | 4669
DRE1 | RS\17\004\D | RS | 17 | 4 | D | 6 DL | 100 | 100 | 100 | 2022-01-07 10:32 | 2022-01-11 20:57 | 332057.0406 |  |  |  | 17072 | 332057 | 267467 |  |  | 0 | 28.45 | 0 | 6.75 | 5827.59
TS6060#1 | GG\13\011\B | GG | 13 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-01-07 13:37 | 2022-01-09 01:47 | 48950.2826 | [6 empty] | 48950 | 35993 | 3.6 | 0 | 0 | 9.82 | 5526
DRE2 | GG\13\006\B | GG | 13 | 6 | B | 6 DL | 100 | 0 | 100 | 2022-01-07 14:23 | 2022-01-10 22:06 | 261007.6681 |  |  |  |  | 261008 | 200775 |  |  | 0 | 20.08 | 0 | 11.13 | 5348.89
TS5500Shv | GG\14\003\B | GG | 14 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-01-08 14:20 | 2022-01-12 02:59 | 90743.6843 | 90744 | [7 empty] | 0 | 0 | 9.02 | 10.35 | 5470.89
TS6060#1 | GG\13\007\B | GG | 13 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-01-09 01:47 | 2022-01-10 15:53 | 51548.0614 | [6 empty] | 51548 | 37638 | 3.76 | 0 | 0 | 10.52 | 5433
TS5500Exc | RS\21\003\X | RS | 21 | 3 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-01-09 16:15 | 2022-01-09 20:39 | 5548.5292 | [6 empty] | 5549 | 3880 | 0.62 | 0 | 0 | 12.56 | 5159
TS5500Exc | RS\16\006\D | RS | 16 | 6 | D | 8 Coal Mining | 53.6 | 0 | 53.6 | 2022-01-09 20:39 | 2022-01-10 22:26 | 32482.7162 | [6 empty] | 32483 | 23519 | 2.35 | 0 | 0 | 7.67 | 5747
TS6060#1 | RS\21\003\A | RS | 21 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-01-10 15:53 | 2022-01-16 03:09 | 135448.9667 | 135449 | [7 empty] | 0 | 0 | 19.66 | 13.72 | 5211.83
DRE2 | GG\13\005\B | GG | 13 | 5 | B | 6 DL | 100 | 0 | 100 | 2022-01-10 22:06 | 2022-01-13 06:36 | 184992.1247 |  |  |  |  | 184992 | 160863 |  |  | 0 | 16 | 0 | 11.96 | 5283.95
TS5500Exc | RS\16\007\D | RS | 16 | 7 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-01-10 22:26 | 2022-01-11 16:46 | 23088.8113 | [6 empty] | 23089 | 16633 | 2.23 | 0 | 0 | 8.46 | 5675
TS5500Exc | RS\17\003\D | RS | 17 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-01-11 16:46 | 2022-01-12 20:02 | 34346.011 | [6 empty] | 34346 | 25022 | 2.23 | 0 | 0 | 6.31 | 5866
PH4100A | RS\20\006\B | RS | 20 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-01-11 17:16 | 2022-01-12 09:05 | 27446.7577 | 27447 | [7 empty] | 0 | 0 | 2.75 | 9.12 | 5574.65
DRE1 | RS\17\005\D | RS | 17 | 5 | D | 6 DL | 100 | 100 | 100 | 2022-01-11 20:57 | 2022-01-16 04:43 | 323847.2262 |  |  |  | 16650 | 323847 | 260854 |  |  | 0 | 27.75 | 0 | 7.07 | 5798.91
TS5500Shv | MW\38\005\D | MW | 38 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-01-12 02:59 | 2022-01-14 04:44 | 60649.7677 | [6 empty] | 60650 | 45676 | 4.57 | 0 | 0 | 6.15 | 5872
PH4100A | RS\21\004\X | RS | 21 | 4 | X | 1 Prestrip - Thick | 100 | 42.3767 | 42.3767 | 2022-01-12 09:05 | 2022-01-17 05:26 | 196038.1894 | 196038 | [7 empty] | 0 | 0 | 19.5 | 12.71 | 5157.09
TS5500Exc | RS\20\006\B | RS | 20 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-01-12 20:02 | 2022-01-13 10:52 | 18679.8198 | [6 empty] | 18680 | 13328 | 1.33 | 0 | 0 | 9.12 | 5575
DRE2 | GG\12\012\D | GG | 12 | 12 | D | 6 DL | 100 | 100 | 100 | 2022-01-13 06:36 | 2022-01-19 14:59 | 498931.3329 |  |  |  | 11617 | 498931 | 220715 |  |  | 0 | 23.25 | 0 | 6.4 | 5826.18
TS5500Exc | RS\17\004\D | RS | 17 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-01-13 10:52 | 2022-01-15 11:09 | 60819.8769 | [6 empty] | 60820 | 44415 | 4.44 | 0 | 0 | 6.75 | 5828
PH4100XPC#1 | GG\14\002\X2 | GG | 14 | 2 | X2 | 1 Prestrip - Thick | 100 | 0 | 8.0948 | 2022-01-14 04:29 | 2022-01-14 06:49 | 5264.2764 | 5264 | [7 empty] | 0 | 0 | 0.65 | 0 | 0
TS5500Shv | RS\20\006\B | RS | 20 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-01-14 04:44 | 2022-01-14 19:33 | 18083.6554 | [6 empty] | 18084 | 12903 | 1.29 | 0 | 0 | 9.12 | 5575
PH4100XPC#1 | GG\14\002\B | GG | 14 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-01-14 06:49 | 2022-01-15 09:46 | 60990.7466 | 60991 | [7 empty] | 0 | 0 | 8.43 | 10.39 | 5481.58
TS5500Shv | MW\38\006\D | MW | 38 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-01-14 19:33 | 2022-01-16 19:47 | 58800.1978 | [6 empty] | 58800 | 44458 | 4.45 | 0 | 0 | 5.68 | 5913
PH4100XPC#1 | GG\14\005\X1 | GG | 14 | 5 | X1 | 1 Prestrip - Thick | 100 | 67.9465 | 67.9465 | 2022-01-15 09:46 | 2022-01-24 10:10 | 491576.8107 | 491577 | [7 empty] | 0 | 0 | 45.11 | 9.97 | 5386.23
TS5500Exc | RS\20\007\A | RS | 20 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-01-15 11:09 | 2022-01-16 06:03 | 23810.6799 | [6 empty] | 23811 | 16086 | 3.35 | 0 | 0 | 19.01 | 4748
TS6060#1 | GG\14\002\B | GG | 14 | 2 | B | 8 Coal Mining | 95.5 | 0 | 95.5 | 2022-01-16 03:09 | 2022-01-17 01:46 | 30617.7486 | [6 empty] | 30618 | 22486 | 3.34 | 0 | 0 | 10.39 | 5482
DRE1 | RS\17\006\D | RS | 17 | 6 | D | 6 DL | 100 | 100 | 100 | 2022-01-16 04:43 | 2022-01-20 12:24 | 323522.9309 |  |  |  | 16634 | 323523 | 260593 |  |  | 0 | 27.71 | 0 | 7.64 | 5749.01
TS5500Exc | RS\17\005\D | RS | 17 | 5 | D | 8 Coal Mining | 78.4 | 0 | 78.4 | 2022-01-16 06:03 | 2022-01-17 19:43 | 47435.6222 | [6 empty] | 47436 | 34559 | 3.46 | 0 | 0 | 7.07 | 5799
TS5500Shv | GG\14\002\B | GG | 14 | 2 | B | 8 Coal Mining | 4.5 | 0 | 4.5 | 2022-01-16 19:47 | 2022-01-16 20:57 | 1436.0171 | [6 empty] | 1436 | 1055 | 0.16 | 0 | 0 | 10.39 | 5482
TS5500Shv | MW\38\010\D | MW | 38 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2022-01-16 20:57 | 2022-01-18 00:32 | 29559.2419 |  |  | 29559 | [5 empty] | 0 | 0 | 0 | 5.14 | 5959.78
TS6060#1 | GG\13\012\B | GG | 13 | 12 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-01-17 01:46 | 2022-01-18 12:30 | 46997.5605 | [6 empty] | 46998 | 34431 | 3.45 | 0 | 0 | 10.39 | 5485
PH4100A | RS\20\007\B | RS | 20 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-01-17 05:26 | 2022-01-17 13:09 | 13394.8288 | 13395 | [7 empty] | 0 | 0 | 2.81 | 9.07 | 5586.05
PH4100A | RS\22\004\X | RS | 22 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-01-17 13:09 | 2022-01-28 23:13 | 462566.5608 | 462567 | [7 empty] | 0 | 0 | 46.23 | 12.63 | 5165.1
TS5500Exc | RS\21\003\A | RS | 21 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-01-17 19:43 | 2022-01-18 10:25 | 18512.7899 | [6 empty] | 18513 | 12833 | 1.7 | 0 | 0 | 13.72 | 5212
TS5500Shv | MW\38\007\D | MW | 38 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-01-18 00:32 | 2022-01-20 01:56 | 60243.7458 | [6 empty] | 60244 | 45663 | 4.57 | 0 | 0 | 5.53 | 5926
TS5500Exc | RS\21\004\X | RS | 21 | 4 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-01-18 10:25 | 2022-01-18 17:03 | 8363.4145 | [6 empty] | 8363 | 5834 | 0.58 | 0 | 0 | 12.71 | 5157
TS6060#1 | GG\13\006\B | GG | 13 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-01-18 12:30 | 2022-01-20 01:42 | 50342.8264 | [6 empty] | 50343 | 36716 | 3.68 | 0 | 0 | 11.13 | 5349
TS5500Exc | RS\22\003\X | RS | 22 | 3 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-01-18 17:03 | 2022-01-18 21:28 | 5552.7362 | [6 empty] | 5553 | 3883 | 0.62 | 0 | 0 | 12.5 | 5164
TS5500Exc | RS\20\007\B | RS | 20 | 7 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-01-18 21:28 | 2022-01-19 04:31 | 8885.6914 | [6 empty] | 8886 | 6344 | 1.34 | 0 | 0 | 9.07 | 5586
TS5500Exc | SC\57\002\D | SC | 57 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2022-01-19 04:31 | 2022-01-31 08:58 | 258642.0294 |  |  | 258642 | [5 empty] | 0 | 0 | 0 | 6.28 | 5858.91
DRE2 | GG\12\011\D | GG | 12 | 11 | D | 6 DL | 100 | 100 | 100 | 2022-01-19 14:59 | 2022-01-26 02:37 | 509563.341 |  |  |  | 9247 | 509563 | 221928 |  |  | 0 | 23.13 | 0 | 6.11 | 5851.29
TS6060#1 | GG\14\003\B | GG | 14 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-01-20 01:42 | 2022-01-21 14:54 | 50345.1755 | [6 empty] | 50345 | 36951 | 3.72 | 0 | 0 | 10.35 | 5471
TS5500Shv | MW\38\008\D | MW | 38 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-01-20 01:56 | 2022-01-22 04:58 | 62224.6822 | [6 empty] | 62225 | 47243 | 4.72 | 0 | 0 | 5.47 | 5932
DRE1 | RS\17\007\D | RS | 17 | 7 | D | 6 DL | 100 | 100 | 100 | 2022-01-20 12:24 | 2022-01-23 21:34 | 253290.0103 |  |  |  | 9242 | 253290 | 142958 |  |  | 0 | 28.31 | 0 | 8.43 | 5676.99
TS Fleet 5 | SC\59\002\D | SC | 59 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-01-21 10:33 | 2022-02-19 06:43 | 1356654.588 | 1356655 | [7 empty] | 0 | 0 | 29.55 | 6.03 | 5884.46
TS6060#1 | GG\13\005\B | GG | 13 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-01-21 14:54 | 2022-01-23 04:44 | 51211.4557 | [6 empty] | 51211 | 37224 | 3.72 | 0 | 0 | 11.96 | 5284
TS5500Shv | MW\38\009\D | MW | 38 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-01-22 04:58 | 2022-01-24 06:24 | 60285.5156 | [6 empty] | 60286 | 45879 | 4.59 | 0 | 0 | 5.31 | 5945
TS6060#1 | GG\14\004\X1 | GG | 14 | 4 | X1 | 8 Coal Mining | 95.9 | 0 | 95.9 | 2022-01-23 04:44 | 2022-01-23 19:30 | 19993.0337 | [6 empty] | 19993 | 14910 | 1.43 | 0 | 0 | 9.73 | 5392
TS6060#1 | RS\23\005\X | RS | 23 | 5 | X | 1 Prestrip - Thick | 70.5859 | 70.5859 | 70.5859 | 2022-01-23 19:30 | 2022-02-09 05:20 | 400066.7998 | 400067 | [7 empty] | 0 | 0 | 39.93 | 12.66 | 5177.57
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2022-01-23 21:34 | 2022-01-25 21:34
TS5500Shv | MW\38\010\D | MW | 38 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-01-24 06:24 | 2022-01-25 09:57 | 33594.1971 | [6 empty] | 33594 | 25669 | 4.46 | 0 | 0 | 5.14 | 5960
PH4100XPC#1 | GG\14\006\X1 | GG | 14 | 6 | X1 | 1 Prestrip - Thick | 100 | 67.8099 | 67.8099 | 2022-01-24 10:10 | 2022-02-01 02:11 | 414410.8103 | 414411 | [7 empty] | 0 | 0 | 40.6 | 10.72 | 5364.16
TS5500Shv | MW\43\005\B | MW | 43 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-01-25 09:57 | 2022-01-25 23:55 | 17023.6967 | [6 empty] | 17024 | 12414 | 1.25 | 0 | 0 | 11.32 | 5366
DRE1 | MW\39\003\D | MW | 39 | 3 | D | 6 DL | 100 | 100 | 100 | 2022-01-25 21:34 | 2022-01-29 18:37 | 290356.9613 |  |  |  | 12991 | 290357 | 246836 |  |  | 0 | 24.77 | 0 | 6.38 | 5852.21
TS5500Shv | GG\14\004\X1 | GG | 14 | 4 | X1 | 8 Coal Mining | 4.1 | 0 | 4.1 | 2022-01-25 23:55 | 2022-01-26 00:36 | 846.9967 | [6 empty] | 847 | 632 | 0.06 | 0 | 0 | 9.73 | 5392
TS5500Shv | GG\14\005\X1 | GG | 14 | 5 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-01-26 00:36 | 2022-01-26 08:28 | 9579.7053 | [6 empty] | 9580 | 7137 | 0.69 | 0 | 0 | 9.97 | 5386
DRE2 | GG\12\010\D | GG | 12 | 10 | D | 6 DL | 100 | 100 | 100 | 2022-01-26 02:37 | 2022-02-01 04:22 | 477142.634 |  |  |  | 11109 | 477143 | 211076 |  |  | 0 | 22.24 | 0 | 6.06 | 5856.38
TS5500Shv | RS\17\003\D | RS | 17 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-01-26 08:28 | 2022-01-27 11:44 | 33249.8617 | [6 empty] | 33250 | 24224 | 2.16 | 0 | 0 | 6.31 | 5866
TS5500Shv | GG\12\012\D | GG | 12 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-01-27 11:44 | 2022-01-29 16:15 | 64040.7303 | [6 empty] | 64041 | 47953 | 4.8 | 0 | 0 | 6.4 | 5826
PH4100A | RS\21\005\X | RS | 21 | 5 | X | 1 Prestrip - Thick | 100 | 45.5681 | 45.5681 | 2022-01-28 23:13 | 2022-02-03 22:12 | 242666.5208 | 242667 | [7 empty] | 0 | 0 | 24.19 | 12.83 | 5163.72
TS5500Shv | RS\17\005\D | RS | 17 | 5 | D | 8 Coal Mining | 21.6 | 0 | 21.6 | 2022-01-29 16:15 | 2022-01-30 02:59 | 13097.8238 | [6 empty] | 13098 | 9542 | 0.95 | 0 | 0 | 7.07 | 5799
DRE1 | MW\39\004\D | MW | 39 | 4 | D | 6 DL | 100 | 0 | 100 | 2022-01-29 18:37 | 2022-02-04 14:27 | 436380.0414 |  |  |  | 31035 | 436380 | 313794 |  |  | 0 | 35 | 0 | 6.63 | 5830.51
TS5500Shv | RS\21\003\A | RS | 21 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-01-30 02:59 | 2022-01-30 17:41 | 17921.9561 | [6 empty] | 17922 | 12423 | 1.64 | 0 | 0 | 13.72 | 5212
TS5500Shv | RS\21\004\X | RS | 21 | 4 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-01-30 17:41 | 2022-01-31 00:19 | 8096.4971 | [6 empty] | 8096 | 5648 | 0.56 | 0 | 0 | 12.71 | 5157
TS5500Shv | RS\22\003\X | RS | 22 | 3 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-01-31 00:19 | 2022-01-31 04:44 | 5375.5212 | [6 empty] | 5376 | 3759 | 0.6 | 0 | 0 | 12.5 | 5164
TS5500Shv | RS\22\004\X | RS | 22 | 4 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-01-31 04:44 | 2022-01-31 11:28 | 8213.4489 | [6 empty] | 8213 | 5736 | 0.57 | 0 | 0 | 12.63 | 5165
TS5500Exc | RS\22\004\X | RS | 22 | 4 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-01-31 08:58 | 2022-01-31 15:42 | 8484.2219 | [6 empty] | 8484 | 5925 | 0.59 | 0 | 0 | 12.63 | 5165
TS5500Shv | RS\20\007\B | RS | 20 | 7 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-01-31 11:28 | 2022-01-31 18:31 | 8602.1055 | [6 empty] | 8602 | 6142 | 1.29 | 0 | 0 | 9.07 | 5586
TS5500Exc | RS\17\006\D | RS | 17 | 6 | D | 8 Coal Mining | 66 | 0 | 66 | 2022-01-31 15:42 | 2022-02-01 23:20 | 39855.3261 | [6 empty] | 39855 | 28856 | 2.89 | 0 | 0 | 7.64 | 5749
TS5500Shv | GG\12\011\D | GG | 12 | 11 | D | 8 Coal Mining | 53.6 | 0 | 53.6 | 2022-01-31 18:31 | 2022-02-01 22:40 | 34315.643 | [6 empty] | 34316 | 25716 | 2.57 | 0 | 0 | 6.11 | 5851
PH4100XPC#1 | GG\14\004\X2 | GG | 14 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2022-02-01 02:11 | 2022-02-03 15:09 | 138008.908 | 138009 | [7 empty] | 0 | 0 | 13.35 | 0 | 0
DRE2 | GG\12\009\D | GG | 12 | 9 | D | 6 DL | 100 | 100 | 100 | 2022-02-01 04:22 | 2022-02-06 22:27 | 452095.1687 |  |  |  | 10526 | 452095 | 199996 |  |  | 0 | 21.06 | 0 | 6.35 | 5829.89
TS5500Shv | GG\14\006\X1 | GG | 14 | 6 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-02-01 22:40 | 2022-02-02 05:00 | 7721.5567 | [6 empty] | 7722 | 5723 | 0.57 | 0 | 0 | 10.72 | 5364
TS5500Exc | SC\57\002\D | SC | 57 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-02-01 23:20 | 2022-02-08 16:39 | 203184.2913 | [6 empty] | 203184 | 152817 | 4.36 | 0 | 0 | 6.28 | 5859
TS5500Shv | RS\17\006\D | RS | 17 | 6 | D | 8 Coal Mining | 34 | 0 | 34 | 2022-02-02 05:00 | 2022-02-02 21:48 | 20491.1422 | [6 empty] | 20491 | 14836 | 1.48 | 0 | 0 | 7.64 | 5749
TS5500Shv | RS\17\007\D | RS | 17 | 7 | D | 7 PostStrip | 100 | 0 | 100 | 2022-02-02 21:48 | 2022-02-04 04:15 | 32645.8972 |  |  | 32646 | [5 empty] | 0 | 0 | 0 | 8.43 | 5676.99
PH4100XPC#1 | GG\14\004\B | GG | 14 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-02-03 15:09 | 2022-02-05 21:04 | 122024.6094 | 122025 | [7 empty] | 0 | 0 | 12.13 | 11.01 | 5386.89
PH4100A | RS\22\005\X | RS | 22 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-02-03 22:12 | 2022-02-17 12:33 | 554227.4945 | 554227 | [7 empty] | 0 | 0 | 55.24 | 12.74 | 5170.77
TS5500Shv | RS\21\005\X | RS | 21 | 5 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-02-04 04:15 | 2022-02-04 10:56 | 8138.9916 | [6 empty] | 8139 | 5669 | 0.57 | 0 | 0 | 12.83 | 5164
TS5500Shv | RS\17\007\D | RS | 17 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-02-04 10:56 | 2022-02-05 19:24 | 39592.3376 | [6 empty] | 39592 | 28542 | 4.4 | 0 | 0 | 8.43 | 5677
DRE1 | MW\39\005\D | MW | 39 | 5 | D | 6 DL | 100 | 0 | 100 | 2022-02-04 14:27 | 2022-02-09 07:39 | 353199.8794 |  |  |  | 25119 | 353200 | 253980 |  |  | 0 | 35 | 0 | 6.06 | 5879.94
TS5500Shv | GG\12\010\D | GG | 12 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-02-05 19:24 | 2022-02-08 00:13 | 64415.2837 | [6 empty] | 64415 | 48234 | 4.82 | 0 | 0 | 6.06 | 5856
PH4100XPC#1 | GG\14\007\X1 | GG | 14 | 7 | X1 | 1 Prestrip - Thick | 100 | 67.7606 | 67.7606 | 2022-02-05 21:04 | 2022-02-12 21:35 | 377675.7473 | 377676 | [7 empty] | 0 | 0 | 36.33 | 10.79 | 5403.27
DRE2 | GG\12\008\D | GG | 12 | 8 | D | 6 DL | 100 | 100 | 100 | 2022-02-06 22:27 | 2022-02-12 11:10 | 434522.8211 |  |  |  | 10117 | 434523 | 192222 |  |  | 0 | 20.24 | 0 | 6.66 | 5801.64
TS5500Shv | GG\14\004\B | GG | 14 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-02-08 00:13 | 2022-02-09 17:49 | 50712.7468 | [6 empty] | 50713 | 37066 | 3.71 | 0 | 0 | 11.01 | 5387
TS5500Exc | RS\21\005\X | RS | 21 | 5 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-02-08 16:39 | 2022-02-08 23:19 | 8407.31 | [6 empty] | 8407 | 5856 | 0.59 | 0 | 0 | 12.83 | 5164
TS5500Exc | SC\58\001\D | SC | 58 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2022-02-08 23:19 | 2022-02-21 14:38 | 268242.438 |  |  | 268242 | [5 empty] | 0 | 0 | 0 | 6.22 | 5867.84
TS6060#1 | GG\14\005\X1 | GG | 14 | 5 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-02-09 05:20 | 2022-02-09 13:11 | 10632.4201 | [6 empty] | 10632 | 7922 | 0.77 | 0 | 0 | 9.97 | 5386
DRE1 | MW\39\006\D | MW | 39 | 6 | D | 6 DL | 100 | 100 | 100 | 2022-02-09 07:39 | 2022-02-13 22:34 | 346154.4516 |  |  |  | 17797 | 346154 | 278822 |  |  | 0 | 29.7 | 0 | 5.65 | 5914.87
TS6060#1 | GG\14\006\X1 | GG | 14 | 6 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-02-09 13:11 | 2022-02-09 19:31 | 8570.0794 | [6 empty] | 8570 | 6352 | 0.63 | 0 | 0 | 10.72 | 5364
TS5500Shv | MW\39\003\D | MW | 39 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-02-09 17:49 | 2022-02-11 22:32 | 64289.1595 | [6 empty] | 64289 | 48382 | 4.72 | 0 | 0 | 6.38 | 5852
TS6060#1 | RS\21\003\B | RS | 21 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-02-09 19:31 | 2022-02-10 14:09 | 19231.8018 | 19232 | [7 empty] | 0 | 0 | 2.49 | 8.79 | 5631.24
TS6060#1 | GG\12\011\D | GG | 12 | 11 | D | 8 Coal Mining | 46.4 | 0 | 46.4 | 2022-02-10 14:09 | 2022-02-11 12:09 | 29754.5515 | [6 empty] | 29755 | 22298 | 2.23 | 0 | 0 | 6.11 | 5851
TS6060#1 | RS\21\004\A | RS | 21 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-02-11 12:09 | 2022-02-19 14:47 | 200837.4685 | 200837 | [7 empty] | 0 | 0 | 20 | 17.15 | 4912.7
TS5500Shv | RS\21\003\B | RS | 21 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-02-11 22:32 | 2022-02-12 10:54 | 15079.3805 | [6 empty] | 15079 | 10748 | 1.36 | 0 | 0 | 8.79 | 5631
TS5500Shv | MW\39\004\D | MW | 39 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-02-12 10:54 | 2022-02-14 14:08 | 62467.7114 | [6 empty] | 62468 | 46823 | 4.68 | 0 | 0 | 6.63 | 5831
DRE2 | GG\12\007\D | GG | 12 | 7 | D | 6 DL | 100 | 100 | 100 | 2022-02-12 11:10 | 2022-02-17 21:36 | 427057.7829 |  |  |  | 7953 | 427058 | 190864 |  |  | 0 | 19.89 | 0 | 6.54 | 5812.43
PH4100XPC#1 | GG\14\005\X2 | GG | 14 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2022-02-12 21:35 | 2022-02-14 23:28 | 112916.645 | 112917 | [7 empty] | 0 | 0 | 10.9 | 0 | 0
DRE1 | MW\39\007\D | MW | 39 | 7 | D | 6 DL | 100 | 100 | 100 | 2022-02-13 22:34 | 2022-02-18 13:29 | 346089.0932 |  |  |  | 17794 | 346089 | 278769 |  |  | 0 | 29.67 | 0 | 5.49 | 5929.59
TS5500Shv | GG\14\007\X1 | GG | 14 | 7 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-02-14 14:08 | 2022-02-14 20:32 | 7803.1876 | [6 empty] | 7803 | 5771 | 0.57 | 0 | 0 | 10.79 | 5403
TS5500Shv | GG\12\008\D | GG | 12 | 8 | D | 8 Coal Mining | 29.4 | 0 | 29.4 | 2022-02-14 20:32 | 2022-02-15 11:30 | 18250.8871 | [6 empty] | 18251 | 13601 | 1.36 | 0 | 0 | 6.66 | 5802
PH4100XPC#1 | GG\14\005\B | GG | 14 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-02-14 23:28 | 2022-02-15 00:46 | 2933.4212 | 2933 | [7 empty] | 0 | 0 | 0.29 | 11.69 | 5308.72
PH4100XPC#1 | GG\14\006\X2 | GG | 14 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2022-02-15 00:46 | 2022-02-16 20:05 | 98068.168 | 98068 | [7 empty] | 0 | 0 | 9.73 | 0 | 0
TS5500Shv | MW\39\005\D | MW | 39 | 5 | D | 8 Coal Mining | 75.3 | 0 | 75.3 | 2022-02-15 11:30 | 2022-02-17 01:05 | 45835.918 | [6 empty] | 45836 | 34547 | 3.45 | 0 | 0 | 6.06 | 5880
PH4100XPC#1 | GG\14\006\B | GG | 14 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-02-16 20:05 | 2022-02-17 10:47 | 33275.4118 | 33275 | [7 empty] | 0 | 0 | 3.37 | 10.72 | 5384.93
TS5500Shv | MW\39\006\D | MW | 39 | 6 | D | 8 Coal Mining | 56 | 0 | 56 | 2022-02-17 01:05 | 2022-02-18 04:15 | 33130.8095 | [6 empty] | 33131 | 25050 | 2.5 | 0 | 0 | 5.65 | 5915
PH4100XPC#1 | GG\14\008\X1 | GG | 14 | 8 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-02-17 10:47 | 2022-02-26 11:47 | 485264.4578 | 485264 | [7 empty] | 0 | 0 | 47.66 | 10.67 | 5441.23
PH4100A | RS\21\006\X | RS | 21 | 6 | X | 1 Prestrip - Thick | 100 | 79.0531 | 79.0531 | 2022-02-17 12:33 | 2022-03-07 12:26 | 734852.066 | 734852 | [7 empty] | 0 | 0 | 47.97 | 12 | 5219.63
DRE2 | GG\12\006\D | GG | 12 | 6 | D | 6 DL | 100 | 100 | 100 | 2022-02-17 21:36 | 2022-02-23 09:08 | 430650.5092 |  |  |  | 10027 | 430651 | 190509 |  |  | 0 | 20.06 | 0 | 6.5 | 5816.9
TS5500Shv | GG\12\007\D | GG | 12 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-02-18 04:15 | 2022-02-20 07:48 | 62862.8901 | [6 empty] | 62863 | 46996 | 4.7 | 0 | 0 | 6.54 | 5812
DRE1 | MW\39\008\D | MW | 39 | 8 | D | 6 DL | 100 | 100 | 100 | 2022-02-18 13:29 | 2022-02-23 03:24 | 343029.5557 |  |  |  | 17636 | 343030 | 276305 |  |  | 0 | 29.42 | 0 | 5.41 | 5937.76
TS Fleet 5 | SC\60\001\D | SC | 60 | 1 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-02-19 06:43 | 2022-03-27 14:05 | 1707869.633 | 1707870 | [7 empty] | 0 | 0 | 35.8 | 6.56 | 5837.06
TS6060#1 | GG\14\007\X1 | GG | 14 | 7 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-02-19 14:47 | 2022-02-19 21:11 | 8660.6808 | [6 empty] | 8661 | 6405 | 0.63 | 0 | 0 | 10.79 | 5403
TS6060#1 | RS\21\005\A | RS | 21 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-02-19 21:11 | 2022-02-27 12:30 | 189140.1609 | 189140 | [7 empty] | 0 | 0 | 18.91 | 20.12 | 4658.57
TS5500Shv | RS\21\004\A | RS | 21 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-02-20 07:48 | 2022-02-21 03:18 | 23775.3908 | [6 empty] | 23775 | 16119 | 1.6 | 0 | 0 | 17.15 | 4913
TS5500Shv | MW\39\007\D | MW | 39 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-02-21 03:18 | 2022-02-23 05:09 | 60780.962 | [6 empty] | 60781 | 46070 | 4.61 | 0 | 0 | 5.49 | 5930
TS5500Exc | RS\22\005\X | RS | 22 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-02-21 14:38 | 2022-02-22 03:56 | 16758.2762 | [6 empty] | 16758 | 11684 | 1.17 | 0 | 0 | 12.74 | 5171
TS5500Exc | RS\21\003\B | RS | 21 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-02-22 03:56 | 2022-02-22 16:18 | 15576.5029 | [6 empty] | 15577 | 11102 | 1.41 | 0 | 0 | 8.79 | 5631
TS5500Exc | MW\39\005\D | MW | 39 | 5 | D | 8 Coal Mining | 24.7 | 0 | 24.7 | 2022-02-22 16:18 | 2022-02-23 04:13 | 15016.0028 | [6 empty] | 15016 | 11318 | 1.13 | 0 | 0 | 6.06 | 5880
DRE1 | MW\39\009\D | MW | 39 | 9 | D | 6 DL | 100 | 100 | 100 | 2022-02-23 03:24 | 2022-02-27 12:48 | 328896.5965 |  |  |  | 16910 | 328897 | 264921 |  |  | 0 | 28.2 | 0 | 5.27 | 5949.17
TS5500Exc | RS\21\004\A | RS | 21 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-02-23 04:13 | 2022-02-23 23:43 | 24559.1949 | [6 empty] | 24559 | 16650 | 1.66 | 0 | 0 | 17.15 | 4913
TS5500Shv | MW\39\008\D | MW | 39 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-02-23 05:09 | 2022-02-25 08:22 | 62449.8039 | [6 empty] | 62450 | 47414 | 4.74 | 0 | 0 | 5.41 | 5938
DRE2 | GG\12\005\D | GG | 12 | 5 | D | 6 DL | 100 | 100 | 100 | 2022-02-23 09:08 | 2022-02-28 19:03 | 425382.349 |  |  |  | 10287 | 425382 | 195460 |  |  | 0 | 20.58 | 0 | 6.45 | 5819.09
TS5500Exc | MW\39\006\D | MW | 39 | 6 | D | 8 Coal Mining | 44 | 0 | 44 | 2022-02-23 23:43 | 2022-02-24 20:24 | 26052.7638 | [6 empty] | 26053 | 19698 | 1.97 | 0 | 0 | 5.65 | 5915
TS5500Exc | SC\58\001\D | SC | 58 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-02-24 20:24 | 2022-03-07 06:09 | 314574.707 | [6 empty] | 314575 | 236991 | 4.93 | 0 | 0 | 6.22 | 5868
TS5500Shv | GG\15\012\X2 | GG | 15 | 12 | X2 | 1 Prestrip - Thick | 1.278 | 0 | 1.278 | 2022-02-25 08:22 | 2022-02-25 12:57 | 4885.439 | 4885 | [7 empty] | 0 | 0 | 0.46 | 0 | 0
TS5500Shv | GG\16\003\X1 | GG | 16 | 3 | X1 | 1 Prestrip - Thick | 2.8059 | 2.8059 | 2.8059 | 2022-02-25 12:57 | 2022-02-27 03:47 | 41445.98 | 41446 | [7 empty] | 0 | 0 | 2.54 | 10.11 | 5350.69
PH4100XPC#1 | GG\14\007\X2 | GG | 14 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2022-02-26 11:47 | 2022-02-28 07:33 | 99064.167 | 99064 | [7 empty] | 0 | 0 | 9.75 | 0 | 0
TS5500Shv | GG\14\008\X1 | GG | 14 | 8 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-02-27 03:47 | 2022-02-27 10:14 | 7869.5569 | [6 empty] | 7870 | 5818 | 0.58 | 0 | 0 | 10.67 | 5441
TS5500Shv | GG\16\011\X2 | GG | 16 | 11 | X2 | 1 Prestrip - Thick | 17.7166 | 0 | 17.7166 | 2022-02-27 10:14 | 2022-03-02 18:20 | 85565.5206 | 85566 | [7 empty] | 0 | 0 | 8.38 | 0 | 0
TS6060#1 | GG\14\008\X1 | GG | 14 | 8 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-02-27 12:30 | 2022-02-27 18:57 | 8734.3434 | [6 empty] | 8734 | 6457 | 0.65 | 0 | 0 | 10.67 | 5441
DRE1 | MW\39\010\D | MW | 39 | 10 | D | 6 DL | 100 | 100 | 100 | 2022-02-27 12:48 | 2022-03-01 22:08 | 178896.5835 |  |  |  | 6605 | 178897 | 101246 |  |  | 0 | 27.24 | 0 | 5.11 | 5962.3
TS6060#1 | GG\12\009\D | GG | 12 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-02-27 18:57 | 2022-03-01 17:48 | 63398.5637 | [6 empty] | 63399 | 47359 | 4.74 | 0 | 0 | 6.35 | 5830
PH4100XPC#1 | GG\14\007\B | GG | 14 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-02-28 07:33 | 2022-03-01 06:15 | 51370.3361 | 51370 | [7 empty] | 0 | 0 | 5.17 | 10.41 | 5443.55
DRE2 | GG\12\004\D | GG | 12 | 4 | D | 6 DL | 100 | 100 | 100 | 2022-02-28 19:03 | 2022-03-03 15:59 | 225642.7346 |  |  |  | 10096 | 225643 | 191822 |  |  | 0 | 20.2 | 0 | 6.32 | 5829.87
PH4100XPC#1 | GG\14\008\X2 | GG | 14 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 95.7381 | 2022-03-01 06:15 | 2022-03-02 22:05 | 90160.7494 | 90161 | [7 empty] | 0 | 0 | 9.01 | 0 | 0
TS6060#1 | GG\12\008\D | GG | 12 | 8 | D | 8 Coal Mining | 70.6 | 0 | 70.6 | 2022-03-01 17:48 | 2022-03-03 02:15 | 43928.8107 | [6 empty] | 43929 | 32736 | 3.27 | 0 | 0 | 6.66 | 5802
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2022-03-01 22:08 | 2022-03-03 22:08
TS5500Shv | GG\14\008\X2 | GG | 14 | 8 | X2 | 1 Prestrip - Thick | 29.1664 | 0 | 4.2619 | 2022-03-02 18:20 | 2022-03-02 22:05 | 4013.6456 | 4014 | [7 empty] | 0 | 0 | 0.4 | 0 | 0
PH4100XPC#1 | GG\14\008\B | GG | 14 | 8 | B | 1 Prestrip - Thick | 100 | 67.8611 | 67.8611 | 2022-03-02 22:05 | 2022-03-03 15:51 | 40207.1299 | 40207 | [7 empty] | 0 | 0 | 4.02 | 10.33 | 5483.49
TS5500Shv | GG\14\008\B | GG | 14 | 8 | B | 1 Prestrip - Thick | 32.1389 | 32.1389 | 32.1389 | 2022-03-02 22:05 | 2022-03-03 15:51 | 19042.0421 | 19042 | [7 empty] | 0 | 0 | 1.91 | 10.33 | 5483.49
TS6060#1 | GG\12\006\D | GG | 12 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-03-03 02:15 | 2022-03-05 00:56 | 63172.3312 | [6 empty] | 63172 | 47302 | 4.73 | 0 | 0 | 6.5 | 5817
PH4100XPC#1 | GG\14\009\X1 | GG | 14 | 9 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-03-03 15:51 | 2022-03-12 05:59 | 462121.4636 | 462121 | [7 empty] | 0 | 0 | 45.34 | 11.47 | 5384.34
TS5500Shv | MW\39\009\D | MW | 39 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-03-03 15:51 | 2022-03-05 17:21 | 60363.9354 | [6 empty] | 60364 | 45976 | 4.6 | 0 | 0 | 5.27 | 5949
DRE2 | GG\12\003\D | GG | 12 | 3 | D | 6 DL | 100 | 100 | 100 | 2022-03-03 15:59 | 2022-03-08 23:10 | 416409.4263 |  |  |  | 7754 | 416409 | 186105 |  |  | 0 | 19.4 | 0 | 6.18 | 5842.65
DRE1 | RS\18\003\D | RS | 18 | 3 | D | 6 DL | 100 | 100 | 100 | 2022-03-03 22:08 | 2022-03-09 00:45 | 382645.8142 |  |  |  | 19673 | 382646 | 308215 |  |  | 0 | 29.35 | 0 | 6.26 | 5870.18
TS6060#1 | RS\21\004\B | RS | 21 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-03-05 00:56 | 2022-03-06 00:37 | 24430.0889 | 24430 | [7 empty] | 0 | 0 | 2.43 | 9.02 | 5592.07
TS5500Shv | GG\12\004\D | GG | 12 | 4 | D | 8 Coal Mining | 43.3 | 0 | 43.3 | 2022-03-05 17:21 | 2022-03-06 14:58 | 26355.1892 | [6 empty] | 26355 | 19765 | 1.98 | 0 | 0 | 6.32 | 5830
TS6060#1 | GG\12\005\D | GG | 12 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-03-06 00:37 | 2022-03-07 22:05 | 61537.324 | [6 empty] | 61537 | 46113 | 4.61 | 0 | 0 | 6.45 | 5819
TS5500Shv | RS\21\004\B | RS | 21 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-03-06 14:58 | 2022-03-07 22:22 | 38297.1782 | [6 empty] | 38297 | 27313 | 2.72 | 0 | 0 | 9.02 | 5592
TS5500Exc | RS\21\005\A | RS | 21 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-03-07 06:09 | 2022-03-08 21:52 | 50031.9508 | [6 empty] | 50032 | 33287 | 3.33 | 0 | 0 | 20.12 | 4659
PH4100A | RS\22\006\X | RS | 22 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-03-07 12:26 | 2022-03-29 08:46 | 893115.1716 | 893115 | [7 empty] | 0 | 0 | 62.27 | 12.3 | 5199.62
TS6060#1 | GG\12\004\D | GG | 12 | 4 | D | 8 Coal Mining | 56.7 | 0 | 56.7 | 2022-03-07 22:05 | 2022-03-08 23:34 | 34500.912 | [6 empty] | 34501 | 25873 | 2.59 | 0 | 0 | 6.32 | 5830
TS5500Shv | RS\21\006\X | RS | 21 | 6 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-03-07 22:22 | 2022-03-08 08:20 | 12161.5577 | [6 empty] | 12162 | 8546 | 0.57 | 0 | 0 | 12 | 5220
TS5500Shv | MW\39\010\D | MW | 39 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2022-03-08 08:20 | 2022-03-09 06:58 | 24249.9701 |  |  | 24250 | [5 empty] | 0 | 0 | 0 | 5.11 | 5962.3
TS5500Exc | RS\21\006\X | RS | 21 | 6 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-03-08 21:52 | 2022-03-09 07:50 | 12562.4882 | [6 empty] | 12562 | 8828 | 0.59 | 0 | 0 | 12 | 5220
DRE2 | GG\12\002\D | GG | 12 | 2 | D | 6 DL | 100 | 100 | 100 | 2022-03-08 23:10 | 2022-03-13 10:50 | 352545.4576 |  |  |  | 5869 | 352545 | 101594 |  |  | 0 | 18.69 | 0 | 6.18 | 5844.07
TS6060#1 | RS\21\005\B | RS | 21 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-03-08 23:34 | 2022-03-10 00:56 | 26177.6544 | 26178 | [7 empty] | 0 | 0 | 2.62 | 9.17 | 5566.02
DRE1 | RS\18\004\D | RS | 18 | 4 | D | 6 DL | 100 | 100 | 100 | 2022-03-09 00:45 | 2022-03-13 13:52 | 340490.8029 |  |  |  | 17506 | 340491 | 274260 |  |  | 0 | 29.17 | 0 | 6.71 | 5830.72
TS5500Shv | MW\39\010\D | MW | 39 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-03-09 06:58 | 2022-03-10 05:26 | 27410.6011 | [6 empty] | 27411 | 20945 | 4.46 | 0 | 0 | 5.11 | 5962
TS5500Exc | RS\18\003\D | RS | 18 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-03-09 07:50 | 2022-03-11 13:34 | 67676.004 | [6 empty] | 67676 | 49342 | 4.39 | 0 | 0 | 6.26 | 5870
TS6060#1 | RS\21\006\A | RS | 21 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-03-10 00:56 | 2022-03-20 06:16 | 253134.3701 | 253134 | [7 empty] | 0 | 0 | 18.19 | 19.99 | 4674.76
TS5500Shv | GG\12\003\D | GG | 12 | 3 | D | 8 Coal Mining | 31.3 | 0 | 31.3 | 2022-03-10 05:26 | 2022-03-10 21:04 | 19061.5564 | [6 empty] | 19062 | 14295 | 1.43 | 0 | 0 | 6.18 | 5843
TS5500Shv | RS\21\005\B | RS | 21 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-03-10 21:04 | 2022-03-12 03:14 | 36778.6987 | [6 empty] | 36779 | 26223 | 2.62 | 0 | 0 | 9.17 | 5566
TS5500Exc | SC\58\002\D | SC | 58 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2022-03-11 13:34 | 2022-03-24 16:47 | 278773.6504 |  |  | 278774 | [5 empty] | 0 | 0 | 0 | 6.26 | 5864.51
TS5500Shv | GG\16\020\B | GG | 16 | 20 | B | 1 Prestrip - Thick | 20.1701 | 20.1701 | 20.1701 | 2022-03-12 03:14 | 2022-03-15 03:00 | 77248.3161 | 77248 | [7 empty] | 0 | 0 | 7.44 | 15.24 | 5127.95
PH4100XPC#1 | GG\14\010\B | GG | 14 | 10 | B | 1 Prestrip - Thick | 100 | 73.5631 | 73.5631 | 2022-03-12 05:59 | 2022-03-20 08:17 | 447509.9646 | 447510 | [7 empty] | 0 | 0 | 45.35 | 9.3 | 5561.57
DRE2 | GG\13\013\B | GG | 13 | 13 | B | 6 DL | 100 | 0 | 100 | 2022-03-13 10:50 | 2022-03-15 10:38 | 156476.9774 |  |  |  |  | 156477 | 130397 |  |  | 0 | 16.52 | 0 | 10.91 | 5443.1
DRE1 | RS\18\005\D | RS | 18 | 5 | D | 6 DL | 100 | 100 | 100 | 2022-03-13 13:52 | 2022-03-18 00:09 | 331661.6563 |  |  |  | 17052 | 331662 | 267148 |  |  | 0 | 28.41 | 0 | 7.07 | 5799.48
TS5500Shv | GG\14\009\X1 | GG | 14 | 9 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-03-15 03:00 | 2022-03-15 09:33 | 7993.6157 | [6 empty] | 7994 | 5868 | 0.59 | 0 | 0 | 11.47 | 5384
TS5500Shv | GG\12\002\D | GG | 12 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2022-03-15 09:33 | 2022-03-16 22:11 | 39258.2688 |  |  | 39258 | [5 empty] | 0 | 0 | 0 | 6.18 | 5844.07
DRE2 | GG\13\018\B | GG | 13 | 18 | B | 6 DL | 100 | 0 | 100 | 2022-03-15 10:38 | 2022-03-17 14:48 | 170805.7687 |  |  |  |  | 170806 | 142338 |  |  | 0 | 16.97 | 0 | 10.84 | 5448.61
TS5500Shv | GG\12\002\D | GG | 12 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-03-16 22:11 | 2022-03-18 14:02 | 48612.859 | [6 empty] | 48613 | 36458 | 4.69 | 0 | 0 | 6.18 | 5844
DRE2 | GG\13\019\B | GG | 13 | 19 | B | 6 DL | 100 | 0 | 100 | 2022-03-17 14:48 | 2022-03-20 11:18 | 224250.7465 |  |  |  |  | 224251 | 186876 |  |  | 0 | 17.6 | 0 | 11.21 | 5428.63
DRE1 | RS\18\006\D | RS | 18 | 6 | D | 6 DL | 100 | 100 | 100 | 2022-03-18 00:09 | 2022-03-22 09:29 | 328698.4357 |  |  |  | 16900 | 328698 | 264761 |  |  | 0 | 28.16 | 0 | 7.53 | 5758.43
TS5500Shv | GG\13\013\B | GG | 13 | 13 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-03-18 14:02 | 2022-03-19 16:29 | 32247.035 | [6 empty] | 32247 | 23559 | 3.01 | 0 | 0 | 10.91 | 5443
TS5500Shv | GG\13\018\B | GG | 13 | 18 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-03-19 16:29 | 2022-03-20 23:21 | 37634.1643 | [6 empty] | 37634 | 27502 | 3.42 | 0 | 0 | 10.84 | 5449
TS6060#1 | GG\14\009\X1 | GG | 14 | 9 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-03-20 06:16 | 2022-03-20 12:50 | 8872.035 | [6 empty] | 8872 | 6513 | 0.65 | 0 | 0 | 11.47 | 5384
PH4100XPC#1 | GG\14\011\B | GG | 14 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-03-20 08:17 | 2022-03-30 17:14 | 580696.1268 | 580696 | [7 empty] | 0 | 0 | 50.06 | 9.75 | 5531.02
DRE2 | GG\13\020\B | GG | 13 | 20 | B | 6 DL | 100 | 0 | 100 | 2022-03-20 11:18 | 2022-03-23 02:20 | 206368.8212 |  |  |  |  | 206369 | 171974 |  |  | 0 | 19.17 | 0 | 13.09 | 5299.15
TS6060#1 | GG\12\003\D | GG | 12 | 3 | D | 8 Coal Mining | 68.7 | 0 | 68.7 | 2022-03-20 12:50 | 2022-03-21 19:44 | 41827.9849 | [6 empty] | 41828 | 31368 | 3.14 | 0 | 0 | 6.18 | 5843
TS5500Shv | RS\21\006\A | RS | 21 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-03-20 23:21 | 2022-03-23 07:46 | 68797.1202 | [6 empty] | 68797 | 46069 | 3.34 | 0 | 0 | 19.99 | 4675
TS6060#1 | GG\13\019\B | GG | 13 | 19 | B | 8 Coal Mining | 65.7 | 0 | 65.7 | 2022-03-21 19:44 | 2022-03-22 21:30 | 34877.9402 | [6 empty] | 34878 | 25407 | 2.53 | 0 | 0 | 11.21 | 5429
DRE1 | RS\18\007\D | RS | 18 | 7 | D | 6 DL | 100 | 100 | 100 | 2022-03-22 09:29 | 2022-03-25 06:44 | 216109.9084 |  |  |  | 7879 | 216110 | 121949 |  |  | 0 | 28.39 | 0 | 8.2 | 5696.77
TS6060#1 | RS\23\006\X | RS | 23 | 6 | X | 1 Prestrip - Thick | 34.4445 | 34.4445 | 34.4445 | 2022-03-22 21:30 | 2022-04-04 02:41 | 298470.2158 | 298470 | [7 empty] | 0 | 0 | 21.99 | 12.56 | 5183.35
DRE2 | GG\13\021\B | GG | 13 | 21 | B | 6 DL | 100 | 0 | 100 | 2022-03-23 02:20 | 2022-03-26 07:59 | 254236.553 |  |  |  |  | 254237 | 195567 |  |  | 0 | 20.26 | 0 | 14.27 | 5221.57
TS5500Shv | RS\18\004\D | RS | 18 | 4 | D | 8 Coal Mining | 57.1 | 0 | 57.1 | 2022-03-23 07:46 | 2022-03-24 12:10 | 34625.1781 | [6 empty] | 34625 | 25286 | 2.53 | 0 | 0 | 6.71 | 5831
TS5500Shv | GG\13\019\B | GG | 13 | 19 | B | 8 Coal Mining | 34.3 | 0 | 34.3 | 2022-03-24 12:10 | 2022-03-25 03:07 | 18226.0249 | [6 empty] | 18226 | 13277 | 1.32 | 0 | 0 | 11.21 | 5429
TS5500Exc | RS\18\004\D | RS | 18 | 4 | D | 8 Coal Mining | 42.9 | 0 | 42.9 | 2022-03-24 16:47 | 2022-03-25 13:28 | 26061.4488 | [6 empty] | 26061 | 19032 | 1.9 | 0 | 0 | 6.71 | 5831
TS5500Shv | GG\13\020\B | GG | 13 | 20 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-03-25 03:07 | 2022-03-26 22:45 | 53207.108 | [6 empty] | 53207 | 38239 | 3.82 | 0 | 0 | 13.09 | 5299
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2022-03-25 06:44 | 2022-03-27 06:44
TS5500Exc | RS\18\005\D | RS | 18 | 5 | D | 8 Coal Mining | 43.6 | 0 | 43.6 | 2022-03-25 13:28 | 2022-03-26 10:19 | 26258.1627 | [6 empty] | 26258 | 19130 | 1.91 | 0 | 0 | 7.07 | 5799
DRE2 | GG\13\022\B | GG | 13 | 22 | B | 6 DL | 100 | 0 | 100 | 2022-03-26 07:59 | 2022-03-29 08:26 | 237238.2869 |  |  |  |  | 237238 | 197699 |  |  | 0 | 19.81 | 0 | 15.51 | 5110.96
TS5500Exc | SC\58\002\D | SC | 58 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-03-26 10:19 | 2022-04-05 10:58 | 303126.3455 | [6 empty] | 303126 | 228185 | 4.93 | 0 | 0 | 6.26 | 5865
TS5500Shv | RS\18\005\D | RS | 18 | 5 | D | 8 Coal Mining | 56.4 | 0 | 56.4 | 2022-03-26 22:45 | 2022-03-28 02:38 | 34017.2399 | [6 empty] | 34017 | 24783 | 2.48 | 0 | 0 | 7.07 | 5799
DRE1 | MW\40\003\B | MW | 40 | 3 | B | 6 DL | 100 | 0 | 100 | 2022-03-27 06:44 | 2022-03-30 04:41 | 218238.3531 |  |  |  |  | 218238 | 189772 |  |  | 0 | 13.49 | 0 | 12.07 | 5295.42
TS Fleet 5 | SC\60\002\D | SC | 60 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-03-27 14:05 | 2022-05-19 21:07 | 2506909.238 | 2506909 | [7 empty] | 0 | 0 | 38.16 | 6.4 | 5850.6
TS5500Shv | GG\13\021\B | GG | 13 | 21 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-03-28 02:38 | 2022-03-29 21:17 | 51998.2166 | [6 empty] | 51998 | 37031 | 3.7 | 0 | 0 | 14.27 | 5222
DRE2 | GG\13\023\B | GG | 13 | 23 | B | 6 DL | 100 | 0 | 100 | 2022-03-29 08:26 | 2022-03-31 22:50 | 204266.8239 |  |  |  |  | 204267 | 170222 |  |  | 0 | 17.69 | 0 | 12.21 | 5326.75
PH4100A | RS\22\003\A | RS | 22 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-03-29 08:46 | 2022-04-01 13:16 | 132803.3181 | 132803 | [7 empty] | 0 | 0 | 19.42 | 13.77 | 5205.3
TS5500Shv | RS\18\006\D | RS | 18 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-03-29 21:17 | 2022-03-31 22:38 | 60185.4797 | [6 empty] | 60185 | 43609 | 4.36 | 0 | 0 | 7.53 | 5758
DRE1 | MW\40\004\D | MW | 40 | 4 | D | 6 DL | 100 | 0 | 100 | 2022-03-30 04:41 | 2022-04-04 07:53 | 384487.3966 |  |  |  | 27344 | 384487 | 276478 |  |  | 0 | 35 | 0 | 6.5 | 5842.15
PH4100XPC#1 | GG\14\009\X2 | GG | 14 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2022-03-30 17:14 | 2022-04-01 08:46 | 89465.334 | 89465 | [7 empty] | 0 | 0 | 8.95 | 0 | 0
TS5500Shv | GG\13\022\B | GG | 13 | 22 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-03-31 22:38 | 2022-04-02 17:52 | 52720.4845 | [6 empty] | 52720 | 37340 | 3.74 | 0 | 0 | 15.51 | 5111
DRE2 | GG\13\024\B | GG | 13 | 24 | B | 6 DL | 100 | 0 | 100 | 2022-03-31 22:50 | 2022-04-03 05:09 | 177857.7808 |  |  |  |  | 177858 | 136814 |  |  | 0 | 20.91 | 0 | 0 | 0
PH4100XPC#1 | GG\14\009\B | GG | 14 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-01 08:46 | 2022-04-02 16:43 | 72337.185 | 72337 | [7 empty] | 0 | 0 | 7.22 | 9.67 | 5537.41
PH4100A | RS\22\004\A | RS | 22 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-01 13:16 | 2022-04-06 06:40 | 196866.1998 | 196866 | [7 empty] | 0 | 0 | 19.65 | 16.78 | 4943.62
PH4100XPC#1 | GG\14\012\B | GG | 14 | 12 | B | 1 Prestrip - Thick | 100 | 71.0402 | 71.0402 | 2022-04-02 16:43 | 2022-04-09 08:02 | 363533.5472 | 363534 | [7 empty] | 0 | 0 | 31.74 | 10.36 | 5485.76
TS5500Shv | RS\22\003\A | RS | 22 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-04-02 17:52 | 2022-04-03 08:56 | 18354.3912 | [6 empty] | 18354 | 12727 | 1.7 | 0 | 0 | 13.77 | 5205
DRE2 | GG\12\013\D | GG | 12 | 13 | D | 6 DL | 100 | 100 | 100 | 2022-04-03 05:09 | 2022-04-07 10:34 | 332014.5523 |  |  |  | 7730 | 332015 | 146875 |  |  | 0 | 23.28 | 0 | 6.72 | 5798.15
TS5500Shv | RS\18\007\D | RS | 18 | 7 | D | 7 PostStrip | 100 | 0 | 100 | 2022-04-03 08:56 | 2022-04-04 10:49 | 27748.5941 |  |  | 27749 | [5 empty] | 0 | 0 | 0 | 8.2 | 5696.77
TS6060#1 | RS\21\006\B | RS | 21 | 6 | B | 1 Prestrip - Thick | 37.2787 | 37.2787 | 37.2787 | 2022-04-04 02:41 | 2022-04-04 16:46 | 14526.8353 | 14527 | [7 empty] | 0 | 0 | 1.05 | 9.08 | 5580.98
DRE1 | MW\40\005\D | MW | 40 | 5 | D | 6 DL | 100 | 0 | 100 | 2022-04-04 07:53 | 2022-04-09 21:01 | 415414.3594 |  |  |  | 23709 | 415414 | 314990 |  |  | 0 | 34.02 | 0 | 5.97 | 5887.96
TS5500Shv | GG\13\023\B | GG | 13 | 23 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-04-04 10:49 | 2022-04-05 19:43 | 40122.0923 | [6 empty] | 40122 | 29036 | 2.92 | 0 | 0 | 12.21 | 5327
TS6060#1 | RS\25\003\X | RS | 25 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-04 16:46 | 2022-04-12 17:27 | 195577.5263 | 195578 | [7 empty] | 0 | 0 | 39.68 | 12.35 | 5191.52
TS5500Exc | RS\22\006\X | RS | 22 | 6 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-04-05 10:58 | 2022-04-06 05:17 | 23073.6125 | [6 empty] | 23074 | 16169 | 1.17 | 0 | 0 | 12.3 | 5200
TS5500Shv | RS\18\007\D | RS | 18 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-04-05 19:43 | 2022-04-06 23:02 | 33309.3713 | [6 empty] | 33309 | 24046 | 4.37 | 0 | 0 | 8.2 | 5697
TS5500Exc | RS\22\006\A | RS | 22 | 6 | A | 1 Prestrip - Thick | 100 | 60.9751 | 60.9751 | 2022-04-06 05:17 | 2022-04-12 21:15 | 141469.1555 | 141469 | [7 empty] | 0 | 0 | 10.94 | 20.14 | 4668.29
PH4100A | RS\22\005\A | RS | 22 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-06 06:40 | 2022-04-10 19:21 | 188654.0551 | 188654 | [7 empty] | 0 | 0 | 18.87 | 19.91 | 4681.09
TS5500Shv | RS\22\004\A | RS | 22 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-04-06 23:02 | 2022-04-07 19:07 | 24500.1836 | [6 empty] | 24500 | 16657 | 1.66 | 0 | 0 | 16.78 | 4944
DRE2 | GG\12\018\D | GG | 12 | 18 | D | 6 DL | 100 | 100 | 100 | 2022-04-07 10:34 | 2022-04-11 16:01 | 332164.3333 |  |  |  | 7734 | 332164 | 146941 |  |  | 0 | 22.66 | 0 | 6.74 | 5796.17
TS5500Shv | MW\40\003\B | MW | 40 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-04-07 19:07 | 2022-04-08 12:50 | 21604.7829 | [6 empty] | 21605 | 15682 | 1.12 | 0 | 0 | 12.07 | 5295
TS5500Shv | GG\12\013\D | GG | 12 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-04-08 12:50 | 2022-04-09 23:35 | 42365.6193 | [6 empty] | 42366 | 31648 | 4.82 | 0 | 0 | 6.72 | 5798
PH4100XPC#1 | GG\14\013\B | GG | 14 | 13 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-09 08:02 | 2022-04-17 08:08 | 442192.7375 | 442193 | [7 empty] | 0 | 0 | 46.7 | 10.88 | 5443.94
DRE1 | MW\40\003\D | MW | 40 | 3 | D | 6 DL | 100 | 100 | 100 | 2022-04-09 21:01 | 2022-04-17 03:09 | 543383.1757 |  |  |  | 13141 | 543383 | 249680 |  |  | 0 | 21.51 | 0 | 6.35 | 5855.52
TS5500Shv | MW\40\004\D | MW | 40 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-04-09 23:35 | 2022-04-12 03:08 | 62865.5194 | [6 empty] | 62866 | 47197 | 4.72 | 0 | 0 | 6.5 | 5842
PH4100A | RS\22\006\A | RS | 22 | 6 | A | 1 Prestrip - Thick | 100 | 37.339 | 37.339 | 2022-04-10 19:21 | 2022-04-12 21:15 | 86630.7993 | 86631 | [7 empty] | 0 | 0 | 6.7 | 20.14 | 4668.29
DRE2 | GG\12\019\D | GG | 12 | 19 | D | 6 DL | 100 | 100 | 100 | 2022-04-11 16:01 | 2022-04-17 16:59 | 474623.2653 |  |  |  | 11051 | 474623 | 209961 |  |  | 0 | 22.07 | 0 | 6.55 | 5813.67
TS5500Shv | RS\22\005\A | RS | 22 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-04-12 03:08 | 2022-04-12 23:13 | 24483.7711 | [6 empty] | 24484 | 16339 | 1.63 | 0 | 0 | 19.91 | 4681
TS6060#1 | RS\22\006\A | RS | 22 | 6 | A | 1 Prestrip - Thick | 100 | 1.6859 | 1.6859 | 2022-04-12 17:27 | 2022-04-12 21:15 | 3911.5065 | 3912 | [7 empty] | 0 | 0 | 0.3 | 20.14 | 4668.29
PH4100A | RS\21\006\B | RS | 21 | 6 | B | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2022-04-12 21:15 | 2022-04-13 11:19 | 24441.351 | 24441 | [7 empty] | 0 | 0 | 1.77 | 9.08 | 5580.98
TS5500Exc | RS\22\003\A | RS | 22 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-04-12 21:15 | 2022-04-13 12:18 | 18959.481 | [6 empty] | 18959 | 13147 | 1.76 | 0 | 0 | 13.77 | 5205
TS6060#1 | GG\12\018\D | GG | 12 | 18 | D | 8 Coal Mining | 94.2 | 0 | 94.2 | 2022-04-12 21:15 | 2022-04-14 03:29 | 40931.2594 | [6 empty] | 40931 | 30576 | 4.53 | 0 | 0 | 6.74 | 5796
TS5500Shv | GG\12\018\D | GG | 12 | 18 | D | 8 Coal Mining | 5.8 | 0 | 5.8 | 2022-04-12 23:13 | 2022-04-13 01:17 | 2518.978 | [6 empty] | 2519 | 1882 | 0.28 | 0 | 0 | 6.74 | 5796
TS5500Shv | RS\25\003\X | RS | 25 | 3 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-04-13 01:17 | 2022-04-13 09:46 | 10338.0845 | [6 empty] | 10338 | 7239 | 1.21 | 0 | 0 | 12.35 | 5192
TS5500Shv | GG\16\022\B | GG | 16 | 22 | B | 1 Prestrip - Thick | 16.4077 | 16.4077 | 16.4077 | 2022-04-13 09:46 | 2022-04-15 09:27 | 51111.4835 | 51111 | [7 empty] | 0 | 0 | 5.28 | 16.7 | 5035.36
PH4100A | RS\23\003\X | RS | 23 | 3 | X | 1 Prestrip - Thick | 100 | 62.5763 | 62.5763 | 2022-04-13 11:19 | 2022-04-16 13:50 | 126113.1069 | 126113 | [7 empty] | 0 | 0 | 23.99 | 12.44 | 5172.75
TS5500Exc | RS\21\006\B | RS | 21 | 6 | B | 8 Coal Mining | 69.3 | 0 | 69.3 | 2022-04-13 12:18 | 2022-04-14 15:48 | 34650.3831 | [6 empty] | 34650 | 24756 | 1.8 | 0 | 0 | 9.08 | 5581
TS6060#1 | RS\22\003\B | RS | 22 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-14 03:29 | 2022-04-14 22:11 | 19282.9021 | 19283 | [7 empty] | 0 | 0 | 2.52 | 8.8 | 5627.08
TS5500Exc | RS\22\004\A | RS | 22 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-04-14 15:48 | 2022-04-15 11:54 | 25307.8819 | [6 empty] | 25308 | 17206 | 1.72 | 0 | 0 | 16.78 | 4944
TS6060#1 | RS\25\003\A | RS | 25 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-14 22:11 | 2022-04-20 00:54 | 126624.2795 | 126624 | [7 empty] | 0 | 0 | 19.19 | 12.71 | 5284.8
TS5500Shv | RS\21\006\B | RS | 21 | 6 | B | 8 Coal Mining | 30.7 | 0 | 30.7 | 2022-04-15 09:27 | 2022-04-15 22:01 | 15318.4948 | [6 empty] | 15318 | 10944 | 0.8 | 0 | 0 | 9.08 | 5581
TS5500Exc | RS\22\003\B | RS | 22 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-04-15 11:54 | 2022-04-16 12:00 | 30363.3454 | [6 empty] | 30363 | 21657 | 2.77 | 0 | 0 | 8.8 | 5627
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 06:07 |  | 1d 06:07 | 2022-04-15 22:01 | 2022-04-17 04:08
TS5500Exc | RS\22\005\A | RS | 22 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-04-16 12:00 | 2022-04-17 08:05 | 25290.9284 | [6 empty] | 25291 | 16878 | 1.69 | 0 | 0 | 19.91 | 4681
PH4100A | RS\22\004\B | RS | 22 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-16 13:50 | 2022-04-17 04:08 | 24829.2402 | 24829 | [7 empty] | 0 | 0 | 2.48 | 8.98 | 5595.19
DRE1 | MW\40\006\D | MW | 40 | 6 | D | 6 DL | 100 | 100 | 100 | 2022-04-17 03:09 | 2022-04-21 17:43 | 345064.4263 |  |  |  | 17741 | 345064 | 277944 |  |  | 0 | 29.62 | 0 | 5.63 | 5917.28
PH4100A | RS\24\003\X | RS | 24 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-17 04:08 | 2022-04-22 00:33 | 197732.6755 | 197733 | [7 empty] | 0 | 0 | 39.08 | 12.4 | 5182.12
TS5500Shv | RS\22\004\B | RS | 22 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-04-17 04:08 | 2022-04-18 11:31 | 38263.973 | [6 empty] | 38264 | 27328 | 2.73 | 0 | 0 | 8.98 | 5595
TS5500Exc | RS\22\006\A | RS | 22 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-04-17 08:05 | 2022-04-19 10:46 | 63841.7132 | [6 empty] | 63842 | 42747 | 3.33 | 0 | 0 | 20.14 | 4668
PH4100XPC#1 | GG\14\018\X2 | GG | 14 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2022-04-17 08:08 | 2022-04-22 08:52 | 270961.0044 | 270961 | [7 empty] | 0 | 0 | 29.02 | 0 | 0
DRE2 | GG\12\020\D | GG | 12 | 20 | D | 6 DL | 100 | 100 | 100 | 2022-04-17 16:59 | 2022-04-23 09:43 | 447677.5353 |  |  |  | 10423 | 447678 | 198041 |  |  | 0 | 20.85 | 0 | 6.36 | 5829.5
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 04:21 |  | 4d 04:21 | 2022-04-18 11:31 | 2022-04-22 15:52
TS5500Exc | RS\23\003\X | RS | 23 | 3 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-04-19 10:46 | 2022-04-19 19:16 | 10703.8141 | [6 empty] | 10704 | 7489 | 1.22 | 0 | 0 | 12.44 | 5173
TS5500Exc | MW\40\003\D | MW | 40 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-04-19 19:16 | 2022-04-22 08:02 | 76548.0674 | [6 empty] | 76548 | 57653 | 4.72 | 0 | 0 | 6.35 | 5856
TS6060#1 | RS\23\003\A | RS | 23 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-20 00:54 | 2022-04-25 07:28 | 130588.8218 | 130589 | [7 empty] | 0 | 0 | 19.32 | 13.65 | 5211.89
DRE1 | MW\40\007\D | MW | 40 | 7 | D | 6 DL | 100 | 100 | 100 | 2022-04-21 17:43 | 2022-04-26 08:25 | 345407.5263 |  |  |  | 17759 | 345408 | 278220 |  |  | 0 | 29.62 | 0 | 5.46 | 5932.52
PH4100A | RS\22\005\B | RS | 22 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-22 00:33 | 2022-04-22 15:52 | 26594.3598 | 26594 | [7 empty] | 0 | 0 | 2.66 | 9.1 | 5574.57
TS5500Exc | RS\24\003\X | RS | 24 | 3 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-04-22 08:02 | 2022-04-22 16:22 | 10489.4354 | [6 empty] | 10489 | 7342 | 1.22 | 0 | 0 | 12.4 | 5182
PH4100XPC#1 | GG\14\018\B | GG | 14 | 18 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-22 08:52 | 2022-04-24 16:50 | 126683.0801 | 126683 | [7 empty] | 0 | 0 | 13.79 | 10.7 | 5458.87
PH4100A | RS\22\006\B | RS | 22 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-22 15:52 | 2022-04-23 13:10 | 36968.4114 | 36968 | [7 empty] | 0 | 0 | 2.89 | 9.05 | 5584.8
TS5500Shv | RS\22\005\B | RS | 22 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-04-22 15:52 | 2022-04-23 21:53 | 36584.603 | [6 empty] | 36585 | 26120 | 2.61 | 0 | 0 | 9.1 | 5575
TS5500Exc | MW\40\005\D | MW | 40 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-04-22 16:22 | 2022-04-24 16:49 | 61023.0512 | [6 empty] | 61023 | 46068 | 4.61 | 0 | 0 | 5.97 | 5888
DRE2 | GG\12\021\D | GG | 12 | 21 | D | 6 DL | 100 | 100 | 100 | 2022-04-23 09:43 | 2022-04-28 19:46 | 425810.4831 |  |  |  | 7929 | 425810 | 190306 |  |  | 0 | 19.83 | 0 | 6.32 | 5832.83
PH4100A | RS\23\004\X | RS | 23 | 4 | X | 1 Prestrip - Thick | 100 | 50.8156 | 50.8156 | 2022-04-23 13:10 | 2022-04-29 07:31 | 233962.3548 | 233962 | [7 empty] | 0 | 0 | 23.43 | 12.56 | 5173.59
TS5500Shv | RS\22\006\B | RS | 22 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-04-23 21:53 | 2022-04-25 11:27 | 45808.9249 | [6 empty] | 45809 | 32748 | 2.57 | 0 | 0 | 9.05 | 5585
TS5500Exc | MW\40\006\D | MW | 40 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-04-24 16:49 | 2022-04-26 16:06 | 59565.1991 | [6 empty] | 59565 | 45038 | 4.5 | 0 | 0 | 5.63 | 5917
PH4100XPC#1 | GG\14\019\B | GG | 14 | 19 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-24 16:50 | 2022-05-01 02:33 | 348912.4234 | 348912 | [7 empty] | 0 | 0 | 33.55 | 11.26 | 5425.19
TS6060#1 | GG\12\019\D | GG | 12 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-04-25 07:28 | 2022-04-27 07:43 | 65306.3908 | [6 empty] | 65306 | 48863 | 4.89 | 0 | 0 | 6.55 | 5814
TS5500Shv | RS\23\003\A | RS | 23 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-04-25 11:27 | 2022-04-26 17:57 | 37202.0797 | [6 empty] | 37202 | 25840 | 3.48 | 0 | 0 | 13.65 | 5212
DRE1 | MW\40\008\D | MW | 40 | 8 | D | 6 DL | 100 | 100 | 100 | 2022-04-26 08:25 | 2022-04-30 21:57 | 341818.5876 |  |  |  | 17574 | 341819 | 275329 |  |  | 0 | 29.31 | 0 | 5.35 | 5943.17
TS5500Exc | MW\40\007\D | MW | 40 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-04-26 16:06 | 2022-04-28 16:43 | 61243.9402 | [6 empty] | 61244 | 46459 | 4.65 | 0 | 0 | 5.46 | 5933
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 01:49 |  | 2d 01:49 | 2022-04-26 17:57 | 2022-04-28 19:46
TS6060#1 | GG\12\020\D | GG | 12 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-04-27 07:43 | 2022-04-29 07:22 | 64495.7819 | [6 empty] | 64496 | 48294 | 4.83 | 0 | 0 | 6.36 | 5830
TS5500Exc | SC\59\001\D | SC | 59 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2022-04-28 16:43 | 2022-05-10 21:09 | 258620.8572 |  |  | 258621 | [5 empty] | 0 | 0 | 0 | 6.12 | 5876.54
DRE2 | GG\12\022\D | GG | 12 | 22 | D | 6 DL | 100 | 100 | 100 | 2022-04-28 19:46 | 2022-05-04 10:23 | 440740.7734 |  |  |  | 10262 | 440741 | 194973 |  |  | 0 | 20.54 | 0 | 6.24 | 5833.63
TS5500Shv | GG\12\021\D | GG | 12 | 21 | D | 8 Coal Mining | 52.5 | 0 | 52.5 | 2022-04-28 19:46 | 2022-04-29 23:09 | 33377.4565 | [6 empty] | 33377 | 25013 | 2.5 | 0 | 0 | 6.32 | 5833
TS6060#1 | RS\23\003\B | RS | 23 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-29 07:22 | 2022-04-30 01:59 | 19200.7588 | 19201 | [7 empty] | 0 | 0 | 2.53 | 8.81 | 5623.38
PH4100A | RS\24\004\X | RS | 24 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-04-29 07:31 | 2022-05-10 14:10 | 458609.705 | 458610 | [7 empty] | 0 | 0 | 46.12 | 12.5 | 5182.05
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 22:49 |  | 0d 22:49 | 2022-04-29 23:09 | 2022-04-30 21:57
TS6060#1 | GG\12\021\D | GG | 12 | 21 | D | 8 Coal Mining | 47.5 | 0 | 47.5 | 2022-04-30 01:59 | 2022-05-01 00:18 | 30206.8548 | [6 empty] | 30207 | 22637 | 2.26 | 0 | 0 | 6.32 | 5833
DRE1 | MW\40\009\D | MW | 40 | 9 | D | 6 DL | 100 | 100 | 100 | 2022-04-30 21:57 | 2022-05-05 06:57 | 327672.648 |  |  |  | 16847 | 327673 | 263935 |  |  | 0 | 28.1 | 0 | 5.23 | 5952.88
TS5500Shv | MW\40\008\D | MW | 40 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-04-30 21:57 | 2022-05-03 01:18 | 62622.2861 | [6 empty] | 62622 | 47584 | 4.76 | 0 | 0 | 5.35 | 5943
TS6060#1 | RS\24\003\A | RS | 24 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-05-01 00:18 | 2022-05-06 04:51 | 128503.7751 | 128504 | [7 empty] | 0 | 0 | 19.26 | 13.22 | 5245.05
PH4100XPC#1 | GG\14\020\B | GG | 14 | 20 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-05-01 02:33 | 2022-05-06 22:53 | 334474.7252 | 334475 | [7 empty] | 0 | 0 | 35.99 | 13.38 | 5279
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 09:05 |  | 1d 09:05 | 2022-05-03 01:18 | 2022-05-04 10:23
DRE2 | GG\12\023\D | GG | 12 | 23 | D | 6 DL | 100 | 100 | 100 | 2022-05-04 10:23 | 2022-05-10 14:12 | 483956.5972 |  |  |  | 11268 | 483957 | 214090 |  |  | 0 | 22.54 | 0 | 6.14 | 5840.21
TS5500Shv | GG\12\022\D | GG | 12 | 22 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-05-04 10:23 | 2022-05-05 08:31 | 26994.3656 | [6 empty] | 26994 | 20260 | 2.02 | 0 | 0 | 6.24 | 5834
DRE1 | MW\40\010\D | MW | 40 | 10 | D | 6 DL | 100 | 100 | 100 | 2022-05-05 06:57 | 2022-05-07 05:14 | 144421.1239 |  |  |  | 5329 | 144421 | 81725 |  |  | 0 | 27.28 | 0 | 5.1 | 5963.71
TS5500Shv | MW\40\009\D | MW | 40 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-05-05 08:31 | 2022-05-07 10:05 | 60440.6129 | [6 empty] | 60441 | 46072 | 4.61 | 0 | 0 | 5.23 | 5953
TS6060#1 | GG\12\022\D | GG | 12 | 22 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-05-06 04:51 | 2022-05-07 02:59 | 29960.7794 | [6 empty] | 29961 | 22487 | 2.24 | 0 | 0 | 6.24 | 5834
PH4100XPC#1 | GG\14\021\B | GG | 14 | 21 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-05-06 22:53 | 2022-05-12 11:32 | 306532.7875 | 306533 | [7 empty] | 0 | 0 | 30.56 | 14.54 | 5206.21
TS6060#1 | RS\25\004\X | RS | 25 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-05-07 02:59 | 2022-05-25 23:39 | 458740.7233 | 458741 | [7 empty] | 0 | 0 | 46.35 | 12.45 | 5190.41
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2022-05-07 05:14 | 2022-05-09 05:14
TS5500Shv | MW\40\010\D | MW | 40 | 10 | D | 7 PostStrip | 84.9322 | 0 | 84.9322 | 2022-05-07 10:05 | 2022-05-08 01:34 | 16589.2435 |  |  | 16589 | [5 empty] | 0 | 0 | 0 | 5.1 | 5963.71
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 12:36 |  | 2d 12:36 | 2022-05-08 01:34 | 2022-05-10 14:10
DRE1 | RS\19\003\D | RS | 19 | 3 | D | 6 DL | 100 | 100 | 100 | 2022-05-09 05:14 | 2022-05-14 17:28 | 412605.1813 |  |  |  | 23549 | 412605 | 312860 |  |  | 0 | 30.21 | 0 | 6.2 | 5875.14
PH4100A | RS\23\005\X | RS | 23 | 5 | X | 1 Prestrip - Thick | 100 | 29.4141 | 29.4141 | 2022-05-10 14:10 | 2022-05-14 16:12 | 166713.2283 | 166713 | [7 empty] | 0 | 0 | 16.64 | 12.66 | 5177.57
TS5500Shv | RS\24\004\X | RS | 24 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-05-10 14:10 | 2022-05-11 03:48 | 16623.4253 | [6 empty] | 16623 | 11620 | 1.17 | 0 | 0 | 12.5 | 5182
DRE2 | GG\12\024\D | GG | 12 | 24 | D | 6 DL | 100 | 100 | 100 | 2022-05-10 14:12 | 2022-05-14 15:02 | 317043.8865 |  |  |  | 5904 | 317044 | 141696 |  |  | 0 | 14.91 | 0 | 6.16 | 5845.08
TS5500Exc | RS\23\004\X | RS | 23 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-05-10 21:09 | 2022-05-11 10:24 | 16686.1487 | [6 empty] | 16686 | 11658 | 1.17 | 0 | 0 | 12.56 | 5174
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 11:14 |  | 3d 11:14 | 2022-05-11 03:48 | 2022-05-14 15:02
TS5500Exc | RS\23\003\B | RS | 23 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-05-11 10:24 | 2022-05-12 10:23 | 30212.6715 | [6 empty] | 30213 | 21581 | 2.79 | 0 | 0 | 8.81 | 5623
TS5500Exc | SC\59\001\D | SC | 59 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-05-12 10:23 | 2022-05-22 17:42 | 311517.5247 | [6 empty] | 311518 | 234500 | 4.88 | 0 | 0 | 6.12 | 5877
PH4100XPC#1 | GG\14\022\B | GG | 14 | 22 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-05-12 11:32 | 2022-05-18 02:14 | 308343.7724 | 308344 | [7 empty] | 0 | 0 | 30.62 | 16.09 | 5073.88
DRE2 | GG\12\025\D | GG | 12 | 25 | D | 6 DL | 100 | 0 | 100 | 2022-05-14 15:02 | 2022-05-18 13:13 | 308332.0183 |  |  |  | 23447 | 308332 | 211026 |  |  | 0 | 40 | 0 | 6.13 | 5847.73
TS5500Shv | GG\12\024\D | GG | 12 | 24 | D | 8 Coal Mining | 55.8 | 0 | 55.8 | 2022-05-14 15:02 | 2022-05-15 18:54 | 33969.835 | [6 empty] | 33970 | 25743 | 2.58 | 0 | 0 | 6.16 | 5845
PH4100A | RS\24\005\X | RS | 24 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-05-14 16:12 | 2022-05-28 15:53 | 571878.7526 | 571879 | [7 empty] | 0 | 0 | 57.33 | 12.62 | 5182.98
DRE1 | RS\19\004\D | RS | 19 | 4 | D | 6 DL | 100 | 100 | 100 | 2022-05-14 17:28 | 2022-05-19 08:51 | 347611.4558 |  |  |  | 17872 | 347611 | 279996 |  |  | 0 | 29.79 | 0 | 6.66 | 5835.13
TS5500Shv | RS\23\005\X | RS | 23 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-05-15 18:54 | 2022-05-16 09:15 | 17510.3928 | [6 empty] | 17510 | 12222 | 1.23 | 0 | 0 | 12.66 | 5178
TS5500Shv | RS\19\003\D | RS | 19 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-05-16 09:15 | 2022-05-18 16:39 | 67555.9574 | [6 empty] | 67556 | 49294 | 4.4 | 0 | 0 | 6.2 | 5875
PH4100XPC#1 | GG\14\023\B | GG | 14 | 23 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-05-18 02:14 | 2022-05-23 10:23 | 299928.6633 | 299929 | [7 empty] | 0 | 0 | 31.73 | 12.47 | 5318.38
DRE2 | GG\14\012\B | GG | 14 | 12 | B | 6 DL | 100 | 0 | 100 | 2022-05-18 13:13 | 2022-05-21 13:21 | 236181.5256 |  |  |  |  | 236182 | 196818 |  |  | 0 | 17.08 | 0 | 10.36 | 5485.76
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 20:42 |  | 2d 20:42 | 2022-05-18 16:39 | 2022-05-21 13:21
DRE1 | RS\19\005\D | RS | 19 | 5 | D | 6 DL | 100 | 100 | 100 | 2022-05-19 08:51 | 2022-05-23 21:03 | 337615.7247 |  |  |  | 17358 | 337616 | 271944 |  |  | 0 | 28.93 | 0 | 7.06 | 5800.34
TS Fleet 5 | GG\15\008\X1 | GG | 15 | 8 | X1 | 1 Prestrip - Thick | 45.7454 | 45.7454 | 45.7454 | 2022-05-19 21:07 | 2022-05-24 21:58 | 236864.3116 | 236864 | [7 empty] | 0 | 0 | 23.2 | 11.07 | 5405.19
DRE2 | GG\14\011\B | GG | 14 | 11 | B | 6 DL | 100 | 0 | 100 | 2022-05-21 13:21 | 2022-05-24 20:39 | 259634.7287 |  |  |  |  | 259635 | 199719 |  |  | 0 | 17.13 | 0 | 9.75 | 5531.02
TS5500Shv | GG\14\012\B | GG | 14 | 12 | B | 8 Coal Mining | 28.7 | 0 | 28.7 | 2022-05-21 13:21 | 2022-05-22 00:21 | 13421.9602 | [6 empty] | 13422 | 9837 | 0.98 | 0 | 0 | 10.36 | 5486
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 20:18 |  | 2d 20:18 | 2022-05-22 00:21 | 2022-05-24 20:39
TS5500Exc | RS\19\004\D | RS | 19 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-05-22 17:42 | 2022-05-24 17:34 | 60306.0693 | [6 empty] | 60306 | 44004 | 4.4 | 0 | 0 | 6.66 | 5835
PH4100XPC#1 | GG\14\024\D | GG | 14 | 24 | D | 1 Prestrip - Thick | 100 | 94.2328 | 94.2328 | 2022-05-23 10:23 | 2022-05-27 05:20 | 212916.7342 | 212917 | [7 empty] | 0 | 0 | 39.02 | 6.28 | 5835.84
DRE1 | RS\19\006\D | RS | 19 | 6 | D | 6 DL | 100 | 100 | 100 | 2022-05-23 21:03 | 2022-05-28 06:14 | 328237.474 |  |  |  | 16876 | 328237 | 264390 |  |  | 0 | 28.13 | 0 | 7.34 | 5774.89
TS5500Exc | RS\24\003\A | RS | 24 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-05-24 17:34 | 2022-05-25 22:31 | 36470.9321 | [6 empty] | 36471 | 25439 | 3.46 | 0 | 0 | 13.22 | 5245
DRE2 | GG\14\010\B | GG | 14 | 10 | B | 6 DL | 100 | 0 | 100 | 2022-05-24 20:39 | 2022-05-27 14:58 | 217140.9814 |  |  |  |  | 217141 | 180951 |  |  | 0 | 18.25 | 0 | 9.3 | 5561.57
TS5500Shv | GG\14\011\B | GG | 14 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-05-24 20:39 | 2022-05-26 12:50 | 49006.3905 | [6 empty] | 49006 | 36049 | 3.59 | 0 | 0 | 9.75 | 5531
TS Fleet 5 | GG\15\009\X1 | GG | 15 | 9 | X1 | 1 Prestrip - Thick | 45.6593 | 45.6593 | 45.6593 | 2022-05-24 21:58 | 2022-05-29 15:44 | 222984.1387 | 222984 | [7 empty] | 0 | 0 | 21.97 | 11.82 | 5354.54
TS5500Exc | RS\19\005\D | RS | 19 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-05-25 22:31 | 2022-05-27 22:07 | 59954.1915 | [6 empty] | 59954 | 43644 | 4.36 | 0 | 0 | 7.06 | 5800
TS6060#1 | RS\23\004\A | RS | 23 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-05-25 23:39 | 2022-06-02 18:56 | 193231.1338 | 193231 | [7 empty] | 0 | 0 | 19.34 | 16.16 | 4995.37
TS5500Shv | RS\25\004\X | RS | 25 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-05-26 12:50 | 2022-05-27 02:25 | 16563.2281 | [6 empty] | 16563 | 11583 | 1.16 | 0 | 0 | 12.45 | 5190
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 12:33 |  | 0d 12:33 | 2022-05-27 02:25 | 2022-05-27 14:58
PH4100XPC#1 | GG\15\003\X1 | GG | 15 | 3 | X1 | 1 Prestrip - Thick | 100 | 67.7936 | 67.7936 | 2022-05-27 05:20 | 2022-06-16 17:36 | 1106632.922 | 1106633 | [7 empty] | 0 | 0 | 59.78 | 10.04 | 5360.15
DRE2 | GG\14\009\B | GG | 14 | 9 | B | 6 DL | 100 | 0 | 100 | 2022-05-27 14:58 | 2022-05-30 13:35 | 231176.4122 |  |  |  |  | 231176 | 192647 |  |  | 0 | 19.22 | 0 | 9.67 | 5537.41
TS5500Shv | GG\14\010\B | GG | 14 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-05-27 14:58 | 2022-05-29 08:10 | 50231.0031 | [6 empty] | 50231 | 37050 | 3.71 | 0 | 0 | 9.3 | 5562
TS5500Exc | SC\59\002\D | SC | 59 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2022-05-27 22:07 | 2022-06-10 01:54 | 279270.0936 |  |  | 279270 | [5 empty] | 0 | 0 | 0 | 6.03 | 5884.46
DRE1 | RS\19\007\D | RS | 19 | 7 | D | 6 DL | 100 | 100 | 100 | 2022-05-28 06:14 | 2022-05-30 15:19 | 178148.1981 |  |  |  | 6492 | 178148 | 100516 |  |  | 0 | 28.44 | 0 | 7.89 | 5723.08
PH4100A | RS\23\005\A | RS | 23 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-05-28 15:53 | 2022-06-02 03:14 | 186375.4085 | 186375 | [7 empty] | 0 | 0 | 18.67 | 19.66 | 4706.66
TS5500Shv | RS\19\006\D | RS | 19 | 6 | D | 8 Coal Mining | 52.9 | 0 | 52.9 | 2022-05-29 08:10 | 2022-05-30 10:03 | 31564.5477 | [6 empty] | 31565 | 22906 | 2.29 | 0 | 0 | 7.34 | 5775
TS Fleet 5 | GG\15\010\B | GG | 15 | 10 | B | 1 Prestrip - Thick | 44.8721 | 44.8721 | 44.8721 | 2022-05-29 15:44 | 2022-06-04 19:02 | 288701.104 | 288701 | [7 empty] | 0 | 0 | 30.63 | 9.36 | 5559.04
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 03:32 |  | 0d 03:32 | 2022-05-30 10:03 | 2022-05-30 13:35
DRE2 | GG\14\008\B | GG | 14 | 8 | B | 6 DL | 100 | 0 | 100 | 2022-05-30 13:35 | 2022-06-02 14:19 | 238130.8489 |  |  |  |  | 238131 | 198442 |  |  | 0 | 19.86 | 0 | 10.33 | 5483.49
TS5500Shv | GG\14\009\B | GG | 14 | 9 | B | 8 Coal Mining | 61.5 | 0 | 61.5 | 2022-05-30 13:35 | 2022-05-31 15:40 | 31810.0478 | [6 empty] | 31810 | 23359 | 2.34 | 0 | 0 | 9.67 | 5537
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2022-05-30 15:19 | 2022-06-01 15:19
TS5500Shv | RS\19\007\D | RS | 19 | 7 | D | 7 PostStrip | 100 | 0 | 100 | 2022-05-31 15:40 | 2022-06-01 12:58 | 22823.6672 |  |  | 22824 | [5 empty] | 0 | 0 | 0 | 7.89 | 5723.08
TS5500Shv | RS\19\007\D | RS | 19 | 7 | D | 8 Coal Mining | 11.8 | 0 | 11.8 | 2022-06-01 12:58 | 2022-06-01 15:34 | 3178.4109 | [6 empty] | 3178 | 2299 | 0.51 | 0 | 0 | 7.89 | 5723
DRE1 | MW\41\002\D | MW | 41 | 2 | D | 6 DL | 100 | 100 | 100 | 2022-06-01 15:19 | 2022-06-03 03:09 | 111786.5045 |  |  |  | 3563 | 111787 | 67418 |  |  | 0 | 24.71 | 0 | 6.27 | 5863.31
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 22:45 |  | 0d 22:45 | 2022-06-01 15:34 | 2022-06-02 14:19
PH4100A | RS\23\006\X | RS | 23 | 6 | X | 1 Prestrip - Thick | 100 | 65.5555 | 65.5555 | 2022-06-02 03:14 | 2022-06-16 00:20 | 568055.4553 | 568055 | [7 empty] | 0 | 0 | 41.84 | 12.56 | 5183.35
DRE2 | GG\14\007\B | GG | 14 | 7 | B | 6 DL | 100 | 0 | 100 | 2022-06-02 14:19 | 2022-06-05 21:38 | 259702.2519 |  |  |  |  | 259702 | 199771 |  |  | 0 | 20.1 | 0 | 10.41 | 5443.55
TS5500Shv | GG\14\008\B | GG | 14 | 8 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-06-02 14:19 | 2022-06-03 10:56 | 25146.6874 | [6 empty] | 25147 | 18353 | 1.84 | 0 | 0 | 10.33 | 5483
TS6060#1 | GG\12\023\D | GG | 12 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-06-02 18:56 | 2022-06-04 11:24 | 54769.6269 | [6 empty] | 54770 | 41370 | 4.15 | 0 | 0 | 6.14 | 5840
DRE1 | MW\41\003\B | MW | 41 | 3 | B | 6 DL | 100 | 0 | 100 | 2022-06-03 03:09 | 2022-06-04 23:58 | 139838.879 |  |  |  |  | 139839 | 121599 |  |  | 0 | 11.73 | 0 | 11.69 | 5324.39
TS5500Shv | MW\41\002\D | MW | 41 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2022-06-03 10:56 | 2022-06-04 03:49 | 18098.2031 |  |  | 18098 | [5 empty] | 0 | 0 | 0 | 6.27 | 5863.31
TS5500Shv | MW\41\002\D | MW | 41 | 2 | D | 8 Coal Mining | 89.4 | 0 | 89.4 | 2022-06-04 03:49 | 2022-06-04 19:32 | 19161.3329 | [6 empty] | 19161 | 14458 | 4.23 | 0 | 0 | 6.27 | 5863
TS6060#1 | MW\40\010\D | MW | 40 | 10 | D | 7 PostStrip | 15.0678 | 0 | 15.0678 | 2022-06-04 11:24 | 2022-06-04 14:15 | 2943.0996 |  |  | 2943 | [5 empty] | 0 | 0 | 0 | 5.1 | 5963.71
TS6060#1 | GG\12\024\D | GG | 12 | 24 | D | 8 Coal Mining | 44.2 | 0 | 44.2 | 2022-06-04 14:15 | 2022-06-05 10:09 | 26940.6948 | [6 empty] | 26941 | 20416 | 2.04 | 0 | 0 | 6.16 | 5845
TS Fleet 5 | GG\15\011\B | GG | 15 | 11 | B | 1 Prestrip - Thick | 45.0628 | 45.0628 | 45.0628 | 2022-06-04 19:02 | 2022-06-10 05:10 | 255060.2093 | 255060 | [7 empty] | 0 | 0 | 21.82 | 9.63 | 5541.68
TS5500Shv | MW\40\010\D | MW | 40 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-06-04 19:32 | 2022-06-05 13:30 | 21912.2442 | [6 empty] | 21912 | 16756 | 4.48 | 0 | 0 | 5.1 | 5964
DRE1 | MW\41\004\D | MW | 41 | 4 | D | 6 DL | 100 | 0 | 100 | 2022-06-04 23:58 | 2022-06-10 21:26 | 441447.3733 |  |  |  | 31395 | 441447 | 317437 |  |  | 0 | 35 | 0 | 6.38 | 5852.68
TS6060#1 | GG\12\025\D | GG | 12 | 25 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-06-05 10:09 | 2022-06-06 12:53 | 36172.936 | [6 empty] | 36173 | 27413 | 4.65 | 0 | 0 | 6.13 | 5848
TS5500Shv | MW\41\003\B | MW | 41 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-06-05 13:30 | 2022-06-06 04:15 | 17977.4744 | [6 empty] | 17977 | 13082 | 1.3 | 0 | 0 | 11.69 | 5324
DRE2 | GG\14\006\B | GG | 14 | 6 | B | 6 DL | 100 | 0 | 100 | 2022-06-05 21:38 | 2022-06-09 04:54 | 259516.6058 |  |  |  |  | 259517 | 199628 |  |  | 0 | 20.2 | 0 | 10.72 | 5384.93
TS5500Shv | GG\14\007\B | GG | 14 | 7 | B | 8 Coal Mining | 67.7 | 0 | 67.7 | 2022-06-06 04:15 | 2022-06-07 08:49 | 34829.3276 | [6 empty] | 34829 | 25453 | 2.54 | 0 | 0 | 10.41 | 5444
TS6060#1 | GG\14\012\B | GG | 14 | 12 | B | 8 Coal Mining | 71.3 | 0 | 71.3 | 2022-06-06 12:53 | 2022-06-07 13:32 | 33358.6018 | [6 empty] | 33359 | 24448 | 2.44 | 0 | 0 | 10.36 | 5486
TS5500Shv | GG\17\008\X1 | GG | 17 | 8 | X1 | 1 Prestrip - Thick | 5.07 | 5.07 | 5.07 | 2022-06-07 08:49 | 2022-06-08 13:25 | 30378.1143 | 30378 | [7 empty] | 0 | 0 | 2.96 | 11.73 | 5343.8
TS6060#1 | GG\14\009\B | GG | 14 | 9 | B | 8 Coal Mining | 38.5 | 0 | 38.5 | 2022-06-07 13:32 | 2022-06-08 04:15 | 19920.2668 | [6 empty] | 19920 | 14628 | 1.46 | 0 | 0 | 9.67 | 5537
TS6060#1 | GG\14\008\B | GG | 14 | 8 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-06-08 04:15 | 2022-06-09 00:52 | 27910.0596 | [6 empty] | 27910 | 20369 | 2.04 | 0 | 0 | 10.33 | 5483
TS5500Shv | GG\17\011\X1 | GG | 17 | 11 | X1 | 1 Prestrip - Thick | 10.6297 | 10.6297 | 10.6297 | 2022-06-08 13:25 | 2022-06-10 05:10 | 42396.0445 | 42396 | [7 empty] | 0 | 0 | 4.41 | 14.93 | 5105.35
TS6060#1 | RS\24\003\B | RS | 24 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-06-09 00:52 | 2022-06-09 19:29 | 19195.8661 | 19196 | [7 empty] | 0 | 0 | 2.55 | 8.8 | 5621.64
DRE2 | GG\14\005\B | GG | 14 | 5 | B | 6 DL | 100 | 0 | 100 | 2022-06-09 04:54 | 2022-06-11 17:21 | 197913.8335 |  |  |  |  | 197914 | 172099 |  |  | 0 | 17 | 0 | 11.69 | 5308.72
TS6060#1 | GG\14\007\B | GG | 14 | 7 | B | 8 Coal Mining | 32.3 | 0 | 32.3 | 2022-06-09 19:29 | 2022-06-10 07:44 | 16589.4129 | [6 empty] | 16589 | 12124 | 1.21 | 0 | 0 | 10.41 | 5444
TS5500Exc | RS\23\004\A | RS | 23 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-06-10 01:54 | 2022-06-11 17:31 | 49903.6032 | [6 empty] | 49904 | 34104 | 3.41 | 0 | 0 | 16.16 | 4995
TS5500Shv | RS\24\003\B | RS | 24 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-06-10 05:10 | 2022-06-10 17:18 | 14799.0596 | [6 empty] | 14799 | 10586 | 1.38 | 0 | 0 | 8.8 | 5622
TS Fleet 5 | GG\15\012\X2 | GG | 15 | 12 | X2 | 1 Prestrip - Thick | 44.9786 | 0 | 44.9786 | 2022-06-10 05:10 | 2022-06-13 20:53 | 171936.687 | 171937 | [7 empty] | 0 | 0 | 16.29 | 0 | 0
TS6060#1 | GG\14\006\B | GG | 14 | 6 | B | 8 Coal Mining | 69.4 | 0 | 69.4 | 2022-06-10 07:44 | 2022-06-11 09:13 | 34484.376 | [6 empty] | 34484 | 25199 | 2.53 | 0 | 0 | 10.72 | 5385
TS5500Shv | GG\14\006\B | GG | 14 | 6 | B | 8 Coal Mining | 30.6 | 0 | 30.6 | 2022-06-10 17:18 | 2022-06-11 05:45 | 15189.8898 | [6 empty] | 15190 | 11100 | 1.11 | 0 | 0 | 10.72 | 5385
DRE1 | MW\41\003\D | MW | 41 | 3 | D | 6 DL | 100 | 100 | 100 | 2022-06-10 21:26 | 2022-06-17 07:05 | 479510.5127 |  |  |  | 11596 | 479511 | 220331 |  |  | 0 | 23.27 | 0 | 6.39 | 5852.17
TS5500Shv | MW\41\004\D | MW | 41 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-06-11 05:45 | 2022-06-13 09:23 | 62959.7814 | [6 empty] | 62960 | 47344 | 4.73 | 0 | 0 | 6.38 | 5853
TS6060#1 | RS\25\004\A | RS | 25 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-06-11 09:13 | 2022-06-18 23:44 | 188323.0874 | 188323 | [7 empty] | 0 | 0 | 18.87 | 14.91 | 5098.02
DRE2 | GG\13\012\D | GG | 13 | 12 | D | 6 DL | 100 | 100 | 100 | 2022-06-11 17:21 | 2022-06-18 00:20 | 494308.648 |  |  |  | 11509 | 494309 | 218670 |  |  | 0 | 23.03 | 0 | 6.48 | 5818.4
TS5500Exc | RS\23\005\A | RS | 23 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-06-11 17:31 | 2022-06-13 08:42 | 49348.2029 | [6 empty] | 49348 | 33049 | 3.31 | 0 | 0 | 19.66 | 4707
TS5500Exc | RS\24\005\X | RS | 24 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-06-13 08:42 | 2022-06-13 23:29 | 18630.6021 | [6 empty] | 18631 | 13010 | 1.31 | 0 | 0 | 12.62 | 5183
TS5500Shv | GG\14\005\B | GG | 14 | 5 | B | 8 Coal Mining | 97.6 | 0 | 97.6 | 2022-06-13 09:23 | 2022-06-15 02:00 | 49528.3556 | [6 empty] | 49528 | 36059 | 3.61 | 0 | 0 | 11.69 | 5309
TS Fleet 5 | GG\15\013\B | GG | 15 | 13 | B | 1 Prestrip - Thick | 45.1941 | 45.1941 | 45.1941 | 2022-06-13 20:53 | 2022-06-18 07:16 | 208509.2549 | 208509 | [7 empty] | 0 | 0 | 20.41 | 10.69 | 5457.8
TS5500Exc | RS\19\006\D | RS | 19 | 6 | D | 8 Coal Mining | 47.1 | 0 | 47.1 | 2022-06-13 23:29 | 2022-06-14 21:49 | 28129.0372 | [6 empty] | 28129 | 20412 | 2.04 | 0 | 0 | 7.34 | 5775
TS5500Exc | RS\24\003\B | RS | 24 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-06-14 21:49 | 2022-06-15 09:57 | 15286.9407 | [6 empty] | 15287 | 10935 | 1.43 | 0 | 0 | 8.8 | 5622
TS5500Shv | GG\17\020\B | GG | 17 | 20 | B | 1 Prestrip - Thick | 13.8066 | 13.8066 | 13.8066 | 2022-06-15 02:00 | 2022-06-16 22:16 | 47632.3222 | 47632 | [7 empty] | 0 | 0 | 4.61 | 14.96 | 5149.11
TS5500Exc | RS\19\007\D | RS | 19 | 7 | D | 8 Coal Mining | 88.2 | 0 | 88.2 | 2022-06-15 09:57 | 2022-06-16 04:54 | 23868.0776 | [6 empty] | 23868 | 17267 | 3.82 | 0 | 0 | 7.89 | 5723
PH4100A | RS\24\006\X | RS | 24 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-06-16 00:20 | 2022-07-07 04:19 | 867331.846 | 867332 | [7 empty] | 0 | 0 | 65.43 | 12.75 | 5172.32
TS5500Exc | MW\41\002\D | MW | 41 | 2 | D | 8 Coal Mining | 10.6 | 0 | 10.6 | 2022-06-16 04:54 | 2022-06-16 06:42 | 2267.5404 | [6 empty] | 2268 | 1711 | 0.5 | 0 | 0 | 6.27 | 5863
TS5500Exc | SC\59\002\D | SC | 59 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-06-16 06:42 | 2022-06-26 15:46 | 313734.329 | [6 empty] | 313734 | 236547 | 4.92 | 0 | 0 | 6.03 | 5884
PH4100XPC#1 | GG\15\004\X1 | GG | 15 | 4 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-06-16 17:36 | 2022-07-01 19:46 | 838110.9151 | 838111 | [7 empty] | 0 | 0 | 83.12 | 9.85 | 5375.5
TS5500Shv | RS\23\006\X | RS | 23 | 6 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-06-16 22:16 | 2022-06-17 16:03 | 21674.758 | [6 empty] | 21675 | 15164 | 1.16 | 0 | 0 | 12.56 | 5183
DRE1 | MW\41\005\D | MW | 41 | 5 | D | 6 DL | 100 | 0 | 100 | 2022-06-17 07:05 | 2022-06-23 08:34 | 453986.3338 |  |  |  | 32287 | 453986 | 326454 |  |  | 0 | 35 | 0 | 5.89 | 5894.71
TS5500Shv | MW\41\003\D | MW | 41 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-06-17 16:03 | 2022-06-19 19:39 | 62919.1934 | [6 empty] | 62919 | 47351 | 4.73 | 0 | 0 | 6.39 | 5852
DRE2 | GG\13\011\D | GG | 13 | 11 | D | 6 DL | 100 | 100 | 100 | 2022-06-18 00:20 | 2022-06-24 11:06 | 506721.0495 |  |  |  | 9194 | 506721 | 220657 |  |  | 0 | 23 | 0 | 6.17 | 5845.79
TS Fleet 5 | GG\15\018\X2 | GG | 15 | 18 | X2 | 1 Prestrip - Thick | 45.6202 | 0 | 45.6202 | 2022-06-18 07:16 | 2022-06-21 00:40 | 128190.6374 | 128191 | [7 empty] | 0 | 0 | 14.1 | 0 | 0
TS6060#1 | RS\23\004\B | RS | 23 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-06-18 23:44 | 2022-06-20 00:04 | 25113.917 | 25114 | [7 empty] | 0 | 0 | 2.51 | 8.92 | 5600.92
TS5500Shv | GG\13\012\D | GG | 13 | 12 | D | 8 Coal Mining | 25.5 | 0 | 25.5 | 2022-06-19 19:39 | 2022-06-20 08:56 | 16197.3869 | [6 empty] | 16197 | 12119 | 1.21 | 0 | 0 | 6.48 | 5818
TS6060#1 | GG\15\003\X1 | GG | 15 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2022-06-20 00:04 | 2022-06-20 21:48 | 29396.3022 | [6 empty] | 29396 | 21841 | 1.31 | 0 | 0 | 10.04 | 5360
TS5500Shv | RS\25\004\A | RS | 25 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-06-20 08:56 | 2022-06-21 05:01 | 24495.0666 | [6 empty] | 24495 | 16920 | 1.69 | 0 | 0 | 14.91 | 5098
TS6060#1 | RS\23\005\B | RS | 23 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-06-20 21:48 | 2022-06-21 23:43 | 26745.8907 | 26746 | [7 empty] | 0 | 0 | 2.68 | 9.01 | 5584.7
TS Fleet 5 | GG\15\019\X2 | GG | 15 | 19 | X2 | 1 Prestrip - Thick | 45.4532 | 0 | 45.4532 | 2022-06-21 00:40 | 2022-06-23 07:48 | 108040.0181 | 108040 | [7 empty] | 0 | 0 | 10.49 | 0 | 0
TS5500Shv | GG\15\003\X2 | GG | 15 | 3 | X2 | 1 Prestrip - Thick | 79.2414 | 0 | 79.2414 | 2022-06-21 05:01 | 2022-06-26 01:49 | 125211.8165 | 125212 | [7 empty] | 0 | 0 | 7.63 | 0 | 0
TS6060#1 | RS\23\006\A | RS | 23 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-06-21 23:43 | 2022-06-30 15:18 | 214187.0439 | 214187 | [7 empty] | 0 | 0 | 17.72 | 20.12 | 4676.13
TS Fleet 5 | GG\15\020\B | GG | 15 | 20 | B | 1 Prestrip - Thick | 44.1799 | 44.1799 | 44.1799 | 2022-06-23 07:48 | 2022-06-26 13:05 | 151483.4451 | 151483 | [7 empty] | 0 | 0 | 14.99 | 14.49 | 5191.38
DRE1 | MW\41\006\D | MW | 41 | 6 | D | 6 DL | 100 | 100 | 100 | 2022-06-23 08:34 | 2022-06-27 23:08 | 344986.5643 |  |  |  | 17737 | 344987 | 277881 |  |  | 0 | 29.58 | 0 | 5.6 | 5919.33
DRE2 | GG\13\010\D | GG | 13 | 10 | D | 6 DL | 100 | 100 | 100 | 2022-06-24 11:06 | 2022-06-30 10:58 | 471057.3504 |  |  |  | 10968 | 471057 | 208384 |  |  | 0 | 21.94 | 0 | 6.02 | 5859.5
TS5500Shv | RS\23\005\B | RS | 23 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-06-26 01:49 | 2022-06-27 08:09 | 36990.1655 | [6 empty] | 36990 | 26450 | 2.65 | 0 | 0 | 9.01 | 5585
TS Fleet 5 | GG\15\021\B | GG | 15 | 21 | B | 1 Prestrip - Thick | 44.867 | 44.867 | 44.867 | 2022-06-26 13:05 | 2022-06-29 19:38 | 153965.3055 | 153965 | [7 empty] | 0 | 0 | 15.29 | 14.66 | 5199.4
TS5500Exc | RS\23\004\B | RS | 23 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-06-26 15:46 | 2022-06-27 22:21 | 38508.5136 | [6 empty] | 38509 | 27524 | 2.75 | 0 | 0 | 8.92 | 5601
TS5500Shv | MW\41\005\D | MW | 41 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-06-27 08:09 | 2022-06-29 09:44 | 60455.0664 | [6 empty] | 60455 | 45675 | 4.57 | 0 | 0 | 5.89 | 5895
TS5500Exc | RS\25\003\A | RS | 25 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-06-27 22:21 | 2022-06-29 02:39 | 35659.4367 | [6 empty] | 35659 | 24989 | 3.44 | 0 | 0 | 12.71 | 5285
DRE1 | MW\41\007\D | MW | 41 | 7 | D | 6 DL | 100 | 100 | 100 | 2022-06-27 23:08 | 2022-07-02 13:32 | 344531.8783 |  |  |  | 17714 | 344532 | 277515 |  |  | 0 | 29.55 | 0 | 5.44 | 5934.67
TS5500Exc | MW\41\006\D | MW | 41 | 6 | D | 8 Coal Mining | 17.8 | 0 | 17.8 | 2022-06-29 02:39 | 2022-06-29 11:08 | 10677.5246 | [6 empty] | 10678 | 8073 | 0.81 | 0 | 0 | 5.6 | 5919
TS5500Shv | MW\41\006\D | MW | 41 | 6 | D | 8 Coal Mining | 82.2 | 0 | 82.2 | 2022-06-29 09:44 | 2022-07-01 02:04 | 49178.7663 | [6 empty] | 49179 | 37185 | 3.72 | 0 | 0 | 5.6 | 5919
TS5500Exc | SC\60\001\D | SC | 60 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2022-06-29 11:08 | 2022-07-12 15:24 | 279705.2484 |  |  | 279705 | [5 empty] | 0 | 0 | 0 | 6.56 | 5837.06
TS Fleet 5 | GG\15\022\B | GG | 15 | 22 | B | 1 Prestrip - Thick | 45.2133 | 45.2133 | 45.2133 | 2022-06-29 19:38 | 2022-07-02 19:00 | 139861.058 | 139861 | [7 empty] | 0 | 0 | 14.14 | 16.4 | 5054.03
DRE2 | GG\13\009\D | GG | 13 | 9 | D | 6 DL | 100 | 100 | 100 | 2022-06-30 10:58 | 2022-07-06 03:51 | 448137.0015 |  |  |  | 10434 | 448137 | 198245 |  |  | 0 | 20.87 | 0 | 6.31 | 5832.9
TS6060#1 | RS\24\005\A | RS | 24 | 5 | A | 1 Prestrip - Thick | 24.3643 | 24.3643 | 24.3643 | 2022-06-30 15:18 | 2022-07-02 10:17 | 44352.3313 | 44352 | [7 empty] | 0 | 0 | 4.46 | 19.26 | 4743.81
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 17:42 |  | 0d 17:42 | 2022-07-01 02:04 | 2022-07-01 19:46
PH4100XPC#1 | GG\15\003\X2 | GG | 15 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 20.7586 | 2022-07-01 19:46 | 2022-07-02 10:15 | 32801.3956 | 32801 | [7 empty] | 0 | 0 | 2 | 0 | 0
TS5500Shv | GG\15\004\X1 | GG | 15 | 4 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-07-01 19:46 | 2022-07-02 03:26 | 9354.1468 | [6 empty] | 9354 | 6972 | 0.68 | 0 | 0 | 9.85 | 5376
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 10:06 |  | 0d 10:06 | 2022-07-02 03:26 | 2022-07-02 13:32
PH4100XPC#1 | GG\15\003\B | GG | 15 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-07-02 10:15 | 2022-07-05 04:30 | 149951.1135 | 149951 | [7 empty] | 0 | 0 | 9.57 | 10.38 | 5468.49
TS6060#1 | GG\15\004\X1 | GG | 15 | 4 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-07-02 10:17 | 2022-07-02 17:57 | 10382.075 | [6 empty] | 10382 | 7739 | 0.75 | 0 | 0 | 9.85 | 5376
DRE1 | MW\41\008\D | MW | 41 | 8 | D | 6 DL | 100 | 100 | 100 | 2022-07-02 13:32 | 2022-07-07 02:49 | 340999.6723 |  |  |  | 17532 | 341000 | 274670 |  |  | 0 | 29.23 | 0 | 5.31 | 5946.66
TS5500Shv | MW\41\007\D | MW | 41 | 7 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-07-02 13:32 | 2022-07-03 14:26 | 30355.6921 | [6 empty] | 30356 | 23028 | 2.3 | 0 | 0 | 5.44 | 5935
TS6060#1 | GG\14\005\B | GG | 14 | 5 | B | 8 Coal Mining | 2.4 | 0 | 2.4 | 2022-07-02 17:57 | 2022-07-02 18:52 | 1220.319 | [6 empty] | 1220 | 888 | 0.09 | 0 | 0 | 11.69 | 5309
TS6060#1 | GG\13\012\D | GG | 13 | 12 | D | 8 Coal Mining | 74.5 | 0 | 74.5 | 2022-07-02 18:52 | 2022-07-04 05:52 | 47384.6401 | [6 empty] | 47385 | 35453 | 3.54 | 0 | 0 | 6.48 | 5818
TS Fleet 5 | GG\15\023\B | GG | 15 | 23 | B | 1 Prestrip - Thick | 44.557 | 44.557 | 44.557 | 2022-07-02 19:00 | 2022-07-05 11:26 | 126304.121 | 126304 | [7 empty] | 0 | 0 | 12.94 | 12.78 | 5303.76
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 14:04 |  | 1d 14:04 | 2022-07-03 14:26 | 2022-07-05 04:30
TS6060#1 | GG\13\011\D | GG | 13 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-07-04 05:52 | 2022-07-06 04:56 | 63695.9236 | [6 empty] | 63696 | 47695 | 4.77 | 0 | 0 | 6.17 | 5846
PH4100XPC#1 | GG\15\004\X2 | GG | 15 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2022-07-05 04:30 | 2022-07-07 16:45 | 136367.451 | 136367 | [7 empty] | 0 | 0 | 13.14 | 0 | 0
TS5500Shv | GG\15\003\B | GG | 15 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-07-05 04:30 | 2022-07-07 15:56 | 72474.7072 | [6 empty] | 72475 | 53203 | 3.52 | 0 | 0 | 10.38 | 5468
TS Fleet 5 | GG\15\024\D | GG | 15 | 24 | D | 1 Prestrip - Thick | 44.5111 | 44.5111 | 44.5111 | 2022-07-05 11:26 | 2022-07-07 07:41 | 86727.7918 | 86728 | [7 empty] | 0 | 0 | 18.35 | 6.3 | 5834.04
DRE2 | GG\13\008\D | GG | 13 | 8 | D | 6 DL | 100 | 100 | 100 | 2022-07-06 03:51 | 2022-07-11 16:06 | 432997.3143 |  |  |  | 10081 | 432997 | 191547 |  |  | 0 | 20.16 | 0 | 6.67 | 5800.47
TS6060#1 | GG\13\010\D | GG | 13 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-07-06 04:56 | 2022-07-08 04:17 | 64083.5576 | [6 empty] | 64084 | 47985 | 4.8 | 0 | 0 | 6.02 | 5860
DRE1 | MW\41\009\D | MW | 41 | 9 | D | 6 DL | 100 | 100 | 100 | 2022-07-07 02:49 | 2022-07-11 12:35 | 330055.025 |  |  |  | 16969 | 330055 | 265854 |  |  | 0 | 28.28 | 0 | 5.21 | 5954.27
PH4100A | RS\24\004\A | RS | 24 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-07-07 04:19 | 2022-07-11 18:04 | 190536.2665 | 190536 | [7 empty] | 0 | 0 | 19.1 | 15.53 | 5047.34
TS Fleet 5 | GG\16\003\X1 | GG | 16 | 3 | X1 | 1 Prestrip - Thick | 44.3367 | 44.3367 | 44.3367 | 2022-07-07 07:41 | 2022-07-21 05:49 | 654891.3539 | 654891 | [7 empty] | 0 | 0 | 40.06 | 10.11 | 5350.69
TS5500Shv | RS\24\006\X | RS | 24 | 6 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-07-07 15:56 | 2022-07-08 00:27 | 10378.535 | [6 empty] | 10379 | 7251 | 0.57 | 0 | 0 | 12.75 | 5172
PH4100XPC#1 | GG\15\004\B | GG | 15 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-07-07 16:45 | 2022-07-10 02:55 | 131680.4722 | 131680 | [7 empty] | 0 | 0 | 12.97 | 10.7 | 5410.87
TS5500Shv | GG\13\009\D | GG | 13 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-07-08 00:27 | 2022-07-10 04:01 | 62879.7921 | [6 empty] | 62880 | 46971 | 4.7 | 0 | 0 | 6.31 | 5833
TS6060#1 | RS\25\003\B | RS | 25 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-07-08 04:17 | 2022-07-08 22:55 | 19225.7459 | 19226 | [7 empty] | 0 | 0 | 2.58 | 8.78 | 5620.15
TS6060#1 | RS\25\005\X | RS | 25 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-07-08 22:55 | 2022-08-01 16:22 | 579636.9888 | 579637 | [7 empty] | 0 | 0 | 58.45 | 12.6 | 5188.52
PH4100XPC#1 | GG\15\005\X1 | GG | 15 | 5 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-07-10 02:55 | 2022-07-23 12:19 | 727978.0573 | 727978 | [7 empty] | 0 | 0 | 69.93 | 10.08 | 5370.47
TS5500Shv | GG\15\004\B | GG | 15 | 4 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-07-10 04:01 | 2022-07-10 23:30 | 23771.7817 | [6 empty] | 23772 | 17402 | 1.74 | 0 | 0 | 10.7 | 5411
TS5500Shv | MW\41\008\D | MW | 41 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-07-10 23:30 | 2022-07-13 03:01 | 62806.5624 | [6 empty] | 62807 | 47763 | 4.78 | 0 | 0 | 5.31 | 5947
DRE1 | MW\41\010\D | MW | 41 | 10 | D | 6 DL | 100 | 100 | 100 | 2022-07-11 12:35 | 2022-07-13 00:05 | 110809.9357 |  |  |  | 4066 | 110810 | 62623 |  |  | 0 | 27.79 | 0 | 5.1 | 5963.14
DRE2 | GG\13\007\D | GG | 13 | 7 | D | 6 DL | 100 | 100 | 100 | 2022-07-11 16:06 | 2022-07-17 02:36 | 427280.6736 |  |  |  | 7957 | 427281 | 190963 |  |  | 0 | 19.89 | 0 | 6.55 | 5811.5
PH4100A | RS\24\005\A | RS | 24 | 5 | A | 1 Prestrip - Thick | 100 | 75.6357 | 75.6357 | 2022-07-11 18:04 | 2022-07-15 01:23 | 137686.1594 | 137686 | [7 empty] | 0 | 0 | 13.84 | 19.26 | 4743.81
TS5500Exc | RS\23\006\A | RS | 23 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-07-12 15:24 | 2022-07-14 14:36 | 59447.3709 | [6 empty] | 59447 | 39868 | 3.33 | 0 | 0 | 20.12 | 4676
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2022-07-13 00:05 | 2022-07-15 00:05
TS5500Shv | RS\24\004\A | RS | 24 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-07-13 03:01 | 2022-07-13 23:07 | 24510.623 | [6 empty] | 24511 | 16840 | 1.69 | 0 | 0 | 15.53 | 5047
TS5500Shv | GG\13\008\D | GG | 13 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-07-13 23:07 | 2022-07-16 01:48 | 61798.158 | [6 empty] | 61798 | 46053 | 4.61 | 0 | 0 | 6.67 | 5800
TS5500Exc | RS\24\004\A | RS | 24 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-07-14 14:36 | 2022-07-15 10:42 | 25318.6655 | [6 empty] | 25319 | 17395 | 1.74 | 0 | 0 | 15.53 | 5047
DRE1 | RS\20\003\D | RS | 20 | 3 | D | 6 DL | 100 | 100 | 100 | 2022-07-15 00:05 | 2022-07-20 14:12 | 418502.8948 |  |  |  | 23885 | 418503 | 317332 |  |  | 0 | 30.81 | 0 | 6.13 | 5881.27
PH4100A | MW\44\002\D | MW | 44 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-07-15 01:23 | 2022-07-17 11:04 | 103922.797 | 103923 | [7 empty] | 0 | 0 | 15.79 | 6.56 | 5832.35
TS5500Exc | RS\24\005\A | RS | 24 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-07-15 10:42 | 2022-07-16 06:21 | 24761.3611 | [6 empty] | 24761 | 16661 | 1.67 | 0 | 0 | 19.26 | 4744
TS5500Shv | RS\24\005\A | RS | 24 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-07-16 01:48 | 2022-07-16 21:27 | 23971.1049 | [6 empty] | 23971 | 16129 | 1.62 | 0 | 0 | 19.26 | 4744
TS5500Exc | RS\24\006\X | RS | 24 | 6 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-07-16 06:21 | 2022-07-16 14:52 | 10720.6845 | [6 empty] | 10721 | 7490 | 0.59 | 0 | 0 | 12.75 | 5172
TS5500Exc | MW\41\007\D | MW | 41 | 7 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-07-16 14:52 | 2022-07-17 15:46 | 31356.4292 | [6 empty] | 31356 | 23787 | 2.38 | 0 | 0 | 5.44 | 5935
TS5500Shv | MW\41\009\D | MW | 41 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-07-16 21:27 | 2022-07-18 23:08 | 60583.2196 | [6 empty] | 60583 | 46181 | 4.62 | 0 | 0 | 5.21 | 5954
DRE2 | GG\13\006\D | GG | 13 | 6 | D | 6 DL | 100 | 100 | 100 | 2022-07-17 02:36 | 2022-07-22 13:16 | 427790.3259 |  |  |  | 7966 | 427790 | 191191 |  |  | 0 | 19.92 | 0 | 6.53 | 5813.66
PH4100A | RS\24\006\A | RS | 24 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-07-17 11:04 | 2022-07-22 08:18 | 203498.1521 | 203498 | [7 empty] | 0 | 0 | 17.53 | 20 | 4692.87
TS5500Exc | SC\60\001\D | SC | 60 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-07-17 15:46 | 2022-07-28 10:27 | 325851.1564 | [6 empty] | 325851 | 244120 | 4.83 | 0 | 0 | 6.56 | 5837
TS5500Shv | MW\41\010\D | MW | 41 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2022-07-18 23:08 | 2022-07-19 12:47 | 14630.158 |  |  | 14630 | [5 empty] | 0 | 0 | 0 | 5.1 | 5963.14
TS5500Shv | MW\41\010\D | MW | 41 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-07-19 12:47 | 2022-07-20 02:10 | 16332.1222 | [6 empty] | 16332 | 12490 | 4.5 | 0 | 0 | 5.1 | 5963
TS5500Shv | GG\13\007\D | GG | 13 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-07-20 02:10 | 2022-07-22 05:12 | 62215.1761 | [6 empty] | 62215 | 46511 | 4.65 | 0 | 0 | 6.55 | 5812
DRE1 | RS\20\004\D | RS | 20 | 4 | D | 6 DL | 100 | 100 | 100 | 2022-07-20 14:12 | 2022-07-25 13:21 | 371784.8166 |  |  |  | 21219 | 371785 | 281908 |  |  | 0 | 30.31 | 0 | 6.59 | 5840.8
TS Fleet 5 | GG\16\004\X1 | GG | 16 | 4 | X1 | 1 Prestrip - Thick | 44.863 | 44.863 | 44.863 | 2022-07-21 05:49 | 2022-07-29 08:24 | 381403.029 | 381403 | [7 empty] | 0 | 0 | 37.23 | 9.98 | 5359.11
TS5500Shv | RS\20\003\D | RS | 20 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-07-22 05:12 | 2022-07-24 12:26 | 67366.3114 | [6 empty] | 67366 | 49156 | 4.4 | 0 | 0 | 6.13 | 5881
PH4100A | MW\44\003\D | MW | 44 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-07-22 08:18 | 2022-07-24 00:23 | 69553.6303 | 69554 | [7 empty] | 0 | 0 | 9.45 | 6.64 | 5829.69
DRE2 | GG\13\005\D | GG | 13 | 5 | D | 6 DL | 100 | 100 | 100 | 2022-07-22 13:16 | 2022-07-27 22:46 | 423990.6813 |  |  |  | 10254 | 423991 | 194820 |  |  | 0 | 20.51 | 0 | 6.5 | 5815.38
PH4100XPC#1 | GG\15\006\X1 | GG | 15 | 6 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-07-23 12:19 | 2022-08-04 11:40 | 646473.8584 | 646474 | [7 empty] | 0 | 0 | 62.65 | 10.73 | 5357.68
PH4100A | MW\44\005\B | MW | 44 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-07-24 00:23 | 2022-07-29 04:32 | 214955.8665 | 214956 | [7 empty] | 0 | 0 | 21.43 | 11.22 | 5367.57
TS5500Shv | GG\15\005\X1 | GG | 15 | 5 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-07-24 12:26 | 2022-07-24 19:47 | 8956.0345 | [6 empty] | 8956 | 6673 | 0.65 | 0 | 0 | 10.08 | 5370
TS5500Shv | RS\24\006\A | RS | 24 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-07-24 19:47 | 2022-07-26 18:24 | 56844.9942 | [6 empty] | 56845 | 38205 | 3.33 | 0 | 0 | 20 | 4693
DRE1 | RS\20\005\D | RS | 20 | 5 | D | 6 DL | 100 | 100 | 100 | 2022-07-25 13:21 | 2022-07-30 02:31 | 340678.7299 |  |  |  | 17516 | 340679 | 274411 |  |  | 0 | 29.2 | 0 | 7 | 5804.83
TS5500Shv | RS\20\004\D | RS | 20 | 4 | D | 8 Coal Mining | 30.3 | 0 | 30.3 | 2022-07-26 18:24 | 2022-07-27 09:11 | 18028.7556 | [6 empty] | 18029 | 13154 | 1.32 | 0 | 0 | 6.59 | 5841
TS5500Shv | RS\25\003\B | RS | 25 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-07-27 09:11 | 2022-07-27 21:16 | 14727.4909 | [6 empty] | 14727 | 10550 | 1.39 | 0 | 0 | 8.78 | 5620
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 01:30 |  | 0d 01:30 | 2022-07-27 21:16 | 2022-07-27 22:46
DRE2 | GG\13\004\D | GG | 13 | 4 | D | 6 DL | 100 | 100 | 100 | 2022-07-27 22:46 | 2022-07-30 19:25 | 224767.1037 |  |  |  | 10057 | 224767 | 191077 |  |  | 0 | 20.12 | 0 | 6.38 | 5824.67
TS5500Shv | GG\13\005\D | GG | 13 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-07-27 22:46 | 2022-07-30 01:29 | 61850.2008 | [6 empty] | 61850 | 46348 | 4.63 | 0 | 0 | 6.5 | 5815
TS5500Exc | RS\20\004\D | RS | 20 | 4 | D | 8 Coal Mining | 69.7 | 0 | 69.7 | 2022-07-28 10:27 | 2022-07-29 19:24 | 41493.5072 | [6 empty] | 41494 | 30275 | 3.03 | 0 | 0 | 6.59 | 5841
PH4100A | MW\43\006\B | MW | 43 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-07-29 04:32 | 2022-08-03 13:27 | 215587.3433 | 215587 | [7 empty] | 0 | 0 | 21.3 | 10.02 | 5475.17
TS Fleet 5 | GG\16\005\X1 | GG | 16 | 5 | X1 | 1 Prestrip - Thick | 45.4049 | 45.4049 | 45.4049 | 2022-07-29 08:24 | 2022-08-05 14:39 | 341506.858 | 341507 | [7 empty] | 0 | 0 | 35.16 | 10.21 | 5354.23
TS5500Exc | RS\25\003\B | RS | 25 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-07-29 19:24 | 2022-07-30 07:28 | 15213.0126 | [6 empty] | 15213 | 10898 | 1.44 | 0 | 0 | 8.78 | 5620
TS5500Shv | MW\44\005\B | MW | 44 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-07-30 01:29 | 2022-07-30 18:01 | 20145.6839 | [6 empty] | 20146 | 14705 | 1.45 | 0 | 0 | 11.22 | 5368
DRE1 | RS\20\006\D | RS | 20 | 6 | D | 6 DL | 100 | 100 | 100 | 2022-07-30 02:31 | 2022-08-03 11:09 | 326507.1189 |  |  |  | 16787 | 326507 | 262996 |  |  | 0 | 27.99 | 0 | 7.14 | 5792.59
TS5500Exc | RS\25\004\A | RS | 25 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-07-30 07:28 | 2022-07-31 03:34 | 25302.5962 | [6 empty] | 25303 | 17477 | 1.75 | 0 | 0 | 14.91 | 5098
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 01:24 |  | 0d 01:24 | 2022-07-30 18:01 | 2022-07-30 19:25
DRE2 | GG\13\003\D | GG | 13 | 3 | D | 6 DL | 100 | 100 | 100 | 2022-07-30 19:25 | 2022-08-05 01:21 | 412307.9093 |  |  |  | 7678 | 412308 | 184272 |  |  | 0 | 19.21 | 0 | 6.22 | 5839.06
TS5500Shv | GG\13\004\D | GG | 13 | 4 | D | 8 Coal Mining | 68.6 | 0 | 68.6 | 2022-07-30 19:25 | 2022-08-01 05:41 | 41780.0586 | [6 empty] | 41780 | 31332 | 3.13 | 0 | 0 | 6.38 | 5825
TS5500Exc | RS\20\005\D | RS | 20 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-07-31 03:34 | 2022-08-02 02:30 | 59128.3122 | [6 empty] | 59128 | 43006 | 4.3 | 0 | 0 | 7 | 5805
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 05:28 |  | 2d 05:28 | 2022-08-01 05:41 | 2022-08-03 11:09
TS6060#1 | GG\15\004\B | GG | 15 | 4 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-08-01 16:22 | 2022-08-02 11:51 | 26384.0654 | [6 empty] | 26384 | 19314 | 1.93 | 0 | 0 | 10.7 | 5411
TS5500Exc | SC\60\002\D | SC | 60 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2022-08-02 02:30 | 2022-08-20 01:12 | 380916.2528 |  |  | 380916 | [5 empty] | 0 | 0 | 0 | 6.4 | 5850.6
TS6060#1 | RS\23\006\B | RS | 23 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-08-02 11:51 | 2022-08-03 21:59 | 35213.6802 | 35214 | [7 empty] | 0 | 0 | 2.95 | 9.02 | 5589.3
DRE1 | RS\20\007\D | RS | 20 | 7 | D | 6 DL | 100 | 100 | 100 | 2022-08-03 11:09 | 2022-08-05 08:13 | 140645.14 |  |  |  | 5117 | 140645 | 79328 |  |  | 0 | 28.59 | 0 | 7.58 | 5749.5
TS5500Shv | RS\20\006\D | RS | 20 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-08-03 11:09 | 2022-08-05 11:35 | 59057.5675 | [6 empty] | 59058 | 42921 | 4.29 | 0 | 0 | 7.14 | 5793
PH4100A | MW\44\006\B | MW | 44 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-08-03 13:27 | 2022-08-09 06:37 | 230908.426 | 230908 | [7 empty] | 0 | 0 | 22.61 | 10.25 | 5450.78
TS6060#1 | RS\24\004\B | RS | 24 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-08-03 21:59 | 2022-08-04 22:35 | 25379.4872 | 25379 | [7 empty] | 0 | 0 | 2.54 | 8.86 | 5605.61
PH4100XPC#1 | GG\15\007\X1 | GG | 15 | 7 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-08-04 11:40 | 2022-08-15 02:57 | 572102.075 | 572102 | [7 empty] | 0 | 0 | 55.67 | 10.88 | 5390.71
TS6060#1 | RS\24\005\B | RS | 24 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-08-04 22:35 | 2022-08-06 00:20 | 26570.8882 | 26571 | [7 empty] | 0 | 0 | 2.67 | 8.91 | 5596.2
DRE2 | GG\13\002\D | GG | 13 | 2 | D | 6 DL | 100 | 100 | 100 | 2022-08-05 01:21 | 2022-08-08 11:27 | 268821.6449 |  |  |  | 4496 | 268822 | 77503 |  |  | 0 | 18.49 | 0 | 6.2 | 5842.91
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2022-08-05 08:13 | 2022-08-07 08:13
TS5500Shv | MW\43\006\B | MW | 43 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-08-05 11:35 | 2022-08-06 08:48 | 25881.8961 | [6 empty] | 25882 | 18996 | 1.89 | 0 | 0 | 10.02 | 5475
TS Fleet 5 | GG\16\006\X1 | GG | 16 | 6 | X1 | 1 Prestrip - Thick | 45.6013 | 45.6013 | 45.6013 | 2022-08-05 14:39 | 2022-08-12 05:13 | 310790.8664 | 310791 | [7 empty] | 0 | 0 | 29.89 | 10.74 | 5351.54
TS6060#1 | GG\15\005\X1 | GG | 15 | 5 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-08-06 00:20 | 2022-08-06 07:41 | 9940.2141 | [6 empty] | 9940 | 7406 | 0.72 | 0 | 0 | 10.08 | 5370
TS6060#1 | RS\24\006\B | RS | 24 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-08-06 07:41 | 2022-08-07 17:03 | 34428.0626 | 34428 | [7 empty] | 0 | 0 | 3.01 | 8.99 | 5594.44
TS5500Shv | GG\15\005\X2 | GG | 15 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2022-08-06 08:48 | 2022-08-10 12:27 | 106815.311 | 106815 | [7 empty] | 0 | 0 | 10.39 | 0 | 0
DRE1 | MW\42\002\D | MW | 42 | 2 | D | 6 DL | 100 | 100 | 100 | 2022-08-07 08:13 | 2022-08-10 01:07 | 202495.7802 |  |  |  | 8251 | 202496 | 106931 |  |  | 0 | 30.74 | 0 | 6.38 | 5854.01
TS6060#1 | GG\15\006\X1 | GG | 15 | 6 | X1 | 8 Coal Mining | 56.1 | 0 | 56.1 | 2022-08-07 17:03 | 2022-08-07 23:44 | 9059.476 | [6 empty] | 9059 | 6713 | 0.67 | 0 | 0 | 10.73 | 5358
TS6060#1 | GG\13\006\D | GG | 13 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-08-07 23:44 | 2022-08-09 22:15 | 62940.5597 | [6 empty] | 62941 | 47129 | 4.71 | 0 | 0 | 6.53 | 5814
DRE2 | GG\14\013\B | GG | 14 | 13 | B | 6 DL | 100 | 0 | 100 | 2022-08-08 11:27 | 2022-08-10 20:30 | 186761.616 |  |  |  |  | 186762 | 155635 |  |  | 0 | 16.34 | 0 | 10.88 | 5443.94
PH4100A | MW\43\007\A | MW | 43 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-08-09 06:37 | 2022-08-15 04:21 | 241037.4544 | 241037 | [7 empty] | 0 | 0 | 24.6 | 12.86 | 5257.49
TS6060#1 | GG\13\004\D | GG | 13 | 4 | D | 8 Coal Mining | 31.4 | 0 | 31.4 | 2022-08-09 22:15 | 2022-08-10 12:21 | 19103.1817 | [6 empty] | 19103 | 14326 | 1.43 | 0 | 0 | 6.38 | 5825
DRE1 | MW\42\003\B | MW | 42 | 3 | B | 6 DL | 100 | 0 | 100 | 2022-08-10 01:07 | 2022-08-11 18:22 | 128735.5449 |  |  |  |  | 128736 | 111944 |  |  | 0 | 11.24 | 0 | 12.72 | 5246.55
TS6060#1 | RS\25\004\B | RS | 25 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-08-10 12:21 | 2022-08-11 13:17 | 25716.6954 | 25717 | [7 empty] | 0 | 0 | 2.58 | 8.82 | 5609
TS5500Shv | GG\15\006\X1 | GG | 15 | 6 | X1 | 8 Coal Mining | 43.9 | 0 | 43.9 | 2022-08-10 12:27 | 2022-08-10 18:16 | 7100.431 | [6 empty] | 7100 | 5262 | 0.52 | 0 | 0 | 10.73 | 5358
TS5500Shv | RS\24\006\B | RS | 24 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-08-10 18:16 | 2022-08-12 03:01 | 39933.041 | [6 empty] | 39933 | 28602 | 2.51 | 0 | 0 | 8.99 | 5594
DRE2 | GG\14\018\B | GG | 14 | 18 | B | 6 DL | 100 | 0 | 100 | 2022-08-10 20:30 | 2022-08-13 04:20 | 182828.8567 |  |  |  |  | 182829 | 152357 |  |  | 0 | 16.59 | 0 | 10.7 | 5458.87
TS6060#1 | RS\25\006\X | RS | 25 | 6 | X | 1 Prestrip - Thick | 92.3632 | 92.3632 | 92.3632 | 2022-08-11 13:17 | 2022-09-14 01:13 | 819574.948 | 819575 | [7 empty] | 0 | 0 | 61.87 | 12.88 | 5165.68
DRE1 | MW\42\004\D | MW | 42 | 4 | D | 6 DL | 100 | 0 | 100 | 2022-08-11 18:22 | 2022-08-17 15:22 | 439971.9322 |  |  |  | 31290 | 439972 | 316376 |  |  | 0 | 35 | 0 | 6.4 | 5850.39
TS5500Shv | GG\15\006\X2 | GG | 15 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 50.8795 | 2022-08-12 03:01 | 2022-08-14 01:17 | 49600.0346 | 49600 | [7 empty] | 0 | 0 | 4.92 | 0 | 0
TS Fleet 5 | GG\15\006\X2 | GG | 15 | 6 | X2 | 1 Prestrip - Thick | 49.1205 | 0 | 49.1205 | 2022-08-12 05:13 | 2022-08-13 05:38 | 47885.3424 | 47885 | [7 empty] | 0 | 0 | 4.75 | 0 | 0
DRE2 | GG\14\019\B | GG | 14 | 19 | B | 6 DL | 100 | 0 | 100 | 2022-08-13 04:20 | 2022-08-15 23:12 | 218892.5448 |  |  |  |  | 218893 | 182410 |  |  | 0 | 17.39 | 0 | 11.26 | 5425.19
TS Fleet 5 | GG\16\007\X1 | GG | 16 | 7 | X1 | 1 Prestrip - Thick | 45.7065 | 45.7065 | 45.7065 | 2022-08-13 05:38 | 2022-08-19 00:48 | 272750.5875 | 272751 | [7 empty] | 0 | 0 | 26.79 | 11.05 | 5371.78
TS5500Shv | MW\44\006\B | MW | 44 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-08-14 01:17 | 2022-08-14 12:31 | 13682.1846 | [6 empty] | 13682 | 10035 | 1 | 0 | 0 | 10.25 | 5451
TS5500Shv | GG\13\003\D | GG | 13 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-08-14 12:31 | 2022-08-16 14:33 | 61019.3201 | [6 empty] | 61019 | 45761 | 4.58 | 0 | 0 | 6.22 | 5839
PH4100XPC#1 | GG\15\006\B | GG | 15 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-08-15 02:57 | 2022-08-15 20:23 | 39455.6258 | 39456 | [7 empty] | 0 | 0 | 4 | 10.36 | 5416.87
PH4100A | MW\44\007\A | MW | 44 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-08-15 04:21 | 2022-08-21 01:16 | 243005.4591 | 243005 | [7 empty] | 0 | 0 | 25 | 13.1 | 5241.29
PH4100XPC#1 | GG\15\008\X1 | GG | 15 | 8 | X1 | 1 Prestrip - Thick | 100 | 54.2546 | 54.2546 | 2022-08-15 20:23 | 2022-08-21 02:08 | 280924.1743 | 280924 | [7 empty] | 0 | 0 | 27.51 | 11.07 | 5405.19
DRE2 | GG\14\020\B | GG | 14 | 20 | B | 6 DL | 100 | 0 | 100 | 2022-08-15 23:12 | 2022-08-18 17:09 | 215906.868 |  |  |  |  | 215907 | 179922 |  |  | 0 | 19.19 | 0 | 13.38 | 5279
TS5500Shv | MW\43\007\A | MW | 43 | 7 | A | 8 Coal Mining | 12.4 | 0 | 12.4 | 2022-08-16 14:33 | 2022-08-16 18:32 | 4866.8468 | [6 empty] | 4867 | 3536 | 0.36 | 0 | 0 | 12.86 | 5257
TS5500Shv | GG\15\007\X1 | GG | 15 | 7 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2022-08-16 18:32 | 2022-08-17 07:56 | 16329.036 | [6 empty] | 16329 | 12066 | 1.19 | 0 | 0 | 10.88 | 5391
TS5500Shv | GG\15\007\X2 | GG | 15 | 7 | X2 | 1 Prestrip - Thick | 62.4518 | 0 | 62.4518 | 2022-08-17 07:56 | 2022-08-19 17:01 | 61202.9274 | 61203 | [7 empty] | 0 | 0 | 6.06 | 0 | 0
DRE1 | MW\42\005\D | MW | 42 | 5 | D | 6 DL | 100 | 100 | 100 | 2022-08-17 15:22 | 2022-08-21 23:49 | 325946.87 |  |  |  | 16758 | 325947 | 262545 |  |  | 0 | 27.9 | 0 | 5.93 | 5891.02
DRE2 | GG\14\021\B | GG | 14 | 21 | B | 6 DL | 100 | 0 | 100 | 2022-08-18 17:09 | 2022-08-22 02:57 | 267834.6874 |  |  |  |  | 267835 | 206027 |  |  | 0 | 20.34 | 0 | 14.54 | 5206.21
TS Fleet 5 | GG\15\007\X2 | GG | 15 | 7 | X2 | 1 Prestrip - Thick | 17.054 | 0 | 17.054 | 2022-08-19 00:48 | 2022-08-19 09:20 | 16712.9488 | 16713 | [7 empty] | 0 | 0 | 1.66 | 0 | 0
TS Fleet 5 | GG\16\008\X1 | GG | 16 | 8 | X1 | 1 Prestrip - Thick | 45.8172 | 45.8172 | 45.8172 | 2022-08-19 09:20 | 2022-08-24 20:33 | 257191.833 | 257192 | [7 empty] | 0 | 0 | 25.08 | 11.42 | 5373.2
TS5500Shv | GG\13\002\D | GG | 13 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2022-08-19 17:01 | 2022-08-20 21:22 | 30391.9606 |  |  | 30392 | [5 empty] | 0 | 0 | 0 | 6.2 | 5842.91
TS5500Exc | RS\23\006\B | RS | 23 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-08-20 01:12 | 2022-08-21 10:43 | 42210.4723 | [6 empty] | 42210 | 30194 | 2.54 | 0 | 0 | 9.02 | 5589
TS5500Shv | GG\13\002\D | GG | 13 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-08-20 21:22 | 2022-08-22 04:34 | 38034.6924 | [6 empty] | 38035 | 28502 | 4.75 | 0 | 0 | 6.2 | 5843
PH4100A | MW\43\008\A | MW | 43 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-08-21 01:16 | 2022-08-29 22:50 | 366809.0281 | 366809 | [7 empty] | 0 | 0 | 37.4 | 13.42 | 5220.31
PH4100XPC#1 | GG\15\007\X2 | GG | 15 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 20.4942 | 2022-08-21 02:08 | 2022-08-21 11:01 | 20084.3408 | 20084 | [7 empty] | 0 | 0 | 1.99 | 0 | 0
TS5500Exc | RS\24\004\B | RS | 24 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-08-21 10:43 | 2022-08-22 17:31 | 38790.8735 | [6 empty] | 38791 | 27766 | 2.78 | 0 | 0 | 8.86 | 5606
PH4100XPC#1 | GG\15\007\B | GG | 15 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-08-21 11:01 | 2022-08-22 10:13 | 52539.1254 | 52539 | [7 empty] | 0 | 0 | 5.26 | 10.35 | 5450.06
DRE1 | MW\42\006\D | MW | 42 | 6 | D | 6 DL | 100 | 100 | 100 | 2022-08-21 23:49 | 2022-08-26 14:40 | 345908.0411 |  |  |  | 17784 | 345908 | 278623 |  |  | 0 | 29.63 | 0 | 5.61 | 5919.03
DRE2 | GG\14\022\B | GG | 14 | 22 | B | 6 DL | 100 | 0 | 100 | 2022-08-22 02:57 | 2022-08-25 12:33 | 267150.1098 |  |  |  |  | 267150 | 205500 |  |  | 0 | 20.21 | 0 | 16.09 | 5073.88
TS5500Shv | MW\44\007\A | MW | 44 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-08-22 04:34 | 2022-08-23 07:10 | 32439.7572 | [6 empty] | 32440 | 23541 | 2.38 | 0 | 0 | 13.1 | 5241
PH4100XPC#1 | GG\15\009\X1 | GG | 15 | 9 | X1 | 1 Prestrip - Thick | 100 | 54.3407 | 54.3407 | 2022-08-22 10:13 | 2022-08-27 08:36 | 265380.7934 | 265381 | [7 empty] | 0 | 0 | 26.14 | 11.82 | 5354.54
TS5500Exc | RS\24\005\B | RS | 24 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-08-22 17:31 | 2022-08-23 23:46 | 38101.6173 | [6 empty] | 38102 | 27270 | 2.74 | 0 | 0 | 8.91 | 5596
TS5500Shv | GG\15\008\X1 | GG | 15 | 8 | X1 | 8 Coal Mining | 41.6 | 0 | 41.6 | 2022-08-23 07:10 | 2022-08-23 12:53 | 6974.1509 | [6 empty] | 6974 | 5138 | 0.51 | 0 | 0 | 11.07 | 5405
TS5500Shv | GG\14\013\B | GG | 14 | 13 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-08-23 12:53 | 2022-08-24 18:15 | 35794.3277 | [6 empty] | 35794 | 26144 | 3.01 | 0 | 0 | 10.88 | 5444
TS5500Exc | MW\44\006\B | MW | 44 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-08-23 23:46 | 2022-08-24 10:59 | 14133.2457 | [6 empty] | 14133 | 10366 | 1.04 | 0 | 0 | 10.25 | 5451
TS5500Exc | MW\43\007\A | MW | 43 | 7 | A | 8 Coal Mining | 87.6 | 0 | 87.6 | 2022-08-24 10:59 | 2022-08-25 14:14 | 34320.6079 | [6 empty] | 34321 | 24935 | 2.52 | 0 | 0 | 12.86 | 5257
TS5500Shv | RS\20\007\D | RS | 20 | 7 | D | 7 PostStrip | 100 | 0 | 100 | 2022-08-24 18:15 | 2022-08-25 10:56 | 17900.2219 |  |  | 17900 | [5 empty] | 0 | 0 | 0 | 7.58 | 5749.5
TS Fleet 5 | GG\16\009\X1 | GG | 16 | 9 | X1 | 1 Prestrip - Thick | 45.6229 | 45.6229 | 45.6229 | 2022-08-24 20:33 | 2022-08-29 20:12 | 234533.0505 | 234533 | [7 empty] | 0 | 0 | 23.63 | 12.24 | 5318.65
TS5500Shv | MW\42\002\D | MW | 42 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2022-08-25 10:56 | 2022-08-26 07:46 | 22327.3588 |  |  | 22327 | [5 empty] | 0 | 0 | 0 | 6.38 | 5854.01
DRE2 | GG\14\023\B | GG | 14 | 23 | B | 6 DL | 100 | 0 | 100 | 2022-08-25 12:33 | 2022-08-28 04:14 | 208519.1234 |  |  |  |  | 208519 | 173766 |  |  | 0 | 18.2 | 0 | 12.47 | 5318.38
TS5500Exc | SC\60\002\D | SC | 60 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-08-25 14:14 | 2022-09-07 17:30 | 397103.2625 | [6 empty] | 397103 | 297969 | 4.7 | 0 | 0 | 6.4 | 5851
TS5500Shv | MW\42\002\D | MW | 42 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-08-26 07:46 | 2022-08-27 05:30 | 26496.3942 | [6 empty] | 26496 | 19977 | 4.75 | 0 | 0 | 6.38 | 5854
DRE1 | MW\42\007\D | MW | 42 | 7 | D | 6 DL | 100 | 100 | 100 | 2022-08-26 14:40 | 2022-08-31 05:02 | 344409.3703 |  |  |  | 17707 | 344409 | 277416 |  |  | 0 | 29.52 | 0 | 5.44 | 5934.9
TS5500Shv | MW\42\003\B | MW | 42 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-08-27 05:30 | 2022-08-27 16:20 | 13212.7292 | [6 empty] | 13213 | 9561 | 0.96 | 0 | 0 | 12.72 | 5247
PH4100XPC#1 | GG\15\010\B | GG | 15 | 10 | B | 1 Prestrip - Thick | 100 | 55.1279 | 55.1279 | 2022-08-27 08:36 | 2022-09-02 17:53 | 354685.9329 | 354686 | [7 empty] | 0 | 0 | 37.63 | 9.36 | 5559.04
TS5500Shv | GG\15\009\X1 | GG | 15 | 9 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-08-27 16:20 | 2022-08-27 22:58 | 8098.2006 | [6 empty] | 8098 | 5929 | 0.59 | 0 | 0 | 11.82 | 5355
TS5500Shv | GG\14\018\B | GG | 14 | 18 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-08-27 22:58 | 2022-08-29 10:04 | 42790.9417 | [6 empty] | 42791 | 31282 | 3.54 | 0 | 0 | 10.7 | 5459
DRE2 | GG\13\013\D | GG | 13 | 13 | D | 6 DL | 100 | 100 | 100 | 2022-08-28 04:14 | 2022-09-01 22:31 | 374147.3437 |  |  |  | 8711 | 374147 | 165513 |  |  | 0 | 23.48 | 0 | 6.86 | 5785.55
TS5500Shv | GG\14\019\B | GG | 14 | 19 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-08-29 10:04 | 2022-08-31 05:30 | 52960.5133 | [6 empty] | 52961 | 38558 | 3.85 | 0 | 0 | 11.26 | 5425
TS Fleet 5 | GG\16\010\B | GG | 16 | 10 | B | 1 Prestrip - Thick | 44.7717 | 44.7717 | 44.7717 | 2022-08-29 20:12 | 2022-09-05 04:23 | 298276.4494 | 298276 | [7 empty] | 0 | 0 | 30.85 | 9.43 | 5557.08
PH4100A | MW\44\008\A | MW | 44 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-08-29 22:50 | 2022-09-07 08:23 | 347751.3441 | 347751 | [7 empty] | 0 | 0 | 35.43 | 13.21 | 5238.77
DRE1 | MW\42\003\D | MW | 42 | 3 | D | 6 DL | 100 | 100 | 100 | 2022-08-31 05:02 | 2022-09-06 19:33 | 494665.8924 |  |  |  | 11963 | 494666 | 227295 |  |  | 0 | 23.76 | 0 | 6.45 | 5846.64
TS5500Shv | MW\43\008\A | MW | 43 | 8 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-08-31 05:30 | 2022-09-01 19:58 | 46913.0683 | [6 empty] | 46913 | 34009 | 3.4 | 0 | 0 | 13.42 | 5220
TS5500Shv | GG\14\020\B | GG | 14 | 20 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-09-01 19:58 | 2022-09-03 13:17 | 50387.9193 | [6 empty] | 50388 | 36144 | 3.65 | 0 | 0 | 13.38 | 5279
DRE2 | GG\13\018\D | GG | 13 | 18 | D | 6 DL | 100 | 100 | 100 | 2022-09-01 22:31 | 2022-09-06 17:23 | 376110.1526 |  |  |  | 8757 | 376110 | 166382 |  |  | 0 | 23.03 | 0 | 6.91 | 5781.81
PH4100XPC#1 | GG\15\011\B | GG | 15 | 11 | B | 1 Prestrip - Thick | 100 | 54.9372 | 54.9372 | 2022-09-02 17:53 | 2022-09-08 09:18 | 310950.9495 | 310951 | [7 empty] | 0 | 0 | 26.6 | 9.63 | 5541.68
TS5500Shv | MW\42\004\D | MW | 42 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-09-03 13:17 | 2022-09-05 16:42 | 62680.7837 | [6 empty] | 62681 | 47171 | 4.72 | 0 | 0 | 6.4 | 5850
TS Fleet 5 | GG\16\011\X2 | GG | 16 | 11 | X2 | 1 Prestrip - Thick | 37.1573 | 0 | 37.1573 | 2022-09-05 04:23 | 2022-09-08 23:57 | 179458.3733 | 179458 | [7 empty] | 0 | 0 | 17.58 | 0 | 0
TS5500Shv | GG\14\021\B | GG | 14 | 21 | B | 8 Coal Mining | 72.3 | 0 | 72.3 | 2022-09-05 16:42 | 2022-09-06 23:52 | 38015.7602 | [6 empty] | 38016 | 27029 | 2.7 | 0 | 0 | 14.54 | 5206
DRE2 | GG\13\019\D | GG | 13 | 19 | D | 6 DL | 100 | 100 | 100 | 2022-09-06 17:23 | 2022-09-12 20:30 | 481652.8695 |  |  |  | 11214 | 481653 | 213071 |  |  | 0 | 22.4 | 0 | 6.7 | 5800.64
DRE1 | MW\42\008\D | MW | 42 | 8 | D | 6 DL | 100 | 100 | 100 | 2022-09-06 19:33 | 2022-09-11 08:57 | 341394.7299 |  |  |  | 17552 | 341395 | 274988 |  |  | 0 | 29.24 | 0 | 5.31 | 5946.94
TS5500Shv | MW\42\003\D | MW | 42 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-09-06 23:52 | 2022-09-09 03:35 | 63068.8637 | [6 empty] | 63069 | 47426 | 4.74 | 0 | 0 | 6.45 | 5847
PH4100A | MW\43\009\A | MW | 43 | 9 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-09-07 08:23 | 2022-09-22 18:39 | 624510.1512 | 624510 | [7 empty] | 0 | 0 | 50.3 | 12.4 | 5304.89
TS5500Exc | MW\42\006\D | MW | 42 | 6 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-09-07 17:30 | 2022-09-08 17:45 | 30545.696 | [6 empty] | 30546 | 23115 | 2.31 | 0 | 0 | 5.61 | 5919
PH4100XPC#1 | GG\15\012\X2 | GG | 15 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.7434 | 2022-09-08 09:18 | 2022-09-12 04:35 | 205441.1741 | 205441 | [7 empty] | 0 | 0 | 19.46 | 0 | 0
TS5500Exc | RS\20\007\D | RS | 20 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-09-08 17:45 | 2022-09-09 10:21 | 20920.3256 | [6 empty] | 20920 | 15166 | 4.29 | 0 | 0 | 7.58 | 5750
TS Fleet 5 | GG\16\012\X1 | GG | 16 | 12 | X1 | 1 Prestrip - Thick | 45.9034 | 45.9034 | 45.9034 | 2022-09-08 23:57 | 2022-09-11 19:16 | 131950.9752 | 131951 | [7 empty] | 0 | 0 | 13.66 | 14.15 | 5168.42
TS5500Shv | MW\44\008\A | MW | 44 | 8 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-09-09 03:35 | 2022-09-10 17:57 | 46777.62 | [6 empty] | 46778 | 33950 | 3.4 | 0 | 0 | 13.21 | 5239
TS5500Exc | RS\25\004\B | RS | 25 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-09-09 10:21 | 2022-09-10 17:19 | 39011.4911 | [6 empty] | 39011 | 27965 | 2.8 | 0 | 0 | 8.82 | 5609
TS5500Exc | RS\25\005\X | RS | 25 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-09-10 17:19 | 2022-09-11 09:03 | 19806.4109 | [6 empty] | 19806 | 13841 | 1.4 | 0 | 0 | 12.6 | 5189
TS5500Shv | MW\42\005\D | MW | 42 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-09-10 17:57 | 2022-09-12 18:47 | 59551.5316 | [6 empty] | 59552 | 44991 | 4.5 | 0 | 0 | 5.93 | 5891
DRE1 | MW\42\009\D | MW | 42 | 9 | D | 6 DL | 100 | 100 | 100 | 2022-09-11 08:57 | 2022-09-17 04:01 | 433919.4812 |  |  |  | 15809 | 433919 | 244820 |  |  | 0 | 28.46 | 0 | 5.22 | 5953.98
TS5500Exc | MW\45\002\D | MW | 45 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-09-11 09:03 | 2022-09-22 00:52 | 226685.8279 | 226686 | [7 empty] | 0 | 0 | 52.15 | 6.67 | 5822.33
TS Fleet 5 | GG\16\013\X2 | GG | 16 | 13 | X2 | 1 Prestrip - Thick | 45.3588 | 0 | 45.3588 | 2022-09-11 19:16 | 2022-09-15 17:18 | 184288.2193 | 184288 | [7 empty] | 0 | 0 | 14.59 | 0 | 0
PH4100XPC#1 | GG\15\012\B | GG | 15 | 12 | B | 1 Prestrip - Thick | 100 | 79.46 | 79.46 | 2022-09-12 04:35 | 2022-09-14 02:08 | 103122.1648 | 103122 | [7 empty] | 0 | 0 | 10.19 | 10.19 | 5498.6
TS5500Shv | GG\15\012\B | GG | 15 | 12 | B | 1 Prestrip - Thick | 20.54 | 20.54 | 20.54 | 2022-09-12 18:47 | 2022-09-13 19:39 | 26656.5672 | 26657 | [7 empty] | 0 | 0 | 2.63 | 10.19 | 5498.6
DRE2 | GG\13\020\D | GG | 13 | 20 | D | 6 DL | 100 | 100 | 100 | 2022-09-12 20:30 | 2022-09-18 13:07 | 447299.5661 |  |  |  | 10414 | 447300 | 197874 |  |  | 0 | 20.83 | 0 | 6.52 | 5815.65
TS5500Shv | MW\42\006\D | MW | 42 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-09-13 19:39 | 2022-09-14 19:54 | 29570.8333 | [6 empty] | 29571 | 22377 | 2.24 | 0 | 0 | 5.61 | 5919
TS6060#1 | GG\15\008\X1 | GG | 15 | 8 | X1 | 8 Coal Mining | 58.4 | 0 | 58.4 | 2022-09-14 01:13 | 2022-09-14 08:27 | 9774.1428 | [6 empty] | 9774 | 7200 | 0.72 | 0 | 0 | 11.07 | 5405
PH4100XPC#1 | GG\15\013\B | GG | 15 | 13 | B | 1 Prestrip - Thick | 100 | 54.8059 | 54.8059 | 2022-09-14 02:08 | 2022-09-18 16:50 | 252855.0466 | 252855 | [7 empty] | 0 | 0 | 24.75 | 10.69 | 5457.8
TS6060#1 | GG\15\009\X1 | GG | 15 | 9 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-09-14 08:27 | 2022-09-14 15:05 | 8988.1127 | [6 empty] | 8988 | 6580 | 0.66 | 0 | 0 | 11.82 | 5355
TS6060#1 | GG\14\021\B | GG | 14 | 21 | B | 8 Coal Mining | 27.7 | 0 | 27.7 | 2022-09-14 15:05 | 2022-09-15 01:52 | 14587.6786 | [6 empty] | 14588 | 10372 | 1.04 | 0 | 0 | 14.54 | 5206
TS5500Shv | GG\15\008\X2 | GG | 15 | 8 | X2 | 1 Prestrip - Thick | 26.7322 | 0 | 26.7322 | 2022-09-14 19:54 | 2022-09-15 19:00 | 24755.4667 | 24755 | [7 empty] | 0 | 0 | 2.47 | 0 | 0
TS6060#1 | GG\14\022\B | GG | 14 | 22 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-09-15 01:52 | 2022-09-16 17:49 | 54067.0678 | [6 empty] | 54067 | 38151 | 3.82 | 0 | 0 | 16.09 | 5074
TS Fleet 5 | GG\15\008\X2 | GG | 15 | 8 | X2 | 1 Prestrip - Thick | 33.2775 | 0 | 33.2775 | 2022-09-15 17:18 | 2022-09-16 09:01 | 30816.6743 | 30817 | [7 empty] | 0 | 0 | 3.08 | 0 | 0
TS5500Shv | GG\13\013\D | GG | 13 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-09-15 19:00 | 2022-09-17 09:48 | 47315.1634 | [6 empty] | 47315 | 35317 | 4.8 | 0 | 0 | 6.86 | 5786
TS Fleet 5 | GG\15\009\X2 | GG | 15 | 9 | X2 | 1 Prestrip - Thick | 45.419 | 0 | 45.419 | 2022-09-16 09:01 | 2022-09-17 05:19 | 39802.835 | 39803 | [7 empty] | 0 | 0 | 3.98 | 0 | 0
TS6060#1 | GG\14\023\B | GG | 14 | 23 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-09-16 17:49 | 2022-09-17 23:20 | 39953.018 | [6 empty] | 39953 | 28850 | 2.9 | 0 | 0 | 12.47 | 5318
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2022-09-17 04:01 | 2022-09-19 04:01
TS Fleet 5 | GG\16\018\X2 | GG | 16 | 18 | X2 | 1 Prestrip - Thick | 45.7389 | 0 | 45.7389 | 2022-09-17 05:19 | 2022-09-19 19:57 | 122731.6746 | 122732 | [7 empty] | 0 | 0 | 12.22 | 0 | 0
TS5500Shv | GG\13\018\D | GG | 13 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-09-17 09:48 | 2022-09-19 01:35 | 48518.3625 | [6 empty] | 48518 | 36187 | 4.8 | 0 | 0 | 6.91 | 5782
TS6060#1 | RS\25\005\A | RS | 25 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-09-17 23:20 | 2022-09-25 02:50 | 176957.9464 | 176958 | [7 empty] | 0 | 0 | 17.82 | 18.74 | 4791.74
DRE2 | GG\13\021\D | GG | 13 | 21 | D | 6 DL | 100 | 100 | 100 | 2022-09-18 13:07 | 2022-09-23 22:33 | 423791.8191 |  |  |  | 7892 | 423792 | 189404 |  |  | 0 | 19.74 | 0 | 6.49 | 5817.79
PH4100XPC#1 | GG\15\008\X2 | GG | 15 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 39.9903 | 2022-09-18 16:50 | 2022-09-19 09:12 | 37033.117 | 37033 | [7 empty] | 0 | 0 | 3.7 | 0 | 0
TS5500Shv | MW\42\007\D | MW | 42 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-09-19 01:35 | 2022-09-21 04:33 | 62140.5125 | [6 empty] | 62141 | 47141 | 4.71 | 0 | 0 | 5.44 | 5935
DRE1 | RS\21\003\D | RS | 21 | 3 | D | 6 DL | 100 | 100 | 100 | 2022-09-19 04:01 | 2022-09-24 18:04 | 418356.9059 |  |  |  | 23877 | 418357 | 317221 |  |  | 0 | 31.01 | 0 | 6.05 | 5888.55
PH4100XPC#1 | GG\15\008\B | GG | 15 | 8 | B | 1 Prestrip - Thick | 100 | 72.2924 | 72.2924 | 2022-09-19 09:12 | 2022-09-20 04:29 | 43640.8358 | 43641 | [7 empty] | 0 | 0 | 4.37 | 10.27 | 5486.52
TS Fleet 5 | GG\15\008\B | GG | 15 | 8 | B | 1 Prestrip - Thick | 45.419 | 27.7076 | 27.7076 | 2022-09-19 19:57 | 2022-09-20 04:29 | 16726.3151 | 16726 | [7 empty] | 0 | 0 | 1.67 | 10.27 | 5486.52
PH4100XPC#1 | GG\15\009\X2 | GG | 15 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.581 | 2022-09-20 04:29 | 2022-09-21 01:37 | 47831.996 | 47832 | [7 empty] | 0 | 0 | 4.78 | 0 | 0
TS Fleet 5 | GG\16\019\X2 | GG | 16 | 19 | X2 | 1 Prestrip - Thick | 45.5995 | 0 | 45.5995 | 2022-09-20 04:29 | 2022-09-22 08:27 | 101856.3017 | 101856 | [7 empty] | 0 | 0 | 10.31 | 0 | 0
PH4100XPC#1 | GG\15\009\B | GG | 15 | 9 | B | 1 Prestrip - Thick | 100 | 97.5128 | 97.5128 | 2022-09-21 01:37 | 2022-09-22 09:23 | 71915.845 | 71916 | [7 empty] | 0 | 0 | 7.19 | 9.67 | 5538.82
TS5500Shv | GG\13\019\D | GG | 13 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-09-21 04:33 | 2022-09-23 10:24 | 65674.3276 | [6 empty] | 65674 | 49061 | 4.91 | 0 | 0 | 6.7 | 5801
TS5500Exc | MW\42\009\D | MW | 42 | 9 | D | 7 PostStrip | 33.6255 | 0 | 33.6255 | 2022-09-22 00:52 | 2022-09-22 22:00 | 18680.8141 |  |  | 18681 | [5 empty] | 0 | 0 | 0 | 5.22 | 5953.98
TS Fleet 5 | GG\15\009\B | GG | 15 | 9 | B | 1 Prestrip - Thick | 45.419 | 2.4872 | 2.4872 | 2022-09-22 08:27 | 2022-09-22 09:23 | 1834.3078 | 1834 | [7 empty] | 0 | 0 | 0.18 | 9.67 | 5538.82
TS Fleet 5 | GG\16\020\B | GG | 16 | 20 | B | 1 Prestrip - Thick | 2.4003 | 2.4003 | 2.4003 | 2022-09-22 09:23 | 2022-09-22 14:04 | 9192.816 | 9193 | [7 empty] | 0 | 0 | 0.89 | 15.24 | 5127.95
PH4100XPC#1 | GG\15\018\X2 | GG | 15 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.3798 | 2022-09-22 09:23 | 2022-09-25 05:26 | 152804.4236 | 152804 | [7 empty] | 0 | 0 | 16.81 | 0 | 0
TS Fleet 5 | GG\16\020\B | GG | 16 | 20 | B | 1 Prestrip - Thick | 33.6995 | 33.6995 | 33.6995 | 2022-09-22 14:04 | 2022-09-25 07:55 | 129063.6569 | 129064 | [7 empty] | 0 | 0 | 12.44 | 15.24 | 5127.95
PH4100A | MW\44\009\A | MW | 44 | 9 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-09-22 18:39 | 2022-10-05 00:32 | 496819.4899 | 496819 | [7 empty] | 0 | 0 | 47.87 | 12.57 | 5292.52
TS5500Exc | MW\45\003\D | MW | 45 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-09-22 22:00 | 2022-10-02 16:04 | 207128.9963 | 207129 | [7 empty] | 0 | 0 | 21.52 | 6.74 | 5820.88
TS5500Shv | MW\43\009\A | MW | 43 | 9 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-09-23 10:24 | 2022-09-25 06:21 | 53575.2264 | [6 empty] | 53575 | 39077 | 3.32 | 0 | 0 | 12.4 | 5305
DRE2 | GG\13\022\D | GG | 13 | 22 | D | 6 DL | 100 | 100 | 100 | 2022-09-23 22:33 | 2022-09-29 10:47 | 432894.3739 |  |  |  | 10079 | 432894 | 191502 |  |  | 0 | 20.19 | 0 | 6.4 | 5821.16
DRE1 | RS\21\004\D | RS | 21 | 4 | D | 6 DL | 100 | 100 | 100 | 2022-09-24 18:04 | 2022-09-29 18:56 | 377154.8597 |  |  |  | 21525 | 377155 | 285980 |  |  | 0 | 30.74 | 0 | 6.52 | 5847.33
TS6060#1 | RS\27\003\X | RS | 27 | 3 | X | 1 Prestrip - Thick | 22.0242 | 22.0242 | 22.0242 | 2022-09-25 02:50 | 2022-09-26 20:52 | 42554.2491 | 42554 | [7 empty] | 0 | 0 | 8.78 | 12.28 | 5209.71
PH4100XPC#1 | GG\15\018\B | GG | 15 | 18 | B | 1 Prestrip - Thick | 100 | 55.4707 | 55.4707 | 2022-09-25 05:26 | 2022-09-26 15:28 | 77009.9142 | 77010 | [7 empty] | 0 | 0 | 7.79 | 10.69 | 5459.66
TS5500Shv | MW\42\008\D | MW | 42 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-09-25 06:21 | 2022-09-27 10:01 | 63008.5152 | [6 empty] | 63009 | 47916 | 4.79 | 0 | 0 | 5.31 | 5947
TS Fleet 5 | GG\15\018\B | GG | 15 | 18 | B | 1 Prestrip - Thick | 45.419 | 44.5293 | 44.5293 | 2022-09-25 07:55 | 2022-09-26 15:28 | 61819.8718 | 61820 | [7 empty] | 0 | 0 | 6.26 | 10.69 | 5459.66
TS Fleet 5 | GG\16\021\B | GG | 16 | 21 | B | 1 Prestrip - Thick | 45.9355 | 45.9355 | 45.9355 | 2022-09-26 15:28 | 2022-09-30 00:55 | 159660.6538 | 159661 | [7 empty] | 0 | 0 | 17 | 14.89 | 5184.21
PH4100XPC#1 | GG\15\019\X2 | GG | 15 | 19 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.5468 | 2022-09-26 15:28 | 2022-09-29 00:49 | 129655.0554 | 129655 | [7 empty] | 0 | 0 | 12.59 | 0 | 0
TS6060#1 | RS\27\004\X | RS | 27 | 4 | X | 1 Prestrip - Thick | 54.3154 | 54.3154 | 54.3154 | 2022-09-26 20:52 | 2022-10-07 03:48 | 249929.7901 | 249930 | [7 empty] | 0 | 0 | 25.32 | 12.36 | 5207.33
TS5500Shv | GG\13\020\D | GG | 13 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-09-27 10:01 | 2022-09-29 15:09 | 64799.6758 | [6 empty] | 64800 | 48445 | 4.84 | 0 | 0 | 6.52 | 5816
PH4100XPC#1 | GG\15\019\B | GG | 15 | 19 | B | 1 Prestrip - Thick | 100 | 76.5055 | 76.5055 | 2022-09-29 00:49 | 2022-09-30 14:10 | 84529.688 | 84530 | [7 empty] | 0 | 0 | 8.3 | 11.46 | 5410.67
DRE2 | GG\13\023\D | GG | 13 | 23 | D | 6 DL | 100 | 100 | 100 | 2022-09-29 10:47 | 2022-10-05 12:48 | 478082.1343 |  |  |  | 11131 | 478082 | 211492 |  |  | 0 | 22.31 | 0 | 6.25 | 5833.73
TS5500Shv | MW\42\009\D | MW | 42 | 9 | D | 7 PostStrip | 66.3745 | 0 | 66.3745 | 2022-09-29 15:09 | 2022-10-01 01:33 | 36874.6569 |  |  | 36875 | [5 empty] | 0 | 0 | 0 | 5.22 | 5953.98
DRE1 | RS\21\005\D | RS | 21 | 5 | D | 6 DL | 100 | 100 | 100 | 2022-09-29 18:56 | 2022-10-04 08:25 | 341614.2173 |  |  |  | 17564 | 341614 | 275165 |  |  | 0 | 29.28 | 0 | 6.86 | 5816.89
TS Fleet 5 | GG\15\019\B | GG | 15 | 19 | B | 1 Prestrip - Thick | 45.419 | 23.4945 | 23.4945 | 2022-09-30 00:55 | 2022-09-30 14:10 | 25958.7549 | 25959 | [7 empty] | 0 | 0 | 2.55 | 11.46 | 5410.67
PH4100XPC#1 | GG\15\020\B | GG | 15 | 20 | B | 1 Prestrip - Thick | 100 | 55.8201 | 55.8201 | 2022-09-30 14:10 | 2022-10-03 22:35 | 191395.1057 | 191395 | [7 empty] | 0 | 0 | 18.94 | 14.49 | 5191.38
TS Fleet 5 | GG\16\022\B | GG | 16 | 22 | B | 1 Prestrip - Thick | 38.7246 | 38.7246 | 38.7246 | 2022-09-30 14:10 | 2022-10-03 03:43 | 120630.6884 | 120631 | [7 empty] | 0 | 0 | 12.47 | 16.7 | 5035.36
TS5500Shv | MW\42\009\D | MW | 42 | 9 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-10-01 01:33 | 2022-10-02 04:23 | 32707.6186 | [6 empty] | 32708 | 24932 | 2.27 | 0 | 0 | 5.22 | 5954
TS5500Shv | GG\13\021\D | GG | 13 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-10-02 04:23 | 2022-10-04 08:40 | 63760.3665 | [6 empty] | 63760 | 47668 | 4.77 | 0 | 0 | 6.49 | 5818
TS5500Exc | MW\42\009\D | MW | 42 | 9 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-10-02 16:04 | 2022-10-03 18:53 | 33785.8917 | [6 empty] | 33786 | 25754 | 2.34 | 0 | 0 | 5.22 | 5954
TS Fleet 5 | GG\16\023\B | GG | 16 | 23 | B | 1 Prestrip - Thick | 45.5622 | 45.5622 | 45.5622 | 2022-10-03 03:43 | 2022-10-07 19:13 | 218563.3212 | 218563 | [7 empty] | 0 | 0 | 15.49 | 0 | 0
TS5500Exc | MW\45\005\B | MW | 45 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-10-03 18:53 | 2022-10-16 23:20 | 280038.5884 | 280039 | [7 empty] | 0 | 0 | 28.96 | 11.17 | 5371.2
PH4100XPC#1 | GG\15\021\B | GG | 15 | 21 | B | 1 Prestrip - Thick | 100 | 55.133 | 55.133 | 2022-10-03 22:35 | 2022-10-07 08:20 | 189193.9941 | 189194 | [7 empty] | 0 | 0 | 18.79 | 14.66 | 5199.4
DRE1 | RS\21\006\D | RS | 21 | 6 | D | 6 DL | 100 | 100 | 100 | 2022-10-04 08:25 | 2022-10-10 19:12 | 483034.1663 |  |  |  | 17673 | 483034 | 272796 |  |  | 0 | 28.06 | 0 | 7.02 | 5801.66
TS5500Shv | GG\13\022\D | GG | 13 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-10-04 08:40 | 2022-10-06 08:27 | 58271.7695 | [6 empty] | 58272 | 43666 | 4.36 | 0 | 0 | 6.4 | 5821
PH4100A | MW\43\007\B | MW | 43 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-10-05 00:32 | 2022-10-06 04:55 | 49258.3585 | 49258 | [7 empty] | 0 | 0 | 4.94 | 9.72 | 5481.1
DRE2 | GG\13\024\D | GG | 13 | 24 | D | 6 DL | 100 | 100 | 100 | 2022-10-05 12:48 | 2022-10-08 20:23 | 260572.7703 |  |  |  | 4299 | 260573 | 75021 |  |  | 0 | 19.09 | 0 | 6.22 | 5840.36
PH4100A | MW\44\007\B | MW | 44 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-10-06 04:55 | 2022-10-07 07:39 | 46411.1147 | 46411 | [7 empty] | 0 | 0 | 4.66 | 9.83 | 5474.03
TS5500Shv | MW\44\009\A | MW | 44 | 9 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-10-06 08:27 | 2022-10-07 20:55 | 44475.4233 | [6 empty] | 44475 | 32396 | 3.32 | 0 | 0 | 12.57 | 5293
TS6060#1 | RS\27\005\X | RS | 27 | 5 | X | 1 Prestrip - Thick | 2.7049 | 2.7049 | 2.7049 | 2022-10-07 03:48 | 2022-10-07 19:37 | 16111.6303 | 16112 | [7 empty] | 0 | 0 | 1.63 | 12.52 | 5202.72
PH4100A | MW\43\008\B | MW | 43 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-10-07 07:39 | 2022-10-08 04:19 | 35877.7244 | 35878 | [7 empty] | 0 | 0 | 3.59 | 10.06 | 5438.8
PH4100XPC#1 | GG\15\022\B | GG | 15 | 22 | B | 1 Prestrip - Thick | 100 | 54.7867 | 54.7867 | 2022-10-07 08:20 | 2022-10-10 10:35 | 169474.8536 | 169475 | [7 empty] | 0 | 0 | 17.13 | 16.4 | 5054.03
TS Fleet 5 | GG\17\003\X1 | GG | 17 | 3 | X1 | 1 Prestrip - Thick | 46.7004 | 46.7004 | 46.7004 | 2022-10-07 19:13 | 2022-10-21 08:46 | 638068.4026 | 638068 | [7 empty] | 0 | 0 | 44.36 | 10.19 | 5342.18
TS6060#1 | RS\27\005\X | RS | 27 | 5 | X | 1 Prestrip - Thick | 17.5347 | 17.5347 | 17.5347 | 2022-10-07 19:37 | 2022-10-12 02:14 | 104445.8891 | 104446 | [7 empty] | 0 | 0 | 10.59 | 12.52 | 5202.72
TS5500Shv | MW\43\007\B | MW | 43 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-10-07 20:55 | 2022-10-09 05:03 | 39180.5596 | [6 empty] | 39181 | 28845 | 2.88 | 0 | 0 | 9.72 | 5481
PH4100A | MW\44\008\B | MW | 44 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-10-08 04:19 | 2022-10-09 00:13 | 34543.3726 | 34543 | [7 empty] | 0 | 0 | 3.46 | 9.99 | 5450.41
DRE2 | GG\15\012\B | GG | 15 | 12 | B | 6 DL | 100 | 0 | 100 | 2022-10-08 20:23 | 2022-10-11 10:52 | 204562.2161 |  |  |  |  | 204562 | 170469 |  |  | 0 | 16.85 | 0 | 10.19 | 5498.6
PH4100A | MW\43\009\B | MW | 43 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-10-09 00:13 | 2022-10-09 22:08 | 38051.9746 | 38052 | [7 empty] | 0 | 0 | 3.25 | 9.45 | 5518.86
TS5500Shv | MW\43\008\B | MW | 43 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-10-09 05:03 | 2022-10-10 12:02 | 37779.1923 | [6 empty] | 37779 | 27826 | 2.78 | 0 | 0 | 10.06 | 5439
PH4100A | MW\44\009\B | MW | 44 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-10-09 22:08 | 2022-10-10 16:26 | 31771.7661 | 31772 | [7 empty] | 0 | 0 | 3.28 | 9.51 | 5512.65
PH4100XPC#1 | GG\15\023\B | GG | 15 | 23 | B | 1 Prestrip - Thick | 100 | 55.443 | 55.443 | 2022-10-10 10:35 | 2022-10-13 05:38 | 157162.1446 | 157162 | [7 empty] | 0 | 0 | 16.1 | 12.78 | 5303.76
TS5500Shv | MW\43\009\B | MW | 43 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-10-10 12:02 | 2022-10-11 23:07 | 42772.0033 | [6 empty] | 42772 | 31635 | 2.72 | 0 | 0 | 9.45 | 5519
PH4100A | RS\26\003\X | RS | 26 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-10-10 16:26 | 2022-10-15 10:58 | 194280.0079 | 194280 | [7 empty] | 0 | 0 | 39.77 | 12.31 | 5200.8
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2022-10-10 19:12 | 2022-10-12 19:12
DRE2 | GG\15\011\B | GG | 15 | 11 | B | 6 DL | 100 | 0 | 100 | 2022-10-11 10:52 | 2022-10-14 18:38 | 261188.5553 |  |  |  |  | 261189 | 200914 |  |  | 0 | 17.1 | 0 | 9.63 | 5541.68
TS5500Shv | MW\44\007\B | MW | 44 | 7 | B | 8 Coal Mining | 87.8 | 0 | 87.8 | 2022-10-11 23:07 | 2022-10-13 03:19 | 34395.6481 | [6 empty] | 34396 | 25322 | 2.53 | 0 | 0 | 9.83 | 5474
TS6060#1 | GG\15\012\B | GG | 15 | 12 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-10-12 02:14 | 2022-10-12 20:06 | 24177.1292 | [6 empty] | 24177 | 17727 | 1.77 | 0 | 0 | 10.19 | 5499
DRE1 | MW\43\002\D | MW | 43 | 2 | D | 6 DL | 100 | 0 | 100 | 2022-10-12 19:12 | 2022-10-17 19:55 | 376685.1441 |  |  |  | 15339 | 376685 | 182255 |  |  | 0 | 35 | 0 | 6.5 | 5842.35
TS6060#1 | RS\27\006\X | RS | 27 | 6 | X | 1 Prestrip - Thick | 59.1226 | 59.1226 | 59.1226 | 2022-10-12 20:06 | 2022-11-03 05:46 | 523284.2905 | 523284 | [7 empty] | 0 | 0 | 40.26 | 13.02 | 5165.56
TS5500Shv | MW\44\008\B | MW | 44 | 8 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-10-13 03:19 | 2022-10-13 18:39 | 18699.0284 | [6 empty] | 18699 | 13773 | 1.38 | 0 | 0 | 9.99 | 5450
PH4100XPC#1 | GG\15\024\D | GG | 15 | 24 | D | 1 Prestrip - Thick | 100 | 55.4889 | 55.4889 | 2022-10-13 05:38 | 2022-10-15 03:41 | 108117.5873 | 108118 | [7 empty] | 0 | 0 | 22.87 | 6.3 | 5834.04
TS5500Shv | MW\44\009\B | MW | 44 | 9 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-10-13 18:39 | 2022-10-14 09:04 | 17577.0455 | [6 empty] | 17577 | 12992 | 1.35 | 0 | 0 | 9.51 | 5513
TS5500Shv | RS\21\003\D | RS | 21 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-10-14 09:04 | 2022-10-16 16:07 | 67131.6773 | [6 empty] | 67132 | 49062 | 4.42 | 0 | 0 | 6.05 | 5889
DRE2 | GG\15\010\B | GG | 15 | 10 | B | 6 DL | 100 | 0 | 100 | 2022-10-14 18:38 | 2022-10-17 10:22 | 208648.8093 |  |  |  |  | 208649 | 173874 |  |  | 0 | 18.36 | 0 | 9.36 | 5559.04
PH4100XPC#1 | GG\16\003\X1 | GG | 16 | 3 | X1 | 1 Prestrip - Thick | 100 | 52.8573 | 52.8573 | 2022-10-15 03:41 | 2022-10-29 15:22 | 780747.8088 | 780748 | [7 empty] | 0 | 0 | 47.76 | 10.11 | 5350.69
PH4100A | RS\26\004\X | RS | 26 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-10-15 10:58 | 2022-10-26 19:17 | 461246.6313 | 461247 | [7 empty] | 0 | 0 | 46.68 | 12.4 | 5198.77
TS5500Shv | GG\13\023\D | GG | 13 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-10-16 16:07 | 2022-10-18 15:20 | 57577.9885 | [6 empty] | 57578 | 43387 | 4.35 | 0 | 0 | 6.25 | 5834
TS5500Exc | MW\44\007\B | MW | 44 | 7 | B | 8 Coal Mining | 12.2 | 0 | 12.2 | 2022-10-16 23:20 | 2022-10-17 03:07 | 4772.0719 | [6 empty] | 4772 | 3513 | 0.35 | 0 | 0 | 9.83 | 5474
TS5500Exc | MW\44\008\B | MW | 44 | 8 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-10-17 03:07 | 2022-10-17 18:27 | 19315.4799 | [6 empty] | 19315 | 14227 | 1.42 | 0 | 0 | 9.99 | 5450
DRE2 | GG\15\009\B | GG | 15 | 9 | B | 6 DL | 100 | 0 | 100 | 2022-10-17 10:22 | 2022-10-20 09:03 | 231423.0625 |  |  |  |  | 231423 | 192853 |  |  | 0 | 19.28 | 0 | 9.67 | 5538.82
TS5500Exc | MW\44\009\B | MW | 44 | 9 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-10-17 18:27 | 2022-10-18 08:52 | 18156.5085 | [6 empty] | 18157 | 13420 | 1.4 | 0 | 0 | 9.51 | 5513
DRE1 | MW\43\003\D | MW | 43 | 3 | D | 6 DL | 100 | 0 | 100 | 2022-10-17 19:55 | 2022-10-23 16:58 | 440159.1687 |  |  |  | 31303 | 440159 | 316511 |  |  | 0 | 35 | 0 | 6.54 | 5838.27
TS5500Exc | RS\26\003\X | RS | 26 | 3 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-10-18 08:52 | 2022-10-18 16:59 | 10215.4284 | [6 empty] | 10215 | 7158 | 1.21 | 0 | 0 | 12.31 | 5201
TS5500Shv | RS\21\004\D | RS | 21 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-10-18 15:20 | 2022-10-20 15:37 | 58873.1155 | [6 empty] | 58873 | 42954 | 4.29 | 0 | 0 | 6.52 | 5847
TS5500Exc | MW\45\005\B | MW | 45 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-10-18 16:59 | 2022-10-19 09:32 | 20852.9103 | [6 empty] | 20853 | 15225 | 1.56 | 0 | 0 | 11.17 | 5371
TS5500Exc | RS\25\005\A | RS | 25 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-10-19 09:32 | 2022-10-20 23:41 | 48050.7907 | [6 empty] | 48051 | 32508 | 3.27 | 0 | 0 | 18.74 | 4792
DRE2 | GG\15\008\B | GG | 15 | 8 | B | 6 DL | 100 | 0 | 100 | 2022-10-20 09:03 | 2022-10-23 09:53 | 238476.1691 |  |  |  |  | 238476 | 198730 |  |  | 0 | 19.88 | 0 | 10.27 | 5486.52
TS5500Shv | GG\13\024\D | GG | 13 | 24 | D | 7 PostStrip | 100 | 0 | 100 | 2022-10-20 15:37 | 2022-10-21 17:53 | 28150.3407 |  |  | 28150 | [5 empty] | 0 | 0 | 0 | 6.22 | 5840.36
TS5500Exc | MW\45\006\B | MW | 45 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-10-20 23:41 | 2022-11-04 18:26 | 314634.3254 | 314634 | [7 empty] | 0 | 0 | 30.16 | 10.34 | 5444.94
TS Fleet 5 | GG\17\004\X1 | GG | 17 | 4 | X1 | 1 Prestrip - Thick | 45.965 | 45.965 | 45.965 | 2022-10-21 08:46 | 2022-10-29 20:02 | 398404.9378 | 398405 | [7 empty] | 0 | 0 | 40.55 | 10.1 | 5344.46
TS5500Shv | GG\13\024\D | GG | 13 | 24 | D | 8 Coal Mining | 51.6 | 0 | 51.6 | 2022-10-21 17:53 | 2022-10-22 08:33 | 17896.8503 | [6 empty] | 17897 | 13541 | 2.43 | 0 | 0 | 6.22 | 5840
TS5500Shv | GG\15\012\B | GG | 15 | 12 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-10-22 08:33 | 2022-10-23 02:25 | 21783.354 | [6 empty] | 21783 | 15972 | 1.59 | 0 | 0 | 10.19 | 5499
TS5500Shv | RS\21\005\D | RS | 21 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-10-23 02:25 | 2022-10-25 02:11 | 58240.4624 | [6 empty] | 58240 | 42390 | 4.24 | 0 | 0 | 6.86 | 5817
DRE2 | GG\15\007\B | GG | 15 | 7 | B | 6 DL | 100 | 0 | 100 | 2022-10-23 09:53 | 2022-10-26 17:29 | 260601.8756 |  |  |  |  | 260602 | 200463 |  |  | 0 | 20.08 | 0 | 10.35 | 5450.06
DRE1 | MW\43\004\D | MW | 43 | 4 | D | 6 DL | 100 | 100 | 100 | 2022-10-23 16:58 | 2022-10-29 08:55 | 424205.864 |  |  |  | 24211 | 424206 | 321656 |  |  | 0 | 35.15 | 0 | 6.47 | 5844.02
TS5500Shv | GG\15\011\B | GG | 15 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-10-25 02:11 | 2022-10-26 18:21 | 48980.9528 | [6 empty] | 48981 | 36035 | 3.6 | 0 | 0 | 9.63 | 5542
DRE2 | GG\15\006\B | GG | 15 | 6 | B | 6 DL | 100 | 0 | 100 | 2022-10-26 17:29 | 2022-10-30 00:54 | 260009.3759 |  |  |  |  | 260009 | 200007 |  |  | 0 | 20.28 | 0 | 10.36 | 5416.87
TS5500Shv | RS\21\006\D | RS | 21 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2022-10-26 18:21 | 2022-10-29 05:06 | 62981.582 |  |  | 62982 | [5 empty] | 0 | 0 | 0 | 7.02 | 5801.66
PH4100A | RS\26\005\X | RS | 26 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-10-26 19:17 | 2022-11-10 04:38 | 588917.845 | 588918 | [7 empty] | 0 | 0 | 59.54 | 12.56 | 5195.14
TS5500Shv | GG\15\010\B | GG | 15 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-10-29 05:06 | 2022-10-30 22:09 | 50057.854 | [6 empty] | 50058 | 36894 | 3.69 | 0 | 0 | 9.36 | 5559
DRE1 | MW\43\005\D | MW | 43 | 5 | D | 6 DL | 100 | 100 | 100 | 2022-10-29 08:55 | 2022-11-02 14:50 | 318040.9328 |  |  |  | 16352 | 318041 | 256177 |  |  | 0 | 27.32 | 0 | 5.99 | 5885.05
PH4100XPC#1 | GG\16\004\X1 | GG | 16 | 4 | X1 | 1 Prestrip - Thick | 100 | 55.137 | 55.137 | 2022-10-29 15:22 | 2022-11-07 01:52 | 468748.1217 | 468748 | [7 empty] | 0 | 0 | 45.75 | 9.98 | 5359.11
TS Fleet 5 | GG\17\005\X1 | GG | 17 | 5 | X1 | 1 Prestrip - Thick | 46.3398 | 46.3398 | 46.3398 | 2022-10-29 20:02 | 2022-11-06 14:43 | 365895.2938 | 365895 | [7 empty] | 0 | 0 | 42.06 | 10.32 | 5340.03
DRE2 | GG\15\005\B | GG | 15 | 5 | B | 6 DL | 100 | 100 | 100 | 2022-10-30 00:54 | 2022-11-01 19:44 | 218787.4849 |  |  |  |  | 218787 | 190250 |  |  | 0 | 18.83 | 0 | 11.15 | 5353.38
TS5500Shv | GG\16\003\X1 | GG | 16 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2022-10-30 22:09 | 2022-10-31 18:25 | 24704.7637 | [6 empty] | 24705 | 18351 | 1.28 | 0 | 0 | 10.11 | 5351
TS5500Shv | GG\15\009\B | GG | 15 | 9 | B | 8 Coal Mining | 53.1 | 0 | 53.1 | 2022-10-31 18:25 | 2022-11-01 16:53 | 27393.4757 | [6 empty] | 27393 | 20114 | 2.01 | 0 | 0 | 9.67 | 5539
TS5500Shv | RS\21\006\D | RS | 21 | 6 | D | 8 Coal Mining | 6.3 | 0 | 6.3 | 2022-11-01 16:53 | 2022-11-01 20:40 | 4609.8084 | [6 empty] | 4610 | 3354 | 0.27 | 0 | 0 | 7.02 | 5802
DRE2 | GG\14\012\D | GG | 14 | 12 | D | 6 DL | 100 | 100 | 100 | 2022-11-01 19:44 | 2022-11-08 02:19 | 493017.9805 |  |  |  | 11479 | 493018 | 218099 |  |  | 0 | 22.92 | 0 | 6.56 | 5811.41
TS5500Shv | MW\43\002\D | MW | 43 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2022-11-01 20:40 | 2022-11-02 16:45 | 21539.8804 |  |  | 21540 | [5 empty] | 0 | 0 | 0 | 6.5 | 5842.35
DRE1 | MW\43\006\D | MW | 43 | 6 | D | 6 DL | 100 | 100 | 100 | 2022-11-02 14:50 | 2022-11-07 05:48 | 346311.9284 |  |  |  | 17805 | 346312 | 278949 |  |  | 0 | 29.67 | 0 | 5.62 | 5918.42
TS5500Shv | MW\43\002\D | MW | 43 | 2 | D | 8 Coal Mining | 68.5 | 0 | 68.5 | 2022-11-02 16:45 | 2022-11-03 13:07 | 24823.8527 | [6 empty] | 24824 | 18698 | 3.15 | 0 | 0 | 6.5 | 5842
TS6060#1 | GG\13\024\D | GG | 13 | 24 | D | 8 Coal Mining | 48.4 | 0 | 48.4 | 2022-11-03 05:46 | 2022-11-03 18:10 | 16797.5342 | [6 empty] | 16798 | 12709 | 2.28 | 0 | 0 | 6.22 | 5840
TS5500Shv | MW\43\003\D | MW | 43 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-11-03 13:07 | 2022-11-05 16:51 | 63093.5526 | [6 empty] | 63094 | 47445 | 4.74 | 0 | 0 | 6.54 | 5838
TS6060#1 | GG\15\009\B | GG | 15 | 9 | B | 8 Coal Mining | 46.9 | 0 | 46.9 | 2022-11-03 18:10 | 2022-11-04 12:04 | 24219.7203 | [6 empty] | 24220 | 17784 | 1.78 | 0 | 0 | 9.67 | 5539
TS6060#1 | RS\25\005\B | RS | 25 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-11-04 12:04 | 2022-11-05 13:31 | 26261.9382 | 26262 | [7 empty] | 0 | 0 | 2.64 | 8.8 | 5607.58
TS5500Exc | RS\26\004\X | RS | 26 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-11-04 18:26 | 2022-11-05 07:32 | 16487.5131 | [6 empty] | 16488 | 11535 | 1.16 | 0 | 0 | 12.4 | 5199
TS5500Exc | RS\21\006\D | RS | 21 | 6 | D | 8 Coal Mining | 93.7 | 0 | 93.7 | 2022-11-05 07:32 | 2022-11-07 14:05 | 68720.3315 | [6 empty] | 68720 | 50005 | 3.98 | 0 | 0 | 7.02 | 5802
TS6060#1 | GG\15\008\B | GG | 15 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-11-05 13:31 | 2022-11-07 04:39 | 52955.4052 | [6 empty] | 52955 | 38671 | 3.87 | 0 | 0 | 10.27 | 5487
TS5500Shv | GG\15\006\B | GG | 15 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-11-05 16:51 | 2022-11-07 09:10 | 49163.9752 | [6 empty] | 49164 | 36012 | 3.61 | 0 | 0 | 10.36 | 5417
TS Fleet 5 | GG\16\003\X2 | GG | 16 | 3 | X2 | 1 Prestrip - Thick | 45.419 | 0 | 45.419 | 2022-11-06 14:43 | 2022-11-08 01:48 | 68748.45 | 68748 | [7 empty] | 0 | 0 | 4.86 | 0 | 0
PH4100XPC#1 | GG\16\003\X2 | GG | 16 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.581 | 2022-11-07 01:52 | 2022-11-08 14:22 | 82616.6174 | 82617 | [7 empty] | 0 | 0 | 5.84 | 0 | 0
TS6060#1 | GG\15\007\B | GG | 15 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-11-07 04:39 | 2022-11-08 18:38 | 51402.9578 | [6 empty] | 51403 | 37585 | 3.75 | 0 | 0 | 10.35 | 5450
DRE1 | MW\43\007\D | MW | 43 | 7 | D | 6 DL | 100 | 100 | 100 | 2022-11-07 05:48 | 2022-11-11 20:19 | 344848.8117 |  |  |  | 17730 | 344849 | 277770 |  |  | 0 | 29.54 | 0 | 5.44 | 5934.93
TS5500Shv | GG\16\004\X1 | GG | 16 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2022-11-07 09:10 | 2022-11-08 00:28 | 18657.1586 | [6 empty] | 18657 | 13909 | 1.36 | 0 | 0 | 9.98 | 5359
TS5500Exc | RS\25\005\B | RS | 25 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-11-07 14:05 | 2022-11-08 21:29 | 39544.19 | [6 empty] | 39544 | 28350 | 2.85 | 0 | 0 | 8.8 | 5608
TS5500Shv | GG\15\005\B | GG | 15 | 5 | B | 8 Coal Mining | 52.7 | 0 | 52.7 | 2022-11-08 00:28 | 2022-11-08 21:57 | 26190.1586 | [6 empty] | 26190 | 19126 | 1.92 | 0 | 0 | 11.15 | 5353
TS Fleet 5 | GG\16\004\X2 | GG | 16 | 4 | X2 | 1 Prestrip - Thick | 45.419 | 0 | 45.419 | 2022-11-08 01:48 | 2022-11-09 06:51 | 56947.8788 | 56948 | [7 empty] | 0 | 0 | 5.54 | 0 | 0
DRE2 | GG\14\011\D | GG | 14 | 11 | D | 6 DL | 100 | 100 | 100 | 2022-11-08 02:19 | 2022-11-14 12:28 | 504732.102 |  |  |  | 9157 | 504732 | 219769 |  |  | 0 | 22.87 | 0 | 6.22 | 5840.9
PH4100XPC#1 | GG\16\003\B | GG | 16 | 3 | B | 1 Prestrip - Thick | 100 | 65.2863 | 65.2863 | 2022-11-08 14:22 | 2022-11-10 09:05 | 96690.0985 | 96690 | [7 empty] | 0 | 0 | 7.09 | 10.35 | 5465.61
TS6060#1 | RS\26\003\A | RS | 26 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-11-08 18:38 | 2022-11-13 19:53 | 125112.5359 | 125113 | [7 empty] | 0 | 0 | 19.13 | 12.23 | 5322.09
TS5500Exc | MW\43\002\D | MW | 43 | 2 | D | 8 Coal Mining | 31.5 | 0 | 31.5 | 2022-11-08 21:29 | 2022-11-09 06:32 | 11407.3909 | [6 empty] | 11407 | 8592 | 1.45 | 0 | 0 | 6.5 | 5842
TS5500Shv | MW\43\004\D | MW | 43 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-11-08 21:57 | 2022-11-11 01:07 | 62394.2499 | [6 empty] | 62394 | 46917 | 4.69 | 0 | 0 | 6.47 | 5844
TS5500Exc | MW\43\005\D | MW | 43 | 5 | D | 8 Coal Mining | 55.7 | 0 | 55.7 | 2022-11-09 06:32 | 2022-11-10 08:43 | 32988.1216 | [6 empty] | 32988 | 24922 | 2.49 | 0 | 0 | 5.99 | 5885
TS Fleet 5 | GG\16\003\B | GG | 16 | 3 | B | 1 Prestrip - Thick | 45.419 | 34.7137 | 34.7137 | 2022-11-09 06:51 | 2022-11-10 09:05 | 51411.6599 | 51412 | [7 empty] | 0 | 0 | 3.77 | 10.35 | 5465.61
PH4100A | RS\25\006\X | RS | 25 | 6 | X | 1 Prestrip - Thick | 100 | 7.6368 | 7.6368 | 2022-11-10 04:38 | 2022-11-11 20:18 | 67764.7483 | 67765 | [7 empty] | 0 | 0 | 5.12 | 12.88 | 5165.68
TS5500Exc | MW\45\006\B | MW | 45 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-11-10 08:43 | 2022-11-10 19:50 | 13996.1445 | [6 empty] | 13996 | 10268 | 1.06 | 0 | 0 | 10.34 | 5445
TS Fleet 5 | GG\17\006\X1 | GG | 17 | 6 | X1 | 1 Prestrip - Thick | 46.7268 | 46.7268 | 46.7268 | 2022-11-10 09:05 | 2022-11-17 10:14 | 331533.4254 | 331533 | [7 empty] | 0 | 0 | 32.2 | 10.75 | 5344.54
PH4100XPC#1 | GG\16\004\X2 | GG | 16 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.581 | 2022-11-10 09:05 | 2022-11-11 15:19 | 68435.5954 | 68436 | [7 empty] | 0 | 0 | 6.65 | 0 | 0
TS5500Exc | MW\43\006\D | MW | 43 | 6 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-11-10 19:50 | 2022-11-11 20:13 | 30718.3433 | [6 empty] | 30718 | 23265 | 2.33 | 0 | 0 | 5.62 | 5918
TS5500Shv | RS\26\005\X | RS | 26 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-11-11 01:07 | 2022-11-11 18:15 | 20895.2501 | [6 empty] | 20895 | 14608 | 1.47 | 0 | 0 | 12.56 | 5195
PH4100XPC#1 | GG\16\004\B | GG | 16 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-11-11 15:19 | 2022-11-14 08:10 | 146796.1519 | 146796 | [7 empty] | 0 | 0 | 14.5 | 10.24 | 5446.31
TS5500Shv | GG\16\003\B | GG | 16 | 3 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-11-11 18:15 | 2022-11-12 20:11 | 31628.5693 | [6 empty] | 31629 | 23212 | 1.75 | 0 | 0 | 10.35 | 5466
TS5500Exc | MW\45\007\A | MW | 45 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-11-11 20:13 | 2022-11-25 15:08 | 293450.5693 | 293451 | [7 empty] | 0 | 0 | 29.4 | 13.31 | 5232.25
PH4100A | RS\26\006\X | RS | 26 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-11-11 20:18 | 2022-12-03 15:33 | 893853.4083 | 893853 | [7 empty] | 0 | 0 | 67.92 | 12.97 | 5163.37
DRE1 | MW\43\008\D | MW | 43 | 8 | D | 6 DL | 100 | 100 | 100 | 2022-11-11 20:19 | 2022-11-16 09:36 | 341003.798 |  |  |  | 17532 | 341004 | 274673 |  |  | 0 | 29.22 | 0 | 5.31 | 5947.15
TS5500Shv | RS\25\006\X | RS | 25 | 6 | X | 8 Coal Mining | 100 | 0 | 100 | 2022-11-12 20:11 | 2022-11-13 13:50 | 21525.0313 | [6 empty] | 21525 | 15028 | 1.18 | 0 | 0 | 12.88 | 5166
TS5500Shv | GG\14\012\D | GG | 14 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-11-13 13:50 | 2022-11-15 17:35 | 63094.708 | [6 empty] | 63095 | 47170 | 4.72 | 0 | 0 | 6.56 | 5811
TS6060#1 | GG\16\003\B | GG | 16 | 3 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-11-13 19:53 | 2022-11-14 21:49 | 35104.2363 | [6 empty] | 35104 | 25763 | 1.94 | 0 | 0 | 10.35 | 5466
PH4100XPC#1 | GG\16\005\X1 | GG | 16 | 5 | X1 | 1 Prestrip - Thick | 100 | 54.5951 | 54.5951 | 2022-11-14 08:10 | 2022-11-21 21:28 | 410628.9688 | 410629 | [7 empty] | 0 | 0 | 42.28 | 10.21 | 5354.23
DRE2 | GG\14\010\D | GG | 14 | 10 | D | 6 DL | 100 | 100 | 100 | 2022-11-14 12:28 | 2022-11-20 11:08 | 467075.8224 |  |  |  | 10875 | 467076 | 206623 |  |  | 0 | 21.75 | 0 | 6.02 | 5859.15
TS6060#1 | GG\16\004\B | GG | 16 | 4 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-11-14 21:49 | 2022-11-15 16:58 | 25910.2961 | [6 empty] | 25910 | 19009 | 1.9 | 0 | 0 | 10.24 | 5446
TS6060#1 | RS\25\006\A | RS | 25 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-11-15 16:58 | 2022-11-23 17:16 | 198416.7869 | 198417 | [7 empty] | 0 | 0 | 17.31 | 19.79 | 4715.78
TS5500Shv | GG\16\004\B | GG | 16 | 4 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-11-15 17:35 | 2022-11-16 12:44 | 23344.9202 | [6 empty] | 23345 | 17127 | 1.71 | 0 | 0 | 10.24 | 5446
DRE1 | MW\43\009\D | MW | 43 | 9 | D | 6 DL | 100 | 100 | 100 | 2022-11-16 09:36 | 2022-11-21 03:25 | 355198.0892 |  |  |  | 12933 | 355198 | 200374 |  |  | 0 | 28.52 | 0 | 5.24 | 5952.08
TS5500Shv | MW\43\005\D | MW | 43 | 5 | D | 8 Coal Mining | 44.3 | 0 | 44.3 | 2022-11-16 12:44 | 2022-11-17 10:16 | 26258.3687 | [6 empty] | 26258 | 19838 | 1.98 | 0 | 0 | 5.99 | 5885
TS Fleet 5 | GG\17\007\X1 | GG | 17 | 7 | X1 | 1 Prestrip - Thick | 46.8512 | 46.8512 | 46.8512 | 2022-11-17 10:14 | 2022-11-23 17:23 | 296257.0021 | 296257 | [7 empty] | 0 | 0 | 29.08 | 11.24 | 5350.81
TS5500Shv | MW\45\006\B | MW | 45 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-11-17 10:16 | 2022-11-17 21:22 | 13549.459 | [6 empty] | 13549 | 9940 | 1.02 | 0 | 0 | 10.34 | 5445
TS5500Shv | RS\26\003\A | RS | 26 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-11-17 21:22 | 2022-11-18 11:29 | 17197.3441 | [6 empty] | 17197 | 12116 | 1.68 | 0 | 0 | 12.23 | 5322
TS5500Shv | MW\43\006\D | MW | 43 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-11-18 11:29 | 2022-11-19 11:52 | 29737.9706 | [6 empty] | 29738 | 22522 | 2.25 | 0 | 0 | 5.62 | 5918
TS5500Shv | GG\14\011\D | GG | 14 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-11-19 11:52 | 2022-11-21 15:43 | 63223.728 | [6 empty] | 63224 | 47341 | 4.73 | 0 | 0 | 6.22 | 5841
DRE2 | GG\14\009\D | GG | 14 | 9 | D | 6 DL | 100 | 100 | 100 | 2022-11-20 11:08 | 2022-11-26 03:24 | 446129.3039 |  |  |  | 10387 | 446129 | 197356 |  |  | 0 | 20.78 | 0 | 6.28 | 5835.1
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2022-11-21 03:25 | 2022-11-23 03:25
TS5500Shv | MW\43\007\D | MW | 43 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-11-21 15:43 | 2022-11-23 18:58 | 62498.6753 | [6 empty] | 62499 | 47451 | 4.74 | 0 | 0 | 5.44 | 5935
PH4100XPC#1 | GG\16\006\X1 | GG | 16 | 6 | X1 | 1 Prestrip - Thick | 100 | 54.3987 | 54.3987 | 2022-11-21 21:28 | 2022-11-28 18:29 | 370749.2205 | 370749 | [7 empty] | 0 | 0 | 35.66 | 10.74 | 5351.54
DRE1 | RS\22\003\D | RS | 22 | 3 | D | 6 DL | 100 | 100 | 100 | 2022-11-23 03:25 | 2022-11-28 16:28 | 415182.3078 |  |  |  | 23696 | 415182 | 314814 |  |  | 0 | 30.96 | 0 | 5.96 | 5896.44
TS6060#1 | GG\15\005\B | GG | 15 | 5 | B | 8 Coal Mining | 47.3 | 0 | 47.3 | 2022-11-23 17:16 | 2022-11-24 10:37 | 23477.6896 | [6 empty] | 23478 | 17145 | 1.72 | 0 | 0 | 11.15 | 5353
TS Fleet 5 | GG\17\008\X1 | GG | 17 | 8 | X1 | 1 Prestrip - Thick | 44.5593 | 44.5593 | 44.5593 | 2022-11-23 17:23 | 2022-11-29 09:36 | 266986.4243 | 266986 | [7 empty] | 0 | 0 | 26 | 11.73 | 5343.8
TS5500Shv | GG\16\005\X1 | GG | 16 | 5 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2022-11-23 18:58 | 2022-11-24 09:36 | 17853.1926 | [6 empty] | 17853 | 13303 | 1.31 | 0 | 0 | 10.21 | 5354
TS5500Shv | RS\25\006\A | RS | 25 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-11-24 09:36 | 2022-11-25 08:07 | 27444.7984 | [6 empty] | 27445 | 18502 | 1.63 | 0 | 0 | 19.79 | 4716
TS6060#1 | RS\26\004\A | RS | 26 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-11-24 10:37 | 2022-12-01 23:14 | 186362.0258 | 186362 | [7 empty] | 0 | 0 | 18.68 | 14.26 | 5151.34
TS5500Shv | MW\43\008\D | MW | 43 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-11-25 08:07 | 2022-11-27 11:49 | 63054.9326 | [6 empty] | 63055 | 47952 | 4.8 | 0 | 0 | 5.31 | 5947
TS5500Exc | RS\25\006\A | RS | 25 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-11-25 15:08 | 2022-11-26 13:38 | 28349.5719 | [6 empty] | 28350 | 19112 | 1.69 | 0 | 0 | 19.79 | 4716
DRE2 | GG\14\008\D | GG | 14 | 8 | D | 6 DL | 100 | 100 | 100 | 2022-11-26 03:24 | 2022-12-01 15:31 | 432565.7705 |  |  |  | 10071 | 432566 | 191356 |  |  | 0 | 20.14 | 0 | 6.65 | 5802.37
TS5500Exc | RS\26\003\A | RS | 26 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-11-26 13:38 | 2022-11-27 03:44 | 17764.2895 | [6 empty] | 17764 | 12515 | 1.74 | 0 | 0 | 12.23 | 5322
TS5500Exc | MW\45\007\A | MW | 45 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-11-27 03:44 | 2022-11-28 03:11 | 29522.73 | [6 empty] | 29523 | 21388 | 2.17 | 0 | 0 | 13.31 | 5232
TS5500Shv | MW\43\009\D | MW | 43 | 9 | D | 7 PostStrip | 100 | 0 | 100 | 2022-11-27 11:49 | 2022-11-29 06:07 | 45345.3581 |  |  | 45345 | [5 empty] | 0 | 0 | 0 | 5.24 | 5952.08
TS5500Exc | MW\45\007\B | MW | 45 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-11-28 03:11 | 2022-11-30 03:03 | 42339.8193 | 42340 | [7 empty] | 0 | 0 | 4.26 | 9.8 | 5485.28
DRE1 | RS\22\004\D | RS | 22 | 4 | D | 6 DL | 100 | 100 | 100 | 2022-11-28 16:28 | 2022-12-03 17:56 | 379013.4316 |  |  |  | 21631 | 379013 | 287389 |  |  | 0 | 30.89 | 0 | 6.41 | 5856.46
PH4100XPC#1 | GG\16\005\X2 | GG | 16 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 68.7622 | 2022-11-28 18:29 | 2022-11-30 02:17 | 72000.2415 | 72000 | [7 empty] | 0 | 0 | 7.04 | 0 | 0
TS5500Shv | GG\16\006\X1 | GG | 16 | 6 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-11-29 06:07 | 2022-11-29 12:25 | 7679.488 | [6 empty] | 7679 | 5694 | 0.56 | 0 | 0 | 10.74 | 5352
TS Fleet 5 | GG\16\005\X2 | GG | 16 | 5 | X2 | 1 Prestrip - Thick | 45.419 | 0 | 31.2378 | 2022-11-29 09:36 | 2022-11-30 02:17 | 32708.7676 | 32709 | [7 empty] | 0 | 0 | 3.2 | 0 | 0
TS5500Shv | MW\43\009\D | MW | 43 | 9 | D | 8 Coal Mining | 56.5 | 0 | 56.5 | 2022-11-29 12:25 | 2022-11-30 13:38 | 30752.556 | [6 empty] | 30753 | 23423 | 2.62 | 0 | 0 | 5.24 | 5952
TS Fleet 5 | GG\16\005\B | GG | 16 | 5 | B | 1 Prestrip - Thick | 45.419 | 45.419 | 45.419 | 2022-11-30 02:17 | 2022-11-30 03:17 | 1955.8749 | 1956 | [7 empty] | 0 | 0 | 0.19 | 10.57 | 5400.31
PH4100XPC#1 | GG\16\005\B | GG | 16 | 5 | B | 1 Prestrip - Thick | 100 | 54.581 | 54.581 | 2022-11-30 02:17 | 2022-11-30 03:19 | 2350.4206 | 2350 | [7 empty] | 0 | 0 | 0.23 | 10.57 | 5400.31
TS5500Exc | MW\43\009\D | MW | 43 | 9 | D | 8 Coal Mining | 100 | 0 | 43.5 | 2022-11-30 03:03 | 2022-11-30 21:50 | 23656.469 | [6 empty] | 23656 | 18018 | 2.01 | 0 | 0 | 5.24 | 5952
TS Fleet 5 | GG\17\009\X1 | GG | 17 | 9 | X1 | 1 Prestrip - Thick | 46.6037 | 46.6037 | 46.6037 | 2022-11-30 03:17 | 2022-12-05 10:55 | 250179.9054 | 250180 | [7 empty] | 0 | 0 | 25.99 | 12.68 | 5280.41
PH4100XPC#1 | GG\16\007\X1 | GG | 16 | 7 | X1 | 1 Prestrip - Thick | 100 | 54.2935 | 54.2935 | 2022-11-30 03:19 | 2022-12-06 04:08 | 323992.4041 | 323992 | [7 empty] | 0 | 0 | 31.82 | 11.05 | 5371.78
TS5500Shv | GG\14\009\D | GG | 14 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-11-30 13:38 | 2022-12-02 16:41 | 62233.463 | [6 empty] | 62233 | 46488 | 4.65 | 0 | 0 | 6.28 | 5835
TS5500Exc | RS\22\003\D | RS | 22 | 3 | D | 8 Coal Mining | 34 | 0 | 34 | 2022-11-30 21:50 | 2022-12-01 15:54 | 22768.6979 | [6 empty] | 22769 | 16654 | 1.51 | 0 | 0 | 5.96 | 5896
DRE2 | GG\14\007\D | GG | 14 | 7 | D | 6 DL | 100 | 100 | 100 | 2022-12-01 15:31 | 2022-12-07 02:06 | 427558.8201 |  |  |  | 7962 | 427559 | 191088 |  |  | 0 | 19.9 | 0 | 6.55 | 5810.49
TS5500Exc | MW\45\007\B | MW | 45 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-12-01 15:54 | 2022-12-02 23:00 | 39157.1266 | [6 empty] | 39157 | 28828 | 2.88 | 0 | 0 | 9.8 | 5485
TS6060#1 | GG\16\006\X1 | GG | 16 | 6 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-12-01 23:14 | 2022-12-02 05:32 | 8523.3878 | [6 empty] | 8523 | 6320 | 0.62 | 0 | 0 | 10.74 | 5352
TS6060#1 | RS\25\006\B | RS | 25 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-12-02 05:32 | 2022-12-03 14:54 | 34422.5082 | 34423 | [7 empty] | 0 | 0 | 3.05 | 8.94 | 5601.38
TS5500Shv | RS\26\004\A | RS | 26 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-12-02 16:41 | 2022-12-03 12:43 | 24436.426 | [6 empty] | 24436 | 16976 | 1.7 | 0 | 0 | 14.26 | 5151
TS5500Exc | RS\26\004\A | RS | 26 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-12-02 23:00 | 2022-12-03 19:02 | 25242.0225 | [6 empty] | 25242 | 17536 | 1.76 | 0 | 0 | 14.26 | 5151
TS5500Shv | GG\14\008\D | GG | 14 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-12-03 12:43 | 2022-12-05 15:20 | 61719.0637 | [6 empty] | 61719 | 45994 | 4.6 | 0 | 0 | 6.65 | 5802
TS6060#1 | RS\26\005\A | RS | 26 | 5 | A | 1 Prestrip - Thick | 95.9195 | 95.9195 | 95.9195 | 2022-12-03 14:54 | 2022-12-10 06:53 | 165068.3598 | 165068 | [7 empty] | 0 | 0 | 16.63 | 18.2 | 4840.87
PH4100A | MW\53\005\D | MW | 53 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-12-03 15:33 | 2022-12-05 06:26 | 70023.6428 | 70024 | [7 empty] | 0 | 0 | 7.26 | 9.19 | 5604.73
DRE1 | RS\22\005\D | RS | 22 | 5 | D | 6 DL | 100 | 100 | 100 | 2022-12-03 17:56 | 2022-12-08 07:26 | 341708.4715 |  |  |  | 17569 | 341708 | 275241 |  |  | 0 | 29.29 | 0 | 6.67 | 5833.16
TS5500Exc | RS\26\006\X | RS | 26 | 6 | X | 8 Coal Mining | 65.3 | 0 | 65.3 | 2022-12-03 19:02 | 2022-12-04 06:29 | 14420.4856 | [6 empty] | 14420 | 10061 | 0.79 | 0 | 0 | 12.97 | 5163
TS5500Exc | RS\22\004\D | RS | 22 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-12-04 06:29 | 2022-12-06 05:07 | 58744.5405 | [6 empty] | 58745 | 42893 | 4.29 | 0 | 0 | 6.41 | 5856
PH4100A | MW\52\004\D | MW | 52 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-12-05 06:26 | 2022-12-05 16:33 | 18512.5735 | 18513 | [7 empty] | 0 | 0 | 3.12 | 8.76 | 5640.54
TS Fleet 5 | GG\16\006\X2 | GG | 16 | 6 | X2 | 1 Prestrip - Thick | 45.419 | 0 | 45.419 | 2022-12-05 10:55 | 2022-12-06 09:33 | 44343.236 | 44343 | [7 empty] | 0 | 0 | 4.38 | 0 | 0
TS5500Shv | RS\26\006\X | RS | 26 | 6 | X | 8 Coal Mining | 34.7 | 0 | 34.7 | 2022-12-05 15:20 | 2022-12-05 21:38 | 7678.1083 | [6 empty] | 7678 | 5357 | 0.42 | 0 | 0 | 12.97 | 5163
PH4100A | MW\52\005\D | MW | 52 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-12-05 16:33 | 2022-12-08 15:58 | 129217.259 | 129217 | [7 empty] | 0 | 0 | 13.14 | 8.78 | 5640.88
TS5500Shv | RS\25\006\B | RS | 25 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-12-05 21:38 | 2022-12-07 05:46 | 39189.7144 | [6 empty] | 39190 | 28089 | 2.5 | 0 | 0 | 8.94 | 5601
PH4100XPC#1 | GG\16\006\X2 | GG | 16 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.581 | 2022-12-06 04:08 | 2022-12-07 03:40 | 53288.302 | 53288 | [7 empty] | 0 | 0 | 5.26 | 0 | 0
TS5500Exc | MW\45\008\A | MW | 45 | 8 | A | 1 Prestrip - Thick | 52.2966 | 52.2966 | 52.2966 | 2022-12-06 05:07 | 2022-12-14 12:59 | 177085.9256 | 177086 | [7 empty] | 0 | 0 | 17.83 | 12.98 | 5262.68
TS Fleet 5 | GG\17\010\X2 | GG | 17 | 10 | X2 | 1 Prestrip - Thick | 45.5239 | 0 | 45.5239 | 2022-12-06 09:33 | 2022-12-12 05:31 | 274331.3424 | 274331 | [7 empty] | 0 | 0 | 27.55 | 0 | 0
DRE2 | GG\14\006\D | GG | 14 | 6 | D | 6 DL | 100 | 100 | 100 | 2022-12-07 02:06 | 2022-12-12 11:59 | 425229.8569 |  |  |  | 7919 | 425230 | 190047 |  |  | 0 | 19.8 | 0 | 6.56 | 5810.73
PH4100XPC#1 | GG\16\006\B | GG | 16 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-12-07 03:40 | 2022-12-07 22:45 | 43191.8461 | 43192 | [7 empty] | 0 | 0 | 4.36 | 10.07 | 5443.52
TS5500Shv | GG\16\007\X1 | GG | 16 | 7 | X1 | 8 Coal Mining | 38.8 | 0 | 38.8 | 2022-12-07 05:46 | 2022-12-07 10:55 | 6282.1491 | [6 empty] | 6282 | 4639 | 0.46 | 0 | 0 | 11.05 | 5372
TS5500Shv | RS\22\003\D | RS | 22 | 3 | D | 8 Coal Mining | 66 | 0 | 66 | 2022-12-07 10:55 | 2022-12-08 23:13 | 44269.9946 | [6 empty] | 44270 | 32380 | 2.94 | 0 | 0 | 5.96 | 5896
PH4100XPC#1 | GG\16\008\X1 | GG | 16 | 8 | X1 | 1 Prestrip - Thick | 100 | 54.1828 | 54.1828 | 2022-12-07 22:45 | 2022-12-13 15:18 | 304151.3666 | 304151 | [7 empty] | 0 | 0 | 29.66 | 11.42 | 5373.2
DRE1 | RS\22\006\D | RS | 22 | 6 | D | 6 DL | 100 | 100 | 100 | 2022-12-08 07:26 | 2022-12-14 05:39 | 443807.1718 |  |  |  | 16250 | 443807 | 250687 |  |  | 0 | 27.99 | 0 | 6.8 | 5820.71
PH4100A | MW\53\006\D | MW | 53 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-12-08 15:58 | 2022-12-10 21:25 | 94067.4815 | 94067 | [7 empty] | 0 | 0 | 9.28 | 7.85 | 5723.76
TS5500Shv | GG\14\007\D | GG | 14 | 7 | D | 8 Coal Mining | 55 | 0 | 55 | 2022-12-08 23:13 | 2022-12-10 03:03 | 33936.2292 | [6 empty] | 33936 | 25350 | 2.54 | 0 | 0 | 6.55 | 5810
TS5500Shv | RS\22\005\D | RS | 22 | 5 | D | 8 Coal Mining | 71 | 0 | 71 | 2022-12-10 03:03 | 2022-12-11 12:29 | 40760.7228 | [6 empty] | 40761 | 29712 | 2.97 | 0 | 0 | 6.67 | 5833
TS6060#1 | GG\16\007\X1 | GG | 16 | 7 | X1 | 8 Coal Mining | 61.2 | 0 | 61.2 | 2022-12-10 06:53 | 2022-12-10 14:11 | 9892.5511 | [6 empty] | 9893 | 7305 | 0.73 | 0 | 0 | 11.05 | 5372
TS6060#1 | RS\26\003\B | RS | 26 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-12-10 14:11 | 2022-12-11 08:53 | 19295.7705 | 19296 | [7 empty] | 0 | 0 | 2.62 | 8.77 | 5617.67
PH4100A | MW\52\006\D | MW | 52 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-12-10 21:25 | 2022-12-14 09:37 | 150538.5614 | 150539 | [7 empty] | 0 | 0 | 14.97 | 7.58 | 5747.26
TS6060#1 | RS\26\004\B | RS | 26 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-12-11 08:53 | 2022-12-12 10:07 | 26028.025 | 26028 | [7 empty] | 0 | 0 | 2.61 | 8.78 | 5611.91
TS5500Shv | GG\16\007\X2 | GG | 16 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 59.4733 | 2022-12-11 12:29 | 2022-12-13 18:04 | 57451.1066 | 57451 | [7 empty] | 0 | 0 | 5.73 | 0 | 0
TS Fleet 5 | GG\16\007\X2 | GG | 16 | 7 | X2 | 1 Prestrip - Thick | 34.026 | 0 | 34.026 | 2022-12-12 05:31 | 2022-12-12 22:17 | 32869.0292 | 32869 | [7 empty] | 0 | 0 | 3.28 | 0 | 0
TS6060#1 | RS\26\006\A | RS | 26 | 6 | A | 1 Prestrip - Thick | 22.5648 | 22.5648 | 22.5648 | 2022-12-12 10:07 | 2022-12-14 04:22 | 43595.8072 | 43596 | [7 empty] | 0 | 0 | 3.84 | 19.5 | 4745.04
DRE2 | GG\14\005\D | GG | 14 | 5 | D | 6 DL | 100 | 100 | 100 | 2022-12-12 11:59 | 2022-12-17 20:51 | 421922.8859 |  |  |  | 10204 | 421923 | 193870 |  |  | 0 | 20.41 | 0 | 6.54 | 5812.14
TS Fleet 5 | GG\17\011\X1 | GG | 17 | 11 | X1 | 1 Prestrip - Thick | 41.2683 | 41.2683 | 41.2683 | 2022-12-12 22:17 | 2022-12-16 10:16 | 164597.3512 | 164597 | [7 empty] | 0 | 0 | 17.12 | 14.93 | 5105.35
PH4100XPC#1 | GG\16\007\X2 | GG | 16 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 6.5008 | 2022-12-13 15:18 | 2022-12-13 18:04 | 6279.7262 | 6280 | [7 empty] | 0 | 0 | 0.63 | 0 | 0
TS5500Shv | GG\16\008\X1 | GG | 16 | 8 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2022-12-13 18:04 | 2022-12-14 00:38 | 7999.7484 | [6 empty] | 8000 | 5881 | 0.59 | 0 | 0 | 11.42 | 5373
PH4100XPC#1 | GG\16\007\B | GG | 16 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-12-13 18:04 | 2022-12-14 17:56 | 54018.1685 | 54018 | [7 empty] | 0 | 0 | 5.41 | 10.33 | 5452.39
TS5500Shv | GG\14\006\D | GG | 14 | 6 | D | 8 Coal Mining | 98.2 | 0 | 98.2 | 2022-12-14 00:38 | 2022-12-16 02:58 | 61375.2066 | [6 empty] | 61375 | 45956 | 4.6 | 0 | 0 | 6.56 | 5811
TS6060#1 | GG\16\008\X1 | GG | 16 | 8 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2022-12-14 04:22 | 2022-12-14 10:56 | 8878.8416 | [6 empty] | 8879 | 6527 | 0.65 | 0 | 0 | 11.42 | 5373
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2022-12-14 05:39 | 2022-12-16 05:39
PH4100A | MW\53\007\A | MW | 53 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-12-14 09:37 | 2022-12-19 12:47 | 211301.2901 | 211301 | [7 empty] | 0 | 0 | 19.26 | 12.46 | 5341.87
TS6060#1 | GG\14\010\D | GG | 14 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-12-14 10:56 | 2022-12-16 09:52 | 63529.023 | [6 empty] | 63529 | 47608 | 4.76 | 0 | 0 | 6.02 | 5859
TS5500Exc | RS\26\003\B | RS | 26 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-12-14 12:59 | 2022-12-15 12:41 | 29838.1701 | [6 empty] | 29838 | 21422 | 2.84 | 0 | 0 | 8.77 | 5618
PH4100XPC#1 | GG\16\008\X2 | GG | 16 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2022-12-14 17:56 | 2022-12-16 10:10 | 91042.637 | 91043 | [7 empty] | 0 | 0 | 9.1 | 0 | 0
TS5500Exc | RS\26\004\B | RS | 26 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-12-15 12:41 | 2022-12-16 19:49 | 39227.6823 | [6 empty] | 39228 | 28161 | 2.82 | 0 | 0 | 8.78 | 5612
TS5500Shv | RS\22\006\D | RS | 22 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2022-12-16 02:58 | 2022-12-18 09:07 | 58058.237 |  |  | 58058 | [5 empty] | 0 | 0 | 0 | 6.8 | 5820.71
DRE1 | MW\44\002\D | MW | 44 | 2 | D | 6 DL | 100 | 0 | 100 | 2022-12-16 05:39 | 2022-12-21 11:13 | 391799.6576 |  |  |  | 21109 | 391800 | 180701 |  |  | 0 | 35 | 0 | 6.56 | 5832.35
TS6060#1 | GG\14\007\D | GG | 14 | 7 | D | 8 Coal Mining | 45 | 0 | 45 | 2022-12-16 09:52 | 2022-12-17 06:23 | 27767.1333 | [6 empty] | 27767 | 20742 | 2.07 | 0 | 0 | 6.55 | 5810
PH4100XPC#1 | GG\16\008\B | GG | 16 | 8 | B | 1 Prestrip - Thick | 100 | 54.581 | 54.581 | 2022-12-16 10:10 | 2022-12-17 00:59 | 33540.712 | 33541 | [7 empty] | 0 | 0 | 3.35 | 10.21 | 5489.57
TS Fleet 5 | GG\16\008\B | GG | 16 | 8 | B | 1 Prestrip - Thick | 45.419 | 45.419 | 45.419 | 2022-12-16 10:16 | 2022-12-17 00:30 | 27910.5105 | 27911 | [7 empty] | 0 | 0 | 2.79 | 10.21 | 5489.57
TS5500Exc | RS\22\005\D | RS | 22 | 5 | D | 8 Coal Mining | 29 | 0 | 29 | 2022-12-16 19:49 | 2022-12-17 09:03 | 16674.2271 | [6 empty] | 16674 | 12155 | 1.22 | 0 | 0 | 6.67 | 5833
TS Fleet 5 | GG\17\012\X1 | GG | 17 | 12 | X1 | 1 Prestrip - Thick | 47.0712 | 47.0712 | 47.0712 | 2022-12-17 00:30 | 2022-12-19 23:34 | 139279.8697 | 139280 | [7 empty] | 0 | 0 | 14.52 | 14.09 | 5172.12
PH4100XPC#1 | GG\16\009\X1 | GG | 16 | 9 | X1 | 1 Prestrip - Thick | 100 | 54.3771 | 54.3771 | 2022-12-17 00:59 | 2022-12-22 05:30 | 279536.0129 | 279536 | [7 empty] | 0 | 0 | 28.16 | 12.24 | 5318.65
TS6060#1 | GG\14\006\D | GG | 14 | 6 | D | 8 Coal Mining | 1.8 | 0 | 1.8 | 2022-12-17 06:23 | 2022-12-17 07:14 | 1149.408 | [6 empty] | 1149 | 861 | 0.09 | 0 | 0 | 6.56 | 5811
TS6060#1 | RS\29\006\X | RS | 29 | 6 | X | 1 Prestrip - Thick | 61.3254 | 41.5554 | 41.5554 | 2022-12-17 07:14 | 2023-01-01 | 358752.0521 | 358752 | [7 empty] | 0 | 0 | 28.01 | 12.97 | 5180.95
TS5500Exc | MW\45\008\A | MW | 45 | 8 | A | 1 Prestrip - Thick | 47.7034 | 47.7034 | 47.7034 | 2022-12-17 09:03 | 2022-12-24 23:22 | 161532.8175 | 161533 | [7 empty] | 0 | 0 | 16.27 | 12.98 | 5262.68
DRE2 | GG\14\004\D | GG | 14 | 4 | D | 6 DL | 100 | 100 | 100 | 2022-12-17 20:51 | 2022-12-20 12:44 | 209154.1175 |  |  |  | 7983 | 209154 | 191592 |  |  | 0 | 19.96 | 0 | 6.44 | 5819.58
TS5500Shv | GG\14\005\D | GG | 14 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-12-18 09:07 | 2022-12-20 11:58 | 61988.8863 | [6 empty] | 61989 | 46452 | 4.65 | 0 | 0 | 6.54 | 5812
PH4100A | MW\52\007\A | MW | 52 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-12-19 12:47 | 2022-12-26 10:25 | 287449.296 | 287449 | [7 empty] | 0 | 0 | 20.49 | 12.02 | 5376.92
TS Fleet 5 | GG\17\013\X2 | GG | 17 | 13 | X2 | 1 Prestrip - Thick | 46.7436 | 0 | 46.7436 | 2022-12-19 23:34 | 2022-12-24 18:57 | 226174.0003 | 226174 | [7 empty] | 0 | 0 | 15.67 | 0 | 0
TS5500Shv | MW\53\007\A | MW | 53 | 7 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2022-12-20 11:58 | 2022-12-21 00:09 | 14866.4044 | [6 empty] | 14866 | 10809 | 0.95 | 0 | 0 | 12.46 | 5342
DRE2 | GG\14\003\D | GG | 14 | 3 | D | 6 DL | 100 | 100 | 100 | 2022-12-20 12:44 | 2022-12-25 17:27 | 408348.9678 |  |  |  | 7604 | 408349 | 182502 |  |  | 0 | 19.03 | 0 | 6.28 | 5834.04
TS5500Shv | GG\14\004\D | GG | 14 | 4 | D | 8 Coal Mining | 25.2 | 0 | 25.2 | 2022-12-21 00:09 | 2022-12-21 12:44 | 15342.2734 | [6 empty] | 15342 | 11497 | 1.15 | 0 | 0 | 6.44 | 5820
DRE1 | MW\44\003\D | MW | 44 | 3 | D | 6 DL | 100 | 0 | 100 | 2022-12-21 11:13 | 2022-12-26 00:11 | 340077.9156 |  |  |  | 24186 | 340078 | 244544 |  |  | 0 | 35 | 0 | 6.64 | 5829.69
TS5500Shv | RS\22\006\D | RS | 22 | 6 | D | 8 Coal Mining | 63.1 | 0 | 63.1 | 2022-12-21 12:44 | 2022-12-22 23:20 | 42189.2873 | [6 empty] | 42189 | 30745 | 2.66 | 0 | 0 | 6.8 | 5821
PH4100XPC#1 | GG\16\010\B | GG | 16 | 10 | B | 1 Prestrip - Thick | 100 | 55.2283 | 55.2283 | 2022-12-22 05:30 | 2022-12-28 19:51 | 367940.539 | 367941 | [7 empty] | 0 | 0 | 38.06 | 9.43 | 5557.08
TS5500Shv | GG\16\009\X1 | GG | 16 | 9 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2022-12-22 23:20 | 2022-12-23 13:29 | 17259.8247 | [6 empty] | 17260 | 12592 | 1.26 | 0 | 0 | 12.24 | 5319
TS5500Shv | RS\22\006\D | RS | 22 | 6 | D | 8 Coal Mining | 36.9 | 0 | 36.9 | 2022-12-23 13:29 | 2022-12-24 09:42 | 24653.9139 | [6 empty] | 24654 | 17966 | 1.55 | 0 | 0 | 6.8 | 5821
TS5500Shv | MW\44\002\D | MW | 44 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2022-12-24 09:42 | 2022-12-25 16:14 | 32730.2114 |  |  | 32730 | [5 empty] | 0 | 0 | 0 | 6.56 | 5832.35
TS Fleet 5 | GG\16\009\X2 | GG | 16 | 9 | X2 | 1 Prestrip - Thick | 45.419 | 0 | 45.419 | 2022-12-24 18:57 | 2022-12-25 14:53 | 39054.1605 | 39054 | [7 empty] | 0 | 0 | 3.9 | 0 | 0
TS5500Exc | MW\53\007\A | MW | 53 | 7 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-12-24 23:22 | 2022-12-25 11:34 | 15356.5056 | [6 empty] | 15357 | 11165 | 0.99 | 0 | 0 | 12.46 | 5342
TS5500Exc | MW\45\008\A | MW | 45 | 8 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2022-12-25 11:34 | 2022-12-26 06:24 | 23734.686 | [6 empty] | 23735 | 17236 | 1.73 | 0 | 0 | 12.98 | 5263
TS Fleet 5 | GG\17\018\X2 | GG | 17 | 18 | X2 | 1 Prestrip - Thick | 46.9525 | 0 | 46.9525 | 2022-12-25 14:53 | 2022-12-28 06:17 | 124250.4482 | 124250 | [7 empty] | 0 | 0 | 12.77 | 0 | 0
TS5500Shv | MW\44\002\D | MW | 44 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-12-25 16:14 | 2022-12-26 19:18 | 33002.4908 | [6 empty] | 33002 | 24828 | 3.92 | 0 | 0 | 6.56 | 5832
DRE2 | GG\14\002\D | GG | 14 | 2 | D | 6 DL | 100 | 100 | 100 | 2022-12-25 17:27 | 2022-12-28 03:21 | 189529.6983 |  |  |  | 3176 | 189530 | 54653 |  |  | 0 | 18.41 | 0 | 6.22 | 5840.92
DRE1 | MW\44\004\D | MW | 44 | 4 | D | 6 DL | 100 | 100 | 100 | 2022-12-26 00:11 | 2022-12-31 10:16 | 405928.0212 |  |  |  | 23168 | 405928 | 307797 |  |  | 0 | 33.52 | 0 | 6.54 | 5837.72
TS5500Exc | MW\44\003\D | MW | 44 | 3 | D | 8 Coal Mining | 20.4 | 0 | 20.4 | 2022-12-26 06:24 | 2022-12-26 16:39 | 12894.7926 | [6 empty] | 12895 | 9689 | 0.97 | 0 | 0 | 6.64 | 5830
PH4100A | MW\53\007\B | MW | 53 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-12-26 10:25 | 2022-12-27 04:36 | 31573.3959 | 31573 | [7 empty] | 0 | 0 | 2.78 | 9.28 | 5574.67
TS5500Exc | MW\45\009\A | MW | 45 | 9 | A | 1 Prestrip - Thick | 100 | 29.8258 | 29.8258 | 2022-12-26 16:39 | 2023-01-01 | 112925.0447 | 112925 | [7 empty] | 0 | 0 | 13.63 | 12.62 | 5292.15
TS5500Shv | MW\52\007\A | MW | 52 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2022-12-26 19:18 | 2022-12-28 06:00 | 42317.6342 | [6 empty] | 42318 | 30852 | 2.24 | 0 | 0 | 12.02 | 5377
PH4100A | RS\26\005\A | RS | 26 | 5 | A | 1 Prestrip - Thick | 100 | 4.0805 | 4.0805 | 2022-12-27 04:36 | 2022-12-27 08:39 | 7022.1926 | 7022 | [7 empty] | 0 | 0 | 0.71 | 18.2 | 4840.87
PH4100A | RS\26\006\A | RS | 26 | 6 | A | 1 Prestrip - Thick | 100 | 77.4352 | 77.4352 | 2022-12-27 08:39 | 2022-12-30 22:50 | 149606.9299 | 149607 | [7 empty] | 0 | 0 | 13.18 | 19.5 | 4745.04
DRE2 | GG\15\013\B | GG | 15 | 13 | B | 6 DL | 100 | 0 | 100 | 2022-12-28 03:21 | 2022-12-30 15:50 | 198014.7169 |  |  |  |  | 198015 | 165012 |  |  | 0 | 16.06 | 0 | 10.69 | 5457.8
TS5500Shv | MW\53\007\B | MW | 53 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2022-12-28 06:00 | 2022-12-29 17:59 | 43875.7122 | [6 empty] | 43876 | 32443 | 2.89 | 0 | 0 | 9.28 | 5575
TS Fleet 5 | GG\17\019\X2 | GG | 17 | 19 | X2 | 1 Prestrip - Thick | 46.7749 | 0 | 46.7749 | 2022-12-28 06:17 | 2022-12-30 09:18 | 100004.5817 | 100005 | [7 empty] | 0 | 0 | 10.49 | 0 | 0
PH4100XPC#1 | GG\16\009\X2 | GG | 16 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.581 | 2022-12-28 19:51 | 2022-12-29 16:35 | 46932.2965 | 46932 | [7 empty] | 0 | 0 | 4.69 | 0 | 0
PH4100XPC#1 | GG\16\009\B | GG | 16 | 9 | B | 1 Prestrip - Thick | 100 | 77.0666 | 77.0666 | 2022-12-29 16:35 | 2022-12-30 18:03 | 57647.2247 | 57647 | [7 empty] | 0 | 0 | 5.77 | 9.71 | 5537.33
TS5500Shv | GG\14\003\D | GG | 14 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2022-12-29 17:59 | 2022-12-31 20:05 | 61084.7421 | [6 empty] | 61085 | 45773 | 4.58 | 0 | 0 | 6.28 | 5834
TS Fleet 5 | GG\16\009\B | GG | 16 | 9 | B | 1 Prestrip - Thick | 45.419 | 22.9334 | 22.9334 | 2022-12-30 09:18 | 2022-12-30 18:03 | 17154.5744 | 17155 | [7 empty] | 0 | 0 | 1.72 | 9.71 | 5537.33
DRE2 | GG\15\018\B | GG | 15 | 18 | B | 6 DL | 100 | 0 | 54.8562 | 2022-12-30 15:50 | 2023-01-01 | 105315.3533 |  |  |  |  | 105315 | 87763 |  |  | 0 | 16.19 | 0 | 10.69 | 5459.66
TS Fleet 5 | GG\17\020\B | GG | 17 | 20 | B | 1 Prestrip - Thick | 39.1367 | 17.0094 | 17.0094 | 2022-12-30 18:03 | 2023-01-01 | 58681.9164 | 58682 | [7 empty] | 0 | 0 | 5.68 | 14.96 | 5149.11
PH4100XPC#1 | GG\16\011\X2 | GG | 16 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 14.1805 | 2022-12-30 18:03 | 2023-01-01 | 68487.65 | 68488 | [7 empty] | 0 | 0 | 6.71 | 0 | 0
PH4100A | MW\52\007\B | MW | 52 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2022-12-30 22:50 | 2022-12-31 18:01 | 33308.147 | 33308 | [7 empty] | 0 | 0 | 2.44 | 9.47 | 5561.07
DRE1 | MW\44\005\D | MW | 44 | 5 | D | 6 DL | 100 | 13.4166 | 13.4166 | 2022-12-31 10:16 | 2023-01-01 | 42810.11 |  |  |  | 2201 | 42810 | 34483 |  |  | 0 | 27.34 | 0 | 6.06 | 5879.04
PH4100A | RS\27\003\X | RS | 27 | 3 | X | 1 Prestrip - Thick | 100 | 5.2377 | 5.2377 | 2022-12-31 18:01 | 2023-01-01 | 10120.0966 | 10120 | [7 empty] | 0 | 0 | 2.09 | 12.28 | 5209.71
TS5500Shv | MW\52\007\B | MW | 52 | 7 | B | 8 Coal Mining | 12.8 | 0 | 10.3 | 2022-12-31 20:05 | 2023-01-01 | 4771.2355 | [6 empty] | 4771 | 3524 | 0.26 | 0 | 0 | 9.47 | 5561
| EOP 75 : 2022 | EOP 75 : 2022 | [7 empty] | 2023-01-01 | 2023-01-01 |  | 62411537 |  | 2607698 | 1753560 | 54257431 | 34559142 | 15550775 | 11448616 | 1038.69 | 0 | 5550.97 | 8.56 | 5645.28
TS Fleet 5 | GG\17\020\B | GG | 17 | 20 | B | 1 Prestrip - Thick | 39.1367 | 22.1272 | 22.1272 | 2023-01-01 | 2023-01-02 14:56 | 76338.1515 | 76338 | [7 empty] | 0 | 0 | 7.39 | 14.96 | 5149.11
DRE1 | MW\44\005\D | MW | 44 | 5 | D | 6 DL | 100 | 86.5834 | 86.5834 | 2023-01-01 | 2023-01-04 07:05 | 276273.563 |  |  |  | 14204 | 276274 | 222534 |  |  | 0 | 27.34 | 0 | 6.06 | 5879.04
PH4100A | RS\27\003\X | RS | 27 | 3 | X | 1 Prestrip - Thick | 100 | 72.738 | 72.738 | 2023-01-01 | 2023-01-04 10:59 | 140541.2337 | 140541 | [7 empty] | 0 | 0 | 28.99 | 12.28 | 5209.71
DRE2 | GG\15\018\B | GG | 15 | 18 | B | 6 DL | 100 | 0 | 45.1438 | 2023-01-01 | 2023-01-02 01:45 | 86669.0342 |  |  |  |  | 86669 | 72224 |  |  | 0 | 16.19 | 0 | 10.69 | 5459.66
PH4100XPC#1 | GG\16\011\X2 | GG | 16 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 30.9456 | 2023-01-01 | 2023-01-03 20:15 | 149457.8651 | 149458 | [7 empty] | 0 | 0 | 14.64 | 0 | 0
TS6060#1 | RS\29\006\X | RS | 29 | 6 | X | 1 Prestrip - Thick | 61.3254 | 19.77 | 19.77 | 2023-01-01 | 2023-01-07 23:49 | 170676.3473 | 170676 | [7 empty] | 0 | 0 | 13.33 | 12.97 | 5180.95
TS5500Shv | MW\52\007\B | MW | 52 | 7 | B | 8 Coal Mining | 12.8 | 0 | 2.5 | 2023-01-01 | 2023-01-01 00:57 | 1158.6371 | [6 empty] | 1159 | 856 | 0.06 | 0 | 0 | 9.47 | 5561
TS5500Exc | MW\45\009\A | MW | 45 | 9 | A | 1 Prestrip - Thick | 100 | 70.1742 | 70.1742 | 2023-01-01 | 2023-01-13 11:37 | 265690.4642 | 265690 | [7 empty] | 0 | 0 | 32.08 | 12.62 | 5292.15
TS5500Shv | RS\26\006\A | RS | 26 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-01-01 00:57 | 2023-01-01 23:03 | 26963.227 | [6 empty] | 26963 | 18244 | 1.63 | 0 | 0 | 19.5 | 4745
TS5500Shv | GG\14\002\D | GG | 14 | 2 | D | 7 PostStrip | 55.2847 | 0 | 55.2847 | 2023-01-01 23:03 | 2023-01-02 10:10 | 11919.5794 |  |  | 11920 | [5 empty] | 0 | 0 | 0 | 6.22 | 5840.92
DRE2 | GG\15\019\B | GG | 15 | 19 | B | 6 DL | 100 | 0 | 100 | 2023-01-02 01:45 | 2023-01-04 16:44 | 211855.6121 |  |  |  |  | 211856 | 176546 |  |  | 0 | 17.35 | 0 | 11.46 | 5410.67
TS5500Shv | GG\15\013\B | GG | 15 | 13 | B | 8 Coal Mining | 36 | 0 | 36 | 2023-01-02 10:10 | 2023-01-02 22:33 | 15083.1109 | [6 empty] | 15083 | 11032 | 1.16 | 0 | 0 | 10.69 | 5458
TS Fleet 5 | GG\17\021\B | GG | 17 | 21 | B | 1 Prestrip - Thick | 45.8448 | 45.8448 | 45.8448 | 2023-01-02 14:56 | 2023-01-06 00:22 | 159604.3972 | 159604 | [7 empty] | 0 | 0 | 17.64 | 15.54 | 5135.76
TS5500Shv | MW\44\003\D | MW | 44 | 3 | D | 8 Coal Mining | 79.6 | 0 | 79.6 | 2023-01-02 22:33 | 2023-01-04 15:42 | 50184.7059 | [6 empty] | 50185 | 37707 | 3.77 | 0 | 0 | 6.64 | 5830
PH4100XPC#1 | GG\16\011\B | GG | 16 | 11 | B | 1 Prestrip - Thick | 100 | 97.8675 | 97.8675 | 2023-01-03 20:15 | 2023-01-06 01:39 | 115698.8028 | 115699 | [7 empty] | 0 | 0 | 11.46 | 9.51 | 5551.89
DRE1 | MW\44\006\D | MW | 44 | 6 | D | 6 DL | 100 | 100 | 100 | 2023-01-04 07:05 | 2023-01-08 10:21 | 346732.4964 |  |  |  | 17827 | 346732 | 279288 |  |  | 0 | 29.7 | 0 | 5.63 | 5917.83
PH4100A | RS\28\003\X | RS | 28 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-01-04 10:59 | 2023-01-09 04:35 | 192067.5659 | 192068 | [7 empty] | 0 | 0 | 39.97 | 12.25 | 5217.76
TS5500Shv | MW\45\008\A | MW | 45 | 8 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-01-04 15:42 | 2023-01-05 10:32 | 22977.196 | [6 empty] | 22977 | 16686 | 1.67 | 0 | 0 | 12.98 | 5263
DRE2 | GG\15\020\B | GG | 15 | 20 | B | 6 DL | 100 | 0 | 100 | 2023-01-04 16:44 | 2023-01-07 14:29 | 234575.798 |  |  |  |  | 234576 | 195480 |  |  | 0 | 19.18 | 0 | 14.49 | 5191.38
TS5500Shv | GG\15\018\B | GG | 15 | 18 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-01-05 10:32 | 2023-01-07 02:16 | 48444.0839 | [6 empty] | 48444 | 35409 | 3.68 | 0 | 0 | 10.69 | 5460
TS Fleet 5 | GG\16\011\B | GG | 16 | 11 | B | 1 Prestrip - Thick | 45.419 | 2.1325 | 2.1325 | 2023-01-06 00:22 | 2023-01-06 01:39 | 2521.0385 | 2521 | [7 empty] | 0 | 0 | 0.25 | 9.51 | 5551.89
TS Fleet 5 | GG\17\022\B | GG | 17 | 22 | B | 1 Prestrip - Thick | 46.3959 | 46.3959 | 46.3959 | 2023-01-06 01:39 | 2023-01-09 01:49 | 141433.3344 | 141433 | [7 empty] | 0 | 0 | 14.92 | 17.49 | 4978.05
PH4100XPC#1 | GG\16\012\X1 | GG | 16 | 12 | X1 | 1 Prestrip - Thick | 100 | 54.0966 | 54.0966 | 2023-01-06 01:39 | 2023-01-09 02:51 | 155502.93 | 155503 | [7 empty] | 0 | 0 | 16.1 | 14.15 | 5168.42
TS5500Shv | GG\15\019\B | GG | 15 | 19 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-01-07 02:16 | 2023-01-08 21:28 | 52671.3894 | [6 empty] | 52671 | 38302 | 3.83 | 0 | 0 | 11.46 | 5411
DRE2 | GG\15\021\B | GG | 15 | 21 | B | 6 DL | 100 | 0 | 100 | 2023-01-07 14:29 | 2023-01-10 22:32 | 269310.6109 |  |  |  |  | 269311 | 207162 |  |  | 0 | 20.4 | 0 | 14.66 | 5199.4
TS6060#1 | MW\52\007\B | MW | 52 | 7 | B | 8 Coal Mining | 100 | 0 | 87.2 | 2023-01-07 23:49 | 2023-01-09 05:48 | 40572.3085 | [6 empty] | 40572 | 29969 | 2.21 | 0 | 0 | 9.47 | 5561
DRE1 | MW\44\007\D | MW | 44 | 7 | D | 6 DL | 100 | 100 | 100 | 2023-01-08 10:21 | 2023-01-12 13:10 | 345182.2316 |  |  |  | 17747 | 345182 | 278039 |  |  | 0 | 29.57 | 0 | 5.44 | 5934.98
TS5500Shv | MW\44\004\D | MW | 44 | 4 | D | 8 Coal Mining | 23.3 | 0 | 23.3 | 2023-01-08 21:28 | 2023-01-09 09:19 | 14460.7146 | [6 empty] | 14461 | 10873 | 1.09 | 0 | 0 | 6.54 | 5838
TS Fleet 5 | GG\17\023\B | GG | 17 | 23 | B | 1 Prestrip - Thick | 45.6046 | 45.6046 | 45.6046 | 2023-01-09 01:49 | 2023-01-13 09:57 | 204089.2236 | 204089 | [7 empty] | 0 | 0 | 15.42 | 0 | 0
PH4100XPC#1 | GG\16\013\X2 | GG | 16 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.6412 | 2023-01-09 02:51 | 2023-01-13 09:04 | 222001.6903 | 222002 | [7 empty] | 0 | 0 | 17.58 | 0 | 0
PH4100A | RS\27\004\X | RS | 27 | 4 | X | 1 Prestrip - Thick | 100 | 45.6846 | 45.6846 | 2023-01-09 04:35 | 2023-01-14 08:48 | 210215.4253 | 210215 | [7 empty] | 0 | 0 | 21.3 | 12.36 | 5207.33
TS6060#1 | GG\16\012\X1 | GG | 16 | 12 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-01-09 05:48 | 2023-01-09 15:52 | 13630.9014 | [6 empty] | 13631 | 9811 | 1 | 0 | 0 | 14.15 | 5168
TS5500Shv | RS\28\003\X | RS | 28 | 3 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-01-09 09:19 | 2023-01-09 13:20 | 4894.013 | [6 empty] | 4894 | 3431 | 0.59 | 0 | 0 | 12.25 | 5218
TS5500Shv | GG\15\020\B | GG | 15 | 20 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-01-09 13:20 | 2023-01-10 13:51 | 29898.6084 | [6 empty] | 29899 | 21325 | 2.13 | 0 | 0 | 14.49 | 5191
TS6060#1 | GG\14\004\D | GG | 14 | 4 | D | 8 Coal Mining | 74.8 | 0 | 74.8 | 2023-01-09 15:52 | 2023-01-11 01:27 | 45461.5666 | [6 empty] | 45462 | 34066 | 3.41 | 0 | 0 | 6.44 | 5820
TS5500Shv | MW\44\005\D | MW | 44 | 5 | D | 8 Coal Mining | 58.2 | 0 | 58.2 | 2023-01-10 13:51 | 2023-01-11 18:09 | 34503.5839 | [6 empty] | 34504 | 26067 | 2.61 | 0 | 0 | 6.06 | 5879
DRE2 | GG\15\022\B | GG | 15 | 22 | B | 6 DL | 100 | 0 | 100 | 2023-01-10 22:32 | 2023-01-14 05:35 | 265864.7596 |  |  |  |  | 265865 | 204511 |  |  | 0 | 20.47 | 0 | 16.4 | 5054.03
TS6060#1 | GG\14\002\D | GG | 14 | 2 | D | 7 PostStrip | 44.7153 | 0 | 44.7153 | 2023-01-11 01:27 | 2023-01-11 10:48 | 9640.7903 |  |  | 9641 | [5 empty] | 0 | 0 | 0 | 6.22 | 5840.92
TS6060#1 | GG\14\002\D | GG | 14 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-01-11 10:48 | 2023-01-12 06:28 | 26612.9293 | [6 empty] | 26613 | 19941 | 4.72 | 0 | 0 | 6.22 | 5841
TS5500Shv | GG\15\021\B | GG | 15 | 21 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-01-11 18:09 | 2023-01-13 13:58 | 53422.0583 | [6 empty] | 53422 | 37933 | 3.8 | 0 | 0 | 14.66 | 5199
TS6060#1 | GG\15\013\B | GG | 15 | 13 | B | 8 Coal Mining | 64 | 0 | 64 | 2023-01-12 06:28 | 2023-01-13 02:14 | 26756.8044 | [6 empty] | 26757 | 19570 | 2.06 | 0 | 0 | 10.69 | 5458
DRE1 | MW\44\008\D | MW | 44 | 8 | D | 6 DL | 100 | 100 | 100 | 2023-01-12 13:10 | 2023-01-16 14:31 | 340102.0193 |  |  |  | 17486 | 340102 | 273947 |  |  | 0 | 29.15 | 0 | 5.3 | 5947.35
TS6060#1 | RS\31\003\X | RS | 31 | 3 | X | 1 Prestrip - Thick | 54.3806 | 54.3806 | 54.3806 | 2023-01-13 02:14 | 2023-01-17 08:55 | 103436.8174 | 103437 | [7 empty] | 0 | 0 | 21.67 | 12.19 | 5238.53
PH4100XPC#1 | GG\16\012\X2 | GG | 16 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2023-01-13 09:04 | 2023-01-14 22:03 | 80119.229 | 80119 | [7 empty] | 0 | 0 | 8.06 | 0 | 0
TS Fleet 5 | GG\16\013\B | GG | 16 | 13 | B | 1 Prestrip - Thick | 45.419 | 45.419 | 45.419 | 2023-01-13 09:57 | 2023-01-14 22:24 | 71439.7365 | 71440 | [7 empty] | 0 | 0 | 6.64 | 10.54 | 5468.74
TS5500Exc | RS\26\005\A | RS | 26 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-01-13 11:37 | 2023-01-15 01:19 | 47486.8229 | [6 empty] | 47487 | 32298 | 3.25 | 0 | 0 | 18.2 | 4841
TS5500Shv | MW\44\006\D | MW | 44 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-01-13 13:58 | 2023-01-15 15:49 | 60797.4862 | [6 empty] | 60797 | 46083 | 4.61 | 0 | 0 | 5.63 | 5918
DRE2 | GG\15\023\B | GG | 15 | 23 | B | 6 DL | 100 | 0 | 100 | 2023-01-14 05:35 | 2023-01-16 23:22 | 221291.0563 |  |  |  |  | 221291 | 184409 |  |  | 0 | 18.7 | 0 | 12.78 | 5303.76
PH4100A | RS\28\004\X | RS | 28 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-01-14 08:48 | 2023-01-25 15:24 | 457472.9387 | 457473 | [7 empty] | 0 | 0 | 46.41 | 12.32 | 5215.89
PH4100XPC#1 | GG\16\012\B | GG | 16 | 12 | B | 1 Prestrip - Thick | 100 | 54.581 | 54.581 | 2023-01-14 22:03 | 2023-01-16 07:57 | 73443.3659 | 73443 | [7 empty] | 0 | 0 | 7.27 | 9.99 | 5513.73
TS Fleet 5 | GG\16\012\B | GG | 16 | 12 | B | 1 Prestrip - Thick | 45.419 | 45.419 | 45.419 | 2023-01-14 22:24 | 2023-01-16 05:34 | 61115.0363 | 61115 | [7 empty] | 0 | 0 | 6.05 | 9.99 | 5513.73
TS5500Exc | RS\26\006\A | RS | 26 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-01-15 01:19 | 2023-01-15 23:26 | 27852.1246 | [6 empty] | 27852 | 18846 | 1.68 | 0 | 0 | 19.5 | 4745
TS5500Shv | RS\27\004\X | RS | 27 | 4 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-01-15 15:49 | 2023-01-15 22:27 | 8076.6277 | [6 empty] | 8077 | 5657 | 0.57 | 0 | 0 | 12.36 | 5207
TS5500Shv | MW\44\007\D | MW | 44 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-01-15 22:27 | 2023-01-18 02:01 | 62896.9161 | [6 empty] | 62897 | 47754 | 4.78 | 0 | 0 | 5.44 | 5935
TS5500Exc | RS\27\003\X | RS | 27 | 3 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-01-15 23:26 | 2023-01-16 07:26 | 10085.917 | [6 empty] | 10086 | 7067 | 1.21 | 0 | 0 | 12.28 | 5210
TS Fleet 5 | GG\18\003\X1 | GG | 18 | 3 | X1 | 1 Prestrip - Thick | 40.7433 | 40.7433 | 40.7433 | 2023-01-16 05:34 | 2023-01-26 21:45 | 502095.4833 | 502095 | [7 empty] | 0 | 0 | 40.82 | 10.28 | 5334.03
TS5500Exc | RS\27\004\X | RS | 27 | 4 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-01-16 07:26 | 2023-01-16 14:03 | 8342.8901 | [6 empty] | 8343 | 5843 | 0.59 | 0 | 0 | 12.36 | 5207
PH4100XPC#1 | GG\16\013\B | GG | 16 | 13 | B | 1 Prestrip - Thick | 100 | 54.581 | 54.581 | 2023-01-16 07:57 | 2023-01-17 23:35 | 85850.7991 | 85851 | [7 empty] | 0 | 0 | 7.98 | 10.54 | 5468.74
TS5500Exc | RS\28\003\X | RS | 28 | 3 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-01-16 14:03 | 2023-01-16 18:04 | 5055.3541 | [6 empty] | 5055 | 3544 | 0.61 | 0 | 0 | 12.25 | 5218
DRE1 | MW\44\009\D | MW | 44 | 9 | D | 6 DL | 100 | 100 | 100 | 2023-01-16 14:31 | 2023-01-19 21:30 | 275884.3272 |  |  |  | 10043 | 275884 | 155624 |  |  | 0 | 28.54 | 0 | 5.25 | 5950.82
TS5500Exc | MW\44\004\D | MW | 44 | 4 | D | 8 Coal Mining | 76.7 | 0 | 76.7 | 2023-01-16 18:04 | 2023-01-18 07:50 | 47559.0624 | [6 empty] | 47559 | 35761 | 3.58 | 0 | 0 | 6.54 | 5838
DRE2 | GG\14\013\D | GG | 14 | 13 | D | 6 DL | 100 | 100 | 100 | 2023-01-16 23:22 | 2023-01-22 03:21 | 417049.4897 |  |  |  | 9710 | 417049 | 184492 |  |  | 0 | 23.66 | 0 | 6.99 | 5774.3
TS6060#1 | RS\26\005\B | RS | 26 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-01-17 08:55 | 2023-01-18 10:06 | 25995.7903 | 25996 | [7 empty] | 0 | 0 | 2.61 | 8.71 | 5617.86
PH4100XPC#1 | GG\16\018\X2 | GG | 16 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.2611 | 2023-01-17 23:35 | 2023-01-20 19:39 | 145599.5803 | 145600 | [7 empty] | 0 | 0 | 14.5 | 0 | 0
TS5500Shv | GG\15\022\B | GG | 15 | 22 | B | 8 Coal Mining | 89.7 | 0 | 89.7 | 2023-01-18 02:01 | 2023-01-19 18:34 | 49435.9713 | [6 empty] | 49436 | 34823 | 3.49 | 0 | 0 | 16.4 | 5054
TS5500Exc | MW\45\008\B | MW | 45 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-01-18 07:50 | 2023-01-19 21:24 | 33224.4391 | 33224 | [7 empty] | 0 | 0 | 3.33 | 9.86 | 5473.68
TS6060#1 | RS\26\006\B | RS | 26 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-01-18 10:06 | 2023-01-19 19:13 | 34166.7567 | 34167 | [7 empty] | 0 | 0 | 3.06 | 8.88 | 5609.38
TS5500Shv | RS\26\005\B | RS | 26 | 5 | B | 8 Coal Mining | 19.3 | 0 | 19.3 | 2023-01-19 18:34 | 2023-01-20 01:03 | 7914.3489 | [6 empty] | 7914 | 5684 | 0.57 | 0 | 0 | 8.71 | 5618
TS6060#1 | RS\27\003\A | RS | 27 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-01-19 19:13 | 2023-01-24 19:03 | 123638.0232 | 123638 | [7 empty] | 0 | 0 | 19.06 | 11.76 | 5357.59
TS5500Exc | RS\26\005\B | RS | 26 | 5 | B | 8 Coal Mining | 80.7 | 0 | 80.7 | 2023-01-19 21:24 | 2023-01-20 23:43 | 33144.3504 | [6 empty] | 33144 | 23802 | 2.39 | 0 | 0 | 8.71 | 5618
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2023-01-19 21:30 | 2023-01-21 21:30
TS5500Shv | MW\45\008\B | MW | 45 | 8 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-01-20 01:03 | 2023-01-20 16:29 | 18817.7815 | [6 empty] | 18818 | 13872 | 1.39 | 0 | 0 | 9.86 | 5474
TS5500Shv | MW\44\008\D | MW | 44 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-01-20 16:29 | 2023-01-22 20:04 | 62893.8743 | [6 empty] | 62894 | 47829 | 4.78 | 0 | 0 | 5.3 | 5947
PH4100XPC#1 | GG\16\018\B | GG | 16 | 18 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-01-20 19:39 | 2023-01-23 13:20 | 142289.6941 | 142290 | [7 empty] | 0 | 0 | 14.17 | 10.8 | 5451.23
TS5500Exc | RS\26\006\B | RS | 26 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-01-20 23:43 | 2023-01-22 06:58 | 39367.4584 | [6 empty] | 39367 | 28240 | 2.54 | 0 | 0 | 8.88 | 5609
DRE1 | RS\23\003\D | RS | 23 | 3 | D | 6 DL | 100 | 100 | 100 | 2023-01-21 21:30 | 2023-01-26 18:54 | 410102.3679 |  |  |  | 23406 | 410102 | 310962 |  |  | 0 | 30.77 | 0 | 5.88 | 5904.22
DRE2 | GG\14\018\D | GG | 14 | 18 | D | 6 DL | 100 | 100 | 100 | 2023-01-22 03:21 | 2023-01-27 08:45 | 421851.1404 |  |  |  | 9822 | 421851 | 186616 |  |  | 0 | 23.41 | 0 | 7.05 | 5769.09
TS5500Exc | MW\44\005\D | MW | 44 | 5 | D | 8 Coal Mining | 41.8 | 0 | 41.8 | 2023-01-22 06:58 | 2023-01-23 02:37 | 24756.2588 | [6 empty] | 24756 | 18703 | 1.87 | 0 | 0 | 6.06 | 5879
TS5500Shv | GG\14\013\D | GG | 14 | 13 | D | 8 Coal Mining | 17.2 | 0 | 17.2 | 2023-01-22 20:04 | 2023-01-23 03:25 | 8971.9351 | [6 empty] | 8972 | 6686 | 0.82 | 0 | 0 | 6.99 | 5774
TS5500Exc | MW\45\008\B | MW | 45 | 8 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-01-23 02:37 | 2023-01-23 18:03 | 19438.1479 | [6 empty] | 19438 | 14329 | 1.43 | 0 | 0 | 9.86 | 5474
TS5500Shv | MW\44\009\D | MW | 44 | 9 | D | 7 PostStrip | 89.5029 | 0 | 89.5029 | 2023-01-23 03:25 | 2023-01-24 08:48 | 31491.8249 |  |  | 31492 | [5 empty] | 0 | 0 | 0 | 5.25 | 5950.82
PH4100XPC#1 | GG\16\019\X2 | GG | 16 | 19 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.4005 | 2023-01-23 13:20 | 2023-01-25 21:50 | 121515.2525 | 121515 | [7 empty] | 0 | 0 | 12.3 | 0 | 0
TS5500Exc | MW\45\009\A | MW | 45 | 9 | A | 8 Coal Mining | 52.7 | 0 | 52.7 | 2023-01-23 18:03 | 2023-01-24 08:47 | 18568.5193 | [6 empty] | 18569 | 13517 | 1.75 | 0 | 0 | 12.62 | 5292
TS5500Exc | MW\46\002\D | MW | 46 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-01-24 08:47 | 2023-02-01 05:17 | 166934.6894 | 166935 | [7 empty] | 0 | 0 | 51.4 | 6.76 | 5813.71
TS5500Shv | MW\45\009\A | MW | 45 | 9 | A | 8 Coal Mining | 47.3 | 0 | 47.3 | 2023-01-24 08:48 | 2023-01-24 22:29 | 16693.0826 | [6 empty] | 16693 | 12151 | 1.57 | 0 | 0 | 12.62 | 5292
TS6060#1 | RS\27\004\A | RS | 27 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-01-24 19:03 | 2023-02-01 06:00 | 184646.7076 | 184647 | [7 empty] | 0 | 0 | 18.51 | 13.6 | 5206.19
TS5500Shv | RS\27\003\A | RS | 27 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-01-24 22:29 | 2023-01-25 12:20 | 16887.5022 | [6 empty] | 16888 | 11953 | 1.67 | 0 | 0 | 11.76 | 5358
TS5500Shv | GG\18\003\X1 | GG | 18 | 3 | X1 | 1 Prestrip - Thick | 12.7083 | 12.7083 | 12.7083 | 2023-01-25 12:20 | 2023-01-31 15:01 | 156609.0541 | 156609 | [7 empty] | 0 | 0 | 12.73 | 10.28 | 5334.03
PH4100A | RS\27\005\X | RS | 27 | 5 | X | 1 Prestrip - Thick | 100 | 79.7604 | 79.7604 | 2023-01-25 15:24 | 2023-02-06 06:04 | 475094.4743 | 475094 | [7 empty] | 0 | 0 | 48.16 | 12.52 | 5202.72
PH4100XPC#1 | GG\16\019\B | GG | 16 | 19 | B | 1 Prestrip - Thick | 100 | 72.4597 | 72.4597 | 2023-01-25 21:50 | 2023-01-27 15:04 | 89362.5114 | 89363 | [7 empty] | 0 | 0 | 8.89 | 11.72 | 5390.77
DRE1 | RS\23\004\D | RS | 23 | 4 | D | 6 DL | 100 | 100 | 100 | 2023-01-26 18:54 | 2023-01-31 06:47 | 376810.505 |  |  |  | 21506 | 376811 | 285719 |  |  | 0 | 30.72 | 0 | 6.27 | 5869.36
TS Fleet 5 | GG\16\019\B | GG | 16 | 19 | B | 1 Prestrip - Thick | 39.6677 | 27.5403 | 27.5403 | 2023-01-26 21:45 | 2023-01-27 15:04 | 33964.5936 | 33965 | [7 empty] | 0 | 0 | 3.38 | 11.72 | 5390.77
DRE2 | GG\14\019\D | GG | 14 | 19 | D | 6 DL | 100 | 100 | 100 | 2023-01-27 08:45 | 2023-02-02 09:13 | 485908.5795 |  |  |  | 11313 | 485909 | 214954 |  |  | 0 | 22.61 | 0 | 6.84 | 5788.51
TS Fleet 5 | GG\18\004\X1 | GG | 18 | 4 | X1 | 1 Prestrip - Thick | 45.9312 | 45.9312 | 45.9312 | 2023-01-27 15:04 | 2023-02-05 05:02 | 403669.2291 | 403669 | [7 empty] | 0 | 0 | 42.9 | 10.22 | 5332.74
PH4100XPC#1 | GG\16\020\B | GG | 16 | 20 | B | 1 Prestrip - Thick | 100 | 43.7301 | 43.7301 | 2023-01-27 15:04 | 2023-01-30 16:42 | 167479.2959 | 167479 | [7 empty] | 0 | 0 | 16.14 | 15.24 | 5127.95
PH4100XPC#1 | GG\16\021\B | GG | 16 | 21 | B | 1 Prestrip - Thick | 100 | 54.0645 | 54.0645 | 2023-01-30 16:42 | 2023-02-03 05:28 | 187915.3664 | 187915 | [7 empty] | 0 | 0 | 20.01 | 14.89 | 5184.21
DRE1 | RS\23\005\D | RS | 23 | 5 | D | 6 DL | 100 | 100 | 100 | 2023-01-31 06:47 | 2023-02-04 07:59 | 339550.1943 |  |  |  | 17458 | 339550 | 273502 |  |  | 0 | 29.1 | 0 | 6.48 | 5849.73
TS5500Shv | GG\14\018\D | GG | 14 | 18 | D | 8 Coal Mining | 36.6 | 0 | 36.6 | 2023-01-31 15:01 | 2023-02-01 07:05 | 19588.9572 | [6 empty] | 19589 | 14599 | 1.76 | 0 | 0 | 7.05 | 5769
TS5500Exc | RS\27\003\A | RS | 27 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-02-01 05:17 | 2023-02-01 19:08 | 17444.2331 | [6 empty] | 17444 | 12347 | 1.73 | 0 | 0 | 11.76 | 5358
TS6060#1 | GG\15\022\B | GG | 15 | 22 | B | 8 Coal Mining | 10.3 | 0 | 10.3 | 2023-02-01 06:00 | 2023-02-01 10:12 | 5677.4962 | [6 empty] | 5677 | 3999 | 0.4 | 0 | 0 | 16.4 | 5054
TS5500Shv | RS\27\004\A | RS | 27 | 4 | A | 8 Coal Mining | 29 | 0 | 29 | 2023-02-01 07:05 | 2023-02-01 18:52 | 14373.243 | [6 empty] | 14373 | 10043 | 1.01 | 0 | 0 | 13.6 | 5206
TS6060#1 | GG\15\023\B | GG | 15 | 23 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-02-01 10:12 | 2023-02-02 13:09 | 36482.0344 | [6 empty] | 36482 | 26270 | 2.64 | 0 | 0 | 12.78 | 5304
TS5500Shv | RS\23\004\D | RS | 23 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-02-01 18:52 | 2023-02-03 19:23 | 59162.9109 | [6 empty] | 59163 | 43268 | 4.33 | 0 | 0 | 6.27 | 5869
TS5500Exc | RS\27\004\A | RS | 27 | 4 | A | 8 Coal Mining | 71 | 0 | 71 | 2023-02-01 19:08 | 2023-02-02 23:00 | 35116.2162 | [6 empty] | 35116 | 24538 | 2.46 | 0 | 0 | 13.6 | 5206
DRE2 | GG\14\020\D | GG | 14 | 20 | D | 6 DL | 100 | 100 | 100 | 2023-02-02 09:13 | 2023-02-07 22:06 | 447013.6788 |  |  |  | 10408 | 447014 | 197748 |  |  | 0 | 20.81 | 0 | 6.67 | 5802.59
TS6060#1 | GG\14\019\D | GG | 14 | 19 | D | 8 Coal Mining | 100 | 0 | 61.6 | 2023-02-02 13:09 | 2023-02-03 18:59 | 40373.79 | [6 empty] | 40374 | 30113 | 3.01 | 0 | 0 | 6.84 | 5789
TS5500Exc | GG\14\019\D | GG | 14 | 19 | D | 8 Coal Mining | 100 | 0 | 38.4 | 2023-02-02 23:00 | 2023-02-03 18:59 | 25167.2264 | [6 empty] | 25167 | 18771 | 1.88 | 0 | 0 | 6.84 | 5789
PH4100XPC#1 | GG\16\022\B | GG | 16 | 22 | B | 1 Prestrip - Thick | 100 | 44.8678 | 44.8678 | 2023-02-03 05:28 | 2023-02-05 21:30 | 139767.3637 | 139767 | [7 empty] | 0 | 0 | 14.45 | 16.7 | 5035.36
TS6060#1 | RS\27\003\B | RS | 27 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-02-03 18:59 | 2023-02-04 13:45 | 19365.3534 | 19365 | [7 empty] | 0 | 0 | 2.65 | 8.76 | 5614.8
TS5500Exc | RS\28\004\X | RS | 28 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-02-03 18:59 | 2023-02-04 07:56 | 16310.4659 | [6 empty] | 16310 | 11429 | 1.15 | 0 | 0 | 12.32 | 5216
TS5500Shv | GG\18\008\X1 | GG | 18 | 8 | X1 | 1 Prestrip - Thick | 19.3854 | 19.3854 | 19.3854 | 2023-02-03 19:23 | 2023-02-08 13:22 | 121074.1193 | 121074 | [7 empty] | 0 | 0 | 11.83 | 12.04 | 5314.64
TS5500Exc | MW\45\009\B | MW | 45 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-02-04 07:56 | 2023-02-05 12:02 | 24852.3721 | 24852 | [7 empty] | 0 | 0 | 3.25 | 9.51 | 5516.38
DRE1 | RS\23\006\D | RS | 23 | 6 | D | 6 DL | 100 | 100 | 100 | 2023-02-04 07:59 | 2023-02-09 05:04 | 408970.6115 |  |  |  | 14981 | 408971 | 231034 |  |  | 0 | 27.95 | 0 | 6.58 | 5840.21
TS6060#1 | GG\14\013\D | GG | 14 | 13 | D | 8 Coal Mining | 82.8 | 0 | 82.8 | 2023-02-04 13:45 | 2023-02-05 21:44 | 43281.1168 | [6 empty] | 43281 | 32255 | 3.97 | 0 | 0 | 6.99 | 5774
TS Fleet 5 | GG\18\005\X1 | GG | 18 | 5 | X1 | 1 Prestrip - Thick | 46.1217 | 46.1217 | 46.1217 | 2023-02-05 05:02 | 2023-02-13 10:44 | 387506.4975 | 387506 | [7 empty] | 0 | 0 | 44.58 | 10.41 | 5328.42
TS5500Exc | RS\27\003\B | RS | 27 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-02-05 12:02 | 2023-02-06 11:40 | 29772.0116 | [6 empty] | 29772 | 21405 | 2.86 | 0 | 0 | 8.76 | 5615
PH4100XPC#1 | GG\16\023\B | GG | 16 | 23 | B | 1 Prestrip - Thick | 100 | 54.4378 | 54.4378 | 2023-02-05 21:30 | 2023-02-10 17:32 | 261139.9321 | 261140 | [7 empty] | 0 | 0 | 18.51 | 0 | 0
TS6060#1 | MW\44\009\D | MW | 44 | 9 | D | 7 PostStrip | 10.4971 | 0 | 10.4971 | 2023-02-05 21:44 | 2023-02-06 01:19 | 3693.4303 |  |  | 3693 | [5 empty] | 0 | 0 | 0 | 5.25 | 5950.82
TS6060#1 | RS\27\004\B | RS | 27 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-02-06 01:19 | 2023-02-07 02:50 | 26335.821 | 26336 | [7 empty] | 0 | 0 | 2.64 | 8.74 | 5615.14
PH4100A | RS\28\005\X | RS | 28 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-02-06 06:04 | 2023-02-20 20:33 | 597083.8776 | 597084 | [7 empty] | 0 | 0 | 60.8 | 12.47 | 5211.96
TS5500Exc | RS\27\005\X | RS | 27 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-02-06 11:40 | 2023-02-07 04:58 | 21786.1879 | [6 empty] | 21786 | 15242 | 1.54 | 0 | 0 | 12.52 | 5203
TS6060#1 | GG\14\018\D | GG | 14 | 18 | D | 8 Coal Mining | 63.4 | 0 | 63.4 | 2023-02-07 02:50 | 2023-02-08 03:58 | 34004.5311 | [6 empty] | 34005 | 25342 | 3.05 | 0 | 0 | 7.05 | 5769
TS5500Exc | RS\27\004\B | RS | 27 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-02-07 04:58 | 2023-02-07 20:52 | 20031.5957 | [6 empty] | 20032 | 14402 | 1.44 | 0 | 0 | 8.74 | 5615
TS5500Exc | MW\45\009\B | MW | 45 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-02-07 20:52 | 2023-02-08 19:29 | 28481.4436 | [6 empty] | 28481 | 21039 | 2.78 | 0 | 0 | 9.51 | 5516
DRE2 | GG\14\021\D | GG | 14 | 21 | D | 6 DL | 100 | 100 | 100 | 2023-02-07 22:06 | 2023-02-13 03:37 | 422167.7922 |  |  |  | 7862 | 422168 | 188678 |  |  | 0 | 19.66 | 0 | 6.65 | 5803.56
TS6060#1 | RS\27\005\A | RS | 27 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-02-08 03:58 | 2023-02-14 22:28 | 167678.1979 | 167678 | [7 empty] | 0 | 0 | 16.88 | 17.69 | 4887.62
TS5500Shv | MW\44\009\D | MW | 44 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-02-08 13:22 | 2023-02-09 23:57 | 42172.9407 | [6 empty] | 42173 | 32122 | 4.64 | 0 | 0 | 5.25 | 5951
TS5500Exc | RS\23\003\D | RS | 23 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-02-08 19:29 | 2023-02-11 00:41 | 67010.9117 | [6 empty] | 67011 | 49091 | 4.48 | 0 | 0 | 5.88 | 5904
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2023-02-09 05:04 | 2023-02-11 05:04
TS5500Shv | RS\27\004\B | RS | 27 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-02-09 23:57 | 2023-02-10 15:51 | 19392.2895 | [6 empty] | 19392 | 13942 | 1.4 | 0 | 0 | 8.74 | 5615
TS5500Shv | GG\14\020\D | GG | 14 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-02-10 15:51 | 2023-02-12 21:06 | 64935.6529 | [6 empty] | 64936 | 48470 | 4.85 | 0 | 0 | 6.67 | 5803
PH4100XPC#1 | GG\17\003\X1 | GG | 17 | 3 | X1 | 1 Prestrip - Thick | 100 | 53.2996 | 53.2996 | 2023-02-10 17:32 | 2023-02-24 20:18 | 728233.9037 | 728234 | [7 empty] | 0 | 0 | 50.63 | 10.19 | 5342.18
TS5500Exc | RS\23\005\D | RS | 23 | 5 | D | 8 Coal Mining | 34.8 | 0 | 34.8 | 2023-02-11 00:41 | 2023-02-11 16:25 | 19822.5805 | [6 empty] | 19823 | 14472 | 1.45 | 0 | 0 | 6.48 | 5850
DRE1 | MW\45\002\D | MW | 45 | 2 | D | 6 DL | 100 | 0 | 100 | 2023-02-11 05:04 | 2023-02-14 07:28 | 259885.5119 |  |  |  | 13761 | 259886 | 119521 |  |  | 0 | 35 | 0 | 6.67 | 5822.33
TS5500Exc | RS\23\006\D | RS | 23 | 6 | D | 7 PostStrip | 22.065 | 0 | 22.065 | 2023-02-11 16:25 | 2023-02-12 05:48 | 11828.2442 |  |  | 11828 | [5 empty] | 0 | 0 | 0 | 6.58 | 5840.21
TS5500Exc | MW\46\003\D | MW | 46 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-02-12 05:48 | 2023-02-23 05:04 | 232972.2038 | 232972 | [7 empty] | 0 | 0 | 25.08 | 6.84 | 5812.07
TS5500Shv | RS\23\005\D | RS | 23 | 5 | D | 8 Coal Mining | 65.2 | 0 | 65.2 | 2023-02-12 21:06 | 2023-02-14 03:37 | 37207.3489 | [6 empty] | 37207 | 27164 | 2.72 | 0 | 0 | 6.48 | 5850
DRE2 | GG\14\022\D | GG | 14 | 22 | D | 6 DL | 100 | 100 | 100 | 2023-02-13 03:37 | 2023-02-18 09:50 | 424613.032 |  |  |  | 7907 | 424613 | 189771 |  |  | 0 | 19.79 | 0 | 6.55 | 5809.59
TS Fleet 5 | GG\18\006\X1 | GG | 18 | 6 | X1 | 1 Prestrip - Thick | 46.7464 | 46.7464 | 46.7464 | 2023-02-13 10:44 | 2023-02-20 17:17 | 342099.2504 | 342099 | [7 empty] | 0 | 0 | 33.83 | 10.81 | 5334.33
TS5500Shv | GG\14\021\D | GG | 14 | 21 | D | 8 Coal Mining | 48.8 | 0 | 48.8 | 2023-02-14 03:37 | 2023-02-15 05:15 | 31253.3368 | [6 empty] | 31253 | 23310 | 2.33 | 0 | 0 | 6.65 | 5804
DRE1 | MW\45\003\D | MW | 45 | 3 | D | 6 DL | 100 | 0 | 100 | 2023-02-14 07:28 | 2023-02-19 11:15 | 432413.099 |  |  |  | 30752 | 432413 | 310941 |  |  | 0 | 35 | 0 | 6.74 | 5820.88
TS6060#1 | GG\14\021\D | GG | 14 | 21 | D | 8 Coal Mining | 51.2 | 0 | 51.2 | 2023-02-14 22:28 | 2023-02-15 22:39 | 32727.1898 | [6 empty] | 32727 | 24409 | 2.44 | 0 | 0 | 6.65 | 5804
TS5500Shv | RS\27\005\A | RS | 27 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-02-15 05:15 | 2023-02-16 19:49 | 47031.8191 | [6 empty] | 47032 | 32166 | 3.23 | 0 | 0 | 17.69 | 4888
TS6060#1 | RS\28\003\A | RS | 28 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-02-15 22:39 | 2023-02-20 20:58 | 122072.3129 | 122072 | [7 empty] | 0 | 0 | 18.99 | 11.32 | 5391.88
TS5500Shv | RS\23\006\D | RS | 23 | 6 | D | 7 PostStrip | 77.935 | 0 | 77.935 | 2023-02-16 19:49 | 2023-02-18 10:47 | 41778.2107 |  |  | 41778 | [5 empty] | 0 | 0 | 0 | 6.58 | 5840.21
DRE2 | GG\14\023\D | GG | 14 | 23 | D | 6 DL | 100 | 100 | 100 | 2023-02-18 09:50 | 2023-02-24 04:44 | 467207.3252 |  |  |  | 10878 | 467207 | 206681 |  |  | 0 | 21.8 | 0 | 6.35 | 5827.21
TS5500Shv | RS\23\006\D | RS | 23 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-02-18 10:47 | 2023-02-19 11:24 | 30003.459 | [6 empty] | 30003 | 21899 | 2.05 | 0 | 0 | 6.58 | 5840
DRE1 | MW\45\004\D | MW | 45 | 4 | D | 6 DL | 100 | 100 | 100 | 2023-02-19 11:15 | 2023-02-24 10:34 | 416754.8457 |  |  |  | 23785 | 416755 | 316007 |  |  | 0 | 34.73 | 0 | 6.62 | 5830.93
TS5500Shv | MW\45\002\D | MW | 45 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2023-02-19 11:24 | 2023-02-20 05:42 | 19621.8614 |  |  | 19622 | [5 empty] | 0 | 0 | 0 | 6.67 | 5822.33
TS5500Shv | MW\45\002\D | MW | 45 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-02-20 05:42 | 2023-02-20 22:07 | 20013.6803 | [6 empty] | 20014 | 15031 | 3.97 | 0 | 0 | 6.67 | 5822
TS Fleet 5 | GG\18\007\X1 | GG | 18 | 7 | X1 | 1 Prestrip - Thick | 46.8959 | 46.8959 | 46.8959 | 2023-02-20 17:17 | 2023-02-27 09:45 | 314527.0708 | 314527 | [7 empty] | 0 | 0 | 30.81 | 11.41 | 5332.29
PH4100A | RS\27\006\X | RS | 27 | 6 | X | 1 Prestrip - Thick | 100 | 40.8774 | 40.8774 | 2023-02-20 20:33 | 2023-03-01 16:30 | 361798.4557 | 361798 | [7 empty] | 0 | 0 | 27.83 | 13.02 | 5165.56
TS6060#1 | RS\27\005\B | RS | 27 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-02-20 20:58 | 2023-02-21 21:59 | 25816.7149 | 25817 | [7 empty] | 0 | 0 | 2.6 | 8.63 | 5626.71
TS5500Shv | RS\28\005\X | RS | 28 | 5 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-02-20 22:07 | 2023-02-21 07:08 | 11006.3715 | [6 empty] | 11006 | 7704 | 0.78 | 0 | 0 | 12.47 | 5212
TS5500Shv | GG\14\022\D | GG | 14 | 22 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2023-02-21 07:08 | 2023-02-22 08:46 | 31261.0023 | [6 empty] | 31261 | 23370 | 2.34 | 0 | 0 | 6.55 | 5810
TS6060#1 | GG\14\022\D | GG | 14 | 22 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2023-02-21 21:59 | 2023-02-22 19:28 | 29082.033 | [6 empty] | 29082 | 21741 | 2.17 | 0 | 0 | 6.55 | 5810
TS5500Shv | RS\28\003\A | RS | 28 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-02-22 08:46 | 2023-02-23 12:25 | 33714.8374 | [6 empty] | 33715 | 23975 | 3.38 | 0 | 0 | 11.32 | 5392
TS6060#1 | RS\28\004\A | RS | 28 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-02-22 19:28 | 2023-03-02 04:59 | 183155.0305 | 183155 | [7 empty] | 0 | 0 | 18.36 | 13 | 5255.65
TS5500Exc | RS\28\005\X | RS | 28 | 5 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-02-23 05:04 | 2023-02-23 14:06 | 11369.2189 | [6 empty] | 11369 | 7958 | 0.8 | 0 | 0 | 12.47 | 5212
TS5500Shv | MW\45\003\D | MW | 45 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-02-23 12:25 | 2023-02-25 15:57 | 62839.9063 | [6 empty] | 62840 | 47178 | 4.72 | 0 | 0 | 6.74 | 5821
TS5500Exc | RS\27\005\B | RS | 27 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-02-23 14:06 | 2023-02-24 23:48 | 42459.5144 | [6 empty] | 42460 | 30520 | 3.07 | 0 | 0 | 8.63 | 5627
DRE2 | GG\14\024\D | GG | 14 | 24 | D | 6 DL | 100 | 0 | 100 | 2023-02-24 04:44 | 2023-03-01 02:41 | 396764.0287 |  |  |  | 21965 | 396764 | 172338 |  |  | 0 | 40 | 0 | 6.28 | 5835.84
DRE1 | MW\45\005\D | MW | 45 | 5 | D | 6 DL | 100 | 100 | 100 | 2023-02-24 10:34 | 2023-02-28 07:46 | 325559.803 |  |  |  | 16738 | 325560 | 262233 |  |  | 0 | 27.9 | 0 | 6.16 | 5870.65
PH4100XPC#1 | GG\17\004\X1 | GG | 17 | 4 | X1 | 1 Prestrip - Thick | 100 | 54.035 | 54.035 | 2023-02-24 20:18 | 2023-03-05 15:49 | 468351.3284 | 468351 | [7 empty] | 0 | 0 | 47.67 | 10.1 | 5344.46
TS5500Exc | MW\45\004\D | MW | 45 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-02-24 23:48 | 2023-02-27 00:48 | 61709.4743 | [6 empty] | 61709 | 46364 | 4.64 | 0 | 0 | 6.62 | 5831
TS5500Shv | GG\17\003\X1 | GG | 17 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-02-25 15:57 | 2023-02-26 09:19 | 21163.3461 | [6 empty] | 21163 | 15716 | 1.25 | 0 | 0 | 10.19 | 5342
TS5500Shv | GG\17\003\X2 | GG | 17 | 3 | X2 | 1 Prestrip - Thick | 55.6937 | 0 | 55.6937 | 2023-02-26 09:19 | 2023-03-01 17:12 | 85645.7667 | 85646 | [7 empty] | 0 | 0 | 6.91 | 0 | 0
TS5500Exc | RS\23\006\D | RS | 23 | 6 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-02-27 00:48 | 2023-02-28 01:24 | 30992.584 | [6 empty] | 30993 | 22621 | 2.12 | 0 | 0 | 6.58 | 5840
TS Fleet 5 | GG\17\003\X2 | GG | 17 | 3 | X2 | 1 Prestrip - Thick | 20.6055 | 0 | 20.6055 | 2023-02-27 09:45 | 2023-02-28 01:55 | 31687.0649 | 31687 | [7 empty] | 0 | 0 | 2.56 | 0 | 0
TS5500Exc | MW\46\004\D | MW | 46 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-02-28 01:24 | 2023-03-03 04:32 | 66471.5488 | 66472 | [7 empty] | 0 | 0 | 7.04 | 6.79 | 5816.07
TS Fleet 5 | GG\18\008\X1 | GG | 18 | 8 | X1 | 1 Prestrip - Thick | 37.8325 | 37.8325 | 37.8325 | 2023-02-28 01:55 | 2023-03-05 02:28 | 236287.9262 | 236288 | [7 empty] | 0 | 0 | 23.09 | 12.04 | 5314.64
DRE1 | MW\45\006\D | MW | 45 | 6 | D | 6 DL | 100 | 100 | 100 | 2023-02-28 07:46 | 2023-03-04 11:07 | 347089.101 |  |  |  | 17845 | 347089 | 279575 |  |  | 0 | 29.73 | 0 | 5.68 | 5913.63
DRE2 | GG\16\012\B | GG | 16 | 12 | B | 6 DL | 100 | 0 | 100 | 2023-03-01 02:41 | 2023-03-03 14:08 | 199968.4657 |  |  |  |  | 199968 | 166640 |  |  | 0 | 16.49 | 0 | 9.99 | 5513.73
PH4100A | RS\28\006\X | RS | 28 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-03-01 16:30 | 2023-03-23 01:45 | 875203.925 | 875204 | [7 empty] | 0 | 0 | 67.83 | 13.02 | 5171.29
TS5500Shv | RS\27\006\X | RS | 27 | 6 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-03-01 17:12 | 2023-03-02 02:10 | 10929.8549 | [6 empty] | 10930 | 7625 | 0.61 | 0 | 0 | 13.02 | 5166
TS5500Shv | GG\14\023\D | GG | 14 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-03-02 02:10 | 2023-03-04 03:09 | 59734.9147 | [6 empty] | 59735 | 44941 | 4.5 | 0 | 0 | 6.35 | 5827
TS6060#1 | GG\14\023\D | GG | 14 | 23 | D | 8 Coal Mining | 0 | 0 | 0 | 2023-03-02 04:59 | 2023-03-02 05:00 | 24.9251 | [6 empty] | 25 | 19 | 0 | 0 | 0 | 6.35 | 5827
TS6060#1 | GG\14\024\D | GG | 14 | 24 | D | 7 PostStrip | 22.3061 | 0 | 22.3061 | 2023-03-02 05:00 | 2023-03-02 10:29 | 5653.2918 |  |  | 5653 | [5 empty] | 0 | 0 | 0 | 6.28 | 5835.84
TS6060#1 | RS\28\003\B | RS | 28 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-03-02 10:29 | 2023-03-03 05:18 | 19419.7469 | 19420 | [7 empty] | 0 | 0 | 2.68 | 8.74 | 5613.47
TS5500Exc | RS\27\006\X | RS | 27 | 6 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-03-03 04:32 | 2023-03-03 13:30 | 11290.1798 | [6 empty] | 11290 | 7877 | 0.63 | 0 | 0 | 13.02 | 5166
TS6060#1 | RS\28\005\A | RS | 28 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-03-03 05:18 | 2023-03-09 20:06 | 163844.1104 | 163844 | [7 empty] | 0 | 0 | 16.48 | 17.23 | 4928.18
TS5500Exc | RS\28\003\B | RS | 28 | 3 | B | 8 Coal Mining | 79.3 | 0 | 79.3 | 2023-03-03 13:30 | 2023-03-04 08:11 | 23546.4178 | [6 empty] | 23546 | 16954 | 2.29 | 0 | 0 | 8.74 | 5613
DRE2 | GG\16\011\B | GG | 16 | 11 | B | 6 DL | 100 | 0 | 100 | 2023-03-03 14:08 | 2023-03-06 08:25 | 222961.3227 |  |  |  |  | 222961 | 171509 |  |  | 0 | 16.98 | 0 | 9.51 | 5551.89
TS5500Shv | GG\14\024\D | GG | 14 | 24 | D | 7 PostStrip | 77.6939 | 0 | 77.6939 | 2023-03-04 03:09 | 2023-03-04 21:31 | 19690.8986 |  |  | 19691 | [5 empty] | 0 | 0 | 0 | 6.28 | 5835.84
TS5500Exc | RS\28\004\A | RS | 28 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-03-04 08:11 | 2023-03-05 04:04 | 25038.8999 | [6 empty] | 25039 | 17586 | 1.76 | 0 | 0 | 13 | 5256
DRE1 | MW\45\007\D | MW | 45 | 7 | D | 6 DL | 100 | 100 | 100 | 2023-03-04 11:07 | 2023-03-08 14:01 | 345455.9204 |  |  |  | 17761 | 345456 | 278259 |  |  | 0 | 29.6 | 0 | 5.47 | 5932.97
TS5500Shv | GG\16\012\B | GG | 16 | 12 | B | 8 Coal Mining | 36 | 0 | 36 | 2023-03-04 21:31 | 2023-03-05 11:11 | 16650.5781 | [6 empty] | 16651 | 12225 | 1.22 | 0 | 0 | 9.99 | 5514
TS Fleet 5 | GG\18\009\X1 | GG | 18 | 9 | X1 | 1 Prestrip - Thick | 46.4191 | 46.4191 | 46.4191 | 2023-03-05 02:28 | 2023-03-10 14:29 | 258742.8146 | 258743 | [7 empty] | 0 | 0 | 28.53 | 13.13 | 5241.43
TS5500Exc | MW\45\005\D | MW | 45 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-03-05 04:04 | 2023-03-06 04:03 | 30206.7832 | [6 empty] | 30207 | 22802 | 2.28 | 0 | 0 | 6.16 | 5871
TS5500Shv | RS\28\003\B | RS | 28 | 3 | B | 8 Coal Mining | 20.7 | 0 | 20.7 | 2023-03-05 11:11 | 2023-03-05 16:13 | 6144.3583 | [6 empty] | 6144 | 4424 | 0.6 | 0 | 0 | 8.74 | 5613
PH4100XPC#1 | GG\17\003\X2 | GG | 17 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 23.7008 | 2023-03-05 15:49 | 2023-03-06 08:38 | 36447.1249 | 36447 | [7 empty] | 0 | 0 | 2.94 | 0 | 0
TS5500Shv | RS\28\004\A | RS | 28 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-03-05 16:13 | 2023-03-06 12:06 | 24239.7861 | [6 empty] | 24240 | 17024 | 1.71 | 0 | 0 | 13 | 5256
TS5500Exc | MW\46\005\D | MW | 46 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-03-06 04:03 | 2023-03-14 00:05 | 166318.8682 | 166319 | [7 empty] | 0 | 0 | 24.81 | 6.45 | 5845.29
DRE2 | GG\16\010\B | GG | 16 | 10 | B | 6 DL | 100 | 0 | 100 | 2023-03-06 08:25 | 2023-03-09 00:22 | 215075.4256 |  |  |  |  | 215075 | 179230 |  |  | 0 | 18.46 | 0 | 9.43 | 5557.08
PH4100XPC#1 | GG\17\003\B | GG | 17 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-03-06 08:38 | 2023-03-09 03:25 | 144667.9896 | 144668 | [7 empty] | 0 | 0 | 12.2 | 10.21 | 5472.29
TS5500Shv | MW\45\005\D | MW | 45 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-03-06 12:06 | 2023-03-07 12:04 | 29242.7369 | [6 empty] | 29243 | 22075 | 2.21 | 0 | 0 | 6.16 | 5871
TS5500Shv | GG\16\011\B | GG | 16 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-03-07 12:04 | 2023-03-09 04:20 | 49081.7569 | [6 empty] | 49082 | 36123 | 3.61 | 0 | 0 | 9.51 | 5552
DRE1 | MW\45\008\D | MW | 45 | 8 | D | 6 DL | 100 | 100 | 100 | 2023-03-08 14:01 | 2023-03-12 15:04 | 339015.7029 |  |  |  | 17430 | 339016 | 273072 |  |  | 0 | 29.07 | 0 | 5.31 | 5946.63
DRE2 | GG\16\009\B | GG | 16 | 9 | B | 6 DL | 100 | 0 | 100 | 2023-03-09 00:22 | 2023-03-11 21:18 | 231880.4063 |  |  |  |  | 231880 | 193234 |  |  | 0 | 19.33 | 0 | 9.71 | 5537.33
PH4100XPC#1 | GG\17\005\X1 | GG | 17 | 5 | X1 | 1 Prestrip - Thick | 100 | 53.6602 | 53.6602 | 2023-03-09 03:25 | 2023-03-17 05:40 | 423696.2279 | 423696 | [7 empty] | 0 | 0 | 48.7 | 10.32 | 5340.03
TS5500Shv | GG\17\003\B | GG | 17 | 3 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2023-03-09 04:20 | 2023-03-10 03:42 | 28507.6037 | [6 empty] | 28508 | 20941 | 1.82 | 0 | 0 | 10.21 | 5472
TS6060#1 | GG\17\003\B | GG | 17 | 3 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2023-03-09 20:06 | 2023-03-10 19:29 | 31640.3074 | [6 empty] | 31640 | 23242 | 2.02 | 0 | 0 | 10.21 | 5472
TS5500Shv | MW\45\006\D | MW | 45 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-03-10 03:42 | 2023-03-12 05:53 | 61180.9629 | [6 empty] | 61181 | 46374 | 4.64 | 0 | 0 | 5.68 | 5914
TS Fleet 5 | GG\18\010\X2 | GG | 18 | 10 | X2 | 1 Prestrip - Thick | 45.5851 | 0 | 45.5851 | 2023-03-10 14:29 | 2023-03-16 17:07 | 287395.1239 | 287395 | [7 empty] | 0 | 0 | 27.11 | 0 | 0
TS6060#1 | GG\17\004\X1 | GG | 17 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-03-10 19:29 | 2023-03-11 08:42 | 17897.3169 | [6 empty] | 17897 | 13336 | 1.3 | 0 | 0 | 10.1 | 5344
TS6060#1 | RS\27\006\A | RS | 27 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-03-11 08:42 | 2023-03-18 22:57 | 188040.9535 | 188041 | [7 empty] | 0 | 0 | 16.78 | 19.22 | 4772.34
DRE2 | GG\16\008\B | GG | 16 | 8 | B | 6 DL | 100 | 0 | 100 | 2023-03-11 21:18 | 2023-03-14 20:19 | 238880.5522 |  |  |  |  | 238881 | 199067 |  |  | 0 | 19.91 | 0 | 10.21 | 5489.57
TS5500Shv | GG\17\004\X2 | GG | 17 | 4 | X2 | 1 Prestrip - Thick | 57.6391 | 0 | 57.6391 | 2023-03-12 05:53 | 2023-03-15 01:02 | 71986.9769 | 71987 | [7 empty] | 0 | 0 | 7.01 | 0 | 0
DRE1 | MW\45\009\D | MW | 45 | 9 | D | 6 DL | 100 | 100 | 100 | 2023-03-12 15:04 | 2023-03-14 23:14 | 196186.088 |  |  |  | 7141 | 196186 | 110665 |  |  | 0 | 28.55 | 0 | 5.28 | 5948.86
TS5500Exc | MW\45\007\D | MW | 45 | 7 | D | 8 Coal Mining | 9.8 | 0 | 9.8 | 2023-03-14 00:05 | 2023-03-14 05:00 | 6197.8172 | [6 empty] | 6198 | 4706 | 0.47 | 0 | 0 | 5.47 | 5933
TS5500Exc | RS\28\005\A | RS | 28 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-03-14 05:00 | 2023-03-14 23:52 | 23763.9931 | [6 empty] | 23764 | 16324 | 1.64 | 0 | 0 | 17.23 | 4928
DRE2 | GG\16\007\B | GG | 16 | 7 | B | 6 DL | 100 | 0 | 100 | 2023-03-14 20:19 | 2023-03-18 01:39 | 260123.6727 |  |  |  |  | 260124 | 200095 |  |  | 0 | 20.04 | 0 | 10.33 | 5452.39
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2023-03-14 23:14 | 2023-03-16 23:14
TS5500Exc | MW\45\008\D | MW | 45 | 8 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-03-14 23:52 | 2023-03-16 01:08 | 31833.2699 | [6 empty] | 31833 | 24208 | 2.42 | 0 | 0 | 5.31 | 5947
TS5500Shv | GG\16\009\B | GG | 16 | 9 | B | 8 Coal Mining | 68.1 | 0 | 68.1 | 2023-03-15 01:02 | 2023-03-16 05:49 | 35097.908 | [6 empty] | 35098 | 25769 | 2.58 | 0 | 0 | 9.71 | 5537
TS5500Exc | MW\46\006\D | MW | 46 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-03-16 01:08 | 2023-03-27 07:01 | 238833.5634 | 238834 | [7 empty] | 0 | 0 | 35.22 | 5.91 | 5893.28
TS5500Shv | MW\45\007\D | MW | 45 | 7 | D | 8 Coal Mining | 90.2 | 0 | 90.2 | 2023-03-16 05:49 | 2023-03-18 04:37 | 57070.0908 | [6 empty] | 57070 | 43330 | 4.33 | 0 | 0 | 5.47 | 5933
TS Fleet 5 | GG\17\004\X2 | GG | 17 | 4 | X2 | 1 Prestrip - Thick | 19.7007 | 0 | 19.7007 | 2023-03-16 17:07 | 2023-03-17 05:40 | 24604.7558 | 24605 | [7 empty] | 0 | 0 | 2.4 | 0 | 0
DRE1 | RS\24\003\D | RS | 24 | 3 | D | 6 DL | 100 | 100 | 100 | 2023-03-16 23:14 | 2023-03-21 18:33 | 402814.7427 |  |  |  | 22990 | 402815 | 305436 |  |  | 0 | 30.42 | 0 | 5.78 | 5912.85
TS Fleet 5 | GG\18\011\X1 | GG | 18 | 11 | X1 | 1 Prestrip - Thick | 44.6909 | 44.6909 | 44.6909 | 2023-03-17 05:40 | 2023-03-21 00:16 | 177572.4821 | 177572 | [7 empty] | 0 | 0 | 16.25 | 14.31 | 5152.96
PH4100XPC#1 | GG\17\004\X2 | GG | 17 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 22.6602 | 2023-03-17 05:40 | 2023-03-17 18:44 | 28300.9048 | 28301 | [7 empty] | 0 | 0 | 2.76 | 0 | 0
PH4100XPC#1 | GG\17\006\X1 | GG | 17 | 6 | X1 | 1 Prestrip - Thick | 100 | 53.2732 | 53.2732 | 2023-03-17 18:44 | 2023-03-25 02:45 | 377981.272 | 377981 | [7 empty] | 0 | 0 | 36.71 | 10.75 | 5344.54
DRE2 | GG\16\006\B | GG | 16 | 6 | B | 6 DL | 100 | 0 | 100 | 2023-03-18 01:39 | 2023-03-21 07:26 | 261681.173 |  |  |  |  | 261681 | 201293 |  |  | 0 | 20.32 | 0 | 10.07 | 5443.52
TS5500Shv | GG\16\008\B | GG | 16 | 8 | B | 8 Coal Mining | 46.5 | 0 | 46.5 | 2023-03-18 04:37 | 2023-03-19 00:46 | 24569.7573 | [6 empty] | 24570 | 17966 | 1.8 | 0 | 0 | 10.21 | 5490
TS6060#1 | GG\17\005\X1 | GG | 17 | 5 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-03-18 22:57 | 2023-03-19 11:31 | 17016.4827 | [6 empty] | 17016 | 12673 | 1.25 | 0 | 0 | 10.32 | 5340
TS5500Shv | RS\27\006\A | RS | 27 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-03-19 00:46 | 2023-03-19 22:29 | 26481.1295 | [6 empty] | 26481 | 17976 | 1.63 | 0 | 0 | 19.22 | 4772
TS6060#1 | GG\14\024\D | GG | 14 | 24 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-03-19 11:31 | 2023-03-20 09:14 | 29382.0412 | [6 empty] | 29382 | 22195 | 4.73 | 0 | 0 | 6.28 | 5836
TS5500Shv | RS\28\005\A | RS | 28 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-03-19 22:29 | 2023-03-20 17:21 | 23005.5678 | [6 empty] | 23006 | 15803 | 1.59 | 0 | 0 | 17.23 | 4928
TS6060#1 | GG\16\012\B | GG | 16 | 12 | B | 8 Coal Mining | 64 | 0 | 64 | 2023-03-20 09:14 | 2023-03-21 07:07 | 29612.5062 | [6 empty] | 29613 | 21741 | 2.17 | 0 | 0 | 9.99 | 5514
TS5500Shv | MW\45\008\D | MW | 45 | 8 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-03-20 17:21 | 2023-03-21 18:37 | 30817.3144 | [6 empty] | 30817 | 23435 | 2.34 | 0 | 0 | 5.31 | 5947
TS Fleet 5 | GG\17\005\X2 | GG | 17 | 5 | X2 | 1 Prestrip - Thick | 46.5068 | 0 | 46.5068 | 2023-03-21 00:16 | 2023-03-22 00:22 | 47231.2729 | 47231 | [7 empty] | 0 | 0 | 4.64 | 0 | 0
TS6060#1 | GG\16\010\B | GG | 16 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-03-21 07:07 | 2023-03-22 20:01 | 49945.2079 | [6 empty] | 49945 | 36785 | 3.68 | 0 | 0 | 9.43 | 5557
DRE2 | GG\16\005\B | GG | 16 | 5 | B | 6 DL | 100 | 0 | 100 | 2023-03-21 07:26 | 2023-03-24 07:12 | 241410.0729 |  |  |  |  | 241410 | 201175 |  |  | 0 | 19.97 | 0 | 10.57 | 5400.31
DRE1 | RS\24\004\D | RS | 24 | 4 | D | 6 DL | 100 | 100 | 100 | 2023-03-21 18:33 | 2023-03-26 05:27 | 373420.4301 |  |  |  | 21312 | 373420 | 283148 |  |  | 0 | 30.45 | 0 | 6.11 | 5883.67
TS5500Shv | GG\16\007\B | GG | 16 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-03-21 18:37 | 2023-03-23 12:47 | 51421.2141 | [6 empty] | 51421 | 37609 | 3.76 | 0 | 0 | 10.33 | 5452
TS Fleet 5 | GG\18\012\X1 | GG | 18 | 12 | X1 | 1 Prestrip - Thick | 47.0979 | 47.0979 | 47.0979 | 2023-03-22 00:22 | 2023-03-25 06:39 | 153433.0592 | 153433 | [7 empty] | 0 | 0 | 15.45 | 14.05 | 5175.11
TS6060#1 | GG\16\009\B | GG | 16 | 9 | B | 8 Coal Mining | 31.9 | 0 | 31.9 | 2023-03-22 20:01 | 2023-03-23 08:10 | 16454.6489 | [6 empty] | 16455 | 12081 | 1.21 | 0 | 0 | 9.71 | 5537
PH4100A | RS\29\003\X | RS | 29 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-03-23 01:45 | 2023-03-27 19:05 | 191308.2518 | 191308 | [7 empty] | 0 | 0 | 40.08 | 12.22 | 5225.27
TS6060#1 | RS\28\004\B | RS | 28 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-03-23 08:10 | 2023-03-24 09:59 | 26627.1312 | 26627 | [7 empty] | 0 | 0 | 2.67 | 8.71 | 5618.25
TS5500Shv | MW\45\009\D | MW | 45 | 9 | D | 7 PostStrip | 100 | 0 | 100 | 2023-03-23 12:47 | 2023-03-24 12:07 | 25013.145 |  |  | 25013 | [5 empty] | 0 | 0 | 0 | 5.28 | 5948.86
DRE2 | GG\15\012\D | GG | 15 | 12 | D | 6 DL | 100 | 100 | 100 | 2023-03-24 07:12 | 2023-03-30 11:14 | 497952.6856 |  |  |  | 11594 | 497953 | 220282 |  |  | 0 | 23.15 | 0 | 6.63 | 5805.04
TS6060#1 | GG\16\008\B | GG | 16 | 8 | B | 8 Coal Mining | 53.5 | 0 | 53.5 | 2023-03-24 09:59 | 2023-03-25 06:50 | 28218.8612 | [6 empty] | 28219 | 20634 | 2.06 | 0 | 0 | 10.21 | 5490
TS5500Shv | RS\28\004\B | RS | 28 | 4 | B | 8 Coal Mining | 17.7 | 0 | 17.7 | 2023-03-24 12:07 | 2023-03-24 17:53 | 7017.3952 | [6 empty] | 7017 | 5049 | 0.51 | 0 | 0 | 8.71 | 5618
TS5500Shv | MW\45\009\D | MW | 45 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-03-24 17:53 | 2023-03-25 18:21 | 29847.8385 | [6 empty] | 29848 | 22716 | 4.65 | 0 | 0 | 5.28 | 5949
PH4100XPC#1 | GG\17\005\X2 | GG | 17 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.4932 | 2023-03-25 02:45 | 2023-03-26 03:49 | 54326.3981 | 54326 | [7 empty] | 0 | 0 | 5.33 | 0 | 0
TS Fleet 5 | GG\18\013\X2 | GG | 18 | 13 | X2 | 1 Prestrip - Thick | 46.991 | 0 | 46.991 | 2023-03-25 06:39 | 2023-03-30 17:49 | 257109.0379 | 257109 | [7 empty] | 0 | 0 | 16.26 | 0 | 0
TS6060#1 | GG\17\006\X1 | GG | 17 | 6 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2023-03-25 06:50 | 2023-03-25 13:06 | 8494.0325 | [6 empty] | 8494 | 6298 | 0.62 | 0 | 0 | 10.75 | 5345
TS6060#1 | GG\16\006\B | GG | 16 | 6 | B | 8 Coal Mining | 5.7 | 0 | 5.7 | 2023-03-25 13:06 | 2023-03-25 15:10 | 2798.6602 | [6 empty] | 2799 | 2053 | 0.21 | 0 | 0 | 10.07 | 5444
TS6060#1 | RS\28\005\B | RS | 28 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-03-25 15:10 | 2023-03-26 16:09 | 25779.0109 | 25779 | [7 empty] | 0 | 0 | 2.59 | 8.57 | 5632.94
TS5500Shv | GG\17\006\X1 | GG | 17 | 6 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2023-03-25 18:21 | 2023-03-26 00:38 | 7653.0392 | [6 empty] | 7653 | 5675 | 0.56 | 0 | 0 | 10.75 | 5345
TS5500Shv | GG\16\006\B | GG | 16 | 6 | B | 8 Coal Mining | 94.3 | 0 | 94.3 | 2023-03-26 00:38 | 2023-03-27 14:24 | 46059.1491 | [6 empty] | 46059 | 33781 | 3.38 | 0 | 0 | 10.07 | 5444
PH4100XPC#1 | GG\17\005\B | GG | 17 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-03-26 03:49 | 2023-03-26 11:30 | 16632.9878 | 16633 | [7 empty] | 0 | 0 | 1.66 | 10.03 | 5444.05
DRE1 | RS\24\005\D | RS | 24 | 5 | D | 6 DL | 100 | 100 | 100 | 2023-03-26 05:27 | 2023-03-30 04:53 | 333351.6534 |  |  |  | 17139 | 333352 | 268509 |  |  | 0 | 28.57 | 0 | 6.3 | 5866.02
PH4100XPC#1 | GG\17\006\X2 | GG | 17 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2023-03-26 11:30 | 2023-03-28 08:25 | 97316.529 | 97317 | [7 empty] | 0 | 0 | 9.61 | 0 | 0
TS6060#1 | GG\16\005\B | GG | 16 | 5 | B | 8 Coal Mining | 77.2 | 0 | 77.2 | 2023-03-26 16:09 | 2023-03-27 19:54 | 37547.6026 | [6 empty] | 37548 | 27491 | 2.76 | 0 | 0 | 10.57 | 5400
TS5500Exc | RS\27\006\A | RS | 27 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-03-27 07:01 | 2023-03-28 04:44 | 27354.1338 | [6 empty] | 27354 | 18569 | 1.68 | 0 | 0 | 19.22 | 4772
TS5500Shv | GG\16\005\B | GG | 16 | 5 | B | 8 Coal Mining | 22.8 | 0 | 22.8 | 2023-03-27 14:24 | 2023-03-27 23:29 | 11072.1278 | [6 empty] | 11072 | 8107 | 0.81 | 0 | 0 | 10.57 | 5400
PH4100A | RS\30\003\X | RS | 30 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-03-27 19:05 | 2023-04-01 12:07 | 190452.5127 | 190453 | [7 empty] | 0 | 0 | 40.16 | 12.21 | 5232.14
TS6060#1 | RS\31\004\X | RS | 31 | 4 | X | 1 Prestrip - Thick | 25.269 | 25.269 | 25.269 | 2023-03-27 19:54 | 2023-04-01 13:30 | 114448.6355 | 114449 | [7 empty] | 0 | 0 | 11.6 | 12.17 | 5243.51
TS5500Shv | RS\29\003\X | RS | 29 | 3 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-03-27 23:29 | 2023-03-28 03:26 | 4829.6995 | [6 empty] | 4830 | 3388 | 0.59 | 0 | 0 | 12.22 | 5225
TS5500Shv | RS\28\005\B | RS | 28 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-03-28 03:26 | 2023-03-29 15:15 | 43662.6229 | [6 empty] | 43663 | 31413 | 3.16 | 0 | 0 | 8.57 | 5633
TS5500Exc | RS\28\006\X | RS | 28 | 6 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-03-28 04:44 | 2023-03-28 22:15 | 22067.2626 | [6 empty] | 22067 | 15402 | 1.24 | 0 | 0 | 13.02 | 5171
PH4100XPC#1 | GG\17\006\B | GG | 17 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-03-28 08:25 | 2023-03-29 04:46 | 44103.4648 | 44103 | [7 empty] | 0 | 0 | 4.4 | 9.86 | 5463.19
TS5500Exc | RS\29\003\X | RS | 29 | 3 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-03-28 22:15 | 2023-03-29 02:13 | 4988.9204 | [6 empty] | 4989 | 3500 | 0.61 | 0 | 0 | 12.22 | 5225
TS5500Exc | RS\28\004\B | RS | 28 | 4 | B | 8 Coal Mining | 82.3 | 0 | 82.3 | 2023-03-29 02:13 | 2023-03-30 04:07 | 32628.4871 | [6 empty] | 32628 | 23476 | 2.35 | 0 | 0 | 8.71 | 5618
PH4100XPC#1 | GG\17\007\X1 | GG | 17 | 7 | X1 | 1 Prestrip - Thick | 100 | 53.1488 | 53.1488 | 2023-03-29 04:46 | 2023-04-04 18:04 | 336079.4562 | 336079 | [7 empty] | 0 | 0 | 32.98 | 11.24 | 5350.81
TS5500Shv | RS\24\003\D | RS | 24 | 3 | D | 8 Coal Mining | 98.8 | 0 | 98.8 | 2023-03-29 15:15 | 2023-03-31 21:28 | 66105.7033 | [6 empty] | 66106 | 48467 | 4.45 | 0 | 0 | 5.78 | 5913
TS5500Exc | RS\24\003\D | RS | 24 | 3 | D | 8 Coal Mining | 1.2 | 0 | 1.2 | 2023-03-30 04:07 | 2023-03-30 04:44 | 780.8427 | [6 empty] | 781 | 572 | 0.05 | 0 | 0 | 5.78 | 5913
TS5500Exc | RS\24\004\D | RS | 24 | 4 | D | 8 Coal Mining | 86.6 | 0 | 86.6 | 2023-03-30 04:44 | 2023-03-31 21:49 | 51738.2034 | [6 empty] | 51738 | 37899 | 3.79 | 0 | 0 | 6.11 | 5884
DRE1 | RS\24\006\D | RS | 24 | 6 | D | 6 DL | 100 | 100 | 100 | 2023-03-30 04:53 | 2023-04-03 19:01 | 384719.7953 |  |  |  | 14092 | 384720 | 217330 |  |  | 0 | 27.95 | 0 | 6.36 | 5859.52
DRE2 | GG\15\011\D | GG | 15 | 11 | D | 6 DL | 100 | 100 | 100 | 2023-03-30 11:14 | 2023-04-05 17:26 | 505209.7766 |  |  |  | 9166 | 505210 | 219982 |  |  | 0 | 22.9 | 0 | 6.27 | 5836.12
TS Fleet 5 | GG\18\018\X2 | GG | 18 | 18 | X2 | 1 Prestrip - Thick | 47.0777 | 0 | 47.0777 | 2023-03-30 17:49 | 2023-04-02 08:48 | 123427.8021 | 123428 | [7 empty] | 0 | 0 | 12.46 | 0 | 0
TS5500Shv | GG\15\012\D | GG | 15 | 12 | D | 8 Coal Mining | 91.8 | 0 | 91.8 | 2023-03-31 21:28 | 2023-04-02 20:36 | 57491.7746 | [6 empty] | 57492 | 42947 | 4.29 | 0 | 0 | 6.63 | 5805
TS5500Exc | MW\46\007\A | MW | 46 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-03-31 21:49 | 2023-04-13 13:48 | 269293.9118 | 269294 | [7 empty] | 0 | 0 | 28.97 | 13.37 | 5234.98
PH4100A | RS\29\004\X | RS | 29 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-04-01 12:07 | 2023-04-12 19:09 | 457523.6175 | 457524 | [7 empty] | 0 | 0 | 46.41 | 12.28 | 5224.58
TS6060#1 | RS\27\006\B | RS | 27 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-04-01 13:30 | 2023-04-02 22:16 | 33824.8795 | 33825 | [7 empty] | 0 | 0 | 3.07 | 8.83 | 5614.17
TS Fleet 5 | GG\18\019\X2 | GG | 18 | 19 | X2 | 1 Prestrip - Thick | 46.8614 | 0 | 46.8614 | 2023-04-02 08:48 | 2023-04-04 10:25 | 97264.3237 | 97264 | [7 empty] | 0 | 0 | 10.22 | 0 | 0
TS5500Shv | RS\30\003\X | RS | 30 | 3 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-04-02 20:36 | 2023-04-03 04:34 | 9701.1823 | [6 empty] | 9701 | 6806 | 1.19 | 0 | 0 | 12.21 | 5232
TS6060#1 | RS\28\006\A | RS | 28 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-04-02 22:16 | 2023-04-10 09:41 | 185112.4507 | 185112 | [7 empty] | 0 | 0 | 16.68 | 18.9 | 4799.93
TS5500Shv | RS\27\006\B | RS | 27 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-04-03 04:34 | 2023-04-03 20:39 | 19616.5111 | [6 empty] | 19617 | 14085 | 1.28 | 0 | 0 | 8.83 | 5614
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2023-04-03 19:01 | 2023-04-05 19:01
TS5500Shv | RS\24\004\D | RS | 24 | 4 | D | 8 Coal Mining | 13.4 | 0 | 13.4 | 2023-04-03 20:39 | 2023-04-04 03:13 | 8006.2339 | [6 empty] | 8006 | 5865 | 0.59 | 0 | 0 | 6.11 | 5884
TS5500Shv | RS\24\005\D | RS | 24 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-04-04 03:13 | 2023-04-06 02:15 | 57355.0676 | [6 empty] | 57355 | 41940 | 4.19 | 0 | 0 | 6.3 | 5866
TS Fleet 5 | GG\18\020\B | GG | 18 | 20 | B | 1 Prestrip - Thick | 45.3933 | 45.3933 | 45.3933 | 2023-04-04 10:25 | 2023-04-08 01:24 | 170491.536 | 170492 | [7 empty] | 0 | 0 | 17.1 | 14.96 | 5150.81
PH4100XPC#1 | GG\17\008\X1 | GG | 17 | 8 | X1 | 1 Prestrip - Thick | 100 | 50.3707 | 50.3707 | 2023-04-04 18:04 | 2023-04-10 15:48 | 301806.8506 | 301807 | [7 empty] | 0 | 0 | 29.39 | 11.73 | 5343.8
DRE2 | GG\15\010\D | GG | 15 | 10 | D | 6 DL | 100 | 100 | 100 | 2023-04-05 17:26 | 2023-04-11 11:32 | 464561.573 |  |  |  | 10816 | 464562 | 205510 |  |  | 0 | 21.64 | 0 | 6.06 | 5854.53
DRE1 | MW\46\002\D | MW | 46 | 2 | D | 6 DL | 100 | 0 | 100 | 2023-04-05 19:01 | 2023-04-08 02:22 | 193336.2521 |  |  |  | 10282 | 193336 | 88979 |  |  | 0 | 35 | 0 | 6.76 | 5813.71
TS5500Shv | GG\17\007\X1 | GG | 17 | 7 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-04-06 02:15 | 2023-04-06 15:30 | 16155.5567 | [6 empty] | 16156 | 11912 | 1.19 | 0 | 0 | 11.24 | 5351
TS5500Shv | GG\15\011\D | GG | 15 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-04-06 15:30 | 2023-04-08 18:50 | 62604.6423 | [6 empty] | 62605 | 46877 | 4.69 | 0 | 0 | 6.27 | 5836
TS Fleet 5 | GG\17\007\X2 | GG | 17 | 7 | X2 | 1 Prestrip - Thick | 46.5068 | 0 | 46.5068 | 2023-04-08 01:24 | 2023-04-09 00:04 | 44432.5024 | 44433 | [7 empty] | 0 | 0 | 4.44 | 0 | 0
DRE1 | MW\46\003\D | MW | 46 | 3 | D | 6 DL | 100 | 0 | 100 | 2023-04-08 02:22 | 2023-04-13 01:41 | 416795.4861 |  |  |  | 29642 | 416795 | 299711 |  |  | 0 | 35 | 0 | 6.84 | 5812.07
TS5500Shv | RS\24\006\D | RS | 24 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2023-04-08 18:50 | 2023-04-10 17:52 | 50410.1849 |  |  | 50410 | [5 empty] | 0 | 0 | 0 | 6.36 | 5859.52
TS Fleet 5 | GG\18\021\B | GG | 18 | 21 | B | 1 Prestrip - Thick | 45.7819 | 45.7819 | 45.7819 | 2023-04-09 00:04 | 2023-04-12 03:47 | 148398.8159 | 148399 | [7 empty] | 0 | 0 | 16.47 | 16.55 | 5056.08
TS6060#1 | RS\29\003\A | RS | 29 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-04-10 09:41 | 2023-04-15 06:30 | 120530.6819 | 120531 | [7 empty] | 0 | 0 | 18.92 | 10.96 | 5420.71
PH4100XPC#1 | GG\17\007\X2 | GG | 17 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.4932 | 2023-04-10 15:48 | 2023-04-11 15:24 | 51107.1936 | 51107 | [7 empty] | 0 | 0 | 5.11 | 0 | 0
TS5500Shv | GG\17\008\X1 | GG | 17 | 8 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2023-04-10 17:52 | 2023-04-11 00:28 | 8059.6444 | [6 empty] | 8060 | 5909 | 0.59 | 0 | 0 | 11.73 | 5344
TS5500Shv | RS\28\006\A | RS | 28 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-04-11 00:28 | 2023-04-12 20:07 | 53223.9941 | [6 empty] | 53224 | 36226 | 3.31 | 0 | 0 | 18.9 | 4800
DRE2 | GG\15\009\D | GG | 15 | 9 | D | 6 DL | 100 | 100 | 100 | 2023-04-11 11:32 | 2023-04-16 23:49 | 444947.5989 |  |  |  | 10360 | 444948 | 196834 |  |  | 0 | 20.72 | 0 | 6.26 | 5835.95
PH4100XPC#1 | GG\17\007\B | GG | 17 | 7 | B | 1 Prestrip - Thick | 100 | 75.26 | 75.26 | 2023-04-11 15:24 | 2023-04-12 10:52 | 42178.1848 | 42178 | [7 empty] | 0 | 0 | 4.23 | 10.33 | 5452.83
TS Fleet 5 | GG\17\007\B | GG | 17 | 7 | B | 1 Prestrip - Thick | 46.5068 | 24.74 | 24.74 | 2023-04-12 03:47 | 2023-04-12 10:52 | 13865.1079 | 13865 | [7 empty] | 0 | 0 | 1.39 | 10.33 | 5452.83
TS Fleet 5 | GG\18\022\B | GG | 18 | 22 | B | 1 Prestrip - Thick | 46.4995 | 46.4995 | 46.4995 | 2023-04-12 10:52 | 2023-04-15 08:19 | 136131.279 | 136131 | [7 empty] | 0 | 0 | 14.63 | 18.46 | 4901.82
PH4100XPC#1 | GG\17\009\X1 | GG | 17 | 9 | X1 | 1 Prestrip - Thick | 100 | 53.3963 | 53.3963 | 2023-04-12 10:52 | 2023-04-17 23:41 | 286644.0294 | 286644 | [7 empty] | 0 | 0 | 29.77 | 12.68 | 5280.41
PH4100A | RS\35\003\X | RS | 35 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-04-12 19:09 | 2023-04-17 18:45 | 200344.8006 | 200345 | [7 empty] | 0 | 0 | 38.09 | 12.09 | 5260.65
TS5500Shv | RS\24\006\D | RS | 24 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-04-12 20:07 | 2023-04-14 18:34 | 56629.9382 | [6 empty] | 56630 | 41399 | 4.13 | 0 | 0 | 6.36 | 5860
DRE1 | MW\46\004\D | MW | 46 | 4 | D | 6 DL | 100 | 0 | 100 | 2023-04-13 01:41 | 2023-04-18 06:48 | 437052.2515 |  |  |  | 31082 | 437052 | 314277 |  |  | 0 | 35 | 0 | 6.79 | 5816.07
TS5500Exc | RS\27\006\B | RS | 27 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-04-13 13:48 | 2023-04-14 05:53 | 20263.2093 | [6 empty] | 20263 | 14549 | 1.33 | 0 | 0 | 8.83 | 5614
TS5500Exc | RS\29\004\X | RS | 29 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-04-14 05:53 | 2023-04-14 18:42 | 16135.1933 | [6 empty] | 16135 | 11314 | 1.13 | 0 | 0 | 12.28 | 5225
TS5500Shv | MW\46\002\D | MW | 46 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2023-04-14 18:34 | 2023-04-15 08:32 | 14982.9371 |  |  | 14983 | [5 empty] | 0 | 0 | 0 | 6.76 | 5813.71
TS5500Exc | MW\46\007\A | MW | 46 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-04-14 18:42 | 2023-04-15 15:20 | 25982.032 | [6 empty] | 25982 | 18818 | 1.98 | 0 | 0 | 13.37 | 5235
TS6060#1 | GG\17\008\X1 | GG | 17 | 8 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2023-04-15 06:30 | 2023-04-15 13:06 | 8945.3196 | [6 empty] | 8945 | 6558 | 0.66 | 0 | 0 | 11.73 | 5344
TS Fleet 5 | GG\18\023\B | GG | 18 | 23 | B | 1 Prestrip - Thick | 45.6585 | 45.6585 | 45.6585 | 2023-04-15 08:19 | 2023-04-19 12:22 | 196109.7656 | 196110 | [7 empty] | 0 | 0 | 15.97 | 0 | 0
TS5500Shv | RS\29\003\A | RS | 29 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-04-15 08:32 | 2023-04-15 21:55 | 16314.1195 | [6 empty] | 16314 | 11639 | 1.66 | 0 | 0 | 10.96 | 5421
TS6060#1 | RS\28\006\B | RS | 28 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-04-15 13:06 | 2023-04-16 21:59 | 33918.9124 | 33919 | [7 empty] | 0 | 0 | 3.12 | 8.83 | 5614.54
TS5500Exc | RS\29\003\A | RS | 29 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-04-15 15:20 | 2023-04-16 04:42 | 16851.9476 | [6 empty] | 16852 | 12022 | 1.71 | 0 | 0 | 10.96 | 5421
TS5500Shv | GG\17\008\X2 | GG | 17 | 8 | X2 | 1 Prestrip - Thick | 49.6031 | 0 | 49.6031 | 2023-04-15 21:55 | 2023-04-17 15:18 | 44364.927 | 44365 | [7 empty] | 0 | 0 | 4.43 | 0 | 0
TS5500Exc | MW\46\003\D | MW | 46 | 3 | D | 8 Coal Mining | 64.1 | 0 | 64.1 | 2023-04-16 04:42 | 2023-04-17 12:23 | 39893.9198 | [6 empty] | 39894 | 29926 | 2.99 | 0 | 0 | 6.84 | 5812
TS6060#1 | GG\15\012\D | GG | 15 | 12 | D | 8 Coal Mining | 8.2 | 0 | 8.2 | 2023-04-16 21:59 | 2023-04-17 01:46 | 5133.3102 | [6 empty] | 5133 | 3835 | 0.38 | 0 | 0 | 6.63 | 5805
DRE2 | GG\15\008\D | GG | 15 | 8 | D | 6 DL | 100 | 100 | 100 | 2023-04-16 23:49 | 2023-04-22 08:16 | 432050.2882 |  |  |  | 10059 | 432050 | 191128 |  |  | 0 | 20.12 | 0 | 6.6 | 5806.84
TS6060#1 | RS\29\004\A | RS | 29 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-04-17 01:46 | 2023-04-24 10:10 | 181994.0348 | 181994 | [7 empty] | 0 | 0 | 18.25 | 12.47 | 5299.77
TS5500Exc | RS\28\006\B | RS | 28 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-04-17 12:23 | 2023-04-18 04:42 | 20552.2215 | [6 empty] | 20552 | 14759 | 1.36 | 0 | 0 | 8.83 | 5615
TS5500Shv | RS\28\006\B | RS | 28 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-04-17 15:18 | 2023-04-18 07:37 | 19896.2996 | [6 empty] | 19896 | 14288 | 1.32 | 0 | 0 | 8.83 | 5615
PH4100A | RS\30\004\X | RS | 30 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-04-17 18:45 | 2023-04-29 02:25 | 457825.9993 | 457826 | [7 empty] | 0 | 0 | 46.46 | 12.23 | 5233.84
PH4100XPC#1 | GG\17\008\X2 | GG | 17 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 50.3969 | 2023-04-17 23:41 | 2023-04-18 20:29 | 45074.965 | 45075 | [7 empty] | 0 | 0 | 4.5 | 0 | 0
TS5500Exc | RS\35\003\X | RS | 35 | 3 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-04-18 04:42 | 2023-04-18 08:31 | 4823.8462 | [6 empty] | 4824 | 3391 | 0.56 | 0 | 0 | 12.09 | 5261
DRE1 | MW\46\005\D | MW | 46 | 5 | D | 6 DL | 100 | 0 | 100 | 2023-04-18 06:48 | 2023-04-21 21:20 | 302263.5807 |  |  |  | 21496 | 302264 | 217353 |  |  | 0 | 35 | 0 | 6.45 | 5845.29
TS5500Shv | RS\35\003\X | RS | 35 | 3 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-04-18 07:37 | 2023-04-18 11:27 | 4669.8936 | [6 empty] | 4670 | 3283 | 0.54 | 0 | 0 | 12.09 | 5261
TS5500Exc | MW\46\007\B | MW | 46 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-04-18 08:31 | 2023-04-20 00:41 | 35512.473 | 35512 | [7 empty] | 0 | 0 | 3.68 | 9.72 | 5501.89
TS5500Shv | MW\46\002\D | MW | 46 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-04-18 11:27 | 2023-04-18 23:29 | 14670.0051 | [6 empty] | 14670 | 11009 | 3.82 | 0 | 0 | 6.76 | 5814
PH4100XPC#1 | GG\17\008\B | GG | 17 | 8 | B | 1 Prestrip - Thick | 100 | 78.6429 | 78.6429 | 2023-04-18 20:29 | 2023-04-19 19:11 | 49169.9465 | 49170 | [7 empty] | 0 | 0 | 4.92 | 10.16 | 5492.78
TS5500Shv | GG\15\010\D | GG | 15 | 10 | D | 8 Coal Mining | 88.9 | 0 | 88.9 | 2023-04-18 23:29 | 2023-04-20 21:20 | 55913.2255 | [6 empty] | 55913 | 41867 | 4.19 | 0 | 0 | 6.06 | 5855
TS Fleet 5 | GG\17\008\B | GG | 17 | 8 | B | 1 Prestrip - Thick | 46.5068 | 21.3571 | 21.3571 | 2023-04-19 12:22 | 2023-04-19 19:11 | 13353.0994 | 13353 | [7 empty] | 0 | 0 | 1.34 | 10.16 | 5492.78
TS Fleet 5 | GG\19\003\X1 | GG | 19 | 3 | X1 | 1 Prestrip - Thick | 46.5617 | 46.5617 | 46.5617 | 2023-04-19 19:11 | 2023-04-30 12:14 | 503824.7574 | 503825 | [7 empty] | 0 | 0 | 51.17 | 10.39 | 5325.34
PH4100XPC#1 | GG\17\010\X2 | GG | 17 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.4761 | 2023-04-19 19:11 | 2023-04-25 20:50 | 328278.4377 | 328278 | [7 empty] | 0 | 0 | 32.97 | 0 | 0
TS5500Exc | MW\46\007\B | MW | 46 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-04-20 00:41 | 2023-04-21 06:58 | 38156.2417 | [6 empty] | 38156 | 28111 | 2.88 | 0 | 0 | 9.72 | 5502
TS5500Shv | GG\15\009\D | GG | 15 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-04-20 21:20 | 2023-04-22 23:56 | 61703.6107 | [6 empty] | 61704 | 46129 | 4.61 | 0 | 0 | 6.26 | 5836
TS5500Exc | MW\46\004\D | MW | 46 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-04-21 06:58 | 2023-04-23 07:43 | 61402.5613 | [6 empty] | 61403 | 46095 | 4.62 | 0 | 0 | 6.79 | 5816
DRE1 | MW\46\006\D | MW | 46 | 6 | D | 6 DL | 100 | 0 | 100 | 2023-04-21 21:20 | 2023-04-25 12:24 | 304133.1935 |  |  |  | 21629 | 304133 | 218697 |  |  | 0 | 35 | 0 | 5.91 | 5893.28
DRE2 | GG\15\007\D | GG | 15 | 7 | D | 6 DL | 100 | 100 | 100 | 2023-04-22 08:16 | 2023-04-27 15:32 | 428107.9644 |  |  |  | 7972 | 428108 | 191333 |  |  | 0 | 19.92 | 0 | 6.56 | 5809.25
TS5500Shv | MW\46\003\D | MW | 46 | 3 | D | 8 Coal Mining | 35.9 | 0 | 35.9 | 2023-04-22 23:56 | 2023-04-23 18:16 | 22343.6528 | [6 empty] | 22344 | 16761 | 1.68 | 0 | 0 | 6.84 | 5812
TS5500Exc | MW\46\008\A | MW | 46 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-04-23 07:43 | 2023-05-08 22:45 | 332243.0974 | 332243 | [7 empty] | 0 | 0 | 32.66 | 12.76 | 5287.33
TS5500Shv | GG\15\008\D | GG | 15 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-04-23 18:16 | 2023-04-25 20:51 | 61696.63 | [6 empty] | 61697 | 46014 | 4.6 | 0 | 0 | 6.6 | 5807
TS6060#1 | GG\17\009\X1 | GG | 17 | 9 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-04-24 10:10 | 2023-04-24 23:02 | 17419.4776 | [6 empty] | 17419 | 12665 | 1.27 | 0 | 0 | 12.68 | 5280
TS6060#1 | RS\29\003\B | RS | 29 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-04-24 23:02 | 2023-04-25 17:54 | 19468.9926 | 19469 | [7 empty] | 0 | 0 | 2.7 | 8.71 | 5614.8
DRE1 | MW\46\007\D | MW | 46 | 7 | D | 6 DL | 100 | 100 | 100 | 2023-04-25 12:24 | 2023-04-29 15:20 | 345598.2651 |  |  |  | 17769 | 345598 | 278374 |  |  | 0 | 29.61 | 0 | 5.56 | 5924.78
TS6060#1 | GG\15\010\D | GG | 15 | 10 | D | 8 Coal Mining | 11.1 | 0 | 11.1 | 2023-04-25 17:54 | 2023-04-25 23:05 | 7006.8667 | [6 empty] | 7007 | 5247 | 0.52 | 0 | 0 | 6.06 | 5855
PH4100XPC#1 | GG\17\009\X2 | GG | 17 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2023-04-25 20:50 | 2023-04-27 11:45 | 84320.564 | 84321 | [7 empty] | 0 | 0 | 8.43 | 0 | 0
TS5500Shv | RS\29\003\B | RS | 29 | 3 | B | 8 Coal Mining | 47.2 | 0 | 47.2 | 2023-04-25 20:51 | 2023-04-26 08:19 | 13969.2495 | [6 empty] | 13969 | 10073 | 1.37 | 0 | 0 | 8.71 | 5615
TS6060#1 | RS\30\003\A | RS | 30 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-04-25 23:05 | 2023-04-30 18:17 | 118871.11 | 118871 | [7 empty] | 0 | 0 | 18.83 | 10.68 | 5442.91
TS5500Shv | RS\29\004\A | RS | 29 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-04-26 08:19 | 2023-04-27 04:05 | 24109.3351 | [6 empty] | 24109 | 17010 | 1.7 | 0 | 0 | 12.47 | 5300
TS5500Shv | MW\46\005\D | MW | 46 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-04-27 04:05 | 2023-04-29 05:05 | 59748.184 | [6 empty] | 59748 | 45031 | 4.5 | 0 | 0 | 6.45 | 5845
PH4100XPC#1 | GG\17\009\B | GG | 17 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-04-27 11:45 | 2023-04-28 22:40 | 75636.2256 | 75636 | [7 empty] | 0 | 0 | 7.57 | 9.77 | 5534.41
DRE2 | GG\15\006\D | GG | 15 | 6 | D | 6 DL | 100 | 100 | 100 | 2023-04-27 15:32 | 2023-05-02 21:26 | 423494.0623 |  |  |  | 7886 | 423494 | 189271 |  |  | 0 | 19.72 | 0 | 6.58 | 5808.29
PH4100XPC#1 | GG\17\010\B | GG | 17 | 10 | B | 1 Prestrip - Thick | 100 | 95.4386 | 95.4386 | 2023-04-28 22:40 | 2023-04-30 14:20 | 85951.8 | 85952 | [7 empty] | 0 | 0 | 8.57 | 9.49 | 5555.11
PH4100A | RS\29\005\X | RS | 29 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-04-29 02:25 | 2023-05-13 07:21 | 579889.0328 | 579889 | [7 empty] | 0 | 0 | 59.34 | 12.4 | 5223.02
TS5500Shv | MW\46\006\D | MW | 46 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-04-29 05:05 | 2023-05-01 07:39 | 61659.4764 | [6 empty] | 61659 | 46662 | 4.67 | 0 | 0 | 5.91 | 5893
DRE1 | RS\25\003\D | RS | 25 | 3 | D | 6 DL | 100 | 100 | 100 | 2023-04-29 15:20 | 2023-05-04 02:44 | 375158.4869 |  |  |  | 19288 | 375158 | 302184 |  |  | 0 | 29.96 | 0 | 5.66 | 5922.93
TS Fleet 5 | GG\17\010\B | GG | 17 | 10 | B | 1 Prestrip - Thick | 46.5068 | 4.5614 | 4.5614 | 2023-04-30 12:14 | 2023-04-30 14:20 | 4108.024 | 4108 | [7 empty] | 0 | 0 | 0.41 | 9.49 | 5555.11
TS Fleet 5 | GG\19\004\X1 | GG | 19 | 4 | X1 | 1 Prestrip - Thick | 45.882 | 45.882 | 45.882 | 2023-04-30 14:20 | 2023-05-09 04:42 | 404480.5952 | 404481 | [7 empty] | 0 | 0 | 41.66 | 10.31 | 5324.71
PH4100XPC#1 | GG\17\011\X1 | GG | 17 | 11 | X1 | 1 Prestrip - Thick | 100 | 48.102 | 48.102 | 2023-04-30 14:20 | 2023-05-04 05:43 | 191853.5045 | 191854 | [7 empty] | 0 | 0 | 19.95 | 14.93 | 5105.35
TS6060#1 | RS\31\005\X | RS | 31 | 5 | X | 1 Prestrip - Thick | 39.2514 | 39.2514 | 39.2514 | 2023-04-30 18:17 | 2023-05-09 12:32 | 212693.6182 | 212694 | [7 empty] | 0 | 0 | 21.61 | 12.23 | 5247.45
TS5500Shv | GG\15\007\D | GG | 15 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-05-01 07:39 | 2023-05-03 09:57 | 61351.3009 | [6 empty] | 61351 | 45828 | 4.58 | 0 | 0 | 6.56 | 5809
DRE2 | GG\15\005\D | GG | 15 | 5 | D | 6 DL | 100 | 100 | 100 | 2023-05-02 21:26 | 2023-05-08 01:47 | 418300.4655 |  |  |  | 10116 | 418300 | 192206 |  |  | 0 | 20.24 | 0 | 6.58 | 5808.85
TS5500Shv | MW\46\007\D | MW | 46 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-05-03 09:57 | 2023-05-05 14:09 | 63636.3889 | [6 empty] | 63636 | 48277 | 4.83 | 0 | 0 | 5.56 | 5925
DRE1 | RS\25\004\D | RS | 25 | 4 | D | 6 DL | 100 | 100 | 100 | 2023-05-04 02:44 | 2023-05-08 12:48 | 370489.1027 |  |  |  | 21145 | 370489 | 280925 |  |  | 0 | 30.21 | 0 | 5.95 | 5897.51
PH4100XPC#1 | GG\17\012\X1 | GG | 17 | 12 | X1 | 1 Prestrip - Thick | 100 | 52.9288 | 52.9288 | 2023-05-04 05:43 | 2023-05-07 07:40 | 156611.7621 | 156612 | [7 empty] | 0 | 0 | 16.32 | 14.09 | 5172.12
TS5500Shv | GG\15\006\D | GG | 15 | 6 | D | 8 Coal Mining | 62.4 | 0 | 62.4 | 2023-05-05 14:09 | 2023-05-06 21:53 | 38710.4035 | [6 empty] | 38710 | 28962 | 2.9 | 0 | 0 | 6.58 | 5808
TS5500Shv | RS\25\003\D | RS | 25 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-05-06 21:53 | 2023-05-09 04:16 | 66300.556 | [6 empty] | 66301 | 48724 | 4.5 | 0 | 0 | 5.66 | 5923
PH4100XPC#1 | GG\17\013\X2 | GG | 17 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.2564 | 2023-05-07 07:40 | 2023-05-12 07:45 | 257687.3146 | 257687 | [7 empty] | 0 | 0 | 17.85 | 0 | 0
DRE2 | GG\15\004\D | GG | 15 | 4 | D | 6 DL | 100 | 100 | 100 | 2023-05-08 01:47 | 2023-05-10 15:26 | 207371.1632 |  |  |  | 7915 | 207371 | 189958 |  |  | 0 | 19.78 | 0 | 6.49 | 5814.95
DRE1 | RS\25\005\D | RS | 25 | 5 | D | 6 DL | 100 | 100 | 100 | 2023-05-08 12:48 | 2023-05-12 09:33 | 323970.573 |  |  |  | 16657 | 323971 | 260953 |  |  | 0 | 27.77 | 0 | 6.13 | 5881.31
TS5500Exc | RS\30\004\X | RS | 30 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-05-08 22:45 | 2023-05-09 11:23 | 15919.0802 | [6 empty] | 15919 | 11168 | 1.12 | 0 | 0 | 12.23 | 5234
TS5500Shv | GG\15\005\D | GG | 15 | 5 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2023-05-09 04:16 | 2023-05-10 04:19 | 29335.2493 | [6 empty] | 29335 | 21965 | 2.2 | 0 | 0 | 6.58 | 5809
TS Fleet 5 | GG\19\005\X1 | GG | 19 | 5 | X1 | 1 Prestrip - Thick | 46.0161 | 46.0161 | 46.0161 | 2023-05-09 04:42 | 2023-05-17 18:57 | 404253.179 | 404253 | [7 empty] | 0 | 0 | 39.72 | 10.45 | 5319.99
TS5500Exc | RS\29\003\B | RS | 29 | 3 | B | 8 Coal Mining | 52.8 | 0 | 52.8 | 2023-05-09 11:23 | 2023-05-09 23:48 | 15634.3894 | [6 empty] | 15634 | 11274 | 1.53 | 0 | 0 | 8.71 | 5615
TS6060#1 | GG\17\011\X1 | GG | 17 | 11 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-05-09 12:32 | 2023-05-09 21:53 | 12653.7284 | [6 empty] | 12654 | 9064 | 0.87 | 0 | 0 | 14.93 | 5105
TS6060#1 | GG\17\012\X1 | GG | 17 | 12 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-05-09 21:53 | 2023-05-10 08:50 | 14812.1736 | [6 empty] | 14812 | 10661 | 1.1 | 0 | 0 | 14.09 | 5172
TS5500Exc | RS\29\004\A | RS | 29 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-05-09 23:48 | 2023-05-10 19:34 | 24904.1483 | [6 empty] | 24904 | 17571 | 1.76 | 0 | 0 | 12.47 | 5300
TS5500Shv | MW\46\008\A | MW | 46 | 8 | A | 8 Coal Mining | 10.7 | 0 | 10.7 | 2023-05-10 04:19 | 2023-05-10 08:25 | 5003.4865 | [6 empty] | 5003 | 3637 | 0.37 | 0 | 0 | 12.76 | 5287
TS5500Shv | RS\25\004\D | RS | 25 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-05-10 08:25 | 2023-05-11 08:43 | 29626.792 | [6 empty] | 29627 | 21737 | 2.17 | 0 | 0 | 5.95 | 5898
TS6060#1 | GG\15\006\D | GG | 15 | 6 | D | 8 Coal Mining | 37.6 | 0 | 37.6 | 2023-05-10 08:50 | 2023-05-11 02:05 | 23355.0539 | [6 empty] | 23355 | 17474 | 1.75 | 0 | 0 | 6.58 | 5808
DRE2 | GG\15\003\D | GG | 15 | 3 | D | 6 DL | 100 | 100 | 100 | 2023-05-10 15:26 | 2023-05-17 18:07 | 574129.0435 |  |  |  | 9509 | 574129 | 165362 |  |  | 0 | 18.91 | 0 | 6.33 | 5829.54
TS5500Exc | MW\46\008\A | MW | 46 | 8 | A | 8 Coal Mining | 89.3 | 0 | 89.3 | 2023-05-10 19:34 | 2023-05-12 04:33 | 41541.7413 | [6 empty] | 41542 | 30197 | 3.04 | 0 | 0 | 12.76 | 5287
TS6060#1 | GG\15\005\D | GG | 15 | 5 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2023-05-11 02:05 | 2023-05-12 02:09 | 32558.9031 | [6 empty] | 32559 | 24379 | 2.44 | 0 | 0 | 6.58 | 5809
TS5500Shv | GG\15\004\D | GG | 15 | 4 | D | 8 Coal Mining | 13.1 | 0 | 13.1 | 2023-05-11 08:43 | 2023-05-11 15:13 | 7922.6082 | [6 empty] | 7923 | 5937 | 0.59 | 0 | 0 | 6.49 | 5815
TS5500Shv | GG\18\011\X1 | GG | 18 | 11 | X1 | 1 Prestrip - Thick | 3.4473 | 3.4473 | 3.4473 | 2023-05-11 15:13 | 2023-05-12 04:04 | 13697.3898 | 13697 | [7 empty] | 0 | 0 | 1.25 | 14.31 | 5152.96
TS6060#1 | RS\29\004\B | RS | 29 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-05-12 02:09 | 2023-05-13 04:12 | 26887.5807 | 26888 | [7 empty] | 0 | 0 | 2.7 | 8.68 | 5620.75
TS5500Shv | GG\19\023\B | GG | 19 | 23 | B | 1 Prestrip - Thick | 11.057 | 11.057 | 11.057 | 2023-05-12 04:04 | 2023-05-13 21:55 | 44955.8181 | 44956 | [7 empty] | 0 | 0 | 3.96 | 0 | 0
TS5500Exc | RS\25\004\D | RS | 25 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-05-12 04:33 | 2023-05-13 04:51 | 30603.4994 | [6 empty] | 30603 | 22453 | 2.24 | 0 | 0 | 5.95 | 5898
PH4100XPC#1 | GG\17\011\X2 | GG | 17 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2023-05-12 07:45 | 2023-05-13 16:03 | 69979.338 | 69979 | [7 empty] | 0 | 0 | 6.93 | 0 | 0
DRE1 | RS\25\006\D | RS | 25 | 6 | D | 6 DL | 100 | 100 | 100 | 2023-05-12 09:33 | 2023-05-16 19:59 | 371801.5354 |  |  |  | 13617 | 371802 | 210028 |  |  | 0 | 27.96 | 0 | 6.15 | 5877.95
TS6060#1 | GG\15\004\D | GG | 15 | 4 | D | 8 Coal Mining | 86.9 | 0 | 86.9 | 2023-05-13 04:12 | 2023-05-14 19:07 | 52664.7508 | [6 empty] | 52665 | 39464 | 3.95 | 0 | 0 | 6.49 | 5815
TS5500Exc | RS\29\004\B | RS | 29 | 4 | B | 8 Coal Mining | 60.9 | 0 | 60.9 | 2023-05-13 04:51 | 2023-05-14 00:06 | 24260.9957 | [6 empty] | 24261 | 17481 | 1.75 | 0 | 0 | 8.68 | 5621
PH4100A | RS\35\004\X | RS | 35 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-05-13 07:21 | 2023-05-24 02:58 | 435651.3126 | 435651 | [7 empty] | 0 | 0 | 44.01 | 11.93 | 5280.18
PH4100XPC#1 | GG\17\011\B | GG | 17 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-05-13 16:03 | 2023-05-16 00:11 | 121640.0782 | 121640 | [7 empty] | 0 | 0 | 12.06 | 9.41 | 5561.23
TS5500Shv | RS\29\005\X | RS | 29 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-05-13 21:55 | 2023-05-14 15:32 | 21466.016 | [6 empty] | 21466 | 15046 | 1.51 | 0 | 0 | 12.4 | 5223
TS5500Exc | MW\46\008\B | MW | 46 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-05-14 00:06 | 2023-05-15 12:10 | 31891.3741 | 31891 | [7 empty] | 0 | 0 | 3.2 | 9.71 | 5499.46
TS5500Shv | RS\29\004\B | RS | 29 | 4 | B | 8 Coal Mining | 39.1 | 0 | 39.1 | 2023-05-14 15:32 | 2023-05-15 04:18 | 15564.1004 | [6 empty] | 15564 | 11214 | 1.12 | 0 | 0 | 8.68 | 5621
TS6060#1 | RS\29\005\A | RS | 29 | 5 | A | 1 Prestrip - Thick | 92.0516 | 92.0516 | 92.0516 | 2023-05-14 19:07 | 2023-05-20 20:12 | 149699.5244 | 149700 | [7 empty] | 0 | 0 | 14.99 | 16.81 | 4963.43
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 15:41 |  | 1d 15:41 | 2023-05-15 04:18 | 2023-05-16 19:59
TS5500Exc | MW\46\008\B | MW | 46 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-05-15 12:10 | 2023-05-16 18:44 | 38499.7184 | [6 empty] | 38500 | 28402 | 2.84 | 0 | 0 | 9.71 | 5499
PH4100XPC#1 | GG\17\012\X2 | GG | 17 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2023-05-16 00:11 | 2023-05-17 12:01 | 77627.699 | 77628 | [7 empty] | 0 | 0 | 8 | 0 | 0
TS5500Exc | RS\25\005\D | RS | 25 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-05-16 18:44 | 2023-05-18 17:07 | 58421.5033 | [6 empty] | 58422 | 42790 | 4.28 | 0 | 0 | 6.13 | 5881
DRE1 | MW\46\008\D | MW | 46 | 8 | D | 6 DL | 100 | 100 | 100 | 2023-05-16 19:59 | 2023-05-20 20:44 | 337939.094 |  |  |  | 17375 | 337939 | 272205 |  |  | 0 | 28.97 | 0 | 5.34 | 5944.26
TS5500Shv | RS\25\006\D | RS | 25 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2023-05-16 19:59 | 2023-05-18 17:25 | 48699.516 |  |  | 48700 | [5 empty] | 0 | 0 | 0 | 6.15 | 5877.95
PH4100XPC#1 | GG\17\012\B | GG | 17 | 12 | B | 1 Prestrip - Thick | 100 | 57.7681 | 57.7681 | 2023-05-17 12:01 | 2023-05-19 00:09 | 78271.7916 | 78272 | [7 empty] | 0 | 0 | 7.81 | 9.84 | 5525.5
DRE2 | GG\16\013\B | GG | 16 | 13 | B | 6 DL | 100 | 0 | 100 | 2023-05-17 18:07 | 2023-05-20 06:22 | 202675.3179 |  |  |  |  | 202675 | 168896 |  |  | 0 | 15.7 | 0 | 10.54 | 5468.74
TS Fleet 5 | GG\17\012\B | GG | 17 | 12 | B | 1 Prestrip - Thick | 46.5068 | 42.2319 | 42.2319 | 2023-05-17 18:57 | 2023-05-19 00:09 | 57221.2818 | 57221 | [7 empty] | 0 | 0 | 5.71 | 9.84 | 5525.5
TS5500Exc | MW\46\009\A | MW | 46 | 9 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-05-18 17:07 | 2023-05-31 06:56 | 267577.1566 | 267577 | [7 empty] | 0 | 0 | 43.34 | 12.49 | 5306.49
TS5500Shv | GG\15\003\D | GG | 15 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2023-05-18 17:25 | 2023-05-21 04:02 | 62849.2656 |  |  | 62849 | [5 empty] | 0 | 0 | 0 | 6.33 | 5829.54
TS Fleet 5 | GG\17\013\B | GG | 17 | 13 | B | 1 Prestrip - Thick | 46.5068 | 46.5068 | 46.5068 | 2023-05-19 00:09 | 2023-05-20 21:25 | 88736.2225 | 88736 | [7 empty] | 0 | 0 | 7.23 | 10.67 | 5457.61
PH4100XPC#1 | GG\17\013\B | GG | 17 | 13 | B | 1 Prestrip - Thick | 100 | 53.4932 | 53.4932 | 2023-05-19 00:09 | 2023-05-20 23:16 | 102066.2592 | 102066 | [7 empty] | 0 | 0 | 8.32 | 10.67 | 5457.61
DRE2 | GG\16\018\B | GG | 16 | 18 | B | 6 DL | 100 | 0 | 100 | 2023-05-20 06:22 | 2023-05-22 15:25 | 191870.5734 |  |  |  |  | 191871 | 159892 |  |  | 0 | 15.93 | 0 | 10.8 | 5451.23
TS6060#1 | GG\16\013\B | GG | 16 | 13 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-05-20 20:12 | 2023-05-22 09:44 | 50796.5685 | [6 empty] | 50797 | 37173 | 3.52 | 0 | 0 | 10.54 | 5469
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 4d 00:00 |  | 4d 00:00 | 2023-05-20 20:44 | 2023-05-24 20:44
TS Fleet 5 | GG\19\006\X1 | GG | 19 | 6 | X1 | 1 Prestrip - Thick | 46.7803 | 46.7803 | 46.7803 | 2023-05-20 21:25 | 2023-05-28 11:02 | 355950.7264 | 355951 | [7 empty] | 0 | 0 | 34.89 | 10.9 | 5323.01
PH4100XPC#1 | GG\17\018\X2 | GG | 17 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.0475 | 2023-05-20 23:16 | 2023-05-23 17:14 | 140379.3973 | 140379 | [7 empty] | 0 | 0 | 14.43 | 0 | 0
TS5500Shv | GG\15\003\D | GG | 15 | 3 | D | 8 Coal Mining | 48.7 | 0 | 48.7 | 2023-05-21 04:02 | 2023-05-22 10:18 | 36908.843 | [6 empty] | 36909 | 27657 | 2.22 | 0 | 0 | 6.33 | 5830
TS6060#1 | GG\15\003\D | GG | 15 | 3 | D | 8 Coal Mining | 51.3 | 0 | 51.3 | 2023-05-22 09:44 | 2023-05-23 14:26 | 38827.7446 | [6 empty] | 38828 | 29095 | 2.34 | 0 | 0 | 6.33 | 5830
TS5500Shv | RS\25\006\D | RS | 25 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-05-22 10:18 | 2023-05-24 06:36 | 54004.4672 | [6 empty] | 54004 | 39575 | 4.09 | 0 | 0 | 6.15 | 5878
DRE2 | GG\16\019\B | GG | 16 | 19 | B | 6 DL | 100 | 0 | 100 | 2023-05-22 15:25 | 2023-05-25 05:46 | 209736.7384 |  |  |  |  | 209737 | 174781 |  |  | 0 | 17.4 | 0 | 11.72 | 5390.77
TS6060#1 | GG\16\018\B | GG | 16 | 18 | B | 8 Coal Mining | 62.5 | 0 | 62.5 | 2023-05-23 14:26 | 2023-05-24 14:00 | 31911.6987 | [6 empty] | 31912 | 23307 | 2.33 | 0 | 0 | 10.8 | 5451
PH4100XPC#1 | GG\17\018\B | GG | 17 | 18 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-05-23 17:14 | 2023-05-26 11:06 | 142726.1771 | 142726 | [7 empty] | 0 | 0 | 14.22 | 10.97 | 5437.77
PH4100A | RS\29\005\A | RS | 29 | 5 | A | 1 Prestrip - Thick | 100 | 7.9484 | 7.9484 | 2023-05-24 02:58 | 2023-05-24 10:24 | 12926.0584 | 12926 | [7 empty] | 0 | 0 | 1.29 | 16.81 | 4963.43
TS5500Shv | RS\35\004\X | RS | 35 | 4 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-05-24 06:36 | 2023-05-24 13:12 | 8055.2135 | [6 empty] | 8055 | 5673 | 0.57 | 0 | 0 | 11.93 | 5280
PH4100A | RS\30\005\X | RS | 30 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-05-24 10:24 | 2023-06-07 04:08 | 559375.481 | 559375 | [7 empty] | 0 | 0 | 56.95 | 12.31 | 5235.06
TS5500Shv | GG\16\018\B | GG | 16 | 18 | B | 8 Coal Mining | 37.5 | 0 | 37.5 | 2023-05-24 13:12 | 2023-05-25 04:53 | 19123.6304 | [6 empty] | 19124 | 13967 | 1.4 | 0 | 0 | 10.8 | 5451
TS6060#1 | RS\30\004\A | RS | 30 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-05-24 14:00 | 2023-05-31 22:20 | 181941.3357 | 181941 | [7 empty] | 0 | 0 | 18.22 | 12.04 | 5334.64
DRE1 | RS\26\003\D | RS | 26 | 3 | D | 6 DL | 100 | 100 | 100 | 2023-05-24 20:44 | 2023-05-29 05:48 | 367036.9914 |  |  |  | 18871 | 367037 | 295642 |  |  | 0 | 29.5 | 0 | 5.54 | 5933.81
TS5500Shv | MW\46\008\D | MW | 46 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-05-25 04:53 | 2023-05-27 08:02 | 62370.6614 | [6 empty] | 62371 | 47430 | 4.74 | 0 | 0 | 5.34 | 5944
DRE2 | GG\16\020\B | GG | 16 | 20 | B | 6 DL | 100 | 0 | 100 | 2023-05-25 05:46 | 2023-05-28 07:41 | 248629.2946 |  |  |  |  | 248629 | 207191 |  |  | 0 | 19.81 | 0 | 15.24 | 5127.95
PH4100XPC#1 | GG\17\019\X2 | GG | 17 | 19 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.2251 | 2023-05-26 11:06 | 2023-05-28 16:12 | 113795.0479 | 113795 | [7 empty] | 0 | 0 | 11.93 | 0 | 0
TS5500Shv | GG\16\019\B | GG | 16 | 19 | B | 8 Coal Mining | 71.4 | 0 | 71.4 | 2023-05-27 08:02 | 2023-05-28 14:57 | 37692.4377 | [6 empty] | 37692 | 27367 | 2.74 | 0 | 0 | 11.72 | 5391
DRE2 | GG\16\021\B | GG | 16 | 21 | B | 6 DL | 100 | 0 | 100 | 2023-05-28 07:41 | 2023-05-31 10:28 | 251597.2538 |  |  |  |  | 251597 | 193536 |  |  | 0 | 20.43 | 0 | 14.89 | 5184.21
TS Fleet 5 | GG\19\007\X1 | GG | 19 | 7 | X1 | 1 Prestrip - Thick | 46.9228 | 46.9228 | 46.9228 | 2023-05-28 11:02 | 2023-06-04 12:17 | 331729.461 | 331729 | [7 empty] | 0 | 0 | 32.33 | 11.56 | 5315.94
TS5500Shv | GG\16\020\B | GG | 16 | 20 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2023-05-28 14:57 | 2023-05-28 22:02 | 8645.7663 | [6 empty] | 8646 | 6142 | 0.63 | 0 | 0 | 15.24 | 5128
PH4100XPC#1 | GG\17\019\B | GG | 17 | 19 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-05-28 16:12 | 2023-05-31 01:41 | 124553.0079 | 124553 | [7 empty] | 0 | 0 | 12.47 | 11.98 | 5371.78
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 07:46 |  | 0d 07:46 | 2023-05-28 22:02 | 2023-05-29 05:48
DRE1 | RS\26\004\D | RS | 26 | 4 | D | 6 DL | 100 | 100 | 100 | 2023-05-29 05:48 | 2023-06-02 09:52 | 349565.3728 |  |  |  | 17973 | 349565 | 281569 |  |  | 0 | 29.96 | 0 | 5.8 | 5910.77
TS5500Shv | RS\26\003\D | RS | 26 | 3 | D | 8 Coal Mining | 12.6 | 0 | 12.6 | 2023-05-29 05:48 | 2023-05-29 12:36 | 8296.8263 | [6 empty] | 8297 | 6107 | 0.57 | 0 | 0 | 5.54 | 5934
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 21:52 |  | 1d 21:52 | 2023-05-29 12:36 | 2023-05-31 10:28
PH4100XPC#1 | GG\17\020\B | GG | 17 | 20 | B | 1 Prestrip - Thick | 100 | 47.0567 | 47.0567 | 2023-05-31 01:41 | 2023-06-03 01:22 | 162343.8913 | 162344 | [7 empty] | 0 | 0 | 15.71 | 14.96 | 5149.11
TS5500Exc | RS\29\005\A | RS | 29 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-05-31 06:56 | 2023-06-01 20:11 | 46924.1326 | [6 empty] | 46924 | 32350 | 3.24 | 0 | 0 | 16.81 | 4963
DRE2 | GG\16\022\B | GG | 16 | 22 | B | 6 DL | 100 | 0 | 100 | 2023-05-31 10:28 | 2023-06-03 16:09 | 261309.7494 |  |  |  |  | 261310 | 201007 |  |  | 0 | 20.58 | 0 | 16.7 | 5035.36
TS5500Shv | GG\16\021\B | GG | 16 | 21 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-05-31 10:28 | 2023-06-02 06:16 | 53407.5395 | [6 empty] | 53408 | 37873 | 3.81 | 0 | 0 | 14.89 | 5184
TS6060#1 | GG\16\019\B | GG | 16 | 19 | B | 8 Coal Mining | 28.6 | 0 | 28.6 | 2023-05-31 22:20 | 2023-06-01 09:29 | 15076.2225 | [6 empty] | 15076 | 10946 | 1.1 | 0 | 0 | 11.72 | 5391
TS6060#1 | GG\16\020\B | GG | 16 | 20 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2023-06-01 09:29 | 2023-06-01 16:34 | 9595.8505 | [6 empty] | 9596 | 6817 | 0.7 | 0 | 0 | 15.24 | 5128
TS6060#1 | RS\31\006\X | RS | 31 | 6 | X | 1 Prestrip - Thick | 59.4557 | 59.4557 | 59.4557 | 2023-06-01 16:34 | 2023-06-22 00:55 | 495492.9053 | 495493 | [7 empty] | 0 | 0 | 39.37 | 12.61 | 5222.95
TS5500Exc | RS\35\004\X | RS | 35 | 4 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-06-01 20:11 | 2023-06-02 02:47 | 8320.7699 | [6 empty] | 8321 | 5860 | 0.59 | 0 | 0 | 11.93 | 5280
TS5500Exc | MW\46\009\A | MW | 46 | 9 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-06-02 02:47 | 2023-06-02 23:23 | 25935.8541 | [6 empty] | 25936 | 18889 | 3.33 | 0 | 0 | 12.49 | 5306
TS5500Shv | RS\30\004\A | RS | 30 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-06-02 06:16 | 2023-06-03 01:57 | 23991.1096 | [6 empty] | 23991 | 16985 | 1.7 | 0 | 0 | 12.04 | 5335
DRE1 | RS\26\005\D | RS | 26 | 5 | D | 6 DL | 100 | 100 | 100 | 2023-06-02 09:52 | 2023-06-06 03:41 | 313717.1535 |  |  |  | 16129 | 313717 | 252694 |  |  | 0 | 26.89 | 0 | 5.98 | 5894.99
TS5500Exc | RS\30\003\A | RS | 30 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-06-02 23:23 | 2023-06-04 01:18 | 32658.3252 | [6 empty] | 32658 | 23366 | 3.35 | 0 | 0 | 10.68 | 5443
PH4100XPC#1 | GG\17\021\B | GG | 17 | 21 | B | 1 Prestrip - Thick | 100 | 54.1552 | 54.1552 | 2023-06-03 01:22 | 2023-06-06 14:06 | 188536.2742 | 188536 | [7 empty] | 0 | 0 | 20.84 | 15.54 | 5135.76
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 14:13 |  | 0d 14:13 | 2023-06-03 01:57 | 2023-06-03 16:09
DRE2 | GG\16\023\B | GG | 16 | 23 | B | 6 DL | 100 | 0 | 100 | 2023-06-03 16:09 | 2023-06-08 14:13 | 397143.4403 |  |  |  |  | 397143 | 305495 |  |  | 0 | 21.48 | 0 | 0 | 0
TS5500Shv | GG\16\022\B | GG | 16 | 22 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-06-03 16:09 | 2023-06-05 13:56 | 55821.2249 | [6 empty] | 55821 | 39230 | 3.92 | 0 | 0 | 16.7 | 5035
TS5500Exc | RS\26\003\D | RS | 26 | 3 | D | 8 Coal Mining | 87.4 | 0 | 87.4 | 2023-06-04 01:18 | 2023-06-05 22:48 | 57308.889 | [6 empty] | 57309 | 42181 | 3.92 | 0 | 0 | 5.54 | 5934
TS Fleet 5 | GG\19\008\X1 | GG | 19 | 8 | X1 | 1 Prestrip - Thick | 46.9093 | 46.9093 | 46.9093 | 2023-06-04 12:17 | 2023-06-10 23:34 | 304372.136 | 304372 | [7 empty] | 0 | 0 | 30.08 | 12.35 | 5286.12
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 13:45 |  | 0d 13:45 | 2023-06-05 13:56 | 2023-06-06 03:41
TS5500Exc | MW\46\009\B | MW | 46 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-06-05 22:48 | 2023-06-06 18:41 | 17573.5685 | 17574 | [7 empty] | 0 | 0 | 3.14 | 9.49 | 5524.35
DRE1 | RS\26\006\D | RS | 26 | 6 | D | 6 DL | 100 | 100 | 100 | 2023-06-06 03:41 | 2023-06-10 10:45 | 360022.3004 |  |  |  | 13225 | 360022 | 203514 |  |  | 0 | 27.69 | 0 | 5.96 | 5895.04
TS5500Shv | RS\26\005\D | RS | 26 | 5 | D | 8 Coal Mining | 37.9 | 0 | 37.9 | 2023-06-06 03:41 | 2023-06-06 22:17 | 22671.9641 | [6 empty] | 22672 | 16634 | 1.66 | 0 | 0 | 5.98 | 5895
PH4100XPC#1 | GG\17\022\B | GG | 17 | 22 | B | 1 Prestrip - Thick | 100 | 53.6041 | 53.6041 | 2023-06-06 14:06 | 2023-06-09 17:12 | 163406.7523 | 163407 | [7 empty] | 0 | 0 | 17.24 | 17.49 | 4978.05
TS5500Exc | MW\46\009\B | MW | 46 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-06-06 18:41 | 2023-06-07 11:21 | 21002.4807 | [6 empty] | 21002 | 15515 | 2.8 | 0 | 0 | 9.49 | 5524
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 05:51 |  | 0d 05:51 | 2023-06-06 22:17 | 2023-06-07 04:08
PH4100A | RS\29\006\X | RS | 29 | 6 | X | 1 Prestrip - Thick | 100 | 38.6746 | 38.6746 | 2023-06-07 04:08 | 2023-06-15 08:10 | 333882.0537 | 333882 | [7 empty] | 0 | 0 | 26.07 | 12.97 | 5180.95
TS5500Shv | RS\30\005\X | RS | 30 | 5 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-06-07 04:08 | 2023-06-07 11:54 | 9481.6071 | [6 empty] | 9482 | 6653 | 0.66 | 0 | 0 | 12.31 | 5235
TS5500Exc | RS\30\005\X | RS | 30 | 5 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-06-07 11:21 | 2023-06-07 19:07 | 9794.1875 | [6 empty] | 9794 | 6873 | 0.68 | 0 | 0 | 12.31 | 5235
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 22:51 |  | 2d 22:51 | 2023-06-07 11:54 | 2023-06-10 10:45
TS5500Exc | RS\26\004\D | RS | 26 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-06-07 19:07 | 2023-06-09 19:14 | 60591.1378 | [6 empty] | 60591 | 44526 | 4.45 | 0 | 0 | 5.8 | 5911
DRE2 | GG\15\013\D | GG | 15 | 13 | D | 6 DL | 100 | 100 | 100 | 2023-06-08 14:13 | 2023-06-14 07:39 | 462286.4133 |  |  |  | 10763 | 462286 | 204504 |  |  | 0 | 23.94 | 0 | 7.07 | 5767.39
PH4100XPC#1 | GG\17\023\B | GG | 17 | 23 | B | 1 Prestrip - Thick | 100 | 54.3954 | 54.3954 | 2023-06-09 17:12 | 2023-06-14 05:33 | 243429.3927 | 243429 | [7 empty] | 0 | 0 | 18.39 | 0 | 0
TS5500Exc | RS\26\005\D | RS | 26 | 5 | D | 8 Coal Mining | 62.1 | 0 | 62.1 | 2023-06-09 19:14 | 2023-06-11 00:42 | 37121.0084 | [6 empty] | 37121 | 27234 | 2.72 | 0 | 0 | 5.98 | 5895
DRE1 | MW\46\009\D | MW | 46 | 9 | D | 6 DL | 100 | 100 | 100 | 2023-06-10 10:45 | 2023-06-11 20:02 | 116255.7191 |  |  |  | 4232 | 116256 | 65580 |  |  | 0 | 28.53 | 0 | 5.31 | 5945.68
TS5500Shv | RS\26\006\D | RS | 26 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2023-06-10 10:45 | 2023-06-12 07:18 | 47761.4638 |  |  | 47761 | [5 empty] | 0 | 0 | 0 | 5.96 | 5895.04
TS Fleet 5 | GG\19\009\X1 | GG | 19 | 9 | X1 | 1 Prestrip - Thick | 46.2109 | 46.2109 | 46.2109 | 2023-06-10 23:34 | 2023-06-16 17:07 | 269591.3721 | 269591 | [7 empty] | 0 | 0 | 31.01 | 13.61 | 5200.18
TS5500Exc | RS\30\004\A | RS | 30 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-06-11 00:42 | 2023-06-11 20:22 | 24782.0253 | [6 empty] | 24782 | 17545 | 1.76 | 0 | 0 | 12.04 | 5335
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2023-06-11 20:02 | 2023-06-13 20:02
TS5500Exc | MW\47\003\D | MW | 47 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-06-11 20:22 | 2023-06-23 00:09 | 236921.1483 | 236921 | [7 empty] | 0 | 0 | 23.52 | 6.9 | 5802.59
TS5500Shv | MW\46\009\D | MW | 46 | 9 | D | 7 PostStrip | 100 | 0 | 100 | 2023-06-12 07:18 | 2023-06-12 21:08 | 14832.4297 |  |  | 14832 | [5 empty] | 0 | 0 | 0 | 5.31 | 5945.68
TS5500Shv | MW\46\009\D | MW | 46 | 9 | D | 8 Coal Mining | 83.4 | 0 | 83.4 | 2023-06-12 21:08 | 2023-06-13 09:03 | 14522.2006 | [6 empty] | 14522 | 11052 | 3.88 | 0 | 0 | 5.31 | 5946
TS5500Shv | RS\26\006\D | RS | 26 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-06-13 09:03 | 2023-06-15 04:20 | 52789.269 | [6 empty] | 52789 | 38746 | 4.09 | 0 | 0 | 5.96 | 5895
DRE1 | RS\27\003\D | RS | 27 | 3 | D | 6 DL | 100 | 100 | 100 | 2023-06-13 20:02 | 2023-06-18 02:50 | 359132.6606 |  |  |  | 18464 | 359133 | 289276 |  |  | 0 | 29.04 | 0 | 5.42 | 5944.6
PH4100XPC#1 | GG\18\003\X1 | GG | 18 | 3 | X1 | 1 Prestrip - Thick | 100 | 46.5484 | 46.5484 | 2023-06-14 05:33 | 2023-06-25 08:07 | 573632.7145 | 573633 | [7 empty] | 0 | 0 | 46.63 | 10.28 | 5334.03
DRE2 | GG\15\018\D | GG | 15 | 18 | D | 6 DL | 100 | 100 | 100 | 2023-06-14 07:39 | 2023-06-20 03:02 | 468824.0946 |  |  |  | 10916 | 468824 | 207396 |  |  | 0 | 23.81 | 0 | 7.11 | 5764.05
TS5500Shv | GG\15\013\D | GG | 15 | 13 | D | 8 Coal Mining | 88.6 | 0 | 88.6 | 2023-06-15 04:20 | 2023-06-16 21:50 | 50590.5753 | [6 empty] | 50591 | 37702 | 4.23 | 0 | 0 | 7.07 | 5767
PH4100A | RS\35\005\X | RS | 35 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-06-15 08:10 | 2023-06-28 04:48 | 520068.6357 | 520069 | [7 empty] | 0 | 0 | 52.42 | 11.63 | 5315.5
TS Fleet 5 | GG\19\010\X2 | GG | 19 | 10 | X2 | 1 Prestrip - Thick | 45.6961 | 0 | 45.6961 | 2023-06-16 17:07 | 2023-06-23 02:38 | 300883.627 | 300884 | [7 empty] | 0 | 0 | 28.99 | 0 | 0
TS5500Shv | RS\29\006\X | RS | 29 | 6 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-06-16 21:50 | 2023-06-17 06:38 | 10736.0669 | [6 empty] | 10736 | 7499 | 0.61 | 0 | 0 | 12.97 | 5181
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 20:13 |  | 0d 20:13 | 2023-06-17 06:38 | 2023-06-18 02:50
DRE1 | RS\27\004\D | RS | 27 | 4 | D | 6 DL | 100 | 100 | 100 | 2023-06-18 02:50 | 2023-06-22 05:59 | 346302.1658 |  |  |  | 17805 | 346302 | 278941 |  |  | 0 | 29.68 | 0 | 5.67 | 5922.54
TS5500Shv | RS\27\003\D | RS | 27 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-06-18 02:50 | 2023-06-20 08:02 | 64865.6966 | [6 empty] | 64866 | 47855 | 4.48 | 0 | 0 | 5.42 | 5945
DRE2 | GG\15\019\D | GG | 15 | 19 | D | 6 DL | 100 | 100 | 100 | 2023-06-20 03:02 | 2023-06-26 03:40 | 486497.3901 |  |  |  | 11327 | 486497 | 215214 |  |  | 0 | 22.65 | 0 | 6.9 | 5782.37
TS5500Shv | GG\15\018\D | GG | 15 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-06-20 08:02 | 2023-06-22 08:14 | 58773.3567 | [6 empty] | 58773 | 43766 | 4.82 | 0 | 0 | 7.11 | 5764
TS6060#1 | RS\29\005\B | RS | 29 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-06-22 00:55 | 2023-06-23 02:16 | 26161.219 | 26161 | [7 empty] | 0 | 0 | 2.62 | 8.56 | 5634.28
DRE1 | RS\27\005\D | RS | 27 | 5 | D | 6 DL | 100 | 100 | 100 | 2023-06-22 05:59 | 2023-06-25 21:03 | 304132.0458 |  |  |  | 15637 | 304132 | 244974 |  |  | 0 | 26.07 | 0 | 5.84 | 5907.44
TS5500Shv | RS\27\004\D | RS | 27 | 4 | D | 8 Coal Mining | 30.7 | 0 | 30.7 | 2023-06-22 08:14 | 2023-06-22 23:33 | 18671.0651 | [6 empty] | 18671 | 13753 | 1.38 | 0 | 0 | 5.67 | 5923
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 02:43 |  | 0d 02:43 | 2023-06-22 23:33 | 2023-06-23 02:16
TS5500Exc | RS\29\006\X | RS | 29 | 6 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-06-23 00:09 | 2023-06-23 08:57 | 11090.0032 | [6 empty] | 11090 | 7746 | 0.63 | 0 | 0 | 12.97 | 5181
TS6060#1 | RS\30\003\B | RS | 30 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-06-23 02:16 | 2023-06-23 21:11 | 19515.6031 | 19516 | [7 empty] | 0 | 0 | 2.73 | 8.68 | 5616.73
TS5500Shv | RS\29\005\B | RS | 29 | 5 | B | 8 Coal Mining | 30.4 | 0 | 30.4 | 2023-06-23 02:16 | 2023-06-23 13:21 | 13504.4541 | [6 empty] | 13504 | 9724 | 0.98 | 0 | 0 | 8.56 | 5634
TS Fleet 5 | GG\19\011\X1 | GG | 19 | 11 | X1 | 1 Prestrip - Thick | 46.7766 | 46.7766 | 46.7766 | 2023-06-23 02:38 | 2023-06-27 08:57 | 200547.3521 | 200547 | [7 empty] | 0 | 0 | 18 | 14.43 | 5143.24
TS5500Exc | RS\29\005\B | RS | 29 | 5 | B | 8 Coal Mining | 69.6 | 0 | 69.6 | 2023-06-23 08:57 | 2023-06-24 09:31 | 30940.6214 | [6 empty] | 30941 | 22278 | 2.24 | 0 | 0 | 8.56 | 5634
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 18:46 |  | 1d 18:46 | 2023-06-23 13:21 | 2023-06-25 08:07
TS6060#1 | RS\29\006\A | RS | 29 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-06-23 21:11 | 2023-07-01 06:23 | 182836.82 | 182837 | [7 empty] | 0 | 0 | 16.64 | 18.7 | 4818.34
TS5500Exc | RS\30\003\B | RS | 30 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-06-24 09:31 | 2023-06-25 08:59 | 29543.2461 | [6 empty] | 29543 | 21334 | 2.92 | 0 | 0 | 8.68 | 5617
PH4100XPC#1 | GG\18\004\X1 | GG | 18 | 4 | X1 | 1 Prestrip - Thick | 100 | 54.0688 | 54.0688 | 2023-06-25 08:07 | 2023-07-04 06:26 | 475187.8343 | 475188 | [7 empty] | 0 | 0 | 50.5 | 10.22 | 5332.74
TS5500Shv | GG\18\003\X1 | GG | 18 | 3 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2023-06-25 08:07 | 2023-06-25 15:02 | 8443.3875 | [6 empty] | 8443 | 6272 | 0.58 | 0 | 0 | 10.28 | 5334
TS5500Exc | MW\46\009\D | MW | 46 | 9 | D | 8 Coal Mining | 16.6 | 0 | 16.6 | 2023-06-25 08:59 | 2023-06-25 11:16 | 2885.8133 | [6 empty] | 2886 | 2196 | 0.77 | 0 | 0 | 5.31 | 5946
TS5500Exc | RS\27\004\D | RS | 27 | 4 | D | 8 Coal Mining | 69.3 | 0 | 69.3 | 2023-06-25 11:16 | 2023-06-26 20:43 | 42143.378 | [6 empty] | 42143 | 31043 | 3.1 | 0 | 0 | 5.67 | 5923
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 06:00 |  | 0d 06:00 | 2023-06-25 15:02 | 2023-06-25 21:03
DRE1 | MW\47\003\D | MW | 47 | 3 | D | 6 DL | 100 | 0 | 100 | 2023-06-25 21:03 | 2023-07-02 22:48 | 593000.3216 |  |  |  | 32146 | 593000 | 273769 |  |  | 0 | 35 | 0 | 6.9 | 5802.59
TS5500Shv | RS\27\005\D | RS | 27 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-06-25 21:03 | 2023-06-27 23:11 | 61139.2196 | [6 empty] | 61139 | 44930 | 4.49 | 0 | 0 | 5.84 | 5907
DRE2 | GG\15\020\D | GG | 15 | 20 | D | 6 DL | 100 | 100 | 100 | 2023-06-26 03:40 | 2023-07-01 16:33 | 447006.3708 |  |  |  | 10408 | 447006 | 197744 |  |  | 0 | 20.82 | 0 | 6.75 | 5796.03
TS5500Exc | MW\47\004\D | MW | 47 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-06-26 20:43 | 2023-07-01 20:25 | 105872.9513 | 105873 | [7 empty] | 0 | 0 | 11.42 | 6.97 | 5798.17
TS Fleet 5 | GG\19\012\X1 | GG | 19 | 12 | X1 | 1 Prestrip - Thick | 47.0609 | 47.0609 | 47.0609 | 2023-06-27 08:57 | 2023-06-30 23:50 | 170292.4776 | 170292 | [7 empty] | 0 | 0 | 16.8 | 14.17 | 5164.72
TS5500Shv | GG\15\019\D | GG | 15 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-06-27 23:11 | 2023-06-30 04:13 | 64673.4345 | [6 empty] | 64673 | 48236 | 4.82 | 0 | 0 | 6.9 | 5782
PH4100A | RS\30\006\X | RS | 30 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-06-28 04:48 | 2023-07-19 00:44 | 850211.0081 | 850211 | [7 empty] | 0 | 0 | 66.9 | 12.83 | 5198.21
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 02:10 |  | 1d 02:10 | 2023-06-30 04:13 | 2023-07-01 06:23
TS Fleet 5 | GG\19\013\X1 | GG | 19 | 13 | X1 | 1 Prestrip - Thick | 47.369 | 47.369 | 47.369 | 2023-06-30 23:50 | 2023-07-05 20:05 | 227834.46 | 227834 | [7 empty] | 0 | 0 | 13.09 | 14.27 | 5158.03
TS6060#1 | GG\18\003\X1 | GG | 18 | 3 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2023-07-01 06:23 | 2023-07-01 13:19 | 9371.2323 | [6 empty] | 9371 | 6961 | 0.64 | 0 | 0 | 10.28 | 5334
TS5500Shv | RS\29\006\A | RS | 29 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-07-01 06:23 | 2023-07-03 01:47 | 52912.1025 | [6 empty] | 52912 | 36092 | 3.33 | 0 | 0 | 18.7 | 4818
TS6060#1 | RS\30\005\A | RS | 30 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-07-01 13:19 | 2023-07-08 07:14 | 167080.0096 | 167080 | [7 empty] | 0 | 0 | 16.58 | 16 | 5028.71
DRE2 | GG\15\021\D | GG | 15 | 21 | D | 6 DL | 100 | 100 | 100 | 2023-07-01 16:33 | 2023-07-06 21:41 | 420915.4619 |  |  |  | 7838 | 420915 | 188119 |  |  | 0 | 19.6 | 0 | 6.72 | 5797.87
TS5500Exc | RS\35\005\X | RS | 35 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-07-01 20:25 | 2023-07-02 09:22 | 16298.3385 | [6 empty] | 16298 | 11514 | 1.15 | 0 | 0 | 11.63 | 5316
TS5500Exc | MW\47\005\D | MW | 47 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-07-02 09:22 | 2023-07-18 04:58 | 335804.4096 | 335804 | [7 empty] | 0 | 0 | 34.52 | 6.78 | 5816.56
DRE1 | MW\47\004\D | MW | 47 | 4 | D | 6 DL | 100 | 0 | 100 | 2023-07-02 22:48 | 2023-07-07 23:27 | 421397.7125 |  |  |  | 29969 | 421398 | 303020 |  |  | 0 | 35 | 0 | 6.97 | 5798.17
TS5500Shv | GG\15\020\D | GG | 15 | 20 | D | 8 Coal Mining | 47.6 | 0 | 47.6 | 2023-07-03 01:47 | 2023-07-04 03:00 | 30754.8532 | [6 empty] | 30755 | 22938 | 2.29 | 0 | 0 | 6.75 | 5796
TS5500Shv | MW\47\003\D | MW | 47 | 3 | D | 7 PostStrip | 93.6449 | 0 | 93.6449 | 2023-07-04 03:00 | 2023-07-05 23:47 | 48005.6033 |  |  | 48006 | [5 empty] | 0 | 0 | 0 | 6.9 | 5802.59
PH4100XPC#1 | GG\18\003\X2 | GG | 18 | 3 | X2 | 1 Prestrip - Thick | 100 | 0 | 77.6898 | 2023-07-04 06:26 | 2023-07-06 13:35 | 119504.1478 | 119504 | [7 empty] | 0 | 0 | 11.18 | 0 | 0
TS Fleet 5 | GG\18\003\X2 | GG | 18 | 3 | X2 | 1 Prestrip - Thick | 46.5068 | 0 | 22.3102 | 2023-07-05 20:05 | 2023-07-06 13:35 | 34317.9482 | 34318 | [7 empty] | 0 | 0 | 3.21 | 0 | 0
TS5500Shv | GG\18\004\X1 | GG | 18 | 4 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2023-07-05 23:47 | 2023-07-06 06:27 | 8125.4037 | [6 empty] | 8125 | 6056 | 0.59 | 0 | 0 | 10.22 | 5333
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 07:09 |  | 0d 07:09 | 2023-07-06 06:27 | 2023-07-06 13:35
TS Fleet 5 | GG\18\003\B | GG | 18 | 3 | B | 1 Prestrip - Thick | 38.0865 | 38.0865 | 38.0865 | 2023-07-06 13:35 | 2023-07-07 16:16 | 52292.2843 | 52292 | [7 empty] | 0 | 0 | 5.17 | 10 | 5485.2
PH4100XPC#1 | GG\18\003\B | GG | 18 | 3 | B | 1 Prestrip - Thick | 100 | 45.4309 | 45.4309 | 2023-07-06 13:35 | 2023-07-07 18:23 | 62376.0529 | 62376 | [7 empty] | 0 | 0 | 6.16 | 10 | 5485.2
TS5500Shv | GG\18\003\B | GG | 18 | 3 | B | 1 Prestrip - Thick | 16.4827 | 16.4827 | 16.4827 | 2023-07-06 13:35 | 2023-07-07 10:42 | 22630.5429 | 22631 | [7 empty] | 0 | 0 | 2.24 | 10 | 5485.2
DRE2 | GG\15\022\D | GG | 15 | 22 | D | 6 DL | 100 | 100 | 100 | 2023-07-06 21:41 | 2023-07-12 02:19 | 419226.2809 |  |  |  | 7807 | 419226 | 187364 |  |  | 0 | 19.53 | 0 | 6.62 | 5805.3
TS5500Shv | GG\15\021\D | GG | 15 | 21 | D | 8 Coal Mining | 60.7 | 0 | 60.7 | 2023-07-07 10:42 | 2023-07-08 18:38 | 38946.0215 | [6 empty] | 38946 | 29024 | 2.9 | 0 | 0 | 6.72 | 5798
TS Fleet 5 | GG\19\018\X2 | GG | 19 | 18 | X2 | 1 Prestrip - Thick | 47.2639 | 0 | 47.2639 | 2023-07-07 16:16 | 2023-07-10 07:50 | 124596.3641 | 124596 | [7 empty] | 0 | 0 | 12.54 | 0 | 0
PH4100XPC#1 | GG\18\005\X1 | GG | 18 | 5 | X1 | 1 Prestrip - Thick | 100 | 53.8783 | 53.8783 | 2023-07-07 18:23 | 2023-07-16 08:06 | 452676.3785 | 452676 | [7 empty] | 0 | 0 | 52.07 | 10.41 | 5328.42
DRE1 | RS\27\006\D | RS | 27 | 6 | D | 6 DL | 100 | 100 | 100 | 2023-07-07 23:27 | 2023-07-12 01:58 | 344158.0075 |  |  |  | 12728 | 344158 | 194851 |  |  | 0 | 27.09 | 0 | 5.82 | 5907.8
TS6060#1 | GG\18\004\X1 | GG | 18 | 4 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2023-07-08 07:14 | 2023-07-08 13:54 | 9018.3052 | [6 empty] | 9018 | 6721 | 0.66 | 0 | 0 | 10.22 | 5333
TS6060#1 | RS\29\006\B | RS | 29 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-07-08 13:54 | 2023-07-09 23:11 | 34345.3376 | 34345 | [7 empty] | 0 | 0 | 3.19 | 8.83 | 5613.77
TS5500Shv | GG\18\003\B | GG | 18 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-07-08 18:38 | 2023-07-10 13:40 | 52477.2497 | [6 empty] | 52477 | 38568 | 3.97 | 0 | 0 | 10 | 5485
TS6060#1 | GG\15\013\D | GG | 15 | 13 | D | 8 Coal Mining | 11.4 | 0 | 11.4 | 2023-07-09 23:11 | 2023-07-10 04:00 | 6513.0284 | [6 empty] | 6513 | 4854 | 0.54 | 0 | 0 | 7.07 | 5767
TS6060#1 | RS\30\004\B | RS | 30 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-07-10 04:00 | 2023-07-11 06:25 | 27256.7158 | 27257 | [7 empty] | 0 | 0 | 2.73 | 8.67 | 5621.79
TS Fleet 5 | GG\18\004\X2 | GG | 18 | 4 | X2 | 1 Prestrip - Thick | 46.5068 | 0 | 46.5068 | 2023-07-10 07:50 | 2023-07-11 12:23 | 55945.9449 | 55946 | [7 empty] | 0 | 0 | 5.45 | 0 | 0
TS5500Shv | RS\30\005\A | RS | 30 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-07-10 13:40 | 2023-07-12 05:12 | 48202.8887 | [6 empty] | 48203 | 33395 | 3.32 | 0 | 0 | 16 | 5029
TS6060#1 | GG\15\020\D | GG | 15 | 20 | D | 8 Coal Mining | 52.4 | 0 | 52.4 | 2023-07-11 06:25 | 2023-07-12 07:29 | 33914.6777 | [6 empty] | 33915 | 25295 | 2.53 | 0 | 0 | 6.75 | 5796
TS Fleet 5 | GG\19\019\X2 | GG | 19 | 19 | X2 | 1 Prestrip - Thick | 47.0012 | 0 | 47.0012 | 2023-07-11 12:23 | 2023-07-13 12:40 | 94633.7777 | 94634 | [7 empty] | 0 | 0 | 9.96 | 0 | 0
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2023-07-12 01:58 | 2023-07-14 01:58
DRE2 | GG\15\023\D | GG | 15 | 23 | D | 6 DL | 100 | 100 | 100 | 2023-07-12 02:19 | 2023-07-17 18:08 | 456841.3052 |  |  |  | 10637 | 456841 | 202095 |  |  | 0 | 21.3 | 0 | 6.4 | 5824.27
TS5500Shv | RS\30\004\B | RS | 30 | 4 | B | 8 Coal Mining | 65.5 | 0 | 65.5 | 2023-07-12 05:12 | 2023-07-13 02:36 | 26091.2893 | [6 empty] | 26091 | 18813 | 1.89 | 0 | 0 | 8.67 | 5622
TS6060#1 | RS\30\005\B | RS | 30 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-07-12 07:29 | 2023-07-13 10:33 | 27939.3585 | 27939 | [7 empty] | 0 | 0 | 2.78 | 8.61 | 5630.14
TS5500Shv | MW\47\004\D | MW | 47 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-07-13 02:36 | 2023-07-14 21:58 | 52892.9601 | [6 empty] | 52893 | 39668 | 4.33 | 0 | 0 | 6.97 | 5798
TS6060#1 | GG\15\021\D | GG | 15 | 21 | D | 8 Coal Mining | 39.3 | 0 | 39.3 | 2023-07-13 10:33 | 2023-07-14 05:11 | 25208.2161 | [6 empty] | 25208 | 18786 | 1.88 | 0 | 0 | 6.72 | 5798
TS Fleet 5 | GG\19\020\B | GG | 19 | 20 | B | 1 Prestrip - Thick | 45.3582 | 45.3582 | 45.3582 | 2023-07-13 12:40 | 2023-07-16 15:25 | 146507.5484 | 146508 | [7 empty] | 0 | 0 | 15.24 | 15.16 | 5134.48
DRE1 | RS\28\003\D | RS | 28 | 3 | D | 6 DL | 100 | 100 | 100 | 2023-07-14 01:58 | 2023-07-18 06:33 | 351355.5138 |  |  |  | 18065 | 351356 | 283011 |  |  | 0 | 28.59 | 0 | 5.3 | 5954.6
TS6060#1 | GG\15\022\D | GG | 15 | 22 | D | 8 Coal Mining | 84 | 0 | 84 | 2023-07-14 05:11 | 2023-07-15 19:36 | 52001.8607 | [6 empty] | 52002 | 38845 | 3.88 | 0 | 0 | 6.62 | 5805
TS5500Shv | GG\15\022\D | GG | 15 | 22 | D | 8 Coal Mining | 16 | 0 | 16 | 2023-07-14 21:58 | 2023-07-15 06:07 | 9939.4807 | [6 empty] | 9939 | 7425 | 0.74 | 0 | 0 | 6.62 | 5805
TS5500Shv | RS\27\006\D | RS | 27 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2023-07-15 06:07 | 2023-07-17 01:57 | 46979.9806 |  |  | 46980 | [5 empty] | 0 | 0 | 0 | 5.82 | 5907.8
TS6060#1 | RS\33\003\X | RS | 33 | 3 | X | 1 Prestrip - Thick | 28.2862 | 28.2862 | 28.2862 | 2023-07-15 19:36 | 2023-07-17 19:54 | 48644.6679 | 48645 | [7 empty] | 0 | 0 | 10.87 | 12.13 | 5251.47
PH4100XPC#1 | GG\18\004\X2 | GG | 18 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.4932 | 2023-07-16 08:06 | 2023-07-17 13:49 | 64350.1961 | 64350 | [7 empty] | 0 | 0 | 6.27 | 0 | 0
TS Fleet 5 | GG\19\021\B | GG | 19 | 21 | B | 1 Prestrip - Thick | 45.6362 | 45.6362 | 45.6362 | 2023-07-16 15:25 | 2023-07-19 23:23 | 156752.8543 | 156753 | [7 empty] | 0 | 0 | 17.48 | 17.56 | 4972.43
TS5500Shv | GG\18\005\X1 | GG | 18 | 5 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-07-17 01:57 | 2023-07-17 15:26 | 16448.7006 | [6 empty] | 16449 | 12253 | 1.21 | 0 | 0 | 10.41 | 5328
PH4100XPC#1 | GG\18\004\B | GG | 18 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-07-17 13:49 | 2023-07-17 15:00 | 2594.2931 | 2594 | [7 empty] | 0 | 0 | 0.26 | 9.49 | 5503.41
PH4100XPC#1 | GG\18\006\X1 | GG | 18 | 6 | X1 | 1 Prestrip - Thick | 100 | 53.2536 | 53.2536 | 2023-07-17 15:00 | 2023-07-25 04:38 | 389719.8435 | 389720 | [7 empty] | 0 | 0 | 38.54 | 10.81 | 5334.33
TS5500Shv | RS\27\006\D | RS | 27 | 6 | D | 8 Coal Mining | 96.2 | 0 | 96.2 | 2023-07-17 15:26 | 2023-07-19 08:51 | 50490.6602 | [6 empty] | 50491 | 37120 | 3.98 | 0 | 0 | 5.82 | 5908
DRE2 | GG\15\024\D | GG | 15 | 24 | D | 6 DL | 100 | 0 | 100 | 2023-07-17 18:08 | 2023-07-22 01:02 | 346163.9623 |  |  |  | 19020 | 346164 | 150192 |  |  | 0 | 40 | 0 | 6.3 | 5834.04
TS6060#1 | RS\33\004\X | RS | 33 | 4 | X | 1 Prestrip - Thick | 50.1196 | 50.1196 | 50.1196 | 2023-07-17 19:54 | 2023-07-27 00:22 | 221871.4799 | 221871 | [7 empty] | 0 | 0 | 22.41 | 12.07 | 5261.07
TS5500Exc | RS\29\006\B | RS | 29 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-07-18 04:58 | 2023-07-19 13:28 | 40930.7492 | [6 empty] | 40931 | 29377 | 2.73 | 0 | 0 | 8.83 | 5614
DRE1 | MW\47\005\D | MW | 47 | 5 | D | 6 DL | 100 | 0 | 100 | 2023-07-18 06:33 | 2023-07-23 11:00 | 434706.9237 |  |  |  | 30916 | 434707 | 312591 |  |  | 0 | 35 | 0 | 6.78 | 5816.56
PH4100A | RS\31\003\X | RS | 31 | 3 | X | 1 Prestrip - Thick | 100 | 45.6194 | 45.6194 | 2023-07-19 00:44 | 2023-07-21 04:20 | 86772.0909 | 86772 | [7 empty] | 0 | 0 | 18.18 | 12.19 | 5238.53
TS5500Shv | RS\30\006\X | RS | 30 | 6 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-07-19 08:51 | 2023-07-19 17:34 | 10628.091 | [6 empty] | 10628 | 7434 | 0.61 | 0 | 0 | 12.83 | 5198
TS5500Exc | RS\30\006\X | RS | 30 | 6 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-07-19 13:28 | 2023-07-19 22:11 | 10978.4677 | [6 empty] | 10978 | 7679 | 0.63 | 0 | 0 | 12.83 | 5198
TS5500Shv | GG\15\023\D | GG | 15 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-07-19 17:34 | 2023-07-21 19:48 | 61263.1601 | [6 empty] | 61263 | 46055 | 4.61 | 0 | 0 | 6.4 | 5824
TS5500Exc | RS\30\004\B | RS | 30 | 4 | B | 8 Coal Mining | 34.5 | 0 | 34.5 | 2023-07-19 22:11 | 2023-07-20 09:07 | 13772.8132 | [6 empty] | 13773 | 9931 | 1 | 0 | 0 | 8.67 | 5622
TS Fleet 5 | GG\18\005\X2 | GG | 18 | 5 | X2 | 1 Prestrip - Thick | 46.5068 | 0 | 46.5068 | 2023-07-19 23:23 | 2023-07-20 22:58 | 46226.0986 | 46226 | [7 empty] | 0 | 0 | 4.54 | 0 | 0
TS5500Exc | RS\30\005\B | RS | 30 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-07-20 09:07 | 2023-07-21 20:00 | 43948.7424 | [6 empty] | 43949 | 31640 | 3.15 | 0 | 0 | 8.61 | 5630
TS Fleet 5 | GG\19\022\B | GG | 19 | 22 | B | 1 Prestrip - Thick | 46.5591 | 46.5591 | 46.5591 | 2023-07-20 22:58 | 2023-07-23 15:02 | 125558.0216 | 125558 | [7 empty] | 0 | 0 | 13.55 | 19.34 | 4827.88
PH4100A | RS\35\006\X | RS | 35 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-07-21 04:20 | 2023-08-08 03:25 | 728057.933 | 728058 | [7 empty] | 0 | 0 | 59.65 | 11.38 | 5348.43
TS5500Shv | RS\31\003\X | RS | 31 | 3 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-07-21 19:48 | 2023-07-21 23:35 | 4621.2096 | [6 empty] | 4621 | 3243 | 0.57 | 0 | 0 | 12.19 | 5239
TS5500Exc | RS\31\003\X | RS | 31 | 3 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-07-21 20:00 | 2023-07-21 23:48 | 4773.5572 | [6 empty] | 4774 | 3350 | 0.59 | 0 | 0 | 12.19 | 5239
TS5500Shv | RS\28\003\D | RS | 28 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-07-21 23:35 | 2023-07-24 04:12 | 64150.5628 | [6 empty] | 64151 | 47439 | 4.47 | 0 | 0 | 5.3 | 5955
TS5500Exc | MW\47\003\D | MW | 47 | 3 | D | 7 PostStrip | 6.3551 | 0 | 6.3551 | 2023-07-21 23:48 | 2023-07-22 03:29 | 3257.8288 |  |  | 3258 | [5 empty] | 0 | 0 | 0 | 6.9 | 5802.59
DRE2 | GG\17\012\B | GG | 17 | 12 | B | 6 DL | 100 | 0 | 100 | 2023-07-22 01:02 | 2023-07-24 10:47 | 194224.5 |  |  |  |  | 194225 | 161854 |  |  | 0 | 16.15 | 0 | 9.84 | 5525.5
TS5500Exc | MW\47\003\D | MW | 47 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-07-22 03:29 | 2023-07-23 02:06 | 28491.3353 | [6 empty] | 28491 | 21348 | 2.07 | 0 | 0 | 6.9 | 5803
TS5500Exc | RS\27\006\D | RS | 27 | 6 | D | 8 Coal Mining | 3.8 | 0 | 3.8 | 2023-07-23 02:06 | 2023-07-23 03:42 | 2011.3275 | [6 empty] | 2011 | 1479 | 0.16 | 0 | 0 | 5.82 | 5908
TS5500Exc | MW\47\006\D | MW | 47 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-07-23 03:42 | 2023-08-11 21:33 | 419333.8504 | 419334 | [7 empty] | 0 | 0 | 42.98 | 6.17 | 5870.87
DRE1 | RS\28\004\D | RS | 28 | 4 | D | 6 DL | 100 | 100 | 100 | 2023-07-23 11:00 | 2023-07-27 13:05 | 342646.2418 |  |  |  | 17617 | 342646 | 275996 |  |  | 0 | 29.36 | 0 | 5.56 | 5932.34
TS Fleet 5 | GG\19\023\B | GG | 19 | 23 | B | 1 Prestrip - Thick | 40.6894 | 40.6894 | 40.6894 | 2023-07-23 15:02 | 2023-07-27 03:26 | 165435.5883 | 165436 | [7 empty] | 0 | 0 | 14.55 | 0 | 0
TS5500Shv | MW\47\003\D | MW | 47 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-07-24 04:12 | 2023-07-25 02:49 | 27582.0374 | [6 empty] | 27582 | 20667 | 2 | 0 | 0 | 6.9 | 5803
DRE2 | GG\17\011\B | GG | 17 | 11 | B | 6 DL | 100 | 0 | 100 | 2023-07-24 10:47 | 2023-07-27 04:40 | 221632.3206 |  |  |  |  | 221632 | 170486 |  |  | 0 | 16.9 | 0 | 9.41 | 5561.23
TS5500Shv | GG\15\024\D | GG | 15 | 24 | D | 7 PostStrip | 65.7654 | 0 | 65.7654 | 2023-07-25 02:49 | 2023-07-25 15:42 | 13804.9405 |  |  | 13805 | [5 empty] | 0 | 0 | 0 | 6.3 | 5834.04
PH4100XPC#1 | GG\18\005\X2 | GG | 18 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.4932 | 2023-07-25 04:38 | 2023-07-26 05:10 | 53170.2254 | 53170 | [7 empty] | 0 | 0 | 5.22 | 0 | 0
TS5500Shv | GG\18\006\X1 | GG | 18 | 6 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2023-07-25 15:42 | 2023-07-25 21:54 | 7571.8556 | [6 empty] | 7572 | 5614 | 0.56 | 0 | 0 | 10.81 | 5334
TS5500Shv | GG\17\012\B | GG | 17 | 12 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-07-25 21:54 | 2023-07-27 13:16 | 47988.8492 | [6 empty] | 47989 | 35248 | 3.52 | 0 | 0 | 9.84 | 5526
PH4100XPC#1 | GG\18\005\B | GG | 18 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-07-26 05:10 | 2023-07-26 17:37 | 26974.6077 | 26975 | [7 empty] | 0 | 0 | 2.69 | 9.57 | 5482.88
PH4100XPC#1 | GG\18\007\X1 | GG | 18 | 7 | X1 | 1 Prestrip - Thick | 100 | 53.1041 | 53.1041 | 2023-07-26 17:37 | 2023-08-02 16:37 | 356164.5315 | 356165 | [7 empty] | 0 | 0 | 34.89 | 11.41 | 5332.29
TS6060#1 | GG\18\006\X1 | GG | 18 | 6 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2023-07-27 00:22 | 2023-07-27 06:35 | 8403.9276 | [6 empty] | 8404 | 6231 | 0.62 | 0 | 0 | 10.81 | 5334
TS Fleet 5 | MW\51\006\D | MW | 51 | 6 | D | 1 Prestrip - Thick | 56.3253 | 56.3253 | 56.3253 | 2023-07-27 03:26 | 2023-07-29 22:26 | 131322.5115 | 131323 | [7 empty] | 0 | 0 | 13.35 | 7.29 | 5773.43
DRE2 | GG\17\010\B | GG | 17 | 10 | B | 6 DL | 100 | 0 | 100 | 2023-07-27 04:40 | 2023-07-29 23:02 | 223252.2384 |  |  |  |  | 223252 | 186044 |  |  | 0 | 18.54 | 0 | 9.49 | 5555.11
TS6060#1 | RS\30\006\A | RS | 30 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-07-27 06:35 | 2023-08-03 13:45 | 180730.3359 | 180730 | [7 empty] | 0 | 0 | 16.6 | 18.4 | 4843.74
DRE1 | RS\28\005\D | RS | 28 | 5 | D | 6 DL | 100 | 100 | 100 | 2023-07-27 13:05 | 2023-07-31 01:46 | 295767.8966 |  |  |  | 15207 | 295768 | 238236 |  |  | 0 | 25.35 | 0 | 5.72 | 5918.83
TS5500Shv | GG\17\011\B | GG | 17 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-07-27 13:16 | 2023-07-29 05:31 | 49092.4344 | [6 empty] | 49092 | 36157 | 3.61 | 0 | 0 | 9.41 | 5561
TS5500Shv | MW\47\005\D | MW | 47 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-07-29 05:31 | 2023-07-31 06:49 | 60114.9691 | [6 empty] | 60115 | 45199 | 4.52 | 0 | 0 | 6.78 | 5817
TS Fleet 5 | GG\18\006\X2 | GG | 18 | 6 | X2 | 1 Prestrip - Thick | 46.5068 | 0 | 46.5068 | 2023-07-29 22:26 | 2023-07-30 21:17 | 44787.5868 | 44788 | [7 empty] | 0 | 0 | 4.45 | 0 | 0
DRE2 | GG\17\009\B | GG | 17 | 9 | B | 6 DL | 100 | 0 | 100 | 2023-07-29 23:02 | 2023-08-01 20:08 | 232457.0992 |  |  |  |  | 232457 | 193714 |  |  | 0 | 19.38 | 0 | 9.77 | 5534.41
TS Fleet 5 | MW\51\007\A | MW | 51 | 7 | A | 1 Prestrip - Thick | 84.8676 | 84.8676 | 84.8676 | 2023-07-30 21:17 | 2023-08-06 16:19 | 319528.5762 | 319529 | [7 empty] | 0 | 0 | 20.12 | 12.02 | 5372.59
DRE1 | RS\28\006\D | RS | 28 | 6 | D | 6 DL | 100 | 100 | 100 | 2023-07-31 01:46 | 2023-08-04 00:25 | 330667.1687 |  |  |  | 12302 | 330667 | 187469 |  |  | 0 | 26.59 | 0 | 5.78 | 5911.79
TS5500Shv | GG\17\010\B | GG | 17 | 10 | B | 8 Coal Mining | 84.3 | 0 | 84.3 | 2023-07-31 06:49 | 2023-08-01 17:20 | 42082.0558 | [6 empty] | 42082 | 30974 | 3.1 | 0 | 0 | 9.49 | 5555
TS5500Shv | RS\28\004\D | RS | 28 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-08-01 17:20 | 2023-08-03 19:23 | 61035.8376 | [6 empty] | 61036 | 44995 | 4.5 | 0 | 0 | 5.56 | 5932
DRE2 | GG\17\008\B | GG | 17 | 8 | B | 6 DL | 100 | 0 | 100 | 2023-08-01 20:08 | 2023-08-04 19:16 | 239255.9093 |  |  |  |  | 239256 | 199380 |  |  | 0 | 19.94 | 0 | 10.16 | 5492.78
PH4100XPC#1 | GG\18\006\X2 | GG | 18 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.4932 | 2023-08-02 16:37 | 2023-08-03 16:23 | 51515.6192 | 51516 | [7 empty] | 0 | 0 | 5.12 | 0 | 0
TS6060#1 | RS\31\003\A | RS | 31 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-08-03 13:45 | 2023-08-08 08:25 | 118323.6458 | 118324 | [7 empty] | 0 | 0 | 18.8 | 10.5 | 5457.11
PH4100XPC#1 | GG\18\006\B | GG | 18 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-08-03 16:23 | 2023-08-04 13:41 | 46137.7064 | 46138 | [7 empty] | 0 | 0 | 4.61 | 9.77 | 5473.51
TS5500Shv | GG\18\007\X1 | GG | 18 | 7 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-08-03 19:23 | 2023-08-04 08:39 | 16179.6923 | [6 empty] | 16180 | 11913 | 1.19 | 0 | 0 | 11.41 | 5332
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2023-08-04 00:25 | 2023-08-06 00:25
TS5500Shv | RS\30\006\A | RS | 30 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-08-04 08:39 | 2023-08-05 05:52 | 25868.4058 | [6 empty] | 25868 | 17685 | 1.65 | 0 | 0 | 18.4 | 4844
PH4100XPC#1 | GG\18\007\X2 | GG | 18 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2023-08-04 13:41 | 2023-08-06 09:18 | 94490.805 | 94491 | [7 empty] | 0 | 0 | 9.44 | 0 | 0
DRE2 | GG\17\007\B | GG | 17 | 7 | B | 6 DL | 100 | 0 | 100 | 2023-08-04 19:16 | 2023-08-08 00:25 | 259527.1322 |  |  |  |  | 259527 | 199636 |  |  | 0 | 20.01 | 0 | 10.33 | 5452.83
TS5500Shv | GG\17\009\B | GG | 17 | 9 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2023-08-05 05:52 | 2023-08-06 01:54 | 24430.9689 | [6 empty] | 24431 | 17923 | 1.79 | 0 | 0 | 9.77 | 5534
DRE1 | RS\29\003\D | RS | 29 | 3 | D | 6 DL | 100 | 100 | 100 | 2023-08-06 00:25 | 2023-08-10 02:49 | 343687.3388 |  |  |  | 17670 | 343687 | 276835 |  |  | 0 | 28.14 | 0 | 5.21 | 5962.44
TS5500Shv | GG\17\008\B | GG | 17 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-08-06 01:54 | 2023-08-07 21:05 | 52654.3731 | [6 empty] | 52654 | 38526 | 3.85 | 0 | 0 | 10.16 | 5493
PH4100XPC#1 | GG\18\007\B | GG | 18 | 7 | B | 1 Prestrip - Thick | 100 | 64.9526 | 64.9526 | 2023-08-06 09:18 | 2023-08-07 02:41 | 37670.7971 | 37671 | [7 empty] | 0 | 0 | 3.77 | 10.33 | 5453.45
TS Fleet 5 | GG\18\007\B | GG | 18 | 7 | B | 1 Prestrip - Thick | 46.5068 | 35.0474 | 35.0474 | 2023-08-06 16:19 | 2023-08-07 02:41 | 20326.5593 | 20327 | [7 empty] | 0 | 0 | 2.04 | 10.33 | 5453.45
TS Fleet 5 | MW\54\005\D | MW | 54 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-08-07 02:41 | 2023-08-07 21:36 | 37069.3004 | 37069 | [7 empty] | 0 | 0 | 4.05 | 9.28 | 5597.21
PH4100XPC#1 | GG\18\008\X1 | GG | 18 | 8 | X1 | 1 Prestrip - Thick | 100 | 42.7821 | 42.7821 | 2023-08-07 02:41 | 2023-08-12 08:08 | 267201.7091 | 267202 | [7 empty] | 0 | 0 | 26.11 | 12.04 | 5314.64
TS5500Shv | RS\28\006\D | RS | 28 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2023-08-07 21:05 | 2023-08-09 16:14 | 46266.8404 |  |  | 46267 | [5 empty] | 0 | 0 | 0 | 5.78 | 5911.79
TS Fleet 5 | MW\54\006\D | MW | 54 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-08-07 21:36 | 2023-08-10 07:02 | 112572.9149 | 112573 | [7 empty] | 0 | 0 | 9.94 | 7.94 | 5715.31
DRE2 | GG\17\006\B | GG | 17 | 6 | B | 6 DL | 100 | 0 | 100 | 2023-08-08 00:25 | 2023-08-11 07:08 | 264741.1591 |  |  |  |  | 264741 | 203647 |  |  | 0 | 20.32 | 0 | 9.86 | 5463.19
PH4100A | RS\32\003\X | RS | 32 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-08-08 03:25 | 2023-08-12 18:13 | 186276.3011 | 186276 | [7 empty] | 0 | 0 | 39.24 | 12.16 | 5245.28
TS6060#1 | GG\15\024\D | GG | 15 | 24 | D | 7 PostStrip | 34.2346 | 0 | 34.2346 | 2023-08-08 08:25 | 2023-08-08 15:23 | 7186.2469 |  |  | 7186 | [5 empty] | 0 | 0 | 0 | 6.3 | 5834.04
TS6060#1 | GG\15\024\D | GG | 15 | 24 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2023-08-08 15:23 | 2023-08-09 00:40 | 12567.168 | [6 empty] | 12567 | 9485 | 2.49 | 0 | 0 | 6.3 | 5834
TS6060#1 | GG\17\010\B | GG | 17 | 10 | B | 8 Coal Mining | 15.7 | 0 | 15.7 | 2023-08-09 00:40 | 2023-08-09 06:27 | 7818.6412 | [6 empty] | 7819 | 5755 | 0.58 | 0 | 0 | 9.49 | 5555
TS6060#1 | GG\17\009\B | GG | 17 | 9 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2023-08-09 06:27 | 2023-08-10 02:29 | 27115.6908 | [6 empty] | 27116 | 19893 | 1.99 | 0 | 0 | 9.77 | 5534
TS5500Shv | RS\35\006\X | RS | 35 | 6 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-08-09 16:14 | 2023-08-09 23:58 | 9427.3386 | [6 empty] | 9427 | 6686 | 0.57 | 0 | 0 | 11.38 | 5348
TS5500Shv | RS\31\003\A | RS | 31 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-08-09 23:58 | 2023-08-11 02:28 | 32317.8297 | [6 empty] | 32318 | 23172 | 3.34 | 0 | 0 | 10.5 | 5457
TS6060#1 | RS\33\005\X | RS | 33 | 5 | X | 1 Prestrip - Thick | 86.6891 | 86.6891 | 86.6891 | 2023-08-10 02:29 | 2023-08-28 23:07 | 456538.5491 | 456539 | [7 empty] | 0 | 0 | 46.03 | 11.96 | 5279.27
DRE1 | RS\29\004\D | RS | 29 | 4 | D | 6 DL | 100 | 100 | 100 | 2023-08-10 02:49 | 2023-08-14 03:43 | 338494.3313 |  |  |  | 17403 | 338494 | 272652 |  |  | 0 | 29.01 | 0 | 5.46 | 5940.9
TS Fleet 5 | MW\54\007\A | MW | 54 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-08-10 07:02 | 2023-08-13 16:16 | 159231.9171 | 159232 | [7 empty] | 0 | 0 | 17.75 | 13.91 | 5227.08
TS5500Shv | GG\15\024\D | GG | 15 | 24 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2023-08-11 02:28 | 2023-08-11 11:46 | 11322.8939 | [6 empty] | 11323 | 8546 | 2.25 | 0 | 0 | 6.3 | 5834
DRE2 | GG\17\005\B | GG | 17 | 5 | B | 6 DL | 100 | 0 | 100 | 2023-08-11 07:08 | 2023-08-14 13:24 | 263271.6838 |  |  |  |  | 263272 | 202517 |  |  | 0 | 20.16 | 0 | 10.03 | 5444.05
TS5500Shv | GG\17\007\B | GG | 17 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-08-11 11:46 | 2023-08-13 05:57 | 51444.5564 | [6 empty] | 51445 | 37636 | 3.76 | 0 | 0 | 10.33 | 5453
TS5500Exc | RS\30\006\A | RS | 30 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-08-11 21:33 | 2023-08-12 18:46 | 26721.2104 | [6 empty] | 26721 | 18268 | 1.7 | 0 | 0 | 18.4 | 4844
PH4100XPC#1 | GG\18\009\X1 | GG | 18 | 9 | X1 | 1 Prestrip - Thick | 100 | 53.5809 | 53.5809 | 2023-08-12 08:08 | 2023-08-18 01:30 | 298662.8966 | 298663 | [7 empty] | 0 | 0 | 32.93 | 13.13 | 5241.43
PH4100A | RS\31\004\X | RS | 31 | 4 | X | 1 Prestrip - Thick | 100 | 74.731 | 74.731 | 2023-08-12 18:13 | 2023-08-21 03:26 | 338473.0408 | 338473 | [7 empty] | 0 | 0 | 34.31 | 12.17 | 5243.51
TS5500Exc | RS\35\006\X | RS | 35 | 6 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-08-12 18:46 | 2023-08-13 02:30 | 9738.1299 | [6 empty] | 9738 | 6906 | 0.58 | 0 | 0 | 11.38 | 5348
TS5500Exc | RS\32\003\X | RS | 32 | 3 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-08-13 02:30 | 2023-08-13 09:32 | 8856.17 | [6 empty] | 8856 | 6220 | 1.1 | 0 | 0 | 12.16 | 5245
TS5500Shv | GG\18\008\X1 | GG | 18 | 8 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-08-13 05:57 | 2023-08-13 20:00 | 17126.0833 | [6 empty] | 17126 | 12529 | 1.25 | 0 | 0 | 12.04 | 5315
TS5500Exc | RS\28\005\D | RS | 28 | 5 | D | 8 Coal Mining | 93.2 | 0 | 93.2 | 2023-08-13 09:32 | 2023-08-15 07:40 | 58112.0106 | [6 empty] | 58112 | 42776 | 4.28 | 0 | 0 | 5.72 | 5919
TS Fleet 5 | GG\20\004\X1 | GG | 20 | 4 | X1 | 1 Prestrip - Thick | 25.0639 | 25.0639 | 25.0639 | 2023-08-13 16:16 | 2023-08-23 14:58 | 467852.4967 | 467852 | [7 empty] | 0 | 0 | 26.3 | 10.48 | 5314.98
TS5500Shv | GG\17\006\B | GG | 17 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-08-13 20:00 | 2023-08-15 11:59 | 48767.4287 | [6 empty] | 48767 | 35798 | 3.58 | 0 | 0 | 9.86 | 5463
DRE1 | MW\47\006\D | MW | 47 | 6 | D | 6 DL | 100 | 0 | 100 | 2023-08-14 03:43 | 2023-08-19 08:19 | 435225.2129 |  |  |  | 30952 | 435225 | 312963 |  |  | 0 | 35 | 0 | 6.17 | 5870.87
DRE2 | GG\17\004\B | GG | 17 | 4 | B | 6 DL | 100 | 100 | 100 | 2023-08-14 13:24 | 2023-08-16 22:57 | 193579.4772 |  |  |  |  | 193579 | 161316 |  |  | 0 | 15.94 | 0 | 9.84 | 5477.21
TS5500Exc | RS\28\006\D | RS | 28 | 6 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-08-15 07:40 | 2023-08-16 04:54 | 26748.0299 | [6 empty] | 26748 | 19682 | 2.14 | 0 | 0 | 5.78 | 5912
TS5500Shv | RS\28\005\D | RS | 28 | 5 | D | 8 Coal Mining | 6.8 | 0 | 6.8 | 2023-08-15 11:59 | 2023-08-15 15:28 | 4241.7724 | [6 empty] | 4242 | 3122 | 0.31 | 0 | 0 | 5.72 | 5919
TS5500Shv | RS\28\006\D | RS | 28 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-08-15 15:28 | 2023-08-16 12:42 | 25894.3694 | [6 empty] | 25894 | 19053 | 2.07 | 0 | 0 | 5.78 | 5912
TS5500Exc | RS\29\003\D | RS | 29 | 3 | D | 8 Coal Mining | 76.7 | 0 | 76.7 | 2023-08-16 04:54 | 2023-08-17 19:33 | 48689.2929 | [6 empty] | 48689 | 36062 | 3.42 | 0 | 0 | 5.21 | 5962
TS5500Shv | GG\17\005\B | GG | 17 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-08-16 12:42 | 2023-08-18 03:49 | 47690.1605 | [6 empty] | 47690 | 35029 | 3.51 | 0 | 0 | 10.03 | 5444
DRE2 | GG\16\012\D | GG | 16 | 12 | D | 6 DL | 100 | 100 | 100 | 2023-08-16 22:57 | 2023-08-23 05:15 | 505579.0623 |  |  |  | 11771 | 505579 | 223655 |  |  | 0 | 23.51 | 0 | 6.69 | 5799.28
TS5500Exc | MW\47\007\A | MW | 47 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-08-17 19:33 | 2023-09-05 03:19 | 389532.2462 | 389532 | [7 empty] | 0 | 0 | 33.5 | 13.48 | 5234.35
PH4100XPC#1 | GG\18\008\X2 | GG | 18 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2023-08-18 01:30 | 2023-08-19 18:02 | 87826.019 | 87826 | [7 empty] | 0 | 0 | 8.77 | 0 | 0
TS5500Shv | RS\29\003\D | RS | 29 | 3 | D | 8 Coal Mining | 23.3 | 0 | 23.3 | 2023-08-18 03:49 | 2023-08-18 15:57 | 14811.0109 | [6 empty] | 14811 | 10970 | 1.04 | 0 | 0 | 5.21 | 5962
TS5500Shv | GG\17\004\B | GG | 17 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-08-18 15:57 | 2023-08-20 07:51 | 48638.5217 | [6 empty] | 48639 | 35779 | 3.58 | 0 | 0 | 9.84 | 5477
DRE1 | RS\29\005\D | RS | 29 | 5 | D | 6 DL | 100 | 100 | 100 | 2023-08-19 08:19 | 2023-08-22 15:34 | 276837.4103 |  |  |  | 12386 | 276837 | 235343 |  |  | 0 | 24.77 | 0 | 5.63 | 5926.45
PH4100XPC#1 | GG\18\008\B | GG | 18 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-08-19 18:02 | 2023-08-20 23:23 | 63585.9649 | 63586 | [7 empty] | 0 | 0 | 6.36 | 10.13 | 5494.67
TS5500Shv | MW\47\006\D | MW | 47 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-08-20 07:51 | 2023-08-22 10:48 | 62134.8969 | [6 empty] | 62135 | 46947 | 4.7 | 0 | 0 | 6.17 | 5871
PH4100XPC#1 | GG\18\010\X2 | GG | 18 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.4149 | 2023-08-20 23:23 | 2023-08-27 07:58 | 343063.505 | 343064 | [7 empty] | 0 | 0 | 32.36 | 0 | 0
PH4100A | RS\32\004\X | RS | 32 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-08-21 03:26 | 2023-09-01 06:35 | 448745.5123 | 448746 | [7 empty] | 0 | 0 | 45.32 | 12.12 | 5252.74
TS5500Shv | RS\31\004\X | RS | 31 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-08-22 10:48 | 2023-08-22 23:44 | 15764.269 | [6 empty] | 15764 | 11067 | 1.11 | 0 | 0 | 12.17 | 5244
DRE1 | RS\29\006\D | RS | 29 | 6 | D | 6 DL | 100 | 100 | 100 | 2023-08-22 15:34 | 2023-08-26 11:41 | 321809.5513 |  |  |  | 12014 | 321810 | 182592 |  |  | 0 | 26.31 | 0 | 5.78 | 5911.38
TS5500Shv | RS\29\004\D | RS | 29 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-08-22 23:44 | 2023-08-25 01:51 | 61117.5295 | [6 empty] | 61118 | 45126 | 4.51 | 0 | 0 | 5.46 | 5941
DRE2 | GG\16\011\D | GG | 16 | 11 | D | 6 DL | 100 | 100 | 100 | 2023-08-23 05:15 | 2023-08-29 12:10 | 507650.0443 |  |  |  | 9211 | 507650 | 221073 |  |  | 0 | 23.02 | 0 | 6.32 | 5831.04
TS Fleet 5 | GG\20\004\X1 | GG | 20 | 4 | X1 | 1 Prestrip - Thick | 20.4891 | 20.4891 | 20.4891 | 2023-08-23 14:58 | 2023-08-31 18:06 | 382457.6081 | 382458 | [7 empty] | 0 | 0 | 21.5 | 10.48 | 5314.98
TS5500Shv | GG\16\012\D | GG | 16 | 12 | D | 8 Coal Mining | 47.5 | 0 | 47.5 | 2023-08-25 01:51 | 2023-08-26 02:03 | 29503.8587 | [6 empty] | 29504 | 22039 | 2.2 | 0 | 0 | 6.69 | 5799
TS5500Shv | RS\29\005\D | RS | 29 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-08-26 02:03 | 2023-08-28 06:04 | 63434.505 | [6 empty] | 63435 | 46770 | 4.68 | 0 | 0 | 5.63 | 5926
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2023-08-26 11:41 | 2023-08-28 11:41
PH4100XPC#1 | GG\18\010\B | GG | 18 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-08-27 07:58 | 2023-08-29 02:34 | 92291.375 | 92291 | [7 empty] | 0 | 0 | 9.23 | 9.57 | 5551.44
TS5500Shv | RS\29\006\D | RS | 29 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2023-08-28 06:04 | 2023-08-30 00:40 | 45667.8942 |  |  | 45668 | [5 empty] | 0 | 0 | 0 | 5.78 | 5911.38
DRE1 | RS\30\003\D | RS | 30 | 3 | D | 6 DL | 100 | 100 | 100 | 2023-08-28 11:41 | 2023-09-01 11:56 | 336161.0891 |  |  |  | 17283 | 336161 | 270772 |  |  | 0 | 27.7 | 0 | 5.15 | 5967.61
TS6060#1 | GG\18\009\X1 | GG | 18 | 9 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-08-28 23:07 | 2023-08-29 11:53 | 17277.7614 | [6 empty] | 17278 | 12517 | 1.26 | 0 | 0 | 13.13 | 5241
PH4100XPC#1 | GG\18\011\X1 | GG | 18 | 11 | X1 | 1 Prestrip - Thick | 100 | 51.8618 | 51.8618 | 2023-08-29 02:34 | 2023-09-02 00:51 | 206064.7614 | 206065 | [7 empty] | 0 | 0 | 18.86 | 14.31 | 5152.96
TS6060#1 | RS\30\006\B | RS | 30 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-08-29 11:53 | 2023-08-30 21:39 | 34830.0168 | 34830 | [7 empty] | 0 | 0 | 3.26 | 8.84 | 5612.78
DRE2 | GG\16\010\D | GG | 16 | 10 | D | 6 DL | 100 | 100 | 100 | 2023-08-29 12:10 | 2023-09-04 05:40 | 462532.096 |  |  |  | 10769 | 462532 | 204613 |  |  | 0 | 21.54 | 0 | 6.13 | 5848.39
TS5500Shv | GG\16\011\D | GG | 16 | 11 | D | 8 Coal Mining | 22 | 0 | 22 | 2023-08-30 00:40 | 2023-08-30 11:49 | 13608.269 | [6 empty] | 13608 | 10181 | 1.02 | 0 | 0 | 6.32 | 5831
TS5500Shv | RS\29\006\D | RS | 29 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-08-30 11:49 | 2023-09-01 07:06 | 52761.0857 | [6 empty] | 52761 | 38856 | 4.29 | 0 | 0 | 5.78 | 5911
TS6060#1 | RS\31\003\B | RS | 31 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-08-30 21:39 | 2023-08-31 16:39 | 19610.2883 | 19610 | [7 empty] | 0 | 0 | 2.76 | 8.65 | 5618.42
TS6060#1 | RS\31\004\A | RS | 31 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-08-31 16:39 | 2023-09-08 02:30 | 183513.6954 | 183514 | [7 empty] | 0 | 0 | 18.35 | 11.83 | 5352.45
TS Fleet 5 | GG\18\009\X2 | GG | 18 | 9 | X2 | 1 Prestrip - Thick | 46.5068 | 0 | 46.5068 | 2023-08-31 18:06 | 2023-09-01 13:42 | 38391.8896 | 38392 | [7 empty] | 0 | 0 | 3.84 | 0 | 0
PH4100A | RS\31\005\X | RS | 31 | 5 | X | 1 Prestrip - Thick | 100 | 60.7486 | 60.7486 | 2023-09-01 06:35 | 2023-09-09 09:14 | 329182.2366 | 329182 | [7 empty] | 0 | 0 | 33.44 | 12.23 | 5247.45
TS5500Shv | RS\30\006\B | RS | 30 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-09-01 07:06 | 2023-09-02 17:03 | 41414.9564 | [6 empty] | 41415 | 29730 | 2.8 | 0 | 0 | 8.84 | 5613
DRE1 | RS\30\004\D | RS | 30 | 4 | D | 6 DL | 100 | 100 | 100 | 2023-09-01 11:56 | 2023-09-05 11:43 | 334588.1337 |  |  |  | 17202 | 334588 | 269505 |  |  | 0 | 28.68 | 0 | 5.37 | 5948.63
TS Fleet 5 | GG\20\005\X1 | GG | 20 | 5 | X1 | 1 Prestrip - Thick | 44.9606 | 44.9606 | 44.9606 | 2023-09-01 13:42 | 2023-09-09 20:46 | 390197.137 | 390197 | [7 empty] | 0 | 0 | 35.56 | 10.48 | 5313.83
PH4100XPC#1 | GG\18\009\X2 | GG | 18 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.4932 | 2023-09-02 00:51 | 2023-09-02 21:14 | 44159.1544 | 44159 | [7 empty] | 0 | 0 | 4.41 | 0 | 0
TS5500Shv | GG\18\011\X1 | GG | 18 | 11 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-09-02 17:03 | 2023-09-03 06:38 | 16563.9784 | [6 empty] | 16564 | 11895 | 1.21 | 0 | 0 | 14.31 | 5153
PH4100XPC#1 | GG\18\009\B | GG | 18 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-09-02 21:14 | 2023-09-04 08:31 | 76442.931 | 76443 | [7 empty] | 0 | 0 | 7.65 | 9.83 | 5531.6
TS5500Shv | RS\31\003\B | RS | 31 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-09-03 06:38 | 2023-09-04 06:51 | 29531.9916 | [6 empty] | 29532 | 21342 | 2.93 | 0 | 0 | 8.65 | 5618
DRE2 | GG\16\009\D | GG | 16 | 9 | D | 6 DL | 100 | 100 | 100 | 2023-09-04 05:40 | 2023-09-09 17:37 | 443815.5704 |  |  |  | 10333 | 443816 | 196333 |  |  | 0 | 20.67 | 0 | 6.29 | 5833.74
TS5500Shv | GG\16\010\D | GG | 16 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-09-04 06:51 | 2023-09-06 09:54 | 62243.9644 | [6 empty] | 62244 | 46607 | 4.66 | 0 | 0 | 6.13 | 5848
PH4100XPC#1 | GG\18\011\X2 | GG | 18 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2023-09-04 08:31 | 2023-09-05 18:39 | 73975.38 | 73975 | [7 empty] | 0 | 0 | 7.54 | 0 | 0
TS5500Exc | RS\32\004\X | RS | 32 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-09-05 03:19 | 2023-09-05 15:55 | 15872.3567 | [6 empty] | 15872 | 11150 | 1.12 | 0 | 0 | 12.12 | 5253
DRE1 | RS\30\005\D | RS | 30 | 5 | D | 6 DL | 100 | 100 | 100 | 2023-09-05 11:43 | 2023-09-08 19:23 | 278312.338 |  |  |  | 12452 | 278312 | 236597 |  |  | 0 | 24.89 | 0 | 5.61 | 5929.02
TS5500Exc | MW\47\007\A | MW | 47 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-09-05 15:55 | 2023-09-06 11:20 | 24452.0304 | [6 empty] | 24452 | 17696 | 1.75 | 0 | 0 | 13.48 | 5234
PH4100XPC#1 | GG\18\011\B | GG | 18 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-09-05 18:39 | 2023-09-08 03:09 | 122412.8119 | 122413 | [7 empty] | 0 | 0 | 12.25 | 9.36 | 5567.21
TS5500Shv | RS\30\003\D | RS | 30 | 3 | D | 8 Coal Mining | 46.8 | 0 | 46.8 | 2023-09-06 09:54 | 2023-09-07 10:03 | 29453.7229 | [6 empty] | 29454 | 21832 | 2.08 | 0 | 0 | 5.15 | 5968
TS5500Exc | RS\30\003\D | RS | 30 | 3 | D | 8 Coal Mining | 53.2 | 0 | 53.2 | 2023-09-06 11:20 | 2023-09-07 13:54 | 33459.6289 | [6 empty] | 33460 | 24801 | 2.37 | 0 | 0 | 5.15 | 5968
TS5500Shv | GG\20\009\X1 | GG | 20 | 9 | X1 | 1 Prestrip - Thick | 16.2055 | 16.2055 | 16.2055 | 2023-09-07 10:03 | 2023-09-11 09:24 | 101741.4699 | 101741 | [7 empty] | 0 | 0 | 11.59 | 14.27 | 5145.74
TS5500Exc | MW\47\007\B | MW | 47 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-09-07 13:54 | 2023-09-08 21:55 | 28325.964 | 28326 | [7 empty] | 0 | 0 | 2.8 | 9.77 | 5508.47
TS6060#1 | GG\16\012\D | GG | 16 | 12 | D | 8 Coal Mining | 52.5 | 0 | 52.5 | 2023-09-08 02:30 | 2023-09-09 02:38 | 32642.2884 | [6 empty] | 32642 | 24384 | 2.44 | 0 | 0 | 6.69 | 5799
PH4100XPC#1 | GG\18\012\X1 | GG | 18 | 12 | X1 | 1 Prestrip - Thick | 100 | 52.9021 | 52.9021 | 2023-09-08 03:09 | 2023-09-11 12:37 | 172341.4165 | 172341 | [7 empty] | 0 | 0 | 17.35 | 14.05 | 5175.11
DRE1 | RS\30\006\D | RS | 30 | 6 | D | 6 DL | 100 | 100 | 100 | 2023-09-08 19:23 | 2023-09-12 13:33 | 314942.2892 |  |  |  | 11787 | 314942 | 178800 |  |  | 0 | 26.1 | 0 | 5.8 | 5910.56
TS5500Exc | MW\47\007\B | MW | 47 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-09-08 21:55 | 2023-09-10 03:08 | 36799.9384 | [6 empty] | 36800 | 27114 | 2.64 | 0 | 0 | 9.77 | 5508
TS6060#1 | GG\16\011\D | GG | 16 | 11 | D | 8 Coal Mining | 78 | 0 | 78 | 2023-09-09 02:38 | 2023-09-10 14:21 | 48349.0582 | [6 empty] | 48349 | 36174 | 3.62 | 0 | 0 | 6.32 | 5831
PH4100A | RS\32\005\X | RS | 32 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-09-09 09:14 | 2023-09-22 12:23 | 531588.8131 | 531589 | [7 empty] | 0 | 0 | 53.84 | 12.11 | 5261.71
DRE2 | GG\16\008\D | GG | 16 | 8 | D | 6 DL | 100 | 100 | 100 | 2023-09-09 17:37 | 2023-09-15 01:52 | 431443.3377 |  |  |  | 10045 | 431443 | 190860 |  |  | 0 | 20.09 | 0 | 6.54 | 5811.3
TS Fleet 5 | GG\20\006\X1 | GG | 20 | 6 | X1 | 1 Prestrip - Thick | 45.6704 | 45.6704 | 45.6704 | 2023-09-09 20:46 | 2023-09-17 14:22 | 363752.1705 | 363752 | [7 empty] | 0 | 0 | 35.19 | 11.01 | 5312.13
TS5500Exc | RS\31\005\X | RS | 31 | 5 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-09-10 03:08 | 2023-09-10 10:08 | 8806.1131 | [6 empty] | 8806 | 6184 | 0.61 | 0 | 0 | 12.23 | 5247
TS5500Exc | RS\30\004\D | RS | 30 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-09-10 10:08 | 2023-09-12 10:39 | 61107.3078 | [6 empty] | 61107 | 45154 | 4.52 | 0 | 0 | 5.37 | 5949
TS6060#1 | RS\32\003\A | RS | 32 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-09-10 14:21 | 2023-09-15 10:53 | 120231.7365 | 120232 | [7 empty] | 0 | 0 | 19.21 | 10.5 | 5456.82
TS5500Shv | RS\31\004\A | RS | 31 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-09-11 09:24 | 2023-09-13 01:07 | 48416.9248 | [6 empty] | 48417 | 34371 | 3.44 | 0 | 0 | 11.83 | 5352
PH4100XPC#1 | GG\18\013\X2 | GG | 18 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.009 | 2023-09-11 12:37 | 2023-09-17 05:07 | 290036.5433 | 290037 | [7 empty] | 0 | 0 | 18.35 | 0 | 0
TS5500Exc | RS\30\005\D | RS | 30 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-09-12 10:39 | 2023-09-14 13:26 | 63965.6289 | [6 empty] | 63966 | 47200 | 4.72 | 0 | 0 | 5.61 | 5929
DRE1 | MW\47\007\D | MW | 47 | 7 | D | 6 DL | 100 | 100 | 100 | 2023-09-12 13:33 | 2023-09-16 16:28 | 345528.484 |  |  |  | 17765 | 345528 | 278318 |  |  | 0 | 29.61 | 0 | 5.66 | 5916.06
TS5500Shv | GG\18\012\X1 | GG | 18 | 12 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2023-09-13 01:07 | 2023-09-13 07:25 | 7684.4552 | [6 empty] | 7684 | 5529 | 0.57 | 0 | 0 | 14.05 | 5175
TS5500Shv | RS\31\005\X | RS | 31 | 5 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-09-13 07:25 | 2023-09-13 14:24 | 8525.067 | [6 empty] | 8525 | 5986 | 0.59 | 0 | 0 | 12.23 | 5247
TS5500Shv | GG\16\009\D | GG | 16 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-09-13 14:24 | 2023-09-15 16:51 | 61510.9435 | [6 empty] | 61511 | 45984 | 4.6 | 0 | 0 | 6.29 | 5834
TS5500Exc | MW\47\008\A | MW | 47 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-09-14 13:26 | 2023-10-07 19:34 | 494463.4453 | 494463 | [7 empty] | 0 | 0 | 34.9 | 12.47 | 5315.68
DRE2 | GG\16\007\D | GG | 16 | 7 | D | 6 DL | 100 | 100 | 100 | 2023-09-15 01:52 | 2023-09-20 09:20 | 428773.3755 |  |  |  | 7985 | 428773 | 191631 |  |  | 0 | 19.96 | 0 | 6.58 | 5808.15
TS6060#1 | GG\18\012\X1 | GG | 18 | 12 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2023-09-15 10:53 | 2023-09-15 17:11 | 8528.9008 | [6 empty] | 8529 | 6137 | 0.63 | 0 | 0 | 14.05 | 5175
TS5500Shv | RS\32\003\A | RS | 32 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-09-15 16:51 | 2023-09-16 05:42 | 15677.0428 | [6 empty] | 15677 | 11251 | 1.63 | 0 | 0 | 10.5 | 5457
TS6060#1 | RS\31\004\B | RS | 31 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-09-15 17:11 | 2023-09-16 19:53 | 27558.8305 | 27559 | [7 empty] | 0 | 0 | 2.76 | 8.7 | 5619.48
TS5500Shv | GG\18\012\X2 | GG | 18 | 12 | X2 | 1 Prestrip - Thick | 33.6454 | 0 | 33.6454 | 2023-09-16 05:42 | 2023-09-17 05:33 | 25565.0256 | 25565 | [7 empty] | 0 | 0 | 2.62 | 0 | 0
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 5d 00:00 |  | 5d 00:00 | 2023-09-16 16:28 | 2023-09-21 16:28
TS6060#1 | RS\31\005\A | RS | 31 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-09-16 19:53 | 2023-09-23 18:01 | 171413.9162 | 171414 | [7 empty] | 0 | 0 | 17 | 15.09 | 5100.82
PH4100XPC#1 | GG\18\012\X2 | GG | 18 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 47.3564 | 2023-09-17 05:07 | 2023-09-17 21:44 | 35983.1713 | 35983 | [7 empty] | 0 | 0 | 3.69 | 0 | 0
TS5500Shv | GG\18\013\B | GG | 18 | 13 | B | 1 Prestrip - Thick | 9.0756 | 9.0756 | 9.0756 | 2023-09-17 05:33 | 2023-09-17 23:53 | 19653.2095 | 19653 | [7 empty] | 0 | 0 | 1.42 | 10.95 | 5433.95
TS Fleet 5 | GG\18\012\X2 | GG | 18 | 12 | X2 | 1 Prestrip - Thick | 30.8594 | 0 | 18.9982 | 2023-09-17 14:22 | 2023-09-17 21:44 | 14435.5861 | 14436 | [7 empty] | 0 | 0 | 1.48 | 0 | 0
TS Fleet 5 | GG\18\012\B | GG | 18 | 12 | B | 1 Prestrip - Thick | 46.5068 | 46.5068 | 46.5068 | 2023-09-17 21:44 | 2023-09-19 06:34 | 64366.7123 | 64367 | [7 empty] | 0 | 0 | 6.46 | 9.88 | 5522.56
PH4100XPC#1 | GG\18\012\B | GG | 18 | 12 | B | 1 Prestrip - Thick | 100 | 53.4932 | 53.4932 | 2023-09-17 21:44 | 2023-09-19 07:54 | 74035.9388 | 74036 | [7 empty] | 0 | 0 | 7.43 | 9.88 | 5522.56
TS5500Shv | RS\31\004\B | RS | 31 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-09-17 23:53 | 2023-09-19 08:07 | 39306.1161 | [6 empty] | 39306 | 28359 | 2.84 | 0 | 0 | 8.7 | 5619
TS Fleet 5 | GG\18\013\B | GG | 18 | 13 | B | 1 Prestrip - Thick | 42.2861 | 42.2861 | 42.2861 | 2023-09-19 06:34 | 2023-09-21 05:17 | 91570.4363 | 91570 | [7 empty] | 0 | 0 | 6.61 | 10.95 | 5433.95
PH4100XPC#1 | GG\18\013\B | GG | 18 | 13 | B | 1 Prestrip - Thick | 100 | 48.6383 | 48.6383 | 2023-09-19 07:54 | 2023-09-21 08:31 | 105326.2311 | 105326 | [7 empty] | 0 | 0 | 7.6 | 10.95 | 5433.95
TS5500Shv | GG\16\008\D | GG | 16 | 8 | D | 8 Coal Mining | 54.5 | 0 | 54.5 | 2023-09-19 08:07 | 2023-09-20 11:40 | 33601.2457 | [6 empty] | 33601 | 25080 | 2.51 | 0 | 0 | 6.54 | 5811
DRE2 | GG\16\006\D | GG | 16 | 6 | D | 6 DL | 100 | 100 | 100 | 2023-09-20 09:20 | 2023-09-25 15:01 | 422721.588 |  |  |  | 7872 | 422722 | 188926 |  |  | 0 | 19.68 | 0 | 6.6 | 5806.35
TS5500Shv | MW\47\007\D | MW | 47 | 7 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-09-20 11:40 | 2023-09-21 13:26 | 31420.308 | [6 empty] | 31420 | 23837 | 2.38 | 0 | 0 | 5.66 | 5916
TS Fleet 5 | GG\20\007\X1 | GG | 20 | 7 | X1 | 1 Prestrip - Thick | 45.7649 | 45.7649 | 45.7649 | 2023-09-21 05:17 | 2023-09-28 09:12 | 336966.3509 | 336966 | [7 empty] | 0 | 0 | 32.92 | 11.72 | 5300.03
PH4100XPC#1 | GG\18\018\X2 | GG | 18 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 52.9223 | 2023-09-21 08:31 | 2023-09-24 02:03 | 138751.3395 | 138751 | [7 empty] | 0 | 0 | 14.01 | 0 | 0
TS5500Shv | GG\16\007\D | GG | 16 | 7 | D | 8 Coal Mining | 44.6 | 0 | 44.6 | 2023-09-21 13:26 | 2023-09-22 11:51 | 27331.6587 | [6 empty] | 27332 | 20416 | 2.04 | 0 | 0 | 6.58 | 5808
DRE1 | MW\52\004\D | MW | 52 | 4 | D | 6 DL | 100 | 0 | 100 | 2023-09-21 16:28 | 2023-09-26 11:31 | 401880.8997 |  |  |  | 15952 | 401881 | 193422 |  |  | 0 | 35 | 0 | 8.76 | 5640.54
TS5500Shv | RS\30\006\D | RS | 30 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2023-09-22 11:51 | 2023-09-24 05:59 | 45159.2014 |  |  | 45159 | [5 empty] | 0 | 0 | 0 | 5.8 | 5910.56
PH4100A | RS\31\006\X | RS | 31 | 6 | X | 1 Prestrip - Thick | 100 | 40.5443 | 40.5443 | 2023-09-22 12:23 | 2023-09-30 19:23 | 337888.5234 | 337889 | [7 empty] | 0 | 0 | 26.85 | 12.61 | 5222.95
TS6060#1 | GG\16\008\D | GG | 16 | 8 | D | 8 Coal Mining | 45.5 | 0 | 45.5 | 2023-09-23 18:01 | 2023-09-24 14:45 | 28064.5402 | [6 empty] | 28065 | 20947 | 2.09 | 0 | 0 | 6.54 | 5811
PH4100XPC#1 | GG\18\018\B | GG | 18 | 18 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-09-24 02:03 | 2023-09-26 20:04 | 143052.2605 | 143052 | [7 empty] | 0 | 0 | 14.28 | 11.23 | 5416.45
TS5500Shv | RS\32\005\X | RS | 32 | 5 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-09-24 05:59 | 2023-09-24 12:34 | 8027.3454 | [6 empty] | 8027 | 5643 | 0.56 | 0 | 0 | 12.11 | 5262
TS5500Shv | RS\30\006\D | RS | 30 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-09-24 12:34 | 2023-09-26 07:58 | 52921.6593 | [6 empty] | 52922 | 39007 | 4.35 | 0 | 0 | 5.8 | 5911
TS6060#1 | GG\16\007\D | GG | 16 | 7 | D | 8 Coal Mining | 55.4 | 0 | 55.4 | 2023-09-24 14:45 | 2023-09-25 15:48 | 33900.6056 | [6 empty] | 33901 | 25323 | 2.53 | 0 | 0 | 6.58 | 5808
DRE2 | GG\16\005\D | GG | 16 | 5 | D | 6 DL | 100 | 100 | 100 | 2023-09-25 15:01 | 2023-09-30 22:48 | 429843.6537 |  |  |  | 10008 | 429844 | 190152 |  |  | 0 | 20.03 | 0 | 6.61 | 5805.43
TS6060#1 | GG\16\006\D | GG | 16 | 6 | D | 8 Coal Mining | 34.1 | 0 | 34.1 | 2023-09-25 15:48 | 2023-09-26 07:17 | 20952.8311 | [6 empty] | 20953 | 15676 | 1.57 | 0 | 0 | 6.6 | 5806
TS6060#1 | RS\33\006\X | RS | 33 | 6 | X | 1 Prestrip - Thick | 71.096 | 71.096 | 71.096 | 2023-09-26 07:17 | 2023-10-19 09:06 | 560356.8627 | 560357 | [7 empty] | 0 | 0 | 45.43 | 12.07 | 5279.48
TS5500Shv | GG\16\006\D | GG | 16 | 6 | D | 8 Coal Mining | 65.9 | 0 | 65.9 | 2023-09-26 07:58 | 2023-09-27 17:13 | 40555.6518 | [6 empty] | 40556 | 30343 | 3.03 | 0 | 0 | 6.6 | 5806
DRE1 | MW\52\005\D | MW | 52 | 5 | D | 6 DL | 100 | 0 | 100 | 2023-09-26 11:31 | 2023-10-01 19:08 | 445777.9782 |  |  |  | 31703 | 445778 | 320552 |  |  | 0 | 35 | 0 | 8.78 | 5640.88
PH4100XPC#1 | GG\18\019\X2 | GG | 18 | 19 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.1386 | 2023-09-26 20:04 | 2023-09-28 23:43 | 110292.95 | 110293 | [7 empty] | 0 | 0 | 11.58 | 0 | 0
TS5500Shv | MW\52\004\D | MW | 52 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2023-09-27 17:13 | 2023-09-28 10:30 | 18512.5735 |  |  | 18513 | [5 empty] | 0 | 0 | 0 | 8.76 | 5640.54
TS Fleet 5 | GG\20\008\X1 | GG | 20 | 8 | X1 | 1 Prestrip - Thick | 45.7356 | 45.7356 | 45.7356 | 2023-09-28 09:12 | 2023-10-05 00:05 | 311393.8222 | 311394 | [7 empty] | 0 | 0 | 31.07 | 12.62 | 5260.72
TS5500Shv | MW\52\004\D | MW | 52 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-09-28 10:30 | 2023-09-29 14:39 | 34331.3573 | [6 empty] | 34331 | 25460 | 4.26 | 0 | 0 | 8.76 | 5641
PH4100XPC#1 | GG\18\019\B | GG | 18 | 19 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-09-28 23:43 | 2023-10-01 07:36 | 121069.7249 | 121070 | [7 empty] | 0 | 0 | 12.04 | 12.22 | 5352.88
TS5500Shv | GG\20\013\X1 | GG | 20 | 13 | X1 | 1 Prestrip - Thick | 19.2012 | 19.2012 | 19.2012 | 2023-09-29 14:39 | 2023-10-02 04:11 | 64851.6106 | 64852 | [7 empty] | 0 | 0 | 6.39 | 14.2 | 5163.11
PH4100A | RS\32\006\X | RS | 32 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-09-30 19:23 | 2023-10-20 18:30 | 812013.2282 | 812013 | [7 empty] | 0 | 0 | 65.24 | 12.34 | 5251.42
DRE2 | GG\16\004\D | GG | 16 | 4 | D | 6 DL | 100 | 100 | 100 | 2023-09-30 22:48 | 2023-10-06 04:01 | 421208.1765 |  |  |  | 7844 | 421208 | 188249 |  |  | 0 | 19.62 | 0 | 6.54 | 5810.9
PH4100XPC#1 | GG\18\020\B | GG | 18 | 20 | B | 1 Prestrip - Thick | 100 | 54.6067 | 54.6067 | 2023-10-01 07:36 | 2023-10-05 02:07 | 205096.1087 | 205096 | [7 empty] | 0 | 0 | 20.57 | 14.96 | 5150.81
DRE1 | MW\52\006\D | MW | 52 | 6 | D | 6 DL | 100 | 0 | 100 | 2023-10-01 19:08 | 2023-10-07 05:13 | 454413.5775 |  |  |  | 32317 | 454414 | 326761 |  |  | 0 | 35 | 0 | 7.58 | 5747.26
TS5500Shv | RS\31\006\X | RS | 31 | 6 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-10-02 04:11 | 2023-10-02 12:46 | 10457.8664 | [6 empty] | 10458 | 7333 | 0.6 | 0 | 0 | 12.61 | 5223
TS5500Shv | GG\16\005\D | GG | 16 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-10-02 12:46 | 2023-10-04 15:17 | 61599.935 | [6 empty] | 61600 | 46124 | 4.61 | 0 | 0 | 6.61 | 5805
TS5500Shv | MW\52\005\D | MW | 52 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-10-04 15:17 | 2023-10-06 16:41 | 60251.671 | [6 empty] | 60252 | 44728 | 4.47 | 0 | 0 | 8.78 | 5641
TS Fleet 5 | GG\20\009\X1 | GG | 20 | 9 | X1 | 1 Prestrip - Thick | 37.6213 | 37.6213 | 37.6213 | 2023-10-05 00:05 | 2023-10-10 00:35 | 236194.4428 | 236194 | [7 empty] | 0 | 0 | 26.92 | 14.27 | 5145.74
PH4100XPC#1 | GG\18\021\B | GG | 18 | 21 | B | 1 Prestrip - Thick | 100 | 54.2181 | 54.2181 | 2023-10-05 02:07 | 2023-10-08 08:54 | 175744.0743 | 175744 | [7 empty] | 0 | 0 | 19.51 | 16.55 | 5056.08
DRE2 | GG\16\003\D | GG | 16 | 3 | D | 6 DL | 100 | 100 | 100 | 2023-10-06 04:01 | 2023-10-12 08:41 | 500098.0729 |  |  |  | 8238 | 500098 | 143960 |  |  | 0 | 19.16 | 0 | 6.41 | 5822.03
TS5500Shv | GG\16\004\D | GG | 16 | 4 | D | 8 Coal Mining | 52.5 | 0 | 52.5 | 2023-10-06 16:41 | 2023-10-07 18:40 | 31670.727 | [6 empty] | 31671 | 23733 | 2.37 | 0 | 0 | 6.54 | 5811
DRE1 | MW\52\007\D | MW | 52 | 7 | D | 6 DL | 100 | 100 | 100 | 2023-10-07 05:13 | 2023-10-11 13:12 | 363222.9231 |  |  |  | 18675 | 363223 | 292570 |  |  | 0 | 28.93 | 0 | 6.19 | 5869.92
TS5500Shv | MW\52\006\D | MW | 52 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-10-07 18:40 | 2023-10-09 22:22 | 63050.3886 | [6 empty] | 63050 | 47223 | 4.72 | 0 | 0 | 7.58 | 5747
TS5500Exc | RS\32\005\X | RS | 32 | 5 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-10-07 19:34 | 2023-10-08 02:09 | 8291.9832 | [6 empty] | 8292 | 5829 | 0.58 | 0 | 0 | 12.11 | 5262
TS5500Exc | RS\31\005\A | RS | 31 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-10-08 02:09 | 2023-10-09 17:17 | 49289.293 | [6 empty] | 49289 | 34325 | 3.41 | 0 | 0 | 15.09 | 5101
PH4100XPC#1 | GG\18\022\B | GG | 18 | 22 | B | 1 Prestrip - Thick | 100 | 53.5005 | 53.5005 | 2023-10-08 08:54 | 2023-10-11 09:10 | 156627.56 | 156628 | [7 empty] | 0 | 0 | 16.84 | 18.46 | 4901.82
TS5500Exc | RS\31\006\X | RS | 31 | 6 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-10-09 17:17 | 2023-10-10 01:51 | 10802.6313 | [6 empty] | 10803 | 7575 | 0.62 | 0 | 0 | 12.61 | 5223
TS5500Shv | MW\47\008\A | MW | 47 | 8 | A | 8 Coal Mining | 1.2 | 0 | 1.2 | 2023-10-09 22:22 | 2023-10-09 22:59 | 754.928 | [6 empty] | 755 | 549 | 0.04 | 0 | 0 | 12.47 | 5316
TS5500Shv | GG\20\018\X2 | GG | 20 | 18 | X2 | 1 Prestrip - Thick | 10.6625 | 0 | 10.6625 | 2023-10-09 22:59 | 2023-10-11 01:52 | 28298.4673 | 28298 | [7 empty] | 0 | 0 | 2.85 | 0 | 0
TS Fleet 5 | GG\20\010\B | GG | 20 | 10 | B | 1 Prestrip - Thick | 44.852 | 44.852 | 44.852 | 2023-10-10 00:35 | 2023-10-17 09:52 | 347448.799 | 347449 | [7 empty] | 0 | 0 | 33.82 | 9.84 | 5536.87
TS5500Exc | RS\32\003\A | RS | 32 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-10-10 01:51 | 2023-10-10 14:43 | 16193.8684 | [6 empty] | 16194 | 11622 | 1.68 | 0 | 0 | 10.5 | 5457
TS5500Exc | MW\47\007\D | MW | 47 | 7 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-10-10 14:43 | 2023-10-11 16:29 | 32456.1423 | [6 empty] | 32456 | 24623 | 2.46 | 0 | 0 | 5.66 | 5916
TS5500Shv | GG\20\021\B | GG | 20 | 21 | B | 1 Prestrip - Thick | 6.1836 | 6.1836 | 6.1836 | 2023-10-11 01:52 | 2023-10-11 21:44 | 21358.9636 | 21359 | [7 empty] | 0 | 0 | 2.42 | 18.66 | 4881.61
PH4100XPC#1 | GG\18\023\B | GG | 18 | 23 | B | 1 Prestrip - Thick | 100 | 54.3415 | 54.3415 | 2023-10-11 09:10 | 2023-10-15 17:17 | 233404.1253 | 233404 | [7 empty] | 0 | 0 | 19 | 0 | 0
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2023-10-11 13:12 | 2023-10-13 13:12
TS5500Exc | MW\47\008\A | MW | 47 | 8 | A | 8 Coal Mining | 98.8 | 0 | 98.8 | 2023-10-11 16:29 | 2023-10-13 18:10 | 62581.6164 | [6 empty] | 62582 | 45550 | 3.35 | 0 | 0 | 12.47 | 5316
TS5500Shv | MW\52\007\D | MW | 52 | 7 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-10-11 21:44 | 2023-10-13 01:10 | 33463.1767 | [6 empty] | 33463 | 25306 | 2.38 | 0 | 0 | 6.19 | 5870
DRE2 | GG\17\013\B | GG | 17 | 13 | B | 6 DL | 100 | 0 | 100 | 2023-10-12 08:41 | 2023-10-15 04:39 | 228623.9913 |  |  |  |  | 228624 | 190520 |  |  | 0 | 15.53 | 0 | 10.67 | 5457.61
TS5500Shv | GG\16\003\D | GG | 16 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2023-10-13 01:10 | 2023-10-15 03:19 | 53757.1624 |  |  | 53757 | [5 empty] | 0 | 0 | 0 | 6.41 | 5822.03
DRE1 | RS\31\003\D | RS | 31 | 3 | D | 6 DL | 100 | 100 | 100 | 2023-10-13 13:12 | 2023-10-17 11:23 | 329000.1715 |  |  |  | 16915 | 329000 | 265004 |  |  | 0 | 27.25 | 0 | 5.11 | 5971.26
TS5500Exc | MW\52\007\D | MW | 52 | 7 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-10-13 18:10 | 2023-10-14 21:36 | 34566.3583 | [6 empty] | 34566 | 26140 | 2.45 | 0 | 0 | 6.19 | 5870
TS5500Exc | MW\47\008\B | MW | 47 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-10-14 21:36 | 2023-10-16 20:24 | 41380.9699 | 41381 | [7 empty] | 0 | 0 | 3.05 | 9.53 | 5528
TS5500Shv | GG\16\003\D | GG | 16 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-10-15 03:19 | 2023-10-17 08:04 | 64329.3492 | [6 empty] | 64329 | 48206 | 4.52 | 0 | 0 | 6.41 | 5822
DRE2 | GG\17\018\B | GG | 17 | 18 | B | 6 DL | 100 | 0 | 100 | 2023-10-15 04:39 | 2023-10-17 13:30 | 191189.04 |  |  |  |  | 191189 | 159324 |  |  | 0 | 15.88 | 0 | 10.97 | 5437.77
PH4100XPC#1 | GG\19\003\X1 | GG | 19 | 3 | X1 | 1 Prestrip - Thick | 100 | 53.4383 | 53.4383 | 2023-10-15 17:17 | 2023-10-26 20:46 | 578234.4411 | 578234 | [7 empty] | 0 | 0 | 58.72 | 10.39 | 5325.34
TS5500Exc | MW\47\008\B | MW | 47 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-10-16 20:24 | 2023-10-18 13:49 | 52184.8525 | [6 empty] | 52185 | 38528 | 2.85 | 0 | 0 | 9.53 | 5528
TS5500Shv | GG\17\013\B | GG | 17 | 13 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-10-17 08:04 | 2023-10-19 09:09 | 59845.5308 | [6 empty] | 59846 | 43760 | 3.63 | 0 | 0 | 10.67 | 5458
TS Fleet 5 | GG\20\011\X1 | GG | 20 | 11 | X1 | 1 Prestrip - Thick | 45.7071 | 45.7071 | 45.7071 | 2023-10-17 09:52 | 2023-10-21 20:34 | 209152.8767 | 209153 | [7 empty] | 0 | 0 | 20.83 | 14.64 | 5126.47
DRE1 | RS\31\004\D | RS | 31 | 4 | D | 6 DL | 100 | 100 | 100 | 2023-10-17 11:23 | 2023-10-21 10:27 | 332075.7644 |  |  |  | 17073 | 332076 | 267482 |  |  | 0 | 28.46 | 0 | 5.31 | 5953.96
DRE2 | GG\17\019\B | GG | 17 | 19 | B | 6 DL | 100 | 0 | 100 | 2023-10-17 13:30 | 2023-10-20 03:43 | 209296.4195 |  |  |  |  | 209296 | 174414 |  |  | 0 | 17.46 | 0 | 11.98 | 5371.78
TS5500Exc | RS\31\003\D | RS | 31 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-10-18 13:49 | 2023-10-20 15:24 | 62446.9369 | [6 empty] | 62447 | 46287 | 4.44 | 0 | 0 | 5.11 | 5971
TS6060#1 | RS\31\005\B | RS | 31 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-10-19 09:06 | 2023-10-20 14:05 | 29904.6222 | 29905 | [7 empty] | 0 | 0 | 2.97 | 8.69 | 5624.1
TS5500Shv | GG\17\018\B | GG | 17 | 18 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-10-19 09:09 | 2023-10-21 02:44 | 50704.4463 | [6 empty] | 50704 | 37018 | 3.71 | 0 | 0 | 10.97 | 5438
DRE2 | GG\17\020\B | GG | 17 | 20 | B | 6 DL | 100 | 0 | 100 | 2023-10-20 03:43 | 2023-10-23 18:12 | 290907.8667 |  |  |  |  | 290908 | 223775 |  |  | 0 | 21.46 | 0 | 14.96 | 5149.11
TS6060#1 | RS\31\006\A | RS | 31 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-10-20 14:05 | 2023-10-27 19:08 | 178566.0158 | 178566 | [7 empty] | 0 | 0 | 16.56 | 18.08 | 4870.01
TS5500Exc | RS\31\005\B | RS | 31 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-10-20 15:24 | 2023-10-21 08:31 | 21552.596 | [6 empty] | 21553 | 15524 | 1.54 | 0 | 0 | 8.69 | 5624
PH4100A | RS\32\004\A | RS | 32 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-10-20 18:30 | 2023-10-25 04:36 | 184181.7889 | 184182 | [7 empty] | 0 | 0 | 18.41 | 11.73 | 5361.89
TS5500Shv | RS\31\005\B | RS | 31 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-10-21 02:44 | 2023-10-21 19:51 | 20864.7471 | [6 empty] | 20865 | 15029 | 1.49 | 0 | 0 | 8.69 | 5624
TS5500Exc | RS\32\006\X | RS | 32 | 6 | X | 8 Coal Mining | 90.9 | 0 | 90.9 | 2023-10-21 08:31 | 2023-10-21 23:21 | 18692.7882 | [6 empty] | 18693 | 13135 | 1.09 | 0 | 0 | 12.34 | 5251
DRE1 | MW\47\008\D | MW | 47 | 8 | D | 6 DL | 100 | 100 | 100 | 2023-10-21 10:27 | 2023-10-25 19:46 | 367898.5947 |  |  |  | 18915 | 367899 | 296336 |  |  | 0 | 28.85 | 0 | 5.36 | 5941.98
TS5500Shv | RS\32\006\X | RS | 32 | 6 | X | 8 Coal Mining | 9.1 | 0 | 9.1 | 2023-10-21 19:51 | 2023-10-21 21:23 | 1872.3901 | [6 empty] | 1872 | 1316 | 0.11 | 0 | 0 | 12.34 | 5251
TS Fleet 5 | GG\20\012\X1 | GG | 20 | 12 | X1 | 1 Prestrip - Thick | 45.8775 | 45.8775 | 45.8775 | 2023-10-21 20:34 | 2023-10-25 18:51 | 184777.9143 | 184778 | [7 empty] | 0 | 0 | 17.98 | 14.4 | 5146.87
TS5500Shv | GG\17\019\B | GG | 17 | 19 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-10-21 21:23 | 2023-10-23 16:50 | 52994.0716 | [6 empty] | 52994 | 38400 | 3.84 | 0 | 0 | 11.98 | 5372
TS5500Exc | RS\31\004\D | RS | 31 | 4 | D | 8 Coal Mining | 83.7 | 0 | 83.7 | 2023-10-21 23:21 | 2023-10-23 15:55 | 51101.4006 | [6 empty] | 51101 | 37790 | 3.78 | 0 | 0 | 5.31 | 5954
TS5500Exc | MW\48\004\D | MW | 48 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-10-23 15:55 | 2023-10-30 08:33 | 142071.5559 | 142072 | [7 empty] | 0 | 0 | 19.66 | 7.21 | 5777.52
TS5500Shv | RS\31\004\D | RS | 31 | 4 | D | 8 Coal Mining | 16.3 | 0 | 16.3 | 2023-10-23 16:50 | 2023-10-24 00:58 | 9918.548 | [6 empty] | 9919 | 7335 | 0.73 | 0 | 0 | 5.31 | 5954
DRE2 | GG\17\021\B | GG | 17 | 21 | B | 6 DL | 100 | 0 | 100 | 2023-10-23 18:12 | 2023-10-26 18:24 | 242861.1322 |  |  |  |  | 242861 | 186816 |  |  | 0 | 20.48 | 0 | 15.54 | 5135.76
TS5500Shv | GG\17\020\B | GG | 17 | 20 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-10-24 00:58 | 2023-10-24 16:12 | 18561.2247 | [6 empty] | 18561 | 13207 | 1.34 | 0 | 0 | 14.96 | 5149
TS5500Shv | GG\20\022\B | GG | 20 | 22 | B | 1 Prestrip - Thick | 3.7008 | 3.7008 | 3.7008 | 2023-10-24 16:12 | 2023-10-25 00:22 | 8747.6596 | 8748 | [7 empty] | 0 | 0 | 0.94 | 20.19 | 4757.18
TS5500Shv | MW\54\007\A | MW | 54 | 7 | A | 8 Coal Mining | 5.4 | 0 | 5.4 | 2023-10-25 00:22 | 2023-10-25 00:58 | 719.8763 | [6 empty] | 720 | 520 | 0.06 | 0 | 0 | 13.91 | 5227
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 03:38 |  | 0d 03:38 | 2023-10-25 00:58 | 2023-10-25 04:36
PH4100A | RS\32\005\A | RS | 32 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-10-25 04:36 | 2023-10-29 08:37 | 173629.1579 | 173629 | [7 empty] | 0 | 0 | 17.29 | 14.46 | 5151.37
TS5500Shv | RS\32\004\A | RS | 32 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-10-25 04:36 | 2023-10-26 | 23648.6497 | [6 empty] | 23649 | 16808 | 1.68 | 0 | 0 | 11.73 | 5362
TS Fleet 5 | GG\20\013\X1 | GG | 20 | 13 | X1 | 1 Prestrip - Thick | 37.2844 | 37.2844 | 37.2844 | 2023-10-25 18:51 | 2023-10-28 11:06 | 125927.1384 | 125927 | [7 empty] | 0 | 0 | 12.41 | 14.2 | 5163.11
DRE1 | RS\31\005\D | RS | 31 | 5 | D | 6 DL | 100 | 100 | 100 | 2023-10-25 19:46 | 2023-10-29 10:13 | 301964.8768 |  |  |  | 15525 | 301965 | 243228 |  |  | 0 | 25.86 | 0 | 5.6 | 5929.66
TS5500Shv | MW\47\008\D | MW | 47 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-10-26 | 2023-10-28 07:00 | 67072.5527 | [6 empty] | 67073 | 51005 | 4.71 | 0 | 0 | 5.36 | 5942
DRE2 | GG\17\022\B | GG | 17 | 22 | B | 6 DL | 100 | 0 | 100 | 2023-10-26 18:24 | 2023-10-29 22:52 | 257203.5485 |  |  |  |  | 257204 | 197849 |  |  | 0 | 20.67 | 0 | 17.49 | 4978.05
PH4100XPC#1 | GG\19\004\X1 | GG | 19 | 4 | X1 | 1 Prestrip - Thick | 100 | 54.118 | 54.118 | 2023-10-26 20:46 | 2023-11-04 19:31 | 477086.6621 | 477087 | [7 empty] | 0 | 0 | 49.13 | 10.31 | 5324.71
TS6060#1 | RS\31\006\A | RS | 31 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-10-27 19:08 | 2023-10-29 09:45 | 52246.6037 | [6 empty] | 52247 | 35810 | 3.37 | 0 | 0 | 18.08 | 4870
TS5500Shv | GG\19\003\X1 | GG | 19 | 3 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-10-28 07:00 | 2023-10-28 18:53 | 14487.4854 | [6 empty] | 14487 | 10756 | 1.17 | 0 | 0 | 10.39 | 5325
TS Fleet 5 | GG\20\014\X1 | GG | 20 | 14 | X1 | 1 Prestrip - Thick | 46.4803 | 46.4803 | 46.4803 | 2023-10-28 11:06 | 2023-10-30 18:39 | 108885.2377 | 108885 | [7 empty] | 0 | 0 | 12.48 | 14.22 | 5162.02
TS5500Shv | GG\19\003\B | GG | 19 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-10-28 18:53 | 2023-10-31 11:19 | 69070.9023 | 69071 | [7 empty] | 0 | 0 | 7.99 | 9.79 | 5498.34
PH4100A | RS\32\006\A | RS | 32 | 6 | A | 1 Prestrip - Thick | 100 | 92.5003 | 92.5003 | 2023-10-29 08:37 | 2023-11-02 06:52 | 163628.9277 | 163629 | [7 empty] | 0 | 0 | 15.31 | 17.69 | 4902.23
TS6060#1 | RS\32\003\B | RS | 32 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-10-29 09:45 | 2023-10-30 04:47 | 19644.9407 | 19645 | [7 empty] | 0 | 0 | 2.78 | 8.68 | 5615.74
DRE1 | MW\53\004\D | MW | 53 | 4 | D | 6 DL | 100 | 100 | 100 | 2023-10-29 10:13 | 2023-11-02 15:43 | 354550.819 |  |  |  | 14068 | 354551 | 186161 |  |  | 0 | 34.23 | 0 | 9.14 | 5607.81
DRE2 | GG\17\023\B | GG | 17 | 23 | B | 6 DL | 100 | 0 | 100 | 2023-10-29 22:52 | 2023-11-03 16:08 | 380990.1734 |  |  |  |  | 380990 | 293069 |  |  | 0 | 21.96 | 0 | 0 | 0
TS6060#1 | RS\31\006\B | RS | 31 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-10-30 04:47 | 2023-10-31 15:01 | 35324.9543 | 35325 | [7 empty] | 0 | 0 | 3.34 | 8.86 | 5610.85
TS5500Exc | RS\32\004\A | RS | 32 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-10-30 08:33 | 2023-10-31 03:57 | 24428.2755 | [6 empty] | 24428 | 17362 | 1.74 | 0 | 0 | 11.73 | 5362
TS Fleet 5 | GG\20\018\X2 | GG | 20 | 18 | X2 | 1 Prestrip - Thick | 41.2764 | 0 | 41.2764 | 2023-10-30 18:39 | 2023-11-02 02:32 | 109548.4061 | 109548 | [7 empty] | 0 | 0 | 11.04 | 0 | 0
TS5500Exc | RS\32\003\B | RS | 32 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-10-31 03:57 | 2023-10-31 15:27 | 14491.7374 | [6 empty] | 14492 | 10478 | 1.45 | 0 | 0 | 8.68 | 5616
TS5500Shv | RS\32\003\B | RS | 32 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-10-31 11:19 | 2023-10-31 22:49 | 14029.2351 | [6 empty] | 14029 | 10144 | 1.4 | 0 | 0 | 8.68 | 5616
TS6060#1 | RS\32\004\B | RS | 32 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-10-31 15:01 | 2023-11-01 18:01 | 27853.0251 | 27853 | [7 empty] | 0 | 0 | 2.78 | 8.74 | 5616.07
TS5500Exc | RS\31\006\B | RS | 31 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-10-31 15:27 | 2023-11-01 08:22 | 21300.3216 | [6 empty] | 21300 | 15304 | 1.45 | 0 | 0 | 8.86 | 5611
TS5500Shv | RS\31\006\B | RS | 31 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-10-31 22:49 | 2023-11-01 15:44 | 20620.5241 | [6 empty] | 20621 | 14815 | 1.41 | 0 | 0 | 8.86 | 5611
TS5500Exc | RS\32\005\A | RS | 32 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-11-01 08:22 | 2023-11-02 04:25 | 25248.4496 | [6 empty] | 25248 | 17656 | 1.76 | 0 | 0 | 14.46 | 5151
TS5500Shv | RS\32\005\A | RS | 32 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-11-01 15:44 | 2023-11-02 11:46 | 24442.648 | [6 empty] | 24443 | 17093 | 1.7 | 0 | 0 | 14.46 | 5151
TS6060#1 | RS\32\006\A | RS | 32 | 6 | A | 1 Prestrip - Thick | 26.1765 | 7.4997 | 7.4997 | 2023-11-01 18:01 | 2023-11-02 06:52 | 13266.5826 | 13267 | [7 empty] | 0 | 0 | 1.24 | 17.69 | 4902.23
TS Fleet 5 | GG\20\019\B | GG | 20 | 19 | B | 1 Prestrip - Thick | 45.6051 | 45.6051 | 45.6051 | 2023-11-02 02:32 | 2023-11-05 03:12 | 142404.8698 | 142405 | [7 empty] | 0 | 0 | 14.43 | 12.63 | 5319.92
TS5500Exc | RS\32\004\B | RS | 32 | 4 | B | 8 Coal Mining | 86.6 | 0 | 86.6 | 2023-11-02 04:25 | 2023-11-03 07:06 | 33627.1474 | [6 empty] | 33627 | 24277 | 2.43 | 0 | 0 | 8.74 | 5616
PH4100A | RS\33\003\X | RS | 33 | 3 | X | 1 Prestrip - Thick | 100 | 71.7138 | 71.7138 | 2023-11-02 06:52 | 2023-11-05 08:13 | 123328.6108 | 123329 | [7 empty] | 0 | 0 | 27.56 | 12.13 | 5251.47
TS6060#1 | GG\16\004\D | GG | 16 | 4 | D | 8 Coal Mining | 47.5 | 0 | 47.5 | 2023-11-02 06:52 | 2023-11-03 04:04 | 28687.7516 | [6 empty] | 28688 | 21497 | 2.15 | 0 | 0 | 6.54 | 5811
TS5500Shv | RS\32\004\B | RS | 32 | 4 | B | 8 Coal Mining | 13.4 | 0 | 13.4 | 2023-11-02 11:46 | 2023-11-02 16:03 | 5222.2819 | [6 empty] | 5222 | 3770 | 0.38 | 0 | 0 | 8.74 | 5616
DRE1 | MW\48\004\D | MW | 48 | 4 | D | 6 DL | 100 | 0 | 100 | 2023-11-02 15:43 | 2023-11-07 17:53 | 426772.6024 |  |  |  | 23120 | 426773 | 197007 |  |  | 0 | 35 | 0 | 7.21 | 5777.52
TS5500Shv | RS\32\006\A | RS | 32 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-11-02 16:03 | 2023-11-04 10:42 | 51993.2748 | [6 empty] | 51993 | 35746 | 3.4 | 0 | 0 | 17.69 | 4902
TS6060#1 | RS\32\005\B | RS | 32 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-11-03 04:04 | 2023-11-04 10:25 | 31312.0439 | 31312 | [7 empty] | 0 | 0 | 3.12 | 8.76 | 5619.08
TS5500Exc | RS\31\005\D | RS | 31 | 5 | D | 8 Coal Mining | 54.2 | 0 | 54.2 | 2023-11-03 07:06 | 2023-11-04 10:21 | 34326.9115 | [6 empty] | 34327 | 25349 | 2.54 | 0 | 0 | 5.6 | 5930
DRE2 | GG\16\013\D | GG | 16 | 13 | D | 6 DL | 100 | 100 | 100 | 2023-11-03 16:08 | 2023-11-10 00:43 | 513290.9557 |  |  |  | 11951 | 513291 | 227067 |  |  | 0 | 24.3 | 0 | 7.09 | 5765.31
TS5500Exc | MW\48\005\D | MW | 48 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-11-04 10:21 | 2023-11-20 17:49 | 346240.7566 | 346241 | [7 empty] | 0 | 0 | 35.92 | 7.1 | 5787.88
TS6060#1 | GG\17\021\B | GG | 17 | 21 | B | 8 Coal Mining | 51.1 | 0 | 51.1 | 2023-11-04 10:25 | 2023-11-05 05:23 | 25671.2482 | [6 empty] | 25671 | 18135 | 1.83 | 0 | 0 | 15.54 | 5136
TS5500Shv | RS\32\005\B | RS | 32 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-11-04 10:42 | 2023-11-05 20:25 | 41118.6064 | [6 empty] | 41119 | 29612 | 2.95 | 0 | 0 | 8.76 | 5619
PH4100XPC#1 | GG\19\005\X1 | GG | 19 | 5 | X1 | 1 Prestrip - Thick | 100 | 53.9839 | 53.9839 | 2023-11-04 19:31 | 2023-11-13 18:08 | 474249.7833 | 474250 | [7 empty] | 0 | 0 | 46.59 | 10.45 | 5319.99
TS Fleet 5 | GG\20\020\B | GG | 20 | 20 | B | 1 Prestrip - Thick | 44.3944 | 44.3944 | 44.3944 | 2023-11-05 03:12 | 2023-11-07 09:58 | 107346.34 | 107346 | [7 empty] | 0 | 0 | 9.88 | 15.57 | 5101.72
TS6060#1 | MW\53\004\D | MW | 53 | 4 | D | 7 PostStrip | 45.9103 | 0 | 45.9103 | 2023-11-05 05:23 | 2023-11-05 20:37 | 15720.361 |  |  | 15720 | [5 empty] | 0 | 0 | 0 | 9.14 | 5607.81
PH4100A | RS\32\006\B | RS | 32 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-11-05 08:13 | 2023-11-06 04:54 | 35922.4507 | 35922 | [7 empty] | 0 | 0 | 3.43 | 8.9 | 5607.94
TS5500Shv | GG\19\004\X1 | GG | 19 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-11-05 20:25 | 2023-11-06 10:08 | 16728.4562 | [6 empty] | 16728 | 12461 | 1.21 | 0 | 0 | 10.31 | 5325
TS6060#1 | RS\35\003\A | RS | 35 | 3 | A | 1 Prestrip - Thick | 37.2787 | 37.2787 | 37.2787 | 2023-11-05 20:37 | 2023-11-07 16:28 | 45237.9031 | 45238 | [7 empty] | 0 | 0 | 7.26 | 10.94 | 5423.94
PH4100A | RS\34\003\X | RS | 34 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-11-06 04:54 | 2023-11-10 13:23 | 175401.7984 | 175402 | [7 empty] | 0 | 0 | 38.15 | 12.11 | 5256.79
TS5500Shv | RS\32\006\B | RS | 32 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-11-06 10:08 | 2023-11-07 20:48 | 42273.5062 | [6 empty] | 42274 | 30376 | 2.91 | 0 | 0 | 8.9 | 5608
TS Fleet 5 | GG\19\004\X2 | GG | 19 | 4 | X2 | 1 Prestrip - Thick | 46.5068 | 0 | 46.5068 | 2023-11-07 09:58 | 2023-11-08 11:56 | 50909.3858 | 50909 | [7 empty] | 0 | 0 | 4.98 | 0 | 0
TS6060#1 | RS\35\005\A | RS | 35 | 5 | A | 1 Prestrip - Thick | 32.8633 | 32.8633 | 32.8633 | 2023-11-07 16:28 | 2023-11-09 23:44 | 57023.3107 | 57023 | [7 empty] | 0 | 0 | 5.71 | 14.36 | 5162.71
DRE1 | RS\31\006\D | RS | 31 | 6 | D | 6 DL | 100 | 100 | 100 | 2023-11-07 17:53 | 2023-11-11 10:02 | 307901.6843 |  |  |  | 11556 | 307902 | 174915 |  |  | 0 | 25.88 | 0 | 5.81 | 5910.1
TS5500Shv | RS\33\003\X | RS | 33 | 3 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-11-07 20:48 | 2023-11-08 03:37 | 8320.2224 | [6 empty] | 8320 | 5845 | 1.08 | 0 | 0 | 12.13 | 5251
TS5500Shv | GG\17\021\B | GG | 17 | 21 | B | 8 Coal Mining | 48.9 | 0 | 48.9 | 2023-11-08 03:37 | 2023-11-08 23:45 | 24547.3285 | [6 empty] | 24547 | 17341 | 1.75 | 0 | 0 | 15.54 | 5136
TS Fleet 5 | GG\20\021\B | GG | 20 | 21 | B | 1 Prestrip - Thick | 41.6099 | 41.6099 | 41.6099 | 2023-11-08 11:56 | 2023-11-11 13:16 | 143726.573 | 143727 | [7 empty] | 0 | 0 | 16.26 | 18.66 | 4881.61
TS5500Shv | GG\17\022\B | GG | 17 | 22 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-11-08 23:45 | 2023-11-10 21:40 | 55989.4121 | [6 empty] | 55989 | 39166 | 3.92 | 0 | 0 | 17.49 | 4978
TS6060#1 | RS\35\006\A | RS | 35 | 6 | A | 1 Prestrip - Thick | 36.2604 | 36.2604 | 36.2604 | 2023-11-09 23:44 | 2023-11-12 13:11 | 63408.7457 | 63409 | [7 empty] | 0 | 0 | 6.08 | 16.55 | 4995.91
DRE2 | GG\16\018\D | GG | 16 | 18 | D | 6 DL | 100 | 100 | 100 | 2023-11-10 00:43 | 2023-11-16 08:25 | 510247.4275 |  |  |  | 11880 | 510247 | 225721 |  |  | 0 | 24.07 | 0 | 7.16 | 5760.11
PH4100A | RS\33\003\A | RS | 33 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-11-10 13:23 | 2023-11-13 10:48 | 120514.8611 | 120515 | [7 empty] | 0 | 0 | 19.69 | 10.66 | 5444.3
TS5500Shv | RS\34\003\X | RS | 34 | 3 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-11-10 21:40 | 2023-11-11 04:42 | 8581.1658 | [6 empty] | 8581 | 6032 | 1.09 | 0 | 0 | 12.11 | 5257
TS5500Shv | RS\31\005\D | RS | 31 | 5 | D | 8 Coal Mining | 45.8 | 0 | 45.8 | 2023-11-11 04:42 | 2023-11-12 04:32 | 29049.3598 | [6 empty] | 29049 | 21451 | 2.15 | 0 | 0 | 5.6 | 5930
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2023-11-11 10:02 | 2023-11-14 10:02
TS Fleet 5 | GG\20\022\B | GG | 20 | 22 | B | 1 Prestrip - Thick | 43.6931 | 43.6931 | 43.6931 | 2023-11-11 13:16 | 2023-11-13 17:58 | 103277.7981 | 103278 | [7 empty] | 0 | 0 | 11.12 | 20.19 | 4757.18
TS5500Shv | RS\31\006\D | RS | 31 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2023-11-12 04:32 | 2023-11-13 22:11 | 44650.2441 |  |  | 44650 | [5 empty] | 0 | 0 | 0 | 5.81 | 5910.1
TS6060#1 | RS\34\003\A | RS | 34 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-11-12 13:11 | 2023-11-17 07:13 | 117651.2266 | 117651 | [7 empty] | 0 | 0 | 19.6 | 10.81 | 5433.57
PH4100A | RS\33\004\X | RS | 33 | 4 | X | 1 Prestrip - Thick | 100 | 49.8804 | 49.8804 | 2023-11-13 10:48 | 2023-11-18 22:17 | 220812.2691 | 220812 | [7 empty] | 0 | 0 | 22.31 | 12.07 | 5261.07
TS Fleet 5 | GG\20\023\B | GG | 20 | 23 | B | 1 Prestrip - Thick | 44.6664 | 44.6664 | 44.6664 | 2023-11-13 17:58 | 2023-11-17 06:22 | 165452.1642 | 165452 | [7 empty] | 0 | 0 | 16.3 | 0 | 0
PH4100XPC#1 | GG\19\004\X2 | GG | 19 | 4 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.4932 | 2023-11-13 18:08 | 2023-11-14 21:10 | 58557.0404 | 58557 | [7 empty] | 0 | 0 | 5.73 | 0 | 0
TS5500Shv | GG\19\005\X1 | GG | 19 | 5 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-11-13 22:11 | 2023-11-14 11:23 | 16096.2576 | [6 empty] | 16096 | 11986 | 1.18 | 0 | 0 | 10.45 | 5320
DRE1 | MW\53\005\D | MW | 53 | 5 | D | 6 DL | 100 | 0 | 100 | 2023-11-14 10:02 | 2023-11-19 17:30 | 445257.705 |  |  |  | 31666 | 445258 | 320177 |  |  | 0 | 35 | 0 | 9.19 | 5604.73
TS5500Shv | GG\19\005\X2 | GG | 19 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 40.2856 | 2023-11-14 11:23 | 2023-11-16 00:05 | 39341.939 | 39342 | [7 empty] | 0 | 0 | 3.86 | 0 | 0
PH4100XPC#1 | GG\19\005\X2 | GG | 19 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 59.7144 | 2023-11-14 21:10 | 2023-11-16 00:05 | 58315.59 | 58316 | [7 empty] | 0 | 0 | 5.73 | 0 | 0
TS5500Shv | RS\31\006\D | RS | 31 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-11-16 00:05 | 2023-11-17 19:37 | 53095.2467 | [6 empty] | 53095 | 39168 | 4.42 | 0 | 0 | 5.81 | 5910
PH4100XPC#1 | GG\19\005\B | GG | 19 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-11-16 00:05 | 2023-11-16 16:00 | 34486.7676 | 34487 | [7 empty] | 0 | 0 | 3.43 | 9.21 | 5512.86
DRE2 | GG\16\019\D | GG | 16 | 19 | D | 6 DL | 100 | 100 | 100 | 2023-11-16 08:25 | 2023-11-22 08:40 | 485262.0519 |  |  |  | 11298 | 485262 | 214668 |  |  | 0 | 22.6 | 0 | 6.96 | 5777.17
PH4100XPC#1 | GG\19\006\X1 | GG | 19 | 6 | X1 | 1 Prestrip - Thick | 100 | 53.2197 | 53.2197 | 2023-11-16 16:00 | 2023-11-24 12:58 | 404948.0136 | 404948 | [7 empty] | 0 | 0 | 39.69 | 10.9 | 5323.01
TS Fleet 5 | MW\55\006\D | MW | 55 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-11-17 06:22 | 2023-11-18 12:03 | 58162.4261 | 58162 | [7 empty] | 0 | 0 | 6.13 | 8.01 | 5708.93
TS6060#1 | RS\35\006\A | RS | 35 | 6 | A | 1 Prestrip - Thick | 1.0183 | 1.0183 | 1.0183 | 2023-11-17 07:13 | 2023-11-17 08:56 | 1780.6861 | 1781 | [7 empty] | 0 | 0 | 0.17 | 16.55 | 4995.91
TS6060#1 | RS\36\003\X | RS | 36 | 3 | X | 1 Prestrip - Thick | 11.9935 | 11.9935 | 11.9935 | 2023-11-17 08:56 | 2023-11-18 11:41 | 26828.5768 | 26829 | [7 empty] | 0 | 0 | 4.48 | 12.07 | 5264.48
TS5500Shv | GG\16\013\D | GG | 16 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-11-17 19:37 | 2023-11-19 22:43 | 62309.1354 | [6 empty] | 62309 | 46399 | 4.77 | 0 | 0 | 7.09 | 5765
TS6060#1 | RS\36\004\X | RS | 36 | 4 | X | 1 Prestrip - Thick | 54.8661 | 54.8661 | 54.8661 | 2023-11-18 11:41 | 2023-11-28 07:21 | 236980.6865 | 236981 | [7 empty] | 0 | 0 | 23.94 | 11.84 | 5290.76
TS Fleet 5 | MW\60\004\D | MW | 60 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-11-18 12:03 | 2023-11-19 09:00 | 41060.6837 | 41061 | [7 empty] | 0 | 0 | 3.27 | 8.7 | 5643.62
PH4100A | RS\34\004\X | RS | 34 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-11-18 22:17 | 2023-11-29 19:37 | 438705.8708 | 438706 | [7 empty] | 0 | 0 | 44.35 | 12.01 | 5269.81
TS Fleet 5 | RS\47\002\A | RS | 47 | 2 | A | 1 Prestrip - Thick | 64.8157 | 64.8157 | 64.8157 | 2023-11-19 09:00 | 2023-11-20 22:42 | 73882.7266 | 73883 | [7 empty] | 0 | 0 | 18.65 | 11.62 | 5406.71
DRE1 | MW\53\006\D | MW | 53 | 6 | D | 6 DL | 100 | 0 | 100 | 2023-11-19 17:30 | 2023-11-25 06:11 | 463505.2486 |  |  |  | 32964 | 463505 | 333299 |  |  | 0 | 35 | 0 | 7.85 | 5723.76
TS5500Shv | RS\33\004\X | RS | 33 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-11-19 22:43 | 2023-11-20 11:52 | 16040.6936 | [6 empty] | 16041 | 11276 | 1.13 | 0 | 0 | 12.07 | 5261
TS5500Shv | MW\48\004\D | MW | 48 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2023-11-20 11:52 | 2023-11-21 22:10 | 36766.0142 |  |  | 36766 | [5 empty] | 0 | 0 | 0 | 7.21 | 5777.52
TS5500Exc | RS\33\003\A | RS | 33 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2023-11-20 17:49 | 2023-11-21 18:32 | 31140.7544 | [6 empty] | 31141 | 22323 | 3.28 | 0 | 0 | 10.66 | 5444
TS Fleet 5 | RS\56\001\D | RS | 56 | 1 | D | 1 Prestrip - Thick | 38.6977 | 38.6977 | 38.6977 | 2023-11-20 22:42 | 2023-11-21 15:51 | 33626.0404 | 33626 | [7 empty] | 0 | 0 | 3.94 | 7.68 | 5744.79
TS Fleet 5 | RS\57\001\D | RS | 57 | 1 | D | 1 Prestrip - Thick | 38.6878 | 38.6878 | 38.6878 | 2023-11-21 15:51 | 2023-11-22 05:38 | 27006.9254 | 27007 | [7 empty] | 0 | 0 | 2.96 | 7.79 | 5735.19
TS5500Exc | MW\53\005\D | MW | 53 | 5 | D | 8 Coal Mining | 74.7 | 0 | 74.7 | 2023-11-21 18:32 | 2023-11-23 06:18 | 45045.8163 | [6 empty] | 45046 | 33361 | 3.34 | 0 | 0 | 9.19 | 5605
TS5500Shv | MW\48\004\D | MW | 48 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-11-21 22:10 | 2023-11-23 08:44 | 42149.0393 | [6 empty] | 42149 | 31559 | 4.36 | 0 | 0 | 7.21 | 5778
TS Fleet 5 | RS\58\001\D | RS | 58 | 1 | D | 1 Prestrip - Thick | 64.6364 | 64.6364 | 64.6364 | 2023-11-22 05:38 | 2023-11-22 20:42 | 29546.3431 | 29546 | [7 empty] | 0 | 0 | 3.1 | 7.87 | 5728.01
DRE2 | GG\16\020\D | GG | 16 | 20 | D | 6 DL | 100 | 100 | 100 | 2023-11-22 08:40 | 2023-11-27 16:54 | 431306.4237 |  |  |  | 10042 | 431306 | 190799 |  |  | 0 | 20.19 | 0 | 6.8 | 5790.52
TS Fleet 5 | RS\59\001\D | RS | 59 | 1 | D | 1 Prestrip - Thick | 64.6723 | 64.6723 | 64.6723 | 2023-11-22 20:42 | 2023-11-23 04:54 | 16053.1491 | 16053 | [7 empty] | 0 | 0 | 1.68 | 7.91 | 5723.83
TS Fleet 5 | CP\04\002\B | CP | 4 | 2 | B | 1 Prestrip - Thick | 34.4393 | 34.4393 | 34.4393 | 2023-11-23 04:54 | 2023-11-29 09:04 | 290412.9054 | 290413 | [7 empty] | 0 | 0 | 8.05 | 9.44 | 5576.4
TS5500Exc | RS\34\003\A | RS | 34 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-11-23 06:18 | 2023-11-23 18:36 | 15492.8491 | [6 empty] | 15493 | 11097 | 1.66 | 0 | 0 | 10.81 | 5434
TS5500Shv | GG\16\018\D | GG | 16 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-11-23 08:44 | 2023-11-25 12:56 | 63656.1373 | [6 empty] | 63656 | 47365 | 4.82 | 0 | 0 | 7.16 | 5760
TS5500Exc | MW\48\006\D | MW | 48 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-11-23 18:36 | 2023-12-12 11:45 | 397379.5963 | 397380 | [7 empty] | 0 | 0 | 40.98 | 6.43 | 5848.22
PH4100XPC#1 | GG\19\007\X1 | GG | 19 | 7 | X1 | 1 Prestrip - Thick | 100 | 53.0772 | 53.0772 | 2023-11-24 12:58 | 2023-12-01 21:06 | 375238.9338 | 375239 | [7 empty] | 0 | 0 | 36.57 | 11.56 | 5315.94
DRE1 | MW\48\005\D | MW | 48 | 5 | D | 6 DL | 100 | 0 | 100 | 2023-11-25 06:11 | 2023-11-30 09:30 | 430716.6656 |  |  |  | 30632 | 430717 | 309721 |  |  | 0 | 35 | 0 | 7.1 | 5787.88
TS5500Shv | GG\19\006\X1 | GG | 19 | 6 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2023-11-25 12:56 | 2023-11-25 19:06 | 7520.8685 | [6 empty] | 7521 | 5572 | 0.56 | 0 | 0 | 10.9 | 5323
TS5500Shv | MW\53\004\D | MW | 53 | 4 | D | 7 PostStrip | 54.0897 | 0 | 54.0897 | 2023-11-25 19:06 | 2023-11-26 12:23 | 18521.1435 |  |  | 18521 | [5 empty] | 0 | 0 | 0 | 9.14 | 5607.81
TS5500Shv | MW\53\004\D | MW | 53 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-11-26 12:23 | 2023-11-27 19:14 | 37619.3599 | [6 empty] | 37619 | 27856 | 4.21 | 0 | 0 | 9.14 | 5608
DRE2 | GG\16\021\D | GG | 16 | 21 | D | 6 DL | 100 | 100 | 100 | 2023-11-27 16:54 | 2023-12-02 21:50 | 420255.2598 |  |  |  | 7826 | 420255 | 187824 |  |  | 0 | 19.57 | 0 | 6.77 | 5794.14
TS5500Shv | GG\16\019\D | GG | 16 | 19 | D | 8 Coal Mining | 98.5 | 0 | 98.5 | 2023-11-27 19:14 | 2023-11-29 22:56 | 63041.2344 | [6 empty] | 63041 | 46981 | 4.7 | 0 | 0 | 6.96 | 5777
TS6060#1 | GG\19\006\X1 | GG | 19 | 6 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2023-11-28 07:21 | 2023-11-28 13:31 | 8347.3376 | [6 empty] | 8347 | 6184 | 0.62 | 0 | 0 | 10.9 | 5323
TS6060#1 | GG\16\019\D | GG | 16 | 19 | D | 8 Coal Mining | 1.5 | 0 | 1.5 | 2023-11-28 13:31 | 2023-11-28 14:15 | 987.2768 | [6 empty] | 987 | 736 | 0.07 | 0 | 0 | 6.96 | 5777
TS6060#1 | RS\36\005\X | RS | 36 | 5 | X | 1 Prestrip - Thick | 53.558 | 53.558 | 53.558 | 2023-11-28 14:15 | 2023-12-09 22:16 | 274447.3301 | 274447 | [7 empty] | 0 | 0 | 27.72 | 11.47 | 5332.43
TS Fleet 5 | GG\19\006\X2 | GG | 19 | 6 | X2 | 1 Prestrip - Thick | 46.5068 | 0 | 46.5068 | 2023-11-29 09:04 | 2023-11-30 07:42 | 44378.9479 | 44379 | [7 empty] | 0 | 0 | 4.43 | 0 | 0
PH4100A | RS\33\003\B | RS | 33 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-11-29 19:37 | 2023-11-30 06:48 | 19437.4104 | 19437 | [7 empty] | 0 | 0 | 2.79 | 8.78 | 5607.3
TS5500Shv | MW\53\005\D | MW | 53 | 5 | D | 8 Coal Mining | 25.3 | 0 | 25.3 | 2023-11-29 22:56 | 2023-11-30 11:27 | 15254.1457 | [6 empty] | 15254 | 11297 | 1.13 | 0 | 0 | 9.19 | 5605
PH4100A | RS\33\004\A | RS | 33 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-11-30 06:48 | 2023-12-04 16:26 | 183379.7082 | 183380 | [7 empty] | 0 | 0 | 18.36 | 11.67 | 5367.49
TS Fleet 5 | CP\04\003\B | CP | 4 | 3 | B | 1 Prestrip - Thick | 45.5542 | 45.5542 | 45.5542 | 2023-11-30 07:42 | 2023-12-12 12:43 | 574290.4913 | 574290 | [7 empty] | 0 | 0 | 18.91 | 8.84 | 5599.54
DRE1 | MW\53\007\D | MW | 53 | 7 | D | 6 DL | 100 | 100 | 100 | 2023-11-30 09:30 | 2023-12-03 23:22 | 299929.693 |  |  |  | 15421 | 299930 | 241589 |  |  | 0 | 29.44 | 0 | 6.43 | 5848.42
TS5500Shv | RS\33\003\B | RS | 33 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-11-30 11:27 | 2023-11-30 22:12 | 13127.7087 | [6 empty] | 13128 | 9488 | 1.33 | 0 | 0 | 8.78 | 5607
TS5500Shv | RS\34\003\A | RS | 34 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-11-30 22:12 | 2023-12-01 10:30 | 14998.3965 | [6 empty] | 14998 | 10742 | 1.61 | 0 | 0 | 10.81 | 5434
TS5500Shv | GG\16\020\D | GG | 16 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-12-01 10:30 | 2023-12-03 14:58 | 63959.2442 | [6 empty] | 63959 | 47665 | 4.77 | 0 | 0 | 6.8 | 5791
PH4100XPC#1 | GG\19\006\X2 | GG | 19 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.4932 | 2023-12-01 21:06 | 2023-12-02 20:39 | 51045.5941 | 51046 | [7 empty] | 0 | 0 | 5.09 | 0 | 0
PH4100XPC#1 | GG\19\006\B | GG | 19 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-12-02 20:39 | 2023-12-03 18:59 | 48359.0364 | 48359 | [7 empty] | 0 | 0 | 4.84 | 9.76 | 5476.21
DRE2 | GG\16\022\D | GG | 16 | 22 | D | 6 DL | 100 | 100 | 100 | 2023-12-02 21:50 | 2023-12-08 01:49 | 417081.8885 |  |  |  | 7767 | 417082 | 186405 |  |  | 0 | 19.42 | 0 | 6.65 | 5803.12
TS5500Shv | GG\19\007\X1 | GG | 19 | 7 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-12-03 14:58 | 2023-12-04 04:16 | 16223.8198 | [6 empty] | 16224 | 11929 | 1.19 | 0 | 0 | 11.56 | 5316
PH4100XPC#1 | GG\19\008\X1 | GG | 19 | 8 | X1 | 1 Prestrip - Thick | 100 | 53.0907 | 53.0907 | 2023-12-03 18:59 | 2023-12-10 12:34 | 344479.7731 | 344480 | [7 empty] | 0 | 0 | 34.04 | 12.35 | 5286.12
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2023-12-03 23:22 | 2023-12-05 23:22
TS5500Shv | GG\19\007\X2 | GG | 19 | 7 | X2 | 1 Prestrip - Thick | 20.929 | 0 | 20.929 | 2023-12-04 04:16 | 2023-12-04 22:29 | 19523.0189 | 19523 | [7 empty] | 0 | 0 | 1.95 | 0 | 0
PH4100A | RS\33\005\X | RS | 33 | 5 | X | 1 Prestrip - Thick | 100 | 13.3109 | 13.3109 | 2023-12-04 16:26 | 2023-12-06 10:03 | 70100.4182 | 70100 | [7 empty] | 0 | 0 | 7.07 | 11.96 | 5279.27
TS5500Shv | RS\33\004\A | RS | 33 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-12-04 22:29 | 2023-12-05 17:43 | 23468.629 | [6 empty] | 23469 | 16694 | 1.67 | 0 | 0 | 11.67 | 5367
TS5500Shv | MW\48\005\D | MW | 48 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-12-05 17:43 | 2023-12-07 19:18 | 60459.9755 | [6 empty] | 60460 | 45386 | 4.54 | 0 | 0 | 7.1 | 5788
DRE1 | RS\32\003\D | RS | 32 | 3 | D | 6 DL | 100 | 100 | 100 | 2023-12-05 23:22 | 2023-12-09 19:49 | 322995.5672 |  |  |  | 16606 | 322996 | 260168 |  |  | 0 | 26.89 | 0 | 5.08 | 5974.28
PH4100A | RS\34\005\X | RS | 34 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-12-06 10:03 | 2023-12-19 08:31 | 523008.4875 | 523008 | [7 empty] | 0 | 0 | 52.65 | 11.79 | 5297.96
TS5500Shv | RS\33\005\X | RS | 33 | 5 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2023-12-07 19:18 | 2023-12-08 01:48 | 7922.2066 | [6 empty] | 7922 | 5580 | 0.56 | 0 | 0 | 11.96 | 5279
TS5500Shv | GG\16\021\D | GG | 16 | 21 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2023-12-08 01:48 | 2023-12-09 02:49 | 30497.4593 | [6 empty] | 30497 | 22728 | 2.27 | 0 | 0 | 6.77 | 5794
DRE2 | GG\16\023\D | GG | 16 | 23 | D | 6 DL | 100 | 100 | 100 | 2023-12-08 01:49 | 2023-12-15 04:15 | 573253.6668 |  |  |  | 9580 | 573254 | 165260 |  |  | 0 | 18.52 | 0 | 6.4 | 5824.91
TS5500Shv | MW\53\006\D | MW | 53 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-12-09 02:49 | 2023-12-11 06:06 | 62533.4713 | [6 empty] | 62533 | 46723 | 4.67 | 0 | 0 | 7.85 | 5724
DRE1 | RS\32\004\D | RS | 32 | 4 | D | 6 DL | 100 | 100 | 100 | 2023-12-09 19:49 | 2023-12-13 18:43 | 331453.189 |  |  |  | 17041 | 331453 | 266980 |  |  | 0 | 28.4 | 0 | 5.29 | 5955.63
TS6060#1 | GG\16\021\D | GG | 16 | 21 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2023-12-09 22:16 | 2023-12-10 23:16 | 33848.8284 | [6 empty] | 33849 | 25226 | 2.52 | 0 | 0 | 6.77 | 5794
PH4100XPC#1 | GG\19\007\X2 | GG | 19 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 79.071 | 2023-12-10 12:34 | 2023-12-11 22:37 | 73759.0151 | 73759 | [7 empty] | 0 | 0 | 7.37 | 0 | 0
TS6060#1 | GG\19\008\X1 | GG | 19 | 8 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-12-10 23:16 | 2023-12-11 12:00 | 17237.6961 | [6 empty] | 17238 | 12576 | 1.26 | 0 | 0 | 12.35 | 5286
TS5500Shv | MW\53\007\D | MW | 53 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-12-11 06:06 | 2023-12-13 03:14 | 55035.8969 | [6 empty] | 55036 | 41553 | 4.82 | 0 | 0 | 6.43 | 5848
TS6060#1 | RS\34\003\B | RS | 34 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-12-11 12:00 | 2023-12-12 06:37 | 19198.935 | 19199 | [7 empty] | 0 | 0 | 2.8 | 8.86 | 5600.5
PH4100XPC#1 | GG\19\007\B | GG | 19 | 7 | B | 1 Prestrip - Thick | 100 | 76.7843 | 76.7843 | 2023-12-11 22:37 | 2023-12-12 19:47 | 45870.6517 | 45871 | [7 empty] | 0 | 0 | 4.59 | 10.32 | 5455.39
TS6060#1 | RS\36\006\X | RS | 36 | 6 | X | 1 Prestrip - Thick | 36.5873 | 36.5873 | 36.5873 | 2023-12-12 06:37 | 2023-12-22 18:43 | 254715.1574 | 254715 | [7 empty] | 0 | 0 | 20.99 | 10.97 | 5387.55
TS5500Exc | RS\34\004\X | RS | 34 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-12-12 11:45 | 2023-12-13 00:37 | 16215.1637 | [6 empty] | 16215 | 11407 | 1.14 | 0 | 0 | 12.01 | 5270
TS Fleet 5 | GG\19\007\B | GG | 19 | 7 | B | 1 Prestrip - Thick | 46.5068 | 23.2157 | 23.2157 | 2023-12-12 12:43 | 2023-12-12 19:47 | 13868.9385 | 13869 | [7 empty] | 0 | 0 | 1.39 | 10.32 | 5455.39
TS Fleet 5 | GG\19\008\X2 | GG | 19 | 8 | X2 | 1 Prestrip - Thick | 46.5068 | 0 | 46.5068 | 2023-12-12 19:47 | 2023-12-13 16:14 | 40081.3597 | 40081 | [7 empty] | 0 | 0 | 4.01 | 0 | 0
PH4100XPC#1 | GG\19\008\X2 | GG | 19 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.4932 | 2023-12-12 19:47 | 2023-12-13 17:04 | 46102.4183 | 46102 | [7 empty] | 0 | 0 | 4.61 | 0 | 0
TS5500Exc | RS\33\003\B | RS | 33 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-12-13 00:37 | 2023-12-13 11:23 | 13560.4903 | [6 empty] | 13560 | 9801 | 1.37 | 0 | 0 | 8.78 | 5607
TS5500Shv | GG\16\022\D | GG | 16 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-12-13 03:14 | 2023-12-15 06:53 | 62999.4444 | [6 empty] | 62999 | 47024 | 4.7 | 0 | 0 | 6.65 | 5803
TS5500Exc | RS\33\004\A | RS | 33 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-12-13 11:23 | 2023-12-14 06:38 | 24242.3201 | [6 empty] | 24242 | 17244 | 1.73 | 0 | 0 | 11.67 | 5367
TS Fleet 5 | CP\04\004\B | CP | 4 | 4 | B | 1 Prestrip - Thick | 45.6862 | 45.6862 | 45.6862 | 2023-12-13 16:14 | 2023-12-27 19:18 | 664557.3022 | 664557 | [7 empty] | 0 | 0 | 22.15 | 8.7 | 5598.26
PH4100XPC#1 | GG\19\008\B | GG | 19 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-12-13 17:04 | 2023-12-14 22:55 | 64662.2315 | 64662 | [7 empty] | 0 | 0 | 6.47 | 10.13 | 5495.07
DRE1 | MW\48\006\D | MW | 48 | 6 | D | 6 DL | 100 | 0 | 100 | 2023-12-13 18:43 | 2023-12-18 22:36 | 432753.4802 |  |  |  | 30777 | 432753 | 311186 |  |  | 0 | 35 | 0 | 6.43 | 5848.22
TS5500Exc | RS\33\005\X | RS | 33 | 5 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2023-12-14 06:38 | 2023-12-14 13:08 | 8183.3782 | [6 empty] | 8183 | 5764 | 0.58 | 0 | 0 | 11.96 | 5279
TS5500Exc | RS\32\003\D | RS | 32 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-12-14 13:08 | 2023-12-16 14:19 | 61960.2522 | [6 empty] | 61960 | 45963 | 4.43 | 0 | 0 | 5.08 | 5974
PH4100XPC#1 | GG\19\009\X1 | GG | 19 | 9 | X1 | 1 Prestrip - Thick | 100 | 53.7891 | 53.7891 | 2023-12-14 22:55 | 2023-12-20 22:02 | 313802.0985 | 313802 | [7 empty] | 0 | 0 | 36.09 | 13.61 | 5200.18
DRE2 | GG\18\012\B | GG | 18 | 12 | B | 6 DL | 100 | 0 | 100 | 2023-12-15 04:15 | 2023-12-17 12:58 | 190792.5225 |  |  |  |  | 190793 | 158994 |  |  | 0 | 15.96 | 0 | 9.88 | 5522.56
TS5500Shv | RS\34\003\B | RS | 34 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-12-15 06:53 | 2023-12-16 03:53 | 25607.5517 | [6 empty] | 25608 | 18505 | 2.64 | 0 | 0 | 8.86 | 5601
TS5500Shv | GG\16\023\D | GG | 16 | 23 | D | 7 PostStrip | 54.8807 | 0 | 54.8807 | 2023-12-16 03:53 | 2023-12-17 13:00 | 35484.2479 |  |  | 35484 | [5 empty] | 0 | 0 | 0 | 6.4 | 5824.91
TS5500Exc | RS\32\004\D | RS | 32 | 4 | D | 8 Coal Mining | 14.9 | 0 | 14.9 | 2023-12-16 14:19 | 2023-12-16 21:32 | 9086.2888 | [6 empty] | 9086 | 6725 | 0.67 | 0 | 0 | 5.29 | 5956
TS5500Exc | MW\48\007\A | MW | 48 | 7 | A | 1 Prestrip - Thick | 43.8541 | 43.8541 | 43.8541 | 2023-12-16 21:32 | 2023-12-22 20:57 | 126997.8036 | 126998 | [7 empty] | 0 | 0 | 12.29 | 13.03 | 5275.66
DRE2 | GG\18\011\B | GG | 18 | 11 | B | 6 DL | 100 | 0 | 100 | 2023-12-17 12:58 | 2023-12-20 05:54 | 218406.1622 |  |  |  |  | 218406 | 168005 |  |  | 0 | 16.82 | 0 | 9.36 | 5567.21
TS5500Shv | GG\18\012\B | GG | 18 | 12 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2023-12-17 13:00 | 2023-12-18 08:03 | 23248.2858 | [6 empty] | 23248 | 17068 | 1.71 | 0 | 0 | 9.88 | 5523
TS5500Shv | RS\32\004\D | RS | 32 | 4 | D | 8 Coal Mining | 1.8 | 0 | 1.8 | 2023-12-18 08:03 | 2023-12-18 08:57 | 1089.1007 | [6 empty] | 1089 | 806 | 0.08 | 0 | 0 | 5.29 | 5956
TS5500Shv | RS\32\004\D | RS | 32 | 4 | D | 8 Coal Mining | 83.3 | 0 | 83.3 | 2023-12-18 08:57 | 2023-12-20 02:31 | 50679.8391 | [6 empty] | 50680 | 37508 | 3.75 | 0 | 0 | 5.29 | 5956
DRE1 | RS\32\005\D | RS | 32 | 5 | D | 6 DL | 100 | 100 | 100 | 2023-12-18 22:36 | 2023-12-22 15:59 | 312206.8953 |  |  |  | 16052 | 312207 | 251478 |  |  | 0 | 26.75 | 0 | 5.59 | 5930.44
PH4100A | RS\33\004\B | RS | 33 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-12-19 08:31 | 2023-12-20 00:43 | 28136.3069 | 28136 | [7 empty] | 0 | 0 | 2.82 | 8.77 | 5613.84
PH4100A | RS\33\005\A | RS | 33 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-12-20 00:43 | 2023-12-24 04:58 | 174027.3341 | 174027 | [7 empty] | 0 | 0 | 17.4 | 14.21 | 5172.45
TS5500Shv | RS\33\004\B | RS | 33 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2023-12-20 02:31 | 2023-12-21 10:20 | 38794.035 | [6 empty] | 38794 | 28007 | 2.8 | 0 | 0 | 8.77 | 5614
DRE2 | GG\18\010\B | GG | 18 | 10 | B | 6 DL | 100 | 0 | 100 | 2023-12-20 05:54 | 2023-12-23 00:18 | 223397.3988 |  |  |  |  | 223397 | 186164 |  |  | 0 | 18.61 | 0 | 9.57 | 5551.44
PH4100XPC#1 | GG\19\010\X2 | GG | 19 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.3039 | 2023-12-20 22:02 | 2023-12-27 13:47 | 357560.6365 | 357561 | [7 empty] | 0 | 0 | 34.45 | 0 | 0
TS5500Shv | MW\48\006\D | MW | 48 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2023-12-21 10:20 | 2023-12-23 13:40 | 62605.6675 | [6 empty] | 62606 | 47228 | 4.72 | 0 | 0 | 6.43 | 5848
DRE1 | RS\32\006\D | RS | 32 | 6 | D | 6 DL | 100 | 100 | 100 | 2023-12-22 15:59 | 2023-12-26 06:19 | 301599.4978 |  |  |  | 11346 | 301599 | 171426 |  |  | 0 | 25.7 | 0 | 5.8 | 5911.22
TS6060#1 | GG\19\009\X1 | GG | 19 | 9 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2023-12-22 18:43 | 2023-12-23 06:50 | 16397.3902 | [6 empty] | 16397 | 11847 | 1.2 | 0 | 0 | 13.61 | 5200
TS5500Exc | RS\34\005\X | RS | 34 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2023-12-22 20:57 | 2023-12-23 09:49 | 16187.2501 | [6 empty] | 16187 | 11420 | 1.14 | 0 | 0 | 11.79 | 5298
DRE2 | GG\18\009\B | GG | 18 | 9 | B | 6 DL | 100 | 0 | 100 | 2023-12-23 00:18 | 2023-12-25 21:35 | 233051.6352 |  |  |  |  | 233052 | 194210 |  |  | 0 | 19.43 | 0 | 9.83 | 5531.6
TS6060#1 | RS\34\004\A | RS | 34 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-12-23 06:50 | 2023-12-30 15:51 | 182637.2391 | 182637 | [7 empty] | 0 | 0 | 18.29 | 11.68 | 5367.88
TS5500Exc | MW\48\007\A | MW | 48 | 7 | A | 1 Prestrip - Thick | 56.1459 | 56.1459 | 56.1459 | 2023-12-23 09:49 | 2023-12-31 01:26 | 162593.6774 | 162594 | [7 empty] | 0 | 0 | 15.74 | 13.03 | 5275.66
TS5500Shv | GG\18\011\B | GG | 18 | 11 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2023-12-23 13:40 | 2023-12-24 08:47 | 23310.0898 | [6 empty] | 23310 | 17167 | 1.72 | 0 | 0 | 9.36 | 5567
PH4100A | RS\34\005\A | RS | 34 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2023-12-24 04:58 | 2023-12-28 09:04 | 173780.2284 | 173780 | [7 empty] | 0 | 0 | 17.41 | 14.23 | 5171.82
TS5500Shv | RS\33\005\A | RS | 33 | 5 | A | 8 Coal Mining | 79.3 | 0 | 79.3 | 2023-12-24 08:47 | 2023-12-25 16:59 | 39271.291 | [6 empty] | 39271 | 27519 | 2.75 | 0 | 0 | 14.21 | 5172
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 04:36 |  | 0d 04:36 | 2023-12-25 16:59 | 2023-12-25 21:35
DRE2 | GG\18\008\B | GG | 18 | 8 | B | 6 DL | 100 | 0 | 100 | 2023-12-25 21:35 | 2023-12-28 20:50 | 239613.3446 |  |  |  |  | 239613 | 199678 |  |  | 0 | 19.97 | 0 | 10.13 | 5494.67
TS5500Shv | GG\18\009\B | GG | 18 | 9 | B | 8 Coal Mining | 24.1 | 0 | 24.1 | 2023-12-25 21:35 | 2023-12-26 07:46 | 12404.5566 | [6 empty] | 12405 | 9099 | 0.91 | 0 | 0 | 9.83 | 5532
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2023-12-26 06:19 | 2023-12-29 06:19
TS5500Shv | RS\32\006\D | RS | 32 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2023-12-26 07:46 | 2023-12-28 00:57 | 44145.5104 |  |  | 44146 | [5 empty] | 0 | 0 | 0 | 5.8 | 5911.22
PH4100XPC#1 | GG\19\009\X2 | GG | 19 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 88.0426 | 2023-12-27 13:47 | 2023-12-28 22:15 | 70336.7929 | 70337 | [7 empty] | 0 | 0 | 7.05 | 0 | 0
TS Fleet 5 | GG\19\010\B | GG | 19 | 10 | B | 1 Prestrip - Thick | 46.5068 | 46.5068 | 46.5068 | 2023-12-27 19:18 | 2023-12-28 17:22 | 43273.3565 | 43273 | [7 empty] | 0 | 0 | 4.33 | 9.7 | 5544.38
TS5500Shv | RS\32\006\D | RS | 32 | 6 | D | 8 Coal Mining | 42.7 | 0 | 42.7 | 2023-12-28 00:57 | 2023-12-28 19:35 | 22730.0574 | [6 empty] | 22730 | 16782 | 1.92 | 0 | 0 | 5.8 | 5911
PH4100A | RS\33\006\X | RS | 33 | 6 | X | 1 Prestrip - Thick | 100 | 18.6558 | 18.6558 | 2023-12-28 09:04 | 2024-01-01 | 147039.2726 | 147039 | [7 empty] | 0 | 0 | 11.92 | 12.07 | 5279.48
TS Fleet 5 | GG\19\009\X2 | GG | 19 | 9 | X2 | 1 Prestrip - Thick | 46.5068 | 0 | 11.9574 | 2023-12-28 17:22 | 2023-12-28 22:15 | 9552.7401 | 9553 | [7 empty] | 0 | 0 | 0.96 | 0 | 0
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 01:14 |  | 0d 01:14 | 2023-12-28 19:35 | 2023-12-28 20:50
DRE2 | GG\18\007\B | GG | 18 | 7 | B | 6 DL | 100 | 0 | 100 | 2023-12-28 20:50 | 2023-12-31 19:59 | 239330.6756 |  |  |  |  | 239331 | 199442 |  |  | 0 | 19.98 | 0 | 10.33 | 5453.45
TS5500Shv | GG\18\008\B | GG | 18 | 8 | B | 8 Coal Mining | 29.3 | 0 | 29.3 | 2023-12-28 20:50 | 2023-12-29 09:28 | 15411.4735 | [6 empty] | 15411 | 11275 | 1.13 | 0 | 0 | 10.13 | 5495
TS Fleet 5 | GG\19\009\B | GG | 19 | 9 | B | 1 Prestrip - Thick | 46.5068 | 46.5068 | 46.5068 | 2023-12-28 22:15 | 2023-12-29 16:35 | 35933.2817 | 35933 | [7 empty] | 0 | 0 | 3.59 | 9.87 | 5529.47
PH4100XPC#1 | GG\19\009\B | GG | 19 | 9 | B | 1 Prestrip - Thick | 100 | 53.4932 | 53.4932 | 2023-12-28 22:15 | 2023-12-29 17:20 | 41331.2122 | 41331 | [7 empty] | 0 | 0 | 4.13 | 9.87 | 5529.47
DRE1 | MW\54\004\D | MW | 54 | 4 | D | 6 DL | 100 | 79.9749 | 79.9749 | 2023-12-29 06:19 | 2024-01-01 | 229408.962 |  |  |  | 9170 | 229409 | 120647 |  |  | 0 | 33.23 | 0 | 9.31 | 5590.62
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 15:58 |  | 1d 15:58 | 2023-12-29 09:28 | 2023-12-31 01:26
TS Fleet 5 | CP\04\005\B | CP | 4 | 5 | B | 1 Prestrip - Thick | 45.4177 | 6.7871 | 6.7871 | 2023-12-29 16:35 | 2024-01-01 | 108603.9463 | 108604 | [7 empty] | 0 | 0 | 3.62 | 8.6 | 5604.54
PH4100XPC#1 | GG\19\010\B | GG | 19 | 10 | B | 1 Prestrip - Thick | 100 | 53.4932 | 53.4932 | 2023-12-29 17:20 | 2023-12-30 16:18 | 49773.9198 | 49774 | [7 empty] | 0 | 0 | 4.98 | 9.7 | 5544.38
TS6060#1 | GG\18\009\B | GG | 18 | 9 | B | 8 Coal Mining | 100 | 0 | 26.7 | 2023-12-30 15:51 | 2023-12-31 02:00 | 13747.4873 | [6 empty] | 13747 | 10085 | 1.01 | 0 | 0 | 9.83 | 5532
PH4100XPC#1 | GG\19\011\X1 | GG | 19 | 11 | X1 | 1 Prestrip - Thick | 100 | 15.8422 | 15.8422 | 2023-12-30 16:18 | 2024-01-01 | 67920.7749 | 67921 | [7 empty] | 0 | 0 | 6.1 | 14.43 | 5143.24
TS5500Exc | GG\18\009\B | GG | 18 | 9 | B | 8 Coal Mining | 100 | 0 | 1.4 | 2023-12-31 01:26 | 2023-12-31 02:00 | 711.723 | [6 empty] | 712 | 522 | 0.05 | 0 | 0 | 9.83 | 5532
TS5500Shv | MW\48\007\A | MW | 48 | 7 | A | 8 Coal Mining | 39.9 | 0 | 2.3 | 2023-12-31 01:26 | 2023-12-31 02:00 | 689.0085 | [6 empty] | 689 | 500 | 0.05 | 0 | 0 | 13.03 | 5276
TS6060#1 | GG\16\023\D | GG | 16 | 23 | D | 7 PostStrip | 45.1193 | 0 | 35.0929 | 2023-12-31 02:00 | 2024-01-01 | 22690.0587 |  |  | 22690 | [5 empty] | 0 | 0 | 0 | 6.4 | 5824.91
TS5500Exc | MW\48\008\A | MW | 48 | 8 | A | 1 Prestrip - Thick | 100 | 4.9895 | 4.9895 | 2023-12-31 02:00 | 2024-01-01 | 19473.8866 | 19474 | [7 empty] | 0 | 0 | 1.63 | 12.28 | 5337.98
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 21:59 |  | 0d 21:59 | 2023-12-31 02:00 | 2024-01-01
DRE2 | GG\18\006\B | GG | 18 | 6 | B | 6 DL | 100 | 0 | 5.1141 | 2023-12-31 19:59 | 2024-01-01 | 13510.6216 |  |  |  |  | 13511 | 10393 |  |  | 0 | 20.29 | 0 | 9.77 | 5473.51
| EOP 76 : 2023 | EOP 76 : 2023 | [7 empty] | 2024-01-01 | 2024-01-01 |  | 65165681 |  | 966443 | 1919476 | 57132000 | 36502238 | 13000000 | 9528071 | 992.03 | 0 | 6474.09 | 8.84 | 5622.71
TS Fleet 5 | CP\04\005\B | CP | 4 | 5 | B | 1 Prestrip - Thick | 45.4177 | 38.6306 | 38.6306 | 2024-01-01 | 2024-01-14 03:22 | 618144.3673 | 618144 | [7 empty] | 0 | 0 | 20.62 | 8.6 | 5604.54
DRE1 | MW\54\004\D | MW | 54 | 4 | D | 6 DL | 100 | 20.0251 | 20.0251 | 2024-01-01 | 2024-01-01 16:53 | 57442.1862 |  |  |  | 2296 | 57442 | 30209 |  |  | 0 | 33.23 | 0 | 9.31 | 5590.62
PH4100A | RS\33\006\X | RS | 33 | 6 | X | 1 Prestrip - Thick | 100 | 10.2483 | 10.2483 | 2024-01-01 | 2024-01-02 23:44 | 80773.639 | 80774 | [7 empty] | 0 | 0 | 6.55 | 12.07 | 5279.48
DRE2 | GG\18\006\B | GG | 18 | 6 | B | 6 DL | 100 | 0 | 94.8859 | 2024-01-01 | 2024-01-04 11:25 | 250674.6824 |  |  |  |  | 250675 | 192827 |  |  | 0 | 20.29 | 0 | 9.77 | 5473.51
PH4100XPC#1 | GG\19\011\X1 | GG | 19 | 11 | X1 | 1 Prestrip - Thick | 100 | 37.3812 | 37.3812 | 2024-01-01 | 2024-01-03 23:34 | 160266.087 | 160266 | [7 empty] | 0 | 0 | 14.39 | 14.43 | 5143.24
TS6060#1 | GG\16\023\D | GG | 16 | 23 | D | 7 PostStrip | 45.1193 | 0 | 10.0264 | 2024-01-01 | 2024-01-01 06:16 | 6482.8133 |  |  | 6483 | [5 empty] | 0 | 0 | 0 | 6.4 | 5824.91
TS5500Exc | MW\48\008\A | MW | 48 | 8 | A | 1 Prestrip - Thick | 100 | 95.0105 | 95.0105 | 2024-01-01 | 2024-01-18 10:44 | 370822.7545 | 370823 | [7 empty] | 0 | 0 | 31.09 | 12.28 | 5337.98
TS5500Shv | MW\48\007\A | MW | 48 | 7 | A | 8 Coal Mining | 39.9 | 0 | 37.6 | 2024-01-01 | 2024-01-01 09:12 | 11220.0674 | [6 empty] | 11220 | 8136 | 0.81 | 0 | 0 | 13.03 | 5276
TS6060#1 | GG\18\009\B | GG | 18 | 9 | B | 8 Coal Mining | 100 | 0 | 47.8 | 2024-01-01 06:16 | 2024-01-02 00:29 | 24635.48 | [6 empty] | 24635 | 18072 | 1.81 | 0 | 0 | 9.83 | 5532
TS5500Shv | GG\16\023\D | GG | 16 | 23 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-01-01 09:12 | 2024-01-02 16:27 | 38124.3329 | [6 empty] | 38124 | 28661 | 2.22 | 0 | 0 | 6.4 | 5825
DRE1 | MW\54\005\D | MW | 54 | 5 | D | 6 DL | 100 | 0 | 100 | 2024-01-01 16:53 | 2024-01-07 01:45 | 438109.6841 |  |  |  | 31158 | 438110 | 315037 |  |  | 0 | 35 | 0 | 9.28 | 5597.21
TS6060#1 | GG\16\023\D | GG | 16 | 23 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-01-02 00:29 | 2024-01-03 07:45 | 42313.82 | [6 empty] | 42314 | 31810 | 2.46 | 0 | 0 | 6.4 | 5825
TS5500Shv | GG\18\007\B | GG | 18 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-01-02 16:27 | 2024-01-04 10:41 | 51492.7069 | [6 empty] | 51493 | 37656 | 3.77 | 0 | 0 | 10.33 | 5453
PH4100A | RS\34\006\X | RS | 34 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-01-02 23:44 | 2024-01-21 17:31 | 759952.2435 | 759952 | [7 empty] | 0 | 0 | 62.01 | 11.76 | 5310.59
TS6060#1 | GG\18\012\B | GG | 18 | 12 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-01-03 07:45 | 2024-01-04 02:48 | 25803.0425 | [6 empty] | 25803 | 18943 | 1.9 | 0 | 0 | 9.88 | 5523
PH4100XPC#1 | GG\19\012\X1 | GG | 19 | 12 | X1 | 1 Prestrip - Thick | 100 | 52.9391 | 52.9391 | 2024-01-03 23:34 | 2024-01-07 14:06 | 191562.8631 | 191563 | [7 empty] | 0 | 0 | 18.89 | 14.17 | 5164.72
TS6060#1 | GG\18\010\B | GG | 18 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-01-04 02:48 | 2024-01-05 15:41 | 49902.5237 | [6 empty] | 49903 | 36704 | 3.67 | 0 | 0 | 9.57 | 5551
TS5500Shv | GG\19\011\X1 | GG | 19 | 11 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-01-04 10:41 | 2024-01-05 01:06 | 17582.2384 | [6 empty] | 17582 | 12607 | 1.28 | 0 | 0 | 14.43 | 5143
DRE2 | GG\18\005\B | GG | 18 | 5 | B | 6 DL | 100 | 0 | 100 | 2024-01-04 11:25 | 2024-01-08 03:43 | 265350.5052 |  |  |  |  | 265351 | 204116 |  |  | 0 | 20.32 | 0 | 9.57 | 5482.88
TS5500Shv | GG\19\011\X2 | GG | 19 | 11 | X2 | 1 Prestrip - Thick | 64.6102 | 0 | 64.6102 | 2024-01-05 01:06 | 2024-01-06 21:27 | 47545.3627 | 47545 | [7 empty] | 0 | 0 | 4.8 | 0 | 0
TS6060#1 | GG\18\011\B | GG | 18 | 11 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-01-05 15:41 | 2024-01-06 10:48 | 25871.6381 | [6 empty] | 25872 | 19054 | 1.91 | 0 | 0 | 9.36 | 5567
TS6060#1 | GG\18\008\B | GG | 18 | 8 | B | 8 Coal Mining | 70.7 | 0 | 70.7 | 2024-01-06 10:48 | 2024-01-07 14:14 | 37144.8252 | [6 empty] | 37145 | 27175 | 2.72 | 0 | 0 | 10.13 | 5495
TS5500Shv | GG\18\006\B | GG | 18 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-01-06 21:27 | 2024-01-08 13:26 | 48754.1261 | [6 empty] | 48754 | 35828 | 3.58 | 0 | 0 | 9.77 | 5474
DRE1 | MW\54\006\D | MW | 54 | 6 | D | 6 DL | 100 | 0 | 100 | 2024-01-07 01:45 | 2024-01-13 09:15 | 515118.8981 |  |  |  | 36634 | 515119 | 370413 |  |  | 0 | 35 | 0 | 7.94 | 5715.31
PH4100XPC#1 | GG\19\011\X2 | GG | 19 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 35.3898 | 2024-01-07 14:06 | 2024-01-08 01:36 | 26042.6203 | 26043 | [7 empty] | 0 | 0 | 2.63 | 0 | 0
TS6060#1 | RS\38\003\X | RS | 38 | 3 | X | 1 Prestrip - Thick | 37.5185 | 37.5185 | 37.5185 | 2024-01-07 14:14 | 2024-01-11 17:13 | 98963.2469 | 98963 | [7 empty] | 0 | 0 | 13.4 | 11.99 | 5273.4
PH4100XPC#1 | GG\19\011\B | GG | 19 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-01-08 01:36 | 2024-01-10 08:23 | 123999.1997 | 123999 | [7 empty] | 0 | 0 | 12.45 | 9.51 | 5557.94
DRE2 | GG\18\004\B | GG | 18 | 4 | B | 6 DL | 100 | 0 | 100 | 2024-01-08 03:43 | 2024-01-11 00:31 | 206763.2615 |  |  |  |  | 206763 | 172303 |  |  | 0 | 17 | 0 | 9.49 | 5503.41
TS5500Shv | GG\19\012\X1 | GG | 19 | 12 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-01-08 13:26 | 2024-01-09 02:57 | 16467.9436 | [6 empty] | 16468 | 11842 | 1.21 | 0 | 0 | 14.17 | 5165
TS5500Shv | MW\54\004\D | MW | 54 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2024-01-09 02:57 | 2024-01-10 05:48 | 28783.6885 |  |  | 28784 | [5 empty] | 0 | 0 | 0 | 9.31 | 5590.62
TS5500Shv | MW\54\004\D | MW | 54 | 4 | D | 8 Coal Mining | 55.4 | 0 | 55.4 | 2024-01-10 05:48 | 2024-01-10 19:11 | 16336.9994 | [6 empty] | 16337 | 12075 | 2.18 | 0 | 0 | 9.31 | 5591
PH4100XPC#1 | GG\19\012\X2 | GG | 19 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2024-01-10 08:23 | 2024-01-11 17:17 | 74455.198 | 74455 | [7 empty] | 0 | 0 | 7.59 | 0 | 0
TS5500Shv | GG\18\005\B | GG | 18 | 5 | B | 8 Coal Mining | 78.7 | 0 | 78.7 | 2024-01-10 19:11 | 2024-01-12 01:30 | 36949.7144 | [6 empty] | 36950 | 27203 | 2.72 | 0 | 0 | 9.57 | 5483
DRE2 | GG\17\012\D | GG | 17 | 12 | D | 6 DL | 100 | 100 | 100 | 2024-01-11 00:31 | 2024-01-18 03:06 | 512558.0752 |  |  |  | 11934 | 512558 | 226743 |  |  | 0 | 23.85 | 0 | 6.73 | 5794.84
TS6060#1 | GG\18\005\B | GG | 18 | 5 | B | 8 Coal Mining | 21.3 | 0 | 21.3 | 2024-01-11 17:13 | 2024-01-12 00:36 | 9994.2193 | [6 empty] | 9994 | 7358 | 0.74 | 0 | 0 | 9.57 | 5483
PH4100XPC#1 | GG\19\012\B | GG | 19 | 12 | B | 1 Prestrip - Thick | 100 | 97.879 | 97.879 | 2024-01-11 17:17 | 2024-01-14 04:52 | 134859.5523 | 134860 | [7 empty] | 0 | 0 | 13.56 | 10.11 | 5503.65
TS6060#1 | GG\18\004\B | GG | 18 | 4 | B | 8 Coal Mining | 13.8 | 0 | 13.8 | 2024-01-12 00:36 | 2024-01-12 05:33 | 6703.3751 | [6 empty] | 6703 | 4937 | 0.49 | 0 | 0 | 9.49 | 5503
TS5500Shv | GG\18\004\B | GG | 18 | 4 | B | 8 Coal Mining | 86.2 | 0 | 86.2 | 2024-01-12 01:30 | 2024-01-13 11:56 | 41997.7521 | [6 empty] | 41998 | 30928 | 3.08 | 0 | 0 | 9.49 | 5503
TS6060#1 | RS\38\004\X | RS | 38 | 4 | X | 1 Prestrip - Thick | 61.5725 | 61.5725 | 61.5725 | 2024-01-12 05:33 | 2024-01-23 05:47 | 265468.1512 | 265468 | [7 empty] | 0 | 0 | 26.88 | 11.69 | 5309.09
DRE1 | RS\33\003\D | RS | 33 | 3 | D | 6 DL | 100 | 100 | 100 | 2024-01-13 09:15 | 2024-01-17 07:12 | 319414.0831 |  |  |  | 16422 | 319414 | 257283 |  |  | 0 | 26.87 | 0 | 5.06 | 5975.7
TS5500Shv | GG\21\004\X1 | GG | 21 | 4 | X1 | 1 Prestrip - Thick | 1.6798 | 1.6798 | 1.6798 | 2024-01-13 11:56 | 2024-01-14 14:27 | 28408.1558 | 28408 | [7 empty] | 0 | 0 | 1.81 | 10.65 | 5302.15
TS Fleet 5 | GG\19\012\B | GG | 19 | 12 | B | 1 Prestrip - Thick | 46.5068 | 2.121 | 2.121 | 2024-01-14 03:22 | 2024-01-14 04:52 | 2922.3103 | 2922 | [7 empty] | 0 | 0 | 0.29 | 10.11 | 5503.65
TS Fleet 5 | GG\21\004\X1 | GG | 21 | 4 | X1 | 1 Prestrip - Thick | 43.9819 | 43.9819 | 43.9819 | 2024-01-14 04:52 | 2024-01-30 00:22 | 743820.6624 | 743821 | [7 empty] | 0 | 0 | 47.4 | 10.65 | 5302.15
PH4100XPC#1 | GG\19\013\X1 | GG | 19 | 13 | X1 | 1 Prestrip - Thick | 100 | 52.631 | 52.631 | 2024-01-14 04:52 | 2024-01-19 00:38 | 253143.8296 | 253144 | [7 empty] | 0 | 0 | 14.54 | 14.27 | 5158.03
TS5500Shv | GG\21\006\X1 | GG | 21 | 6 | X1 | 1 Prestrip - Thick | 8.7054 | 8.7054 | 8.7054 | 2024-01-14 14:27 | 2024-01-17 10:07 | 71983.0297 | 71983 | [7 empty] | 0 | 0 | 6.99 | 11.11 | 5302.87
DRE1 | RS\33\004\D | RS | 33 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-01-17 07:12 | 2024-01-21 08:20 | 330276.4939 |  |  |  | 16981 | 330276 | 266032 |  |  | 0 | 28.31 | 0 | 5.29 | 5955.51
TS5500Shv | RS\33\003\D | RS | 33 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-01-17 10:07 | 2024-01-18 10:50 | 30123.6534 | [6 empty] | 30124 | 22346 | 2.18 | 0 | 0 | 5.06 | 5976
DRE2 | GG\17\011\D | GG | 17 | 11 | D | 6 DL | 100 | 100 | 100 | 2024-01-18 03:06 | 2024-01-25 04:38 | 509438.4096 |  |  |  | 9245 | 509438 | 221872 |  |  | 0 | 23.1 | 0 | 6.38 | 5825.39
TS5500Exc | RS\33\005\A | RS | 33 | 5 | A | 8 Coal Mining | 20.7 | 0 | 20.7 | 2024-01-18 10:44 | 2024-01-18 18:51 | 10224.6476 | [6 empty] | 10225 | 7165 | 0.72 | 0 | 0 | 14.21 | 5172
TS5500Shv | GG\17\012\D | GG | 17 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-01-18 10:50 | 2024-01-20 13:28 | 61747.6209 | [6 empty] | 61748 | 46125 | 4.61 | 0 | 0 | 6.73 | 5795
TS5500Exc | RS\33\006\X | RS | 33 | 6 | X | 8 Coal Mining | 100 | 0 | 100 | 2024-01-18 18:51 | 2024-01-19 10:27 | 19643.48 | [6 empty] | 19643 | 13842 | 1.16 | 0 | 0 | 12.07 | 5279
PH4100XPC#1 | GG\19\018\X2 | GG | 19 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 52.7361 | 2024-01-19 00:38 | 2024-01-21 15:57 | 139022.0069 | 139022 | [7 empty] | 0 | 0 | 13.99 | 0 | 0
TS5500Exc | RS\34\004\A | RS | 34 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-01-19 10:27 | 2024-01-21 00:03 | 47353.2657 | [6 empty] | 47353 | 33708 | 3.38 | 0 | 0 | 11.68 | 5368
TS5500Shv | GG\19\013\X1 | GG | 19 | 13 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-01-20 13:28 | 2024-01-21 08:15 | 22914.4288 | [6 empty] | 22914 | 16482 | 1 | 0 | 0 | 14.27 | 5158
TS5500Exc | MW\48\007\A | MW | 48 | 7 | A | 8 Coal Mining | 60.1 | 0 | 60.1 | 2024-01-21 00:03 | 2024-01-21 14:19 | 17966.3281 | [6 empty] | 17966 | 13028 | 1.29 | 0 | 0 | 13.03 | 5276
TS5500Shv | GG\19\013\X2 | GG | 19 | 13 | X2 | 1 Prestrip - Thick | 24.5694 | 0 | 24.5694 | 2024-01-21 08:15 | 2024-01-22 14:20 | 32235.5906 | 32236 | [7 empty] | 0 | 0 | 1.97 | 0 | 0
DRE1 | MW\55\004\D | MW | 55 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-01-21 08:20 | 2024-01-24 00:02 | 216557.0474 |  |  |  | 8691 | 216557 | 113985 |  |  | 0 | 32.39 | 0 | 9.38 | 5581.11
TS5500Exc | RS\32\005\D | RS | 32 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-01-21 14:19 | 2024-01-23 15:57 | 62520.3522 | [6 empty] | 62520 | 46202 | 4.62 | 0 | 0 | 5.59 | 5930
PH4100XPC#1 | GG\19\013\X2 | GG | 19 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 75.4306 | 2024-01-21 15:57 | 2024-01-23 11:40 | 98966.4044 | 98966 | [7 empty] | 0 | 0 | 6.04 | 0 | 0
PH4100A | RS\33\005\B | RS | 33 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-01-21 17:31 | 2024-01-22 12:03 | 32179.1492 | 32179 | [7 empty] | 0 | 0 | 3.22 | 8.81 | 5615.29
PH4100A | RS\33\006\A | RS | 33 | 6 | A | 1 Prestrip - Thick | 100 | 69.2349 | 69.2349 | 2024-01-22 12:03 | 2024-01-25 10:18 | 121930.7632 | 121931 | [7 empty] | 0 | 0 | 11.51 | 17.2 | 4942.42
TS5500Shv | RS\33\005\B | RS | 33 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-01-22 14:20 | 2024-01-23 23:30 | 40456.3448 | [6 empty] | 40456 | 29132 | 2.91 | 0 | 0 | 8.81 | 5615
TS6060#1 | RS\33\006\A | RS | 33 | 6 | A | 1 Prestrip - Thick | 100 | 30.7651 | 30.7651 | 2024-01-23 05:47 | 2024-01-25 10:18 | 54181.0359 | 54181 | [7 empty] | 0 | 0 | 5.11 | 17.2 | 4942.42
PH4100XPC#1 | GG\19\013\B | GG | 19 | 13 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-01-23 11:40 | 2024-01-27 18:45 | 233316.2038 | 233316 | [7 empty] | 0 | 0 | 15.14 | 11.24 | 5407.4
TS5500Exc | RS\32\006\D | RS | 32 | 6 | D | 8 Coal Mining | 57.3 | 0 | 57.3 | 2024-01-23 15:57 | 2024-01-24 16:10 | 30501.7903 | [6 empty] | 30502 | 22520 | 2.57 | 0 | 0 | 5.8 | 5911
TS5500Shv | RS\34\006\X | RS | 34 | 6 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-01-23 23:30 | 2024-01-24 07:13 | 9406.1119 | [6 empty] | 9406 | 6647 | 0.56 | 0 | 0 | 11.76 | 5311
DRE1 | RS\33\005\D | RS | 33 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-01-24 00:02 | 2024-01-27 21:11 | 316692.5773 |  |  |  | 16282 | 316693 | 255091 |  |  | 0 | 27.14 | 0 | 5.58 | 5931.08
TS5500Shv | RS\33\004\D | RS | 33 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-01-24 07:13 | 2024-01-25 07:42 | 29857.9247 | [6 empty] | 29858 | 22115 | 2.21 | 0 | 0 | 5.29 | 5956
TS5500Exc | RS\34\005\A | RS | 34 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-01-24 16:10 | 2024-01-26 07:07 | 49073.4233 | [6 empty] | 49073 | 34404 | 3.45 | 0 | 0 | 14.23 | 5172
DRE2 | GG\17\010\D | GG | 17 | 10 | D | 6 DL | 100 | 100 | 100 | 2024-01-25 04:38 | 2024-01-31 13:56 | 460670.8149 |  |  |  | 10726 | 460671 | 203789 |  |  | 0 | 21.46 | 0 | 6.2 | 5841.85
TS5500Shv | MW\55\004\D | MW | 55 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2024-01-25 07:42 | 2024-01-26 04:23 | 22170.8741 |  |  | 22171 | [5 empty] | 0 | 0 | 0 | 9.38 | 5581.11
PH4100A | RS\35\003\A | RS | 35 | 3 | A | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2024-01-25 10:18 | 2024-01-27 06:08 | 76112.6186 | 76113 | [7 empty] | 0 | 0 | 12.21 | 10.94 | 5423.94
TS6060#1 | RS\34\004\B | RS | 34 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-01-25 10:18 | 2024-01-26 13:54 | 28476.9756 | 28477 | [7 empty] | 0 | 0 | 2.85 | 8.8 | 5611.78
TS5500Shv | RS\33\006\A | RS | 33 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-01-26 04:23 | 2024-01-27 22:57 | 51908.9427 | [6 empty] | 51909 | 35825 | 3.43 | 0 | 0 | 17.2 | 4942
TS5500Exc | MW\54\004\D | MW | 54 | 4 | D | 8 Coal Mining | 44.6 | 0 | 44.6 | 2024-01-26 07:07 | 2024-01-26 17:33 | 13131.2161 | [6 empty] | 13131 | 9705 | 1.75 | 0 | 0 | 9.31 | 5591
TS6060#1 | RS\34\005\B | RS | 34 | 5 | B | 1 Prestrip - Thick | 22.6943 | 22.6943 | 22.6943 | 2024-01-26 13:54 | 2024-01-26 21:06 | 7436.3468 | 7436 | [7 empty] | 0 | 0 | 0.74 | 8.86 | 5612.28
TS5500Exc | RS\34\004\B | RS | 34 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-01-26 17:33 | 2024-01-28 00:23 | 38853.1813 | [6 empty] | 38853 | 28050 | 2.81 | 0 | 0 | 8.8 | 5612
TS6060#1 | GG\17\011\D | GG | 17 | 11 | D | 8 Coal Mining | 60.1 | 0 | 60.1 | 2024-01-26 21:06 | 2024-01-28 00:19 | 36839.2795 | [6 empty] | 36839 | 27562 | 2.76 | 0 | 0 | 6.38 | 5825
PH4100A | RS\35\004\A | RS | 35 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-01-27 06:08 | 2024-01-31 14:59 | 182018.9759 | 182019 | [7 empty] | 0 | 0 | 18.22 | 11.77 | 5361.23
PH4100XPC#1 | GG\19\018\B | GG | 19 | 18 | B | 1 Prestrip - Thick | 100 | 92.9762 | 92.9762 | 2024-01-27 18:45 | 2024-01-30 05:29 | 132949.552 | 132950 | [7 empty] | 0 | 0 | 13.29 | 11.53 | 5390.12
DRE1 | MW\55\005\D | MW | 55 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-01-27 21:11 | 2024-02-01 17:46 | 396405.65 |  |  |  | 22624 | 396406 | 300577 |  |  | 0 | 31.86 | 0 | 9.29 | 5595.82
TS5500Shv | MW\55\004\D | MW | 55 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-01-27 22:57 | 2024-01-28 15:45 | 20479.9769 | [6 empty] | 20480 | 15131 | 3.57 | 0 | 0 | 9.38 | 5581
TS6060#1 | RS\38\005\X | RS | 38 | 5 | X | 1 Prestrip - Thick | 74.546 | 74.546 | 74.546 | 2024-01-28 00:19 | 2024-02-11 03:20 | 341910.7064 | 341911 | [7 empty] | 0 | 0 | 34.73 | 11.11 | 5369.03
TS5500Exc | RS\34\006\X | RS | 34 | 6 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-01-28 00:23 | 2024-01-28 08:06 | 9716.2035 | [6 empty] | 9716 | 6866 | 0.58 | 0 | 0 | 11.76 | 5311
TS5500Exc | RS\35\003\A | RS | 35 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-01-28 08:06 | 2024-01-29 09:05 | 31472.0799 | [6 empty] | 31472 | 22526 | 3.26 | 0 | 0 | 10.94 | 5424
TS5500Shv | GG\17\011\D | GG | 17 | 11 | D | 8 Coal Mining | 39.9 | 0 | 39.9 | 2024-01-28 15:45 | 2024-01-29 11:47 | 24426.8734 | [6 empty] | 24427 | 18276 | 1.83 | 0 | 0 | 6.38 | 5825
TS5500Exc | RS\33\003\D | RS | 33 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-01-29 09:05 | 2024-01-30 09:48 | 31116.7408 | [6 empty] | 31117 | 23083 | 2.25 | 0 | 0 | 5.06 | 5976
TS5500Shv | GG\21\019\B | GG | 21 | 19 | B | 1 Prestrip - Thick | 10.5516 | 10.5516 | 10.5516 | 2024-01-29 11:47 | 2024-01-30 18:17 | 32483.5564 | 32484 | [7 empty] | 0 | 0 | 3.29 | 12.76 | 5308.58
TS Fleet 5 | GG\19\018\B | GG | 19 | 18 | B | 1 Prestrip - Thick | 46.5068 | 7.0238 | 7.0238 | 2024-01-30 00:22 | 2024-01-30 05:29 | 10043.5459 | 10044 | [7 empty] | 0 | 0 | 1 | 11.53 | 5390.12
TS Fleet 5 | GG\21\005\X1 | GG | 21 | 5 | X1 | 1 Prestrip - Thick | 45.097 | 45.097 | 45.097 | 2024-01-30 05:29 | 2024-02-07 12:35 | 390223.2763 | 390223 | [7 empty] | 0 | 0 | 35.46 | 10.54 | 5309.19
PH4100XPC#1 | GG\19\019\X2 | GG | 19 | 19 | X2 | 1 Prestrip - Thick | 100 | 0 | 52.9988 | 2024-01-30 05:29 | 2024-02-01 05:35 | 106709.3338 | 106709 | [7 empty] | 0 | 0 | 11.23 | 0 | 0
TS5500Exc | RS\33\004\D | RS | 33 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-01-30 09:48 | 2024-01-31 10:17 | 30842.2519 | [6 empty] | 30842 | 22844 | 2.28 | 0 | 0 | 5.29 | 5956
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 20:43 |  | 0d 20:43 | 2024-01-30 18:17 | 2024-01-31 14:59
TS5500Exc | RS\33\005\D | RS | 33 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-01-31 10:17 | 2024-02-02 11:24 | 61879.5994 | [6 empty] | 61880 | 45763 | 4.58 | 0 | 0 | 5.58 | 5931
DRE2 | GG\17\009\D | GG | 17 | 9 | D | 6 DL | 100 | 100 | 100 | 2024-01-31 13:56 | 2024-02-06 17:17 | 442773.9835 |  |  |  | 10309 | 442774 | 195872 |  |  | 0 | 20.62 | 0 | 6.34 | 5829.54
PH4100A | RS\33\006\B | RS | 33 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-01-31 14:59 | 2024-02-01 12:08 | 36711.1896 | 36711 | [7 empty] | 0 | 0 | 3.54 | 8.96 | 5604.01
TS5500Shv | RS\35\004\A | RS | 35 | 4 | A | 8 Coal Mining | 42.2 | 0 | 42.2 | 2024-01-31 14:59 | 2024-02-01 07:18 | 19885.5592 | [6 empty] | 19886 | 14145 | 1.42 | 0 | 0 | 11.77 | 5361
PH4100XPC#1 | GG\19\019\B | GG | 19 | 19 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-01 05:35 | 2024-02-03 09:50 | 118304.5189 | 118305 | [7 empty] | 0 | 0 | 11.76 | 12.44 | 5334.94
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 04:50 |  | 0d 04:50 | 2024-02-01 07:18 | 2024-02-01 12:08
PH4100A | RS\34\005\B | RS | 34 | 5 | B | 1 Prestrip - Thick | 100 | 77.3057 | 77.3057 | 2024-02-01 12:08 | 2024-02-02 02:43 | 25331.1678 | 25331 | [7 empty] | 0 | 0 | 2.54 | 8.86 | 5612.28
TS5500Shv | RS\33\006\B | RS | 33 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-02-01 12:08 | 2024-02-02 22:45 | 42209.2037 | [6 empty] | 42209 | 30353 | 2.94 | 0 | 0 | 8.96 | 5604
DRE1 | MW\55\006\D | MW | 55 | 6 | D | 6 DL | 100 | 0 | 100 | 2024-02-01 17:46 | 2024-02-07 03:51 | 442271.4297 |  |  |  | 31454 | 442271 | 318030 |  |  | 0 | 35 | 0 | 8.01 | 5708.93
PH4100A | RS\35\005\A | RS | 35 | 5 | A | 1 Prestrip - Thick | 100 | 67.1367 | 67.1367 | 2024-02-02 02:43 | 2024-02-04 21:50 | 116493.3303 | 116493 | [7 empty] | 0 | 0 | 11.67 | 14.36 | 5162.71
TS5500Exc | RS\35\004\A | RS | 35 | 4 | A | 8 Coal Mining | 57.8 | 0 | 57.8 | 2024-02-02 11:24 | 2024-02-03 09:02 | 27236.8841 | [6 empty] | 27237 | 19375 | 1.94 | 0 | 0 | 11.77 | 5361
TS5500Shv | MW\55\005\D | MW | 55 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-02-02 22:45 | 2024-02-04 23:55 | 59964.1569 | [6 empty] | 59964 | 44374 | 4.44 | 0 | 0 | 9.29 | 5596
TS5500Exc | RS\34\005\B | RS | 34 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-02-03 09:02 | 2024-02-04 16:58 | 40230.7003 | [6 empty] | 40231 | 28989 | 2.9 | 0 | 0 | 8.86 | 5612
PH4100XPC#1 | GG\19\020\B | GG | 19 | 20 | B | 1 Prestrip - Thick | 100 | 54.6418 | 54.6418 | 2024-02-03 09:50 | 2024-02-06 12:17 | 176493.809 | 176494 | [7 empty] | 0 | 0 | 18.36 | 15.16 | 5134.48
TS5500Exc | MW\48\007\B | MW | 48 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-04 16:58 | 2024-02-06 01:05 | 28400.2263 | 28400 | [7 empty] | 0 | 0 | 2.83 | 9.79 | 5517.74
PH4100A | RS\34\006\A | RS | 34 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-04 21:50 | 2024-02-09 02:44 | 175180.9945 | 175181 | [7 empty] | 0 | 0 | 16.69 | 16.74 | 4979.87
TS5500Shv | RS\35\005\A | RS | 35 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-02-04 23:55 | 2024-02-05 19:35 | 23971.3444 | [6 empty] | 23971 | 16805 | 1.68 | 0 | 0 | 14.36 | 5163
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 08:16 |  | 1d 08:16 | 2024-02-05 19:35 | 2024-02-07 03:51
TS5500Exc | RS\35\005\A | RS | 35 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-02-06 01:05 | 2024-02-06 20:44 | 24761.6085 | [6 empty] | 24762 | 17359 | 1.74 | 0 | 0 | 14.36 | 5163
PH4100XPC#1 | GG\19\021\B | GG | 19 | 21 | B | 1 Prestrip - Thick | 100 | 54.3638 | 54.3638 | 2024-02-06 12:17 | 2024-02-09 19:57 | 186730.6692 | 186731 | [7 empty] | 0 | 0 | 20.82 | 17.56 | 4972.43
DRE2 | GG\17\008\D | GG | 17 | 8 | D | 6 DL | 100 | 100 | 100 | 2024-02-06 17:17 | 2024-02-12 16:38 | 430791.5974 |  |  |  | 10030 | 430792 | 190571 |  |  | 0 | 20.06 | 0 | 6.51 | 5814.24
TS5500Exc | MW\48\007\B | MW | 48 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-02-06 20:44 | 2024-02-07 23:28 | 33669.2973 | [6 empty] | 33669 | 24812 | 2.48 | 0 | 0 | 9.79 | 5518
DRE1 | RS\33\006\D | RS | 33 | 6 | D | 6 DL | 100 | 100 | 100 | 2024-02-07 03:51 | 2024-02-10 19:38 | 298472.7869 |  |  |  | 11225 | 298473 | 169638 |  |  | 0 | 25.72 | 0 | 5.78 | 5912.61
TS5500Shv | MW\55\006\D | MW | 55 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-02-07 03:51 | 2024-02-08 04:43 | 30333.4552 | [6 empty] | 30333 | 22646 | 2.26 | 0 | 0 | 8.01 | 5709
TS Fleet 5 | GG\21\006\X1 | GG | 21 | 6 | X1 | 1 Prestrip - Thick | 41.715 | 41.715 | 41.715 | 2024-02-07 12:35 | 2024-02-14 20:34 | 344932.9831 | 344933 | [7 empty] | 0 | 0 | 33.47 | 11.11 | 5302.87
TS5500Exc | MW\48\008\A | MW | 48 | 8 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-02-07 23:28 | 2024-02-09 18:21 | 54004.2405 | [6 empty] | 54004 | 39336 | 3.4 | 0 | 0 | 12.28 | 5338
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 22:01 |  | 0d 22:01 | 2024-02-08 04:43 | 2024-02-09 02:44
PH4100A | RS\35\006\A | RS | 35 | 6 | A | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2024-02-09 02:44 | 2024-02-11 17:55 | 109680.998 | 109681 | [7 empty] | 0 | 0 | 10.51 | 16.55 | 4995.91
TS5500Shv | RS\34\006\A | RS | 34 | 6 | A | 8 Coal Mining | 38.6 | 0 | 38.6 | 2024-02-09 02:44 | 2024-02-09 19:07 | 19978.0922 | [6 empty] | 19978 | 13826 | 1.34 | 0 | 0 | 16.74 | 4980
TS5500Exc | RS\34\006\A | RS | 34 | 6 | A | 8 Coal Mining | 61.4 | 0 | 61.4 | 2024-02-09 18:21 | 2024-02-10 19:33 | 31755.7516 | [6 empty] | 31756 | 21977 | 2.13 | 0 | 0 | 16.74 | 4980
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 00:31 |  | 1d 00:31 | 2024-02-09 19:07 | 2024-02-10 19:38
PH4100XPC#1 | GG\19\022\B | GG | 19 | 22 | B | 1 Prestrip - Thick | 100 | 53.4409 | 53.4409 | 2024-02-09 19:57 | 2024-02-12 11:45 | 144116.2788 | 144116 | [7 empty] | 0 | 0 | 15.56 | 19.34 | 4827.88
TS5500Exc | MW\48\008\B | MW | 48 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-10 19:33 | 2024-02-12 09:46 | 33790.9228 | 33791 | [7 empty] | 0 | 0 | 2.93 | 9.42 | 5549.64
DRE1 | MW\48\007\D | MW | 48 | 7 | D | 6 DL | 100 | 100 | 100 | 2024-02-10 19:38 | 2024-02-15 01:00 | 344638.4561 |  |  |  | 17719 | 344638 | 277601 |  |  | 0 | 29.54 | 0 | 5.77 | 5907.19
TS5500Shv | RS\33\006\D | RS | 33 | 6 | D | 7 PostStrip | 79.5285 | 0 | 79.5285 | 2024-02-10 19:38 | 2024-02-12 04:01 | 34708.4148 |  |  | 34708 | [5 empty] | 0 | 0 | 0 | 5.78 | 5912.61
TS6060#1 | RS\35\003\B | RS | 35 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-11 03:20 | 2024-02-11 22:49 | 20113.7252 | 20114 | [7 empty] | 0 | 0 | 2.84 | 8.9 | 5595.65
PH4100A | RS\36\003\X | RS | 36 | 3 | X | 1 Prestrip - Thick | 100 | 88.0065 | 88.0065 | 2024-02-11 17:55 | 2024-02-16 15:42 | 196864.0742 | 196864 | [7 empty] | 0 | 0 | 32.89 | 12.07 | 5264.48
TS6060#1 | RS\34\006\B | RS | 34 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-11 22:49 | 2024-02-13 11:12 | 37531.4093 | 37531 | [7 empty] | 0 | 0 | 3.65 | 9.01 | 5600.29
TS5500Shv | RS\35\003\B | RS | 35 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-02-12 04:01 | 2024-02-12 14:47 | 13143.5864 | [6 empty] | 13144 | 9499 | 1.31 | 0 | 0 | 8.9 | 5596
TS5500Exc | RS\35\003\B | RS | 35 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-02-12 09:46 | 2024-02-12 20:33 | 13576.8914 | [6 empty] | 13577 | 9812 | 1.35 | 0 | 0 | 8.9 | 5596
PH4100XPC#1 | GG\19\023\B | GG | 19 | 23 | B | 1 Prestrip - Thick | 100 | 48.2536 | 48.2536 | 2024-02-12 11:45 | 2024-02-15 23:49 | 196190.3543 | 196190 | [7 empty] | 0 | 0 | 17.26 | 0 | 0
TS5500Shv | RS\35\006\A | RS | 35 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-02-12 14:47 | 2024-02-13 11:33 | 25319.9116 | [6 empty] | 25320 | 17557 | 1.71 | 0 | 0 | 16.55 | 4996
DRE2 | GG\17\007\D | GG | 17 | 7 | D | 6 DL | 100 | 100 | 100 | 2024-02-12 16:38 | 2024-02-18 15:34 | 429491.6043 |  |  |  | 7998 | 429492 | 191952 |  |  | 0 | 19.99 | 0 | 6.58 | 5807.65
TS5500Exc | RS\35\006\A | RS | 35 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-02-12 20:33 | 2024-02-13 17:18 | 26154.6339 | [6 empty] | 26155 | 18136 | 1.77 | 0 | 0 | 16.55 | 4996
TS6060#1 | RS\35\004\B | RS | 35 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-13 11:12 | 2024-02-14 15:11 | 28875.8706 | 28876 | [7 empty] | 0 | 0 | 2.89 | 8.83 | 5609.34
TS5500Shv | RS\34\006\B | RS | 34 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-02-13 11:33 | 2024-02-14 04:27 | 20607.3594 | [6 empty] | 20607 | 14819 | 1.45 | 0 | 0 | 9.01 | 5600
TS5500Exc | RS\34\006\B | RS | 34 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-02-13 17:18 | 2024-02-14 10:12 | 21286.7229 | [6 empty] | 21287 | 15308 | 1.5 | 0 | 0 | 9.01 | 5600
TS5500Shv | GG\17\008\D | GG | 17 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-02-14 04:27 | 2024-02-16 07:02 | 61678.9203 | [6 empty] | 61679 | 46037 | 4.6 | 0 | 0 | 6.51 | 5814
TS5500Exc | RS\33\006\D | RS | 33 | 6 | D | 7 PostStrip | 20.4715 | 0 | 20.4715 | 2024-02-14 10:12 | 2024-02-14 20:18 | 8934.3146 |  |  | 8934 | [5 empty] | 0 | 0 | 0 | 5.78 | 5912.61
TS6060#1 | RS\35\005\B | RS | 35 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-14 15:11 | 2024-02-15 23:30 | 33341.8135 | 33342 | [7 empty] | 0 | 0 | 3.34 | 8.9 | 5609.96
TS5500Exc | RS\35\004\B | RS | 35 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-02-14 20:18 | 2024-02-15 12:00 | 19764.184 | [6 empty] | 19764 | 14269 | 1.43 | 0 | 0 | 8.83 | 5609
TS Fleet 5 | GG\21\007\X1 | GG | 21 | 7 | X1 | 1 Prestrip - Thick | 45.7694 | 45.7694 | 45.7694 | 2024-02-14 20:34 | 2024-02-22 07:42 | 351110.0592 | 351110 | [7 empty] | 0 | 0 | 34.28 | 11.88 | 5284.4
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 5d 00:00 |  | 5d 00:00 | 2024-02-15 01:00 | 2024-02-20 01:00
TS5500Exc | RS\33\006\D | RS | 33 | 6 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-02-15 12:00 | 2024-02-16 09:26 | 27000.6157 | [6 empty] | 27001 | 19967 | 2.31 | 0 | 0 | 5.78 | 5913
TS6060#1 | RS\35\006\B | RS | 35 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-15 23:30 | 2024-02-17 12:38 | 38320.7397 | 38321 | [7 empty] | 0 | 0 | 3.75 | 9.06 | 5597.58
PH4100XPC#1 | GG\20\004\X1 | GG | 20 | 4 | X1 | 1 Prestrip - Thick | 100 | 54.447 | 54.447 | 2024-02-15 23:49 | 2024-03-05 09:10 | 1016328.099 | 1016328 | [7 empty] | 0 | 0 | 57.14 | 10.48 | 5314.98
TS5500Shv | RS\35\004\B | RS | 35 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-02-16 07:02 | 2024-02-16 22:44 | 19133.4122 | [6 empty] | 19133 | 13813 | 1.38 | 0 | 0 | 8.83 | 5609
TS5500Exc | RS\35\005\B | RS | 35 | 5 | B | 8 Coal Mining | 75.1 | 0 | 75.1 | 2024-02-16 09:26 | 2024-02-17 09:25 | 30198.5288 | [6 empty] | 30199 | 21745 | 2.18 | 0 | 0 | 8.9 | 5610
PH4100A | RS\37\003\X | RS | 37 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-16 15:42 | 2024-02-22 18:37 | 245036.4109 | 245036 | [7 empty] | 0 | 0 | 36.62 | 12.03 | 5269.3
TS5500Shv | RS\35\005\B | RS | 35 | 5 | B | 8 Coal Mining | 24.9 | 0 | 24.9 | 2024-02-16 22:44 | 2024-02-17 06:57 | 10030.6156 | [6 empty] | 10031 | 7223 | 0.72 | 0 | 0 | 8.9 | 5610
TS5500Shv | RS\36\003\X | RS | 36 | 3 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-02-17 06:57 | 2024-02-17 11:12 | 5181.383 | [6 empty] | 5181 | 3645 | 0.54 | 0 | 0 | 12.07 | 5264
TS5500Exc | RS\36\003\X | RS | 36 | 3 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-02-17 09:25 | 2024-02-17 13:39 | 5352.1978 | [6 empty] | 5352 | 3765 | 0.56 | 0 | 0 | 12.07 | 5264
TS5500Shv | RS\33\006\D | RS | 33 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-02-17 11:12 | 2024-02-18 08:38 | 26138.8939 | [6 empty] | 26139 | 19330 | 2.23 | 0 | 0 | 5.78 | 5913
TS6060#1 | GG\17\010\D | GG | 17 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-02-17 12:38 | 2024-02-19 10:11 | 61652.2239 | [6 empty] | 61652 | 46164 | 4.62 | 0 | 0 | 6.2 | 5842
TS5500Exc | MW\48\008\B | MW | 48 | 8 | B | 8 Coal Mining | 83.2 | 0 | 83.2 | 2024-02-17 13:39 | 2024-02-18 19:10 | 37161.8622 | [6 empty] | 37162 | 27458 | 2.4 | 0 | 0 | 9.42 | 5550
TS5500Shv | MW\48\007\D | MW | 48 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-02-18 08:38 | 2024-02-20 13:11 | 64082.1848 | [6 empty] | 64082 | 48577 | 4.86 | 0 | 0 | 5.77 | 5907
DRE2 | GG\17\006\D | GG | 17 | 6 | D | 6 DL | 100 | 100 | 100 | 2024-02-18 15:34 | 2024-02-24 12:16 | 422786.9022 |  |  |  | 7873 | 422787 | 188955 |  |  | 0 | 19.68 | 0 | 6.62 | 5804.59
TS5500Exc | MW\49\004\D | MW | 49 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-18 19:10 | 2024-02-25 09:11 | 139767.2457 | 139767 | [7 empty] | 0 | 0 | 27.97 | 7.47 | 5752.67
TS6060#1 | RS\36\003\A | RS | 36 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-19 10:11 | 2024-02-20 17:42 | 32519.5353 | 32520 | [7 empty] | 0 | 0 | 4.68 | 11.1 | 5411.18
DRE1 | RS\34\003\D | RS | 34 | 3 | D | 6 DL | 100 | 100 | 100 | 2024-02-20 01:00 | 2024-02-23 22:14 | 317009.6967 |  |  |  | 16299 | 317010 | 255346 |  |  | 0 | 27.18 | 0 | 5.08 | 5974.04
TS5500Shv | RS\35\006\B | RS | 35 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-02-20 13:11 | 2024-02-21 23:25 | 41734.4165 | [6 empty] | 41734 | 30013 | 2.96 | 0 | 0 | 9.06 | 5598
TS6060#1 | GG\17\009\D | GG | 17 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-02-20 17:42 | 2024-02-22 15:09 | 61500.0451 | [6 empty] | 61500 | 45976 | 4.6 | 0 | 0 | 6.34 | 5830
TS5500Shv | RS\36\003\A | RS | 36 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-02-21 23:25 | 2024-02-23 03:40 | 34459.1551 | [6 empty] | 34459 | 24626 | 3.25 | 0 | 0 | 11.1 | 5411
TS Fleet 5 | GG\21\008\X1 | GG | 21 | 8 | X1 | 1 Prestrip - Thick | 45.7043 | 45.7043 | 45.7043 | 2024-02-22 07:42 | 2024-02-29 08:16 | 330375.6212 | 330376 | [7 empty] | 0 | 0 | 32.61 | 12.86 | 5238.62
TS6060#1 | GG\17\007\D | GG | 17 | 7 | D | 8 Coal Mining | 53.4 | 0 | 53.4 | 2024-02-22 15:09 | 2024-02-23 15:18 | 32678.66 | [6 empty] | 32679 | 24410 | 2.44 | 0 | 0 | 6.58 | 5808
PH4100A | RS\36\004\X | RS | 36 | 4 | X | 1 Prestrip - Thick | 100 | 45.1339 | 45.1339 | 2024-02-22 18:37 | 2024-02-27 14:48 | 194944.4852 | 194944 | [7 empty] | 0 | 0 | 19.69 | 11.84 | 5290.76
TS5500Shv | MW\48\008\B | MW | 48 | 8 | B | 8 Coal Mining | 16.8 | 0 | 16.8 | 2024-02-23 03:40 | 2024-02-23 09:51 | 7528.2729 | [6 empty] | 7528 | 5562 | 0.49 | 0 | 0 | 9.42 | 5550
TS5500Shv | GG\17\007\D | GG | 17 | 7 | D | 8 Coal Mining | 46.6 | 0 | 46.6 | 2024-02-23 09:51 | 2024-02-24 09:16 | 28556.2284 | [6 empty] | 28556 | 21331 | 2.13 | 0 | 0 | 6.58 | 5808
TS6060#1 | RS\36\003\B | RS | 36 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-23 15:18 | 2024-02-24 12:55 | 22308.7409 | 22309 | [7 empty] | 0 | 0 | 2.88 | 8.96 | 5589.59
DRE1 | MW\48\008\D | MW | 48 | 8 | D | 6 DL | 100 | 100 | 100 | 2024-02-23 22:14 | 2024-02-27 14:15 | 299214.62 |  |  |  | 15384 | 299215 | 241013 |  |  | 0 | 28.82 | 0 | 5.39 | 5939.48
TS5500Shv | RS\34\003\D | RS | 34 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-02-24 09:16 | 2024-02-26 10:34 | 60121.1335 | [6 empty] | 60121 | 44636 | 4.43 | 0 | 0 | 5.08 | 5974
DRE2 | GG\17\005\D | GG | 17 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-02-24 12:16 | 2024-03-01 09:59 | 425871.6825 |  |  |  | 7931 | 425872 | 190334 |  |  | 0 | 19.84 | 0 | 6.64 | 5802.45
TS6060#1 | GG\17\006\D | GG | 17 | 6 | D | 8 Coal Mining | 42.6 | 0 | 42.6 | 2024-02-24 12:55 | 2024-02-25 08:08 | 26021.4145 | [6 empty] | 26021 | 19468 | 1.95 | 0 | 0 | 6.62 | 5805
TS6060#1 | RS\40\003\X | RS | 40 | 3 | X | 1 Prestrip - Thick | 34.887 | 34.887 | 34.887 | 2024-02-25 08:08 | 2024-02-29 10:25 | 98357.4942 | 98357 | [7 empty] | 0 | 0 | 11.33 | 11.94 | 5279.05
TS5500Exc | RS\37\003\X | RS | 37 | 3 | X | 8 Coal Mining | 100 | 0 | 100 | 2024-02-25 09:11 | 2024-02-25 18:20 | 11526.5207 | [6 empty] | 11527 | 8114 | 1.1 | 0 | 0 | 12.03 | 5269
TS5500Exc | RS\36\003\B | RS | 36 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-02-25 18:20 | 2024-02-26 06:12 | 14928.2697 | [6 empty] | 14928 | 10782 | 1.36 | 0 | 0 | 8.96 | 5590
TS5500Exc | MW\49\005\D | MW | 49 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-26 06:12 | 2024-03-14 17:05 | 370505.6609 | 370506 | [7 empty] | 0 | 0 | 39.66 | 7.44 | 5758.29
TS5500Shv | RS\36\003\B | RS | 36 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-02-26 10:34 | 2024-02-26 22:25 | 14451.8356 | [6 empty] | 14452 | 10437 | 1.32 | 0 | 0 | 8.96 | 5590
TS5500Shv | GG\17\006\D | GG | 17 | 6 | D | 8 Coal Mining | 57.4 | 0 | 57.4 | 2024-02-26 22:25 | 2024-02-28 03:08 | 35006.9047 | [6 empty] | 35007 | 26191 | 2.62 | 0 | 0 | 6.62 | 5805
DRE1 | MW\49\004\D | MW | 49 | 4 | D | 6 DL | 100 | 0 | 100 | 2024-02-27 14:15 | 2024-03-02 04:25 | 292991.3676 |  |  |  | 15914 | 292991 | 135308 |  |  | 0 | 35 | 0 | 7.47 | 5752.67
PH4100A | RS\37\004\X | RS | 37 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-27 14:48 | 2024-03-09 09:03 | 433052.948 | 433053 | [7 empty] | 0 | 0 | 43.72 | 11.76 | 5300.27
TS5500Shv | MW\48\008\D | MW | 48 | 8 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-02-28 03:08 | 2024-02-29 01:04 | 26755.3217 | [6 empty] | 26755 | 20346 | 2.32 | 0 | 0 | 5.39 | 5939
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 08:55 |  | 1d 08:55 | 2024-02-29 01:04 | 2024-03-01 09:59
TS Fleet 5 | GG\21\009\X2 | GG | 21 | 9 | X2 | 1 Prestrip - Thick | 44.8418 | 0 | 44.8418 | 2024-02-29 08:16 | 2024-03-07 11:13 | 335077.8976 | 335078 | [7 empty] | 0 | 0 | 36.18 | 0 | 0
TS6060#1 | RS\37\003\A | RS | 37 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-02-29 10:25 | 2024-03-01 20:14 | 34894.5794 | 34895 | [7 empty] | 0 | 0 | 4.59 | 11.33 | 5393.71
DRE2 | GG\17\004\D | GG | 17 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-03-01 09:59 | 2024-03-07 05:19 | 418692.3946 |  |  |  | 7797 | 418692 | 187125 |  |  | 0 | 19.5 | 0 | 6.58 | 5807.38
TS5500Shv | GG\17\005\D | GG | 17 | 5 | D | 8 Coal Mining | 36.8 | 0 | 36.8 | 2024-03-01 09:59 | 2024-03-02 04:28 | 22531.7035 | [6 empty] | 22532 | 16871 | 1.69 | 0 | 0 | 6.64 | 5802
TS6060#1 | GG\17\005\D | GG | 17 | 5 | D | 8 Coal Mining | 63.2 | 0 | 63.2 | 2024-03-01 20:14 | 2024-03-03 00:53 | 38767.5103 | [6 empty] | 38768 | 29028 | 2.9 | 0 | 0 | 6.64 | 5802
DRE1 | RS\34\004\D | RS | 34 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-03-02 04:25 | 2024-03-06 05:02 | 328499.0549 |  |  |  | 16889 | 328499 | 264601 |  |  | 0 | 28.15 | 0 | 5.3 | 5954.82
TS5500Shv | RS\37\003\A | RS | 37 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-03-02 04:28 | 2024-03-03 11:08 | 37396.3824 | [6 empty] | 37396 | 26698 | 3.25 | 0 | 0 | 11.33 | 5394
TS6060#1 | RS\40\004\X | RS | 40 | 4 | X | 1 Prestrip - Thick | 37.3352 | 37.3352 | 37.3352 | 2024-03-03 00:53 | 2024-03-09 02:16 | 145646.8491 | 145647 | [7 empty] | 0 | 0 | 14.88 | 11.51 | 5327.4
TS5500Shv | MW\49\004\D | MW | 49 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2024-03-03 11:08 | 2024-03-04 11:01 | 25603.6384 |  |  | 25604 | [5 empty] | 0 | 0 | 0 | 7.47 | 5752.67
TS5500Shv | MW\49\004\D | MW | 49 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-03-04 11:01 | 2024-03-05 09:57 | 27951.6257 | [6 empty] | 27952 | 20893 | 4.1 | 0 | 0 | 7.47 | 5753
PH4100XPC#1 | GG\20\005\X1 | GG | 20 | 5 | X1 | 1 Prestrip - Thick | 100 | 55.0394 | 55.0394 | 2024-03-05 09:10 | 2024-03-14 00:53 | 477667.5647 | 477668 | [7 empty] | 0 | 0 | 43.53 | 10.48 | 5313.83
TS5500Shv | GG\20\004\X1 | GG | 20 | 4 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-03-05 09:57 | 2024-03-05 20:26 | 12785.3795 | [6 empty] | 12785 | 9509 | 0.54 | 0 | 0 | 10.48 | 5315
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 08:37 |  | 0d 08:37 | 2024-03-05 20:26 | 2024-03-06 05:02
DRE1 | RS\34\005\D | RS | 34 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-03-06 05:02 | 2024-03-10 01:58 | 315944.8938 |  |  |  | 16244 | 315945 | 254489 |  |  | 0 | 27.08 | 0 | 5.58 | 5931
TS5500Shv | RS\34\004\D | RS | 34 | 4 | D | 8 Coal Mining | 35.7 | 0 | 35.7 | 2024-03-06 05:02 | 2024-03-06 22:47 | 21649.1134 | [6 empty] | 21649 | 16035 | 1.6 | 0 | 0 | 5.3 | 5955
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 06:32 |  | 0d 06:32 | 2024-03-06 22:47 | 2024-03-07 05:19
DRE2 | GG\17\003\D | GG | 17 | 3 | D | 6 DL | 100 | 100 | 100 | 2024-03-07 05:19 | 2024-03-13 01:33 | 421380.7172 |  |  |  | 6922 | 421381 | 121265 |  |  | 0 | 19.29 | 0 | 6.49 | 5814.89
TS5500Shv | GG\17\004\D | GG | 17 | 4 | D | 8 Coal Mining | 26.8 | 0 | 26.8 | 2024-03-07 05:19 | 2024-03-07 18:33 | 16121.7763 | [6 empty] | 16122 | 12081 | 1.21 | 0 | 0 | 6.58 | 5807
TS Fleet 5 | GG\21\010\X2 | GG | 21 | 10 | X2 | 1 Prestrip - Thick | 44.9136 | 0 | 44.9136 | 2024-03-07 11:13 | 2024-03-14 06:24 | 319837.6452 | 319838 | [7 empty] | 0 | 0 | 25.07 | 0 | 0
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 14:30 |  | 1d 14:30 | 2024-03-07 18:33 | 2024-03-09 09:03
TS6060#1 | GG\20\004\X1 | GG | 20 | 4 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-03-09 02:16 | 2024-03-09 12:46 | 14190.3663 | [6 empty] | 14190 | 10554 | 0.6 | 0 | 0 | 10.48 | 5315
PH4100A | RS\36\005\X | RS | 36 | 5 | X | 1 Prestrip - Thick | 100 | 46.442 | 46.442 | 2024-03-09 09:03 | 2024-03-15 06:16 | 237982.9804 | 237983 | [7 empty] | 0 | 0 | 24.04 | 11.47 | 5332.43
TS5500Shv | RS\37\004\X | RS | 37 | 4 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-03-09 09:03 | 2024-03-09 15:46 | 8197.9632 | [6 empty] | 8198 | 5786 | 0.58 | 0 | 0 | 11.76 | 5300
TS6060#1 | RS\37\003\B | RS | 37 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-03-09 12:46 | 2024-03-10 12:33 | 24546.744 | 24547 | [7 empty] | 0 | 0 | 2.92 | 9.01 | 5584.18
TS5500Shv | GG\20\004\B | GG | 20 | 4 | B | 1 Prestrip - Thick | 96.0039 | 77.7307 | 77.7307 | 2024-03-09 15:46 | 2024-03-14 11:54 | 124488.0981 | 124488 | [7 empty] | 0 | 0 | 7.31 | 9.39 | 5517.67
DRE1 | RS\34\006\D | RS | 34 | 6 | D | 6 DL | 100 | 100 | 100 | 2024-03-10 01:58 | 2024-03-13 17:38 | 298063.8225 |  |  |  | 11181 | 298064 | 169305 |  |  | 0 | 25.92 | 0 | 5.78 | 5913.29
TS6060#1 | GG\17\004\D | GG | 17 | 4 | D | 8 Coal Mining | 73.2 | 0 | 73.2 | 2024-03-10 12:33 | 2024-03-11 21:06 | 44043.0808 | [6 empty] | 44043 | 33004 | 3.3 | 0 | 0 | 6.58 | 5807
TS6060#1 | RS\41\003\X | RS | 41 | 3 | X | 1 Prestrip - Thick | 37.5106 | 37.5106 | 37.5106 | 2024-03-11 21:06 | 2024-03-16 05:03 | 104047.6775 | 104048 | [7 empty] | 0 | 0 | 11.19 | 11.91 | 5282.45
DRE2 | GG\18\013\B | GG | 18 | 13 | B | 6 DL | 100 | 0 | 100 | 2024-03-13 01:33 | 2024-03-16 16:06 | 260047.2407 |  |  |  |  | 260047 | 216706 |  |  | 0 | 15.63 | 0 | 10.95 | 5433.95
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2024-03-13 17:38 | 2024-03-16 17:38
PH4100XPC#1 | GG\20\004\B | GG | 20 | 4 | B | 1 Prestrip - Thick | 100 | 15.5512 | 15.5512 | 2024-03-14 00:53 | 2024-03-14 11:54 | 24905.7806 | 24906 | [7 empty] | 0 | 0 | 1.46 | 9.39 | 5517.67
TS Fleet 5 | GG\20\004\B | GG | 20 | 4 | B | 1 Prestrip - Thick | 22.8847 | 6.7181 | 6.7181 | 2024-03-14 06:24 | 2024-03-14 11:54 | 10759.2049 | 10759 | [7 empty] | 0 | 0 | 0.63 | 9.39 | 5517.67
TS5500Shv | GG\20\005\X1 | GG | 20 | 5 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-03-14 11:54 | 2024-03-14 18:02 | 7491.8375 | [6 empty] | 7492 | 5582 | 0.55 | 0 | 0 | 10.48 | 5314
TS Fleet 5 | GG\21\011\X1 | GG | 21 | 11 | X1 | 1 Prestrip - Thick | 45.7019 | 45.7019 | 45.7019 | 2024-03-14 11:54 | 2024-03-19 06:50 | 225294.4249 | 225294 | [7 empty] | 0 | 0 | 22.03 | 14.78 | 5115.38
PH4100XPC#1 | GG\20\006\X1 | GG | 20 | 6 | X1 | 1 Prestrip - Thick | 100 | 54.3296 | 54.3296 | 2024-03-14 11:54 | 2024-03-22 13:33 | 432721.1194 | 432721 | [7 empty] | 0 | 0 | 41.87 | 11.01 | 5312.13
TS5500Exc | RS\36\004\X | RS | 36 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2024-03-14 17:05 | 2024-03-15 06:12 | 16531.2369 | [6 empty] | 16531 | 11654 | 1.17 | 0 | 0 | 11.84 | 5291
TS5500Shv | RS\34\005\D | RS | 34 | 5 | D | 8 Coal Mining | 19.8 | 0 | 19.8 | 2024-03-14 18:02 | 2024-03-15 04:01 | 12166.5833 | [6 empty] | 12167 | 9005 | 0.9 | 0 | 0 | 5.58 | 5931
TS5500Shv | RS\34\006\D | RS | 34 | 6 | D | 7 PostStrip | 72.1047 | 0 | 72.1047 | 2024-03-15 04:01 | 2024-03-16 09:01 | 31097.4046 |  |  | 31097 | [5 empty] | 0 | 0 | 0 | 5.78 | 5913.29
TS5500Exc | RS\37\004\X | RS | 37 | 4 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-03-15 06:12 | 2024-03-15 12:56 | 8468.2257 | [6 empty] | 8468 | 5976 | 0.6 | 0 | 0 | 11.76 | 5300
PH4100A | RS\37\005\X | RS | 37 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-03-15 06:16 | 2024-03-27 09:48 | 491250.0603 | 491250 | [7 empty] | 0 | 0 | 49.77 | 11.3 | 5350.9
TS5500Exc | RS\34\004\D | RS | 34 | 4 | D | 8 Coal Mining | 64.3 | 0 | 64.3 | 2024-03-15 12:56 | 2024-03-16 19:50 | 38935.8898 | [6 empty] | 38936 | 28838 | 2.88 | 0 | 0 | 5.3 | 5955
TS6060#1 | GG\20\005\X1 | GG | 20 | 5 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-03-16 05:03 | 2024-03-16 11:11 | 8315.1164 | [6 empty] | 8315 | 6195 | 0.61 | 0 | 0 | 10.48 | 5314
TS5500Shv | RS\36\005\X | RS | 36 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2024-03-16 09:01 | 2024-03-16 22:34 | 16517.9169 | [6 empty] | 16518 | 11691 | 1.17 | 0 | 0 | 11.47 | 5332
TS6060#1 | RS\36\004\A | RS | 36 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-03-16 11:11 | 2024-03-18 01:09 | 39173.0195 | 39173 | [7 empty] | 0 | 0 | 3.92 | 11.97 | 5346.85
DRE2 | GG\18\018\B | GG | 18 | 18 | B | 6 DL | 100 | 0 | 100 | 2024-03-16 16:06 | 2024-03-19 07:47 | 191398.7093 |  |  |  |  | 191399 | 159499 |  |  | 0 | 15.93 | 0 | 11.23 | 5416.45
DRE1 | MW\49\005\D | MW | 49 | 5 | D | 6 DL | 100 | 0 | 100 | 2024-03-16 17:38 | 2024-03-21 20:19 | 417153.9934 |  |  |  | 29667 | 417154 | 299968 |  |  | 0 | 35 | 0 | 7.44 | 5758.29
TS5500Exc | RS\34\005\D | RS | 34 | 5 | D | 8 Coal Mining | 80.2 | 0 | 80.2 | 2024-03-16 19:50 | 2024-03-18 11:01 | 49358.9263 | [6 empty] | 49359 | 36532 | 3.65 | 0 | 0 | 5.58 | 5931
TS5500Shv | RS\37\003\B | RS | 37 | 3 | B | 8 Coal Mining | 96.8 | 0 | 96.8 | 2024-03-16 22:34 | 2024-03-18 00:01 | 31036.6828 | [6 empty] | 31037 | 22401 | 2.62 | 0 | 0 | 9.01 | 5584
TS5500Shv | GG\17\003\D | GG | 17 | 3 | D | 7 PostStrip | 47.508 | 0 | 47.508 | 2024-03-18 00:01 | 2024-03-18 19:54 | 21308.7993 |  |  | 21309 | [5 empty] | 0 | 0 | 0 | 6.49 | 5814.89
TS6060#1 | RS\36\005\A | RS | 36 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-03-18 01:09 | 2024-03-19 13:37 | 37622.9569 | 37623 | [7 empty] | 0 | 0 | 3.77 | 14.54 | 5149.85
TS5500Exc | RS\34\006\D | RS | 34 | 6 | D | 7 PostStrip | 27.8954 | 0 | 27.8954 | 2024-03-18 11:01 | 2024-03-19 00:38 | 12030.7494 |  |  | 12031 | [5 empty] | 0 | 0 | 0 | 5.78 | 5913.29
TS5500Shv | RS\36\004\A | RS | 36 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-03-18 19:54 | 2024-03-20 10:18 | 46832.2097 | [6 empty] | 46832 | 33297 | 3.33 | 0 | 0 | 11.97 | 5347
TS5500Exc | RS\34\006\D | RS | 34 | 6 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-03-19 00:38 | 2024-03-19 21:55 | 26827.6304 | [6 empty] | 26828 | 19855 | 2.32 | 0 | 0 | 5.78 | 5913
TS Fleet 5 | GG\20\005\X2 | GG | 20 | 5 | X2 | 1 Prestrip - Thick | 45.3511 | 0 | 45.3511 | 2024-03-19 06:50 | 2024-03-20 05:03 | 43535.5138 | 43536 | [7 empty] | 0 | 0 | 4.3 | 0 | 0
DRE2 | GG\18\019\B | GG | 18 | 19 | B | 6 DL | 100 | 0 | 100 | 2024-03-19 07:47 | 2024-03-22 05:58 | 210906.7413 |  |  |  |  | 210907 | 175756 |  |  | 0 | 17.48 | 0 | 12.22 | 5352.88
TS6060#1 | RS\37\004\A | RS | 37 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-03-19 13:37 | 2024-03-21 01:45 | 37289.851 | 37290 | [7 empty] | 0 | 0 | 3.73 | 12.23 | 5327.26
TS5500Exc | RS\36\005\A | RS | 36 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-03-19 21:55 | 2024-03-20 17:27 | 24596.812 | [6 empty] | 24597 | 17237 | 1.73 | 0 | 0 | 14.54 | 5150
TS Fleet 5 | GG\21\012\X1 | GG | 21 | 12 | X1 | 1 Prestrip - Thick | 45.8539 | 45.8539 | 45.8539 | 2024-03-20 05:03 | 2024-03-24 12:39 | 203047.6727 | 203048 | [7 empty] | 0 | 0 | 19.79 | 14.59 | 5131.32
TS5500Shv | RS\36\005\A | RS | 36 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-03-20 10:18 | 2024-03-21 05:50 | 23811.8073 | [6 empty] | 23812 | 16687 | 1.67 | 0 | 0 | 14.54 | 5150
TS5500Exc | MW\48\008\D | MW | 48 | 8 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-03-20 17:27 | 2024-03-21 15:24 | 27637.3653 | [6 empty] | 27637 | 21017 | 2.39 | 0 | 0 | 5.39 | 5939
TS6060#1 | RS\36\004\B | RS | 36 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-03-21 01:45 | 2024-03-22 06:08 | 29274.2065 | 29274 | [7 empty] | 0 | 0 | 2.93 | 8.88 | 5607.12
TS5500Shv | RS\34\006\D | RS | 34 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-03-21 05:50 | 2024-03-22 03:08 | 25971.4295 | [6 empty] | 25971 | 19222 | 2.25 | 0 | 0 | 5.78 | 5913
TS5500Exc | RS\37\003\B | RS | 37 | 3 | B | 8 Coal Mining | 3.2 | 0 | 3.2 | 2024-03-21 15:24 | 2024-03-21 16:12 | 1012.5612 | [6 empty] | 1013 | 731 | 0.09 | 0 | 0 | 9.01 | 5584
TS5500Exc | RS\37\004\A | RS | 37 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-03-21 16:12 | 2024-03-22 11:00 | 23680.237 | [6 empty] | 23680 | 16803 | 1.68 | 0 | 0 | 12.23 | 5327
DRE1 | MW\56\004\D | MW | 56 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-03-21 20:19 | 2024-03-23 23:43 | 174765.1027 |  |  |  | 7072 | 174765 | 92152 |  |  | 0 | 31.97 | 0 | 9.42 | 5577.97
TS5500Shv | RS\37\004\A | RS | 37 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-03-22 03:08 | 2024-03-22 21:56 | 22924.4848 | [6 empty] | 22924 | 16267 | 1.63 | 0 | 0 | 12.23 | 5327
DRE2 | GG\18\020\B | GG | 18 | 20 | B | 6 DL | 100 | 0 | 100 | 2024-03-22 05:58 | 2024-03-26 07:21 | 292622.8944 |  |  |  |  | 292623 | 225095 |  |  | 0 | 22.4 | 0 | 14.96 | 5150.81
TS6060#1 | RS\36\005\B | RS | 36 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-03-22 06:08 | 2024-03-23 15:01 | 33932.5845 | 33933 | [7 empty] | 0 | 0 | 3.4 | 8.95 | 5607.7
TS5500Exc | RS\36\004\B | RS | 36 | 4 | B | 8 Coal Mining | 96.5 | 0 | 96.5 | 2024-03-22 11:00 | 2024-03-23 16:50 | 37572.5432 | [6 empty] | 37573 | 27107 | 2.71 | 0 | 0 | 8.88 | 5607
PH4100XPC#1 | GG\20\005\X2 | GG | 20 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.6489 | 2024-03-22 13:33 | 2024-03-23 12:43 | 52460.9792 | 52461 | [7 empty] | 0 | 0 | 5.19 | 0 | 0
TS5500Shv | GG\20\006\X1 | GG | 20 | 6 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-03-22 21:56 | 2024-03-23 10:55 | 15830.5864 | [6 empty] | 15831 | 11720 | 1.17 | 0 | 0 | 11.01 | 5312
TS5500Shv | RS\36\004\B | RS | 36 | 4 | B | 8 Coal Mining | 3.5 | 0 | 3.5 | 2024-03-23 10:55 | 2024-03-23 12:02 | 1366.5148 | [6 empty] | 1367 | 986 | 0.1 | 0 | 0 | 8.88 | 5607
TS5500Shv | GG\18\013\B | GG | 18 | 13 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-03-23 12:02 | 2024-03-25 19:17 | 67378.4702 | [6 empty] | 67378 | 49194 | 3.61 | 0 | 0 | 10.95 | 5434
PH4100XPC#1 | GG\20\005\B | GG | 20 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-03-23 12:43 | 2024-03-24 06:01 | 39149.7885 | 39150 | [7 empty] | 0 | 0 | 3.9 | 9.02 | 5528.89
TS6060#1 | RS\37\004\B | RS | 37 | 4 | B | 1 Prestrip - Thick | 31.7596 | 31.7596 | 31.7596 | 2024-03-23 15:01 | 2024-03-24 00:10 | 9441.5355 | 9442 | [7 empty] | 0 | 0 | 0.95 | 8.92 | 5604.91
TS5500Exc | RS\36\005\B | RS | 36 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-03-23 16:50 | 2024-03-24 09:03 | 20432.983 | [6 empty] | 20433 | 14713 | 1.47 | 0 | 0 | 8.95 | 5608
DRE1 | MW\56\005\D | MW | 56 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-03-23 23:43 | 2024-03-28 13:37 | 373616.806 |  |  |  | 21323 | 373617 | 283297 |  |  | 0 | 30.77 | 0 | 9.3 | 5594.34
TS6060#1 | MW\56\004\D | MW | 56 | 4 | D | 7 PostStrip | 49.0446 | 0 | 49.0446 | 2024-03-24 00:10 | 2024-03-24 09:02 | 9142.4413 |  |  | 9142 | [5 empty] | 0 | 0 | 0 | 9.42 | 5577.97
PH4100XPC#1 | GG\20\006\X2 | GG | 20 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 60.9287 | 2024-03-24 06:01 | 2024-03-25 07:35 | 57870.0298 | 57870 | [7 empty] | 0 | 0 | 5.77 | 0 | 0
TS6060#1 | GG\17\003\D | GG | 17 | 3 | D | 7 PostStrip | 52.492 | 0 | 52.492 | 2024-03-24 09:02 | 2024-03-25 07:51 | 23544.317 |  |  | 23544 | [5 empty] | 0 | 0 | 0 | 6.49 | 5814.89
TS5500Exc | MW\49\006\D | MW | 49 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-03-24 09:03 | 2024-04-09 15:44 | 345620.8638 | 345621 | [7 empty] | 0 | 0 | 35.51 | 6.7 | 5825
TS Fleet 5 | GG\20\006\X2 | GG | 20 | 6 | X2 | 1 Prestrip - Thick | 45.3511 | 0 | 39.0713 | 2024-03-24 12:39 | 2024-03-25 07:35 | 37109.9212 | 37110 | [7 empty] | 0 | 0 | 3.7 | 0 | 0
TS Fleet 5 | GG\20\006\B | GG | 20 | 6 | B | 1 Prestrip - Thick | 45.3511 | 45.3511 | 45.3511 | 2024-03-25 07:35 | 2024-03-25 19:27 | 23258.4846 | 23258 | [7 empty] | 0 | 0 | 2.33 | 9.83 | 5474.5
PH4100XPC#1 | GG\20\006\B | GG | 20 | 6 | B | 1 Prestrip - Thick | 100 | 54.6489 | 54.6489 | 2024-03-25 07:35 | 2024-03-25 19:58 | 28026.84 | 28027 | [7 empty] | 0 | 0 | 2.81 | 9.83 | 5474.5
TS6060#1 | GG\17\003\D | GG | 17 | 3 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-03-25 07:51 | 2024-03-26 04:38 | 28126.7661 | [6 empty] | 28127 | 21077 | 2.37 | 0 | 0 | 6.49 | 5815
TS5500Shv | RS\36\005\B | RS | 36 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-03-25 19:17 | 2024-03-26 11:31 | 19780.8665 | [6 empty] | 19781 | 14244 | 1.43 | 0 | 0 | 8.95 | 5608
TS Fleet 5 | GG\21\013\X1 | GG | 21 | 13 | X1 | 1 Prestrip - Thick | 46.1246 | 46.1246 | 46.1246 | 2024-03-25 19:27 | 2024-03-29 12:00 | 173567.5396 | 173568 | [7 empty] | 0 | 0 | 16.89 | 14.38 | 5148.39
PH4100XPC#1 | GG\20\007\X1 | GG | 20 | 7 | X1 | 1 Prestrip - Thick | 100 | 54.2351 | 54.2351 | 2024-03-25 19:58 | 2024-04-02 07:21 | 399332.7509 | 399333 | [7 empty] | 0 | 0 | 39.01 | 11.72 | 5300.03
TS6060#1 | RS\41\004\X | RS | 41 | 4 | X | 1 Prestrip - Thick | 34.6029 | 34.6029 | 34.6029 | 2024-03-26 04:38 | 2024-03-31 08:43 | 123987.9482 | 123988 | [7 empty] | 0 | 0 | 12.71 | 11.43 | 5335.82
DRE2 | GG\18\021\B | GG | 18 | 21 | B | 6 DL | 100 | 0 | 100 | 2024-03-26 07:21 | 2024-03-29 16:37 | 244176.344 |  |  |  |  | 244176 | 187828 |  |  | 0 | 20.66 | 0 | 16.55 | 5056.08
TS5500Shv | MW\56\004\D | MW | 56 | 4 | D | 7 PostStrip | 50.9554 | 0 | 50.9554 | 2024-03-26 11:31 | 2024-03-26 20:22 | 9498.6403 |  |  | 9499 | [5 empty] | 0 | 0 | 0 | 9.42 | 5577.97
TS5500Shv | MW\56\004\D | MW | 56 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-03-26 20:22 | 2024-03-27 10:42 | 17480.5992 | [6 empty] | 17481 | 12916 | 3.62 | 0 | 0 | 9.42 | 5578
PH4100A | RS\36\006\X | RS | 36 | 6 | X | 1 Prestrip - Thick | 100 | 63.4127 | 63.4127 | 2024-03-27 09:48 | 2024-04-07 07:16 | 441469.9444 | 441470 | [7 empty] | 0 | 0 | 36.38 | 10.97 | 5387.55
TS5500Shv | RS\37\005\X | RS | 37 | 5 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-03-27 10:42 | 2024-03-27 17:37 | 8429.571 | [6 empty] | 8430 | 5974 | 0.6 | 0 | 0 | 11.3 | 5351
TS5500Shv | GG\17\003\D | GG | 17 | 3 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-03-27 17:37 | 2024-03-28 14:24 | 25341.9378 | [6 empty] | 25342 | 18990 | 2.14 | 0 | 0 | 6.49 | 5815
DRE1 | RS\35\003\D | RS | 35 | 3 | D | 6 DL | 100 | 100 | 100 | 2024-03-28 13:37 | 2024-04-01 11:27 | 319071.8973 |  |  |  | 16405 | 319072 | 257007 |  |  | 0 | 27.39 | 0 | 5.13 | 5968.64
TS5500Shv | MW\56\005\D | MW | 56 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-03-28 14:24 | 2024-03-29 14:20 | 29186.4046 | [6 empty] | 29186 | 21597 | 2.16 | 0 | 0 | 9.3 | 5594
TS Fleet 5 | GG\21\014\X1 | GG | 21 | 14 | X1 | 1 Prestrip - Thick | 46.5147 | 46.5147 | 46.5147 | 2024-03-29 12:00 | 2024-04-01 07:04 | 131461.648 | 131462 | [7 empty] | 0 | 0 | 12.77 | 14.23 | 5160.09
TS5500Shv | GG\18\018\B | GG | 18 | 18 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-03-29 14:20 | 2024-03-31 07:41 | 50406.358 | [6 empty] | 50406 | 36730 | 3.68 | 0 | 0 | 11.23 | 5416
DRE2 | GG\18\022\B | GG | 18 | 22 | B | 6 DL | 100 | 0 | 100 | 2024-03-29 16:37 | 2024-04-02 05:53 | 256240.6772 |  |  |  |  | 256241 | 197108 |  |  | 0 | 20.97 | 0 | 18.46 | 4901.82
TS5500Shv | GG\18\019\B | GG | 18 | 19 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-03-31 07:41 | 2024-04-02 03:10 | 53035.5665 | [6 empty] | 53036 | 38378 | 3.84 | 0 | 0 | 12.22 | 5353
TS6060#1 | RS\41\005\X | RS | 41 | 5 | X | 1 Prestrip - Thick | 33.3844 | 33.3844 | 33.3844 | 2024-03-31 08:43 | 2024-04-05 16:47 | 128836.1452 | 128836 | [7 empty] | 0 | 0 | 13.1 | 10.72 | 5408.89
TS Fleet 5 | GG\21\018\X2 | GG | 21 | 18 | X2 | 1 Prestrip - Thick | 46.2283 | 0 | 46.2283 | 2024-04-01 07:04 | 2024-04-03 20:34 | 120537.43 | 120537 | [7 empty] | 0 | 0 | 12.08 | 0 | 0
DRE1 | RS\35\004\D | RS | 35 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-04-01 11:27 | 2024-04-05 11:31 | 326600.6035 |  |  |  | 16792 | 326601 | 263072 |  |  | 0 | 27.99 | 0 | 5.31 | 5953.62
TS5500Shv | RS\35\003\D | RS | 35 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-04-02 03:10 | 2024-04-04 04:24 | 60033.4213 | [6 empty] | 60033 | 44559 | 4.43 | 0 | 0 | 5.13 | 5969
DRE2 | GG\18\023\B | GG | 18 | 23 | B | 6 DL | 100 | 0 | 100 | 2024-04-02 05:53 | 2024-04-07 05:32 | 359520.3421 |  |  |  |  | 359520 | 276554 |  |  | 0 | 22.34 | 0 | 0 | 0
PH4100XPC#1 | GG\20\008\X1 | GG | 20 | 8 | X1 | 1 Prestrip - Thick | 100 | 54.2644 | 54.2644 | 2024-04-02 07:21 | 2024-04-09 05:08 | 369463.2514 | 369463 | [7 empty] | 0 | 0 | 36.86 | 12.62 | 5260.72
TS Fleet 5 | GG\21\019\B | GG | 21 | 19 | B | 1 Prestrip - Thick | 40.8307 | 40.8307 | 40.8307 | 2024-04-03 20:34 | 2024-04-06 12:42 | 125699.0254 | 125699 | [7 empty] | 0 | 0 | 12.72 | 12.76 | 5308.58
TS5500Shv | GG\20\007\X1 | GG | 20 | 7 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-04-04 04:24 | 2024-04-04 10:44 | 7713.1677 | [6 empty] | 7713 | 5668 | 0.57 | 0 | 0 | 11.72 | 5300
TS5500Shv | GG\18\020\B | GG | 18 | 20 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-04-04 10:44 | 2024-04-05 05:20 | 22683.8983 | [6 empty] | 22684 | 16143 | 1.62 | 0 | 0 | 14.96 | 5151
TS5500Shv | GG\18\021\B | GG | 18 | 21 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-04-05 05:20 | 2024-04-06 15:41 | 41889.5969 | [6 empty] | 41890 | 29442 | 3.01 | 0 | 0 | 16.55 | 5056
DRE1 | RS\35\005\D | RS | 35 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-04-05 11:31 | 2024-04-09 07:37 | 313140.9048 |  |  |  | 16100 | 313141 | 252230 |  |  | 0 | 26.84 | 0 | 5.59 | 5929.98
TS6060#1 | GG\20\007\X1 | GG | 20 | 7 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-04-05 16:47 | 2024-04-05 23:07 | 8560.7686 | [6 empty] | 8561 | 6290 | 0.63 | 0 | 0 | 11.72 | 5300
TS6060#1 | RS\42\003\X | RS | 42 | 3 | X | 1 Prestrip - Thick | 37.5211 | 37.5211 | 37.5211 | 2024-04-05 23:07 | 2024-04-10 05:15 | 102090.7273 | 102091 | [7 empty] | 0 | 0 | 10.3 | 11.87 | 5286.84
TS Fleet 5 | GG\20\007\X2 | GG | 20 | 7 | X2 | 1 Prestrip - Thick | 45.3511 | 0 | 45.3511 | 2024-04-06 12:42 | 2024-04-07 09:58 | 41681.8145 | 41682 | [7 empty] | 0 | 0 | 4.17 | 0 | 0
TS5500Shv | RS\35\004\D | RS | 35 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-04-06 15:41 | 2024-04-08 17:14 | 60417.5124 | [6 empty] | 60418 | 44784 | 4.48 | 0 | 0 | 5.31 | 5954
DRE2 | GG\17\013\D | GG | 17 | 13 | D | 6 DL | 100 | 100 | 100 | 2024-04-07 05:32 | 2024-04-15 10:11 | 590946.9547 |  |  |  | 13759 | 590947 | 261420 |  |  | 0 | 24.47 | 0 | 7.11 | 5763.83
PH4100A | RS\37\006\X | RS | 37 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-04-07 07:16 | 2024-04-23 14:19 | 660034.3616 | 660034 | [7 empty] | 0 | 0 | 55.22 | 10.6 | 5422.92
TS Fleet 5 | GG\21\020\B | GG | 21 | 20 | B | 1 Prestrip - Thick | 44.5954 | 44.5954 | 44.5954 | 2024-04-07 09:58 | 2024-04-09 14:04 | 102089.9086 | 102090 | [7 empty] | 0 | 0 | 9.87 | 15.62 | 5098.53
TS5500Shv | GG\18\022\B | GG | 18 | 22 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-04-08 17:14 | 2024-04-10 15:13 | 56070.3704 | [6 empty] | 56070 | 39024 | 3.92 | 0 | 0 | 18.46 | 4902
PH4100XPC#1 | GG\20\007\X2 | GG | 20 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.6489 | 2024-04-09 05:08 | 2024-04-10 03:19 | 50227.2425 | 50227 | [7 empty] | 0 | 0 | 5.02 | 0 | 0
DRE1 | RS\35\006\D | RS | 35 | 6 | D | 6 DL | 100 | 100 | 100 | 2024-04-09 07:37 | 2024-04-12 22:50 | 296531.7682 |  |  |  | 11109 | 296532 | 168387 |  |  | 0 | 26.02 | 0 | 5.78 | 5913.33
TS Fleet 5 | GG\21\021\B | GG | 21 | 21 | B | 1 Prestrip - Thick | 44.2169 | 44.2169 | 44.2169 | 2024-04-09 14:04 | 2024-04-12 16:28 | 145843.1058 | 145843 | [7 empty] | 0 | 0 | 16.27 | 19.73 | 4791.58
TS5500Exc | RS\37\005\X | RS | 37 | 5 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-04-09 15:44 | 2024-04-09 22:39 | 8707.4689 | [6 empty] | 8707 | 6171 | 0.62 | 0 | 0 | 11.3 | 5351
TS5500Exc | RS\36\006\X | RS | 36 | 6 | X | 8 Coal Mining | 100 | 0 | 100 | 2024-04-09 22:39 | 2024-04-10 14:03 | 19404.7466 | [6 empty] | 19405 | 13810 | 1.17 | 0 | 0 | 10.97 | 5388
PH4100XPC#1 | GG\20\007\B | GG | 20 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-04-10 03:19 | 2024-04-11 06:23 | 61278.7151 | 61279 | [7 empty] | 0 | 0 | 6.13 | 10.32 | 5457.86
TS6060#1 | RS\37\005\A | RS | 37 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-04-10 05:15 | 2024-04-11 18:40 | 38612.9097 | 38613 | [7 empty] | 0 | 0 | 3.86 | 14.57 | 5148.44
TS5500Exc | MW\56\005\D | MW | 56 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-04-10 14:03 | 2024-04-11 13:59 | 30148.5938 | [6 empty] | 30149 | 22309 | 2.23 | 0 | 0 | 9.3 | 5594
TS5500Shv | GG\20\008\X1 | GG | 20 | 8 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-04-10 15:13 | 2024-04-11 05:27 | 17361.2281 | [6 empty] | 17361 | 12640 | 1.26 | 0 | 0 | 12.62 | 5261
TS5500Shv | RS\35\005\D | RS | 35 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-04-11 05:27 | 2024-04-13 07:47 | 61374.5697 | [6 empty] | 61375 | 45424 | 4.54 | 0 | 0 | 5.59 | 5930
PH4100XPC#1 | GG\20\008\X2 | GG | 20 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 95.8964 | 2024-04-11 06:23 | 2024-04-12 18:14 | 81150.3834 | 81150 | [7 empty] | 0 | 0 | 8.11 | 0 | 0
TS5500Exc | MW\49\007\A | MW | 49 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-04-11 13:59 | 2024-04-23 18:20 | 258800.3259 | 258800 | [7 empty] | 0 | 0 | 28.16 | 12.61 | 5313.2
TS6060#1 | RS\36\006\A | RS | 36 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-04-11 18:40 | 2024-04-13 07:19 | 37818.0732 | 37818 | [7 empty] | 0 | 0 | 3.64 | 16.37 | 5010.42
TS Fleet 5 | GG\20\008\X2 | GG | 20 | 8 | X2 | 1 Prestrip - Thick | 45.3511 | 0 | 4.1036 | 2024-04-12 16:28 | 2024-04-12 18:14 | 3472.5916 | 3473 | [7 empty] | 0 | 0 | 0.35 | 0 | 0
TS Fleet 5 | GG\20\008\B | GG | 20 | 8 | B | 1 Prestrip - Thick | 45.3511 | 45.3511 | 45.3511 | 2024-04-12 18:14 | 2024-04-13 09:28 | 29839.3188 | 29839 | [7 empty] | 0 | 0 | 2.98 | 10.14 | 5494.75
PH4100XPC#1 | GG\20\008\B | GG | 20 | 8 | B | 1 Prestrip - Thick | 100 | 54.6489 | 54.6489 | 2024-04-12 18:14 | 2024-04-13 10:08 | 35956.8488 | 35957 | [7 empty] | 0 | 0 | 3.6 | 10.14 | 5494.75
DRE1 | MW\49\006\D | MW | 49 | 6 | D | 6 DL | 100 | 0 | 100 | 2024-04-12 22:50 | 2024-04-18 06:43 | 434799.9869 |  |  |  | 30922 | 434800 | 312657 |  |  | 0 | 35 | 0 | 6.7 | 5825
TS6060#1 | RS\41\006\X | RS | 41 | 6 | X | 1 Prestrip - Thick | 37.4493 | 37.4493 | 37.4493 | 2024-04-13 07:19 | 2024-04-20 21:08 | 183418.9361 | 183419 | [7 empty] | 0 | 0 | 17.53 | 9.7 | 5508.47
TS5500Shv | RS\36\006\A | RS | 36 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-04-13 07:47 | 2024-04-14 04:22 | 25101.1816 | [6 empty] | 25101 | 17419 | 1.71 | 0 | 0 | 16.37 | 5010
TS Fleet 5 | GG\21\022\B | GG | 21 | 22 | B | 1 Prestrip - Thick | 45.3091 | 45.3091 | 45.3091 | 2024-04-13 09:28 | 2024-04-15 10:36 | 96290.1211 | 96290 | [7 empty] | 0 | 0 | 10.54 | 20.7 | 4712.85
PH4100XPC#1 | GG\20\009\X1 | GG | 20 | 9 | X1 | 1 Prestrip - Thick | 100 | 46.1732 | 46.1732 | 2024-04-13 10:08 | 2024-04-18 15:52 | 289885.0239 | 289885 | [7 empty] | 0 | 0 | 33.03 | 14.27 | 5145.74
TS5500Shv | RS\37\005\A | RS | 37 | 5 | A | 8 Coal Mining | 32.1 | 0 | 32.1 | 2024-04-14 04:22 | 2024-04-14 17:02 | 15454.8395 | [6 empty] | 15455 | 10831 | 1.08 | 0 | 0 | 14.57 | 5148
TS5500Shv | RS\35\006\D | RS | 35 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2024-04-14 17:02 | 2024-04-16 08:52 | 42693.1857 |  |  | 42693 | [5 empty] | 0 | 0 | 0 | 5.78 | 5913.33
DRE2 | GG\17\018\D | GG | 17 | 18 | D | 6 DL | 100 | 100 | 100 | 2024-04-15 10:11 | 2024-04-22 14:33 | 517946.4468 |  |  |  | 12059 | 517946 | 229126 |  |  | 0 | 24.12 | 0 | 7.19 | 5756.78
TS Fleet 5 | GG\21\023\B | GG | 21 | 23 | B | 1 Prestrip - Thick | 44.4937 | 44.4937 | 44.4937 | 2024-04-15 10:36 | 2024-04-19 02:40 | 172611.9924 | 172612 | [7 empty] | 0 | 0 | 21.26 | 0 | 0
TS5500Shv | RS\35\006\D | RS | 35 | 6 | D | 8 Coal Mining | 34.7 | 0 | 34.7 | 2024-04-16 08:52 | 2024-04-16 23:46 | 18181.8091 | [6 empty] | 18182 | 13467 | 1.59 | 0 | 0 | 5.78 | 5913
TS5500Shv | MW\49\005\D | MW | 49 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-04-16 23:46 | 2024-04-19 01:36 | 60760.03 | [6 empty] | 60760 | 45503 | 4.55 | 0 | 0 | 7.44 | 5758
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2024-04-18 06:43 | 2024-04-21 06:43
PH4100XPC#1 | GG\20\010\B | GG | 20 | 10 | B | 1 Prestrip - Thick | 100 | 55.148 | 55.148 | 2024-04-18 15:52 | 2024-04-26 08:50 | 427208.2177 | 427208 | [7 empty] | 0 | 0 | 41.59 | 9.84 | 5536.87
TS5500Shv | GG\20\009\X1 | GG | 20 | 9 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-04-19 01:36 | 2024-04-19 06:56 | 6496.062 | [6 empty] | 6496 | 4673 | 0.48 | 0 | 0 | 14.27 | 5146
TS Fleet 5 | W1\01\003\D | W1 | 1 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-04-19 02:40 | 2024-05-09 14:10 | 963340.2614 | 963340 | [7 empty] | 0 | 0 | 47.78 | 7.33 | 5632.58
TS5500Shv | GG\17\013\D | GG | 17 | 13 | D | 8 Coal Mining | 45.4 | 0 | 45.4 | 2024-04-19 06:56 | 2024-04-20 09:24 | 32285.0757 | [6 empty] | 32285 | 24041 | 2.16 | 0 | 0 | 7.11 | 5764
TS5500Shv | MW\49\006\D | MW | 49 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-04-20 09:24 | 2024-04-22 13:08 | 63080.476 | [6 empty] | 63080 | 47511 | 4.75 | 0 | 0 | 6.7 | 5825
TS6060#1 | GG\20\009\X1 | GG | 20 | 9 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-04-20 21:08 | 2024-04-21 02:27 | 7209.9149 | [6 empty] | 7210 | 5186 | 0.53 | 0 | 0 | 14.27 | 5146
TS6060#1 | GG\17\013\D | GG | 17 | 13 | D | 8 Coal Mining | 54.6 | 0 | 54.6 | 2024-04-21 02:27 | 2024-04-22 07:08 | 38808.2746 | [6 empty] | 38808 | 28899 | 2.6 | 0 | 0 | 7.11 | 5764
DRE1 | MW\57\004\D | MW | 57 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-04-21 06:43 | 2024-04-22 17:43 | 119014.8923 |  |  |  | 4303 | 119015 | 67029 |  |  | 0 | 29.22 | 0 | 9.44 | 5570.45
TS6060#1 | RS\42\004\X | RS | 42 | 4 | X | 1 Prestrip - Thick | 30.302 | 30.302 | 30.302 | 2024-04-22 07:08 | 2024-04-26 10:16 | 98746.0418 | 98746 | [7 empty] | 0 | 0 | 10.14 | 11.37 | 5343.15
TS5500Shv | GG\20\009\X2 | GG | 20 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2024-04-22 13:08 | 2024-04-25 09:23 | 73164.236 | 73164 | [7 empty] | 0 | 0 | 7.38 | 0 | 0
DRE2 | GG\17\019\D | GG | 17 | 19 | D | 6 DL | 100 | 100 | 100 | 2024-04-22 14:33 | 2024-04-29 07:37 | 483992.5141 |  |  |  | 11269 | 483993 | 214106 |  |  | 0 | 22.54 | 0 | 7.01 | 5772.16
DRE1 | MW\57\005\D | MW | 57 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-04-22 17:43 | 2024-04-26 19:57 | 333982.8071 |  |  |  | 17171 | 333983 | 269018 |  |  | 0 | 29.28 | 0 | 9.29 | 5594.88
PH4100A | RS\37\004\B | RS | 37 | 4 | B | 1 Prestrip - Thick | 100 | 68.2404 | 68.2404 | 2024-04-23 14:19 | 2024-04-24 02:00 | 20286.5904 | 20287 | [7 empty] | 0 | 0 | 2.03 | 8.92 | 5604.91
TS5500Exc | RS\36\006\A | RS | 36 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-04-23 18:20 | 2024-04-24 14:55 | 25928.6931 | [6 empty] | 25929 | 17993 | 1.76 | 0 | 0 | 16.37 | 5010
PH4100A | RS\38\003\X | RS | 38 | 3 | X | 1 Prestrip - Thick | 100 | 62.4815 | 62.4815 | 2024-04-24 02:00 | 2024-04-28 04:58 | 164808.3987 | 164808 | [7 empty] | 0 | 0 | 22.31 | 11.99 | 5273.4
TS5500Exc | RS\37\005\A | RS | 37 | 5 | A | 8 Coal Mining | 67.9 | 0 | 67.9 | 2024-04-24 14:55 | 2024-04-25 16:49 | 32617.6031 | [6 empty] | 32618 | 22860 | 2.29 | 0 | 0 | 14.57 | 5148
TS5500Shv | RS\37\004\B | RS | 37 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-04-25 09:23 | 2024-04-26 01:07 | 19181.982 | [6 empty] | 19182 | 13829 | 1.39 | 0 | 0 | 8.92 | 5605
TS5500Exc | RS\37\004\B | RS | 37 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-04-25 16:49 | 2024-04-26 08:33 | 19814.3551 | [6 empty] | 19814 | 14285 | 1.43 | 0 | 0 | 8.92 | 5605
TS5500Shv | RS\37\006\X | RS | 37 | 6 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-04-26 01:07 | 2024-04-26 08:56 | 9532.5976 | [6 empty] | 9533 | 6807 | 0.59 | 0 | 0 | 10.6 | 5423
TS5500Exc | RS\37\006\X | RS | 37 | 6 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-04-26 08:33 | 2024-04-26 16:22 | 9846.8591 | [6 empty] | 9847 | 7031 | 0.6 | 0 | 0 | 10.6 | 5423
PH4100XPC#1 | GG\20\009\B | GG | 20 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-04-26 08:50 | 2024-04-27 19:20 | 78079.5436 | 78080 | [7 empty] | 0 | 0 | 7.81 | 9.92 | 5527.05
TS5500Shv | MW\57\004\D | MW | 57 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2024-04-26 08:56 | 2024-04-26 22:41 | 14730.0567 |  |  | 14730 | [5 empty] | 0 | 0 | 0 | 9.44 | 5570.45
TS6060#1 | RS\36\006\B | RS | 36 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-04-26 10:16 | 2024-04-27 23:03 | 37954.0669 | 37954 | [7 empty] | 0 | 0 | 3.73 | 9.08 | 5596.5
TS5500Exc | RS\35\006\D | RS | 35 | 6 | D | 8 Coal Mining | 65.3 | 0 | 65.3 | 2024-04-26 16:22 | 2024-04-27 19:30 | 34182.1328 | [6 empty] | 34182 | 25319 | 2.99 | 0 | 0 | 5.78 | 5913
DRE1 | RS\36\003\D | RS | 36 | 3 | D | 6 DL | 100 | 100 | 100 | 2024-04-26 19:57 | 2024-04-30 23:39 | 338969.3227 |  |  |  | 17428 | 338969 | 273034 |  |  | 0 | 27.44 | 0 | 5.16 | 5966.85
TS5500Shv | MW\57\004\D | MW | 57 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-04-26 22:41 | 2024-04-27 08:04 | 11446.7568 | [6 empty] | 11447 | 8452 | 3.06 | 0 | 0 | 9.44 | 5570
TS5500Shv | MW\57\005\D | MW | 57 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-04-27 08:04 | 2024-04-29 08:18 | 58821.6045 | [6 empty] | 58822 | 43525 | 4.35 | 0 | 0 | 9.29 | 5595
PH4100XPC#1 | GG\20\011\X1 | GG | 20 | 11 | X1 | 1 Prestrip - Thick | 100 | 54.2929 | 54.2929 | 2024-04-27 19:20 | 2024-05-02 10:41 | 248440.7578 | 248441 | [7 empty] | 0 | 0 | 24.74 | 14.64 | 5126.47
TS5500Exc | MW\49\007\A | MW | 49 | 7 | A | 8 Coal Mining | 83.7 | 0 | 83.7 | 2024-04-27 19:30 | 2024-04-28 16:53 | 26931.3378 | [6 empty] | 26931 | 19575 | 1.97 | 0 | 0 | 12.61 | 5313
TS6060#1 | GG\17\018\D | GG | 17 | 18 | D | 8 Coal Mining | 60.8 | 0 | 60.8 | 2024-04-27 23:03 | 2024-04-29 04:05 | 39299.1158 | [6 empty] | 39299 | 29242 | 2.92 | 0 | 0 | 7.19 | 5757
PH4100A | RS\37\006\A | RS | 37 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-04-28 04:58 | 2024-04-29 03:08 | 38480.7115 | 38481 | [7 empty] | 0 | 0 | 3.75 | 16.15 | 5028.47
TS5500Exc | RS\38\003\X | RS | 38 | 3 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-04-28 16:53 | 2024-04-28 21:55 | 6339.1952 | [6 empty] | 6339 | 4462 | 0.56 | 0 | 0 | 11.99 | 5273
TS5500Exc | MW\49\008\A | MW | 49 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-04-28 21:55 | 2024-05-12 19:20 | 295101.6461 | 295102 | [7 empty] | 0 | 0 | 30.84 | 12.05 | 5361.48
PH4100A | RS\37\005\B | RS | 37 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-04-29 03:08 | 2024-04-29 22:47 | 34088.7252 | 34089 | [7 empty] | 0 | 0 | 3.41 | 8.98 | 5606.36
TS6060#1 | RS\42\005\X | RS | 42 | 5 | X | 1 Prestrip - Thick | 37.4817 | 37.4817 | 37.4817 | 2024-04-29 04:05 | 2024-05-04 18:52 | 135396.1082 | 135396 | [7 empty] | 0 | 0 | 13.83 | 10.64 | 5416.14
DRE2 | GG\17\020\D | GG | 17 | 20 | D | 6 DL | 100 | 100 | 100 | 2024-04-29 07:37 | 2024-05-04 19:24 | 396031.4763 |  |  |  | 7375 | 396031 | 176997 |  |  | 0 | 18.54 | 0 | 6.86 | 5785.13
TS5500Shv | RS\36\006\B | RS | 36 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-04-29 08:18 | 2024-04-30 18:27 | 41645.483 | [6 empty] | 41645 | 29949 | 2.96 | 0 | 0 | 9.08 | 5597
PH4100A | RS\39\003\X | RS | 39 | 3 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-04-29 22:47 | 2024-05-06 21:56 | 278422.7787 | 278423 | [7 empty] | 0 | 0 | 34.62 | 11.97 | 5276.5
TS5500Shv | RS\37\006\A | RS | 37 | 6 | A | 8 Coal Mining | 6.7 | 0 | 6.7 | 2024-04-30 18:27 | 2024-04-30 21:13 | 3375.4553 | [6 empty] | 3375 | 2345 | 0.23 | 0 | 0 | 16.15 | 5028
TS5500Shv | RS\38\003\X | RS | 38 | 3 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-04-30 21:13 | 2024-05-01 02:15 | 6136.8805 | [6 empty] | 6137 | 4320 | 0.54 | 0 | 0 | 11.99 | 5273
DRE1 | RS\36\004\D | RS | 36 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-04-30 23:39 | 2024-05-04 23:06 | 324509.6682 |  |  |  | 16684 | 324510 | 261387 |  |  | 0 | 27.81 | 0 | 5.34 | 5951.2
TS5500Shv | RS\36\003\D | RS | 36 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-05-01 02:15 | 2024-05-03 06:28 | 63662.5944 | [6 empty] | 63663 | 47300 | 4.44 | 0 | 0 | 5.16 | 5967
PH4100XPC#1 | GG\20\012\X1 | GG | 20 | 12 | X1 | 1 Prestrip - Thick | 100 | 54.1225 | 54.1225 | 2024-05-02 10:41 | 2024-05-06 13:03 | 217985.7187 | 217986 | [7 empty] | 0 | 0 | 21.21 | 14.4 | 5146.87
TS5500Shv | GG\17\018\D | GG | 17 | 18 | D | 8 Coal Mining | 39.2 | 0 | 39.2 | 2024-05-03 06:28 | 2024-05-04 03:17 | 25384.3736 | [6 empty] | 25384 | 18888 | 1.89 | 0 | 0 | 7.19 | 5757
TS5500Shv | MW\49\007\A | MW | 49 | 7 | A | 8 Coal Mining | 16.3 | 0 | 16.3 | 2024-05-04 03:17 | 2024-05-04 07:35 | 5257.1423 | [6 empty] | 5257 | 3821 | 0.38 | 0 | 0 | 12.61 | 5313
TS5500Shv | GG\17\019\D | GG | 17 | 19 | D | 8 Coal Mining | 83.2 | 0 | 83.2 | 2024-05-04 07:35 | 2024-05-06 03:11 | 53161.9794 | [6 empty] | 53162 | 39587 | 3.96 | 0 | 0 | 7.01 | 5772
TS6060#1 | GG\20\011\X1 | GG | 20 | 11 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-05-04 18:52 | 2024-05-05 07:31 | 17124.5177 | [6 empty] | 17125 | 12267 | 1.24 | 0 | 0 | 14.64 | 5126
DRE2 | GG\17\021\D | GG | 17 | 21 | D | 6 DL | 100 | 100 | 100 | 2024-05-04 19:24 | 2024-05-10 14:57 | 419334.0043 |  |  |  | 7809 | 419334 | 187412 |  |  | 0 | 19.52 | 0 | 6.81 | 5790.47
DRE1 | RS\36\005\D | RS | 36 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-05-04 23:06 | 2024-05-08 18:18 | 310102.9692 |  |  |  | 15944 | 310103 | 249783 |  |  | 0 | 26.58 | 0 | 5.61 | 5928.22
TS6060#1 | RS\38\003\A | RS | 38 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-05 07:31 | 2024-05-11 15:32 | 156852.7715 | 156853 | [7 empty] | 0 | 0 | 19 | 11.61 | 5373.07
TS5500Shv | RS\36\004\D | RS | 36 | 4 | D | 8 Coal Mining | 39.4 | 0 | 39.4 | 2024-05-06 03:11 | 2024-05-06 22:41 | 23770.8845 | [6 empty] | 23771 | 17620 | 1.76 | 0 | 0 | 5.34 | 5951
PH4100XPC#1 | GG\20\011\X2 | GG | 20 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2024-05-06 13:03 | 2024-05-07 20:54 | 72106.685 | 72107 | [7 empty] | 0 | 0 | 7.28 | 0 | 0
PH4100A | RS\38\004\X | RS | 38 | 4 | X | 1 Prestrip - Thick | 100 | 38.4275 | 38.4275 | 2024-05-06 21:56 | 2024-05-11 00:48 | 165678.8355 | 165679 | [7 empty] | 0 | 0 | 16.77 | 11.69 | 5309.09
TS5500Shv | GG\20\012\X1 | GG | 20 | 12 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-05-06 22:41 | 2024-05-07 11:49 | 16011.701 | [6 empty] | 16012 | 11492 | 1.16 | 0 | 0 | 14.4 | 5147
TS5500Shv | RS\39\003\X | RS | 39 | 3 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-05-07 11:49 | 2024-05-07 17:12 | 6560.9276 | [6 empty] | 6561 | 4621 | 0.53 | 0 | 0 | 11.97 | 5277
TS5500Shv | GG\17\020\D | GG | 17 | 20 | D | 8 Coal Mining | 60.7 | 0 | 60.7 | 2024-05-07 17:12 | 2024-05-09 00:47 | 38515.8854 | [6 empty] | 38516 | 28703 | 2.87 | 0 | 0 | 6.86 | 5785
PH4100XPC#1 | GG\20\011\B | GG | 20 | 11 | B | 1 Prestrip - Thick | 100 | 89.0873 | 89.0873 | 2024-05-07 20:54 | 2024-05-09 20:57 | 108776.8531 | 108777 | [7 empty] | 0 | 0 | 10.92 | 9.77 | 5538.76
DRE1 | RS\36\006\D | RS | 36 | 6 | D | 6 DL | 100 | 100 | 100 | 2024-05-08 18:18 | 2024-05-12 08:41 | 293722.7677 |  |  |  | 11009 | 293723 | 166810 |  |  | 0 | 25.98 | 0 | 5.79 | 5912.68
TS5500Shv | RS\36\005\D | RS | 36 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-05-09 00:47 | 2024-05-11 02:57 | 61188.8373 | [6 empty] | 61189 | 45322 | 4.53 | 0 | 0 | 5.61 | 5928
TS Fleet 5 | GG\20\011\B | GG | 20 | 11 | B | 1 Prestrip - Thick | 45.3511 | 10.9127 | 10.9127 | 2024-05-09 14:10 | 2024-05-09 20:57 | 13324.5627 | 13325 | [7 empty] | 0 | 0 | 1.34 | 9.77 | 5538.76
TS Fleet 5 | GG\20\012\X2 | GG | 20 | 12 | X2 | 1 Prestrip - Thick | 45.3511 | 0 | 45.3511 | 2024-05-09 20:57 | 2024-05-10 14:01 | 33444.7078 | 33445 | [7 empty] | 0 | 0 | 3.38 | 0 | 0
PH4100XPC#1 | GG\20\012\X2 | GG | 20 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.6489 | 2024-05-09 20:57 | 2024-05-10 14:46 | 40301.3992 | 40301 | [7 empty] | 0 | 0 | 4.08 | 0 | 0
TS Fleet 5 | W1\01\004\D | W1 | 1 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-10 14:01 | 2024-05-31 10:40 | 981280.7563 | 981281 | [7 empty] | 0 | 0 | 33.77 | 7.43 | 5620.98
PH4100XPC#1 | GG\20\012\B | GG | 20 | 12 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-10 14:46 | 2024-05-13 02:23 | 134953.547 | 134954 | [7 empty] | 0 | 0 | 13.56 | 10.44 | 5477.43
DRE2 | GG\17\022\D | GG | 17 | 22 | D | 6 DL | 100 | 100 | 100 | 2024-05-10 14:57 | 2024-05-16 09:05 | 415044.4288 |  |  |  | 7729 | 415044 | 185495 |  |  | 0 | 19.33 | 0 | 6.68 | 5800.56
PH4100A | RS\39\004\X | RS | 39 | 4 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-11 00:48 | 2024-05-21 09:37 | 416375.1386 | 416375 | [7 empty] | 0 | 0 | 42.37 | 11.6 | 5318.24
TS5500Shv | RS\38\004\X | RS | 38 | 4 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-05-11 02:57 | 2024-05-11 09:46 | 8310.0647 | [6 empty] | 8310 | 5869 | 0.59 | 0 | 0 | 11.69 | 5309
TS5500Shv | GG\17\021\D | GG | 17 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-05-11 09:46 | 2024-05-13 14:29 | 64282.21 | [6 empty] | 64282 | 47868 | 4.79 | 0 | 0 | 6.81 | 5790
TS6060#1 | GG\17\019\D | GG | 17 | 19 | D | 8 Coal Mining | 16.8 | 0 | 16.8 | 2024-05-11 15:32 | 2024-05-11 23:28 | 10743.8704 | [6 empty] | 10744 | 8000 | 0.8 | 0 | 0 | 7.01 | 5772
TS6060#1 | GG\17\020\D | GG | 17 | 20 | D | 8 Coal Mining | 39.3 | 0 | 39.3 | 2024-05-11 23:28 | 2024-05-12 17:54 | 24936.0012 | [6 empty] | 24936 | 18583 | 1.86 | 0 | 0 | 6.86 | 5785
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2024-05-12 08:41 | 2024-05-15 08:41
TS6060#1 | RS\42\006\X | RS | 42 | 6 | X | 1 Prestrip - Thick | 37.4561 | 37.4561 | 37.4561 | 2024-05-12 17:54 | 2024-05-18 20:39 | 147931.0748 | 147931 | [7 empty] | 0 | 0 | 16.7 | 9.68 | 5510.24
TS5500Exc | RS\37\005\B | RS | 37 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-05-12 19:20 | 2024-05-14 03:21 | 40323.7959 | [6 empty] | 40324 | 29036 | 2.91 | 0 | 0 | 8.98 | 5606
PH4100XPC#1 | GG\20\013\X1 | GG | 20 | 13 | X1 | 1 Prestrip - Thick | 100 | 43.5143 | 43.5143 | 2024-05-13 02:23 | 2024-05-15 21:25 | 146968.4121 | 146968 | [7 empty] | 0 | 0 | 14.48 | 14.2 | 5163.11
TS5500Shv | RS\38\003\A | RS | 38 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-05-13 14:29 | 2024-05-14 23:37 | 40403.7439 | [6 empty] | 40404 | 28791 | 3.25 | 0 | 0 | 11.61 | 5373
TS5500Exc | RS\37\006\A | RS | 37 | 6 | A | 8 Coal Mining | 93.3 | 0 | 93.3 | 2024-05-14 03:21 | 2024-05-15 16:28 | 46757.3066 | [6 empty] | 46757 | 32486 | 3.22 | 0 | 0 | 16.15 | 5028
TS5500Shv | RS\36\006\D | RS | 36 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2024-05-14 23:37 | 2024-05-16 15:09 | 42368.7011 |  |  | 42369 | [5 empty] | 0 | 0 | 0 | 5.79 | 5912.68
DRE1 | MW\58\004\D | MW | 58 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-05-15 08:41 | 2024-05-16 08:38 | 81401.2363 |  |  |  | 2776 | 81401 | 49463 |  |  | 0 | 19.93 | 0 | 9.28 | 5585.52
TS5500Exc | RS\38\004\X | RS | 38 | 4 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-05-15 16:28 | 2024-05-15 23:17 | 8584.0229 | [6 empty] | 8584 | 6062 | 0.61 | 0 | 0 | 11.69 | 5309
PH4100XPC#1 | GG\20\014\X1 | GG | 20 | 14 | X1 | 1 Prestrip - Thick | 100 | 53.5197 | 53.5197 | 2024-05-15 21:25 | 2024-05-18 07:23 | 125375.816 | 125376 | [7 empty] | 0 | 0 | 14.37 | 14.22 | 5162.02
TS5500Exc | RS\39\003\X | RS | 39 | 3 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-05-15 23:17 | 2024-05-16 04:40 | 6777.222 | [6 empty] | 6777 | 4773 | 0.55 | 0 | 0 | 11.97 | 5277
TS5500Exc | RS\36\004\D | RS | 36 | 4 | D | 8 Coal Mining | 60.6 | 0 | 60.6 | 2024-05-16 04:40 | 2024-05-17 09:39 | 36517.4673 | [6 empty] | 36517 | 27068 | 2.71 | 0 | 0 | 5.34 | 5951
DRE1 | MW\58\005\D | MW | 58 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-05-16 08:38 | 2024-05-21 15:07 | 430057.493 |  |  |  | 22111 | 430057 | 346404 |  |  | 0 | 27.57 | 0 | 9.04 | 5617.27
DRE2 | GG\17\023\D | GG | 17 | 23 | D | 6 DL | 100 | 100 | 100 | 2024-05-16 09:05 | 2024-05-23 12:17 | 514459.9996 |  |  |  | 8698 | 514460 | 148482 |  |  | 0 | 18.04 | 0 | 6.43 | 5822.58
TS5500Shv | GG\20\013\X1 | GG | 20 | 13 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-05-16 15:09 | 2024-05-16 20:56 | 7060.8297 | [6 empty] | 7061 | 5078 | 0.52 | 0 | 0 | 14.2 | 5163
TS5500Shv | MW\58\004\D | MW | 58 | 4 | D | 7 PostStrip | 87.9664 | 0 | 87.9664 | 2024-05-16 20:56 | 2024-05-17 11:01 | 15096.8894 |  |  | 15097 | [5 empty] | 0 | 0 | 0 | 9.28 | 5585.52
TS5500Exc | RS\36\006\D | RS | 36 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-05-17 09:39 | 2024-05-19 03:00 | 52068.658 | [6 empty] | 52069 | 38568 | 4.59 | 0 | 0 | 5.79 | 5913
TS5500Shv | GG\17\022\D | GG | 17 | 22 | D | 8 Coal Mining | 97.5 | 0 | 97.5 | 2024-05-17 11:01 | 2024-05-19 13:31 | 61567.5578 | [6 empty] | 61568 | 45919 | 4.59 | 0 | 0 | 6.68 | 5801
PH4100XPC#1 | GG\20\018\X2 | GG | 20 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 48.061 | 2024-05-18 07:23 | 2024-05-20 17:43 | 127554.8405 | 127555 | [7 empty] | 0 | 0 | 12.85 | 0 | 0
TS6060#1 | GG\20\013\X1 | GG | 20 | 13 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-05-18 20:39 | 2024-05-19 02:27 | 7836.7451 | [6 empty] | 7837 | 5636 | 0.58 | 0 | 0 | 14.2 | 5163
TS6060#1 | GG\20\014\X1 | GG | 20 | 14 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-05-19 02:27 | 2024-05-19 10:57 | 11514.2703 | [6 empty] | 11514 | 8288 | 1 | 0 | 0 | 14.22 | 5162
TS5500Exc | MW\49\007\B | MW | 49 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-19 03:00 | 2024-05-20 11:33 | 28790.5799 | 28791 | [7 empty] | 0 | 0 | 2.89 | 9.7 | 5530.21
TS6060#1 | RS\38\004\A | RS | 38 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-19 10:57 | 2024-05-26 18:09 | 180764.5999 | 180765 | [7 empty] | 0 | 0 | 18.1 | 12.55 | 5303.37
TS5500Shv | MW\49\008\A | MW | 49 | 8 | A | 8 Coal Mining | 38.6 | 0 | 38.6 | 2024-05-19 13:31 | 2024-05-20 03:38 | 17217.4734 | [6 empty] | 17217 | 12555 | 1.32 | 0 | 0 | 12.05 | 5361
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 07:55 |  | 0d 07:55 | 2024-05-20 03:38 | 2024-05-20 11:33
TS5500Exc | MW\49\007\B | MW | 49 | 7 | B | 8 Coal Mining | 69.4 | 0 | 69.4 | 2024-05-20 11:33 | 2024-05-21 06:24 | 23749.6778 | [6 empty] | 23750 | 17504 | 1.75 | 0 | 0 | 9.7 | 5530
TS5500Shv | MW\49\007\B | MW | 49 | 7 | B | 8 Coal Mining | 30.6 | 0 | 30.6 | 2024-05-20 11:33 | 2024-05-20 20:08 | 10461.3906 | [6 empty] | 10461 | 7710 | 0.77 | 0 | 0 | 9.7 | 5530
PH4100XPC#1 | GG\20\013\X2 | GG | 20 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2024-05-20 17:43 | 2024-05-22 03:06 | 75564.358 | 75564 | [7 empty] | 0 | 0 | 7.7 | 0 | 0
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 13:30 |  | 0d 13:30 | 2024-05-20 20:08 | 2024-05-21 09:37
TS5500Exc | MW\49\008\A | MW | 49 | 8 | A | 8 Coal Mining | 61.4 | 0 | 61.4 | 2024-05-21 06:24 | 2024-05-22 04:09 | 27381.8943 | [6 empty] | 27382 | 19966 | 2.09 | 0 | 0 | 12.05 | 5361
PH4100A | RS\37\006\B | RS | 37 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-21 09:37 | 2024-05-22 06:30 | 36252.7144 | 36253 | [7 empty] | 0 | 0 | 3.61 | 9.09 | 5596.99
TS5500Shv | RS\39\004\X | RS | 39 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2024-05-21 09:37 | 2024-05-21 23:58 | 17502.4025 | [6 empty] | 17502 | 12369 | 1.24 | 0 | 0 | 11.6 | 5318
DRE1 | MW\49\007\D | MW | 49 | 7 | D | 6 DL | 100 | 100 | 100 | 2024-05-21 15:07 | 2024-05-25 20:06 | 343325.7353 |  |  |  | 17652 | 343326 | 276543 |  |  | 0 | 29.43 | 0 | 5.87 | 5897.86
TS5500Shv | MW\58\005\D | MW | 58 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-05-21 23:58 | 2024-05-23 04:35 | 34891.6098 | [6 empty] | 34892 | 25881 | 2.13 | 0 | 0 | 9.04 | 5617
PH4100XPC#1 | GG\20\013\B | GG | 20 | 13 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-22 03:06 | 2024-05-24 17:41 | 141689.5481 | 141690 | [7 empty] | 0 | 0 | 14.23 | 11.3 | 5400.04
TS5500Exc | MW\58\005\D | MW | 58 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-05-22 04:09 | 2024-05-23 08:45 | 36041.8826 | [6 empty] | 36042 | 26734 | 2.2 | 0 | 0 | 9.04 | 5617
PH4100A | RS\38\005\X | RS | 38 | 5 | X | 1 Prestrip - Thick | 100 | 25.454 | 25.454 | 2024-05-22 06:30 | 2024-05-25 03:49 | 116746.3881 | 116746 | [7 empty] | 0 | 0 | 11.86 | 11.11 | 5369.03
TS5500Shv | RS\37\006\B | RS | 37 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-05-23 04:35 | 2024-05-24 14:19 | 41135.0448 | [6 empty] | 41135 | 29582 | 2.95 | 0 | 0 | 9.09 | 5597
TS5500Exc | MW\49\008\B | MW | 49 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-23 08:45 | 2024-05-24 14:59 | 26728.9162 | 26729 | [7 empty] | 0 | 0 | 2.82 | 9.34 | 5561.86
DRE2 | GG\19\012\B | GG | 19 | 12 | B | 6 DL | 100 | 0 | 100 | 2024-05-23 12:17 | 2024-05-26 04:01 | 191542.7767 |  |  |  |  | 191543 | 159619 |  |  | 0 | 16.04 | 0 | 10.11 | 5503.65
TS5500Shv | GG\17\023\D | GG | 17 | 23 | D | 7 PostStrip | 52.9909 | 0 | 52.9909 | 2024-05-24 14:19 | 2024-05-25 20:07 | 31935.6517 |  |  | 31936 | [5 empty] | 0 | 0 | 0 | 6.43 | 5822.58
TS5500Exc | MW\49\008\B | MW | 49 | 8 | B | 8 Coal Mining | 57.6 | 0 | 57.6 | 2024-05-24 14:59 | 2024-05-25 07:56 | 21354.1307 | [6 empty] | 21354 | 15779 | 1.67 | 0 | 0 | 9.34 | 5562
PH4100XPC#1 | GG\20\014\X2 | GG | 20 | 14 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2024-05-24 17:41 | 2024-05-25 22:06 | 64316.654 | 64317 | [7 empty] | 0 | 0 | 7.94 | 0 | 0
PH4100A | RS\39\005\X | RS | 39 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-25 03:49 | 2024-06-04 18:13 | 428172.0437 | 428172 | [7 empty] | 0 | 0 | 43.57 | 10.95 | 5384.99
TS5500Exc | MW\50\004\D | MW | 50 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-25 07:56 | 2024-06-01 16:40 | 156325.854 | 156326 | [7 empty] | 0 | 0 | 54.63 | 7.94 | 5708.08
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 4d 00:00 |  | 4d 00:00 | 2024-05-25 20:06 | 2024-05-29 20:06
TS5500Shv | RS\38\005\X | RS | 38 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2024-05-25 20:07 | 2024-05-26 10:54 | 18026.8094 | [6 empty] | 18027 | 12804 | 1.28 | 0 | 0 | 11.11 | 5369
PH4100XPC#1 | GG\20\014\B | GG | 20 | 14 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-25 22:06 | 2024-05-27 23:16 | 111268.7319 | 111269 | [7 empty] | 0 | 0 | 15.97 | 11.98 | 5344.17
DRE2 | GG\19\011\B | GG | 19 | 11 | B | 6 DL | 100 | 0 | 100 | 2024-05-26 04:01 | 2024-05-29 04:31 | 217853.9161 |  |  |  |  | 217854 | 167580 |  |  | 0 | 16.82 | 0 | 9.51 | 5557.94
TS5500Shv | MW\49\007\D | MW | 49 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-05-26 10:54 | 2024-05-28 15:33 | 64199.0439 | [6 empty] | 64199 | 48627 | 4.86 | 0 | 0 | 5.87 | 5898
TS6060#1 | RS\38\003\B | RS | 38 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-26 18:09 | 2024-05-27 20:12 | 26878.0424 | 26878 | [7 empty] | 0 | 0 | 2.97 | 9.06 | 5580.37
TS6060#1 | RS\38\005\A | RS | 38 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-27 20:12 | 2024-06-03 23:56 | 177200.1275 | 177200 | [7 empty] | 0 | 0 | 17.71 | 14.24 | 5175.25
PH4100XPC#1 | GG\20\018\B | GG | 20 | 18 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-27 23:16 | 2024-05-30 14:25 | 142944.621 | 142945 | [7 empty] | 0 | 0 | 14.29 | 11.85 | 5362.79
TS5500Shv | RS\38\004\A | RS | 38 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-05-28 15:33 | 2024-05-30 05:34 | 46369.9511 | [6 empty] | 46370 | 32846 | 3.29 | 0 | 0 | 12.55 | 5303
DRE2 | GG\19\010\B | GG | 19 | 10 | B | 6 DL | 100 | 0 | 100 | 2024-05-29 04:31 | 2024-06-01 07:02 | 223910.6732 |  |  |  |  | 223911 | 186592 |  |  | 0 | 18.66 | 0 | 9.7 | 5544.38
DRE1 | RS\37\003\D | RS | 37 | 3 | D | 6 DL | 100 | 100 | 100 | 2024-05-29 20:06 | 2024-06-03 06:02 | 360150.781 |  |  |  | 18517 | 360151 | 290096 |  |  | 0 | 27.47 | 0 | 5.19 | 5965.21
TS5500Shv | RS\38\003\B | RS | 38 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-05-30 05:34 | 2024-05-31 10:07 | 34799.4663 | [6 empty] | 34799 | 25100 | 2.73 | 0 | 0 | 9.06 | 5580
PH4100XPC#1 | GG\20\019\B | GG | 20 | 19 | B | 1 Prestrip - Thick | 100 | 54.3949 | 54.3949 | 2024-05-30 14:25 | 2024-06-02 18:13 | 169851.7567 | 169852 | [7 empty] | 0 | 0 | 17.21 | 12.63 | 5319.92
TS5500Shv | GG\19\012\B | GG | 19 | 12 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-05-31 10:07 | 2024-06-01 05:08 | 23204.8584 | [6 empty] | 23205 | 17023 | 1.71 | 0 | 0 | 10.11 | 5504
TS Fleet 5 | W1\01\005\D | W1 | 1 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-05-31 10:40 | 2024-06-15 20:22 | 724599.0821 | 724599 | [7 empty] | 0 | 0 | 31.66 | 7.39 | 5606.77
TS5500Shv | GG\19\011\B | GG | 19 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-06-01 05:08 | 2024-06-02 21:28 | 49170.103 | [6 empty] | 49170 | 36175 | 3.63 | 0 | 0 | 9.51 | 5558
DRE2 | GG\19\009\B | GG | 19 | 9 | B | 6 DL | 100 | 0 | 100 | 2024-06-01 07:02 | 2024-06-04 12:46 | 233599.6433 |  |  |  |  | 233600 | 194666 |  |  | 0 | 19.47 | 0 | 9.87 | 5529.47
TS5500Exc | MW\50\005\D | MW | 50 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-06-01 16:40 | 2024-06-18 00:30 | 346590.0627 | 346590 | [7 empty] | 0 | 0 | 37.27 | 7.87 | 5720.64
PH4100XPC#1 | GG\20\020\B | GG | 20 | 20 | B | 1 Prestrip - Thick | 100 | 55.6056 | 55.6056 | 2024-06-02 18:13 | 2024-06-05 03:22 | 134455.2908 | 134455 | [7 empty] | 0 | 0 | 12.37 | 15.57 | 5101.72
TS5500Shv | GG\19\010\B | GG | 19 | 10 | B | 8 Coal Mining | 49.7 | 0 | 49.7 | 2024-06-02 21:28 | 2024-06-03 17:48 | 24807.2133 | [6 empty] | 24807 | 18230 | 1.82 | 0 | 0 | 9.7 | 5544
DRE1 | MW\50\004\D | MW | 50 | 4 | D | 6 DL | 100 | 0 | 100 | 2024-06-03 06:02 | 2024-06-05 07:35 | 168476.1359 |  |  |  | 9060 | 168476 | 77679 |  |  | 0 | 35 | 0 | 7.94 | 5708.08
TS5500Shv | RS\37\003\D | RS | 37 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-06-03 17:48 | 2024-06-06 01:18 | 67661.6712 | [6 empty] | 67662 | 50321 | 4.45 | 0 | 0 | 5.19 | 5965
TS6060#1 | MW\58\004\D | MW | 58 | 4 | D | 7 PostStrip | 12.0336 | 0 | 12.0336 | 2024-06-03 23:56 | 2024-06-04 01:56 | 2065.2146 |  |  | 2065 | [5 empty] | 0 | 0 | 0 | 9.28 | 5585.52
TS6060#1 | RS\38\004\B | RS | 38 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-06-04 01:56 | 2024-06-05 07:14 | 30225.0473 | 30225 | [7 empty] | 0 | 0 | 3.03 | 8.96 | 5602.65
DRE2 | GG\19\008\B | GG | 19 | 8 | B | 6 DL | 100 | 0 | 100 | 2024-06-04 12:46 | 2024-06-07 20:37 | 239919.6115 |  |  |  |  | 239920 | 199933 |  |  | 0 | 20 | 0 | 10.13 | 5495.07
PH4100A | RS\38\006\X | RS | 38 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-06-04 18:13 | 2024-06-20 05:12 | 625963.2219 | 625963 | [7 empty] | 0 | 0 | 53.1 | 10.27 | 5454.09
PH4100XPC#1 | GG\20\021\B | GG | 20 | 21 | B | 1 Prestrip - Thick | 100 | 52.2065 | 52.2065 | 2024-06-05 03:22 | 2024-06-08 07:53 | 180328.8356 | 180329 | [7 empty] | 0 | 0 | 20.41 | 18.66 | 4881.61
TS6060#1 | RS\39\003\A | RS | 39 | 3 | A | 1 Prestrip - Thick | 85.6083 | 85.6083 | 85.6083 | 2024-06-05 07:14 | 2024-06-11 01:58 | 143142.97 | 143143 | [7 empty] | 0 | 0 | 16.07 | 11.92 | 5350.55
DRE1 | RS\37\004\D | RS | 37 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-06-05 07:35 | 2024-06-09 06:22 | 322285.0839 |  |  |  | 16570 | 322285 | 259596 |  |  | 0 | 27.62 | 0 | 5.38 | 5947.48
TS5500Shv | MW\58\004\D | MW | 58 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-06-06 01:18 | 2024-06-06 11:54 | 12930.6868 | [6 empty] | 12931 | 9556 | 3.15 | 0 | 0 | 9.28 | 5586
TS5500Shv | RS\38\005\A | RS | 38 | 5 | A | 8 Coal Mining | 14.1 | 0 | 14.1 | 2024-06-06 11:54 | 2024-06-06 17:26 | 6741.0285 | [6 empty] | 6741 | 4729 | 0.47 | 0 | 0 | 14.24 | 5175
TS5500Shv | RS\38\004\B | RS | 38 | 4 | B | 8 Coal Mining | 22.8 | 0 | 22.8 | 2024-06-06 17:26 | 2024-06-07 00:43 | 8896.5103 | [6 empty] | 8897 | 6414 | 0.64 | 0 | 0 | 8.96 | 5603
TS5500Shv | GG\19\009\B | GG | 19 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-06-07 00:43 | 2024-06-08 18:55 | 51449.9145 | [6 empty] | 51450 | 37738 | 3.78 | 0 | 0 | 9.87 | 5529
DRE2 | GG\19\007\B | GG | 19 | 7 | B | 6 DL | 100 | 0 | 100 | 2024-06-07 20:37 | 2024-06-11 04:14 | 239226.3074 |  |  |  |  | 239226 | 199355 |  |  | 0 | 19.96 | 0 | 10.32 | 5455.39
PH4100XPC#1 | GG\20\022\B | GG | 20 | 22 | B | 1 Prestrip - Thick | 100 | 52.6061 | 52.6061 | 2024-06-08 07:53 | 2024-06-10 14:52 | 124345.5696 | 124346 | [7 empty] | 0 | 0 | 13.39 | 20.19 | 4757.18
TS5500Shv | GG\19\008\B | GG | 19 | 8 | B | 8 Coal Mining | 34 | 0 | 34 | 2024-06-08 18:55 | 2024-06-09 09:33 | 17843.3513 | [6 empty] | 17843 | 13062 | 1.31 | 0 | 0 | 10.13 | 5495
DRE1 | RS\37\005\D | RS | 37 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-06-09 06:22 | 2024-06-13 00:46 | 307341.3651 |  |  |  | 15802 | 307341 | 247559 |  |  | 0 | 26.34 | 0 | 5.63 | 5925.99
TS5500Shv | RS\37\004\D | RS | 37 | 4 | D | 8 Coal Mining | 7 | 0 | 7 | 2024-06-09 09:33 | 2024-06-09 13:00 | 4218.2973 | [6 empty] | 4218 | 3129 | 0.31 | 0 | 0 | 5.38 | 5947
TS5500Shv | MW\49\008\B | MW | 49 | 8 | B | 8 Coal Mining | 42.4 | 0 | 42.4 | 2024-06-09 13:00 | 2024-06-10 01:54 | 15730.9111 | [6 empty] | 15731 | 11624 | 1.23 | 0 | 0 | 9.34 | 5562
TS5500Shv | MW\50\004\D | MW | 50 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2024-06-10 01:54 | 2024-06-10 14:54 | 13927.5289 |  |  | 13928 | [5 empty] | 0 | 0 | 0 | 7.94 | 5708.08
PH4100XPC#1 | GG\20\023\B | GG | 20 | 23 | B | 1 Prestrip - Thick | 100 | 55.3336 | 55.3336 | 2024-06-10 14:52 | 2024-06-14 06:57 | 204965.7584 | 204966 | [7 empty] | 0 | 0 | 20.19 | 0 | 0
TS5500Shv | MW\50\004\D | MW | 50 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-06-10 14:54 | 2024-06-11 01:34 | 13015.7083 | [6 empty] | 13016 | 9702 | 3.75 | 0 | 0 | 7.94 | 5708
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 02:39 |  | 0d 02:39 | 2024-06-11 01:34 | 2024-06-11 04:14
TS6060#1 | GG\17\022\D | GG | 17 | 22 | D | 8 Coal Mining | 2.5 | 0 | 2.5 | 2024-06-11 01:58 | 2024-06-11 03:07 | 1564.2132 | [6 empty] | 1564 | 1167 | 0.12 | 0 | 0 | 6.68 | 5801
TS6060#1 | RS\39\004\A | RS | 39 | 4 | A | 1 Prestrip - Thick | 36.8667 | 36.8667 | 36.8667 | 2024-06-11 03:07 | 2024-06-13 19:59 | 66928.3163 | 66928 | [7 empty] | 0 | 0 | 6.69 | 12.72 | 5290.88
DRE2 | GG\19\006\B | GG | 19 | 6 | B | 6 DL | 100 | 0 | 100 | 2024-06-11 04:14 | 2024-06-14 19:45 | 263024.1964 |  |  |  |  | 263024 | 202326 |  |  | 0 | 20.25 | 0 | 9.76 | 5476.21
TS5500Shv | GG\19\007\B | GG | 19 | 7 | B | 8 Coal Mining | 47.9 | 0 | 47.9 | 2024-06-11 04:14 | 2024-06-12 00:25 | 24626.6067 | [6 empty] | 24627 | 18016 | 1.8 | 0 | 0 | 10.32 | 5455
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 19:20 |  | 2d 19:20 | 2024-06-12 00:25 | 2024-06-14 19:45
DRE1 | MW\49\008\D | MW | 49 | 8 | D | 6 DL | 100 | 100 | 100 | 2024-06-13 00:46 | 2024-06-15 20:37 | 230681.5583 |  |  |  | 11860 | 230682 | 185810 |  |  | 0 | 28.8 | 0 | 5.41 | 5937.21
TS6060#1 | GG\17\023\D | GG | 17 | 23 | D | 7 PostStrip | 47.0091 | 0 | 47.0091 | 2024-06-13 19:59 | 2024-06-14 23:26 | 28330.6694 |  |  | 28331 | [5 empty] | 0 | 0 | 0 | 6.43 | 5822.58
PH4100XPC#1 | GG\21\004\X1 | GG | 21 | 4 | X1 | 1 Prestrip - Thick | 100 | 54.3383 | 54.3383 | 2024-06-14 06:57 | 2024-06-30 18:56 | 918966.7211 | 918967 | [7 empty] | 0 | 0 | 58.56 | 10.65 | 5302.15
DRE2 | GG\19\005\B | GG | 19 | 5 | B | 6 DL | 100 | 0 | 100 | 2024-06-14 19:45 | 2024-06-18 12:46 | 267465.0636 |  |  |  |  | 267465 | 205742 |  |  | 0 | 20.45 | 0 | 9.21 | 5512.86
TS5500Shv | GG\19\006\B | GG | 19 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-06-14 19:45 | 2024-06-16 11:49 | 48847.8089 | [6 empty] | 48848 | 35902 | 3.59 | 0 | 0 | 9.76 | 5476
TS6060#1 | GG\17\023\D | GG | 17 | 23 | D | 8 Coal Mining | 64.6 | 0 | 64.6 | 2024-06-14 23:26 | 2024-06-16 11:27 | 48745.6949 | [6 empty] | 48746 | 36587 | 3.04 | 0 | 0 | 6.43 | 5823
TS Fleet 5 | W1\02\003\B | W1 | 2 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-06-15 20:22 | 2024-07-05 04:12 | 909107.9394 | 909108 | [7 empty] | 0 | 0 | 40.62 | 12.86 | 4983.57
DRE1 | RS\37\006\D | RS | 37 | 6 | D | 6 DL | 100 | 100 | 100 | 2024-06-15 20:37 | 2024-06-19 10:02 | 290401.208 |  |  |  | 10888 | 290401 | 164935 |  |  | 0 | 25.96 | 0 | 5.79 | 5912.04
TS6060#1 | GG\19\012\B | GG | 19 | 12 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-06-16 11:27 | 2024-06-17 06:29 | 25754.8428 | [6 empty] | 25755 | 18893 | 1.9 | 0 | 0 | 10.11 | 5504
TS5500Shv | GG\17\023\D | GG | 17 | 23 | D | 8 Coal Mining | 35.4 | 0 | 35.4 | 2024-06-16 11:49 | 2024-06-17 09:43 | 26701.915 | [6 empty] | 26702 | 20042 | 1.67 | 0 | 0 | 6.43 | 5823
TS6060#1 | GG\19\010\B | GG | 19 | 10 | B | 8 Coal Mining | 50.3 | 0 | 50.3 | 2024-06-17 06:29 | 2024-06-18 01:02 | 25100.2673 | [6 empty] | 25100 | 18445 | 1.84 | 0 | 0 | 9.7 | 5544
TS5500Shv | MW\49\008\D | MW | 49 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-06-17 09:43 | 2024-06-18 19:59 | 41788.2869 | [6 empty] | 41788 | 31752 | 4.7 | 0 | 0 | 5.41 | 5937
TS5500Exc | RS\38\005\A | RS | 38 | 5 | A | 8 Coal Mining | 85.9 | 0 | 85.9 | 2024-06-18 00:30 | 2024-06-19 08:59 | 40904.9925 | [6 empty] | 40905 | 28698 | 2.87 | 0 | 0 | 14.24 | 5175
TS6060#1 | GG\19\008\B | GG | 19 | 8 | B | 8 Coal Mining | 66 | 0 | 66 | 2024-06-18 01:02 | 2024-06-19 02:34 | 34569.1843 | [6 empty] | 34569 | 25306 | 2.53 | 0 | 0 | 10.13 | 5495
DRE2 | GG\19\004\B | GG | 19 | 4 | B | 6 DL | 100 | 100 | 100 | 2024-06-18 12:46 | 2024-06-21 15:52 | 225704.8108 |  |  |  |  | 225705 | 188087 |  |  | 0 | 18.56 | 0 | 9.33 | 5515.38
TS5500Shv | GG\19\005\B | GG | 19 | 5 | B | 8 Coal Mining | 80.4 | 0 | 80.4 | 2024-06-18 19:59 | 2024-06-20 02:36 | 37334.2957 | [6 empty] | 37334 | 27536 | 2.75 | 0 | 0 | 9.21 | 5513
TS6060#1 | GG\19\007\B | GG | 19 | 7 | B | 8 Coal Mining | 52.1 | 0 | 52.1 | 2024-06-19 02:34 | 2024-06-19 22:24 | 26832.2114 | [6 empty] | 26832 | 19630 | 1.96 | 0 | 0 | 10.32 | 5455
TS5500Exc | RS\39\005\X | RS | 39 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2024-06-19 08:59 | 2024-06-19 23:58 | 18872.3976 | [6 empty] | 18872 | 13423 | 1.34 | 0 | 0 | 10.95 | 5385
DRE1 | MW\50\005\D | MW | 50 | 5 | D | 6 DL | 100 | 0 | 100 | 2024-06-19 10:02 | 2024-06-24 12:13 | 415426.7319 |  |  |  | 29544 | 415427 | 298726 |  |  | 0 | 35 | 0 | 7.87 | 5720.64
TS6060#1 | RS\38\005\B | RS | 38 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-06-19 22:24 | 2024-06-21 06:35 | 33200.847 | 33201 | [7 empty] | 0 | 0 | 3.32 | 9 | 5606.84
TS5500Exc | RS\38\004\B | RS | 38 | 4 | B | 8 Coal Mining | 77.2 | 0 | 77.2 | 2024-06-19 23:58 | 2024-06-20 23:52 | 30103.0442 | [6 empty] | 30103 | 21702 | 2.17 | 0 | 0 | 8.96 | 5603
TS5500Shv | RS\37\006\D | RS | 37 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2024-06-20 02:36 | 2024-06-21 17:44 | 41944.0616 |  |  | 41944 | [5 empty] | 0 | 0 | 0 | 5.79 | 5912.04
PH4100A | RS\39\006\X | RS | 39 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-06-20 05:12 | 2024-07-04 23:56 | 598422.7449 | 598423 | [7 empty] | 0 | 0 | 51.01 | 10 | 5479.95
TS5500Exc | RS\38\006\X | RS | 38 | 6 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-06-20 23:52 | 2024-06-21 07:38 | 9784.0755 | [6 empty] | 9784 | 7006 | 0.61 | 0 | 0 | 10.27 | 5454
TS6060#1 | GG\19\005\B | GG | 19 | 5 | B | 8 Coal Mining | 19.6 | 0 | 19.6 | 2024-06-21 06:35 | 2024-06-21 13:18 | 9086.7619 | [6 empty] | 9087 | 6702 | 0.67 | 0 | 0 | 9.21 | 5513
TS5500Exc | RS\38\005\B | RS | 38 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-06-21 07:38 | 2024-06-22 15:50 | 40565.1341 | [6 empty] | 40565 | 29211 | 2.92 | 0 | 0 | 9 | 5607
TS6060#1 | RS\43\002\A | RS | 43 | 2 | A | 1 Prestrip - Thick | 37.3223 | 37.3223 | 37.3223 | 2024-06-21 13:18 | 2024-06-22 04:58 | 16079.6333 | 16080 | [7 empty] | 0 | 0 | 13.11 | 11.96 | 5359.21
DRE2 | GG\19\003\B | GG | 19 | 3 | B | 6 DL | 100 | 0 | 100 | 2024-06-21 15:52 | 2024-06-26 20:22 | 374091.2544 |  |  |  |  | 374091 | 178139 |  |  | 0 | 20.61 | 0 | 9.79 | 5498.34
TS5500Shv | RS\38\006\X | RS | 38 | 6 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-06-21 17:44 | 2024-06-22 01:30 | 9471.8178 | [6 empty] | 9472 | 6782 | 0.59 | 0 | 0 | 10.27 | 5454
TS5500Shv | RS\37\006\D | RS | 37 | 6 | D | 8 Coal Mining | 58.5 | 0 | 58.5 | 2024-06-22 01:30 | 2024-06-23 02:17 | 30233.4391 | [6 empty] | 30233 | 22412 | 2.69 | 0 | 0 | 5.79 | 5912
TS6060#1 | RS\38\006\A | RS | 38 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-06-22 04:58 | 2024-06-29 07:36 | 176051.0801 | 176051 | [7 empty] | 0 | 0 | 17.36 | 15.99 | 5041.44
TS5500Exc | RS\37\004\D | RS | 37 | 4 | D | 8 Coal Mining | 93 | 0 | 93 | 2024-06-22 15:50 | 2024-06-24 12:13 | 55909.4138 | [6 empty] | 55909 | 41475 | 4.15 | 0 | 0 | 5.38 | 5947
TS5500Shv | GG\19\004\B | GG | 19 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-06-23 02:17 | 2024-06-24 18:05 | 48536.9374 | [6 empty] | 48537 | 35786 | 3.59 | 0 | 0 | 9.33 | 5515
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2024-06-24 12:13 | 2024-06-27 12:13
TS5500Exc | RS\37\005\D | RS | 37 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-06-24 12:13 | 2024-06-26 12:44 | 61100.0945 | [6 empty] | 61100 | 45256 | 4.53 | 0 | 0 | 5.63 | 5926
TS5500Shv | GG\22\004\X1 | GG | 22 | 4 | X1 | 1 Prestrip - Thick | 10.6269 | 10.6269 | 10.6269 | 2024-06-24 18:05 | 2024-06-30 20:40 | 157159.4546 | 157159 | [7 empty] | 0 | 0 | 11.18 | 10.77 | 5292.65
TS5500Exc | RS\37\006\D | RS | 37 | 6 | D | 8 Coal Mining | 41.5 | 0 | 41.5 | 2024-06-26 12:44 | 2024-06-27 05:44 | 21426.8329 | [6 empty] | 21427 | 15884 | 1.91 | 0 | 0 | 5.79 | 5912
DRE2 | GG\18\012\D | GG | 18 | 12 | D | 6 DL | 100 | 100 | 100 | 2024-06-26 20:22 | 2024-07-04 00:03 | 515923.5254 |  |  |  | 12012 | 515924 | 228232 |  |  | 0 | 24.04 | 0 | 6.76 | 5792.35
TS5500Exc | MW\50\006\D | MW | 50 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-06-27 05:44 | 2024-07-10 15:32 | 284652.2416 | 284652 | [7 empty] | 0 | 0 | 29.06 | 6.99 | 5799.39
DRE1 | MW\59\004\D | MW | 59 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-06-27 12:13 | 2024-06-29 06:46 | 144693.627 |  |  |  | 5794 | 144694 | 89358 |  |  | 0 | 16.04 | 0 | 9.02 | 5612.51
DRE1 | MW\59\005\D | MW | 59 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-06-29 06:46 | 2024-07-05 16:31 | 522756.9916 |  |  |  | 23390 | 522757 | 444402 |  |  | 0 | 24.11 | 0 | 8.91 | 5629.09
TS6060#1 | GG\19\003\B | GG | 19 | 3 | B | 8 Coal Mining | 74.5 | 0 | 74.5 | 2024-06-29 07:36 | 2024-06-30 08:00 | 33032.5046 | [6 empty] | 33033 | 24290 | 3.05 | 0 | 0 | 9.79 | 5498
TS6060#1 | RS\43\003\X | RS | 43 | 3 | X | 1 Prestrip - Thick | 37.2881 | 37.2881 | 37.2881 | 2024-06-30 08:00 | 2024-07-04 00:54 | 88602.1801 | 88602 | [7 empty] | 0 | 0 | 9.14 | 11.81 | 5293.65
PH4100XPC#1 | GG\21\005\X1 | GG | 21 | 5 | X1 | 1 Prestrip - Thick | 100 | 54.903 | 54.903 | 2024-06-30 18:56 | 2024-07-09 10:40 | 475074.0085 | 475074 | [7 empty] | 0 | 0 | 43.17 | 10.54 | 5309.19
TS5500Shv | GG\21\004\X1 | GG | 21 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-06-30 20:40 | 2024-07-01 15:39 | 23142.4265 | [6 empty] | 23142 | 17199 | 1.08 | 0 | 0 | 10.65 | 5302
TS5500Shv | RS\38\006\A | RS | 38 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-07-01 15:39 | 2024-07-03 08:00 | 49217.2783 | [6 empty] | 49217 | 34217 | 3.43 | 0 | 0 | 15.99 | 5041
TS5500Shv | MW\59\004\D | MW | 59 | 4 | D | 7 PostStrip | 69.6601 | 0 | 69.6601 | 2024-07-03 08:00 | 2024-07-04 16:18 | 34627.0361 |  |  | 34627 | [5 empty] | 0 | 0 | 0 | 9.02 | 5612.51
DRE2 | GG\18\011\D | GG | 18 | 11 | D | 6 DL | 100 | 100 | 100 | 2024-07-04 00:03 | 2024-07-11 02:05 | 510916.5309 |  |  |  | 9272 | 510917 | 222533 |  |  | 0 | 23.18 | 0 | 6.44 | 5819.72
TS6060#1 | RS\38\006\B | RS | 38 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-07-04 00:54 | 2024-07-05 10:13 | 34376.6518 | 34377 | [7 empty] | 0 | 0 | 3.46 | 9.09 | 5597.93
TS5500Shv | GG\19\003\B | GG | 19 | 3 | B | 8 Coal Mining | 25.5 | 0 | 25.5 | 2024-07-04 16:18 | 2024-07-05 01:34 | 11287.9228 | [6 empty] | 11288 | 8300 | 1.04 | 0 | 0 | 9.79 | 5498
PH4100A | RS\39\003\A | RS | 39 | 3 | A | 1 Prestrip - Thick | 100 | 14.3917 | 14.3917 | 2024-07-04 23:56 | 2024-07-05 13:48 | 24063.8201 | 24064 | [7 empty] | 0 | 0 | 2.7 | 11.92 | 5350.55
TS5500Shv | GG\18\012\D | GG | 18 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-07-05 01:34 | 2024-07-07 03:57 | 61449.762 | [6 empty] | 61450 | 45902 | 4.59 | 0 | 0 | 6.76 | 5792
TS Fleet 5 | GG\21\004\B | GG | 21 | 4 | B | 1 Prestrip - Thick | 45.3511 | 45.3511 | 45.3511 | 2024-07-05 04:12 | 2024-07-06 15:27 | 69081.5677 | 69082 | [7 empty] | 0 | 0 | 4.57 | 9.28 | 5524.87
TS6060#1 | RS\43\004\X | RS | 43 | 4 | X | 1 Prestrip - Thick | 31.9886 | 31.9886 | 31.9886 | 2024-07-05 10:13 | 2024-07-09 09:09 | 94189.2615 | 94189 | [7 empty] | 0 | 0 | 9.69 | 11.31 | 5348.87
PH4100A | RS\39\004\A | RS | 39 | 4 | A | 1 Prestrip - Thick | 100 | 63.1333 | 63.1333 | 2024-07-05 13:48 | 2024-07-08 07:49 | 114613.0742 | 114613 | [7 empty] | 0 | 0 | 11.46 | 12.72 | 5290.88
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2024-07-05 16:31 | 2024-07-07 16:31
TS Fleet 5 | GG\22\004\X1 | GG | 22 | 4 | X1 | 1 Prestrip - Thick | 39.8341 | 39.8341 | 39.8341 | 2024-07-06 15:27 | 2024-07-19 04:00 | 589102.2159 | 589102 | [7 empty] | 0 | 0 | 41.89 | 10.77 | 5292.65
TS5500Shv | RS\38\006\B | RS | 38 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-07-07 03:57 | 2024-07-07 20:18 | 19935.3924 | [6 empty] | 19935 | 14336 | 1.45 | 0 | 0 | 9.09 | 5598
DRE1 | RS\38\003\D | RS | 38 | 3 | D | 6 DL | 100 | 100 | 100 | 2024-07-07 16:31 | 2024-07-12 08:46 | 381612.5458 |  |  |  | 19620 | 381613 | 307383 |  |  | 0 | 27.52 | 0 | 5.24 | 5961.49
TS5500Shv | RS\39\003\A | RS | 39 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-07-07 20:18 | 2024-07-08 13:50 | 21377.2945 | [6 empty] | 21377 | 15202 | 1.6 | 0 | 0 | 11.92 | 5351
PH4100A | RS\39\005\A | RS | 39 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-07-08 07:49 | 2024-07-12 15:49 | 180529.8524 | 180530 | [7 empty] | 0 | 0 | 18.06 | 13.7 | 5217.81
TS5500Shv | RS\39\004\A | RS | 39 | 4 | A | 8 Coal Mining | 42 | 0 | 42 | 2024-07-08 13:50 | 2024-07-09 05:42 | 19344.6339 | [6 empty] | 19345 | 13686 | 1.37 | 0 | 0 | 12.72 | 5291
TS5500Shv | MW\59\005\D | MW | 59 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-07-09 05:42 | 2024-07-11 00:28 | 52150.0104 | [6 empty] | 52150 | 38714 | 2.13 | 0 | 0 | 8.91 | 5629
TS6060#1 | RS\43\005\X | RS | 43 | 5 | X | 1 Prestrip - Thick | 34.8898 | 34.8898 | 34.8898 | 2024-07-09 09:09 | 2024-07-14 06:28 | 117559.8526 | 117560 | [7 empty] | 0 | 0 | 12.03 | 10.59 | 5421.62
PH4100XPC#1 | GG\21\004\B | GG | 21 | 4 | B | 1 Prestrip - Thick | 100 | 54.6489 | 54.6489 | 2024-07-09 10:40 | 2024-07-10 23:27 | 83244.3763 | 83244 | [7 empty] | 0 | 0 | 5.51 | 9.28 | 5524.87
TS5500Exc | RS\38\006\B | RS | 38 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-07-10 15:32 | 2024-07-11 07:53 | 20592.6031 | [6 empty] | 20593 | 14809 | 1.5 | 0 | 0 | 9.09 | 5598
PH4100XPC#1 | GG\21\006\X1 | GG | 21 | 6 | X1 | 1 Prestrip - Thick | 100 | 49.5796 | 49.5796 | 2024-07-10 23:27 | 2024-07-18 15:05 | 409963.6094 | 409964 | [7 empty] | 0 | 0 | 39.79 | 11.11 | 5302.87
TS5500Shv | GG\21\005\X1 | GG | 21 | 5 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-07-11 00:28 | 2024-07-11 13:17 | 15629.7614 | [6 empty] | 15630 | 11636 | 1.16 | 0 | 0 | 10.54 | 5309
DRE2 | GG\18\010\D | GG | 18 | 10 | D | 6 DL | 100 | 100 | 100 | 2024-07-11 02:05 | 2024-07-17 10:54 | 459230.5816 |  |  |  | 10692 | 459231 | 203152 |  |  | 0 | 21.39 | 0 | 6.27 | 5835.08
TS5500Exc | RS\39\003\A | RS | 39 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-07-11 07:53 | 2024-07-12 01:25 | 22082.0405 | [6 empty] | 22082 | 15704 | 1.65 | 0 | 0 | 11.92 | 5351
TS5500Shv | GG\18\011\D | GG | 18 | 11 | D | 8 Coal Mining | 62.6 | 0 | 62.6 | 2024-07-11 13:17 | 2024-07-12 20:22 | 37900.7438 | [6 empty] | 37901 | 28356 | 2.84 | 0 | 0 | 6.44 | 5820
TS5500Exc | RS\39\004\A | RS | 39 | 4 | A | 8 Coal Mining | 58 | 0 | 58 | 2024-07-12 01:25 | 2024-07-12 22:40 | 26760.9888 | [6 empty] | 26761 | 18934 | 1.89 | 0 | 0 | 12.72 | 5291
DRE1 | MW\50\006\D | MW | 50 | 6 | D | 6 DL | 100 | 0 | 100 | 2024-07-12 08:46 | 2024-07-17 17:44 | 438495.3282 |  |  |  | 31185 | 438495 | 315315 |  |  | 0 | 35 | 0 | 6.99 | 5799.39
PH4100A | RS\39\003\B | RS | 39 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-07-12 15:49 | 2024-07-13 08:44 | 29380.2329 | 29380 | [7 empty] | 0 | 0 | 3.03 | 9.1 | 5576.93
TS5500Shv | RS\38\003\D | RS | 38 | 3 | D | 8 Coal Mining | 33.8 | 0 | 33.8 | 2024-07-12 20:22 | 2024-07-13 16:14 | 24230.6006 | [6 empty] | 24231 | 18035 | 1.51 | 0 | 0 | 5.24 | 5961
TS5500Exc | RS\39\005\A | RS | 39 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-07-12 22:40 | 2024-07-14 12:03 | 47090.2361 | [6 empty] | 47090 | 33115 | 3.32 | 0 | 0 | 13.7 | 5218
PH4100A | RS\39\004\B | RS | 39 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-07-13 08:44 | 2024-07-14 02:14 | 30365.1299 | 30365 | [7 empty] | 0 | 0 | 3.04 | 9 | 5601.05
TS5500Shv | MW\50\005\D | MW | 50 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-07-13 16:14 | 2024-07-15 18:03 | 60732.1056 | [6 empty] | 60732 | 45338 | 4.53 | 0 | 0 | 7.87 | 5721
PH4100A | RS\40\003\X | RS | 40 | 3 | X | 1 Prestrip - Thick | 100 | 65.113 | 65.113 | 2024-07-14 02:14 | 2024-07-18 16:20 | 183573.8681 | 183574 | [7 empty] | 0 | 0 | 21.15 | 11.94 | 5279.05
TS6060#1 | GG\18\011\D | GG | 18 | 11 | D | 8 Coal Mining | 37.4 | 0 | 37.4 | 2024-07-14 06:28 | 2024-07-14 23:14 | 22689.6784 | [6 empty] | 22690 | 16976 | 1.7 | 0 | 0 | 6.44 | 5820
TS5500Exc | RS\39\003\B | RS | 39 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-07-14 12:03 | 2024-07-15 17:55 | 37622.3827 | [6 empty] | 37622 | 27119 | 2.75 | 0 | 0 | 9.1 | 5577
TS6060#1 | RS\39\005\B | RS | 39 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-07-14 23:14 | 2024-07-16 05:52 | 31608.184 | 31608 | [7 empty] | 0 | 0 | 3.16 | 9 | 5608.35
TS5500Exc | RS\39\004\B | RS | 39 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-07-15 17:55 | 2024-07-17 00:59 | 39127.9738 | [6 empty] | 39128 | 28189 | 2.82 | 0 | 0 | 9 | 5601
TS5500Shv | GG\22\008\X1 | GG | 22 | 8 | X1 | 1 Prestrip - Thick | 2.4824 | 2.4824 | 2.4824 | 2024-07-15 18:03 | 2024-07-16 11:44 | 18792.6164 | 18793 | [7 empty] | 0 | 0 | 1.85 | 13.04 | 5221.78
TS6060#1 | RS\43\006\X | RS | 43 | 6 | X | 1 Prestrip - Thick | 31.4838 | 31.4838 | 31.4838 | 2024-07-16 05:52 | 2024-07-20 05:11 | 95947.9005 | 95948 | [7 empty] | 0 | 0 | 13.27 | 9.69 | 5509.03
TS5500Shv | RS\39\005\B | RS | 39 | 5 | B | 8 Coal Mining | 18.6 | 0 | 18.6 | 2024-07-16 11:44 | 2024-07-16 17:57 | 7582.4745 | [6 empty] | 7582 | 5456 | 0.55 | 0 | 0 | 9 | 5608
TS5500Shv | GG\22\010\X1 | GG | 22 | 10 | X1 | 1 Prestrip - Thick | 10.1618 | 10.1618 | 10.1618 | 2024-07-16 17:57 | 2024-07-19 08:29 | 66460.3235 | 66460 | [7 empty] | 0 | 0 | 5.83 | 15.83 | 5028.89
TS5500Exc | RS\39\006\X | RS | 39 | 6 | X | 8 Coal Mining | 100 | 0 | 100 | 2024-07-17 00:59 | 2024-07-17 16:14 | 19214.4295 | [6 empty] | 19214 | 13788 | 1.21 | 0 | 0 | 10 | 5480
DRE2 | GG\18\009\D | GG | 18 | 9 | D | 6 DL | 100 | 100 | 100 | 2024-07-17 10:54 | 2024-07-23 13:55 | 441737.8417 |  |  |  | 10285 | 441738 | 195414 |  |  | 0 | 20.57 | 0 | 6.39 | 5825.04
TS5500Exc | RS\39\006\A | RS | 39 | 6 | A | 1 Prestrip - Thick | 100 | 38.5616 | 38.5616 | 2024-07-17 16:14 | 2024-07-20 21:19 | 68169.9829 | 68170 | [7 empty] | 0 | 0 | 6.77 | 15.94 | 5046.56
DRE1 | RS\38\004\D | RS | 38 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-07-17 17:44 | 2024-07-21 15:49 | 319867.5774 |  |  |  | 16446 | 319868 | 257648 |  |  | 0 | 27.42 | 0 | 5.43 | 5943.14
PH4100XPC#1 | GG\21\005\X2 | GG | 21 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 67.8843 | 2024-07-18 15:05 | 2024-07-19 19:35 | 64510.4386 | 64510 | [7 empty] | 0 | 0 | 6.44 | 0 | 0
PH4100A | RS\39\006\A | RS | 39 | 6 | A | 1 Prestrip - Thick | 100 | 52.0278 | 52.0278 | 2024-07-18 16:20 | 2024-07-20 21:19 | 91975.794 | 91976 | [7 empty] | 0 | 0 | 9.14 | 15.94 | 5046.56
TS Fleet 5 | GG\21\005\X2 | GG | 21 | 5 | X2 | 1 Prestrip - Thick | 45.3511 | 0 | 32.1157 | 2024-07-19 04:00 | 2024-07-19 19:35 | 30519.4814 | 30519 | [7 empty] | 0 | 0 | 3.05 | 0 | 0
TS5500Shv | GG\21\006\X1 | GG | 21 | 6 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-07-19 08:29 | 2024-07-19 21:26 | 15776.9445 | [6 empty] | 15777 | 11671 | 1.16 | 0 | 0 | 11.11 | 5303
TS Fleet 5 | GG\21\005\B | GG | 21 | 5 | B | 1 Prestrip - Thick | 45.3511 | 45.3511 | 45.3511 | 2024-07-19 19:35 | 2024-07-20 04:54 | 18281.368 | 18281 | [7 empty] | 0 | 0 | 1.83 | 9.05 | 5527.7
PH4100XPC#1 | GG\21\005\B | GG | 21 | 5 | B | 1 Prestrip - Thick | 100 | 54.6489 | 54.6489 | 2024-07-19 19:35 | 2024-07-20 05:19 | 22029.3361 | 22029 | [7 empty] | 0 | 0 | 2.21 | 9.05 | 5527.7
TS5500Shv | MW\50\006\D | MW | 50 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-07-19 21:26 | 2024-07-22 01:33 | 63560.8446 | [6 empty] | 63561 | 47797 | 4.78 | 0 | 0 | 6.99 | 5799
TS Fleet 5 | GG\21\006\X2 | GG | 21 | 6 | X2 | 1 Prestrip - Thick | 45.3511 | 0 | 45.3511 | 2024-07-20 04:54 | 2024-07-21 02:46 | 42833.9541 | 42834 | [7 empty] | 0 | 0 | 4.27 | 0 | 0
TS6060#1 | RS\39\006\A | RS | 39 | 6 | A | 1 Prestrip - Thick | 100 | 9.4105 | 9.4105 | 2024-07-20 05:11 | 2024-07-20 21:19 | 16636.1417 | 16636 | [7 empty] | 0 | 0 | 1.65 | 15.94 | 5046.56
PH4100XPC#1 | GG\21\006\X2 | GG | 21 | 6 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.6489 | 2024-07-20 05:19 | 2024-07-21 04:07 | 51615.5889 | 51616 | [7 empty] | 0 | 0 | 5.15 | 0 | 0
TS6060#1 | GG\18\010\D | GG | 18 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-07-20 21:19 | 2024-07-22 18:35 | 61263.9531 | [6 empty] | 61264 | 45873 | 4.59 | 0 | 0 | 6.27 | 5835
PH4100A | RS\40\004\X | RS | 40 | 4 | X | 1 Prestrip - Thick | 100 | 62.6648 | 62.6648 | 2024-07-20 21:19 | 2024-07-26 23:46 | 244459.5815 | 244460 | [7 empty] | 0 | 0 | 24.98 | 11.51 | 5327.4
TS5500Exc | RS\40\003\X | RS | 40 | 3 | X | 8 Coal Mining | 100 | 0 | 100 | 2024-07-20 21:19 | 2024-07-21 08:26 | 14010.6626 | [6 empty] | 14011 | 9868 | 1.06 | 0 | 0 | 11.94 | 5279
TS Fleet 5 | GG\22\005\X1 | GG | 22 | 5 | X1 | 1 Prestrip - Thick | 45.2036 | 45.2036 | 45.2036 | 2024-07-21 02:46 | 2024-07-29 15:19 | 400944.4608 | 400944 | [7 empty] | 0 | 0 | 38.45 | 10.64 | 5304.22
PH4100XPC#1 | GG\21\006\B | GG | 21 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-07-21 04:07 | 2024-07-22 03:55 | 53864.4013 | 53864 | [7 empty] | 0 | 0 | 5.4 | 9.93 | 5470.42
TS5500Exc | MW\59\004\D | MW | 59 | 4 | D | 7 PostStrip | 30.3399 | 0 | 30.3399 | 2024-07-21 08:26 | 2024-07-22 01:29 | 15081.5386 |  |  | 15082 | [5 empty] | 0 | 0 | 0 | 9.02 | 5612.51
DRE1 | RS\38\005\D | RS | 38 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-07-21 15:49 | 2024-07-25 09:32 | 305068.7871 |  |  |  | 15685 | 305069 | 245728 |  |  | 0 | 26.14 | 0 | 5.66 | 5923.39
TS5500Exc | MW\59\004\D | MW | 59 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-07-22 01:29 | 2024-07-22 19:23 | 22535.654 | [6 empty] | 22536 | 16690 | 1.82 | 0 | 0 | 9.02 | 5613
TS5500Shv | MW\59\004\D | MW | 59 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-07-22 01:33 | 2024-07-22 19:26 | 21816.431 | [6 empty] | 21816 | 16157 | 1.76 | 0 | 0 | 9.02 | 5613
PH4100XPC#1 | GG\21\007\X1 | GG | 21 | 7 | X1 | 1 Prestrip - Thick | 100 | 54.2306 | 54.2306 | 2024-07-22 03:55 | 2024-07-29 22:50 | 416018.7205 | 416019 | [7 empty] | 0 | 0 | 40.62 | 11.88 | 5284.4
TS6060#1 | RS\40\003\A | RS | 40 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-07-22 18:35 | 2024-07-29 23:26 | 178343.4441 | 178343 | [7 empty] | 0 | 0 | 18.64 | 12.11 | 5337.62
TS5500Exc | RS\39\005\B | RS | 39 | 5 | B | 8 Coal Mining | 81.4 | 0 | 81.4 | 2024-07-22 19:23 | 2024-07-23 21:48 | 33270.9191 | [6 empty] | 33271 | 23942 | 2.39 | 0 | 0 | 9 | 5608
TS5500Shv | RS\39\006\A | RS | 39 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-07-22 19:26 | 2024-07-23 15:04 | 23924.8011 | [6 empty] | 23925 | 16637 | 1.68 | 0 | 0 | 15.94 | 5047
DRE2 | GG\18\008\D | GG | 18 | 8 | D | 6 DL | 100 | 100 | 100 | 2024-07-23 13:55 | 2024-07-29 13:04 | 430160.377 |  |  |  | 10015 | 430160 | 190292 |  |  | 0 | 20.03 | 0 | 6.5 | 5815.07
TS5500Shv | RS\38\004\D | RS | 38 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-07-23 15:04 | 2024-07-25 16:16 | 59993.1657 | [6 empty] | 59993 | 44504 | 4.45 | 0 | 0 | 5.43 | 5943
TS5500Exc | RS\39\006\A | RS | 39 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-07-23 21:48 | 2024-07-24 17:25 | 24713.5308 | [6 empty] | 24714 | 17186 | 1.74 | 0 | 0 | 15.94 | 5047
TS5500Exc | MW\59\005\D | MW | 59 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-07-24 17:25 | 2024-07-26 12:11 | 53869.2415 | [6 empty] | 53869 | 39990 | 2.2 | 0 | 0 | 8.91 | 5629
DRE1 | RS\38\006\D | RS | 38 | 6 | D | 6 DL | 100 | 100 | 100 | 2024-07-25 09:32 | 2024-07-28 21:58 | 287072.2563 |  |  |  | 10760 | 287072 | 163031 |  |  | 0 | 25.99 | 0 | 5.8 | 5911.61
TS5500Shv | RS\38\005\D | RS | 38 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-07-25 16:16 | 2024-07-27 18:35 | 61358.7774 | [6 empty] | 61359 | 45448 | 4.54 | 0 | 0 | 5.66 | 5923
TS5500Exc | RS\38\003\D | RS | 38 | 3 | D | 8 Coal Mining | 66.2 | 0 | 66.2 | 2024-07-26 12:11 | 2024-07-28 01:54 | 47501.929 | [6 empty] | 47502 | 35356 | 2.96 | 0 | 0 | 5.24 | 5961
PH4100A | RS\39\006\B | RS | 39 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-07-26 23:46 | 2024-07-27 18:39 | 32785.1495 | 32785 | [7 empty] | 0 | 0 | 3.33 | 9.1 | 5599.57
TS5500Shv | GG\18\009\D | GG | 18 | 9 | D | 8 Coal Mining | 44.8 | 0 | 44.8 | 2024-07-27 18:35 | 2024-07-28 17:12 | 27591.9463 | [6 empty] | 27592 | 20627 | 2.06 | 0 | 0 | 6.39 | 5825
PH4100A | RS\40\005\X | RS | 40 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-07-27 18:39 | 2024-08-06 21:02 | 407334.4393 | 407334 | [7 empty] | 0 | 0 | 41.45 | 10.82 | 5398.44
TS5500Exc | RS\40\004\X | RS | 40 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2024-07-28 01:54 | 2024-07-28 16:28 | 18364.816 | [6 empty] | 18365 | 12988 | 1.3 | 0 | 0 | 11.51 | 5327
TS5500Exc | RS\39\006\B | RS | 39 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-07-28 16:28 | 2024-07-29 08:38 | 20361.5425 | [6 empty] | 20362 | 14642 | 1.49 | 0 | 0 | 9.1 | 5600
TS5500Shv | RS\39\006\B | RS | 39 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-07-28 17:12 | 2024-07-29 09:22 | 19711.706 | [6 empty] | 19712 | 14175 | 1.44 | 0 | 0 | 9.1 | 5600
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2024-07-28 21:58 | 2024-07-31 21:58
TS5500Exc | MW\50\007\A | MW | 50 | 7 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-07-29 08:38 | 2024-08-09 17:03 | 241042.3259 | 241042 | [7 empty] | 0 | 0 | 25.17 | 12.53 | 5324.71
TS5500Shv | RS\38\006\D | RS | 38 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2024-07-29 09:22 | 2024-07-31 | 41401.1562 |  |  | 41401 | [5 empty] | 0 | 0 | 0 | 5.8 | 5911.61
DRE2 | GG\18\007\D | GG | 18 | 7 | D | 6 DL | 100 | 100 | 100 | 2024-07-29 13:04 | 2024-08-04 12:09 | 429978.2298 |  |  |  | 10011 | 429978 | 190212 |  |  | 0 | 20.02 | 0 | 6.58 | 5807.57
TS Fleet 5 | GG\22\006\X1 | GG | 22 | 6 | X1 | 1 Prestrip - Thick | 45.7076 | 45.7076 | 45.7076 | 2024-07-29 15:19 | 2024-08-06 21:57 | 389324.1926 | 389324 | [7 empty] | 0 | 0 | 38.17 | 11.21 | 5294.51
PH4100XPC#1 | GG\21\008\X1 | GG | 21 | 8 | X1 | 1 Prestrip - Thick | 100 | 54.2957 | 54.2957 | 2024-07-29 22:50 | 2024-08-06 06:43 | 392479.685 | 392480 | [7 empty] | 0 | 0 | 38.74 | 12.86 | 5238.62
TS6060#1 | GG\21\007\X1 | GG | 21 | 7 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-07-29 23:26 | 2024-07-30 11:31 | 16350.905 | [6 empty] | 16351 | 11998 | 1.2 | 0 | 0 | 11.88 | 5284
TS6060#1 | RS\40\004\A | RS | 40 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-07-30 11:31 | 2024-08-06 21:52 | 184025.8602 | 184026 | [7 empty] | 0 | 0 | 18.38 | 12.47 | 5311.62
TS5500Shv | GG\21\007\X2 | GG | 21 | 7 | X2 | 1 Prestrip - Thick | 50.7674 | 0 | 50.7674 | 2024-07-31 | 2024-08-01 18:49 | 45913.3374 | 45913 | [7 empty] | 0 | 0 | 4.59 | 0 | 0
DRE1 | MW\60\004\D | MW | 60 | 4 | D | 6 DL | 100 | 0 | 100 | 2024-07-31 21:58 | 2024-08-03 12:24 | 212280.4927 |  |  |  | 8102 | 212280 | 194455 |  |  | 0 | 14.88 | 0 | 8.7 | 5643.62
TS5500Shv | RS\40\003\A | RS | 40 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-08-01 18:49 | 2024-08-03 09:00 | 46562.1607 | [6 empty] | 46562 | 33063 | 3.25 | 0 | 0 | 12.11 | 5338
TS5500Shv | RS\38\006\D | RS | 38 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-08-03 09:00 | 2024-08-05 02:57 | 51154.4355 | [6 empty] | 51154 | 37921 | 4.62 | 0 | 0 | 5.8 | 5912
DRE1 | RS\39\003\D | RS | 39 | 3 | D | 6 DL | 100 | 100 | 100 | 2024-08-03 12:24 | 2024-08-08 11:02 | 403329.9706 |  |  |  | 20737 | 403330 | 324876 |  |  | 0 | 27.57 | 0 | 5.28 | 5957.26
DRE2 | GG\18\006\D | GG | 18 | 6 | D | 6 DL | 100 | 100 | 100 | 2024-08-04 12:09 | 2024-08-10 09:04 | 423459.0086 |  |  |  | 7886 | 423459 | 189255 |  |  | 0 | 19.71 | 0 | 6.63 | 5802.85
TS5500Shv | GG\18\008\D | GG | 18 | 8 | D | 8 Coal Mining | 49.1 | 0 | 49.1 | 2024-08-05 02:57 | 2024-08-06 03:46 | 30243.5879 | [6 empty] | 30244 | 22592 | 2.26 | 0 | 0 | 6.5 | 5815
TS5500Shv | GG\18\007\D | GG | 18 | 7 | D | 8 Coal Mining | 38 | 0 | 38 | 2024-08-06 03:46 | 2024-08-06 22:51 | 23274.1102 | [6 empty] | 23274 | 17399 | 1.74 | 0 | 0 | 6.58 | 5808
PH4100XPC#1 | GG\21\007\X2 | GG | 21 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 44.0968 | 2024-08-06 06:43 | 2024-08-07 00:20 | 39880.5219 | 39881 | [7 empty] | 0 | 0 | 3.99 | 0 | 0
PH4100A | RS\40\006\X | RS | 40 | 6 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-08-06 21:02 | 2024-08-20 21:59 | 568252.0571 | 568252 | [7 empty] | 0 | 0 | 48.95 | 9.79 | 5499.52
TS6060#1 | RS\40\003\B | RS | 40 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-08-06 21:52 | 2024-08-08 04:20 | 31446.3635 | 31446 | [7 empty] | 0 | 0 | 3.04 | 9.14 | 5574.51
TS Fleet 5 | GG\21\007\X2 | GG | 21 | 7 | X2 | 1 Prestrip - Thick | 22.3275 | 0 | 5.1357 | 2024-08-06 21:57 | 2024-08-07 00:20 | 4644.6896 | 4645 | [7 empty] | 0 | 0 | 0.46 | 0 | 0
TS5500Shv | GG\21\008\X1 | GG | 21 | 8 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-08-06 22:51 | 2024-08-07 13:10 | 17462.3198 | [6 empty] | 17462 | 12697 | 1.27 | 0 | 0 | 12.86 | 5239
TS Fleet 5 | GG\21\007\B | GG | 21 | 7 | B | 1 Prestrip - Thick | 45.3511 | 45.3511 | 45.3511 | 2024-08-07 00:20 | 2024-08-07 14:49 | 28414.8349 | 28415 | [7 empty] | 0 | 0 | 2.84 | 10.32 | 5459.53
PH4100XPC#1 | GG\21\007\B | GG | 21 | 7 | B | 1 Prestrip - Thick | 100 | 54.6489 | 54.6489 | 2024-08-07 00:20 | 2024-08-07 15:27 | 34240.3232 | 34240 | [7 empty] | 0 | 0 | 3.43 | 10.32 | 5459.53
TS5500Shv | GG\21\008\X2 | GG | 21 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 23.6073 | 2024-08-07 13:10 | 2024-08-08 07:27 | 19595.0275 | 19595 | [7 empty] | 0 | 0 | 1.96 | 0 | 0
TS Fleet 5 | GG\21\008\X2 | GG | 21 | 8 | X2 | 1 Prestrip - Thick | 32.7868 | 0 | 32.7868 | 2024-08-07 14:49 | 2024-08-08 04:43 | 27214.4231 | 27214 | [7 empty] | 0 | 0 | 2.72 | 0 | 0
PH4100XPC#1 | GG\21\008\X2 | GG | 21 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 43.6059 | 2024-08-07 15:27 | 2024-08-08 07:27 | 36194.6424 | 36195 | [7 empty] | 0 | 0 | 3.62 | 0 | 0
TS6060#1 | GG\18\009\D | GG | 18 | 9 | D | 8 Coal Mining | 55.2 | 0 | 55.2 | 2024-08-08 04:20 | 2024-08-09 05:25 | 33942.1024 | [6 empty] | 33942 | 25374 | 2.54 | 0 | 0 | 6.39 | 5825
TS Fleet 5 | GG\22\007\X1 | GG | 22 | 7 | X1 | 1 Prestrip - Thick | 45.7727 | 45.7727 | 45.7727 | 2024-08-08 04:43 | 2024-08-15 23:15 | 365616.7768 | 365617 | [7 empty] | 0 | 0 | 35.6 | 12.03 | 5270.33
PH4100XPC#1 | GG\21\008\B | GG | 21 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-08-08 07:27 | 2024-08-09 12:59 | 66877.9907 | 66878 | [7 empty] | 0 | 0 | 6.69 | 10.16 | 5494.46
TS5500Shv | RS\40\005\X | RS | 40 | 5 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-08-08 07:27 | 2024-08-08 15:20 | 9625.1634 | [6 empty] | 9625 | 6853 | 0.69 | 0 | 0 | 10.82 | 5398
DRE1 | RS\39\004\D | RS | 39 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-08-08 11:02 | 2024-08-12 08:25 | 317512.3013 |  |  |  | 16325 | 317512 | 255751 |  |  | 0 | 27.21 | 0 | 5.49 | 5938.48
TS5500Shv | RS\40\004\A | RS | 40 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-08-08 15:20 | 2024-08-10 04:48 | 45687.6977 | [6 empty] | 45688 | 32348 | 3.24 | 0 | 0 | 12.47 | 5312
TS6060#1 | GG\18\008\D | GG | 18 | 8 | D | 8 Coal Mining | 50.9 | 0 | 50.9 | 2024-08-09 05:25 | 2024-08-10 04:37 | 31399.4765 | [6 empty] | 31399 | 23455 | 2.35 | 0 | 0 | 6.5 | 5815
PH4100XPC#1 | GG\21\009\X2 | GG | 21 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 55.1582 | 2024-08-09 12:59 | 2024-08-16 23:22 | 412166.9404 | 412167 | [7 empty] | 0 | 0 | 44.51 | 0 | 0
TS5500Exc | RS\40\005\X | RS | 40 | 5 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-08-09 17:03 | 2024-08-10 00:56 | 9942.4764 | [6 empty] | 9942 | 7079 | 0.71 | 0 | 0 | 10.82 | 5398
TS5500Exc | RS\39\003\D | RS | 39 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-08-10 00:56 | 2024-08-11 07:32 | 38544.8094 | [6 empty] | 38545 | 28712 | 2.28 | 0 | 0 | 5.28 | 5957
TS6060#1 | RS\40\005\A | RS | 40 | 5 | A | 1 Prestrip - Thick | 84.7123 | 84.7123 | 84.7123 | 2024-08-10 04:37 | 2024-08-16 11:34 | 155752.7344 | 155753 | [7 empty] | 0 | 0 | 15.59 | 13.24 | 5254.77
TS5500Shv | RS\40\003\B | RS | 40 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-08-10 04:48 | 2024-08-11 14:03 | 40548.2702 | [6 empty] | 40548 | 29209 | 2.78 | 0 | 0 | 9.14 | 5575
DRE2 | GG\18\005\D | GG | 18 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-08-10 09:04 | 2024-08-16 05:40 | 422463.5653 |  |  |  | 7867 | 422464 | 188811 |  |  | 0 | 19.68 | 0 | 6.66 | 5800.38
TS5500Exc | MW\50\007\A | MW | 50 | 7 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-08-11 07:32 | 2024-08-12 05:46 | 28006.2804 | [6 empty] | 28006 | 20361 | 2.07 | 0 | 0 | 12.53 | 5325
TS5500Shv | RS\39\003\D | RS | 39 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-08-11 14:03 | 2024-08-12 20:40 | 37314.6559 | [6 empty] | 37315 | 27796 | 2.21 | 0 | 0 | 5.28 | 5957
TS5500Exc | MW\50\008\A | MW | 50 | 8 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-08-12 05:46 | 2024-08-22 08:46 | 214964.9608 | 214965 | [7 empty] | 0 | 0 | 28.41 | 11.79 | 5387.52
DRE1 | RS\39\005\D | RS | 39 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-08-12 08:25 | 2024-08-16 01:37 | 303234.0365 |  |  |  | 15590 | 303234 | 244250 |  |  | 0 | 25.98 | 0 | 5.7 | 5920.56
TS5500Shv | RS\39\004\D | RS | 39 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-08-12 20:40 | 2024-08-14 21:46 | 59885.3019 | [6 empty] | 59885 | 44423 | 4.44 | 0 | 0 | 5.49 | 5938
TS5500Shv | GG\18\006\D | GG | 18 | 6 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-08-14 21:46 | 2024-08-15 21:23 | 28797.1807 | [6 empty] | 28797 | 21545 | 2.15 | 0 | 0 | 6.63 | 5803
TS5500Shv | GG\22\012\X1 | GG | 22 | 12 | X1 | 1 Prestrip - Thick | 8.7044 | 8.7044 | 8.7044 | 2024-08-15 21:23 | 2024-08-17 12:38 | 41632.6246 | 41633 | [7 empty] | 0 | 0 | 4.06 | 14.75 | 5119.05
TS Fleet 5 | GG\22\008\X1 | GG | 22 | 8 | X1 | 1 Prestrip - Thick | 44.5218 | 44.5218 | 44.5218 | 2024-08-15 23:15 | 2024-08-23 03:13 | 337049.1697 | 337049 | [7 empty] | 0 | 0 | 33.15 | 13.04 | 5221.78
DRE1 | RS\39\006\D | RS | 39 | 6 | D | 6 DL | 100 | 100 | 100 | 2024-08-16 01:37 | 2024-08-19 13:27 | 285071.2924 |  |  |  | 10672 | 285071 | 161852 |  |  | 0 | 26.08 | 0 | 5.81 | 5910.89
DRE2 | GG\18\004\D | GG | 18 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-08-16 05:40 | 2024-08-22 00:22 | 416804.3479 |  |  |  | 7762 | 416804 | 186281 |  |  | 0 | 19.4 | 0 | 6.61 | 5804.15
TS6060#1 | RS\40\004\B | RS | 40 | 4 | B | 1 Prestrip - Thick | 37.2787 | 37.2787 | 37.2787 | 2024-08-16 11:34 | 2024-08-16 22:14 | 11008.3507 | 11008 | [7 empty] | 0 | 0 | 1.1 | 9.03 | 5600.74
TS6060#1 | GG\18\007\D | GG | 18 | 7 | D | 8 Coal Mining | 62 | 0 | 62 | 2024-08-16 22:14 | 2024-08-18 02:16 | 37933.1531 | [6 empty] | 37933 | 28358 | 2.84 | 0 | 0 | 6.58 | 5808
PH4100XPC#1 | GG\21\009\B | GG | 21 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-08-16 23:22 | 2024-08-18 10:15 | 78948.1877 | 78948 | [7 empty] | 0 | 0 | 7.9 | 9.97 | 5524
TS5500Shv | RS\39\005\D | RS | 39 | 5 | D | 8 Coal Mining | 69.1 | 0 | 69.1 | 2024-08-17 12:38 | 2024-08-18 23:52 | 42949.5011 | [6 empty] | 42950 | 31814 | 3.18 | 0 | 0 | 5.7 | 5921
TS6060#1 | GG\18\006\D | GG | 18 | 6 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-08-18 02:16 | 2024-08-19 01:53 | 31961.7061 | [6 empty] | 31962 | 23913 | 2.39 | 0 | 0 | 6.63 | 5803
PH4100XPC#1 | GG\21\010\X2 | GG | 21 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 55.0864 | 2024-08-18 10:15 | 2024-08-25 12:31 | 392280.304 | 392280 | [7 empty] | 0 | 0 | 30.75 | 0 | 0
TS5500Shv | GG\18\005\D | GG | 18 | 5 | D | 8 Coal Mining | 99.8 | 0 | 99.8 | 2024-08-18 23:52 | 2024-08-21 01:43 | 60795.9595 | [6 empty] | 60796 | 45522 | 4.55 | 0 | 0 | 6.66 | 5800
TS6060#1 | GG\18\005\D | GG | 18 | 5 | D | 8 Coal Mining | 0.2 | 0 | 0.2 | 2024-08-19 01:53 | 2024-08-19 02:00 | 150.8494 | [6 empty] | 151 | 113 | 0.01 | 0 | 0 | 6.66 | 5800
TS6060#1 | RS\44\002\A | RS | 44 | 2 | A | 1 Prestrip - Thick | 37.335 | 37.335 | 37.335 | 2024-08-19 02:00 | 2024-08-20 02:06 | 24689.7061 | 24690 | [7 empty] | 0 | 0 | 13.25 | 11.81 | 5376.17
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2024-08-19 13:27 | 2024-08-22 13:27
TS6060#1 | RS\44\003\A | RS | 44 | 3 | A | 1 Prestrip - Thick | 28.4978 | 28.4978 | 28.4978 | 2024-08-20 02:06 | 2024-08-25 01:37 | 120814.6477 | 120815 | [7 empty] | 0 | 0 | 12.21 | 12.16 | 5345.46
PH4100A | MW\50\007\B | MW | 50 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-08-20 21:59 | 2024-08-21 12:42 | 25544.62 | 25545 | [7 empty] | 0 | 0 | 2.58 | 9.7 | 5533.46
TS5500Shv | RS\40\006\X | RS | 40 | 6 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-08-21 01:43 | 2024-08-21 09:27 | 9423.215 | [6 empty] | 9423 | 6777 | 0.6 | 0 | 0 | 9.79 | 5500
TS5500Shv | RS\39\006\D | RS | 39 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2024-08-21 09:27 | 2024-08-22 23:37 | 40921.1373 |  |  | 40921 | [5 empty] | 0 | 0 | 0 | 5.81 | 5910.89
PH4100A | RS\40\005\A | RS | 40 | 5 | A | 1 Prestrip - Thick | 100 | 15.2877 | 15.2877 | 2024-08-21 12:42 | 2024-08-22 04:53 | 28108.0964 | 28108 | [7 empty] | 0 | 0 | 2.81 | 13.24 | 5254.77
DRE2 | GG\18\003\D | GG | 18 | 3 | D | 6 DL | 100 | 100 | 100 | 2024-08-22 00:22 | 2024-08-24 05:41 | 160199.2429 |  |  |  | 5562 | 160199 | 97533 |  |  | 0 | 19.33 | 0 | 6.54 | 5810.34
PH4100A | RS\40\004\B | RS | 40 | 4 | B | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2024-08-22 04:53 | 2024-08-22 15:34 | 18521.5127 | 18522 | [7 empty] | 0 | 0 | 1.85 | 9.03 | 5600.74
TS5500Exc | RS\40\005\A | RS | 40 | 5 | A | 8 Coal Mining | 92.1 | 0 | 92.1 | 2024-08-22 08:46 | 2024-08-23 18:51 | 42950.1895 | [6 empty] | 42950 | 30269 | 3.03 | 0 | 0 | 13.24 | 5255
DRE1 | RS\40\003\D | RS | 40 | 3 | D | 6 DL | 100 | 100 | 100 | 2024-08-22 13:27 | 2024-08-27 18:34 | 425381.3683 |  |  |  | 21871 | 425381 | 342638 |  |  | 0 | 27.64 | 0 | 5.34 | 5951.58
PH4100A | RS\41\003\X | RS | 41 | 3 | X | 1 Prestrip - Thick | 100 | 62.4894 | 62.4894 | 2024-08-22 15:34 | 2024-08-26 23:31 | 173334.6935 | 173335 | [7 empty] | 0 | 0 | 18.64 | 11.91 | 5282.45
TS5500Shv | RS\40\004\B | RS | 40 | 4 | B | 8 Coal Mining | 92 | 0 | 79.4 | 2024-08-22 23:37 | 2024-08-24 01:17 | 31307.2928 | [6 empty] | 31307 | 22540 | 2.25 | 0 | 0 | 9.03 | 5601
TS Fleet 5 | GG\22\009\X2 | GG | 22 | 9 | X2 | 1 Prestrip - Thick | 44.7879 | 0 | 44.7879 | 2024-08-23 03:13 | 2024-08-30 15:47 | 353911.3797 | 353911 | [7 empty] | 0 | 0 | 36.31 | 0 | 0
TS5500Exc | RS\40\004\B | RS | 40 | 4 | B | 8 Coal Mining | 100 | 0 | 20.6 | 2024-08-23 18:51 | 2024-08-24 01:17 | 8103.7359 | [6 empty] | 8104 | 5834 | 0.58 | 0 | 0 | 9.03 | 5601
TS5500Exc | RS\40\006\X | RS | 40 | 6 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-08-24 01:17 | 2024-08-24 09:01 | 9733.8705 | [6 empty] | 9734 | 7000 | 0.61 | 0 | 0 | 9.79 | 5500
TS5500Shv | RS\40\005\A | RS | 40 | 5 | A | 8 Coal Mining | 7.9 | 0 | 7.9 | 2024-08-24 01:17 | 2024-08-24 04:18 | 3678.6951 | [6 empty] | 3679 | 2593 | 0.26 | 0 | 0 | 13.24 | 5255
TS5500Shv | RS\39\006\D | RS | 39 | 6 | D | 8 Coal Mining | 13 | 0 | 13 | 2024-08-24 04:18 | 2024-08-24 09:42 | 6576.2459 | [6 empty] | 6576 | 4875 | 0.6 | 0 | 0 | 5.81 | 5911
DRE2 | GG\19\013\B | GG | 19 | 13 | B | 6 DL | 100 | 0 | 100 | 2024-08-24 05:41 | 2024-08-28 07:02 | 292535.0175 |  |  |  |  | 292535 | 243779 |  |  | 0 | 15.82 | 0 | 11.24 | 5407.4
TS5500Exc | RS\40\006\A | RS | 40 | 6 | A | 1 Prestrip - Thick | 100 | 41.338 | 41.338 | 2024-08-24 09:01 | 2024-08-27 20:03 | 73433.5768 | 73434 | [7 empty] | 0 | 0 | 7.34 | 15.93 | 5048.28
TS5500Shv | MW\50\007\B | MW | 50 | 7 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-08-24 09:42 | 2024-08-24 22:51 | 16037.286 | [6 empty] | 16037 | 11824 | 1.19 | 0 | 0 | 9.7 | 5533
TS5500Shv | GG\18\004\D | GG | 18 | 4 | D | 8 Coal Mining | 92.5 | 0 | 92.5 | 2024-08-24 22:51 | 2024-08-26 20:22 | 55506.4183 | [6 empty] | 55506 | 41594 | 4.16 | 0 | 0 | 6.61 | 5804
TS6060#1 | RS\40\006\A | RS | 40 | 6 | A | 1 Prestrip - Thick | 100 | 38.5899 | 38.5899 | 2024-08-25 01:37 | 2024-08-27 20:03 | 68551.8044 | 68552 | [7 empty] | 0 | 0 | 6.85 | 15.93 | 5048.28
PH4100XPC#1 | GG\21\010\B | GG | 21 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-08-25 12:31 | 2024-08-27 05:49 | 93464.8036 | 93465 | [7 empty] | 0 | 0 | 9.32 | 9.97 | 5530.13
TS5500Shv | GG\18\003\D | GG | 18 | 3 | D | 7 PostStrip | 38.7666 | 0 | 38.7666 | 2024-08-26 20:22 | 2024-08-27 09:23 | 13942.4723 |  |  | 13942 | [5 empty] | 0 | 0 | 0 | 6.54 | 5810.34
PH4100A | RS\40\006\A | RS | 40 | 6 | A | 1 Prestrip - Thick | 100 | 20.0721 | 20.0721 | 2024-08-26 23:31 | 2024-08-27 20:03 | 35656.3407 | 35656 | [7 empty] | 0 | 0 | 3.56 | 15.93 | 5048.28
PH4100XPC#1 | GG\21\011\X1 | GG | 21 | 11 | X1 | 1 Prestrip - Thick | 100 | 54.2981 | 54.2981 | 2024-08-27 05:49 | 2024-09-01 05:45 | 267670.4772 | 267670 | [7 empty] | 0 | 0 | 26.17 | 14.78 | 5115.38
TS5500Shv | RS\41\003\X | RS | 41 | 3 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-08-27 09:23 | 2024-08-27 15:17 | 7199.7524 | [6 empty] | 7200 | 5074 | 0.51 | 0 | 0 | 11.91 | 5282
TS5500Shv | MW\50\008\A | MW | 50 | 8 | A | 8 Coal Mining | 33.4 | 0 | 33.4 | 2024-08-27 15:17 | 2024-08-28 00:56 | 11767.8825 | [6 empty] | 11768 | 8591 | 1.14 | 0 | 0 | 11.79 | 5388
DRE1 | RS\40\004\D | RS | 40 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-08-27 18:34 | 2024-08-31 15:21 | 315438.0817 |  |  |  | 16218 | 315438 | 254080 |  |  | 0 | 27.03 | 0 | 5.54 | 5933.63
TS6060#1 | RS\40\005\B | RS | 40 | 5 | B | 1 Prestrip - Thick | 100 | 37.2787 | 37.2787 | 2024-08-27 20:03 | 2024-08-28 06:52 | 11158.8674 | 11159 | [7 empty] | 0 | 0 | 1.12 | 9.01 | 5609.68
PH4100A | RS\40\005\B | RS | 40 | 5 | B | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2024-08-27 20:03 | 2024-08-28 06:52 | 18774.7565 | 18775 | [7 empty] | 0 | 0 | 1.88 | 9.01 | 5609.68
TS5500Exc | RS\41\003\X | RS | 41 | 3 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-08-27 20:03 | 2024-08-28 01:57 | 7437.1068 | [6 empty] | 7437 | 5241 | 0.52 | 0 | 0 | 11.91 | 5282
TS5500Shv | RS\40\006\A | RS | 40 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-08-28 00:56 | 2024-08-28 20:21 | 23669.7957 | [6 empty] | 23670 | 16457 | 1.68 | 0 | 0 | 15.93 | 5048
TS5500Exc | RS\39\005\D | RS | 39 | 5 | D | 8 Coal Mining | 30.9 | 0 | 30.9 | 2024-08-28 01:57 | 2024-08-28 17:10 | 19161.7635 | [6 empty] | 19162 | 14194 | 1.42 | 0 | 0 | 5.7 | 5921
TS6060#1 | RS\41\003\A | RS | 41 | 3 | A | 1 Prestrip - Thick | 37.2787 | 37.2787 | 37.2787 | 2024-08-28 06:52 | 2024-08-31 03:47 | 71109.1239 | 71109 | [7 empty] | 0 | 0 | 6.96 | 12.11 | 5339.81
PH4100A | RS\41\003\A | RS | 41 | 3 | A | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2024-08-28 06:52 | 2024-08-31 03:47 | 119640.8597 | 119641 | [7 empty] | 0 | 0 | 11.72 | 12.11 | 5339.81
DRE2 | GG\19\018\B | GG | 19 | 18 | B | 6 DL | 100 | 0 | 100 | 2024-08-28 07:02 | 2024-08-30 23:07 | 192603.0955 |  |  |  |  | 192603 | 160503 |  |  | 0 | 16.04 | 0 | 11.53 | 5390.12
TS5500Exc | RS\40\006\A | RS | 40 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-08-28 17:10 | 2024-08-29 12:35 | 24450.1186 | [6 empty] | 24450 | 17000 | 1.73 | 0 | 0 | 15.93 | 5048
TS5500Shv | RS\40\005\B | RS | 40 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-08-28 20:21 | 2024-08-30 06:01 | 41057.4198 | [6 empty] | 41057 | 29547 | 2.96 | 0 | 0 | 9.01 | 5610
TS5500Exc | RS\39\006\D | RS | 39 | 6 | D | 8 Coal Mining | 87 | 0 | 87 | 2024-08-29 12:35 | 2024-08-30 23:31 | 44005.8652 | [6 empty] | 44006 | 32622 | 4.02 | 0 | 0 | 5.81 | 5911
TS5500Shv | RS\40\003\D | RS | 40 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-08-30 06:01 | 2024-09-01 23:42 | 80091.7751 | [6 empty] | 80092 | 59650 | 4.5 | 0 | 0 | 5.34 | 5952
TS Fleet 5 | GG\22\010\X1 | GG | 22 | 10 | X1 | 1 Prestrip - Thick | 40.7602 | 40.7602 | 40.7602 | 2024-08-30 15:47 | 2024-09-05 07:47 | 266579.3543 | 266579 | [7 empty] | 0 | 0 | 23.38 | 15.83 | 5028.89
DRE2 | GG\19\019\B | GG | 19 | 19 | B | 6 DL | 100 | 0 | 100 | 2024-08-30 23:07 | 2024-09-02 21:17 | 210838.6204 |  |  |  |  | 210839 | 175699 |  |  | 0 | 17.46 | 0 | 12.44 | 5334.94
TS5500Exc | MW\50\007\B | MW | 50 | 7 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-08-30 23:31 | 2024-08-31 12:40 | 16565.9877 | [6 empty] | 16566 | 12214 | 1.23 | 0 | 0 | 9.7 | 5533
PH4100A | RS\40\006\B | RS | 40 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-08-31 03:47 | 2024-08-31 21:48 | 31279.0859 | 31279 | [7 empty] | 0 | 0 | 3.2 | 9.06 | 5606.65
TS6060#1 | GG\18\004\D | GG | 18 | 4 | D | 8 Coal Mining | 7.5 | 0 | 7.5 | 2024-08-31 03:47 | 2024-08-31 07:08 | 4528.5925 | [6 empty] | 4529 | 3394 | 0.34 | 0 | 0 | 6.61 | 5804
TS6060#1 | GG\18\003\D | GG | 18 | 3 | D | 7 PostStrip | 61.2334 | 0 | 61.2334 | 2024-08-31 07:08 | 2024-09-01 04:28 | 22022.7303 |  |  | 22023 | [5 empty] | 0 | 0 | 0 | 6.54 | 5810.34
TS5500Exc | RS\41\003\A | RS | 41 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-08-31 12:40 | 2024-09-02 04:08 | 49719.272 | [6 empty] | 49719 | 35306 | 3.27 | 0 | 0 | 12.11 | 5340
DRE1 | MW\50\007\D | MW | 50 | 7 | D | 6 DL | 100 | 100 | 100 | 2024-08-31 15:21 | 2024-09-04 19:59 | 342159.0007 |  |  |  | 17592 | 342159 | 275604 |  |  | 0 | 29.33 | 0 | 5.99 | 5887.63
PH4100A | RS\41\004\X | RS | 41 | 4 | X | 1 Prestrip - Thick | 100 | 65.3971 | 65.3971 | 2024-08-31 21:48 | 2024-09-06 18:39 | 234328.2855 | 234328 | [7 empty] | 0 | 0 | 24.03 | 11.43 | 5335.82
TS6060#1 | GG\18\003\D | GG | 18 | 3 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-09-01 04:28 | 2024-09-01 21:06 | 22492.9332 | [6 empty] | 22493 | 16855 | 2.37 | 0 | 0 | 6.54 | 5810
PH4100XPC#1 | GG\21\012\X1 | GG | 21 | 12 | X1 | 1 Prestrip - Thick | 100 | 54.1461 | 54.1461 | 2024-09-01 05:45 | 2024-09-05 17:51 | 239767.0591 | 239767 | [7 empty] | 0 | 0 | 23.37 | 14.59 | 5131.32
TS6060#1 | GG\19\013\B | GG | 19 | 13 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-09-01 21:06 | 2024-09-03 01:05 | 37891.018 | [6 empty] | 37891 | 27622 | 1.82 | 0 | 0 | 11.24 | 5407
TS5500Shv | GG\21\011\X1 | GG | 21 | 11 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-09-01 23:42 | 2024-09-02 13:16 | 16542.2692 | [6 empty] | 16542 | 11837 | 1.2 | 0 | 0 | 14.78 | 5115
TS5500Exc | RS\40\006\B | RS | 40 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-09-02 04:08 | 2024-09-02 20:08 | 20155.4083 | [6 empty] | 20155 | 14493 | 1.49 | 0 | 0 | 9.06 | 5607
TS5500Shv | RS\40\006\B | RS | 40 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-09-02 13:16 | 2024-09-03 05:16 | 19512.1506 | [6 empty] | 19512 | 14031 | 1.44 | 0 | 0 | 9.06 | 5607
TS5500Exc | RS\40\004\D | RS | 40 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-09-02 20:08 | 2024-09-04 19:54 | 60150.7572 | [6 empty] | 60151 | 44586 | 4.46 | 0 | 0 | 5.54 | 5934
DRE2 | GG\19\020\B | GG | 19 | 20 | B | 6 DL | 100 | 0 | 100 | 2024-09-02 21:17 | 2024-09-06 22:11 | 291182.7374 |  |  |  |  | 291183 | 223987 |  |  | 0 | 23.08 | 0 | 15.16 | 5134.48
TS6060#1 | RS\41\003\B | RS | 41 | 3 | B | 1 Prestrip - Thick | 14.9536 | 14.9536 | 14.9536 | 2024-09-03 01:05 | 2024-09-03 05:48 | 4865.0921 | 4865 | [7 empty] | 0 | 0 | 0.44 | 9.17 | 5574.02
TS5500Shv | GG\18\003\D | GG | 18 | 3 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-09-03 05:16 | 2024-09-03 21:53 | 20265.9101 | [6 empty] | 20266 | 15186 | 2.14 | 0 | 0 | 6.54 | 5810
TS6060#1 | GG\19\018\B | GG | 19 | 18 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-09-03 05:48 | 2024-09-04 01:18 | 26382.2476 | [6 empty] | 26382 | 19196 | 1.92 | 0 | 0 | 11.53 | 5390
TS5500Shv | GG\19\013\B | GG | 19 | 13 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-09-03 21:53 | 2024-09-05 03:56 | 36637.6112 | [6 empty] | 36638 | 26708 | 1.76 | 0 | 0 | 11.24 | 5407
TS6060#1 | GG\19\019\B | GG | 19 | 19 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-09-04 01:18 | 2024-09-05 16:21 | 52847.119 | [6 empty] | 52847 | 38194 | 3.82 | 0 | 0 | 12.44 | 5335
TS5500Exc | MW\50\008\A | MW | 50 | 8 | A | 8 Coal Mining | 66.6 | 0 | 66.6 | 2024-09-04 19:54 | 2024-09-05 14:31 | 23452.8554 | [6 empty] | 23453 | 17121 | 2.28 | 0 | 0 | 11.79 | 5388
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2024-09-04 19:59 | 2024-09-06 19:59
TS5500Shv | MW\50\007\D | MW | 50 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-09-05 03:56 | 2024-09-07 08:36 | 64225.2335 | [6 empty] | 64225 | 48608 | 4.86 | 0 | 0 | 5.99 | 5888
TS Fleet 5 | GG\21\011\X2 | GG | 21 | 11 | X2 | 1 Prestrip - Thick | 45.3511 | 0 | 45.3511 | 2024-09-05 07:47 | 2024-09-06 00:07 | 32009.1475 | 32009 | [7 empty] | 0 | 0 | 3.24 | 0 | 0
TS5500Exc | MW\50\008\B | MW | 50 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-09-05 14:31 | 2024-09-06 13:22 | 20215.0189 | 20215 | [7 empty] | 0 | 0 | 2.71 | 9.28 | 5571.83
TS6060#1 | RS\44\004\X | RS | 44 | 4 | X | 1 Prestrip - Thick | 24.8855 | 24.8855 | 24.8855 | 2024-09-05 16:21 | 2024-09-08 12:00 | 66841.9033 | 66842 | [7 empty] | 0 | 0 | 6.86 | 11.23 | 5357.47
PH4100XPC#1 | GG\21\011\X2 | GG | 21 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.6489 | 2024-09-05 17:51 | 2024-09-06 10:53 | 38571.5265 | 38572 | [7 empty] | 0 | 0 | 3.9 | 0 | 0
TS Fleet 5 | GG\22\011\X1 | GG | 22 | 11 | X1 | 1 Prestrip - Thick | 45.7084 | 45.7084 | 45.7084 | 2024-09-06 00:07 | 2024-09-11 04:03 | 242915.6106 | 242916 | [7 empty] | 0 | 0 | 23.82 | 14.89 | 5107.08
PH4100XPC#1 | GG\21\011\B | GG | 21 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-09-06 10:53 | 2024-09-08 15:40 | 119452.4759 | 119452 | [7 empty] | 0 | 0 | 12 | 10.06 | 5518.05
TS5500Exc | MW\50\008\B | MW | 50 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-09-06 13:22 | 2024-09-07 12:43 | 29396.1976 | [6 empty] | 29396 | 21739 | 2.93 | 0 | 0 | 9.28 | 5572
PH4100A | RS\41\003\B | RS | 41 | 3 | B | 1 Prestrip - Thick | 100 | 85.0464 | 85.0464 | 2024-09-06 18:39 | 2024-09-07 10:35 | 27669.3946 | 27669 | [7 empty] | 0 | 0 | 2.52 | 9.17 | 5574.02
DRE1 | RS\40\005\D | RS | 40 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-09-06 19:59 | 2024-09-10 12:47 | 301948.2704 |  |  |  | 15524 | 301948 | 243215 |  |  | 0 | 25.87 | 0 | 5.74 | 5917.3
DRE2 | GG\19\021\B | GG | 19 | 21 | B | 6 DL | 100 | 0 | 100 | 2024-09-06 22:11 | 2024-09-10 10:24 | 253026.8088 |  |  |  |  | 253027 | 194636 |  |  | 0 | 21.52 | 0 | 17.56 | 4972.43
TS5500Shv | GG\21\012\X1 | GG | 21 | 12 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-09-07 08:36 | 2024-09-07 14:35 | 7294.5545 | [6 empty] | 7295 | 5229 | 0.53 | 0 | 0 | 14.59 | 5131
PH4100A | RS\41\005\X | RS | 41 | 5 | X | 1 Prestrip - Thick | 100 | 66.6156 | 66.6156 | 2024-09-07 10:35 | 2024-09-13 19:45 | 257081.2414 | 257081 | [7 empty] | 0 | 0 | 26.14 | 10.72 | 5408.89
TS5500Exc | RS\41\003\B | RS | 41 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-09-07 12:43 | 2024-09-08 06:13 | 22061.4164 | [6 empty] | 22061 | 15882 | 1.42 | 0 | 0 | 9.17 | 5574
TS5500Shv | RS\41\003\B | RS | 41 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-09-07 14:35 | 2024-09-08 08:06 | 21357.3287 | [6 empty] | 21357 | 15375 | 1.38 | 0 | 0 | 9.17 | 5574
TS5500Exc | RS\41\004\X | RS | 41 | 4 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-09-08 06:13 | 2024-09-08 13:49 | 9565.6275 | [6 empty] | 9566 | 6770 | 0.68 | 0 | 0 | 11.43 | 5336
TS5500Shv | RS\41\004\X | RS | 41 | 4 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-09-08 08:06 | 2024-09-08 15:41 | 9260.3415 | [6 empty] | 9260 | 6554 | 0.65 | 0 | 0 | 11.43 | 5336
TS6060#1 | GG\21\012\X1 | GG | 21 | 12 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-09-08 12:00 | 2024-09-08 17:59 | 8096.1539 | [6 empty] | 8096 | 5804 | 0.59 | 0 | 0 | 14.59 | 5131
TS5500Exc | MW\51\004\D | MW | 51 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-09-08 13:49 | 2024-09-13 05:27 | 98741.0798 | 98741 | [7 empty] | 0 | 0 | 25.02 | 8.42 | 5666.85
PH4100XPC#1 | GG\21\013\X1 | GG | 21 | 13 | X1 | 1 Prestrip - Thick | 100 | 53.8754 | 53.8754 | 2024-09-08 15:40 | 2024-09-12 12:04 | 202734.1953 | 202734 | [7 empty] | 0 | 0 | 19.73 | 14.38 | 5148.39
TS5500Shv | GG\19\018\B | GG | 19 | 18 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-09-08 15:41 | 2024-09-09 11:11 | 23770.1439 | [6 empty] | 23770 | 17295 | 1.73 | 0 | 0 | 11.53 | 5390
TS6060#1 | RS\41\004\A | RS | 41 | 4 | A | 1 Prestrip - Thick | 17.3 | 17.3 | 17.3 | 2024-09-08 17:59 | 2024-09-10 01:21 | 32365.3598 | 32365 | [7 empty] | 0 | 0 | 3.23 | 12.22 | 5332.09
TS5500Shv | GG\21\012\X2 | GG | 21 | 12 | X2 | 1 Prestrip - Thick | 41.7138 | 0 | 41.7138 | 2024-09-09 11:11 | 2024-09-10 15:25 | 30273.4149 | 30273 | [7 empty] | 0 | 0 | 3.06 | 0 | 0
TS6060#1 | RS\44\005\X | RS | 44 | 5 | X | 1 Prestrip - Thick | 35.0459 | 35.0459 | 35.0459 | 2024-09-10 01:21 | 2024-09-17 17:46 | 184618.749 | 184619 | [7 empty] | 0 | 0 | 11.98 | 10.28 | 5451.74
DRE2 | GG\19\022\B | GG | 19 | 22 | B | 6 DL | 100 | 0 | 100 | 2024-09-10 10:24 | 2024-09-14 01:31 | 261801.5409 |  |  |  |  | 261802 | 201386 |  |  | 0 | 21.5 | 0 | 19.34 | 4827.88
DRE1 | MW\50\008\D | MW | 50 | 8 | D | 6 DL | 100 | 100 | 100 | 2024-09-10 12:47 | 2024-09-12 12:31 | 162296.4692 |  |  |  | 8344 | 162296 | 130727 |  |  | 0 | 28.79 | 0 | 5.44 | 5935.24
TS5500Shv | RS\40\005\D | RS | 40 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-09-10 15:25 | 2024-09-11 16:52 | 31020.7373 | [6 empty] | 31021 | 22961 | 2.3 | 0 | 0 | 5.74 | 5917
TS Fleet 5 | GG\21\012\X2 | GG | 21 | 12 | X2 | 1 Prestrip - Thick | 38.207 | 0 | 38.207 | 2024-09-11 04:03 | 2024-09-11 18:12 | 27728.3824 | 27728 | [7 empty] | 0 | 0 | 2.8 | 0 | 0
TS5500Shv | GG\19\020\B | GG | 19 | 20 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-09-11 16:52 | 2024-09-12 12:37 | 24089.2242 | [6 empty] | 24089 | 17122 | 1.73 | 0 | 0 | 15.16 | 5134
TS Fleet 5 | GG\22\012\X1 | GG | 22 | 12 | X1 | 1 Prestrip - Thick | 41.8539 | 41.8539 | 41.8539 | 2024-09-11 18:12 | 2024-09-16 00:20 | 200184.8963 | 200185 | [7 empty] | 0 | 0 | 19.51 | 14.75 | 5119.05
PH4100XPC#1 | GG\21\012\X2 | GG | 21 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 20.0793 | 2024-09-12 12:04 | 2024-09-12 18:30 | 14572.3617 | 14572 | [7 empty] | 0 | 0 | 1.47 | 0 | 0
DRE1 | RS\40\006\D | RS | 40 | 6 | D | 6 DL | 100 | 100 | 100 | 2024-09-12 12:31 | 2024-09-16 00:02 | 283945.1466 |  |  |  | 10616 | 283945 | 161163 |  |  | 0 | 26.19 | 0 | 5.82 | 5909.54
TS5500Shv | GG\19\021\B | GG | 19 | 21 | B | 8 Coal Mining | 43.2 | 0 | 43.2 | 2024-09-12 12:37 | 2024-09-12 23:55 | 13776.5178 | [6 empty] | 13777 | 9635 | 1 | 0 | 0 | 17.56 | 4972
PH4100XPC#1 | GG\21\012\B | GG | 21 | 12 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-09-12 18:30 | 2024-09-15 04:14 | 130687.4592 | 130687 | [7 empty] | 0 | 0 | 13.11 | 10.82 | 5447.23
TS5500Shv | MW\50\008\D | MW | 50 | 8 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-09-12 23:55 | 2024-09-13 11:41 | 14353.7603 | [6 empty] | 14354 | 10906 | 2.31 | 0 | 0 | 5.44 | 5935
TS5500Exc | GG\19\021\B | GG | 19 | 21 | B | 8 Coal Mining | 100 | 0 | 56.8 | 2024-09-13 05:27 | 2024-09-13 19:50 | 18118.8797 | [6 empty] | 18119 | 12671 | 1.32 | 0 | 0 | 17.56 | 4972
TS5500Shv | GG\22\014\X1 | GG | 22 | 14 | X1 | 1 Prestrip - Thick | 14.1123 | 14.1123 | 14.1123 | 2024-09-13 11:41 | 2024-09-15 06:54 | 45136.7773 | 45137 | [7 empty] | 0 | 0 | 3.9 | 14.31 | 5153.7
PH4100A | RS\41\004\A | RS | 41 | 4 | A | 1 Prestrip - Thick | 100 | 82.7 | 82.7 | 2024-09-13 19:45 | 2024-09-17 12:52 | 154717.3101 | 154717 | [7 empty] | 0 | 0 | 15.45 | 12.22 | 5332.09
TS5500Exc | RS\41\005\X | RS | 41 | 5 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-09-13 19:50 | 2024-09-14 03:56 | 10203.0543 | [6 empty] | 10203 | 7272 | 0.73 | 0 | 0 | 10.72 | 5409
DRE2 | GG\19\023\B | GG | 19 | 23 | B | 6 DL | 100 | 0 | 100 | 2024-09-14 01:31 | 2024-09-18 20:17 | 344887.6857 |  |  |  |  | 344888 | 265298 |  |  | 0 | 23.16 | 0 | 0 | 0
TS5500Exc | RS\40\005\D | RS | 40 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-09-14 03:56 | 2024-09-15 05:22 | 32043.399 | [6 empty] | 32043 | 23718 | 2.37 | 0 | 0 | 5.74 | 5917
PH4100XPC#1 | GG\21\014\X1 | GG | 21 | 14 | X1 | 1 Prestrip - Thick | 100 | 53.4853 | 53.4853 | 2024-09-15 04:14 | 2024-09-18 02:13 | 151162.1159 | 151162 | [7 empty] | 0 | 0 | 14.69 | 14.23 | 5160.09
TS5500Exc | MW\50\008\D | MW | 50 | 8 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-09-15 05:22 | 2024-09-15 17:08 | 14826.9611 | [6 empty] | 14827 | 11266 | 2.39 | 0 | 0 | 5.44 | 5935
TS5500Shv | RS\41\005\X | RS | 41 | 5 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-09-15 06:54 | 2024-09-15 15:00 | 9877.4249 | [6 empty] | 9877 | 7040 | 0.7 | 0 | 0 | 10.72 | 5409
TS5500Shv | GG\19\022\B | GG | 19 | 22 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-09-15 15:00 | 2024-09-17 13:20 | 56503.3587 | [6 empty] | 56503 | 39184 | 3.94 | 0 | 0 | 19.34 | 4828
TS5500Exc | MW\51\005\D | MW | 51 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-09-15 17:08 | 2024-09-25 08:32 | 204678.9576 | 204679 | [7 empty] | 0 | 0 | 20.98 | 8.32 | 5680.83
DRE1 | MW\51\004\D | MW | 51 | 4 | D | 6 DL | 100 | 0 | 100 | 2024-09-16 00:02 | 2024-09-18 20:51 | 233984.096 |  |  |  | 12568 | 233984 | 107862 |  |  | 0 | 35 | 0 | 8.42 | 5666.85
TS Fleet 5 | GG\22\013\X1 | GG | 22 | 13 | X1 | 1 Prestrip - Thick | 46.1305 | 46.1305 | 46.1305 | 2024-09-16 00:20 | 2024-09-19 20:38 | 180908.8611 | 180909 | [7 empty] | 0 | 0 | 17.64 | 14.54 | 5136.08
PH4100A | RS\41\005\A | RS | 41 | 5 | A | 1 Prestrip - Thick | 100 | 68.1795 | 68.1795 | 2024-09-17 12:52 | 2024-09-20 14:19 | 127502.2771 | 127502 | [7 empty] | 0 | 0 | 12.76 | 12.91 | 5280.92
TS5500Shv | RS\41\004\A | RS | 41 | 4 | A | 8 Coal Mining | 83.1 | 0 | 83.1 | 2024-09-17 13:20 | 2024-09-18 20:17 | 37735.7187 | [6 empty] | 37736 | 26733 | 2.67 | 0 | 0 | 12.22 | 5332
TS6060#1 | GG\21\013\X1 | GG | 21 | 13 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-09-17 17:46 | 2024-09-18 04:38 | 14720.2992 | [6 empty] | 14720 | 10574 | 1.05 | 0 | 0 | 14.38 | 5148
PH4100XPC#1 | GG\21\018\X2 | GG | 21 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.7717 | 2024-09-18 02:13 | 2024-09-20 18:24 | 140206.4316 | 140206 | [7 empty] | 0 | 0 | 14.05 | 0 | 0
TS6060#1 | RS\41\005\A | RS | 41 | 5 | A | 1 Prestrip - Thick | 37.2787 | 31.8205 | 31.8205 | 2024-09-18 04:38 | 2024-09-20 14:19 | 59507.429 | 59507 | [7 empty] | 0 | 0 | 5.95 | 12.91 | 5280.92
TS5500Shv | GG\21\014\X1 | GG | 21 | 14 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-09-18 20:17 | 2024-09-19 07:55 | 14190.9322 | [6 empty] | 14191 | 10210 | 1.02 | 0 | 0 | 14.23 | 5160
DRE2 | GG\18\013\D | GG | 18 | 13 | D | 6 DL | 100 | 100 | 100 | 2024-09-18 20:17 | 2024-09-28 03:12 | 669846.912 |  |  |  | 15596 | 669847 | 296323 |  |  | 0 | 24.37 | 0 | 7.12 | 5762.43
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2024-09-18 20:51 | 2024-09-21 20:51
TS5500Shv | RS\40\006\D | RS | 40 | 6 | D | 7 PostStrip | 43.9522 | 0 | 43.9522 | 2024-09-19 07:55 | 2024-09-20 00:32 | 17819.0565 |  |  | 17819 | [5 empty] | 0 | 0 | 0 | 5.82 | 5909.54
TS Fleet 5 | GG\21\013\X2 | GG | 21 | 13 | X2 | 1 Prestrip - Thick | 45.3511 | 0 | 45.3511 | 2024-09-19 20:38 | 2024-09-20 14:11 | 34384.3636 | 34384 | [7 empty] | 0 | 0 | 3.43 | 0 | 0
TS5500Shv | MW\51\004\D | MW | 51 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2024-09-20 00:32 | 2024-09-20 18:28 | 19214.8918 |  |  | 19215 | [5 empty] | 0 | 0 | 0 | 8.42 | 5666.85
TS Fleet 5 | GG\21\014\X2 | GG | 21 | 14 | X2 | 1 Prestrip - Thick | 45.3511 | 0 | 45.3511 | 2024-09-20 14:11 | 2024-09-21 07:54 | 34733.9045 | 34734 | [7 empty] | 0 | 0 | 3.53 | 0 | 0
PH4100A | RS\41\006\X | RS | 41 | 6 | X | 1 Prestrip - Thick | 100 | 62.5507 | 62.5507 | 2024-09-20 14:19 | 2024-09-28 04:07 | 306359.9884 | 306360 | [7 empty] | 0 | 0 | 29.28 | 9.7 | 5508.47
TS6060#1 | RS\45\002\A | RS | 45 | 2 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-09-20 14:19 | 2024-09-23 22:06 | 81822.7527 | 81823 | [7 empty] | 0 | 0 | 31.86 | 11.69 | 5390.41
PH4100XPC#1 | GG\21\013\X2 | GG | 21 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.6489 | 2024-09-20 18:24 | 2024-09-21 12:42 | 41433.6994 | 41434 | [7 empty] | 0 | 0 | 4.14 | 0 | 0
TS5500Shv | RS\41\005\A | RS | 41 | 5 | A | 8 Coal Mining | 37.8 | 0 | 37.8 | 2024-09-20 18:28 | 2024-09-21 08:49 | 17497.8478 | [6 empty] | 17498 | 12343 | 1.24 | 0 | 0 | 12.91 | 5281
TS Fleet 5 | GG\21\018\B | GG | 21 | 18 | B | 1 Prestrip - Thick | 45.3511 | 45.3511 | 45.3511 | 2024-09-21 07:54 | 2024-09-22 17:15 | 65341.7786 | 65342 | [7 empty] | 0 | 0 | 6.5 | 12.19 | 5334.72
TS5500Shv | MW\51\004\D | MW | 51 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-09-21 08:49 | 2024-09-21 23:40 | 18105.6904 | [6 empty] | 18106 | 13454 | 3.73 | 0 | 0 | 8.42 | 5667
PH4100XPC#1 | GG\21\013\B | GG | 21 | 13 | B | 1 Prestrip - Thick | 100 | 74.9936 | 74.9936 | 2024-09-21 12:42 | 2024-09-23 11:07 | 105075.2895 | 105075 | [7 empty] | 0 | 0 | 10.54 | 11.68 | 5366.88
DRE1 | RS\41\003\D | RS | 41 | 3 | D | 6 DL | 100 | 100 | 100 | 2024-09-21 20:51 | 2024-09-27 08:17 | 446850.3577 |  |  |  | 22974 | 446850 | 359931 |  |  | 0 | 27.68 | 0 | 5.38 | 5948.92
TS5500Shv | GG\22\021\D | GG | 22 | 21 | D | 1 Prestrip - Thick | 1.6431 | 1.6431 | 1.6431 | 2024-09-21 23:40 | 2024-09-22 04:55 | 5651.5152 | 5652 | [7 empty] | 0 | 0 | 0.57 | 6.8 | 5789.37
TS5500Shv | GG\22\022\B | GG | 22 | 22 | B | 1 Prestrip - Thick | 20.4693 | 20.4693 | 20.4693 | 2024-09-22 04:55 | 2024-09-23 20:46 | 42701.9425 | 42702 | [7 empty] | 0 | 0 | 4.96 | 20.5 | 4725.37
TS Fleet 5 | GG\21\013\B | GG | 21 | 13 | B | 1 Prestrip - Thick | 45.3511 | 25.0064 | 25.0064 | 2024-09-22 17:15 | 2024-09-23 11:07 | 35037.0721 | 35037 | [7 empty] | 0 | 0 | 3.52 | 11.68 | 5366.88
PH4100XPC#1 | GG\21\014\X2 | GG | 21 | 14 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.6489 | 2024-09-23 11:07 | 2024-09-24 05:37 | 41854.9015 | 41855 | [7 empty] | 0 | 0 | 4.25 | 0 | 0
TS Fleet 5 | GG\22\014\X1 | GG | 22 | 14 | X1 | 1 Prestrip - Thick | 39.9924 | 39.9924 | 39.9924 | 2024-09-23 11:07 | 2024-09-26 04:23 | 127911.9323 | 127912 | [7 empty] | 0 | 0 | 11.04 | 14.31 | 5153.7
TS5500Shv | RS\46\003\A | RS | 46 | 3 | A | 1 Prestrip - Thick | 9.939 | 9.939 | 9.939 | 2024-09-23 20:46 | 2024-09-25 08:45 | 37497.1721 | 37497 | [7 empty] | 0 | 0 | 3.86 | 12.29 | 5343.44
TS6060#1 | RS\45\003\A | RS | 45 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-09-23 22:06 | 2024-10-10 15:31 | 405427.1337 | 405427 | [7 empty] | 0 | 0 | 41.49 | 12.22 | 5344.91
PH4100XPC#1 | GG\21\014\B | GG | 21 | 14 | B | 1 Prestrip - Thick | 100 | 89.9059 | 89.9059 | 2024-09-24 05:37 | 2024-09-26 11:21 | 121636.5531 | 121637 | [7 empty] | 0 | 0 | 14.18 | 12.3 | 5314.14
TS5500Exc | RS\41\004\A | RS | 41 | 4 | A | 8 Coal Mining | 16.9 | 0 | 16.9 | 2024-09-25 08:32 | 2024-09-25 14:39 | 7690.5718 | [6 empty] | 7691 | 5448 | 0.54 | 0 | 0 | 12.22 | 5332
TS5500Shv | RS\45\002\A | RS | 45 | 2 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-09-25 08:45 | 2024-09-25 21:59 | 16152.6993 | [6 empty] | 16153 | 11515 | 3.37 | 0 | 0 | 11.69 | 5390
TS5500Exc | RS\46\004\A | RS | 46 | 4 | A | 1 Prestrip - Thick | 100 | 86.8727 | 86.8727 | 2024-09-25 14:39 | 2024-10-12 23:12 | 369870.4167 | 369870 | [7 empty] | 0 | 0 | 37.61 | 14.53 | 5153.02
TS5500Shv | MW\60\004\D | MW | 60 | 4 | D | 8 Coal Mining | 52.1 | 0 | 52.1 | 2024-09-25 21:59 | 2024-09-26 22:55 | 30388.8908 | [6 empty] | 30389 | 22587 | 1.93 | 0 | 0 | 8.7 | 5644
TS Fleet 5 | GG\21\014\B | GG | 21 | 14 | B | 1 Prestrip - Thick | 45.3511 | 10.0941 | 10.0941 | 2024-09-26 04:23 | 2024-09-26 11:21 | 13656.6208 | 13657 | [7 empty] | 0 | 0 | 1.59 | 12.3 | 5314.14
PH4100XPC#1 | GG\21\018\B | GG | 21 | 18 | B | 1 Prestrip - Thick | 100 | 54.6489 | 54.6489 | 2024-09-26 11:21 | 2024-09-27 22:08 | 78737.8716 | 78738 | [7 empty] | 0 | 0 | 7.83 | 12.19 | 5334.72
TS Fleet 5 | GG\22\018\X2 | GG | 22 | 18 | X2 | 1 Prestrip - Thick | 46.2628 | 0 | 46.2628 | 2024-09-26 11:21 | 2024-09-28 20:55 | 112830.0817 | 112830 | [7 empty] | 0 | 0 | 11.54 | 0 | 0
TS5500Shv | RS\46\005\X | RS | 46 | 5 | X | 1 Prestrip - Thick | 12.0138 | 12.0138 | 12.0138 | 2024-09-26 22:55 | 2024-09-28 14:17 | 40286.253 | 40286 | [7 empty] | 0 | 0 | 3.26 | 10.42 | 5438.39
DRE1 | MW\51\005\D | MW | 51 | 5 | D | 6 DL | 100 | 0 | 100 | 2024-09-27 08:17 | 2024-10-02 17:14 | 438431.9924 |  |  |  | 31180 | 438432 | 315269 |  |  | 0 | 35 | 0 | 8.32 | 5680.83
PH4100XPC#1 | GG\21\019\B | GG | 21 | 19 | B | 1 Prestrip - Thick | 100 | 48.6178 | 48.6178 | 2024-09-27 22:08 | 2024-09-30 17:03 | 149671.9741 | 149672 | [7 empty] | 0 | 0 | 15.14 | 12.76 | 5308.58
DRE2 | GG\18\018\D | GG | 18 | 18 | D | 6 DL | 100 | 100 | 100 | 2024-09-28 03:12 | 2024-10-05 07:11 | 516792.6334 |  |  |  | 12032 | 516793 | 228616 |  |  | 0 | 24.07 | 0 | 7.22 | 5754.19
PH4100A | RS\41\004\B | RS | 41 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-09-28 04:07 | 2024-09-28 20:25 | 28304.2183 | 28304 | [7 empty] | 0 | 0 | 2.83 | 9.05 | 5601.08
TS5500Shv | RS\41\006\X | RS | 41 | 6 | X | 8 Coal Mining | 100 | 0 | 100 | 2024-09-28 14:17 | 2024-09-29 04:44 | 17611.5514 | [6 empty] | 17612 | 12674 | 1.22 | 0 | 0 | 9.7 | 5508
PH4100A | RS\42\003\X | RS | 42 | 3 | X | 1 Prestrip - Thick | 100 | 62.4789 | 62.4789 | 2024-09-28 20:25 | 2024-10-03 02:33 | 169997.8751 | 169998 | [7 empty] | 0 | 0 | 17.15 | 11.87 | 5286.84
TS Fleet 5 | GG\22\019\B | GG | 22 | 19 | B | 1 Prestrip - Thick | 45.6594 | 45.6594 | 45.6594 | 2024-09-28 20:55 | 2024-10-01 19:41 | 138705.2018 | 138705 | [7 empty] | 0 | 0 | 14 | 12.95 | 5293.55
TS5500Shv | RS\41\004\B | RS | 41 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-09-29 04:44 | 2024-09-29 20:45 | 19520.8961 | [6 empty] | 19521 | 14045 | 1.4 | 0 | 0 | 9.05 | 5601
TS5500Shv | RS\41\003\D | RS | 41 | 3 | D | 8 Coal Mining | 34.6 | 0 | 34.6 | 2024-09-29 20:45 | 2024-09-30 20:39 | 29161.4839 | [6 empty] | 29161 | 21722 | 1.56 | 0 | 0 | 5.38 | 5949
PH4100XPC#1 | GG\21\020\B | GG | 21 | 20 | B | 1 Prestrip - Thick | 100 | 55.4046 | 55.4046 | 2024-09-30 17:03 | 2024-10-02 23:24 | 126834.8647 | 126835 | [7 empty] | 0 | 0 | 12.27 | 15.62 | 5098.53
TS5500Shv | GG\18\013\D | GG | 18 | 13 | D | 8 Coal Mining | 65 | 0 | 65 | 2024-09-30 20:39 | 2024-10-02 15:50 | 52654.6902 | [6 empty] | 52655 | 39210 | 3.09 | 0 | 0 | 7.12 | 5762
TS Fleet 5 | GG\22\020\B | GG | 22 | 20 | B | 1 Prestrip - Thick | 44.7517 | 44.7517 | 44.7517 | 2024-10-01 19:41 | 2024-10-03 18:58 | 92688.0596 | 92688 | [7 empty] | 0 | 0 | 9.42 | 15.83 | 5080.85
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 01:24 |  | 0d 01:24 | 2024-10-02 15:50 | 2024-10-02 17:14
DRE1 | SC\39\016\D | SC | 39 | 16 | D | 6 DL | 100 | 0 | 100 | 2024-10-02 17:14 | 2024-10-09 19:43 | 579659.9596 |  |  |  | 30743 | 579660 | 408442 |  |  | 0 | 33.36 | 0 | 7.09 | 5784.42
TS5500Shv | MW\51\005\D | MW | 51 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-10-02 17:14 | 2024-10-04 18:46 | 60407.4989 | [6 empty] | 60407 | 44987 | 4.5 | 0 | 0 | 8.32 | 5681
PH4100XPC#1 | GG\21\021\B | GG | 21 | 21 | B | 1 Prestrip - Thick | 100 | 55.7831 | 55.7831 | 2024-10-02 23:24 | 2024-10-06 05:02 | 183992.4232 | 183992 | [7 empty] | 0 | 0 | 20.53 | 19.73 | 4791.58
PH4100A | RS\41\006\A | RS | 41 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-10-03 02:33 | 2024-10-07 05:13 | 171276.9882 | 171277 | [7 empty] | 0 | 0 | 17.96 | 15.94 | 5049.98
TS Fleet 5 | GG\22\021\D | GG | 22 | 21 | D | 1 Prestrip - Thick | 43.5973 | 43.5973 | 43.5973 | 2024-10-03 18:58 | 2024-10-06 23:29 | 149957.7226 | 149958 | [7 empty] | 0 | 0 | 15.26 | 6.8 | 5789.37
TS5500Shv | RS\42\003\X | RS | 42 | 3 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-10-04 18:46 | 2024-10-05 01:02 | 7624.2876 | [6 empty] | 7624 | 5375 | 0.51 | 0 | 0 | 11.87 | 5287
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 06:09 |  | 0d 06:09 | 2024-10-05 01:02 | 2024-10-05 07:11
DRE2 | GG\18\019\D | GG | 18 | 19 | D | 6 DL | 100 | 100 | 100 | 2024-10-05 07:11 | 2024-10-12 00:07 | 483576.848 |  |  |  | 11259 | 483577 | 213922 |  |  | 0 | 22.52 | 0 | 7.06 | 5767.9
TS5500Shv | GG\18\018\D | GG | 18 | 18 | D | 8 Coal Mining | 83.5 | 0 | 83.5 | 2024-10-05 07:11 | 2024-10-07 03:23 | 53896.561 | [6 empty] | 53897 | 40103 | 4.01 | 0 | 0 | 7.22 | 5754
PH4100XPC#1 | GG\21\022\B | GG | 21 | 22 | B | 1 Prestrip - Thick | 100 | 54.6909 | 54.6909 | 2024-10-06 05:02 | 2024-10-08 08:18 | 116228.0911 | 116228 | [7 empty] | 0 | 0 | 12.73 | 20.7 | 4712.85
TS Fleet 5 | GG\22\022\B | GG | 22 | 22 | B | 1 Prestrip - Thick | 35.8853 | 35.8853 | 35.8853 | 2024-10-06 23:29 | 2024-10-08 13:40 | 74862.1581 | 74862 | [7 empty] | 0 | 0 | 8.69 | 20.5 | 4725.37
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 12:08 |  | 3d 12:08 | 2024-10-07 03:23 | 2024-10-10 15:31
PH4100A | RS\42\004\X | RS | 42 | 4 | X | 1 Prestrip - Thick | 100 | 69.698 | 69.698 | 2024-10-07 05:13 | 2024-10-12 22:19 | 227127.4257 | 227127 | [7 empty] | 0 | 0 | 23.32 | 11.37 | 5343.15
PH4100XPC#1 | GG\21\023\B | GG | 21 | 23 | B | 1 Prestrip - Thick | 100 | 55.5063 | 55.5063 | 2024-10-08 08:18 | 2024-10-12 04:12 | 215334.9912 | 215335 | [7 empty] | 0 | 0 | 26.52 | 0 | 0
TS Fleet 5 | GG\22\023\B | GG | 22 | 23 | B | 1 Prestrip - Thick | 44.1683 | 44.1683 | 44.1683 | 2024-10-08 13:40 | 2024-10-12 00:05 | 161507.3919 | 161507 | [7 empty] | 0 | 0 | 23.21 | 0 | 0
DRE1 | SC\39\015\D | SC | 39 | 15 | D | 6 DL | 100 | 0 | 100 | 2024-10-09 19:43 | 2024-10-17 06:10 | 606708.3275 |  |  |  | 34627 | 606708 | 460040 |  |  | 0 | 33.89 | 0 | 7.39 | 5758.94
TS6060#1 | RS\46\004\A | RS | 46 | 4 | A | 1 Prestrip - Thick | 100 | 13.1273 | 13.1273 | 2024-10-10 15:31 | 2024-10-12 23:12 | 55891.1007 | 55891 | [7 empty] | 0 | 0 | 5.68 | 14.53 | 5153.02
TS5500Shv | RS\45\003\A | RS | 45 | 3 | A | 8 Coal Mining | 52.7 | 0 | 52.7 | 2024-10-10 15:31 | 2024-10-11 11:32 | 24397.6218 | [6 empty] | 24398 | 17306 | 1.73 | 0 | 0 | 12.22 | 5345
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 12:35 |  | 0d 12:35 | 2024-10-11 11:32 | 2024-10-12 00:07
TS Fleet 5 | RS\46\003\A | RS | 46 | 3 | A | 1 Prestrip - Thick | 53.1527 | 53.1527 | 53.1527 | 2024-10-12 00:05 | 2024-10-16 06:23 | 200530.4456 | 200530 | [7 empty] | 0 | 0 | 20.64 | 12.29 | 5343.44
DRE2 | GG\18\020\D | GG | 18 | 20 | D | 6 DL | 100 | 100 | 100 | 2024-10-12 00:07 | 2024-10-17 05:42 | 377412.4198 |  |  |  | 7028 | 377412 | 168676 |  |  | 0 | 17.6 | 0 | 6.92 | 5780.34
TS5500Shv | GG\18\019\D | GG | 18 | 19 | D | 8 Coal Mining | 38.6 | 0 | 38.6 | 2024-10-12 00:07 | 2024-10-12 20:20 | 24653.7315 | [6 empty] | 24654 | 18358 | 1.84 | 0 | 0 | 7.06 | 5768
PH4100XPC#1 | GG\22\004\X1 | GG | 22 | 4 | X1 | 1 Prestrip - Thick | 100 | 49.539 | 49.539 | 2024-10-12 04:12 | 2024-10-25 05:49 | 732625.9919 | 732626 | [7 empty] | 0 | 0 | 52.09 | 10.77 | 5292.65
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 01:59 |  | 0d 01:59 | 2024-10-12 20:20 | 2024-10-12 22:19
PH4100A | RS\42\005\X | RS | 42 | 5 | X | 1 Prestrip - Thick | 100 | 62.5183 | 62.5183 | 2024-10-12 22:19 | 2024-10-18 13:05 | 225836.1574 | 225836 | [7 empty] | 0 | 0 | 23.06 | 10.64 | 5416.14
TS5500Shv | RS\42\004\X | RS | 42 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2024-10-12 22:19 | 2024-10-13 13:53 | 18980.2791 | [6 empty] | 18980 | 13442 | 1.34 | 0 | 0 | 11.37 | 5343
TS5500Exc | RS\41\005\A | RS | 41 | 5 | A | 8 Coal Mining | 62.2 | 0 | 62.2 | 2024-10-12 23:12 | 2024-10-13 22:03 | 28777.8675 | [6 empty] | 28778 | 20300 | 2.03 | 0 | 0 | 12.91 | 5281
TS6060#1 | GG\18\013\D | GG | 18 | 13 | D | 8 Coal Mining | 35 | 0 | 35 | 2024-10-12 23:12 | 2024-10-13 20:08 | 28316.8023 | [6 empty] | 28317 | 21086 | 1.66 | 0 | 0 | 7.12 | 5762
TS5500Shv | RS\46\004\A | RS | 46 | 4 | A | 8 Coal Mining | 25.1 | 0 | 25.1 | 2024-10-13 13:53 | 2024-10-13 23:27 | 11654.3157 | [6 empty] | 11654 | 8146 | 0.81 | 0 | 0 | 14.53 | 5153
TS6060#1 | RS\42\004\A | RS | 42 | 4 | A | 1 Prestrip - Thick | 23.943 | 23.943 | 23.943 | 2024-10-13 20:08 | 2024-10-15 16:06 | 45370.0961 | 45370 | [7 empty] | 0 | 0 | 4.53 | 12.59 | 5304.02
TS5500Exc | RS\41\004\B | RS | 41 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-10-13 22:03 | 2024-10-14 14:04 | 20164.4421 | [6 empty] | 20164 | 14508 | 1.45 | 0 | 0 | 9.05 | 5601
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 04:46 |  | 3d 04:46 | 2024-10-13 23:27 | 2024-10-17 04:12
TS5500Exc | RS\41\006\A | RS | 41 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-10-14 14:04 | 2024-10-16 02:31 | 45910.8894 | [6 empty] | 45911 | 31905 | 3.39 | 0 | 0 | 15.94 | 5050
TS6060#1 | RS\41\005\B | RS | 41 | 5 | B | 1 Prestrip - Thick | 37.2787 | 37.2787 | 37.2787 | 2024-10-15 16:06 | 2024-10-16 02:21 | 10569.3973 | 10569 | [7 empty] | 0 | 0 | 1.06 | 9.03 | 5610.86
TS6060#1 | GG\18\018\D | GG | 18 | 18 | D | 8 Coal Mining | 16.5 | 0 | 16.5 | 2024-10-16 02:21 | 2024-10-16 10:12 | 10626.6805 | [6 empty] | 10627 | 7907 | 0.79 | 0 | 0 | 7.22 | 5754
TS5500Exc | RS\40\006\D | RS | 40 | 6 | D | 7 PostStrip | 56.0478 | 0 | 56.0478 | 2024-10-16 02:31 | 2024-10-17 04:12 | 22722.8186 |  |  | 22723 | [5 empty] | 0 | 0 | 0 | 5.82 | 5909.54
TS Fleet 5 | RS\46\005\X | RS | 46 | 5 | X | 1 Prestrip - Thick | 54.2922 | 54.2922 | 54.2922 | 2024-10-16 06:23 | 2024-10-20 03:17 | 182059.6715 | 182060 | [7 empty] | 0 | 0 | 14.74 | 10.42 | 5438.39
TS6060#1 | RS\41\006\B | RS | 41 | 6 | B | 1 Prestrip - Thick | 29.7436 | 29.7436 | 29.7436 | 2024-10-16 10:12 | 2024-10-16 18:29 | 8547.7412 | 8548 | [7 empty] | 0 | 0 | 0.91 | 9 | 5617.26
TS6060#1 | GG\18\019\D | GG | 18 | 19 | D | 8 Coal Mining | 61.4 | 0 | 61.4 | 2024-10-16 18:29 | 2024-10-17 23:27 | 39200.5781 | [6 empty] | 39201 | 29191 | 2.92 | 0 | 0 | 7.06 | 5768
TS5500Exc | RS\40\006\D | RS | 40 | 6 | D | 8 Coal Mining | 100 | 0 | 67.2 | 2024-10-17 04:12 | 2024-10-18 06:56 | 33664.0406 | [6 empty] | 33664 | 24936 | 3.1 | 0 | 0 | 5.82 | 5910
TS5500Shv | RS\40\006\D | RS | 40 | 6 | D | 8 Coal Mining | 12.5 | 0 | 12.5 | 2024-10-17 04:12 | 2024-10-17 09:21 | 6270.1675 | [6 empty] | 6270 | 4644 | 0.58 | 0 | 0 | 5.82 | 5910
DRE2 | GG\18\021\D | GG | 18 | 21 | D | 6 DL | 100 | 100 | 100 | 2024-10-17 05:42 | 2024-10-22 23:43 | 414686.4704 |  |  |  | 7722 | 414686 | 185335 |  |  | 0 | 19.34 | 0 | 6.84 | 5787.11
DRE1 | RS\41\004\D | RS | 41 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-10-17 06:10 | 2024-10-21 02:29 | 313837.8469 |  |  |  | 16136 | 313838 | 252791 |  |  | 0 | 26.89 | 0 | 5.6 | 5928.48
TS5500Shv | GG\18\020\D | GG | 18 | 20 | D | 8 Coal Mining | 74.7 | 0 | 74.7 | 2024-10-17 09:21 | 2024-10-19 00:19 | 47528.8749 | [6 empty] | 47529 | 35392 | 3.54 | 0 | 0 | 6.92 | 5780
TS6060#1 | RS\40\006\D | RS | 40 | 6 | D | 8 Coal Mining | 100 | 0 | 20.2 | 2024-10-17 23:27 | 2024-10-18 06:56 | 10129.2577 | [6 empty] | 10129 | 7503 | 0.93 | 0 | 0 | 5.82 | 5910
TS6060#1 | GG\18\020\D | GG | 18 | 20 | D | 8 Coal Mining | 25.3 | 0 | 25.3 | 2024-10-18 06:56 | 2024-10-18 18:49 | 16079.4093 | [6 empty] | 16079 | 11974 | 1.2 | 0 | 0 | 6.92 | 5780
TS5500Exc | RS\42\003\X | RS | 42 | 3 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-10-18 06:56 | 2024-10-18 13:11 | 7875.6377 | [6 empty] | 7876 | 5552 | 0.52 | 0 | 0 | 11.87 | 5287
PH4100A | RS\41\005\B | RS | 41 | 5 | B | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2024-10-18 13:05 | 2024-10-18 23:20 | 17782.975 | 17783 | [7 empty] | 0 | 0 | 1.78 | 9.03 | 5610.86
TS5500Exc | RS\42\003\A | RS | 42 | 3 | A | 1 Prestrip - Thick | 100 | 29.3965 | 29.3965 | 2024-10-18 13:11 | 2024-10-21 08:57 | 59931.0291 | 59931 | [7 empty] | 0 | 0 | 5.52 | 12.09 | 5344.32
TS6060#1 | RS\42\003\A | RS | 42 | 3 | A | 1 Prestrip - Thick | 100 | 31.4474 | 31.4474 | 2024-10-18 18:49 | 2024-10-21 08:57 | 64112.2946 | 64112 | [7 empty] | 0 | 0 | 5.91 | 12.09 | 5344.32
PH4100A | RS\41\006\B | RS | 41 | 6 | B | 1 Prestrip - Thick | 100 | 70.2564 | 70.2564 | 2024-10-18 23:20 | 2024-10-19 10:58 | 20190.3506 | 20190 | [7 empty] | 0 | 0 | 2.15 | 9 | 5617.26
TS5500Shv | RS\41\005\B | RS | 41 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-10-19 00:19 | 2024-10-19 16:57 | 20278.7818 | [6 empty] | 20279 | 14583 | 1.46 | 0 | 0 | 9.03 | 5611
PH4100A | RS\42\003\A | RS | 42 | 3 | A | 1 Prestrip - Thick | 100 | 39.1561 | 39.1561 | 2024-10-19 10:58 | 2024-10-21 08:57 | 79828.1687 | 79828 | [7 empty] | 0 | 0 | 7.36 | 12.09 | 5344.32
TS5500Shv | RS\41\006\B | RS | 41 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-10-19 16:57 | 2024-10-20 08:17 | 18694.9306 | [6 empty] | 18695 | 13433 | 1.44 | 0 | 0 | 9 | 5617
TS Fleet 5 | W1\02\004\D | W1 | 2 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-10-20 03:17 | 2024-11-01 04:40 | 567208.1492 | 567208 | [7 empty] | 0 | 0 | 33.29 | 7.54 | 5612.59
TS5500Shv | RS\42\005\X | RS | 42 | 5 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-10-20 08:17 | 2024-10-20 16:26 | 9925.8606 | [6 empty] | 9926 | 7080 | 0.71 | 0 | 0 | 10.64 | 5416
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 10:03 |  | 0d 10:03 | 2024-10-20 16:26 | 2024-10-21 02:29
DRE1 | SC\39\014\D | SC | 39 | 14 | D | 6 DL | 100 | 0 | 100 | 2024-10-21 02:29 | 2024-10-27 21:37 | 554694.2301 |  |  |  | 39449 | 554694 | 398871 |  |  | 0 | 35.77 | 0 | 7.63 | 5739.85
TS5500Shv | RS\41\004\D | RS | 41 | 4 | D | 8 Coal Mining | 15.8 | 0 | 15.8 | 2024-10-21 02:29 | 2024-10-21 10:21 | 9597.1491 | [6 empty] | 9597 | 7114 | 0.71 | 0 | 0 | 5.6 | 5928
PH4100A | RS\42\004\A | RS | 42 | 4 | A | 1 Prestrip - Thick | 100 | 76.057 | 76.057 | 2024-10-21 08:57 | 2024-10-24 19:58 | 144121.791 | 144122 | [7 empty] | 0 | 0 | 14.39 | 12.59 | 5304.02
TS6060#1 | RS\41\004\D | RS | 41 | 4 | D | 8 Coal Mining | 100 | 0 | 43.6 | 2024-10-21 08:57 | 2024-10-22 04:35 | 26569.5278 | [6 empty] | 26570 | 19695 | 1.97 | 0 | 0 | 5.6 | 5928
TS5500Exc | RS\41\004\D | RS | 41 | 4 | D | 8 Coal Mining | 100 | 0 | 40.6 | 2024-10-21 08:57 | 2024-10-22 04:35 | 24728.0753 | [6 empty] | 24728 | 18330 | 1.83 | 0 | 0 | 5.6 | 5928
TS5500Shv | RS\42\003\A | RS | 42 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-10-21 10:21 | 2024-10-23 05:42 | 52871.2871 | [6 empty] | 52871 | 37538 | 3.28 | 0 | 0 | 12.09 | 5344
TS6060#1 | RS\45\004\A | RS | 45 | 4 | A | 1 Prestrip - Thick | 55.4736 | 55.4736 | 55.4736 | 2024-10-22 04:35 | 2024-11-01 12:27 | 249178.5875 | 249179 | [7 empty] | 0 | 0 | 25.32 | 14.19 | 5179.24
TS5500Exc | RS\41\005\B | RS | 41 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-10-22 04:35 | 2024-10-22 21:13 | 20947.3131 | [6 empty] | 20947 | 15064 | 1.51 | 0 | 0 | 9.03 | 5611
TS5500Exc | RS\41\006\B | RS | 41 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-10-22 21:13 | 2024-10-23 12:32 | 19311.247 | [6 empty] | 19311 | 13876 | 1.48 | 0 | 0 | 9 | 5617
DRE2 | GG\18\022\D | GG | 18 | 22 | D | 6 DL | 100 | 100 | 100 | 2024-10-22 23:43 | 2024-10-28 15:30 | 408049.0856 |  |  |  | 7599 | 408049 | 182368 |  |  | 0 | 19.03 | 0 | 6.7 | 5798.05
TS5500Shv | GG\18\021\D | GG | 18 | 21 | D | 8 Coal Mining | 7.8 | 0 | 7.8 | 2024-10-23 05:42 | 2024-10-23 09:47 | 4970.9045 | [6 empty] | 4971 | 3699 | 0.37 | 0 | 0 | 6.84 | 5787
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 10:11 |  | 1d 10:11 | 2024-10-23 09:47 | 2024-10-24 19:58
TS5500Exc | RS\42\003\B | RS | 42 | 3 | B | 1 Prestrip - Thick | 100 | 89.0543 | 89.0543 | 2024-10-23 12:32 | 2024-10-24 22:04 | 29650.0768 | 29650 | [7 empty] | 0 | 0 | 2.55 | 9.19 | 5575.17
PH4100A | RS\42\003\B | RS | 42 | 3 | B | 1 Prestrip - Thick | 100 | 10.9457 | 10.9457 | 2024-10-24 19:58 | 2024-10-24 22:04 | 3644.2972 | 3644 | [7 empty] | 0 | 0 | 0.31 | 9.19 | 5575.17
TS5500Shv | RS\42\004\A | RS | 42 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-10-24 19:58 | 2024-10-25 14:21 | 22421.3494 | [6 empty] | 22421 | 15845 | 1.58 | 0 | 0 | 12.59 | 5304
PH4100A | RS\42\006\X | RS | 42 | 6 | X | 1 Prestrip - Thick | 100 | 62.5439 | 62.5439 | 2024-10-24 22:04 | 2024-10-31 00:50 | 247013.9674 | 247014 | [7 empty] | 0 | 0 | 27.88 | 9.68 | 5510.24
TS5500Exc | RS\41\003\D | RS | 41 | 3 | D | 8 Coal Mining | 65.4 | 0 | 65.4 | 2024-10-24 22:04 | 2024-10-26 17:44 | 55006.226 | [6 empty] | 55006 | 40974 | 2.95 | 0 | 0 | 5.38 | 5949
PH4100XPC#1 | GG\22\005\X1 | GG | 22 | 5 | X1 | 1 Prestrip - Thick | 100 | 54.7964 | 54.7964 | 2024-10-25 05:49 | 2024-11-03 03:16 | 486030.3783 | 486030 | [7 empty] | 0 | 0 | 46.61 | 10.64 | 5304.22
TS5500Shv | RS\42\003\B | RS | 42 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-10-25 14:21 | 2024-10-26 08:59 | 22713.818 | [6 empty] | 22714 | 16352 | 1.39 | 0 | 0 | 9.19 | 5575
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 03:09 |  | 1d 03:09 | 2024-10-26 08:59 | 2024-10-27 12:07
TS5500Exc | RS\42\004\A | RS | 42 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-10-26 17:44 | 2024-10-27 12:07 | 23160.5148 | [6 empty] | 23161 | 16368 | 1.63 | 0 | 0 | 12.59 | 5304
TS5500Exc | RS\42\003\B | RS | 42 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-10-27 12:07 | 2024-10-28 06:45 | 23462.6251 | [6 empty] | 23463 | 16891 | 1.43 | 0 | 0 | 9.19 | 5575
TS5500Shv | RS\47\004\A | RS | 47 | 4 | A | 1 Prestrip - Thick | 4.4213 | 4.4213 | 4.4213 | 2024-10-27 12:07 | 2024-10-28 05:18 | 17763.991 | 17764 | [7 empty] | 0 | 0 | 1.82 | 14.79 | 5132.7
DRE1 | RS\41\005\D | RS | 41 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-10-27 21:37 | 2024-10-31 14:14 | 301282.7878 |  |  |  | 15490 | 301283 | 242679 |  |  | 0 | 25.82 | 0 | 5.78 | 5913.53
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 10:12 |  | 0d 10:12 | 2024-10-28 05:18 | 2024-10-28 15:30
TS5500Exc | RS\42\005\X | RS | 42 | 5 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-10-28 06:45 | 2024-10-28 14:53 | 10253.0868 | [6 empty] | 10253 | 7313 | 0.73 | 0 | 0 | 10.64 | 5416
TS5500Exc | MW\51\006\D | MW | 51 | 6 | D | 1 Prestrip - Thick | 100 | 43.6747 | 43.6747 | 2024-10-28 14:53 | 2024-11-02 10:01 | 101827.6156 | 101828 | [7 empty] | 0 | 0 | 10.35 | 7.29 | 5773.43
DRE2 | GG\18\023\D | GG | 18 | 23 | D | 6 DL | 100 | 100 | 100 | 2024-10-28 15:30 | 2024-11-04 01:18 | 462161.4182 |  |  |  | 7890 | 462161 | 133516 |  |  | 0 | 17.66 | 0 | 6.46 | 5820.26
TS5500Shv | GG\18\022\D | GG | 18 | 22 | D | 8 Coal Mining | 25.6 | 0 | 25.6 | 2024-10-28 15:30 | 2024-10-29 04:39 | 16038.5535 | [6 empty] | 16039 | 11962 | 1.2 | 0 | 0 | 6.7 | 5798
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 20:10 |  | 1d 20:10 | 2024-10-29 04:39 | 2024-10-31 00:50
PH4100A | RS\42\004\B | RS | 42 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-10-31 00:50 | 2024-10-31 16:46 | 27679.6464 | 27680 | [7 empty] | 0 | 0 | 2.77 | 9.07 | 5601.16
TS5500Shv | RS\42\006\X | RS | 42 | 6 | X | 8 Coal Mining | 100 | 0 | 100 | 2024-10-31 00:50 | 2024-10-31 13:13 | 15098.7938 | [6 empty] | 15099 | 10866 | 1.24 | 0 | 0 | 9.68 | 5510
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 01:02 |  | 0d 01:02 | 2024-10-31 13:13 | 2024-10-31 14:14
DRE1 | RS\41\006\D | RS | 41 | 6 | D | 6 DL | 100 | 100 | 100 | 2024-10-31 14:14 | 2024-11-04 01:03 | 281573.5789 |  |  |  | 10519 | 281574 | 159789 |  |  | 0 | 26.25 | 0 | 5.85 | 5907.23
TS5500Shv | RS\41\005\D | RS | 41 | 5 | D | 8 Coal Mining | 34.9 | 0 | 34.9 | 2024-10-31 14:14 | 2024-11-01 08:29 | 22252.3502 | [6 empty] | 22252 | 16471 | 1.65 | 0 | 0 | 5.78 | 5914
PH4100A | RS\42\005\A | RS | 42 | 5 | A | 1 Prestrip - Thick | 100 | 85.4109 | 85.4109 | 2024-10-31 16:46 | 2024-11-04 14:08 | 162087.8336 | 162088 | [7 empty] | 0 | 0 | 16.2 | 12.81 | 5288.85
TS Fleet 5 | RS\47\003\A | RS | 47 | 3 | A | 1 Prestrip - Thick | 65.1815 | 65.1815 | 65.1815 | 2024-11-01 04:40 | 2024-11-05 21:04 | 220309.7527 | 220310 | [7 empty] | 0 | 0 | 22.78 | 12.4 | 5337.32
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 18:46 |  | 1d 18:46 | 2024-11-01 08:29 | 2024-11-03 03:16
TS6060#1 | RS\41\005\D | RS | 41 | 5 | D | 8 Coal Mining | 100 | 0 | 55.8 | 2024-11-01 12:27 | 2024-11-02 14:44 | 35581.035 | [6 empty] | 35581 | 26337 | 2.63 | 0 | 0 | 5.78 | 5914
TS5500Exc | RS\41\005\D | RS | 41 | 5 | D | 8 Coal Mining | 100 | 0 | 9.3 | 2024-11-02 10:01 | 2024-11-02 14:44 | 5952.7824 | [6 empty] | 5953 | 4406 | 0.44 | 0 | 0 | 5.78 | 5914
TS6060#1 | GG\22\004\X1 | GG | 22 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2024-11-02 14:44 | 2024-11-03 05:16 | 19663.197 | [6 empty] | 19663 | 14605 | 1.04 | 0 | 0 | 10.77 | 5293
TS5500Exc | RS\42\004\B | RS | 42 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-11-02 14:44 | 2024-11-03 22:21 | 39818.2336 | [6 empty] | 39818 | 28628 | 2.86 | 0 | 0 | 9.07 | 5601
PH4100XPC#1 | GG\22\006\X1 | GG | 22 | 6 | X1 | 1 Prestrip - Thick | 100 | 54.2924 | 54.2924 | 2024-11-03 03:16 | 2024-11-11 18:31 | 462447.7646 | 462448 | [7 empty] | 0 | 0 | 45.34 | 11.21 | 5294.51
TS5500Shv | GG\22\005\X1 | GG | 22 | 5 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-11-03 03:16 | 2024-11-03 09:18 | 7366.2819 | [6 empty] | 7366 | 5480 | 0.55 | 0 | 0 | 10.64 | 5304
TS6060#1 | GG\22\005\X1 | GG | 22 | 5 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-11-03 05:16 | 2024-11-03 11:18 | 8175.7635 | [6 empty] | 8176 | 6082 | 0.61 | 0 | 0 | 10.64 | 5304
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 02:00 |  | 0d 02:00 | 2024-11-03 09:18 | 2024-11-03 11:18
TS6060#1 | RS\42\005\A | RS | 42 | 5 | A | 1 Prestrip - Thick | 37.2787 | 14.5891 | 14.5891 | 2024-11-03 11:18 | 2024-11-04 14:08 | 27686.4496 | 27686 | [7 empty] | 0 | 0 | 2.77 | 12.81 | 5288.85
TS5500Shv | GG\22\005\X2 | GG | 22 | 5 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2024-11-03 11:18 | 2024-11-07 04:03 | 95124.433 | 95124 | [7 empty] | 0 | 0 | 9.51 | 0 | 0
TS5500Exc | MW\51\007\A | MW | 51 | 7 | A | 1 Prestrip - Thick | 52.9579 | 15.1324 | 15.1324 | 2024-11-03 22:21 | 2024-11-06 14:45 | 56973.6377 | 56974 | [7 empty] | 0 | 0 | 3.59 | 12.02 | 5372.59
DRE1 | MW\51\006\D | MW | 51 | 6 | D | 6 DL | 100 | 0 | 100 | 2024-11-04 01:03 | 2024-11-09 10:53 | 441422.686 |  |  |  | 31393 | 441423 | 317420 |  |  | 0 | 35 | 0 | 7.29 | 5773.43
DRE2 | GG\20\012\B | GG | 20 | 12 | B | 6 DL | 100 | 0 | 100 | 2024-11-04 01:18 | 2024-11-06 17:59 | 194351.6398 |  |  |  |  | 194352 | 161960 |  |  | 0 | 16.27 | 0 | 10.44 | 5477.43
TS6060#1 | RS\42\006\A | RS | 42 | 6 | A | 1 Prestrip - Thick | 37.2787 | 37.2787 | 37.2787 | 2024-11-04 14:08 | 2024-11-06 18:44 | 54272.5435 | 54273 | [7 empty] | 0 | 0 | 6.78 | 15.8 | 5061.43
PH4100A | RS\42\006\A | RS | 42 | 6 | A | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2024-11-04 14:08 | 2024-11-06 18:44 | 91313.3704 | 91313 | [7 empty] | 0 | 0 | 11.41 | 15.8 | 5061.43
TS Fleet 5 | GG\22\004\B | GG | 22 | 4 | B | 1 Prestrip - Thick | 45.3511 | 45.3511 | 45.3511 | 2024-11-05 21:04 | 2024-11-07 06:17 | 65102.1858 | 65102 | [7 empty] | 0 | 0 | 4.88 | 9.34 | 5521.53
TS5500Exc | RS\42\005\A | RS | 42 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-11-06 14:45 | 2024-11-07 09:20 | 23411.5426 | [6 empty] | 23412 | 16513 | 1.65 | 0 | 0 | 12.81 | 5289
DRE2 | GG\20\011\B | GG | 20 | 11 | B | 6 DL | 100 | 0 | 100 | 2024-11-06 17:59 | 2024-11-09 18:57 | 219297.7503 |  |  |  |  | 219298 | 168691 |  |  | 0 | 16.94 | 0 | 9.77 | 5538.76
PH4100A | RS\43\002\A | RS | 43 | 2 | A | 1 Prestrip - Thick | 100 | 62.6777 | 62.6777 | 2024-11-06 18:44 | 2024-11-07 10:25 | 27003.5489 | 27004 | [7 empty] | 0 | 0 | 22.02 | 11.96 | 5359.21
TS6060#1 | GG\18\021\D | GG | 18 | 21 | D | 8 Coal Mining | 92.2 | 0 | 92.2 | 2024-11-06 18:44 | 2024-11-08 14:12 | 58816.389 | [6 empty] | 58816 | 43763 | 4.38 | 0 | 0 | 6.84 | 5787
TS5500Shv | RS\41\006\D | RS | 41 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2024-11-07 04:03 | 2024-11-08 17:26 | 40078.2792 |  |  | 40078 | [5 empty] | 0 | 0 | 0 | 5.85 | 5907.23
TS Fleet 5 | GG\22\005\B | GG | 22 | 5 | B | 1 Prestrip - Thick | 45.3511 | 45.3511 | 45.3511 | 2024-11-07 06:17 | 2024-11-07 15:36 | 18251.6194 | 18252 | [7 empty] | 0 | 0 | 1.83 | 9.27 | 5514.49
TS5500Exc | MW\51\007\A | MW | 51 | 7 | A | 8 Coal Mining | 80 | 0 | 80 | 2024-11-07 09:20 | 2024-11-08 17:23 | 40365.0554 | [6 empty] | 40365 | 29431 | 1.91 | 0 | 0 | 12.02 | 5373
PH4100A | RS\43\003\X | RS | 43 | 3 | X | 1 Prestrip - Thick | 100 | 62.7119 | 62.7119 | 2024-11-07 10:25 | 2024-11-11 04:18 | 149013.2327 | 149013 | [7 empty] | 0 | 0 | 15.38 | 11.81 | 5293.65
TS Fleet 5 | RS\47\004\A | RS | 47 | 4 | A | 1 Prestrip - Thick | 59.917 | 59.917 | 59.917 | 2024-11-07 15:36 | 2024-11-12 18:25 | 240734.2524 | 240734 | [7 empty] | 0 | 0 | 24.66 | 14.79 | 5132.7
TS6060#1 | GG\18\022\D | GG | 18 | 22 | D | 8 Coal Mining | 74.4 | 0 | 74.4 | 2024-11-08 14:12 | 2024-11-10 00:38 | 46606.7774 | [6 empty] | 46607 | 34760 | 3.48 | 0 | 0 | 6.7 | 5798
TS5500Exc | RS\43\002\A | RS | 43 | 2 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-11-08 17:23 | 2024-11-08 21:23 | 5042.6145 | [6 empty] | 5043 | 3589 | 1.7 | 0 | 0 | 11.96 | 5359
TS5500Shv | RS\41\006\D | RS | 41 | 6 | D | 8 Coal Mining | 66.7 | 0 | 66.7 | 2024-11-08 17:26 | 2024-11-09 20:27 | 32952.1246 | [6 empty] | 32952 | 24408 | 3.07 | 0 | 0 | 5.85 | 5907
TS5500Exc | RS\41\006\D | RS | 41 | 6 | D | 8 Coal Mining | 33.3 | 0 | 33.3 | 2024-11-08 21:23 | 2024-11-09 10:28 | 16482.2179 | [6 empty] | 16482 | 12209 | 1.54 | 0 | 0 | 5.85 | 5907
TS5500Exc | MW\54\007\A | MW | 54 | 7 | A | 8 Coal Mining | 94.6 | 0 | 94.6 | 2024-11-09 10:28 | 2024-11-09 20:31 | 12652.7829 | [6 empty] | 12653 | 9131 | 0.97 | 0 | 0 | 13.91 | 5227
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 5d 00:00 |  | 5d 00:00 | 2024-11-09 10:53 | 2024-11-14 10:53
DRE2 | GG\20\010\B | GG | 20 | 10 | B | 6 DL | 100 | 0 | 100 | 2024-11-09 18:57 | 2024-11-12 23:58 | 231426.7612 |  |  |  |  | 231427 | 192856 |  |  | 0 | 18.7 | 0 | 9.84 | 5536.87
TS5500Shv | RS\42\005\A | RS | 42 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-11-09 20:27 | 2024-11-10 15:02 | 22664.3658 | [6 empty] | 22664 | 15986 | 1.6 | 0 | 0 | 12.81 | 5289
TS5500Exc | MW\54\007\B | MW | 54 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-11-09 20:31 | 2024-11-10 20:08 | 20890.0813 | 20890 | [7 empty] | 0 | 0 | 2.26 | 9.32 | 5569.27
TS6060#1 | GG\18\023\D | GG | 18 | 23 | D | 7 PostStrip | 24.5894 | 0 | 24.5894 | 2024-11-10 00:38 | 2024-11-10 13:57 | 13732.9526 |  |  | 13733 | [5 empty] | 0 | 0 | 0 | 6.46 | 5820.26
TS6060#1 | GG\20\012\B | GG | 20 | 12 | B | 8 Coal Mining | 53.4 | 0 | 53.4 | 2024-11-10 13:57 | 2024-11-11 09:11 | 26041.651 | [6 empty] | 26042 | 19066 | 1.91 | 0 | 0 | 10.44 | 5477
TS5500Shv | RS\42\006\A | RS | 42 | 6 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-11-10 15:02 | 2024-11-11 22:25 | 38266.539 | [6 empty] | 38267 | 26602 | 3.37 | 0 | 0 | 15.8 | 5061
TS5500Exc | MW\54\005\D | MW | 54 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-11-10 20:08 | 2024-11-12 20:06 | 60410.4502 | [6 empty] | 60410 | 44705 | 4.47 | 0 | 0 | 9.28 | 5597
PH4100A | RS\42\005\B | RS | 42 | 5 | B | 1 Prestrip - Thick | 100 | 74.4686 | 74.4686 | 2024-11-11 04:18 | 2024-11-11 15:51 | 20075.1984 | 20075 | [7 empty] | 0 | 0 | 2.01 | 9.03 | 5612.97
TS6060#1 | RS\42\005\B | RS | 42 | 5 | B | 1 Prestrip - Thick | 37.2787 | 25.5314 | 25.5314 | 2024-11-11 09:11 | 2024-11-11 15:51 | 6882.742 | 6883 | [7 empty] | 0 | 0 | 0.69 | 9.03 | 5612.97
PH4100A | RS\43\004\X | RS | 43 | 4 | X | 1 Prestrip - Thick | 100 | 68.0114 | 68.0114 | 2024-11-11 15:51 | 2024-11-16 17:22 | 200256.6469 | 200257 | [7 empty] | 0 | 0 | 20.61 | 11.31 | 5348.87
TS6060#1 | GG\20\011\B | GG | 20 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-11-11 15:51 | 2024-11-13 04:11 | 49166.4344 | [6 empty] | 49166 | 36112 | 3.62 | 0 | 0 | 9.77 | 5539
PH4100XPC#1 | GG\22\004\B | GG | 22 | 4 | B | 1 Prestrip - Thick | 100 | 54.6489 | 54.6489 | 2024-11-11 18:31 | 2024-11-13 05:11 | 78449.1585 | 78449 | [7 empty] | 0 | 0 | 5.88 | 9.34 | 5521.53
TS5500Shv | GG\22\006\X1 | GG | 22 | 6 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-11-11 22:25 | 2024-11-12 04:32 | 7451.8864 | [6 empty] | 7452 | 5508 | 0.55 | 0 | 0 | 11.21 | 5295
TS5500Shv | RS\42\005\B | RS | 42 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-11-12 04:32 | 2024-11-13 14:24 | 41301.1543 | [6 empty] | 41301 | 29681 | 2.97 | 0 | 0 | 9.03 | 5613
TS Fleet 5 | RS\47\005\A | RS | 47 | 5 | A | 1 Prestrip - Thick | 59.6835 | 59.6835 | 59.6835 | 2024-11-12 18:25 | 2024-11-18 18:00 | 281407.749 | 281408 | [7 empty] | 0 | 0 | 26.89 | 16.2 | 5019.99
TS5500Exc | RS\43\003\X | RS | 43 | 3 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-11-12 20:06 | 2024-11-13 02:06 | 7556.6345 | [6 empty] | 7557 | 5331 | 0.53 | 0 | 0 | 11.81 | 5294
DRE2 | GG\20\009\B | GG | 20 | 9 | B | 6 DL | 100 | 0 | 100 | 2024-11-12 23:58 | 2024-11-16 05:55 | 234198.8543 |  |  |  |  | 234199 | 195166 |  |  | 0 | 19.52 | 0 | 9.92 | 5527.05
TS5500Exc | MW\54\007\B | MW | 54 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-11-13 02:06 | 2024-11-14 05:51 | 34961.7404 | [6 empty] | 34962 | 25845 | 2.79 | 0 | 0 | 9.32 | 5569
TS6060#1 | GG\22\006\X1 | GG | 22 | 6 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-11-13 04:11 | 2024-11-13 10:18 | 8270.775 | [6 empty] | 8271 | 6114 | 0.61 | 0 | 0 | 11.21 | 5295
PH4100XPC#1 | GG\22\005\B | GG | 22 | 5 | B | 1 Prestrip - Thick | 100 | 54.6489 | 54.6489 | 2024-11-13 05:11 | 2024-11-13 14:54 | 21993.4886 | 21993 | [7 empty] | 0 | 0 | 2.21 | 9.27 | 5514.49
TS6060#1 | RS\42\006\B | RS | 42 | 6 | B | 1 Prestrip - Thick | 37.2787 | 37.2787 | 37.2787 | 2024-11-13 10:18 | 2024-11-13 18:35 | 8553.6142 | 8554 | [7 empty] | 0 | 0 | 1.09 | 8.96 | 5624.81
TS5500Shv | RS\43\002\A | RS | 43 | 2 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-11-13 14:24 | 2024-11-13 18:24 | 4881.68 | [6 empty] | 4882 | 3474 | 1.64 | 0 | 0 | 11.96 | 5359
PH4100XPC#1 | GG\22\006\B | GG | 22 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-11-13 14:54 | 2024-11-16 09:04 | 149797.2558 | 149797 | [7 empty] | 0 | 0 | 15 | 10.05 | 5464.78
TS5500Shv | RS\43\003\X | RS | 43 | 3 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-11-13 18:24 | 2024-11-14 00:24 | 7315.4653 | [6 empty] | 7315 | 5161 | 0.52 | 0 | 0 | 11.81 | 5294
TS6060#1 | RS\43\002\B | RS | 43 | 2 | B | 1 Prestrip - Thick | 37.2787 | 37.2787 | 37.2787 | 2024-11-13 18:35 | 2024-11-13 20:56 | 2423.3417 | 2423 | [7 empty] | 0 | 0 | 1.06 | 9.28 | 5561.6
TS6060#1 | GG\20\010\B | GG | 20 | 10 | B | 8 Coal Mining | 49 | 0 | 49 | 2024-11-13 20:56 | 2024-11-14 15:00 | 24460.2308 | [6 empty] | 24460 | 17958 | 1.8 | 0 | 0 | 9.84 | 5537
TS5500Shv | MW\51\006\D | MW | 51 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-11-14 00:24 | 2024-11-16 04:38 | 63699.1725 | [6 empty] | 63699 | 47787 | 4.78 | 0 | 0 | 7.29 | 5773
TS5500Exc | MW\55\007\B | MW | 55 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-11-14 05:51 | 2024-11-20 03:35 | 125533.8423 | 125534 | [7 empty] | 0 | 0 | 17.9 | 9.48 | 5555.34
DRE1 | MW\54\007\D | MW | 54 | 7 | D | 6 DL | 100 | 100 | 100 | 2024-11-14 10:53 | 2024-11-17 06:53 | 231186.7233 |  |  |  | 11886 | 231187 | 186217 |  |  | 0 | 29.58 | 0 | 6.67 | 5827.93
TS6060#1 | RS\43\003\A | RS | 43 | 3 | A | 1 Prestrip - Thick | 37.2787 | 37.2787 | 37.2787 | 2024-11-14 15:00 | 2024-11-17 11:16 | 70423.3384 | 70423 | [7 empty] | 0 | 0 | 7.04 | 12.11 | 5345.53
TS5500Shv | MW\51\007\A | MW | 51 | 7 | A | 8 Coal Mining | 20 | 0 | 20 | 2024-11-16 04:38 | 2024-11-16 12:56 | 10101.0285 | [6 empty] | 10101 | 7365 | 0.48 | 0 | 0 | 12.02 | 5373
DRE2 | GG\20\008\B | GG | 20 | 8 | B | 6 DL | 100 | 0 | 100 | 2024-11-16 05:55 | 2024-11-19 20:32 | 260302.2653 |  |  |  |  | 260302 | 200233 |  |  | 0 | 20.02 | 0 | 10.14 | 5494.75
PH4100XPC#1 | GG\22\007\X1 | GG | 22 | 7 | X1 | 1 Prestrip - Thick | 100 | 54.2273 | 54.2273 | 2024-11-16 09:04 | 2024-11-24 11:43 | 433149.4567 | 433149 | [7 empty] | 0 | 0 | 42.18 | 12.03 | 5270.33
TS5500Shv | GG\18\023\D | GG | 18 | 23 | D | 7 PostStrip | 75.4106 | 0 | 75.4106 | 2024-11-16 12:56 | 2024-11-18 04:13 | 42116.028 |  |  | 42116 | [5 empty] | 0 | 0 | 0 | 6.46 | 5820.26
PH4100A | MW\51\007\B | MW | 51 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-11-16 17:22 | 2024-11-17 14:21 | 36411.0997 | 36411 | [7 empty] | 0 | 0 | 2.37 | 9.54 | 5552.52
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2024-11-17 06:53 | 2024-11-19 06:53
TS6060#1 | GG\20\009\B | GG | 20 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-11-17 11:16 | 2024-11-19 01:15 | 51406.5871 | [6 empty] | 51407 | 37703 | 3.77 | 0 | 0 | 9.92 | 5527
PH4100A | RS\42\006\B | RS | 42 | 6 | B | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2024-11-17 14:21 | 2024-11-17 22:38 | 14391.4269 | 14391 | [7 empty] | 0 | 0 | 1.83 | 8.96 | 5624.81
PH4100A | RS\43\002\B | RS | 43 | 2 | B | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2024-11-17 22:38 | 2024-11-18 00:59 | 4077.2641 | 4077 | [7 empty] | 0 | 0 | 1.78 | 9.28 | 5561.6
PH4100A | RS\43\003\A | RS | 43 | 3 | A | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2024-11-18 00:59 | 2024-11-20 21:14 | 118487.028 | 118487 | [7 empty] | 0 | 0 | 11.84 | 12.11 | 5345.53
TS5500Shv | RS\42\006\B | RS | 42 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-11-18 04:13 | 2024-11-19 06:22 | 31894.6364 | [6 empty] | 31895 | 22918 | 2.91 | 0 | 0 | 8.96 | 5625
TS Fleet 5 | RS\48\002\A | RS | 48 | 2 | A | 1 Prestrip - Thick | 77.183 | 77.183 | 77.183 | 2024-11-18 18:00 | 2024-11-20 21:23 | 100708.4973 | 100708 | [7 empty] | 0 | 0 | 21.59 | 11.74 | 5399.18
TS6060#1 | GG\18\023\D | GG | 18 | 23 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-11-19 01:15 | 2024-11-20 04:46 | 37250.0178 | [6 empty] | 37250 | 27937 | 2.51 | 0 | 0 | 6.46 | 5820
TS5500Shv | RS\43\002\B | RS | 43 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-11-19 06:22 | 2024-11-19 14:21 | 9722.935 | [6 empty] | 9723 | 7000 | 2.86 | 0 | 0 | 9.28 | 5562
DRE1 | RS\42\003\D | RS | 42 | 3 | D | 6 DL | 100 | 100 | 100 | 2024-11-19 06:53 | 2024-11-25 00:38 | 468348.13 |  |  |  | 24080 | 468348 | 377247 |  |  | 0 | 27.72 | 0 | 5.42 | 5945.47
TS5500Shv | RS\43\004\X | RS | 43 | 4 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-11-19 14:21 | 2024-11-19 22:01 | 9366.2849 | [6 empty] | 9366 | 6638 | 0.67 | 0 | 0 | 11.31 | 5349
DRE2 | GG\20\007\B | GG | 20 | 7 | B | 6 DL | 100 | 0 | 100 | 2024-11-19 20:32 | 2024-11-23 04:09 | 239230.3976 |  |  |  |  | 239230 | 199359 |  |  | 0 | 19.95 | 0 | 10.32 | 5457.86
TS5500Shv | MW\51\007\B | MW | 51 | 7 | B | 8 Coal Mining | 31.6 | 0 | 31.6 | 2024-11-19 22:01 | 2024-11-20 11:23 | 16293.6604 | [6 empty] | 16294 | 12025 | 0.78 | 0 | 0 | 9.54 | 5553
TS5500Exc | RS\43\004\X | RS | 43 | 4 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-11-20 03:35 | 2024-11-20 11:16 | 9675.0636 | [6 empty] | 9675 | 6857 | 0.69 | 0 | 0 | 11.31 | 5349
TS6060#1 | GG\20\008\B | GG | 20 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-11-20 04:46 | 2024-11-21 19:25 | 52306.4909 | [6 empty] | 52306 | 38287 | 3.83 | 0 | 0 | 10.14 | 5495
TS5500Exc | MW\51\007\B | MW | 51 | 7 | B | 8 Coal Mining | 68.4 | 0 | 68.4 | 2024-11-20 11:16 | 2024-11-21 15:17 | 35280.9761 | [6 empty] | 35281 | 26037 | 1.7 | 0 | 0 | 9.54 | 5553
TS5500Shv | GG\18\023\D | GG | 18 | 23 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-11-20 11:23 | 2024-11-21 14:54 | 33561.8973 | [6 empty] | 33562 | 25171 | 2.26 | 0 | 0 | 6.46 | 5820
PH4100A | RS\43\004\A | RS | 43 | 4 | A | 1 Prestrip - Thick | 100 | 70.2233 | 70.2233 | 2024-11-20 21:14 | 2024-11-24 02:38 | 134372.9975 | 134373 | [7 empty] | 0 | 0 | 13.41 | 13.22 | 5255.44
TS Fleet 5 | W1\02\005\D | W1 | 2 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-11-20 21:23 | 2024-12-02 10:39 | 543444.3395 | 543444 | [7 empty] | 0 | 0 | 30.44 | 7.57 | 5605.01
TS5500Shv | RS\43\003\A | RS | 43 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-11-21 14:54 | 2024-11-22 09:32 | 22703.9127 | [6 empty] | 22704 | 16112 | 1.61 | 0 | 0 | 12.11 | 5346
TS5500Exc | RS\43\003\A | RS | 43 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-11-21 15:17 | 2024-11-22 09:54 | 23452.3933 | [6 empty] | 23452 | 16643 | 1.66 | 0 | 0 | 12.11 | 5346
TS6060#1 | RS\43\004\A | RS | 43 | 4 | A | 1 Prestrip - Thick | 37.2787 | 29.7767 | 29.7767 | 2024-11-21 19:25 | 2024-11-24 02:38 | 56978.0845 | 56978 | [7 empty] | 0 | 0 | 5.69 | 13.22 | 5255.44
TS5500Shv | GG\20\012\B | GG | 20 | 12 | B | 8 Coal Mining | 46.6 | 0 | 46.6 | 2024-11-22 09:32 | 2024-11-23 04:11 | 22743.3934 | [6 empty] | 22743 | 16651 | 1.67 | 0 | 0 | 10.44 | 5477
TS5500Exc | RS\43\003\B | RS | 43 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-11-22 09:54 | 2024-11-23 17:10 | 27652.8634 | 27653 | [7 empty] | 0 | 0 | 2.76 | 9.17 | 5580.61
DRE2 | GG\20\006\B | GG | 20 | 6 | B | 6 DL | 100 | 0 | 100 | 2024-11-23 04:09 | 2024-11-26 19:17 | 261836.1787 |  |  |  |  | 261836 | 201412 |  |  | 0 | 20.2 | 0 | 9.83 | 5474.5
TS5500Shv | GG\23\004\X1 | GG | 23 | 4 | X1 | 1 Prestrip - Thick | 35.9639 | 35.9639 | 35.9639 | 2024-11-23 04:11 | 2024-12-11 16:02 | 476163.3081 | 476163 | [7 empty] | 0 | 0 | 36.01 | 10.83 | 5289.5
TS5500Exc | RS\43\003\B | RS | 43 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-11-23 17:10 | 2024-11-24 09:00 | 19949.9547 | [6 empty] | 19950 | 14352 | 1.43 | 0 | 0 | 9.17 | 5581
PH4100A | RS\43\005\X | RS | 43 | 5 | X | 1 Prestrip - Thick | 100 | 65.1102 | 65.1102 | 2024-11-24 02:38 | 2024-11-29 14:01 | 219386.1262 | 219386 | [7 empty] | 0 | 0 | 22.45 | 10.59 | 5421.62
TS6060#1 | RS\45\004\A | RS | 45 | 4 | A | 1 Prestrip - Thick | 44.5264 | 44.5264 | 44.5264 | 2024-11-24 02:38 | 2024-12-02 09:35 | 200005.8445 | 200006 | [7 empty] | 0 | 0 | 20.33 | 14.19 | 5179.24
TS5500Exc | MW\54\006\D | MW | 54 | 6 | D | 8 Coal Mining | 51 | 0 | 51 | 2024-11-24 09:00 | 2024-11-25 10:10 | 31694.917 | [6 empty] | 31695 | 23681 | 2.37 | 0 | 0 | 7.94 | 5715
PH4100XPC#1 | GG\22\008\X1 | GG | 22 | 8 | X1 | 1 Prestrip - Thick | 100 | 52.9958 | 52.9958 | 2024-11-24 11:43 | 2024-12-01 23:09 | 401200.5624 | 401201 | [7 empty] | 0 | 0 | 39.46 | 13.04 | 5221.78
DRE1 | MW\51\007\D | MW | 51 | 7 | D | 6 DL | 100 | 100 | 100 | 2024-11-25 00:38 | 2024-11-30 08:08 | 433512.7866 |  |  |  | 22289 | 433513 | 349188 |  |  | 0 | 29.04 | 0 | 5.98 | 5888.43
TS5500Exc | RS\42\003\D | RS | 42 | 3 | D | 8 Coal Mining | 26.8 | 0 | 26.8 | 2024-11-25 10:10 | 2024-11-26 04:54 | 23587.6269 | [6 empty] | 23588 | 17570 | 1.21 | 0 | 0 | 5.42 | 5945
TS5500Exc | MW\56\006\D | MW | 56 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-11-26 04:54 | 2024-11-29 08:26 | 66809.7633 | 66810 | [7 empty] | 0 | 0 | 5.68 | 8.05 | 5706.33
DRE2 | GG\20\005\B | GG | 20 | 5 | B | 6 DL | 100 | 0 | 100 | 2024-11-26 19:17 | 2024-11-30 12:22 | 267691.7408 |  |  |  |  | 267692 | 205917 |  |  | 0 | 20.51 | 0 | 9.02 | 5528.89
TS5500Exc | MW\57\006\D | MW | 57 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-11-29 08:26 | 2024-11-30 00:09 | 13907.1706 | 13907 | [7 empty] | 0 | 0 | 2.25 | 8.49 | 5667.88
PH4100A | RS\43\006\X | RS | 43 | 6 | X | 1 Prestrip - Thick | 100 | 68.5162 | 68.5162 | 2024-11-29 14:01 | 2024-12-04 18:18 | 208804.9911 | 208805 | [7 empty] | 0 | 0 | 28.87 | 9.69 | 5509.03
TS5500Exc | RS\43\005\X | RS | 43 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2024-11-30 00:09 | 2024-11-30 15:51 | 19779.729 | [6 empty] | 19780 | 14114 | 1.41 | 0 | 0 | 10.59 | 5422
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2024-11-30 08:08 | 2024-12-02 08:08
DRE2 | GG\20\004\B | GG | 20 | 4 | B | 6 DL | 100 | 0 | 100 | 2024-11-30 12:22 | 2024-12-10 17:33 | 736758.465 |  |  |  |  | 736758 | 350837 |  |  | 0 | 20.61 | 0 | 9.39 | 5517.67
TS5500Exc | MW\51\007\D | MW | 51 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-11-30 15:51 | 2024-12-03 07:57 | 80727.2757 | [6 empty] | 80727 | 61145 | 4.82 | 0 | 0 | 5.98 | 5888
PH4100XPC#1 | GG\22\009\X2 | GG | 22 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 55.2121 | 2024-12-01 23:09 | 2024-12-09 19:33 | 436282.0416 | 436282 | [7 empty] | 0 | 0 | 44.77 | 0 | 0
DRE1 | MW\56\006\D | MW | 56 | 6 | D | 6 DL | 100 | 0 | 100 | 2024-12-02 08:08 | 2024-12-09 00:12 | 544215.7214 |  |  |  | 38704 | 544216 | 391336 |  |  | 0 | 35 | 0 | 8.05 | 5706.33
TS6060#1 | GG\22\007\X1 | GG | 22 | 7 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-12-02 09:35 | 2024-12-02 15:59 | 8653.4468 | [6 empty] | 8653 | 6341 | 0.63 | 0 | 0 | 12.03 | 5270
TS Fleet 5 | GG\23\004\X1 | GG | 23 | 4 | X1 | 1 Prestrip - Thick | 64.0361 | 64.0361 | 64.0361 | 2024-12-02 10:39 | 2024-12-20 11:13 | 847840.7649 | 847841 | [7 empty] | 0 | 0 | 64.11 | 10.83 | 5289.5
TS6060#1 | GG\22\008\X1 | GG | 22 | 8 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-12-02 15:59 | 2024-12-02 22:49 | 9240.9462 | [6 empty] | 9241 | 6705 | 0.67 | 0 | 0 | 13.04 | 5222
TS6060#1 | RS\43\005\A | RS | 43 | 5 | A | 1 Prestrip - Thick | 37.2787 | 37.2787 | 37.2787 | 2024-12-02 22:49 | 2024-12-05 20:09 | 71541.6351 | 71542 | [7 empty] | 0 | 0 | 7.13 | 13.38 | 5243.79
TS5500Exc | GG\23\005\X1 | GG | 23 | 5 | X1 | 1 Prestrip - Thick | 21.5036 | 21.5036 | 21.5036 | 2024-12-03 07:57 | 2024-12-12 12:20 | 195056.5769 | 195057 | [7 empty] | 0 | 0 | 19.21 | 10.75 | 5299.89
PH4100A | RS\43\005\A | RS | 43 | 5 | A | 1 Prestrip - Thick | 100 | 62.7213 | 62.7213 | 2024-12-04 18:18 | 2024-12-07 15:38 | 120368.5584 | 120369 | [7 empty] | 0 | 0 | 12 | 13.38 | 5243.79
TS6060#1 | GG\20\005\B | GG | 20 | 5 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-12-05 20:09 | 2024-12-06 14:04 | 24254.9243 | [6 empty] | 24255 | 17909 | 1.79 | 0 | 0 | 9.02 | 5529
TS6060#1 | GG\20\006\B | GG | 20 | 6 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-12-06 14:04 | 2024-12-07 09:07 | 25775.4747 | [6 empty] | 25775 | 18933 | 1.89 | 0 | 0 | 9.83 | 5475
TS6060#1 | GG\20\007\B | GG | 20 | 7 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2024-12-07 09:07 | 2024-12-08 05:05 | 27034.493 | [6 empty] | 27034 | 19783 | 1.98 | 0 | 0 | 10.32 | 5458
PH4100A | RS\44\002\A | RS | 44 | 2 | A | 1 Prestrip - Thick | 100 | 62.665 | 62.665 | 2024-12-07 15:38 | 2024-12-08 15:45 | 41440.5368 | 41441 | [7 empty] | 0 | 0 | 22.24 | 11.81 | 5376.17
TS6060#1 | GG\20\010\B | GG | 20 | 10 | B | 8 Coal Mining | 26.8 | 0 | 26.8 | 2024-12-08 05:05 | 2024-12-08 14:58 | 13376.2254 | [6 empty] | 13376 | 9820 | 0.98 | 0 | 0 | 9.84 | 5537
TS6060#1 | RS\45\002\B | RS | 45 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-12-08 14:58 | 2024-12-09 00:06 | 9420.6389 | 9421 | [7 empty] | 0 | 0 | 2.62 | 9.2 | 5574.99
PH4100A | RS\44\003\A | RS | 44 | 3 | A | 1 Prestrip - Thick | 100 | 71.5022 | 71.5022 | 2024-12-08 15:45 | 2024-12-16 03:09 | 303129.416 | 303129 | [7 empty] | 0 | 0 | 30.64 | 12.16 | 5345.46
TS6060#1 | RS\45\005\X | RS | 45 | 5 | X | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-12-09 00:06 | 2024-12-26 17:24 | 424107.0283 | 424107 | [7 empty] | 0 | 0 | 30.57 | 10.35 | 5445.47
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2024-12-09 00:12 | 2024-12-11 00:12
PH4100XPC#1 | GG\22\009\B | GG | 22 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-12-09 19:33 | 2024-12-11 06:48 | 79776.9088 | 79777 | [7 empty] | 0 | 0 | 7.98 | 10.03 | 5520.4
DRE2 | GG\19\012\D | GG | 19 | 12 | D | 6 DL | 100 | 100 | 100 | 2024-12-10 17:33 | 2024-12-17 20:34 | 513900.4403 |  |  |  | 11965 | 513900 | 227337 |  |  | 0 | 23.96 | 0 | 6.77 | 5791.46
DRE1 | MW\57\006\D | MW | 57 | 6 | D | 6 DL | 100 | 0 | 100 | 2024-12-11 00:12 | 2024-12-14 16:59 | 301866.7747 |  |  |  | 21468 | 301867 | 217067 |  |  | 0 | 35 | 0 | 8.49 | 5667.88
PH4100XPC#1 | GG\22\010\X1 | GG | 22 | 10 | X1 | 1 Prestrip - Thick | 100 | 49.078 | 49.078 | 2024-12-11 06:48 | 2024-12-17 04:43 | 320979.5763 | 320980 | [7 empty] | 0 | 0 | 28.15 | 15.83 | 5028.89
TS5500Shv | GG\22\007\X1 | GG | 22 | 7 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-12-11 16:02 | 2024-12-11 22:26 | 7796.6699 | [6 empty] | 7797 | 5713 | 0.57 | 0 | 0 | 12.03 | 5270
TS5500Shv | GG\22\008\X1 | GG | 22 | 8 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-12-11 22:26 | 2024-12-12 05:15 | 8326.0011 | [6 empty] | 8326 | 6041 | 0.6 | 0 | 0 | 13.04 | 5222
TS5500Shv | GG\22\008\X2 | GG | 22 | 8 | X2 | 1 Prestrip - Thick | 87.3026 | 0 | 87.3026 | 2024-12-12 05:15 | 2024-12-14 23:34 | 71077.5855 | 71078 | [7 empty] | 0 | 0 | 7.1 | 0 | 0
TS5500Exc | RS\43\006\X | RS | 43 | 6 | X | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-12-12 12:20 | 2024-12-12 17:21 | 6311.2678 | [6 empty] | 6311 | 4542 | 0.63 | 0 | 0 | 9.69 | 5509
TS5500Exc | RS\44\002\A | RS | 44 | 2 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-12-12 17:21 | 2024-12-12 22:36 | 6621.4346 | [6 empty] | 6621 | 4716 | 1.7 | 0 | 0 | 11.81 | 5376
TS5500Exc | GG\23\006\X1 | GG | 23 | 6 | X1 | 1 Prestrip - Thick | 23.1323 | 23.1323 | 23.1323 | 2024-12-12 22:36 | 2024-12-22 11:21 | 202507.9276 | 202508 | [7 empty] | 0 | 0 | 19.92 | 11.32 | 5286.48
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 2d 00:00 |  | 2d 00:00 | 2024-12-14 16:59 | 2024-12-16 16:59
TS5500Shv | RS\42\003\D | RS | 42 | 3 | D | 8 Coal Mining | 73.2 | 0 | 73.2 | 2024-12-14 23:34 | 2024-12-17 04:26 | 64481.0857 | [6 empty] | 64481 | 48031 | 3.3 | 0 | 0 | 5.42 | 5945
PH4100A | RS\44\004\X | RS | 44 | 4 | X | 1 Prestrip - Thick | 100 | 75.1145 | 75.1145 | 2024-12-16 03:09 | 2024-12-21 06:16 | 201755.778 | 201756 | [7 empty] | 0 | 0 | 20.7 | 11.23 | 5357.47
DRE1 | RS\42\004\D | RS | 42 | 4 | D | 6 DL | 100 | 100 | 100 | 2024-12-16 16:59 | 2024-12-20 13:23 | 314164.5418 |  |  |  | 16152 | 314165 | 253055 |  |  | 0 | 26.92 | 0 | 5.67 | 5923.12
TS5500Shv | RS\43\003\B | RS | 43 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-12-17 04:26 | 2024-12-17 20:17 | 19313.254 | [6 empty] | 19313 | 13894 | 1.39 | 0 | 0 | 9.17 | 5581
PH4100XPC#1 | GG\22\007\B | GG | 22 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-12-17 04:43 | 2024-12-20 00:15 | 152839.3548 | 152839 | [7 empty] | 0 | 0 | 15.28 | 10.34 | 5460.32
TS5500Shv | GG\22\010\X1 | GG | 22 | 10 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2024-12-17 20:17 | 2024-12-18 01:30 | 6363.7959 | [6 empty] | 6364 | 4523 | 0.45 | 0 | 0 | 15.83 | 5029
DRE2 | GG\19\011\D | GG | 19 | 11 | D | 6 DL | 100 | 100 | 100 | 2024-12-17 20:34 | 2024-12-24 22:27 | 510488.9663 |  |  |  | 9264 | 510489 | 222341 |  |  | 0 | 23.18 | 0 | 6.5 | 5814.03
TS5500Shv | RS\43\006\X | RS | 43 | 6 | X | 8 Coal Mining | 49.2 | 0 | 49.2 | 2024-12-18 01:30 | 2024-12-18 06:30 | 6109.8443 | [6 empty] | 6110 | 4397 | 0.61 | 0 | 0 | 9.69 | 5509
TS5500Shv | RS\43\004\A | RS | 43 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-12-18 06:30 | 2024-12-19 20:08 | 45876.9982 | [6 empty] | 45877 | 32310 | 3.23 | 0 | 0 | 13.22 | 5255
TS5500Shv | RS\43\005\A | RS | 43 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2024-12-19 20:08 | 2024-12-21 10:10 | 46388.8137 | [6 empty] | 46389 | 32613 | 3.26 | 0 | 0 | 13.38 | 5244
PH4100XPC#1 | GG\22\008\X2 | GG | 22 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 12.6974 | 2024-12-20 00:15 | 2024-12-20 04:49 | 10337.5765 | 10338 | [7 empty] | 0 | 0 | 1.03 | 0 | 0
PH4100XPC#1 | GG\22\008\B | GG | 22 | 8 | B | 1 Prestrip - Thick | 100 | 63.4907 | 63.4907 | 2024-12-20 04:49 | 2024-12-20 23:53 | 43183.7087 | 43184 | [7 empty] | 0 | 0 | 4.32 | 10.17 | 5494
TS Fleet 5 | GG\22\008\B | GG | 22 | 8 | B | 1 Prestrip - Thick | 45.3511 | 36.5093 | 36.5093 | 2024-12-20 11:13 | 2024-12-20 23:53 | 24832.0712 | 24832 | [7 empty] | 0 | 0 | 2.48 | 10.17 | 5494
DRE1 | RS\42\005\D | RS | 42 | 5 | D | 6 DL | 100 | 100 | 100 | 2024-12-20 13:23 | 2024-12-24 05:57 | 301122.5924 |  |  |  | 15482 | 301123 | 242549 |  |  | 0 | 25.8 | 0 | 5.83 | 5909.26
TS Fleet 5 | GG\23\005\X1 | GG | 23 | 5 | X1 | 1 Prestrip - Thick | 59.9966 | 57.0665 | 57.0665 | 2024-12-20 23:53 | 2025-01-01 | 517644.0513 | 517644 | [7 empty] | 0 | 0 | 50.98 | 10.75 | 5299.89
PH4100XPC#1 | GG\22\011\X1 | GG | 22 | 11 | X1 | 1 Prestrip - Thick | 100 | 54.2916 | 54.2916 | 2024-12-20 23:53 | 2024-12-26 09:12 | 288530.7517 | 288531 | [7 empty] | 0 | 0 | 28.29 | 14.89 | 5107.08
PH4100A | RS\43\004\B | RS | 43 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-12-21 06:16 | 2024-12-21 22:04 | 27427.8365 | 27428 | [7 empty] | 0 | 0 | 2.74 | 9.1 | 5601.21
TS5500Shv | RS\42\004\D | RS | 42 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2024-12-21 10:10 | 2024-12-23 12:33 | 61431.6376 | [6 empty] | 61432 | 45502 | 4.55 | 0 | 0 | 5.67 | 5923
PH4100A | RS\43\005\B | RS | 43 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-12-21 22:04 | 2024-12-22 13:11 | 26264.0925 | 26264 | [7 empty] | 0 | 0 | 2.62 | 9.04 | 5615.15
TS5500Exc | RS\44\003\A | RS | 44 | 3 | A | 8 Coal Mining | 75.8 | 0 | 75.8 | 2024-12-22 11:21 | 2024-12-23 15:11 | 35048.9689 | [6 empty] | 35049 | 24865 | 2.48 | 0 | 0 | 12.16 | 5345
PH4100A | RS\43\006\A | RS | 43 | 6 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-12-22 13:11 | 2024-12-25 09:15 | 118148.6471 | 118149 | [7 empty] | 0 | 0 | 18.44 | 15.68 | 5069.75
TS5500Shv | RS\43\004\B | RS | 43 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2024-12-23 12:33 | 2024-12-24 21:14 | 39861.2524 | [6 empty] | 39861 | 28639 | 2.86 | 0 | 0 | 9.1 | 5601
TS5500Exc | RS\43\005\B | RS | 43 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2024-12-23 15:11 | 2024-12-24 07:49 | 20954.8934 | [6 empty] | 20955 | 15059 | 1.5 | 0 | 0 | 9.04 | 5615
DRE1 | RS\42\006\D | RS | 42 | 6 | D | 6 DL | 100 | 100 | 100 | 2024-12-24 05:57 | 2024-12-27 05:27 | 243113.2463 |  |  |  | 9091 | 243113 | 137993 |  |  | 0 | 26.17 | 0 | 5.9 | 5899.09
TS5500Exc | RS\42\005\D | RS | 42 | 5 | D | 8 Coal Mining | 35.7 | 0 | 33.5 | 2024-12-24 07:49 | 2024-12-25 00:58 | 21590.9893 | [6 empty] | 21591 | 15970 | 1.6 | 0 | 0 | 5.83 | 5909
TS5500Shv | RS\42\005\D | RS | 42 | 5 | D | 8 Coal Mining | 64.3 | 0 | 7 | 2024-12-24 21:14 | 2024-12-25 00:58 | 4535.017 | [6 empty] | 4535 | 3354 | 0.34 | 0 | 0 | 5.83 | 5909
DRE2 | GG\19\010\D | GG | 19 | 10 | D | 6 DL | 100 | 100 | 100 | 2024-12-24 22:27 | 2024-12-31 06:56 | 458220.4339 |  |  |  | 10669 | 458220 | 202705 |  |  | 0 | 21.34 | 0 | 6.35 | 5828.22
TS5500Exc | GG\23\007\X1 | GG | 23 | 7 | X1 | 1 Prestrip - Thick | 21.0548 | 17.8311 | 17.8311 | 2024-12-25 00:58 | 2025-01-01 | 147886.7237 | 147887 | [7 empty] | 0 | 0 | 14.4 | 12.17 | 5258.43
TS5500Shv | GG\23\005\X1 | GG | 23 | 5 | X1 | 1 Prestrip - Thick | 28.4409 | 19.6533 | 19.6533 | 2024-12-25 00:58 | 2025-01-01 | 178272.5023 | 178273 | [7 empty] | 0 | 0 | 17.56 | 10.75 | 5299.89
PH4100A | RS\44\005\X | RS | 44 | 5 | X | 1 Prestrip - Thick | 100 | 50.2602 | 50.2602 | 2024-12-25 09:15 | 2025-01-01 | 264766.0544 | 264766 | [7 empty] | 0 | 0 | 17.18 | 10.28 | 5451.74
PH4100XPC#1 | GG\22\012\X1 | GG | 22 | 12 | X1 | 1 Prestrip - Thick | 100 | 49.4418 | 49.4418 | 2024-12-26 09:12 | 2024-12-30 19:47 | 236477.5399 | 236478 | [7 empty] | 0 | 0 | 23.04 | 14.75 | 5119.05
TS6060#1 | RS\46\002\A | RS | 46 | 2 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2024-12-26 17:24 | 2024-12-30 16:17 | 97368.6727 | 97369 | [7 empty] | 0 | 0 | 29.46 | 11.63 | 5400.72
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2024-12-27 05:27 | 2024-12-30 05:27
DRE1 | RS\43\002\D | RS | 43 | 2 | D | 6 DL | 100 | 87.693 | 87.693 | 2024-12-30 05:27 | 2025-01-01 | 144616.9098 |  |  |  | 7435 | 144617 | 116487 |  |  | 0 | 27.57 | 0 | 5.39 | 5945.24
TS6060#1 | RS\42\006\D | RS | 42 | 6 | D | 7 PostStrip | 100 | 0 | 94.1646 | 2024-12-30 16:17 | 2025-01-01 | 32708.6688 |  |  | 32709 | [5 empty] | 0 | 0 | 0 | 5.9 | 5899.09
PH4100XPC#1 | GG\22\013\X1 | GG | 22 | 13 | X1 | 1 Prestrip - Thick | 100 | 15.7809 | 15.7809 | 2024-12-30 19:47 | 2025-01-01 | 61887.4973 | 61887 | [7 empty] | 0 | 0 | 6.03 | 14.54 | 5136.08
DRE2 | GG\19\009\D | GG | 19 | 9 | D | 6 DL | 100 | 11.6294 | 11.6294 | 2024-12-31 06:56 | 2025-01-01 | 51250.7046 |  |  |  | 1193 | 51251 | 22672 |  |  | 0 | 20.53 | 0 | 6.43 | 5821.63
| EOP 77 : 2024 | EOP 77 : 2024 | [7 empty] | 2025-01-01 | 2025-01-01 |  | 66095291 |  | 822787 | 1739288 | 52180891 | 33640901 | 13000000 | 9504609 | 970.11 | 0 | 6291.69 | 9.1 | 5597.41
TS Fleet 5 | GG\23\005\X1 | GG | 23 | 5 | X1 | 1 Prestrip - Thick | 59.9966 | 1.1324 | 1.1324 | 2025-01-01 | 2025-01-01 05:28 | 10271.8654 | 10272 | [7 empty] | 0 | 0 | 1.01 | 10.75 | 5299.89
DRE1 | RS\43\002\D | RS | 43 | 2 | D | 6 DL | 100 | 12.307 | 12.307 | 2025-01-01 | 2025-01-01 05:48 | 20295.7561 |  |  |  | 1043 | 20296 | 16348 |  |  | 0 | 27.57 | 0 | 5.39 | 5945.24
PH4100A | RS\44\005\X | RS | 44 | 5 | X | 1 Prestrip - Thick | 100 | 14.6938 | 14.6938 | 2025-01-01 | 2025-01-03 00:29 | 77405.7313 | 77406 | [7 empty] | 0 | 0 | 5.02 | 10.28 | 5451.74
DRE2 | GG\19\009\D | GG | 19 | 9 | D | 6 DL | 100 | 88.3706 | 88.3706 | 2025-01-01 | 2025-01-05 19:46 | 389448.6436 |  |  |  | 9067 | 389449 | 172282 |  |  | 0 | 20.53 | 0 | 6.43 | 5821.63
PH4100XPC#1 | GG\22\013\X1 | GG | 22 | 13 | X1 | 1 Prestrip - Thick | 100 | 38.0886 | 38.0886 | 2025-01-01 | 2025-01-03 20:05 | 149370.9158 | 149371 | [7 empty] | 0 | 0 | 14.56 | 14.54 | 5136.08
TS6060#1 | RS\42\006\D | RS | 42 | 6 | D | 7 PostStrip | 100 | 0 | 5.8354 | 2025-01-01 | 2025-01-01 01:57 | 2026.9801 |  |  | 2027 | [5 empty] | 0 | 0 | 0 | 5.9 | 5899.09
TS5500Exc | GG\23\007\X1 | GG | 23 | 7 | X1 | 1 Prestrip - Thick | 21.0548 | 3.2237 | 3.2237 | 2025-01-01 | 2025-01-02 06:11 | 26737.0036 | 26737 | [7 empty] | 0 | 0 | 2.6 | 12.17 | 5258.43
TS5500Shv | GG\23\005\X1 | GG | 23 | 5 | X1 | 1 Prestrip - Thick | 28.4409 | 0.64424 | 0.64424 | 2025-01-01 | 2025-01-01 05:28 | 5843.8552 | 5844 | [7 empty] | 0 | 0 | 0.58 | 10.75 | 5299.89
TS6060#1 | GG\22\010\X1 | GG | 22 | 10 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-01-01 01:57 | 2025-01-01 07:11 | 7063.1141 | [6 empty] | 7063 | 5020 | 0.49 | 0 | 0 | 15.83 | 5029
TS5500Shv | GG\22\011\X1 | GG | 22 | 11 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-01-01 05:28 | 2025-01-01 18:30 | 15898.0412 | [6 empty] | 15898 | 11370 | 1.15 | 0 | 0 | 14.89 | 5107
TS Fleet 5 | GG\23\006\X1 | GG | 23 | 6 | X1 | 1 Prestrip - Thick | 49.2014 | 49.2014 | 49.2014 | 2025-01-01 05:28 | 2025-01-10 19:04 | 430725.7319 | 430726 | [7 empty] | 0 | 0 | 42.36 | 11.32 | 5286.48
DRE1 | RS\43\003\D | RS | 43 | 3 | D | 6 DL | 100 | 100 | 100 | 2025-01-01 05:48 | 2025-01-05 03:06 | 325926.8279 |  |  |  | 16757 | 325927 | 262529 |  |  | 0 | 27.93 | 0 | 5.5 | 5937.33
TS6060#1 | GG\22\012\X1 | GG | 22 | 12 | X1 | 8 Coal Mining | 8.9 | 0 | 8.9 | 2025-01-01 07:11 | 2025-01-01 08:09 | 1323.0282 | [6 empty] | 1323 | 948 | 0.1 | 0 | 0 | 14.75 | 5119
TS6060#1 | GG\19\010\D | GG | 19 | 10 | D | 8 Coal Mining | 96.3 | 0 | 96.3 | 2025-01-01 08:09 | 2025-01-03 03:38 | 58839.717 | [6 empty] | 58840 | 44057 | 4.41 | 0 | 0 | 6.35 | 5828
TS5500Shv | GG\22\010\X2 | GG | 22 | 10 | X2 | 1 Prestrip - Thick | 22.9288 | 0 | 22.9288 | 2025-01-01 18:30 | 2025-01-02 08:25 | 14910.6873 | 14911 | [7 empty] | 0 | 0 | 1.47 | 0 | 0
TS5500Exc | RS\42\005\D | RS | 42 | 5 | D | 8 Coal Mining | 35.7 | 0 | 2.2 | 2025-01-02 06:11 | 2025-01-02 07:17 | 1386.0295 | [6 empty] | 1386 | 1025 | 0.1 | 0 | 0 | 5.83 | 5909
TS5500Exc | RS\42\006\D | RS | 42 | 6 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-01-02 07:17 | 2025-01-03 00:38 | 21843.5172 | [6 empty] | 21844 | 16155 | 2.34 | 0 | 0 | 5.9 | 5899
TS5500Shv | GG\22\011\X2 | GG | 22 | 11 | X2 | 1 Prestrip - Thick | 20.5603 | 0 | 20.5603 | 2025-01-02 08:25 | 2025-01-02 21:41 | 14219.5595 | 14220 | [7 empty] | 0 | 0 | 1.44 | 0 | 0
TS5500Shv | GG\22\012\X1 | GG | 22 | 12 | X1 | 8 Coal Mining | 91.1 | 0 | 91.1 | 2025-01-02 21:41 | 2025-01-03 08:49 | 13575.0552 | [6 empty] | 13575 | 9726 | 0.97 | 0 | 0 | 14.75 | 5119
PH4100A | SC\40\010\D | SC | 40 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-01-03 00:29 | 2025-01-10 23:31 | 316059.5945 | 316060 | [7 empty] | 0 | 0 | 26.5 | 7.72 | 5735.86
TS5500Exc | RS\43\006\A | RS | 43 | 6 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-01-03 00:38 | 2025-01-03 12:52 | 15413.3484 | [6 empty] | 15413 | 10718 | 1.7 | 0 | 0 | 15.68 | 5070
TS6060#1 | GG\19\011\D | GG | 19 | 11 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-01-03 03:38 | 2025-01-04 02:59 | 31612.4865 | [6 empty] | 31612 | 23651 | 2.37 | 0 | 0 | 6.5 | 5814
TS5500Shv | RS\42\005\D | RS | 42 | 5 | D | 8 Coal Mining | 64.3 | 0 | 57.3 | 2025-01-03 08:49 | 2025-01-04 15:02 | 36859.6029 | [6 empty] | 36860 | 27263 | 2.73 | 0 | 0 | 5.83 | 5909
TS5500Exc | RS\44\004\X | RS | 44 | 4 | X | 8 Coal Mining | 100 | 0 | 100 | 2025-01-03 12:52 | 2025-01-04 01:17 | 15638.2634 | [6 empty] | 15638 | 11090 | 1.1 | 0 | 0 | 11.23 | 5357
PH4100XPC#1 | GG\22\010\X2 | GG | 22 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 77.0712 | 2025-01-03 20:05 | 2025-01-04 18:14 | 50119.6417 | 50120 | [7 empty] | 0 | 0 | 4.95 | 0 | 0
TS5500Exc | GG\23\008\X1 | GG | 23 | 8 | X1 | 1 Prestrip - Thick | 0.19446 | 0.19446 | 0.19446 | 2025-01-04 01:17 | 2025-01-04 03:00 | 1522.2264 | 1522 | [7 empty] | 0 | 0 | 0.15 | 13.18 | 5209.43
TS6060#1 | GG\22\013\X1 | GG | 22 | 13 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-01-04 02:59 | 2025-01-04 08:39 | 7656.7925 | [6 empty] | 7657 | 5494 | 0.54 | 0 | 0 | 14.54 | 5136
TS5500Exc | GG\23\008\X1 | GG | 23 | 8 | X1 | 1 Prestrip - Thick | 14.391 | 14.391 | 14.391 | 2025-01-04 03:00 | 2025-01-09 10:14 | 112654.964 | 112655 | [7 empty] | 0 | 0 | 11.23 | 13.18 | 5209.43
TS6060#1 | RS\44\004\A | RS | 44 | 4 | A | 1 Prestrip - Thick | 5.4966 | 5.4966 | 5.4966 | 2025-01-04 08:39 | 2025-01-04 18:55 | 10599.6463 | 10600 | [7 empty] | 0 | 0 | 1.06 | 13.77 | 5212.51
TS5500Shv | GG\22\013\X1 | GG | 22 | 13 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-01-04 15:02 | 2025-01-04 20:42 | 6898.6942 | [6 empty] | 6899 | 4950 | 0.48 | 0 | 0 | 14.54 | 5136
PH4100XPC#1 | GG\22\010\B | GG | 22 | 10 | B | 1 Prestrip - Thick | 100 | 63.1793 | 63.1793 | 2025-01-04 18:14 | 2025-01-05 20:31 | 59510.5207 | 59511 | [7 empty] | 0 | 0 | 5.94 | 10.08 | 5524.1
TS6060#1 | GG\22\010\B | GG | 22 | 10 | B | 1 Prestrip - Thick | 100 | 28.0476 | 28.0476 | 2025-01-04 18:55 | 2025-01-05 20:31 | 26418.9153 | 26419 | [7 empty] | 0 | 0 | 2.64 | 10.08 | 5524.1
TS5500Shv | GG\22\010\B | GG | 22 | 10 | B | 1 Prestrip - Thick | 8.7731 | 8.7731 | 8.7731 | 2025-01-04 20:42 | 2025-01-05 04:24 | 8263.6311 | 8264 | [7 empty] | 0 | 0 | 0.83 | 10.08 | 5524.1
DRE1 | RS\43\004\D | RS | 43 | 4 | D | 6 DL | 100 | 100 | 100 | 2025-01-05 03:06 | 2025-01-08 21:41 | 316399.6874 |  |  |  | 16267 | 316400 | 254855 |  |  | 0 | 27.11 | 0 | 5.73 | 5917.83
TS5500Shv | RS\42\006\D | RS | 42 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-01-05 04:24 | 2025-01-05 21:45 | 21146.3836 | [6 empty] | 21146 | 15639 | 2.27 | 0 | 0 | 5.9 | 5899
DRE2 | GG\19\008\D | GG | 19 | 8 | D | 6 DL | 100 | 100 | 100 | 2025-01-05 19:46 | 2025-01-11 03:28 | 429541.9398 |  |  |  | 10001 | 429542 | 190019 |  |  | 0 | 20 | 0 | 6.51 | 5814.25
TS6060#1 | GG\19\012\D | GG | 19 | 12 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-01-05 20:31 | 2025-01-06 20:20 | 32222.5312 | [6 empty] | 32223 | 24070 | 2.41 | 0 | 0 | 6.77 | 5791
PH4100XPC#1 | GG\22\011\X2 | GG | 22 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 79.4397 | 2025-01-05 20:31 | 2025-01-06 20:48 | 54940.7605 | 54941 | [7 empty] | 0 | 0 | 5.56 | 0 | 0
TS5500Shv | RS\43\002\D | RS | 43 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-01-05 21:45 | 2025-01-06 23:57 | 31961.2424 | [6 empty] | 31961 | 23870 | 4.59 | 0 | 0 | 5.39 | 5945
TS6060#1 | GG\19\009\D | GG | 19 | 9 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-01-06 20:20 | 2025-01-07 20:15 | 32382.7209 | [6 empty] | 32383 | 24209 | 2.42 | 0 | 0 | 6.43 | 5822
PH4100XPC#1 | GG\22\011\B | GG | 22 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-01-06 20:48 | 2025-01-09 00:08 | 116218.0085 | 116218 | [7 empty] | 0 | 0 | 11.68 | 10.37 | 5495.01
TS5500Shv | RS\43\005\B | RS | 43 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-01-06 23:57 | 2025-01-07 16:36 | 20286.1202 | [6 empty] | 20286 | 14578 | 1.46 | 0 | 0 | 9.04 | 5615
TS5500Shv | RS\43\006\A | RS | 43 | 6 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-01-07 16:36 | 2025-01-08 04:50 | 14921.433 | [6 empty] | 14921 | 10376 | 1.65 | 0 | 0 | 15.68 | 5070
TS6060#1 | GG\20\004\B | GG | 20 | 4 | B | 8 Coal Mining | 70.2 | 0 | 70.2 | 2025-01-07 20:15 | 2025-01-09 16:01 | 59215.6628 | [6 empty] | 59216 | 43619 | 2.7 | 0 | 0 | 9.39 | 5518
TS5500Shv | RS\44\002\A | RS | 44 | 2 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-01-08 04:50 | 2025-01-08 10:05 | 6410.1122 | [6 empty] | 6410 | 4565 | 1.65 | 0 | 0 | 11.81 | 5376
TS5500Shv | RS\43\006\B | RS | 43 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-01-08 10:05 | 2025-01-09 02:16 | 17347.3428 | 17347 | [7 empty] | 0 | 0 | 2.76 | 8.95 | 5628.79
DRE1 | RS\43\005\D | RS | 43 | 5 | D | 6 DL | 100 | 100 | 100 | 2025-01-08 21:41 | 2025-01-12 12:13 | 302286.4522 |  |  |  | 15542 | 302286 | 243487 |  |  | 0 | 25.9 | 0 | 5.88 | 5905.01
PH4100XPC#1 | GG\22\012\X2 | GG | 22 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2025-01-09 00:08 | 2025-01-10 07:51 | 71791.949 | 71792 | [7 empty] | 0 | 0 | 7.2 | 0 | 0
TS5500Shv | RS\43\006\B | RS | 43 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-01-09 02:16 | 2025-01-09 23:05 | 25381.9678 | [6 empty] | 25382 | 18238 | 2.91 | 0 | 0 | 8.95 | 5629
TS5500Exc | RS\43\003\D | RS | 43 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-01-09 10:14 | 2025-01-11 09:45 | 59845.4817 | [6 empty] | 59845 | 44535 | 4.45 | 0 | 0 | 5.5 | 5937
TS6060#1 | GG\23\004\X1 | GG | 23 | 4 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-01-09 16:01 | 2025-01-09 22:37 | 8944.1193 | [6 empty] | 8944 | 6638 | 0.55 | 0 | 0 | 10.83 | 5290
TS6060#1 | GG\23\005\X1 | GG | 23 | 5 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-01-09 22:37 | 2025-01-10 04:39 | 8160.0052 | [6 empty] | 8160 | 6061 | 0.6 | 0 | 0 | 10.75 | 5300
TS5500Shv | RS\44\003\A | RS | 44 | 3 | A | 8 Coal Mining | 24.2 | 0 | 24.2 | 2025-01-09 23:05 | 2025-01-10 08:15 | 11186.9913 | [6 empty] | 11187 | 7937 | 0.79 | 0 | 0 | 12.16 | 5345
TS6060#1 | RS\46\003\A | RS | 46 | 3 | A | 1 Prestrip - Thick | 28.4471 | 28.4471 | 28.4471 | 2025-01-10 04:39 | 2025-01-14 15:07 | 107323.0392 | 107323 | [7 empty] | 0 | 0 | 11.05 | 12.29 | 5343.44
PH4100XPC#1 | GG\22\012\B | GG | 22 | 12 | B | 1 Prestrip - Thick | 100 | 63.7624 | 63.7624 | 2025-01-10 07:51 | 2025-01-11 19:32 | 80743.4125 | 80743 | [7 empty] | 0 | 0 | 8.1 | 11.22 | 5415.51
TS5500Shv | GG\23\006\X1 | GG | 23 | 6 | X1 | 1 Prestrip - Thick | 27.7846 | 27.6663 | 27.6663 | 2025-01-10 08:15 | 2025-01-19 20:02 | 242200.5507 | 242201 | [7 empty] | 0 | 0 | 23.82 | 11.32 | 5286.48
TS Fleet 5 | GG\22\012\B | GG | 22 | 12 | B | 1 Prestrip - Thick | 45.3511 | 36.2376 | 36.2376 | 2025-01-10 19:04 | 2025-01-11 19:32 | 45888.2467 | 45888 | [7 empty] | 0 | 0 | 4.6 | 11.22 | 5415.51
PH4100A | RS\44\002\B | RS | 44 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-01-10 23:31 | 2025-01-11 04:20 | 8009.4915 | 8009 | [7 empty] | 0 | 0 | 2.73 | 9.25 | 5567.31
DRE2 | GG\19\007\D | GG | 19 | 7 | D | 6 DL | 100 | 100 | 100 | 2025-01-11 03:28 | 2025-01-16 11:25 | 430362.8275 |  |  |  | 10020 | 430363 | 190382 |  |  | 0 | 20.04 | 0 | 6.59 | 5807.37
PH4100A | RS\44\003\B | RS | 44 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-01-11 04:20 | 2025-01-11 20:38 | 27057.9972 | 27058 | [7 empty] | 0 | 0 | 2.7 | 9.17 | 5582.76
TS5500Exc | RS\44\002\B | RS | 44 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-01-11 09:45 | 2025-01-11 19:36 | 12400.0102 | [6 empty] | 12400 | 8935 | 2.89 | 0 | 0 | 9.25 | 5567
PH4100XPC#1 | GG\22\013\X2 | GG | 22 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.6807 | 2025-01-11 19:32 | 2025-01-12 13:59 | 41774.6283 | 41775 | [7 empty] | 0 | 0 | 4.09 | 0 | 0
TS Fleet 5 | GG\22\013\X2 | GG | 22 | 13 | X2 | 1 Prestrip - Thick | 45.3511 | 0 | 45.3193 | 2025-01-11 19:32 | 2025-01-12 13:59 | 34622.7127 | 34623 | [7 empty] | 0 | 0 | 3.39 | 0 | 0
TS5500Exc | MW\54\006\D | MW | 54 | 6 | D | 8 Coal Mining | 49 | 0 | 49 | 2025-01-11 19:36 | 2025-01-12 19:46 | 30451.0669 | [6 empty] | 30451 | 22752 | 2.28 | 0 | 0 | 7.94 | 5715
PH4100A | RS\44\004\A | RS | 44 | 4 | A | 1 Prestrip - Thick | 100 | 94.5034 | 94.5034 | 2025-01-11 20:38 | 2025-01-16 10:18 | 182241.1869 | 182241 | [7 empty] | 0 | 0 | 18.2 | 13.77 | 5212.51
DRE1 | RS\43\006\D | RS | 43 | 6 | D | 6 DL | 100 | 100 | 100 | 2025-01-12 12:13 | 2025-01-14 18:18 | 188908.6628 |  |  |  | 7049 | 188909 | 107175 |  |  | 0 | 26.34 | 0 | 5.94 | 5894.53
TS Fleet 5 | GG\22\013\B | GG | 22 | 13 | B | 1 Prestrip - Thick | 45.3511 | 45.3193 | 45.3193 | 2025-01-12 13:59 | 2025-01-13 23:20 | 62568.5894 | 62569 | [7 empty] | 0 | 0 | 6.23 | 12.05 | 5334.07
PH4100XPC#1 | GG\22\013\B | GG | 22 | 13 | B | 1 Prestrip - Thick | 100 | 54.6807 | 54.6807 | 2025-01-12 13:59 | 2025-01-13 23:20 | 75493.2054 | 75493 | [7 empty] | 0 | 0 | 7.51 | 12.05 | 5334.07
TS5500Exc | RS\44\003\B | RS | 44 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-01-12 19:46 | 2025-01-14 02:57 | 39275.6557 | [6 empty] | 39276 | 28256 | 2.82 | 0 | 0 | 9.17 | 5583
TS Fleet 5 | GG\23\007\X1 | GG | 23 | 7 | X1 | 1 Prestrip - Thick | 43.6402 | 43.6402 | 43.6402 | 2025-01-13 23:20 | 2025-01-22 00:16 | 361941.9297 | 361942 | [7 empty] | 0 | 0 | 35.23 | 12.17 | 5258.43
PH4100XPC#1 | GG\22\014\X1 | GG | 22 | 14 | X1 | 1 Prestrip - Thick | 100 | 45.8953 | 45.8953 | 2025-01-13 23:20 | 2025-01-16 19:26 | 146791.9853 | 146792 | [7 empty] | 0 | 0 | 12.67 | 14.31 | 5153.7
TS5500Exc | MW\54\007\D | MW | 54 | 7 | D | 8 Coal Mining | 52 | 0 | 52 | 2025-01-14 02:57 | 2025-01-14 20:14 | 21770.5861 | [6 empty] | 21771 | 16411 | 2.49 | 0 | 0 | 6.67 | 5828
TS6060#1 | GG\19\008\D | GG | 19 | 8 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-01-14 15:07 | 2025-01-15 15:05 | 32433.3513 | [6 empty] | 32433 | 24227 | 2.42 | 0 | 0 | 6.51 | 5814
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2025-01-14 18:18 | 2025-01-17 18:18
TS5500Exc | MW\55\006\D | MW | 55 | 6 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-01-14 20:14 | 2025-01-15 21:07 | 31333.4592 | [6 empty] | 31333 | 23392 | 2.34 | 0 | 0 | 8.01 | 5709
TS6060#1 | RS\46\005\X | RS | 46 | 5 | X | 1 Prestrip - Thick | 23.2506 | 23.2506 | 23.2506 | 2025-01-15 15:05 | 2025-01-18 21:37 | 77967.1402 | 77967 | [7 empty] | 0 | 0 | 6.31 | 10.42 | 5438.39
TS5500Exc | MW\55\007\B | MW | 55 | 7 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-01-15 21:07 | 2025-01-16 06:49 | 12218.0038 | [6 empty] | 12218 | 9024 | 1.27 | 0 | 0 | 9.48 | 5555
TS5500Exc | MW\56\006\D | MW | 56 | 6 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-01-16 06:49 | 2025-01-17 08:14 | 32022.7414 | [6 empty] | 32023 | 23911 | 2.32 | 0 | 0 | 8.05 | 5706
PH4100A | SC\41\010\D | SC | 41 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-01-16 10:18 | 2025-01-24 19:37 | 333188.0008 | 333188 | [7 empty] | 0 | 0 | 27.88 | 7.65 | 5740.91
DRE2 | GG\19\006\D | GG | 19 | 6 | D | 6 DL | 100 | 100 | 100 | 2025-01-16 11:25 | 2025-01-21 17:34 | 424359.6902 |  |  |  | 7902 | 424360 | 189658 |  |  | 0 | 19.75 | 0 | 6.65 | 5801.65
PH4100XPC#1 | GG\22\018\X2 | GG | 22 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.7372 | 2025-01-16 19:26 | 2025-01-19 07:30 | 131059.326 | 131059 | [7 empty] | 0 | 0 | 13.4 | 0 | 0
TS5500Exc | MW\57\006\D | MW | 57 | 6 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-01-17 08:14 | 2025-01-17 20:07 | 14967.0035 | [6 empty] | 14967 | 11141 | 2.25 | 0 | 0 | 8.49 | 5668
DRE1 | RS\44\002\D | RS | 44 | 2 | D | 6 DL | 100 | 100 | 100 | 2025-01-17 18:18 | 2025-01-19 23:39 | 186370.377 |  |  |  | 9582 | 186370 | 150118 |  |  | 0 | 27.65 | 0 | 5.41 | 5943.68
TS5500Exc | RS\43\004\D | RS | 43 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-01-17 20:07 | 2025-01-19 20:47 | 61311.3852 | [6 empty] | 61311 | 45413 | 4.54 | 0 | 0 | 5.73 | 5918
TS6060#1 | GG\22\014\X1 | GG | 22 | 14 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-01-18 21:37 | 2025-01-19 03:50 | 8398.1884 | [6 empty] | 8398 | 6037 | 0.53 | 0 | 0 | 14.31 | 5154
TS6060#1 | RS\47\002\A | RS | 47 | 2 | A | 1 Prestrip - Thick | 35.1843 | 35.1843 | 35.1843 | 2025-01-19 03:50 | 2025-01-20 19:03 | 40106.1723 | 40106 | [7 empty] | 0 | 0 | 10.12 | 11.62 | 5406.71
PH4100XPC#1 | GG\22\018\B | GG | 22 | 18 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-01-19 07:30 | 2025-01-21 22:14 | 142014.6753 | 142015 | [7 empty] | 0 | 0 | 14.06 | 12.54 | 5305.06
TS5500Shv | GG\22\014\X1 | GG | 22 | 14 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-01-19 20:02 | 2025-01-20 02:15 | 7566.6846 | [6 empty] | 7567 | 5440 | 0.48 | 0 | 0 | 14.31 | 5154
TS5500Exc | RS\43\005\D | RS | 43 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-01-19 20:47 | 2025-01-22 00:03 | 64576.753 | [6 empty] | 64577 | 47727 | 4.77 | 0 | 0 | 5.88 | 5905
DRE1 | RS\44\003\D | RS | 44 | 3 | D | 6 DL | 100 | 100 | 100 | 2025-01-19 23:39 | 2025-01-23 21:29 | 327742.7335 |  |  |  | 16851 | 327743 | 263992 |  |  | 0 | 28.08 | 0 | 5.54 | 5933.94
TS5500Shv | GG\23\007\X1 | GG | 23 | 7 | X1 | 1 Prestrip - Thick | 25.2607 | 25.2607 | 25.2607 | 2025-01-20 02:15 | 2025-01-28 07:28 | 209506.6019 | 209507 | [7 empty] | 0 | 0 | 20.39 | 12.17 | 5258.43
TS6060#1 | GG\23\006\X1 | GG | 23 | 6 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-01-20 19:03 | 2025-01-21 01:09 | 8247.208 | [6 empty] | 8247 | 6092 | 0.61 | 0 | 0 | 11.32 | 5286
TS6060#1 | RS\47\003\A | RS | 47 | 3 | A | 1 Prestrip - Thick | 34.8185 | 34.8185 | 34.8185 | 2025-01-21 01:09 | 2025-01-25 22:07 | 117684.5811 | 117685 | [7 empty] | 0 | 0 | 12.17 | 12.4 | 5337.32
DRE2 | GG\19\005\D | GG | 19 | 5 | D | 6 DL | 100 | 100 | 100 | 2025-01-21 17:34 | 2025-01-26 22:25 | 419954.5274 |  |  |  | 7820 | 419955 | 187689 |  |  | 0 | 19.55 | 0 | 6.67 | 5799
PH4100XPC#1 | GG\22\014\B | GG | 22 | 14 | B | 1 Prestrip - Thick | 100 | 55.5596 | 55.5596 | 2025-01-21 22:14 | 2025-01-24 08:23 | 131630.8375 | 131631 | [7 empty] | 0 | 0 | 12.69 | 12.56 | 5289.84
TS5500Exc | RS\44\002\D | RS | 44 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-01-22 00:03 | 2025-01-23 04:36 | 35960.0432 | [6 empty] | 35960 | 26858 | 4.59 | 0 | 0 | 5.41 | 5944
TS Fleet 5 | GG\22\014\B | GG | 22 | 14 | B | 1 Prestrip - Thick | 45.3511 | 44.4404 | 44.4404 | 2025-01-22 00:16 | 2025-01-24 08:23 | 105287.2849 | 105287 | [7 empty] | 0 | 0 | 10.15 | 12.56 | 5289.84
TS5500Exc | RS\44\004\A | RS | 44 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2025-01-23 04:36 | 2025-01-24 17:14 | 46130.3268 | [6 empty] | 46130 | 32384 | 3.24 | 0 | 0 | 13.77 | 5213
DRE1 | SC\39\013\D | SC | 39 | 13 | D | 6 DL | 100 | 0 | 100 | 2025-01-23 21:29 | 2025-01-30 15:36 | 566323.6243 |  |  |  | 40276 | 566324 | 407234 |  |  | 0 | 36.68 | 0 | 7.59 | 5744.61
TS Fleet 5 | GG\23\008\X1 | GG | 23 | 8 | X1 | 1 Prestrip - Thick | 31.0277 | 31.0277 | 31.0277 | 2025-01-24 08:23 | 2025-01-29 17:52 | 242888.811 | 242889 | [7 empty] | 0 | 0 | 24.21 | 13.18 | 5209.43
PH4100XPC#1 | GG\22\019\B | GG | 22 | 19 | B | 1 Prestrip - Thick | 100 | 54.3406 | 54.3406 | 2025-01-24 08:23 | 2025-01-27 10:14 | 165077.328 | 165077 | [7 empty] | 0 | 0 | 16.66 | 12.95 | 5293.55
TS5500Exc | RS\44\003\D | RS | 44 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-01-24 17:14 | 2025-01-26 16:30 | 59546.3068 | [6 empty] | 59546 | 44276 | 4.43 | 0 | 0 | 5.54 | 5934
PH4100A | RS\44\004\B | RS | 44 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-01-24 19:37 | 2025-01-25 11:58 | 27167.7291 | 27168 | [7 empty] | 0 | 0 | 2.71 | 9.11 | 5601.76
PH4100A | SC\40\011\D | SC | 40 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-01-25 11:58 | 2025-01-31 04:30 | 226038.379 | 226038 | [7 empty] | 0 | 0 | 19.16 | 7.58 | 5746.88
TS6060#1 | RS\44\004\B | RS | 44 | 4 | B | 8 Coal Mining | 100 | 0 | 81.9 | 2025-01-25 22:07 | 2025-01-26 22:14 | 32642.5457 | [6 empty] | 32643 | 23436 | 2.34 | 0 | 0 | 9.11 | 5602
TS5500Exc | RS\44\004\B | RS | 44 | 4 | B | 8 Coal Mining | 100 | 0 | 18.1 | 2025-01-26 16:30 | 2025-01-26 22:14 | 7213.1748 | [6 empty] | 7213 | 5179 | 0.52 | 0 | 0 | 9.11 | 5602
TS6060#1 | GG\19\006\D | GG | 19 | 6 | D | 8 Coal Mining | 33.7 | 0 | 33.7 | 2025-01-26 22:14 | 2025-01-27 13:20 | 20441.2172 | [6 empty] | 20441 | 15293 | 1.53 | 0 | 0 | 6.65 | 5802
TS5500Exc | SC\39\016\D | SC | 39 | 16 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-01-26 22:14 | 2025-01-29 04:04 | 67806.7012 | [6 empty] | 67807 | 50789 | 3.91 | 0 | 0 | 7.09 | 5784
DRE2 | GG\19\004\D | GG | 19 | 4 | D | 6 DL | 100 | 100 | 100 | 2025-01-26 22:25 | 2025-02-01 02:13 | 416471.2145 |  |  |  | 7756 | 416471 | 186132 |  |  | 0 | 19.39 | 0 | 6.64 | 5801.85
PH4100XPC#1 | GG\22\020\B | GG | 22 | 20 | B | 1 Prestrip - Thick | 100 | 55.2483 | 55.2483 | 2025-01-27 10:14 | 2025-01-29 11:35 | 114428.2015 | 114428 | [7 empty] | 0 | 0 | 11.63 | 15.83 | 5080.85
TS6060#1 | GG\19\005\D | GG | 19 | 5 | D | 8 Coal Mining | 58.8 | 0 | 58.8 | 2025-01-27 13:20 | 2025-01-28 15:40 | 35636.7913 | [6 empty] | 35637 | 26683 | 2.67 | 0 | 0 | 6.67 | 5799
TS5500Shv | GG\23\008\X1 | GG | 23 | 8 | X1 | 1 Prestrip - Thick | 0.23336 | 0.23336 | 0.23336 | 2025-01-28 07:28 | 2025-01-28 09:12 | 1826.7613 | 1827 | [7 empty] | 0 | 0 | 0.18 | 13.18 | 5209.43
TS5500Shv | GG\23\008\X1 | GG | 23 | 8 | X1 | 1 Prestrip - Thick | 17.2701 | 17.2701 | 17.2701 | 2025-01-28 09:12 | 2025-02-02 16:26 | 135192.593 | 135193 | [7 empty] | 0 | 0 | 13.48 | 13.18 | 5209.43
TS6060#1 | RS\47\004\A | RS | 47 | 4 | A | 1 Prestrip - Thick | 31.8655 | 31.8655 | 31.8655 | 2025-01-28 15:40 | 2025-02-02 23:28 | 128028.869 | 128029 | [7 empty] | 0 | 0 | 13.12 | 14.79 | 5132.7
TS5500Exc | RS\45\003\A | RS | 45 | 3 | A | 8 Coal Mining | 47.3 | 0 | 47.3 | 2025-01-29 04:04 | 2025-01-29 21:25 | 21863.909 | [6 empty] | 21864 | 15509 | 1.55 | 0 | 0 | 12.22 | 5345
PH4100XPC#1 | GG\22\021\D | GG | 22 | 21 | D | 1 Prestrip - Thick | 100 | 54.7596 | 54.7596 | 2025-01-29 11:35 | 2025-02-01 19:24 | 188351.7704 | 188352 | [7 empty] | 0 | 0 | 19.16 | 6.8 | 5789.37
TS Fleet 5 | GG\23\009\X2 | GG | 23 | 9 | X2 | 1 Prestrip - Thick | 44.83 | 0 | 44.83 | 2025-01-29 17:52 | 2025-02-07 00:31 | 372687.7598 | 372688 | [7 empty] | 0 | 0 | 37.68 | 0 | 0
TS5500Exc | RS\45\004\A | RS | 45 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2025-01-29 21:25 | 2025-01-31 10:12 | 46334.0289 | [6 empty] | 46334 | 32447 | 3.24 | 0 | 0 | 14.19 | 5179
DRE1 | RS\44\004\D | RS | 44 | 4 | D | 6 DL | 100 | 100 | 100 | 2025-01-30 15:36 | 2025-02-03 10:58 | 319134.9003 |  |  |  | 16408 | 319135 | 257058 |  |  | 0 | 27.34 | 0 | 5.78 | 5912.8
PH4100A | SC\41\011\D | SC | 41 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-01-31 04:30 | 2025-02-07 07:37 | 285931.7919 | 285932 | [7 empty] | 0 | 0 | 24.49 | 7.57 | 5747.47
TS5500Exc | SC\39\015\D | SC | 39 | 15 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-01-31 10:12 | 2025-02-02 19:07 | 71680.1388 | [6 empty] | 71680 | 53691 | 3.94 | 0 | 0 | 7.39 | 5759
DRE2 | GG\19\003\D | GG | 19 | 3 | D | 6 DL | 100 | 100 | 100 | 2025-02-01 02:13 | 2025-02-04 06:24 | 256213.5485 |  |  |  | 4199 | 256214 | 73716 |  |  | 0 | 19.39 | 0 | 6.57 | 5808.19
PH4100XPC#1 | GG\22\022\B | GG | 22 | 22 | B | 1 Prestrip - Thick | 100 | 43.6454 | 43.6454 | 2025-02-01 19:24 | 2025-02-03 11:16 | 91050.7379 | 91051 | [7 empty] | 0 | 0 | 10.57 | 20.5 | 4725.37
TS5500Shv | RS\43\006\D | RS | 43 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2025-02-02 16:26 | 2025-02-03 17:24 | 26763.6996 |  |  | 26764 | [5 empty] | 0 | 0 | 0 | 5.94 | 5894.53
TS5500Exc | RS\45\002\B | RS | 45 | 2 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-02-02 19:07 | 2025-02-03 01:12 | 7670.3484 | [6 empty] | 7670 | 5531 | 1.48 | 0 | 0 | 9.2 | 5575
TS6060#1 | RS\45\003\B | RS | 45 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-02-02 23:28 | 2025-02-04 01:15 | 26598.0245 | 26598 | [7 empty] | 0 | 0 | 2.66 | 9.16 | 5585.84
TS5500Exc | GG\23\013\X1 | GG | 23 | 13 | X1 | 1 Prestrip - Thick | 10.4123 | 10.4123 | 10.4123 | 2025-02-03 01:12 | 2025-02-04 23:01 | 40603.8029 | 40604 | [7 empty] | 0 | 0 | 4.07 | 14.64 | 5127.81
DRE1 | SC\39\012\D | SC | 39 | 12 | D | 6 DL | 100 | 0 | 100 | 2025-02-03 10:58 | 2025-02-11 00:22 | 633634.0761 |  |  |  | 48185 | 633634 | 433666 |  |  | 0 | 40 | 0 | 7.49 | 5754.39
PH4100XPC#1 | GG\22\023\B | GG | 22 | 23 | B | 1 Prestrip - Thick | 100 | 55.8317 | 55.8317 | 2025-02-03 11:16 | 2025-02-07 01:14 | 204156.1818 | 204156 | [7 empty] | 0 | 0 | 29.34 | 0 | 0
TS5500Shv | MW\54\007\D | MW | 54 | 7 | D | 8 Coal Mining | 48 | 0 | 48 | 2025-02-03 17:24 | 2025-02-04 09:53 | 20111.2962 | [6 empty] | 20111 | 15160 | 2.3 | 0 | 0 | 6.67 | 5828
TS6060#1 | RS\45\004\B | RS | 45 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-02-04 01:15 | 2025-02-05 03:17 | 26853.4271 | 26853 | [7 empty] | 0 | 0 | 2.68 | 9.12 | 5602.75
DRE2 | GG\20\013\B | GG | 20 | 13 | B | 6 DL | 100 | 0 | 100 | 2025-02-04 06:24 | 2025-02-06 15:21 | 191591.2523 |  |  |  |  | 191591 | 159659 |  |  | 0 | 16.03 | 0 | 11.3 | 5400.04
TS5500Shv | MW\55\007\B | MW | 55 | 7 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-02-04 09:53 | 2025-02-04 19:35 | 11828.0675 | [6 empty] | 11828 | 8736 | 1.23 | 0 | 0 | 9.48 | 5555
TS5500Shv | MW\56\006\D | MW | 56 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-02-04 19:35 | 2025-02-05 21:00 | 31000.739 | [6 empty] | 31001 | 23148 | 2.24 | 0 | 0 | 8.05 | 5706
TS5500Exc | RS\43\006\D | RS | 43 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-02-04 23:01 | 2025-02-06 01:21 | 33159.6767 | [6 empty] | 33160 | 24499 | 4.62 | 0 | 0 | 5.94 | 5895
TS6060#1 | RS\47\005\A | RS | 47 | 5 | A | 1 Prestrip - Thick | 31.9075 | 31.9075 | 31.9075 | 2025-02-05 03:17 | 2025-02-11 08:41 | 150443.8709 | 150444 | [7 empty] | 0 | 0 | 14.38 | 16.2 | 5019.99
TS5500Shv | MW\57\006\D | MW | 57 | 6 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-02-05 21:00 | 2025-02-06 08:53 | 14489.3332 | [6 empty] | 14489 | 10785 | 2.18 | 0 | 0 | 8.49 | 5668
TS5500Exc | RS\45\003\B | RS | 45 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-02-06 01:21 | 2025-02-06 17:09 | 19910.4376 | [6 empty] | 19910 | 14324 | 1.43 | 0 | 0 | 9.16 | 5586
TS5500Shv | GG\19\010\D | GG | 19 | 10 | D | 8 Coal Mining | 3.7 | 0 | 3.7 | 2025-02-06 08:53 | 2025-02-06 10:45 | 2261.3722 | [6 empty] | 2261 | 1693 | 0.17 | 0 | 0 | 6.35 | 5828
TS5500Shv | GG\19\011\D | GG | 19 | 11 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-02-06 10:45 | 2025-02-07 10:06 | 28482.5374 | [6 empty] | 28483 | 21309 | 2.13 | 0 | 0 | 6.5 | 5814
DRE2 | GG\20\014\B | GG | 20 | 14 | B | 6 DL | 100 | 0 | 100 | 2025-02-06 15:21 | 2025-02-08 06:59 | 133292.3685 |  |  |  |  | 133292 | 111077 |  |  | 0 | 15.94 | 0 | 11.98 | 5344.17
TS5500Exc | RS\44\004\D | RS | 44 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-02-06 17:09 | 2025-02-07 17:45 | 30995.957 | [6 empty] | 30996 | 22940 | 2.29 | 0 | 0 | 5.78 | 5913
TS Fleet 5 | GG\23\010\X1 | GG | 23 | 10 | X1 | 1 Prestrip - Thick | 45.5243 | 45.5243 | 45.5243 | 2025-02-07 00:31 | 2025-02-13 11:30 | 290745.4322 | 290745 | [7 empty] | 0 | 0 | 29.36 | 15.11 | 5086.16
PH4100XPC#1 | GG\23\007\X1 | GG | 23 | 7 | X1 | 1 Prestrip - Thick | 100 | 10.0443 | 10.0443 | 2025-02-07 01:14 | 2025-02-08 14:41 | 83305.0518 | 83305 | [7 empty] | 0 | 0 | 8.11 | 12.17 | 5258.43
PH4100A | SC\40\012\D | SC | 40 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-02-07 07:37 | 2025-02-10 08:20 | 119979.8752 | 119980 | [7 empty] | 0 | 0 | 10.22 | 7.47 | 5755.83
TS5500Shv | GG\19\012\D | GG | 19 | 12 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-02-07 10:06 | 2025-02-08 09:55 | 29032.1816 | [6 empty] | 29032 | 21687 | 2.17 | 0 | 0 | 6.77 | 5791
TS5500Exc | RS\45\004\B | RS | 45 | 4 | B | 8 Coal Mining | 70.3 | 0 | 70.3 | 2025-02-07 17:45 | 2025-02-08 16:00 | 28017.4596 | [6 empty] | 28017 | 20101 | 2.01 | 0 | 0 | 9.12 | 5603
DRE2 | GG\20\018\B | GG | 20 | 18 | B | 6 DL | 100 | 0 | 100 | 2025-02-08 06:59 | 2025-02-10 16:49 | 194563.5949 |  |  |  |  | 194564 | 162136 |  |  | 0 | 16.21 | 0 | 11.85 | 5362.79
TS5500Shv | GG\19\009\D | GG | 19 | 9 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-02-08 09:55 | 2025-02-09 09:50 | 29176.5109 | [6 empty] | 29177 | 21812 | 2.18 | 0 | 0 | 6.43 | 5822
PH4100XPC#1 | GG\23\008\X1 | GG | 23 | 8 | X1 | 1 Prestrip - Thick | 100 | 36.8834 | 36.8834 | 2025-02-08 14:41 | 2025-02-13 23:38 | 288728.1975 | 288728 | [7 empty] | 0 | 0 | 28.78 | 13.18 | 5209.43
TS5500Exc | GG\23\018\X2 | GG | 23 | 18 | X2 | 1 Prestrip - Thick | 11.9184 | 0 | 11.9184 | 2025-02-08 16:00 | 2025-02-09 22:50 | 27334.8418 | 27335 | [7 empty] | 0 | 0 | 2.83 | 0 | 0
TS5500Shv | GG\20\004\B | GG | 20 | 4 | B | 8 Coal Mining | 29.8 | 0 | 29.8 | 2025-02-09 09:50 | 2025-02-10 06:27 | 25142.6906 | [6 empty] | 25143 | 18520 | 1.15 | 0 | 0 | 9.39 | 5518
TS5500Exc | RS\45\005\X | RS | 45 | 5 | X | 8 Coal Mining | 60.6 | 0 | 60.6 | 2025-02-09 22:50 | 2025-02-10 11:14 | 15612.5741 | [6 empty] | 15613 | 11168 | 0.79 | 0 | 0 | 10.35 | 5445
TS5500Shv | GG\20\005\B | GG | 20 | 5 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-02-10 06:27 | 2025-02-11 00:23 | 21853.4466 | [6 empty] | 21853 | 16136 | 1.61 | 0 | 0 | 9.02 | 5529
PH4100A | SC\41\012\D | SC | 41 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-02-10 08:20 | 2025-02-15 15:52 | 212799.1668 | 212799 | [7 empty] | 0 | 0 | 18.16 | 7.46 | 5756.51
TS5500Exc | GG\23\019\B | GG | 23 | 19 | B | 1 Prestrip - Thick | 16.4089 | 16.4089 | 16.4089 | 2025-02-10 11:14 | 2025-02-12 18:13 | 48671.9012 | 48672 | [7 empty] | 0 | 0 | 4.93 | 13.32 | 5263.07
DRE2 | GG\20\019\B | GG | 20 | 19 | B | 6 DL | 100 | 0 | 100 | 2025-02-10 16:49 | 2025-02-13 06:45 | 208324.5646 |  |  |  |  | 208325 | 173604 |  |  | 0 | 17.42 | 0 | 12.63 | 5319.92
DRE1 | MW\55\007\D | MW | 55 | 7 | D | 6 DL | 100 | 100 | 100 | 2025-02-11 00:22 | 2025-02-12 21:25 | 157380.9837 |  |  |  | 8092 | 157381 | 126768 |  |  | 0 | 29.5 | 0 | 6.89 | 5808.01
TS5500Shv | GG\20\006\B | GG | 20 | 6 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-02-11 00:23 | 2025-02-11 19:25 | 23223.4475 | [6 empty] | 23223 | 17058 | 1.7 | 0 | 0 | 9.83 | 5475
TS6060#1 | GG\23\007\X1 | GG | 23 | 7 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-02-11 08:41 | 2025-02-11 15:07 | 8705.579 | [6 empty] | 8706 | 6371 | 0.64 | 0 | 0 | 12.17 | 5258
TS6060#1 | RS\48\002\A | RS | 48 | 2 | A | 1 Prestrip - Thick | 22.817 | 22.817 | 22.817 | 2025-02-11 15:07 | 2025-02-12 20:21 | 29771.7387 | 29772 | [7 empty] | 0 | 0 | 6.38 | 11.74 | 5399.18
TS5500Shv | GG\20\007\B | GG | 20 | 7 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-02-11 19:25 | 2025-02-12 15:24 | 24357.8105 | [6 empty] | 24358 | 17825 | 1.78 | 0 | 0 | 10.32 | 5458
TS5500Shv | GG\19\008\D | GG | 19 | 8 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-02-12 15:24 | 2025-02-13 15:22 | 29222.1284 | [6 empty] | 29222 | 21829 | 2.18 | 0 | 0 | 6.51 | 5814
TS5500Exc | SC\39\014\D | SC | 39 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-02-12 18:13 | 2025-02-14 23:20 | 66903.0789 | [6 empty] | 66903 | 50076 | 4.17 | 0 | 0 | 7.63 | 5740
TS6060#1 | RS\48\003\A | RS | 48 | 3 | A | 1 Prestrip - Thick | 27.8162 | 27.8162 | 27.8162 | 2025-02-12 20:21 | 2025-02-16 08:50 | 84697.5891 | 84698 | [7 empty] | 0 | 0 | 8.75 | 12.54 | 5327.57
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2025-02-12 21:25 | 2025-02-15 21:25
DRE2 | GG\20\020\B | GG | 20 | 20 | B | 6 DL | 100 | 0 | 100 | 2025-02-13 06:45 | 2025-02-17 12:15 | 341427.2448 |  |  |  |  | 341427 | 262636 |  |  | 0 | 23.87 | 0 | 15.57 | 5101.72
TS Fleet 5 | GG\23\011\X1 | GG | 23 | 11 | X1 | 1 Prestrip - Thick | 45.7686 | 45.7686 | 45.7686 | 2025-02-13 11:30 | 2025-02-19 08:05 | 263731.2151 | 263731 | [7 empty] | 0 | 0 | 25.58 | 14.95 | 5103.27
TS5500Shv | MW\55\007\D | MW | 55 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-02-13 15:22 | 2025-02-14 14:30 | 28210.0352 | [6 empty] | 28210 | 21230 | 4.75 | 0 | 0 | 6.89 | 5808
PH4100XPC#1 | GG\23\009\X2 | GG | 23 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 55.17 | 2025-02-13 23:38 | 2025-02-22 05:30 | 458648.4826 | 458648 | [7 empty] | 0 | 0 | 46.37 | 0 | 0
TS5500Shv | GG\20\010\B | GG | 20 | 10 | B | 8 Coal Mining | 24.2 | 0 | 24.2 | 2025-02-14 14:30 | 2025-02-15 00:23 | 12051.8467 | [6 empty] | 12052 | 8848 | 0.88 | 0 | 0 | 9.84 | 5537
TS5500Exc | GG\23\020\B | GG | 23 | 20 | B | 1 Prestrip - Thick | 1.8901 | 1.8901 | 1.8901 | 2025-02-14 23:20 | 2025-02-15 05:45 | 5680.1378 | 5680 | [7 empty] | 0 | 0 | 0.57 | 16.2 | 5049.99
TS5500Shv | GG\23\004\X1 | GG | 23 | 4 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-02-15 00:23 | 2025-02-15 06:59 | 8058.563 | [6 empty] | 8059 | 5981 | 0.49 | 0 | 0 | 10.83 | 5290
TS5500Exc | GG\23\021\D | GG | 23 | 21 | D | 1 Prestrip - Thick | 14.2746 | 14.2746 | 14.2746 | 2025-02-15 05:45 | 2025-02-16 14:31 | 28968.087 | 28968 | [7 empty] | 0 | 0 | 2.95 | 6.8 | 5789.61
TS5500Shv | GG\23\005\X1 | GG | 23 | 5 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-02-15 06:59 | 2025-02-15 13:01 | 7352.0839 | [6 empty] | 7352 | 5461 | 0.54 | 0 | 0 | 10.75 | 5300
TS5500Shv | GG\23\006\X1 | GG | 23 | 6 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-02-15 13:01 | 2025-02-15 19:07 | 7430.6528 | [6 empty] | 7431 | 5489 | 0.55 | 0 | 0 | 11.32 | 5286
PH4100A | SC\40\013\D | SC | 40 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-02-15 15:52 | 2025-02-19 03:17 | 136933.0697 | 136933 | [7 empty] | 0 | 0 | 11.52 | 7.52 | 5750.14
TS5500Shv | GG\23\007\X1 | GG | 23 | 7 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-02-15 19:07 | 2025-02-16 01:33 | 7843.6405 | [6 empty] | 7844 | 5740 | 0.57 | 0 | 0 | 12.17 | 5258
DRE1 | SC\39\011\D | SC | 39 | 11 | D | 6 DL | 100 | 0 | 100 | 2025-02-15 21:25 | 2025-02-23 09:55 | 630516.2626 |  |  |  | 47948 | 630516 | 431532 |  |  | 0 | 40 | 0 | 7.6 | 5745.81
TS5500Shv | GG\23\008\X1 | GG | 23 | 8 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-02-16 01:33 | 2025-02-16 08:25 | 8369.0913 | [6 empty] | 8369 | 6069 | 0.61 | 0 | 0 | 13.18 | 5209
TS5500Shv | RS\44\005\X | RS | 44 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2025-02-16 08:25 | 2025-02-17 08:06 | 28894.3242 | [6 empty] | 28894 | 20683 | 1.32 | 0 | 0 | 10.28 | 5452
TS6060#1 | GG\23\008\X1 | GG | 23 | 8 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-02-16 08:50 | 2025-02-16 15:42 | 9288.7717 | [6 empty] | 9289 | 6735 | 0.67 | 0 | 0 | 13.18 | 5209
TS5500Exc | GG\23\007\B | GG | 23 | 7 | B | 1 Prestrip - Thick | 10.5085 | 10.5085 | 10.5085 | 2025-02-16 14:31 | 2025-02-17 08:38 | 16025.9829 | 16026 | [7 empty] | 0 | 0 | 1.6 | 10.37 | 5460.57
TS6060#1 | GG\20\019\B | GG | 20 | 19 | B | 8 Coal Mining | 2.3 | 0 | 2.3 | 2025-02-16 15:42 | 2025-02-16 16:35 | 1196.6187 | [6 empty] | 1197 | 864 | 0.09 | 0 | 0 | 12.63 | 5320
TS6060#1 | RS\48\004\A | RS | 48 | 4 | A | 1 Prestrip - Thick | 22.9396 | 22.9396 | 22.9396 | 2025-02-16 16:35 | 2025-02-20 08:56 | 88266.3586 | 88266 | [7 empty] | 0 | 0 | 9 | 14.86 | 5128.69
TS5500Shv | GG\19\007\D | GG | 19 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-02-17 08:06 | 2025-02-19 10:19 | 61221.7749 | [6 empty] | 61222 | 45768 | 4.58 | 0 | 0 | 6.59 | 5807
TS5500Exc | GG\23\008\X2 | GG | 23 | 8 | X2 | 1 Prestrip - Thick | 14.4901 | 0 | 14.4901 | 2025-02-17 08:38 | 2025-02-17 21:42 | 11565.2311 | 11565 | [7 empty] | 0 | 0 | 1.16 | 0 | 0
DRE2 | GG\20\021\B | GG | 20 | 21 | B | 6 DL | 100 | 0 | 100 | 2025-02-17 12:15 | 2025-02-20 20:35 | 270200.4827 |  |  |  |  | 270200 | 207847 |  |  | 0 | 23.32 | 0 | 18.66 | 4881.61
TS5500Exc | GG\23\022\B | GG | 23 | 22 | B | 1 Prestrip - Thick | 17.4112 | 17.4112 | 17.4112 | 2025-02-17 21:42 | 2025-02-19 17:46 | 38977.7152 | 38978 | [7 empty] | 0 | 0 | 4.71 | 19.72 | 4784.01
PH4100A | RS\44\005\A | RS | 44 | 5 | A | 1 Prestrip - Thick | 100 | 73.2022 | 73.2022 | 2025-02-19 03:17 | 2025-02-24 08:14 | 207599.5439 | 207600 | [7 empty] | 0 | 0 | 13.95 | 14.96 | 5120.01
TS Fleet 5 | GG\23\004\B | GG | 23 | 4 | B | 1 Prestrip - Thick | 45.419 | 45.419 | 45.419 | 2025-02-19 08:05 | 2025-02-20 17:08 | 61983.9899 | 61984 | [7 empty] | 0 | 0 | 5.35 | 9.42 | 5516.42
TS5500Shv | GG\23\007\B | GG | 23 | 7 | B | 1 Prestrip - Thick | 13.2522 | 13.2522 | 13.2522 | 2025-02-19 10:19 | 2025-02-20 05:10 | 20210.1508 | 20210 | [7 empty] | 0 | 0 | 2.02 | 10.37 | 5460.57
TS5500Exc | SC\39\013\D | SC | 39 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-02-19 17:46 | 2025-02-22 02:14 | 71126.0245 | [6 empty] | 71126 | 53113 | 4.42 | 0 | 0 | 7.59 | 5745
TS5500Shv | GG\23\008\X2 | GG | 23 | 8 | X2 | 1 Prestrip - Thick | 17.5637 | 0 | 17.5637 | 2025-02-20 05:10 | 2025-02-20 18:14 | 14018.4619 | 14018 | [7 empty] | 0 | 0 | 1.4 | 0 | 0
TS6060#1 | RS\44\005\A | RS | 44 | 5 | A | 1 Prestrip - Thick | 26.7978 | 26.7978 | 26.7978 | 2025-02-20 08:56 | 2025-02-23 10:35 | 75997.8535 | 75998 | [7 empty] | 0 | 0 | 5.11 | 14.96 | 5120.01
TS Fleet 5 | GG\23\005\B | GG | 23 | 5 | B | 1 Prestrip - Thick | 45.419 | 45.419 | 45.419 | 2025-02-20 17:08 | 2025-02-22 01:45 | 61198.1294 | 61198 | [7 empty] | 0 | 0 | 6.14 | 9.59 | 5496
TS5500Shv | GG\19\006\D | GG | 19 | 6 | D | 8 Coal Mining | 66.3 | 0 | 66.3 | 2025-02-20 18:14 | 2025-02-22 03:15 | 40251.3505 | [6 empty] | 40251 | 30115 | 3.01 | 0 | 0 | 6.65 | 5802
DRE2 | GG\20\022\B | GG | 20 | 22 | B | 6 DL | 100 | 0 | 100 | 2025-02-20 20:35 | 2025-02-24 05:18 | 271541.2916 |  |  |  |  | 271541 | 208878 |  |  | 0 | 22.21 | 0 | 20.19 | 4757.18
TS Fleet 5 | GG\23\006\B | GG | 23 | 6 | B | 1 Prestrip - Thick | 45.419 | 45.419 | 45.419 | 2025-02-22 01:45 | 2025-02-23 14:23 | 68729.9565 | 68730 | [7 empty] | 0 | 0 | 6.89 | 10.2 | 5457.56
TS5500Exc | RS\46\003\A | RS | 46 | 3 | A | 1 Prestrip - Thick | 8.4613 | 8.4613 | 8.4613 | 2025-02-22 02:14 | 2025-02-23 14:13 | 31922.0402 | 31922 | [7 empty] | 0 | 0 | 3.29 | 12.29 | 5343.44
TS5500Shv | RS\45\002\B | RS | 45 | 2 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-02-22 03:15 | 2025-02-22 09:20 | 7425.55 | [6 empty] | 7426 | 5355 | 1.43 | 0 | 0 | 9.2 | 5575
PH4100XPC#1 | GG\23\004\B | GG | 23 | 4 | B | 1 Prestrip - Thick | 100 | 54.581 | 54.581 | 2025-02-22 05:30 | 2025-02-23 14:24 | 74487.6077 | 74488 | [7 empty] | 0 | 0 | 6.43 | 9.42 | 5516.42
TS5500Shv | RS\45\003\B | RS | 45 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-02-22 09:20 | 2025-02-23 01:09 | 19274.9981 | [6 empty] | 19275 | 13867 | 1.38 | 0 | 0 | 9.16 | 5586
TS5500Shv | RS\44\004\D | RS | 44 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-02-23 01:09 | 2025-02-24 01:45 | 30006.7243 | [6 empty] | 30007 | 22208 | 2.22 | 0 | 0 | 5.78 | 5913
DRE1 | RS\45\002\D | RS | 45 | 2 | D | 6 DL | 100 | 100 | 100 | 2025-02-23 09:55 | 2025-02-25 21:26 | 207867.6884 |  |  |  | 10687 | 207868 | 167434 |  |  | 0 | 27.73 | 0 | 5.43 | 5942.35
TS6060#1 | GG\20\020\B | GG | 20 | 20 | B | 8 Coal Mining | 6.6 | 0 | 6.6 | 2025-02-23 10:35 | 2025-02-23 11:49 | 1663.0571 | [6 empty] | 1663 | 1180 | 0.12 | 0 | 0 | 15.57 | 5102
TS6060#1 | RS\48\005\A | RS | 48 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-02-23 11:49 | 2025-03-10 21:56 | 371830.6491 | 371831 | [7 empty] | 0 | 0 | 42.68 | 15.7 | 5063.42
TS5500Exc | RS\46\003\A | RS | 46 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-02-23 14:13 | 2025-02-24 08:53 | 23510.069 | [6 empty] | 23510 | 16673 | 1.67 | 0 | 0 | 12.29 | 5343
TS Fleet 5 | GG\23\009\B | GG | 23 | 9 | B | 1 Prestrip - Thick | 45.419 | 45.419 | 45.419 | 2025-02-23 14:23 | 2025-02-24 09:53 | 36567.3732 | 36567 | [7 empty] | 0 | 0 | 3.66 | 10.09 | 5517.13
PH4100XPC#1 | GG\23\005\B | GG | 23 | 5 | B | 1 Prestrip - Thick | 100 | 54.581 | 54.581 | 2025-02-23 14:24 | 2025-02-24 22:54 | 73543.2208 | 73543 | [7 empty] | 0 | 0 | 7.38 | 9.59 | 5496
TS5500Shv | GG\19\005\D | GG | 19 | 5 | D | 8 Coal Mining | 41.2 | 0 | 41.2 | 2025-02-24 01:45 | 2025-02-24 22:12 | 24934.5974 | [6 empty] | 24935 | 18670 | 1.87 | 0 | 0 | 6.67 | 5799
DRE2 | GG\20\023\B | GG | 20 | 23 | B | 6 DL | 100 | 0 | 100 | 2025-02-24 05:18 | 2025-02-28 05:50 | 324670.7049 |  |  |  |  | 324671 | 249747 |  |  | 0 | 24.42 | 0 | 0 | 0
PH4100A | SC\41\013\D | SC | 41 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-02-24 08:14 | 2025-03-01 02:25 | 188385.4891 | 188385 | [7 empty] | 0 | 0 | 15.81 | 7.47 | 5753.2
TS5500Exc | RS\44\005\A | RS | 44 | 5 | A | 8 Coal Mining | 41.3 | 0 | 41.3 | 2025-02-24 08:53 | 2025-02-25 07:47 | 28859.5488 | [6 empty] | 28860 | 20130 | 1.36 | 0 | 0 | 14.96 | 5120
TS Fleet 5 | GG\23\007\B | GG | 23 | 7 | B | 1 Prestrip - Thick | 34.6271 | 34.6271 | 34.6271 | 2025-02-24 09:53 | 2025-02-25 14:02 | 52807.8898 | 52808 | [7 empty] | 0 | 0 | 5.28 | 10.37 | 5460.57
TS5500Shv | RS\44\005\A | RS | 44 | 5 | A | 8 Coal Mining | 58.7 | 0 | 58.7 | 2025-02-24 22:12 | 2025-02-26 07:47 | 40953.609 | [6 empty] | 40954 | 28566 | 1.93 | 0 | 0 | 14.96 | 5120
PH4100XPC#1 | GG\23\006\B | GG | 23 | 6 | B | 1 Prestrip - Thick | 100 | 54.581 | 54.581 | 2025-02-24 22:54 | 2025-02-26 11:23 | 82594.3932 | 82594 | [7 empty] | 0 | 0 | 8.27 | 10.2 | 5457.56
TS5500Exc | SC\39\012\D | SC | 39 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-02-25 07:47 | 2025-02-27 18:59 | 74559.9238 | [6 empty] | 74560 | 55547 | 4.63 | 0 | 0 | 7.49 | 5754
TS Fleet 5 | GG\23\008\X2 | GG | 23 | 8 | X2 | 1 Prestrip - Thick | 30.8604 | 0 | 30.8604 | 2025-02-25 14:02 | 2025-02-26 03:09 | 24631.1914 | 24631 | [7 empty] | 0 | 0 | 2.46 | 0 | 0
DRE1 | RS\45\003\D | RS | 45 | 3 | D | 6 DL | 100 | 100 | 100 | 2025-02-25 21:26 | 2025-03-01 19:59 | 330310.2633 |  |  |  | 16983 | 330310 | 266060 |  |  | 0 | 28.3 | 0 | 5.57 | 5931.39
TS Fleet 5 | GG\23\012\X1 | GG | 23 | 12 | X1 | 1 Prestrip - Thick | 45.9366 | 45.9366 | 45.9366 | 2025-02-26 03:09 | 2025-03-03 05:57 | 230373.8103 | 230374 | [7 empty] | 0 | 0 | 22.33 | 14.86 | 5110.9
TS5500Shv | RS\45\002\D | RS | 45 | 2 | D | 8 Coal Mining | 17.5 | 0 | 17.5 | 2025-02-26 07:47 | 2025-02-26 13:31 | 6985.4625 | [6 empty] | 6985 | 5218 | 0.8 | 0 | 0 | 5.43 | 5942
PH4100XPC#1 | GG\23\007\B | GG | 23 | 7 | B | 1 Prestrip - Thick | 100 | 41.6122 | 41.6122 | 2025-02-26 11:23 | 2025-02-27 15:25 | 63460.474 | 63460 | [7 empty] | 0 | 0 | 6.34 | 10.37 | 5460.57
TS5500Shv | RS\45\004\B | RS | 45 | 4 | B | 8 Coal Mining | 29.7 | 0 | 29.7 | 2025-02-26 13:31 | 2025-02-26 23:13 | 11827.414 | [6 empty] | 11827 | 8486 | 0.85 | 0 | 0 | 9.12 | 5603
TS5500Shv | GG\19\004\D | GG | 19 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-02-26 23:13 | 2025-03-01 00:24 | 59975.1465 | [6 empty] | 59975 | 44942 | 4.49 | 0 | 0 | 6.64 | 5802
PH4100XPC#1 | GG\23\008\X2 | GG | 23 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 37.0857 | 2025-02-27 15:25 | 2025-02-28 04:30 | 29599.8777 | 29600 | [7 empty] | 0 | 0 | 2.96 | 0 | 0
TS5500Exc | RS\45\002\D | RS | 45 | 2 | D | 8 Coal Mining | 100 | 0 | 82.5 | 2025-02-27 18:59 | 2025-02-28 21:10 | 32972.3695 | [6 empty] | 32972 | 24628 | 3.79 | 0 | 0 | 5.43 | 5942
PH4100XPC#1 | GG\23\008\B | GG | 23 | 8 | B | 1 Prestrip - Thick | 100 | 81.627 | 81.627 | 2025-02-28 04:30 | 2025-03-01 05:26 | 56436.397 | 56436 | [7 empty] | 0 | 0 | 5.64 | 10.21 | 5492.53
DRE2 | GG\19\013\D | GG | 19 | 13 | D | 6 DL | 100 | 100 | 100 | 2025-02-28 05:50 | 2025-03-09 11:30 | 745681.0426 |  |  |  | 17362 | 745681 | 329871 |  |  | 0 | 24.18 | 0 | 7.13 | 5762.02
TS5500Exc | GG\23\008\B | GG | 23 | 8 | B | 1 Prestrip - Thick | 14.4901 | 10.5761 | 10.5761 | 2025-02-28 21:10 | 2025-03-01 05:26 | 7312.2219 | 7312 | [7 empty] | 0 | 0 | 0.73 | 10.21 | 5492.53
TS5500Shv | GG\23\008\B | GG | 23 | 8 | B | 1 Prestrip - Thick | 17.5637 | 7.7969 | 7.7969 | 2025-03-01 00:24 | 2025-03-01 05:26 | 5390.719 | 5391 | [7 empty] | 0 | 0 | 0.54 | 10.21 | 5492.53
PH4100A | RS\44\005\B | RS | 44 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-03-01 02:25 | 2025-03-02 01:42 | 38679.2185 | 38679 | [7 empty] | 0 | 0 | 2.62 | 9.03 | 5620.64
PH4100XPC#1 | GG\23\009\B | GG | 23 | 9 | B | 1 Prestrip - Thick | 100 | 54.581 | 54.581 | 2025-03-01 05:26 | 2025-03-02 00:50 | 43943.8661 | 43944 | [7 empty] | 0 | 0 | 4.39 | 10.09 | 5517.13
TS5500Exc | MW\60\004\D | MW | 60 | 4 | D | 8 Coal Mining | 47.9 | 0 | 47.9 | 2025-03-01 05:26 | 2025-03-02 03:37 | 27946.7555 | [6 empty] | 27947 | 20772 | 1.78 | 0 | 0 | 8.7 | 5644
TS5500Shv | GG\19\003\D | GG | 19 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2025-03-01 05:26 | 2025-03-02 06:40 | 27064.6302 |  |  | 27065 | [5 empty] | 0 | 0 | 0 | 6.57 | 5808.19
DRE1 | RS\45\004\D | RS | 45 | 4 | D | 6 DL | 100 | 100 | 100 | 2025-03-01 19:59 | 2025-03-05 16:08 | 321903.4526 |  |  |  | 16550 | 321903 | 259288 |  |  | 0 | 27.58 | 0 | 5.83 | 5908.18
PH4100XPC#1 | GG\23\010\X1 | GG | 23 | 10 | X1 | 1 Prestrip - Thick | 100 | 54.4757 | 54.4757 | 2025-03-02 00:50 | 2025-03-08 11:12 | 347914.312 | 347914 | [7 empty] | 0 | 0 | 35.14 | 15.11 | 5086.16
PH4100A | SC\40\014\D | SC | 40 | 14 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-03-02 01:42 | 2025-03-05 20:56 | 149489.2543 | 149489 | [7 empty] | 0 | 0 | 12.54 | 7.59 | 5742.6
TS5500Exc | RS\44\005\B | RS | 44 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-03-02 03:37 | 2025-03-03 03:50 | 30501.5547 | [6 empty] | 30502 | 21918 | 1.49 | 0 | 0 | 9.03 | 5621
TS5500Shv | RS\44\005\B | RS | 44 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-03-02 06:40 | 2025-03-03 06:53 | 29528.1008 | [6 empty] | 29528 | 21218 | 1.44 | 0 | 0 | 9.03 | 5621
TS5500Exc | RS\45\003\D | RS | 45 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-03-03 03:50 | 2025-03-05 02:44 | 59084.7439 | [6 empty] | 59085 | 43932 | 4.39 | 0 | 0 | 5.57 | 5931
TS Fleet 5 | GG\23\013\X1 | GG | 23 | 13 | X1 | 1 Prestrip - Thick | 41.4035 | 41.4035 | 41.4035 | 2025-03-03 05:57 | 2025-03-06 20:01 | 161457.7954 | 161458 | [7 empty] | 0 | 0 | 16.17 | 14.64 | 5127.81
TS5500Shv | GG\19\003\D | GG | 19 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-03-03 06:53 | 2025-03-04 09:10 | 32049.2984 | [6 empty] | 32049 | 24016 | 4.51 | 0 | 0 | 6.57 | 5808
TS5500Shv | GG\20\013\B | GG | 20 | 13 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-03-04 09:10 | 2025-03-06 01:05 | 48667.4109 | [6 empty] | 48667 | 35471 | 3.56 | 0 | 0 | 11.3 | 5400
TS5500Exc | RS\46\004\A | RS | 46 | 4 | A | 8 Coal Mining | 74.9 | 0 | 74.9 | 2025-03-05 02:44 | 2025-03-06 06:24 | 34850.0291 | [6 empty] | 34850 | 24360 | 2.43 | 0 | 0 | 14.53 | 5153
DRE1 | RS\44\005\D | RS | 44 | 5 | D | 6 DL | 100 | 100 | 100 | 2025-03-05 16:08 | 2025-03-11 11:20 | 486211.1731 |  |  |  | 18142 | 486211 | 275839 |  |  | 0 | 26.35 | 0 | 5.94 | 5897.59
PH4100A | SC\41\014\D | SC | 41 | 14 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-03-05 20:56 | 2025-03-10 16:36 | 190844.8242 | 190845 | [7 empty] | 0 | 0 | 16.14 | 7.55 | 5745.59
TS5500Shv | GG\20\014\B | GG | 20 | 14 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-03-06 01:05 | 2025-03-07 04:07 | 32969.8873 | [6 empty] | 32970 | 23937 | 3.55 | 0 | 0 | 11.98 | 5344
TS5500Exc | RS\45\004\D | RS | 45 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-03-06 06:24 | 2025-03-08 06:34 | 60670.3643 | [6 empty] | 60670 | 44866 | 4.49 | 0 | 0 | 5.83 | 5908
TS Fleet 5 | GG\23\014\X1 | GG | 23 | 14 | X1 | 1 Prestrip - Thick | 46.6872 | 46.6872 | 46.6872 | 2025-03-06 20:01 | 2025-03-10 14:21 | 169457.5152 | 169458 | [7 empty] | 0 | 0 | 12.98 | 14.38 | 5147.61
TS5500Shv | GG\20\018\B | GG | 20 | 18 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-03-07 04:07 | 2025-03-08 21:04 | 49938.0734 | [6 empty] | 49938 | 36259 | 3.63 | 0 | 0 | 11.85 | 5363
TS5500Exc | RS\46\004\B | RS | 46 | 4 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2025-03-08 06:34 | 2025-03-08 20:08 | 11987.3736 | 11987 | [7 empty] | 0 | 0 | 1.2 | 9.12 | 5603.77
PH4100XPC#1 | GG\23\011\X1 | GG | 23 | 11 | X1 | 1 Prestrip - Thick | 100 | 54.2314 | 54.2314 | 2025-03-08 11:12 | 2025-03-14 07:13 | 312495.8847 | 312496 | [7 empty] | 0 | 0 | 30.31 | 14.95 | 5103.27
TS5500Exc | RS\46\005\X | RS | 46 | 5 | X | 1 Prestrip - Thick | 10.4434 | 10.4434 | 10.4434 | 2025-03-08 20:08 | 2025-03-10 11:30 | 35020.2466 | 35020 | [7 empty] | 0 | 0 | 2.84 | 10.42 | 5438.39
TS5500Shv | GG\23\010\X1 | GG | 23 | 10 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-03-08 21:04 | 2025-03-09 10:31 | 16384.2759 | [6 empty] | 16384 | 11694 | 1.16 | 0 | 0 | 15.11 | 5086
TS5500Shv | GG\23\010\X2 | GG | 23 | 10 | X2 | 1 Prestrip - Thick | 20.54 | 0 | 20.54 | 2025-03-09 10:31 | 2025-03-09 23:44 | 14176.7161 | 14177 | [7 empty] | 0 | 0 | 1.42 | 0 | 0
DRE2 | GG\19\018\D | GG | 19 | 18 | D | 6 DL | 100 | 100 | 100 | 2025-03-09 11:30 | 2025-03-15 20:21 | 514151.1023 |  |  |  | 11971 | 514151 | 227448 |  |  | 0 | 23.96 | 0 | 7.21 | 5755.32
TS5500Shv | GG\20\019\B | GG | 20 | 19 | B | 8 Coal Mining | 97.7 | 0 | 97.7 | 2025-03-09 23:44 | 2025-03-11 17:49 | 51323.4317 | [6 empty] | 51323 | 37059 | 3.71 | 0 | 0 | 12.63 | 5320
TS5500Exc | RS\46\005\X | RS | 46 | 5 | X | 8 Coal Mining | 100 | 0 | 100 | 2025-03-10 11:30 | 2025-03-11 04:39 | 21595.1507 | [6 empty] | 21595 | 15431 | 1.25 | 0 | 0 | 10.42 | 5438
TS Fleet 5 | GG\23\010\X2 | GG | 23 | 10 | X2 | 1 Prestrip - Thick | 36.0899 | 0 | 36.0899 | 2025-03-10 14:21 | 2025-03-11 03:38 | 24909.2526 | 24909 | [7 empty] | 0 | 0 | 2.5 | 0 | 0
PH4100A | SC\40\015\D | SC | 40 | 15 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-03-10 16:36 | 2025-03-17 03:24 | 252604.7515 | 252605 | [7 empty] | 0 | 0 | 15.01 | 7.38 | 5759.35
TS6060#1 | GG\19\013\D | GG | 19 | 13 | D | 8 Coal Mining | 27 | 0 | 27 | 2025-03-10 21:56 | 2025-03-11 16:03 | 24510.2342 | [6 empty] | 24510 | 18252 | 1.28 | 0 | 0 | 7.13 | 5762
TS Fleet 5 | GG\23\018\X2 | GG | 23 | 18 | X2 | 1 Prestrip - Thick | 40.8499 | 0 | 40.8499 | 2025-03-11 03:38 | 2025-03-13 05:34 | 93689.3783 | 93689 | [7 empty] | 0 | 0 | 9.69 | 0 | 0
TS5500Exc | RS\47\002\A | RS | 47 | 2 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-03-11 04:39 | 2025-03-11 13:41 | 11373.825 | [6 empty] | 11374 | 8118 | 1.72 | 0 | 0 | 11.62 | 5407
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2025-03-11 11:20 | 2025-03-14 11:20
TS5500Exc | RS\44\005\D | RS | 44 | 5 | D | 7 PostStrip | 50.8285 | 0 | 50.8285 | 2025-03-11 13:41 | 2025-03-13 05:15 | 34997.5368 |  |  | 34998 | [5 empty] | 0 | 0 | 0 | 5.94 | 5897.59
TS6060#1 | RS\46\005\A | RS | 46 | 5 | A | 1 Prestrip - Thick | 21.7516 | 21.7516 | 21.7516 | 2025-03-11 16:03 | 2025-03-13 16:23 | 49879.094 | 49879 | [7 empty] | 0 | 0 | 4.23 | 16.24 | 5015.86
TS5500Shv | RS\44\005\D | RS | 44 | 5 | D | 7 PostStrip | 49.1715 | 0 | 49.1715 | 2025-03-11 17:49 | 2025-03-13 01:24 | 33856.5798 |  |  | 33857 | [5 empty] | 0 | 0 | 0 | 5.94 | 5897.59
TS5500Shv | RS\45\005\X | RS | 45 | 5 | X | 8 Coal Mining | 39.4 | 0 | 39.4 | 2025-03-13 01:24 | 2025-03-13 09:44 | 10146.4977 | [6 empty] | 10146 | 7258 | 0.51 | 0 | 0 | 10.35 | 5445
TS5500Exc | RS\44\005\D | RS | 44 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-03-13 05:15 | 2025-03-16 02:33 | 87294.4113 | [6 empty] | 87294 | 64439 | 4.7 | 0 | 0 | 5.94 | 5898
TS Fleet 5 | GG\23\019\B | GG | 23 | 19 | B | 1 Prestrip - Thick | 34.921 | 34.921 | 34.921 | 2025-03-13 05:34 | 2025-03-15 12:47 | 103582.1309 | 103582 | [7 empty] | 0 | 0 | 10.49 | 13.32 | 5263.07
TS5500Shv | GG\20\020\B | GG | 20 | 20 | B | 8 Coal Mining | 93.4 | 0 | 93.4 | 2025-03-13 09:44 | 2025-03-14 04:53 | 23366.1904 | [6 empty] | 23366 | 16575 | 1.64 | 0 | 0 | 15.57 | 5102
TS6060#1 | RS\45\005\A | RS | 45 | 5 | A | 1 Prestrip - Thick | 89.9777 | 89.9777 | 89.9777 | 2025-03-13 16:23 | 2025-03-23 00:15 | 230981.7202 | 230982 | [7 empty] | 0 | 0 | 17.32 | 15.75 | 5056.01
TS5500Shv | RS\46\002\A | RS | 46 | 2 | A | 8 Coal Mining | 100 | 0 | 100 | 2025-03-14 04:53 | 2025-03-14 20:43 | 19295.0852 | [6 empty] | 19295 | 13763 | 3.37 | 0 | 0 | 11.63 | 5401
PH4100XPC#1 | GG\23\010\X2 | GG | 23 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 43.3701 | 2025-03-14 07:13 | 2025-03-14 20:27 | 29934.0303 | 29934 | [7 empty] | 0 | 0 | 3 | 0 | 0
DRE1 | SC\39\010\D | SC | 39 | 10 | D | 6 DL | 100 | 0 | 100 | 2025-03-14 11:20 | 2025-03-24 16:41 | 857021.4143 |  |  |  | 48098 | 857021 | 372999 |  |  | 0 | 40 | 0 | 7.77 | 5731.33
PH4100XPC#1 | GG\23\010\B | GG | 23 | 10 | B | 1 Prestrip - Thick | 100 | 72.4422 | 72.4422 | 2025-03-14 20:27 | 2025-03-16 02:39 | 68365.2291 | 68365 | [7 empty] | 0 | 0 | 6.84 | 10.18 | 5518.02
TS5500Shv | GG\23\011\X1 | GG | 23 | 11 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-03-14 20:43 | 2025-03-15 09:15 | 15295.8713 | [6 empty] | 15296 | 10933 | 1.1 | 0 | 0 | 14.95 | 5103
TS5500Shv | GG\23\011\X2 | GG | 23 | 11 | X2 | 1 Prestrip - Thick | 54.7945 | 0 | 46.6472 | 2025-03-15 09:15 | 2025-03-16 14:53 | 31751.9895 | 31752 | [7 empty] | 0 | 0 | 3.2 | 0 | 0
TS Fleet 5 | GG\23\010\B | GG | 23 | 10 | B | 1 Prestrip - Thick | 45.419 | 27.5578 | 27.5578 | 2025-03-15 12:47 | 2025-03-16 02:39 | 26006.8356 | 26007 | [7 empty] | 0 | 0 | 2.6 | 10.18 | 5518.02
DRE2 | GG\19\019\D | GG | 19 | 19 | D | 6 DL | 100 | 100 | 100 | 2025-03-15 20:21 | 2025-03-21 20:15 | 484028.6109 |  |  |  | 11270 | 484029 | 214122 |  |  | 0 | 22.54 | 0 | 7.06 | 5767.71
TS5500Exc | RS\46\002\B | RS | 46 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-03-16 02:33 | 2025-03-16 14:46 | 10799.5762 | 10800 | [7 empty] | 0 | 0 | 2.54 | 9.16 | 5582.98
TS Fleet 5 | GG\23\011\X2 | GG | 23 | 11 | X2 | 1 Prestrip - Thick | 12.5381 | 0 | 12.5381 | 2025-03-16 02:39 | 2025-03-16 07:12 | 8534.5056 | 8535 | [7 empty] | 0 | 0 | 0.86 | 0 | 0
PH4100XPC#1 | GG\23\011\X2 | GG | 23 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 40.6711 | 2025-03-16 02:39 | 2025-03-16 14:53 | 27684.1564 | 27684 | [7 empty] | 0 | 0 | 2.79 | 0 | 0
TS Fleet 5 | GG\23\020\B | GG | 23 | 20 | B | 1 Prestrip - Thick | 37.314 | 37.314 | 37.314 | 2025-03-16 07:12 | 2025-03-18 18:58 | 112137.7903 | 112138 | [7 empty] | 0 | 0 | 11.2 | 16.2 | 5049.99
TS5500Exc | GG\23\011\X2 | GG | 23 | 11 | X2 | 1 Prestrip - Thick | 45.2055 | 0 | 0.14356 | 2025-03-16 14:46 | 2025-03-16 14:53 | 97.7165 | 98 | [7 empty] | 0 | 0 | 0.01 | 0 | 0
TS5500Shv | GG\23\011\B | GG | 23 | 11 | B | 1 Prestrip - Thick | 54.7945 | 25.4033 | 25.4033 | 2025-03-16 14:53 | 2025-03-17 17:33 | 28601.6859 | 28602 | [7 empty] | 0 | 0 | 2.87 | 10.71 | 5469.7
PH4100XPC#1 | GG\23\011\B | GG | 23 | 11 | B | 1 Prestrip - Thick | 100 | 53.6389 | 53.6389 | 2025-03-16 14:53 | 2025-03-17 17:33 | 60392.2463 | 60392 | [7 empty] | 0 | 0 | 6.06 | 10.71 | 5469.7
TS5500Exc | GG\23\011\B | GG | 23 | 11 | B | 1 Prestrip - Thick | 45.2055 | 20.9577 | 20.9577 | 2025-03-16 14:53 | 2025-03-17 17:33 | 23596.3909 | 23596 | [7 empty] | 0 | 0 | 2.37 | 10.71 | 5469.7
PH4100A | SC\41\015\D | SC | 41 | 15 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-03-17 03:24 | 2025-03-21 06:46 | 163659.6719 | 163660 | [7 empty] | 0 | 0 | 13.79 | 7.42 | 5756.08
PH4100XPC#1 | GG\23\012\X1 | GG | 23 | 12 | X1 | 1 Prestrip - Thick | 100 | 54.0634 | 54.0634 | 2025-03-17 17:33 | 2025-03-22 19:52 | 271130.0986 | 271130 | [7 empty] | 0 | 0 | 26.29 | 14.86 | 5110.9
TS5500Exc | RS\46\002\B | RS | 46 | 2 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-03-17 17:33 | 2025-03-18 00:44 | 9029.5797 | [6 empty] | 9030 | 6516 | 1.48 | 0 | 0 | 9.16 | 5583
TS5500Shv | GG\23\019\B | GG | 23 | 19 | B | 1 Prestrip - Thick | 7.1862 | 7.1862 | 7.1862 | 2025-03-17 17:33 | 2025-03-18 13:34 | 21315.461 | 21315 | [7 empty] | 0 | 0 | 2.16 | 13.32 | 5263.07
TS5500Exc | RS\46\005\A | RS | 46 | 5 | A | 1 Prestrip - Thick | 8.1775 | 8.1775 | 8.1775 | 2025-03-18 00:44 | 2025-03-18 21:56 | 18751.9095 | 18752 | [7 empty] | 0 | 0 | 1.59 | 16.24 | 5015.86
TS5500Shv | GG\20\021\B | GG | 20 | 21 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-03-18 13:34 | 2025-03-19 08:05 | 22573.3035 | [6 empty] | 22573 | 15701 | 1.66 | 0 | 0 | 18.66 | 4882
TS Fleet 5 | GG\23\021\D | GG | 23 | 21 | D | 1 Prestrip - Thick | 30.4 | 30.4 | 30.4 | 2025-03-18 18:58 | 2025-03-20 03:51 | 61692.2846 | 61692 | [7 empty] | 0 | 0 | 6.28 | 6.8 | 5789.61
TS5500Exc | RS\47\003\A | RS | 47 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-03-18 21:56 | 2025-03-19 16:37 | 23530.7039 | [6 empty] | 23531 | 16673 | 1.66 | 0 | 0 | 12.4 | 5337
TS5500Shv | GG\23\020\B | GG | 23 | 20 | B | 1 Prestrip - Thick | 14.6399 | 14.6399 | 14.6399 | 2025-03-19 08:05 | 2025-03-21 01:06 | 43996.5263 | 43997 | [7 empty] | 0 | 0 | 4.39 | 16.2 | 5049.99
TS5500Exc | RS\47\004\A | RS | 47 | 4 | A | 1 Prestrip - Thick | 3.7962 | 3.7962 | 3.7962 | 2025-03-19 16:37 | 2025-03-20 09:47 | 15252.4107 | 15252 | [7 empty] | 0 | 0 | 1.56 | 14.79 | 5132.7
TS Fleet 5 | GG\23\022\B | GG | 23 | 22 | B | 1 Prestrip - Thick | 37.0761 | 37.0761 | 37.0761 | 2025-03-20 03:51 | 2025-03-22 00:06 | 83000.4547 | 83000 | [7 empty] | 0 | 0 | 10.04 | 19.72 | 4784.01
TS5500Exc | RS\47\004\A | RS | 47 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-03-20 09:47 | 2025-03-21 04:35 | 23673.9139 | [6 empty] | 23674 | 16524 | 1.65 | 0 | 0 | 14.79 | 5133
TS5500Shv | GG\23\021\D | GG | 23 | 21 | D | 1 Prestrip - Thick | 17.3597 | 17.3597 | 17.3597 | 2025-03-21 01:06 | 2025-03-22 09:51 | 35228.9229 | 35229 | [7 empty] | 0 | 0 | 3.58 | 6.8 | 5789.61
TS5500Exc | RS\47\005\A | RS | 47 | 5 | A | 1 Prestrip - Thick | 3.8699 | 3.8699 | 3.8699 | 2025-03-21 04:35 | 2025-03-22 01:08 | 18246.5848 | 18247 | [7 empty] | 0 | 0 | 1.74 | 16.2 | 5019.99
PH4100A | SC\41\016\D | SC | 41 | 16 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-03-21 06:46 | 2025-03-24 05:38 | 116689.8202 | 116690 | [7 empty] | 0 | 0 | 16.01 | 7.29 | 5766.48
DRE2 | GG\19\020\D | GG | 19 | 20 | D | 6 DL | 100 | 100 | 100 | 2025-03-21 20:15 | 2025-03-26 08:00 | 362453.5092 |  |  |  | 6750 | 362454 | 161990 |  |  | 0 | 16.92 | 0 | 6.92 | 5779.67
TS Fleet 5 | GG\23\023\D | GG | 23 | 23 | D | 1 Prestrip - Thick | 36.1802 | 36.1802 | 36.1802 | 2025-03-22 00:06 | 2025-03-23 05:18 | 54775.5804 | 54776 | [7 empty] | 0 | 0 | 12.03 | 6.59 | 5810.63
TS5500Exc | RS\48\002\A | RS | 48 | 2 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-03-22 01:08 | 2025-03-22 11:23 | 12909.3233 | [6 empty] | 12909 | 9204 | 1.71 | 0 | 0 | 11.74 | 5399
TS5500Shv | GG\20\022\B | GG | 20 | 22 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-03-22 09:51 | 2025-03-24 08:46 | 57210.4943 | [6 empty] | 57210 | 39522 | 3.98 | 0 | 0 | 20.19 | 4757
TS5500Exc | RS\48\003\A | RS | 48 | 3 | A | 1 Prestrip - Thick | 9.1972 | 9.1972 | 9.1972 | 2025-03-22 11:23 | 2025-03-23 18:55 | 28004.6071 | 28005 | [7 empty] | 0 | 0 | 2.89 | 12.54 | 5327.57
PH4100XPC#1 | GG\23\013\X1 | GG | 23 | 13 | X1 | 1 Prestrip - Thick | 100 | 48.1843 | 48.1843 | 2025-03-22 19:52 | 2025-03-26 09:35 | 187900.1862 | 187900 | [7 empty] | 0 | 0 | 18.82 | 14.64 | 5127.81
TS6060#1 | GG\19\018\D | GG | 19 | 18 | D | 8 Coal Mining | 52.4 | 0 | 52.4 | 2025-03-23 00:15 | 2025-03-24 01:09 | 33696.8859 | [6 empty] | 33697 | 25073 | 2.51 | 0 | 0 | 7.21 | 5755
TS Fleet 5 | RS\45\005\A | RS | 45 | 5 | A | 1 Prestrip - Thick | 0.58568 | 0.58568 | 0.58568 | 2025-03-23 05:18 | 2025-03-23 06:06 | 1503.4925 | 1503 | [7 empty] | 0 | 0 | 0.11 | 15.75 | 5056.01
TS Fleet 5 | RS\46\005\A | RS | 46 | 5 | A | 1 Prestrip - Thick | 81.9105 | 70.0709 | 70.0709 | 2025-03-23 06:06 | 2025-03-26 19:45 | 160681.2168 | 160681 | [7 empty] | 0 | 0 | 13.61 | 16.24 | 5015.86
TS5500Exc | SC\39\011\D | SC | 39 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-03-23 18:55 | 2025-03-26 07:31 | 76319.6962 | [6 empty] | 76320 | 56950 | 4.75 | 0 | 0 | 7.6 | 5746
TS6060#1 | RS\49\002\A | RS | 49 | 2 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-03-24 01:09 | 2025-03-29 14:39 | 135717.0022 | 135717 | [7 empty] | 0 | 0 | 25.25 | 11.95 | 5384.17
PH4100A | SC\40\016\D | SC | 40 | 16 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-03-24 05:38 | 2025-03-27 03:59 | 115821.1676 | 115821 | [7 empty] | 0 | 0 | 8.94 | 7.13 | 5780.78
TS5500Shv | GG\23\012\X1 | GG | 23 | 12 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-03-24 08:46 | 2025-03-24 20:53 | 14769.1226 | [6 empty] | 14769 | 10570 | 1.04 | 0 | 0 | 14.86 | 5111
DRE1 | SC\39\017\D | SC | 39 | 17 | D | 6 DL | 100 | 0 | 100 | 2025-03-24 16:41 | 2025-04-01 04:43 | 628880.0326 |  |  |  | 47824 | 628880 | 430412 |  |  | 0 | 40 | 0 | 6.9 | 5802.84
TS5500Shv | GG\23\023\D | GG | 23 | 23 | D | 1 Prestrip - Thick | 18.6339 | 18.6339 | 18.6339 | 2025-03-24 20:53 | 2025-03-25 23:07 | 28211.0884 | 28211 | [7 empty] | 0 | 0 | 6.2 | 6.59 | 5810.63
TS5500Shv | RS\45\005\A | RS | 45 | 5 | A | 1 Prestrip - Thick | 9.4366 | 9.4366 | 9.4366 | 2025-03-25 23:07 | 2025-03-26 21:42 | 24224.7431 | 24225 | [7 empty] | 0 | 0 | 1.82 | 15.75 | 5056.01
TS5500Exc | SC\39\010\D | SC | 39 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2025-03-26 07:31 | 2025-03-29 03:13 | 59879.7368 |  |  | 59880 | [5 empty] | 0 | 0 | 0 | 7.77 | 5731.33
DRE2 | GG\19\021\D | GG | 19 | 21 | D | 6 DL | 100 | 100 | 100 | 2025-03-26 08:00 | 2025-03-31 05:24 | 394903.9334 |  |  |  | 7354 | 394904 | 176493 |  |  | 0 | 18.48 | 0 | 6.84 | 5787.01
PH4100XPC#1 | GG\23\012\X2 | GG | 23 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 69.0945 | 2025-03-26 09:35 | 2025-03-27 07:40 | 49984.3802 | 49984 | [7 empty] | 0 | 0 | 4.9 | 0 | 0
TS Fleet 5 | GG\23\012\X2 | GG | 23 | 12 | X2 | 1 Prestrip - Thick | 45.419 | 0 | 30.9055 | 2025-03-26 19:45 | 2025-03-27 07:40 | 22357.7038 | 22358 | [7 empty] | 0 | 0 | 2.19 | 0 | 0
TS5500Shv | GG\23\013\X1 | GG | 23 | 13 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-03-26 21:42 | 2025-03-27 09:11 | 13989.4432 | [6 empty] | 13989 | 10035 | 1 | 0 | 0 | 14.64 | 5128
PH4100A | SC\41\017\D | SC | 41 | 17 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-03-27 03:59 | 2025-04-02 01:50 | 236835.1248 | 236835 | [7 empty] | 0 | 0 | 16.26 | 7.16 | 5776.59
PH4100XPC#1 | GG\23\012\B | GG | 23 | 12 | B | 1 Prestrip - Thick | 100 | 54.6807 | 54.6807 | 2025-03-27 07:40 | 2025-03-28 13:42 | 67988.0329 | 67988 | [7 empty] | 0 | 0 | 6.78 | 11.6 | 5384.67
TS Fleet 5 | GG\23\012\B | GG | 23 | 12 | B | 1 Prestrip - Thick | 45.419 | 45.3193 | 45.3193 | 2025-03-27 07:40 | 2025-03-28 13:42 | 56348.3202 | 56348 | [7 empty] | 0 | 0 | 5.62 | 11.6 | 5384.67
TS5500Shv | GG\23\013\X2 | GG | 23 | 13 | X2 | 1 Prestrip - Thick | 4.7191 | 0 | 4.7191 | 2025-03-27 09:11 | 2025-03-27 12:28 | 3515.1871 | 3515 | [7 empty] | 0 | 0 | 0.35 | 0 | 0
TS5500Shv | RS\45\005\A | RS | 45 | 5 | A | 8 Coal Mining | 53.9 | 0 | 53.9 | 2025-03-27 12:28 | 2025-03-28 16:18 | 33956.8932 | [6 empty] | 33957 | 23582 | 1.78 | 0 | 0 | 15.75 | 5056
TS Fleet 5 | GG\23\013\X2 | GG | 23 | 13 | X2 | 1 Prestrip - Thick | 43.2756 | 0 | 41.5708 | 2025-03-28 13:42 | 2025-03-29 06:13 | 30965.1816 | 30965 | [7 empty] | 0 | 0 | 3.09 | 0 | 0
PH4100XPC#1 | GG\23\013\X2 | GG | 23 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 50.1579 | 2025-03-28 13:42 | 2025-03-29 06:13 | 37361.5713 | 37362 | [7 empty] | 0 | 0 | 3.73 | 0 | 0
TS5500Shv | RS\46\002\B | RS | 46 | 2 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-03-28 16:18 | 2025-03-28 23:29 | 8741.4016 | [6 empty] | 8741 | 6308 | 1.43 | 0 | 0 | 9.16 | 5583
TS5500Shv | RS\46\003\A | RS | 46 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-03-28 23:29 | 2025-03-29 18:08 | 22759.7476 | [6 empty] | 22760 | 16141 | 1.61 | 0 | 0 | 12.29 | 5343
TS5500Exc | GG\23\013\X2 | GG | 23 | 13 | X2 | 1 Prestrip - Thick | 3.8933 | 0 | 3.5521 | 2025-03-29 03:13 | 2025-03-29 06:13 | 2645.912 | 2646 | [7 empty] | 0 | 0 | 0.26 | 0 | 0
TS Fleet 5 | GG\23\013\B | GG | 23 | 13 | B | 1 Prestrip - Thick | 31.3347 | 31.3347 | 31.3347 | 2025-03-29 06:13 | 2025-03-30 04:12 | 41247.1741 | 41247 | [7 empty] | 0 | 0 | 4.1 | 12.18 | 5321.24
PH4100XPC#1 | GG\23\013\B | GG | 23 | 13 | B | 1 Prestrip - Thick | 100 | 43.3577 | 43.3577 | 2025-03-29 06:13 | 2025-03-30 07:25 | 57073.6131 | 57074 | [7 empty] | 0 | 0 | 5.68 | 12.18 | 5321.24
TS5500Exc | GG\23\013\B | GG | 23 | 13 | B | 1 Prestrip - Thick | 14.4901 | 14.4901 | 14.4901 | 2025-03-29 06:13 | 2025-03-30 03:47 | 19073.9286 | 19074 | [7 empty] | 0 | 0 | 1.9 | 12.18 | 5321.24
TS6060#1 | RS\49\003\A | RS | 49 | 3 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-03-29 14:39 | 2025-04-10 11:18 | 284123.4964 | 284123 | [7 empty] | 0 | 0 | 29.17 | 12.75 | 5313.05
TS5500Shv | GG\23\013\B | GG | 23 | 13 | B | 1 Prestrip - Thick | 17.5637 | 10.8175 | 10.8175 | 2025-03-29 18:08 | 2025-03-30 07:25 | 14239.5823 | 14240 | [7 empty] | 0 | 0 | 1.42 | 12.18 | 5321.24
TS5500Exc | RS\45\005\A | RS | 45 | 5 | A | 8 Coal Mining | 46.1 | 0 | 46.1 | 2025-03-30 03:47 | 2025-03-31 02:50 | 29044.6431 | [6 empty] | 29045 | 20171 | 1.52 | 0 | 0 | 15.75 | 5056
TS Fleet 5 | RS\48\003\A | RS | 48 | 3 | A | 1 Prestrip - Thick | 52.2641 | 52.2641 | 52.2641 | 2025-03-30 04:12 | 2025-04-02 17:01 | 159139.1037 | 159139 | [7 empty] | 0 | 0 | 16.45 | 12.54 | 5327.57
TS5500Shv | RS\46\003\B | RS | 46 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-03-30 07:25 | 2025-03-31 07:52 | 26200.0651 | 26200 | [7 empty] | 0 | 0 | 2.62 | 9.14 | 5588.88
PH4100XPC#1 | GG\23\014\X1 | GG | 23 | 14 | X1 | 1 Prestrip - Thick | 100 | 53.3128 | 53.3128 | 2025-03-30 07:25 | 2025-04-03 01:23 | 193506.3841 | 193506 | [7 empty] | 0 | 0 | 14.82 | 14.38 | 5147.61
TS5500Exc | RS\45\005\B | RS | 45 | 5 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2025-03-31 02:50 | 2025-03-31 20:26 | 15558.5176 | 15559 | [7 empty] | 0 | 0 | 1.18 | 9.07 | 5619.36
DRE2 | GG\19\022\D | GG | 19 | 22 | D | 6 DL | 100 | 100 | 100 | 2025-03-31 05:24 | 2025-04-05 03:17 | 396535.9566 |  |  |  | 7384 | 396536 | 177223 |  |  | 0 | 18.5 | 0 | 6.71 | 5797.14
TS5500Shv | RS\45\005\B | RS | 45 | 5 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-03-31 07:52 | 2025-04-01 01:27 | 18858.8093 | 18859 | [7 empty] | 0 | 0 | 1.43 | 9.07 | 5619.36
TS5500Exc | RS\46\005\A | RS | 46 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-03-31 20:26 | 2025-04-01 18:53 | 28289.7202 | [6 empty] | 28290 | 19598 | 1.68 | 0 | 0 | 16.24 | 5016
TS5500Shv | RS\45\005\B | RS | 45 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-04-01 01:27 | 2025-04-01 23:03 | 26321.8115 | [6 empty] | 26322 | 18900 | 1.43 | 0 | 0 | 9.07 | 5619
DRE1 | RS\46\002\D | RS | 46 | 2 | D | 6 DL | 100 | 100 | 100 | 2025-04-01 04:43 | 2025-04-03 22:28 | 229702.8859 |  |  |  | 11810 | 229703 | 185022 |  |  | 0 | 27.83 | 0 | 5.45 | 5941.07
TS5500Exc | RS\45\005\B | RS | 45 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-04-01 18:53 | 2025-04-02 16:28 | 27189.5635 | [6 empty] | 27190 | 19523 | 1.48 | 0 | 0 | 9.07 | 5619
TS5500Shv | RS\46\003\B | RS | 46 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-04-01 23:03 | 2025-04-03 07:04 | 39043.7247 | [6 empty] | 39044 | 28087 | 2.8 | 0 | 0 | 9.14 | 5589
PH4100A | SC\40\017\D | SC | 40 | 17 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-04-02 01:50 | 2025-04-10 06:27 | 342332.2848 | 342332 | [7 empty] | 0 | 0 | 26.79 | 6.37 | 5794.15
TS5500Exc | SC\39\010\D | SC | 39 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-04-02 16:28 | 2025-04-05 06:20 | 77927.753 | [6 empty] | 77928 | 58335 | 4.86 | 0 | 0 | 7.77 | 5731
TS Fleet 5 | RS\48\004\A | RS | 48 | 4 | A | 1 Prestrip - Thick | 77.0604 | 77.0604 | 77.0604 | 2025-04-02 17:01 | 2025-04-09 07:05 | 296510.2936 | 296510 | [7 empty] | 0 | 0 | 30.22 | 14.86 | 5128.69
PH4100XPC#1 | GG\23\018\X2 | GG | 23 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 47.2317 | 2025-04-03 01:23 | 2025-04-05 03:08 | 108326.0826 | 108326 | [7 empty] | 0 | 0 | 11.2 | 0 | 0
TS5500Shv | GG\23\014\X1 | GG | 23 | 14 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-04-03 07:04 | 2025-04-03 14:01 | 8490.3568 | [6 empty] | 8490 | 6103 | 0.47 | 0 | 0 | 14.38 | 5148
TS5500Shv | GG\19\013\D | GG | 19 | 13 | D | 8 Coal Mining | 73 | 0 | 73 | 2025-04-03 14:01 | 2025-04-05 20:24 | 66303.4676 | [6 empty] | 66303 | 49373 | 3.47 | 0 | 0 | 7.13 | 5762
DRE1 | RS\45\005\D | RS | 45 | 5 | D | 6 DL | 100 | 100 | 100 | 2025-04-03 22:28 | 2025-04-09 04:41 | 440876.3611 |  |  |  | 16364 | 440876 | 249816 |  |  | 0 | 26.79 | 0 | 5.99 | 5893.43
PH4100XPC#1 | GG\23\018\B | GG | 23 | 18 | B | 1 Prestrip - Thick | 100 | 82.4227 | 82.4227 | 2025-04-05 03:08 | 2025-04-07 06:44 | 116791.7216 | 116792 | [7 empty] | 0 | 0 | 11.59 | 12.93 | 5273.11
DRE2 | GG\19\023\D | GG | 19 | 23 | D | 6 DL | 100 | 100 | 100 | 2025-04-05 03:17 | 2025-04-10 00:53 | 395524.6797 |  |  |  | 6909 | 395525 | 114516 |  |  | 0 | 16.84 | 0 | 6.48 | 5819.15
TS5500Exc | GG\23\018\B | GG | 23 | 18 | B | 1 Prestrip - Thick | 17.5773 | 17.5773 | 17.5773 | 2025-04-05 06:20 | 2025-04-06 10:30 | 24906.8158 | 24907 | [7 empty] | 0 | 0 | 2.47 | 12.93 | 5273.11
TS5500Shv | RS\46\004\B | RS | 46 | 4 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-04-05 20:24 | 2025-04-06 09:57 | 14530.1498 | 14530 | [7 empty] | 0 | 0 | 1.45 | 9.12 | 5603.77
TS5500Shv | RS\46\004\B | RS | 46 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-04-06 09:57 | 2025-04-07 02:00 | 19578.3118 | [6 empty] | 19578 | 14046 | 1.4 | 0 | 0 | 9.12 | 5604
TS5500Exc | RS\46\004\B | RS | 46 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-04-06 10:30 | 2025-04-07 02:33 | 20223.7506 | [6 empty] | 20224 | 14509 | 1.45 | 0 | 0 | 9.12 | 5604
TS5500Shv | GG\19\018\D | GG | 19 | 18 | D | 8 Coal Mining | 47.6 | 0 | 47.6 | 2025-04-07 02:00 | 2025-04-08 03:09 | 30663.862 | [6 empty] | 30664 | 22816 | 2.28 | 0 | 0 | 7.21 | 5755
TS5500Exc | RS\46\002\D | RS | 46 | 2 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-04-07 02:33 | 2025-04-07 20:17 | 22333.4178 | [6 empty] | 22333 | 16669 | 2.33 | 0 | 0 | 5.45 | 5941
PH4100XPC#1 | GG\23\019\B | GG | 23 | 19 | B | 1 Prestrip - Thick | 100 | 41.4839 | 41.4839 | 2025-04-07 06:44 | 2025-04-09 13:43 | 123048.6455 | 123049 | [7 empty] | 0 | 0 | 12.46 | 13.32 | 5263.07
TS5500Exc | RS\48\005\A | RS | 48 | 5 | A | 8 Coal Mining | 9.9 | 0 | 9.9 | 2025-04-07 20:17 | 2025-04-07 23:18 | 3796.2663 | [6 empty] | 3796 | 2636 | 0.32 | 0 | 0 | 15.7 | 5063
TS5500Exc | RS\49\002\A | RS | 49 | 2 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-04-07 23:18 | 2025-04-08 10:45 | 14418.2789 | [6 empty] | 14418 | 10266 | 1.71 | 0 | 0 | 11.95 | 5384
TS5500Shv | RS\47\002\A | RS | 47 | 2 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-04-08 03:09 | 2025-04-08 12:11 | 11010.8306 | [6 empty] | 11011 | 7859 | 1.66 | 0 | 0 | 11.62 | 5407
TS5500Exc | SC\39\017\D | SC | 39 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-04-08 10:45 | 2025-04-10 18:57 | 70795.7628 | [6 empty] | 70796 | 53032 | 4.12 | 0 | 0 | 6.9 | 5803
TS5500Shv | RS\46\002\D | RS | 46 | 2 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-04-08 12:11 | 2025-04-09 05:55 | 21620.6491 | [6 empty] | 21621 | 16137 | 2.26 | 0 | 0 | 5.45 | 5941
DRE1 | RS\46\003\D | RS | 46 | 3 | D | 6 DL | 100 | 100 | 100 | 2025-04-09 04:41 | 2025-04-13 04:06 | 333338.0024 |  |  |  | 17138 | 333338 | 268498 |  |  | 0 | 28.56 | 0 | 5.58 | 5929.59
TS5500Shv | RS\45\005\D | RS | 45 | 5 | D | 7 PostStrip | 68.3944 | 0 | 68.3944 | 2025-04-09 05:55 | 2025-04-10 20:53 | 41782.5734 |  |  | 41783 | [5 empty] | 0 | 0 | 0 | 5.99 | 5893.43
TS Fleet 5 | RS\47\002\B | RS | 47 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-04-09 07:05 | 2025-04-09 13:33 | 12147.9516 | 12148 | [7 empty] | 0 | 0 | 2.48 | 9.12 | 5590.29
TS Fleet 5 | RS\50\003\A | RS | 50 | 3 | A | 1 Prestrip - Thick | 45.6426 | 45.6426 | 45.6426 | 2025-04-09 13:33 | 2025-04-12 08:54 | 126352.317 | 126352 | [7 empty] | 0 | 0 | 12.94 | 12.96 | 5298.15
PH4100XPC#1 | GG\23\020\B | GG | 23 | 20 | B | 1 Prestrip - Thick | 100 | 46.156 | 46.156 | 2025-04-09 13:43 | 2025-04-12 01:15 | 138709.9905 | 138710 | [7 empty] | 0 | 0 | 13.85 | 16.2 | 5049.99
DRE2 | GG\21\012\B | GG | 21 | 12 | B | 6 DL | 100 | 0 | 100 | 2025-04-10 00:53 | 2025-04-12 11:36 | 197558.0492 |  |  |  |  | 197558 | 164632 |  |  | 0 | 16.52 | 0 | 10.82 | 5447.23
PH4100A | SC\40\018\D | SC | 40 | 18 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-04-10 06:27 | 2025-04-20 17:25 | 425462.9876 | 425463 | [7 empty] | 0 | 0 | 27.62 | 6.98 | 5793.07
TS6060#1 | RS\45\005\D | RS | 45 | 5 | D | 7 PostStrip | 100 | 0 | 22.9846 | 2025-04-10 11:18 | 2025-04-11 00:54 | 14041.4549 |  |  | 14041 | [5 empty] | 0 | 0 | 0 | 5.99 | 5893.43
TS5500Exc | RS\45\005\D | RS | 45 | 5 | D | 7 PostStrip | 100 | 0 | 8.621 | 2025-04-10 18:57 | 2025-04-11 00:54 | 5266.6154 |  |  | 5267 | [5 empty] | 0 | 0 | 0 | 5.99 | 5893.43
TS5500Shv | RS\46\005\A | RS | 46 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-04-10 20:53 | 2025-04-11 19:21 | 27386.8568 | [6 empty] | 27387 | 18973 | 1.62 | 0 | 0 | 16.24 | 5016
TS5500Exc | RS\45\005\D | RS | 45 | 5 | D | 8 Coal Mining | 71.2 | 0 | 71.2 | 2025-04-11 00:54 | 2025-04-12 20:10 | 54485.0301 | [6 empty] | 54485 | 40185 | 3.3 | 0 | 0 | 5.99 | 5893
TS6060#1 | GG\23\014\X1 | GG | 23 | 14 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-04-11 00:54 | 2025-04-11 07:52 | 9423.363 | [6 empty] | 9423 | 6773 | 0.53 | 0 | 0 | 14.38 | 5148
TS6060#1 | GG\19\022\D | GG | 19 | 22 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-04-11 07:52 | 2025-04-12 08:06 | 32799.8757 | [6 empty] | 32800 | 24462 | 2.45 | 0 | 0 | 6.71 | 5797
TS5500Shv | GG\23\014\B | GG | 23 | 14 | B | 1 Prestrip - Thick | 17.5637 | 17.5637 | 17.5637 | 2025-04-11 19:21 | 2025-04-13 15:08 | 46937.5713 | 46938 | [7 empty] | 0 | 0 | 3.94 | 12.75 | 5270.06
PH4100XPC#1 | GG\23\014\B | GG | 23 | 14 | B | 1 Prestrip - Thick | 100 | 42.3807 | 42.3807 | 2025-04-12 01:15 | 2025-04-14 03:18 | 113258.7091 | 113259 | [7 empty] | 0 | 0 | 9.52 | 12.75 | 5270.06
TS6060#1 | GG\19\023\D | GG | 19 | 23 | D | 7 PostStrip | 49.0446 | 0 | 49.0446 | 2025-04-12 08:06 | 2025-04-13 08:29 | 25157.6343 |  |  | 25158 | [5 empty] | 0 | 0 | 0 | 6.48 | 5819.15
TS Fleet 5 | GG\23\014\B | GG | 23 | 14 | B | 1 Prestrip - Thick | 35.4859 | 29.7541 | 29.7541 | 2025-04-12 08:54 | 2025-04-14 03:18 | 79515.2678 | 79515 | [7 empty] | 0 | 0 | 6.68 | 12.75 | 5270.06
DRE2 | GG\21\011\B | GG | 21 | 11 | B | 6 DL | 100 | 0 | 100 | 2025-04-12 11:36 | 2025-04-15 05:19 | 221055.9507 |  |  |  |  | 221056 | 170043 |  |  | 0 | 17.08 | 0 | 10.06 | 5518.05
TS5500Exc | GG\23\014\B | GG | 23 | 14 | B | 1 Prestrip - Thick | 14.4901 | 10.3014 | 10.3014 | 2025-04-12 20:10 | 2025-04-14 03:18 | 27529.6875 | 27530 | [7 empty] | 0 | 0 | 2.31 | 12.75 | 5270.06
DRE1 | RS\46\004\D | RS | 46 | 4 | D | 6 DL | 100 | 100 | 100 | 2025-04-13 04:06 | 2025-04-17 01:03 | 324679.2977 |  |  |  | 16693 | 324679 | 261524 |  |  | 0 | 27.82 | 0 | 5.88 | 5903.66
TS6060#1 | GG\21\012\B | GG | 21 | 12 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-04-13 08:29 | 2025-04-14 03:27 | 25658.3883 | [6 empty] | 25658 | 18742 | 1.88 | 0 | 0 | 10.82 | 5447
TS5500Shv | RS\45\005\D | RS | 45 | 5 | D | 8 Coal Mining | 28.8 | 0 | 28.8 | 2025-04-13 15:08 | 2025-04-14 09:15 | 22082.2841 | [6 empty] | 22082 | 16287 | 1.34 | 0 | 0 | 5.99 | 5893
PH4100XPC#1 | GG\23\021\D | GG | 23 | 21 | D | 1 Prestrip - Thick | 100 | 37.9657 | 37.9657 | 2025-04-14 03:18 | 2025-04-15 12:03 | 77045.6939 | 77046 | [7 empty] | 0 | 0 | 7.84 | 6.8 | 5789.61
TS5500Exc | RS\47\002\B | RS | 47 | 2 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-04-14 03:18 | 2025-04-14 11:31 | 10355.7951 | [6 empty] | 10356 | 7478 | 1.48 | 0 | 0 | 9.12 | 5590
TS Fleet 5 | RS\50\004\A | RS | 50 | 4 | A | 1 Prestrip - Thick | 59.8806 | 59.8806 | 59.8806 | 2025-04-14 03:18 | 2025-04-19 05:46 | 229777.4917 | 229777 | [7 empty] | 0 | 0 | 23.35 | 14.63 | 5158.95
TS6060#1 | RS\49\004\A | RS | 49 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-04-14 03:27 | 2025-04-30 12:14 | 391760.2204 | 391760 | [7 empty] | 0 | 0 | 39.58 | 14.75 | 5142.83
TS5500Shv | RS\47\002\B | RS | 47 | 2 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-04-14 09:15 | 2025-04-14 17:28 | 10025.291 | [6 empty] | 10025 | 7240 | 1.44 | 0 | 0 | 9.12 | 5590
TS5500Exc | RS\46\005\B | RS | 46 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-04-14 11:31 | 2025-04-15 21:58 | 30473.6613 | 30474 | [7 empty] | 0 | 0 | 2.61 | 9.12 | 5615.32
TS5500Shv | GG\19\019\D | GG | 19 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-04-14 17:28 | 2025-04-16 21:45 | 63746.083 | [6 empty] | 63746 | 47468 | 4.75 | 0 | 0 | 7.06 | 5768
DRE2 | GG\21\010\B | GG | 21 | 10 | B | 6 DL | 100 | 0 | 100 | 2025-04-15 05:19 | 2025-04-18 00:24 | 225645.6523 |  |  |  |  | 225646 | 188038 |  |  | 0 | 18.75 | 0 | 9.97 | 5530.13
PH4100XPC#1 | GG\23\022\B | GG | 23 | 22 | B | 1 Prestrip - Thick | 100 | 45.5127 | 45.5127 | 2025-04-15 12:03 | 2025-04-17 08:07 | 101887.1811 | 101887 | [7 empty] | 0 | 0 | 12.32 | 19.72 | 4784.01
TS5500Exc | RS\46\005\B | RS | 46 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-04-15 21:58 | 2025-04-17 11:13 | 46917.2134 | [6 empty] | 46917 | 33663 | 2.89 | 0 | 0 | 9.12 | 5615
TS5500Shv | RS\46\003\D | RS | 46 | 3 | D | 8 Coal Mining | 69.8 | 0 | 69.8 | 2025-04-16 21:45 | 2025-04-18 07:14 | 40834.4762 | [6 empty] | 40834 | 30361 | 3.04 | 0 | 0 | 5.58 | 5930
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2025-04-17 01:03 | 2025-04-20 01:03
PH4100XPC#1 | GG\23\023\D | GG | 23 | 23 | D | 1 Prestrip - Thick | 100 | 45.1859 | 45.1859 | 2025-04-17 08:07 | 2025-04-18 13:12 | 68409.7952 | 68410 | [7 empty] | 0 | 0 | 15.03 | 6.59 | 5810.63
TS5500Exc | RS\46\003\D | RS | 46 | 3 | D | 8 Coal Mining | 30.2 | 0 | 30.2 | 2025-04-17 11:13 | 2025-04-18 01:17 | 17709.1753 | [6 empty] | 17709 | 13167 | 1.32 | 0 | 0 | 5.58 | 5930
DRE2 | GG\21\009\B | GG | 21 | 9 | B | 6 DL | 100 | 0 | 100 | 2025-04-18 00:24 | 2025-04-20 22:12 | 234788.0716 |  |  |  |  | 234788 | 195657 |  |  | 0 | 19.57 | 0 | 9.97 | 5524
TS5500Exc | RS\46\004\D | RS | 46 | 4 | D | 8 Coal Mining | 72.7 | 0 | 72.7 | 2025-04-18 01:17 | 2025-04-19 12:06 | 43860.8354 | [6 empty] | 43861 | 32409 | 3.24 | 0 | 0 | 5.88 | 5904
TS5500Shv | RS\47\003\A | RS | 47 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-04-18 07:14 | 2025-04-19 01:55 | 22779.7239 | [6 empty] | 22780 | 16141 | 1.61 | 0 | 0 | 12.4 | 5337
PH4100XPC#1 | W2\01\012\B | W2 | 1 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2025-04-18 13:12 | 2025-04-18 13:12 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\01\011\A1 | W2 | 1 | 11 | A1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2025-04-18 13:12 | 2025-04-18 13:12 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\01\010\A1 | W2 | 1 | 10 | A1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2025-04-18 13:12 | 2025-04-18 13:12 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\01\012\D | W2 | 1 | 12 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2025-04-18 13:12 | 2025-04-18 13:12 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\01\009\B | W2 | 1 | 9 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2025-04-18 13:12 | 2025-04-18 13:12 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\01\011\B | W2 | 1 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2025-04-18 13:12 | 2025-04-18 13:12 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\01\011\D | W2 | 1 | 11 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2025-04-18 13:12 | 2025-04-18 13:12 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\01\008\B | W2 | 1 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-04-18 13:12 | 2025-06-15 05:12 | 3225060.831 | 3225061 | [7 empty] | 0 | 0 | 62.15 | 9.95 | 5314.43
TS5500Shv | RS\47\003\B | RS | 47 | 3 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-04-19 01:55 | 2025-04-19 15:06 | 14137.6854 | 14138 | [7 empty] | 0 | 0 | 1.41 | 9.12 | 5590.16
TS Fleet 5 | RS\50\005\A | RS | 50 | 5 | A | 1 Prestrip - Thick | 57.0609 | 57.0609 | 57.0609 | 2025-04-19 05:46 | 2025-04-22 23:25 | 168158.7448 | 168159 | [7 empty] | 0 | 0 | 22.96 | 14.12 | 5201.01
TS5500Exc | RS\47\003\B | RS | 47 | 3 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2025-04-19 12:06 | 2025-04-20 01:17 | 11663.5905 | 11664 | [7 empty] | 0 | 0 | 1.16 | 9.12 | 5590.16
TS5500Shv | GG\19\020\D | GG | 19 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-04-19 15:06 | 2025-04-21 19:19 | 63679.0121 | [6 empty] | 63679 | 47419 | 4.74 | 0 | 0 | 6.92 | 5780
DRE1 | RS\46\005\D | RS | 46 | 5 | D | 6 DL | 100 | 100 | 100 | 2025-04-20 01:03 | 2025-04-24 17:56 | 394324.7522 |  |  |  | 14558 | 394325 | 223164 |  |  | 0 | 27.24 | 0 | 6.03 | 5888.8
TS5500Exc | RS\47\003\B | RS | 47 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-04-20 01:17 | 2025-04-21 08:11 | 38922.2665 | [6 empty] | 38922 | 27980 | 2.79 | 0 | 0 | 9.12 | 5590
PH4100A | SC\40\019\D | SC | 40 | 19 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-04-20 17:25 | 2025-04-28 14:05 | 311391.08 | 311391 | [7 empty] | 0 | 0 | 16.18 | 6.88 | 5807.19
DRE2 | GG\21\008\B | GG | 21 | 8 | B | 6 DL | 100 | 0 | 100 | 2025-04-20 22:12 | 2025-04-24 03:41 | 260634.0754 |  |  |  |  | 260634 | 200488 |  |  | 0 | 20.05 | 0 | 10.16 | 5494.46
TS5500Exc | RS\48\004\A | RS | 48 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-04-21 08:11 | 2025-04-22 02:50 | 23480.3594 | [6 empty] | 23480 | 16370 | 1.64 | 0 | 0 | 14.86 | 5129
TS5500Shv | RS\46\004\D | RS | 46 | 4 | D | 8 Coal Mining | 27.3 | 0 | 27.3 | 2025-04-21 19:19 | 2025-04-22 08:49 | 16462.076 | [6 empty] | 16462 | 12164 | 1.22 | 0 | 0 | 5.88 | 5904
TS5500Exc | RS\49\003\A | RS | 49 | 3 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-04-22 02:50 | 2025-04-22 21:25 | 23407.5652 | [6 empty] | 23408 | 16532 | 1.66 | 0 | 0 | 12.75 | 5313
TS5500Shv | RS\47\004\A | RS | 47 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-04-22 08:49 | 2025-04-23 03:37 | 22918.3635 | [6 empty] | 22918 | 15996 | 1.6 | 0 | 0 | 14.79 | 5133
TS5500Exc | RS\50\003\A | RS | 50 | 3 | A | 1 Prestrip - Thick | 11.1495 | 11.1495 | 11.1495 | 2025-04-22 21:25 | 2025-04-24 08:08 | 30865.2716 | 30865 | [7 empty] | 0 | 0 | 3.16 | 12.96 | 5298.15
TS Fleet 5 | RS\51\002\A | RS | 51 | 2 | A | 1 Prestrip - Thick | 63.1369 | 63.1369 | 63.1369 | 2025-04-22 23:25 | 2025-04-25 07:23 | 104994.0376 | 104994 | [7 empty] | 0 | 0 | 12.53 | 11.15 | 5448.53
TS5500Shv | RS\47\004\B | RS | 47 | 4 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-04-23 03:37 | 2025-04-23 16:58 | 14318.6064 | 14319 | [7 empty] | 0 | 0 | 1.43 | 9.11 | 5604.97
TS5500Shv | GG\19\021\D | GG | 19 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-04-23 16:58 | 2025-04-25 20:49 | 63224.8311 | [6 empty] | 63225 | 47080 | 4.71 | 0 | 0 | 6.84 | 5787
DRE2 | GG\21\007\B | GG | 21 | 7 | B | 6 DL | 100 | 0 | 100 | 2025-04-24 03:41 | 2025-04-27 02:51 | 239365.2145 |  |  |  |  | 239365 | 199471 |  |  | 0 | 19.95 | 0 | 10.32 | 5459.53
TS5500Exc | RS\47\004\B | RS | 47 | 4 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2025-04-24 08:08 | 2025-04-24 21:29 | 11812.8503 | 11813 | [7 empty] | 0 | 0 | 1.18 | 9.11 | 5604.97
DRE1 | RS\47\002\D | RS | 47 | 2 | D | 6 DL | 100 | 100 | 100 | 2025-04-24 17:56 | 2025-04-27 18:09 | 252252.7772 |  |  |  | 12969 | 252253 | 203186 |  |  | 0 | 27.99 | 0 | 5.46 | 5940.18
TS5500Exc | RS\47\004\B | RS | 47 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-04-24 21:29 | 2025-04-26 05:06 | 39824.3294 | [6 empty] | 39824 | 28551 | 2.85 | 0 | 0 | 9.11 | 5605
TS Fleet 5 | RS\51\003\A | RS | 51 | 3 | A | 1 Prestrip - Thick | 57.0775 | 57.0775 | 57.0775 | 2025-04-25 07:23 | 2025-04-28 16:57 | 153023.8703 | 153024 | [7 empty] | 0 | 0 | 15.7 | 13.16 | 5284.14
TS5500Shv | RS\46\005\D | RS | 46 | 5 | D | 7 PostStrip | 36.4462 | 0 | 36.4462 | 2025-04-25 20:49 | 2025-04-26 14:59 | 19475.6055 |  |  | 19476 | [5 empty] | 0 | 0 | 0 | 6.03 | 5888.8
TS5500Exc | RS\46\005\D | RS | 46 | 5 | D | 7 PostStrip | 63.5538 | 0 | 63.5538 | 2025-04-26 05:06 | 2025-04-27 19:30 | 33960.9834 |  |  | 33961 | [5 empty] | 0 | 0 | 0 | 6.03 | 5888.8
TS5500Shv | RS\47\005\A | RS | 47 | 5 | A | 1 Prestrip - Thick | 4.5391 | 4.5391 | 4.5391 | 2025-04-26 14:59 | 2025-04-27 11:33 | 21401.7282 | 21402 | [7 empty] | 0 | 0 | 2.05 | 16.2 | 5019.99
DRE2 | GG\21\006\B | GG | 21 | 6 | B | 6 DL | 100 | 0 | 100 | 2025-04-27 02:51 | 2025-04-30 08:30 | 261194.8339 |  |  |  |  | 261195 | 200919 |  |  | 0 | 20.15 | 0 | 9.93 | 5470.42
TS5500Shv | GG\19\022\D | GG | 19 | 22 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-04-27 11:33 | 2025-04-28 11:47 | 29552.3633 | [6 empty] | 29552 | 22040 | 2.2 | 0 | 0 | 6.71 | 5797
DRE1 | RS\47\003\D | RS | 47 | 3 | D | 6 DL | 100 | 100 | 100 | 2025-04-27 18:09 | 2025-05-01 18:29 | 336493.2863 |  |  |  | 17300 | 336493 | 271040 |  |  | 0 | 28.83 | 0 | 5.61 | 5927.33
TS5500Exc | RS\46\005\D | RS | 46 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-04-27 19:30 | 2025-04-28 22:11 | 33598.7025 | [6 empty] | 33599 | 24758 | 2.33 | 0 | 0 | 6.03 | 5889
TS5500Shv | RS\46\005\D | RS | 46 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-04-28 11:47 | 2025-04-29 14:27 | 32526.4035 | [6 empty] | 32526 | 23968 | 2.25 | 0 | 0 | 6.03 | 5889
PH4100A | SC\46\019\D | SC | 46 | 19 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-04-28 14:05 | 2025-05-03 14:23 | 199052.1713 | 199052 | [7 empty] | 0 | 0 | 16.85 | 6.93 | 5803.02
TS Fleet 5 | RS\51\004\A | RS | 51 | 4 | A | 1 Prestrip - Thick | 63.8017 | 63.8017 | 63.8017 | 2025-04-28 16:57 | 2025-05-03 16:37 | 224507.7017 | 224508 | [7 empty] | 0 | 0 | 22.84 | 14.69 | 5160.55
TS5500Exc | RS\47\005\A | RS | 47 | 5 | A | 8 Coal Mining | 82.5 | 0 | 82.5 | 2025-04-28 22:11 | 2025-04-30 05:11 | 39064.1508 | [6 empty] | 39064 | 27055 | 2.69 | 0 | 0 | 16.2 | 5020
TS5500Shv | RS\47\005\A | RS | 47 | 5 | A | 8 Coal Mining | 17.5 | 0 | 17.5 | 2025-04-29 14:27 | 2025-04-29 21:14 | 8265.0594 | [6 empty] | 8265 | 5724 | 0.57 | 0 | 0 | 16.2 | 5020
TS5500Shv | RS\47\002\D | RS | 47 | 2 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-04-29 21:14 | 2025-04-30 16:32 | 23525.2505 | [6 empty] | 23525 | 17558 | 2.25 | 0 | 0 | 5.46 | 5940
TS5500Exc | RS\47\005\B | RS | 47 | 5 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2025-04-30 05:11 | 2025-04-30 18:46 | 12009.7576 | 12010 | [7 empty] | 0 | 0 | 1.2 | 9.16 | 5608.61
DRE2 | GG\21\005\B | GG | 21 | 5 | B | 6 DL | 100 | 0 | 100 | 2025-04-30 08:30 | 2025-05-03 15:29 | 265688.7214 |  |  |  |  | 265689 | 204376 |  |  | 0 | 20.5 | 0 | 9.05 | 5527.7
TS6060#1 | GG\21\011\B | GG | 21 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-04-30 12:14 | 2025-05-02 00:31 | 49105.6579 | [6 empty] | 49106 | 36000 | 3.61 | 0 | 0 | 10.06 | 5518
TS5500Shv | RS\47\005\B | RS | 47 | 5 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-04-30 16:32 | 2025-05-01 06:06 | 14557.2819 | 14557 | [7 empty] | 0 | 0 | 1.45 | 9.16 | 5608.61
TS5500Exc | RS\47\002\D | RS | 47 | 2 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-04-30 18:46 | 2025-05-01 14:04 | 24300.8082 | [6 empty] | 24301 | 18137 | 2.33 | 0 | 0 | 5.46 | 5940
TS5500Shv | RS\47\005\B | RS | 47 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-05-01 06:06 | 2025-05-01 22:10 | 19588.1787 | [6 empty] | 19588 | 14043 | 1.4 | 0 | 0 | 9.16 | 5609
TS5500Exc | RS\47\005\B | RS | 47 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-05-01 14:04 | 2025-05-02 06:07 | 20233.9429 | [6 empty] | 20234 | 14506 | 1.45 | 0 | 0 | 9.16 | 5609
DRE1 | RS\47\004\D | RS | 47 | 4 | D | 6 DL | 100 | 100 | 100 | 2025-05-01 18:29 | 2025-05-05 16:15 | 327509.3218 |  |  |  | 16839 | 327509 | 263804 |  |  | 0 | 28.06 | 0 | 5.93 | 5899.06
TS5500Shv | RS\48\002\A | RS | 48 | 2 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-05-01 22:10 | 2025-05-02 08:25 | 12497.3236 | [6 empty] | 12497 | 8910 | 1.66 | 0 | 0 | 11.74 | 5399
TS6060#1 | GG\21\010\B | GG | 21 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-05-02 00:31 | 2025-05-03 13:21 | 49854.7824 | [6 empty] | 49855 | 36567 | 3.66 | 0 | 0 | 9.97 | 5530
TS5500Exc | RS\47\003\D | RS | 47 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-05-02 06:07 | 2025-05-04 04:09 | 57980.6428 | [6 empty] | 57981 | 43108 | 4.31 | 0 | 0 | 5.61 | 5927
TS5500Shv | RS\48\002\B | RS | 48 | 2 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-05-02 08:25 | 2025-05-02 15:23 | 7466.7578 | 7467 | [7 empty] | 0 | 0 | 1.35 | 9.09 | 5593.5
TS5500Shv | RS\48\003\A | RS | 48 | 3 | A | 1 Prestrip - Thick | 10.7225 | 10.7225 | 10.7225 | 2025-05-02 15:23 | 2025-05-03 22:55 | 32648.9763 | 32649 | [7 empty] | 0 | 0 | 3.37 | 12.54 | 5327.57
TS6060#1 | GG\21\008\B | GG | 21 | 8 | B | 8 Coal Mining | 30.4 | 0 | 30.4 | 2025-05-03 13:21 | 2025-05-04 01:05 | 15883.0641 | [6 empty] | 15883 | 11625 | 1.16 | 0 | 0 | 10.16 | 5494
PH4100A | SC\40\020\D | SC | 40 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-05-03 14:23 | 2025-05-08 00:28 | 174288.485 | 174288 | [7 empty] | 0 | 0 | 14.91 | 6.9 | 5804.89
DRE2 | GG\21\004\B | GG | 21 | 4 | B | 6 DL | 100 | 0 | 100 | 2025-05-03 15:29 | 2025-05-11 17:45 | 653457.0227 |  |  |  |  | 653457 | 311170 |  |  | 0 | 20.58 | 0 | 9.28 | 5524.87
TS Fleet 5 | RS\51\005\A | RS | 51 | 5 | A | 1 Prestrip - Thick | 51.4366 | 51.4366 | 51.4366 | 2025-05-03 16:37 | 2025-05-06 21:24 | 144027.8903 | 144028 | [7 empty] | 0 | 0 | 20.18 | 13.69 | 5241.26
TS5500Shv | GG\19\023\D | GG | 19 | 23 | D | 7 PostStrip | 50.9554 | 0 | 50.9554 | 2025-05-03 22:55 | 2025-05-04 23:18 | 26137.8018 |  |  | 26138 | [5 empty] | 0 | 0 | 0 | 6.48 | 5819.15
TS6060#1 | GG\21\009\B | GG | 21 | 9 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-05-04 01:05 | 2025-05-04 21:04 | 27036.6721 | [6 empty] | 27037 | 19814 | 1.98 | 0 | 0 | 9.97 | 5524
TS5500Exc | RS\48\002\B | RS | 48 | 2 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2025-05-04 04:09 | 2025-05-04 11:07 | 6160.0752 | 6160 | [7 empty] | 0 | 0 | 1.11 | 9.09 | 5593.5
TS5500Exc | RS\48\002\B | RS | 48 | 2 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-05-04 11:07 | 2025-05-04 20:23 | 11661.4951 | [6 empty] | 11661 | 8415 | 1.48 | 0 | 0 | 9.09 | 5594
TS5500Exc | RS\48\003\A | RS | 48 | 3 | A | 8 Coal Mining | 81.7 | 0 | 81.7 | 2025-05-04 20:23 | 2025-05-06 02:22 | 37776.026 | [6 empty] | 37776 | 26731 | 2.67 | 0 | 0 | 12.54 | 5328
TS6060#1 | GG\21\007\B | GG | 21 | 7 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-05-04 21:04 | 2025-05-05 17:00 | 26986.2777 | [6 empty] | 26986 | 19748 | 1.98 | 0 | 0 | 10.32 | 5460
TS5500Shv | RS\48\002\B | RS | 48 | 2 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-05-04 23:18 | 2025-05-05 08:34 | 11289.3198 | [6 empty] | 11289 | 8147 | 1.43 | 0 | 0 | 9.09 | 5594
TS5500Shv | GG\19\023\D | GG | 19 | 23 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-05-05 08:34 | 2025-05-06 10:17 | 31366.9505 | [6 empty] | 31367 | 23506 | 2.29 | 0 | 0 | 6.48 | 5819
DRE1 | RS\47\005\D | RS | 47 | 5 | D | 6 DL | 100 | 100 | 100 | 2025-05-05 16:15 | 2025-05-09 17:49 | 340819.0575 |  |  |  | 12523 | 340819 | 192670 |  |  | 0 | 27.67 | 0 | 6.08 | 5883.91
TS6060#1 | GG\19\023\D | GG | 19 | 23 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-05-05 17:00 | 2025-05-06 18:44 | 34813.8682 | [6 empty] | 34814 | 26089 | 2.54 | 0 | 0 | 6.48 | 5819
TS5500Exc | RS\47\004\D | RS | 47 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-05-06 02:22 | 2025-05-08 02:00 | 59987.8736 | [6 empty] | 59988 | 44289 | 4.43 | 0 | 0 | 5.93 | 5899
TS5500Shv | GG\21\012\B | GG | 21 | 12 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-05-06 10:17 | 2025-05-07 05:15 | 23117.9538 | [6 empty] | 23118 | 16887 | 1.69 | 0 | 0 | 10.82 | 5447
TS6060#1 | RS\49\005\A | RS | 49 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-05-06 18:44 | 2025-05-19 16:51 | 310667.2173 | 310667 | [7 empty] | 0 | 0 | 41.02 | 14.95 | 5127.91
TS Fleet 5 | GG\24\004\X1 | GG | 24 | 4 | X1 | 1 Prestrip - Thick | 54.8161 | 54.8161 | 54.8161 | 2025-05-06 21:24 | 2025-05-21 03:53 | 642498.5898 | 642499 | [7 empty] | 0 | 0 | 52.53 | 10.92 | 5285.98
TS5500Shv | RS\48\003\A | RS | 48 | 3 | A | 8 Coal Mining | 18.3 | 0 | 18.3 | 2025-05-07 05:15 | 2025-05-07 12:12 | 8483.951 | [6 empty] | 8484 | 6003 | 0.6 | 0 | 0 | 12.54 | 5328
TS5500Shv | GG\24\004\X1 | GG | 24 | 4 | X1 | 1 Prestrip - Thick | 20.5498 | 20.5498 | 20.5498 | 2025-05-07 12:12 | 2025-05-16 20:41 | 240864.135 | 240864 | [7 empty] | 0 | 0 | 19.69 | 10.92 | 5285.98
PH4100A | SC\46\020\D | SC | 46 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-05-08 00:28 | 2025-05-12 10:08 | 173238.6868 | 173239 | [7 empty] | 0 | 0 | 14.81 | 6.99 | 5797.1
TS5500Exc | GG\24\004\X1 | GG | 24 | 4 | X1 | 1 Prestrip - Thick | 16.9442 | 16.9442 | 16.9442 | 2025-05-08 02:00 | 2025-05-17 10:28 | 198602.2757 | 198602 | [7 empty] | 0 | 0 | 16.24 | 10.92 | 5285.98
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2025-05-09 17:49 | 2025-05-12 17:49
DRE2 | GG\20\012\D | GG | 20 | 12 | D | 6 DL | 100 | 100 | 100 | 2025-05-11 17:45 | 2025-05-18 01:05 | 509034.1384 |  |  |  | 11852 | 509034 | 225184 |  |  | 0 | 23.73 | 0 | 6.77 | 5791.23
PH4100A | SC\40\021\D | SC | 40 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-05-12 10:08 | 2025-05-17 12:41 | 200364.7005 | 200365 | [7 empty] | 0 | 0 | 16.99 | 7.33 | 5766.79
DRE1 | RS\48\002\D | RS | 48 | 2 | D | 6 DL | 100 | 100 | 100 | 2025-05-12 17:49 | 2025-05-16 00:33 | 275012.3328 |  |  |  | 14139 | 275012 | 221518 |  |  | 0 | 28.17 | 0 | 5.47 | 5938.83
DRE1 | SC\39\018\D | SC | 39 | 18 | D | 6 DL | 100 | 0 | 100 | 2025-05-16 00:33 | 2025-05-23 01:43 | 590971.139 |  |  |  | 44941 | 590971 | 404467 |  |  | 0 | 40 | 0 | 6.88 | 5802.84
TS5500Shv | RS\47\005\D | RS | 47 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2025-05-16 20:41 | 2025-05-18 14:54 | 45262.0605 |  |  | 45262 | [5 empty] | 0 | 0 | 0 | 6.08 | 5883.91
TS5500Exc | RS\48\002\D | RS | 48 | 2 | D | 8 Coal Mining | 82 | 0 | 82 | 2025-05-17 10:28 | 2025-05-18 20:07 | 42369.31 | [6 empty] | 42369 | 31624 | 3.74 | 0 | 0 | 5.47 | 5939
PH4100A | SC\46\021\D | SC | 46 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-05-17 12:41 | 2025-05-22 04:05 | 182413.0409 | 182413 | [7 empty] | 0 | 0 | 15.48 | 7.3 | 5768.99
DRE2 | GG\20\011\D | GG | 20 | 11 | D | 6 DL | 100 | 100 | 100 | 2025-05-18 01:05 | 2025-05-24 08:07 | 508069.4708 |  |  |  | 9219 | 508069 | 221260 |  |  | 0 | 23.06 | 0 | 6.55 | 5809.71
TS5500Shv | GG\21\008\B | GG | 21 | 8 | B | 8 Coal Mining | 69.6 | 0 | 69.6 | 2025-05-18 14:54 | 2025-05-19 20:41 | 36318.7604 | [6 empty] | 36319 | 26582 | 2.66 | 0 | 0 | 10.16 | 5494
TS5500Exc | RS\47\005\D | RS | 47 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-05-18 20:07 | 2025-05-20 16:06 | 55410.701 | [6 empty] | 55411 | 40791 | 4.53 | 0 | 0 | 6.08 | 5884
TS6060#1 | RS\48\003\B | RS | 48 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-05-19 16:51 | 2025-05-20 17:28 | 25407.4146 | 25407 | [7 empty] | 0 | 0 | 2.54 | 9.08 | 5590.62
TS5500Shv | GG\21\009\B | GG | 21 | 9 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-05-19 20:41 | 2025-05-20 16:40 | 24359.7738 | [6 empty] | 24360 | 17852 | 1.79 | 0 | 0 | 9.97 | 5524
TS5500Exc | GG\24\006\X1 | GG | 24 | 6 | X1 | 1 Prestrip - Thick | 4.6872 | 4.6872 | 4.6872 | 2025-05-20 16:06 | 2025-05-22 15:46 | 42192.3014 | 42192 | [7 empty] | 0 | 0 | 4.15 | 11.43 | 5278.96
TS5500Shv | GG\21\007\B | GG | 21 | 7 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-05-20 16:40 | 2025-05-21 12:36 | 24314.369 | [6 empty] | 24314 | 17793 | 1.78 | 0 | 0 | 10.32 | 5460
TS6060#1 | RS\50\002\A | RS | 50 | 2 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-05-20 17:28 | 2025-05-26 05:32 | 133823.559 | 133824 | [7 empty] | 0 | 0 | 21.94 | 12.17 | 5367.62
TS Fleet 5 | GG\24\005\X1 | GG | 24 | 5 | X1 | 1 Prestrip - Thick | 45.2587 | 45.2587 | 45.2587 | 2025-05-21 03:53 | 2025-05-30 10:32 | 417707.398 | 417707 | [7 empty] | 0 | 0 | 38.75 | 10.88 | 5294.94
TS5500Shv | RS\48\002\D | RS | 48 | 2 | D | 8 Coal Mining | 18 | 0 | 18 | 2025-05-21 12:36 | 2025-05-21 20:14 | 9294.8758 | [6 empty] | 9295 | 6937 | 0.82 | 0 | 0 | 5.47 | 5939
TS5500Shv | RS\48\004\A | RS | 48 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-05-21 20:14 | 2025-05-22 14:52 | 22730.9862 | [6 empty] | 22731 | 15848 | 1.59 | 0 | 0 | 14.86 | 5129
PH4100A | SC\40\022\D | SC | 40 | 22 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-05-22 04:05 | 2025-05-26 07:57 | 163829.8063 | 163830 | [7 empty] | 0 | 0 | 13.99 | 7.41 | 5761.04
TS5500Shv | RS\48\003\B | RS | 48 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-05-22 14:52 | 2025-05-23 06:31 | 19090.1659 | [6 empty] | 19090 | 13694 | 1.37 | 0 | 0 | 9.08 | 5591
TS5500Exc | RS\48\003\B | RS | 48 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-05-22 15:46 | 2025-05-23 07:25 | 19719.5121 | [6 empty] | 19720 | 14145 | 1.41 | 0 | 0 | 9.08 | 5591
DRE1 | SC\39\019\D | SC | 39 | 19 | D | 6 DL | 100 | 0 | 100 | 2025-05-23 01:43 | 2025-06-01 13:33 | 795850.0767 |  |  |  | 60521 | 795850 | 544688 |  |  | 0 | 40 | 0 | 6.8 | 5814.6
TS5500Shv | GG\21\006\B | GG | 21 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-05-23 06:31 | 2025-05-24 22:51 | 49166.5406 | [6 empty] | 49167 | 36092 | 3.61 | 0 | 0 | 9.93 | 5470
TS5500Exc | GG\24\007\X1 | GG | 24 | 7 | X1 | 1 Prestrip - Thick | 17.7282 | 17.7282 | 17.7282 | 2025-05-23 07:25 | 2025-05-30 11:17 | 152171.3756 | 152171 | [7 empty] | 0 | 0 | 14.82 | 12.29 | 5248.55
DRE2 | GG\20\010\D | GG | 20 | 10 | D | 6 DL | 100 | 100 | 100 | 2025-05-24 08:07 | 2025-05-30 00:05 | 457316.6333 |  |  |  | 10648 | 457317 | 202305 |  |  | 0 | 21.3 | 0 | 6.42 | 5821.31
TS5500Shv | GG\21\005\B | GG | 21 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-05-24 22:51 | 2025-05-26 12:49 | 46297.269 | [6 empty] | 46297 | 34168 | 3.41 | 0 | 0 | 9.05 | 5528
TS6060#1 | RS\48\004\B | RS | 48 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-05-26 05:32 | 2025-05-27 06:02 | 25295.1778 | 25295 | [7 empty] | 0 | 0 | 2.54 | 9.1 | 5604.19
PH4100A | SC\46\022\D | SC | 46 | 22 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-05-26 07:57 | 2025-05-29 21:46 | 140946.7441 | 140947 | [7 empty] | 0 | 0 | 12.1 | 7.4 | 5762.07
TS5500Shv | GG\24\006\X1 | GG | 24 | 6 | X1 | 1 Prestrip - Thick | 5.6295 | 5.6295 | 5.6295 | 2025-05-26 12:49 | 2025-05-28 12:28 | 50674.3141 | 50674 | [7 empty] | 0 | 0 | 4.98 | 11.43 | 5278.96
TS6060#1 | RS\50\003\A | RS | 50 | 3 | A | 1 Prestrip - Thick | 30.353 | 30.353 | 30.353 | 2025-05-27 06:02 | 2025-05-30 18:33 | 84026.2113 | 84026 | [7 empty] | 0 | 0 | 8.6 | 12.96 | 5298.15
TS5500Shv | GG\21\004\B | GG | 21 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-05-28 12:28 | 2025-05-31 02:18 | 75402.3946 | [6 empty] | 75402 | 55562 | 3.84 | 0 | 0 | 9.28 | 5525
PH4100A | SC\40\023\D | SC | 40 | 23 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-05-29 21:46 | 2025-06-02 02:11 | 124997.3849 | 124997 | [7 empty] | 0 | 0 | 10.79 | 7.36 | 5766.65
DRE2 | GG\20\009\D | GG | 20 | 9 | D | 6 DL | 100 | 100 | 100 | 2025-05-30 00:05 | 2025-06-04 10:47 | 439661.2127 |  |  |  | 10237 | 439661 | 194495 |  |  | 0 | 20.48 | 0 | 6.46 | 5818.88
TS Fleet 5 | GG\24\006\X1 | GG | 24 | 6 | X1 | 1 Prestrip - Thick | 41.063 | 41.063 | 41.063 | 2025-05-30 10:32 | 2025-06-07 15:34 | 369629.1763 | 369629 | [7 empty] | 0 | 0 | 36.35 | 11.43 | 5278.96
TS5500Exc | GG\24\010\X1 | GG | 24 | 10 | X1 | 1 Prestrip - Thick | 14.8172 | 14.8172 | 14.8172 | 2025-05-30 11:17 | 2025-06-04 03:19 | 99180.112 | 99180 | [7 empty] | 0 | 0 | 11.24 | 14.77 | 5114.38
TS6060#1 | RS\50\004\A | RS | 50 | 4 | A | 1 Prestrip - Thick | 30.1234 | 30.1234 | 30.1234 | 2025-05-30 18:33 | 2025-06-04 14:36 | 115591.2679 | 115591 | [7 empty] | 0 | 0 | 11.75 | 14.63 | 5158.95
TS5500Shv | GG\20\012\D | GG | 20 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-05-31 02:18 | 2025-06-02 04:38 | 61365.554 | [6 empty] | 61366 | 45839 | 4.58 | 0 | 0 | 6.77 | 5791
DRE1 | RS\48\003\D | RS | 48 | 3 | D | 6 DL | 100 | 100 | 100 | 2025-06-01 13:33 | 2025-06-05 14:46 | 339587.4516 |  |  |  | 17460 | 339587 | 273532 |  |  | 0 | 29.1 | 0 | 5.65 | 5923.58
PH4100A | SC\46\023\D | SC | 46 | 23 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-06-02 02:11 | 2025-06-04 18:09 | 104788.3603 | 104788 | [7 empty] | 0 | 0 | 9.07 | 7.41 | 5762.81
TS5500Shv | RS\48\004\B | RS | 48 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-06-02 04:38 | 2025-06-03 12:39 | 39038.9452 | [6 empty] | 39039 | 27946 | 2.81 | 0 | 0 | 9.1 | 5604
TS5500Shv | RS\48\005\A | RS | 48 | 5 | A | 8 Coal Mining | 90.1 | 0 | 90.1 | 2025-06-03 12:39 | 2025-06-04 16:49 | 34357.2405 | [6 empty] | 34357 | 23854 | 2.87 | 0 | 0 | 15.7 | 5063
TS5500Exc | SC\39\018\D | SC | 39 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-06-04 03:19 | 2025-06-05 15:37 | 45722.6727 | [6 empty] | 45723 | 34221 | 3.86 | 0 | 0 | 6.88 | 5803
DRE2 | GG\20\008\D | GG | 20 | 8 | D | 6 DL | 100 | 100 | 100 | 2025-06-04 10:47 | 2025-06-09 18:20 | 429054.9362 |  |  |  | 7990 | 429055 | 191756 |  |  | 0 | 19.98 | 0 | 6.53 | 5812.92
TS6060#1 | RS\50\005\A | RS | 50 | 5 | A | 1 Prestrip - Thick | 30.2686 | 30.2686 | 30.2686 | 2025-06-04 14:36 | 2025-06-08 07:53 | 89201.6517 | 89202 | [7 empty] | 0 | 0 | 12.18 | 14.12 | 5201.01
TS5500Shv | RS\49\002\A | RS | 49 | 2 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-06-04 16:49 | 2025-06-05 04:16 | 13958.1211 | [6 empty] | 13958 | 9938 | 1.65 | 0 | 0 | 11.95 | 5384
PH4100A | SC\40\024\D | SC | 40 | 24 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-06-04 18:09 | 2025-06-07 16:56 | 115880.8818 | 115881 | [7 empty] | 0 | 0 | 9.99 | 7.41 | 5762.12
TS5500Shv | GG\20\011\D | GG | 20 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-06-05 04:16 | 2025-06-07 05:31 | 60058.4184 | [6 empty] | 60058 | 44933 | 4.49 | 0 | 0 | 6.55 | 5810
DRE1 | RS\48\004\D | RS | 48 | 4 | D | 6 DL | 100 | 100 | 100 | 2025-06-05 14:46 | 2025-06-09 13:00 | 329172.9445 |  |  |  | 16924 | 329173 | 265144 |  |  | 0 | 28.23 | 0 | 5.98 | 5894.56
TS5500Exc | RS\48\003\D | RS | 48 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-06-05 15:37 | 2025-06-06 14:48 | 29209.0454 | [6 empty] | 29209 | 21682 | 2.17 | 0 | 0 | 5.65 | 5924
TS5500Exc | GG\24\012\X1 | GG | 24 | 12 | X1 | 1 Prestrip - Thick | 17.7653 | 17.7653 | 17.7653 | 2025-06-06 14:48 | 2025-06-10 18:56 | 88683.2 | 88683 | [7 empty] | 0 | 0 | 8.73 | 14.92 | 5106.32
TS5500Shv | RS\48\003\D | RS | 48 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-06-07 05:31 | 2025-06-08 04:42 | 28276.8418 | [6 empty] | 28277 | 20990 | 2.1 | 0 | 0 | 5.65 | 5924
TS Fleet 5 | GG\24\007\X1 | GG | 24 | 7 | X1 | 1 Prestrip - Thick | 38.5985 | 38.5985 | 38.5985 | 2025-06-07 15:34 | 2025-06-15 00:10 | 331312.4708 | 331312 | [7 empty] | 0 | 0 | 32.27 | 12.29 | 5248.55
PH4100A | SC\46\024\D | SC | 46 | 24 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-06-07 16:56 | 2025-06-10 12:25 | 110529.156 | 110529 | [7 empty] | 0 | 0 | 9.54 | 7.55 | 5749.83
TS5500Shv | GG\20\010\D | GG | 20 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-06-08 04:42 | 2025-06-10 06:41 | 60941.4455 | [6 empty] | 60941 | 45631 | 4.56 | 0 | 0 | 6.42 | 5821
TS6060#1 | RS\48\005\B | RS | 48 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-06-08 07:53 | 2025-06-09 05:40 | 22489.8462 | 22490 | [7 empty] | 0 | 0 | 2.71 | 9.17 | 5601.2
TS6060#1 | RS\49\002\B | RS | 49 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-06-09 05:40 | 2025-06-09 20:43 | 15521.27 | 15521 | [7 empty] | 0 | 0 | 2.51 | 9.07 | 5593.87
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2025-06-09 13:00 | 2025-06-12 13:00
DRE2 | GG\20\007\D | GG | 20 | 7 | D | 6 DL | 100 | 100 | 100 | 2025-06-09 18:20 | 2025-06-15 02:19 | 430526.0874 |  |  |  | 10024 | 430526 | 190454 |  |  | 0 | 20.05 | 0 | 6.59 | 5807.19
TS6060#1 | RS\51\002\A | RS | 51 | 2 | A | 1 Prestrip - Thick | 33.785 | 33.785 | 33.785 | 2025-06-09 20:43 | 2025-06-12 04:27 | 56183.0465 | 56183 | [7 empty] | 0 | 0 | 6.71 | 11.15 | 5448.53
TS5500Shv | RS\49\003\A | RS | 49 | 3 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-06-10 06:41 | 2025-06-11 01:16 | 22660.5153 | [6 empty] | 22661 | 16005 | 1.6 | 0 | 0 | 12.75 | 5313
PH4100A | SC\40\025\D | SC | 40 | 25 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-06-10 12:25 | 2025-06-14 11:24 | 154796.4065 | 154796 | [7 empty] | 0 | 0 | 13.23 | 7.24 | 5777.62
TS5500Exc | RS\48\004\D | RS | 48 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-06-10 18:56 | 2025-06-12 18:13 | 59555.0325 | [6 empty] | 59555 | 43934 | 4.39 | 0 | 0 | 5.98 | 5895
TS5500Shv | RS\48\005\B | RS | 48 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-06-11 01:16 | 2025-06-11 14:16 | 15845.6562 | [6 empty] | 15846 | 11334 | 1.37 | 0 | 0 | 9.17 | 5601
TS5500Shv | GG\20\009\D | GG | 20 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-06-11 14:16 | 2025-06-13 16:44 | 61535.8637 | [6 empty] | 61536 | 46040 | 4.6 | 0 | 0 | 6.46 | 5819
TS6060#1 | RS\49\003\B | RS | 49 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-06-12 04:27 | 2025-06-13 04:48 | 25117.9625 | 25118 | [7 empty] | 0 | 0 | 2.52 | 9.05 | 5590.9
DRE1 | SC\39\020\D | SC | 39 | 20 | D | 6 DL | 100 | 0 | 100 | 2025-06-12 13:00 | 2025-06-20 00:35 | 627297.9581 |  |  |  | 47703 | 627298 | 429329 |  |  | 0 | 40 | 0 | 6.83 | 5812.04
TS5500Exc | RS\48\005\B | RS | 48 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-06-12 18:13 | 2025-06-13 07:13 | 16368.0405 | [6 empty] | 16368 | 11708 | 1.42 | 0 | 0 | 9.17 | 5601
TS6060#1 | RS\51\003\A | RS | 51 | 3 | A | 1 Prestrip - Thick | 30.018 | 30.018 | 30.018 | 2025-06-13 04:48 | 2025-06-16 14:03 | 80477.9018 | 80478 | [7 empty] | 0 | 0 | 8.26 | 13.16 | 5284.14
TS5500Exc | RS\49\002\B | RS | 49 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-06-13 07:13 | 2025-06-14 03:27 | 25501.0745 | [6 empty] | 25501 | 18389 | 2.9 | 0 | 0 | 9.07 | 5594
TS5500Shv | GG\24\010\X1 | GG | 24 | 10 | X1 | 1 Prestrip - Thick | 15.5561 | 15.5561 | 15.5561 | 2025-06-13 16:44 | 2025-06-17 18:33 | 104125.8035 | 104126 | [7 empty] | 0 | 0 | 11.8 | 14.77 | 5114.38
TS5500Exc | RS\49\004\A | RS | 49 | 4 | A | 8 Coal Mining | 38.6 | 0 | 38.6 | 2025-06-14 03:27 | 2025-06-14 17:26 | 17602.0309 | [6 empty] | 17602 | 12277 | 1.23 | 0 | 0 | 14.75 | 5143
PH4100A | SC\46\025\D | SC | 46 | 25 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-06-14 11:24 | 2025-06-18 11:46 | 156968.5712 | 156969 | [7 empty] | 0 | 0 | 13.48 | 7.28 | 5773.74
TS5500Exc | RS\49\003\B | RS | 49 | 3 | B | 8 Coal Mining | 44.4 | 0 | 44.4 | 2025-06-14 17:26 | 2025-06-15 07:03 | 17149.5983 | [6 empty] | 17150 | 12284 | 1.23 | 0 | 0 | 9.05 | 5591
TS Fleet 5 | GG\24\008\X1 | GG | 24 | 8 | X1 | 1 Prestrip - Thick | 45.6203 | 45.6203 | 45.6203 | 2025-06-15 00:10 | 2025-06-23 03:39 | 366712.4855 | 366712 | [7 empty] | 0 | 0 | 38.25 | 13.29 | 5199.88
DRE2 | GG\20\006\D | GG | 20 | 6 | D | 6 DL | 100 | 100 | 100 | 2025-06-15 02:19 | 2025-06-20 08:47 | 425395.2072 |  |  |  | 7922 | 425395 | 190121 |  |  | 0 | 19.8 | 0 | 6.65 | 5801.12
PH4100XPC#1 | GG\24\004\X1 | GG | 24 | 4 | X1 | 1 Prestrip - Thick | 100 | 7.6899 | 7.6899 | 2025-06-15 05:12 | 2025-06-16 19:38 | 90133.3626 | 90133 | [7 empty] | 0 | 0 | 7.37 | 10.92 | 5285.98
TS5500Exc | W2\01\008\B | W2 | 1 | 8 | B | 8 Coal Mining | 0.5 | 0 | 0.5 | 2025-06-15 07:03 | 2025-06-15 07:47 | 922.0425 | [6 empty] | 922 | 648 | 0.02 | 0 | 0 | 9.95 | 5314
TS5500Exc | SC\39\019\D | SC | 39 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-06-15 07:47 | 2025-06-18 02:30 | 84046.1041 | [6 empty] | 84046 | 62961 | 4.49 | 0 | 0 | 6.8 | 5815
TS6060#1 | W2\01\008\B | W2 | 1 | 8 | B | 8 Coal Mining | 99.5 | 0 | 99.5 | 2025-06-16 14:03 | 2025-06-22 00:38 | 176730.1001 | [6 empty] | 176730 | 124126 | 2.97 | 0 | 0 | 9.95 | 5314
PH4100XPC#1 | GG\24\005\X1 | GG | 24 | 5 | X1 | 1 Prestrip - Thick | 100 | 54.7413 | 54.7413 | 2025-06-16 19:38 | 2025-06-26 01:24 | 505225.8259 | 505226 | [7 empty] | 0 | 0 | 46.87 | 10.88 | 5294.94
TS5500Shv | GG\24\004\X1 | GG | 24 | 4 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-06-17 18:33 | 2025-06-18 00:15 | 6959.3664 | [6 empty] | 6959 | 5165 | 0.49 | 0 | 0 | 10.92 | 5286
TS5500Shv | GG\20\008\D | GG | 20 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-06-18 00:15 | 2025-06-20 02:47 | 61618.4477 | [6 empty] | 61618 | 46065 | 4.61 | 0 | 0 | 6.53 | 5813
TS5500Exc | GG\24\013\X1 | GG | 24 | 13 | X1 | 1 Prestrip - Thick | 5.1382 | 5.1382 | 5.1382 | 2025-06-18 02:30 | 2025-06-19 01:23 | 20285.5987 | 20286 | [7 empty] | 0 | 0 | 2.05 | 14.72 | 5121.24
PH4100A | SC\40\026\D | SC | 40 | 26 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-06-18 11:46 | 2025-06-24 23:53 | 251911.9371 | 251912 | [7 empty] | 0 | 0 | 19.82 | 6.93 | 5805.23
TS5500Exc | GG\24\017\X1 | GG | 24 | 17 | X1 | 1 Prestrip - Thick | 8.0787 | 8.0787 | 8.0787 | 2025-06-19 01:23 | 2025-06-19 17:13 | 14046.1747 | 14046 | [7 empty] | 0 | 0 | 1.94 | 14.31 | 5152.61
TS5500Exc | GG\24\018\X2 | GG | 24 | 18 | X2 | 1 Prestrip - Thick | 17.9386 | 0 | 17.9386 | 2025-06-19 17:13 | 2025-06-21 13:28 | 39239.5442 | 39240 | [7 empty] | 0 | 0 | 4.05 | 0 | 0
DRE1 | RS\48\005\D | RS | 48 | 5 | D | 6 DL | 100 | 100 | 100 | 2025-06-20 00:35 | 2025-06-23 09:37 | 283029.2254 |  |  |  | 10349 | 283029 | 159819 |  |  | 0 | 28.12 | 0 | 6.1 | 5880.97
TS5500Shv | GG\20\007\D | GG | 20 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-06-20 02:47 | 2025-06-22 05:00 | 61233.6067 | [6 empty] | 61234 | 45777 | 4.58 | 0 | 0 | 6.59 | 5807
DRE2 | GG\20\005\D | GG | 20 | 5 | D | 6 DL | 100 | 100 | 100 | 2025-06-20 08:47 | 2025-06-25 13:17 | 418771.2639 |  |  |  | 7798 | 418771 | 187160 |  |  | 0 | 19.49 | 0 | 6.69 | 5797.85
TS5500Exc | RS\49\005\A | RS | 49 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2025-06-21 13:28 | 2025-06-22 13:49 | 30677.6746 | [6 empty] | 30678 | 21368 | 3.08 | 0 | 0 | 14.95 | 5128
TS6060#1 | GG\24\004\X1 | GG | 24 | 4 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-06-22 00:38 | 2025-06-22 06:20 | 7724.1319 | [6 empty] | 7724 | 5732 | 0.54 | 0 | 0 | 10.92 | 5286
TS5500Shv | GG\20\006\D | GG | 20 | 6 | D | 8 Coal Mining | 28.1 | 0 | 28.1 | 2025-06-22 05:00 | 2025-06-22 18:59 | 17046.7238 | [6 empty] | 17047 | 12754 | 1.28 | 0 | 0 | 6.65 | 5801
TS6060#1 | GG\20\006\D | GG | 20 | 6 | D | 8 Coal Mining | 71.9 | 0 | 71.9 | 2025-06-22 06:20 | 2025-06-23 14:36 | 43662.8851 | [6 empty] | 43663 | 32667 | 3.27 | 0 | 0 | 6.65 | 5801
TS5500Exc | GG\24\004\B | GG | 24 | 4 | B | 1 Prestrip - Thick | 47.3833 | 47.3833 | 47.3833 | 2025-06-22 13:49 | 2025-06-25 12:55 | 62878.0346 | 62878 | [7 empty] | 0 | 0 | 6.52 | 9.57 | 5507.73
TS5500Shv | GG\24\004\B | GG | 24 | 4 | B | 1 Prestrip - Thick | 24.8623 | 24.8623 | 24.8623 | 2025-06-22 18:59 | 2025-06-24 01:45 | 32992.4671 | 32992 | [7 empty] | 0 | 0 | 3.42 | 9.57 | 5507.73
TS Fleet 5 | GG\24\004\B | GG | 24 | 4 | B | 1 Prestrip - Thick | 16.8377 | 16.8377 | 16.8377 | 2025-06-23 03:39 | 2025-06-23 15:34 | 22343.8218 | 22344 | [7 empty] | 0 | 0 | 2.32 | 9.57 | 5507.73
DRE1 | RS\49\002\D | RS | 49 | 2 | D | 6 DL | 100 | 100 | 100 | 2025-06-23 09:37 | 2025-06-26 22:54 | 297933.2049 |  |  |  | 15318 | 297933 | 239980 |  |  | 0 | 28.32 | 0 | 5.56 | 5931.65
TS6060#1 | RS\49\005\B | RS | 49 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-06-23 14:36 | 2025-06-24 09:31 | 19516.6581 | 19517 | [7 empty] | 0 | 0 | 2.82 | 9.15 | 5594.85
TS Fleet 5 | GG\24\009\X2 | GG | 24 | 9 | X2 | 1 Prestrip - Thick | 44.8461 | 0 | 44.8461 | 2025-06-23 15:34 | 2025-07-02 10:07 | 395019.6514 | 395020 | [7 empty] | 0 | 0 | 39.89 | 0 | 0
TS5500Shv | RS\48\005\D | RS | 48 | 5 | D | 7 PostStrip | 36.055 | 0 | 36.055 | 2025-06-24 01:45 | 2025-06-24 14:08 | 13270.0374 |  |  | 13270 | [5 empty] | 0 | 0 | 0 | 6.1 | 5880.97
TS6060#1 | RS\51\004\A | RS | 51 | 4 | A | 1 Prestrip - Thick | 31.9395 | 31.9395 | 31.9395 | 2025-06-24 09:31 | 2025-06-29 02:33 | 112389.7542 | 112390 | [7 empty] | 0 | 0 | 11.43 | 14.69 | 5160.55
TS5500Shv | RS\49\004\A | RS | 49 | 4 | A | 8 Coal Mining | 61.4 | 0 | 61.4 | 2025-06-24 14:08 | 2025-06-25 13:06 | 28010.3133 | [6 empty] | 28010 | 19536 | 1.96 | 0 | 0 | 14.75 | 5143
PH4100A | SC\46\026\D | SC | 46 | 26 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-06-24 23:53 | 2025-07-01 19:18 | 263125.3925 | 263125 | [7 empty] | 0 | 0 | 21.11 | 6.94 | 5803.8
TS5500Exc | RS\48\005\D | RS | 48 | 5 | D | 7 PostStrip | 63.945 | 0 | 63.945 | 2025-06-25 12:55 | 2025-06-26 15:32 | 23534.9304 |  |  | 23535 | [5 empty] | 0 | 0 | 0 | 6.1 | 5880.97
TS5500Shv | RS\49\003\B | RS | 49 | 3 | B | 8 Coal Mining | 55.6 | 0 | 55.6 | 2025-06-25 13:06 | 2025-06-26 06:44 | 21487.9823 | [6 empty] | 21488 | 15392 | 1.54 | 0 | 0 | 9.05 | 5591
DRE2 | GG\20\004\D | GG | 20 | 4 | D | 6 DL | 100 | 100 | 100 | 2025-06-25 13:17 | 2025-07-03 13:09 | 645381.9328 |  |  |  | 10577 | 645382 | 185685 |  |  | 0 | 19.39 | 0 | 6.63 | 5802.43
PH4100XPC#1 | GG\24\004\B | GG | 24 | 4 | B | 1 Prestrip - Thick | 100 | 10.9167 | 10.9167 | 2025-06-26 01:24 | 2025-06-26 07:48 | 14486.586 | 14487 | [7 empty] | 0 | 0 | 1.5 | 9.57 | 5507.73
TS5500Shv | GG\24\005\X1 | GG | 24 | 5 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-06-26 06:44 | 2025-06-26 19:26 | 15490.9271 | [6 empty] | 15491 | 11496 | 1.13 | 0 | 0 | 10.88 | 5295
PH4100XPC#1 | GG\24\006\X1 | GG | 24 | 6 | X1 | 1 Prestrip - Thick | 100 | 48.6202 | 48.6202 | 2025-06-26 07:48 | 2025-07-04 12:03 | 437655.084 | 437655 | [7 empty] | 0 | 0 | 43.04 | 11.43 | 5278.96
TS5500Exc | RS\48\005\D | RS | 48 | 5 | D | 8 Coal Mining | 70.1 | 0 | 70.1 | 2025-06-26 15:32 | 2025-06-27 16:21 | 31266.0105 | [6 empty] | 31266 | 22995 | 3.15 | 0 | 0 | 6.1 | 5881
TS5500Shv | GG\24\005\B | GG | 24 | 5 | B | 1 Prestrip - Thick | 58.2928 | 58.2928 | 58.2928 | 2025-06-26 19:26 | 2025-06-29 22:09 | 80099.3675 | 80099 | [7 empty] | 0 | 0 | 8.03 | 9.91 | 5478.1
DRE1 | RS\49\003\D | RS | 49 | 3 | D | 6 DL | 100 | 100 | 100 | 2025-06-26 22:54 | 2025-07-01 00:29 | 340853.0443 |  |  |  | 17525 | 340853 | 274552 |  |  | 0 | 29.22 | 0 | 5.7 | 5918.97
TS5500Exc | GG\24\005\B | GG | 24 | 5 | B | 1 Prestrip - Thick | 41.7072 | 41.7072 | 41.7072 | 2025-06-27 16:21 | 2025-06-30 09:09 | 57309.2255 | 57309 | [7 empty] | 0 | 0 | 5.74 | 9.91 | 5478.1
TS6060#1 | RS\49\004\B | RS | 49 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-06-29 02:33 | 2025-06-30 02:27 | 24646.455 | 24646 | [7 empty] | 0 | 0 | 2.47 | 9.06 | 5601.01
TS5500Shv | RS\48\005\D | RS | 48 | 5 | D | 8 Coal Mining | 29.9 | 0 | 29.9 | 2025-06-29 22:09 | 2025-06-30 09:06 | 13351.8619 | [6 empty] | 13352 | 9820 | 1.34 | 0 | 0 | 6.1 | 5881
TS6060#1 | RS\51\005\A | RS | 51 | 5 | A | 1 Prestrip - Thick | 27.2349 | 27.2349 | 27.2349 | 2025-06-30 02:27 | 2025-07-03 06:54 | 76260.744 | 76261 | [7 empty] | 0 | 0 | 10.68 | 13.69 | 5241.26
TS5500Shv | RS\49\004\B | RS | 49 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-06-30 09:06 | 2025-07-01 16:17 | 38032.8189 | [6 empty] | 38033 | 27182 | 2.73 | 0 | 0 | 9.06 | 5601
TS5500Exc | RS\49\002\D | RS | 49 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-06-30 09:09 | 2025-07-02 05:24 | 55722.7081 | [6 empty] | 55723 | 41525 | 4.57 | 0 | 0 | 5.56 | 5932
DRE1 | SC\39\021\D | SC | 39 | 21 | D | 6 DL | 100 | 0 | 100 | 2025-07-01 00:29 | 2025-07-08 13:31 | 632348.6166 |  |  |  | 48087 | 632349 | 432786 |  |  | 0 | 40 | 0 | 7.33 | 5766.54
TS5500Shv | GG\20\005\D | GG | 20 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-07-01 16:17 | 2025-07-03 17:44 | 60297.5536 | [6 empty] | 60298 | 45148 | 4.52 | 0 | 0 | 6.69 | 5798
PH4100A | SC\42\010\D | SC | 42 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-07-01 19:18 | 2025-07-10 14:26 | 349694.3299 | 349694 | [7 empty] | 0 | 0 | 29.15 | 7.6 | 5745.61
TS5500Exc | RS\49\003\D | RS | 49 | 3 | D | 8 Coal Mining | 62.9 | 0 | 62.9 | 2025-07-02 05:24 | 2025-07-03 09:57 | 35977.62 | [6 empty] | 35978 | 26663 | 2.67 | 0 | 0 | 5.7 | 5919
TS Fleet 5 | GG\24\010\X1 | GG | 24 | 10 | X1 | 1 Prestrip - Thick | 31.5221 | 31.5221 | 31.5221 | 2025-07-02 10:07 | 2025-07-07 02:36 | 210995.689 | 210996 | [7 empty] | 0 | 0 | 23.92 | 14.77 | 5114.38
TS6060#1 | RS\52\002\A | RS | 52 | 2 | A | 1 Prestrip - Thick | 24.2378 | 24.2378 | 24.2378 | 2025-07-03 06:54 | 2025-07-05 08:29 | 49797.3889 | 49797 | [7 empty] | 0 | 0 | 4.72 | 14.64 | 5171.43
TS5500Exc | GG\24\019\B | GG | 24 | 19 | B | 1 Prestrip - Thick | 11.5828 | 11.5828 | 11.5828 | 2025-07-03 09:57 | 2025-07-05 00:08 | 33793.4278 | 33793 | [7 empty] | 0 | 0 | 3.44 | 13.91 | 5215.35
DRE2 | GG\21\013\B | GG | 21 | 13 | B | 6 DL | 100 | 0 | 100 | 2025-07-03 13:09 | 2025-07-05 22:54 | 194286.0614 |  |  |  |  | 194286 | 161905 |  |  | 0 | 16.25 | 0 | 11.68 | 5366.88
TS5500Shv | GG\24\013\X1 | GG | 24 | 13 | X1 | 1 Prestrip - Thick | 2.3945 | 2.3945 | 2.3945 | 2025-07-03 17:44 | 2025-07-04 02:43 | 9453.628 | 9454 | [7 empty] | 0 | 0 | 0.96 | 14.72 | 5121.24
TS5500Shv | RS\49\003\D | RS | 49 | 3 | D | 8 Coal Mining | 37.1 | 0 | 37.1 | 2025-07-04 02:43 | 2025-07-04 20:06 | 21191.0716 | [6 empty] | 21191 | 15705 | 1.57 | 0 | 0 | 5.7 | 5919
PH4100XPC#1 | GG\24\007\X1 | GG | 24 | 7 | X1 | 1 Prestrip - Thick | 100 | 43.6733 | 43.6733 | 2025-07-04 12:03 | 2025-07-11 12:31 | 374872.574 | 374873 | [7 empty] | 0 | 0 | 36.51 | 12.29 | 5248.55
TS5500Shv | GG\24\006\X1 | GG | 24 | 6 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-07-04 20:06 | 2025-07-05 08:57 | 15688.2612 | [6 empty] | 15688 | 11572 | 1.16 | 0 | 0 | 11.43 | 5279
TS5500Exc | RS\49\005\B | RS | 49 | 5 | B | 8 Coal Mining | 76.7 | 0 | 76.7 | 2025-07-05 00:08 | 2025-07-05 15:53 | 19826.3626 | [6 empty] | 19826 | 14158 | 2.06 | 0 | 0 | 9.15 | 5595
TS6060#1 | RS\52\003\A | RS | 52 | 3 | A | 1 Prestrip - Thick | 30.739 | 30.739 | 30.739 | 2025-07-05 08:29 | 2025-07-08 15:41 | 78151.0861 | 78151 | [7 empty] | 0 | 0 | 8.04 | 13.5 | 5259.4
TS5500Shv | GG\24\006\B | GG | 24 | 6 | B | 1 Prestrip - Thick | 74.7771 | 74.7771 | 74.7771 | 2025-07-05 08:57 | 2025-07-09 19:25 | 114117.4897 | 114117 | [7 empty] | 0 | 0 | 11.43 | 10.37 | 5449.38
TS5500Exc | GG\24\020\B | GG | 24 | 20 | B | 1 Prestrip - Thick | 10.526 | 10.526 | 10.526 | 2025-07-05 15:53 | 2025-07-06 21:36 | 26294.9369 | 26295 | [7 empty] | 0 | 0 | 2.52 | 16.53 | 5021.02
DRE2 | GG\21\014\B | GG | 21 | 14 | B | 6 DL | 100 | 0 | 100 | 2025-07-05 22:54 | 2025-07-08 00:17 | 166069.1512 |  |  |  |  | 166069 | 138391 |  |  | 0 | 16.13 | 0 | 12.3 | 5314.14
TS5500Exc | SC\39\020\D | SC | 39 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-07-06 21:36 | 2025-07-09 06:36 | 71781.682 | [6 empty] | 71782 | 53817 | 4.48 | 0 | 0 | 6.83 | 5812
TS Fleet 5 | GG\24\006\B | GG | 24 | 6 | B | 1 Prestrip - Thick | 11.456 | 11.456 | 11.456 | 2025-07-07 02:36 | 2025-07-07 11:55 | 17482.9681 | 17483 | [7 empty] | 0 | 0 | 1.75 | 10.37 | 5449.38
TS Fleet 5 | GG\24\011\X1 | GG | 24 | 11 | X1 | 1 Prestrip - Thick | 45.6575 | 45.6575 | 45.6575 | 2025-07-07 11:55 | 2025-07-13 18:19 | 282140.8079 | 282141 | [7 empty] | 0 | 0 | 28.43 | 14.95 | 5104.76
DRE2 | GG\21\018\B | GG | 21 | 18 | B | 6 DL | 100 | 0 | 100 | 2025-07-08 00:17 | 2025-07-10 11:12 | 198188.1702 |  |  |  |  | 198188 | 165157 |  |  | 0 | 16.42 | 0 | 12.19 | 5334.72
DRE1 | RS\49\004\D | RS | 49 | 4 | D | 6 DL | 100 | 100 | 100 | 2025-07-08 13:31 | 2025-07-12 11:29 | 328285.0176 |  |  |  | 16878 | 328285 | 264428 |  |  | 0 | 28.15 | 0 | 6.01 | 5891.8
TS6060#1 | GG\21\013\B | GG | 21 | 13 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-07-08 15:41 | 2025-07-09 10:33 | 25515.5417 | [6 empty] | 25516 | 18560 | 1.86 | 0 | 0 | 11.68 | 5367
TS5500Exc | GG\24\022\B | GG | 24 | 22 | B | 1 Prestrip - Thick | 10.3131 | 10.3131 | 10.3131 | 2025-07-09 06:36 | 2025-07-11 04:23 | 40508.1401 | 40508 | [7 empty] | 0 | 0 | 3.86 | 21.41 | 4639.45
TS6060#1 | GG\21\014\B | GG | 21 | 14 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-07-09 10:33 | 2025-07-10 02:15 | 21247.2108 | [6 empty] | 21247 | 15399 | 1.86 | 0 | 0 | 12.3 | 5314
TS5500Shv | GG\20\004\D | GG | 20 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2025-07-09 19:25 | 2025-07-12 11:00 | 68172.7369 |  |  | 68173 | [5 empty] | 0 | 0 | 0 | 6.63 | 5802.43
TS6060#1 | RS\52\004\A | RS | 52 | 4 | A | 1 Prestrip - Thick | 24.7865 | 24.7865 | 24.7865 | 2025-07-10 02:15 | 2025-07-13 09:29 | 78618.2118 | 78618 | [7 empty] | 0 | 0 | 8.02 | 14.86 | 5151.3
DRE2 | GG\21\019\B | GG | 21 | 19 | B | 6 DL | 100 | 0 | 100 | 2025-07-10 11:12 | 2025-07-13 01:02 | 208009.1079 |  |  |  |  | 208009 | 173341 |  |  | 0 | 17.37 | 0 | 12.76 | 5308.58
PH4100A | SC\43\010\D | SC | 43 | 10 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-07-10 14:26 | 2025-07-20 01:57 | 377426.3944 | 377426 | [7 empty] | 0 | 0 | 31.55 | 7.55 | 5749.5
TS5500Exc | RS\50\002\A | RS | 50 | 2 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-07-11 04:23 | 2025-07-11 16:45 | 15556.6791 | [6 empty] | 15557 | 11061 | 1.7 | 0 | 0 | 12.17 | 5368
PH4100XPC#1 | GG\24\006\B | GG | 24 | 6 | B | 1 Prestrip - Thick | 100 | 13.7669 | 13.7669 | 2025-07-11 12:31 | 2025-07-11 21:48 | 21009.6909 | 21010 | [7 empty] | 0 | 0 | 2.1 | 10.37 | 5449.38
TS5500Exc | SC\39\021\D | SC | 39 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-07-11 16:45 | 2025-07-13 22:53 | 68204.5942 | [6 empty] | 68205 | 51133 | 4.26 | 0 | 0 | 7.33 | 5767
PH4100XPC#1 | GG\24\008\X1 | GG | 24 | 8 | X1 | 1 Prestrip - Thick | 100 | 54.3797 | 54.3797 | 2025-07-11 21:48 | 2025-07-20 00:29 | 437123.8659 | 437124 | [7 empty] | 0 | 0 | 45.59 | 13.29 | 5199.88
TS5500Shv | GG\24\007\X1 | GG | 24 | 7 | X1 | 8 Coal Mining | 93.8 | 0 | 93.8 | 2025-07-12 11:00 | 2025-07-12 23:48 | 15597.2133 | [6 empty] | 15597 | 11407 | 1.14 | 0 | 0 | 12.29 | 5249
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2025-07-12 11:29 | 2025-07-15 11:29
TS5500Shv | RS\49\004\D | RS | 49 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-07-12 23:48 | 2025-07-13 23:44 | 29185.8879 | [6 empty] | 29186 | 21496 | 2.15 | 0 | 0 | 6.01 | 5892
DRE2 | GG\21\020\B | GG | 21 | 20 | B | 6 DL | 100 | 0 | 100 | 2025-07-13 01:02 | 2025-07-17 01:13 | 323524.6349 |  |  |  |  | 323525 | 248865 |  |  | 0 | 23.75 | 0 | 15.62 | 5098.53
TS6060#1 | GG\24\007\X1 | GG | 24 | 7 | X1 | 8 Coal Mining | 6.2 | 0 | 6.2 | 2025-07-13 09:29 | 2025-07-13 10:15 | 1035.3655 | [6 empty] | 1035 | 757 | 0.08 | 0 | 0 | 12.29 | 5249
TS6060#1 | GG\20\004\D | GG | 20 | 4 | D | 8 Coal Mining | 44.1 | 0 | 44.1 | 2025-07-13 10:15 | 2025-07-14 12:45 | 35857.2985 | [6 empty] | 35857 | 26870 | 1.98 | 0 | 0 | 6.63 | 5802
TS Fleet 5 | GG\24\007\B | GG | 24 | 7 | B | 1 Prestrip - Thick | 22.0953 | 22.0953 | 22.0953 | 2025-07-13 18:19 | 2025-07-14 12:14 | 33617.5594 | 33618 | [7 empty] | 0 | 0 | 3.36 | 10.42 | 5460.13
TS5500Exc | GG\24\007\B | GG | 24 | 7 | B | 1 Prestrip - Thick | 43.1915 | 43.1915 | 43.1915 | 2025-07-13 22:53 | 2025-07-17 01:12 | 65715.0225 | 65715 | [7 empty] | 0 | 0 | 6.57 | 10.42 | 5460.13
TS5500Shv | GG\24\007\B | GG | 24 | 7 | B | 1 Prestrip - Thick | 17.6512 | 17.6512 | 17.6512 | 2025-07-13 23:44 | 2025-07-15 00:47 | 26855.9632 | 26856 | [7 empty] | 0 | 0 | 2.68 | 10.42 | 5460.13
TS Fleet 5 | GG\24\012\X1 | GG | 24 | 12 | X1 | 1 Prestrip - Thick | 37.784 | 37.784 | 37.784 | 2025-07-14 12:14 | 2025-07-18 16:46 | 188615.462 | 188615 | [7 empty] | 0 | 0 | 18.57 | 14.92 | 5106.32
TS6060#1 | GG\21\018\B | GG | 21 | 18 | B | 8 Coal Mining | 73.6 | 0 | 73.6 | 2025-07-14 12:45 | 2025-07-15 15:49 | 36645.497 | [6 empty] | 36645 | 26555 | 2.66 | 0 | 0 | 12.19 | 5335
TS5500Shv | GG\20\004\D | GG | 20 | 4 | D | 8 Coal Mining | 55.9 | 0 | 55.9 | 2025-07-15 00:47 | 2025-07-16 14:04 | 45457.6259 | [6 empty] | 45458 | 34064 | 2.52 | 0 | 0 | 6.63 | 5802
DRE1 | SC\39\022\D | SC | 39 | 22 | D | 6 DL | 100 | 0 | 100 | 2025-07-15 11:29 | 2025-07-23 00:14 | 631367.6299 |  |  |  | 48013 | 631368 | 432115 |  |  | 0 | 40 | 0 | 7.41 | 5760.69
TS6060#1 | RS\52\005\A | RS | 52 | 5 | A | 1 Prestrip - Thick | 21.4211 | 21.4211 | 21.4211 | 2025-07-15 15:49 | 2025-07-18 00:23 | 56347.8709 | 56348 | [7 empty] | 0 | 0 | 8.07 | 14.03 | 5217.34
TS5500Shv | GG\21\013\B | GG | 21 | 13 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-07-16 14:04 | 2025-07-17 08:55 | 22989.2504 | [6 empty] | 22989 | 16722 | 1.68 | 0 | 0 | 11.68 | 5367
TS5500Exc | RS\49\004\D | RS | 49 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-07-17 01:12 | 2025-07-18 01:08 | 30148.0601 | [6 empty] | 30148 | 22205 | 2.22 | 0 | 0 | 6.01 | 5892
DRE2 | GG\21\021\B | GG | 21 | 21 | B | 6 DL | 100 | 0 | 100 | 2025-07-17 01:13 | 2025-07-20 19:14 | 302829.1426 |  |  |  |  | 302829 | 232945 |  |  | 0 | 25.75 | 0 | 19.73 | 4791.58
TS5500Shv | GG\21\014\B | GG | 21 | 14 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-07-17 08:55 | 2025-07-18 00:37 | 19143.5265 | [6 empty] | 19144 | 13875 | 1.67 | 0 | 0 | 12.3 | 5314
TS6060#1 | GG\21\020\B | GG | 21 | 20 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-07-18 00:23 | 2025-07-18 21:59 | 29241.6543 | [6 empty] | 29242 | 20734 | 2.04 | 0 | 0 | 15.62 | 5099
TS5500Shv | GG\21\018\B | GG | 21 | 18 | B | 8 Coal Mining | 26.4 | 0 | 26.4 | 2025-07-18 00:37 | 2025-07-18 11:25 | 13168.3098 | [6 empty] | 13168 | 9542 | 0.96 | 0 | 0 | 12.19 | 5335
TS5500Exc | RS\50\004\A | RS | 50 | 4 | A | 1 Prestrip - Thick | 7.7851 | 7.7851 | 7.7851 | 2025-07-18 01:08 | 2025-07-19 10:44 | 29873.4165 | 29873 | [7 empty] | 0 | 0 | 3.04 | 14.63 | 5158.95
TS5500Shv | RS\49\005\B | RS | 49 | 5 | B | 8 Coal Mining | 23.3 | 0 | 23.3 | 2025-07-18 11:25 | 2025-07-18 16:21 | 6025.2965 | [6 empty] | 6025 | 4303 | 0.63 | 0 | 0 | 9.15 | 5595
TS5500Shv | GG\24\020\B | GG | 24 | 20 | B | 1 Prestrip - Thick | 12.7709 | 12.7709 | 12.7709 | 2025-07-18 16:21 | 2025-07-19 22:05 | 31902.9164 | 31903 | [7 empty] | 0 | 0 | 3.05 | 16.53 | 5021.02
TS Fleet 5 | GG\24\013\X1 | GG | 24 | 13 | X1 | 1 Prestrip - Thick | 42.7536 | 42.7536 | 42.7536 | 2025-07-18 16:46 | 2025-07-22 10:45 | 168792.1115 | 168792 | [7 empty] | 0 | 0 | 17.06 | 14.72 | 5121.24
TS6060#1 | RS\53\002\B | RS | 53 | 2 | B | 1 Prestrip - Thick | 18.0415 | 18.0415 | 18.0415 | 2025-07-18 21:59 | 2025-07-21 00:08 | 50463.329 | 50463 | [7 empty] | 0 | 0 | 3.85 | 9.33 | 5565.66
TS5500Exc | RS\50\005\A | RS | 50 | 5 | A | 1 Prestrip - Thick | 5.8643 | 5.8643 | 5.8643 | 2025-07-19 10:44 | 2025-07-20 06:11 | 17282.084 | 17282 | [7 empty] | 0 | 0 | 2.36 | 14.12 | 5201.01
TS5500Shv | GG\21\019\B | GG | 21 | 19 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-07-19 22:05 | 2025-07-21 16:42 | 51968.3287 | [6 empty] | 51968 | 37478 | 3.76 | 0 | 0 | 12.76 | 5309
PH4100XPC#1 | GG\24\007\B | GG | 24 | 7 | B | 1 Prestrip - Thick | 100 | 17.0621 | 17.0621 | 2025-07-20 00:29 | 2025-07-20 11:57 | 25959.5997 | 25960 | [7 empty] | 0 | 0 | 2.59 | 10.42 | 5460.13
PH4100A | SC\43\011\D | SC | 43 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-07-20 01:57 | 2025-07-29 20:07 | 400996.4995 | 400996 | [7 empty] | 0 | 0 | 35.91 | 7.53 | 5750.26
TS5500Exc | RS\51\002\A | RS | 51 | 2 | A | 1 Prestrip - Thick | 1.4156 | 1.4156 | 1.4156 | 2025-07-20 06:11 | 2025-07-20 08:50 | 2354.1039 | 2354 | [7 empty] | 0 | 0 | 0.28 | 11.15 | 5448.53
TS5500Exc | RS\51\003\A | RS | 51 | 3 | A | 1 Prestrip - Thick | 12.9045 | 12.9045 | 12.9045 | 2025-07-20 08:50 | 2025-07-21 23:44 | 34596.8502 | 34597 | [7 empty] | 0 | 0 | 3.55 | 13.16 | 5284.14
PH4100XPC#1 | GG\24\009\X2 | GG | 24 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 55.1539 | 2025-07-20 11:57 | 2025-07-29 05:40 | 485814.0381 | 485814 | [7 empty] | 0 | 0 | 49.06 | 0 | 0
DRE2 | GG\21\022\B | GG | 21 | 22 | B | 6 DL | 100 | 0 | 100 | 2025-07-20 19:14 | 2025-07-24 05:34 | 276926.7866 |  |  |  |  | 276927 | 213021 |  |  | 0 | 23 | 0 | 20.7 | 4712.85
TS6060#1 | GG\21\021\B | GG | 21 | 21 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-07-21 00:08 | 2025-07-21 06:05 | 8044.5209 | [6 empty] | 8045 | 5566 | 0.61 | 0 | 0 | 19.73 | 4792
TS6060#1 | RS\53\003\A | RS | 53 | 3 | A | 1 Prestrip - Thick | 30.5853 | 30.5853 | 30.5853 | 2025-07-21 06:05 | 2025-07-24 10:07 | 74751.8718 | 74752 | [7 empty] | 0 | 0 | 7.66 | 14.29 | 5197.16
TS5500Shv | GG\24\008\X1 | GG | 24 | 8 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-07-21 16:42 | 2025-07-22 07:15 | 17742.3738 | [6 empty] | 17742 | 12857 | 1.29 | 0 | 0 | 13.29 | 5200
TS5500Exc | RS\51\003\A | RS | 51 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2025-07-21 23:44 | 2025-07-23 11:50 | 45477.0665 | [6 empty] | 45477 | 32027 | 3.21 | 0 | 0 | 13.16 | 5284
TS5500Shv | GG\24\008\X2 | GG | 24 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2025-07-22 07:15 | 2025-07-25 08:14 | 78234.73 | 78235 | [7 empty] | 0 | 0 | 7.82 | 0 | 0
TS Fleet 5 | GG\24\014\X1 | GG | 24 | 14 | X1 | 1 Prestrip - Thick | 46.6461 | 46.6461 | 46.6461 | 2025-07-22 10:45 | 2025-07-24 20:41 | 108700.4292 | 108700 | [7 empty] | 0 | 0 | 14.81 | 14.59 | 5131.25
DRE1 | RS\49\005\D | RS | 49 | 5 | D | 6 DL | 100 | 100 | 100 | 2025-07-23 00:14 | 2025-07-25 18:25 | 231198.8938 |  |  |  | 8415 | 231199 | 130413 |  |  | 0 | 28.55 | 0 | 6.1 | 5880.74
TS5500Exc | RS\51\003\B | RS | 51 | 3 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2025-07-23 11:50 | 2025-07-24 00:27 | 11155.6784 | 11156 | [7 empty] | 0 | 0 | 1.12 | 8.98 | 5590.48
TS5500Exc | RS\51\004\A | RS | 51 | 4 | A | 1 Prestrip - Thick | 1.9782 | 1.9782 | 1.9782 | 2025-07-24 00:27 | 2025-07-24 08:17 | 6961.0813 | 6961 | [7 empty] | 0 | 0 | 0.71 | 14.69 | 5160.55
DRE2 | GG\21\023\B | GG | 21 | 23 | B | 6 DL | 100 | 0 | 100 | 2025-07-24 05:34 | 2025-07-27 13:42 | 269537.9062 |  |  |  |  | 269538 | 207337 |  |  | 0 | 25.37 | 0 | 0 | 0
TS5500Exc | RS\51\005\A | RS | 51 | 5 | A | 1 Prestrip - Thick | 9.8846 | 9.8846 | 9.8846 | 2025-07-24 08:17 | 2025-07-25 15:26 | 27677.9991 | 27678 | [7 empty] | 0 | 0 | 3.88 | 13.69 | 5241.26
TS6060#1 | RS\53\004\A | RS | 53 | 4 | A | 1 Prestrip - Thick | 30.4658 | 30.4658 | 30.4658 | 2025-07-24 10:07 | 2025-07-28 04:38 | 89567.6874 | 89568 | [7 empty] | 0 | 0 | 9.18 | 14.92 | 5148.09
TS Fleet 5 | GG\24\017\X1 | GG | 24 | 17 | X1 | 1 Prestrip - Thick | 43.0723 | 43.0723 | 43.0723 | 2025-07-24 20:41 | 2025-07-26 12:36 | 74888.1159 | 74888 | [7 empty] | 0 | 0 | 10.34 | 14.31 | 5152.61
TS5500Shv | GG\24\008\B | GG | 24 | 8 | B | 1 Prestrip - Thick | 31.3365 | 31.3365 | 31.3365 | 2025-07-25 08:14 | 2025-07-26 04:46 | 22023.8454 | 22024 | [7 empty] | 0 | 0 | 2.2 | 10.25 | 5490.05
TS5500Exc | GG\24\008\B | GG | 24 | 8 | B | 1 Prestrip - Thick | 68.6635 | 68.6635 | 68.6635 | 2025-07-25 15:26 | 2025-07-27 21:59 | 48257.8113 | 48258 | [7 empty] | 0 | 0 | 4.83 | 10.25 | 5490.05
DRE1 | SC\39\023\D | SC | 39 | 23 | D | 6 DL | 100 | 0 | 100 | 2025-07-25 18:25 | 2025-08-01 16:37 | 580539.4867 |  |  |  | 41287 | 580539 | 417456 |  |  | 0 | 38.41 | 0 | 7.31 | 5770.82
TS5500Shv | GG\24\021\D | GG | 24 | 21 | D | 1 Prestrip - Thick | 7.9947 | 7.9947 | 7.9947 | 2025-07-26 04:46 | 2025-07-27 03:01 | 23925.1827 | 23925 | [7 empty] | 0 | 0 | 2.56 | 6.78 | 5789.52
TS Fleet 5 | GG\24\018\X2 | GG | 24 | 18 | X2 | 1 Prestrip - Thick | 38.1055 | 0 | 38.1055 | 2025-07-26 12:36 | 2025-07-28 09:02 | 83353.1254 | 83353 | [7 empty] | 0 | 0 | 8.61 | 0 | 0
TS5500Shv | RS\49\005\D | RS | 49 | 5 | D | 7 PostStrip | 41.8555 | 0 | 41.8555 | 2025-07-27 03:01 | 2025-07-27 14:31 | 12334.7432 |  |  | 12335 | [5 empty] | 0 | 0 | 0 | 6.1 | 5880.74
DRE2 | GG\20\013\D | GG | 20 | 13 | D | 6 DL | 100 | 100 | 100 | 2025-07-27 13:42 | 2025-08-02 22:34 | 514241.4761 |  |  |  | 11973 | 514241 | 227487 |  |  | 0 | 23.97 | 0 | 7.07 | 5766.76
TS5500Shv | GG\24\022\B | GG | 24 | 22 | B | 1 Prestrip - Thick | 12.5345 | 12.5345 | 12.5345 | 2025-07-27 14:31 | 2025-07-29 12:19 | 49233.123 | 49233 | [7 empty] | 0 | 0 | 4.69 | 21.41 | 4639.45
TS5500Exc | RS\49\005\D | RS | 49 | 5 | D | 7 PostStrip | 58.1445 | 0 | 58.1445 | 2025-07-27 21:59 | 2025-07-28 17:22 | 17135.0597 |  |  | 17135 | [5 empty] | 0 | 0 | 0 | 6.1 | 5880.74
TS6060#1 | RS\53\005\A | RS | 53 | 5 | A | 1 Prestrip - Thick | 17.965 | 17.965 | 17.965 | 2025-07-28 04:38 | 2025-07-30 01:56 | 45092.4019 | 45092 | [7 empty] | 0 | 0 | 6.42 | 14.4 | 5189.45
TS Fleet 5 | GG\24\019\B | GG | 24 | 19 | B | 1 Prestrip - Thick | 40.3764 | 40.3764 | 40.3764 | 2025-07-28 09:02 | 2025-07-30 23:50 | 117799.8874 | 117800 | [7 empty] | 0 | 0 | 11.97 | 13.91 | 5215.35
TS5500Exc | RS\49\005\D | RS | 49 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-07-28 17:22 | 2025-07-29 07:38 | 17967.5846 | [6 empty] | 17968 | 13214 | 2.26 | 0 | 0 | 6.1 | 5881
PH4100XPC#1 | GG\24\009\B | GG | 24 | 9 | B | 1 Prestrip - Thick | 100 | 82.562 | 82.562 | 2025-07-29 05:40 | 2025-07-30 11:18 | 67071.5531 | 67072 | [7 empty] | 0 | 0 | 6.71 | 10.15 | 5513.77
TS5500Exc | GG\24\009\B | GG | 24 | 9 | B | 1 Prestrip - Thick | 17.438 | 17.438 | 17.438 | 2025-07-29 07:38 | 2025-07-29 23:39 | 14166.2463 | 14166 | [7 empty] | 0 | 0 | 1.42 | 10.15 | 5513.77
TS5500Shv | RS\49\005\D | RS | 49 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-07-29 12:19 | 2025-07-30 02:35 | 17394.151 | [6 empty] | 17394 | 12792 | 2.19 | 0 | 0 | 6.1 | 5881
PH4100A | SC\42\011\D | SC | 42 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-07-29 20:07 | 2025-08-07 15:37 | 358076.168 | 358076 | [7 empty] | 0 | 0 | 31.37 | 7.55 | 5748.49
TS5500Exc | RS\52\002\A | RS | 52 | 2 | A | 1 Prestrip - Thick | 3.4278 | 3.4278 | 3.4278 | 2025-07-29 23:39 | 2025-07-30 07:35 | 7042.5215 | 7043 | [7 empty] | 0 | 0 | 0.67 | 14.64 | 5171.43
TS6060#1 | RS\54\002\B | RS | 54 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-07-30 01:56 | 2025-08-11 21:15 | 309763.5155 | 309764 | [7 empty] | 0 | 0 | 19.34 | 10.65 | 5457.03
TS5500Shv | RS\50\002\A | RS | 50 | 2 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-07-30 02:35 | 2025-07-30 14:56 | 15060.1894 | [6 empty] | 15060 | 10708 | 1.65 | 0 | 0 | 12.17 | 5368
TS5500Exc | RS\52\003\A | RS | 52 | 3 | A | 1 Prestrip - Thick | 4.9402 | 4.9402 | 4.9402 | 2025-07-30 07:35 | 2025-07-30 21:42 | 12560.0156 | 12560 | [7 empty] | 0 | 0 | 1.29 | 13.5 | 5259.4
PH4100XPC#1 | GG\24\010\X1 | GG | 24 | 10 | X1 | 1 Prestrip - Thick | 100 | 38.1045 | 38.1045 | 2025-07-30 11:18 | 2025-08-04 03:19 | 255055.4055 | 255055 | [7 empty] | 0 | 0 | 28.92 | 14.77 | 5114.38
TS5500Shv | RS\50\002\B | RS | 50 | 2 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-07-30 14:56 | 2025-07-30 23:48 | 9519.036 | 9519 | [7 empty] | 0 | 0 | 1.44 | 9.06 | 5592.94
TS5500Exc | RS\50\002\B | RS | 50 | 2 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2025-07-30 21:42 | 2025-07-31 06:34 | 7853.2047 | 7853 | [7 empty] | 0 | 0 | 1.18 | 9.06 | 5592.94
TS5500Shv | RS\50\003\A | RS | 50 | 3 | A | 1 Prestrip - Thick | 12.8549 | 12.8549 | 12.8549 | 2025-07-30 23:48 | 2025-08-01 10:31 | 35586.2867 | 35586 | [7 empty] | 0 | 0 | 3.64 | 12.96 | 5298.15
TS Fleet 5 | GG\24\020\B | GG | 24 | 20 | B | 1 Prestrip - Thick | 34.2808 | 34.2808 | 34.2808 | 2025-07-30 23:50 | 2025-08-01 21:29 | 85636.4805 | 85636 | [7 empty] | 0 | 0 | 8.2 | 16.53 | 5021.02
TS5500Exc | RS\50\002\B | RS | 50 | 2 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-07-31 06:34 | 2025-07-31 17:42 | 14026.7719 | [6 empty] | 14027 | 10100 | 1.47 | 0 | 0 | 9.06 | 5593
TS5500Exc | RS\52\004\A | RS | 52 | 4 | A | 1 Prestrip - Thick | 6.268 | 6.268 | 6.268 | 2025-07-31 17:42 | 2025-08-01 16:04 | 19880.873 | 19881 | [7 empty] | 0 | 0 | 2.03 | 14.86 | 5151.3
TS5500Shv | RS\50\002\B | RS | 50 | 2 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-08-01 10:31 | 2025-08-01 21:40 | 13579.1089 | [6 empty] | 13579 | 9777 | 1.42 | 0 | 0 | 9.06 | 5593
TS5500Exc | RS\50\003\A | RS | 50 | 3 | A | 8 Coal Mining | 100 | 0 | 66.3 | 2025-08-01 16:04 | 2025-08-02 16:19 | 30544.4826 | [6 empty] | 30544 | 21536 | 2.16 | 0 | 0 | 12.96 | 5298
DRE1 | SC\39\024\D | SC | 39 | 24 | D | 6 DL | 100 | 0 | 100 | 2025-08-01 16:37 | 2025-08-08 12:27 | 572264.5196 |  |  |  | 40698 | 572265 | 411506 |  |  | 0 | 37.83 | 0 | 7.27 | 5774.74
TS Fleet 5 | GG\24\021\D | GG | 24 | 21 | D | 1 Prestrip - Thick | 40.8202 | 40.8202 | 40.8202 | 2025-08-01 21:29 | 2025-08-04 14:36 | 122160.6031 | 122161 | [7 empty] | 0 | 0 | 13.08 | 6.78 | 5789.52
TS5500Shv | GG\21\021\B | GG | 21 | 21 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-08-01 21:40 | 2025-08-02 03:36 | 7248.0337 | [6 empty] | 7248 | 5015 | 0.55 | 0 | 0 | 19.73 | 4792
TS5500Shv | RS\50\003\A | RS | 50 | 3 | A | 8 Coal Mining | 41.2 | 0 | 33.7 | 2025-08-02 03:36 | 2025-08-02 16:19 | 15496.3331 | [6 empty] | 15496 | 10926 | 1.09 | 0 | 0 | 12.96 | 5298
TS5500Shv | RS\50\003\B | RS | 50 | 3 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-08-02 16:19 | 2025-08-03 05:03 | 13655.747 | 13656 | [7 empty] | 0 | 0 | 1.37 | 9.01 | 5591.04
TS5500Exc | RS\50\003\B | RS | 50 | 3 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2025-08-02 16:19 | 2025-08-03 05:03 | 11265.9913 | 11266 | [7 empty] | 0 | 0 | 1.13 | 9.01 | 5591.04
DRE2 | GG\20\014\D | GG | 20 | 14 | D | 6 DL | 100 | 100 | 100 | 2025-08-02 22:34 | 2025-08-06 17:32 | 305937.4091 |  |  |  | 7123 | 305937 | 135339 |  |  | 0 | 24.06 | 0 | 7.2 | 5756.46
TS5500Exc | RS\52\005\A | RS | 52 | 5 | A | 1 Prestrip - Thick | 6.1485 | 6.1485 | 6.1485 | 2025-08-03 05:03 | 2025-08-03 23:15 | 16173.6695 | 16174 | [7 empty] | 0 | 0 | 2.32 | 14.03 | 5217.34
TS5500Shv | RS\50\003\B | RS | 50 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-08-03 05:03 | 2025-08-04 12:43 | 38610.4096 | [6 empty] | 38610 | 27617 | 2.76 | 0 | 0 | 9.01 | 5591
TS5500Exc | RS\53\002\B | RS | 53 | 2 | B | 1 Prestrip - Thick | 13.2231 | 13.2231 | 13.2231 | 2025-08-03 23:15 | 2025-08-05 16:55 | 36985.9199 | 36986 | [7 empty] | 0 | 0 | 2.82 | 9.33 | 5565.66
PH4100XPC#1 | GG\24\011\X1 | GG | 24 | 11 | X1 | 1 Prestrip - Thick | 100 | 54.3425 | 54.3425 | 2025-08-04 03:19 | 2025-08-10 09:07 | 335809.8898 | 335810 | [7 empty] | 0 | 0 | 33.84 | 14.95 | 5104.76
TS5500Shv | GG\24\010\X1 | GG | 24 | 10 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-08-04 12:43 | 2025-08-05 02:35 | 16916.2972 | [6 empty] | 16916 | 12107 | 1.22 | 0 | 0 | 14.77 | 5114
TS Fleet 5 | GG\24\022\B | GG | 24 | 22 | B | 1 Prestrip - Thick | 34.3202 | 34.3202 | 34.3202 | 2025-08-04 14:36 | 2025-08-07 14:27 | 134803.6164 | 134804 | [7 empty] | 0 | 0 | 12.85 | 21.41 | 4639.45
TS5500Shv | GG\24\010\X2 | GG | 24 | 10 | X2 | 1 Prestrip - Thick | 54.7945 | 0 | 54.7945 | 2025-08-05 02:35 | 2025-08-06 13:25 | 37332.6466 | 37333 | [7 empty] | 0 | 0 | 3.75 | 0 | 0
TS5500Exc | GG\24\010\X2 | GG | 24 | 10 | X2 | 1 Prestrip - Thick | 45.2055 | 0 | 45.2055 | 2025-08-05 16:55 | 2025-08-07 03:44 | 30799.4334 | 30799 | [7 empty] | 0 | 0 | 3.09 | 0 | 0
TS5500Shv | GG\21\022\B | GG | 21 | 22 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-08-06 13:25 | 2025-08-08 13:15 | 58329.4246 | [6 empty] | 58329 | 40203 | 4.04 | 0 | 0 | 20.7 | 4713
DRE2 | GG\20\018\D | GG | 20 | 18 | D | 6 DL | 100 | 100 | 100 | 2025-08-06 17:32 | 2025-08-13 01:18 | 510533.1397 |  |  |  | 11887 | 510533 | 225847 |  |  | 0 | 23.79 | 0 | 7.19 | 5756.9
TS5500Exc | GG\24\010\B | GG | 24 | 10 | B | 1 Prestrip - Thick | 4.4447 | 4.4447 | 4.4447 | 2025-08-07 03:44 | 2025-08-07 08:29 | 4195.3311 | 4195 | [7 empty] | 0 | 0 | 0.42 | 10.28 | 5510.81
TS5500Exc | RS\53\003\A | RS | 53 | 3 | A | 1 Prestrip - Thick | 10.8165 | 10.8165 | 10.8165 | 2025-08-07 08:29 | 2025-08-08 14:10 | 26436.0776 | 26436 | [7 empty] | 0 | 0 | 2.71 | 14.29 | 5197.16
TS Fleet 5 | GG\24\010\B | GG | 24 | 10 | B | 1 Prestrip - Thick | 43.4002 | 43.4002 | 43.4002 | 2025-08-07 14:27 | 2025-08-08 12:17 | 40965.4789 | 40965 | [7 empty] | 0 | 0 | 4.1 | 10.28 | 5510.81
PH4100A | SC\42\012\D | SC | 42 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-08-07 15:37 | 2025-08-15 04:11 | 306178.6697 | 306179 | [7 empty] | 0 | 0 | 26.45 | 7.45 | 5756.61
TS Fleet 5 | RS\51\003\B | RS | 51 | 3 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-08-08 12:17 | 2025-08-08 19:30 | 13522.0344 | 13522 | [7 empty] | 0 | 0 | 1.35 | 8.98 | 5590.48
DRE1 | RS\50\002\D | RS | 50 | 2 | D | 6 DL | 100 | 100 | 100 | 2025-08-08 12:27 | 2025-08-12 08:22 | 321074.9399 |  |  |  | 16508 | 321075 | 258621 |  |  | 0 | 28.48 | 0 | 5.72 | 5917.65
TS5500Shv | RS\50\004\A | RS | 50 | 4 | A | 1 Prestrip - Thick | 2.211 | 2.211 | 2.211 | 2025-08-08 13:15 | 2025-08-08 21:30 | 8484.0931 | 8484 | [7 empty] | 0 | 0 | 0.86 | 14.63 | 5158.95
TS5500Exc | RS\53\004\A | RS | 53 | 4 | A | 1 Prestrip - Thick | 5.0277 | 5.0277 | 5.0277 | 2025-08-08 14:10 | 2025-08-09 06:47 | 14781.1807 | 14781 | [7 empty] | 0 | 0 | 1.52 | 14.92 | 5148.09
TS Fleet 5 | RS\52\002\A | RS | 52 | 2 | A | 1 Prestrip - Thick | 68.327 | 68.327 | 68.327 | 2025-08-08 19:30 | 2025-08-11 22:20 | 140380.4909 | 140380 | [7 empty] | 0 | 0 | 13.3 | 14.64 | 5171.43
TS5500Shv | RS\50\004\A | RS | 50 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-08-08 21:30 | 2025-08-09 15:44 | 22233.1274 | [6 empty] | 22233 | 15516 | 1.55 | 0 | 0 | 14.63 | 5159
TS5500Exc | RS\50\004\A | RS | 50 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-08-09 06:47 | 2025-08-10 01:01 | 22966.0876 | [6 empty] | 22966 | 16027 | 1.6 | 0 | 0 | 14.63 | 5159
TS5500Shv | RS\50\005\A | RS | 50 | 5 | A | 1 Prestrip - Thick | 6.8063 | 6.8063 | 6.8063 | 2025-08-09 15:44 | 2025-08-10 11:11 | 20058.0624 | 20058 | [7 empty] | 0 | 0 | 2.74 | 14.12 | 5201.01
TS5500Exc | RS\50\004\B | RS | 50 | 4 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2025-08-10 01:01 | 2025-08-10 13:27 | 10989.8909 | 10990 | [7 empty] | 0 | 0 | 1.1 | 9 | 5597.63
PH4100XPC#1 | GG\24\010\B | GG | 24 | 10 | B | 1 Prestrip - Thick | 100 | 52.1551 | 52.1551 | 2025-08-10 09:07 | 2025-08-11 06:52 | 49229.1724 | 49229 | [7 empty] | 0 | 0 | 4.92 | 10.28 | 5510.81
TS5500Shv | GG\24\011\X1 | GG | 24 | 11 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-08-10 11:11 | 2025-08-10 23:30 | 15013.5996 | [6 empty] | 15014 | 10740 | 1.06 | 0 | 0 | 14.95 | 5105
TS5500Exc | RS\50\005\A | RS | 50 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-08-10 13:27 | 2025-08-11 00:26 | 13832.5035 | [6 empty] | 13833 | 9672 | 1.49 | 0 | 0 | 14.12 | 5201
TS5500Shv | GG\24\011\X2 | GG | 24 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 38.5139 | 2025-08-10 23:30 | 2025-08-12 | 26264.8232 | 26265 | [7 empty] | 0 | 0 | 2.59 | 0 | 0
TS5500Exc | RS\51\003\B | RS | 51 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-08-11 00:26 | 2025-08-11 15:59 | 19604.6583 | [6 empty] | 19605 | 14003 | 1.4 | 0 | 0 | 8.98 | 5590
PH4100XPC#1 | GG\24\011\X2 | GG | 24 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 56.8838 | 2025-08-11 06:52 | 2025-08-12 | 38792.3324 | 38792 | [7 empty] | 0 | 0 | 3.83 | 0 | 0
TS5500Exc | SC\39\022\D | SC | 39 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-08-11 15:59 | 2025-08-14 00:04 | 70633.7667 | [6 empty] | 70634 | 52871 | 4.41 | 0 | 0 | 7.41 | 5761
TS6060#1 | GG\20\013\D | GG | 20 | 13 | D | 8 Coal Mining | 13.2 | 0 | 13.2 | 2025-08-11 21:15 | 2025-08-12 03:24 | 8319.2844 | [6 empty] | 8319 | 6195 | 0.62 | 0 | 0 | 7.07 | 5767
TS Fleet 5 | GG\24\011\X2 | GG | 24 | 11 | X2 | 1 Prestrip - Thick | 33.3594 | 0 | 4.6024 | 2025-08-11 22:20 | 2025-08-12 | 3138.6094 | 3139 | [7 empty] | 0 | 0 | 0.31 | 0 | 0
TS5500Shv | RS\50\004\B | RS | 50 | 4 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-08-12 | 2025-08-12 12:26 | 13321.0798 | 13321 | [7 empty] | 0 | 0 | 1.33 | 9 | 5597.63
TS Fleet 5 | GG\24\011\B | GG | 24 | 11 | B | 1 Prestrip - Thick | 43.1205 | 43.1205 | 43.1205 | 2025-08-12 | 2025-08-13 01:13 | 47297.7965 | 47298 | [7 empty] | 0 | 0 | 4.7 | 11.07 | 5442.79
PH4100XPC#1 | GG\24\011\B | GG | 24 | 11 | B | 1 Prestrip - Thick | 100 | 56.8795 | 56.8795 | 2025-08-12 | 2025-08-13 03:34 | 62389.7447 | 62390 | [7 empty] | 0 | 0 | 6.2 | 11.07 | 5442.79
TS6060#1 | RS\54\003\B | RS | 54 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-08-12 03:24 | 2025-08-23 09:23 | 266456.587 | 266457 | [7 empty] | 0 | 0 | 27.28 | 9.05 | 5579.51
DRE1 | RS\50\003\D | RS | 50 | 3 | D | 6 DL | 100 | 100 | 100 | 2025-08-12 08:22 | 2025-08-16 09:39 | 339860.9331 |  |  |  | 17474 | 339861 | 273753 |  |  | 0 | 29.13 | 0 | 5.76 | 5913.59
TS5500Shv | RS\50\002\D | RS | 50 | 2 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-08-12 12:26 | 2025-08-13 12:36 | 29470.5469 | [6 empty] | 29471 | 21910 | 2.25 | 0 | 0 | 5.72 | 5918
TS Fleet 5 | RS\52\003\A | RS | 52 | 3 | A | 1 Prestrip - Thick | 40.5013 | 40.5013 | 40.5013 | 2025-08-13 01:13 | 2025-08-15 08:06 | 102970.8467 | 102971 | [7 empty] | 0 | 0 | 10.59 | 13.5 | 5259.4
DRE2 | GG\20\019\D | GG | 20 | 19 | D | 6 DL | 100 | 100 | 100 | 2025-08-13 01:18 | 2025-08-19 01:28 | 484940.2876 |  |  |  | 11291 | 484940 | 214525 |  |  | 0 | 22.58 | 0 | 7.05 | 5768.16
PH4100XPC#1 | GG\24\012\X1 | GG | 24 | 12 | X1 | 1 Prestrip - Thick | 100 | 44.4507 | 44.4507 | 2025-08-13 03:34 | 2025-08-17 07:42 | 221895.5126 | 221896 | [7 empty] | 0 | 0 | 21.85 | 14.92 | 5106.32
TS5500Shv | RS\50\004\B | RS | 50 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-08-13 12:36 | 2025-08-14 03:36 | 18289.0868 | [6 empty] | 18289 | 13041 | 1.3 | 0 | 0 | 9 | 5598
TS5500Exc | RS\50\002\D | RS | 50 | 2 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-08-14 00:04 | 2025-08-15 00:14 | 30442.1034 | [6 empty] | 30442 | 22632 | 2.32 | 0 | 0 | 5.72 | 5918
TS5500Shv | RS\50\005\A | RS | 50 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-08-14 03:36 | 2025-08-14 14:35 | 13391.0407 | [6 empty] | 13391 | 9363 | 1.45 | 0 | 0 | 14.12 | 5201
TS5500Shv | RS\50\005\B | RS | 50 | 5 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-08-14 14:35 | 2025-08-15 00:21 | 10483.0235 | 10483 | [7 empty] | 0 | 0 | 1.63 | 9.13 | 5588.03
TS5500Exc | RS\50\004\B | RS | 50 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-08-15 00:14 | 2025-08-15 15:14 | 18892.0238 | [6 empty] | 18892 | 13471 | 1.34 | 0 | 0 | 9 | 5598
TS5500Shv | RS\51\002\A | RS | 51 | 2 | A | 1 Prestrip - Thick | 1.6625 | 1.6625 | 1.6625 | 2025-08-15 00:21 | 2025-08-15 03:00 | 2764.6251 | 2765 | [7 empty] | 0 | 0 | 0.33 | 11.15 | 5448.53
TS5500Shv | RS\51\002\A | RS | 51 | 2 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-08-15 03:00 | 2025-08-15 18:50 | 19295.7794 | [6 empty] | 19296 | 13779 | 1.48 | 0 | 0 | 11.15 | 5449
PH4100A | SC\43\012\D | SC | 43 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-08-15 04:11 | 2025-08-24 06:41 | 375429.199 | 375429 | [7 empty] | 0 | 0 | 32.81 | 7.44 | 5756.37
TS Fleet 5 | RS\50\005\B | RS | 50 | 5 | B | 1 Prestrip - Thick | 7.7956 | 0 | 7.7956 | 2025-08-15 08:06 | 2025-08-15 08:54 | 1491.421 | 1491 | [7 empty] | 0 | 0 | 0.23 | 9.13 | 5588.03
TS Fleet 5 | RS\52\003\A | RS | 52 | 3 | A | 1 Prestrip - Thick | 18.1828 | 18.1828 | 18.1828 | 2025-08-15 08:54 | 2025-08-16 09:32 | 46228.0244 | 46228 | [7 empty] | 0 | 0 | 4.75 | 13.5 | 5259.4
TS5500Exc | RS\50\005\B | RS | 50 | 5 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 37.4099 | 2025-08-15 15:14 | 2025-08-15 23:20 | 7157.0734 | 7157 | [7 empty] | 0 | 0 | 1.11 | 9.13 | 5588.03
TS5500Shv | GG\20\013\D | GG | 20 | 13 | D | 8 Coal Mining | 86.8 | 0 | 86.8 | 2025-08-15 18:50 | 2025-08-17 15:52 | 54921.1286 | [6 empty] | 54921 | 40897 | 4.09 | 0 | 0 | 7.07 | 5767
TS5500Exc | RS\50\005\B | RS | 50 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-08-15 23:20 | 2025-08-16 08:32 | 11595.439 | [6 empty] | 11595 | 8260 | 1.29 | 0 | 0 | 9.13 | 5588
TS5500Exc | RS\51\002\A | RS | 51 | 2 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-08-16 08:32 | 2025-08-17 00:21 | 19931.9039 | [6 empty] | 19932 | 14233 | 1.53 | 0 | 0 | 11.15 | 5449
TS Fleet 5 | RS\52\004\A | RS | 52 | 4 | A | 1 Prestrip - Thick | 61.74 | 61.74 | 61.74 | 2025-08-16 09:32 | 2025-08-20 17:55 | 195827.63 | 195828 | [7 empty] | 0 | 0 | 19.98 | 14.86 | 5151.3
DRE1 | RS\50\004\D | RS | 50 | 4 | D | 6 DL | 100 | 100 | 100 | 2025-08-16 09:39 | 2025-08-20 07:26 | 327603.5564 |  |  |  | 16843 | 327604 | 263879 |  |  | 0 | 28.06 | 0 | 6.01 | 5891.94
TS5500Exc | RS\50\003\D | RS | 50 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-08-17 00:21 | 2025-08-17 23:29 | 29125.9618 | [6 empty] | 29126 | 21551 | 2.15 | 0 | 0 | 5.76 | 5914
PH4100XPC#1 | GG\24\013\X1 | GG | 24 | 13 | X1 | 1 Prestrip - Thick | 100 | 49.7137 | 49.7137 | 2025-08-17 07:42 | 2025-08-21 01:19 | 196271.0072 | 196271 | [7 empty] | 0 | 0 | 19.84 | 14.72 | 5121.24
TS5500Shv | GG\24\012\X1 | GG | 24 | 12 | X1 | 8 Coal Mining | 53.6 | 0 | 53.6 | 2025-08-17 15:52 | 2025-08-17 22:09 | 7652.4683 | [6 empty] | 7652 | 5475 | 0.54 | 0 | 0 | 14.92 | 5106
TS5500Shv | RS\50\003\D | RS | 50 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-08-17 22:09 | 2025-08-18 21:16 | 28196.4099 | [6 empty] | 28196 | 20863 | 2.09 | 0 | 0 | 5.76 | 5914
TS5500Exc | RS\51\002\B | RS | 51 | 2 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2025-08-17 23:29 | 2025-08-18 11:57 | 11035.2221 | 11035 | [7 empty] | 0 | 0 | 1.26 | 9.07 | 5590.03
TS5500Exc | SC\39\023\D | SC | 39 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-08-18 11:57 | 2025-08-20 23:13 | 74633.6478 | [6 empty] | 74634 | 55823 | 4.65 | 0 | 0 | 7.31 | 5771
TS5500Shv | RS\50\005\B | RS | 50 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-08-18 21:16 | 2025-08-19 06:29 | 11225.3718 | [6 empty] | 11225 | 7996 | 1.25 | 0 | 0 | 9.13 | 5588
DRE2 | GG\20\020\D | GG | 20 | 20 | D | 6 DL | 100 | 100 | 100 | 2025-08-19 01:28 | 2025-08-23 08:15 | 345745.0646 |  |  |  | 6438 | 345745 | 154523 |  |  | 0 | 16.13 | 0 | 6.92 | 5779.8
TS5500Shv | RS\51\002\B | RS | 51 | 2 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-08-19 06:29 | 2025-08-19 18:57 | 13376.0268 | 13376 | [7 empty] | 0 | 0 | 1.52 | 9.07 | 5590.03
TS5500Shv | RS\51\002\B | RS | 51 | 2 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-08-19 18:57 | 2025-08-20 09:00 | 17129.6612 | [6 empty] | 17130 | 12316 | 1.41 | 0 | 0 | 9.07 | 5590
DRE1 | RS\50\005\D | RS | 50 | 5 | D | 6 DL | 100 | 100 | 100 | 2025-08-20 07:26 | 2025-08-22 15:39 | 196354.2624 |  |  |  | 7102 | 196354 | 110597 |  |  | 0 | 29.17 | 0 | 6.09 | 5882.26
TS5500Shv | RS\50\004\D | RS | 50 | 4 | D | 8 Coal Mining | 42.8 | 0 | 42.8 | 2025-08-20 09:00 | 2025-08-21 05:49 | 25384.9869 | [6 empty] | 25385 | 18697 | 1.87 | 0 | 0 | 6.01 | 5892
TS Fleet 5 | RS\52\005\A | RS | 52 | 5 | A | 1 Prestrip - Thick | 65.3218 | 65.3218 | 65.3218 | 2025-08-20 17:55 | 2025-08-24 13:31 | 171828.2954 | 171828 | [7 empty] | 0 | 0 | 24.6 | 14.03 | 5217.34
TS5500Exc | RS\51\002\B | RS | 51 | 2 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-08-20 23:13 | 2025-08-21 13:15 | 17694.3753 | [6 empty] | 17694 | 12722 | 1.46 | 0 | 0 | 9.07 | 5590
PH4100XPC#1 | GG\24\014\X1 | GG | 24 | 14 | X1 | 1 Prestrip - Thick | 100 | 53.3539 | 53.3539 | 2025-08-21 01:19 | 2025-08-23 11:02 | 124331.9909 | 124332 | [7 empty] | 0 | 0 | 16.94 | 14.59 | 5131.25
TS5500Shv | GG\24\013\X1 | GG | 24 | 13 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-08-21 05:49 | 2025-08-21 17:00 | 13638.3265 | [6 empty] | 13638 | 9780 | 0.98 | 0 | 0 | 14.72 | 5121
TS5500Exc | RS\50\004\D | RS | 50 | 4 | D | 8 Coal Mining | 57.2 | 0 | 57.2 | 2025-08-21 13:15 | 2025-08-22 16:13 | 33964.5549 | [6 empty] | 33965 | 25016 | 2.5 | 0 | 0 | 6.01 | 5892
TS5500Shv | GG\24\013\X2 | GG | 24 | 13 | X2 | 1 Prestrip - Thick | 46.4362 | 0 | 46.4362 | 2025-08-21 17:00 | 2025-08-23 00:51 | 34145.317 | 34145 | [7 empty] | 0 | 0 | 3.43 | 0 | 0
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2025-08-22 15:39 | 2025-08-25 15:39
TS5500Exc | GG\24\013\X2 | GG | 24 | 13 | X2 | 1 Prestrip - Thick | 38.3099 | 0 | 31.3112 | 2025-08-22 16:13 | 2025-08-23 18:15 | 23023.6654 | 23024 | [7 empty] | 0 | 0 | 2.31 | 0 | 0
TS5500Shv | RS\50\005\D | RS | 50 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2025-08-23 00:51 | 2025-08-23 23:34 | 24343.2785 |  |  | 24343 | [5 empty] | 0 | 0 | 0 | 6.09 | 5882.26
DRE2 | GG\20\021\D | GG | 20 | 21 | D | 6 DL | 100 | 100 | 100 | 2025-08-23 08:15 | 2025-08-27 17:58 | 355573.3921 |  |  |  | 6621 | 355573 | 158915 |  |  | 0 | 16.68 | 0 | 6.82 | 5787.82
TS6060#1 | GG\24\012\X1 | GG | 24 | 12 | X1 | 8 Coal Mining | 46.4 | 0 | 46.4 | 2025-08-23 09:23 | 2025-08-23 14:17 | 6634.8308 | [6 empty] | 6635 | 4747 | 0.47 | 0 | 0 | 14.92 | 5106
PH4100XPC#1 | GG\24\013\X2 | GG | 24 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 22.2526 | 2025-08-23 11:02 | 2025-08-23 18:15 | 16362.6796 | 16363 | [7 empty] | 0 | 0 | 1.65 | 0 | 0
TS6060#1 | GG\24\012\X2 | GG | 24 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 28.1453 | 2025-08-23 14:17 | 2025-08-24 09:39 | 19986.1282 | 19986 | [7 empty] | 0 | 0 | 1.98 | 0 | 0
PH4100XPC#1 | GG\24\012\X2 | GG | 24 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 49.08 | 2025-08-23 18:15 | 2025-08-24 09:39 | 34852.0174 | 34852 | [7 empty] | 0 | 0 | 3.45 | 0 | 0
TS5500Exc | GG\24\012\X2 | GG | 24 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 19.1765 | 2025-08-23 18:15 | 2025-08-24 09:39 | 13617.3412 | 13617 | [7 empty] | 0 | 0 | 1.35 | 0 | 0
TS5500Shv | GG\24\012\X2 | GG | 24 | 12 | X2 | 1 Prestrip - Thick | 3.5982 | 0 | 3.5982 | 2025-08-23 23:34 | 2025-08-24 01:57 | 2555.1032 | 2555 | [7 empty] | 0 | 0 | 0.25 | 0 | 0
TS5500Shv | GG\24\014\X1 | GG | 24 | 14 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-08-24 01:57 | 2025-08-24 09:50 | 9611.6133 | [6 empty] | 9612 | 6900 | 0.96 | 0 | 0 | 14.59 | 5131
PH4100A | SC\42\013\D | SC | 42 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-08-24 06:41 | 2025-08-30 10:38 | 246614.6293 | 246615 | [7 empty] | 0 | 0 | 21.06 | 7.45 | 5754.53
PH4100XPC#1 | GG\24\012\B | GG | 24 | 12 | B | 1 Prestrip - Thick | 100 | 67.9462 | 67.9462 | 2025-08-24 09:39 | 2025-08-25 21:24 | 80924.1994 | 80924 | [7 empty] | 0 | 0 | 8.03 | 11.78 | 5369.27
TS5500Exc | GG\24\012\B | GG | 24 | 12 | B | 1 Prestrip - Thick | 14.4901 | 14.4901 | 14.4901 | 2025-08-24 09:39 | 2025-08-25 05:10 | 17257.7654 | 17258 | [7 empty] | 0 | 0 | 1.71 | 11.78 | 5369.27
TS6060#1 | GG\20\018\D | GG | 20 | 18 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-08-24 09:39 | 2025-08-25 10:37 | 33777.1152 | [6 empty] | 33777 | 25132 | 2.51 | 0 | 0 | 7.19 | 5757
TS5500Shv | GG\24\012\B | GG | 24 | 12 | B | 1 Prestrip - Thick | 17.5637 | 17.5637 | 17.5637 | 2025-08-24 09:50 | 2025-08-25 05:21 | 20918.5035 | 20919 | [7 empty] | 0 | 0 | 2.07 | 11.78 | 5369.27
TS Fleet 5 | GG\24\013\B | GG | 24 | 13 | B | 1 Prestrip - Thick | 38.1425 | 38.1425 | 38.1425 | 2025-08-24 13:31 | 2025-08-25 15:32 | 48790.554 | 48791 | [7 empty] | 0 | 0 | 4.88 | 12.15 | 5320.62
TS5500Exc | GG\24\013\B | GG | 24 | 13 | B | 1 Prestrip - Thick | 15.4473 | 15.4473 | 15.4473 | 2025-08-25 05:10 | 2025-08-26 03:30 | 19759.5956 | 19760 | [7 empty] | 0 | 0 | 1.98 | 12.15 | 5320.62
TS5500Shv | GG\24\013\B | GG | 24 | 13 | B | 1 Prestrip - Thick | 12.1183 | 12.1183 | 12.1183 | 2025-08-25 05:21 | 2025-08-25 19:48 | 15501.2551 | 15501 | [7 empty] | 0 | 0 | 1.55 | 12.15 | 5320.62
TS6060#1 | GG\20\019\D | GG | 20 | 19 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-08-25 10:37 | 2025-08-26 11:20 | 33460.6877 | [6 empty] | 33461 | 24916 | 2.49 | 0 | 0 | 7.05 | 5768
TS Fleet 5 | GG\24\014\B | GG | 24 | 14 | B | 1 Prestrip - Thick | 34.4645 | 34.4645 | 34.4645 | 2025-08-25 15:32 | 2025-08-26 18:13 | 50066.6997 | 50067 | [7 empty] | 0 | 0 | 7.37 | 12.41 | 5288.96
DRE1 | RS\51\002\D | RS | 51 | 2 | D | 6 DL | 100 | 100 | 100 | 2025-08-25 15:39 | 2025-08-29 18:23 | 344860.4156 |  |  |  | 17731 | 344860 | 277780 |  |  | 0 | 28.66 | 0 | 5.91 | 5901.99
TS5500Shv | GG\24\014\B | GG | 24 | 14 | B | 1 Prestrip - Thick | 17.5637 | 17.5637 | 17.5637 | 2025-08-25 19:48 | 2025-08-26 19:36 | 25514.9088 | 25515 | [7 empty] | 0 | 0 | 3.75 | 12.41 | 5288.96
PH4100XPC#1 | GG\24\013\B | GG | 24 | 13 | B | 1 Prestrip - Thick | 100 | 34.292 | 34.292 | 2025-08-25 21:24 | 2025-08-26 16:47 | 43865.0954 | 43865 | [7 empty] | 0 | 0 | 4.39 | 12.15 | 5320.62
TS5500Exc | GG\24\014\B | GG | 24 | 14 | B | 1 Prestrip - Thick | 14.4901 | 14.4901 | 14.4901 | 2025-08-26 03:30 | 2025-08-27 03:19 | 21049.7997 | 21050 | [7 empty] | 0 | 0 | 3.1 | 12.41 | 5288.96
TS6060#1 | GG\20\020\D | GG | 20 | 20 | D | 8 Coal Mining | 73.8 | 0 | 73.8 | 2025-08-26 11:20 | 2025-08-27 22:00 | 46919.221 | [6 empty] | 46919 | 34966 | 3.5 | 0 | 0 | 6.92 | 5780
PH4100XPC#1 | GG\24\014\B | GG | 24 | 14 | B | 1 Prestrip - Thick | 100 | 33.4817 | 33.4817 | 2025-08-26 16:47 | 2025-08-27 14:16 | 48638.9064 | 48639 | [7 empty] | 0 | 0 | 7.16 | 12.41 | 5288.96
TS Fleet 5 | RS\53\002\B | RS | 53 | 2 | B | 1 Prestrip - Thick | 53.2415 | 53.2415 | 53.2415 | 2025-08-26 18:13 | 2025-08-30 01:36 | 148920.4921 | 148920 | [7 empty] | 0 | 0 | 11.37 | 9.33 | 5565.66
TS5500Shv | GG\20\014\D | GG | 20 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-08-26 19:36 | 2025-08-28 02:17 | 37420.4096 | [6 empty] | 37420 | 27844 | 4.81 | 0 | 0 | 7.2 | 5756
TS5500Exc | RS\50\005\D | RS | 50 | 5 | D | 8 Coal Mining | 88 | 0 | 88 | 2025-08-27 03:19 | 2025-08-27 23:26 | 25339.2109 | [6 empty] | 25339 | 18624 | 3.89 | 0 | 0 | 6.09 | 5882
PH4100XPC#1 | GG\24\017\X1 | GG | 24 | 17 | X1 | 1 Prestrip - Thick | 100 | 48.849 | 48.849 | 2025-08-27 14:16 | 2025-08-29 06:02 | 84931.8901 | 84932 | [7 empty] | 0 | 0 | 11.73 | 14.31 | 5152.61
DRE2 | GG\20\022\D | GG | 20 | 22 | D | 6 DL | 100 | 100 | 100 | 2025-08-27 17:58 | 2025-09-01 11:16 | 381116.6165 |  |  |  | 7097 | 381117 | 170331 |  |  | 0 | 17.79 | 0 | 6.72 | 5796.68
TS6060#1 | GG\20\021\D | GG | 20 | 21 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-08-27 22:00 | 2025-08-28 22:25 | 33049.4408 | [6 empty] | 33049 | 24629 | 2.46 | 0 | 0 | 6.82 | 5788
TS5500Exc | RS\54\003\B | RS | 54 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-08-27 23:26 | 2025-08-29 05:56 | 38418.7675 | [6 empty] | 38419 | 27362 | 2.74 | 0 | 0 | 9.05 | 5580
TS5500Shv | RS\50\005\D | RS | 50 | 5 | D | 8 Coal Mining | 12 | 0 | 12 | 2025-08-28 02:17 | 2025-08-28 05:07 | 3445.2946 | [6 empty] | 3445 | 2532 | 0.53 | 0 | 0 | 6.09 | 5882
TS5500Shv | RS\51\003\B | RS | 51 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-08-28 05:07 | 2025-08-28 20:41 | 18978.9777 | [6 empty] | 18979 | 13556 | 1.36 | 0 | 0 | 8.98 | 5590
TS5500Shv | RS\51\004\A | RS | 51 | 4 | A | 1 Prestrip - Thick | 2.2806 | 2.2806 | 2.2806 | 2025-08-28 20:41 | 2025-08-29 04:31 | 8025.0131 | 8025 | [7 empty] | 0 | 0 | 0.82 | 14.69 | 5160.55
TS6060#1 | RS\54\004\A | RS | 54 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-08-28 22:25 | 2025-09-09 10:23 | 272309.5482 | 272310 | [7 empty] | 0 | 0 | 27.98 | 14.89 | 5150.54
TS5500Shv | RS\51\004\A | RS | 51 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-08-29 04:31 | 2025-08-29 22:46 | 22256.5615 | [6 empty] | 22257 | 15519 | 1.54 | 0 | 0 | 14.69 | 5161
TS5500Exc | RS\51\004\A | RS | 51 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-08-29 05:56 | 2025-08-30 00:11 | 22990.2943 | [6 empty] | 22990 | 16031 | 1.59 | 0 | 0 | 14.69 | 5161
PH4100XPC#1 | GG\24\018\X2 | GG | 24 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 43.9559 | 2025-08-29 06:02 | 2025-08-31 02:17 | 96150.6055 | 96151 | [7 empty] | 0 | 0 | 9.93 | 0 | 0
DRE1 | RS\51\003\D | RS | 51 | 3 | D | 6 DL | 100 | 100 | 100 | 2025-08-29 18:23 | 2025-09-02 19:10 | 338118.4152 |  |  |  | 17384 | 338118 | 272349 |  |  | 0 | 28.98 | 0 | 5.82 | 5908.48
TS5500Shv | GG\24\017\X1 | GG | 24 | 17 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-08-29 22:46 | 2025-08-30 02:46 | 4878.0347 | [6 empty] | 4878 | 3507 | 0.48 | 0 | 0 | 14.31 | 5153
TS5500Exc | RS\51\002\D | RS | 51 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-08-30 00:11 | 2025-09-01 03:10 | 64221.933 | [6 empty] | 64222 | 47570 | 4.58 | 0 | 0 | 5.91 | 5902
TS Fleet 5 | RS\53\003\A | RS | 53 | 3 | A | 1 Prestrip - Thick | 58.5981 | 58.5981 | 58.5981 | 2025-08-30 01:36 | 2025-09-02 05:56 | 143216.3602 | 143216 | [7 empty] | 0 | 0 | 14.67 | 14.29 | 5197.16
TS5500Shv | RS\51\004\B | RS | 51 | 4 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-08-30 02:46 | 2025-08-30 15:00 | 13120.2908 | 13120 | [7 empty] | 0 | 0 | 1.31 | 8.92 | 5595.51
PH4100A | SC\43\013\D | SC | 43 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-08-30 10:38 | 2025-09-06 02:43 | 269285.2687 | 269285 | [7 empty] | 0 | 0 | 23.4 | 7.44 | 5755.32
TS5500Shv | RS\51\005\A | RS | 51 | 5 | A | 1 Prestrip - Thick | 11.4439 | 11.4439 | 11.4439 | 2025-08-30 15:00 | 2025-08-31 22:09 | 32044.0537 | 32044 | [7 empty] | 0 | 0 | 4.49 | 13.69 | 5241.26
PH4100XPC#1 | GG\24\018\B | GG | 24 | 18 | B | 1 Prestrip - Thick | 100 | 82.3719 | 82.3719 | 2025-08-31 02:17 | 2025-09-02 06:32 | 118257.6279 | 118258 | [7 empty] | 0 | 0 | 11.74 | 13.32 | 5240.93
TS5500Shv | GG\20\018\D | GG | 20 | 18 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-08-31 22:09 | 2025-09-01 23:06 | 30432.8464 | [6 empty] | 30433 | 22644 | 2.26 | 0 | 0 | 7.19 | 5757
TS5500Exc | GG\24\018\B | GG | 24 | 18 | B | 1 Prestrip - Thick | 17.5773 | 16.8561 | 16.8561 | 2025-09-01 03:10 | 2025-09-02 06:32 | 24199.6021 | 24200 | [7 empty] | 0 | 0 | 2.4 | 13.32 | 5240.93
DRE2 | GG\20\023\D | GG | 20 | 23 | D | 6 DL | 100 | 100 | 100 | 2025-09-01 11:16 | 2025-09-05 10:36 | 320680.711 |  |  |  | 5832 | 320681 | 93190 |  |  | 0 | 15.58 | 0 | 6.5 | 5818.16
TS5500Shv | RS\51\005\A | RS | 51 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-09-01 23:06 | 2025-09-02 09:26 | 12590.0888 | [6 empty] | 12590 | 8819 | 1.42 | 0 | 0 | 13.69 | 5241
TS Fleet 5 | GG\24\018\B | GG | 24 | 18 | B | 1 Prestrip - Thick | 45.419 | 0.77195 | 0.77195 | 2025-09-02 05:56 | 2025-09-02 06:32 | 1108.2593 | 1108 | [7 empty] | 0 | 0 | 0.11 | 13.32 | 5240.93
TS Fleet 5 | RS\53\004\A | RS | 53 | 4 | A | 1 Prestrip - Thick | 64.5065 | 64.5065 | 64.5065 | 2025-09-02 06:32 | 2025-09-06 11:37 | 189645.457 | 189645 | [7 empty] | 0 | 0 | 19.45 | 14.92 | 5148.09
PH4100XPC#1 | GG\24\019\B | GG | 24 | 19 | B | 1 Prestrip - Thick | 100 | 48.0408 | 48.0408 | 2025-09-02 06:32 | 2025-09-04 21:04 | 140161.3338 | 140161 | [7 empty] | 0 | 0 | 14.25 | 13.91 | 5215.35
TS5500Exc | RS\53\003\A | RS | 53 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2025-09-02 06:32 | 2025-09-03 07:16 | 31163.8073 | [6 empty] | 31164 | 21823 | 2.18 | 0 | 0 | 14.29 | 5197
TS5500Shv | RS\52\002\A | RS | 52 | 2 | A | 1 Prestrip - Thick | 4.0074 | 4.0074 | 4.0074 | 2025-09-02 09:26 | 2025-09-02 17:22 | 8233.3899 | 8233 | [7 empty] | 0 | 0 | 0.78 | 14.64 | 5171.43
TS5500Shv | RS\52\002\A | RS | 52 | 2 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-09-02 17:22 | 2025-09-03 02:50 | 11548.4387 | [6 empty] | 11548 | 8102 | 0.63 | 0 | 0 | 14.64 | 5171
DRE1 | RS\54\003\D | RS | 54 | 3 | D | 6 DL | 100 | 100 | 100 | 2025-09-02 19:10 | 2025-09-06 19:51 | 337722.8437 |  |  |  | 17364 | 337723 | 272030 |  |  | 0 | 28.94 | 0 | 5.93 | 5899.15
TS5500Shv | RS\51\003\D | RS | 51 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-09-03 02:50 | 2025-09-04 02:04 | 28335.3851 | [6 empty] | 28335 | 20933 | 2.09 | 0 | 0 | 5.82 | 5908
TS5500Exc | RS\51\004\B | RS | 51 | 4 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2025-09-03 07:16 | 2025-09-03 19:30 | 10824.2399 | 10824 | [7 empty] | 0 | 0 | 1.08 | 8.92 | 5595.51
TS5500Exc | RS\51\004\B | RS | 51 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-09-03 19:30 | 2025-09-04 10:20 | 18680.58 | [6 empty] | 18681 | 13300 | 1.32 | 0 | 0 | 8.92 | 5596
TS5500Shv | RS\51\004\B | RS | 51 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-09-04 02:04 | 2025-09-04 16:54 | 18084.3913 | [6 empty] | 18084 | 12875 | 1.28 | 0 | 0 | 8.92 | 5596
TS5500Exc | RS\51\005\A | RS | 51 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-09-04 10:20 | 2025-09-04 20:40 | 13005.1467 | [6 empty] | 13005 | 9110 | 1.46 | 0 | 0 | 13.69 | 5241
TS5500Shv | RS\52\003\A | RS | 52 | 3 | A | 1 Prestrip - Thick | 5.6367 | 5.6367 | 5.6367 | 2025-09-04 16:54 | 2025-09-05 07:01 | 14330.6803 | 14331 | [7 empty] | 0 | 0 | 1.47 | 13.5 | 5259.4
TS5500Exc | RS\51\005\B | RS | 51 | 5 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2025-09-04 20:40 | 2025-09-05 06:12 | 8429.594 | 8430 | [7 empty] | 0 | 0 | 1.36 | 9.12 | 5579.65
PH4100XPC#1 | GG\24\020\B | GG | 24 | 20 | B | 1 Prestrip - Thick | 100 | 42.4222 | 42.4222 | 2025-09-04 21:04 | 2025-09-06 18:32 | 105974.3612 | 105974 | [7 empty] | 0 | 0 | 10.15 | 16.53 | 5021.02
TS5500Exc | RS\52\002\A | RS | 52 | 2 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-09-05 06:12 | 2025-09-05 15:40 | 11929.1565 | [6 empty] | 11929 | 8369 | 0.65 | 0 | 0 | 14.64 | 5171
TS5500Shv | RS\51\005\B | RS | 51 | 5 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-09-05 07:01 | 2025-09-05 16:33 | 10217.6897 | 10218 | [7 empty] | 0 | 0 | 1.65 | 9.12 | 5579.65
DRE2 | GG\22\013\B | GG | 22 | 13 | B | 6 DL | 100 | 0 | 100 | 2025-09-05 10:36 | 2025-09-07 21:43 | 198879.6718 |  |  |  |  | 198880 | 165733 |  |  | 0 | 16.49 | 0 | 12.05 | 5334.07
TS5500Exc | RS\52\003\A | RS | 52 | 3 | A | 8 Coal Mining | 100 | 0 | 100 | 2025-09-05 15:40 | 2025-09-07 01:48 | 43002.9035 | [6 empty] | 43003 | 30240 | 3.03 | 0 | 0 | 13.5 | 5259
TS5500Shv | RS\51\005\B | RS | 51 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-09-05 16:33 | 2025-09-06 01:06 | 10435.4907 | [6 empty] | 10435 | 7416 | 1.21 | 0 | 0 | 9.12 | 5580
TS5500Shv | RS\52\002\B | RS | 52 | 2 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-09-06 01:06 | 2025-09-06 15:37 | 15564.2749 | 15564 | [7 empty] | 0 | 0 | 1.41 | 9.11 | 5585
PH4100A | SC\42\014\D | SC | 42 | 14 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-09-06 02:43 | 2025-09-10 23:37 | 194044.0723 | 194044 | [7 empty] | 0 | 0 | 16.49 | 7.51 | 5748.67
TS Fleet 5 | RS\52\002\B | RS | 52 | 2 | B | 1 Prestrip - Thick | 54.7945 | 45.2055 | 45.2055 | 2025-09-06 11:37 | 2025-09-06 18:28 | 12840.5268 | 12841 | [7 empty] | 0 | 0 | 1.16 | 9.11 | 5585
TS5500Shv | GG\20\019\D | GG | 20 | 19 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-09-06 15:37 | 2025-09-07 16:21 | 30147.7483 | [6 empty] | 30148 | 22449 | 2.24 | 0 | 0 | 7.05 | 5768
TS Fleet 5 | RS\53\003\B | RS | 53 | 3 | B | 1 Prestrip - Thick | 83.831 | 83.831 | 83.831 | 2025-09-06 18:28 | 2025-09-07 05:28 | 20654.6364 | 20655 | [7 empty] | 0 | 0 | 2.06 | 9 | 5585.17
PH4100XPC#1 | GG\24\021\D | GG | 24 | 21 | D | 1 Prestrip - Thick | 100 | 51.1851 | 51.1851 | 2025-09-06 18:32 | 2025-09-09 11:23 | 153179.0072 | 153179 | [7 empty] | 0 | 0 | 16.4 | 6.78 | 5789.52
DRE1 | RS\51\004\D | RS | 51 | 4 | D | 6 DL | 100 | 100 | 100 | 2025-09-06 19:51 | 2025-09-10 18:45 | 331496.6517 |  |  |  | 17044 | 331497 | 267015 |  |  | 0 | 28.39 | 0 | 6 | 5893.26
TS5500Exc | RS\51\005\B | RS | 51 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-09-07 01:48 | 2025-09-07 10:22 | 10779.5179 | [6 empty] | 10780 | 7660 | 1.25 | 0 | 0 | 9.12 | 5580
TS Fleet 5 | RS\52\003\B | RS | 52 | 3 | B | 1 Prestrip - Thick | 1.0447 | 1.0447 | 1.0447 | 2025-09-07 05:28 | 2025-09-07 05:37 | 257.1584 | 257 | [7 empty] | 0 | 0 | 0.03 | 8.98 | 5588.35
TS Fleet 5 | RS\53\005\A | RS | 53 | 5 | A | 1 Prestrip - Thick | 82.035 | 82.035 | 82.035 | 2025-09-07 05:37 | 2025-09-11 19:22 | 205909.1974 | 205909 | [7 empty] | 0 | 0 | 29.3 | 14.4 | 5189.45
TS5500Exc | RS\51\003\D | RS | 51 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-09-07 10:22 | 2025-09-08 09:36 | 29269.5187 | [6 empty] | 29270 | 21624 | 2.16 | 0 | 0 | 5.82 | 5908
TS5500Shv | RS\52\002\B | RS | 52 | 2 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-09-07 16:21 | 2025-09-08 10:13 | 21794.041 | [6 empty] | 21794 | 15647 | 1.4 | 0 | 0 | 9.11 | 5585
DRE2 | GG\22\012\B | GG | 22 | 12 | B | 6 DL | 100 | 0 | 100 | 2025-09-07 21:43 | 2025-09-10 09:23 | 200666.2148 |  |  |  |  | 200666 | 167222 |  |  | 0 | 16.78 | 0 | 11.22 | 5415.51
TS5500Exc | RS\52\002\B | RS | 52 | 2 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-09-08 09:36 | 2025-09-09 03:28 | 22512.5259 | [6 empty] | 22513 | 16162 | 1.45 | 0 | 0 | 9.11 | 5585
TS5500Shv | RS\52\003\B | RS | 52 | 3 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-09-08 10:13 | 2025-09-08 22:48 | 13487.6304 | 13488 | [7 empty] | 0 | 0 | 1.35 | 8.98 | 5588.35
TS5500Shv | RS\52\004\A | RS | 52 | 4 | A | 1 Prestrip - Thick | 7.2055 | 7.2055 | 7.2055 | 2025-09-08 22:48 | 2025-09-09 21:09 | 22854.6342 | 22855 | [7 empty] | 0 | 0 | 2.33 | 14.86 | 5151.3
TS5500Exc | RS\52\003\B | RS | 52 | 3 | B | 1 Prestrip - Thick | 45.2055 | 44.1608 | 44.1608 | 2025-09-09 03:28 | 2025-09-09 15:46 | 10870.1367 | 10870 | [7 empty] | 0 | 0 | 1.09 | 8.98 | 5588.35
TS6060#1 | GG\24\017\X1 | GG | 24 | 17 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-09-09 10:23 | 2025-09-09 14:23 | 5414.0825 | [6 empty] | 5414 | 3892 | 0.54 | 0 | 0 | 14.31 | 5153
PH4100XPC#1 | GG\24\022\B | GG | 24 | 22 | B | 1 Prestrip - Thick | 100 | 42.8321 | 42.8321 | 2025-09-09 11:23 | 2025-09-12 10:57 | 168236.7392 | 168237 | [7 empty] | 0 | 0 | 16.03 | 21.41 | 4639.45
TS6060#1 | GG\20\022\D | GG | 20 | 22 | D | 8 Coal Mining | 22.1 | 0 | 22.1 | 2025-09-09 14:23 | 2025-09-10 00:33 | 13756.2944 | [6 empty] | 13756 | 10268 | 1.03 | 0 | 0 | 6.72 | 5797
TS5500Exc | GG\24\017\B | GG | 24 | 17 | B | 1 Prestrip - Thick | 13.3209 | 13.3209 | 13.3209 | 2025-09-09 15:46 | 2025-09-10 15:14 | 20753.5762 | 20754 | [7 empty] | 0 | 0 | 3.04 | 13.42 | 5216.22
TS5500Shv | GG\24\017\B | GG | 24 | 17 | B | 1 Prestrip - Thick | 24.2153 | 24.2153 | 24.2153 | 2025-09-09 21:09 | 2025-09-11 08:21 | 37726.6475 | 37727 | [7 empty] | 0 | 0 | 5.52 | 13.42 | 5216.22
TS6060#1 | GG\22\013\B | GG | 22 | 13 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-09-10 00:33 | 2025-09-10 19:28 | 25597.5246 | [6 empty] | 25598 | 18582 | 1.86 | 0 | 0 | 12.05 | 5334
DRE2 | GG\22\011\B | GG | 22 | 11 | B | 6 DL | 100 | 0 | 100 | 2025-09-10 09:23 | 2025-09-13 03:44 | 223231.4708 |  |  |  |  | 223231 | 171717 |  |  | 0 | 17.26 | 0 | 10.37 | 5495.01
TS5500Exc | GG\22\012\B | GG | 22 | 12 | B | 8 Coal Mining | 100 | 0 | 53.9 | 2025-09-10 15:14 | 2025-09-11 12:04 | 26247.061 | [6 empty] | 26247 | 19128 | 1.92 | 0 | 0 | 11.22 | 5416
DRE1 | RS\51\005\D | RS | 51 | 5 | D | 6 DL | 100 | 100 | 100 | 2025-09-10 18:45 | 2025-09-12 23:33 | 184399.9341 |  |  |  | 6648 | 184400 | 103785 |  |  | 0 | 29.51 | 0 | 6.08 | 5884.31
TS6060#1 | GG\22\012\B | GG | 22 | 12 | B | 8 Coal Mining | 100 | 0 | 46.1 | 2025-09-10 19:28 | 2025-09-11 12:04 | 22467.1559 | [6 empty] | 22467 | 16373 | 1.64 | 0 | 0 | 11.22 | 5416
PH4100A | SC\43\014\D | SC | 43 | 14 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-09-10 23:37 | 2025-09-16 03:00 | 206060.119 | 206060 | [7 empty] | 0 | 0 | 17.54 | 7.48 | 5751.68
TS5500Shv | RS\51\004\D | RS | 51 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-09-11 08:21 | 2025-09-12 08:19 | 29230.6547 | [6 empty] | 29231 | 21512 | 2.15 | 0 | 0 | 6 | 5893
TS5500Exc | RS\51\004\D | RS | 51 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-09-11 12:04 | 2025-09-12 12:02 | 30194.3026 | [6 empty] | 30194 | 22222 | 2.22 | 0 | 0 | 6 | 5893
TS6060#1 | RS\54\005\A | RS | 54 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-09-11 12:04 | 2025-09-21 10:00 | 236562.0912 | 236562 | [7 empty] | 0 | 0 | 33.41 | 14.54 | 5179.25
TS Fleet 5 | GG\24\017\B | GG | 24 | 17 | B | 1 Prestrip - Thick | 36.4139 | 36.4139 | 36.4139 | 2025-09-11 19:22 | 2025-09-13 01:37 | 56731.6729 | 56732 | [7 empty] | 0 | 0 | 8.31 | 13.42 | 5216.22
TS5500Shv | RS\52\003\B | RS | 52 | 3 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-09-12 08:19 | 2025-09-12 23:52 | 18963.3065 | [6 empty] | 18963 | 13535 | 1.35 | 0 | 0 | 8.98 | 5588
PH4100XPC#1 | GG\24\017\B | GG | 24 | 17 | B | 1 Prestrip - Thick | 100 | 26.0499 | 26.0499 | 2025-09-12 10:57 | 2025-09-13 04:53 | 40584.8973 | 40585 | [7 empty] | 0 | 0 | 5.94 | 13.42 | 5216.22
TS5500Exc | RS\52\003\B | RS | 52 | 3 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-09-12 12:02 | 2025-09-13 03:35 | 19588.4705 | [6 empty] | 19588 | 13981 | 1.4 | 0 | 0 | 8.98 | 5588
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2025-09-12 23:33 | 2025-09-15 23:33
TS5500Shv | RS\51\005\D | RS | 51 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2025-09-12 23:52 | 2025-09-13 20:53 | 22530.6375 |  |  | 22531 | [5 empty] | 0 | 0 | 0 | 6.08 | 5884.31
TS Fleet 5 | RS\55\005\A | RS | 55 | 5 | A | 1 Prestrip - Thick | 36.773 | 36.773 | 36.773 | 2025-09-13 01:37 | 2025-09-14 21:03 | 81499.5996 | 81500 | [7 empty] | 0 | 0 | 11.47 | 14.53 | 5180.28
TS5500Exc | RS\52\004\A | RS | 52 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2025-09-13 03:35 | 2025-09-14 15:44 | 45524.5053 | [6 empty] | 45525 | 31713 | 3.16 | 0 | 0 | 14.86 | 5151
DRE2 | GG\22\010\B | GG | 22 | 10 | B | 6 DL | 100 | 0 | 100 | 2025-09-13 03:44 | 2025-09-15 22:52 | 225800.5348 |  |  |  |  | 225801 | 188167 |  |  | 0 | 18.79 | 0 | 10.08 | 5524.1
PH4100XPC#1 | W2\01\010\B | W2 | 1 | 10 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2025-09-13 04:53 | 2025-09-13 04:53 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\01\010\D | W2 | 1 | 10 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2025-09-13 04:53 | 2025-09-13 04:53 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\01\007\B | W2 | 1 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-09-13 04:53 | 2025-10-29 18:22 | 2564416.655 | 2564417 | [7 empty] | 0 | 0 | 53.79 | 9.87 | 5313.92
TS5500Shv | GG\20\020\D | GG | 20 | 20 | D | 8 Coal Mining | 26.2 | 0 | 26.2 | 2025-09-13 20:53 | 2025-09-14 10:32 | 16645.1534 | [6 empty] | 16645 | 12405 | 1.24 | 0 | 0 | 6.92 | 5780
TS5500Shv | RS\51\005\D | RS | 51 | 5 | D | 8 Coal Mining | 52.7 | 0 | 52.7 | 2025-09-14 10:32 | 2025-09-14 21:55 | 13885.643 | [6 empty] | 13886 | 10200 | 2.31 | 0 | 0 | 6.08 | 5884
TS5500Exc | RS\51\005\D | RS | 51 | 5 | D | 8 Coal Mining | 47.3 | 0 | 47.3 | 2025-09-14 15:44 | 2025-09-15 01:39 | 12486.3 | [6 empty] | 12486 | 9172 | 2.07 | 0 | 0 | 6.08 | 5884
TS Fleet 5 | RS\56\002\D | RS | 56 | 2 | D | 1 Prestrip - Thick | 38.8913 | 38.8913 | 38.8913 | 2025-09-14 21:03 | 2025-09-16 09:41 | 68712.2666 | 68712 | [7 empty] | 0 | 0 | 7.04 | 6.58 | 5841.95
TS5500Shv | RS\52\004\B | RS | 52 | 4 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-09-14 21:55 | 2025-09-15 10:00 | 12941.6829 | 12942 | [7 empty] | 0 | 0 | 1.29 | 8.87 | 5593.63
TS5500Exc | RS\52\004\B | RS | 52 | 4 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2025-09-15 01:39 | 2025-09-15 13:43 | 10676.8884 | 10677 | [7 empty] | 0 | 0 | 1.06 | 8.87 | 5593.63
TS5500Shv | RS\52\005\A | RS | 52 | 5 | A | 1 Prestrip - Thick | 7.1085 | 7.1085 | 7.1085 | 2025-09-15 10:00 | 2025-09-16 04:11 | 18698.9258 | 18699 | [7 empty] | 0 | 0 | 2.68 | 14.03 | 5217.34
TS5500Exc | RS\52\004\B | RS | 52 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-09-15 13:43 | 2025-09-16 04:37 | 18769.7839 | [6 empty] | 18770 | 13336 | 1.33 | 0 | 0 | 8.87 | 5594
DRE2 | GG\22\009\B | GG | 22 | 9 | B | 6 DL | 100 | 0 | 100 | 2025-09-15 22:52 | 2025-09-18 20:51 | 235402.0268 |  |  |  |  | 235402 | 196168 |  |  | 0 | 19.62 | 0 | 10.03 | 5520.4
DRE1 | RS\52\002\D | RS | 52 | 2 | D | 6 DL | 100 | 100 | 100 | 2025-09-15 23:33 | 2025-09-20 08:52 | 367927.9403 |  |  |  | 18917 | 367928 | 296360 |  |  | 0 | 28.8 | 0 | 6.13 | 5881.49
PH4100A | SC\42\015\D | SC | 42 | 15 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-09-16 03:00 | 2025-09-20 07:50 | 167566.9988 | 167567 | [7 empty] | 0 | 0 | 14.18 | 7.43 | 5755.89
TS5500Shv | RS\52\004\B | RS | 52 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-09-16 04:11 | 2025-09-16 19:05 | 18170.7483 | [6 empty] | 18171 | 12910 | 1.29 | 0 | 0 | 8.87 | 5594
TS5500Exc | RS\52\005\A | RS | 52 | 5 | A | 8 Coal Mining | 100 | 0 | 100 | 2025-09-16 04:37 | 2025-09-17 00:55 | 25570.083 | [6 empty] | 25570 | 17884 | 2.98 | 0 | 0 | 14.03 | 5217
TS Fleet 5 | RS\56\004\A | RS | 56 | 4 | A | 1 Prestrip - Thick | 39.5324 | 39.5324 | 39.5324 | 2025-09-16 09:41 | 2025-09-18 12:25 | 95180.0325 | 95180 | [7 empty] | 0 | 0 | 9.77 | 15.09 | 5134.64
TS5500Shv | GG\20\021\D | GG | 20 | 21 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-09-16 19:05 | 2025-09-17 19:31 | 29777.2189 | [6 empty] | 29777 | 22191 | 2.22 | 0 | 0 | 6.82 | 5788
TS5500Exc | RS\52\005\B | RS | 52 | 5 | B | 1 Prestrip - Thick | 44.6245 | 44.6245 | 44.6245 | 2025-09-17 00:55 | 2025-09-17 09:32 | 7616.372 | 7616 | [7 empty] | 0 | 0 | 1.28 | 9.32 | 5557.08
TS5500Exc | RS\53\003\B | RS | 53 | 3 | B | 1 Prestrip - Thick | 45.1777 | 16.169 | 16.169 | 2025-09-17 09:32 | 2025-09-17 14:02 | 3983.8001 | 3984 | [7 empty] | 0 | 0 | 0.4 | 9 | 5585.17
TS5500Exc | RS\53\003\B | RS | 53 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-09-17 14:02 | 2025-09-18 20:36 | 38490.4874 | [6 empty] | 38490 | 27452 | 2.74 | 0 | 0 | 9 | 5585
TS5500Shv | RS\52\005\B | RS | 52 | 5 | B | 1 Prestrip - Thick | 28.2168 | 28.2168 | 28.2168 | 2025-09-17 19:31 | 2025-09-18 | 4815.964 | 4816 | [7 empty] | 0 | 0 | 0.81 | 9.32 | 5557.08
TS5500Shv | RS\53\002\B | RS | 53 | 2 | B | 1 Prestrip - Thick | 15.494 | 15.494 | 15.494 | 2025-09-18 | 2025-09-19 17:40 | 43337.7779 | 43338 | [7 empty] | 0 | 0 | 3.31 | 9.33 | 5565.66
TS Fleet 5 | RS\56\005\A | RS | 56 | 5 | A | 1 Prestrip - Thick | 39.3857 | 39.3857 | 39.3857 | 2025-09-18 12:25 | 2025-09-20 07:49 | 81418.4554 | 81418 | [7 empty] | 0 | 0 | 11.37 | 14.65 | 5169.91
TS5500Exc | RS\53\004\A | RS | 53 | 4 | A | 8 Coal Mining | 100 | 0 | 100 | 2025-09-18 20:36 | 2025-09-20 08:43 | 45510.6303 | [6 empty] | 45511 | 31700 | 3.18 | 0 | 0 | 14.92 | 5148
DRE2 | GG\22\008\B | GG | 22 | 8 | B | 6 DL | 100 | 0 | 100 | 2025-09-18 20:51 | 2025-09-22 02:26 | 260949.054 |  |  |  |  | 260949 | 200730 |  |  | 0 | 20.08 | 0 | 10.17 | 5494
TS5500Shv | RS\53\002\B | RS | 53 | 2 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-09-19 17:40 | 2025-09-20 12:25 | 22846.2131 | [6 empty] | 22846 | 16364 | 1.24 | 0 | 0 | 9.33 | 5566
TS Fleet 5 | RS\57\004\A | RS | 57 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-09-20 07:49 | 2025-09-25 13:07 | 235072.0532 | 235072 | [7 empty] | 0 | 0 | 24.13 | 15.92 | 5068.87
PH4100A | SC\43\015\D | SC | 43 | 15 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-09-20 07:50 | 2025-09-24 15:49 | 174176.5159 | 174177 | [7 empty] | 0 | 0 | 14.76 | 7.43 | 5755.59
TS5500Exc | RS\53\002\B | RS | 53 | 2 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-09-20 08:43 | 2025-09-21 03:28 | 23599.3849 | [6 empty] | 23599 | 16904 | 1.28 | 0 | 0 | 9.33 | 5566
DRE1 | RS\52\003\D | RS | 52 | 3 | D | 6 DL | 100 | 100 | 100 | 2025-09-20 08:52 | 2025-09-24 09:22 | 337044.9458 |  |  |  | 17329 | 337045 | 271484 |  |  | 0 | 28.89 | 0 | 5.86 | 5904.95
TS5500Shv | RS\52\002\D | RS | 52 | 2 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-09-20 12:25 | 2025-09-21 16:01 | 33670.0036 | [6 empty] | 33670 | 24856 | 2.25 | 0 | 0 | 6.13 | 5881
TS5500Exc | RS\52\002\D | RS | 52 | 2 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-09-21 03:28 | 2025-09-22 07:04 | 34780.0037 | [6 empty] | 34780 | 25676 | 2.33 | 0 | 0 | 6.13 | 5881
TS6060#1 | RS\52\005\B | RS | 52 | 5 | B | 1 Prestrip - Thick | 27.1587 | 27.1587 | 27.1587 | 2025-09-21 10:00 | 2025-09-21 14:30 | 4635.3653 | 4635 | [7 empty] | 0 | 0 | 0.78 | 9.32 | 5557.08
TS6060#1 | RS\53\004\B | RS | 53 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-09-21 14:30 | 2025-09-22 13:30 | 23746.2929 | 23746 | [7 empty] | 0 | 0 | 2.38 | 9.01 | 5578.21
TS5500Shv | RS\52\005\B | RS | 52 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-09-21 16:01 | 2025-09-22 00:30 | 10342.2799 | [6 empty] | 10342 | 7331 | 1.24 | 0 | 0 | 9.32 | 5557
TS5500Shv | GG\20\022\D | GG | 20 | 22 | D | 8 Coal Mining | 77.9 | 0 | 77.9 | 2025-09-22 00:30 | 2025-09-23 16:21 | 48594.9861 | [6 empty] | 48595 | 36271 | 3.63 | 0 | 0 | 6.72 | 5797
DRE2 | GG\22\007\B | GG | 22 | 7 | B | 6 DL | 100 | 0 | 100 | 2025-09-22 02:26 | 2025-09-25 01:40 | 239640.8965 |  |  |  |  | 239641 | 199701 |  |  | 0 | 19.97 | 0 | 10.34 | 5460.32
TS5500Exc | RS\52\005\B | RS | 52 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-09-22 07:04 | 2025-09-22 15:33 | 10683.2342 | [6 empty] | 10683 | 7572 | 1.28 | 0 | 0 | 9.32 | 5557
TS6060#1 | RS\53\004\B | RS | 53 | 4 | B | 8 Coal Mining | 100 | 0 | 55.4 | 2025-09-22 13:30 | 2025-09-23 04:41 | 20527.8703 | [6 empty] | 20528 | 14565 | 1.46 | 0 | 0 | 9.01 | 5578
TS5500Exc | RS\53\004\B | RS | 53 | 4 | B | 8 Coal Mining | 100 | 0 | 44.6 | 2025-09-22 15:33 | 2025-09-23 04:41 | 16529.1011 | [6 empty] | 16529 | 11728 | 1.18 | 0 | 0 | 9.01 | 5578
TS5500Exc | RS\53\005\A | RS | 53 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-09-23 04:41 | 2025-09-23 15:25 | 13527.439 | [6 empty] | 13527 | 9445 | 1.56 | 0 | 0 | 14.4 | 5189
TS6060#1 | GG\22\011\B | GG | 22 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-09-23 04:41 | 2025-09-24 16:54 | 49035.0804 | [6 empty] | 49035 | 35873 | 3.6 | 0 | 0 | 10.37 | 5495
TS5500Exc | RS\54\003\D | RS | 54 | 3 | D | 8 Coal Mining | 58.6 | 0 | 58.6 | 2025-09-23 15:25 | 2025-09-24 18:36 | 34239.7121 | [6 empty] | 34240 | 25177 | 2.52 | 0 | 0 | 5.93 | 5899
TS5500Shv | GG\20\023\D | GG | 20 | 23 | D | 7 PostStrip | 100 | 0 | 100 | 2025-09-23 16:21 | 2025-09-25 11:59 | 46779.6386 |  |  | 46780 | [5 empty] | 0 | 0 | 0 | 6.5 | 5818.16
DRE1 | RS\52\004\D | RS | 52 | 4 | D | 6 DL | 100 | 100 | 100 | 2025-09-24 09:22 | 2025-09-28 09:26 | 335618.1917 |  |  |  | 17255 | 335618 | 270335 |  |  | 0 | 28.75 | 0 | 5.98 | 5894.51
PH4100A | SC\42\016\D | SC | 42 | 16 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-09-24 15:49 | 2025-09-29 09:30 | 190198.5417 | 190199 | [7 empty] | 0 | 0 | 19.71 | 7.33 | 5764.22
TS6060#1 | GG\22\010\B | GG | 22 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-09-24 16:54 | 2025-09-26 05:44 | 49846.6097 | [6 empty] | 49847 | 36525 | 3.65 | 0 | 0 | 10.08 | 5524
TS5500Exc | RS\52\003\D | RS | 52 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-09-24 18:36 | 2025-09-25 17:57 | 29419.3401 | [6 empty] | 29419 | 21700 | 2.17 | 0 | 0 | 5.86 | 5905
DRE2 | GG\22\006\B | GG | 22 | 6 | B | 6 DL | 100 | 0 | 100 | 2025-09-25 01:40 | 2025-09-28 07:13 | 260862.931 |  |  |  |  | 260863 | 200664 |  |  | 0 | 20.1 | 0 | 10.05 | 5464.78
TS5500Shv | RS\52\003\D | RS | 52 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-09-25 11:59 | 2025-09-26 11:21 | 28480.425 | [6 empty] | 28480 | 21008 | 2.1 | 0 | 0 | 5.86 | 5905
TS Fleet 5 | RS\57\002\D | RS | 57 | 2 | D | 1 Prestrip - Thick | 38.938 | 38.938 | 38.938 | 2025-09-25 13:07 | 2025-09-26 23:13 | 63970.587 | 63971 | [7 empty] | 0 | 0 | 6.6 | 6.66 | 5835.03
TS5500Exc | RS\54\004\A | RS | 54 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-09-25 17:57 | 2025-09-26 12:14 | 23016.059 | [6 empty] | 23016 | 16030 | 1.61 | 0 | 0 | 14.89 | 5151
TS6060#1 | GG\20\023\D | GG | 20 | 23 | D | 8 Coal Mining | 48.9 | 0 | 48.9 | 2025-09-26 05:44 | 2025-09-27 03:50 | 29900.5577 | [6 empty] | 29901 | 22407 | 2.39 | 0 | 0 | 6.5 | 5818
TS5500Shv | GG\20\023\D | GG | 20 | 23 | D | 8 Coal Mining | 51.1 | 0 | 51.1 | 2025-09-26 11:21 | 2025-09-27 12:58 | 31232.0172 | [6 empty] | 31232 | 23405 | 2.5 | 0 | 0 | 6.5 | 5818
TS5500Exc | SC\39\024\D | SC | 39 | 24 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-09-26 12:14 | 2025-09-29 00:30 | 75913.4622 | [6 empty] | 75913 | 56691 | 4.72 | 0 | 0 | 7.27 | 5775
TS Fleet 5 | RS\57\003\D | RS | 57 | 3 | D | 1 Prestrip - Thick | 64.409 | 64.409 | 64.409 | 2025-09-26 23:13 | 2025-09-30 07:56 | 151410.4293 | 151410 | [7 empty] | 0 | 0 | 15.5 | 5.99 | 5893.2
TS6060#1 | RS\55\001\D | RS | 55 | 1 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-09-27 03:50 | 2025-09-30 22:27 | 93256.8255 | 93257 | [7 empty] | 0 | 0 | 13.02 | 7.47 | 5759.32
TS5500Shv | GG\22\013\B | GG | 22 | 13 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-09-27 12:58 | 2025-09-28 07:52 | 23063.1162 | [6 empty] | 23063 | 16742 | 1.67 | 0 | 0 | 12.05 | 5334
DRE2 | GG\22\005\B | GG | 22 | 5 | B | 6 DL | 100 | 0 | 100 | 2025-09-28 07:13 | 2025-10-01 13:48 | 264335.7324 |  |  |  |  | 264336 | 203335 |  |  | 0 | 20.44 | 0 | 9.27 | 5514.49
TS5500Shv | RS\53\005\A | RS | 53 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-09-28 07:52 | 2025-09-28 18:37 | 13095.7123 | [6 empty] | 13096 | 9144 | 1.51 | 0 | 0 | 14.4 | 5189
DRE1 | RS\52\005\D | RS | 52 | 5 | D | 6 DL | 100 | 100 | 100 | 2025-09-28 09:26 | 2025-09-30 12:00 | 176599.1775 |  |  |  | 6345 | 176599 | 99315 |  |  | 0 | 29.87 | 0 | 6.07 | 5886.61
TS5500Shv | RS\52\004\D | RS | 52 | 4 | D | 8 Coal Mining | 44.1 | 0 | 44.1 | 2025-09-28 18:37 | 2025-09-29 16:08 | 26241.1731 | [6 empty] | 26241 | 19297 | 1.93 | 0 | 0 | 5.98 | 5895
TS5500Exc | GG\25\005\X1 | GG | 25 | 5 | X1 | 1 Prestrip - Thick | 100 | 45.4884 | 45.4884 | 2025-09-29 00:30 | 2025-10-19 02:50 | 426836.9122 | 426837 | [7 empty] | 0 | 0 | 40.46 | 11.03 | 5287.95
PH4100A | SC\43\016\D | SC | 43 | 16 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-09-29 09:30 | 2025-10-05 18:47 | 260119.665 | 260120 | [7 empty] | 0 | 0 | 21.36 | 7.35 | 5762.8
TS5500Shv | GG\25\004\X1 | GG | 25 | 4 | X1 | 1 Prestrip - Thick | 16.5631 | 16.5631 | 16.5631 | 2025-09-29 16:08 | 2025-10-05 20:44 | 159445.9647 | 159446 | [7 empty] | 0 | 0 | 15.42 | 11.02 | 5281.85
TS Fleet 5 | GG\25\004\X1 | GG | 25 | 4 | X1 | 1 Prestrip - Thick | 64.9027 | 64.9027 | 64.9027 | 2025-09-30 07:56 | 2025-10-14 04:58 | 624791.7082 | 624792 | [7 empty] | 0 | 0 | 60.41 | 11.02 | 5281.85
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2025-09-30 12:00 | 2025-10-03 12:00
TS6060#1 | GG\25\005\X1 | GG | 25 | 5 | X1 | 1 Prestrip - Thick | 100 | 47.5012 | 47.5012 | 2025-09-30 22:27 | 2025-10-19 02:50 | 445723.7376 | 445724 | [7 empty] | 0 | 0 | 42.25 | 11.03 | 5287.95
DRE2 | GG\22\004\B | GG | 22 | 4 | B | 6 DL | 100 | 0 | 100 | 2025-10-01 13:48 | 2025-10-08 16:30 | 574197.5619 |  |  |  |  | 574198 | 273427 |  |  | 0 | 20.49 | 0 | 9.34 | 5521.53
DRE1 | RS\53\002\D | RS | 53 | 2 | D | 6 DL | 100 | 100 | 100 | 2025-10-03 12:00 | 2025-10-08 13:24 | 424088.3995 |  |  |  | 21804 | 424088 | 341596 |  |  | 0 | 29.2 | 0 | 6.37 | 5861.44
PH4100A | SC\42\017\D | SC | 42 | 17 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-10-05 18:47 | 2025-10-14 22:48 | 371236.9287 | 371237 | [7 empty] | 0 | 0 | 25.66 | 7.2 | 5772.1
TS5500Shv | RS\52\005\D | RS | 52 | 5 | D | 7 PostStrip | 54.7945 | 0 | 54.7945 | 2025-10-05 20:44 | 2025-10-06 07:35 | 11640.1073 |  |  | 11640 | [5 empty] | 0 | 0 | 0 | 6.07 | 5886.61
TS5500Shv | GG\22\009\B | GG | 22 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-10-06 07:35 | 2025-10-08 01:42 | 51349.2969 | [6 empty] | 51349 | 37628 | 3.76 | 0 | 0 | 10.03 | 5520
TS5500Shv | GG\22\008\B | GG | 22 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-10-08 01:42 | 2025-10-09 20:25 | 52084.2131 | [6 empty] | 52084 | 38117 | 3.81 | 0 | 0 | 10.17 | 5494
DRE1 | RS\53\003\D | RS | 53 | 3 | D | 6 DL | 100 | 100 | 100 | 2025-10-08 13:24 | 2025-10-12 13:58 | 337306.2691 |  |  |  | 17342 | 337306 | 271695 |  |  | 0 | 28.9 | 0 | 5.89 | 5902.16
DRE2 | GG\21\013\D | GG | 21 | 13 | D | 6 DL | 100 | 100 | 100 | 2025-10-08 16:30 | 2025-10-14 23:58 | 509470.8513 |  |  |  | 11862 | 509471 | 225377 |  |  | 0 | 23.75 | 0 | 7.04 | 5769.15
TS5500Shv | RS\53\002\D | RS | 53 | 2 | D | 8 Coal Mining | 7.8 | 0 | 7.8 | 2025-10-09 20:25 | 2025-10-10 01:21 | 6024.8347 | [6 empty] | 6025 | 4431 | 0.36 | 0 | 0 | 6.37 | 5861
TS5500Shv | GG\22\007\B | GG | 22 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-10-10 01:21 | 2025-10-11 19:21 | 51214.4299 | [6 empty] | 51214 | 37465 | 3.75 | 0 | 0 | 10.34 | 5460
TS5500Shv | GG\25\005\X1 | GG | 25 | 5 | X1 | 1 Prestrip - Thick | 0.72453 | 0.72453 | 0.72453 | 2025-10-11 19:21 | 2025-10-12 01:43 | 6798.5809 | 6799 | [7 empty] | 0 | 0 | 0.64 | 11.03 | 5287.95
TS5500Shv | GG\22\006\B | GG | 22 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-10-12 01:43 | 2025-10-13 18:11 | 49339.7475 | [6 empty] | 49340 | 36172 | 3.62 | 0 | 0 | 10.05 | 5465
DRE1 | RS\53\004\D | RS | 53 | 4 | D | 6 DL | 100 | 100 | 100 | 2025-10-12 13:58 | 2025-10-16 13:28 | 333611.726 |  |  |  | 17152 | 333612 | 268719 |  |  | 0 | 28.59 | 0 | 5.97 | 5895.51
TS5500Shv | RS\54\002\B | RS | 54 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-10-13 18:11 | 2025-10-14 18:37 | 29795.3348 | [6 empty] | 29795 | 21175 | 1.36 | 0 | 0 | 10.65 | 5457
TS Fleet 5 | GG\25\005\X1 | GG | 25 | 5 | X1 | 1 Prestrip - Thick | 6.2858 | 6.2858 | 6.2858 | 2025-10-14 04:58 | 2025-10-15 12:25 | 58982.4003 | 58982 | [7 empty] | 0 | 0 | 5.59 | 11.03 | 5287.95
TS5500Shv | GG\22\005\B | GG | 22 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-10-14 18:37 | 2025-10-16 08:56 | 46720.8136 | [6 empty] | 46721 | 34426 | 3.44 | 0 | 0 | 9.27 | 5514
PH4100A | SC\43\017\D | SC | 43 | 17 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-10-14 22:48 | 2025-10-25 09:21 | 429939.9213 | 429940 | [7 empty] | 0 | 0 | 29.95 | 7.24 | 5766.95
DRE2 | GG\21\012\D | GG | 21 | 12 | D | 6 DL | 100 | 100 | 100 | 2025-10-14 23:58 | 2025-10-21 05:44 | 503764.9749 |  |  |  | 11729 | 503765 | 222853 |  |  | 0 | 23.48 | 0 | 6.78 | 5791.13
TS Fleet 5 | GG\25\006\X1 | GG | 25 | 6 | X1 | 1 Prestrip - Thick | 43.4986 | 43.4986 | 43.4986 | 2025-10-15 12:25 | 2025-10-24 10:26 | 401508.9613 | 401509 | [7 empty] | 0 | 0 | 39.75 | 11.54 | 5272.44
TS5500Shv | GG\22\004\B | GG | 22 | 4 | B | 8 Coal Mining | 71.5 | 0 | 71.5 | 2025-10-16 08:56 | 2025-10-18 01:25 | 49377.8503 | [6 empty] | 49378 | 36352 | 2.84 | 0 | 0 | 9.34 | 5522
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2025-10-16 13:28 | 2025-10-19 13:28
TS5500Shv | RS\53\004\D | RS | 53 | 4 | D | 8 Coal Mining | 9 | 0 | 9 | 2025-10-18 01:25 | 2025-10-18 05:48 | 5342.8229 | [6 empty] | 5343 | 3926 | 0.39 | 0 | 0 | 5.97 | 5896
TS5500Shv | GG\21\013\D | GG | 21 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-10-18 05:48 | 2025-10-20 09:41 | 63263.7343 | [6 empty] | 63264 | 47146 | 4.71 | 0 | 0 | 7.04 | 5769
TS6060#1 | RS\53\004\D | RS | 53 | 4 | D | 8 Coal Mining | 100 | 0 | 47.1 | 2025-10-19 02:50 | 2025-10-19 23:31 | 27989.5404 | [6 empty] | 27990 | 20566 | 2.06 | 0 | 0 | 5.97 | 5896
TS5500Exc | RS\53\004\D | RS | 53 | 4 | D | 8 Coal Mining | 100 | 0 | 43.9 | 2025-10-19 02:50 | 2025-10-19 23:31 | 26049.6712 | [6 empty] | 26050 | 19141 | 1.91 | 0 | 0 | 5.97 | 5896
DRE1 | RS\54\002\D | RS | 54 | 2 | D | 6 DL | 100 | 100 | 100 | 2025-10-19 13:28 | 2025-10-25 11:36 | 496496.861 |  |  |  | 25527 | 496497 | 399920 |  |  | 0 | 29.04 | 0 | 6.62 | 5842.27
TS6060#1 | GG\25\004\X1 | GG | 25 | 4 | X1 | 1 Prestrip - Thick | 100 | 9.8991 | 9.8991 | 2025-10-19 23:31 | 2025-10-23 21:28 | 95294.3983 | 95294 | [7 empty] | 0 | 0 | 9.21 | 11.02 | 5281.85
TS5500Exc | GG\25\004\X1 | GG | 25 | 4 | X1 | 1 Prestrip - Thick | 100 | 8.6352 | 8.6352 | 2025-10-19 23:31 | 2025-10-23 21:28 | 83127.5835 | 83128 | [7 empty] | 0 | 0 | 8.04 | 11.02 | 5281.85
TS5500Shv | GG\25\005\X1 | GG | 25 | 5 | X1 | 8 Coal Mining | 78 | 0 | 78 | 2025-10-20 09:41 | 2025-10-20 19:33 | 12021.2108 | [6 empty] | 12021 | 8906 | 0.87 | 0 | 0 | 11.03 | 5288
TS5500Shv | RS\54\003\D | RS | 54 | 3 | D | 8 Coal Mining | 41.4 | 0 | 41.4 | 2025-10-20 19:33 | 2025-10-21 15:24 | 24216.0989 | [6 empty] | 24216 | 17807 | 1.78 | 0 | 0 | 5.93 | 5899
DRE2 | GG\21\011\D | GG | 21 | 11 | D | 6 DL | 100 | 100 | 100 | 2025-10-21 05:44 | 2025-10-27 11:50 | 504899.9885 |  |  |  | 9160 | 504900 | 219844 |  |  | 0 | 22.92 | 0 | 6.58 | 5807.42
TS5500Shv | GG\21\012\D | GG | 21 | 12 | D | 8 Coal Mining | 91.9 | 0 | 91.9 | 2025-10-21 15:24 | 2025-10-23 14:01 | 56847.5424 | [6 empty] | 56848 | 42464 | 4.25 | 0 | 0 | 6.78 | 5791
TS5500Shv | RS\54\004\A | RS | 54 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-10-23 14:01 | 2025-10-24 08:18 | 22281.504 | [6 empty] | 22282 | 15519 | 1.56 | 0 | 0 | 14.89 | 5151
TS6060#1 | RS\53\005\B | RS | 53 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-10-23 21:28 | 2025-10-24 13:14 | 16255.0139 | 16255 | [7 empty] | 0 | 0 | 2.71 | 9.65 | 5525.06
TS5500Exc | RS\52\004\D | RS | 52 | 4 | D | 8 Coal Mining | 55.9 | 0 | 55.9 | 2025-10-23 21:28 | 2025-10-24 23:52 | 33247.317 | [6 empty] | 33247 | 24449 | 2.44 | 0 | 0 | 5.98 | 5895
TS5500Shv | GG\25\004\X1 | GG | 25 | 4 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-10-24 08:18 | 2025-10-24 18:04 | 11917.2965 | [6 empty] | 11917 | 8831 | 1.03 | 0 | 0 | 11.02 | 5282
TS Fleet 5 | GG\25\007\X1 | GG | 25 | 7 | X1 | 1 Prestrip - Thick | 41.5181 | 41.5181 | 41.5181 | 2025-10-24 10:26 | 2025-11-01 14:17 | 367412.559 | 367413 | [7 empty] | 0 | 0 | 35.41 | 12.38 | 5241.28
TS6060#1 | GG\25\005\X1 | GG | 25 | 5 | X1 | 8 Coal Mining | 22 | 0 | 22 | 2025-10-24 13:14 | 2025-10-24 15:44 | 3385.5982 | [6 empty] | 3386 | 2508 | 0.24 | 0 | 0 | 11.03 | 5288
TS6060#1 | GG\22\004\B | GG | 22 | 4 | B | 8 Coal Mining | 28.5 | 0 | 28.5 | 2025-10-24 15:44 | 2025-10-25 06:16 | 19679.9584 | [6 empty] | 19680 | 14488 | 1.13 | 0 | 0 | 9.34 | 5522
TS5500Shv | RS\53\005\B | RS | 53 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2025-10-24 18:04 | 2025-10-25 02:52 | 10733.1928 | [6 empty] | 10733 | 7593 | 1.27 | 0 | 0 | 9.65 | 5525
TS5500Exc | RS\52\005\D | RS | 52 | 5 | D | 7 PostStrip | 45.2055 | 0 | 45.2055 | 2025-10-24 23:52 | 2025-10-25 10:44 | 9603.0885 |  |  | 9603 | [5 empty] | 0 | 0 | 0 | 6.07 | 5886.61
TS5500Shv | GG\25\004\B | GG | 25 | 4 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-10-25 02:52 | 2025-10-27 16:21 | 65914.4781 | 65914 | [7 empty] | 0 | 0 | 8.56 | 9.87 | 5491.43
TS6060#1 | GG\21\012\D | GG | 21 | 12 | D | 8 Coal Mining | 8.1 | 0 | 8.1 | 2025-10-25 06:16 | 2025-10-25 09:59 | 5016.6468 | [6 empty] | 5017 | 3747 | 0.37 | 0 | 0 | 6.78 | 5791
PH4100A | SC\47\018\D | SC | 47 | 18 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-10-25 09:21 | 2025-11-09 21:51 | 622200.1221 | 622200 | [7 empty] | 0 | 0 | 27.7 | 7.15 | 5782.1
TS6060#1 | RS\54\004\B | RS | 54 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-10-25 09:59 | 2025-10-26 09:30 | 24267.7821 | 24268 | [7 empty] | 0 | 0 | 2.44 | 9.34 | 5548.78
TS5500Exc | RS\52\005\D | RS | 52 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-10-25 10:44 | 2025-10-26 06:15 | 24591.6347 | [6 empty] | 24592 | 18069 | 4.35 | 0 | 0 | 6.07 | 5887
DRE1 | RS\55\001\D | RS | 55 | 1 | D | 6 DL | 100 | 0 | 100 | 2025-10-25 11:36 | 2025-10-28 16:43 | 269356.0786 |  |  |  | 15373 | 269356 | 204241 |  |  | 0 | 30 | 0 | 7.47 | 5759.32
TS5500Exc | RS\53\002\D | RS | 53 | 2 | D | 8 Coal Mining | 92.2 | 0 | 92.2 | 2025-10-26 06:15 | 2025-10-28 15:04 | 71575.7609 | [6 empty] | 71576 | 52644 | 4.22 | 0 | 0 | 6.37 | 5861
TS6060#1 | RS\55\002\D | RS | 55 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-10-26 09:30 | 2025-11-03 06:49 | 192928.4168 | 192928 | [7 empty] | 0 | 0 | 19.67 | 6.49 | 5850.4
DRE2 | GG\21\010\D | GG | 21 | 10 | D | 6 DL | 100 | 100 | 100 | 2025-10-27 11:50 | 2025-11-02 03:30 | 456371.5904 |  |  |  | 10626 | 456372 | 201887 |  |  | 0 | 21.25 | 0 | 6.49 | 5815.03
TS5500Shv | GG\25\005\B | GG | 25 | 5 | B | 1 Prestrip - Thick | 59.038 | 59.038 | 59.038 | 2025-10-27 16:21 | 2025-10-31 00:32 | 85952.4933 | 85952 | [7 empty] | 0 | 0 | 8.57 | 10.21 | 5462.49
TS5500Exc | RS\53\005\B | RS | 53 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2025-10-28 15:04 | 2025-10-28 23:53 | 11087.0343 | [6 empty] | 11087 | 7844 | 1.32 | 0 | 0 | 9.65 | 5525
DRE1 | RS\56\003\D | RS | 56 | 3 | D | 6 DL | 100 | 100 | 100 | 2025-10-28 16:43 | 2025-11-01 13:45 | 324968.5093 |  |  |  | 16708 | 324969 | 261757 |  |  | 0 | 28.16 | 0 | 5.98 | 5893.95
TS5500Exc | GG\25\004\B | GG | 25 | 4 | B | 1 Prestrip - Thick | 45.2055 | 22.4748 | 22.4748 | 2025-10-28 23:53 | 2025-10-30 06:27 | 27035.806 | 27036 | [7 empty] | 0 | 0 | 3.51 | 9.87 | 5491.43
PH4100XPC#1 | GG\25\004\B | GG | 25 | 4 | B | 1 Prestrip - Thick | 100 | 22.7307 | 22.7307 | 2025-10-29 18:22 | 2025-10-30 06:27 | 27343.6385 | 27344 | [7 empty] | 0 | 0 | 3.55 | 9.87 | 5491.43
TS5500Exc | RS\53\003\D | RS | 53 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-10-30 06:27 | 2025-11-01 04:38 | 58183.8411 | [6 empty] | 58184 | 42851 | 4.29 | 0 | 0 | 5.89 | 5902
PH4100XPC#1 | GG\25\005\B | GG | 25 | 5 | B | 1 Prestrip - Thick | 100 | 40.962 | 40.962 | 2025-10-30 06:27 | 2025-10-31 08:47 | 59636.0291 | 59636 | [7 empty] | 0 | 0 | 5.95 | 10.21 | 5462.49
TS5500Shv | RS\54\002\D | RS | 54 | 2 | D | 8 Coal Mining | 85.5 | 0 | 85.5 | 2025-10-31 00:32 | 2025-11-02 16:32 | 78038.3816 | [6 empty] | 78038 | 57202 | 3.89 | 0 | 0 | 6.62 | 5842
PH4100XPC#1 | GG\25\006\X1 | GG | 25 | 6 | X1 | 1 Prestrip - Thick | 100 | 41.8528 | 41.8528 | 2025-10-31 08:47 | 2025-11-07 13:23 | 386316.8861 | 386317 | [7 empty] | 0 | 0 | 38.25 | 11.54 | 5272.44
TS5500Exc | GG\25\006\X1 | GG | 25 | 6 | X1 | 1 Prestrip - Thick | 15.3037 | 14.6486 | 14.6486 | 2025-11-01 04:38 | 2025-11-07 13:23 | 135212.239 | 135212 | [7 empty] | 0 | 0 | 13.39 | 11.54 | 5272.44
DRE1 | RS\53\005\D | RS | 53 | 5 | D | 6 DL | 100 | 100 | 100 | 2025-11-01 13:45 | 2025-11-03 18:57 | 185838.8555 |  |  |  | 7621 | 185839 | 98270 |  |  | 0 | 30.06 | 0 | 6.06 | 5887.4
TS Fleet 5 | GG\25\008\X1 | GG | 25 | 8 | X1 | 1 Prestrip - Thick | 39.1608 | 39.1608 | 39.1608 | 2025-11-01 14:17 | 2025-11-08 16:43 | 319729.3064 | 319729 | [7 empty] | 0 | 0 | 34.61 | 13.38 | 5191.97
DRE2 | GG\21\009\D | GG | 21 | 9 | D | 6 DL | 100 | 100 | 100 | 2025-11-02 03:30 | 2025-11-07 13:54 | 438620.8979 |  |  |  | 10212 | 438621 | 194035 |  |  | 0 | 20.43 | 0 | 6.49 | 5816.01
TS5500Shv | RS\56\003\D | RS | 56 | 3 | D | 8 Coal Mining | 20.2 | 0 | 20.2 | 2025-11-02 16:32 | 2025-11-03 02:13 | 11807.4414 | [6 empty] | 11807 | 8655 | 0.87 | 0 | 0 | 5.98 | 5894
TS5500Shv | GG\21\011\D | GG | 21 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-11-03 02:13 | 2025-11-05 03:38 | 60267.2621 | [6 empty] | 60267 | 45090 | 4.51 | 0 | 0 | 6.58 | 5807
TS6060#1 | W2\01\007\B | W2 | 1 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-11-03 06:49 | 2025-11-08 17:03 | 176257.8902 | [6 empty] | 176258 | 123828 | 3.28 | 0 | 0 | 9.87 | 5314
DRE1 | RS\55\002\D | RS | 55 | 2 | D | 6 DL | 100 | 0 | 100 | 2025-11-03 18:57 | 2025-11-08 03:52 | 366516.75 |  |  |  | 20918 | 366517 | 277913 |  |  | 0 | 30 | 0 | 6.49 | 5850.4
TS5500Shv | RS\53\005\D | RS | 53 | 5 | D | 7 PostStrip | 54.7945 | 0 | 54.7945 | 2025-11-05 03:38 | 2025-11-05 14:26 | 11576.7884 |  |  | 11577 | [5 empty] | 0 | 0 | 0 | 6.06 | 5887.4
TS5500Shv | GG\25\009\X2 | GG | 25 | 9 | X2 | 1 Prestrip - Thick | 1.7862 | 0 | 1.7862 | 2025-11-05 14:26 | 2025-11-06 05:27 | 16006.8317 | 16007 | [7 empty] | 0 | 0 | 1.57 | 0 | 0
TS5500Shv | GG\25\010\X1 | GG | 25 | 10 | X1 | 1 Prestrip - Thick | 17.9713 | 17.9713 | 17.9713 | 2025-11-06 05:27 | 2025-11-11 06:40 | 129228.7862 | 129229 | [7 empty] | 0 | 0 | 15.24 | 14.62 | 5127.55
PH4100XPC#1 | GG\25\007\X1 | GG | 25 | 7 | X1 | 1 Prestrip - Thick | 100 | 49.082 | 49.082 | 2025-11-07 13:23 | 2025-11-15 16:27 | 434348.8848 | 434349 | [7 empty] | 0 | 0 | 41.86 | 12.38 | 5241.28
TS5500Exc | RS\53\005\D | RS | 53 | 5 | D | 7 PostStrip | 45.2055 | 0 | 45.2055 | 2025-11-07 13:23 | 2025-11-08 00:11 | 9550.8505 |  |  | 9551 | [5 empty] | 0 | 0 | 0 | 6.06 | 5887.4
DRE2 | GG\21\008\D | GG | 21 | 8 | D | 6 DL | 100 | 100 | 100 | 2025-11-07 13:54 | 2025-11-12 21:17 | 428468.7835 |  |  |  | 7979 | 428469 | 191494 |  |  | 0 | 19.95 | 0 | 6.54 | 5811.76
TS5500Exc | RS\53\005\D | RS | 53 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-11-08 00:11 | 2025-11-08 19:28 | 24293.6742 | [6 empty] | 24294 | 17836 | 4.32 | 0 | 0 | 6.06 | 5887
DRE1 | SC\39\025\D | SC | 39 | 25 | D | 6 DL | 100 | 0 | 100 | 2025-11-08 03:52 | 2025-11-14 06:12 | 511121.8268 |  |  |  | 29171 | 511122 | 387561 |  |  | 0 | 34.77 | 0 | 7.2 | 5781.22
TS Fleet 5 | GG\25\009\X2 | GG | 25 | 9 | X2 | 1 Prestrip - Thick | 44.0319 | 0 | 44.0319 | 2025-11-08 16:43 | 2025-11-17 11:03 | 394593.9705 | 394594 | [7 empty] | 0 | 0 | 38.63 | 0 | 0
TS6060#1 | GG\21\010\D | GG | 21 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-11-08 17:03 | 2025-11-10 13:55 | 60722.0501 | [6 empty] | 60722 | 45466 | 4.55 | 0 | 0 | 6.49 | 5815
TS5500Exc | RS\56\003\D | RS | 56 | 3 | D | 8 Coal Mining | 79.8 | 0 | 79.8 | 2025-11-08 19:28 | 2025-11-10 08:27 | 46573.3832 | [6 empty] | 46573 | 34139 | 3.41 | 0 | 0 | 5.98 | 5894
PH4100A | SC\48\018\D | SC | 48 | 18 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-11-09 21:51 | 2025-11-14 23:12 | 198921.1409 | 198921 | [7 empty] | 0 | 0 | 16.9 | 7.17 | 5781.13
TS5500Exc | GG\25\007\X1 | GG | 25 | 7 | X1 | 1 Prestrip - Thick | 9.3999 | 9.3999 | 9.3999 | 2025-11-10 08:27 | 2025-11-14 06:24 | 83183.8367 | 83184 | [7 empty] | 0 | 0 | 8.02 | 12.38 | 5241.28
TS6060#1 | GG\21\009\D | GG | 21 | 9 | D | 8 Coal Mining | 10 | 0 | 10 | 2025-11-10 13:55 | 2025-11-10 18:29 | 6174.9663 | [6 empty] | 6175 | 4620 | 0.46 | 0 | 0 | 6.49 | 5816
TS6060#1 | RS\55\003\B | RS | 55 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-11-10 18:29 | 2025-11-21 04:30 | 245837.2114 | 245837 | [7 empty] | 0 | 0 | 25.28 | 9.46 | 5544.73
TS5500Shv | GG\25\006\X1 | GG | 25 | 6 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-11-11 06:40 | 2025-11-11 19:35 | 15744.2926 | [6 empty] | 15744 | 11605 | 1.16 | 0 | 0 | 11.54 | 5272
TS5500Shv | GG\25\006\B | GG | 25 | 6 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2025-11-11 19:35 | 2025-11-15 02:05 | 84163.7591 | 84164 | [7 empty] | 0 | 0 | 8.42 | 10.53 | 5441.61
DRE2 | GG\21\007\D | GG | 21 | 7 | D | 6 DL | 100 | 100 | 100 | 2025-11-12 21:17 | 2025-11-18 05:15 | 430452.5576 |  |  |  | 10022 | 430453 | 190421 |  |  | 0 | 20.05 | 0 | 6.59 | 5806.87
DRE1 | SC\39\026\D | SC | 39 | 26 | D | 6 DL | 100 | 0 | 100 | 2025-11-14 06:12 | 2025-11-20 09:26 | 514307.5861 |  |  |  | 21379 | 514308 | 272742 |  |  | 0 | 27.51 | 0 | 6.91 | 5806.8
TS5500Exc | GG\25\006\B | GG | 25 | 6 | B | 1 Prestrip - Thick | 45.2055 | 26.7955 | 26.7955 | 2025-11-14 06:24 | 2025-11-16 04:57 | 41157.6429 | 41158 | [7 empty] | 0 | 0 | 4.12 | 10.53 | 5441.61
PH4100A | SC\49\018\D | SC | 49 | 18 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-11-14 23:12 | 2025-11-20 06:38 | 209325.3957 | 209325 | [7 empty] | 0 | 0 | 17.35 | 7.22 | 5776.93
TS5500Shv | RS\54\004\B | RS | 54 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-11-15 02:05 | 2025-11-16 08:36 | 37207.7838 | [6 empty] | 37208 | 26364 | 2.65 | 0 | 0 | 9.34 | 5549
PH4100XPC#1 | GG\25\006\B | GG | 25 | 6 | B | 1 Prestrip - Thick | 100 | 18.4099 | 18.4099 | 2025-11-15 16:27 | 2025-11-16 04:57 | 28277.4584 | 28277 | [7 empty] | 0 | 0 | 2.83 | 10.53 | 5441.61
PH4100XPC#1 | GG\25\008\X1 | GG | 25 | 8 | X1 | 1 Prestrip - Thick | 100 | 46.8809 | 46.8809 | 2025-11-16 04:57 | 2025-11-23 06:41 | 382760.4619 | 382760 | [7 empty] | 0 | 0 | 41.44 | 13.38 | 5191.97
TS5500Exc | RS\54\002\D | RS | 54 | 2 | D | 8 Coal Mining | 14.5 | 0 | 14.5 | 2025-11-16 04:57 | 2025-11-16 15:29 | 13268.2807 | [6 empty] | 13268 | 9726 | 0.66 | 0 | 0 | 6.62 | 5842
TS5500Shv | GG\25\007\X1 | GG | 25 | 7 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-11-16 08:36 | 2025-11-16 22:19 | 16716.0609 | [6 empty] | 16716 | 12217 | 1.22 | 0 | 0 | 12.38 | 5241
TS5500Exc | GG\25\008\X1 | GG | 25 | 8 | X1 | 1 Prestrip - Thick | 13.9583 | 13.9583 | 13.9583 | 2025-11-16 15:29 | 2025-11-22 00:11 | 113962.9855 | 113963 | [7 empty] | 0 | 0 | 12.34 | 13.38 | 5191.97
TS5500Shv | GG\25\007\B | GG | 25 | 7 | B | 1 Prestrip - Thick | 73.093 | 73.093 | 73.093 | 2025-11-16 22:19 | 2025-11-21 05:47 | 110919.7556 | 110920 | [7 empty] | 0 | 0 | 11.09 | 10.47 | 5458.63
TS Fleet 5 | GG\25\007\B | GG | 25 | 7 | B | 1 Prestrip - Thick | 12.2209 | 12.2209 | 12.2209 | 2025-11-17 11:03 | 2025-11-17 20:57 | 18545.393 | 18545 | [7 empty] | 0 | 0 | 1.85 | 10.47 | 5458.63
TS Fleet 5 | GG\25\010\X1 | GG | 25 | 10 | X1 | 1 Prestrip - Thick | 31.7497 | 31.7497 | 31.7497 | 2025-11-17 20:57 | 2025-11-22 22:38 | 228306.6287 | 228307 | [7 empty] | 0 | 0 | 26.92 | 14.62 | 5127.55
DRE2 | GG\21\006\D | GG | 21 | 6 | D | 6 DL | 100 | 100 | 100 | 2025-11-18 05:15 | 2025-11-23 12:02 | 426495.4834 |  |  |  | 7942 | 426495 | 190613 |  |  | 0 | 19.85 | 0 | 6.65 | 5801.21
PH4100A | SC\47\019\D | SC | 47 | 19 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-11-20 06:38 | 2025-11-25 13:45 | 210221.0746 | 210221 | [7 empty] | 0 | 0 | 17.87 | 7.01 | 5795.54
DRE1 | RS\54\004\D | RS | 54 | 4 | D | 6 DL | 100 | 100 | 100 | 2025-11-20 09:26 | 2025-11-24 07:06 | 327223.9275 |  |  |  | 16824 | 327224 | 263574 |  |  | 0 | 28.05 | 0 | 5.96 | 5896.43
TS6060#1 | GG\21\007\D | GG | 21 | 7 | D | 8 Coal Mining | 46 | 0 | 46 | 2025-11-21 04:30 | 2025-11-22 01:18 | 28135.7681 | [6 empty] | 28136 | 21050 | 2.11 | 0 | 0 | 6.59 | 5807
TS5500Shv | RS\54\005\A | RS | 54 | 5 | A | 8 Coal Mining | 86 | 0 | 86 | 2025-11-21 05:47 | 2025-11-22 01:01 | 23461.8392 | [6 empty] | 23462 | 16367 | 2.7 | 0 | 0 | 14.54 | 5179
TS5500Exc | GG\25\010\X1 | GG | 25 | 10 | X1 | 1 Prestrip - Thick | 11.4038 | 11.4038 | 11.4038 | 2025-11-22 00:11 | 2025-11-25 20:49 | 82002.5099 | 82003 | [7 empty] | 0 | 0 | 9.67 | 14.62 | 5127.55
TS5500Shv | GG\21\009\D | GG | 21 | 9 | D | 8 Coal Mining | 90 | 0 | 90 | 2025-11-22 01:01 | 2025-11-23 22:27 | 55388.5456 | [6 empty] | 55389 | 41440 | 4.14 | 0 | 0 | 6.49 | 5816
TS6060#1 | RS\55\004\A | RS | 55 | 4 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-11-22 01:18 | 2025-12-02 18:49 | 253352.5634 | 253353 | [7 empty] | 0 | 0 | 26.03 | 14.98 | 5143.48
TS Fleet 5 | GG\25\011\X1 | GG | 25 | 11 | X1 | 1 Prestrip - Thick | 45.3701 | 45.3701 | 45.3701 | 2025-11-22 22:38 | 2025-11-29 07:38 | 287017.287 | 287017 | [7 empty] | 0 | 0 | 32.96 | 14.87 | 5112.28
PH4100XPC#1 | GG\25\007\B | GG | 25 | 7 | B | 1 Prestrip - Thick | 100 | 14.6861 | 14.6861 | 2025-11-23 06:41 | 2025-11-23 16:32 | 22286.4318 | 22286 | [7 empty] | 0 | 0 | 2.23 | 10.47 | 5458.63
DRE2 | GG\21\005\D | GG | 21 | 5 | D | 6 DL | 100 | 100 | 100 | 2025-11-23 12:02 | 2025-11-28 16:36 | 419020.4487 |  |  |  | 7803 | 419020 | 187272 |  |  | 0 | 19.5 | 0 | 6.69 | 5797.15
PH4100XPC#1 | GG\25\009\X2 | GG | 25 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.182 | 2025-11-23 16:32 | 2025-12-02 10:02 | 485554.7257 | 485555 | [7 empty] | 0 | 0 | 47.53 | 0 | 0
TS5500Shv | GG\25\008\X1 | GG | 25 | 8 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2025-11-23 22:27 | 2025-11-24 05:23 | 8456.6994 | [6 empty] | 8457 | 6120 | 0.61 | 0 | 0 | 13.38 | 5192
TS5500Shv | GG\21\008\D | GG | 21 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-11-24 05:23 | 2025-11-26 07:55 | 61629.8296 | [6 empty] | 61630 | 46073 | 4.61 | 0 | 0 | 6.54 | 5812
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2025-11-24 07:06 | 2025-11-27 07:06
PH4100A | SC\48\019\D | SC | 48 | 19 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-11-25 13:45 | 2025-11-30 23:05 | 213670.7107 | 213671 | [7 empty] | 0 | 0 | 18.18 | 7.09 | 5788.58
TS5500Exc | RS\54\004\D | RS | 54 | 4 | D | 8 Coal Mining | 100 | 0 | 76.3 | 2025-11-25 20:49 | 2025-11-27 08:45 | 45270.5638 | [6 empty] | 45271 | 33212 | 3.32 | 0 | 0 | 5.96 | 5896
TS5500Shv | RS\54\004\D | RS | 54 | 4 | D | 8 Coal Mining | 23.7 | 0 | 23.7 | 2025-11-26 07:55 | 2025-11-26 19:25 | 14025.797 | [6 empty] | 14026 | 10290 | 1.03 | 0 | 0 | 5.96 | 5896
TS5500Shv | GG\21\007\D | GG | 21 | 7 | D | 8 Coal Mining | 54 | 0 | 54 | 2025-11-26 19:25 | 2025-11-27 22:32 | 33059.3416 | [6 empty] | 33059 | 24734 | 2.47 | 0 | 0 | 6.59 | 5807
DRE1 | SC\40\016\D | SC | 40 | 16 | D | 6 DL | 100 | 0 | 100 | 2025-11-27 07:06 | 2025-12-05 18:23 | 710095.9382 |  |  |  | 46803 | 710096 | 473226 |  |  | 0 | 38.8 | 0 | 7.13 | 5780.78
TS5500Exc | RS\54\005\A | RS | 54 | 5 | A | 8 Coal Mining | 14 | 0 | 14 | 2025-11-27 08:45 | 2025-11-27 11:47 | 3825.0034 | [6 empty] | 3825 | 2668 | 0.44 | 0 | 0 | 14.54 | 5179
TS5500Exc | SC\39\025\D | SC | 39 | 25 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-11-27 11:47 | 2025-11-30 00:59 | 77071.6941 | [6 empty] | 77072 | 57603 | 4.8 | 0 | 0 | 7.2 | 5781
TS5500Shv | GG\25\013\X1 | GG | 25 | 13 | X1 | 1 Prestrip - Thick | 17.5148 | 17.5148 | 17.5148 | 2025-11-27 22:32 | 2025-11-30 17:39 | 70665.8373 | 70666 | [7 empty] | 0 | 0 | 7.13 | 14.79 | 5115.81
DRE2 | GG\21\004\D | GG | 21 | 4 | D | 6 DL | 100 | 100 | 100 | 2025-11-28 16:36 | 2025-12-05 15:45 | 562210.8991 |  |  |  | 9210 | 562211 | 161748 |  |  | 0 | 19.42 | 0 | 6.64 | 5801.93
TS Fleet 5 | GG\25\012\X1 | GG | 25 | 12 | X1 | 1 Prestrip - Thick | 45.8749 | 45.8749 | 45.8749 | 2025-11-29 07:38 | 2025-12-04 10:36 | 230691.5583 | 230692 | [7 empty] | 0 | 0 | 23.9 | 14.95 | 5104.34
TS5500Exc | GG\25\013\X1 | GG | 25 | 13 | X1 | 1 Prestrip - Thick | 14.745 | 14.745 | 14.745 | 2025-11-30 00:59 | 2025-12-02 20:06 | 59490.5361 | 59491 | [7 empty] | 0 | 0 | 6 | 14.79 | 5115.81
TS5500Shv | GG\21\006\D | GG | 21 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-11-30 17:39 | 2025-12-02 19:25 | 60684.8414 | [6 empty] | 60685 | 45439 | 4.54 | 0 | 0 | 6.65 | 5801
PH4100A | SC\49\019\D | SC | 49 | 19 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-11-30 23:05 | 2025-12-06 11:36 | 218809.402 | 218809 | [7 empty] | 0 | 0 | 18.61 | 7.15 | 5783.1
PH4100XPC#1 | GG\25\009\B | GG | 25 | 9 | B | 1 Prestrip - Thick | 100 | 79.46 | 79.46 | 2025-12-02 10:02 | 2025-12-03 14:42 | 64888.3839 | 64888 | [7 empty] | 0 | 0 | 6.49 | 10.2 | 5509.92
TS6060#1 | GG\25\008\X1 | GG | 25 | 8 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-12-02 18:49 | 2025-12-03 01:45 | 9386.0071 | [6 empty] | 9386 | 6792 | 0.68 | 0 | 0 | 13.38 | 5192
TS5500Shv | GG\25\009\B | GG | 25 | 9 | B | 1 Prestrip - Thick | 20.54 | 20.54 | 20.54 | 2025-12-02 19:25 | 2025-12-03 11:04 | 16773.3248 | 16773 | [7 empty] | 0 | 0 | 1.68 | 10.2 | 5509.92
TS5500Exc | RS\55\001\D | RS | 55 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-12-02 20:06 | 2025-12-04 06:39 | 43529.7749 | [6 empty] | 43530 | 31588 | 4.58 | 0 | 0 | 7.47 | 5759
TS6060#1 | RS\54\005\B | RS | 54 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-12-03 01:45 | 2025-12-03 17:18 | 16049.8033 | 16050 | [7 empty] | 0 | 0 | 2.66 | 10.02 | 5490.51
TS5500Shv | GG\25\008\X2 | GG | 25 | 8 | X2 | 1 Prestrip - Thick | 54.7945 | 0 | 33.5772 | 2025-12-03 11:04 | 2025-12-04 11:04 | 25734.8865 | 25735 | [7 empty] | 0 | 0 | 2.57 | 0 | 0
PH4100XPC#1 | GG\25\008\X2 | GG | 25 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 60.1782 | 2025-12-03 14:42 | 2025-12-04 11:04 | 46122.9767 | 46123 | [7 empty] | 0 | 0 | 4.61 | 0 | 0
TS6060#1 | GG\21\005\D | GG | 21 | 5 | D | 8 Coal Mining | 37.5 | 0 | 37.5 | 2025-12-03 17:18 | 2025-12-04 09:59 | 22582.4111 | [6 empty] | 22582 | 16922 | 1.69 | 0 | 0 | 6.69 | 5797
TS5500Exc | GG\25\008\X2 | GG | 25 | 8 | X2 | 1 Prestrip - Thick | 45.2055 | 0 | 5.0969 | 2025-12-04 06:39 | 2025-12-04 11:04 | 3906.4693 | 3906 | [7 empty] | 0 | 0 | 0.39 | 0 | 0
TS6060#1 | RS\55\005\A | RS | 55 | 5 | A | 1 Prestrip - Thick | 25.8987 | 25.8987 | 25.8987 | 2025-12-04 09:59 | 2025-12-06 19:50 | 57398.9973 | 57399 | [7 empty] | 0 | 0 | 8.08 | 14.53 | 5180.28
TS Fleet 5 | GG\25\008\X2 | GG | 25 | 8 | X2 | 1 Prestrip - Thick | 2.4104 | 0 | 1.1477 | 2025-12-04 10:36 | 2025-12-04 11:04 | 879.6735 | 880 | [7 empty] | 0 | 0 | 0.09 | 0 | 0
TS Fleet 5 | GG\25\008\B | GG | 25 | 8 | B | 1 Prestrip - Thick | 34.0061 | 30.7747 | 30.7747 | 2025-12-04 11:04 | 2025-12-04 22:48 | 21995.0647 | 21995 | [7 empty] | 0 | 0 | 2.2 | 10.3 | 5487.28
PH4100XPC#1 | GG\25\008\B | GG | 25 | 8 | B | 1 Prestrip - Thick | 100 | 37.1317 | 37.1317 | 2025-12-04 11:04 | 2025-12-04 22:48 | 26538.5229 | 26539 | [7 empty] | 0 | 0 | 2.65 | 10.3 | 5487.28
TS5500Exc | GG\25\008\B | GG | 25 | 8 | B | 1 Prestrip - Thick | 78.7166 | 14.5081 | 14.5081 | 2025-12-04 11:04 | 2025-12-04 22:48 | 10369.1019 | 10369 | [7 empty] | 0 | 0 | 1.04 | 10.3 | 5487.28
TS5500Shv | GG\25\008\B | GG | 25 | 8 | B | 1 Prestrip - Thick | 21.2834 | 17.5855 | 17.5855 | 2025-12-04 11:04 | 2025-12-04 22:48 | 12568.6084 | 12569 | [7 empty] | 0 | 0 | 1.26 | 10.3 | 5487.28
TS Fleet 5 | GG\25\013\X1 | GG | 25 | 13 | X1 | 1 Prestrip - Thick | 31.3353 | 31.3353 | 31.3353 | 2025-12-04 22:48 | 2025-12-07 18:11 | 126426.3281 | 126426 | [7 empty] | 0 | 0 | 12.76 | 14.79 | 5115.81
PH4100XPC#1 | GG\25\010\X1 | GG | 25 | 10 | X1 | 1 Prestrip - Thick | 100 | 38.8752 | 38.8752 | 2025-12-04 22:48 | 2025-12-10 00:01 | 279544.8444 | 279545 | [7 empty] | 0 | 0 | 32.97 | 14.62 | 5127.55
TS5500Exc | RS\54\005\B | RS | 54 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2025-12-04 22:48 | 2025-12-05 16:35 | 22405.5569 | [6 empty] | 22406 | 15809 | 2.64 | 0 | 0 | 10.02 | 5491
TS5500Shv | RS\55\002\D | RS | 55 | 2 | D | 8 Coal Mining | 65.2 | 0 | 65.2 | 2025-12-04 22:48 | 2025-12-06 07:17 | 39619.3587 | [6 empty] | 39619 | 29001 | 2.9 | 0 | 0 | 6.49 | 5850
DRE2 | GG\22\018\B | GG | 22 | 18 | B | 6 DL | 100 | 0 | 100 | 2025-12-05 15:45 | 2025-12-08 03:33 | 201188.2889 |  |  |  |  | 201188 | 167657 |  |  | 0 | 16.59 | 0 | 12.54 | 5305.06
TS5500Exc | GG\25\017\X1 | GG | 25 | 17 | X1 | 1 Prestrip - Thick | 17.8994 | 17.8994 | 17.8994 | 2025-12-05 16:35 | 2025-12-07 06:53 | 33995.403 | 33995 | [7 empty] | 0 | 0 | 4.26 | 14.34 | 5149.75
DRE1 | RS\54\005\D | RS | 54 | 5 | D | 6 DL | 100 | 100 | 100 | 2025-12-05 18:23 | 2025-12-07 21:15 | 177647.433 |  |  |  | 6379 | 177647 | 99892 |  |  | 0 | 29.93 | 0 | 6.05 | 5888.07
TS5500Shv | GG\21\005\D | GG | 21 | 5 | D | 8 Coal Mining | 62.5 | 0 | 62.5 | 2025-12-06 07:17 | 2025-12-07 14:06 | 37573.8315 | [6 empty] | 37574 | 28156 | 2.82 | 0 | 0 | 6.69 | 5797
PH4100A | SC\47\020\D | SC | 47 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-12-06 11:36 | 2025-12-10 21:41 | 173680.6047 | 173681 | [7 empty] | 0 | 0 | 14.83 | 7.08 | 5789.24
TS6060#1 | RS\56\001\D | RS | 56 | 1 | D | 1 Prestrip - Thick | 21.1559 | 21.1559 | 21.1559 | 2025-12-06 19:50 | 2025-12-07 13:41 | 18383.1947 | 18383 | [7 empty] | 0 | 0 | 2.16 | 7.68 | 5744.79
TS5500Exc | RS\55\002\D | RS | 55 | 2 | D | 8 Coal Mining | 34.8 | 0 | 34.8 | 2025-12-07 06:53 | 2025-12-07 23:40 | 21152.4885 | [6 empty] | 21152 | 15483 | 1.55 | 0 | 0 | 6.49 | 5850
TS6060#1 | RS\56\002\D | RS | 56 | 2 | D | 1 Prestrip - Thick | 21.0263 | 21.0263 | 21.0263 | 2025-12-07 13:41 | 2025-12-09 02:10 | 37148.7795 | 37149 | [7 empty] | 0 | 0 | 3.8 | 6.58 | 5841.95
TS5500Shv | RS\55\003\B | RS | 55 | 3 | B | 8 Coal Mining | 24.9 | 0 | 24.9 | 2025-12-07 14:06 | 2025-12-07 20:44 | 8095.5331 | [6 empty] | 8096 | 5751 | 0.58 | 0 | 0 | 9.46 | 5545
TS Fleet 5 | GG\25\014\X1 | GG | 25 | 14 | X1 | 1 Prestrip - Thick | 46.6754 | 46.6754 | 46.6754 | 2025-12-07 18:11 | 2025-12-10 10:42 | 121011.0395 | 121011 | [7 empty] | 0 | 0 | 14.98 | 14.67 | 5124.58
TS5500Shv | GG\25\018\X2 | GG | 25 | 18 | X2 | 1 Prestrip - Thick | 17.5021 | 0 | 17.5021 | 2025-12-07 20:44 | 2025-12-09 08:03 | 36993.3555 | 36993 | [7 empty] | 0 | 0 | 3.81 | 0 | 0
DRE1 | SC\40\015\D | SC | 40 | 15 | D | 6 DL | 100 | 0 | 100 | 2025-12-07 21:15 | 2025-12-17 11:01 | 802632.8092 |  |  |  | 57082 | 802633 | 577160 |  |  | 0 | 36.97 | 0 | 7.38 | 5759.35
TS5500Exc | RS\54\005\D | RS | 54 | 5 | D | 7 PostStrip | 45.2055 | 0 | 45.2055 | 2025-12-07 23:40 | 2025-12-08 10:34 | 9636.8837 |  |  | 9637 | [5 empty] | 0 | 0 | 0 | 6.05 | 5888.07
DRE2 | GG\22\019\B | GG | 22 | 19 | B | 6 DL | 100 | 0 | 100 | 2025-12-08 03:33 | 2025-12-10 17:19 | 207729.4669 |  |  |  |  | 207729 | 173108 |  |  | 0 | 17.3 | 0 | 12.95 | 5293.55
TS5500Exc | RS\55\003\B | RS | 55 | 3 | B | 8 Coal Mining | 75.1 | 0 | 75.1 | 2025-12-08 10:34 | 2025-12-09 06:00 | 24472.7173 | [6 empty] | 24473 | 17384 | 1.75 | 0 | 0 | 9.46 | 5545
TS6060#1 | RS\56\004\A | RS | 56 | 4 | A | 1 Prestrip - Thick | 20.5971 | 20.5971 | 20.5971 | 2025-12-09 02:10 | 2025-12-11 04:41 | 49590.4982 | 49590 | [7 empty] | 0 | 0 | 5.09 | 15.09 | 5134.64
TS5500Exc | GG\25\018\X2 | GG | 25 | 18 | X2 | 1 Prestrip - Thick | 14.8147 | 0 | 14.8147 | 2025-12-09 06:00 | 2025-12-10 17:18 | 31313.2216 | 31313 | [7 empty] | 0 | 0 | 3.22 | 0 | 0
TS5500Shv | RS\54\005\D | RS | 54 | 5 | D | 7 PostStrip | 54.7945 | 0 | 54.7945 | 2025-12-09 08:03 | 2025-12-09 18:57 | 11681.0712 |  |  | 11681 | [5 empty] | 0 | 0 | 0 | 6.05 | 5888.07
TS5500Shv | GG\25\019\B | GG | 25 | 19 | B | 1 Prestrip - Thick | 20.5411 | 20.5411 | 20.5411 | 2025-12-09 18:57 | 2025-12-12 01:24 | 58128.2926 | 58128 | [7 empty] | 0 | 0 | 5.89 | 14.66 | 5155.33
PH4100XPC#1 | GG\25\011\X1 | GG | 25 | 11 | X1 | 1 Prestrip - Thick | 100 | 54.6299 | 54.6299 | 2025-12-10 00:01 | 2025-12-16 08:23 | 345596.1106 | 345596 | [7 empty] | 0 | 0 | 39.69 | 14.87 | 5112.28
TS Fleet 5 | GG\25\017\X1 | GG | 25 | 17 | X1 | 1 Prestrip - Thick | 38.5399 | 38.5399 | 38.5399 | 2025-12-10 10:42 | 2025-12-12 01:43 | 73197.0418 | 73197 | [7 empty] | 0 | 0 | 9.17 | 14.34 | 5149.75
TS5500Exc | RS\54\005\D | RS | 54 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2025-12-10 17:18 | 2025-12-11 12:40 | 24387.467 | [6 empty] | 24387 | 17905 | 4.3 | 0 | 0 | 6.05 | 5888
DRE2 | GG\22\020\B | GG | 22 | 20 | B | 6 DL | 100 | 0 | 100 | 2025-12-10 17:19 | 2025-12-14 08:35 | 293571.9167 |  |  |  |  | 293572 | 225825 |  |  | 0 | 22.63 | 0 | 15.83 | 5080.85
PH4100A | SC\48\020\D | SC | 48 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-12-10 21:41 | 2025-12-15 08:52 | 175365.9958 | 175366 | [7 empty] | 0 | 0 | 14.92 | 7.15 | 5782.34
TS6060#1 | GG\25\010\X1 | GG | 25 | 10 | X1 | 8 Coal Mining | 0.2 | 0 | 0.2 | 2025-12-11 04:41 | 2025-12-11 04:43 | 36.5151 | [6 empty] | 37 | 26 | 0 | 0 | 0 | 14.62 | 5128
TS6060#1 | RS\56\005\A | RS | 56 | 5 | A | 1 Prestrip - Thick | 20.6954 | 20.6954 | 20.6954 | 2025-12-11 04:43 | 2025-12-12 23:57 | 42781.6479 | 42782 | [7 empty] | 0 | 0 | 5.97 | 14.65 | 5169.91
TS5500Exc | SC\39\026\D | SC | 39 | 26 | D | 7 PostStrip | 100 | 0 | 100 | 2025-12-11 12:40 | 2025-12-14 10:59 | 62191.8371 |  |  | 62192 | [5 empty] | 0 | 0 | 0 | 6.91 | 5806.8
TS5500Shv | GG\25\010\X1 | GG | 25 | 10 | X1 | 8 Coal Mining | 99.8 | 0 | 99.8 | 2025-12-12 01:24 | 2025-12-12 14:57 | 16523.998 | [6 empty] | 16524 | 11839 | 1.19 | 0 | 0 | 14.62 | 5128
TS Fleet 5 | GG\25\018\X2 | GG | 25 | 18 | X2 | 1 Prestrip - Thick | 31.4653 | 0 | 31.4653 | 2025-12-12 01:43 | 2025-12-13 13:10 | 66506.9682 | 66507 | [7 empty] | 0 | 0 | 6.85 | 0 | 0
TS5500Shv | GG\25\010\X2 | GG | 25 | 10 | X2 | 1 Prestrip - Thick | 21.9869 | 0 | 21.9869 | 2025-12-12 14:57 | 2025-12-13 04:43 | 14751.9709 | 14752 | [7 empty] | 0 | 0 | 1.48 | 0 | 0
TS6060#1 | RS\57\001\D | RS | 57 | 1 | D | 1 Prestrip - Thick | 21.1625 | 21.1625 | 21.1625 | 2025-12-12 23:57 | 2025-12-13 14:17 | 14772.9845 | 14773 | [7 empty] | 0 | 0 | 1.62 | 7.79 | 5735.19
TS5500Shv | GG\21\004\D | GG | 21 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2025-12-13 04:43 | 2025-12-15 12:01 | 59289.9995 |  |  | 59290 | [5 empty] | 0 | 0 | 0 | 6.64 | 5801.93
TS Fleet 5 | GG\25\019\B | GG | 25 | 19 | B | 1 Prestrip - Thick | 36.2425 | 36.2425 | 36.2425 | 2025-12-13 13:10 | 2025-12-15 19:50 | 102561.1441 | 102561 | [7 empty] | 0 | 0 | 10.39 | 14.66 | 5155.33
TS6060#1 | RS\57\002\D | RS | 57 | 2 | D | 1 Prestrip - Thick | 20.995 | 20.995 | 20.995 | 2025-12-13 14:17 | 2025-12-15 00:15 | 34492.4011 | 34492 | [7 empty] | 0 | 0 | 3.56 | 6.66 | 5835.03
DRE2 | GG\22\022\B | GG | 22 | 22 | B | 6 DL | 100 | 0 | 100 | 2025-12-14 08:35 | 2025-12-17 15:42 | 266119.9103 |  |  |  |  | 266120 | 204708 |  |  | 0 | 23.42 | 0 | 20.5 | 4725.37
TS5500Exc | GG\25\010\X2 | GG | 25 | 10 | X2 | 1 Prestrip - Thick | 78.0131 | 0 | 64.9501 | 2025-12-14 10:59 | 2025-12-16 12:16 | 43577.8153 | 43578 | [7 empty] | 0 | 0 | 4.36 | 0 | 0
TS6060#1 | GG\22\018\B | GG | 22 | 18 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-12-15 00:15 | 2025-12-15 19:31 | 26079.3477 | [6 empty] | 26079 | 18865 | 1.89 | 0 | 0 | 12.54 | 5305
PH4100A | SC\49\020\D | SC | 49 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-12-15 08:52 | 2025-12-19 22:25 | 179232.7444 | 179233 | [7 empty] | 0 | 0 | 15.2 | 7.21 | 5777.44
TS5500Shv | GG\21\004\D | GG | 21 | 4 | D | 8 Coal Mining | 91.9 | 0 | 91.9 | 2025-12-15 12:01 | 2025-12-17 17:16 | 64941.6629 | [6 empty] | 64942 | 48664 | 4.14 | 0 | 0 | 6.64 | 5802
TS6060#1 | GG\21\004\D | GG | 21 | 4 | D | 8 Coal Mining | 0.9 | 0 | 0.9 | 2025-12-15 19:31 | 2025-12-15 20:00 | 667.5413 | [6 empty] | 668 | 500 | 0.04 | 0 | 0 | 6.64 | 5802
TS Fleet 5 | GG\25\020\B | GG | 25 | 20 | B | 1 Prestrip - Thick | 45.0267 | 45.0267 | 45.0267 | 2025-12-15 19:50 | 2025-12-16 15:37 | 37109.6832 | 37110 | [7 empty] | 0 | 0 | 6.17 | 17.08 | 4976.13
TS6060#1 | GG\22\019\B | GG | 22 | 19 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-12-15 20:00 | 2025-12-16 15:59 | 27045.9276 | [6 empty] | 27046 | 19482 | 1.95 | 0 | 0 | 12.95 | 5294
PH4100XPC#1 | GG\25\010\X2 | GG | 25 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 13.0629 | 2025-12-16 08:23 | 2025-12-16 12:16 | 8764.4728 | 8764 | [7 empty] | 0 | 0 | 0.88 | 0 | 0
TS5500Exc | GG\25\010\A | GG | 25 | 10 | A | 1 Prestrip - Thick | 33.778 | 0 | 18.9098 | 2025-12-16 12:16 | 2025-12-17 08:10 | 17610.1528 | 17610 | [7 empty] | 0 | 0 | 1.76 | 0 | 0
PH4100XPC#1 | GG\25\010\A | GG | 25 | 10 | A | 1 Prestrip - Thick | 100 | 0 | 48.3974 | 2025-12-16 12:16 | 2025-12-17 08:10 | 45071.159 | 45071 | [7 empty] | 0 | 0 | 4.5 | 0 | 0
TS Fleet 5 | GG\25\010\A | GG | 25 | 10 | A | 1 Prestrip - Thick | 32.6928 | 0 | 32.6928 | 2025-12-16 15:37 | 2025-12-17 07:51 | 30445.878 | 30446 | [7 empty] | 0 | 0 | 3.04 | 0 | 0
TS6060#1 | GG\22\020\B | GG | 22 | 20 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2025-12-16 15:59 | 2025-12-17 04:31 | 16943.0646 | [6 empty] | 16943 | 12003 | 1.18 | 0 | 0 | 15.83 | 5081
TS6060#1 | RS\58\001\D | RS | 58 | 1 | D | 1 Prestrip - Thick | 35.3636 | 35.3636 | 35.3636 | 2025-12-17 04:31 | 2025-12-17 20:12 | 16165.2567 | 16165 | [7 empty] | 0 | 0 | 1.7 | 7.87 | 5728.01
TS Fleet 5 | GG\25\021\D | GG | 25 | 21 | D | 1 Prestrip - Thick | 44.2402 | 44.2402 | 44.2402 | 2025-12-17 07:51 | 2025-12-20 10:17 | 139637.864 | 139638 | [7 empty] | 0 | 0 | 16.02 | 6.64 | 5786.19
PH4100XPC#1 | GG\25\010\B | GG | 25 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-12-17 08:10 | 2025-12-18 02:27 | 41387.0593 | 41387 | [7 empty] | 0 | 0 | 4.13 | 10.46 | 5497.16
TS5500Exc | SC\39\026\D | SC | 39 | 26 | D | 8 Coal Mining | 100 | 0 | 41.7 | 2025-12-17 08:10 | 2025-12-18 09:46 | 32233.1347 | [6 empty] | 32233 | 24167 | 2.01 | 0 | 0 | 6.91 | 5807
DRE1 | RS\55\003\D | RS | 55 | 3 | D | 6 DL | 100 | 100 | 100 | 2025-12-17 11:01 | 2025-12-21 11:08 | 335750.3232 |  |  |  | 17262 | 335750 | 270442 |  |  | 0 | 28.78 | 0 | 5.96 | 5896.08
DRE2 | GG\22\023\B | GG | 22 | 23 | B | 6 DL | 100 | 0 | 100 | 2025-12-17 15:42 | 2025-12-20 13:31 | 234842.7649 |  |  |  |  | 234843 | 180648 |  |  | 0 | 25.8 | 0 | 0 | 0
TS5500Shv | GG\25\011\X1 | GG | 25 | 11 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2025-12-17 17:16 | 2025-12-18 05:22 | 14749.8301 | [6 empty] | 14750 | 10558 | 1.05 | 0 | 0 | 14.87 | 5112
TS6060#1 | GG\22\022\B | GG | 22 | 22 | B | 8 Coal Mining | 52.6 | 0 | 30.9 | 2025-12-17 20:12 | 2025-12-18 09:46 | 18360.7325 | [6 empty] | 18361 | 12673 | 1.28 | 0 | 0 | 20.5 | 4725
PH4100XPC#1 | GG\25\012\X1 | GG | 25 | 12 | X1 | 1 Prestrip - Thick | 100 | 54.1251 | 54.1251 | 2025-12-18 02:27 | 2025-12-23 04:56 | 272179.9516 | 272180 | [7 empty] | 0 | 0 | 28.2 | 14.95 | 5104.34
TS5500Shv | GG\25\010\B | GG | 25 | 10 | B | 8 Coal Mining | 100 | 0 | 10.8 | 2025-12-18 05:22 | 2025-12-18 09:46 | 5355.2254 | [6 empty] | 5355 | 3915 | 0.39 | 0 | 0 | 10.46 | 5497
TS6060#1 | RS\58\002\D | RS | 58 | 2 | D | 1 Prestrip - Thick | 34.9157 | 34.9157 | 34.9157 | 2025-12-18 09:46 | 2025-12-20 23:04 | 61939.213 | 61939 | [7 empty] | 0 | 0 | 6.43 | 6.71 | 5830.73
TS5500Shv | GG\25\011\X2 | GG | 25 | 11 | X2 | 1 Prestrip - Thick | 36.478 | 0 | 36.478 | 2025-12-18 09:46 | 2025-12-19 08:45 | 24639.9551 | 24640 | [7 empty] | 0 | 0 | 2.45 | 0 | 0
TS5500Exc | GG\25\011\X2 | GG | 25 | 11 | X2 | 1 Prestrip - Thick | 30.0943 | 0 | 30.0943 | 2025-12-18 09:46 | 2025-12-19 08:45 | 20327.963 | 20328 | [7 empty] | 0 | 0 | 2.02 | 0 | 0
TS5500Exc | GG\25\022\D | GG | 25 | 22 | D | 1 Prestrip - Thick | 10.5764 | 10.5764 | 10.5764 | 2025-12-19 08:45 | 2025-12-20 13:04 | 25046.8573 | 25047 | [7 empty] | 0 | 0 | 3.9 | 6.73 | 5796.41
TS5500Shv | GG\25\022\D | GG | 25 | 22 | D | 1 Prestrip - Thick | 12.8474 | 12.8474 | 12.8474 | 2025-12-19 08:45 | 2025-12-20 13:04 | 30424.991 | 30425 | [7 empty] | 0 | 0 | 4.74 | 6.73 | 5796.41
PH4100A | SC\47\021\D | SC | 47 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-12-19 22:25 | 2025-12-24 03:10 | 165330.8099 | 165331 | [7 empty] | 0 | 0 | 14.06 | 7.28 | 5770.96
TS Fleet 5 | GG\25\011\X2 | GG | 25 | 11 | X2 | 1 Prestrip - Thick | 15.1825 | 0 | 15.1825 | 2025-12-20 10:17 | 2025-12-20 15:45 | 10255.3965 | 10255 | [7 empty] | 0 | 0 | 1.02 | 0 | 0
TS5500Shv | RS\55\005\A | RS | 55 | 5 | A | 1 Prestrip - Thick | 19.9658 | 19.9658 | 19.9658 | 2025-12-20 13:04 | 2025-12-22 08:20 | 44250.0627 | 44250 | [7 empty] | 0 | 0 | 6.23 | 14.53 | 5180.28
TS5500Exc | RS\55\005\A | RS | 55 | 5 | A | 1 Prestrip - Thick | 17.3625 | 17.3625 | 17.3625 | 2025-12-20 13:04 | 2025-12-22 08:20 | 38480.4135 | 38480 | [7 empty] | 0 | 0 | 5.41 | 14.53 | 5180.28
DRE2 | GG\21\014\D | GG | 21 | 14 | D | 6 DL | 100 | 100 | 100 | 2025-12-20 13:31 | 2025-12-25 07:30 | 383411.3727 |  |  |  | 8927 | 383411 | 169612 |  |  | 0 | 23.87 | 0 | 7.17 | 5759.11
TS Fleet 5 | GG\25\022\D | GG | 25 | 22 | D | 1 Prestrip - Thick | 34.2377 | 34.2377 | 34.2377 | 2025-12-20 15:45 | 2025-12-22 10:58 | 81081.1121 | 81081 | [7 empty] | 0 | 0 | 12.64 | 6.73 | 5796.41
TS6060#1 | RS\58\003\D | RS | 58 | 3 | D | 1 Prestrip - Thick | 31.5783 | 31.5783 | 31.5783 | 2025-12-20 23:04 | 2025-12-24 00:06 | 73432.6153 | 73433 | [7 empty] | 0 | 0 | 7.5 | 6 | 5892.55
DRE1 | RS\58\001\D | RS | 58 | 1 | D | 6 DL | 100 | 0 | 100 | 2025-12-21 11:08 | 2025-12-25 22:16 | 374202.4422 |  |  |  | 21357 | 374202 | 283741 |  |  | 0 | 30 | 0 | 7.87 | 5728.01
TS5500Exc | RS\56\001\D | RS | 56 | 1 | D | 1 Prestrip - Thick | 18.1753 | 18.1753 | 18.1753 | 2025-12-22 08:20 | 2025-12-23 02:11 | 15793.2466 | 15793 | [7 empty] | 0 | 0 | 1.85 | 7.68 | 5744.79
TS5500Shv | RS\56\002\D | RS | 56 | 2 | D | 1 Prestrip - Thick | 21.7868 | 21.7868 | 21.7868 | 2025-12-22 08:20 | 2025-12-23 20:49 | 38492.4616 | 38492 | [7 empty] | 0 | 0 | 3.94 | 6.58 | 5841.95
TS Fleet 5 | RS\57\005\A | RS | 57 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-12-22 10:58 | 2025-12-26 17:58 | 193235.6231 | 193236 | [7 empty] | 0 | 0 | 26.63 | 14.99 | 5141.64
TS5500Exc | RS\56\002\D | RS | 56 | 2 | D | 1 Prestrip - Thick | 18.2956 | 18.2956 | 18.2956 | 2025-12-23 02:11 | 2025-12-24 14:40 | 32324.2891 | 32324 | [7 empty] | 0 | 0 | 3.31 | 6.58 | 5841.95
PH4100XPC#1 | GG\25\011\X2 | GG | 25 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 18.2452 | 2025-12-23 04:56 | 2025-12-23 10:23 | 12324.1494 | 12324 | [7 empty] | 0 | 0 | 1.22 | 0 | 0
PH4100XPC#1 | GG\25\011\B | GG | 25 | 11 | B | 1 Prestrip - Thick | 100 | 88.8941 | 88.8941 | 2025-12-23 10:23 | 2025-12-25 03:58 | 94133.8596 | 94134 | [7 empty] | 0 | 0 | 9.35 | 11.32 | 5423.04
TS5500Shv | RS\56\004\A | RS | 56 | 4 | A | 1 Prestrip - Thick | 21.1762 | 21.1762 | 21.1762 | 2025-12-23 20:49 | 2025-12-25 23:21 | 50984.7919 | 50985 | [7 empty] | 0 | 0 | 5.23 | 15.09 | 5134.64
TS6060#1 | RS\58\004\B | RS | 58 | 4 | B | 1 Prestrip - Thick | 23.605 | 23.605 | 23.605 | 2025-12-24 00:06 | 2025-12-26 14:11 | 61064.0257 | 61064 | [7 empty] | 0 | 0 | 6.26 | 10.81 | 5420
PH4100A | SC\48\021\D | SC | 48 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-12-24 03:10 | 2025-12-27 21:25 | 148288.8766 | 148289 | [7 empty] | 0 | 0 | 12.71 | 7.27 | 5771.12
TS5500Exc | GG\25\011\B | GG | 25 | 11 | B | 1 Prestrip - Thick | 17.5773 | 11.1059 | 11.1059 | 2025-12-24 14:40 | 2025-12-25 03:58 | 11760.5563 | 11761 | [7 empty] | 0 | 0 | 1.17 | 11.32 | 5423.04
TS5500Exc | RS\56\004\A | RS | 56 | 4 | A | 1 Prestrip - Thick | 18.6942 | 18.6942 | 18.6942 | 2025-12-25 03:58 | 2025-12-27 06:30 | 45008.997 | 45009 | [7 empty] | 0 | 0 | 4.62 | 15.09 | 5134.64
PH4100XPC#1 | GG\25\013\X1 | GG | 25 | 13 | X1 | 1 Prestrip - Thick | 100 | 36.4048 | 36.4048 | 2025-12-25 03:58 | 2025-12-27 23:05 | 146879.7319 | 146880 | [7 empty] | 0 | 0 | 14.82 | 14.79 | 5115.81
DRE2 | GG\21\018\D | GG | 21 | 18 | D | 6 DL | 100 | 100 | 100 | 2025-12-25 07:30 | 2025-12-31 13:54 | 505936.7765 |  |  |  | 11780 | 505937 | 223814 |  |  | 0 | 23.58 | 0 | 7.17 | 5758.56
DRE1 | RS\56\001\D | RS | 56 | 1 | D | 6 DL | 100 | 0 | 100 | 2025-12-25 22:16 | 2025-12-29 18:49 | 323276.4065 |  |  |  | 18450 | 323276 | 245126 |  |  | 0 | 30 | 0 | 7.68 | 5744.79
TS5500Shv | RS\56\005\A | RS | 56 | 5 | A | 1 Prestrip - Thick | 21.316 | 21.316 | 21.316 | 2025-12-25 23:21 | 2025-12-27 18:34 | 44064.6423 | 44065 | [7 empty] | 0 | 0 | 6.15 | 14.65 | 5169.91
TS6060#1 | RS\58\005\A | RS | 58 | 5 | A | 1 Prestrip - Thick | 15.909 | 15.909 | 15.909 | 2025-12-26 14:11 | 2025-12-27 19:34 | 28889.3049 | 28889 | [7 empty] | 0 | 0 | 3.93 | 15.75 | 5080.62
TS Fleet 5 | RS\58\002\D | RS | 58 | 2 | D | 1 Prestrip - Thick | 65.0843 | 65.0843 | 65.0843 | 2025-12-26 17:58 | 2025-12-29 07:31 | 115457.1382 | 115457 | [7 empty] | 0 | 0 | 11.99 | 6.71 | 5830.73
TS5500Exc | RS\56\005\A | RS | 56 | 5 | A | 1 Prestrip - Thick | 18.603 | 18.603 | 18.603 | 2025-12-27 06:30 | 2025-12-29 01:43 | 38456.2372 | 38456 | [7 empty] | 0 | 0 | 5.37 | 14.65 | 5169.91
TS5500Shv | RS\57\002\D | RS | 57 | 2 | D | 1 Prestrip - Thick | 21.7423 | 21.7423 | 21.7423 | 2025-12-27 18:34 | 2025-12-29 04:32 | 35720.1527 | 35720 | [7 empty] | 0 | 0 | 3.69 | 6.66 | 5835.03
TS6060#1 | RS\59\001\D | RS | 59 | 1 | D | 1 Prestrip - Thick | 35.3277 | 35.3277 | 35.3277 | 2025-12-27 19:34 | 2025-12-28 04:06 | 8769.1461 | 8769 | [7 empty] | 0 | 0 | 0.92 | 7.91 | 5723.83
PH4100A | SC\49\021\D | SC | 49 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2025-12-27 21:25 | 2025-12-31 07:12 | 134368.0997 | 134368 | [7 empty] | 0 | 0 | 11.56 | 7.28 | 5770.08
PH4100XPC#1 | GG\25\014\X1 | GG | 25 | 14 | X1 | 1 Prestrip - Thick | 100 | 53.3246 | 53.3246 | 2025-12-27 23:05 | 2025-12-30 15:20 | 138250.0203 | 138250 | [7 empty] | 0 | 0 | 17.12 | 14.67 | 5124.58
TS6060#1 | RS\59\002\D | RS | 59 | 2 | D | 1 Prestrip - Thick | 24.5881 | 24.5881 | 24.5881 | 2025-12-28 04:06 | 2025-12-30 09:20 | 53444.2878 | 53444 | [7 empty] | 0 | 0 | 5.57 | 6.73 | 5828.63
TS5500Exc | RS\57\001\D | RS | 57 | 1 | D | 1 Prestrip - Thick | 18.1691 | 18.1691 | 18.1691 | 2025-12-29 01:43 | 2025-12-29 16:04 | 12683.3728 | 12683 | [7 empty] | 0 | 0 | 1.39 | 7.79 | 5735.19
TS5500Shv | RS\57\003\D | RS | 57 | 3 | D | 1 Prestrip - Thick | 33.1331 | 29.8667 | 29.8667 | 2025-12-29 04:32 | 2026-01-01 | 70209.6832 | 70210 | [7 empty] | 0 | 0 | 7.19 | 5.99 | 5893.2
TS Fleet 5 | RS\58\003\D | RS | 58 | 3 | D | 1 Prestrip - Thick | 68.4217 | 52.0172 | 52.0172 | 2025-12-29 07:31 | 2026-01-01 | 120961.5552 | 120962 | [7 empty] | 0 | 0 | 12.35 | 6 | 5892.55
TS5500Exc | RS\57\002\D | RS | 57 | 2 | D | 1 Prestrip - Thick | 18.3246 | 18.3246 | 18.3246 | 2025-12-29 16:04 | 2025-12-31 02:01 | 30105.2654 | 30105 | [7 empty] | 0 | 0 | 3.11 | 6.66 | 5835.03
DRE1 | RS\56\002\D | RS | 56 | 2 | D | 6 DL | 100 | 0 | 50.8301 | 2025-12-29 18:49 | 2026-01-01 | 185768.9992 |  |  |  | 10602 | 185769 | 140860 |  |  | 0 | 30 | 0 | 6.58 | 5841.95
TS6060#1 | RS\59\003\D | RS | 59 | 3 | D | 1 Prestrip - Thick | 22.1546 | 16.7825 | 16.7825 | 2025-12-30 09:20 | 2026-01-01 | 38808.2 | 38808 | [7 empty] | 0 | 0 | 3.96 | 6.01 | 5891.77
PH4100XPC#1 | GG\25\017\X1 | GG | 25 | 17 | X1 | 1 Prestrip - Thick | 100 | 36.6095 | 36.6095 | 2025-12-30 15:20 | 2026-01-01 | 69530.7695 | 69531 | [7 empty] | 0 | 0 | 8.71 | 14.34 | 5149.75
TS5500Exc | RS\58\004\B | RS | 58 | 4 | B | 1 Prestrip - Thick | 11.622 | 7.5615 | 7.5615 | 2025-12-31 02:01 | 2026-01-01 | 19560.843 | 19561 | [7 empty] | 0 | 0 | 2.01 | 10.81 | 5420
PH4100A | SC\48\022\D | SC | 48 | 22 | D | 1 Prestrip - Thick | 100 | 32.573 | 32.573 | 2025-12-31 07:12 | 2026-01-01 | 27612.2023 | 27612 | [7 empty] | 0 | 0 | 2.42 | 7.37 | 5764.78
DRE2 | GG\21\019\D | GG | 21 | 19 | D | 6 DL | 100 | 6.98 | 6.98 | 2025-12-31 13:54 | 2026-01-01 | 33926.6701 |  |  |  | 790 | 33927 | 15008 |  |  | 0 | 22.63 | 0 | 7.05 | 5768.61
| EOP 78 : 2025 | EOP 78 : 2025 | [7 empty] | 2026-01-01 | 2026-01-01 |  | 65781144 |  | 808946 | 1966768 | 57048165 | 35907236 | 13000000 | 9501067 | 968.26 | 0 | 6030.06 | 8.73 | 5634.2
TS Fleet 5 | RS\58\003\D | RS | 58 | 3 | D | 1 Prestrip - Thick | 68.4217 | 16.4045 | 16.4045 | 2026-01-01 | 2026-01-01 19:27 | 38147.3905 | 38147 | [7 empty] | 0 | 0 | 3.9 | 6 | 5892.55
DRE1 | RS\56\002\D | RS | 56 | 2 | D | 6 DL | 100 | 0 | 49.1699 | 2026-01-01 | 2026-01-03 03:26 | 179701.7545 |  |  |  | 10256 | 179702 | 136260 |  |  | 0 | 30 | 0 | 6.58 | 5841.95
PH4100A | SC\48\022\D | SC | 48 | 22 | D | 1 Prestrip - Thick | 100 | 67.427 | 67.427 | 2026-01-01 | 2026-01-02 09:16 | 57157.8875 | 57158 | [7 empty] | 0 | 0 | 5.02 | 7.37 | 5764.78
DRE2 | GG\21\019\D | GG | 21 | 19 | D | 6 DL | 100 | 93.02 | 93.02 | 2026-01-01 | 2026-01-06 14:24 | 452126.4692 |  |  |  | 10527 | 452126 | 200009 |  |  | 0 | 22.63 | 0 | 7.05 | 5768.61
PH4100XPC#1 | GG\25\017\X1 | GG | 25 | 17 | X1 | 1 Prestrip - Thick | 100 | 6.9512 | 6.9512 | 2026-01-01 | 2026-01-01 06:12 | 13202.0375 | 13202 | [7 empty] | 0 | 0 | 1.65 | 14.34 | 5149.75
TS6060#1 | RS\59\003\D | RS | 59 | 3 | D | 1 Prestrip - Thick | 22.1546 | 5.3721 | 5.3721 | 2026-01-01 | 2026-01-01 12:22 | 12422.6469 | 12423 | [7 empty] | 0 | 0 | 1.27 | 6.01 | 5891.77
TS5500Exc | RS\58\004\B | RS | 58 | 4 | B | 1 Prestrip - Thick | 11.622 | 4.0606 | 4.0606 | 2026-01-01 | 2026-01-01 11:47 | 10504.2895 | 10504 | [7 empty] | 0 | 0 | 1.08 | 10.81 | 5420
TS5500Shv | RS\57\003\D | RS | 57 | 3 | D | 1 Prestrip - Thick | 33.1331 | 3.2664 | 3.2664 | 2026-01-01 | 2026-01-01 07:22 | 7678.4539 | 7678 | [7 empty] | 0 | 0 | 0.79 | 5.99 | 5893.2
PH4100XPC#1 | GG\25\018\X2 | GG | 25 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 36.2179 | 2026-01-01 06:12 | 2026-01-02 17:30 | 76552.2188 | 76552 | [7 empty] | 0 | 0 | 7.88 | 0 | 0
TS5500Shv | GG\25\010\B | GG | 25 | 10 | B | 8 Coal Mining | 100 | 0 | 89.2 | 2026-01-01 07:22 | 2026-01-02 19:45 | 44367.5215 | [6 empty] | 44368 | 32433 | 3.24 | 0 | 0 | 10.46 | 5497
TS5500Exc | SC\39\026\D | SC | 39 | 26 | D | 8 Coal Mining | 100 | 0 | 58.3 | 2026-01-01 11:47 | 2026-01-02 23:38 | 45151.3344 | [6 empty] | 45151 | 33853 | 2.82 | 0 | 0 | 6.91 | 5807
TS6060#1 | GG\21\014\D | GG | 21 | 14 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-01-01 12:22 | 2026-01-02 06:48 | 24952.6375 | [6 empty] | 24953 | 18567 | 2.53 | 0 | 0 | 7.17 | 5759
TS Fleet 5 | RS\58\004\B | RS | 58 | 4 | B | 1 Prestrip - Thick | 51.5674 | 51.5674 | 51.5674 | 2026-01-01 19:27 | 2026-01-04 15:31 | 133399.9937 | 133400 | [7 empty] | 0 | 0 | 13.68 | 10.81 | 5420
TS6060#1 | GG\22\022\B | GG | 22 | 22 | B | 8 Coal Mining | 52.6 | 0 | 21.7 | 2026-01-02 06:48 | 2026-01-02 16:18 | 12855.5845 | [6 empty] | 12856 | 8873 | 0.9 | 0 | 0 | 20.5 | 4725
PH4100A | SC\47\022\D | SC | 47 | 22 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-02 09:16 | 2026-01-05 01:56 | 111099.1453 | 111099 | [7 empty] | 0 | 0 | 9.62 | 7.38 | 5763.36
TS6060#1 | RS\59\004\B | RS | 59 | 4 | B | 1 Prestrip - Thick | 13.7348 | 13.7348 | 13.7348 | 2026-01-02 16:18 | 2026-01-04 02:36 | 33632.0211 | 33632 | [7 empty] | 0 | 0 | 3.44 | 11.73 | 5343.68
PH4100XPC#1 | GG\25\018\B | GG | 25 | 18 | B | 1 Prestrip - Thick | 100 | 68.9499 | 68.9499 | 2026-01-02 17:30 | 2026-01-04 13:37 | 99863.1154 | 99863 | [7 empty] | 0 | 0 | 9.93 | 13.73 | 5206.8
TS5500Shv | GG\25\012\X1 | GG | 25 | 12 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-01-02 19:45 | 2026-01-03 07:05 | 13807.0362 | [6 empty] | 13807 | 9883 | 1 | 0 | 0 | 14.95 | 5104
TS5500Exc | GG\25\018\B | GG | 25 | 18 | B | 1 Prestrip - Thick | 100 | 23.1954 | 23.1954 | 2026-01-02 23:38 | 2026-01-04 13:37 | 33594.9672 | 33595 | [7 empty] | 0 | 0 | 3.34 | 13.73 | 5206.8
DRE1 | RS\57\001\D | RS | 57 | 1 | D | 6 DL | 100 | 0 | 100 | 2026-01-03 03:26 | 2026-01-07 07:36 | 349886.2269 |  |  |  | 19969 | 349886 | 265303 |  |  | 0 | 30 | 0 | 7.79 | 5735.19
TS5500Shv | GG\25\013\X1 | GG | 25 | 13 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-01-03 07:05 | 2026-01-03 18:04 | 13409.8001 | [6 empty] | 13410 | 9607 | 0.97 | 0 | 0 | 14.79 | 5116
TS5500Shv | GG\25\014\X1 | GG | 25 | 14 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-01-03 18:04 | 2026-01-04 02:39 | 10458.9241 | [6 empty] | 10459 | 7506 | 0.95 | 0 | 0 | 14.67 | 5125
TS6060#1 | GG\25\018\B | GG | 25 | 18 | B | 1 Prestrip - Thick | 100 | 7.8546 | 7.8546 | 2026-01-04 02:36 | 2026-01-04 13:37 | 11376.222 | 11376 | [7 empty] | 0 | 0 | 1.13 | 13.73 | 5206.8
TS5500Shv | GG\25\013\X2 | GG | 25 | 13 | X2 | 1 Prestrip - Thick | 45.1907 | 0 | 45.1907 | 2026-01-04 02:39 | 2026-01-05 09:29 | 33059.4387 | 33059 | [7 empty] | 0 | 0 | 3.32 | 0 | 0
TS6060#1 | RS\59\005\A | RS | 59 | 5 | A | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-04 13:37 | 2026-01-12 02:40 | 177663.6847 | 177664 | [7 empty] | 0 | 0 | 24.06 | 16.44 | 5025.2
PH4100XPC#1 | GG\25\012\X2 | GG | 25 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 47.0417 | 2026-01-04 13:37 | 2026-01-05 04:03 | 32646.4159 | 32646 | [7 empty] | 0 | 0 | 3.29 | 0 | 0
TS5500Exc | GG\25\012\X2 | GG | 25 | 12 | X2 | 1 Prestrip - Thick | 17.5773 | 0 | 17.5773 | 2026-01-04 13:37 | 2026-01-05 03:25 | 12198.4694 | 12198 | [7 empty] | 0 | 0 | 1.23 | 0 | 0
TS Fleet 5 | GG\25\012\X2 | GG | 25 | 12 | X2 | 1 Prestrip - Thick | 37.4355 | 0 | 35.381 | 2026-01-04 15:31 | 2026-01-05 04:03 | 24554.0007 | 24554 | [7 empty] | 0 | 0 | 2.48 | 0 | 0
PH4100A | SC\49\022\D | SC | 49 | 22 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-05 01:56 | 2026-01-07 10:25 | 96820.4189 | 96820 | [7 empty] | 0 | 0 | 8.43 | 7.35 | 5766.21
TS5500Exc | GG\25\013\X2 | GG | 25 | 13 | X2 | 1 Prestrip - Thick | 9.634 | 0 | 9.634 | 2026-01-05 03:25 | 2026-01-05 11:23 | 7047.7991 | 7048 | [7 empty] | 0 | 0 | 0.71 | 0 | 0
TS Fleet 5 | GG\25\012\B | GG | 25 | 12 | B | 1 Prestrip - Thick | 38.6957 | 35.1141 | 35.1141 | 2026-01-05 04:03 | 2026-01-06 00:39 | 40402.0984 | 40402 | [7 empty] | 0 | 0 | 4.05 | 11.78 | 5369.11
PH4100XPC#1 | GG\25\012\B | GG | 25 | 12 | B | 1 Prestrip - Thick | 100 | 40.5518 | 40.5518 | 2026-01-05 04:03 | 2026-01-06 00:39 | 46658.6519 | 46659 | [7 empty] | 0 | 0 | 4.67 | 11.78 | 5369.11
TS5500Shv | GG\25\012\B | GG | 25 | 12 | B | 1 Prestrip - Thick | 14.8029 | 14.131 | 14.131 | 2026-01-05 09:29 | 2026-01-06 00:39 | 16259.02 | 16259 | [7 empty] | 0 | 0 | 1.63 | 11.78 | 5369.11
TS5500Exc | GG\25\012\B | GG | 25 | 12 | B | 1 Prestrip - Thick | 100 | 10.2032 | 10.2032 | 2026-01-05 11:23 | 2026-01-06 00:39 | 11739.7188 | 11740 | [7 empty] | 0 | 0 | 1.18 | 11.78 | 5369.11
TS Fleet 5 | GG\25\013\X2 | GG | 25 | 13 | X2 | 1 Prestrip - Thick | 20.5181 | 0 | 20.5181 | 2026-01-06 00:39 | 2026-01-06 08:19 | 15010.1357 | 15010 | [7 empty] | 0 | 0 | 1.51 | 0 | 0
PH4100XPC#1 | GG\25\013\X2 | GG | 25 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 24.6571 | 2026-01-06 00:39 | 2026-01-06 08:38 | 18038.0305 | 18038 | [7 empty] | 0 | 0 | 1.81 | 0 | 0
TS5500Exc | GG\25\014\B | GG | 25 | 14 | B | 1 Prestrip - Thick | 9.9421 | 9.9421 | 9.9421 | 2026-01-06 00:39 | 2026-01-06 18:41 | 15939.8641 | 15940 | [7 empty] | 0 | 0 | 2.1 | 12.4 | 5285.38
TS5500Shv | GG\25\017\X1 | GG | 25 | 17 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-01-06 00:39 | 2026-01-06 09:59 | 11368.3276 | [6 empty] | 11368 | 8173 | 1.02 | 0 | 0 | 14.34 | 5150
TS Fleet 5 | GG\25\014\B | GG | 25 | 14 | B | 1 Prestrip - Thick | 40.9033 | 40.9033 | 40.9033 | 2026-01-06 08:19 | 2026-01-07 17:46 | 65578.8083 | 65579 | [7 empty] | 0 | 0 | 8.65 | 12.4 | 5285.38
PH4100XPC#1 | GG\25\013\B | GG | 25 | 13 | B | 1 Prestrip - Thick | 100 | 81.2515 | 81.2515 | 2026-01-06 08:38 | 2026-01-08 05:49 | 102288.5442 | 102289 | [7 empty] | 0 | 0 | 10.23 | 12.11 | 5321.95
TS5500Shv | GG\25\017\B | GG | 25 | 17 | B | 1 Prestrip - Thick | 9.3643 | 9.3643 | 9.3643 | 2026-01-06 09:59 | 2026-01-07 01:03 | 16162.1486 | 16162 | [7 empty] | 0 | 0 | 2.12 | 13.76 | 5185.88
DRE2 | GG\21\020\D | GG | 21 | 20 | D | 6 DL | 100 | 100 | 100 | 2026-01-06 14:24 | 2026-01-10 22:31 | 350205.1039 |  |  |  | 6522 | 350205 | 156516 |  |  | 0 | 16.25 | 0 | 6.92 | 5779.82
TS5500Exc | GG\25\017\B | GG | 25 | 17 | B | 1 Prestrip - Thick | 100 | 40.6137 | 40.6137 | 2026-01-06 18:41 | 2026-01-10 01:56 | 70096.5619 | 70097 | [7 empty] | 0 | 0 | 9.21 | 13.76 | 5185.88
TS5500Shv | RS\57\003\D | RS | 57 | 3 | D | 1 Prestrip - Thick | 2.458 | 2.458 | 2.458 | 2026-01-07 01:03 | 2026-01-07 06:36 | 5778.0821 | 5778 | [7 empty] | 0 | 0 | 0.59 | 5.99 | 5893.2
TS5500Shv | GG\21\004\D | GG | 21 | 4 | D | 8 Coal Mining | 7.1 | 0 | 7.1 | 2026-01-07 06:36 | 2026-01-07 10:44 | 5031.3635 | [6 empty] | 5031 | 3770 | 0.32 | 0 | 0 | 6.64 | 5802
DRE1 | RS\57\002\D | RS | 57 | 2 | D | 6 DL | 100 | 0 | 100 | 2026-01-07 07:36 | 2026-01-11 15:32 | 363032.1385 |  |  |  | 20719 | 363032 | 275271 |  |  | 0 | 30 | 0 | 6.66 | 5835.03
PH4100A | SC\47\023\D | SC | 47 | 23 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-07 10:25 | 2026-01-09 18:28 | 96023.2452 | 96023 | [7 empty] | 0 | 0 | 8.33 | 7.43 | 5760.52
TS5500Shv | GG\21\014\D | GG | 21 | 14 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-01-07 10:44 | 2026-01-08 05:10 | 22482.0793 | [6 empty] | 22482 | 16728 | 2.28 | 0 | 0 | 7.17 | 5759
TS Fleet 5 | GG\25\013\B | GG | 25 | 13 | B | 1 Prestrip - Thick | 40.4483 | 18.7485 | 18.7485 | 2026-01-07 17:46 | 2026-01-08 05:49 | 23602.7956 | 23603 | [7 empty] | 0 | 0 | 2.36 | 12.11 | 5321.95
TS5500Shv | GG\22\018\B | GG | 22 | 18 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-01-08 05:10 | 2026-01-09 00:26 | 23497.2341 | [6 empty] | 23497 | 16997 | 1.7 | 0 | 0 | 12.54 | 5305
PH4100XPC#1 | GG\25\014\B | GG | 25 | 14 | B | 1 Prestrip - Thick | 100 | 49.1545 | 49.1545 | 2026-01-08 05:49 | 2026-01-09 16:38 | 78807.585 | 78808 | [7 empty] | 0 | 0 | 10.4 | 12.4 | 5285.38
TS Fleet 5 | GG\25\017\B | GG | 25 | 17 | B | 1 Prestrip - Thick | 37.8164 | 37.8164 | 37.8164 | 2026-01-08 05:49 | 2026-01-09 15:07 | 65268.5431 | 65269 | [7 empty] | 0 | 0 | 8.57 | 13.76 | 5185.88
TS5500Shv | GG\22\019\B | GG | 22 | 19 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-01-09 00:26 | 2026-01-09 20:25 | 24368.113 | [6 empty] | 24368 | 17553 | 1.75 | 0 | 0 | 12.95 | 5294
TS Fleet 5 | RS\58\005\A | RS | 58 | 5 | A | 1 Prestrip - Thick | 55.7063 | 55.7063 | 55.7063 | 2026-01-09 15:07 | 2026-01-11 18:44 | 101157.5773 | 101158 | [7 empty] | 0 | 0 | 13.77 | 15.75 | 5080.62
PH4100XPC#1 | GG\25\017\B | GG | 25 | 17 | B | 1 Prestrip - Thick | 100 | 12.2057 | 12.2057 | 2026-01-09 16:38 | 2026-01-10 01:56 | 21066.1693 | 21066 | [7 empty] | 0 | 0 | 2.77 | 13.76 | 5185.88
PH4100A | SC\48\023\D | SC | 48 | 23 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-09 18:28 | 2026-01-12 10:47 | 109970.3631 | 109970 | [7 empty] | 0 | 0 | 9.54 | 7.38 | 5765.32
TS5500Shv | GG\22\020\B | GG | 22 | 20 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-01-09 20:25 | 2026-01-10 08:57 | 15265.5335 | [6 empty] | 15266 | 10814 | 1.07 | 0 | 0 | 15.83 | 5081
PH4100XPC#1 | GG\25\019\B | GG | 25 | 19 | B | 1 Prestrip - Thick | 100 | 43.2164 | 43.2164 | 2026-01-10 01:56 | 2026-01-12 08:23 | 122296.3256 | 122296 | [7 empty] | 0 | 0 | 12.39 | 14.66 | 5155.33
TS5500Exc | RS\55\003\D | RS | 55 | 3 | D | 8 Coal Mining | 67.3 | 0 | 67.3 | 2026-01-10 01:56 | 2026-01-11 09:12 | 39373.6553 | [6 empty] | 39374 | 28907 | 2.89 | 0 | 0 | 5.96 | 5896
TS5500Shv | GG\22\022\B | GG | 22 | 22 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-01-10 08:57 | 2026-01-11 08:00 | 28125.5926 | [6 empty] | 28126 | 19413 | 1.96 | 0 | 0 | 20.5 | 4725
DRE2 | GG\21\021\D | GG | 21 | 21 | D | 6 DL | 100 | 100 | 100 | 2026-01-10 22:31 | 2026-01-14 16:34 | 302908.4915 |  |  |  | 5641 | 302908 | 135378 |  |  | 0 | 14.25 | 0 | 6.81 | 5788.55
TS5500Shv | RS\55\004\A | RS | 55 | 4 | A | 8 Coal Mining | 12.7 | 0 | 12.7 | 2026-01-11 08:00 | 2026-01-11 12:26 | 5391.0801 | [6 empty] | 5391 | 3755 | 0.38 | 0 | 0 | 14.98 | 5143
TS5500Exc | SC\40\016\D | SC | 40 | 16 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-01-11 09:12 | 2026-01-13 14:44 | 67430.6639 | [6 empty] | 67431 | 50464 | 3.86 | 0 | 0 | 7.13 | 5781
TS5500Shv | RS\55\005\A | RS | 55 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-01-11 12:26 | 2026-01-11 23:31 | 13523.4338 | [6 empty] | 13523 | 9435 | 1.55 | 0 | 0 | 14.53 | 5180
DRE1 | RS\57\003\D | RS | 57 | 3 | D | 6 DL | 100 | 0 | 100 | 2026-01-11 15:32 | 2026-01-15 10:15 | 316892.0927 |  |  |  | 16293 | 316892 | 255252 |  |  | 0 | 27.44 | 0 | 5.99 | 5893.2
TS Fleet 5 | RS\59\002\D | RS | 59 | 2 | D | 1 Prestrip - Thick | 46.1301 | 46.1301 | 46.1301 | 2026-01-11 18:44 | 2026-01-13 21:53 | 100267.3934 | 100267 | [7 empty] | 0 | 0 | 10.45 | 6.73 | 5828.63
TS5500Shv | RS\56\001\D | RS | 56 | 1 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-01-11 23:31 | 2026-01-12 21:22 | 26633.3817 | [6 empty] | 26633 | 19280 | 2.22 | 0 | 0 | 7.68 | 5745
TS6060#1 | GG\21\019\D | GG | 21 | 19 | D | 8 Coal Mining | 24.4 | 0 | 24.4 | 2026-01-12 02:40 | 2026-01-12 14:06 | 15471.054 | [6 empty] | 15471 | 11520 | 1.15 | 0 | 0 | 7.05 | 5769
PH4100XPC#1 | GG\25\020\B | GG | 25 | 20 | B | 1 Prestrip - Thick | 100 | 54.9733 | 54.9733 | 2026-01-12 08:23 | 2026-01-13 04:05 | 45307.2991 | 45307 | [7 empty] | 0 | 0 | 7.53 | 17.08 | 4976.13
PH4100A | SC\49\023\D | SC | 49 | 23 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-12 10:47 | 2026-01-15 15:45 | 131226.3101 | 131226 | [7 empty] | 0 | 0 | 11.32 | 7.31 | 5771.08
TS6060#1 | GG\21\020\D | GG | 21 | 20 | D | 8 Coal Mining | 38.3 | 0 | 38.3 | 2026-01-12 14:06 | 2026-01-13 08:00 | 24235.5403 | [6 empty] | 24236 | 18075 | 1.81 | 0 | 0 | 6.92 | 5780
TS5500Shv | RS\56\002\D | RS | 56 | 2 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-01-12 21:22 | 2026-01-13 21:34 | 29508.9182 | [6 empty] | 29509 | 21565 | 2.16 | 0 | 0 | 6.58 | 5842
PH4100XPC#1 | GG\25\021\D | GG | 25 | 21 | D | 1 Prestrip - Thick | 100 | 55.7598 | 55.7598 | 2026-01-13 04:05 | 2026-01-16 06:14 | 175998.0014 | 175998 | [7 empty] | 0 | 0 | 20.19 | 6.64 | 5786.19
TS6060#1 | RS\60\001\D | RS | 60 | 1 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-13 08:00 | 2026-02-16 20:53 | 835079.1386 | 835079 | [7 empty] | 0 | 0 | 29.16 | 7.87 | 5728.33
TS5500Exc | RS\55\003\D | RS | 55 | 3 | D | 8 Coal Mining | 32.7 | 0 | 32.7 | 2026-01-13 14:44 | 2026-01-14 05:54 | 19111.4457 | [6 empty] | 19111 | 14031 | 1.4 | 0 | 0 | 5.96 | 5896
TS5500Shv | GG\21\018\D | GG | 21 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-01-13 21:34 | 2026-01-16 02:06 | 64066.8697 | [6 empty] | 64067 | 47670 | 4.77 | 0 | 0 | 7.17 | 5759
TS Fleet 5 | RS\59\003\D | RS | 59 | 3 | D | 1 Prestrip - Thick | 61.3879 | 61.3879 | 61.3879 | 2026-01-13 21:53 | 2026-01-16 22:19 | 141954.696 | 141955 | [7 empty] | 0 | 0 | 14.5 | 6.01 | 5891.77
TS5500Exc | RS\55\004\A | RS | 55 | 4 | A | 8 Coal Mining | 87.3 | 0 | 87.3 | 2026-01-14 05:54 | 2026-01-15 11:23 | 37136.1495 | [6 empty] | 37136 | 25866 | 2.6 | 0 | 0 | 14.98 | 5143
DRE2 | GG\21\022\D | GG | 21 | 22 | D | 6 DL | 100 | 100 | 100 | 2026-01-14 16:34 | 2026-01-19 04:50 | 364174.0624 |  |  |  | 6782 | 364174 | 162759 |  |  | 0 | 17 | 0 | 6.73 | 5796.17
DRE1 | RS\58\002\D | RS | 58 | 2 | D | 6 DL | 100 | 0 | 100 | 2026-01-15 10:15 | 2026-01-19 03:00 | 310021.9934 |  |  |  | 15939 | 310022 | 249718 |  |  | 0 | 27.13 | 0 | 6.71 | 5830.73
TS5500Exc | RS\55\005\A | RS | 55 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-01-15 11:23 | 2026-01-15 22:29 | 13969.2613 | [6 empty] | 13969 | 9746 | 1.6 | 0 | 0 | 14.53 | 5180
PH4100A | SC\47\024\D | SC | 47 | 24 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-15 15:45 | 2026-01-18 13:13 | 118716.5232 | 118717 | [7 empty] | 0 | 0 | 10.3 | 7.62 | 5743.54
TS5500Exc | RS\56\001\D | RS | 56 | 1 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-01-15 22:29 | 2026-01-16 20:19 | 27511.4052 | [6 empty] | 27511 | 19915 | 2.29 | 0 | 0 | 7.68 | 5745
TS5500Shv | RS\56\004\A | RS | 56 | 4 | A | 8 Coal Mining | 40.4 | 0 | 40.4 | 2026-01-16 02:06 | 2026-01-16 13:13 | 13562.7615 | [6 empty] | 13563 | 9445 | 0.95 | 0 | 0 | 15.09 | 5135
PH4100XPC#1 | GG\25\022\D | GG | 25 | 22 | D | 1 Prestrip - Thick | 100 | 42.3385 | 42.3385 | 2026-01-16 06:14 | 2026-01-18 01:16 | 100265.254 | 100265 | [7 empty] | 0 | 0 | 15.63 | 6.73 | 5796.41
TS5500Shv | RS\56\005\A | RS | 56 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-01-16 13:13 | 2026-01-17 00:23 | 13599.7209 | [6 empty] | 13600 | 9487 | 1.55 | 0 | 0 | 14.65 | 5170
TS5500Exc | RS\56\002\D | RS | 56 | 2 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-01-16 20:19 | 2026-01-17 20:31 | 30481.7397 | [6 empty] | 30482 | 22276 | 2.23 | 0 | 0 | 6.58 | 5842
TS Fleet 5 | RS\55\004\B | RS | 55 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-16 22:19 | 2026-01-17 11:01 | 24905.364 | 24905 | [7 empty] | 0 | 0 | 2.5 | 9.69 | 5517.24
TS5500Shv | RS\57\001\D | RS | 57 | 1 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-01-17 00:23 | 2026-01-17 23:47 | 28545.2248 | [6 empty] | 28545 | 20616 | 2.18 | 0 | 0 | 7.79 | 5735
TS Fleet 5 | RS\55\005\B | RS | 55 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-17 11:01 | 2026-01-17 19:21 | 16325.4333 | 16325 | [7 empty] | 0 | 0 | 2.7 | 10.41 | 5454.51
TS Fleet 5 | RS\59\004\B | RS | 59 | 4 | B | 1 Prestrip - Thick | 58.5674 | 58.5674 | 58.5674 | 2026-01-17 19:21 | 2026-01-20 20:31 | 143412.6207 | 143413 | [7 empty] | 0 | 0 | 14.69 | 11.73 | 5343.68
TS5500Exc | RS\55\004\B | RS | 55 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-01-17 20:31 | 2026-01-19 02:15 | 37449.4069 | [6 empty] | 37449 | 26481 | 2.66 | 0 | 0 | 9.69 | 5517
TS5500Shv | RS\57\002\D | RS | 57 | 2 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-01-17 23:47 | 2026-01-18 23:44 | 29208.3311 | [6 empty] | 29208 | 21295 | 2.13 | 0 | 0 | 6.66 | 5835
PH4100XPC#1 | W2\01\009\D | W2 | 1 | 9 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2026-01-18 01:16 | 2026-01-18 01:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\01\006\B | W2 | 1 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-18 01:16 | 2026-03-14 07:39 | 3122523.599 | 3122524 | [7 empty] | 0 | 0 | 59.78 | 10.57 | 5255.69
PH4100A | SC\48\024\D | SC | 48 | 24 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-18 13:13 | 2026-01-22 06:20 | 151606.9941 | 151607 | [7 empty] | 0 | 0 | 13.24 | 7.5 | 5754.24
TS5500Shv | GG\21\019\D | GG | 21 | 19 | D | 8 Coal Mining | 75.6 | 0 | 75.6 | 2026-01-18 23:44 | 2026-01-20 15:04 | 47953.4547 | [6 empty] | 47953 | 35708 | 3.57 | 0 | 0 | 7.05 | 5769
TS5500Exc | RS\55\005\B | RS | 55 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-01-19 02:15 | 2026-01-19 20:17 | 22711.6811 | [6 empty] | 22712 | 15993 | 2.66 | 0 | 0 | 10.41 | 5455
DRE1 | RS\55\004\D | RS | 55 | 4 | D | 6 DL | 100 | 100 | 100 | 2026-01-19 03:00 | 2026-01-22 22:30 | 319621.5145 |  |  |  | 16433 | 319622 | 257450 |  |  | 0 | 27.4 | 0 | 5.95 | 5897.4
DRE2 | GG\21\023\D | GG | 21 | 23 | D | 6 DL | 100 | 100 | 100 | 2026-01-19 04:50 | 2026-01-22 11:09 | 263472.3028 |  |  |  | 4969 | 263472 | 76805 |  |  | 0 | 14.63 | 0 | 6.52 | 5816.79
TS5500Exc | RS\56\004\A | RS | 56 | 4 | A | 8 Coal Mining | 59.6 | 0 | 59.6 | 2026-01-19 20:17 | 2026-01-20 12:11 | 20027.7619 | [6 empty] | 20028 | 13946 | 1.4 | 0 | 0 | 15.09 | 5135
TS5500Exc | RS\56\005\A | RS | 56 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-01-20 12:11 | 2026-01-20 23:20 | 14048.0634 | [6 empty] | 14048 | 9800 | 1.6 | 0 | 0 | 14.65 | 5170
TS5500Shv | RS\57\003\D | RS | 57 | 3 | D | 8 Coal Mining | 7.7 | 0 | 7.7 | 2026-01-20 15:04 | 2026-01-20 18:45 | 4487.5604 | [6 empty] | 4488 | 3284 | 0.33 | 0 | 0 | 5.99 | 5893
TS5500Shv | RS\57\004\A | RS | 57 | 4 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-01-20 18:45 | 2026-01-21 02:44 | 9745.3849 | [6 empty] | 9745 | 6759 | 0.68 | 0 | 0 | 15.92 | 5069
TS Fleet 5 | RS\56\004\B | RS | 56 | 4 | B | 1 Prestrip - Thick | 67.4055 | 67.4055 | 67.4055 | 2026-01-20 20:31 | 2026-01-21 05:14 | 17081.5941 | 17082 | [7 empty] | 0 | 0 | 1.72 | 10.03 | 5487.44
TS5500Exc | RS\57\001\D | RS | 57 | 1 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-01-20 23:20 | 2026-01-21 22:45 | 29486.2762 | [6 empty] | 29486 | 21296 | 2.26 | 0 | 0 | 7.79 | 5735
TS5500Shv | RS\57\005\A | RS | 57 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-01-21 02:44 | 2026-01-21 13:58 | 13697.88 | [6 empty] | 13698 | 9540 | 1.55 | 0 | 0 | 14.99 | 5142
TS Fleet 5 | RS\56\005\B | RS | 56 | 5 | B | 1 Prestrip - Thick | 64.6082 | 64.6082 | 64.6082 | 2026-01-21 05:14 | 2026-01-21 10:46 | 10852.2284 | 10852 | [7 empty] | 0 | 0 | 1.78 | 10.86 | 5414.7
TS Fleet 5 | RS\60\004\B | RS | 60 | 4 | B | 1 Prestrip - Thick | 57.6179 | 57.6179 | 57.6179 | 2026-01-21 10:46 | 2026-01-23 19:11 | 110581.4061 | 110581 | [7 empty] | 0 | 0 | 13.94 | 14.26 | 5138.25
TS5500Shv | GG\21\020\D | GG | 21 | 20 | D | 8 Coal Mining | 61.7 | 0 | 61.7 | 2026-01-21 13:58 | 2026-01-22 22:01 | 39077.2507 | [6 empty] | 39077 | 29145 | 2.91 | 0 | 0 | 6.92 | 5780
TS5500Exc | RS\57\002\D | RS | 57 | 2 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-01-21 22:45 | 2026-01-22 22:42 | 30171.2431 | [6 empty] | 30171 | 21997 | 2.2 | 0 | 0 | 6.66 | 5835
PH4100A | SC\49\024\D | SC | 49 | 24 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-22 06:20 | 2026-01-26 07:49 | 165400.179 | 165400 | [7 empty] | 0 | 0 | 14.11 | 7.37 | 5766.1
DRE2 | GG\23\012\B | GG | 23 | 12 | B | 6 DL | 100 | 0 | 100 | 2026-01-22 11:09 | 2026-01-25 00:06 | 204999.4539 |  |  |  |  | 204999 | 170833 |  |  | 0 | 17.03 | 0 | 11.6 | 5384.67
TS5500Shv | RS\58\004\B | RS | 58 | 4 | B | 1 Prestrip - Thick | 13.2055 | 13.2055 | 13.2055 | 2026-01-22 22:01 | 2026-01-24 07:47 | 34161.5139 | 34162 | [7 empty] | 0 | 0 | 3.5 | 10.81 | 5420
DRE1 | RS\55\005\D | RS | 55 | 5 | D | 6 DL | 100 | 100 | 100 | 2026-01-22 22:30 | 2026-01-25 00:45 | 175507.127 |  |  |  | 6330 | 175507 | 98789 |  |  | 0 | 29.47 | 0 | 6.04 | 5889.01
TS5500Exc | RS\57\003\D | RS | 57 | 3 | D | 8 Coal Mining | 92.3 | 0 | 92.3 | 2026-01-22 22:42 | 2026-01-24 17:42 | 54169.8397 | [6 empty] | 54170 | 39646 | 3.96 | 0 | 0 | 5.99 | 5893
TS Fleet 5 | RS\60\005\B | RS | 60 | 5 | B | 1 Prestrip - Thick | 74.5821 | 74.5821 | 74.5821 | 2026-01-23 19:11 | 2026-01-25 12:22 | 80713.3606 | 80713 | [7 empty] | 0 | 0 | 19.73 | 12.53 | 5269.68
TS5500Shv | RS\55\004\D | RS | 55 | 4 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-01-24 07:47 | 2026-01-25 07:37 | 29076.6406 | [6 empty] | 29077 | 21315 | 2.13 | 0 | 0 | 5.95 | 5897
TS5500Exc | RS\57\004\A | RS | 57 | 4 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-01-24 17:42 | 2026-01-25 01:42 | 10066.6614 | [6 empty] | 10067 | 6982 | 0.7 | 0 | 0 | 15.92 | 5069
DRE2 | GG\23\011\B | GG | 23 | 11 | B | 6 DL | 100 | 0 | 100 | 2026-01-25 00:06 | 2026-01-27 19:18 | 226049.1019 |  |  |  |  | 226049 | 173884 |  |  | 0 | 17.45 | 0 | 10.71 | 5469.7
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2026-01-25 00:45 | 2026-01-28 00:45
TS5500Exc | RS\57\005\A | RS | 57 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-01-25 01:42 | 2026-01-25 12:56 | 14149.4585 | [6 empty] | 14149 | 9855 | 1.6 | 0 | 0 | 14.99 | 5142
TS5500Shv | RS\57\004\B | RS | 57 | 4 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2026-01-25 07:37 | 2026-01-25 19:47 | 13026.4843 | 13026 | [7 empty] | 0 | 0 | 1.31 | 10.37 | 5457.86
TS Fleet 5 | W1\03\002\D | W1 | 3 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-25 12:22 | 2026-02-08 22:14 | 677884.6608 | 677885 | [7 empty] | 0 | 0 | 55.32 | 7.34 | 5628.47
TS5500Exc | RS\57\004\B | RS | 57 | 4 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2026-01-25 12:56 | 2026-01-26 01:05 | 10746.8496 | 10747 | [7 empty] | 0 | 0 | 1.08 | 10.37 | 5457.86
TS5500Shv | RS\55\005\D | RS | 55 | 5 | D | 7 PostStrip | 91.9763 | 0 | 91.9763 | 2026-01-25 19:47 | 2026-01-26 14:13 | 19759.3164 |  |  | 19759 | [5 empty] | 0 | 0 | 0 | 6.04 | 5889.01
TS5500Exc | RS\55\004\D | RS | 55 | 4 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-01-26 01:05 | 2026-01-27 00:55 | 30035.2112 | [6 empty] | 30035 | 22017 | 2.2 | 0 | 0 | 5.95 | 5897
PH4100A | SC\47\025\D | SC | 47 | 25 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-26 07:49 | 2026-01-30 16:19 | 177289.5844 | 177290 | [7 empty] | 0 | 0 | 15.52 | 7.24 | 5777.3
TS5500Shv | GG\21\021\D | GG | 21 | 21 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-01-26 14:13 | 2026-01-27 14:31 | 29650.2383 | [6 empty] | 29650 | 22131 | 2.21 | 0 | 0 | 6.81 | 5789
TS5500Exc | RS\57\004\B | RS | 57 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-01-27 00:55 | 2026-01-28 06:56 | 37806.4557 | [6 empty] | 37806 | 26661 | 2.68 | 0 | 0 | 10.37 | 5458
TS5500Shv | RS\58\004\B | RS | 58 | 4 | B | 8 Coal Mining | 7.7 | 0 | 7.7 | 2026-01-27 14:31 | 2026-01-27 16:48 | 2783.1304 | [6 empty] | 2783 | 1959 | 0.2 | 0 | 0 | 10.81 | 5420
TS5500Shv | RS\58\005\A | RS | 58 | 5 | A | 1 Prestrip - Thick | 15.0914 | 15.0914 | 15.0914 | 2026-01-27 16:48 | 2026-01-28 19:55 | 27404.5734 | 27405 | [7 empty] | 0 | 0 | 3.73 | 15.75 | 5080.62
DRE2 | GG\23\010\B | GG | 23 | 10 | B | 6 DL | 100 | 0 | 100 | 2026-01-27 19:18 | 2026-01-30 14:28 | 225942.6219 |  |  |  |  | 225943 | 188286 |  |  | 0 | 18.83 | 0 | 10.18 | 5518.02
DRE1 | RS\58\003\D | RS | 58 | 3 | D | 6 DL | 100 | 0 | 100 | 2026-01-28 00:45 | 2026-01-31 06:00 | 269894.4287 |  |  |  | 12076 | 269894 | 229440 |  |  | 0 | 24.35 | 0 | 6 | 5892.55
TS5500Exc | RS\55\005\D | RS | 55 | 5 | D | 7 PostStrip | 8.0237 | 0 | 8.0237 | 2026-01-28 06:56 | 2026-01-28 08:53 | 1723.741 |  |  | 1724 | [5 empty] | 0 | 0 | 0 | 6.04 | 5889.01
TS5500Exc | RS\55\005\D | RS | 55 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-01-28 08:53 | 2026-01-28 18:46 | 12451.4796 | [6 empty] | 12451 | 9134 | 2.17 | 0 | 0 | 6.04 | 5889
TS5500Exc | RS\58\004\B | RS | 58 | 4 | B | 8 Coal Mining | 92.3 | 0 | 92.3 | 2026-01-28 18:46 | 2026-01-29 21:22 | 33502.6007 | [6 empty] | 33503 | 23586 | 2.37 | 0 | 0 | 10.81 | 5420
TS5500Shv | RS\55\005\D | RS | 55 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-01-28 19:55 | 2026-01-29 05:48 | 12054.0919 | [6 empty] | 12054 | 8843 | 2.1 | 0 | 0 | 6.04 | 5889
TS5500Shv | RS\59\002\D | RS | 59 | 2 | D | 1 Prestrip - Thick | 15.7766 | 15.7766 | 15.7766 | 2026-01-29 05:48 | 2026-01-30 14:52 | 34291.7577 | 34292 | [7 empty] | 0 | 0 | 3.57 | 6.73 | 5828.63
TS5500Exc | RS\58\005\A | RS | 58 | 5 | A | 1 Prestrip - Thick | 13.2933 | 13.2933 | 13.2933 | 2026-01-29 21:22 | 2026-01-31 00:29 | 24139.5063 | 24140 | [7 empty] | 0 | 0 | 3.29 | 15.75 | 5080.62
DRE2 | GG\23\009\B | GG | 23 | 9 | B | 6 DL | 100 | 0 | 100 | 2026-01-30 14:28 | 2026-02-02 12:38 | 235998.101 |  |  |  |  | 235998 | 196665 |  |  | 0 | 19.67 | 0 | 10.09 | 5517.13
TS5500Shv | GG\21\022\D | GG | 21 | 22 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-01-30 14:52 | 2026-01-31 15:11 | 29663.3131 | [6 empty] | 29663 | 22158 | 2.22 | 0 | 0 | 6.73 | 5796
PH4100A | SC\48\025\D | SC | 48 | 25 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-01-30 16:19 | 2026-02-04 09:55 | 191751.1667 | 191751 | [7 empty] | 0 | 0 | 16.48 | 7.06 | 5793.31
TS5500Exc | RS\58\005\A | RS | 58 | 5 | A | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-01-31 00:29 | 2026-01-31 10:36 | 12744.838 | [6 empty] | 12745 | 8846 | 1.42 | 0 | 0 | 15.75 | 5081
DRE1 | RS\57\004\D | RS | 57 | 4 | D | 6 DL | 100 | 100 | 100 | 2026-01-31 06:00 | 2026-02-03 21:20 | 305065.5709 |  |  |  | 15685 | 305066 | 245725 |  |  | 0 | 26.15 | 0 | 5.93 | 5899.01
TS5500Exc | RS\59\002\D | RS | 59 | 2 | D | 1 Prestrip - Thick | 13.5051 | 13.5051 | 13.5051 | 2026-01-31 10:36 | 2026-02-01 19:39 | 29354.5049 | 29355 | [7 empty] | 0 | 0 | 3.06 | 6.73 | 5828.63
TS5500Shv | RS\58\005\A | RS | 58 | 5 | A | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-01-31 15:11 | 2026-02-01 01:18 | 12338.0878 | [6 empty] | 12338 | 8564 | 1.37 | 0 | 0 | 15.75 | 5081
TS5500Shv | RS\58\005\B | RS | 58 | 5 | B | 1 Prestrip - Thick | 54.7945 | 54.7945 | 54.7945 | 2026-02-01 01:18 | 2026-02-01 10:21 | 9704.2387 | 9704 | [7 empty] | 0 | 0 | 1.57 | 11.8 | 5332.94
TS5500Shv | RS\59\003\D | RS | 59 | 3 | D | 1 Prestrip - Thick | 8.8659 | 8.8659 | 8.8659 | 2026-02-01 10:21 | 2026-02-02 06:08 | 20501.6201 | 20502 | [7 empty] | 0 | 0 | 2.09 | 6.01 | 5891.77
TS5500Exc | RS\58\005\B | RS | 58 | 5 | B | 1 Prestrip - Thick | 45.2055 | 45.2055 | 45.2055 | 2026-02-01 19:39 | 2026-02-02 04:43 | 8005.9969 | 8006 | [7 empty] | 0 | 0 | 1.29 | 11.8 | 5332.94
TS5500Exc | RS\58\005\B | RS | 58 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-02-02 04:43 | 2026-02-02 14:14 | 11995.9426 | [6 empty] | 11996 | 8401 | 1.36 | 0 | 0 | 11.8 | 5333
TS5500Shv | RS\58\005\B | RS | 58 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-02-02 06:08 | 2026-02-02 15:39 | 11613.0934 | [6 empty] | 11613 | 8133 | 1.32 | 0 | 0 | 11.8 | 5333
DRE2 | GG\23\008\B | GG | 23 | 8 | B | 6 DL | 100 | 0 | 100 | 2026-02-02 12:38 | 2026-02-05 18:19 | 261305.291 |  |  |  |  | 261305 | 201004 |  |  | 0 | 20.1 | 0 | 10.21 | 5492.53
TS5500Exc | RS\59\003\D | RS | 59 | 3 | D | 1 Prestrip - Thick | 7.5915 | 7.5915 | 7.5915 | 2026-02-02 14:14 | 2026-02-03 10:00 | 17554.8133 | 17555 | [7 empty] | 0 | 0 | 1.79 | 6.01 | 5891.77
TS5500Shv | GG\21\023\D | GG | 21 | 23 | D | 7 PostStrip | 50.9554 | 0 | 50.9554 | 2026-02-02 15:39 | 2026-02-03 11:50 | 21628.9512 |  |  | 21629 | [5 empty] | 0 | 0 | 0 | 6.52 | 5816.79
TS5500Exc | RS\59\004\B | RS | 59 | 4 | B | 1 Prestrip - Thick | 27.6978 | 27.6978 | 27.6978 | 2026-02-03 10:00 | 2026-02-06 14:09 | 67823.0571 | 67823 | [7 empty] | 0 | 0 | 6.95 | 11.73 | 5343.68
TS5500Shv | RS\59\005\A | RS | 59 | 5 | A | 8 Coal Mining | 29.6 | 0 | 29.6 | 2026-02-03 11:50 | 2026-02-03 14:33 | 3317.7435 | [6 empty] | 3318 | 2300 | 0.36 | 0 | 0 | 16.44 | 5025
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 23:18 |  | 5d 23:18 | 2026-02-03 14:33 | 2026-02-09 13:51
DRE1 | RS\58\004\D | RS | 58 | 4 | D | 6 DL | 100 | 100 | 100 | 2026-02-03 21:20 | 2026-02-07 11:21 | 300439.9932 |  |  |  | 15447 | 300440 | 242000 |  |  | 0 | 25.75 | 0 | 5.93 | 5898.97
PH4100A | SC\49\025\D | SC | 49 | 25 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-02-04 09:55 | 2026-02-08 18:17 | 176472.5797 | 176473 | [7 empty] | 0 | 0 | 14.83 | 6.87 | 5809.74
DRE2 | GG\23\007\B | GG | 23 | 7 | B | 6 DL | 100 | 0 | 100 | 2026-02-05 18:19 | 2026-02-08 17:38 | 239911.8948 |  |  |  |  | 239912 | 199927 |  |  | 0 | 19.98 | 0 | 10.37 | 5460.57
TS5500Exc | RS\59\004\B | RS | 59 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-02-06 14:09 | 2026-02-07 12:18 | 27913.1923 | [6 empty] | 27913 | 19567 | 1.96 | 0 | 0 | 11.73 | 5344
DRE1 | RS\58\005\D | RS | 58 | 5 | D | 6 DL | 100 | 100 | 100 | 2026-02-07 11:21 | 2026-02-09 13:51 | 176390.1122 |  |  |  | 6392 | 176390 | 99396 |  |  | 0 | 28.98 | 0 | 6.03 | 5889.06
TS5500Exc | RS\57\004\D | RS | 57 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-02-07 12:18 | 2026-02-09 10:54 | 58698.2604 | [6 empty] | 58698 | 42960 | 4.3 | 0 | 0 | 5.93 | 5899
DRE2 | GG\23\006\B | GG | 23 | 6 | B | 6 DL | 100 | 0 | 100 | 2026-02-08 17:38 | 2026-02-11 23:00 | 260223.8285 |  |  |  |  | 260224 | 200172 |  |  | 0 | 20.05 | 0 | 10.2 | 5457.56
PH4100A | SC\47\026\D | SC | 47 | 26 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-02-08 18:17 | 2026-02-15 12:06 | 270073.9041 | 270074 | [7 empty] | 0 | 0 | 21.9 | 6.94 | 5804.21
TS Fleet 5 | RS\57\005\B | RS | 57 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-02-08 22:14 | 2026-02-09 07:02 | 17265.2068 | 17265 | [7 empty] | 0 | 0 | 2.81 | 11.35 | 5372.68
TS Fleet 5 | W1\03\003\D | W1 | 3 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-02-09 07:02 | 2026-02-10 19:01 | 70538.4092 | 70538 | [7 empty] | 0 | 0 | 8.8 | 7.5 | 5615.57
TS5500Exc | RS\57\005\B | RS | 57 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-02-09 10:54 | 2026-02-10 05:25 | 23321.2276 | [6 empty] | 23321 | 16355 | 2.68 | 0 | 0 | 11.35 | 5373
TS5500Shv | RS\58\005\D | RS | 58 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2026-02-09 13:51 | 2026-02-10 10:25 | 22054.0911 |  |  | 22054 | [5 empty] | 0 | 0 | 0 | 6.03 | 5889.06
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2026-02-09 13:51 | 2026-02-12 13:51
TS5500Exc | RS\58\001\D | RS | 58 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-02-10 05:25 | 2026-02-12 05:57 | 61124.3663 | [6 empty] | 61124 | 44075 | 4.36 | 0 | 0 | 7.87 | 5728
TS5500Shv | RS\58\005\D | RS | 58 | 5 | D | 8 Coal Mining | 26.3 | 0 | 26.3 | 2026-02-10 10:25 | 2026-02-10 15:44 | 6479.984 | [6 empty] | 6480 | 4749 | 1.1 | 0 | 0 | 6.03 | 5889
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 23:50 |  | 3d 23:50 | 2026-02-10 15:44 | 2026-02-14 15:34
TS Fleet 5 | W1\03\004\B | W1 | 3 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-02-10 19:01 | 2026-02-23 01:33 | 577267.1316 | 577267 | [7 empty] | 0 | 0 | 28.24 | 12.39 | 5005.9
DRE2 | GG\23\005\B | GG | 23 | 5 | B | 6 DL | 100 | 0 | 100 | 2026-02-11 23:00 | 2026-02-15 05:26 | 263862.6536 |  |  |  |  | 263863 | 202971 |  |  | 0 | 20.36 | 0 | 9.59 | 5496
TS5500Exc | RS\58\005\D | RS | 58 | 5 | D | 8 Coal Mining | 100 | 0 | 73.7 | 2026-02-12 05:57 | 2026-02-12 20:22 | 18167.6858 | [6 empty] | 18168 | 13316 | 3.08 | 0 | 0 | 6.03 | 5889
DRE1 | RS\57\005\D | RS | 57 | 5 | D | 6 DL | 100 | 100 | 100 | 2026-02-12 13:51 | 2026-02-14 15:34 | 173686.3078 |  |  |  | 6302 | 173686 | 97902 |  |  | 0 | 28.85 | 0 | 6.02 | 5890.23
TS5500Exc | RS\58\002\D | RS | 58 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-02-12 20:22 | 2026-02-14 19:22 | 59196.5083 | [6 empty] | 59197 | 43123 | 4.31 | 0 | 0 | 6.71 | 5831
TS5500Shv | RS\57\005\D | RS | 57 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2026-02-14 15:34 | 2026-02-15 11:57 | 21843.2132 |  |  | 21843 | [5 empty] | 0 | 0 | 0 | 6.02 | 5890.23
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2026-02-14 15:34 | 2026-02-17 15:34
TS5500Exc | RS\58\003\D | RS | 58 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-02-14 19:22 | 2026-02-16 18:17 | 59101.4147 | [6 empty] | 59101 | 43222 | 4.32 | 0 | 0 | 6 | 5893
DRE2 | GG\23\004\B | GG | 23 | 4 | B | 6 DL | 100 | 0 | 100 | 2026-02-15 05:26 | 2026-02-21 08:28 | 494563.8011 |  |  |  |  | 494564 | 235507 |  |  | 0 | 20.33 | 0 | 9.42 | 5516.42
TS5500Shv | GG\23\005\B | GG | 23 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-02-15 11:57 | 2026-02-17 02:57 | 47564.087 | [6 empty] | 47564 | 34968 | 3.49 | 0 | 0 | 9.59 | 5496
PH4100A | SC\48\026\D | SC | 48 | 26 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-02-15 12:06 | 2026-02-21 15:39 | 246746.6351 | 246747 | [7 empty] | 0 | 0 | 18.76 | 6.9 | 5807.72
TS5500Exc | RS\57\005\D | RS | 57 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-02-16 18:17 | 2026-02-17 13:51 | 24643.5378 | [6 empty] | 24644 | 18063 | 4.22 | 0 | 0 | 6.02 | 5890
TS6060#1 | RS\56\004\B | RS | 56 | 4 | B | 1 Prestrip - Thick | 89.0939 | 32.5945 | 32.5945 | 2026-02-16 20:53 | 2026-02-17 04:53 | 8259.9581 | 8260 | [7 empty] | 0 | 0 | 0.83 | 10.03 | 5487.44
TS5500Shv | RS\60\001\D | RS | 60 | 1 | D | 7 PostStrip | 54.7945 | 0 | 54.7945 | 2026-02-17 02:57 | 2026-02-20 20:25 | 95913.8194 |  |  | 95914 | [5 empty] | 0 | 0 | 0 | 7.87 | 5728.33
TS6060#1 | RS\56\005\B | RS | 56 | 5 | B | 1 Prestrip - Thick | 35.3918 | 35.3918 | 35.3918 | 2026-02-17 04:53 | 2026-02-17 10:39 | 5944.7639 | 5945 | [7 empty] | 0 | 0 | 0.98 | 10.86 | 5414.7
TS6060#1 | GG\21\021\D | GG | 21 | 21 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-02-17 10:39 | 2026-02-18 10:58 | 32908.5062 | [6 empty] | 32909 | 24563 | 2.46 | 0 | 0 | 6.81 | 5789
TS5500Exc | RS\56\004\B | RS | 56 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-02-17 13:51 | 2026-02-18 05:03 | 19145.4765 | [6 empty] | 19145 | 13520 | 1.36 | 0 | 0 | 10.03 | 5487
DRE1 | RS\59\001\D | RS | 59 | 1 | D | 6 DL | 100 | 0 | 100 | 2026-02-17 15:34 | 2026-02-22 09:34 | 398218.0075 |  |  |  | 22727 | 398218 | 301951 |  |  | 0 | 30 | 0 | 7.91 | 5723.83
TS5500Exc | RS\56\005\B | RS | 56 | 5 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-02-18 05:03 | 2026-02-18 14:19 | 11677.9472 | [6 empty] | 11678 | 8207 | 1.36 | 0 | 0 | 10.86 | 5415
TS6060#1 | GG\21\022\D | GG | 21 | 22 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-02-18 10:58 | 2026-02-19 11:17 | 32923.0179 | [6 empty] | 32923 | 24593 | 2.46 | 0 | 0 | 6.73 | 5796
TS5500Exc | RS\58\004\D | RS | 58 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-02-18 14:19 | 2026-02-20 12:41 | 58393.5046 | [6 empty] | 58394 | 42702 | 4.27 | 0 | 0 | 5.93 | 5899
TS6060#1 | GG\21\023\D | GG | 21 | 23 | D | 7 PostStrip | 49.0446 | 0 | 49.0446 | 2026-02-19 11:17 | 2026-02-20 07:28 | 20817.8655 |  |  | 20818 | [5 empty] | 0 | 0 | 0 | 6.52 | 5816.79
TS6060#1 | GG\21\023\D | GG | 21 | 23 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-02-20 07:28 | 2026-02-21 05:08 | 29330.0319 | [6 empty] | 29330 | 21980 | 2.59 | 0 | 0 | 6.52 | 5817
TS5500Exc | RS\59\005\A | RS | 59 | 5 | A | 8 Coal Mining | 70.4 | 0 | 70.4 | 2026-02-20 12:41 | 2026-02-20 18:56 | 7884.6361 | [6 empty] | 7885 | 5465 | 0.86 | 0 | 0 | 16.44 | 5025
TS5500Exc | RS\60\001\D | RS | 60 | 1 | D | 7 PostStrip | 45.2055 | 0 | 45.2055 | 2026-02-20 18:56 | 2026-02-24 12:25 | 79128.901 |  |  | 79129 | [5 empty] | 0 | 0 | 0 | 7.87 | 5728.33
TS5500Shv | RS\56\004\B | RS | 56 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-02-20 20:25 | 2026-02-21 11:37 | 18534.4507 | [6 empty] | 18534 | 13088 | 1.31 | 0 | 0 | 10.03 | 5487
TS6060#1 | GG\23\012\B | GG | 23 | 12 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-02-21 05:08 | 2026-02-22 17:08 | 48727.5778 | [6 empty] | 48728 | 35435 | 3.55 | 0 | 0 | 11.6 | 5385
DRE2 | GG\22\012\D | GG | 22 | 12 | D | 6 DL | 100 | 100 | 100 | 2026-02-21 08:28 | 2026-02-27 12:35 | 498240.752 |  |  |  | 11600 | 498241 | 220409 |  |  | 0 | 23.22 | 0 | 6.78 | 5791.68
TS5500Shv | RS\56\005\B | RS | 56 | 5 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-02-21 11:37 | 2026-02-21 20:54 | 11305.2468 | [6 empty] | 11305 | 7945 | 1.31 | 0 | 0 | 10.86 | 5415
PH4100A | SC\49\026\D | SC | 49 | 26 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-02-21 15:39 | 2026-02-26 14:10 | 199721.2502 | 199721 | [7 empty] | 0 | 0 | 15.23 | 6.86 | 5811.36
TS5500Shv | GG\21\023\D | GG | 21 | 23 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-02-21 20:54 | 2026-02-22 18:34 | 26426.0684 | [6 empty] | 26426 | 19804 | 2.33 | 0 | 0 | 6.52 | 5817
DRE1 | RS\56\004\D | RS | 56 | 4 | D | 6 DL | 100 | 100 | 100 | 2026-02-22 09:34 | 2026-02-26 02:54 | 312045.2351 |  |  |  | 16043 | 312045 | 251347 |  |  | 0 | 26.75 | 0 | 5.94 | 5898.26
TS6060#1 | GG\23\011\B | GG | 23 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-02-22 17:08 | 2026-02-24 05:19 | 48952.0016 | [6 empty] | 48952 | 35756 | 3.58 | 0 | 0 | 10.71 | 5470
TS5500Shv | GG\26\005\X1 | GG | 26 | 5 | X1 | 1 Prestrip - Thick | 29.0552 | 24.2943 | 24.2943 | 2026-02-22 18:34 | 2026-03-20 19:08 | 668884.7385 | 668885 | [7 empty] | 0 | 0 | 23.74 | 11.26 | 5275.02
TS Fleet 5 | GG\26\005\X1 | GG | 26 | 5 | X1 | 1 Prestrip - Thick | 49.2863 | 43.9649 | 43.9649 | 2026-02-23 01:33 | 2026-03-20 19:08 | 1210469.146 | 1210469 | [7 empty] | 0 | 0 | 42.96 | 11.26 | 5275.02
TS6060#1 | GG\23\008\B | GG | 23 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-02-24 05:19 | 2026-02-25 19:43 | 51977.6007 | [6 empty] | 51978 | 38035 | 3.8 | 0 | 0 | 10.21 | 5493
TS5500Exc | GG\26\005\X1 | GG | 26 | 5 | X1 | 1 Prestrip - Thick | 22.1894 | 18.7255 | 18.7255 | 2026-02-24 12:25 | 2026-03-20 19:08 | 515563.3124 | 515563 | [7 empty] | 0 | 0 | 18.3 | 11.26 | 5275.02
TS6060#1 | GG\23\009\B | GG | 23 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-02-25 19:43 | 2026-02-27 09:39 | 51332.7803 | [6 empty] | 51333 | 37585 | 3.76 | 0 | 0 | 10.09 | 5517
DRE1 | RS\56\005\D | RS | 56 | 5 | D | 6 DL | 100 | 100 | 100 | 2026-02-26 02:54 | 2026-02-28 04:26 | 173030.2822 |  |  |  | 6271 | 173030 | 97506 |  |  | 0 | 28.97 | 0 | 6.03 | 5890.18
PH4100A | SC\44\011\D | SC | 44 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-02-26 14:10 | 2026-03-10 11:55 | 514569.1484 | 514569 | [7 empty] | 0 | 0 | 34.23 | 7.49 | 5751.89
TS6060#1 | GG\23\007\B | GG | 23 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-02-27 09:39 | 2026-02-28 23:25 | 51118.1025 | [6 empty] | 51118 | 37371 | 3.74 | 0 | 0 | 10.37 | 5461
DRE2 | GG\22\011\D | GG | 22 | 11 | D | 6 DL | 100 | 100 | 100 | 2026-02-27 12:35 | 2026-03-05 17:35 | 501153.6676 |  |  |  | 9090 | 501154 | 218169 |  |  | 0 | 22.74 | 0 | 6.58 | 5807.11
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 3d 00:00 |  | 3d 00:00 | 2026-02-28 04:26 | 2026-03-03 04:26
TS6060#1 | GG\23\010\B | GG | 23 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-02-28 23:25 | 2026-03-02 12:10 | 49750.4314 | [6 empty] | 49750 | 36441 | 3.65 | 0 | 0 | 10.18 | 5518
TS6060#1 | GG\23\006\B | GG | 23 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-03-02 12:10 | 2026-03-04 00:45 | 49492.2288 | [6 empty] | 49492 | 36239 | 3.62 | 0 | 0 | 10.2 | 5458
DRE1 | RS\59\002\D | RS | 59 | 2 | D | 6 DL | 100 | 0 | 100 | 2026-03-03 04:26 | 2026-03-05 19:50 | 221450.1187 |  |  |  | 9908 | 221450 | 188257 |  |  | 0 | 20.37 | 0 | 6.73 | 5828.63
TS6060#1 | RS\59\005\B | RS | 59 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-03-04 00:45 | 2026-03-04 18:00 | 17800.2011 | 17800 | [7 empty] | 0 | 0 | 2.86 | 12.23 | 5295.79
TS6060#1 | RS\60\002\D | RS | 60 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-03-04 18:00 | 2026-04-04 04:13 | 725613.5947 | 725614 | [7 empty] | 0 | 0 | 36.09 | 6.79 | 5824.01
DRE2 | GG\22\010\D | GG | 22 | 10 | D | 6 DL | 100 | 100 | 100 | 2026-03-05 17:35 | 2026-03-11 08:58 | 455447.7175 |  |  |  | 10604 | 455448 | 201479 |  |  | 0 | 21.21 | 0 | 6.55 | 5810.1
DRE1 | RS\59\003\D | RS | 59 | 3 | D | 6 DL | 100 | 0 | 100 | 2026-03-05 19:50 | 2026-03-08 16:07 | 238523.6541 |  |  |  | 10672 | 238524 | 202772 |  |  | 0 | 21.52 | 0 | 6.01 | 5891.77
DRE1 | RS\59\004\D | RS | 59 | 4 | D | 6 DL | 100 | 100 | 100 | 2026-03-08 16:07 | 2026-03-12 05:49 | 299381.1864 |  |  |  | 15392 | 299381 | 241147 |  |  | 0 | 25.66 | 0 | 5.94 | 5897.54
PH4100A | SC\44\012\D | SC | 44 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-03-10 11:55 | 2026-03-19 14:50 | 396703.9486 | 396704 | [7 empty] | 0 | 0 | 35.02 | 7.43 | 5756.28
DRE2 | GG\22\009\D | GG | 22 | 9 | D | 6 DL | 100 | 100 | 100 | 2026-03-11 08:58 | 2026-03-16 19:04 | 437581.2923 |  |  |  | 10188 | 437581 | 193575 |  |  | 0 | 20.38 | 0 | 6.52 | 5813.06
DRE1 | In Path Delay | In Path Delay |  |  |  | 102 Deadheading | 7d 00:00 |  | 7d 00:00 | 2026-03-12 05:49 | 2026-03-19 05:49
PH4100XPC#1 | GG\26\005\X1 | GG | 26 | 5 | X1 | 1 Prestrip - Thick | 100 | 13.0153 | 13.0153 | 2026-03-14 07:39 | 2026-03-20 19:08 | 358345.0584 | 358345 | [7 empty] | 0 | 0 | 12.72 | 11.26 | 5275.02
DRE2 | GG\22\008\D | GG | 22 | 8 | D | 6 DL | 100 | 100 | 100 | 2026-03-16 19:04 | 2026-03-22 02:17 | 427926.6989 |  |  |  | 7969 | 427927 | 191252 |  |  | 0 | 19.92 | 0 | 6.55 | 5810.86
DRE1 | SC\40\014\D | SC | 40 | 14 | D | 6 DL | 100 | 0 | 100 | 2026-03-19 05:49 | 2026-03-26 21:43 | 642368.8179 |  |  |  | 48849 | 642369 | 439644 |  |  | 0 | 40 | 0 | 7.59 | 5742.6
PH4100A | SC\44\013\D | SC | 44 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-03-19 14:50 | 2026-03-26 10:05 | 289546.6422 | 289547 | [7 empty] | 0 | 0 | 25.3 | 7.44 | 5755.9
TS5500Shv | RS\56\005\D | RS | 56 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2026-03-20 19:08 | 2026-03-21 15:20 | 21647.8507 |  |  | 21648 | [5 empty] | 0 | 0 | 0 | 6.03 | 5890.18
TS Fleet 5 | GG\26\006\X1 | GG | 26 | 6 | X1 | 1 Prestrip - Thick | 52.6521 | 46.4992 | 46.4992 | 2026-03-20 19:08 | 2026-03-30 02:42 | 438183.8611 | 438184 | [7 empty] | 0 | 0 | 44.91 | 11.65 | 5266.6
PH4100XPC#1 | GG\26\006\X1 | GG | 26 | 6 | X1 | 1 Prestrip - Thick | 100 | 53.5008 | 53.5008 | 2026-03-20 19:08 | 2026-03-30 02:42 | 504162.2839 | 504162 | [7 empty] | 0 | 0 | 51.67 | 11.65 | 5266.6
TS5500Exc | RS\59\002\D | RS | 59 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-03-20 19:08 | 2026-03-22 18:38 | 59829.7268 | [6 empty] | 59830 | 43519 | 4.35 | 0 | 0 | 6.73 | 5829
TS5500Shv | RS\56\004\D | RS | 56 | 4 | D | 8 Coal Mining | 2.4 | 0 | 2.4 | 2026-03-21 15:20 | 2026-03-21 16:28 | 1396.0577 | [6 empty] | 1396 | 1023 | 0.1 | 0 | 0 | 5.94 | 5898
TS5500Shv | RS\56\005\D | RS | 56 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-03-21 16:28 | 2026-03-22 02:24 | 12107.506 | [6 empty] | 12108 | 8875 | 2.09 | 0 | 0 | 6.03 | 5890
DRE2 | GG\22\007\D | GG | 22 | 7 | D | 6 DL | 100 | 100 | 100 | 2026-03-22 02:17 | 2026-03-27 10:10 | 430195.025 |  |  |  | 10016 | 430195 | 190307 |  |  | 0 | 20.03 | 0 | 6.59 | 5806.64
TS5500Shv | GG\23\004\B | GG | 23 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-03-22 02:24 | 2026-03-24 04:46 | 61413.116 | [6 empty] | 61413 | 45168 | 4.16 | 0 | 0 | 9.42 | 5516
TS5500Exc | W2\01\006\B | W2 | 1 | 6 | B | 8 Coal Mining | 38.5 | 0 | 38.5 | 2026-03-22 18:38 | 2026-03-24 04:18 | 42399.2314 | [6 empty] | 42399 | 29700 | 0.72 | 0 | 0 | 10.57 | 5256
TS5500Exc | RS\56\004\D | RS | 56 | 4 | D | 8 Coal Mining | 97.6 | 0 | 97.6 | 2026-03-24 04:18 | 2026-03-26 01:58 | 57519.5307 | [6 empty] | 57520 | 42131 | 4.21 | 0 | 0 | 5.94 | 5898
TS5500Shv | GG\22\012\D | GG | 22 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-03-24 04:46 | 2026-03-26 08:00 | 62465.6947 | [6 empty] | 62466 | 46662 | 4.67 | 0 | 0 | 6.78 | 5792
TS5500Exc | RS\56\005\D | RS | 56 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-03-26 01:58 | 2026-03-26 11:53 | 12506.6545 | [6 empty] | 12507 | 9167 | 2.16 | 0 | 0 | 6.03 | 5890
TS5500Shv | GG\26\005\X1 | GG | 26 | 5 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-03-26 08:00 | 2026-03-27 16:49 | 40027.654 | [6 empty] | 40028 | 29590 | 1.06 | 0 | 0 | 11.26 | 5275
PH4100A | SC\44\014\D | SC | 44 | 14 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-03-26 10:05 | 2026-03-31 16:00 | 221214.3254 | 221214 | [7 empty] | 0 | 0 | 18.92 | 7.46 | 5753.6
TS5500Exc | RS\59\001\D | RS | 59 | 1 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-03-26 11:53 | 2026-03-27 13:49 | 32668.3188 | [6 empty] | 32668 | 23537 | 2.19 | 0 | 0 | 7.91 | 5724
DRE1 | SC\40\013\D | SC | 40 | 13 | D | 6 DL | 100 | 0 | 100 | 2026-03-26 21:43 | 2026-04-03 13:21 | 641435.8086 |  |  |  | 48778 | 641436 | 439005 |  |  | 0 | 40 | 0 | 7.52 | 5750.14
DRE2 | GG\22\006\D | GG | 22 | 6 | D | 6 DL | 100 | 100 | 100 | 2026-03-27 10:10 | 2026-04-01 17:17 | 427558.0098 |  |  |  | 7962 | 427558 | 191087 |  |  | 0 | 19.9 | 0 | 6.64 | 5801.83
TS5500Exc | RS\59\003\D | RS | 59 | 3 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-03-27 13:49 | 2026-03-28 13:51 | 30258.3041 | [6 empty] | 30258 | 22112 | 2.21 | 0 | 0 | 6.01 | 5892
TS5500Shv | GG\22\011\D | GG | 22 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-03-27 16:49 | 2026-03-29 18:31 | 60612.0283 | [6 empty] | 60612 | 45384 | 4.54 | 0 | 0 | 6.58 | 5807
TS5500Exc | RS\59\004\D | RS | 59 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-03-28 13:51 | 2026-03-30 11:52 | 57969.5908 | [6 empty] | 57970 | 42391 | 4.24 | 0 | 0 | 5.94 | 5898
TS5500Shv | RS\59\001\D | RS | 59 | 1 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-03-29 18:31 | 2026-03-30 20:28 | 31625.7128 | [6 empty] | 31626 | 22785 | 2.12 | 0 | 0 | 7.91 | 5724
TS Fleet 5 | GG\26\007\X1 | GG | 26 | 7 | X1 | 1 Prestrip - Thick | 39.0862 | 39.0862 | 39.0862 | 2026-03-30 02:42 | 2026-04-06 16:12 | 355755.0782 | 355755 | [7 empty] | 0 | 0 | 33.83 | 12.46 | 5236.03
PH4100XPC#1 | GG\26\005\B | GG | 26 | 5 | B | 1 Prestrip - Thick | 100 | 96.0756 | 96.0756 | 2026-03-30 02:42 | 2026-04-07 01:12 | 431186.6703 | 431187 | [7 empty] | 0 | 0 | 16.26 | 10.51 | 5449.21
TS5500Exc | GG\26\007\X1 | GG | 26 | 7 | X1 | 1 Prestrip - Thick | 14.5958 | 14.5958 | 14.5958 | 2026-03-30 11:52 | 2026-04-05 17:57 | 132848.5331 | 132849 | [7 empty] | 0 | 0 | 12.63 | 12.46 | 5236.03
TS5500Shv | GG\26\006\X1 | GG | 26 | 6 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-03-30 20:28 | 2026-03-31 09:17 | 15642.7947 | [6 empty] | 15643 | 11513 | 1.15 | 0 | 0 | 11.65 | 5267
TS5500Shv | RS\59\003\D | RS | 59 | 3 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-03-31 09:17 | 2026-04-01 09:19 | 29292.6135 | [6 empty] | 29293 | 21406 | 2.14 | 0 | 0 | 6.01 | 5892
PH4100A | SC\44\015\D | SC | 44 | 15 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-03-31 16:00 | 2026-04-05 06:22 | 194855.9717 | 194856 | [7 empty] | 0 | 0 | 16.04 | 7.43 | 5755.65
TS5500Shv | GG\22\010\D | GG | 22 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-04-01 09:19 | 2026-04-03 10:52 | 60434.7528 | [6 empty] | 60435 | 45251 | 4.53 | 0 | 0 | 6.55 | 5810
DRE2 | GG\22\005\D | GG | 22 | 5 | D | 6 DL | 100 | 100 | 100 | 2026-04-01 17:17 | 2026-04-06 22:15 | 420364.1401 |  |  |  | 7828 | 420364 | 187872 |  |  | 0 | 19.56 | 0 | 6.69 | 5797.46
TS5500Shv | GG\26\006\B | GG | 26 | 6 | B | 1 Prestrip - Thick | 8.9267 | 8.9267 | 8.9267 | 2026-04-03 10:52 | 2026-04-03 23:43 | 13765.8278 | 13766 | [7 empty] | 0 | 0 | 1.38 | 10.69 | 5433.79
DRE1 | SC\40\012\D | SC | 40 | 12 | D | 6 DL | 100 | 0 | 100 | 2026-04-03 13:21 | 2026-04-11 03:27 | 636124.7718 |  |  |  | 48375 | 636125 | 435371 |  |  | 0 | 40 | 0 | 7.47 | 5755.83
TS5500Shv | GG\26\007\X1 | GG | 26 | 7 | X1 | 1 Prestrip - Thick | 17.5431 | 17.5431 | 17.5431 | 2026-04-03 23:43 | 2026-04-10 05:47 | 159674.2884 | 159674 | [7 empty] | 0 | 0 | 15.18 | 12.46 | 5236.03
TS6060#1 | W2\01\006\B | W2 | 1 | 6 | B | 8 Coal Mining | 61.5 | 0 | 61.5 | 2026-04-04 04:13 | 2026-04-06 06:15 | 67728.4405 | [6 empty] | 67728 | 47443 | 1.15 | 0 | 0 | 10.57 | 5256
PH4100A | SC\44\016\D | SC | 44 | 16 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-04-05 06:22 | 2026-04-12 16:19 | 319016.638 | 319017 | [7 empty] | 0 | 0 | 21.99 | 7.38 | 5760.94
TS5500Exc | GG\26\006\B | GG | 26 | 6 | B | 1 Prestrip - Thick | 7.3645 | 7.3645 | 7.3645 | 2026-04-05 17:57 | 2026-04-06 06:47 | 11356.8079 | 11357 | [7 empty] | 0 | 0 | 1.14 | 10.69 | 5433.79
TS6060#1 | GG\22\009\D | GG | 22 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-04-06 06:15 | 2026-04-08 03:44 | 61544.7257 | [6 empty] | 61545 | 46083 | 4.61 | 0 | 0 | 6.52 | 5813
TS5500Exc | SC\40\015\D | SC | 40 | 15 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-04-06 06:47 | 2026-04-09 01:18 | 83776.2661 | [6 empty] | 83776 | 62701 | 3.89 | 0 | 0 | 7.38 | 5759
TS Fleet 5 | GG\26\005\B | GG | 26 | 5 | B | 1 Prestrip - Thick | 45.419 | 3.9244 | 3.9244 | 2026-04-06 16:12 | 2026-04-07 01:12 | 17612.8946 | 17613 | [7 empty] | 0 | 0 | 0.66 | 10.51 | 5449.21
DRE2 | GG\22\004\D | GG | 22 | 4 | D | 6 DL | 100 | 100 | 100 | 2026-04-06 22:15 | 2026-04-12 21:10 | 480774.2749 |  |  |  | 7861 | 480774 | 138292 |  |  | 0 | 19.51 | 0 | 6.64 | 5801.99
TS Fleet 5 | GG\26\006\B | GG | 26 | 6 | B | 1 Prestrip - Thick | 38.0197 | 38.0197 | 38.0197 | 2026-04-07 01:12 | 2026-04-08 07:06 | 58630.0577 | 58630 | [7 empty] | 0 | 0 | 5.87 | 10.69 | 5433.79
PH4100XPC#1 | GG\26\006\B | GG | 26 | 6 | B | 1 Prestrip - Thick | 100 | 45.6891 | 45.6891 | 2026-04-07 01:12 | 2026-04-08 08:19 | 70457.109 | 70457 | [7 empty] | 0 | 0 | 7.06 | 10.69 | 5433.79
TS6060#1 | GG\22\008\D | GG | 22 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-04-08 03:44 | 2026-04-10 01:14 | 61590.8002 | [6 empty] | 61591 | 46081 | 4.61 | 0 | 0 | 6.55 | 5811
TS Fleet 5 | GG\26\008\X1 | GG | 26 | 8 | X1 | 1 Prestrip - Thick | 45.3489 | 45.3489 | 45.3489 | 2026-04-08 07:06 | 2026-04-16 07:32 | 377173.039 | 377173 | [7 empty] | 0 | 0 | 41.16 | 13.44 | 5186.55
PH4100XPC#1 | GG\26\007\X1 | GG | 26 | 7 | X1 | 1 Prestrip - Thick | 100 | 28.7748 | 28.7748 | 2026-04-08 08:19 | 2026-04-13 05:39 | 261902.9656 | 261903 | [7 empty] | 0 | 0 | 24.9 | 12.46 | 5236.03
TS5500Exc | RS\59\005\B | RS | 59 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-04-09 01:18 | 2026-04-09 20:15 | 23865.7392 | [6 empty] | 23866 | 16680 | 2.7 | 0 | 0 | 12.23 | 5296
TS5500Exc | RS\60\001\D | RS | 60 | 1 | D | 8 Coal Mining | 27 | 0 | 27 | 2026-04-09 20:15 | 2026-04-11 18:09 | 57820.2194 | [6 empty] | 57820 | 41667 | 1.17 | 0 | 0 | 7.87 | 5728
TS6060#1 | RS\60\003\D | RS | 60 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-04-10 01:14 | 2026-05-02 17:14 | 544508.5557 | 544509 | [7 empty] | 0 | 0 | 41.48 | 6.08 | 5886.05
TS5500Shv | RS\60\001\D | RS | 60 | 1 | D | 8 Coal Mining | 73 | 0 | 73 | 2026-04-10 05:47 | 2026-04-15 14:06 | 156465.8905 | [6 empty] | 156466 | 112753 | 3.15 | 0 | 0 | 7.87 | 5728
DRE1 | RS\59\005\D | RS | 59 | 5 | D | 6 DL | 100 | 100 | 100 | 2026-04-11 03:27 | 2026-04-13 06:42 | 179022.0375 |  |  |  | 6479 | 179022 | 100850 |  |  | 0 | 29.11 | 0 | 6.05 | 5887.74
TS5500Exc | GG\26\009\X1 | GG | 26 | 9 | X1 | 1 Prestrip - Thick | 17.4113 | 17.4113 | 17.4113 | 2026-04-11 18:09 | 2026-04-18 18:18 | 148899.6856 | 148900 | [7 empty] | 0 | 0 | 12.67 | 14.26 | 5142.05
PH4100A | SC\44\017\D | SC | 44 | 17 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-04-12 16:19 | 2026-04-24 07:35 | 506242.8541 | 506243 | [7 empty] | 0 | 0 | 37.31 | 7.29 | 5761.38
DRE2 | GG\23\013\B | GG | 23 | 13 | B | 6 DL | 100 | 0 | 100 | 2026-04-12 21:10 | 2026-04-15 08:58 | 201103.2191 |  |  |  |  | 201103 | 167586 |  |  | 0 | 16.67 | 0 | 12.18 | 5321.24
PH4100XPC#1 | GG\26\008\X1 | GG | 26 | 8 | X1 | 1 Prestrip - Thick | 100 | 54.6511 | 54.6511 | 2026-04-13 05:39 | 2026-04-21 13:54 | 454541.5207 | 454542 | [7 empty] | 0 | 0 | 49.6 | 13.44 | 5186.55
DRE1 | SC\40\011\D | SC | 40 | 11 | D | 6 DL | 100 | 0 | 100 | 2026-04-13 06:42 | 2026-04-20 19:11 | 630442.895 |  |  |  | 47942 | 630443 | 431482 |  |  | 0 | 40 | 0 | 7.58 | 5746.88
DRE2 | GG\23\014\B | GG | 23 | 14 | B | 6 DL | 100 | 0 | 100 | 2026-04-15 08:58 | 2026-04-18 05:54 | 231911.1972 |  |  |  |  | 231911 | 193259 |  |  | 0 | 16.24 | 0 | 12.75 | 5270.06
TS5500Shv | GG\26\007\X1 | GG | 26 | 7 | X1 | 8 Coal Mining | 22.1 | 0 | 22.1 | 2026-04-15 14:06 | 2026-04-15 17:09 | 3715.625 | [6 empty] | 3716 | 2712 | 0.27 | 0 | 0 | 12.46 | 5236
TS5500Shv | GG\22\007\D | GG | 22 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-04-15 17:09 | 2026-04-17 19:20 | 61202.822 | [6 empty] | 61203 | 45790 | 4.58 | 0 | 0 | 6.59 | 5807
TS Fleet 5 | GG\26\009\X1 | GG | 26 | 9 | X1 | 1 Prestrip - Thick | 37.0343 | 37.0343 | 37.0343 | 2026-04-16 07:32 | 2026-04-23 01:08 | 316712.815 | 316713 | [7 empty] | 0 | 0 | 26.96 | 14.26 | 5142.05
TS5500Shv | RS\59\005\D | RS | 59 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2026-04-17 19:20 | 2026-04-18 16:06 | 22260.4268 |  |  | 22260 | [5 empty] | 0 | 0 | 0 | 6.05 | 5887.74
DRE2 | GG\23\018\B | GG | 23 | 18 | B | 6 DL | 100 | 0 | 100 | 2026-04-18 05:54 | 2026-04-20 17:32 | 200573.4674 |  |  |  |  | 200573 | 167145 |  |  | 0 | 16.59 | 0 | 12.93 | 5273.11
TS5500Shv | GG\22\006\D | GG | 22 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-04-18 16:06 | 2026-04-20 17:53 | 60704.1738 | [6 empty] | 60704 | 45453 | 4.54 | 0 | 0 | 6.64 | 5802
TS5500Exc | SC\40\014\D | SC | 40 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-04-18 18:18 | 2026-04-20 22:04 | 65213.8226 | [6 empty] | 65214 | 48810 | 4.07 | 0 | 0 | 7.59 | 5743
DRE2 | GG\23\019\B | GG | 23 | 19 | B | 6 DL | 100 | 0 | 100 | 2026-04-20 17:32 | 2026-04-23 06:47 | 206021.9449 |  |  |  |  | 206022 | 171685 |  |  | 0 | 17.21 | 0 | 13.32 | 5263.07
TS5500Shv | GG\22\005\D | GG | 22 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-04-20 17:53 | 2026-04-22 19:15 | 60189.9692 | [6 empty] | 60190 | 45104 | 4.51 | 0 | 0 | 6.69 | 5797
DRE1 | SC\40\010\D | SC | 40 | 10 | D | 6 DL | 100 | 0 | 100 | 2026-04-20 19:11 | 2026-05-01 01:09 | 859197.188 |  |  |  | 48253 | 859197 | 373984 |  |  | 0 | 40 | 0 | 7.72 | 5735.86
TS5500Exc | RS\59\005\D | RS | 59 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-04-20 22:04 | 2026-04-21 17:39 | 24670.3814 | [6 empty] | 24670 | 18081 | 4.15 | 0 | 0 | 6.05 | 5888
PH4100XPC#1 | GG\26\009\X1 | GG | 26 | 9 | X1 | 1 Prestrip - Thick | 100 | 45.5544 | 45.5544 | 2026-04-21 13:54 | 2026-04-28 14:03 | 389575.8108 | 389576 | [7 empty] | 0 | 0 | 33.16 | 14.26 | 5142.05
TS5500Exc | GG\26\010\X1 | GG | 26 | 10 | X1 | 1 Prestrip - Thick | 12.081 | 12.081 | 12.081 | 2026-04-21 17:39 | 2026-04-25 23:18 | 89977.2101 | 89977 | [7 empty] | 0 | 0 | 9.59 | 14.54 | 5134.7
TS5500Shv | GG\26\008\X1 | GG | 26 | 8 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-04-22 19:15 | 2026-04-23 09:57 | 17933.3424 | [6 empty] | 17933 | 12969 | 1.3 | 0 | 0 | 13.44 | 5187
TS Fleet 5 | GG\26\010\X1 | GG | 26 | 10 | X1 | 1 Prestrip - Thick | 39.3278 | 39.3278 | 39.3278 | 2026-04-23 01:08 | 2026-04-29 06:34 | 292906.0416 | 292906 | [7 empty] | 0 | 0 | 31.22 | 14.54 | 5134.7
DRE2 | GG\23\020\B | GG | 23 | 20 | B | 6 DL | 100 | 0 | 100 | 2026-04-23 06:47 | 2026-04-26 20:28 | 288219.9131 |  |  |  |  | 288220 | 221708 |  |  | 0 | 21.92 | 0 | 16.2 | 5049.99
TS5500Shv | GG\26\008\X2 | GG | 26 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2026-04-23 09:57 | 2026-04-26 08:01 | 75106.16 | 75106 | [7 empty] | 0 | 0 | 7.51 | 0 | 0
PH4100A | SC\46\018\D | SC | 46 | 18 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-04-24 07:35 | 2026-05-10 10:04 | 678225.3794 | 678225 | [7 empty] | 0 | 0 | 35.65 | 7.07 | 5789.77
TS5500Exc | SC\40\013\D | SC | 40 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-04-25 23:18 | 2026-04-28 06:22 | 69374.3756 | [6 empty] | 69374 | 51761 | 4.31 | 0 | 0 | 7.52 | 5750
TS5500Shv | GG\22\004\D | GG | 22 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2026-04-26 08:01 | 2026-04-28 07:01 | 50377.7702 |  |  | 50378 | [5 empty] | 0 | 0 | 0 | 6.64 | 5801.99
DRE2 | GG\23\022\B | GG | 23 | 22 | B | 6 DL | 100 | 0 | 100 | 2026-04-26 20:28 | 2026-04-29 23:35 | 252708.4543 |  |  |  |  | 252708 | 194391 |  |  | 0 | 23.2 | 0 | 19.72 | 4784.01
TS5500Exc | GG\26\011\X1 | GG | 26 | 11 | X1 | 1 Prestrip - Thick | 12.5479 | 12.5479 | 12.5479 | 2026-04-28 06:22 | 2026-05-02 02:17 | 81344.6224 | 81345 | [7 empty] | 0 | 0 | 10.14 | 14.76 | 5121.56
TS5500Shv | GG\22\004\D | GG | 22 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-04-28 07:01 | 2026-04-30 08:12 | 59979.7277 | [6 empty] | 59980 | 44946 | 4.5 | 0 | 0 | 6.64 | 5802
PH4100XPC#1 | GG\26\008\B | GG | 26 | 8 | B | 1 Prestrip - Thick | 100 | 77.5194 | 77.5194 | 2026-04-28 14:03 | 2026-04-29 14:53 | 56236.9159 | 56237 | [7 empty] | 0 | 0 | 5.62 | 10.36 | 5484.34
TS Fleet 5 | GG\26\008\B | GG | 26 | 8 | B | 1 Prestrip - Thick | 45.419 | 22.4806 | 22.4806 | 2026-04-29 06:34 | 2026-04-29 14:53 | 16308.6897 | 16309 | [7 empty] | 0 | 0 | 1.63 | 10.36 | 5484.34
TS Fleet 5 | GG\26\011\X1 | GG | 26 | 11 | X1 | 1 Prestrip - Thick | 39.3678 | 39.3678 | 39.3678 | 2026-04-29 14:53 | 2026-05-05 01:06 | 255210.1556 | 255210 | [7 empty] | 0 | 0 | 31.81 | 14.76 | 5121.56
PH4100XPC#1 | GG\26\010\X1 | GG | 26 | 10 | X1 | 1 Prestrip - Thick | 100 | 48.5911 | 48.5911 | 2026-04-29 14:53 | 2026-05-06 02:24 | 361897.2357 | 361897 | [7 empty] | 0 | 0 | 38.58 | 14.54 | 5134.7
DRE2 | GG\22\013\D | GG | 22 | 13 | D | 6 DL | 100 | 100 | 100 | 2026-04-29 23:35 | 2026-05-06 05:36 | 504606.2814 |  |  |  | 11749 | 504606 | 223225 |  |  | 0 | 23.51 | 0 | 7.01 | 5772.03
TS5500Shv | GG\26\009\X1 | GG | 26 | 9 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-04-30 08:12 | 2026-04-30 22:47 | 17792.6368 | [6 empty] | 17793 | 12785 | 1.28 | 0 | 0 | 14.26 | 5142
TS5500Shv | GG\26\009\X2 | GG | 26 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2026-04-30 22:47 | 2026-05-03 15:20 | 69194.657 | 69195 | [7 empty] | 0 | 0 | 6.92 | 0 | 0
DRE1 | SC\40\017\D | SC | 40 | 17 | D | 6 DL | 100 | 0 | 100 | 2026-05-01 01:09 | 2026-05-09 03:49 | 679977.11 |  |  |  | 51709 | 679977 | 465384 |  |  | 0 | 40 | 0 | 6.37 | 5794.15
TS5500Exc | SC\40\012\D | SC | 40 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-05-02 02:17 | 2026-05-04 12:30 | 73336.3603 | [6 empty] | 73336 | 54634 | 4.55 | 0 | 0 | 7.47 | 5756
TS6060#1 | GG\26\007\X1 | GG | 26 | 7 | X1 | 8 Coal Mining | 77.9 | 0 | 77.9 | 2026-05-02 17:14 | 2026-05-03 02:54 | 13097.3222 | [6 empty] | 13097 | 9559 | 0.96 | 0 | 0 | 12.46 | 5236
TS6060#1 | GG\23\019\B | GG | 23 | 19 | B | 8 Coal Mining | 29 | 0 | 29 | 2026-05-03 02:54 | 2026-05-03 13:38 | 14524.5056 | [6 empty] | 14525 | 10447 | 1.04 | 0 | 0 | 13.32 | 5263
TS6060#1 | RS\60\004\B | RS | 60 | 4 | B | 1 Prestrip - Thick | 42.3821 | 42.3821 | 42.3821 | 2026-05-03 13:38 | 2026-05-07 00:43 | 81340.596 | 81341 | [7 empty] | 0 | 0 | 10.26 | 14.26 | 5138.25
TS5500Shv | GG\26\009\B | GG | 26 | 9 | B | 1 Prestrip - Thick | 41.6232 | 41.6232 | 41.6232 | 2026-05-03 15:20 | 2026-05-04 23:02 | 33981.5566 | 33982 | [7 empty] | 0 | 0 | 3.39 | 10.27 | 5504.43
TS5500Exc | GG\26\007\B | GG | 26 | 7 | B | 1 Prestrip - Thick | 7.6469 | 7.6469 | 7.6469 | 2026-05-04 12:30 | 2026-05-05 01:34 | 11556.5537 | 11557 | [7 empty] | 0 | 0 | 1.15 | 10.55 | 5455.86
TS5500Shv | GG\23\013\B | GG | 23 | 13 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-05-04 23:02 | 2026-05-06 14:58 | 48688.0105 | [6 empty] | 48688 | 35318 | 3.52 | 0 | 0 | 12.18 | 5321
TS Fleet 5 | GG\26\007\B | GG | 26 | 7 | B | 1 Prestrip - Thick | 45.2107 | 45.2107 | 45.2107 | 2026-05-05 01:06 | 2026-05-06 11:58 | 68325.9916 | 68326 | [7 empty] | 0 | 0 | 6.83 | 10.55 | 5455.86
TS5500Exc | GG\26\012\X1 | GG | 26 | 12 | X1 | 1 Prestrip - Thick | 9.5037 | 9.5037 | 9.5037 | 2026-05-05 01:34 | 2026-05-07 09:35 | 49592.1526 | 49592 | [7 empty] | 0 | 0 | 5.72 | 14.92 | 5106.84
PH4100XPC#1 | GG\26\007\B | GG | 26 | 7 | B | 1 Prestrip - Thick | 100 | 47.1424 | 47.1424 | 2026-05-06 02:24 | 2026-05-07 09:52 | 71245.2474 | 71245 | [7 empty] | 0 | 0 | 7.12 | 10.55 | 5455.86
DRE2 | GG\22\014\B | GG | 22 | 14 | B | 6 DL | 100 | 0 | 100 | 2026-05-06 05:36 | 2026-05-08 17:43 | 202196.6755 |  |  |  |  | 202197 | 168497 |  |  | 0 | 16.24 | 0 | 12.56 | 5289.84
TS Fleet 5 | GG\26\009\B | GG | 26 | 9 | B | 1 Prestrip - Thick | 36.0899 | 36.0899 | 36.0899 | 2026-05-06 11:58 | 2026-05-07 03:00 | 29464.1543 | 29464 | [7 empty] | 0 | 0 | 2.94 | 10.27 | 5504.43
TS5500Shv | GG\23\014\B | GG | 23 | 14 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-05-06 14:58 | 2026-05-08 12:04 | 54998.0833 | [6 empty] | 54998 | 39774 | 3.48 | 0 | 0 | 12.75 | 5270
TS6060#1 | RS\60\005\B | RS | 60 | 5 | B | 1 Prestrip - Thick | 25.4179 | 25.4179 | 25.4179 | 2026-05-07 00:43 | 2026-05-08 04:39 | 27507.3874 | 27507 | [7 empty] | 0 | 0 | 6.72 | 12.53 | 5269.68
TS Fleet 5 | GG\26\012\X1 | GG | 26 | 12 | X1 | 1 Prestrip - Thick | 41.2325 | 41.2325 | 41.2325 | 2026-05-07 03:00 | 2026-05-11 16:46 | 215159.3929 | 215159 | [7 empty] | 0 | 0 | 24.81 | 14.92 | 5106.84
TS5500Exc | SC\40\011\D | SC | 40 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-05-07 09:35 | 2026-05-09 21:22 | 75322.5409 | [6 empty] | 75323 | 56205 | 4.68 | 0 | 0 | 7.58 | 5747
PH4100XPC#1 | GG\26\009\B | GG | 26 | 9 | B | 1 Prestrip - Thick | 100 | 22.2869 | 22.2869 | 2026-05-07 09:52 | 2026-05-07 17:55 | 18195.2736 | 18195 | [7 empty] | 0 | 0 | 1.82 | 10.27 | 5504.43
PH4100XPC#1 | GG\26\011\X1 | GG | 26 | 11 | X1 | 1 Prestrip - Thick | 100 | 48.0843 | 48.0843 | 2026-05-07 17:55 | 2026-05-13 09:24 | 311716.8835 | 311717 | [7 empty] | 0 | 0 | 38.86 | 14.76 | 5121.56
TS6060#1 | CP\03\002\B | CP | 3 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-05-08 04:39 | 2026-06-15 11:57 | 936793.929 | 936794 | [7 empty] | 0 | 0 | 15.83 | 9.45 | 5578.5
TS5500Shv | GG\23\018\B | GG | 23 | 18 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-05-08 12:04 | 2026-05-10 04:19 | 49087.1856 | [6 empty] | 49087 | 35439 | 3.55 | 0 | 0 | 12.93 | 5273
DRE2 | GG\22\018\D | GG | 22 | 18 | D | 6 DL | 100 | 100 | 100 | 2026-05-08 17:43 | 2026-05-14 23:11 | 502765.8668 |  |  |  | 11706 | 502766 | 222411 |  |  | 0 | 23.41 | 0 | 7.15 | 5760.33
DRE1 | SC\40\018\D | SC | 40 | 18 | D | 6 DL | 100 | 0 | 100 | 2026-05-09 03:49 | 2026-05-18 22:04 | 818254.9304 |  |  |  | 62225 | 818255 | 560022 |  |  | 0 | 40 | 0 | 6.98 | 5793.07
TS5500Exc | RS\60\002\D | RS | 60 | 2 | D | 7 PostStrip | 11.0578 | 0 | 11.0578 | 2026-05-09 21:22 | 2026-05-10 12:07 | 13031.2627 |  |  | 13031 | [5 empty] | 0 | 0 | 0 | 6.79 | 5824.01
TS5500Shv | GG\26\010\X1 | GG | 26 | 10 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-05-10 04:19 | 2026-05-10 17:49 | 16449.8917 | [6 empty] | 16450 | 11800 | 1.17 | 0 | 0 | 14.54 | 5135
PH4100A | W2\05\004\B | W2 | 5 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-05-10 10:04 | 2026-06-07 08:47 | 1223547.331 | 1223547 | [7 empty] | 0 | 0 | 52.87 | 10.71 | 5224.15
TS5500Exc | GG\26\013\X1 | GG | 26 | 13 | X1 | 1 Prestrip - Thick | 1.1186 | 1.1186 | 1.1186 | 2026-05-10 12:07 | 2026-05-10 17:18 | 4598.3462 | 4598 | [7 empty] | 0 | 0 | 0.47 | 14.84 | 5111.44
TS5500Exc | GG\26\014\X1 | GG | 26 | 14 | X1 | 1 Prestrip - Thick | 18.0408 | 18.0408 | 18.0408 | 2026-05-10 17:18 | 2026-05-13 03:12 | 51376.2132 | 51376 | [7 empty] | 0 | 0 | 5.84 | 14.74 | 5118.63
TS5500Shv | GG\23\019\B | GG | 23 | 19 | B | 8 Coal Mining | 71 | 0 | 71 | 2026-05-10 17:49 | 2026-05-11 23:02 | 35637.0947 | [6 empty] | 35637 | 25633 | 2.56 | 0 | 0 | 13.32 | 5263
TS Fleet 5 | GG\26\010\X2 | GG | 26 | 10 | X2 | 1 Prestrip - Thick | 45.419 | 0 | 45.419 | 2026-05-11 16:46 | 2026-05-12 08:21 | 30551.6954 | 30552 | [7 empty] | 0 | 0 | 3.03 | 0 | 0
TS5500Shv | RS\60\002\D | RS | 60 | 2 | D | 7 PostStrip | 88.9422 | 0 | 88.9422 | 2026-05-11 23:02 | 2026-05-16 00:49 | 104815.3866 |  |  | 104815 | [5 empty] | 0 | 0 | 0 | 6.79 | 5824.01
TS Fleet 5 | GG\26\013\X1 | GG | 26 | 13 | X1 | 1 Prestrip - Thick | 45.0684 | 45.0684 | 45.0684 | 2026-05-12 08:21 | 2026-05-16 06:53 | 185272.2482 | 185272 | [7 empty] | 0 | 0 | 19.12 | 14.84 | 5111.44
TS5500Exc | SC\40\010\D | SC | 40 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2026-05-13 03:12 | 2026-05-15 23:22 | 60293.316 |  |  | 60293 | [5 empty] | 0 | 0 | 0 | 7.72 | 5735.86
PH4100XPC#1 | GG\26\010\X2 | GG | 26 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.581 | 2026-05-13 09:24 | 2026-05-14 01:37 | 36714.6856 | 36715 | [7 empty] | 0 | 0 | 3.65 | 0 | 0
PH4100XPC#1 | GG\26\010\A | GG | 26 | 10 | A | 1 Prestrip - Thick | 100 | 0 | 100 | 2026-05-14 01:37 | 2026-05-15 18:17 | 92034.146 | 92034 | [7 empty] | 0 | 0 | 9.14 | 0 | 0
DRE2 | GG\22\019\D | GG | 22 | 19 | D | 6 DL | 100 | 100 | 100 | 2026-05-14 23:11 | 2026-05-21 00:08 | 487598.5267 |  |  |  | 11353 | 487599 | 215701 |  |  | 0 | 22.7 | 0 | 7.04 | 5769.28
PH4100XPC#1 | GG\26\010\B | GG | 26 | 10 | B | 1 Prestrip - Thick | 100 | 84.5955 | 84.5955 | 2026-05-15 18:17 | 2026-05-16 10:14 | 36109.3136 | 36109 | [7 empty] | 0 | 0 | 3.6 | 10.7 | 5477.6
TS5500Exc | SC\40\010\D | SC | 40 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-05-15 23:22 | 2026-05-18 12:20 | 76789.2018 | [6 empty] | 76789 | 57482 | 4.79 | 0 | 0 | 7.72 | 5736
TS5500Shv | GG\23\020\B | GG | 23 | 20 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-05-16 00:49 | 2026-05-17 01:54 | 30583.8507 | [6 empty] | 30584 | 21625 | 2.15 | 0 | 0 | 16.2 | 5050
TS Fleet 5 | GG\26\010\B | GG | 26 | 10 | B | 1 Prestrip - Thick | 45.419 | 15.4045 | 15.4045 | 2026-05-16 06:53 | 2026-05-16 10:14 | 6575.352 | 6575 | [7 empty] | 0 | 0 | 0.66 | 10.7 | 5477.6
TS Fleet 5 | GG\26\014\X1 | GG | 26 | 14 | X1 | 1 Prestrip - Thick | 38.2949 | 38.2949 | 38.2949 | 2026-05-16 10:14 | 2026-05-18 17:53 | 109055.4351 | 109055 | [7 empty] | 0 | 0 | 12.4 | 14.74 | 5118.63
PH4100XPC#1 | GG\26\012\X1 | GG | 26 | 12 | X1 | 1 Prestrip - Thick | 100 | 49.2638 | 49.2638 | 2026-05-16 10:14 | 2026-05-21 04:28 | 257068.059 | 257068 | [7 empty] | 0 | 0 | 29.64 | 14.92 | 5106.84
TS5500Shv | GG\23\022\B | GG | 23 | 22 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-05-17 01:54 | 2026-05-18 22:09 | 53958.037 | [6 empty] | 53958 | 37410 | 3.72 | 0 | 0 | 19.72 | 4784
TS5500Exc | RS\60\002\D | RS | 60 | 2 | D | 8 Coal Mining | 97.1 | 0 | 97.1 | 2026-05-18 12:20 | 2026-05-23 06:08 | 143334.8272 | [6 empty] | 143335 | 104190 | 4.34 | 0 | 0 | 6.79 | 5824
TS Fleet 5 | GG\26\017\X1 | GG | 26 | 17 | X1 | 1 Prestrip - Thick | 47.0387 | 47.0387 | 47.0387 | 2026-05-18 17:53 | 2026-05-20 20:04 | 98367.4665 | 98367 | [7 empty] | 0 | 0 | 11.18 | 14.37 | 5147.05
DRE1 | SC\40\019\D | SC | 40 | 19 | D | 6 DL | 100 | 0 | 100 | 2026-05-18 22:04 | 2026-05-31 05:00 | 1030285.843 |  |  |  | 78349 | 1030286 | 705139 |  |  | 0 | 40 | 0 | 6.88 | 5807.19
TS5500Shv | GG\26\010\B | GG | 26 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-05-18 22:09 | 2026-05-20 15:02 | 49865.0741 | [6 empty] | 49865 | 36411 | 3.64 | 0 | 0 | 10.7 | 5478
TS5500Shv | RS\60\002\D | RS | 60 | 2 | D | 8 Coal Mining | 2.9 | 0 | 2.9 | 2026-05-20 15:02 | 2026-05-20 18:36 | 4353.3497 | [6 empty] | 4353 | 3164 | 0.13 | 0 | 0 | 6.79 | 5824
TS5500Shv | GG\26\013\X1 | GG | 26 | 13 | X1 | 1 Prestrip - Thick | 1.3292 | 1.3292 | 1.3292 | 2026-05-20 18:36 | 2026-05-20 23:48 | 5464.41 | 5464 | [7 empty] | 0 | 0 | 0.56 | 14.84 | 5111.44
TS Fleet 5 | GG\26\018\X2 | GG | 26 | 18 | X2 | 1 Prestrip - Thick | 46.5154 | 0 | 46.5154 | 2026-05-20 20:04 | 2026-05-22 21:07 | 96136.1264 | 96136 | [7 empty] | 0 | 0 | 9.92 | 0 | 0
TS5500Shv | GG\22\013\D | GG | 22 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-05-20 23:48 | 2026-05-23 04:03 | 63724.874 | [6 empty] | 63725 | 47490 | 4.75 | 0 | 0 | 7.01 | 5772
DRE2 | GG\22\020\D | GG | 22 | 20 | D | 6 DL | 100 | 100 | 100 | 2026-05-21 00:08 | 2026-05-25 15:28 | 374503.24 |  |  |  | 6974 | 374503 | 167376 |  |  | 0 | 17.37 | 0 | 6.91 | 5780.02
PH4100XPC#1 | GG\26\013\X1 | GG | 26 | 13 | X1 | 1 Prestrip - Thick | 100 | 52.4838 | 52.4838 | 2026-05-21 04:28 | 2026-05-25 06:50 | 215756.6972 | 215757 | [7 empty] | 0 | 0 | 22.27 | 14.84 | 5111.44
TS Fleet 5 | GG\26\019\B | GG | 26 | 19 | B | 1 Prestrip - Thick | 37.1379 | 37.1379 | 37.1379 | 2026-05-22 21:07 | 2026-05-25 02:10 | 103985.6636 | 103986 | [7 empty] | 0 | 0 | 10.52 | 15.49 | 5089.86
TS5500Shv | GG\22\014\B | GG | 22 | 14 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-05-23 04:03 | 2026-05-24 19:16 | 47817.1719 | [6 empty] | 47817 | 34613 | 3.5 | 0 | 0 | 12.56 | 5290
TS5500Exc | SC\40\017\D | SC | 40 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-05-23 06:08 | 2026-05-24 02:13 | 25303.5081 | [6 empty] | 25304 | 18908 | 1.43 | 0 | 0 | 6.37 | 5794
TS5500Exc | GG\26\019\B | GG | 26 | 19 | B | 1 Prestrip - Thick | 17.4448 | 17.4448 | 17.4448 | 2026-05-24 02:13 | 2026-05-26 09:25 | 48845.2023 | 48845 | [7 empty] | 0 | 0 | 4.94 | 15.49 | 5089.86
TS5500Shv | GG\22\018\D | GG | 22 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-05-24 19:16 | 2026-05-26 23:40 | 63895.9538 | [6 empty] | 63896 | 47543 | 4.75 | 0 | 0 | 7.15 | 5760
TS Fleet 5 | GG\26\020\B | GG | 26 | 20 | B | 1 Prestrip - Thick | 30.7399 | 30.7399 | 30.7399 | 2026-05-25 02:10 | 2026-05-26 19:25 | 80859.3723 | 80859 | [7 empty] | 0 | 0 | 10.18 | 19.71 | 4767.72
PH4100XPC#1 | GG\26\014\X1 | GG | 26 | 14 | X1 | 1 Prestrip - Thick | 100 | 43.6643 | 43.6643 | 2026-05-25 06:50 | 2026-05-27 16:44 | 124346.3802 | 124346 | [7 empty] | 0 | 0 | 14.14 | 14.74 | 5118.63
DRE2 | GG\22\021\D | GG | 22 | 21 | D | 6 DL | 100 | 0 | 100 | 2026-05-25 15:28 | 2026-06-01 02:31 | 521532.3572 |  |  |  | 39660 | 521532 | 356942 |  |  | 0 | 40 | 0 | 6.8 | 5789.37
TS5500Exc | GG\26\020\B | GG | 26 | 20 | B | 1 Prestrip - Thick | 14.4353 | 14.4353 | 14.4353 | 2026-05-26 09:25 | 2026-05-28 04:21 | 37971.1337 | 37971 | [7 empty] | 0 | 0 | 4.78 | 19.71 | 4767.72
TS Fleet 5 | W1\03\005\B | W1 | 3 | 5 | B | 1 Prestrip - Thick | 100 | 0 | 100 | 2026-05-26 19:25 | 2026-06-10 18:43 | 704205.5148 | 704206 | [7 empty] | 0 | 0 | 30.62 | 0 | 0
TS5500Shv | GG\26\013\X1 | GG | 26 | 13 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-05-26 23:40 | 2026-05-27 10:27 | 13146.1019 | [6 empty] | 13146 | 9416 | 0.95 | 0 | 0 | 14.84 | 5111
TS5500Shv | GG\26\013\B | GG | 26 | 13 | B | 1 Prestrip - Thick | 40.9632 | 34.4636 | 34.4636 | 2026-05-27 10:27 | 2026-05-30 01:38 | 67727.3477 | 67727 | [7 empty] | 0 | 0 | 6.79 | 12.06 | 5323.44
PH4100XPC#1 | GG\26\013\B | GG | 26 | 13 | B | 1 Prestrip - Thick | 100 | 65.5364 | 65.5364 | 2026-05-27 16:44 | 2026-05-30 01:38 | 128791.0963 | 128791 | [7 empty] | 0 | 0 | 12.92 | 12.06 | 5323.44
TS5500Exc | RS\60\003\D | RS | 60 | 3 | D | 7 PostStrip | 45.2055 | 0 | 45.2055 | 2026-05-28 04:21 | 2026-05-29 18:49 | 34021.218 |  |  | 34021 | [5 empty] | 0 | 0 | 0 | 6.08 | 5886.05
TS5500Exc | RS\60\004\B | RS | 60 | 4 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2026-05-29 18:49 | 2026-05-29 23:09 | 5450.1277 | [6 empty] | 5450 | 3773 | 0.47 | 0 | 0 | 14.26 | 5138
TS5500Exc | SC\40\018\D | SC | 40 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-05-29 23:09 | 2026-06-01 06:26 | 69649.1781 | [6 empty] | 69649 | 52086 | 3.74 | 0 | 0 | 6.98 | 5793
TS5500Shv | GG\26\014\X1 | GG | 26 | 14 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-05-30 01:38 | 2026-05-30 10:50 | 11225.9878 | [6 empty] | 11226 | 8054 | 0.93 | 0 | 0 | 14.74 | 5119
PH4100XPC#1 | GG\26\017\X1 | GG | 26 | 17 | X1 | 1 Prestrip - Thick | 100 | 52.9613 | 52.9613 | 2026-05-30 01:38 | 2026-06-01 05:51 | 110752.6114 | 110753 | [7 empty] | 0 | 0 | 12.59 | 14.37 | 5147.05
TS5500Shv | GG\26\014\B | GG | 26 | 14 | B | 1 Prestrip - Thick | 13.5448 | 13.5448 | 13.5448 | 2026-05-30 10:50 | 2026-05-31 08:56 | 23696.9528 | 23697 | [7 empty] | 0 | 0 | 2.84 | 12.37 | 5284.32
DRE1 | SC\40\020\D | SC | 40 | 20 | D | 6 DL | 100 | 0 | 100 | 2026-05-31 05:00 | 2026-06-07 16:43 | 627758.7632 |  |  |  | 47738 | 627759 | 429645 |  |  | 0 | 40 | 0 | 6.9 | 5804.89
TS5500Shv | GG\26\019\B | GG | 26 | 19 | B | 1 Prestrip - Thick | 1.0712 | 1.0712 | 1.0712 | 2026-05-31 08:56 | 2026-05-31 11:45 | 2999.2992 | 2999 | [7 empty] | 0 | 0 | 0.3 | 15.49 | 5089.86
TS5500Shv | GG\26\020\B | GG | 26 | 20 | B | 1 Prestrip - Thick | 17.4974 | 17.4974 | 17.4974 | 2026-05-31 11:45 | 2026-06-02 06:41 | 46025.6548 | 46026 | [7 empty] | 0 | 0 | 5.8 | 19.71 | 4767.72
DRE2 | GG\22\022\D | GG | 22 | 22 | D | 6 DL | 100 | 100 | 100 | 2026-06-01 02:31 | 2026-06-05 12:20 | 355922.9915 |  |  |  | 6628 | 355923 | 159072 |  |  | 0 | 16.58 | 0 | 6.73 | 5795.73
PH4100XPC#1 | GG\26\014\B | GG | 26 | 14 | B | 1 Prestrip - Thick | 100 | 70.3828 | 70.3828 | 2026-06-01 05:51 | 2026-06-03 12:15 | 123136.5013 | 123137 | [7 empty] | 0 | 0 | 14.76 | 12.37 | 5284.32
TS5500Exc | GG\26\014\B | GG | 26 | 14 | B | 1 Prestrip - Thick | 16.0724 | 16.0724 | 16.0724 | 2026-06-01 06:26 | 2026-06-02 14:14 | 28119.035 | 28119 | [7 empty] | 0 | 0 | 3.37 | 12.37 | 5284.32
TS5500Shv | GG\26\017\X1 | GG | 26 | 17 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-06-02 06:41 | 2026-06-02 16:51 | 12403.2923 | [6 empty] | 12403 | 8917 | 1.01 | 0 | 0 | 14.37 | 5147
TS5500Exc | RS\60\005\B | RS | 60 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-06-02 14:14 | 2026-06-03 01:00 | 13564.6263 | [6 empty] | 13565 | 9468 | 2.7 | 0 | 0 | 12.53 | 5270
TS5500Shv | GG\26\017\B | GG | 26 | 17 | B | 1 Prestrip - Thick | 17.5637 | 17.5637 | 17.5637 | 2026-06-02 16:51 | 2026-06-03 23:59 | 33379.9371 | 33380 | [7 empty] | 0 | 0 | 3.97 | 14.03 | 5163.32
TS5500Exc | GG\26\017\B | GG | 26 | 17 | B | 1 Prestrip - Thick | 14.4901 | 14.4901 | 14.4901 | 2026-06-03 01:00 | 2026-06-04 08:09 | 27538.4481 | 27538 | [7 empty] | 0 | 0 | 3.27 | 14.03 | 5163.32
PH4100XPC#1 | GG\26\017\B | GG | 26 | 17 | B | 1 Prestrip - Thick | 100 | 67.9462 | 67.9462 | 2026-06-03 12:15 | 2026-06-05 21:18 | 129131.8325 | 129132 | [7 empty] | 0 | 0 | 15.35 | 14.03 | 5163.32
TS5500Shv | RS\60\003\D | RS | 60 | 3 | D | 7 PostStrip | 54.7945 | 0 | 54.7945 | 2026-06-03 23:59 | 2026-06-05 14:27 | 41237.84 |  |  | 41238 | [5 empty] | 0 | 0 | 0 | 6.08 | 5886.05
TS5500Exc | SC\40\019\D | SC | 40 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-06-04 08:09 | 2026-06-07 23:15 | 109717.3296 | [6 empty] | 109717 | 82127 | 4.48 | 0 | 0 | 6.88 | 5807
DRE2 | GG\22\023\D | GG | 22 | 23 | D | 6 DL | 100 | 100 | 100 | 2026-06-05 12:20 | 2026-06-08 06:43 | 223335.9487 |  |  |  | 4291 | 223336 | 65205 |  |  | 0 | 14.2 | 0 | 6.54 | 5814.75
TS5500Shv | GG\22\019\D | GG | 22 | 19 | D | 8 Coal Mining | 68 | 0 | 68 | 2026-06-05 14:27 | 2026-06-07 01:37 | 42874.4578 | [6 empty] | 42874 | 31951 | 3.19 | 0 | 0 | 7.04 | 5769
PH4100XPC#1 | GG\26\018\X2 | GG | 26 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.4846 | 2026-06-05 21:18 | 2026-06-08 00:20 | 110539.8055 | 110540 | [7 empty] | 0 | 0 | 11.41 | 0 | 0
TS5500Shv | RS\60\003\D | RS | 60 | 3 | D | 8 Coal Mining | 25 | 0 | 25 | 2026-06-07 01:37 | 2026-06-07 20:09 | 22605.7504 | [6 empty] | 22606 | 16494 | 1.09 | 0 | 0 | 6.08 | 5886
PH4100A | W2\06\003\B | W2 | 6 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-06-07 08:47 | 2026-07-26 08:03 | 2084719.262 | 2084719 | [7 empty] | 0 | 0 | 78.8 | 9.72 | 5306.69
DRE1 | SC\40\021\D | SC | 40 | 21 | D | 6 DL | 100 | 0 | 100 | 2026-06-07 16:43 | 2026-06-15 05:26 | 631285.3408 |  |  |  | 48006 | 631285 | 432058 |  |  | 0 | 40 | 0 | 7.33 | 5766.79
TS5500Shv | RS\60\004\B | RS | 60 | 4 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2026-06-07 20:09 | 2026-06-08 00:29 | 5276.1875 | [6 empty] | 5276 | 3653 | 0.45 | 0 | 0 | 14.26 | 5138
TS5500Exc | W2\05\004\B | W2 | 5 | 4 | B | 8 Coal Mining | 94.1 | 0 | 94.1 | 2026-06-07 23:15 | 2026-06-09 12:57 | 47489.0412 | [6 empty] | 47489 | 33223 | 1.65 | 0 | 0 | 10.71 | 5224
PH4100XPC#1 | GG\26\018\B | GG | 26 | 18 | B | 1 Prestrip - Thick | 100 | 76.2472 | 76.2472 | 2026-06-08 00:20 | 2026-06-10 01:20 | 110880.3287 | 110880 | [7 empty] | 0 | 0 | 11.05 | 14.19 | 5171.15
TS5500Shv | GG\26\018\B | GG | 26 | 18 | B | 1 Prestrip - Thick | 19.7095 | 19.7095 | 19.7095 | 2026-06-08 00:29 | 2026-06-09 03:13 | 28662.0141 | 28662 | [7 empty] | 0 | 0 | 2.86 | 14.19 | 5171.15
DRE2 | GG\22\014\D | GG | 22 | 14 | D | 6 DL | 100 | 100 | 100 | 2026-06-08 06:43 | 2026-06-13 23:54 | 461436.5448 |  |  |  | 10744 | 461437 | 204128 |  |  | 0 | 23.76 | 0 | 7.14 | 5761.31
TS5500Shv | RS\60\004\D | RS | 60 | 4 | D | 1 Prestrip - Thick | 29.2796 | 29.2796 | 29.2796 | 2026-06-09 03:13 | 2026-06-11 00:30 | 48553.1567 | 48553 | [7 empty] | 0 | 0 | 7.45 | 5.96 | 5895.75
TS5500Exc | GG\26\018\B | GG | 26 | 18 | B | 1 Prestrip - Thick | 4.0433 | 4.0433 | 4.0433 | 2026-06-09 12:57 | 2026-06-09 19:36 | 5879.8687 | 5880 | [7 empty] | 0 | 0 | 0.59 | 14.19 | 5171.15
TS5500Exc | RS\60\003\D | RS | 60 | 3 | D | 8 Coal Mining | 75 | 0 | 75 | 2026-06-09 19:36 | 2026-06-12 01:18 | 67638.8963 | [6 empty] | 67639 | 49352 | 3.27 | 0 | 0 | 6.08 | 5886
PH4100XPC#1 | GG\26\019\B | GG | 26 | 19 | B | 1 Prestrip - Thick | 100 | 44.3462 | 44.3462 | 2026-06-10 01:20 | 2026-06-12 08:32 | 124168.8732 | 124169 | [7 empty] | 0 | 0 | 12.56 | 15.49 | 5089.86
TS Fleet 5 | RS\60\004\D | RS | 60 | 4 | D | 1 Prestrip - Thick | 45.6911 | 45.6911 | 45.6911 | 2026-06-10 18:43 | 2026-06-12 09:22 | 75767.6048 | 75768 | [7 empty] | 0 | 0 | 11.62 | 5.96 | 5895.75
TS5500Shv | GG\22\020\D | GG | 22 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-06-11 00:30 | 2026-06-13 04:03 | 62852.5244 | [6 empty] | 62853 | 46877 | 4.69 | 0 | 0 | 6.91 | 5780
TS5500Exc | SC\40\020\D | SC | 40 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-06-12 01:18 | 2026-06-14 09:51 | 71241.4378 | [6 empty] | 71241 | 53369 | 4.45 | 0 | 0 | 6.9 | 5805
PH4100XPC#1 | GG\26\020\B | GG | 26 | 20 | B | 1 Prestrip - Thick | 100 | 37.3274 | 37.3274 | 2026-06-12 08:32 | 2026-06-14 03:28 | 98187.3034 | 98187 | [7 empty] | 0 | 0 | 12.36 | 19.71 | 4767.72
TS Fleet 5 | W1\03\005\D | W1 | 3 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-06-12 09:22 | 2026-06-13 18:21 | 64644.8712 | 64645 | [7 empty] | 0 | 0 | 8.29 | 7.64 | 5598.75
TS5500Shv | RS\60\005\D | RS | 60 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-06-13 04:03 | 2026-06-15 12:58 | 61014.2179 | 61014 | [7 empty] | 0 | 0 | 29.17 | 6.06 | 5886.77
TS Fleet 5 | W1\04\002\D | W1 | 4 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-06-13 18:21 | 2026-06-17 16:12 | 183939.0275 | 183939 | [7 empty] | 0 | 0 | 15.51 | 7.37 | 5621.22
DRE2 | GG\24\012\B | GG | 24 | 12 | B | 6 DL | 100 | 0 | 100 | 2026-06-13 23:54 | 2026-06-16 13:55 | 208619.2356 |  |  |  |  | 208619 | 173849 |  |  | 0 | 17.24 | 0 | 11.78 | 5369.27
PH4100XPC#1 | W2\01\008\D | W2 | 1 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-06-14 03:28 | 2026-06-23 00:43 | 482714.8768 | 482715 | [7 empty] | 0 | 0 | 19.99 | 5.9 | 5739.49
TS5500Exc | W1\01\003\D | W1 | 1 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2026-06-14 09:51 | 2026-06-19 17:35 | 112969.9431 |  |  | 112970 | [5 empty] | 0 | 0 | 0 | 7.33 | 5632.58
DRE1 | SC\40\022\D | SC | 40 | 22 | D | 6 DL | 100 | 0 | 100 | 2026-06-15 05:26 | 2026-06-22 17:40 | 629543.3963 |  |  |  | 47874 | 629543 | 430866 |  |  | 0 | 40 | 0 | 7.41 | 5761.04
TS6060#1 | GG\26\011\X1 | GG | 26 | 11 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-06-15 11:57 | 2026-06-15 22:52 | 14776.4544 | [6 empty] | 14776 | 10586 | 1.06 | 0 | 0 | 14.76 | 5122
TS5500Shv | RS\60\005\D | RS | 60 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2026-06-15 12:58 | 2026-06-16 00:44 | 12619.8791 |  |  | 12620 | [5 empty] | 0 | 0 | 0 | 6.06 | 5886.77
TS6060#1 | GG\26\012\X1 | GG | 26 | 12 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-06-15 22:52 | 2026-06-16 09:01 | 13728.3656 | [6 empty] | 13728 | 9827 | 1 | 0 | 0 | 14.92 | 5107
TS5500Shv | RS\60\005\D | RS | 60 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-06-16 00:44 | 2026-06-16 12:09 | 13919.6962 | [6 empty] | 13920 | 10202 | 4.13 | 0 | 0 | 6.06 | 5887
TS6060#1 | W2\05\004\B | W2 | 5 | 4 | B | 8 Coal Mining | 5.9 | 0 | 5.9 | 2026-06-16 09:01 | 2026-06-16 11:11 | 2951.1584 | [6 empty] | 2951 | 2065 | 0.1 | 0 | 0 | 10.71 | 5224
TS6060#1 | GG\22\019\D | GG | 22 | 19 | D | 8 Coal Mining | 32 | 0 | 32 | 2026-06-16 11:11 | 2026-06-17 02:07 | 20192.3905 | [6 empty] | 20192 | 15048 | 1.5 | 0 | 0 | 7.04 | 5769
TS5500Shv | GG\22\021\D | GG | 22 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-06-16 12:09 | 2026-06-18 15:25 | 62507.3886 | [6 empty] | 62507 | 46693 | 4.67 | 0 | 0 | 6.8 | 5789
DRE2 | GG\24\011\B | GG | 24 | 11 | B | 6 DL | 100 | 0 | 100 | 2026-06-16 13:55 | 2026-06-19 10:38 | 231145.4024 |  |  |  |  | 231145 | 177804 |  |  | 0 | 17.67 | 0 | 11.07 | 5442.79
TS6060#1 | RS\60\004\D | RS | 60 | 4 | D | 1 Prestrip - Thick | 25.0292 | 25.0292 | 25.0292 | 2026-06-17 02:07 | 2026-06-18 18:20 | 41504.8878 | 41505 | [7 empty] | 0 | 0 | 6.37 | 5.96 | 5895.75
TS Fleet 5 | GG\26\011\X2 | GG | 26 | 11 | X2 | 1 Prestrip - Thick | 45.419 | 0 | 45.419 | 2026-06-17 16:12 | 2026-06-18 07:45 | 30495.8759 | 30496 | [7 empty] | 0 | 0 | 3.07 | 0 | 0
TS Fleet 5 | GG\26\012\X2 | GG | 26 | 12 | X2 | 1 Prestrip - Thick | 45.419 | 0 | 45.419 | 2026-06-18 07:45 | 2026-06-18 23:44 | 31315.3472 | 31315 | [7 empty] | 0 | 0 | 3.18 | 0 | 0
TS5500Shv | GG\22\022\D | GG | 22 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-06-18 15:25 | 2026-06-20 18:55 | 62803.7358 | [6 empty] | 62804 | 46952 | 4.7 | 0 | 0 | 6.73 | 5796
TS6060#1 | GG\24\012\B | GG | 24 | 12 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-06-18 18:20 | 2026-06-20 06:25 | 48839.7276 | [6 empty] | 48840 | 35478 | 3.54 | 0 | 0 | 11.78 | 5369
TS Fleet 5 | W1\04\003\A | W1 | 4 | 3 | A | 1 Prestrip - Thick | 100 | 0 | 100 | 2026-06-18 23:44 | 2026-07-01 04:37 | 574060.4142 | 574060 | [7 empty] | 0 | 0 | 28.94 | 0 | 0
DRE2 | GG\24\010\B | GG | 24 | 10 | B | 6 DL | 100 | 0 | 100 | 2026-06-19 10:38 | 2026-06-22 05:59 | 226530.1408 |  |  |  |  | 226530 | 188775 |  |  | 0 | 18.88 | 0 | 10.28 | 5510.81
TS5500Exc | RS\60\004\D | RS | 60 | 4 | D | 7 PostStrip | 20.4008 | 0 | 20.4008 | 2026-06-19 17:35 | 2026-06-20 02:57 | 8278.8537 |  |  | 8279 | [5 empty] | 0 | 0 | 0 | 5.96 | 5895.75
TS5500Exc | SC\40\021\D | SC | 40 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-06-20 02:57 | 2026-06-22 09:05 | 68187.1831 | [6 empty] | 68187 | 51079 | 4.26 | 0 | 0 | 7.33 | 5767
TS6060#1 | GG\24\011\B | GG | 24 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-06-20 06:25 | 2026-06-21 18:33 | 48886.0326 | [6 empty] | 48886 | 35649 | 3.57 | 0 | 0 | 11.07 | 5443
TS5500Shv | RS\60\004\D | RS | 60 | 4 | D | 7 PostStrip | 79.5992 | 0 | 79.5992 | 2026-06-20 18:55 | 2026-06-22 01:03 | 32302.0765 |  |  | 32302 | [5 empty] | 0 | 0 | 0 | 5.96 | 5895.75
TS6060#1 | W1\01\003\D | W1 | 1 | 3 | D | 8 Coal Mining | 2.1 | 0 | 2.1 | 2026-06-21 18:33 | 2026-06-21 19:55 | 1849.6234 | [6 empty] | 1850 | 1333 | 0.12 | 0 | 0 | 7.33 | 5633
TS6060#1 | W1\01\004\D | W1 | 1 | 4 | D | 7 PostStrip | 40.9359 | 0 | 40.9359 | 2026-06-21 19:55 | 2026-06-24 16:03 | 70310.2535 |  |  | 70310 | [5 empty] | 0 | 0 | 0 | 7.43 | 5620.98
TS5500Shv | GG\22\023\D | GG | 22 | 23 | D | 7 PostStrip | 100 | 0 | 100 | 2026-06-22 01:03 | 2026-06-23 12:18 | 37782.5575 |  |  | 37783 | [5 empty] | 0 | 0 | 0 | 6.54 | 5814.75
DRE2 | GG\24\009\B | GG | 24 | 9 | B | 6 DL | 100 | 0 | 100 | 2026-06-22 05:59 | 2026-06-25 04:20 | 236637.0814 |  |  |  |  | 236637 | 197198 |  |  | 0 | 19.72 | 0 | 10.15 | 5513.77
TS5500Exc | RS\60\004\D | RS | 60 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-06-22 09:05 | 2026-06-23 22:11 | 46720.8203 | [6 empty] | 46721 | 34164 | 4.21 | 0 | 0 | 5.96 | 5896
DRE1 | SC\40\023\D | SC | 40 | 23 | D | 6 DL | 100 | 0 | 100 | 2026-06-22 17:40 | 2026-06-29 09:56 | 559861.0635 |  |  |  | 39816 | 559861 | 402587 |  |  | 0 | 37.11 | 0 | 7.36 | 5766.65
PH4100XPC#1 | GG\26\011\X2 | GG | 26 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.581 | 2026-06-23 00:43 | 2026-06-23 16:55 | 36647.6061 | 36648 | [7 empty] | 0 | 0 | 3.69 | 0 | 0
TS5500Shv | GG\22\023\D | GG | 22 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-06-23 12:18 | 2026-06-25 05:14 | 49923.914 | [6 empty] | 49924 | 37413 | 4.91 | 0 | 0 | 6.54 | 5815
PH4100XPC#1 | GG\26\011\B | GG | 26 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-06-23 16:55 | 2026-06-25 13:26 | 100782.879 | 100783 | [7 empty] | 0 | 0 | 10.09 | 11.41 | 5415.77
TS5500Exc | W2\01\008\D | W2 | 1 | 8 | D | 7 PostStrip | 41.1086 | 0 | 41.1086 | 2026-06-23 22:11 | 2026-06-27 01:01 | 66182.9101 |  |  | 66183 | [5 empty] | 0 | 0 | 0 | 5.9 | 5739.49
TS6060#1 | W2\01\008\D | W2 | 1 | 8 | D | 7 PostStrip | 47.96 | 0 | 47.96 | 2026-06-24 16:03 | 2026-06-27 18:53 | 77213.3951 |  |  | 77213 | [5 empty] | 0 | 0 | 0 | 5.9 | 5739.49
DRE2 | GG\24\008\B | GG | 24 | 8 | B | 6 DL | 100 | 0 | 100 | 2026-06-25 04:20 | 2026-06-28 10:06 | 261607.6835 |  |  |  |  | 261608 | 201237 |  |  | 0 | 20.13 | 0 | 10.25 | 5490.05
TS5500Shv | GG\22\014\D | GG | 22 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-06-25 05:14 | 2026-06-27 04:15 | 57331.0063 | [6 empty] | 57331 | 42658 | 4.79 | 0 | 0 | 7.14 | 5761
PH4100XPC#1 | GG\26\012\X2 | GG | 26 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 54.581 | 2026-06-25 13:26 | 2026-06-26 06:04 | 37632.3838 | 37632 | [7 empty] | 0 | 0 | 3.82 | 0 | 0
PH4100XPC#1 | GG\26\012\B | GG | 26 | 12 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-06-26 06:04 | 2026-06-28 07:35 | 112099.2201 | 112099 | [7 empty] | 0 | 0 | 11.28 | 11.73 | 5372.67
TS5500Exc | W2\01\008\D | W2 | 1 | 8 | D | 7 PostStrip | 5.0453 | 0 | 5.0453 | 2026-06-27 01:01 | 2026-06-27 10:12 | 8122.643 |  |  | 8123 | [5 empty] | 0 | 0 | 0 | 5.9 | 5739.49
TS5500Shv | GG\27\006\X1 | GG | 27 | 6 | X1 | 1 Prestrip - Thick | 55.8341 | 22.9688 | 22.9688 | 2026-06-27 04:15 | 2026-07-13 07:45 | 414262.6044 | 414263 | [7 empty] | 0 | 0 | 23.12 | 11.9 | 5253.4
TS5500Exc | GG\27\020\B | GG | 27 | 20 | B | 1 Prestrip - Thick | 100 | 47.8022 | 47.8022 | 2026-06-27 10:12 | 2026-07-04 00:18 | 139851.0279 | 139851 | [7 empty] | 0 | 0 | 16.02 | 0 | 0
TS6060#1 | GG\27\020\B | GG | 27 | 20 | B | 1 Prestrip - Thick | 100 | 52.1978 | 52.1978 | 2026-06-27 18:53 | 2026-07-04 00:18 | 152710.9663 | 152711 | [7 empty] | 0 | 0 | 17.5 | 0 | 0
PH4100XPC#1 | GG\27\006\X1 | GG | 27 | 6 | X1 | 1 Prestrip - Thick | 100 | 45.3943 | 45.3943 | 2026-06-28 07:35 | 2026-07-13 07:45 | 818724.7577 | 818725 | [7 empty] | 0 | 0 | 45.69 | 11.9 | 5253.4
DRE2 | GG\24\007\B | GG | 24 | 7 | B | 6 DL | 100 | 0 | 100 | 2026-06-28 10:06 | 2026-07-01 15:27 | 260159.2862 |  |  |  |  | 260159 | 200123 |  |  | 0 | 20 | 0 | 10.42 | 5460.13
DRE1 | SC\40\024\D | SC | 40 | 24 | D | 6 DL | 100 | 0 | 100 | 2026-06-29 09:56 | 2026-07-06 01:40 | 557962.9106 |  |  |  | 39681 | 557963 | 401222 |  |  | 0 | 36.87 | 0 | 7.41 | 5762.12
TS Fleet 5 | GG\27\006\X1 | GG | 27 | 6 | X1 | 1 Prestrip - Thick | 37.9456 | 31.6369 | 31.6369 | 2026-07-01 04:37 | 2026-07-13 07:45 | 570598.7165 | 570599 | [7 empty] | 0 | 0 | 31.84 | 11.9 | 5253.4
DRE2 | GG\24\006\B | GG | 24 | 6 | B | 6 DL | 100 | 0 | 100 | 2026-07-01 15:27 | 2026-07-04 20:42 | 259850.9964 |  |  |  |  | 259851 | 199885 |  |  | 0 | 20.01 | 0 | 10.37 | 5449.38
TS6060#1 | W2\01\008\D | W2 | 1 | 8 | D | 7 PostStrip | 5.8861 | 0 | 5.8861 | 2026-07-04 00:18 | 2026-07-04 09:29 | 9476.4168 |  |  | 9476 | [5 empty] | 0 | 0 | 0 | 5.9 | 5739.49
TS5500Exc | SC\40\022\D | SC | 40 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-07-04 00:18 | 2026-07-06 08:59 | 71391.0212 | [6 empty] | 71391 | 53438 | 4.45 | 0 | 0 | 7.41 | 5761
TS6060#1 | W2\01\008\D | W2 | 1 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-07-04 09:29 | 2026-07-09 20:57 | 177927.8903 | [6 empty] | 177928 | 129395 | 4.23 | 0 | 0 | 5.9 | 5739
DRE2 | GG\24\005\B | GG | 24 | 5 | B | 6 DL | 100 | 0 | 100 | 2026-07-04 20:42 | 2026-07-08 02:53 | 263013.5415 |  |  |  |  | 263014 | 202318 |  |  | 0 | 20.27 | 0 | 9.91 | 5478.1
DRE1 | SC\40\025\D | SC | 40 | 25 | D | 6 DL | 100 | 0 | 100 | 2026-07-06 01:40 | 2026-07-12 02:17 | 505125.2355 |  |  |  | 28829 | 505125 | 383014 |  |  | 0 | 34.39 | 0 | 7.24 | 5777.62
TS5500Exc | SC\40\023\D | SC | 40 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-07-06 08:59 | 2026-07-08 20:51 | 75407.8289 | [6 empty] | 75408 | 56403 | 4.7 | 0 | 0 | 7.36 | 5767
DRE2 | GG\24\004\B | GG | 24 | 4 | B | 6 DL | 100 | 0 | 100 | 2026-07-08 02:53 | 2026-07-13 05:28 | 412303.8087 |  |  |  |  | 412304 | 196335 |  |  | 0 | 20.36 | 0 | 9.57 | 5507.73
TS5500Exc | CP\03\002\B | CP | 3 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-07-08 20:51 | 2026-07-12 11:14 | 108820.2968 | [6 empty] | 108820 | 76802 | 3.6 | 0 | 0 | 9.45 | 5579
TS6060#1 | GG\24\007\B | GG | 24 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-07-09 20:57 | 2026-07-11 10:38 | 50994.6593 | [6 empty] | 50995 | 37276 | 3.73 | 0 | 0 | 10.42 | 5460
TS6060#1 | GG\24\008\B | GG | 24 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-07-11 10:38 | 2026-07-13 00:57 | 51862.0148 | [6 empty] | 51862 | 37946 | 3.8 | 0 | 0 | 10.25 | 5490
DRE1 | SC\40\026\D | SC | 40 | 26 | D | 6 DL | 100 | 0 | 100 | 2026-07-12 02:17 | 2026-07-18 03:56 | 508806.818 |  |  |  | 21181 | 508807 | 269908 |  |  | 0 | 27.38 | 0 | 6.93 | 5805.23
TS5500Exc | SC\40\024\D | SC | 40 | 24 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-07-12 11:14 | 2026-07-14 23:28 | 75869.9828 | [6 empty] | 75870 | 56749 | 4.73 | 0 | 0 | 7.41 | 5762
TS6060#1 | GG\24\006\B | GG | 24 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-07-13 00:57 | 2026-07-14 13:36 | 49600.9728 | [6 empty] | 49601 | 36276 | 3.63 | 0 | 0 | 10.37 | 5449
DRE2 | GG\23\012\D | GG | 23 | 12 | D | 6 DL | 100 | 100 | 100 | 2026-07-13 05:28 | 2026-07-19 07:59 | 492856.9067 |  |  |  | 11475 | 492857 | 218028 |  |  | 0 | 22.97 | 0 | 6.77 | 5793.03
TS5500Shv | GG\27\006\X1 | GG | 27 | 6 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-07-13 07:45 | 2026-07-14 06:20 | 27541.7933 | [6 empty] | 27542 | 20234 | 1.12 | 0 | 0 | 11.9 | 5253
TS Fleet 5 | GG\27\007\X1 | GG | 27 | 7 | X1 | 1 Prestrip - Thick | 45.6998 | 45.6998 | 45.6998 | 2026-07-13 07:45 | 2026-07-22 09:28 | 426739.3032 | 426739 | [7 empty] | 0 | 0 | 41.36 | 12.54 | 5230.35
PH4100XPC#1 | GG\27\007\X1 | GG | 27 | 7 | X1 | 1 Prestrip - Thick | 100 | 54.3002 | 54.3002 | 2026-07-13 07:45 | 2026-07-22 18:18 | 507049.3532 | 507049 | [7 empty] | 0 | 0 | 49.14 | 12.54 | 5230.35
TS5500Shv | GG\27\006\B | GG | 27 | 6 | B | 1 Prestrip - Thick | 100 | 78.0768 | 78.0768 | 2026-07-14 06:20 | 2026-07-23 05:32 | 230706.1601 | 230706 | [7 empty] | 0 | 0 | 13.1 | 10.86 | 5428.19
TS6060#1 | GG\24\009\B | GG | 24 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-07-14 13:36 | 2026-07-16 03:30 | 51297.0797 | [6 empty] | 51297 | 37554 | 3.76 | 0 | 0 | 10.15 | 5514
TS5500Exc | W1\01\003\D | W1 | 1 | 3 | D | 8 Coal Mining | 97.9 | 0 | 97.9 | 2026-07-14 23:28 | 2026-07-17 19:40 | 85906.6702 | [6 empty] | 85907 | 61910 | 5.74 | 0 | 0 | 7.33 | 5633
TS6060#1 | GG\24\005\B | GG | 24 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-07-16 03:30 | 2026-07-17 16:07 | 49550.7088 | [6 empty] | 49551 | 36327 | 3.62 | 0 | 0 | 9.91 | 5478
TS6060#1 | GG\24\010\B | GG | 24 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-07-17 16:07 | 2026-07-19 04:51 | 49708.8884 | [6 empty] | 49709 | 36368 | 3.64 | 0 | 0 | 10.28 | 5511
TS5500Exc | SC\40\025\D | SC | 40 | 25 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-07-17 19:40 | 2026-07-20 08:44 | 76900.6835 | [6 empty] | 76901 | 57657 | 4.81 | 0 | 0 | 7.24 | 5778
DRE1 | SC\41\017\D | SC | 41 | 17 | D | 6 DL | 100 | 0 | 100 | 2026-07-18 03:56 | 2026-07-30 21:07 | 1066013.104 |  |  |  | 59218 | 1066013 | 463267 |  |  | 0 | 40 | 0 | 7.16 | 5776.59
TS6060#1 | GG\24\004\B | GG | 24 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-07-19 04:51 | 2026-07-20 19:25 | 52204.5298 | [6 empty] | 52205 | 38329 | 4.25 | 0 | 0 | 9.57 | 5508
DRE2 | GG\23\011\D | GG | 23 | 11 | D | 6 DL | 100 | 100 | 100 | 2026-07-19 07:59 | 2026-07-25 11:43 | 496926.8144 |  |  |  | 9012 | 496927 | 216280 |  |  | 0 | 22.55 | 0 | 6.58 | 5807.51
TS5500Exc | W1\01\004\D | W1 | 1 | 4 | D | 7 PostStrip | 59.0641 | 0 | 59.0641 | 2026-07-20 08:44 | 2026-07-25 03:26 | 101446.5149 |  |  | 101447 | [5 empty] | 0 | 0 | 0 | 7.43 | 5620.98
TS6060#1 | GG\23\012\D | GG | 23 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-07-20 19:25 | 2026-07-22 17:59 | 63018.7715 | [6 empty] | 63019 | 47112 | 4.71 | 0 | 0 | 6.77 | 5793
TS Fleet 5 | GG\27\006\B | GG | 27 | 6 | B | 1 Prestrip - Thick | 13.3274 | 13.3148 | 13.3148 | 2026-07-22 09:28 | 2026-07-23 05:32 | 39343.4415 | 39343 | [7 empty] | 0 | 0 | 2.23 | 10.86 | 5428.19
TS6060#1 | GG\27\008\X1 | GG | 27 | 8 | X1 | 1 Prestrip - Thick | 15.1757 | 15.1757 | 15.1757 | 2026-07-22 17:59 | 2026-07-27 22:17 | 126191.9709 | 126192 | [7 empty] | 0 | 0 | 13.22 | 13.46 | 5185.28
PH4100XPC#1 | GG\27\006\B | GG | 27 | 6 | B | 1 Prestrip - Thick | 100 | 8.6083 | 8.6083 | 2026-07-22 18:18 | 2026-07-23 05:32 | 25436.4038 | 25436 | [7 empty] | 0 | 0 | 1.44 | 10.86 | 5428.19
TS5500Shv | GG\27\007\X1 | GG | 27 | 7 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-07-23 05:32 | 2026-07-23 12:03 | 7937.0335 | [6 empty] | 7937 | 5789 | 0.58 | 0 | 0 | 12.54 | 5230
TS Fleet 5 | GG\27\008\X1 | GG | 27 | 8 | X1 | 1 Prestrip - Thick | 38.001 | 31.8214 | 31.8214 | 2026-07-23 05:32 | 2026-07-28 20:33 | 264608.3388 | 264608 | [7 empty] | 0 | 0 | 27.72 | 13.46 | 5185.28
PH4100XPC#1 | GG\27\008\X1 | GG | 27 | 8 | X1 | 1 Prestrip - Thick | 100 | 37.0728 | 37.0728 | 2026-07-23 05:32 | 2026-07-28 20:33 | 308276.0904 | 308276 | [7 empty] | 0 | 0 | 32.3 | 13.46 | 5185.28
TS5500Shv | GG\27\008\X1 | GG | 27 | 8 | X1 | 1 Prestrip - Thick | 15.9301 | 15.9301 | 15.9301 | 2026-07-23 12:03 | 2026-07-28 16:21 | 132465.5611 | 132466 | [7 empty] | 0 | 0 | 13.88 | 13.46 | 5185.28
TS5500Exc | W1\01\004\D | W1 | 1 | 4 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2026-07-25 03:26 | 2026-07-28 01:02 | 87676.3193 | [6 empty] | 87676 | 63175 | 2.69 | 0 | 0 | 7.43 | 5621
DRE2 | GG\23\010\D | GG | 23 | 10 | D | 6 DL | 100 | 100 | 100 | 2026-07-25 11:43 | 2026-07-31 02:49 | 454479.219 |  |  |  | 10582 | 454479 | 201050 |  |  | 0 | 21.17 | 0 | 6.57 | 5807.58
PH4100A | W2\06\004\B | W2 | 6 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-07-26 08:03 | 2026-08-23 19:25 | 1198376.038 | 1198376 | [7 empty] | 0 | 0 | 57.2 | 9.89 | 5286.59
TS6060#1 | W1\01\004\D | W1 | 1 | 4 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2026-07-27 22:17 | 2026-07-30 19:54 | 94205.4069 | [6 empty] | 94205 | 67879 | 2.89 | 0 | 0 | 7.43 | 5621
TS5500Exc | W2\06\003\B | W2 | 6 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-07-28 01:02 | 2026-07-31 11:02 | 103280.4584 | [6 empty] | 103280 | 72825 | 2.95 | 0 | 0 | 9.72 | 5307
TS5500Shv | GG\23\011\D | GG | 23 | 11 | D | 8 Coal Mining | 76 | 0 | 76 | 2026-07-28 16:21 | 2026-07-30 06:29 | 46490.3869 | [6 empty] | 46490 | 34810 | 3.48 | 0 | 0 | 6.58 | 5808
PH4100XPC#1 | GG\27\009\X1 | GG | 27 | 9 | X1 | 1 Prestrip - Thick | 100 | 46.8842 | 46.8842 | 2026-07-28 20:33 | 2026-08-05 09:18 | 413423.4308 | 413423 | [7 empty] | 0 | 0 | 30.33 | 14.13 | 5152.34
TS Fleet 5 | GG\27\009\X1 | GG | 27 | 9 | X1 | 1 Prestrip - Thick | 38.6109 | 38.6109 | 38.6109 | 2026-07-28 20:33 | 2026-08-05 02:15 | 340469.509 | 340470 | [7 empty] | 0 | 0 | 24.97 | 14.13 | 5152.34
TS5500Shv | GG\27\008\X1 | GG | 27 | 8 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-07-30 06:29 | 2026-07-30 13:28 | 8526.3403 | [6 empty] | 8526 | 6166 | 0.62 | 0 | 0 | 13.46 | 5185
TS5500Shv | GG\27\009\X1 | GG | 27 | 9 | X1 | 1 Prestrip - Thick | 14.505 | 14.505 | 14.505 | 2026-07-30 13:28 | 2026-08-04 13:43 | 127904.4313 | 127904 | [7 empty] | 0 | 0 | 9.38 | 14.13 | 5152.34
TS6060#1 | GG\23\011\D | GG | 23 | 11 | D | 8 Coal Mining | 24 | 0 | 24 | 2026-07-30 19:54 | 2026-07-31 06:45 | 14704.5778 | [6 empty] | 14705 | 11010 | 1.1 | 0 | 0 | 6.58 | 5808
DRE1 | SC\41\016\D | SC | 41 | 16 | D | 6 DL | 100 | 0 | 100 | 2026-07-30 21:07 | 2026-08-04 12:42 | 389775.7635 |  |  |  | 29641 | 389776 | 266767 |  |  | 0 | 40 | 0 | 7.29 | 5766.48
DRE2 | GG\23\009\D | GG | 23 | 9 | D | 6 DL | 100 | 100 | 100 | 2026-07-31 02:49 | 2026-08-05 12:36 | 436556.6045 |  |  |  | 10164 | 436557 | 193122 |  |  | 0 | 20.33 | 0 | 6.55 | 5810.66
TS6060#1 | GG\23\010\D | GG | 23 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-07-31 06:45 | 2026-08-02 03:08 | 60066.1956 | [6 empty] | 60066 | 45011 | 4.5 | 0 | 0 | 6.57 | 5808
TS5500Exc | SC\40\026\D | SC | 40 | 26 | D | 7 PostStrip | 100 | 0 | 100 | 2026-07-31 11:02 | 2026-08-03 09:04 | 61931.7306 |  |  | 61932 | [5 empty] | 0 | 0 | 0 | 6.93 | 5805.23
TS6060#1 | GG\27\007\X1 | GG | 27 | 7 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-08-02 03:08 | 2026-08-02 09:39 | 8809.2349 | [6 empty] | 8809 | 6425 | 0.64 | 0 | 0 | 12.54 | 5230
TS6060#1 | GG\27\007\B | GG | 27 | 7 | B | 1 Prestrip - Thick | 49.0446 | 49.0446 | 49.0446 | 2026-08-02 09:39 | 2026-08-05 09:42 | 74347.5213 | 74348 | [7 empty] | 0 | 0 | 7.45 | 10.62 | 5452.38
TS5500Exc | SC\40\026\D | SC | 40 | 26 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-08-03 09:04 | 2026-08-05 22:18 | 77145.5277 | [6 empty] | 77146 | 58072 | 4.84 | 0 | 0 | 6.93 | 5805
DRE1 | SC\41\015\D | SC | 41 | 15 | D | 6 DL | 100 | 0 | 100 | 2026-08-04 12:42 | 2026-08-11 20:02 | 612476.4334 |  |  |  | 43558 | 612476 | 440422 |  |  | 0 | 39.89 | 0 | 7.42 | 5756.08
TS5500Shv | GG\27\007\B | GG | 27 | 7 | B | 1 Prestrip - Thick | 50.9554 | 25.7783 | 25.7783 | 2026-08-04 13:43 | 2026-08-06 02:10 | 39077.7163 | 39078 | [7 empty] | 0 | 0 | 3.92 | 10.62 | 5452.38
TS Fleet 5 | GG\27\010\X1 | GG | 27 | 10 | X1 | 1 Prestrip - Thick | 39.3256 | 39.3256 | 39.3256 | 2026-08-05 02:15 | 2026-08-11 03:57 | 285555.1634 | 285555 | [7 empty] | 0 | 0 | 21.62 | 14.47 | 5139.24
PH4100XPC#1 | GG\27\007\B | GG | 27 | 7 | B | 1 Prestrip - Thick | 100 | 25.1771 | 25.1771 | 2026-08-05 09:18 | 2026-08-06 02:10 | 38166.4616 | 38166 | [7 empty] | 0 | 0 | 3.83 | 10.62 | 5452.38
TS6060#1 | GG\27\008\X1 | GG | 27 | 8 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-08-05 09:42 | 2026-08-05 16:42 | 9463.3008 | [6 empty] | 9463 | 6844 | 0.69 | 0 | 0 | 13.46 | 5185
DRE2 | GG\23\008\D | GG | 23 | 8 | D | 6 DL | 100 | 100 | 100 | 2026-08-05 12:36 | 2026-08-10 19:40 | 427388.3022 |  |  |  | 7959 | 427388 | 191012 |  |  | 0 | 19.9 | 0 | 6.56 | 5810.14
TS6060#1 | GG\23\009\D | GG | 23 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-08-05 16:42 | 2026-08-07 14:11 | 61565.6112 | [6 empty] | 61566 | 46099 | 4.61 | 0 | 0 | 6.55 | 5811
TS5500Exc | SC\41\017\D | SC | 41 | 17 | D | 7 PostStrip | 100 | 0 | 100 | 2026-08-05 22:18 | 2026-08-09 05:07 | 69694.154 |  |  | 69694 | [5 empty] | 0 | 0 | 0 | 7.16 | 5776.59
PH4100XPC#1 | GG\27\008\X2 | GG | 27 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 67.8611 | 2026-08-06 02:10 | 2026-08-07 00:11 | 49840.0445 | 49840 | [7 empty] | 0 | 0 | 4.98 | 0 | 0
TS5500Shv | GG\27\008\X2 | GG | 27 | 8 | X2 | 1 Prestrip - Thick | 50.9554 | 0 | 32.1389 | 2026-08-06 02:10 | 2026-08-07 00:11 | 23604.1775 | 23604 | [7 empty] | 0 | 0 | 2.36 | 0 | 0
PH4100XPC#1 | GG\27\008\B | GG | 27 | 8 | B | 1 Prestrip - Thick | 100 | 62.0123 | 62.0123 | 2026-08-07 00:11 | 2026-08-07 20:20 | 45595.5258 | 45596 | [7 empty] | 0 | 0 | 4.56 | 10.42 | 5480.94
TS5500Shv | GG\27\008\B | GG | 27 | 8 | B | 1 Prestrip - Thick | 50.9554 | 29.3689 | 29.3689 | 2026-08-07 00:11 | 2026-08-07 20:20 | 21593.9792 | 21594 | [7 empty] | 0 | 0 | 2.16 | 10.42 | 5480.94
TS6060#1 | GG\27\008\B | GG | 27 | 8 | B | 1 Prestrip - Thick | 49.0446 | 8.6188 | 8.6188 | 2026-08-07 14:11 | 2026-08-07 20:20 | 6337.1162 | 6337 | [7 empty] | 0 | 0 | 0.63 | 10.42 | 5480.94
TS5500Shv | GG\27\010\X1 | GG | 27 | 10 | X1 | 1 Prestrip - Thick | 12.3544 | 12.3544 | 12.3544 | 2026-08-07 20:20 | 2026-08-11 08:22 | 89709.1063 | 89709 | [7 empty] | 0 | 0 | 6.79 | 14.47 | 5139.24
PH4100XPC#1 | GG\27\010\X1 | GG | 27 | 10 | X1 | 1 Prestrip - Thick | 100 | 45.4884 | 45.4884 | 2026-08-07 20:20 | 2026-08-13 19:03 | 330305.6571 | 330306 | [7 empty] | 0 | 0 | 25.01 | 14.47 | 5139.24
TS6060#1 | GG\27\009\X1 | GG | 27 | 9 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-08-07 20:20 | 2026-08-08 09:44 | 18150.877 | [6 empty] | 18151 | 13054 | 1.3 | 0 | 0 | 14.13 | 5152
TS6060#1 | GG\27\009\X2 | GG | 27 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 67.3956 | 2026-08-08 09:44 | 2026-08-10 06:13 | 45885.5402 | 45886 | [7 empty] | 0 | 0 | 4.57 | 0 | 0
TS5500Exc | GG\27\009\X2 | GG | 27 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 32.6044 | 2026-08-09 05:07 | 2026-08-10 06:13 | 22198.3398 | 22198 | [7 empty] | 0 | 0 | 2.21 | 0 | 0
TS6060#1 | GG\27\009\B | GG | 27 | 9 | B | 1 Prestrip - Thick | 30.0372 | 30.0372 | 30.0372 | 2026-08-10 06:13 | 2026-08-11 06:02 | 24576.4755 | 24576 | [7 empty] | 0 | 0 | 2.45 | 10.38 | 5495.39
TS5500Exc | SC\41\016\D | SC | 41 | 16 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-08-10 06:13 | 2026-08-11 09:04 | 33827.8574 | [6 empty] | 33828 | 25318 | 3.86 | 0 | 0 | 7.29 | 5766
DRE2 | GG\23\007\D | GG | 23 | 7 | D | 6 DL | 100 | 100 | 100 | 2026-08-10 19:40 | 2026-08-16 03:27 | 429823.4129 |  |  |  | 10008 | 429823 | 190143 |  |  | 0 | 20.02 | 0 | 6.59 | 5806.78
TS Fleet 5 | GG\27\011\X1 | GG | 27 | 11 | X1 | 1 Prestrip - Thick | 37.6159 | 37.6159 | 37.6159 | 2026-08-11 03:57 | 2026-08-16 14:05 | 255073.9076 | 255074 | [7 empty] | 0 | 0 | 31.38 | 14.65 | 5129.38
TS6060#1 | GG\23\008\D | GG | 23 | 8 | D | 8 Coal Mining | 89.4 | 0 | 89.4 | 2026-08-11 06:02 | 2026-08-12 22:42 | 55040.7442 | [6 empty] | 55041 | 41180 | 4.12 | 0 | 0 | 6.56 | 5810
TS5500Shv | GG\23\008\D | GG | 23 | 8 | D | 8 Coal Mining | 10.6 | 0 | 10.6 | 2026-08-11 08:22 | 2026-08-11 13:45 | 6560.2576 | [6 empty] | 6560 | 4908 | 0.49 | 0 | 0 | 6.56 | 5810
TS5500Exc | SC\41\017\D | SC | 41 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-08-11 09:04 | 2026-08-13 12:00 | 64159.7642 | [6 empty] | 64160 | 48017 | 3.71 | 0 | 0 | 7.16 | 5777
TS5500Shv | GG\27\009\B | GG | 27 | 9 | B | 1 Prestrip - Thick | 31.2075 | 31.2075 | 31.2075 | 2026-08-11 13:45 | 2026-08-12 13:34 | 25534.0006 | 25534 | [7 empty] | 0 | 0 | 2.55 | 10.38 | 5495.39
DRE1 | SC\41\014\D | SC | 41 | 14 | D | 6 DL | 100 | 0 | 100 | 2026-08-11 20:02 | 2026-08-19 09:24 | 633543.1949 |  |  |  | 48178 | 633543 | 433604 |  |  | 0 | 40 | 0 | 7.55 | 5745.59
TS5500Shv | GG\27\011\X1 | GG | 27 | 11 | X1 | 1 Prestrip - Thick | 15.8873 | 15.8873 | 15.8873 | 2026-08-12 13:34 | 2026-08-16 18:19 | 107732.2022 | 107732 | [7 empty] | 0 | 0 | 13.25 | 14.65 | 5129.38
TS6060#1 | GG\27\010\X1 | GG | 27 | 10 | X1 | 1 Prestrip - Thick | 11.6947 | 2.8316 | 2.8316 | 2026-08-12 22:42 | 2026-08-13 19:03 | 20561.3131 | 20561 | [7 empty] | 0 | 0 | 1.56 | 14.47 | 5139.24
TS5500Exc | SC\41\015\D | SC | 41 | 15 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-08-13 12:00 | 2026-08-15 14:25 | 63501.8593 | [6 empty] | 63502 | 47528 | 3.96 | 0 | 0 | 7.42 | 5756
PH4100XPC#1 | GG\27\009\B | GG | 27 | 9 | B | 1 Prestrip - Thick | 100 | 38.7554 | 38.7554 | 2026-08-13 19:03 | 2026-08-14 09:03 | 31709.7322 | 31710 | [7 empty] | 0 | 0 | 3.16 | 10.38 | 5495.39
TS6060#1 | GG\27\010\X1 | GG | 27 | 10 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-08-13 19:03 | 2026-08-14 01:28 | 8689.2958 | [6 empty] | 8689 | 6234 | 0.62 | 0 | 0 | 14.47 | 5139
TS6060#1 | GG\27\011\X1 | GG | 27 | 11 | X1 | 1 Prestrip - Thick | 15.0105 | 12.8991 | 12.8991 | 2026-08-14 01:28 | 2026-08-17 16:03 | 87469.1197 | 87469 | [7 empty] | 0 | 0 | 10.76 | 14.65 | 5129.38
PH4100XPC#1 | GG\27\011\X1 | GG | 27 | 11 | X1 | 1 Prestrip - Thick | 100 | 27.1202 | 27.1202 | 2026-08-14 09:03 | 2026-08-17 16:03 | 183902.4739 | 183902 | [7 empty] | 0 | 0 | 22.62 | 14.65 | 5129.38
TS5500Exc | GG\27\011\X1 | GG | 27 | 11 | X1 | 1 Prestrip - Thick | 13.1497 | 6.4773 | 6.4773 | 2026-08-15 14:25 | 2026-08-17 16:03 | 43922.8212 | 43923 | [7 empty] | 0 | 0 | 5.4 | 14.65 | 5129.38
DRE2 | GG\23\006\D | GG | 23 | 6 | D | 6 DL | 100 | 100 | 100 | 2026-08-16 03:27 | 2026-08-21 10:50 | 428516.7479 |  |  |  | 7980 | 428517 | 191516 |  |  | 0 | 19.95 | 0 | 6.63 | 5802.72
TS Fleet 5 | GG\27\012\X1 | GG | 27 | 12 | X1 | 1 Prestrip - Thick | 34.995 | 34.995 | 34.995 | 2026-08-16 14:05 | 2026-08-20 14:57 | 189848.4845 | 189848 | [7 empty] | 0 | 0 | 23.59 | 14.84 | 5112.55
TS5500Shv | GG\23\007\D | GG | 23 | 7 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-08-16 18:19 | 2026-08-17 18:07 | 29011.1202 | [6 empty] | 29011 | 21705 | 2.17 | 0 | 0 | 6.59 | 5807
PH4100XPC#1 | GG\27\012\X1 | GG | 27 | 12 | X1 | 1 Prestrip - Thick | 100 | 40.282 | 40.282 | 2026-08-17 16:03 | 2026-08-21 15:27 | 218530.373 | 218530 | [7 empty] | 0 | 0 | 27.15 | 14.84 | 5112.55
TS6060#1 | GG\23\007\D | GG | 23 | 7 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-08-17 16:03 | 2026-08-18 15:50 | 32199.1554 | [6 empty] | 32199 | 24091 | 2.41 | 0 | 0 | 6.59 | 5807
TS5500Exc | GG\27\012\X1 | GG | 27 | 12 | X1 | 1 Prestrip - Thick | 12.6475 | 12.6475 | 12.6475 | 2026-08-17 16:03 | 2026-08-20 21:33 | 68612.7878 | 68613 | [7 empty] | 0 | 0 | 8.53 | 14.84 | 5112.55
TS5500Shv | GG\27\010\X1 | GG | 27 | 10 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-08-17 18:07 | 2026-08-18 00:32 | 7828.9695 | [6 empty] | 7829 | 5616 | 0.56 | 0 | 0 | 14.47 | 5139
TS5500Shv | GG\27\010\X2 | GG | 27 | 10 | X2 | 1 Prestrip - Thick | 41.9193 | 0 | 41.9193 | 2026-08-18 00:32 | 2026-08-19 02:55 | 28282.8927 | 28283 | [7 empty] | 0 | 0 | 2.82 | 0 | 0
TS6060#1 | GG\27\010\X2 | GG | 27 | 10 | X2 | 1 Prestrip - Thick | 40.3473 | 0 | 40.3473 | 2026-08-18 15:50 | 2026-08-19 18:13 | 27222.2842 | 27222 | [7 empty] | 0 | 0 | 2.71 | 0 | 0
TS5500Shv | GG\27\011\X1 | GG | 27 | 11 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-08-19 02:55 | 2026-08-19 08:46 | 7129.1281 | [6 empty] | 7129 | 5109 | 0.51 | 0 | 0 | 14.65 | 5129
TS5500Shv | GG\27\012\X1 | GG | 27 | 12 | X1 | 1 Prestrip - Thick | 15.2201 | 10.7408 | 10.7408 | 2026-08-19 08:46 | 2026-08-21 15:27 | 58268.8362 | 58269 | [7 empty] | 0 | 0 | 7.24 | 14.84 | 5112.55
DRE1 | SC\41\013\D | SC | 41 | 13 | D | 6 DL | 100 | 0 | 100 | 2026-08-19 09:24 | 2026-08-27 00:13 | 638599.5993 |  |  |  | 48563 | 638600 | 437064 |  |  | 0 | 40 | 0 | 7.47 | 5753.2
TS6060#1 | GG\27\011\X1 | GG | 27 | 11 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-08-19 18:13 | 2026-08-20 00:04 | 7912.5487 | [6 empty] | 7913 | 5670 | 0.57 | 0 | 0 | 14.65 | 5129
TS6060#1 | GG\27\011\X2 | GG | 27 | 11 | X2 | 1 Prestrip - Thick | 49.0446 | 0 | 49.0446 | 2026-08-20 00:04 | 2026-08-21 08:18 | 33261.1677 | 33261 | [7 empty] | 0 | 0 | 3.34 | 0 | 0
TS Fleet 5 | GG\27\013\X1 | GG | 27 | 13 | X1 | 1 Prestrip - Thick | 38.119 | 38.119 | 38.119 | 2026-08-20 14:57 | 2026-08-24 01:25 | 161650.3241 | 161650 | [7 empty] | 0 | 0 | 17.88 | 14.84 | 5111.78
TS5500Exc | SC\41\014\D | SC | 41 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-08-20 21:33 | 2026-08-23 00:37 | 64324.3986 | [6 empty] | 64324 | 48105 | 4.01 | 0 | 0 | 7.55 | 5746
TS6060#1 | GG\27\012\X1 | GG | 27 | 12 | X1 | 1 Prestrip - Thick | 14.4705 | 1.3348 | 1.3348 | 2026-08-21 08:18 | 2026-08-21 15:27 | 7241.2205 | 7241 | [7 empty] | 0 | 0 | 0.9 | 14.84 | 5112.55
DRE2 | GG\23\005\D | GG | 23 | 5 | D | 6 DL | 100 | 100 | 100 | 2026-08-21 10:50 | 2026-08-26 16:18 | 422040.4125 |  |  |  | 7859 | 422040 | 188621 |  |  | 0 | 19.64 | 0 | 6.67 | 5799.27
PH4100XPC#1 | GG\27\010\X2 | GG | 27 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 17.7333 | 2026-08-21 15:27 | 2026-08-21 20:44 | 11964.6462 | 11965 | [7 empty] | 0 | 0 | 1.19 | 0 | 0
TS6060#1 | GG\23\006\D | GG | 23 | 6 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-08-21 15:27 | 2026-08-22 15:03 | 31942.9794 | [6 empty] | 31943 | 23918 | 2.39 | 0 | 0 | 6.63 | 5803
TS5500Shv | GG\23\006\D | GG | 23 | 6 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-08-21 15:27 | 2026-08-22 15:03 | 28780.3082 | [6 empty] | 28780 | 21550 | 2.16 | 0 | 0 | 6.63 | 5803
PH4100XPC#1 | GG\27\010\B | GG | 27 | 10 | B | 1 Prestrip - Thick | 100 | 73.2161 | 73.2161 | 2026-08-21 20:44 | 2026-08-23 01:59 | 66209.1954 | 66209 | [7 empty] | 0 | 0 | 6.59 | 10.89 | 5462.18
TS6060#1 | GG\27\010\B | GG | 27 | 10 | B | 1 Prestrip - Thick | 34.5291 | 12.4761 | 12.4761 | 2026-08-22 15:03 | 2026-08-23 01:59 | 11282.0934 | 11282 | [7 empty] | 0 | 0 | 1.12 | 10.89 | 5462.18
TS5500Shv | GG\27\010\B | GG | 27 | 10 | B | 1 Prestrip - Thick | 35.8744 | 12.9621 | 12.9621 | 2026-08-22 15:03 | 2026-08-23 01:59 | 11721.6554 | 11722 | [7 empty] | 0 | 0 | 1.17 | 10.89 | 5462.18
TS5500Exc | GG\27\010\B | GG | 27 | 10 | B | 1 Prestrip - Thick | 29.5964 | 1.3457 | 1.3457 | 2026-08-23 00:37 | 2026-08-23 01:59 | 1216.9412 | 1217 | [7 empty] | 0 | 0 | 0.12 | 10.89 | 5462.18
PH4100XPC#1 | GG\27\011\X2 | GG | 27 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 34.5789 | 2026-08-23 01:59 | 2026-08-23 12:21 | 23450.7934 | 23451 | [7 empty] | 0 | 0 | 2.36 | 0 | 0
TS6060#1 | GG\27\012\X1 | GG | 27 | 12 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-08-23 01:59 | 2026-08-23 07:26 | 7377.3308 | [6 empty] | 7377 | 5282 | 0.53 | 0 | 0 | 14.84 | 5113
TS5500Exc | GG\27\013\X1 | GG | 27 | 13 | X1 | 1 Prestrip - Thick | 6.675 | 6.675 | 6.675 | 2026-08-23 01:59 | 2026-08-24 09:56 | 28306.6809 | 28307 | [7 empty] | 0 | 0 | 3.13 | 14.84 | 5111.78
TS5500Shv | GG\27\011\X2 | GG | 27 | 11 | X2 | 1 Prestrip - Thick | 50.9554 | 0 | 16.3765 | 2026-08-23 01:59 | 2026-08-23 12:21 | 11106.2639 | 11106 | [7 empty] | 0 | 0 | 1.12 | 0 | 0
TS6060#1 | GG\27\013\X1 | GG | 27 | 13 | X1 | 1 Prestrip - Thick | 10.8274 | 10.8274 | 10.8274 | 2026-08-23 07:26 | 2026-08-25 04:46 | 45915.315 | 45915 | [7 empty] | 0 | 0 | 5.08 | 14.84 | 5111.78
PH4100XPC#1 | GG\27\011\B | GG | 27 | 11 | B | 1 Prestrip - Thick | 100 | 66.5159 | 66.5159 | 2026-08-23 12:21 | 2026-08-24 16:33 | 63823.2337 | 63823 | [7 empty] | 0 | 0 | 6.39 | 11.47 | 5410.87
TS5500Shv | GG\27\011\B | GG | 27 | 11 | B | 1 Prestrip - Thick | 37.0206 | 31.5018 | 31.5018 | 2026-08-23 12:21 | 2026-08-24 16:33 | 30226.5968 | 30227 | [7 empty] | 0 | 0 | 3.03 | 11.47 | 5410.87
PH4100A | SC\45\011\D | SC | 45 | 11 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-08-23 19:25 | 2026-09-05 05:47 | 542586.192 | 542586 | [7 empty] | 0 | 0 | 40.08 | 7.3 | 5750.53
TS Fleet 5 | GG\27\014\X1 | GG | 27 | 14 | X1 | 1 Prestrip - Thick | 37.4673 | 37.4673 | 37.4673 | 2026-08-24 01:25 | 2026-08-26 13:36 | 117954.6576 | 117955 | [7 empty] | 0 | 0 | 12.27 | 14.8 | 5113.61
TS5500Exc | W2\06\004\B | W2 | 6 | 4 | B | 8 Coal Mining | 6 | 0 | 6 | 2026-08-24 09:56 | 2026-08-24 14:23 | 5621.8083 | [6 empty] | 5622 | 3951 | 0.2 | 0 | 0 | 9.89 | 5287
TS5500Exc | GG\27\011\B | GG | 27 | 11 | B | 1 Prestrip - Thick | 27.3471 | 1.9823 | 1.9823 | 2026-08-24 14:23 | 2026-08-24 16:33 | 1902.021 | 1902 | [7 empty] | 0 | 0 | 0.19 | 11.47 | 5410.87
TS5500Shv | GG\27\012\X1 | GG | 27 | 12 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-08-24 16:33 | 2026-08-24 22:00 | 6646.902 | [6 empty] | 6647 | 4759 | 0.48 | 0 | 0 | 14.84 | 5113
PH4100XPC#1 | GG\27\013\X1 | GG | 27 | 13 | X1 | 1 Prestrip - Thick | 100 | 36.6065 | 36.6065 | 2026-08-24 16:33 | 2026-08-27 14:24 | 155235.9863 | 155236 | [7 empty] | 0 | 0 | 17.17 | 14.84 | 5111.78
TS5500Exc | GG\27\014\X1 | GG | 27 | 14 | X1 | 1 Prestrip - Thick | 29.2385 | 29.2385 | 29.2385 | 2026-08-24 16:33 | 2026-08-29 00:16 | 92048.557 | 92049 | [7 empty] | 0 | 0 | 9.58 | 14.8 | 5113.61
TS5500Shv | GG\27\012\X2 | GG | 27 | 12 | X2 | 1 Prestrip - Thick | 50.9554 | 0 | 50.9554 | 2026-08-24 22:00 | 2026-08-26 07:11 | 35573.651 | 35574 | [7 empty] | 0 | 0 | 3.59 | 0 | 0
TS6060#1 | W2\06\004\B | W2 | 6 | 4 | B | 8 Coal Mining | 94 | 0 | 94 | 2026-08-25 04:46 | 2026-08-27 22:17 | 88667.7838 | [6 empty] | 88668 | 62315 | 3.11 | 0 | 0 | 9.89 | 5287
TS5500Shv | GG\27\013\X1 | GG | 27 | 13 | X1 | 1 Prestrip - Thick | 11.2855 | 7.7721 | 7.7721 | 2026-08-26 07:11 | 2026-08-27 14:24 | 32958.8721 | 32959 | [7 empty] | 0 | 0 | 3.65 | 14.84 | 5111.78
TS Fleet 5 | GG\27\017\X1 | GG | 27 | 17 | X1 | 1 Prestrip - Thick | 38.5419 | 38.5419 | 38.5419 | 2026-08-26 13:36 | 2026-08-28 09:35 | 86212.5774 | 86213 | [7 empty] | 0 | 0 | 9.01 | 14.57 | 5130.52
DRE2 | GG\23\004\D | GG | 23 | 4 | D | 6 DL | 100 | 100 | 100 | 2026-08-26 16:18 | 2026-08-31 15:21 | 400456.195 |  |  |  | 6526 | 400456 | 115149 |  |  | 0 | 19.67 | 0 | 6.63 | 5802.25
DRE1 | SC\41\012\D | SC | 41 | 12 | D | 6 DL | 100 | 0 | 100 | 2026-08-27 00:13 | 2026-09-03 11:38 | 626728.1999 |  |  |  | 47660 | 626728 | 428939 |  |  | 0 | 40 | 0 | 7.46 | 5756.51
TS5500Shv | GG\23\005\D | GG | 23 | 5 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-08-27 14:24 | 2026-08-28 13:49 | 28554.0188 | [6 empty] | 28554 | 21397 | 2.14 | 0 | 0 | 6.67 | 5799
PH4100XPC#1 | GG\27\012\X2 | GG | 27 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 49.0446 | 2026-08-27 14:24 | 2026-08-28 05:32 | 34239.639 | 34240 | [7 empty] | 0 | 0 | 3.46 | 0 | 0
TS6060#1 | GG\23\005\D | GG | 23 | 5 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-08-27 22:17 | 2026-08-28 21:42 | 31691.823 | [6 empty] | 31692 | 23749 | 2.37 | 0 | 0 | 6.67 | 5799
PH4100XPC#1 | GG\27\012\B | GG | 27 | 12 | B | 1 Prestrip - Thick | 100 | 64.0498 | 64.0498 | 2026-08-28 05:32 | 2026-08-29 12:13 | 69478.6923 | 69479 | [7 empty] | 0 | 0 | 6.97 | 11.77 | 5369.87
TS Fleet 5 | GG\27\018\X2 | GG | 27 | 18 | X2 | 1 Prestrip - Thick | 46.4856 | 0 | 46.4856 | 2026-08-28 09:35 | 2026-08-30 09:54 | 94686.0541 | 94686 | [7 empty] | 0 | 0 | 9.75 | 0 | 0
TS5500Shv | GG\27\012\B | GG | 27 | 12 | B | 1 Prestrip - Thick | 50.9554 | 22.1417 | 22.1417 | 2026-08-28 13:49 | 2026-08-29 12:13 | 24018.4269 | 24018 | [7 empty] | 0 | 0 | 2.41 | 11.77 | 5369.87
TS6060#1 | GG\27\012\B | GG | 27 | 12 | B | 1 Prestrip - Thick | 49.0446 | 13.8085 | 13.8085 | 2026-08-28 21:42 | 2026-08-29 12:13 | 14978.8719 | 14979 | [7 empty] | 0 | 0 | 1.5 | 11.77 | 5369.87
TS5500Exc | SC\41\013\D | SC | 41 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-08-29 00:16 | 2026-08-31 05:55 | 67561.7788 | [6 empty] | 67562 | 50367 | 4.2 | 0 | 0 | 7.47 | 5753
PH4100XPC#1 | GG\27\014\X1 | GG | 27 | 14 | X1 | 1 Prestrip - Thick | 100 | 33.2942 | 33.2942 | 2026-08-29 12:13 | 2026-08-31 13:02 | 104816.7861 | 104817 | [7 empty] | 0 | 0 | 10.91 | 14.8 | 5113.61
TS6060#1 | GG\27\013\X1 | GG | 27 | 13 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-08-29 12:13 | 2026-08-29 17:18 | 6871.9259 | [6 empty] | 6872 | 4922 | 0.5 | 0 | 0 | 14.84 | 5112
TS5500Shv | GG\27\013\X1 | GG | 27 | 13 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-08-29 12:13 | 2026-08-29 17:18 | 6191.5372 | [6 empty] | 6192 | 4435 | 0.45 | 0 | 0 | 14.84 | 5112
TS6060#1 | GG\27\013\B | GG | 27 | 13 | B | 1 Prestrip - Thick | 35.3771 | 35.3771 | 35.3771 | 2026-08-29 17:18 | 2026-09-01 11:30 | 68313.5175 | 68314 | [7 empty] | 0 | 0 | 6.89 | 12.03 | 5324.05
TS5500Shv | GG\27\013\B | GG | 27 | 13 | B | 1 Prestrip - Thick | 36.7554 | 36.7554 | 36.7554 | 2026-08-29 17:18 | 2026-09-01 11:30 | 70975.0831 | 70975 | [7 empty] | 0 | 0 | 7.15 | 12.03 | 5324.05
TS Fleet 5 | GG\27\019\B | GG | 27 | 19 | B | 1 Prestrip - Thick | 34.2487 | 34.2487 | 34.2487 | 2026-08-30 09:54 | 2026-09-01 11:05 | 96391.9096 | 96392 | [7 empty] | 0 | 0 | 9.78 | 16.39 | 5019.41
TS5500Exc | GG\27\017\X1 | GG | 27 | 17 | X1 | 1 Prestrip - Thick | 18.174 | 18.174 | 18.174 | 2026-08-31 05:55 | 2026-09-02 03:41 | 40652.5959 | 40653 | [7 empty] | 0 | 0 | 4.25 | 14.57 | 5130.52
PH4100XPC#1 | GG\27\013\B | GG | 27 | 13 | B | 1 Prestrip - Thick | 100 | 26.9299 | 26.9299 | 2026-08-31 13:02 | 2026-09-01 12:00 | 52001.9331 | 52002 | [7 empty] | 0 | 0 | 5.24 | 12.03 | 5324.05
DRE2 | GG\24\013\B | GG | 24 | 13 | B | 6 DL | 100 | 0 | 100 | 2026-08-31 15:21 | 2026-09-03 03:03 | 200830.1394 |  |  |  |  | 200830 | 167358 |  |  | 0 | 16.75 | 0 | 12.15 | 5320.62
TS Fleet 5 | GG\27\013\B | GG | 27 | 13 | B | 1 Prestrip - Thick | 32.4612 | 0.93759 | 0.93759 | 2026-09-01 11:05 | 2026-09-01 12:00 | 1810.5043 | 1811 | [7 empty] | 0 | 0 | 0.18 | 12.03 | 5324.05
TS5500Shv | GG\23\004\D | GG | 23 | 4 | D | 7 PostStrip | 67.9546 | 0 | 67.9546 | 2026-09-01 11:30 | 2026-09-02 13:48 | 28186.9241 |  |  | 28187 | [5 empty] | 0 | 0 | 0 | 6.63 | 5802.25
TS6060#1 | GG\23\004\D | GG | 23 | 4 | D | 7 PostStrip | 32.0454 | 0 | 32.0454 | 2026-09-01 11:30 | 2026-09-02 00:23 | 13292.1171 |  |  | 13292 | [5 empty] | 0 | 0 | 0 | 6.63 | 5802.25
TS Fleet 5 | W1\04\003\B | W1 | 4 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-09-01 12:00 | 2026-09-01 19:50 | 15357.6206 | 15358 | [7 empty] | 0 | 0 | 0.75 | 11.44 | 5098.38
PH4100XPC#1 | GG\27\017\X1 | GG | 27 | 17 | X1 | 1 Prestrip - Thick | 100 | 43.284 | 43.284 | 2026-09-01 12:00 | 2026-09-03 09:46 | 96819.8985 | 96820 | [7 empty] | 0 | 0 | 10.12 | 14.57 | 5130.52
TS Fleet 5 | W1\04\004\A | W1 | 4 | 4 | A | 1 Prestrip - Thick | 100 | 0 | 100 | 2026-09-01 19:50 | 2026-09-14 19:32 | 610932.5255 | 610933 | [7 empty] | 0 | 0 | 31.49 | 0 | 0
TS6060#1 | GG\27\014\X1 | GG | 27 | 14 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-09-02 00:23 | 2026-09-02 05:01 | 6271.205 | [6 empty] | 6271 | 4498 | 0.48 | 0 | 0 | 14.8 | 5114
TS5500Exc | GG\27\019\B | GG | 27 | 19 | B | 1 Prestrip - Thick | 9.2324 | 9.2324 | 9.2324 | 2026-09-02 03:41 | 2026-09-03 09:03 | 25984.3912 | 25984 | [7 empty] | 0 | 0 | 2.64 | 16.39 | 5019.41
TS6060#1 | GG\27\019\B | GG | 27 | 19 | B | 1 Prestrip - Thick | 14.9799 | 14.9799 | 14.9799 | 2026-09-02 05:01 | 2026-09-03 22:00 | 42160.3873 | 42160 | [7 empty] | 0 | 0 | 4.28 | 16.39 | 5019.41
TS5500Shv | GG\23\004\D | GG | 23 | 4 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-09-02 13:48 | 2026-09-03 08:58 | 23375.2998 | [6 empty] | 23375 | 17516 | 2.14 | 0 | 0 | 6.63 | 5802
DRE2 | GG\24\014\B | GG | 24 | 14 | B | 6 DL | 100 | 0 | 100 | 2026-09-03 03:03 | 2026-09-04 18:34 | 132922.2023 |  |  |  |  | 132922 | 110769 |  |  | 0 | 16.3 | 0 | 12.41 | 5288.96
TS5500Shv | GG\24\013\B | GG | 24 | 13 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-09-03 08:58 | 2026-09-04 03:52 | 23031.9212 | [6 empty] | 23032 | 16708 | 1.67 | 0 | 0 | 12.15 | 5321
TS5500Exc | SC\51\020\D | SC | 51 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-09-03 09:03 | 2026-10-27 06:23 | 1145408.43 | 1145408 | [7 empty] | 0 | 0 | 53.04 | 7.38 | 5763.19
PH4100XPC#1 | GG\27\018\X2 | GG | 27 | 18 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.5144 | 2026-09-03 09:46 | 2026-09-05 12:02 | 109003.1585 | 109003 | [7 empty] | 0 | 0 | 11.23 | 0 | 0
DRE1 | SC\41\011\D | SC | 41 | 11 | D | 6 DL | 100 | 0 | 100 | 2026-09-03 11:38 | 2026-09-10 21:41 | 621963.7593 |  |  |  | 47298 | 621964 | 425679 |  |  | 0 | 40 | 0 | 7.57 | 5747.47
TS6060#1 | GG\23\004\D | GG | 23 | 4 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-09-03 22:00 | 2026-09-04 17:11 | 25944.0141 | [6 empty] | 25944 | 19441 | 2.37 | 0 | 0 | 6.63 | 5802
TS5500Shv | GG\27\014\X1 | GG | 27 | 14 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-09-04 03:52 | 2026-09-04 08:30 | 5650.2936 | [6 empty] | 5650 | 4053 | 0.43 | 0 | 0 | 14.8 | 5114
TS5500Shv | GG\27\014\B | GG | 27 | 14 | B | 1 Prestrip - Thick | 32.6295 | 32.6295 | 32.6295 | 2026-09-04 08:30 | 2026-09-06 18:01 | 61669.9706 | 61670 | [7 empty] | 0 | 0 | 6.79 | 12.28 | 5289.79
TS6060#1 | GG\24\013\B | GG | 24 | 13 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-09-04 17:11 | 2026-09-05 12:04 | 25562.9016 | [6 empty] | 25563 | 18544 | 1.85 | 0 | 0 | 12.15 | 5321
DRE2 | GG\24\017\B | GG | 24 | 17 | B | 6 DL | 100 | 0 | 100 | 2026-09-04 18:34 | 2026-09-06 09:49 | 131989.4354 |  |  |  |  | 131989 | 109991 |  |  | 0 | 16.11 | 0 | 13.42 | 5216.22
PH4100A | SC\45\012\D | SC | 45 | 12 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-09-05 05:47 | 2026-09-14 01:57 | 387083.3364 | 387083 | [7 empty] | 0 | 0 | 36.09 | 7.28 | 5754.71
PH4100XPC#1 | GG\27\014\B | GG | 27 | 14 | B | 1 Prestrip - Thick | 100 | 67.3705 | 67.3705 | 2026-09-05 12:02 | 2026-09-07 20:18 | 127330.4354 | 127330 | [7 empty] | 0 | 0 | 14.02 | 12.28 | 5289.79
TS6060#1 | GG\27\018\B | GG | 27 | 18 | B | 1 Prestrip - Thick | 100 | 54.593 | 54.593 | 2026-09-05 12:04 | 2026-09-08 17:00 | 79386.7063 | 79387 | [7 empty] | 0 | 0 | 7.92 | 14.76 | 5128.3
DRE2 | GG\24\018\B | GG | 24 | 18 | B | 6 DL | 100 | 0 | 100 | 2026-09-06 09:49 | 2026-09-08 21:10 | 199643.5064 |  |  |  |  | 199644 | 166370 |  |  | 0 | 16.52 | 0 | 13.32 | 5240.93
TS5500Shv | GG\24\014\B | GG | 24 | 14 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-09-06 18:01 | 2026-09-07 06:03 | 14676.0688 | [6 empty] | 14676 | 10636 | 1.66 | 0 | 0 | 12.41 | 5289
TS5500Shv | GG\24\017\B | GG | 24 | 17 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-09-07 06:03 | 2026-09-07 18:11 | 14796.4078 | [6 empty] | 14796 | 10661 | 1.62 | 0 | 0 | 13.42 | 5216
TS5500Shv | GG\27\017\X1 | GG | 27 | 17 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-09-07 18:11 | 2026-09-07 23:08 | 6029.4767 | [6 empty] | 6029 | 4330 | 0.45 | 0 | 0 | 14.57 | 5131
PH4100XPC#1 | GG\27\018\B | GG | 27 | 18 | B | 1 Prestrip - Thick | 100 | 32.2345 | 32.2345 | 2026-09-07 20:18 | 2026-09-08 17:00 | 46874.0216 | 46874 | [7 empty] | 0 | 0 | 4.68 | 14.76 | 5128.3
TS5500Shv | GG\27\018\B | GG | 27 | 18 | B | 1 Prestrip - Thick | 17.1496 | 13.1725 | 13.1725 | 2026-09-07 23:08 | 2026-09-08 17:00 | 19154.8796 | 19155 | [7 empty] | 0 | 0 | 1.91 | 14.76 | 5128.3
PH4100XPC#1 | GG\27\019\B | GG | 27 | 19 | B | 1 Prestrip - Thick | 100 | 28.1719 | 28.1719 | 2026-09-08 17:00 | 2026-09-10 04:12 | 79288.921 | 79289 | [7 empty] | 0 | 0 | 8.04 | 16.39 | 5019.41
TS6060#1 | GG\24\014\B | GG | 24 | 14 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-09-08 17:00 | 2026-09-09 05:02 | 16288.8236 | [6 empty] | 16289 | 11805 | 1.84 | 0 | 0 | 12.41 | 5289
TS5500Shv | GG\27\019\B | GG | 27 | 19 | B | 1 Prestrip - Thick | 15.5622 | 13.367 | 13.367 | 2026-09-08 17:00 | 2026-09-10 04:12 | 37620.9121 | 37621 | [7 empty] | 0 | 0 | 3.82 | 16.39 | 5019.41
DRE2 | GG\24\019\B | GG | 24 | 19 | B | 6 DL | 100 | 0 | 100 | 2026-09-08 21:10 | 2026-09-11 09:44 | 203760.9693 |  |  |  |  | 203761 | 169801 |  |  | 0 | 17.08 | 0 | 13.91 | 5215.35
TS6060#1 | GG\24\017\B | GG | 24 | 17 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-09-09 05:02 | 2026-09-09 17:10 | 16422.3867 | [6 empty] | 16422 | 11833 | 1.8 | 0 | 0 | 13.42 | 5216
TS6060#1 | GG\24\018\B | GG | 24 | 18 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-09-09 17:10 | 2026-09-10 12:05 | 25596.5106 | [6 empty] | 25597 | 18433 | 1.84 | 0 | 0 | 13.32 | 5241
TS5500Shv | GG\24\018\B | GG | 24 | 18 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-09-10 04:12 | 2026-09-10 23:07 | 23062.2026 | [6 empty] | 23062 | 16608 | 1.66 | 0 | 0 | 13.32 | 5241
PH4100XPC#1 | W2\01\005\A | W2 | 1 | 5 | A | 1 Prestrip - Thick | 100 | 0 | 100 | 2026-09-10 04:12 | 2026-11-18 20:27 | 3855510.66 | 3855511 | [7 empty] | 0 | 0 | 50.49 | 0 | 0
TS6060#1 | GG\27\017\X1 | GG | 27 | 17 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-09-10 12:05 | 2026-09-10 17:02 | 6692.0565 | [6 empty] | 6692 | 4806 | 0.5 | 0 | 0 | 14.57 | 5131
TS6060#1 | GG\27\017\B | GG | 27 | 17 | B | 1 Prestrip - Thick | 23.4005 | 23.4005 | 23.4005 | 2026-09-10 17:02 | 2026-09-12 15:27 | 47900.7552 | 47901 | [7 empty] | 0 | 0 | 5.13 | 14.27 | 5144.85
DRE1 | SC\41\010\D | SC | 41 | 10 | D | 6 DL | 100 | 0 | 100 | 2026-09-10 21:41 | 2026-09-21 03:58 | 860306.3181 |  |  |  | 48314 | 860306 | 374465 |  |  | 0 | 40 | 0 | 7.65 | 5740.91
TS5500Shv | GG\27\017\B | GG | 27 | 17 | B | 1 Prestrip - Thick | 24.3122 | 24.3122 | 24.3122 | 2026-09-10 23:07 | 2026-09-12 21:32 | 49767.0184 | 49767 | [7 empty] | 0 | 0 | 5.33 | 14.27 | 5144.85
DRE2 | GG\24\020\B | GG | 24 | 20 | B | 6 DL | 100 | 0 | 100 | 2026-09-11 09:44 | 2026-09-15 03:59 | 303556.1425 |  |  |  |  | 303556 | 233505 |  |  | 0 | 22.09 | 0 | 16.53 | 5021.02
TS6060#1 | GG\24\019\B | GG | 24 | 19 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-09-12 15:27 | 2026-09-13 10:10 | 25319.3475 | [6 empty] | 25319 | 18153 | 1.82 | 0 | 0 | 13.91 | 5215
TS5500Shv | GG\24\019\B | GG | 24 | 19 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-09-12 21:32 | 2026-09-13 16:15 | 22812.4814 | [6 empty] | 22812 | 16356 | 1.64 | 0 | 0 | 13.91 | 5215
TS6060#1 | CP\03\002\D | CP | 3 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-09-13 10:10 | 2026-10-14 01:43 | 758942.5997 | 758943 | [7 empty] | 0 | 0 | 46.5 | 5.98 | 5881.17
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 11:44 |  | 1d 11:44 | 2026-09-13 16:15 | 2026-09-15 03:59
PH4100A | SC\45\013\D | SC | 45 | 13 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-09-14 01:57 | 2026-09-20 09:36 | 271379.5241 | 271380 | [7 empty] | 0 | 0 | 25.4 | 7.43 | 5756.37
TS Fleet 5 | GG\27\017\B | GG | 27 | 17 | B | 1 Prestrip - Thick | 52.2874 | 52.2874 | 52.2874 | 2026-09-14 19:32 | 2026-09-17 02:09 | 107032.2887 | 107032 | [7 empty] | 0 | 0 | 11.47 | 14.27 | 5144.85
DRE2 | GG\24\022\B | GG | 24 | 22 | B | 6 DL | 100 | 0 | 100 | 2026-09-15 03:59 | 2026-09-19 11:23 | 347827.9821 |  |  |  |  | 347828 | 267560 |  |  | 0 | 25.26 | 0 | 21.41 | 4639.45
TS5500Shv | GG\24\020\B | GG | 24 | 20 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-09-15 03:59 | 2026-09-15 14:31 | 12854.787 | [6 empty] | 12855 | 9078 | 0.9 | 0 | 0 | 16.53 | 5021
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 20:52 |  | 3d 20:52 | 2026-09-15 14:31 | 2026-09-19 11:23
TS Fleet 5 | W1\04\004\B | W1 | 4 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-09-17 02:09 | 2026-09-17 12:50 | 20949.1069 | 20949 | [7 empty] | 0 | 0 | 1.03 | 12.03 | 5033.74
TS Fleet 5 | W1\04\005\D | W1 | 4 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-09-17 12:50 | 2026-09-20 12:47 | 141021.3841 | 141021 | [7 empty] | 0 | 0 | 12.17 | 7.71 | 5591.44
DRE2 | GG\23\013\D | GG | 23 | 13 | D | 6 DL | 100 | 100 | 100 | 2026-09-19 11:23 | 2026-09-25 16:22 | 501117.5366 |  |  |  | 11667 | 501118 | 221682 |  |  | 0 | 23.33 | 0 | 6.98 | 5774.65
TS5500Shv | GG\24\022\B | GG | 24 | 22 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-09-19 11:23 | 2026-09-19 18:12 | 8313.8249 | [6 empty] | 8314 | 5713 | 0.53 | 0 | 0 | 21.41 | 4639
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 22:09 |  | 5d 22:09 | 2026-09-19 18:12 | 2026-09-25 16:22
PH4100A | SC\45\014\D | SC | 45 | 14 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-09-20 09:36 | 2026-09-25 12:12 | 216946.386 | 216946 | [7 empty] | 0 | 0 | 19.66 | 7.45 | 5754.68
TS Fleet 5 | W1\05\002\D | W1 | 5 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-09-20 12:47 | 2026-09-30 13:15 | 471329.0738 | 471329 | [7 empty] | 0 | 0 | 21.83 | 7.45 | 5610.43
DRE1 | SC\42\017\D | SC | 42 | 17 | D | 6 DL | 100 | 0 | 100 | 2026-09-21 03:58 | 2026-10-03 17:30 | 1053279.32 |  |  |  | 58488 | 1053279 | 457706 |  |  | 0 | 40 | 0 | 7.2 | 5772.1
PH4100A | SC\45\015\D | SC | 45 | 15 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-09-25 12:12 | 2026-09-29 19:25 | 183870.2524 | 183870 | [7 empty] | 0 | 0 | 16.69 | 7.43 | 5756.09
DRE2 | GG\23\014\D | GG | 23 | 14 | D | 6 DL | 100 | 100 | 100 | 2026-09-25 16:22 | 2026-10-02 09:12 | 541007.1379 |  |  |  | 12596 | 541007 | 239328 |  |  | 0 | 23.76 | 0 | 7.1 | 5763.88
TS5500Shv | GG\23\013\D | GG | 23 | 13 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-09-25 16:22 | 2026-09-26 17:09 | 30233.0356 | [6 empty] | 30233 | 22531 | 2.25 | 0 | 0 | 6.98 | 5775
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 16:02 |  | 5d 16:02 | 2026-09-26 17:09 | 2026-10-02 09:12
PH4100A | SC\45\016\D | SC | 45 | 16 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-09-29 19:25 | 2026-10-06 14:25 | 294546.8297 | 294547 | [7 empty] | 0 | 0 | 21.75 | 7.4 | 5759.01
TS Fleet 5 | W1\05\003\B | W1 | 5 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-09-30 13:15 | 2026-10-12 17:36 | 572992.1235 | 572992 | [7 empty] | 0 | 0 | 28.52 | 11.33 | 5109.96
DRE2 | GG\23\018\D | GG | 23 | 18 | D | 6 DL | 100 | 100 | 100 | 2026-10-02 09:12 | 2026-10-08 14:42 | 502892.0624 |  |  |  | 11709 | 502892 | 222467 |  |  | 0 | 23.41 | 0 | 7.11 | 5763.01
TS5500Shv | GG\23\014\D | GG | 23 | 14 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-10-02 09:12 | 2026-10-03 11:07 | 31607.5623 | [6 empty] | 31608 | 23537 | 2.25 | 0 | 0 | 7.1 | 5764
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 03:35 |  | 5d 03:35 | 2026-10-03 11:07 | 2026-10-08 14:42
DRE1 | SC\42\016\D | SC | 42 | 16 | D | 6 DL | 100 | 0 | 100 | 2026-10-03 17:30 | 2026-10-09 20:53 | 514816.262 |  |  |  | 39150 | 514816 | 352346 |  |  | 0 | 40 | 0 | 7.33 | 5764.22
PH4100A | W2\05\005\B | W2 | 5 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-10-06 14:25 | 2026-11-01 10:23 | 1086519.228 | 1086519 | [7 empty] | 0 | 0 | 52.55 | 10.04 | 5271.12
DRE2 | GG\23\019\D | GG | 23 | 19 | D | 6 DL | 100 | 100 | 100 | 2026-10-08 14:42 | 2026-10-14 16:18 | 489737.6488 |  |  |  | 11403 | 489738 | 216648 |  |  | 0 | 22.79 | 0 | 7.01 | 5771.25
TS5500Shv | GG\23\018\D | GG | 23 | 18 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-10-08 14:42 | 2026-10-09 15:25 | 30130.9667 | [6 empty] | 30131 | 22437 | 2.24 | 0 | 0 | 7.11 | 5763
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 00:53 |  | 5d 00:53 | 2026-10-09 15:25 | 2026-10-14 16:18
DRE1 | SC\42\015\D | SC | 42 | 15 | D | 6 DL | 100 | 0 | 100 | 2026-10-09 20:53 | 2026-10-17 10:35 | 634714.328 |  |  |  | 48267 | 634714 | 434405 |  |  | 0 | 40 | 0 | 7.43 | 5755.89
TS Fleet 5 | W1\05\004\D | W1 | 5 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-10-12 17:36 | 2026-10-17 04:06 | 208732.2127 | 208732 | [7 empty] | 0 | 0 | 15.72 | 7.82 | 5574.67
TS6060#1 | GG\24\020\B | GG | 24 | 20 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-10-14 01:43 | 2026-10-14 12:15 | 14267.401 | [6 empty] | 14267 | 10075 | 1 | 0 | 0 | 16.53 | 5021
TS6060#1 | GG\24\022\B | GG | 24 | 22 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-10-14 12:15 | 2026-10-14 19:04 | 9227.432 | [6 empty] | 9227 | 6340 | 0.59 | 0 | 0 | 21.41 | 4639
DRE2 | GG\23\020\D | GG | 23 | 20 | D | 6 DL | 100 | 100 | 100 | 2026-10-14 16:18 | 2026-10-19 11:43 | 388267.6882 |  |  |  | 7230 | 388268 | 173527 |  |  | 0 | 18.08 | 0 | 6.89 | 5780.9
TS5500Shv | GG\23\019\D | GG | 23 | 19 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-10-14 16:18 | 2026-10-15 16:39 | 29706.8548 | [6 empty] | 29707 | 22138 | 2.21 | 0 | 0 | 7.01 | 5771
TS6060#1 | GG\23\013\D | GG | 23 | 13 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-10-14 19:04 | 2026-10-15 19:52 | 33555.3472 | [6 empty] | 33555 | 25007 | 2.5 | 0 | 0 | 6.98 | 5775
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 19:04 |  | 3d 19:04 | 2026-10-15 16:39 | 2026-10-19 11:43
TS6060#1 | GG\23\014\D | GG | 23 | 14 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-10-15 19:52 | 2026-10-16 21:47 | 35080.9208 | [6 empty] | 35081 | 26123 | 2.5 | 0 | 0 | 7.1 | 5764
TS6060#1 | GG\23\018\D | GG | 23 | 18 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-10-16 21:47 | 2026-10-17 22:30 | 33442.062 | [6 empty] | 33442 | 24903 | 2.49 | 0 | 0 | 7.11 | 5763
TS Fleet 5 | W1\05\005\D | W1 | 5 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-10-17 04:06 | 2026-11-23 08:33 | 1749202.216 | 1749202 | [7 empty] | 0 | 0 | 66.2 | 7.76 | 5582
DRE1 | SC\42\014\D | SC | 42 | 14 | D | 6 DL | 100 | 0 | 100 | 2026-10-17 10:35 | 2026-10-24 23:01 | 630282.1945 |  |  |  | 47930 | 630282 | 431372 |  |  | 0 | 40 | 0 | 7.51 | 5748.67
TS6060#1 | GG\23\019\D | GG | 23 | 19 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2026-10-17 22:30 | 2026-10-18 22:52 | 32971.3444 | [6 empty] | 32971 | 24571 | 2.46 | 0 | 0 | 7.01 | 5771
TS6060#1 | W1\02\003\B | W1 | 2 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-10-18 22:52 | 2026-10-20 05:06 | 40934.1616 | [6 empty] | 40934 | 28357 | 1.32 | 0 | 0 | 12.86 | 4984
DRE2 | GG\23\021\D | GG | 23 | 21 | D | 6 DL | 100 | 0 | 100 | 2026-10-19 11:43 | 2026-10-25 23:43 | 524739.1432 |  |  |  | 39904 | 524739 | 359137 |  |  | 0 | 40 | 0 | 6.8 | 5789.61
TS5500Shv | GG\23\020\D | GG | 23 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-10-19 11:43 | 2026-10-21 14:29 | 61895.3987 | [6 empty] | 61895 | 46199 | 4.62 | 0 | 0 | 6.89 | 5781
TS6060#1 | W1\01\005\D | W1 | 1 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2026-10-20 05:06 | 2026-10-25 17:37 | 136719.7492 |  |  | 136720 | [5 empty] | 0 | 0 | 0 | 7.39 | 5606.77
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 09:14 |  | 4d 09:14 | 2026-10-21 14:29 | 2026-10-25 23:43
DRE1 | SC\42\013\D | SC | 42 | 13 | D | 6 DL | 100 | 0 | 100 | 2026-10-24 23:01 | 2026-11-01 09:55 | 624932.825 |  |  |  | 47523 | 624933 | 427711 |  |  | 0 | 40 | 0 | 7.45 | 5754.53
TS6060#1 | W1\01\005\D | W1 | 1 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-10-25 17:37 | 2026-10-28 08:13 | 84720.2964 | [6 empty] | 84720 | 60941 | 4.08 | 0 | 0 | 7.39 | 5607
DRE2 | GG\23\022\D | GG | 23 | 22 | D | 6 DL | 100 | 100 | 100 | 2026-10-25 23:43 | 2026-10-30 11:08 | 361333.6114 |  |  |  | 6729 | 361334 | 161490 |  |  | 0 | 16.8 | 0 | 6.74 | 5795.63
TS5500Shv | GG\23\021\D | GG | 23 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-10-25 23:43 | 2026-10-28 02:42 | 62164.7387 | [6 empty] | 62165 | 46474 | 4.65 | 0 | 0 | 6.8 | 5790
TS5500Exc | SC\41\012\D | SC | 41 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-10-27 06:23 | 2026-10-29 15:16 | 71665.9458 | [6 empty] | 71666 | 53388 | 4.45 | 0 | 0 | 7.46 | 5757
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 08:26 |  | 2d 08:26 | 2026-10-28 02:42 | 2026-10-30 11:08
TS6060#1 | CP\03\003\B | CP | 3 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-10-28 08:13 | 2026-12-25 03:34 | 1422145.445 | 1422145 | [7 empty] | 0 | 0 | 33.28 | 8.8 | 5601.79
TS5500Exc | SC\41\011\D | SC | 41 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-10-29 15:16 | 2026-11-01 02:11 | 74201.3312 | [6 empty] | 74201 | 55367 | 4.61 | 0 | 0 | 7.57 | 5747
DRE2 | GG\23\023\D | GG | 23 | 23 | D | 6 DL | 100 | 0 | 100 | 2026-10-30 11:08 | 2026-11-03 10:32 | 320871.4657 |  |  |  | 18408 | 320871 | 140092 |  |  | 0 | 40 | 0 | 6.59 | 5810.63
TS5500Shv | GG\23\022\D | GG | 23 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-10-30 11:08 | 2026-11-01 14:42 | 62865.7301 | [6 empty] | 62866 | 47035 | 4.71 | 0 | 0 | 6.74 | 5796
TS5500Exc | SC\41\010\D | SC | 41 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2026-11-01 02:11 | 2026-11-03 22:26 | 60363.1891 |  |  | 60363 | [5 empty] | 0 | 0 | 0 | 7.65 | 5740.91
DRE1 | SC\42\012\D | SC | 42 | 12 | D | 6 DL | 100 | 0 | 100 | 2026-11-01 09:55 | 2026-11-08 18:19 | 616138.01 |  |  |  | 46855 | 616138 | 421691 |  |  | 0 | 40 | 0 | 7.45 | 5756.61
PH4100A | W2\06\005\B | W2 | 6 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-11-01 10:23 | 2026-11-29 01:35 | 1151115.539 | 1151116 | [7 empty] | 0 | 0 | 57.86 | 10.02 | 5272.43
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 19:50 |  | 1d 19:50 | 2026-11-01 14:42 | 2026-11-03 10:32
DRE2 | GG\25\012\B | GG | 25 | 12 | B | 6 DL | 100 | 0 | 100 | 2026-11-03 10:32 | 2026-11-06 00:18 | 207782.7308 |  |  |  |  | 207783 | 173152 |  |  | 0 | 17.34 | 0 | 11.78 | 5369.11
TS5500Shv | GG\23\023\D | GG | 23 | 23 | D | 7 PostStrip | 100 | 0 | 100 | 2026-11-03 10:32 | 2026-11-04 10:24 | 25584.1714 |  |  | 25584 | [5 empty] | 0 | 0 | 0 | 6.59 | 5810.63
TS5500Exc | SC\41\010\D | SC | 41 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-11-03 22:26 | 2026-11-06 10:34 | 75741.628 | [6 empty] | 75742 | 56652 | 4.72 | 0 | 0 | 7.65 | 5741
TS5500Shv | GG\23\023\D | GG | 23 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-11-04 10:24 | 2026-11-05 15:54 | 35983.0195 | [6 empty] | 35983 | 26966 | 4.87 | 0 | 0 | 6.59 | 5811
TS5500Shv | GG\28\007\X1 | GG | 28 | 7 | X1 | 1 Prestrip - Thick | 37.5472 | 37.5472 | 37.5472 | 2026-11-05 15:54 | 2026-11-19 20:58 | 363454.835 | 363455 | [7 empty] | 0 | 0 | 35.2 | 12.67 | 5221.65
DRE2 | GG\25\011\B | GG | 25 | 11 | B | 6 DL | 100 | 0 | 100 | 2026-11-06 00:18 | 2026-11-08 21:49 | 233850.0026 |  |  |  |  | 233850 | 179885 |  |  | 0 | 17.86 | 0 | 11.32 | 5423.04
TS5500Exc | SC\42\017\D | SC | 42 | 17 | D | 7 PostStrip | 100 | 0 | 100 | 2026-11-06 10:34 | 2026-11-09 16:13 | 68681.7941 |  |  | 68682 | [5 empty] | 0 | 0 | 0 | 7.2 | 5772.1
DRE1 | SC\42\011\D | SC | 42 | 11 | D | 6 DL | 100 | 0 | 100 | 2026-11-08 18:19 | 2026-11-15 23:56 | 606514.3947 |  |  |  | 46123 | 606514 | 415105 |  |  | 0 | 40 | 0 | 7.55 | 5748.49
DRE2 | GG\25\009\B | GG | 25 | 9 | B | 6 DL | 100 | 0 | 100 | 2026-11-08 21:49 | 2026-11-11 20:20 | 237193.5205 |  |  |  |  | 237194 | 197661 |  |  | 0 | 19.76 | 0 | 10.2 | 5509.92
TS5500Exc | SC\42\017\D | SC | 42 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-11-09 16:13 | 2026-11-11 17:55 | 62583.9067 | [6 empty] | 62584 | 46835 | 3.55 | 0 | 0 | 7.2 | 5772
TS5500Exc | SC\42\016\D | SC | 42 | 16 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-11-11 17:55 | 2026-11-13 07:47 | 47714.8385 | [6 empty] | 47715 | 35712 | 3.97 | 0 | 0 | 7.33 | 5764
DRE2 | GG\25\008\B | GG | 25 | 8 | B | 6 DL | 100 | 0 | 100 | 2026-11-11 20:20 | 2026-11-15 02:12 | 261893.9944 |  |  |  |  | 261894 | 201457 |  |  | 0 | 20.15 | 0 | 10.3 | 5487.28
TS5500Exc | SC\42\012\D | SC | 42 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-11-13 07:47 | 2026-11-15 15:14 | 69843.108 | [6 empty] | 69843 | 52029 | 4.34 | 0 | 0 | 7.45 | 5757
DRE2 | GG\25\007\B | GG | 25 | 7 | B | 6 DL | 100 | 0 | 100 | 2026-11-15 02:12 | 2026-11-18 07:37 | 260423.4126 |  |  |  |  | 260423 | 200326 |  |  | 0 | 20.02 | 0 | 10.47 | 5458.63
TS5500Exc | SC\42\013\D | SC | 42 | 13 | D | 8 Coal Mining | 40.3 | 0 | 40.3 | 2026-11-15 15:14 | 2026-11-16 12:25 | 26669.1867 | [6 empty] | 26669 | 19881 | 1.66 | 0 | 0 | 7.45 | 5755
DRE1 | SC\42\010\D | SC | 42 | 10 | D | 6 DL | 100 | 0 | 100 | 2026-11-15 23:56 | 2026-11-26 07:03 | 863171.7478 |  |  |  | 48482 | 863172 | 375720 |  |  | 0 | 40 | 0 | 7.6 | 5745.61
TS5500Exc | SC\42\011\D | SC | 42 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-11-16 12:25 | 2026-11-18 22:23 | 73029.4001 | [6 empty] | 73029 | 54492 | 4.54 | 0 | 0 | 7.55 | 5748
DRE2 | GG\25\006\B | GG | 25 | 6 | B | 6 DL | 100 | 0 | 100 | 2026-11-18 07:37 | 2026-11-21 06:53 | 239750.5367 |  |  |  |  | 239751 | 199792 |  |  | 0 | 19.99 | 0 | 10.53 | 5441.61
PH4100XPC#1 | GG\28\007\X1 | GG | 28 | 7 | X1 | 1 Prestrip - Thick | 100 | 44.9703 | 44.9703 | 2026-11-18 20:27 | 2026-11-26 22:53 | 435309.8964 | 435310 | [7 empty] | 0 | 0 | 42.17 | 12.67 | 5221.65
TS5500Exc | SC\42\013\D | SC | 42 | 13 | D | 8 Coal Mining | 59.7 | 0 | 59.7 | 2026-11-18 22:23 | 2026-11-20 05:43 | 39454.4736 | [6 empty] | 39454 | 29413 | 2.45 | 0 | 0 | 7.45 | 5755
TS5500Shv | GG\25\007\B | GG | 25 | 7 | B | 8 Coal Mining | 35.3 | 0 | 35.3 | 2026-11-19 20:58 | 2026-11-20 11:43 | 17991.7805 | [6 empty] | 17992 | 13141 | 1.31 | 0 | 0 | 10.47 | 5459
TS5500Exc | SC\42\014\D | SC | 42 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-11-20 05:43 | 2026-11-22 08:53 | 64451.6794 | [6 empty] | 64452 | 48162 | 4.01 | 0 | 0 | 7.51 | 5749
TS5500Shv | GG\25\009\B | GG | 25 | 9 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-11-20 11:43 | 2026-11-21 07:39 | 24301.1873 | [6 empty] | 24301 | 17779 | 1.78 | 0 | 0 | 10.2 | 5510
DRE2 | GG\25\005\B | GG | 25 | 5 | B | 6 DL | 100 | 0 | 100 | 2026-11-21 06:53 | 2026-11-24 13:06 | 263068.8555 |  |  |  |  | 263069 | 202361 |  |  | 0 | 20.18 | 0 | 10.21 | 5462.49
TS5500Shv | GG\25\006\B | GG | 25 | 6 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-11-21 07:39 | 2026-11-22 02:59 | 23574.9728 | [6 empty] | 23575 | 17210 | 1.72 | 0 | 0 | 10.53 | 5442
TS5500Shv | GG\25\011\B | GG | 25 | 11 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-11-22 02:59 | 2026-11-22 22:01 | 23202.2853 | [6 empty] | 23202 | 16892 | 1.69 | 0 | 0 | 11.32 | 5423
TS5500Exc | SC\42\015\D | SC | 42 | 15 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-11-22 08:53 | 2026-11-24 11:28 | 63721.2736 | [6 empty] | 63721 | 47692 | 3.98 | 0 | 0 | 7.43 | 5756
TS5500Shv | GG\25\012\B | GG | 25 | 12 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-11-22 22:01 | 2026-11-23 16:58 | 23108.5588 | [6 empty] | 23109 | 16784 | 1.68 | 0 | 0 | 11.78 | 5369
TS Fleet 5 | GG\28\007\X1 | GG | 28 | 7 | X1 | 1 Prestrip - Thick | 62.4528 | 17.4824 | 17.4824 | 2026-11-23 08:33 | 2026-11-26 22:53 | 169228.8618 | 169229 | [7 empty] | 0 | 0 | 16.39 | 12.67 | 5221.65
TS5500Shv | GG\28\009\X1 | GG | 28 | 9 | X1 | 1 Prestrip - Thick | 2.3818 | 2.3818 | 2.3818 | 2026-11-23 16:58 | 2026-11-24 13:06 | 21422.7229 | 21423 | [7 empty] | 0 | 0 | 1.85 | 14.06 | 5157.4
TS5500Exc | SC\51\020\D | SC | 51 | 20 | D | 7 PostStrip | 100 | 0 | 100 | 2026-11-24 11:28 | 2026-11-30 03:06 | 119952.6596 |  |  | 119953 | [5 empty] | 0 | 0 | 0 | 7.38 | 5763.19
DRE2 | GG\25\004\B | GG | 25 | 4 | B | 6 DL | 100 | 0 | 100 | 2026-11-24 13:06 | 2026-11-28 14:22 | 327200.3911 |  |  |  |  | 327200 | 155810 |  |  | 0 | 20.24 | 0 | 9.87 | 5491.43
TS5500Shv | GG\28\010\X1 | GG | 28 | 10 | X1 | 1 Prestrip - Thick | 0.79839 | 0.79839 | 0.79839 | 2026-11-24 13:06 | 2026-11-24 18:26 | 5671.3441 | 5671 | [7 empty] | 0 | 0 | 0.45 | 14.41 | 5142.68
TS5500Shv | GG\28\018\B | GG | 28 | 18 | B | 1 Prestrip - Thick | 14.7291 | 14.7291 | 14.7291 | 2026-11-24 18:26 | 2026-11-26 18:39 | 51270.5821 | 51271 | [7 empty] | 0 | 0 | 5.21 | 15.47 | 5073.72
DRE1 | SC\43\017\D | SC | 43 | 17 | D | 6 DL | 100 | 0 | 100 | 2026-11-26 07:03 | 2026-12-08 18:32 | 1046118.299 |  |  |  | 57959 | 1046118 | 454444 |  |  | 0 | 40 | 0 | 7.24 | 5766.95
TS5500Shv | GG\28\019\B | GG | 28 | 19 | B | 1 Prestrip - Thick | 17.1176 | 17.1176 | 17.1176 | 2026-11-26 18:39 | 2026-11-28 18:55 | 51565.283 | 51565 | [7 empty] | 0 | 0 | 5.48 | 17.37 | 4942.41
TS Fleet 5 | GG\28\008\X1 | GG | 28 | 8 | X1 | 1 Prestrip - Thick | 100 | 46.1415 | 46.1415 | 2026-11-26 22:53 | 2026-12-05 05:39 | 389562.4574 | 389562 | [7 empty] | 0 | 0 | 39.04 | 13.45 | 5185.72
PH4100XPC#1 | GG\28\008\X1 | GG | 28 | 8 | X1 | 1 Prestrip - Thick | 100 | 53.8585 | 53.8585 | 2026-11-26 22:53 | 2026-12-05 05:39 | 454716.0483 | 454716 | [7 empty] | 0 | 0 | 45.57 | 13.45 | 5185.72
DRE2 | GG\24\012\D | GG | 24 | 12 | D | 6 DL | 100 | 100 | 100 | 2026-11-28 14:22 | 2026-12-04 15:41 | 488817.02 |  |  |  | 11381 | 488817 | 216240 |  |  | 0 | 22.76 | 0 | 6.75 | 5794.39
TS5500Shv | GG\28\007\X1 | GG | 28 | 7 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-11-28 18:55 | 2026-11-29 01:24 | 7908.3648 | [6 empty] | 7908 | 5762 | 0.57 | 0 | 0 | 12.67 | 5222
TS5500Shv | GG\25\004\B | GG | 25 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-11-29 01:24 | 2026-11-30 11:07 | 41106.7993 | [6 empty] | 41107 | 30103 | 4.19 | 0 | 0 | 9.87 | 5491
PH4100A | W2\05\006\B | W2 | 5 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-11-29 01:35 | 2026-12-25 06:23 | 1084126.81 | 1084127 | [7 empty] | 0 | 0 | 54.01 | 10.08 | 5267.26
TS5500Exc | W2\06\005\B | W2 | 6 | 5 | B | 8 Coal Mining | 39.2 | 0 | 39.2 | 2026-11-30 03:06 | 2026-12-01 09:25 | 38175.4504 | [6 empty] | 38175 | 26769 | 1.34 | 0 | 0 | 10.02 | 5272
TS5500Shv | GG\28\020\B | GG | 28 | 20 | B | 1 Prestrip - Thick | 6.5885 | 6.5885 | 6.5885 | 2026-11-30 11:07 | 2026-12-01 08:02 | 22477.2083 | 22477 | [7 empty] | 0 | 0 | 3.37 | 0 | 0
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 07:39 |  | 3d 07:39 | 2026-12-01 08:02 | 2026-12-04 15:41
TS5500Exc | SC\42\010\D | SC | 42 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2026-12-01 09:25 | 2026-12-04 05:57 | 60617.8039 |  |  | 60618 | [5 empty] | 0 | 0 | 0 | 7.6 | 5745.61
TS5500Exc | SC\42\010\D | SC | 42 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-12-04 05:57 | 2026-12-06 17:12 | 74635.7481 | [6 empty] | 74636 | 55825 | 4.65 | 0 | 0 | 7.6 | 5746
DRE2 | GG\24\011\D | GG | 24 | 11 | D | 6 DL | 100 | 100 | 100 | 2026-12-04 15:41 | 2026-12-10 18:03 | 492319.3532 |  |  |  | 8926 | 492319 | 214221 |  |  | 0 | 22.33 | 0 | 6.58 | 5808.16
TS5500Shv | GG\24\012\D | GG | 24 | 12 | D | 8 Coal Mining | 7.1 | 0 | 7.1 | 2026-12-04 15:41 | 2026-12-04 19:22 | 4489.4134 | [6 empty] | 4489 | 3356 | 0.34 | 0 | 0 | 6.75 | 5794
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 10:16 |  | 0d 10:16 | 2026-12-04 19:22 | 2026-12-05 05:39
TS Fleet 5 | GG\28\009\X1 | GG | 28 | 9 | X1 | 1 Prestrip - Thick | 85.1168 | 45.2812 | 45.2812 | 2026-12-05 05:39 | 2026-12-13 21:26 | 407276.0413 | 407276 | [7 empty] | 0 | 0 | 35.26 | 14.06 | 5157.4
PH4100XPC#1 | GG\28\009\X1 | GG | 28 | 9 | X1 | 1 Prestrip - Thick | 100 | 52.337 | 52.337 | 2026-12-05 05:39 | 2026-12-13 21:26 | 470739.0171 | 470739 | [7 empty] | 0 | 0 | 40.75 | 14.06 | 5157.4
TS5500Shv | GG\28\008\X1 | GG | 28 | 8 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-12-05 05:39 | 2026-12-05 20:32 | 18162.6346 | [6 empty] | 18163 | 13135 | 1.3 | 0 | 0 | 13.45 | 5186
TS5500Shv | GG\28\008\B | GG | 28 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-12-05 20:32 | 2026-12-11 15:44 | 149215.3919 | 149215 | [7 empty] | 0 | 0 | 14.95 | 10.48 | 5476.89
TS5500Exc | SC\51\020\D | SC | 51 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-12-06 17:12 | 2026-12-11 08:58 | 140774.2303 | [6 empty] | 140774 | 105037 | 4.38 | 0 | 0 | 7.38 | 5763
DRE1 | SC\43\016\D | SC | 43 | 16 | D | 6 DL | 100 | 0 | 100 | 2026-12-08 18:32 | 2026-12-16 12:18 | 648947.5692 |  |  |  | 49350 | 648948 | 444147 |  |  | 0 | 40 | 0 | 7.35 | 5762.8
DRE2 | GG\24\010\D | GG | 24 | 10 | D | 6 DL | 100 | 100 | 100 | 2026-12-10 18:03 | 2026-12-16 08:49 | 453322.7148 |  |  |  | 10555 | 453323 | 200539 |  |  | 0 | 21.12 | 0 | 6.57 | 5807.54
TS5500Exc | SC\43\017\D | SC | 43 | 17 | D | 7 PostStrip | 100 | 0 | 100 | 2026-12-11 08:58 | 2026-12-14 12:56 | 67187.2027 |  |  | 67187 | [5 empty] | 0 | 0 | 0 | 7.24 | 5766.95
TS5500Shv | GG\24\011\D | GG | 24 | 11 | D | 8 Coal Mining | 20.7 | 0 | 20.7 | 2026-12-11 15:44 | 2026-12-12 02:13 | 12789.9402 | [6 empty] | 12790 | 9577 | 0.96 | 0 | 0 | 6.58 | 5808
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 19:13 |  | 1d 19:13 | 2026-12-12 02:13 | 2026-12-13 21:26
TS Fleet 5 | GG\28\010\X1 | GG | 28 | 10 | X1 | 1 Prestrip - Thick | 45.1588 | 45.1588 | 45.1588 | 2026-12-13 21:26 | 2026-12-20 17:06 | 320782.6074 | 320783 | [7 empty] | 0 | 0 | 25.44 | 14.41 | 5142.68
PH4100XPC#1 | GG\28\010\X1 | GG | 28 | 10 | X1 | 1 Prestrip - Thick | 100 | 54.0428 | 54.0428 | 2026-12-13 21:26 | 2026-12-20 23:45 | 383888.8471 | 383889 | [7 empty] | 0 | 0 | 30.44 | 14.41 | 5142.68
TS5500Shv | GG\28\009\X1 | GG | 28 | 9 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-12-13 21:26 | 2026-12-14 12:26 | 18284.0357 | [6 empty] | 18284 | 13159 | 1.3 | 0 | 0 | 14.06 | 5157
TS5500Shv | GG\28\009\X2 | GG | 28 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2026-12-14 12:26 | 2026-12-17 03:51 | 67980.612 | 67981 | [7 empty] | 0 | 0 | 6.74 | 0 | 0
TS5500Exc | SC\43\017\D | SC | 43 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-12-14 12:56 | 2026-12-16 13:20 | 60973.4183 | [6 empty] | 60973 | 45591 | 3.44 | 0 | 0 | 7.24 | 5767
DRE2 | GG\24\009\D | GG | 24 | 9 | D | 6 DL | 100 | 100 | 100 | 2026-12-16 08:49 | 2026-12-21 18:18 | 435524.089 |  |  |  | 10140 | 435524 | 192665 |  |  | 0 | 20.28 | 0 | 6.57 | 5808.81
DRE1 | SC\43\015\D | SC | 43 | 15 | D | 6 DL | 100 | 0 | 100 | 2026-12-16 12:18 | 2026-12-24 01:43 | 633668.3838 |  |  |  | 48188 | 633668 | 433689 |  |  | 0 | 40 | 0 | 7.43 | 5755.59
TS5500Exc | SC\43\016\D | SC | 43 | 16 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-12-16 13:20 | 2026-12-18 14:30 | 61928.2144 | [6 empty] | 61928 | 46351 | 4.04 | 0 | 0 | 7.35 | 5763
TS5500Shv | GG\28\009\B | GG | 28 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2026-12-17 03:51 | 2026-12-20 07:56 | 81560.6855 | 81561 | [7 empty] | 0 | 0 | 8.11 | 10.52 | 5484.31
TS5500Exc | CP\03\002\D | CP | 3 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2026-12-18 14:30 | 2026-12-22 21:54 | 91447.7382 |  |  | 91448 | [5 empty] | 0 | 0 | 0 | 5.98 | 5881.17
TS5500Shv | GG\24\010\D | GG | 24 | 10 | D | 8 Coal Mining | 97.3 | 0 | 97.3 | 2026-12-20 07:56 | 2026-12-22 07:39 | 58183.6302 | [6 empty] | 58184 | 43600 | 4.36 | 0 | 0 | 6.57 | 5808
TS Fleet 5 | GG\28\011\X1 | GG | 28 | 11 | X1 | 1 Prestrip - Thick | 44.5886 | 44.5886 | 44.5886 | 2026-12-20 17:06 | 2026-12-26 23:23 | 294543.5958 | 294544 | [7 empty] | 0 | 0 | 29.86 | 14.58 | 5134.17
PH4100XPC#1 | GG\28\011\X1 | GG | 28 | 11 | X1 | 1 Prestrip - Thick | 100 | 55.4114 | 55.4114 | 2026-12-20 23:45 | 2026-12-27 12:07 | 366036.5736 | 366037 | [7 empty] | 0 | 0 | 37.11 | 14.58 | 5134.17
DRE2 | GG\24\008\D | GG | 24 | 8 | D | 6 DL | 100 | 100 | 100 | 2026-12-21 18:18 | 2026-12-27 01:12 | 426864.7827 |  |  |  | 7949 | 426865 | 190778 |  |  | 0 | 19.87 | 0 | 6.57 | 5809.41
TS5500Shv | GG\28\010\X1 | GG | 28 | 10 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2026-12-22 07:39 | 2026-12-22 21:18 | 16659.6163 | [6 empty] | 16660 | 11954 | 1.2 | 0 | 0 | 14.41 | 5143
TS5500Shv | GG\28\010\X2 | GG | 28 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2026-12-22 21:18 | 2026-12-25 12:25 | 67653.984 | 67654 | [7 empty] | 0 | 0 | 6.79 | 0 | 0
TS5500Exc | CP\03\002\D | CP | 3 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-12-22 21:54 | 2026-12-26 09:38 | 105458.595 | [6 empty] | 105459 | 75466 | 5.12 | 0 | 0 | 5.98 | 5881
DRE1 | SC\43\014\D | SC | 43 | 14 | D | 6 DL | 100 | 0 | 100 | 2026-12-24 01:43 | 2026-12-31 13:41 | 628664.6612 |  |  |  | 47807 | 628665 | 430265 |  |  | 0 | 40 | 0 | 7.48 | 5751.68
TS6060#1 | W2\05\005\B | W2 | 5 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-12-25 03:34 | 2026-12-28 03:11 | 96920.0116 | [6 empty] | 96920 | 67920 | 3.4 | 0 | 0 | 10.04 | 5271
PH4100A | W2\06\006\B | W2 | 6 | 6 | B | 1 Prestrip - Thick | 100 | 26.0063 | 26.0063 | 2026-12-25 06:23 | 2027-01-01 | 280430.4758 | 280430 | [7 empty] | 0 | 0 | 15.29 | 10.07 | 5266.67
TS5500Shv | GG\28\010\B | GG | 28 | 10 | B | 1 Prestrip - Thick | 52.1079 | 52.1079 | 52.1079 | 2026-12-25 12:25 | 2026-12-27 06:15 | 44837.1623 | 44837 | [7 empty] | 0 | 0 | 4.47 | 10.96 | 5455.59
TS5500Exc | SC\43\015\D | SC | 43 | 15 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-12-26 09:38 | 2026-12-28 12:32 | 64124.5825 | [6 empty] | 64125 | 47956 | 4 | 0 | 0 | 7.43 | 5756
TS Fleet 5 | GG\28\010\B | GG | 28 | 10 | B | 1 Prestrip - Thick | 21.7521 | 21.7521 | 21.7521 | 2026-12-26 23:23 | 2026-12-27 08:56 | 18716.9652 | 18717 | [7 empty] | 0 | 0 | 1.87 | 10.96 | 5455.59
DRE2 | GG\24\007\D | GG | 24 | 7 | D | 6 DL | 100 | 93.0403 | 93.0403 | 2026-12-27 01:12 | 2027-01-01 | 399608.7486 |  |  |  | 7442 | 399609 | 178596 |  |  | 0 | 20 | 0 | 6.59 | 5807.18
TS5500Shv | GG\24\009\D | GG | 24 | 9 | D | 8 Coal Mining | 69 | 0 | 69 | 2026-12-27 06:15 | 2026-12-28 17:06 | 42501.3172 | [6 empty] | 42501 | 31824 | 3.18 | 0 | 0 | 6.57 | 5809
TS Fleet 5 | GG\28\012\X1 | GG | 28 | 12 | X1 | 1 Prestrip - Thick | 44.7326 | 38.6263 | 38.6263 | 2026-12-27 08:56 | 2027-01-01 | 217683.8467 | 217684 | [7 empty] | 0 | 0 | 26.13 | 14.84 | 5112.73
PH4100XPC#1 | GG\28\010\B | GG | 28 | 10 | B | 1 Prestrip - Thick | 100 | 26.14 | 26.14 | 2026-12-27 12:07 | 2026-12-27 22:03 | 22492.6141 | 22493 | [7 empty] | 0 | 0 | 2.24 | 10.96 | 5455.59
PH4100XPC#1 | GG\28\012\X1 | GG | 28 | 12 | X1 | 1 Prestrip - Thick | 100 | 40.4409 | 40.4409 | 2026-12-27 22:03 | 2027-01-01 | 227910.4337 | 227910 | [7 empty] | 0 | 0 | 27.36 | 14.84 | 5112.73
TS6060#1 | W2\06\005\B | W2 | 6 | 5 | B | 8 Coal Mining | 60.8 | 0 | 60.8 | 2026-12-28 03:11 | 2026-12-29 23:01 | 59315.0298 | [6 empty] | 59315 | 41592 | 2.08 | 0 | 0 | 10.02 | 5272
TS5500Exc | W1\02\004\D | W1 | 2 | 4 | D | 7 PostStrip | 100 | 0 | 72.8372 | 2026-12-28 12:32 | 2027-01-01 | 73805.1793 |  |  | 73805 | [5 empty] | 0 | 0 | 0 | 7.54 | 5612.59
TS5500Shv | GG\28\011\X1 | GG | 28 | 11 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2026-12-28 17:06 | 2026-12-28 22:59 | 7176.1293 | [6 empty] | 7176 | 5147 | 0.52 | 0 | 0 | 14.58 | 5134
TS5500Shv | GG\24\008\D | GG | 24 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2026-12-28 22:59 | 2026-12-31 01:28 | 61561.5995 | [6 empty] | 61562 | 46096 | 4.61 | 0 | 0 | 6.57 | 5809
TS6060#1 | GG\25\008\B | GG | 25 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2026-12-29 23:01 | 2026-12-31 13:16 | 51780.9033 | [6 empty] | 51781 | 37856 | 3.79 | 0 | 0 | 10.3 | 5487
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 22:32 |  | 0d 22:32 | 2026-12-31 01:28 | 2027-01-01
TS6060#1 | GG\25\007\B | GG | 25 | 7 | B | 8 Coal Mining | 64.7 | 0 | 28.5 | 2026-12-31 13:16 | 2027-01-01 | 14507.5992 | [6 empty] | 14508 | 10596 | 1.06 | 0 | 0 | 10.47 | 5459
DRE1 | SC\43\013\D | SC | 43 | 13 | D | 6 DL | 100 | 0 | 5.8719 | 2026-12-31 13:41 | 2027-01-01 | 36014.9579 |  |  |  | 2739 | 36015 | 24649 |  |  | 0 | 40 | 0 | 7.44 | 5755.32
| EOP 79 : 2026 | EOP 79 : 2026 | [7 empty] | 2027-01-01 | 2027-01-01 |  | 66533669 |  | 2044725 | 2396498 | 58473360 | 35046262 | 11202801 | 8214681 | 749.15 | 0 | 4575.14 | 8.49 | 5631.41
TS Fleet 5 | GG\28\012\X1 | GG | 28 | 12 | X1 | 1 Prestrip - Thick | 44.7326 | 6.1063 | 6.1063 | 2027-01-01 | 2027-01-01 17:33 | 34412.7465 | 34413 | [7 empty] | 0 | 0 | 4.13 | 14.84 | 5112.73
PH4100A | W2\06\006\B | W2 | 6 | 6 | B | 1 Prestrip - Thick | 100 | 73.9937 | 73.9937 | 2027-01-01 | 2027-01-20 03:49 | 797885.5861 | 797886 | [7 empty] | 0 | 0 | 43.51 | 10.07 | 5266.67
DRE1 | SC\43\013\D | SC | 43 | 13 | D | 6 DL | 100 | 0 | 94.1281 | 2027-01-01 | 2027-01-08 17:00 | 577330.7444 |  |  |  | 43903 | 577331 | 395131 |  |  | 0 | 40 | 0 | 7.44 | 5755.32
DRE2 | GG\24\007\D | GG | 24 | 7 | D | 6 DL | 100 | 6.9597 | 6.9597 | 2027-01-01 | 2027-01-01 09:07 | 29891.9728 |  |  |  | 557 | 29892 | 13360 |  |  | 0 | 20 | 0 | 6.59 | 5807.18
PH4100XPC#1 | GG\28\012\X1 | GG | 28 | 12 | X1 | 1 Prestrip - Thick | 100 | 14.8265 | 14.8265 | 2027-01-01 | 2027-01-02 11:54 | 83556.5456 | 83557 | [7 empty] | 0 | 0 | 10.03 | 14.84 | 5112.73
TS6060#1 | GG\25\007\B | GG | 25 | 7 | B | 8 Coal Mining | 64.7 | 0 | 36.2 | 2027-01-01 | 2027-01-01 13:35 | 18404.9828 | [6 empty] | 18405 | 13443 | 1.34 | 0 | 0 | 10.47 | 5459
TS5500Exc | W1\02\004\D | W1 | 2 | 4 | D | 7 PostStrip | 100 | 0 | 27.1628 | 2027-01-01 | 2027-01-02 07:07 | 27523.8392 |  |  | 27524 | [5 empty] | 0 | 0 | 0 | 7.54 | 5612.59
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 09:08 |  | 0d 09:08 | 2027-01-01 | 2027-01-01 09:07
DRE2 | GG\24\006\D | GG | 24 | 6 | D | 6 DL | 100 | 100 | 100 | 2027-01-01 09:07 | 2027-01-06 20:15 | 429307.4386 |  |  |  | 7995 | 429307 | 191869 |  |  | 0 | 19.99 | 0 | 6.62 | 5804.05
TS5500Shv | GG\24\007\D | GG | 24 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-01-01 09:07 | 2027-01-03 11:17 | 61167.7998 | [6 empty] | 61168 | 45800 | 4.58 | 0 | 0 | 6.59 | 5807
TS6060#1 | GG\25\009\B | GG | 25 | 9 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-01-01 13:35 | 2027-01-02 09:31 | 26971.6474 | [6 empty] | 26972 | 19732 | 1.97 | 0 | 0 | 10.2 | 5510
TS Fleet 5 | GG\28\013\X1 | GG | 28 | 13 | X1 | 1 Prestrip - Thick | 45.3736 | 45.3736 | 45.3736 | 2027-01-01 17:33 | 2027-01-05 23:56 | 200664.4093 | 200664 | [7 empty] | 0 | 0 | 23.63 | 14.79 | 5115.49
TS5500Exc | SC\43\014\D | SC | 43 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-01-02 07:07 | 2027-01-04 10:30 | 64728.0549 | [6 empty] | 64728 | 48369 | 4.03 | 0 | 0 | 7.48 | 5752
TS6060#1 | GG\25\006\B | GG | 25 | 6 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-01-02 09:31 | 2027-01-03 04:51 | 26165.6291 | [6 empty] | 26166 | 19101 | 1.91 | 0 | 0 | 10.53 | 5442
PH4100XPC#1 | GG\28\013\X1 | GG | 28 | 13 | X1 | 1 Prestrip - Thick | 100 | 54.6264 | 54.6264 | 2027-01-02 11:54 | 2027-01-06 22:26 | 241585.1261 | 241585 | [7 empty] | 0 | 0 | 28.45 | 14.79 | 5115.49
TS6060#1 | GG\25\011\B | GG | 25 | 11 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-01-03 04:51 | 2027-01-03 23:53 | 25751.987 | [6 empty] | 25752 | 18748 | 1.87 | 0 | 0 | 11.32 | 5423
TS5500Shv | GG\28\012\X1 | GG | 28 | 12 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2027-01-03 11:17 | 2027-01-03 22:29 | 13649.4495 | [6 empty] | 13649 | 9777 | 1 | 0 | 0 | 14.84 | 5113
TS5500Shv | GG\28\012\X2 | GG | 28 | 12 | X2 | 1 Prestrip - Thick | 74.8425 | 0 | 74.8425 | 2027-01-03 22:29 | 2027-01-05 23:36 | 52661.1964 | 52661 | [7 empty] | 0 | 0 | 5.31 | 0 | 0
TS6060#1 | GG\25\012\B | GG | 25 | 12 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-01-03 23:53 | 2027-01-04 18:50 | 25647.9609 | [6 empty] | 25648 | 18629 | 1.86 | 0 | 0 | 11.78 | 5369
TS5500Exc | W1\02\004\D | W1 | 2 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-01-04 10:30 | 2027-01-09 17:02 | 159370.5959 | [6 empty] | 159371 | 114839 | 5.74 | 0 | 0 | 7.54 | 5613
TS6060#1 | GG\28\007\X1 | GG | 28 | 7 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-01-04 18:50 | 2027-01-05 01:19 | 8777.4158 | [6 empty] | 8777 | 6395 | 0.63 | 0 | 0 | 12.67 | 5222
TS6060#1 | GG\25\005\B | GG | 25 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-01-05 01:19 | 2027-01-06 15:44 | 52000.7042 | [6 empty] | 52001 | 38028 | 3.8 | 0 | 0 | 10.21 | 5462
TS5500Shv | GG\28\007\B | GG | 28 | 7 | B | 1 Prestrip - Thick | 94.4908 | 40.7871 | 40.7871 | 2027-01-05 23:36 | 2027-01-08 12:15 | 65016.099 | 65016 | [7 empty] | 0 | 0 | 6.56 | 10.67 | 5450.91
TS Fleet 5 | GG\28\007\B | GG | 28 | 7 | B | 1 Prestrip - Thick | 5.5092 | 5.5092 | 5.5092 | 2027-01-05 23:56 | 2027-01-06 04:25 | 8781.8488 | 8782 | [7 empty] | 0 | 0 | 0.89 | 10.67 | 5450.91
TS Fleet 5 | GG\28\012\X2 | GG | 28 | 12 | X2 | 1 Prestrip - Thick | 11.4263 | 0 | 11.4263 | 2027-01-06 04:25 | 2027-01-06 08:31 | 8039.8433 | 8040 | [7 empty] | 0 | 0 | 0.81 | 0 | 0
TS Fleet 5 | GG\28\014\X1 | GG | 28 | 14 | X1 | 1 Prestrip - Thick | 46.5325 | 46.5325 | 46.5325 | 2027-01-06 08:31 | 2027-01-09 20:19 | 164247.5511 | 164248 | [7 empty] | 0 | 0 | 15.85 | 14.82 | 5111.22
TS6060#1 | GG\24\012\D | GG | 24 | 12 | D | 8 Coal Mining | 92.9 | 0 | 92.9 | 2027-01-06 15:44 | 2027-01-08 11:11 | 58787.8852 | [6 empty] | 58788 | 43950 | 4.4 | 0 | 0 | 6.75 | 5794
DRE2 | GG\24\005\D | GG | 24 | 5 | D | 6 DL | 100 | 100 | 100 | 2027-01-06 20:15 | 2027-01-12 05:42 | 423862.6038 |  |  |  | 7893 | 423863 | 189436 |  |  | 0 | 19.73 | 0 | 6.64 | 5801.98
PH4100XPC#1 | GG\28\007\B | GG | 28 | 7 | B | 1 Prestrip - Thick | 100 | 53.7037 | 53.7037 | 2027-01-06 22:26 | 2027-01-08 12:15 | 85605.7358 | 85606 | [7 empty] | 0 | 0 | 8.63 | 10.67 | 5450.91
TS6060#1 | W2\05\006\B | W2 | 5 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-01-08 11:11 | 2027-01-11 11:56 | 98460.2095 | [6 empty] | 98460 | 68962 | 3.45 | 0 | 0 | 10.08 | 5267
PH4100XPC#1 | GG\28\012\X2 | GG | 28 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 13.7312 | 2027-01-08 12:15 | 2027-01-08 16:31 | 9661.6673 | 9662 | [7 empty] | 0 | 0 | 0.97 | 0 | 0
TS5500Shv | GG\28\013\X1 | GG | 28 | 13 | X1 | 8 Coal Mining | 48.9 | 0 | 48.9 | 2027-01-08 12:15 | 2027-01-08 17:36 | 6527.2008 | [6 empty] | 6527 | 4679 | 0.47 | 0 | 0 | 14.79 | 5115
PH4100XPC#1 | GG\28\012\B | GG | 28 | 12 | B | 1 Prestrip - Thick | 100 | 81.9222 | 81.9222 | 2027-01-08 16:31 | 2027-01-10 05:49 | 84421.6056 | 84422 | [7 empty] | 0 | 0 | 8.46 | 11.86 | 5362.8
DRE1 | SC\43\012\D | SC | 43 | 12 | D | 6 DL | 100 | 0 | 100 | 2027-01-08 17:00 | 2027-01-16 19:44 | 607668.9557 |  |  |  | 46211 | 607669 | 415895 |  |  | 0 | 40 | 0 | 7.44 | 5756.37
TS5500Shv | GG\24\006\D | GG | 24 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-01-08 17:36 | 2027-01-10 19:23 | 60691.8097 | [6 empty] | 60692 | 45480 | 4.55 | 0 | 0 | 6.62 | 5804
TS5500Exc | SC\43\013\D | SC | 43 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-01-09 17:02 | 2027-01-11 21:15 | 65782.5837 | [6 empty] | 65783 | 49040 | 4.09 | 0 | 0 | 7.44 | 5755
TS Fleet 5 | GG\28\012\B | GG | 28 | 12 | B | 1 Prestrip - Thick | 45.419 | 18.0778 | 18.0778 | 2027-01-09 20:19 | 2027-01-10 05:49 | 18629.3901 | 18629 | [7 empty] | 0 | 0 | 1.87 | 11.86 | 5362.8
TS Fleet 5 | GG\28\017\B | GG | 28 | 17 | B | 1 Prestrip - Thick | 46.0464 | 46.0464 | 46.0464 | 2027-01-10 05:49 | 2027-01-14 17:26 | 210934.2277 | 210934 | [7 empty] | 0 | 0 | 21.11 | 14.44 | 5130.79
PH4100XPC#1 | GG\28\014\X1 | GG | 28 | 14 | X1 | 1 Prestrip - Thick | 100 | 53.4675 | 53.4675 | 2027-01-10 05:49 | 2027-01-13 21:01 | 188726.5827 | 188727 | [7 empty] | 0 | 0 | 18.22 | 14.82 | 5111.22
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 10:20 |  | 1d 10:20 | 2027-01-10 19:23 | 2027-01-12 05:42
TS6060#1 | GG\24\011\D | GG | 24 | 11 | D | 8 Coal Mining | 79.3 | 0 | 79.3 | 2027-01-11 11:56 | 2027-01-13 00:13 | 49113.7177 | [6 empty] | 49114 | 36775 | 3.68 | 0 | 0 | 6.58 | 5808
TS5500Exc | W1\02\005\D | W1 | 2 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2027-01-11 21:15 | 2027-01-16 23:15 | 107900.2213 |  |  | 107900 | [5 empty] | 0 | 0 | 0 | 7.57 | 5605.01
DRE2 | GG\24\004\D | GG | 24 | 4 | D | 6 DL | 100 | 100 | 100 | 2027-01-12 05:42 | 2027-01-16 05:25 | 313348.0365 |  |  |  | 5110 | 313348 | 90108 |  |  | 0 | 19.64 | 0 | 6.62 | 5803.31
TS5500Shv | GG\24\005\D | GG | 24 | 5 | D | 8 Coal Mining | 24.1 | 0 | 24.1 | 2027-01-12 05:42 | 2027-01-12 17:38 | 14549.8287 | [6 empty] | 14550 | 10903 | 1.09 | 0 | 0 | 6.64 | 5802
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 03:23 |  | 1d 03:23 | 2027-01-12 17:38 | 2027-01-13 21:01
TS6060#1 | GG\24\010\D | GG | 24 | 10 | D | 8 Coal Mining | 2.7 | 0 | 2.7 | 2027-01-13 00:13 | 2027-01-13 01:23 | 1591.141 | [6 empty] | 1591 | 1192 | 0.12 | 0 | 0 | 6.57 | 5808
TS6060#1 | GG\24\009\D | GG | 24 | 9 | D | 8 Coal Mining | 31 | 0 | 31 | 2027-01-13 01:23 | 2027-01-13 15:28 | 19058.4126 | [6 empty] | 19058 | 14270 | 1.43 | 0 | 0 | 6.57 | 5809
TS6060#1 | GG\28\011\X1 | GG | 28 | 11 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-01-13 15:28 | 2027-01-13 21:21 | 7964.7149 | [6 empty] | 7965 | 5712 | 0.58 | 0 | 0 | 14.58 | 5134
PH4100XPC#1 | GG\28\017\B | GG | 28 | 17 | B | 1 Prestrip - Thick | 100 | 53.9536 | 53.9536 | 2027-01-13 21:01 | 2027-01-18 13:00 | 247156.7692 | 247157 | [7 empty] | 0 | 0 | 24.74 | 14.44 | 5130.79
TS5500Shv | GG\28\014\X1 | GG | 28 | 14 | X1 | 8 Coal Mining | 67.4 | 0 | 67.4 | 2027-01-13 21:01 | 2027-01-14 04:02 | 8562.5345 | [6 empty] | 8563 | 6141 | 0.61 | 0 | 0 | 14.82 | 5111
TS6060#1 | GG\28\013\X1 | GG | 28 | 13 | X1 | 8 Coal Mining | 51.1 | 0 | 51.1 | 2027-01-13 21:21 | 2027-01-14 02:24 | 6816.7523 | [6 empty] | 6817 | 4887 | 0.49 | 0 | 0 | 14.79 | 5115
TS6060#1 | GG\28\014\X1 | GG | 28 | 14 | X1 | 8 Coal Mining | 32.6 | 0 | 32.6 | 2027-01-14 02:24 | 2027-01-14 05:27 | 4133.3493 | [6 empty] | 4133 | 2964 | 0.29 | 0 | 0 | 14.82 | 5111
TS5500Shv | GG\28\011\X2 | GG | 28 | 11 | X2 | 1 Prestrip - Thick | 31.8368 | 0 | 31.8368 | 2027-01-14 04:02 | 2027-01-15 00:23 | 21810.3585 | 21810 | [7 empty] | 0 | 0 | 2.19 | 0 | 0
TS6060#1 | GG\24\005\D | GG | 24 | 5 | D | 8 Coal Mining | 75.9 | 0 | 75.9 | 2027-01-14 05:27 | 2027-01-15 15:16 | 45761.2275 | [6 empty] | 45761 | 34292 | 3.43 | 0 | 0 | 6.64 | 5802
TS Fleet 5 | GG\28\018\B | GG | 28 | 18 | B | 1 Prestrip - Thick | 32.5474 | 32.5474 | 32.5474 | 2027-01-14 17:26 | 2027-01-17 03:14 | 113294.1937 | 113294 | [7 empty] | 0 | 0 | 11.51 | 15.47 | 5073.72
TS5500Shv | GG\28\011\X2 | GG | 28 | 11 | X2 | 1 Prestrip - Thick | 68.1632 | 0 | 68.1632 | 2027-01-15 00:23 | 2027-01-16 19:57 | 46696.3805 | 46696 | [7 empty] | 0 | 0 | 4.69 | 0 | 0
TS6060#1 | GG\28\018\B | GG | 28 | 18 | B | 1 Prestrip - Thick | 14.1956 | 14.1956 | 14.1956 | 2027-01-15 15:16 | 2027-01-17 15:29 | 49413.5172 | 49414 | [7 empty] | 0 | 0 | 5.02 | 15.47 | 5073.72
DRE2 | GG\25\013\B | GG | 25 | 13 | B | 6 DL | 100 | 0 | 100 | 2027-01-16 05:25 | 2027-01-18 18:56 | 201431.9312 |  |  |  |  | 201432 | 167860 |  |  | 0 | 16.79 | 0 | 12.11 | 5321.95
DRE1 | SC\43\011\D | SC | 43 | 11 | D | 6 DL | 100 | 0 | 100 | 2027-01-16 19:44 | 2027-01-24 17:40 | 592681.2872 |  |  |  | 45071 | 592681 | 405637 |  |  | 0 | 40 | 0 | 7.53 | 5750.26
TS5500Shv | GG\28\011\B | GG | 28 | 11 | B | 1 Prestrip - Thick | 47.9503 | 47.9503 | 47.9503 | 2027-01-16 19:57 | 2027-01-18 12:32 | 43504.923 | 43505 | [7 empty] | 0 | 0 | 4.35 | 11.53 | 5405.92
TS5500Exc | SC\43\012\D | SC | 43 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-01-16 23:15 | 2027-01-19 05:16 | 68029.9337 | [6 empty] | 68030 | 50717 | 4.23 | 0 | 0 | 7.44 | 5756
TS Fleet 5 | GG\28\019\B | GG | 28 | 19 | B | 1 Prestrip - Thick | 30.1793 | 30.1793 | 30.1793 | 2027-01-17 03:14 | 2027-01-19 01:37 | 90912.4323 | 90912 | [7 empty] | 0 | 0 | 9.65 | 17.37 | 4942.41
TS6060#1 | GG\28\019\B | GG | 28 | 19 | B | 1 Prestrip - Thick | 16.4227 | 16.4227 | 16.4227 | 2027-01-17 15:29 | 2027-01-19 15:45 | 49471.8637 | 49472 | [7 empty] | 0 | 0 | 5.25 | 17.37 | 4942.41
TS5500Shv | GG\28\013\B | GG | 28 | 13 | B | 1 Prestrip - Thick | 45.856 | 40.2999 | 40.2999 | 2027-01-18 12:32 | 2027-01-21 12:02 | 76659.4537 | 76659 | [7 empty] | 0 | 0 | 7.7 | 12.07 | 5321.2
PH4100XPC#1 | GG\28\011\B | GG | 28 | 11 | B | 1 Prestrip - Thick | 100 | 52.0497 | 52.0497 | 2027-01-18 13:00 | 2027-01-19 09:52 | 47224.3601 | 47224 | [7 empty] | 0 | 0 | 4.73 | 11.53 | 5405.92
DRE2 | GG\25\014\B | GG | 25 | 14 | B | 6 DL | 100 | 0 | 100 | 2027-01-18 18:56 | 2027-01-20 16:16 | 148390.3721 |  |  |  |  | 148390 | 123659 |  |  | 0 | 16.32 | 0 | 12.4 | 5285.38
TS Fleet 5 | GG\28\020\B | GG | 28 | 20 | B | 1 Prestrip - Thick | 38.8002 | 38.8002 | 38.8002 | 2027-01-19 01:37 | 2027-01-21 21:10 | 132370.7692 | 132371 | [7 empty] | 0 | 0 | 19.83 | 0 | 0
TS5500Exc | W1\02\005\D | W1 | 2 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-01-19 05:16 | 2027-01-23 13:58 | 131882.5008 | [6 empty] | 131883 | 95005 | 5.14 | 0 | 0 | 7.57 | 5605
PH4100XPC#1 | GG\28\013\B | GG | 28 | 13 | B | 1 Prestrip - Thick | 100 | 59.7001 | 59.7001 | 2027-01-19 09:52 | 2027-01-21 12:02 | 113562.9732 | 113563 | [7 empty] | 0 | 0 | 11.41 | 12.07 | 5321.2
TS6060#1 | GG\24\004\D | GG | 24 | 4 | D | 7 PostStrip | 49.0446 | 0 | 49.0446 | 2027-01-19 15:45 | 2027-01-20 07:12 | 15953.9546 |  |  | 15954 | [5 empty] | 0 | 0 | 0 | 6.62 | 5803.31
PH4100A | W2\05\007\B | W2 | 5 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-01-20 03:49 | 2027-02-15 00:39 | 1084317.413 | 1084317 | [7 empty] | 0 | 0 | 61.43 | 10.08 | 5269.02
TS6060#1 | W2\06\006\B | W2 | 6 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-01-20 07:12 | 2027-01-23 07:25 | 97734.5598 | [6 empty] | 97735 | 68445 | 3.42 | 0 | 0 | 10.07 | 5267
DRE2 | GG\25\017\B | GG | 25 | 17 | B | 6 DL | 100 | 0 | 100 | 2027-01-20 16:16 | 2027-01-22 13:00 | 146461.5456 |  |  |  |  | 146462 | 122051 |  |  | 0 | 16.03 | 0 | 13.76 | 5185.88
TS5500Shv | GG\28\014\B | GG | 28 | 14 | B | 1 Prestrip - Thick | 43.8392 | 23.941 | 23.941 | 2027-01-21 12:02 | 2027-01-23 09:06 | 48309.2329 | 48309 | [7 empty] | 0 | 0 | 4.93 | 12.16 | 5299.19
PH4100XPC#1 | GG\28\014\B | GG | 28 | 14 | B | 1 Prestrip - Thick | 100 | 50.5513 | 50.5513 | 2027-01-21 12:02 | 2027-01-23 09:06 | 102004.5848 | 102005 | [7 empty] | 0 | 0 | 10.42 | 12.16 | 5299.19
TS Fleet 5 | W1\02\003\C | W1 | 2 | 3 | C | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-01-21 21:10 | 2027-01-22 05:07 | 15601.3511 | 15601 | [7 empty] | 0 | 0 | 0.94 | 12.38 | 5127.32
TS Fleet 5 | GG\28\014\B | GG | 28 | 14 | B | 1 Prestrip - Thick | 25.5077 | 25.5077 | 25.5077 | 2027-01-22 05:07 | 2027-01-23 07:23 | 51470.4214 | 51470 | [7 empty] | 0 | 0 | 5.26 | 12.16 | 5299.19
DRE2 | GG\25\018\B | GG | 25 | 18 | B | 6 DL | 100 | 0 | 100 | 2027-01-22 13:00 | 2027-01-25 01:37 | 198486.8547 |  |  |  |  | 198487 | 165406 |  |  | 0 | 16.45 | 0 | 13.73 | 5206.8
TS Fleet 5 | W1\06\002\B | W1 | 6 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-01-23 07:23 | 2027-02-12 10:37 | 947159.1035 | 947159 | [7 empty] | 0 | 0 | 29.69 | 11.06 | 5154.04
TS6060#1 | GG\25\013\B | GG | 25 | 13 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-01-23 07:25 | 2027-01-24 02:19 | 25563.4683 | [6 empty] | 25563 | 18547 | 1.86 | 0 | 0 | 12.11 | 5322
PH4100XPC#1 | GG\28\018\B | GG | 28 | 18 | B | 1 Prestrip - Thick | 100 | 38.5278 | 38.5278 | 2027-01-23 09:06 | 2027-01-25 21:15 | 134111.2406 | 134111 | [7 empty] | 0 | 0 | 13.62 | 15.47 | 5073.72
TS5500Shv | GG\24\004\D | GG | 24 | 4 | D | 7 PostStrip | 50.9554 | 0 | 50.9554 | 2027-01-23 09:06 | 2027-01-24 00:34 | 16575.5372 |  |  | 16576 | [5 empty] | 0 | 0 | 0 | 6.62 | 5803.31
TS5500Exc | CP\03\003\B | CP | 3 | 3 | B | 8 Coal Mining | 42.4 | 0 | 42.4 | 2027-01-23 13:58 | 2027-01-26 21:49 | 100589.8212 | [6 empty] | 100590 | 71811 | 1.94 | 0 | 0 | 8.8 | 5602
TS5500Shv | GG\24\004\D | GG | 24 | 4 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-01-24 00:34 | 2027-01-24 15:34 | 18294.5559 | [6 empty] | 18295 | 13720 | 2.14 | 0 | 0 | 6.62 | 5803
TS6060#1 | GG\24\004\D | GG | 24 | 4 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-01-24 02:19 | 2027-01-24 17:19 | 20304.9466 | [6 empty] | 20305 | 15228 | 2.37 | 0 | 0 | 6.62 | 5803
TS5500Shv | GG\25\013\B | GG | 25 | 13 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-01-24 15:34 | 2027-01-25 10:27 | 23032.4318 | [6 empty] | 23032 | 16711 | 1.67 | 0 | 0 | 12.11 | 5322
TS6060#1 | GG\28\020\B | GG | 28 | 20 | B | 1 Prestrip - Thick | 6.2179 | 6.2179 | 6.2179 | 2027-01-24 17:19 | 2027-01-25 14:14 | 21212.948 | 21213 | [7 empty] | 0 | 0 | 3.18 | 0 | 0
DRE1 | SC\43\010\D | SC | 43 | 10 | D | 6 DL | 100 | 0 | 100 | 2027-01-24 17:40 | 2027-02-05 05:16 | 860045.7665 |  |  |  | 48310 | 860046 | 374363 |  |  | 0 | 40 | 0 | 7.55 | 5749.5
DRE2 | GG\25\019\B | GG | 25 | 19 | B | 6 DL | 100 | 0 | 100 | 2027-01-25 01:37 | 2027-01-27 15:36 | 202906.5948 |  |  |  |  | 202907 | 169089 |  |  | 0 | 16.95 | 0 | 14.66 | 5155.33
TS5500Shv | GG\25\014\B | GG | 25 | 14 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-01-25 10:27 | 2027-01-25 23:57 | 16456.5731 | [6 empty] | 16457 | 11927 | 1.66 | 0 | 0 | 12.4 | 5285
TS6060#1 | GG\25\014\B | GG | 25 | 14 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-01-25 14:14 | 2027-01-26 03:44 | 18264.9878 | [6 empty] | 18265 | 13238 | 1.84 | 0 | 0 | 12.4 | 5285
PH4100XPC#1 | GG\28\019\B | GG | 28 | 19 | B | 1 Prestrip - Thick | 100 | 36.2805 | 36.2805 | 2027-01-25 21:15 | 2027-01-27 21:31 | 109291.8831 | 109292 | [7 empty] | 0 | 0 | 11.6 | 17.37 | 4942.41
TS5500Shv | GG\25\017\B | GG | 25 | 17 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-01-25 23:57 | 2027-01-27 04:19 | 34596.3431 | [6 empty] | 34596 | 24886 | 3.38 | 0 | 0 | 13.76 | 5186
TS6060#1 | W1\02\003\C | W1 | 2 | 3 | C | 8 Coal Mining | 100 | 0 | 100 | 2027-01-26 03:44 | 2027-01-26 18:51 | 20472.1251 | [6 empty] | 20472 | 14130 | 0.86 | 0 | 0 | 12.38 | 5127
TS6060#1 | CP\03\003\B | CP | 3 | 3 | B | 8 Coal Mining | 57.6 | 0 | 57.6 | 2027-01-26 18:51 | 2027-01-30 23:52 | 136710.2638 | [6 empty] | 136710 | 97597 | 2.63 | 0 | 0 | 8.8 | 5602
TS5500Exc | SC\43\011\D | SC | 43 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-01-26 21:49 | 2027-01-29 06:41 | 71626.1109 | [6 empty] | 71626 | 53444 | 4.45 | 0 | 0 | 7.53 | 5750
TS5500Shv | GG\25\018\B | GG | 25 | 18 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-01-27 04:19 | 2027-01-28 19:45 | 48086.6399 | [6 empty] | 48087 | 34556 | 3.46 | 0 | 0 | 13.73 | 5207
DRE2 | GG\25\020\B | GG | 25 | 20 | B | 6 DL | 100 | 0 | 100 | 2027-01-27 15:36 | 2027-01-29 21:11 | 175446.2232 |  |  |  |  | 175446 | 134959 |  |  | 0 | 21.65 | 0 | 17.08 | 4976.13
PH4100XPC#1 | GG\28\020\B | GG | 28 | 20 | B | 1 Prestrip - Thick | 100 | 48.3935 | 48.3935 | 2027-01-27 21:31 | 2027-01-30 19:48 | 165099.5119 | 165100 | [7 empty] | 0 | 0 | 24.73 | 0 | 0
TS5500Shv | GG\25\019\B | GG | 25 | 19 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-01-28 19:45 | 2027-01-30 09:17 | 45752.2149 | [6 empty] | 45752 | 32667 | 3.27 | 0 | 0 | 14.66 | 5155
TS5500Exc | W1\03\004\B | W1 | 3 | 4 | B | 8 Coal Mining | 77.1 | 0 | 77.1 | 2027-01-29 06:41 | 2027-01-30 16:26 | 42514.1335 | [6 empty] | 42514 | 29429 | 1.45 | 0 | 0 | 12.39 | 5006
DRE2 | GG\24\013\D | GG | 24 | 13 | D | 6 DL | 100 | 100 | 100 | 2027-01-29 21:11 | 2027-02-05 05:41 | 499280.0634 |  |  |  | 11625 | 499280 | 220869 |  |  | 0 | 23.25 | 0 | 6.95 | 5776.95
TS5500Shv | GG\25\020\B | GG | 25 | 20 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-01-30 09:17 | 2027-01-30 22:41 | 16344.7967 | [6 empty] | 16345 | 11510 | 1.87 | 0 | 0 | 17.08 | 4976
TS5500Exc | W1\03\002\D | W1 | 3 | 2 | D | 7 PostStrip | 61.4232 | 0 | 61.4232 | 2027-01-30 16:26 | 2027-02-01 15:18 | 41446.1732 |  |  | 41446 | [5 empty] | 0 | 0 | 0 | 7.34 | 5628.47
PH4100XPC#1 | W2\01\007\D | W2 | 1 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-01-30 19:48 | 2027-02-07 14:50 | 423382.6931 | 423383 | [7 empty] | 0 | 0 | 20.11 | 5.83 | 5748.03
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 07:00 |  | 5d 07:00 | 2027-01-30 22:41 | 2027-02-05 05:41
TS6060#1 | W1\03\004\B | W1 | 3 | 4 | B | 8 Coal Mining | 22.9 | 0 | 22.9 | 2027-01-30 23:52 | 2027-01-31 09:11 | 12600.8808 | [6 empty] | 12601 | 8723 | 0.43 | 0 | 0 | 12.39 | 5006
TS6060#1 | W1\03\002\D | W1 | 3 | 2 | D | 7 PostStrip | 38.5768 | 0 | 38.5768 | 2027-01-31 09:11 | 2027-02-01 10:24 | 26030.2456 |  |  | 26030 | [5 empty] | 0 | 0 | 0 | 7.34 | 5628.47
TS6060#1 | W1\03\003\D | W1 | 3 | 3 | D | 7 PostStrip | 55.2942 | 0 | 55.2942 | 2027-02-01 10:24 | 2027-02-03 16:25 | 55731.8612 |  |  | 55732 | [5 empty] | 0 | 0 | 0 | 7.5 | 5615.57
TS5500Exc | W1\03\003\D | W1 | 3 | 3 | D | 7 PostStrip | 44.7058 | 0 | 44.7058 | 2027-02-01 15:18 | 2027-02-03 18:15 | 45059.5799 |  |  | 45060 | [5 empty] | 0 | 0 | 0 | 7.5 | 5615.57
TS6060#1 | W1\03\002\D | W1 | 3 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-02-03 16:25 | 2027-02-04 16:29 | 32560.4696 | [6 empty] | 32560 | 23463 | 5.45 | 0 | 0 | 7.34 | 5628
TS5500Exc | W1\03\003\D | W1 | 3 | 3 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2027-02-03 18:15 | 2027-02-06 06:32 | 75929.016 | [6 empty] | 75929 | 54711 | 2.74 | 0 | 0 | 7.5 | 5616
TS6060#1 | W1\03\003\D | W1 | 3 | 3 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2027-02-04 16:29 | 2027-02-07 04:46 | 81583.3044 | [6 empty] | 81583 | 58786 | 2.94 | 0 | 0 | 7.5 | 5616
DRE1 | SC\44\017\D | SC | 44 | 17 | D | 6 DL | 100 | 0 | 100 | 2027-02-05 05:16 | 2027-02-18 10:50 | 990943.8426 |  |  |  | 54644 | 990944 | 430176 |  |  | 0 | 40 | 0 | 7.29 | 5761.38
DRE2 | GG\24\014\D | GG | 24 | 14 | D | 6 DL | 100 | 100 | 100 | 2027-02-05 05:41 | 2027-02-09 02:46 | 304785.2985 |  |  |  | 7096 | 304785 | 134829 |  |  | 0 | 23.7 | 0 | 7.04 | 5767.97
TS5500Shv | GG\24\013\D | GG | 24 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-02-05 05:41 | 2027-02-07 09:16 | 62903.7908 | [6 empty] | 62904 | 46915 | 4.69 | 0 | 0 | 6.95 | 5777
TS5500Exc | SC\43\010\D | SC | 43 | 10 | D | 7 PostStrip | 100 | 0 | 100 | 2027-02-06 06:32 | 2027-02-09 02:51 | 60425.0918 |  |  | 60425 | [5 empty] | 0 | 0 | 0 | 7.55 | 5749.5
TS6060#1 | CP\03\003\D | CP | 3 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-02-07 04:46 | 2027-04-23 16:10 | 1869012.297 | 1869012 | [7 empty] | 0 | 0 | 53.41 | 6.54 | 5831.86
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 17:30 |  | 1d 17:30 | 2027-02-07 09:16 | 2027-02-09 02:46
PH4100XPC#1 | W2\01\005\B | W2 | 1 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-02-07 14:50 | 2027-02-11 22:49 | 235367.6386 | 235368 | [7 empty] | 0 | 0 | 3.47 | 10.22 | 5287.17
DRE2 | GG\24\017\D | GG | 24 | 17 | D | 6 DL | 100 | 100 | 100 | 2027-02-09 02:46 | 2027-02-13 03:29 | 316659.6731 |  |  |  | 7373 | 316660 | 140082 |  |  | 0 | 23.89 | 0 | 7.09 | 5765.36
TS5500Shv | GG\24\014\D | GG | 24 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-02-09 02:46 | 2027-02-10 09:01 | 36878.9408 | [6 empty] | 36879 | 27461 | 4.64 | 0 | 0 | 7.04 | 5768
TS5500Exc | W2\01\007\D | W2 | 1 | 7 | D | 7 PostStrip | 100 | 0 | 100 | 2027-02-09 02:51 | 2027-02-15 17:13 | 140055.8497 |  |  | 140056 | [5 empty] | 0 | 0 | 0 | 5.83 | 5748.03
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 18:28 |  | 2d 18:28 | 2027-02-10 09:01 | 2027-02-13 03:29
PH4100XPC#1 | W2\01\006\D | W2 | 1 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-02-11 22:49 | 2027-02-19 10:21 | 406368.1917 | 406368 | [7 empty] | 0 | 0 | 17.95 | 5.73 | 5752.65
TS Fleet 5 | W1\02\003\D | W1 | 2 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-02-12 10:37 | 2027-02-12 13:29 | 5589.699 | 5590 | [7 empty] | 0 | 0 | 2.65 | 7.41 | 5626.61
TS Fleet 5 | W1\03\004\D | W1 | 3 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-02-12 13:29 | 2027-02-14 03:23 | 74297.8951 | 74298 | [7 empty] | 0 | 0 | 8.7 | 7.65 | 5601.99
DRE2 | GG\24\018\D | GG | 24 | 18 | D | 6 DL | 100 | 100 | 100 | 2027-02-13 03:29 | 2027-02-19 13:32 | 504382.9952 |  |  |  | 11743 | 504383 | 223126 |  |  | 0 | 23.48 | 0 | 7.08 | 5765.87
TS5500Shv | GG\24\017\D | GG | 24 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-02-13 03:29 | 2027-02-14 11:20 | 38829.646 | [6 empty] | 38830 | 28892 | 4.73 | 0 | 0 | 7.09 | 5765
TS Fleet 5 | W1\06\003\B | W1 | 6 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-02-14 03:23 | 2027-02-26 23:05 | 603103.417 | 603103 | [7 empty] | 0 | 0 | 29.11 | 11.3 | 5115.95
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 02:13 |  | 5d 02:13 | 2027-02-14 11:20 | 2027-02-19 13:32
PH4100A | W2\06\007\B | W2 | 6 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-02-15 00:39 | 2027-03-13 17:52 | 1152307.203 | 1152307 | [7 empty] | 0 | 0 | 70.27 | 10.52 | 5235.17
TS5500Exc | W2\01\005\B | W2 | 1 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-02-15 17:13 | 2027-02-22 12:42 | 205913.8402 | [6 empty] | 205914 | 144686 | 2.25 | 0 | 0 | 10.22 | 5287
DRE1 | SC\44\016\D | SC | 44 | 16 | D | 6 DL | 100 | 0 | 100 | 2027-02-18 10:50 | 2027-02-28 18:33 | 773021.2128 |  |  |  | 58785 | 773021 | 529064 |  |  | 0 | 40 | 0 | 7.38 | 5760.94
PH4100XPC#1 | W2\01\004\A | W2 | 1 | 4 | A | 1 Prestrip - Thick | 100 | 0 | 87.1333 | 2027-02-19 10:21 | 2027-06-03 11:52 | 5818584.776 | 5818585 | [7 empty] | 0 | 0 | 57.85 | 0 | 0
DRE2 | GG\24\019\D | GG | 24 | 19 | D | 6 DL | 100 | 100 | 100 | 2027-02-19 13:32 | 2027-02-25 19:55 | 492339.0271 |  |  |  | 11463 | 492339 | 217798 |  |  | 0 | 22.92 | 0 | 6.98 | 5773.43
TS5500Shv | GG\24\018\D | GG | 24 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-02-19 13:32 | 2027-02-21 17:24 | 63242.7041 | [6 empty] | 63243 | 47093 | 4.71 | 0 | 0 | 7.08 | 5766
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 02:31 |  | 4d 02:31 | 2027-02-21 17:24 | 2027-02-25 19:55
TS5500Exc | W2\01\006\D | W2 | 1 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2027-02-22 12:42 | 2027-03-01 22:06 | 156898.4251 |  |  | 156898 | [5 empty] | 0 | 0 | 0 | 5.73 | 5752.65
DRE2 | GG\24\020\D | GG | 24 | 20 | D | 6 DL | 100 | 100 | 100 | 2027-02-25 19:55 | 2027-03-02 17:25 | 384715.6693 |  |  |  | 7164 | 384716 | 171940 |  |  | 0 | 17.91 | 0 | 6.87 | 5781.86
TS5500Shv | GG\24\019\D | GG | 24 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-02-25 19:55 | 2027-02-27 23:08 | 62455.9898 | [6 empty] | 62456 | 46544 | 4.65 | 0 | 0 | 6.98 | 5773
TS Fleet 5 | W1\06\004\D | W1 | 6 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-02-26 23:05 | 2027-03-02 08:38 | 159831.9076 | 159832 | [7 empty] | 0 | 0 | 14.39 | 7.9 | 5559.82
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 18:17 |  | 2d 18:17 | 2027-02-27 23:08 | 2027-03-02 17:25
DRE1 | SC\44\015\D | SC | 44 | 15 | D | 6 DL | 100 | 0 | 100 | 2027-02-28 18:33 | 2027-03-09 11:15 | 651229.6677 |  |  |  | 49523 | 651230 | 445709 |  |  | 0 | 40 | 0 | 7.43 | 5755.65
TS5500Exc | W2\01\007\D | W2 | 1 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-03-01 22:06 | 2027-03-07 05:29 | 160447.3218 | [6 empty] | 160447 | 116698 | 4.42 | 0 | 0 | 5.83 | 5748
TS Fleet 5 | W1\07\002\B | W1 | 7 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-03-02 08:38 | 2027-03-18 04:34 | 744656.7073 | 744657 | [7 empty] | 0 | 0 | 30.24 | 10.79 | 5179.68
DRE2 | GG\24\021\D | GG | 24 | 21 | D | 6 DL | 100 | 0 | 100 | 2027-03-02 17:25 | 2027-03-09 01:00 | 496255.0513 |  |  |  | 37738 | 496255 | 339642 |  |  | 0 | 40 | 0 | 6.78 | 5789.52
TS5500Shv | GG\24\020\D | GG | 24 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-03-02 17:25 | 2027-03-04 19:07 | 60603.7336 | [6 empty] | 60604 | 45234 | 4.52 | 0 | 0 | 6.87 | 5782
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 05:52 |  | 4d 05:52 | 2027-03-04 19:07 | 2027-03-09 01:00
TS5500Exc | W2\01\006\D | W2 | 1 | 6 | D | 8 Coal Mining | 65.4 | 0 | 65.4 | 2027-03-07 05:29 | 2027-03-10 21:06 | 110355.6339 | [6 empty] | 110356 | 80311 | 2.68 | 0 | 0 | 5.73 | 5753
DRE2 | GG\24\022\D | GG | 24 | 22 | D | 6 DL | 100 | 100 | 100 | 2027-03-09 01:00 | 2027-03-14 01:30 | 394529.5904 |  |  |  | 7409 | 394530 | 114968 |  |  | 0 | 14.74 | 0 | 6.72 | 5797.93
TS5500Shv | GG\24\021\D | GG | 24 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-03-09 01:00 | 2027-03-11 02:41 | 60588.4114 | [6 empty] | 60588 | 45294 | 4.53 | 0 | 0 | 6.78 | 5790
DRE1 | SC\44\014\D | SC | 44 | 14 | D | 6 DL | 100 | 0 | 100 | 2027-03-09 11:15 | 2027-03-17 19:31 | 624943.3578 |  |  |  | 47524 | 624943 | 427718 |  |  | 0 | 40 | 0 | 7.46 | 5753.6
TS5500Exc | W2\05\007\B | W2 | 5 | 7 | B | 8 Coal Mining | 15.9 | 0 | 15.9 | 2027-03-10 21:06 | 2027-03-11 09:24 | 15499.8785 | [6 empty] | 15500 | 10849 | 0.54 | 0 | 0 | 10.08 | 5269
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 22:49 |  | 2d 22:49 | 2027-03-11 02:41 | 2027-03-14 01:30
TS5500Exc | W1\02\003\D | W1 | 2 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2027-03-11 09:24 | 2027-03-13 04:14 | 37889.806 |  |  | 37890 | [5 empty] | 0 | 0 | 0 | 7.41 | 5626.61
TS5500Exc | W1\02\003\D | W1 | 2 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-03-13 04:14 | 2027-03-17 16:39 | 136545.7746 | [6 empty] | 136546 | 98408 | 6.06 | 0 | 0 | 7.41 | 5627
PH4100A | W2\05\008\B | W2 | 5 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-03-13 17:52 | 2027-04-11 17:09 | 1267893.788 | 1267894 | [7 empty] | 0 | 0 | 72.86 | 11.02 | 5204.31
DRE2 | GG\26\012\B | GG | 26 | 12 | B | 6 DL | 100 | 0 | 100 | 2027-03-14 01:30 | 2027-03-16 16:49 | 207329.7251 |  |  |  |  | 207330 | 172775 |  |  | 0 | 17.38 | 0 | 11.73 | 5372.67
TS5500Shv | GG\24\022\D | GG | 24 | 22 | D | 7 PostStrip | 100 | 0 | 100 | 2027-03-14 01:30 | 2027-03-16 12:07 | 62840.008 |  |  | 62840 | [5 empty] | 0 | 0 | 0 | 6.72 | 5797.93
TS5500Shv | GG\24\022\D | GG | 24 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-03-16 12:07 | 2027-03-19 04:20 | 78300.5958 | [6 empty] | 78301 | 58638 | 4.72 | 0 | 0 | 6.72 | 5798
DRE2 | GG\26\011\B | GG | 26 | 11 | B | 6 DL | 100 | 0 | 100 | 2027-03-16 16:49 | 2027-03-19 16:18 | 234051.196 |  |  |  |  | 234051 | 180039 |  |  | 0 | 18.03 | 0 | 11.41 | 5415.77
TS5500Exc | W2\06\007\B | W2 | 6 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-03-17 16:39 | 2027-03-19 19:50 | 64484.6014 | [6 empty] | 64485 | 45076 | 2.25 | 0 | 0 | 10.52 | 5235
DRE1 | SC\44\013\D | SC | 44 | 13 | D | 6 DL | 100 | 0 | 100 | 2027-03-17 19:31 | 2027-03-25 22:49 | 609447.8043 |  |  |  | 46346 | 609448 | 417113 |  |  | 0 | 40 | 0 | 7.44 | 5755.9
TS Fleet 5 | W1\07\003\B | W1 | 7 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-03-18 04:34 | 2027-03-31 19:48 | 641392.6267 | 641393 | [7 empty] | 0 | 0 | 33.43 | 11.43 | 5111.34
TS5500Shv | GG\26\012\B | GG | 26 | 12 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-03-19 04:20 | 2027-03-20 20:19 | 48754.2365 | [6 empty] | 48754 | 35395 | 3.54 | 0 | 0 | 11.73 | 5373
DRE2 | GG\26\009\B | GG | 26 | 9 | B | 6 DL | 100 | 0 | 100 | 2027-03-19 16:18 | 2027-03-22 17:01 | 238047.0802 |  |  |  |  | 238047 | 198373 |  |  | 0 | 19.81 | 0 | 10.27 | 5504.43
TS5500Exc | GG\29\011\X1 | GG | 29 | 11 | X1 | 1 Prestrip - Thick | 100 | 96.3984 | 95.9174 | 2027-03-19 19:50 | 2027-04-18 02:32 | 621893.8865 | 621894 | [7 empty] | 0 | 0 | 46.56 | 14.63 | 5129.88
TS5500Shv | GG\26\011\B | GG | 26 | 11 | B | 8 Coal Mining | 55.7 | 0 | 55.7 | 2027-03-20 20:19 | 2027-03-21 18:44 | 27342.6077 | [6 empty] | 27343 | 19882 | 1.99 | 0 | 0 | 11.41 | 5416
TS5500Shv | GG\29\009\X1 | GG | 29 | 9 | X1 | 1 Prestrip - Thick | 35.5351 | 35.5351 | 35.5351 | 2027-03-21 18:44 | 2027-04-02 01:16 | 288001.4172 | 288001 | [7 empty] | 0 | 0 | 29.23 | 14.01 | 5161.05
DRE2 | GG\26\008\B | GG | 26 | 8 | B | 6 DL | 100 | 0 | 100 | 2027-03-22 17:01 | 2027-03-26 01:07 | 262234.4391 |  |  |  |  | 262234 | 201719 |  |  | 0 | 20.17 | 0 | 10.36 | 5484.34
DRE1 | SC\44\012\D | SC | 44 | 12 | D | 6 DL | 100 | 0 | 100 | 2027-03-25 22:49 | 2027-04-02 23:29 | 601211.2369 |  |  |  | 45719 | 601211 | 411475 |  |  | 0 | 40 | 0 | 7.43 | 5756.28
DRE2 | GG\26\007\B | GG | 26 | 7 | B | 6 DL | 100 | 0 | 100 | 2027-03-26 01:07 | 2027-03-29 08:45 | 260733.7834 |  |  |  |  | 260734 | 200564 |  |  | 0 | 20.04 | 0 | 10.55 | 5455.86
DRE2 | GG\26\006\B | GG | 26 | 6 | B | 6 DL | 100 | 0 | 100 | 2027-03-29 08:45 | 2027-04-01 09:47 | 239131.853 |  |  |  |  | 239132 | 199277 |  |  | 0 | 19.96 | 0 | 10.69 | 5433.79
TS Fleet 5 | GG\29\009\X1 | GG | 29 | 9 | X1 | 1 Prestrip - Thick | 35.6289 | 35.6289 | 35.6289 | 2027-03-31 19:48 | 2027-04-06 23:08 | 288761.7118 | 288762 | [7 empty] | 0 | 0 | 29.31 | 14.01 | 5161.05
DRE2 | GG\26\005\B | GG | 26 | 5 | B | 6 DL | 100 | 0 | 100 | 2027-04-01 09:47 | 2027-04-15 15:23 | 1118399.057 |  |  |  |  | 1118399 | 532571 |  |  | 0 | 20.08 | 0 | 10.51 | 5449.21
TS5500Shv | GG\26\006\B | GG | 26 | 6 | B | 8 Coal Mining | 50.8 | 0 | 50.8 | 2027-04-02 01:16 | 2027-04-02 22:04 | 25381.1875 | [6 empty] | 25381 | 18509 | 1.85 | 0 | 0 | 10.69 | 5434
TS5500Shv | GG\29\010\X1 | GG | 29 | 10 | X1 | 1 Prestrip - Thick | 1.4662 | 1.4662 | 1.4662 | 2027-04-02 22:04 | 2027-04-03 08:12 | 10782.0402 | 10782 | [7 empty] | 0 | 0 | 1.04 | 14.35 | 5146.14
DRE1 | SC\44\011\D | SC | 44 | 11 | D | 6 DL | 100 | 0 | 100 | 2027-04-02 23:29 | 2027-04-17 13:16 | 1091492.812 |  |  |  | 60543 | 1091493 | 474236 |  |  | 0 | 40 | 0 | 7.49 | 5751.89
TS5500Shv | GG\29\011\X1 | GG | 29 | 11 | X1 | 1 Prestrip - Thick | 3.6016 | 3.6016 | 3.6016 | 2027-04-03 08:12 | 2027-04-04 06:02 | 23351.2494 | 23351 | [7 empty] | 0 | 0 | 1.75 | 14.63 | 5129.88
TS5500Shv | GG\29\013\X1 | GG | 29 | 13 | X1 | 1 Prestrip - Thick | 7.7514 | 7.7514 | 7.7514 | 2027-04-04 06:02 | 2027-04-05 15:49 | 35885.6973 | 35886 | [7 empty] | 0 | 0 | 3.94 | 15.14 | 5087.53
TS5500Shv | GG\29\017\B | GG | 29 | 17 | B | 1 Prestrip - Thick | 1.6522 | 1.6522 | 1.6522 | 2027-04-05 15:49 | 2027-04-05 22:44 | 7323.4098 | 7323 | [7 empty] | 0 | 0 | 0.74 | 14.75 | 5107.03
TS5500Shv | GG\29\018\B | GG | 29 | 18 | B | 1 Prestrip - Thick | 15.0001 | 15.0001 | 15.0001 | 2027-04-05 22:44 | 2027-04-08 00:25 | 52849.0094 | 52849 | [7 empty] | 0 | 0 | 5.41 | 16.33 | 5007.3
TS Fleet 5 | GG\29\010\X1 | GG | 29 | 10 | X1 | 1 Prestrip - Thick | 45.0328 | 45.0328 | 45.0328 | 2027-04-06 23:08 | 2027-04-14 00:06 | 331164.687 | 331165 | [7 empty] | 0 | 0 | 31.89 | 14.35 | 5146.14
TS5500Shv | GG\29\019\B | GG | 29 | 19 | B | 1 Prestrip - Thick | 9.4873 | 9.4873 | 9.4873 | 2027-04-08 00:25 | 2027-04-09 04:55 | 30483.6105 | 30484 | [7 empty] | 0 | 0 | 3.6 | 18.44 | 4858.73
TS5500Shv | GG\29\020\B | GG | 29 | 20 | B | 1 Prestrip - Thick | 16.9435 | 16.9435 | 16.9435 | 2027-04-09 04:55 | 2027-04-11 12:43 | 60031.7502 | 60032 | [7 empty] | 0 | 0 | 8.63 | 0 | 0
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 02:40 |  | 4d 02:40 | 2027-04-11 12:43 | 2027-04-15 15:23
PH4100A | W2\06\008\D | W2 | 6 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-04-11 17:09 | 2027-05-14 12:35 | 1426991.101 | 1426991 | [7 empty] | 0 | 0 | 75.69 | 5.93 | 5746
TS Fleet 5 | GG\29\011\X1 | GG | 29 | 11 | X1 | 1 Prestrip - Thick | 0.48103 | 0 | 0.48103 | 2027-04-14 00:06 | 2027-04-14 01:41 | 3118.7984 | 3119 | [7 empty] | 0 | 0 | 0.23 | 14.63 | 5129.88
TS Fleet 5 | GG\29\012\X2 | GG | 29 | 12 | X2 | 1 Prestrip - Thick | 36.8969 | 0 | 36.8969 | 2027-04-14 01:41 | 2027-04-19 06:46 | 245156.475 | 245156 | [7 empty] | 0 | 0 | 23.55 | 0 | 0
DRE2 | GG\25\012\D | GG | 25 | 12 | D | 6 DL | 100 | 100 | 100 | 2027-04-15 15:23 | 2027-04-21 20:02 | 486685.0554 |  |  |  | 11331 | 486685 | 215297 |  |  | 0 | 22.66 | 0 | 6.74 | 5795.45
TS5500Shv | GG\26\005\B | GG | 26 | 5 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-04-15 15:23 | 2027-04-17 20:56 | 65310.0653 | [6 empty] | 65310 | 47590 | 1.84 | 0 | 0 | 10.51 | 5449
DRE1 | SC\45\016\D | SC | 45 | 16 | D | 6 DL | 100 | 0 | 100 | 2027-04-17 13:16 | 2027-04-30 16:11 | 982728.1065 |  |  |  | 54908 | 982728 | 427434 |  |  | 0 | 40 | 0 | 7.4 | 5759.01
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 05:36 |  | 0d 05:36 | 2027-04-17 20:56 | 2027-04-18 02:32
TS5500Exc | GG\29\010\X1 | GG | 29 | 10 | X1 | 1 Prestrip - Thick | 100 | 33.4136 | 33.4136 | 2027-04-18 02:32 | 2027-04-29 16:09 | 245719.074 | 245719 | [7 empty] | 0 | 0 | 23.66 | 14.35 | 5146.14
TS5500Shv | GG\29\011\X1 | GG | 29 | 11 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-04-18 02:32 | 2027-04-18 08:20 | 7065.6704 | [6 empty] | 7066 | 5066 | 0.51 | 0 | 0 | 14.63 | 5130
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 11:42 |  | 3d 11:42 | 2027-04-18 08:20 | 2027-04-21 20:02
TS Fleet 5 | GG\29\013\X1 | GG | 29 | 13 | X1 | 1 Prestrip - Thick | 34.807 | 34.807 | 34.807 | 2027-04-19 06:46 | 2027-04-22 16:59 | 161141.2953 | 161141 | [7 empty] | 0 | 0 | 17.71 | 15.14 | 5087.53
DRE2 | GG\25\011\D | GG | 25 | 11 | D | 6 DL | 100 | 100 | 100 | 2027-04-21 20:02 | 2027-04-28 01:16 | 488630.3861 |  |  |  | 8857 | 488630 | 212572 |  |  | 0 | 22.14 | 0 | 6.58 | 5808.76
TS5500Shv | GG\25\012\D | GG | 25 | 12 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-04-21 20:02 | 2027-04-22 20:23 | 29689.5148 | [6 empty] | 29690 | 22196 | 2.22 | 0 | 0 | 6.74 | 5795
TS Fleet 5 | GG\29\014\X1 | GG | 29 | 14 | X1 | 1 Prestrip - Thick | 46.2118 | 46.2118 | 46.2118 | 2027-04-22 16:59 | 2027-04-26 21:38 | 197283.9149 | 197284 | [7 empty] | 0 | 0 | 16.27 | 14.8 | 5112.73
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 04:54 |  | 5d 04:54 | 2027-04-22 20:23 | 2027-04-28 01:16
TS6060#1 | GG\29\010\X1 | GG | 29 | 10 | X1 | 1 Prestrip - Thick | 100 | 20.0874 | 20.0874 | 2027-04-23 16:10 | 2027-04-29 16:09 | 147719.9092 | 147720 | [7 empty] | 0 | 0 | 14.22 | 14.35 | 5146.14
TS Fleet 5 | GG\29\017\B | GG | 29 | 17 | B | 1 Prestrip - Thick | 44.6226 | 44.6226 | 44.6226 | 2027-04-26 21:38 | 2027-05-01 02:33 | 197796.1159 | 197796 | [7 empty] | 0 | 0 | 20 | 14.75 | 5107.03
DRE2 | GG\25\010\D | GG | 25 | 10 | D | 6 DL | 100 | 100 | 100 | 2027-04-28 01:16 | 2027-05-03 19:20 | 452008.7976 |  |  |  | 10524 | 452009 | 199957 |  |  | 0 | 21.05 | 0 | 6.56 | 5808.68
TS5500Shv | GG\25\011\D | GG | 25 | 11 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-04-28 01:16 | 2027-04-29 01:33 | 29613.9778 | [6 empty] | 29614 | 22174 | 2.22 | 0 | 0 | 6.58 | 5809
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 14:36 |  | 0d 14:36 | 2027-04-29 01:33 | 2027-04-29 16:09
TS6060#1 | W2\01\006\D | W2 | 1 | 6 | D | 8 Coal Mining | 34.6 | 0 | 34.6 | 2027-04-29 16:09 | 2027-05-01 11:23 | 58507.411 | [6 empty] | 58507 | 42578 | 1.42 | 0 | 0 | 5.73 | 5753
TS5500Exc | SC\43\010\D | SC | 43 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-04-29 16:09 | 2027-05-02 02:31 | 73501.5089 | [6 empty] | 73502 | 54975 | 4.58 | 0 | 0 | 7.55 | 5750
TS5500Shv | GG\29\010\X1 | GG | 29 | 10 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2027-04-29 16:09 | 2027-04-30 06:02 | 16913.7783 | [6 empty] | 16914 | 12147 | 1.22 | 0 | 0 | 14.35 | 5146
TS5500Shv | GG\29\010\X2 | GG | 29 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2027-04-30 06:02 | 2027-05-02 21:45 | 68311.731 | 68312 | [7 empty] | 0 | 0 | 6.87 | 0 | 0
DRE1 | SC\45\015\D | SC | 45 | 15 | D | 6 DL | 100 | 0 | 100 | 2027-04-30 16:11 | 2027-05-08 13:24 | 590453.476 |  |  |  | 44901 | 590453 | 404113 |  |  | 0 | 40 | 0 | 7.43 | 5756.09
TS Fleet 5 | GG\29\018\B | GG | 29 | 18 | B | 1 Prestrip - Thick | 33.1709 | 33.1709 | 33.1709 | 2027-05-01 02:33 | 2027-05-03 14:11 | 116869.454 | 116869 | [7 empty] | 0 | 0 | 11.95 | 16.33 | 5007.3
TS6060#1 | W2\05\007\B | W2 | 5 | 7 | B | 8 Coal Mining | 84.1 | 0 | 84.1 | 2027-05-01 11:23 | 2027-05-04 00:02 | 82069.0045 | [6 empty] | 82069 | 57442 | 2.88 | 0 | 0 | 10.08 | 5269
TS5500Exc | SC\44\017\D | SC | 44 | 17 | D | 7 PostStrip | 100 | 0 | 100 | 2027-05-02 02:31 | 2027-05-05 00:11 | 61618.6038 |  |  | 61619 | [5 empty] | 0 | 0 | 0 | 7.29 | 5761.38
TS5500Shv | GG\29\010\B | GG | 29 | 10 | B | 1 Prestrip - Thick | 51.8746 | 51.8746 | 51.8746 | 2027-05-02 21:45 | 2027-05-04 13:10 | 42250.9855 | 42251 | [7 empty] | 0 | 0 | 4.22 | 10.99 | 5451.69
TS Fleet 5 | GG\29\010\B | GG | 29 | 10 | B | 1 Prestrip - Thick | 21.8581 | 21.8581 | 21.8581 | 2027-05-03 14:11 | 2027-05-03 23:16 | 17803.0079 | 17803 | [7 empty] | 0 | 0 | 1.78 | 10.99 | 5451.69
DRE2 | GG\25\009\D | GG | 25 | 9 | D | 6 DL | 100 | 100 | 100 | 2027-05-03 19:20 | 2027-05-09 08:03 | 434525.0036 |  |  |  | 10117 | 434525 | 192223 |  |  | 0 | 20.24 | 0 | 6.58 | 5807.88
TS Fleet 5 | GG\29\019\B | GG | 29 | 19 | B | 1 Prestrip - Thick | 34.3683 | 34.3683 | 34.3683 | 2027-05-03 23:16 | 2027-05-06 07:36 | 110428.6802 | 110429 | [7 empty] | 0 | 0 | 13.06 | 18.44 | 4858.73
TS6060#1 | GG\26\011\B | GG | 26 | 11 | B | 8 Coal Mining | 44.3 | 0 | 44.3 | 2027-05-04 00:02 | 2027-05-04 16:07 | 21771.0335 | [6 empty] | 21771 | 15831 | 1.58 | 0 | 0 | 11.41 | 5416
TS5500Shv | GG\25\010\D | GG | 25 | 10 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-05-04 13:10 | 2027-05-05 12:21 | 28265.7617 | [6 empty] | 28266 | 21181 | 2.12 | 0 | 0 | 6.56 | 5809
TS6060#1 | GG\26\009\B | GG | 26 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-05-04 16:07 | 2027-05-06 05:57 | 51217.0338 | [6 empty] | 51217 | 37457 | 3.75 | 0 | 0 | 10.27 | 5504
TS5500Exc | SC\44\017\D | SC | 44 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-05-05 00:11 | 2027-05-06 16:23 | 50631.8005 | [6 empty] | 50632 | 37856 | 3.27 | 0 | 0 | 7.29 | 5761
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 19:42 |  | 3d 19:42 | 2027-05-05 12:21 | 2027-05-09 08:03
TS6060#1 | GG\26\008\B | GG | 26 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-05-06 05:57 | 2027-05-07 20:09 | 51691.4731 | [6 empty] | 51691 | 37767 | 3.78 | 0 | 0 | 10.36 | 5484
TS Fleet 5 | GG\29\020\B | GG | 29 | 20 | B | 1 Prestrip - Thick | 29.6578 | 29.6578 | 29.6578 | 2027-05-06 07:36 | 2027-05-08 13:13 | 105079.0245 | 105079 | [7 empty] | 0 | 0 | 15.11 | 0 | 0
TS5500Exc | SC\44\016\D | SC | 44 | 16 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-05-06 16:23 | 2027-05-09 04:26 | 75641.1183 | [6 empty] | 75641 | 56570 | 4.1 | 0 | 0 | 7.38 | 5761
TS6060#1 | GG\26\007\B | GG | 26 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-05-07 20:09 | 2027-05-09 09:42 | 50822.7593 | [6 empty] | 50823 | 37090 | 3.71 | 0 | 0 | 10.55 | 5456
TS Fleet 5 | W1\07\004\D | W1 | 7 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-05-08 13:13 | 2027-05-17 00:08 | 397713.7651 | 397714 | [7 empty] | 0 | 0 | 81.44 | 8.05 | 5547.71
DRE1 | SC\45\014\D | SC | 45 | 14 | D | 6 DL | 100 | 0 | 100 | 2027-05-08 13:24 | 2027-05-16 10:20 | 589557.4646 |  |  |  | 44833 | 589557 | 403499 |  |  | 0 | 40 | 0 | 7.45 | 5754.68
TS5500Exc | W2\05\008\B | W2 | 5 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-05-09 04:26 | 2027-05-10 16:53 | 45920.66 | [6 empty] | 45921 | 31993 | 1.62 | 0 | 0 | 11.02 | 5204
DRE2 | GG\25\008\D | GG | 25 | 8 | D | 6 DL | 100 | 100 | 100 | 2027-05-09 08:03 | 2027-05-14 18:17 | 426392.9493 |  |  |  | 7940 | 426393 | 190567 |  |  | 0 | 19.85 | 0 | 6.57 | 5809.04
TS5500Shv | GG\25\009\D | GG | 25 | 9 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-05-09 08:03 | 2027-05-10 07:57 | 29153.4195 | [6 empty] | 29153 | 21829 | 2.18 | 0 | 0 | 6.58 | 5808
TS6060#1 | GG\26\006\B | GG | 26 | 6 | B | 8 Coal Mining | 49.2 | 0 | 49.2 | 2027-05-09 09:42 | 2027-05-10 03:51 | 24555.4571 | [6 empty] | 24555 | 17907 | 1.79 | 0 | 0 | 10.69 | 5434
TS6060#1 | GG\29\010\B | GG | 29 | 10 | B | 1 Prestrip - Thick | 25.9137 | 25.9137 | 25.9137 | 2027-05-10 03:51 | 2027-05-11 00:18 | 21106.2375 | 21106 | [7 empty] | 0 | 0 | 2.11 | 10.99 | 5451.69
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 22:08 |  | 0d 22:08 | 2027-05-10 07:57 | 2027-05-11 06:06
TS5500Exc | SC\44\015\D | SC | 44 | 15 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-05-10 16:53 | 2027-05-12 21:46 | 66611.8918 | [6 empty] | 66612 | 49816 | 4.02 | 0 | 0 | 7.43 | 5756
TS6060#1 | GG\29\011\X1 | GG | 29 | 11 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-05-11 00:18 | 2027-05-11 06:06 | 7842.1177 | [6 empty] | 7842 | 5623 | 0.56 | 0 | 0 | 14.63 | 5130
TS6060#1 | GG\29\011\X2 | GG | 29 | 11 | X2 | 1 Prestrip - Thick | 49.0446 | 0 | 49.0446 | 2027-05-11 06:06 | 2027-05-12 14:59 | 33930.7876 | 33931 | [7 empty] | 0 | 0 | 3.41 | 0 | 0
TS5500Shv | GG\29\011\X2 | GG | 29 | 11 | X2 | 1 Prestrip - Thick | 50.9554 | 0 | 50.9554 | 2027-05-11 06:06 | 2027-05-12 14:59 | 35252.7664 | 35253 | [7 empty] | 0 | 0 | 3.54 | 0 | 0
TS6060#1 | GG\26\005\B | GG | 26 | 5 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-05-12 14:59 | 2027-05-14 20:32 | 72486.9956 | [6 empty] | 72487 | 52819 | 2.05 | 0 | 0 | 10.51 | 5449
TS5500Shv | GG\29\011\B | GG | 29 | 11 | B | 1 Prestrip - Thick | 48.4672 | 48.4672 | 48.4672 | 2027-05-12 14:59 | 2027-05-14 05:44 | 41538.894 | 41539 | [7 empty] | 0 | 0 | 4.16 | 11.58 | 5401.12
TS5500Exc | SC\44\014\D | SC | 44 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-05-12 21:46 | 2027-05-15 01:22 | 64989.6531 | [6 empty] | 64990 | 48564 | 4.05 | 0 | 0 | 7.46 | 5754
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 12:33 |  | 0d 12:33 | 2027-05-14 05:44 | 2027-05-14 18:17
PH4100A | W2\01\004\A | W2 | 1 | 4 | A | 1 Prestrip - Thick | 100 | 0 | 12.8667 | 2027-05-14 12:35 | 2027-06-03 11:52 | 859208.9516 | 859209 | [7 empty] | 0 | 0 | 8.54 | 0 | 0
DRE2 | GG\25\007\D | GG | 25 | 7 | D | 6 DL | 100 | 100 | 100 | 2027-05-14 18:17 | 2027-05-20 05:20 | 429058.8782 |  |  |  | 7990 | 429059 | 191758 |  |  | 0 | 19.98 | 0 | 6.58 | 5807.94
TS5500Shv | GG\25\008\D | GG | 25 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-05-14 18:17 | 2027-05-16 20:46 | 61570.6747 | [6 empty] | 61571 | 46102 | 4.61 | 0 | 0 | 6.57 | 5809
TS6060#1 | W2\06\008\D | W2 | 6 | 8 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2027-05-14 20:32 | 2027-05-17 01:26 | 54577.6753 |  |  | 54578 | [5 empty] | 0 | 0 | 0 | 5.93 | 5746
TS5500Exc | SC\44\013\D | SC | 44 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-05-15 01:22 | 2027-05-17 05:45 | 65988.118 | [6 empty] | 65988 | 49232 | 4.1 | 0 | 0 | 7.44 | 5756
DRE1 | SC\45\013\D | SC | 45 | 13 | D | 6 DL | 100 | 0 | 100 | 2027-05-16 10:20 | 2027-05-24 00:40 | 569013.3956 |  |  |  | 43271 | 569013 | 389439 |  |  | 0 | 40 | 0 | 7.43 | 5756.37
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 08:33 |  | 3d 08:33 | 2027-05-16 20:46 | 2027-05-20 05:20
TS Fleet 5 | GG\29\011\B | GG | 29 | 11 | B | 1 Prestrip - Thick | 30.9248 | 30.9248 | 30.9248 | 2027-05-17 00:08 | 2027-05-17 13:39 | 26504.1756 | 26504 | [7 empty] | 0 | 0 | 2.65 | 11.58 | 5401.12
TS6060#1 | GG\29\011\B | GG | 29 | 11 | B | 1 Prestrip - Thick | 46.6497 | 20.6079 | 20.6079 | 2027-05-17 01:26 | 2027-05-17 18:33 | 17662.0663 | 17662 | [7 empty] | 0 | 0 | 1.77 | 11.58 | 5401.12
TS5500Exc | W2\06\008\D | W2 | 6 | 8 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2027-05-17 05:45 | 2027-05-19 10:39 | 46780.8646 |  |  | 46781 | [5 empty] | 0 | 0 | 0 | 5.93 | 5746
TS Fleet 5 | W1\08\002\B | W1 | 8 | 2 | B | 1 Prestrip - Thick | 19.7903 | 19.7903 | 19.7903 | 2027-05-17 13:39 | 2027-05-20 07:47 | 129628.8268 | 129629 | [7 empty] | 0 | 0 | 6.45 | 10.87 | 5178.48
TS6060#1 | GG\25\012\D | GG | 25 | 12 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-05-17 18:33 | 2027-05-18 18:54 | 32952.0989 | [6 empty] | 32952 | 24635 | 2.46 | 0 | 0 | 6.74 | 5795
TS6060#1 | GG\29\013\X1 | GG | 29 | 13 | X1 | 1 Prestrip - Thick | 7.3202 | 7.3202 | 7.3202 | 2027-05-18 18:54 | 2027-05-20 04:41 | 33889.2006 | 33889 | [7 empty] | 0 | 0 | 3.72 | 15.14 | 5087.53
TS5500Exc | W2\06\008\D | W2 | 6 | 8 | D | 8 Coal Mining | 100 | 0 | 56.9 | 2027-05-19 10:39 | 2027-05-21 23:54 | 77156.2685 | [6 empty] | 77156 | 55829 | 2.79 | 0 | 0 | 5.93 | 5746
TS6060#1 | W2\06\008\D | W2 | 6 | 8 | D | 8 Coal Mining | 100 | 0 | 43.1 | 2027-05-20 04:41 | 2027-05-21 23:54 | 58498.235 | [6 empty] | 58498 | 42329 | 2.12 | 0 | 0 | 5.93 | 5746
DRE2 | GG\25\006\D | GG | 25 | 6 | D | 6 DL | 100 | 100 | 100 | 2027-05-20 05:20 | 2027-05-25 16:36 | 429779.3885 |  |  |  | 10007 | 429779 | 190124 |  |  | 0 | 20.01 | 0 | 6.6 | 5805.86
TS5500Shv | GG\25\007\D | GG | 25 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-05-20 05:20 | 2027-05-22 07:30 | 61174.6934 | [6 empty] | 61175 | 45806 | 4.58 | 0 | 0 | 6.58 | 5808
TS Fleet 5 | W1\08\002\B | W1 | 8 | 2 | B | 1 Prestrip - Thick | 80.2097 | 80.2097 | 80.2097 | 2027-05-20 07:47 | 2027-05-31 11:50 | 525382.8424 | 525383 | [7 empty] | 0 | 0 | 26.16 | 10.87 | 5178.48
TS6060#1 | GG\25\011\D | GG | 25 | 11 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-05-21 23:54 | 2027-05-23 00:12 | 32868.2611 | [6 empty] | 32868 | 24611 | 2.46 | 0 | 0 | 6.58 | 5809
TS5500Exc | SC\44\012\D | SC | 44 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-05-21 23:54 | 2027-05-24 04:27 | 66184.1296 | [6 empty] | 66184 | 49339 | 4.12 | 0 | 0 | 7.43 | 5756
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 09:06 |  | 3d 09:06 | 2027-05-22 07:30 | 2027-05-25 16:36
TS6060#1 | GG\29\017\B | GG | 29 | 17 | B | 1 Prestrip - Thick | 1.5937 | 1.5937 | 1.5937 | 2027-05-23 00:12 | 2027-05-23 07:07 | 7064.2691 | 7064 | [7 empty] | 0 | 0 | 0.71 | 14.75 | 5107.03
TS6060#1 | GG\29\018\B | GG | 29 | 18 | B | 1 Prestrip - Thick | 14.444 | 14.444 | 14.444 | 2027-05-23 07:07 | 2027-05-25 08:48 | 50889.8008 | 50890 | [7 empty] | 0 | 0 | 5.21 | 16.33 | 5007.3
DRE1 | SC\45\012\D | SC | 45 | 12 | D | 6 DL | 100 | 0 | 100 | 2027-05-24 00:40 | 2027-05-31 15:01 | 569017.0161 |  |  |  | 43271 | 569017 | 389441 |  |  | 0 | 40 | 0 | 7.28 | 5754.71
TS5500Exc | GG\29\010\B | GG | 29 | 10 | B | 1 Prestrip - Thick | 22.2117 | 0.35366 | 0.35366 | 2027-05-24 04:27 | 2027-05-24 04:47 | 288.0528 | 288 | [7 empty] | 0 | 0 | 0.03 | 10.99 | 5451.69
TS5500Exc | GG\29\012\X2 | GG | 29 | 12 | X2 | 1 Prestrip - Thick | 17.3376 | 0 | 17.3376 | 2027-05-24 04:47 | 2027-05-29 14:56 | 115197.62 | 115198 | [7 empty] | 0 | 0 | 11.07 | 0 | 0
TS6060#1 | GG\25\010\D | GG | 25 | 10 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-05-25 08:48 | 2027-05-26 07:59 | 31371.8893 | [6 empty] | 31372 | 23509 | 2.35 | 0 | 0 | 6.56 | 5809
DRE2 | GG\25\005\D | GG | 25 | 5 | D | 6 DL | 100 | 100 | 100 | 2027-05-25 16:36 | 2027-05-31 02:39 | 425813.7752 |  |  |  | 7929 | 425814 | 190308 |  |  | 0 | 19.82 | 0 | 6.6 | 5805.15
TS5500Shv | GG\25\006\D | GG | 25 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-05-25 16:36 | 2027-05-27 18:23 | 60707.6149 | [6 empty] | 60708 | 45492 | 4.55 | 0 | 0 | 6.6 | 5806
TS6060#1 | GG\29\019\B | GG | 29 | 19 | B | 1 Prestrip - Thick | 9.0366 | 9.0366 | 9.0366 | 2027-05-26 07:59 | 2027-05-27 12:29 | 29035.4045 | 29035 | [7 empty] | 0 | 0 | 3.43 | 18.44 | 4858.73
TS6060#1 | GG\29\020\B | GG | 29 | 20 | B | 1 Prestrip - Thick | 15.8794 | 15.8794 | 15.8794 | 2027-05-27 12:29 | 2027-05-29 20:16 | 56261.2704 | 56261 | [7 empty] | 0 | 0 | 8.09 | 0 | 0
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 08:16 |  | 3d 08:16 | 2027-05-27 18:23 | 2027-05-31 02:39
TS5500Exc | GG\29\013\X1 | GG | 29 | 13 | X1 | 1 Prestrip - Thick | 14.8215 | 14.8215 | 14.8215 | 2027-05-29 14:56 | 2027-06-01 20:24 | 68617.3177 | 68617 | [7 empty] | 0 | 0 | 7.54 | 15.14 | 5087.53
TS6060#1 | GG\25\009\D | GG | 25 | 9 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-05-29 20:16 | 2027-05-30 20:11 | 32357.092 | [6 empty] | 32357 | 24228 | 2.42 | 0 | 0 | 6.58 | 5808
TS6060#1 | W1\04\005\D | W1 | 4 | 5 | D | 7 PostStrip | 71.5513 | 0 | 71.5513 | 2027-05-30 20:11 | 2027-06-02 19:20 | 73417.6265 |  |  | 73418 | [5 empty] | 0 | 0 | 0 | 7.71 | 5591.44
DRE2 | GG\25\004\D | GG | 25 | 4 | D | 6 DL | 100 | 100 | 100 | 2027-05-31 02:39 | 2027-06-03 00:51 | 229809.2024 |  |  |  | 3738 | 229809 | 66067 |  |  | 0 | 19.76 | 0 | 6.59 | 5806.43
TS5500Shv | GG\25\005\D | GG | 25 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-05-31 02:39 | 2027-06-02 04:07 | 60313.4166 | [6 empty] | 60313 | 45233 | 4.52 | 0 | 0 | 6.6 | 5805
TS Fleet 5 | W1\08\003\B | W1 | 8 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-05-31 11:50 | 2027-06-20 11:22 | 939876.202 | 939876 | [7 empty] | 0 | 0 | 46.51 | 12.71 | 5023.68
DRE1 | SC\45\011\D | SC | 45 | 11 | D | 6 DL | 100 | 0 | 100 | 2027-05-31 15:01 | 2027-06-13 17:02 | 979870.201 |  |  |  | 54484 | 979870 | 425890 |  |  | 0 | 40 | 0 | 7.3 | 5750.53
TS5500Exc | SC\44\011\D | SC | 44 | 11 | D | 7 PostStrip | 100 | 0 | 100 | 2027-06-01 20:24 | 2027-06-05 04:17 | 70652.3479 |  |  | 70652 | [5 empty] | 0 | 0 | 0 | 7.49 | 5751.89
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 20:44 |  | 0d 20:44 | 2027-06-02 04:07 | 2027-06-03 00:51
TS6060#1 | W1\05\002\D | W1 | 5 | 2 | D | 7 PostStrip | 72.9237 | 0 | 72.9237 | 2027-06-02 19:20 | 2027-06-07 00:03 | 103923.731 |  |  | 103924 | [5 empty] | 0 | 0 | 0 | 7.45 | 5610.43
DRE2 | GG\26\013\B | GG | 26 | 13 | B | 6 DL | 100 | 0 | 100 | 2027-06-03 00:51 | 2027-06-05 14:20 | 201324.371 |  |  |  |  | 201324 | 167770 |  |  | 0 | 16.83 | 0 | 12.06 | 5323.44
TS5500Shv | GG\25\004\D | GG | 25 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2027-06-03 00:51 | 2027-06-03 22:54 | 23640.512 |  |  | 23641 | [5 empty] | 0 | 0 | 0 | 6.59 | 5806.43
PH4100XPC#1 | GG\29\008\X1 | GG | 29 | 8 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2027-06-03 11:52 | 2027-06-03 11:52 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\29\008\B | GG | 29 | 8 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2027-06-03 11:52 | 2027-06-03 11:52 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\29\009\X1 | GG | 29 | 9 | X1 | 1 Prestrip - Thick | 100 | 28.836 | 28.836 | 2027-06-03 11:52 | 2027-06-07 19:15 | 233707.6889 | 233708 | [7 empty] | 0 | 0 | 23.72 | 14.01 | 5161.05
PH4100A | W2\01\004\B | W2 | 1 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-06-03 11:52 | 2027-06-12 12:16 | 375664.6838 | 375665 | [7 empty] | 0 | 0 | 4.22 | 10.02 | 5300.66
TS5500Shv | GG\25\004\D | GG | 25 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-06-03 22:54 | 2027-06-04 21:46 | 27887.8337 | [6 empty] | 27888 | 20915 | 4.5 | 0 | 0 | 6.59 | 5806
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 16:34 |  | 0d 16:34 | 2027-06-04 21:46 | 2027-06-05 14:20
TS5500Exc | SC\44\011\D | SC | 44 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-06-05 04:17 | 2027-06-07 10:17 | 68025.2155 | [6 empty] | 68025 | 50794 | 4.24 | 0 | 0 | 7.49 | 5752
DRE2 | GG\26\014\B | GG | 26 | 14 | B | 6 DL | 100 | 0 | 100 | 2027-06-05 14:20 | 2027-06-07 16:18 | 163588.384 |  |  |  |  | 163588 | 136324 |  |  | 0 | 16.34 | 0 | 12.37 | 5284.32
TS5500Shv | GG\26\013\B | GG | 26 | 13 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-06-05 14:20 | 2027-06-07 06:12 | 48613.7914 | [6 empty] | 48614 | 35276 | 3.53 | 0 | 0 | 12.06 | 5323
TS6060#1 | W1\05\004\D | W1 | 5 | 4 | D | 7 PostStrip | 40.7964 | 0 | 40.7964 | 2027-06-07 00:03 | 2027-06-08 15:38 | 40843.7105 |  |  | 40844 | [5 empty] | 0 | 0 | 0 | 7.82 | 5574.67
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 10:06 |  | 0d 10:06 | 2027-06-07 06:12 | 2027-06-07 16:18
TS5500Exc | GG\29\017\B | GG | 29 | 17 | B | 1 Prestrip - Thick | 1.3829 | 1.3829 | 1.3829 | 2027-06-07 10:17 | 2027-06-07 17:12 | 6129.9706 | 6130 | [7 empty] | 0 | 0 | 0.62 | 14.75 | 5107.03
DRE2 | GG\26\017\B | GG | 26 | 17 | B | 6 DL | 100 | 0 | 100 | 2027-06-07 16:18 | 2027-06-09 17:32 | 161156.0666 |  |  |  |  | 161156 | 134297 |  |  | 0 | 15.96 | 0 | 14.03 | 5163.32
TS5500Shv | GG\26\014\B | GG | 26 | 14 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-06-07 16:18 | 2027-06-08 23:51 | 38458.4324 | [6 empty] | 38458 | 27874 | 3.5 | 0 | 0 | 12.37 | 5284
TS5500Exc | GG\29\018\B | GG | 29 | 18 | B | 1 Prestrip - Thick | 12.4847 | 12.4847 | 12.4847 | 2027-06-07 17:12 | 2027-06-09 18:54 | 43986.815 | 43987 | [7 empty] | 0 | 0 | 4.5 | 16.33 | 5007.3
PH4100XPC#1 | GG\29\012\X2 | GG | 29 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 45.7655 | 2027-06-07 19:15 | 2027-06-13 05:24 | 304082.6903 | 304083 | [7 empty] | 0 | 0 | 29.22 | 0 | 0
TS6060#1 | GG\29\009\X1 | GG | 29 | 9 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-06-08 15:38 | 2027-06-08 22:46 | 9638.1808 | [6 empty] | 9638 | 6937 | 0.69 | 0 | 0 | 14.01 | 5161
TS6060#1 | W1\05\005\D | W1 | 5 | 5 | D | 7 PostStrip | 47.3375 | 0 | 47.3375 | 2027-06-08 22:46 | 2027-06-11 16:38 | 67964.3455 |  |  | 67964 | [5 empty] | 0 | 0 | 0 | 7.76 | 5582
TS5500Shv | GG\29\009\X1 | GG | 29 | 9 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-06-08 23:51 | 2027-06-09 06:58 | 8683.9054 | [6 empty] | 8684 | 6250 | 0.62 | 0 | 0 | 14.01 | 5161
TS5500Shv | GG\29\009\X2 | GG | 29 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2027-06-09 06:58 | 2027-06-11 22:26 | 68042.07 | 68042 | [7 empty] | 0 | 0 | 6.77 | 0 | 0
DRE2 | GG\26\018\B | GG | 26 | 18 | B | 6 DL | 100 | 0 | 100 | 2027-06-09 17:32 | 2027-06-12 05:43 | 197096.0063 |  |  |  |  | 197096 | 164247 |  |  | 0 | 16.37 | 0 | 14.19 | 5171.15
TS5500Exc | GG\29\019\B | GG | 29 | 19 | B | 1 Prestrip - Thick | 14.2331 | 14.2331 | 14.2331 | 2027-06-09 18:54 | 2027-06-11 22:35 | 45732.4924 | 45732 | [7 empty] | 0 | 0 | 5.41 | 18.44 | 4858.73
TS6060#1 | W1\06\002\B | W1 | 6 | 2 | B | 8 Coal Mining | 23.1 | 0 | 23.1 | 2027-06-11 16:38 | 2027-06-12 08:05 | 20905.7235 | [6 empty] | 20906 | 14684 | 0.48 | 0 | 0 | 11.06 | 5154
TS5500Shv | GG\29\009\B | GG | 29 | 9 | B | 1 Prestrip - Thick | 100 | 60.4322 | 60.4322 | 2027-06-11 22:26 | 2027-06-13 19:20 | 48125.7218 | 48126 | [7 empty] | 0 | 0 | 4.79 | 10.58 | 5478.98
TS5500Exc | SC\45\016\D | SC | 45 | 16 | D | 7 PostStrip | 100 | 0 | 100 | 2027-06-11 22:35 | 2027-06-15 02:02 | 66738.7625 |  |  | 66739 | [5 empty] | 0 | 0 | 0 | 7.4 | 5759.01
DRE2 | GG\26\019\B | GG | 26 | 19 | B | 6 DL | 100 | 0 | 100 | 2027-06-12 05:43 | 2027-06-14 19:21 | 201764.0493 |  |  |  |  | 201764 | 168137 |  |  | 0 | 16.82 | 0 | 15.49 | 5089.86
TS6060#1 | W1\06\003\B | W1 | 6 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-06-12 08:05 | 2027-06-14 12:31 | 70961.1793 | [6 empty] | 70961 | 49599 | 2.46 | 0 | 0 | 11.3 | 5116
PH4100A | W2\02\003\B | W2 | 2 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-06-12 12:16 | 2027-07-19 07:03 | 1615939.69 | 1615940 | [7 empty] | 0 | 0 | 120.1 | 11.35 | 5191.89
PH4100XPC#1 | GG\29\009\B | GG | 29 | 9 | B | 1 Prestrip - Thick | 100 | 39.5678 | 39.5678 | 2027-06-13 05:24 | 2027-06-13 19:20 | 31510.1666 | 31510 | [7 empty] | 0 | 0 | 3.14 | 10.58 | 5478.98
DRE1 | SC\46\018\D | SC | 46 | 18 | D | 6 DL | 100 | 0 | 100 | 2027-06-13 17:02 | 2027-07-02 12:50 | 1409881.274 |  |  |  | 76539 | 1409881 | 610608 |  |  | 0 | 40 | 0 | 7.07 | 5789.77
PH4100XPC#1 | GG\29\012\A | GG | 29 | 12 | A | 1 Prestrip - Thick | 100 | 0 | 70.9306 | 2027-06-13 19:20 | 2027-06-15 01:42 | 68752.9195 | 68753 | [7 empty] | 0 | 0 | 6.89 | 0 | 0
TS5500Shv | GG\29\012\A | GG | 29 | 12 | A | 1 Prestrip - Thick | 15.0239 | 0 | 15.0239 | 2027-06-13 19:20 | 2027-06-14 08:55 | 14562.684 | 14563 | [7 empty] | 0 | 0 | 1.46 | 0 | 0
TS5500Shv | GG\26\017\B | GG | 26 | 17 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-06-14 08:55 | 2027-06-15 16:02 | 37940.7294 | [6 empty] | 37941 | 27249 | 3.35 | 0 | 0 | 14.03 | 5163
TS6060#1 | GG\29\012\A | GG | 29 | 12 | A | 1 Prestrip - Thick | 100 | 0 | 14.0455 | 2027-06-14 12:31 | 2027-06-15 01:42 | 13614.2955 | 13614 | [7 empty] | 0 | 0 | 1.37 | 0 | 0
DRE2 | GG\26\020\B | GG | 26 | 20 | B | 6 DL | 100 | 0 | 100 | 2027-06-14 19:21 | 2027-06-17 05:20 | 189823.5141 |  |  |  |  | 189824 | 146018 |  |  | 0 | 18.23 | 0 | 19.71 | 4767.72
TS6060#1 | W2\01\004\B | W2 | 1 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-06-15 01:42 | 2027-06-24 05:35 | 297587.0617 | [6 empty] | 297587 | 209351 | 2.54 | 0 | 0 | 10.02 | 5301
PH4100XPC#1 | GG\29\012\B | GG | 29 | 12 | B | 1 Prestrip - Thick | 100 | 82.4247 | 82.4247 | 2027-06-15 01:42 | 2027-06-15 18:13 | 37385.3014 | 37385 | [7 empty] | 0 | 0 | 3.74 | 11.97 | 5355.14
TS5500Exc | GG\29\012\B | GG | 29 | 12 | B | 1 Prestrip - Thick | 12.3947 | 12.3947 | 12.3947 | 2027-06-15 02:02 | 2027-06-15 08:24 | 5621.8751 | 5622 | [7 empty] | 0 | 0 | 0.56 | 11.97 | 5355.14
TS5500Exc | SC\45\016\D | SC | 45 | 16 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-06-15 08:24 | 2027-06-17 18:59 | 73799.45 | [6 empty] | 73799 | 55193 | 4.14 | 0 | 0 | 7.4 | 5759
TS5500Shv | GG\29\012\B | GG | 29 | 12 | B | 1 Prestrip - Thick | 15.0239 | 5.1806 | 5.1806 | 2027-06-15 16:02 | 2027-06-15 18:13 | 2349.746 | 2350 | [7 empty] | 0 | 0 | 0.23 | 11.97 | 5355.14
TS5500Shv | GG\29\012\B | GG | 29 | 12 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-06-15 18:13 | 2027-06-16 13:33 | 23575.5423 | [6 empty] | 23576 | 17065 | 1.71 | 0 | 0 | 11.97 | 5355
PH4100XPC#1 | GG\29\013\X1 | GG | 29 | 13 | X1 | 1 Prestrip - Thick | 100 | 35.2999 | 35.2999 | 2027-06-15 18:13 | 2027-06-18 17:05 | 163423.6271 | 163424 | [7 empty] | 0 | 0 | 17.96 | 15.14 | 5087.53
TS5500Shv | GG\26\018\B | GG | 26 | 18 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-06-16 13:33 | 2027-06-18 04:13 | 47149.9029 | [6 empty] | 47150 | 33798 | 3.38 | 0 | 0 | 14.19 | 5171
DRE2 | GG\25\013\D | GG | 25 | 13 | D | 6 DL | 100 | 100 | 100 | 2027-06-17 05:20 | 2027-06-23 13:33 | 498370.2162 |  |  |  | 11603 | 498370 | 220466 |  |  | 0 | 23.21 | 0 | 6.91 | 5779.15
TS5500Exc | W1\03\004\D | W1 | 3 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2027-06-17 18:59 | 2027-06-22 12:23 | 100284.7812 |  |  | 100285 | [5 empty] | 0 | 0 | 0 | 7.65 | 5601.99
TS5500Shv | GG\26\019\B | GG | 26 | 19 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-06-18 04:13 | 2027-06-19 15:41 | 43236.5454 | [6 empty] | 43237 | 30748 | 3.07 | 0 | 0 | 15.49 | 5090
PH4100XPC#1 | GG\29\014\X1 | GG | 29 | 14 | X1 | 1 Prestrip - Thick | 100 | 53.7882 | 53.7882 | 2027-06-18 17:05 | 2027-06-23 01:49 | 229628.4735 | 229628 | [7 empty] | 0 | 0 | 18.94 | 14.8 | 5112.73
TS5500Shv | GG\29\013\X1 | GG | 29 | 13 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-06-19 15:41 | 2027-06-19 20:21 | 5692.2145 | [6 empty] | 5692 | 4073 | 0.41 | 0 | 0 | 15.14 | 5088
TS5500Shv | GG\26\020\B | GG | 26 | 20 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-06-19 20:21 | 2027-06-21 03:50 | 38388.1365 | [6 empty] | 38388 | 26673 | 3.13 | 0 | 0 | 19.71 | 4768
TS Fleet 5 | W1\06\003\D | W1 | 6 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-06-20 11:22 | 2027-06-28 09:02 | 371729.2423 | 371729 | [7 empty] | 0 | 0 | 23.41 | 7.93 | 5561.82
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 21:59 |  | 1d 21:59 | 2027-06-21 03:50 | 2027-06-23 01:49
TS5500Exc | SC\45\015\D | SC | 45 | 15 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-06-22 12:23 | 2027-06-24 13:22 | 61709.2827 | [6 empty] | 61709 | 46150 | 4.04 | 0 | 0 | 7.43 | 5756
PH4100XPC#1 | GG\29\017\B | GG | 29 | 17 | B | 1 Prestrip - Thick | 100 | 50.7487 | 50.7487 | 2027-06-23 01:49 | 2027-06-27 07:38 | 224950.8383 | 224951 | [7 empty] | 0 | 0 | 22.74 | 14.75 | 5107.03
TS5500Shv | GG\29\014\X1 | GG | 29 | 14 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-06-23 01:49 | 2027-06-23 07:40 | 7132.022 | [6 empty] | 7132 | 5115 | 0.43 | 0 | 0 | 14.8 | 5113
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 05:53 |  | 0d 05:53 | 2027-06-23 07:40 | 2027-06-23 13:33
DRE2 | GG\25\014\D | GG | 25 | 14 | D | 6 DL | 100 | 100 | 100 | 2027-06-23 13:33 | 2027-06-27 22:40 | 344158.4451 |  |  |  | 8013 | 344158 | 152247 |  |  | 0 | 23.68 | 0 | 7.01 | 5770.28
TS5500Shv | GG\25\013\D | GG | 25 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-06-23 13:33 | 2027-06-25 16:10 | 61725.248 | [6 empty] | 61725 | 46035 | 4.6 | 0 | 0 | 6.91 | 5779
TS6060#1 | GG\29\012\B | GG | 29 | 12 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-06-24 05:35 | 2027-06-25 00:55 | 26166.2613 | [6 empty] | 26166 | 18940 | 1.9 | 0 | 0 | 11.97 | 5355
TS5500Exc | W1\03\004\D | W1 | 3 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-06-24 13:22 | 2027-06-29 16:41 | 155333.7158 | [6 empty] | 155334 | 111922 | 5.6 | 0 | 0 | 7.65 | 5602
TS6060#1 | GG\29\013\X1 | GG | 29 | 13 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-06-25 00:55 | 2027-06-25 05:35 | 6317.7326 | [6 empty] | 6318 | 4521 | 0.45 | 0 | 0 | 15.14 | 5088
TS6060#1 | GG\29\013\X2 | GG | 29 | 13 | X2 | 1 Prestrip - Thick | 49.0446 | 0 | 49.0446 | 2027-06-25 05:35 | 2027-06-26 16:27 | 35968.3916 | 35968 | [7 empty] | 0 | 0 | 3.63 | 0 | 0
TS5500Shv | GG\29\013\X2 | GG | 29 | 13 | X2 | 1 Prestrip - Thick | 50.9554 | 0 | 50.9554 | 2027-06-25 16:10 | 2027-06-27 03:02 | 37369.7574 | 37370 | [7 empty] | 0 | 0 | 3.77 | 0 | 0
TS6060#1 | GG\29\014\X1 | GG | 29 | 14 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-06-26 16:27 | 2027-06-26 22:18 | 7915.7607 | [6 empty] | 7916 | 5678 | 0.48 | 0 | 0 | 14.8 | 5113
TS6060#1 | GG\29\014\X2 | GG | 29 | 14 | X2 | 1 Prestrip - Thick | 38.2051 | 0 | 38.2051 | 2027-06-26 22:18 | 2027-06-28 08:27 | 35244.6696 | 35245 | [7 empty] | 0 | 0 | 3 | 0 | 0
TS5500Shv | GG\29\013\B | GG | 29 | 13 | B | 1 Prestrip - Thick | 50.9554 | 32.0393 | 32.0393 | 2027-06-27 03:02 | 2027-06-28 12:26 | 35808.8836 | 35809 | [7 empty] | 0 | 0 | 3.59 | 12.12 | 5318.79
PH4100XPC#1 | GG\29\013\B | GG | 29 | 13 | B | 1 Prestrip - Thick | 100 | 58.3228 | 58.3228 | 2027-06-27 07:38 | 2027-06-28 12:26 | 65184.8471 | 65185 | [7 empty] | 0 | 0 | 6.53 | 12.12 | 5318.79
DRE2 | GG\25\017\D | GG | 25 | 17 | D | 6 DL | 100 | 100 | 100 | 2027-06-27 22:40 | 2027-07-02 11:56 | 357771.9367 |  |  |  | 8330 | 357772 | 158269 |  |  | 0 | 23.97 | 0 | 7.05 | 5767.92
TS6060#1 | GG\29\013\B | GG | 29 | 13 | B | 1 Prestrip - Thick | 49.0446 | 3.6709 | 3.6709 | 2027-06-28 08:27 | 2027-06-28 12:26 | 4102.8166 | 4103 | [7 empty] | 0 | 0 | 0.41 | 12.12 | 5318.79
TS Fleet 5 | GG\29\013\B | GG | 29 | 13 | B | 1 Prestrip - Thick | 36.37 | 5.967 | 5.967 | 2027-06-28 09:02 | 2027-06-28 12:26 | 6669.02 | 6669 | [7 empty] | 0 | 0 | 0.67 | 12.12 | 5318.79
TS Fleet 5 | GG\29\014\X2 | GG | 29 | 14 | X2 | 1 Prestrip - Thick | 15.1511 | 0 | 15.1511 | 2027-06-28 12:26 | 2027-06-28 19:34 | 13977.0777 | 13977 | [7 empty] | 0 | 0 | 1.19 | 0 | 0
PH4100XPC#1 | GG\29\014\X2 | GG | 29 | 14 | X2 | 1 Prestrip - Thick | 100 | 0 | 31.653 | 2027-06-28 12:26 | 2027-06-29 01:20 | 29200.2235 | 29200 | [7 empty] | 0 | 0 | 2.49 | 0 | 0
TS6060#1 | CP\03\004\B | CP | 3 | 4 | B | 1 Prestrip - Thick | 20.7767 | 20.7767 | 20.7767 | 2027-06-28 12:26 | 2027-07-19 17:48 | 521674.4381 | 521674 | [7 empty] | 0 | 0 | 9.62 | 8.84 | 5585.19
TS5500Shv | GG\29\014\X2 | GG | 29 | 14 | X2 | 1 Prestrip - Thick | 39.6936 | 0 | 14.9908 | 2027-06-28 12:26 | 2027-06-29 01:20 | 13829.1862 | 13829 | [7 empty] | 0 | 0 | 1.18 | 0 | 0
TS Fleet 5 | W1\09\002\B | W1 | 9 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-06-28 19:34 | 2027-07-12 13:11 | 646061.5528 | 646062 | [7 empty] | 0 | 0 | 36.33 | 11.01 | 5174.71
PH4100XPC#1 | GG\29\014\B | GG | 29 | 14 | B | 1 Prestrip - Thick | 100 | 59.1612 | 59.1612 | 2027-06-29 01:20 | 2027-06-30 11:49 | 78066.3561 | 78066 | [7 empty] | 0 | 0 | 6.97 | 12.26 | 5291.84
TS5500Shv | GG\29\014\B | GG | 29 | 14 | B | 1 Prestrip - Thick | 35.8744 | 28.0187 | 28.0187 | 2027-06-29 01:20 | 2027-06-30 11:49 | 36972.1203 | 36972 | [7 empty] | 0 | 0 | 3.3 | 12.26 | 5291.84
TS5500Exc | GG\29\014\B | GG | 29 | 14 | B | 1 Prestrip - Thick | 29.5964 | 12.8201 | 12.8201 | 2027-06-29 16:41 | 2027-06-30 11:49 | 16916.867 | 16917 | [7 empty] | 0 | 0 | 1.51 | 12.26 | 5291.84
PH4100XPC#1 | GG\29\018\B | GG | 29 | 18 | B | 1 Prestrip - Thick | 100 | 24.9002 | 24.9002 | 2027-06-30 11:49 | 2027-07-02 03:05 | 87729.7231 | 87730 | [7 empty] | 0 | 0 | 8.97 | 16.33 | 5007.3
TS5500Exc | SC\45\014\D | SC | 45 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-06-30 11:49 | 2027-07-02 13:20 | 62377.9466 | [6 empty] | 62378 | 46613 | 4.06 | 0 | 0 | 7.45 | 5755
TS5500Shv | GG\25\014\D | GG | 25 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-06-30 11:49 | 2027-07-01 21:24 | 40944.9319 | [6 empty] | 40945 | 30488 | 4.55 | 0 | 0 | 7.01 | 5770
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 14:33 |  | 0d 14:33 | 2027-07-01 21:24 | 2027-07-02 11:56
PH4100XPC#1 | GG\29\019\B | GG | 29 | 19 | B | 1 Prestrip - Thick | 100 | 32.8747 | 32.8747 | 2027-07-02 03:05 | 2027-07-04 01:04 | 105629.561 | 105630 | [7 empty] | 0 | 0 | 12.49 | 18.44 | 4858.73
DRE2 | GG\25\018\D | GG | 25 | 18 | D | 6 DL | 100 | 100 | 100 | 2027-07-02 11:56 | 2027-07-08 22:28 | 505938.7879 |  |  |  | 11780 | 505939 | 223815 |  |  | 0 | 23.55 | 0 | 7.04 | 5768.63
TS5500Shv | GG\25\017\D | GG | 25 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-07-02 11:56 | 2027-07-03 23:35 | 43461.0099 | [6 empty] | 43461 | 32363 | 4.7 | 0 | 0 | 7.05 | 5768
DRE1 | SC\46\019\D | SC | 46 | 19 | D | 6 DL | 100 | 0 | 100 | 2027-07-02 12:50 | 2027-07-10 23:32 | 632493.2819 |  |  |  | 48098 | 632493 | 432885 |  |  | 0 | 40 | 0 | 6.93 | 5803.02
TS5500Exc | W1\03\005\D | W1 | 3 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2027-07-02 13:20 | 2027-07-07 04:31 | 98322.9391 |  |  | 98323 | [5 empty] | 0 | 0 | 0 | 7.64 | 5598.75
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 22:53 |  | 4d 22:53 | 2027-07-03 23:35 | 2027-07-08 22:28
PH4100XPC#1 | GG\29\020\B | GG | 29 | 20 | B | 1 Prestrip - Thick | 100 | 37.5193 | 37.5193 | 2027-07-04 01:04 | 2027-07-06 08:52 | 132932.5326 | 132933 | [7 empty] | 0 | 0 | 19.11 | 0 | 0
PH4100XPC#1 | W2\01\005\D | W2 | 1 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-07-06 08:52 | 2027-07-21 03:53 | 803606.2175 | 803606 | [7 empty] | 0 | 0 | 19.65 | 5.72 | 5756.18
TS5500Exc | SC\45\013\D | SC | 45 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-07-07 04:31 | 2027-07-09 06:03 | 62391.701 | [6 empty] | 62392 | 46549 | 4.12 | 0 | 0 | 7.43 | 5756
DRE2 | GG\25\019\D | GG | 25 | 19 | D | 6 DL | 100 | 100 | 100 | 2027-07-08 22:28 | 2027-07-15 05:41 | 495097.9294 |  |  |  | 11527 | 495098 | 219019 |  |  | 0 | 23.05 | 0 | 6.96 | 5775.63
TS5500Shv | GG\25\018\D | GG | 25 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-07-08 22:28 | 2027-07-11 02:04 | 62914.4586 | [6 empty] | 62914 | 46848 | 4.68 | 0 | 0 | 7.04 | 5769
TS5500Exc | W1\03\005\D | W1 | 3 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-07-09 06:03 | 2027-07-13 20:02 | 138532.7302 | [6 empty] | 138533 | 99795 | 5.14 | 0 | 0 | 7.64 | 5599
DRE1 | SC\46\020\D | SC | 46 | 20 | D | 6 DL | 100 | 0 | 100 | 2027-07-10 23:32 | 2027-07-19 08:48 | 628092.7189 |  |  |  | 47764 | 628093 | 429873 |  |  | 0 | 40 | 0 | 6.99 | 5797.1
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 03:37 |  | 4d 03:37 | 2027-07-11 02:04 | 2027-07-15 05:41
TS Fleet 5 | W1\09\003\D | W1 | 9 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-07-12 13:11 | 2027-08-04 22:48 | 1100779.262 | 1100779 | [7 empty] | 0 | 0 | 68.05 | 8.32 | 5529.02
TS5500Exc | SC\45\012\D | SC | 45 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-07-13 20:02 | 2027-07-15 05:00 | 41521.9763 | [6 empty] | 41522 | 30935 | 2.78 | 0 | 0 | 7.28 | 5755
TS5500Exc | W1\04\003\B | W1 | 4 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-07-15 05:00 | 2027-07-17 14:05 | 71918.8094 | [6 empty] | 71919 | 50200 | 2.47 | 0 | 0 | 11.44 | 5098
DRE2 | GG\25\020\D | GG | 25 | 20 | D | 6 DL | 100 | 100 | 100 | 2027-07-15 05:41 | 2027-07-20 06:43 | 396237.3929 |  |  |  | 7379 | 396237 | 177089 |  |  | 0 | 18.35 | 0 | 6.85 | 5782.84
TS5500Shv | GG\25\019\D | GG | 25 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-07-15 05:41 | 2027-07-17 08:50 | 62363.0941 | [6 empty] | 62363 | 46511 | 4.65 | 0 | 0 | 6.96 | 5776
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 21:53 |  | 2d 21:53 | 2027-07-17 08:50 | 2027-07-20 06:43
TS5500Exc | W1\04\002\D | W1 | 4 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2027-07-17 14:05 | 2027-07-21 19:46 | 89920.1941 |  |  | 89920 | [5 empty] | 0 | 0 | 0 | 7.37 | 5621.22
PH4100A | W2\03\003\D | W2 | 3 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-07-19 07:03 | 2027-09-04 00:35 | 2053353.692 | 2053354 | [7 empty] | 0 | 0 | 132.12 | 5.71 | 5763.07
DRE1 | SC\46\021\D | SC | 46 | 21 | D | 6 DL | 100 | 0 | 100 | 2027-07-19 08:48 | 2027-07-27 19:22 | 632094.8653 |  |  |  | 48068 | 632095 | 432612 |  |  | 0 | 40 | 0 | 7.3 | 5768.99
TS6060#1 | CP\03\004\B | CP | 3 | 4 | B | 1 Prestrip - Thick | 79.2233 | 79.2233 | 79.2233 | 2027-07-19 17:48 | 2027-10-08 16:03 | 1989182.855 | 1989183 | [7 empty] | 0 | 0 | 36.68 | 8.84 | 5585.19
DRE2 | GG\25\021\D | GG | 25 | 21 | D | 6 DL | 100 | 0 | 100 | 2027-07-20 06:43 | 2027-07-26 04:06 | 462919.8453 |  |  |  | 35203 | 462920 | 316827 |  |  | 0 | 40 | 0 | 6.64 | 5786.19
TS5500Shv | GG\25\020\D | GG | 25 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-07-20 06:43 | 2027-07-22 07:27 | 59429.293 | [6 empty] | 59429 | 44391 | 4.44 | 0 | 0 | 6.85 | 5783
PH4100XPC#1 | W2\02\005\A1 | W2 | 2 | 5 | A1 | 1 Prestrip - Thick | 100 | 0 | 100 | 2027-07-21 03:53 | 2027-08-06 21:42 | 895273.3162 | 895273 | [7 empty] | 0 | 0 | 44.87 | 0 | 0
TS5500Exc | W2\02\003\B | W2 | 2 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-07-21 19:46 | 2027-07-22 11:41 | 20048.1746 | [6 empty] | 20048 | 14003 | 1.19 | 0 | 0 | 11.35 | 5192
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 20:39 |  | 3d 20:39 | 2027-07-22 07:27 | 2027-07-26 04:06
TS5500Exc | W1\04\002\D | W1 | 4 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-07-22 11:41 | 2027-07-26 10:14 | 119093.4301 | [6 empty] | 119093 | 85857 | 5.05 | 0 | 0 | 7.37 | 5621
DRE2 | GG\25\022\D | GG | 25 | 22 | D | 6 DL | 100 | 0 | 100 | 2027-07-26 04:06 | 2027-07-31 21:48 | 450858.1896 |  |  |  | 25944 | 450858 | 196927 |  |  | 0 | 40 | 0 | 6.73 | 5796.41
TS5500Shv | GG\25\021\D | GG | 25 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-07-26 04:06 | 2027-07-27 18:35 | 46931.3818 | [6 empty] | 46931 | 35106 | 3.48 | 0 | 0 | 6.64 | 5786
TS5500Exc | SC\45\011\D | SC | 45 | 11 | D | 7 PostStrip | 100 | 0 | 100 | 2027-07-26 10:14 | 2027-07-29 11:07 | 64466.7059 |  |  | 64467 | [5 empty] | 0 | 0 | 0 | 7.3 | 5750.53
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 03:13 |  | 4d 03:13 | 2027-07-27 18:35 | 2027-07-31 21:48
DRE1 | SC\46\022\D | SC | 46 | 22 | D | 6 DL | 100 | 0 | 100 | 2027-07-27 19:22 | 2027-08-05 04:46 | 628485.2923 |  |  |  | 47794 | 628485 | 430142 |  |  | 0 | 40 | 0 | 7.4 | 5762.07
TS5500Exc | SC\45\011\D | SC | 45 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-07-29 11:07 | 2027-07-30 17:33 | 38327.9383 | [6 empty] | 38328 | 28599 | 2.62 | 0 | 0 | 7.3 | 5751
TS5500Exc | W1\04\004\B | W1 | 4 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-07-30 17:33 | 2027-08-01 23:03 | 67383.898 | [6 empty] | 67384 | 46723 | 2.3 | 0 | 0 | 12.03 | 5034
DRE2 | GG\27\013\B | GG | 27 | 13 | B | 6 DL | 100 | 0 | 100 | 2027-07-31 21:48 | 2027-08-03 11:09 | 200848.0156 |  |  |  |  | 200848 | 167373 |  |  | 0 | 16.87 | 0 | 12.03 | 5324.05
TS5500Shv | GG\25\022\D | GG | 25 | 22 | D | 7 PostStrip | 100 | 0 | 100 | 2027-07-31 21:48 | 2027-08-02 07:55 | 36569.905 |  |  | 36570 | [5 empty] | 0 | 0 | 0 | 6.73 | 5796.41
TS5500Exc | SC\46\018\D | SC | 46 | 18 | D | 7 PostStrip | 100 | 0 | 100 | 2027-08-01 23:03 | 2027-08-05 15:31 | 78241.1221 |  |  | 78241 | [5 empty] | 0 | 0 | 0 | 7.07 | 5789.77
TS5500Shv | GG\25\022\D | GG | 25 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-08-02 07:55 | 2027-08-04 06:21 | 56610.0359 | [6 empty] | 56610 | 42395 | 4.69 | 0 | 0 | 6.73 | 5796
DRE2 | GG\27\012\B | GG | 27 | 12 | B | 6 DL | 100 | 0 | 100 | 2027-08-03 11:09 | 2027-08-06 03:09 | 209504.8893 |  |  |  |  | 209505 | 174587 |  |  | 0 | 17.52 | 0 | 11.77 | 5369.87
TS5500Shv | GG\27\013\B | GG | 27 | 13 | B | 8 Coal Mining | 55.8 | 0 | 55.8 | 2027-08-04 06:21 | 2027-08-05 04:36 | 27129.023 | [6 empty] | 27129 | 19686 | 1.97 | 0 | 0 | 12.03 | 5324
TS Fleet 5 | GG\30\009\X1 | GG | 30 | 9 | X1 | 1 Prestrip - Thick | 47.2449 | 42.3502 | 42.3502 | 2027-08-04 22:48 | 2027-08-11 21:40 | 327054.9027 | 327055 | [7 empty] | 0 | 0 | 37.31 | 13.98 | 5162.54
TS5500Shv | GG\30\009\X1 | GG | 30 | 9 | X1 | 1 Prestrip - Thick | 31.9397 | 22.2548 | 22.2548 | 2027-08-05 04:36 | 2027-08-11 21:40 | 171865.8159 | 171866 | [7 empty] | 0 | 0 | 19.6 | 13.98 | 5162.54
DRE1 | SC\46\023\D | SC | 46 | 23 | D | 6 DL | 100 | 0 | 100 | 2027-08-05 04:46 | 2027-08-12 09:37 | 539383.2828 |  |  |  | 38360 | 539383 | 387862 |  |  | 0 | 35.68 | 0 | 7.41 | 5762.81
TS5500Exc | SC\46\018\D | SC | 46 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-08-05 15:31 | 2027-08-08 03:51 | 75986.7364 | [6 empty] | 75987 | 56832 | 4.4 | 0 | 0 | 7.07 | 5790
DRE2 | GG\27\011\B | GG | 27 | 11 | B | 6 DL | 100 | 0 | 100 | 2027-08-06 03:09 | 2027-08-09 03:40 | 237429.8131 |  |  |  |  | 237430 | 182638 |  |  | 0 | 18.29 | 0 | 11.47 | 5410.87
PH4100XPC#1 | GG\30\008\X1 | GG | 30 | 8 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2027-08-06 21:42 | 2027-08-06 21:42 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\30\008\B | GG | 30 | 8 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2027-08-06 21:42 | 2027-08-06 21:42 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\30\009\X1 | GG | 30 | 9 | X1 | 1 Prestrip - Thick | 100 | 35.3949 | 35.3949 | 2027-08-06 21:42 | 2027-08-11 21:40 | 273341.7085 | 273342 | [7 empty] | 0 | 0 | 31.18 | 13.98 | 5162.54
TS5500Exc | SC\46\019\D | SC | 46 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-08-08 03:51 | 2027-08-10 12:57 | 71936.0018 | [6 empty] | 71936 | 53846 | 4.49 | 0 | 0 | 6.93 | 5803
DRE2 | GG\27\010\B | GG | 27 | 10 | B | 6 DL | 100 | 0 | 100 | 2027-08-09 03:40 | 2027-08-12 01:30 | 228641.3386 |  |  |  |  | 228641 | 190534 |  |  | 0 | 18.95 | 0 | 10.89 | 5462.18
TS5500Exc | W1\05\003\B | W1 | 5 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-08-10 12:57 | 2027-08-12 23:55 | 74279.1136 | [6 empty] | 74279 | 51895 | 2.55 | 0 | 0 | 11.33 | 5110
TS Fleet 5 | GG\30\010\X1 | GG | 30 | 10 | X1 | 1 Prestrip - Thick | 40.9889 | 40.9889 | 40.9889 | 2027-08-11 21:40 | 2027-08-18 08:35 | 303636.7698 | 303637 | [7 empty] | 0 | 0 | 30.46 | 14.29 | 5149.99
PH4100XPC#1 | GG\30\010\X1 | GG | 30 | 10 | X1 | 1 Prestrip - Thick | 100 | 48.7664 | 48.7664 | 2027-08-11 21:40 | 2027-08-18 14:52 | 361250.6289 | 361251 | [7 empty] | 0 | 0 | 36.24 | 14.29 | 5149.99
TS5500Shv | GG\30\009\X1 | GG | 30 | 9 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-08-11 21:40 | 2027-08-12 04:44 | 8605.4628 | [6 empty] | 8605 | 6194 | 0.62 | 0 | 0 | 13.98 | 5163
DRE2 | GG\27\009\B | GG | 27 | 9 | B | 6 DL | 100 | 0 | 100 | 2027-08-12 01:30 | 2027-08-15 02:27 | 238864.4326 |  |  |  |  | 238864 | 199054 |  |  | 0 | 19.85 | 0 | 10.38 | 5495.39
TS5500Shv | GG\27\010\B | GG | 27 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-08-12 04:44 | 2027-08-13 21:50 | 50127.1507 | [6 empty] | 50127 | 36554 | 3.65 | 0 | 0 | 10.89 | 5462
DRE1 | SC\46\024\D | SC | 46 | 24 | D | 6 DL | 100 | 0 | 100 | 2027-08-12 09:37 | 2027-08-19 16:39 | 546191.178 |  |  |  | 38844 | 546191 | 392757 |  |  | 0 | 36.08 | 0 | 7.55 | 5749.83
TS5500Exc | SC\46\020\D | SC | 46 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-08-12 23:55 | 2027-08-15 07:59 | 70622.0516 | [6 empty] | 70622 | 52904 | 4.41 | 0 | 0 | 6.99 | 5797
TS5500Shv | GG\30\010\X1 | GG | 30 | 10 | X1 | 1 Prestrip - Thick | 10.2447 | 10.2447 | 10.2447 | 2027-08-13 21:50 | 2027-08-16 21:02 | 75890.5359 | 75891 | [7 empty] | 0 | 0 | 7.61 | 14.29 | 5149.99
DRE2 | GG\27\008\B | GG | 27 | 8 | B | 6 DL | 100 | 0 | 100 | 2027-08-15 02:27 | 2027-08-18 10:37 | 262479.7576 |  |  |  |  | 262480 | 201908 |  |  | 0 | 20.19 | 0 | 10.42 | 5480.94
TS5500Exc | SC\46\021\D | SC | 46 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-08-15 07:59 | 2027-08-17 14:01 | 68055.9713 | [6 empty] | 68056 | 50980 | 4.25 | 0 | 0 | 7.3 | 5769
TS5500Shv | GG\27\009\B | GG | 27 | 9 | B | 8 Coal Mining | 37.1 | 0 | 37.1 | 2027-08-16 21:02 | 2027-08-17 12:36 | 18983.0922 | [6 empty] | 18983 | 13871 | 1.39 | 0 | 0 | 10.38 | 5495
TS5500Shv | GG\30\017\X2 | GG | 30 | 17 | X2 | 1 Prestrip - Thick | 20.5469 | 0 | 20.5469 | 2027-08-17 12:36 | 2027-08-19 21:57 | 59852.2003 | 59852 | [7 empty] | 0 | 0 | 6.19 | 0 | 0
TS5500Exc | W1\04\005\D | W1 | 4 | 5 | D | 7 PostStrip | 28.4487 | 0 | 28.4487 | 2027-08-17 14:01 | 2027-08-18 23:02 | 29190.7558 |  |  | 29191 | [5 empty] | 0 | 0 | 0 | 7.71 | 5591.44
TS Fleet 5 | GG\30\011\X1 | GG | 30 | 11 | X1 | 1 Prestrip - Thick | 45.3659 | 45.3659 | 45.3659 | 2027-08-18 08:35 | 2027-08-24 15:51 | 296464.9883 | 296465 | [7 empty] | 0 | 0 | 23.79 | 14.45 | 5142.26
DRE2 | GG\27\007\B | GG | 27 | 7 | B | 6 DL | 100 | 0 | 100 | 2027-08-18 10:37 | 2027-08-21 18:03 | 260048.9786 |  |  |  |  | 260049 | 200038 |  |  | 0 | 20.05 | 0 | 10.62 | 5452.38
PH4100XPC#1 | GG\30\011\X1 | GG | 30 | 11 | X1 | 1 Prestrip - Thick | 100 | 54.6341 | 54.6341 | 2027-08-18 14:52 | 2027-08-25 04:16 | 357032.9217 | 357033 | [7 empty] | 0 | 0 | 28.65 | 14.45 | 5142.26
TS5500Exc | W1\04\005\D | W1 | 4 | 5 | D | 8 Coal Mining | 81.5 | 0 | 81.5 | 2027-08-18 23:02 | 2027-08-22 19:11 | 116072.8248 | [6 empty] | 116073 | 83611 | 4.11 | 0 | 0 | 7.71 | 5591
DRE1 | SC\46\025\D | SC | 46 | 25 | D | 6 DL | 100 | 0 | 100 | 2027-08-19 16:39 | 2027-08-26 06:11 | 491600.3052 |  |  |  | 28057 | 491600 | 372758 |  |  | 0 | 33.64 | 0 | 7.28 | 5773.74
TS5500Shv | GG\27\008\B | GG | 27 | 8 | B | 8 Coal Mining | 36.1 | 0 | 36.1 | 2027-08-19 21:57 | 2027-08-20 13:13 | 18625.2637 | [6 empty] | 18625 | 13604 | 1.36 | 0 | 0 | 10.42 | 5481
TS5500Shv | GG\30\010\X1 | GG | 30 | 10 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-08-20 13:13 | 2027-08-20 19:54 | 8149.8877 | [6 empty] | 8150 | 5854 | 0.59 | 0 | 0 | 14.29 | 5150
TS5500Shv | GG\30\018\B | GG | 30 | 18 | B | 1 Prestrip - Thick | 20.4938 | 20.4938 | 20.4938 | 2027-08-20 19:54 | 2027-08-23 15:36 | 72039.831 | 72040 | [7 empty] | 0 | 0 | 7.48 | 17.36 | 4930.25
DRE2 | GG\27\006\B | GG | 27 | 6 | B | 6 DL | 100 | 0 | 100 | 2027-08-21 18:03 | 2027-08-27 02:54 | 421875.588 |  |  |  |  | 421876 | 351563 |  |  | 0 | 19.96 | 0 | 10.86 | 5428.19
TS5500Exc | SC\46\022\D | SC | 46 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-08-22 19:11 | 2027-08-25 04:16 | 71911.354 | [6 empty] | 71911 | 53828 | 4.49 | 0 | 0 | 7.4 | 5762
TS5500Shv | GG\27\007\B | GG | 27 | 7 | B | 8 Coal Mining | 26.8 | 0 | 26.8 | 2027-08-23 15:36 | 2027-08-24 02:44 | 13581.8653 | [6 empty] | 13582 | 9904 | 0.99 | 0 | 0 | 10.62 | 5452
TS5500Shv | GG\30\019\B | GG | 30 | 19 | B | 1 Prestrip - Thick | 20.2562 | 20.2562 | 20.2562 | 2027-08-24 02:44 | 2027-08-26 15:04 | 64636.882 | 64637 | [7 empty] | 0 | 0 | 7.81 | 19.74 | 4756.77
TS Fleet 5 | GG\30\012\X1 | GG | 30 | 12 | X1 | 1 Prestrip - Thick | 45.0503 | 45.0503 | 45.0503 | 2027-08-24 15:51 | 2027-08-30 03:45 | 258525.1712 | 258525 | [7 empty] | 0 | 0 | 17.15 | 15.17 | 5085.78
TS5500Exc | W1\05\002\D | W1 | 5 | 2 | D | 7 PostStrip | 27.0763 | 0 | 27.0763 | 2027-08-25 04:16 | 2027-08-26 23:54 | 38586.533 |  |  | 38587 | [5 empty] | 0 | 0 | 0 | 7.45 | 5610.43
PH4100XPC#1 | GG\30\012\X1 | GG | 30 | 12 | X1 | 1 Prestrip - Thick | 100 | 54.9497 | 54.9497 | 2027-08-25 04:16 | 2027-08-30 21:31 | 315333.2768 | 315333 | [7 empty] | 0 | 0 | 20.91 | 15.17 | 5085.78
DRE1 | SC\46\026\D | SC | 46 | 26 | D | 6 DL | 100 | 0 | 100 | 2027-08-26 06:11 | 2027-09-01 11:48 | 466881.5701 |  |  |  | 19758 | 466882 | 248521 |  |  | 0 | 26.06 | 0 | 6.94 | 5803.8
TS5500Shv | GG\30\011\X1 | GG | 30 | 11 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-08-26 15:04 | 2027-08-26 21:13 | 7499.3934 | [6 empty] | 7499 | 5381 | 0.54 | 0 | 0 | 14.45 | 5142
TS5500Shv | GG\30\020\D | GG | 30 | 20 | D | 1 Prestrip - Thick | 5.2947 | 5.2947 | 5.2947 | 2027-08-26 21:13 | 2027-08-27 09:34 | 13283.212 | 13283 | [7 empty] | 0 | 0 | 1.54 | 6.76 | 5791.71
TS5500Exc | W1\05\002\D | W1 | 5 | 2 | D | 8 Coal Mining | 59.3 | 0 | 59.3 | 2027-08-26 23:54 | 2027-08-30 13:10 | 107411.6875 | [6 empty] | 107412 | 77417 | 2.8 | 0 | 0 | 7.45 | 5610
DRE2 | GG\26\013\D | GG | 26 | 13 | D | 6 DL | 100 | 100 | 100 | 2027-08-27 02:54 | 2027-09-02 10:52 | 497542.1625 |  |  |  | 11584 | 497542 | 220100 |  |  | 0 | 23.17 | 0 | 6.88 | 5781.31
TS5500Shv | GG\27\006\B | GG | 27 | 6 | B | 8 Coal Mining | 80 | 0 | 80 | 2027-08-27 09:34 | 2027-08-29 19:07 | 70166.0245 | [6 empty] | 70166 | 51055 | 2.89 | 0 | 0 | 10.86 | 5428
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 02:25 |  | 1d 02:25 | 2027-08-29 19:07 | 2027-08-30 21:31
TS Fleet 5 | GG\30\013\X1 | GG | 30 | 13 | X1 | 1 Prestrip - Thick | 45.005 | 45.005 | 45.005 | 2027-08-30 03:45 | 2027-09-03 16:10 | 212500.5502 | 212501 | [7 empty] | 0 | 0 | 16.9 | 15.02 | 5096.31
TS5500Exc | SC\46\023\D | SC | 46 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-08-30 13:10 | 2027-09-02 01:38 | 76150.7592 | [6 empty] | 76151 | 57004 | 4.75 | 0 | 0 | 7.41 | 5763
PH4100XPC#1 | GG\30\013\X1 | GG | 30 | 13 | X1 | 1 Prestrip - Thick | 100 | 54.995 | 54.995 | 2027-08-30 21:31 | 2027-09-04 14:21 | 259670.5335 | 259671 | [7 empty] | 0 | 0 | 20.66 | 15.02 | 5096.31
TS5500Shv | GG\30\012\X1 | GG | 30 | 12 | X1 | 8 Coal Mining | 93.1 | 0 | 93.1 | 2027-08-30 21:31 | 2027-08-31 06:53 | 11403.4011 | [6 empty] | 11403 | 8157 | 0.81 | 0 | 0 | 15.17 | 5086
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 04:00 |  | 2d 04:00 | 2027-08-31 06:53 | 2027-09-02 10:52
DRE1 | SC\47\018\D | SC | 47 | 18 | D | 6 DL | 100 | 0 | 100 | 2027-09-01 11:48 | 2027-09-23 10:37 | 1643954.004 |  |  |  | 90587 | 1643954 | 713575 |  |  | 0 | 40 | 0 | 7.15 | 5782.1
TS5500Exc | W1\05\004\D | W1 | 5 | 4 | D | 7 PostStrip | 59.2036 | 0 | 59.2036 | 2027-09-02 01:38 | 2027-09-04 20:39 | 59272.2573 |  |  | 59272 | [5 empty] | 0 | 0 | 0 | 7.82 | 5574.67
DRE2 | GG\26\012\D | GG | 26 | 12 | D | 6 DL | 100 | 100 | 100 | 2027-09-02 10:52 | 2027-09-08 15:09 | 485499.1837 |  |  |  | 11304 | 485499 | 214773 |  |  | 0 | 22.62 | 0 | 6.72 | 5796.22
TS5500Shv | GG\26\013\D | GG | 26 | 13 | D | 8 Coal Mining | 95.7 | 0 | 95.7 | 2027-09-02 10:52 | 2027-09-04 10:24 | 57949.0267 | [6 empty] | 57949 | 43218 | 4.32 | 0 | 0 | 6.88 | 5781
TS Fleet 5 | GG\30\014\X1 | GG | 30 | 14 | X1 | 1 Prestrip - Thick | 45.9925 | 45.9925 | 45.9925 | 2027-09-03 16:10 | 2027-09-08 14:06 | 231168.6816 | 231169 | [7 empty] | 0 | 0 | 16.04 | 14.76 | 5115.63
PH4100A | W2\02\004\A1 | W2 | 2 | 4 | A1 | 1 Prestrip - Thick | 100 | 0 | 88.0507 | 2027-09-04 00:35 | 2027-09-23 16:36 | 835378.0988 | 835378 | [7 empty] | 0 | 0 | 44.91 | 0 | 0
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 03:57 |  | 0d 03:57 | 2027-09-04 10:24 | 2027-09-04 14:21
PH4100XPC#1 | GG\30\014\X1 | GG | 30 | 14 | X1 | 1 Prestrip - Thick | 100 | 54.0075 | 54.0075 | 2027-09-04 14:21 | 2027-09-09 17:04 | 271454.352 | 271454 | [7 empty] | 0 | 0 | 18.84 | 14.76 | 5115.63
TS5500Shv | GG\30\013\X1 | GG | 30 | 13 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-09-04 14:21 | 2027-09-04 19:08 | 5852.2592 | [6 empty] | 5852 | 4190 | 0.42 | 0 | 0 | 15.02 | 5096
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 20:01 |  | 3d 20:01 | 2027-09-04 19:08 | 2027-09-08 15:09
TS5500Exc | SC\46\024\D | SC | 46 | 24 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-09-04 20:39 | 2027-09-07 08:49 | 75784.8223 | [6 empty] | 75785 | 56775 | 4.73 | 0 | 0 | 7.55 | 5750
TS5500Exc | W1\05\004\D | W1 | 5 | 4 | D | 8 Coal Mining | 16.4 | 0 | 16.4 | 2027-09-07 08:49 | 2027-09-08 00:51 | 20206.3653 | [6 empty] | 20206 | 14550 | 0.73 | 0 | 0 | 7.82 | 5575
TS5500Exc | W1\05\005\D | W1 | 5 | 5 | D | 7 PostStrip | 52.6625 | 0 | 52.6625 | 2027-09-08 00:51 | 2027-09-11 14:21 | 75609.569 |  |  | 75610 | [5 empty] | 0 | 0 | 0 | 7.76 | 5582
TS Fleet 5 | GG\30\017\X2 | GG | 30 | 17 | X2 | 1 Prestrip - Thick | 37.0871 | 0 | 37.0871 | 2027-09-08 14:06 | 2027-09-10 21:14 | 108033.0813 | 108033 | [7 empty] | 0 | 0 | 11.17 | 0 | 0
DRE2 | GG\26\011\D | GG | 26 | 11 | D | 6 DL | 100 | 100 | 100 | 2027-09-08 15:09 | 2027-09-14 19:14 | 484786.0371 |  |  |  | 8786 | 484786 | 210854 |  |  | 0 | 21.97 | 0 | 6.58 | 5808.84
TS5500Shv | GG\26\012\D | GG | 26 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-09-08 15:09 | 2027-09-10 17:35 | 61499.1716 | [6 empty] | 61499 | 45976 | 4.6 | 0 | 0 | 6.72 | 5796
PH4100XPC#1 | GG\30\017\X2 | GG | 30 | 17 | X2 | 1 Prestrip - Thick | 100 | 0 | 42.366 | 2027-09-09 17:04 | 2027-09-12 02:26 | 123410.2452 | 123410 | [7 empty] | 0 | 0 | 12.76 | 0 | 0
TS5500Shv | GG\30\014\X1 | GG | 30 | 14 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-09-10 17:35 | 2027-09-11 00:20 | 8220.8265 | [6 empty] | 8221 | 5897 | 0.44 | 0 | 0 | 14.76 | 5116
TS Fleet 5 | GG\30\018\B | GG | 30 | 18 | B | 1 Prestrip - Thick | 36.2716 | 36.2716 | 36.2716 | 2027-09-10 21:14 | 2027-09-13 14:17 | 127501.8128 | 127502 | [7 empty] | 0 | 0 | 13.24 | 17.36 | 4930.25
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 02:06 |  | 1d 02:06 | 2027-09-11 00:20 | 2027-09-12 02:26
TS5500Exc | SC\46\025\D | SC | 46 | 25 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-09-11 14:21 | 2027-09-14 03:11 | 76638.1646 | [6 empty] | 76638 | 57644 | 4.8 | 0 | 0 | 7.28 | 5774
PH4100XPC#1 | GG\30\017\B | GG | 30 | 17 | B | 1 Prestrip - Thick | 100 | 73.7799 | 73.7799 | 2027-09-12 02:26 | 2027-09-13 23:19 | 101590.6806 | 101591 | [7 empty] | 0 | 0 | 10.12 | 15.33 | 5068.63
TS5500Shv | GG\30\017\B | GG | 30 | 17 | B | 1 Prestrip - Thick | 13.3654 | 13.3654 | 13.3654 | 2027-09-12 02:26 | 2027-09-12 19:36 | 18403.4062 | 18403 | [7 empty] | 0 | 0 | 1.83 | 15.33 | 5068.63
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 23:38 |  | 1d 23:38 | 2027-09-12 19:36 | 2027-09-14 19:14
TS Fleet 5 | GG\30\017\B | GG | 30 | 17 | B | 1 Prestrip - Thick | 39.3485 | 12.8546 | 12.8546 | 2027-09-13 14:17 | 2027-09-13 23:19 | 17700.0917 | 17700 | [7 empty] | 0 | 0 | 1.76 | 15.33 | 5068.63
TS Fleet 5 | GG\30\019\B | GG | 30 | 19 | B | 1 Prestrip - Thick | 35.6127 | 35.6127 | 35.6127 | 2027-09-13 23:19 | 2027-09-16 09:17 | 113638.8336 | 113639 | [7 empty] | 0 | 0 | 13.73 | 19.74 | 4756.77
PH4100XPC#1 | GG\30\018\B | GG | 30 | 18 | B | 1 Prestrip - Thick | 100 | 43.2346 | 43.2346 | 2027-09-13 23:19 | 2027-09-16 19:00 | 151978.2579 | 151978 | [7 empty] | 0 | 0 | 15.78 | 17.36 | 4930.25
TS5500Exc | W1\05\005\D | W1 | 5 | 5 | D | 8 Coal Mining | 25.3 | 0 | 25.3 | 2027-09-14 03:11 | 2027-09-15 14:04 | 43931.0281 | [6 empty] | 43931 | 31637 | 1.17 | 0 | 0 | 7.76 | 5582
DRE2 | GG\26\010\D | GG | 26 | 10 | D | 6 DL | 100 | 100 | 100 | 2027-09-14 19:14 | 2027-09-20 13:25 | 452453.301 |  |  |  | 10534 | 452453 | 200154 |  |  | 0 | 21.06 | 0 | 6.55 | 5810.1
TS5500Shv | GG\26\011\D | GG | 26 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-09-14 19:14 | 2027-09-16 22:33 | 62580.4389 | [6 empty] | 62580 | 46859 | 4.69 | 0 | 0 | 6.58 | 5809
TS5500Exc | SC\46\026\D | SC | 46 | 26 | D | 7 PostStrip | 100 | 0 | 100 | 2027-09-15 14:04 | 2027-09-18 11:04 | 61020.0053 |  |  | 61020 | [5 empty] | 0 | 0 | 0 | 6.94 | 5803.8
TS Fleet 5 | GG\30\020\D | GG | 30 | 20 | D | 1 Prestrip - Thick | 42.0211 | 42.0211 | 42.0211 | 2027-09-16 09:17 | 2027-09-18 15:04 | 105422.1014 | 105422 | [7 empty] | 0 | 0 | 12.23 | 6.76 | 5791.71
PH4100XPC#1 | GG\30\019\B | GG | 30 | 19 | B | 1 Prestrip - Thick | 100 | 44.1311 | 44.1311 | 2027-09-16 19:00 | 2027-09-19 07:20 | 140820.6703 | 140821 | [7 empty] | 0 | 0 | 17.02 | 19.74 | 4756.77
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 14:52 |  | 3d 14:52 | 2027-09-16 22:33 | 2027-09-20 13:25
TS5500Exc | SC\46\026\D | SC | 46 | 26 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-09-18 11:04 | 2027-09-21 00:13 | 77022.9836 | [6 empty] | 77023 | 58211 | 4.85 | 0 | 0 | 6.94 | 5804
TS Fleet 5 | W1\04\003\D | W1 | 4 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-09-18 15:04 | 2027-09-22 12:11 | 182494.7928 | 182495 | [7 empty] | 0 | 0 | 14.05 | 7.64 | 5599.23
PH4100XPC#1 | GG\30\020\D | GG | 30 | 20 | D | 1 Prestrip - Thick | 100 | 52.6842 | 52.6842 | 2027-09-19 07:20 | 2027-09-21 15:18 | 132173.6711 | 132174 | [7 empty] | 0 | 0 | 15.33 | 6.76 | 5791.71
DRE2 | GG\26\009\D | GG | 26 | 9 | D | 6 DL | 100 | 100 | 100 | 2027-09-20 13:25 | 2027-09-26 01:50 | 433515.5017 |  |  |  | 10093 | 433516 | 191776 |  |  | 0 | 20.19 | 0 | 6.58 | 5807.98
TS5500Shv | GG\26\010\D | GG | 26 | 10 | D | 8 Coal Mining | 18.5 | 0 | 18.5 | 2027-09-20 13:25 | 2027-09-20 22:37 | 11212.5805 | [6 empty] | 11213 | 8402 | 0.84 | 0 | 0 | 6.55 | 5810
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 03:13 |  | 5d 03:13 | 2027-09-20 22:37 | 2027-09-26 01:50
TS5500Exc | W2\03\003\D | W2 | 3 | 3 | D | 7 PostStrip | 51.4826 | 0 | 51.4826 | 2027-09-21 00:13 | 2027-09-22 23:19 | 41653.9133 |  |  | 41654 | [5 empty] | 0 | 0 | 0 | 5.71 | 5763.07
PH4100XPC#1 | W2\02\004\A1 | W2 | 2 | 4 | A1 | 1 Prestrip - Thick | 100 | 0 | 11.9493 | 2027-09-21 15:18 | 2027-09-23 16:36 | 113368.4258 | 113368 | [7 empty] | 0 | 0 | 6.1 | 0 | 0
TS Fleet 5 | W1\04\004\D | W1 | 4 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-09-22 12:11 | 2027-09-25 13:31 | 143724.139 | 143724 | [7 empty] | 0 | 0 | 12.15 | 7.74 | 5589.66
TS5500Exc | W1\04\003\D | W1 | 4 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2027-09-22 23:19 | 2027-09-27 17:17 | 100792.8796 |  |  | 100793 | [5 empty] | 0 | 0 | 0 | 7.64 | 5599.23
DRE1 | SC\47\019\D | SC | 47 | 19 | D | 6 DL | 100 | 0 | 100 | 2027-09-23 10:37 | 2027-10-01 20:19 | 629381.7063 |  |  |  | 47862 | 629382 | 430756 |  |  | 0 | 40 | 0 | 7.01 | 5795.54
PH4100XPC#1 | W2\01\004\D | W2 | 1 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-09-23 16:36 | 2027-10-14 02:33 | 1109010.774 | 1109011 | [7 empty] | 0 | 0 | 22.06 | 5.73 | 5760.14
PH4100A | W2\03\004\B | W2 | 3 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-09-23 16:36 | 2027-10-19 23:46 | 1135357.133 | 1135357 | [7 empty] | 0 | 0 | 63.41 | 10.06 | 5277.9
TS Fleet 5 | W1\05\003\D | W1 | 5 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-09-25 13:31 | 2027-10-01 16:26 | 287953.5085 | 287954 | [7 empty] | 0 | 0 | 19.28 | 7.78 | 5580.98
DRE2 | GG\26\008\D | GG | 26 | 8 | D | 6 DL | 100 | 100 | 100 | 2027-09-26 01:50 | 2027-10-01 11:54 | 425876.2595 |  |  |  | 7931 | 425876 | 190336 |  |  | 0 | 19.83 | 0 | 6.57 | 5808.96
TS5500Shv | GG\26\009\D | GG | 26 | 9 | D | 8 Coal Mining | 23 | 0 | 23 | 2027-09-26 01:50 | 2027-09-26 13:26 | 14142.1573 | [6 empty] | 14142 | 10589 | 1.06 | 0 | 0 | 6.58 | 5808
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 22:29 |  | 4d 22:29 | 2027-09-26 13:26 | 2027-10-01 11:54
TS5500Exc | W1\04\003\D | W1 | 4 | 3 | D | 8 Coal Mining | 39.7 | 0 | 39.7 | 2027-09-27 17:17 | 2027-09-29 14:40 | 57165.3907 | [6 empty] | 57165 | 41181 | 2.06 | 0 | 0 | 7.64 | 5599
TS5500Exc | W1\04\004\D | W1 | 4 | 4 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2027-09-29 14:40 | 2027-10-01 19:06 | 46377.354 |  |  | 46377 | [5 empty] | 0 | 0 | 0 | 7.74 | 5589.66
DRE2 | GG\26\007\D | GG | 26 | 7 | D | 6 DL | 100 | 100 | 100 | 2027-10-01 11:54 | 2027-10-06 22:49 | 428636.47 |  |  |  | 7982 | 428636 | 191569 |  |  | 0 | 19.96 | 0 | 6.57 | 5808.9
TS5500Shv | GG\26\008\D | GG | 26 | 8 | D | 8 Coal Mining | 86.4 | 0 | 86.4 | 2027-10-01 11:54 | 2027-10-03 07:32 | 53190.6759 | [6 empty] | 53191 | 39828 | 3.98 | 0 | 0 | 6.57 | 5809
TS Fleet 5 | W1\10\002\B | W1 | 10 | 2 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-10-01 16:26 | 2027-10-08 11:05 | 318797.117 | 318797 | [7 empty] | 0 | 0 | 36.08 | 11.18 | 5167.25
TS5500Exc | SC\47\018\D | SC | 47 | 18 | D | 7 PostStrip | 100 | 0 | 100 | 2027-10-01 19:06 | 2027-10-06 14:06 | 101707.4465 |  |  | 101707 | [5 empty] | 0 | 0 | 0 | 7.15 | 5782.1
DRE1 | SC\47\020\D | SC | 47 | 20 | D | 6 DL | 100 | 0 | 100 | 2027-10-01 20:19 | 2027-10-10 05:52 | 628955.1984 |  |  |  | 47829 | 628955 | 430464 |  |  | 0 | 40 | 0 | 7.08 | 5789.24
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 15:18 |  | 3d 15:18 | 2027-10-03 07:32 | 2027-10-06 22:49
TS5500Exc | SC\47\018\D | SC | 47 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-10-06 14:06 | 2027-10-09 19:40 | 97704.7586 | [6 empty] | 97705 | 73016 | 4.2 | 0 | 0 | 7.15 | 5782
DRE2 | GG\26\006\D | GG | 26 | 6 | D | 6 DL | 100 | 100 | 100 | 2027-10-06 22:49 | 2027-10-12 10:16 | 430341.4488 |  |  |  | 10020 | 430341 | 190372 |  |  | 0 | 20.04 | 0 | 6.57 | 5808.06
TS5500Shv | GG\26\007\D | GG | 26 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-10-06 22:49 | 2027-10-09 01:00 | 61180.8023 | [6 empty] | 61181 | 45810 | 4.58 | 0 | 0 | 6.57 | 5809
TS Fleet 5 | W1\10\003\D | W1 | 10 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-10-08 11:05 | 2027-11-03 11:33 | 1223957.58 | 1223958 | [7 empty] | 0 | 0 | 77.75 | 8.28 | 5534.31
TS6060#1 | W2\01\005\D | W2 | 1 | 5 | D | 7 PostStrip | 7.6553 | 0 | 7.6553 | 2027-10-08 16:03 | 2027-10-09 12:24 | 20992.47 |  |  | 20992 | [5 empty] | 0 | 0 | 0 | 5.72 | 5756.18
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 09:16 |  | 3d 09:16 | 2027-10-09 01:00 | 2027-10-12 10:16
TS6060#1 | W2\01\005\D | W2 | 1 | 5 | D | 7 PostStrip | 92.3447 | 0 | 92.3447 | 2027-10-09 12:24 | 2027-10-19 17:49 | 253228.7297 |  |  | 253229 | [5 empty] | 0 | 0 | 0 | 5.72 | 5756.18
TS5500Exc | SC\47\019\D | SC | 47 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-10-09 19:40 | 2027-10-12 04:32 | 71615.0299 | [6 empty] | 71615 | 53606 | 4.47 | 0 | 0 | 7.01 | 5796
DRE1 | SC\47\021\D | SC | 47 | 21 | D | 6 DL | 100 | 0 | 100 | 2027-10-10 05:52 | 2027-10-18 16:21 | 631826.6865 |  |  |  | 48048 | 631827 | 432429 |  |  | 0 | 40 | 0 | 7.28 | 5770.96
TS5500Exc | SC\47\020\D | SC | 47 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-10-12 04:32 | 2027-10-14 12:06 | 70000.0955 | [6 empty] | 70000 | 52396 | 4.37 | 0 | 0 | 7.08 | 5789
DRE2 | GG\26\005\D | GG | 26 | 5 | D | 6 DL | 100 | 100 | 100 | 2027-10-12 10:16 | 2027-10-21 22:23 | 746886.8898 |  |  |  | 12110 | 746887 | 214649 |  |  | 0 | 19.92 | 0 | 6.56 | 5809.31
TS5500Shv | GG\26\006\D | GG | 26 | 6 | D | 8 Coal Mining | 97.6 | 0 | 97.6 | 2027-10-12 10:16 | 2027-10-14 10:52 | 59256.9638 | [6 empty] | 59257 | 44405 | 4.44 | 0 | 0 | 6.57 | 5808
PH4100XPC#1 | W2\02\005\A2 | W2 | 2 | 5 | A2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2027-10-14 02:33 | 2027-10-14 21:47 | 43565.3 | 43565 | [7 empty] | 0 | 0 | 2.18 | 0 | 0
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 7d 11:32 |  | 7d 11:32 | 2027-10-14 10:52 | 2027-10-21 22:23
TS5500Exc | W2\01\004\D | W2 | 1 | 4 | D | 7 PostStrip | 47.3365 | 0 | 47.3365 | 2027-10-14 12:06 | 2027-10-21 18:01 | 153815.2876 |  |  | 153815 | [5 empty] | 0 | 0 | 0 | 5.73 | 5760.14
PH4100XPC#1 | W2\02\004\A2 | W2 | 2 | 4 | A2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2027-10-14 21:47 | 2027-10-15 13:07 | 34680.686 | 34681 | [7 empty] | 0 | 0 | 1.75 | 0 | 0
PH4100XPC#1 | W2\02\003\D | W2 | 2 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-10-15 13:07 | 2027-10-18 09:13 | 154158.6512 | 154159 | [7 empty] | 0 | 0 | 20.89 | 5.71 | 5763.3
PH4100XPC#1 | W2\03\005\B | W2 | 3 | 5 | B | 1 Prestrip - Thick | 100 | 60.1829 | 60.1829 | 2027-10-18 09:13 | 2027-10-29 20:14 | 619058.0566 | 619058 | [7 empty] | 0 | 0 | 31.5 | 10 | 5280.42
DRE1 | SC\47\022\D | SC | 47 | 22 | D | 6 DL | 100 | 0 | 100 | 2027-10-18 16:21 | 2027-10-27 01:22 | 627289.348 |  |  |  | 47703 | 627289 | 429324 |  |  | 0 | 40 | 0 | 7.38 | 5763.36
TS6060#1 | W2\01\005\D | W2 | 1 | 5 | D | 8 Coal Mining | 58.3 | 0 | 58.3 | 2027-10-19 17:49 | 2027-10-25 08:56 | 182857.2992 | [6 empty] | 182857 | 133191 | 2.5 | 0 | 0 | 5.72 | 5756
PH4100A | W2\03\005\B | W2 | 3 | 5 | B | 1 Prestrip - Thick | 100 | 39.8171 | 39.8171 | 2027-10-19 23:46 | 2027-10-29 20:14 | 409569.2579 | 409569 | [7 empty] | 0 | 0 | 20.84 | 10 | 5280.42
TS5500Exc | W2\01\005\D | W2 | 1 | 5 | D | 8 Coal Mining | 41.7 | 0 | 41.7 | 2027-10-21 18:01 | 2027-10-26 02:02 | 131011.0547 | [6 empty] | 131011 | 95427 | 1.79 | 0 | 0 | 5.72 | 5756
DRE2 | GG\27\014\B | GG | 27 | 14 | B | 6 DL | 100 | 0 | 100 | 2027-10-21 22:23 | 2027-10-24 04:50 | 178239.8166 |  |  |  |  | 178240 | 148533 |  |  | 0 | 16.35 | 0 | 12.28 | 5289.79
TS5500Shv | GG\26\005\D | GG | 26 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2027-10-21 22:23 | 2027-10-24 21:16 | 75980.6784 |  |  | 75981 | [5 empty] | 0 | 0 | 0 | 6.56 | 5809.31
DRE2 | GG\27\017\B | GG | 27 | 17 | B | 6 DL | 100 | 0 | 100 | 2027-10-24 04:50 | 2027-10-26 11:13 | 178071.0858 |  |  |  |  | 178071 | 148393 |  |  | 0 | 15.9 | 0 | 14.27 | 5144.85
TS5500Shv | GG\26\005\D | GG | 26 | 5 | D | 8 Coal Mining | 63.2 | 0 | 63.2 | 2027-10-24 21:16 | 2027-10-26 20:27 | 57539.5174 | [6 empty] | 57540 | 43152 | 2.85 | 0 | 0 | 6.56 | 5809
TS6060#1 | W1\04\003\D | W1 | 4 | 3 | D | 8 Coal Mining | 60.3 | 0 | 60.3 | 2027-10-25 08:56 | 2027-10-28 01:03 | 86788.1418 | [6 empty] | 86788 | 62521 | 3.13 | 0 | 0 | 7.64 | 5599
TS5500Exc | W2\03\004\B | W2 | 3 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-10-26 02:02 | 2027-10-28 18:21 | 81017.6865 | [6 empty] | 81018 | 56849 | 2.86 | 0 | 0 | 10.06 | 5278
DRE2 | GG\27\018\B | GG | 27 | 18 | B | 6 DL | 100 | 0 | 100 | 2027-10-26 11:13 | 2027-10-28 23:00 | 195711.0258 |  |  |  |  | 195711 | 163093 |  |  | 0 | 16.28 | 0 | 14.76 | 5128.3
TS5500Shv | GG\27\014\B | GG | 27 | 14 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-10-26 20:27 | 2027-10-27 12:50 | 19973.2483 | [6 empty] | 19973 | 14487 | 1.66 | 0 | 0 | 12.28 | 5290
DRE1 | SC\47\023\D | SC | 47 | 23 | D | 6 DL | 100 | 0 | 100 | 2027-10-27 01:22 | 2027-11-02 21:19 | 511603.7241 |  |  |  | 29199 | 511604 | 387926 |  |  | 0 | 34.88 | 0 | 7.43 | 5760.52
TS5500Shv | GG\27\017\B | GG | 27 | 17 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2027-10-27 12:50 | 2027-10-28 04:50 | 19521.8214 | [6 empty] | 19522 | 14006 | 1.57 | 0 | 0 | 14.27 | 5145
TS6060#1 | W1\04\004\D | W1 | 4 | 4 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2027-10-28 01:03 | 2027-10-30 05:30 | 54106.913 |  |  | 54107 | [5 empty] | 0 | 0 | 0 | 7.74 | 5589.66
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 18:09 |  | 0d 18:09 | 2027-10-28 04:50 | 2027-10-28 23:00
TS5500Exc | W1\05\003\D | W1 | 5 | 3 | D | 7 PostStrip | 19.9078 | 0 | 19.9078 | 2027-10-28 18:21 | 2027-10-29 17:03 | 20073.7088 |  |  | 20074 | [5 empty] | 0 | 0 | 0 | 7.78 | 5580.98
DRE2 | GG\27\019\B | GG | 27 | 19 | B | 6 DL | 100 | 0 | 100 | 2027-10-28 23:00 | 2027-10-31 11:55 | 199483.2358 |  |  |  |  | 199483 | 166236 |  |  | 0 | 16.69 | 0 | 16.39 | 5019.41
TS5500Shv | GG\27\018\B | GG | 27 | 18 | B | 8 Coal Mining | 73.2 | 0 | 73.2 | 2027-10-28 23:00 | 2027-10-30 02:26 | 33465.525 | [6 empty] | 33466 | 23918 | 2.39 | 0 | 0 | 14.76 | 5128
TS5500Exc | SC\47\021\D | SC | 47 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-10-29 17:03 | 2027-10-31 22:55 | 67843.294 | [6 empty] | 67843 | 50821 | 4.23 | 0 | 0 | 7.28 | 5771
PH4100A | W2\02\004\B | W2 | 2 | 4 | B | 1 Prestrip - Thick | 100 | 84.4919 | 84.4919 | 2027-10-29 20:14 | 2027-11-01 04:34 | 97771.7083 | 97772 | [7 empty] | 0 | 0 | 4.91 | 9.89 | 5296.13
PH4100XPC#1 | W2\02\005\B | W2 | 2 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-10-29 20:14 | 2027-10-31 20:38 | 109536.0866 | 109536 | [7 empty] | 0 | 0 | 5.48 | 9.96 | 5290.04
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 09:29 |  | 1d 09:29 | 2027-10-30 02:26 | 2027-10-31 11:55
TS6060#1 | W1\04\004\D | W1 | 4 | 4 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2027-10-30 05:30 | 2027-11-01 11:50 | 73540.7418 | [6 empty] | 73541 | 52975 | 2.65 | 0 | 0 | 7.74 | 5590
DRE2 | GG\27\020\B | GG | 27 | 20 | B | 6 DL | 100 | 0 | 100 | 2027-10-31 11:55 | 2027-11-03 02:29 | 204847.104 |  |  |  |  | 204847 | 157575 |  |  | 0 | 17.92 | 0 | 0 | 0
TS5500Shv | GG\27\019\B | GG | 27 | 19 | B | 8 Coal Mining | 54.6 | 0 | 54.6 | 2027-10-31 11:55 | 2027-11-01 06:09 | 22222.7411 | [6 empty] | 22223 | 15725 | 1.57 | 0 | 0 | 16.39 | 5019
PH4100XPC#1 | W2\02\004\B | W2 | 2 | 4 | B | 1 Prestrip - Thick | 100 | 15.5081 | 15.5081 | 2027-10-31 20:38 | 2027-11-01 04:34 | 17945.6053 | 17946 | [7 empty] | 0 | 0 | 0.9 | 9.89 | 5296.13
TS5500Exc | W2\02\005\B | W2 | 2 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-10-31 22:55 | 2027-11-04 01:50 | 94369.9106 | [6 empty] | 94370 | 66222 | 3.31 | 0 | 0 | 9.96 | 5290
PH4100A | W2\02\006\B | W2 | 2 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-11-01 04:34 | 2027-11-25 09:49 | 1006366.175 | 1006366 | [7 empty] | 0 | 0 | 49.4 | 9.95 | 5291.69
PH4100XPC#1 | W2\03\004\D | W2 | 3 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-11-01 04:34 | 2027-11-07 01:54 | 319911.1142 | 319911 | [7 empty] | 0 | 0 | 21.04 | 5.71 | 5762.79
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 6d 00:36 |  | 6d 00:36 | 2027-11-01 06:09 | 2027-11-07 06:45
TS6060#1 | GG\27\013\B | GG | 27 | 13 | B | 8 Coal Mining | 44.2 | 0 | 44.2 | 2027-11-01 11:50 | 2027-11-02 03:43 | 21493.6287 | [6 empty] | 21494 | 15597 | 1.56 | 0 | 0 | 12.03 | 5324
TS6060#1 | GG\27\012\B | GG | 27 | 12 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-11-02 03:43 | 2027-11-03 15:53 | 48947.7829 | [6 empty] | 48948 | 35519 | 3.56 | 0 | 0 | 11.77 | 5370
DRE1 | SC\47\024\D | SC | 47 | 24 | D | 6 DL | 100 | 0 | 100 | 2027-11-02 21:19 | 2027-11-09 21:57 | 526259.0583 |  |  |  | 37427 | 526259 | 378424 |  |  | 0 | 35 | 0 | 7.62 | 5743.54
DRE2 | GG\26\014\D | GG | 26 | 14 | D | 6 DL | 100 | 100 | 100 | 2027-11-03 02:29 | 2027-11-07 23:37 | 383464.3065 |  |  |  | 8928 | 383464 | 169635 |  |  | 0 | 23.66 | 0 | 6.97 | 5772.53
TS Fleet 5 | W2\08\006\B | W2 | 8 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-11-03 11:33 | 2027-11-24 23:09 | 1010570.975 | 1010571 | [7 empty] | 0 | 0 | 48.83 | 10.24 | 5257.45
TS6060#1 | GG\27\011\B | GG | 27 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-11-03 15:53 | 2027-11-05 04:24 | 49420.9431 | [6 empty] | 49421 | 35918 | 3.6 | 0 | 0 | 11.47 | 5411
TS5500Exc | W2\02\004\B | W2 | 2 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-11-04 01:50 | 2027-11-07 02:12 | 91156.7891 | [6 empty] | 91157 | 64040 | 3.22 | 0 | 0 | 9.89 | 5296
TS6060#1 | W1\04\005\D | W1 | 4 | 5 | D | 8 Coal Mining | 18.5 | 0 | 18.5 | 2027-11-05 04:24 | 2027-11-05 23:52 | 26347.8198 | [6 empty] | 26348 | 18979 | 0.93 | 0 | 0 | 7.71 | 5591
TS6060#1 | GG\27\009\B | GG | 27 | 9 | B | 8 Coal Mining | 62.9 | 0 | 62.9 | 2027-11-05 23:52 | 2027-11-06 23:41 | 32241.9585 | [6 empty] | 32242 | 23559 | 2.36 | 0 | 0 | 10.38 | 5495
TS6060#1 | GG\30\009\X1 | GG | 30 | 9 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-11-06 23:41 | 2027-11-07 06:45 | 9551.1181 | [6 empty] | 9551 | 6874 | 0.69 | 0 | 0 | 13.98 | 5163
PH4100XPC#1 | W2\02\005\D | W2 | 2 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-11-07 01:54 | 2027-11-13 03:22 | 329294.667 | 329295 | [7 empty] | 0 | 0 | 21.46 | 5.71 | 5759.11
TS5500Exc | W2\03\005\B | W2 | 3 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-11-07 02:12 | 2027-11-10 05:41 | 95080.0184 | [6 empty] | 95080 | 66675 | 3.34 | 0 | 0 | 10 | 5280
TS6060#1 | W1\05\002\D | W1 | 5 | 2 | D | 8 Coal Mining | 40.7 | 0 | 40.7 | 2027-11-07 06:45 | 2027-11-09 13:08 | 73617.3537 | [6 empty] | 73617 | 53060 | 1.92 | 0 | 0 | 7.45 | 5610
TS5500Shv | GG\30\009\X2 | GG | 30 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2027-11-07 06:45 | 2027-11-09 22:13 | 68044.222 | 68044 | [7 empty] | 0 | 0 | 6.81 | 0 | 0
DRE2 | GG\26\017\D | GG | 26 | 17 | D | 6 DL | 100 | 100 | 100 | 2027-11-07 23:37 | 2027-11-13 01:30 | 399047.3504 |  |  |  | 9291 | 399047 | 176529 |  |  | 0 | 24.04 | 0 | 7.02 | 5770.49
TS6060#1 | GG\27\008\B | GG | 27 | 8 | B | 8 Coal Mining | 63.9 | 0 | 63.9 | 2027-11-09 13:08 | 2027-11-10 13:30 | 32960.4726 | [6 empty] | 32960 | 24074 | 2.41 | 0 | 0 | 10.42 | 5481
DRE1 | SC\47\025\D | SC | 47 | 25 | D | 6 DL | 100 | 0 | 100 | 2027-11-09 21:57 | 2027-11-15 18:41 | 439123.1665 |  |  |  | 25062 | 439123 | 332967 |  |  | 0 | 30.71 | 0 | 7.24 | 5777.3
TS5500Shv | GG\30\009\B | GG | 30 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-11-09 22:13 | 2027-11-12 22:06 | 77063.979 | 77064 | [7 empty] | 0 | 0 | 7.72 | 10.61 | 5476.63
TS5500Exc | W1\04\004\D | W1 | 4 | 4 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2027-11-10 05:41 | 2027-11-12 12:01 | 68443.8587 | [6 empty] | 68444 | 49304 | 2.47 | 0 | 0 | 7.74 | 5590
TS6060#1 | GG\27\007\B | GG | 27 | 7 | B | 8 Coal Mining | 73.2 | 0 | 73.2 | 2027-11-10 13:30 | 2027-11-11 16:56 | 37130.2973 | [6 empty] | 37130 | 27075 | 2.71 | 0 | 0 | 10.62 | 5452
TS6060#1 | W1\05\004\D | W1 | 5 | 4 | D | 8 Coal Mining | 83.6 | 0 | 83.6 | 2027-11-11 16:56 | 2027-11-14 21:08 | 103139.4675 | [6 empty] | 103139 | 74265 | 3.72 | 0 | 0 | 7.82 | 5575
TS5500Exc | SC\47\022\D | SC | 47 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-11-12 12:01 | 2027-11-14 21:11 | 72008.3583 | [6 empty] | 72008 | 53901 | 4.49 | 0 | 0 | 7.38 | 5763
TS5500Shv | GG\26\014\D | GG | 26 | 14 | D | 8 Coal Mining | 80.2 | 0 | 80.2 | 2027-11-12 22:06 | 2027-11-14 03:35 | 35941.3858 | [6 empty] | 35941 | 26762 | 3.58 | 0 | 0 | 6.97 | 5773
DRE2 | GG\26\018\D | GG | 26 | 18 | D | 6 DL | 100 | 100 | 100 | 2027-11-13 01:30 | 2027-11-19 12:33 | 507645.8767 |  |  |  | 11819 | 507646 | 224570 |  |  | 0 | 23.63 | 0 | 7.01 | 5771.39
PH4100XPC#1 | W2\02\004\D | W2 | 2 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-11-13 03:22 | 2027-11-19 07:59 | 336369.3687 | 336369 | [7 empty] | 0 | 0 | 21.83 | 5.72 | 5761.71
TS5500Shv | GG\26\017\D | GG | 26 | 17 | D | 8 Coal Mining | 93.7 | 0 | 93.7 | 2027-11-14 03:35 | 2027-11-15 16:30 | 45024.5137 | [6 empty] | 45025 | 33527 | 4.38 | 0 | 0 | 7.02 | 5770
TS6060#1 | GG\27\006\B | GG | 27 | 6 | B | 8 Coal Mining | 20 | 0 | 20 | 2027-11-14 21:08 | 2027-11-15 10:04 | 17512.0352 | [6 empty] | 17512 | 12742 | 0.72 | 0 | 0 | 10.86 | 5428
TS5500Exc | W1\06\002\B | W1 | 6 | 2 | B | 8 Coal Mining | 76.9 | 0 | 76.9 | 2027-11-14 21:11 | 2027-11-17 04:27 | 69616.3614 | [6 empty] | 69616 | 48897 | 1.61 | 0 | 0 | 11.06 | 5154
TS6060#1 | GG\30\010\X1 | GG | 30 | 10 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-11-15 10:04 | 2027-11-15 16:45 | 9045.4798 | [6 empty] | 9045 | 6497 | 0.65 | 0 | 0 | 14.29 | 5150
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 00:15 |  | 0d 00:15 | 2027-11-15 16:30 | 2027-11-15 16:45
TS6060#1 | W1\05\005\D | W1 | 5 | 5 | D | 8 Coal Mining | 74.7 | 0 | 74.7 | 2027-11-15 16:45 | 2027-11-19 16:29 | 129547.7496 | [6 empty] | 129548 | 93294 | 3.46 | 0 | 0 | 7.76 | 5582
TS5500Shv | GG\30\010\X2 | GG | 30 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2027-11-15 16:45 | 2027-11-18 09:10 | 69045.721 | 69046 | [7 empty] | 0 | 0 | 6.94 | 0 | 0
DRE1 | SC\47\026\D | SC | 47 | 26 | D | 6 DL | 100 | 0 | 100 | 2027-11-15 18:41 | 2027-11-19 00:32 | 242933.9282 |  |  |  | 8660 | 242934 | 148314 |  |  | 0 | 17.32 | 0 | 6.94 | 5804.21
TS5500Exc | SC\47\023\D | SC | 47 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-11-17 04:27 | 2027-11-19 17:26 | 76811.3668 | [6 empty] | 76811 | 57499 | 4.79 | 0 | 0 | 7.43 | 5761
TS5500Shv | GG\30\010\B | GG | 30 | 10 | B | 1 Prestrip - Thick | 71.9508 | 53.7316 | 53.7316 | 2027-11-18 09:10 | 2027-11-19 23:41 | 41291.482 | 41291 | [7 empty] | 0 | 0 | 4.12 | 11.02 | 5448.44
DRE1 | SC\48\017\D | SC | 48 | 17 | D | 6 DL | 100 | 0 | 0 | 2027-11-19 00:32 | 2027-11-19 00:32 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE1 | SC\48\018\D | SC | 48 | 18 | D | 6 DL | 100 | 0 | 100 | 2027-11-19 00:32 | 2027-11-27 10:32 | 630378.131 |  |  |  | 47938 | 630378 | 431438 |  |  | 0 | 40 | 0 | 7.17 | 5781.13
PH4100XPC#1 | GG\30\010\B | GG | 30 | 10 | B | 1 Prestrip - Thick | 100 | 46.2684 | 46.2684 | 2027-11-19 07:59 | 2027-11-19 23:41 | 35556.2102 | 35556 | [7 empty] | 0 | 0 | 3.55 | 11.02 | 5448.44
DRE2 | GG\26\019\D | GG | 26 | 19 | D | 6 DL | 100 | 100 | 100 | 2027-11-19 12:33 | 2027-11-25 20:38 | 497972.613 |  |  |  | 11594 | 497973 | 220291 |  |  | 0 | 23.18 | 0 | 6.93 | 5777.86
TS6060#1 | GG\26\013\D | GG | 26 | 13 | D | 8 Coal Mining | 4.3 | 0 | 4.3 | 2027-11-19 16:29 | 2027-11-19 18:24 | 2598.2808 | [6 empty] | 2598 | 1938 | 0.19 | 0 | 0 | 6.88 | 5781
TS5500Exc | W2\02\004\D | W2 | 2 | 4 | D | 7 PostStrip | 62.7928 | 0 | 62.7928 | 2027-11-19 17:26 | 2027-11-22 16:22 | 62732.9643 |  |  | 62733 | [5 empty] | 0 | 0 | 0 | 5.72 | 5761.71
TS6060#1 | GG\30\011\X1 | GG | 30 | 11 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-11-19 18:24 | 2027-11-20 00:33 | 8323.5026 | [6 empty] | 8324 | 5973 | 0.6 | 0 | 0 | 14.45 | 5142
PH4100XPC#1 | W2\03\005\D | W2 | 3 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-11-19 23:41 | 2027-11-25 21:52 | 321829.3298 | 321829 | [7 empty] | 0 | 0 | 21.1 | 5.72 | 5761.63
TS5500Shv | GG\26\018\D | GG | 26 | 18 | D | 8 Coal Mining | 47.2 | 0 | 47.2 | 2027-11-19 23:41 | 2027-11-20 23:55 | 29544.6428 | [6 empty] | 29545 | 22000 | 2.2 | 0 | 0 | 7.01 | 5771
TS6060#1 | W2\01\004\D | W2 | 1 | 4 | D | 7 PostStrip | 52.6635 | 0 | 52.6635 | 2027-11-20 00:33 | 2027-11-26 22:24 | 171124.6607 |  |  | 171125 | [5 empty] | 0 | 0 | 0 | 5.73 | 5760.14
TS5500Shv | GG\30\011\X2 | GG | 30 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2027-11-20 23:55 | 2027-11-23 17:04 | 69852.824 | 69853 | [7 empty] | 0 | 0 | 7.02 | 0 | 0
TS5500Exc | W2\03\004\D | W2 | 3 | 4 | D | 7 PostStrip | 20.1764 | 0 | 20.1764 | 2027-11-22 16:22 | 2027-11-23 15:08 | 20124.0691 |  |  | 20124 | [5 empty] | 0 | 0 | 0 | 5.71 | 5762.79
TS5500Exc | SC\47\024\D | SC | 47 | 24 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-11-23 15:08 | 2027-11-26 03:13 | 75681.0964 | [6 empty] | 75681 | 56742 | 4.73 | 0 | 0 | 7.62 | 5744
TS5500Shv | GG\26\018\D | GG | 26 | 18 | D | 8 Coal Mining | 52.8 | 0 | 52.8 | 2027-11-23 17:04 | 2027-11-24 20:12 | 33073.8926 | [6 empty] | 33074 | 24628 | 2.46 | 0 | 0 | 7.01 | 5771
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 00:27 |  | 1d 00:27 | 2027-11-24 20:12 | 2027-11-25 20:38
TS Fleet 5 | GG\30\011\A | GG | 30 | 11 | A | 1 Prestrip - Thick | 45.419 | 0 | 45.419 | 2027-11-24 23:09 | 2027-11-25 17:52 | 36699.8429 | 36700 | [7 empty] | 0 | 0 | 3.68 | 0 | 0
PH4100A | W2\03\006\B | W2 | 3 | 6 | B | 1 Prestrip - Thick | 100 | 57.4239 | 57.4239 | 2027-11-25 09:49 | 2027-12-09 11:47 | 582780.1877 | 582780 | [7 empty] | 0 | 0 | 29.12 | 10.01 | 5279.72
TS Fleet 5 | W1\06\002\D | W1 | 6 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-11-25 17:52 | 2027-12-09 01:16 | 626034.4228 | 626034 | [7 empty] | 0 | 0 | 26.78 | 7.64 | 5591.51
DRE2 | GG\26\020\D | GG | 26 | 20 | D | 6 DL | 100 | 100 | 100 | 2027-11-25 20:38 | 2027-12-01 17:16 | 460420.5782 |  |  |  | 7222 | 460421 | 131853 |  |  | 0 | 21.77 | 0 | 6.83 | 5784.7
TS5500Shv | GG\26\019\D | GG | 26 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-11-25 20:38 | 2027-11-27 23:47 | 62362.3221 | [6 empty] | 62362 | 46511 | 4.65 | 0 | 0 | 6.93 | 5778
PH4100XPC#1 | GG\30\011\A | GG | 30 | 11 | A | 1 Prestrip - Thick | 100 | 0 | 54.581 | 2027-11-25 21:52 | 2027-11-26 17:21 | 44103.058 | 44103 | [7 empty] | 0 | 0 | 4.42 | 0 | 0
TS5500Exc | W2\02\006\B | W2 | 2 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-11-26 03:13 | 2027-11-29 08:59 | 97962.0203 | [6 empty] | 97962 | 68749 | 3.44 | 0 | 0 | 9.95 | 5292
PH4100XPC#1 | GG\30\011\B | GG | 30 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-11-26 17:21 | 2027-11-27 14:30 | 47892.2495 | 47892 | [7 empty] | 0 | 0 | 4.78 | 11.63 | 5396.54
TS6060#1 | GG\30\012\X1 | GG | 30 | 12 | X1 | 8 Coal Mining | 6.9 | 0 | 6.9 | 2027-11-26 22:24 | 2027-11-26 23:01 | 848.226 | [6 empty] | 848 | 607 | 0.06 | 0 | 0 | 15.17 | 5086
TS6060#1 | W2\01\004\D | W2 | 1 | 4 | D | 8 Coal Mining | 51.7 | 0 | 51.7 | 2027-11-26 23:01 | 2027-12-03 06:13 | 204617.8739 | [6 empty] | 204618 | 149304 | 2.41 | 0 | 0 | 5.73 | 5760
DRE1 | SC\48\019\D | SC | 48 | 19 | D | 6 DL | 100 | 0 | 100 | 2027-11-27 10:32 | 2027-12-05 20:01 | 628746.922 |  |  |  | 47813 | 628747 | 430321 |  |  | 0 | 40 | 0 | 7.09 | 5788.58
PH4100XPC#1 | GG\30\012\X2 | GG | 30 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2027-11-27 14:30 | 2027-11-28 21:43 | 70636.168 | 70636 | [7 empty] | 0 | 0 | 7.09 | 0 | 0
TS5500Shv | GG\30\011\B | GG | 30 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-11-27 23:47 | 2027-11-29 17:19 | 50642.3186 | [6 empty] | 50642 | 36697 | 3.68 | 0 | 0 | 11.63 | 5397
PH4100XPC#1 | GG\30\012\A | GG | 30 | 12 | A | 1 Prestrip - Thick | 100 | 0 | 100 | 2027-11-28 21:43 | 2027-11-30 13:53 | 90925.6616 | 90926 | [7 empty] | 0 | 0 | 9.12 | 0 | 0
TS5500Exc | W2\01\004\D | W2 | 1 | 4 | D | 8 Coal Mining | 48.3 | 0 | 48.3 | 2027-11-29 08:59 | 2027-12-05 16:48 | 191225.8752 | [6 empty] | 191226 | 139532 | 2.25 | 0 | 0 | 5.73 | 5760
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 17:23 |  | 1d 17:23 | 2027-11-29 17:19 | 2027-12-01 10:42
PH4100XPC#1 | GG\30\012\B | GG | 30 | 12 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-11-30 13:53 | 2027-12-01 10:42 | 47110.8895 | 47111 | [7 empty] | 0 | 0 | 4.71 | 12.08 | 5347.32
PH4100XPC#1 | W2\03\006\B | W2 | 3 | 6 | B | 1 Prestrip - Thick | 100 | 42.5761 | 42.5761 | 2027-12-01 10:42 | 2027-12-09 11:47 | 432092.8814 | 432093 | [7 empty] | 0 | 0 | 21.59 | 10.01 | 5279.72
TS5500Shv | GG\30\012\B | GG | 30 | 12 | B | 8 Coal Mining | 95.9 | 0 | 95.9 | 2027-12-01 10:42 | 2027-12-03 02:07 | 48074.591 | [6 empty] | 48075 | 34753 | 3.48 | 0 | 0 | 12.08 | 5347
DRE2 | GG\28\013\B | GG | 28 | 13 | B | 6 DL | 100 | 0 | 100 | 2027-12-01 17:16 | 2027-12-04 07:18 | 203100.5707 |  |  |  |  | 203101 | 169250 |  |  | 0 | 17.01 | 0 | 12.07 | 5321.2
TS5500Shv | GG\26\020\D | GG | 26 | 20 | D | 7 PostStrip | 100 | 0 | 100 | 2027-12-03 02:07 | 2027-12-04 16:48 | 41464.065 |  |  | 41464 | [5 empty] | 0 | 0 | 0 | 6.83 | 5784.7
TS6060#1 | GG\30\012\B | GG | 30 | 12 | B | 8 Coal Mining | 4.1 | 0 | 4.1 | 2027-12-03 06:13 | 2027-12-03 07:44 | 2065.4763 | [6 empty] | 2065 | 1493 | 0.15 | 0 | 0 | 12.08 | 5347
TS6060#1 | GG\30\013\X1 | GG | 30 | 13 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-12-03 07:44 | 2027-12-03 12:32 | 6495.3646 | [6 empty] | 6495 | 4650 | 0.46 | 0 | 0 | 15.02 | 5096
TS6060#1 | GG\26\010\D | GG | 26 | 10 | D | 8 Coal Mining | 81.5 | 0 | 81.5 | 2027-12-03 12:32 | 2027-12-05 00:57 | 49275.9399 | [6 empty] | 49276 | 36925 | 3.69 | 0 | 0 | 6.55 | 5810
DRE2 | GG\28\012\B | GG | 28 | 12 | B | 6 DL | 100 | 0 | 100 | 2027-12-04 07:18 | 2027-12-07 00:28 | 213346.4615 |  |  |  |  | 213346 | 177789 |  |  | 0 | 17.82 | 0 | 11.86 | 5362.8
TS5500Shv | GG\30\013\X2 | GG | 30 | 13 | X2 | 1 Prestrip - Thick | 90.3206 | 0 | 90.3206 | 2027-12-04 16:48 | 2027-12-07 07:00 | 66670.7745 | 66671 | [7 empty] | 0 | 0 | 6.71 | 0 | 0
TS6060#1 | GG\30\014\X1 | GG | 30 | 14 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2027-12-05 00:57 | 2027-12-05 07:41 | 9124.214 | [6 empty] | 9124 | 6545 | 0.48 | 0 | 0 | 14.76 | 5116
TS6060#1 | W2\02\003\D | W2 | 2 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2027-12-05 07:41 | 2027-12-07 06:43 | 48516.381 |  |  | 48516 | [5 empty] | 0 | 0 | 0 | 5.71 | 5763.3
TS5500Exc | W2\03\005\D | W2 | 3 | 5 | D | 7 PostStrip | 47.2122 | 0 | 47.2122 | 2027-12-05 16:48 | 2027-12-07 22:09 | 47180.703 |  |  | 47181 | [5 empty] | 0 | 0 | 0 | 5.72 | 5761.63
DRE1 | SC\48\020\D | SC | 48 | 20 | D | 6 DL | 100 | 0 | 100 | 2027-12-05 20:01 | 2027-12-14 06:09 | 630744.6312 |  |  |  | 47965 | 630745 | 431688 |  |  | 0 | 40 | 0 | 7.15 | 5782.34
DRE2 | GG\28\011\B | GG | 28 | 11 | B | 6 DL | 100 | 0 | 100 | 2027-12-07 00:28 | 2027-12-10 02:18 | 241717.9763 |  |  |  |  | 241718 | 185937 |  |  | 0 | 18.61 | 0 | 11.53 | 5405.92
TS6060#1 | W2\02\003\D | W2 | 2 | 3 | D | 8 Coal Mining | 94.9 | 0 | 94.9 | 2027-12-07 06:43 | 2027-12-09 01:07 | 57393.5205 | [6 empty] | 57394 | 41912 | 4.5 | 0 | 0 | 5.71 | 5763
TS5500Shv | GG\30\014\X2 | GG | 30 | 14 | X2 | 1 Prestrip - Thick | 20.54 | 0 | 20.54 | 2027-12-07 07:00 | 2027-12-08 03:42 | 22200.0542 | 22200 | [7 empty] | 0 | 0 | 1.66 | 0 | 0
TS5500Exc | W2\02\003\D | W2 | 2 | 3 | D | 8 Coal Mining | 5.1 | 0 | 5.1 | 2027-12-07 22:09 | 2027-12-08 00:35 | 3065.8961 | [6 empty] | 3066 | 2239 | 0.24 | 0 | 0 | 5.71 | 5763
TS5500Exc | SC\47\026\D | SC | 47 | 26 | D | 7 PostStrip | 100 | 0 | 100 | 2027-12-08 00:35 | 2027-12-10 19:53 | 59530.2132 |  |  | 59530 | [5 empty] | 0 | 0 | 0 | 6.94 | 5804.21
TS5500Shv | GG\26\020\D | GG | 26 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-12-08 03:42 | 2027-12-09 17:06 | 45597.739 | [6 empty] | 45598 | 34066 | 4.41 | 0 | 0 | 6.83 | 5785
TS6060#1 | GG\26\009\D | GG | 26 | 9 | D | 8 Coal Mining | 77 | 0 | 77 | 2027-12-09 01:07 | 2027-12-10 12:01 | 47242.7063 | [6 empty] | 47243 | 35374 | 3.54 | 0 | 0 | 6.58 | 5808
TS Fleet 5 | GG\30\014\X2 | GG | 30 | 14 | X2 | 1 Prestrip - Thick | 6.0287 | 0 | 6.0287 | 2027-12-09 01:16 | 2027-12-09 04:36 | 6515.9898 | 6516 | [7 empty] | 0 | 0 | 0.49 | 0 | 0
TS Fleet 5 | W2\08\007\B | W2 | 8 | 7 | B | 1 Prestrip - Thick | 69.1645 | 69.1645 | 69.1645 | 2027-12-09 04:36 | 2027-12-23 10:09 | 669449.4321 | 669449 | [7 empty] | 0 | 0 | 32.29 | 10.1 | 5265.2
PH4100A | W2\02\007\B | W2 | 2 | 7 | B | 1 Prestrip - Thick | 100 | 81.7944 | 81.7944 | 2027-12-09 11:47 | 2027-12-29 08:20 | 824876.6811 | 824877 | [7 empty] | 0 | 0 | 41.12 | 9.93 | 5296.56
PH4100XPC#1 | GG\30\013\X2 | GG | 30 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 9.6794 | 2027-12-09 11:47 | 2027-12-09 14:57 | 7144.8945 | 7145 | [7 empty] | 0 | 0 | 0.72 | 0 | 0
PH4100XPC#1 | GG\30\013\B | GG | 30 | 13 | B | 1 Prestrip - Thick | 100 | 92.3025 | 92.3025 | 2027-12-09 14:57 | 2027-12-11 10:03 | 97568.5436 | 97569 | [7 empty] | 0 | 0 | 9.78 | 12.15 | 5319.97
TS5500Shv | GG\30\013\B | GG | 30 | 13 | B | 1 Prestrip - Thick | 7.6975 | 7.6975 | 7.6975 | 2027-12-09 17:06 | 2027-12-10 00:41 | 8136.6699 | 8137 | [7 empty] | 0 | 0 | 0.82 | 12.15 | 5319.97
TS5500Shv | GG\28\012\B | GG | 28 | 12 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-12-10 00:41 | 2027-12-11 17:09 | 49349.0567 | [6 empty] | 49349 | 35763 | 3.58 | 0 | 0 | 11.86 | 5363
DRE2 | GG\28\010\B | GG | 28 | 10 | B | 6 DL | 100 | 0 | 100 | 2027-12-10 02:18 | 2027-12-13 00:38 | 230322.4157 |  |  |  |  | 230322 | 191935 |  |  | 0 | 19.13 | 0 | 10.96 | 5455.59
TS6060#1 | W2\03\006\B | W2 | 3 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-12-10 12:01 | 2027-12-13 13:01 | 98794.8355 | [6 empty] | 98795 | 69246 | 3.46 | 0 | 0 | 10.01 | 5280
TS5500Exc | W1\06\002\D | W1 | 6 | 2 | D | 7 PostStrip | 58.2994 | 0 | 58.2994 | 2027-12-10 19:53 | 2027-12-14 18:37 | 83776.3412 |  |  | 83776 | [5 empty] | 0 | 0 | 0 | 7.64 | 5591.51
PH4100XPC#1 | GG\30\014\X2 | GG | 30 | 14 | X2 | 1 Prestrip - Thick | 100 | 0 | 73.4312 | 2027-12-11 10:03 | 2027-12-12 21:07 | 79365.948 | 79366 | [7 empty] | 0 | 0 | 5.93 | 0 | 0
TS5500Shv | GG\28\011\B | GG | 28 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-12-11 17:09 | 2027-12-13 10:01 | 49831.5004 | [6 empty] | 49832 | 36183 | 3.62 | 0 | 0 | 11.53 | 5406
PH4100XPC#1 | GG\30\014\B | GG | 30 | 14 | B | 1 Prestrip - Thick | 100 | 62.92 | 62.92 | 2027-12-12 21:07 | 2027-12-14 12:24 | 88933.559 | 88934 | [7 empty] | 0 | 0 | 6.93 | 12.71 | 5259.97
DRE2 | GG\28\009\B | GG | 28 | 9 | B | 6 DL | 100 | 0 | 100 | 2027-12-13 00:38 | 2027-12-16 01:56 | 239941.9792 |  |  |  |  | 239942 | 199952 |  |  | 0 | 19.87 | 0 | 10.52 | 5484.31
TS5500Shv | GG\30\014\B | GG | 30 | 14 | B | 1 Prestrip - Thick | 20.54 | 20.0099 | 20.0099 | 2027-12-13 10:01 | 2027-12-14 12:24 | 28282.7864 | 28283 | [7 empty] | 0 | 0 | 2.2 | 12.71 | 5259.97
TS6060#1 | GG\30\014\B | GG | 30 | 14 | B | 1 Prestrip - Thick | 100 | 17.0701 | 17.0701 | 2027-12-13 13:01 | 2027-12-14 12:24 | 24127.5866 | 24128 | [7 empty] | 0 | 0 | 1.88 | 12.71 | 5259.97
DRE1 | SC\48\021\D | SC | 48 | 21 | D | 6 DL | 100 | 0 | 100 | 2027-12-14 06:09 | 2027-12-22 15:32 | 628398.6933 |  |  |  | 47787 | 628399 | 430083 |  |  | 0 | 40 | 0 | 7.27 | 5771.12
TS5500Shv | GG\28\010\B | GG | 28 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-12-14 12:24 | 2027-12-16 05:45 | 50424.992 | [6 empty] | 50425 | 36733 | 3.68 | 0 | 0 | 10.96 | 5456
PH4100XPC#1 | W2\02\006\D | W2 | 2 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-12-14 12:24 | 2027-12-20 06:23 | 312331.2018 | 312331 | [7 empty] | 0 | 0 | 20.62 | 5.73 | 5754.86
TS6060#1 | W2\02\004\D | W2 | 2 | 4 | D | 7 PostStrip | 37.2072 | 0 | 37.2072 | 2027-12-14 12:24 | 2027-12-16 00:26 | 37171.7417 |  |  | 37172 | [5 empty] | 0 | 0 | 0 | 5.72 | 5761.71
TS5500Exc | CP\03\003\D | CP | 3 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2027-12-14 18:37 | 2027-12-23 20:52 | 193020.6212 |  |  | 193021 | [5 empty] | 0 | 0 | 0 | 6.54 | 5831.86
TS6060#1 | W2\02\004\D | W2 | 2 | 4 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2027-12-16 00:26 | 2027-12-18 02:04 | 67173.9864 | [6 empty] | 67174 | 49015 | 2.45 | 0 | 0 | 5.72 | 5762
DRE2 | GG\28\008\B | GG | 28 | 8 | B | 6 DL | 100 | 0 | 100 | 2027-12-16 01:56 | 2027-12-19 10:02 | 262251.751 |  |  |  |  | 262252 | 201732 |  |  | 0 | 20.21 | 0 | 10.48 | 5476.89
TS5500Shv | GG\28\009\B | GG | 28 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-12-16 05:45 | 2027-12-17 23:50 | 51305.5908 | [6 empty] | 51306 | 37465 | 3.74 | 0 | 0 | 10.52 | 5484
TS5500Shv | GG\28\013\B | GG | 28 | 13 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-12-17 23:50 | 2027-12-19 15:51 | 48789.9424 | [6 empty] | 48790 | 35393 | 3.55 | 0 | 0 | 12.07 | 5321
TS6060#1 | W2\02\005\D | W2 | 2 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2027-12-18 02:04 | 2027-12-22 03:01 | 100037.4472 |  |  | 100037 | [5 empty] | 0 | 0 | 0 | 5.71 | 5759.11
DRE2 | GG\28\007\B | GG | 28 | 7 | B | 6 DL | 100 | 0 | 100 | 2027-12-19 10:02 | 2027-12-22 17:12 | 259220.8918 |  |  |  |  | 259221 | 199401 |  |  | 0 | 20.11 | 0 | 10.67 | 5450.91
TS5500Shv | GG\28\008\B | GG | 28 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-12-19 15:51 | 2027-12-21 10:01 | 51420.4803 | [6 empty] | 51420 | 37528 | 3.76 | 0 | 0 | 10.48 | 5477
PH4100XPC#1 | W2\03\006\D | W2 | 3 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2027-12-20 06:23 | 2027-12-25 22:49 | 308793.863 | 308794 | [7 empty] | 0 | 0 | 20.44 | 5.74 | 5758.06
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 07:11 |  | 1d 07:11 | 2027-12-21 10:01 | 2027-12-22 17:12
TS6060#1 | GG\26\008\D | GG | 26 | 8 | D | 8 Coal Mining | 13.6 | 0 | 13.6 | 2027-12-22 03:01 | 2027-12-22 09:13 | 8387.7882 | [6 empty] | 8388 | 6281 | 0.63 | 0 | 0 | 6.57 | 5809
TS6060#1 | W2\02\005\D | W2 | 2 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2027-12-22 09:13 | 2027-12-26 03:48 | 122586.1307 | [6 empty] | 122586 | 89297 | 4.46 | 0 | 0 | 5.71 | 5759
DRE1 | SC\48\022\D | SC | 48 | 22 | D | 6 DL | 100 | 0 | 100 | 2027-12-22 15:32 | 2027-12-30 15:07 | 597837.4006 |  |  |  | 42517 | 597837 | 429895 |  |  | 0 | 39.78 | 0 | 7.37 | 5764.78
DRE2 | GG\27\013\D | GG | 27 | 13 | D | 6 DL | 100 | 100 | 100 | 2027-12-22 17:12 | 2027-12-29 00:51 | 496483.2232 |  |  |  | 11560 | 496483 | 219632 |  |  | 0 | 23.13 | 0 | 6.84 | 5783.02
TS5500Shv | GG\28\007\B | GG | 28 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2027-12-22 17:12 | 2027-12-24 10:24 | 50236.8859 | [6 empty] | 50237 | 36607 | 3.68 | 0 | 0 | 10.67 | 5451
TS Fleet 5 | W2\09\006\B | W2 | 9 | 6 | B | 1 Prestrip - Thick | 11.9427 | 11.9427 | 11.9427 | 2027-12-23 10:09 | 2027-12-25 22:57 | 119145.0228 | 119145 | [7 empty] | 0 | 0 | 5.54 | 9.98 | 5278.79
TS5500Exc | W2\02\004\D | W2 | 2 | 4 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2027-12-23 20:52 | 2027-12-25 22:30 | 62518.3636 | [6 empty] | 62518 | 45618 | 2.28 | 0 | 0 | 5.72 | 5762
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 14:27 |  | 4d 14:27 | 2027-12-24 10:24 | 2027-12-29 00:51
TS5500Exc | W2\02\006\D | W2 | 2 | 6 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2027-12-25 22:30 | 2027-12-28 02:41 | 46153.7073 |  |  | 46154 | [5 empty] | 0 | 0 | 0 | 5.73 | 5754.86
PH4100XPC#1 | W2\02\007\B | W2 | 2 | 7 | B | 1 Prestrip - Thick | 100 | 18.2056 | 18.2056 | 2027-12-25 22:49 | 2027-12-29 08:20 | 183598.9623 | 183599 | [7 empty] | 0 | 0 | 9.15 | 9.93 | 5296.56
TS Fleet 5 | W2\10\005\B | W2 | 10 | 5 | B | 1 Prestrip - Thick | 100 | 25.9703 | 25.9703 | 2027-12-25 22:57 | 2028-01-01 | 284294.5213 | 284295 | [7 empty] | 0 | 0 | 14.2 | 9.74 | 5308.75
TS6060#1 | W2\02\006\D | W2 | 2 | 6 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2027-12-26 03:48 | 2027-12-28 07:59 | 53845.9919 |  |  | 53846 | [5 empty] | 0 | 0 | 0 | 5.73 | 5754.86
TS5500Exc | W2\03\006\D | W2 | 3 | 6 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2027-12-28 02:41 | 2027-12-30 06:53 | 46164.6608 |  |  | 46165 | [5 empty] | 0 | 0 | 0 | 5.74 | 5758.06
TS6060#1 | GG\26\006\D | GG | 26 | 6 | D | 8 Coal Mining | 2.4 | 0 | 2.4 | 2027-12-28 07:59 | 2027-12-28 09:04 | 1467.3684 | [6 empty] | 1467 | 1100 | 0.11 | 0 | 0 | 6.57 | 5808
TS6060#1 | W2\02\006\D | W2 | 2 | 6 | D | 8 Coal Mining | 51.2 | 0 | 51.2 | 2027-12-28 09:04 | 2027-12-30 05:46 | 60506.9284 | [6 empty] | 60507 | 44003 | 2.2 | 0 | 0 | 5.73 | 5755
DRE2 | GG\27\012\D | GG | 27 | 12 | D | 6 DL | 100 | 48.3064 | 48.3064 | 2027-12-29 00:51 | 2028-01-01 | 232943.0244 |  |  |  | 5424 | 232943 | 103048 |  |  | 0 | 22.48 | 0 | 6.7 | 5796.94
TS5500Shv | GG\27\013\D | GG | 27 | 13 | D | 8 Coal Mining | 100 | 0 | 84.5 | 2027-12-29 00:51 | 2027-12-30 17:57 | 50125.0491 | [6 empty] | 50125 | 37412 | 3.74 | 0 | 0 | 6.84 | 5783
PH4100A | W2\03\007\B | W2 | 3 | 7 | B | 1 Prestrip - Thick | 100 | 10.5235 | 10.5235 | 2027-12-29 08:20 | 2028-01-01 | 110195.7925 | 110196 | [7 empty] | 0 | 0 | 5.52 | 10 | 5284.29
PH4100XPC#1 | W2\03\007\B | W2 | 3 | 7 | B | 1 Prestrip - Thick | 100 | 13.6845 | 13.6845 | 2027-12-29 08:20 | 2028-01-01 | 143296.0797 | 143296 | [7 empty] | 0 | 0 | 7.18 | 10 | 5284.29
TS6060#1 | W2\02\007\B | W2 | 2 | 7 | B | 8 Coal Mining | 75.4 | 0 | 16.5 | 2027-12-30 05:46 | 2027-12-30 17:57 | 16482.4717 | [6 empty] | 16482 | 11560 | 0.58 | 0 | 0 | 9.93 | 5297
TS5500Exc | W2\02\007\B | W2 | 2 | 7 | B | 8 Coal Mining | 24.6 | 0 | 14 | 2027-12-30 06:53 | 2027-12-30 17:57 | 13936.942 | [6 empty] | 13937 | 9775 | 0.49 | 0 | 0 | 9.93 | 5297
DRE1 | SC\48\023\D | SC | 48 | 23 | D | 6 DL | 100 | 0 | 20.791 | 2027-12-30 15:07 | 2028-01-01 | 102606.2847 |  |  |  | 5856 | 102606 | 77802 |  |  | 0 | 33.79 | 0 | 7.38 | 5765.32
TS6060#1 | W1\05\003\D | W1 | 5 | 3 | D | 7 PostStrip | 80.0922 | 0 | 30.7411 | 2027-12-30 17:57 | 2028-01-01 | 30997.2917 |  |  | 30997 | [5 empty] | 0 | 0 | 0 | 7.78 | 5580.98
TS5500Exc | W1\06\003\D | W1 | 6 | 3 | D | 7 PostStrip | 100 | 0 | 26.3136 | 2027-12-30 17:57 | 2028-01-01 | 26569.1072 |  |  | 26569 | [5 empty] | 0 | 0 | 0 | 7.93 | 5561.82
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 06:03 |  | 1d 06:03 | 2027-12-30 17:57 | 2028-01-01
| EOP 80 : 2027 | EOP 80 : 2027 | [7 empty] | 2028-01-01 | 2028-01-01 |  | 61193398 |  | 4073113 | 2325341 | 56016477 | 32514110 | 13000000 | 9482017 | 688.23 | 0 | 3630.49 | 8.29 | 5597.29
PH4100A | W2\03\007\B | W2 | 3 | 7 | B | 1 Prestrip - Thick | 100 | 33.7657 | 33.7657 | 2028-01-01 | 2028-01-09 12:16 | 353573.9245 | 353574 | [7 empty] | 0 | 0 | 17.71 | 10 | 5284.29
TS Fleet 5 | W2\10\005\B | W2 | 10 | 5 | B | 1 Prestrip - Thick | 100 | 74.0297 | 74.0297 | 2028-01-01 | 2028-01-18 05:28 | 810396.937 | 810397 | [7 empty] | 0 | 0 | 40.49 | 9.74 | 5308.75
DRE1 | SC\48\023\D | SC | 48 | 23 | D | 6 DL | 100 | 0 | 79.209 | 2028-01-01 | 2028-01-05 15:54 | 390905.7986 |  |  |  | 22310 | 390906 | 296406 |  |  | 0 | 33.79 | 0 | 7.38 | 5765.32
DRE2 | GG\27\012\D | GG | 27 | 12 | D | 6 DL | 100 | 51.6936 | 51.6936 | 2028-01-01 | 2028-01-04 02:06 | 249277.209 |  |  |  | 5804 | 249277 | 110274 |  |  | 0 | 22.48 | 0 | 6.7 | 5796.94
PH4100XPC#1 | W2\03\007\B | W2 | 3 | 7 | B | 1 Prestrip - Thick | 100 | 42.0263 | 42.0263 | 2028-01-01 | 2028-01-09 12:16 | 440074.5852 | 440075 | [7 empty] | 0 | 0 | 22.05 | 10 | 5284.29
TS6060#1 | W1\05\003\D | W1 | 5 | 3 | D | 7 PostStrip | 80.0922 | 0 | 49.3512 | 2028-01-01 | 2028-01-03 00:13 | 49762.539 |  |  | 49763 | [5 empty] | 0 | 0 | 0 | 7.78 | 5580.98
TS5500Exc | W1\06\003\D | W1 | 6 | 3 | D | 7 PostStrip | 100 | 0 | 73.6864 | 2028-01-01 | 2028-01-04 12:07 | 74401.951 |  |  | 74402 | [5 empty] | 0 | 0 | 0 | 7.93 | 5561.82
TS5500Shv | GG\27\013\D | GG | 27 | 13 | D | 8 Coal Mining | 100 | 0 | 15.5 | 2028-01-01 | 2028-01-01 07:33 | 9215.3365 | [6 empty] | 9215 | 6878 | 0.69 | 0 | 0 | 6.84 | 5783
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 18:33 |  | 2d 18:33 | 2028-01-01 07:33 | 2028-01-04 02:06
TS6060#1 | W2\02\007\B | W2 | 2 | 7 | B | 8 Coal Mining | 75.4 | 0 | 58.9 | 2028-01-03 00:13 | 2028-01-04 19:38 | 58754.8824 | [6 empty] | 58755 | 41207 | 2.06 | 0 | 0 | 9.93 | 5297
DRE2 | GG\27\011\D | GG | 27 | 11 | D | 6 DL | 100 | 100 | 100 | 2028-01-04 02:06 | 2028-01-10 00:27 | 478850.8214 |  |  |  | 8675 | 478851 | 208201 |  |  | 0 | 21.71 | 0 | 6.59 | 5808.4
TS5500Shv | GG\27\012\D | GG | 27 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-01-04 02:06 | 2028-01-06 03:53 | 60705.0561 | [6 empty] | 60705 | 45381 | 4.54 | 0 | 0 | 6.7 | 5797
TS5500Exc | W2\02\007\B | W2 | 2 | 7 | B | 8 Coal Mining | 24.6 | 0 | 10.6 | 2028-01-04 12:07 | 2028-01-04 20:33 | 10611.2662 | [6 empty] | 10611 | 7442 | 0.37 | 0 | 0 | 9.93 | 5297
TS6060#1 | W1\05\003\D | W1 | 5 | 3 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2028-01-04 19:38 | 2028-01-06 21:03 | 66883.6707 | [6 empty] | 66884 | 48204 | 2.41 | 0 | 0 | 7.78 | 5581
TS5500Exc | W2\02\006\D | W2 | 2 | 6 | D | 8 Coal Mining | 48.8 | 0 | 48.8 | 2028-01-04 20:33 | 2028-01-06 18:20 | 57679.0485 | [6 empty] | 57679 | 41947 | 2.1 | 0 | 0 | 5.73 | 5755
DRE1 | SC\48\024\D | SC | 48 | 24 | D | 6 DL | 100 | 0 | 100 | 2028-01-05 15:54 | 2028-01-10 23:26 | 445490.5 |  |  |  | 25425 | 445491 | 337795 |  |  | 0 | 30.98 | 0 | 7.5 | 5754.24
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 20:34 |  | 3d 20:34 | 2028-01-06 03:53 | 2028-01-10 00:27
TS5500Exc | W1\05\003\D | W1 | 5 | 3 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2028-01-06 18:20 | 2028-01-08 19:45 | 62248.1687 | [6 empty] | 62248 | 44863 | 2.25 | 0 | 0 | 7.78 | 5581
TS6060#1 | GG\26\005\D | GG | 26 | 5 | D | 8 Coal Mining | 36.8 | 0 | 36.8 | 2028-01-06 21:03 | 2028-01-07 21:52 | 33575.6641 | [6 empty] | 33576 | 25180 | 1.67 | 0 | 0 | 6.56 | 5809
TS6060#1 | GG\27\014\B | GG | 27 | 14 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2028-01-07 21:52 | 2028-01-08 14:14 | 22168.1107 | [6 empty] | 22168 | 16079 | 1.84 | 0 | 0 | 12.28 | 5290
TS6060#1 | GG\27\017\B | GG | 27 | 17 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2028-01-08 14:14 | 2028-01-09 06:15 | 21667.0765 | [6 empty] | 21667 | 15545 | 1.74 | 0 | 0 | 14.27 | 5145
TS5500Exc | W1\06\004\D | W1 | 6 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2028-01-08 19:45 | 2028-01-12 23:11 | 87936.9435 |  |  | 87937 | [5 empty] | 0 | 0 | 0 | 7.9 | 5559.82
TS6060#1 | GG\27\018\B | GG | 27 | 18 | B | 8 Coal Mining | 26.8 | 0 | 26.8 | 2028-01-09 06:15 | 2028-01-09 15:18 | 12253.0242 | [6 empty] | 12253 | 8757 | 0.88 | 0 | 0 | 14.76 | 5128
PH4100A | W2\02\008\B | W2 | 2 | 8 | B | 1 Prestrip - Thick | 100 | 68.7028 | 68.7028 | 2028-01-09 12:16 | 2028-01-28 01:04 | 784499.6731 | 784500 | [7 empty] | 0 | 0 | 41.11 | 9.92 | 5304.02
PH4100XPC#1 | W2\02\007\D | W2 | 2 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-01-09 12:16 | 2028-01-15 08:28 | 303778.1866 | 303778 | [7 empty] | 0 | 0 | 20.18 | 5.84 | 5749.33
TS6060#1 | W2\03\007\B | W2 | 3 | 7 | B | 8 Coal Mining | 47.6 | 0 | 47.6 | 2028-01-09 15:18 | 2028-01-11 02:17 | 47340.6451 | [6 empty] | 47341 | 33159 | 1.66 | 0 | 0 | 10 | 5284
DRE2 | GG\27\010\D | GG | 27 | 10 | D | 6 DL | 100 | 100 | 100 | 2028-01-10 00:27 | 2028-01-15 14:49 | 451944.4776 |  |  |  | 10523 | 451944 | 199929 |  |  | 0 | 21.05 | 0 | 6.55 | 5811.04
TS5500Shv | GG\27\011\D | GG | 27 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-01-10 00:27 | 2028-01-12 03:45 | 62540.5727 | [6 empty] | 62541 | 46829 | 4.68 | 0 | 0 | 6.59 | 5808
DRE1 | SC\48\025\D | SC | 48 | 25 | D | 6 DL | 100 | 0 | 100 | 2028-01-10 23:26 | 2028-01-14 20:28 | 324956.1653 |  |  |  | 14539 | 324956 | 276249 |  |  | 0 | 24.53 | 0 | 7.06 | 5793.31
TS6060#1 | W2\03\003\D | W2 | 3 | 3 | D | 7 PostStrip | 48.5174 | 0 | 48.5174 | 2028-01-11 02:17 | 2028-01-12 16:20 | 39254.8176 |  |  | 39255 | [5 empty] | 0 | 0 | 0 | 5.71 | 5763.07
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 11:04 |  | 3d 11:04 | 2028-01-12 03:45 | 2028-01-15 14:49
TS6060#1 | GG\27\019\B | GG | 27 | 19 | B | 8 Coal Mining | 45.4 | 0 | 45.4 | 2028-01-12 16:20 | 2028-01-13 05:59 | 18492.4076 | [6 empty] | 18492 | 13085 | 1.31 | 0 | 0 | 16.39 | 5019
TS5500Exc | W2\03\007\B | W2 | 3 | 7 | B | 8 Coal Mining | 52.4 | 0 | 52.4 | 2028-01-12 23:11 | 2028-01-14 16:29 | 52027.1256 | [6 empty] | 52027 | 36442 | 1.82 | 0 | 0 | 10 | 5284
TS6060#1 | W2\03\003\D | W2 | 3 | 3 | D | 8 Coal Mining | 40.6 | 0 | 40.6 | 2028-01-13 05:59 | 2028-01-14 05:57 | 32420.5864 | [6 empty] | 32421 | 23694 | 1.94 | 0 | 0 | 5.71 | 5763
TS6060#1 | GG\26\014\D | GG | 26 | 14 | D | 8 Coal Mining | 19.8 | 0 | 19.8 | 2028-01-14 05:57 | 2028-01-14 12:31 | 8895.4681 | [6 empty] | 8895 | 6624 | 0.89 | 0 | 0 | 6.97 | 5773
TS6060#1 | W2\03\004\D | W2 | 3 | 4 | D | 7 PostStrip | 79.8236 | 0 | 79.8236 | 2028-01-14 12:31 | 2028-01-17 17:41 | 79616.3365 |  |  | 79616 | [5 empty] | 0 | 0 | 0 | 5.71 | 5762.79
TS5500Exc | W2\03\003\D | W2 | 3 | 3 | D | 8 Coal Mining | 59.4 | 0 | 59.4 | 2028-01-14 16:29 | 2028-01-16 06:06 | 47384.3706 | [6 empty] | 47384 | 34630 | 2.84 | 0 | 0 | 5.71 | 5763
DRE1 | SC\48\026\D | SC | 48 | 26 | D | 6 DL | 100 | 0 | 100 | 2028-01-14 20:28 | 2028-01-17 19:30 | 248130.6182 |  |  |  | 8889 | 248131 | 151564 |  |  | 0 | 16.65 | 0 | 6.9 | 5807.72
PH4100XPC#1 | W2\03\007\D | W2 | 3 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-01-15 08:28 | 2028-01-21 06:39 | 308025.2315 | 308025 | [7 empty] | 0 | 0 | 20.39 | 5.83 | 5751.4
DRE2 | GG\27\009\D | GG | 27 | 9 | D | 6 DL | 100 | 100 | 100 | 2028-01-15 14:49 | 2028-01-20 23:27 | 432721.9792 |  |  |  | 10075 | 432722 | 191425 |  |  | 0 | 20.15 | 0 | 6.57 | 5808.57
TS5500Shv | GG\27\010\D | GG | 27 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-01-15 14:49 | 2028-01-17 17:28 | 61762.9432 | [6 empty] | 61763 | 46283 | 4.63 | 0 | 0 | 6.55 | 5811
TS5500Exc | W2\02\007\D | W2 | 2 | 7 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2028-01-16 06:06 | 2028-01-18 10:19 | 46177.7021 |  |  | 46178 | [5 empty] | 0 | 0 | 0 | 5.84 | 5749.33
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 06:00 |  | 3d 06:00 | 2028-01-17 17:28 | 2028-01-20 23:27
TS6060#1 | W2\02\007\D | W2 | 2 | 7 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2028-01-17 17:41 | 2028-01-19 21:54 | 53873.9858 |  |  | 53874 | [5 empty] | 0 | 0 | 0 | 5.84 | 5749.33
DRE1 | SC\49\017\D | SC | 49 | 17 | D | 6 DL | 100 | 0 | 0 | 2028-01-17 19:30 | 2028-01-17 19:30 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE1 | SC\49\018\D | SC | 49 | 18 | D | 6 DL | 100 | 0 | 100 | 2028-01-17 19:30 | 2028-01-25 12:21 | 645697.2164 |  |  |  | 49102 | 645697 | 441922 |  |  | 0 | 40 | 0 | 7.22 | 5776.93
TS Fleet 5 | W2\10\006\B | W2 | 10 | 6 | B | 1 Prestrip - Thick | 3.1497 | 3.1497 | 3.1497 | 2028-01-18 05:28 | 2028-01-18 21:02 | 30533.0049 | 30533 | [7 empty] | 0 | 0 | 1.52 | 9.94 | 5283.14
TS5500Exc | W2\03\004\D | W2 | 3 | 4 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2028-01-18 10:19 | 2028-01-20 12:16 | 62913.3907 | [6 empty] | 62913 | 45907 | 2.3 | 0 | 0 | 5.71 | 5763
TS Fleet 5 | W2\11\005\B | W2 | 11 | 5 | B | 1 Prestrip - Thick | 7.256 | 7.256 | 7.256 | 2028-01-18 21:02 | 2028-01-20 11:14 | 74851.8865 | 74852 | [7 empty] | 0 | 0 | 3.75 | 9.65 | 5321.18
TS6060#1 | W2\02\007\D | W2 | 2 | 7 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2028-01-19 21:54 | 2028-01-21 22:04 | 65197.5545 | [6 empty] | 65198 | 47386 | 2.37 | 0 | 0 | 5.84 | 5749
TS Fleet 5 | W2\12\005\B | W2 | 12 | 5 | B | 1 Prestrip - Thick | 78.5788 | 78.5788 | 78.5788 | 2028-01-20 11:14 | 2028-02-07 13:24 | 850990.9087 | 850991 | [7 empty] | 0 | 0 | 39.85 | 9.76 | 5323.19
TS5500Exc | W2\02\007\D | W2 | 2 | 7 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2028-01-20 12:16 | 2028-01-22 12:27 | 60678.9121 | [6 empty] | 60679 | 44101 | 2.2 | 0 | 0 | 5.84 | 5749
DRE2 | GG\27\008\D | GG | 27 | 8 | D | 6 DL | 100 | 100 | 100 | 2028-01-20 23:27 | 2028-01-26 05:56 | 425464.7999 |  |  |  | 7923 | 425465 | 190152 |  |  | 0 | 19.81 | 0 | 6.57 | 5809.24
TS5500Shv | GG\27\009\D | GG | 27 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-01-20 23:27 | 2028-01-23 01:40 | 61229.1352 | [6 empty] | 61229 | 45883 | 4.59 | 0 | 0 | 6.57 | 5809
PH4100XPC#1 | W2\02\008\B | W2 | 2 | 8 | B | 1 Prestrip - Thick | 100 | 31.2972 | 31.2972 | 2028-01-21 06:39 | 2028-01-28 01:04 | 357374.6519 | 357375 | [7 empty] | 0 | 0 | 18.73 | 9.92 | 5304.02
TS6060#1 | W2\03\004\D | W2 | 3 | 4 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2028-01-21 22:04 | 2028-01-24 00:01 | 67598.4304 | [6 empty] | 67598 | 49325 | 2.47 | 0 | 0 | 5.71 | 5763
TS5500Exc | W2\03\007\D | W2 | 3 | 7 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2028-01-22 12:27 | 2028-01-24 16:40 | 46185.9397 |  |  | 46186 | [5 empty] | 0 | 0 | 0 | 5.83 | 5751.4
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 00:34 |  | 1d 00:34 | 2028-01-23 01:40 | 2028-01-24 02:14
TS6060#1 | GG\26\017\D | GG | 26 | 17 | D | 8 Coal Mining | 6.3 | 0 | 6.3 | 2028-01-24 00:01 | 2028-01-24 02:14 | 3005.954 | [6 empty] | 3006 | 2238 | 0.29 | 0 | 0 | 7.02 | 5770
TS6060#1 | W2\03\005\D | W2 | 3 | 5 | D | 7 PostStrip | 52.7878 | 0 | 52.7878 | 2028-01-24 02:14 | 2028-01-26 05:22 | 52752.4856 |  |  | 52752 | [5 empty] | 0 | 0 | 0 | 5.72 | 5761.63
TS5500Shv | GG\31\009\X1 | GG | 31 | 9 | X1 | 1 Prestrip - Thick | 5.2042 | 5.2042 | 5.2042 | 2028-01-24 02:14 | 2028-01-25 15:45 | 40087.4411 | 40087 | [7 empty] | 0 | 0 | 4.96 | 13.97 | 5162.47
TS5500Exc | SC\47\025\D | SC | 47 | 25 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-01-24 16:40 | 2028-01-27 05:21 | 76444.8088 | [6 empty] | 76445 | 57543 | 4.8 | 0 | 0 | 7.24 | 5777
DRE1 | SC\49\019\D | SC | 49 | 19 | D | 6 DL | 100 | 0 | 100 | 2028-01-25 12:21 | 2028-02-02 00:16 | 628491.652 |  |  |  | 47794 | 628492 | 430146 |  |  | 0 | 40 | 0 | 7.15 | 5783.1
TS5500Shv | GG\31\018\B | GG | 31 | 18 | B | 1 Prestrip - Thick | 20.8724 | 20.8724 | 20.8724 | 2028-01-25 15:45 | 2028-01-28 11:12 | 71754.7939 | 71755 | [7 empty] | 0 | 0 | 7.45 | 17.81 | 4899.54
TS6060#1 | W2\03\005\D | W2 | 3 | 5 | D | 8 Coal Mining | 40.6 | 0 | 40.6 | 2028-01-26 05:22 | 2028-01-27 20:10 | 52509.5452 | [6 empty] | 52510 | 38255 | 1.91 | 0 | 0 | 5.72 | 5762
DRE2 | GG\27\007\D | GG | 27 | 7 | D | 6 DL | 100 | 100 | 100 | 2028-01-26 05:56 | 2028-01-31 13:18 | 428422.4629 |  |  |  | 7978 | 428422 | 191474 |  |  | 0 | 19.95 | 0 | 6.55 | 5810.13
TS5500Exc | W2\03\005\D | W2 | 3 | 5 | D | 8 Coal Mining | 30.3 | 0 | 30.3 | 2028-01-27 05:21 | 2028-01-28 12:30 | 39232.2511 | [6 empty] | 39232 | 28582 | 1.43 | 0 | 0 | 5.72 | 5762
TS6060#1 | W2\03\006\D | W2 | 3 | 6 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2028-01-27 20:10 | 2028-01-30 00:22 | 53858.7709 |  |  | 53859 | [5 empty] | 0 | 0 | 0 | 5.74 | 5758.06
PH4100A | W2\03\008\B | W2 | 3 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-01-28 01:04 | 2028-02-24 08:17 | 1166449.778 | 1166450 | [7 empty] | 0 | 0 | 63.07 | 9.99 | 5289.9
PH4100XPC#1 | GG\31\008\X1 | GG | 31 | 8 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-01-28 01:04 | 2028-01-28 01:04 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\31\008\B | GG | 31 | 8 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-01-28 01:04 | 2028-01-28 01:04 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\31\009\X1 | GG | 31 | 9 | X1 | 1 Prestrip - Thick | 100 | 87.1803 | 84.1794 | 2028-01-28 01:04 | 2028-02-09 07:08 | 648428.719 | 648429 | [7 empty] | 0 | 0 | 80.29 | 13.97 | 5162.47
TS5500Shv | GG\27\008\D | GG | 27 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-01-28 11:12 | 2028-01-30 13:42 | 61586.6956 | [6 empty] | 61587 | 46114 | 4.61 | 0 | 0 | 6.57 | 5809
TS5500Exc | W2\02\008\B | W2 | 2 | 8 | B | 8 Coal Mining | 12.1 | 0 | 12.1 | 2028-01-28 12:30 | 2028-01-28 22:12 | 12217.536 | [6 empty] | 12218 | 8569 | 0.43 | 0 | 0 | 9.92 | 5304
TS5500Exc | SC\47\026\D | SC | 47 | 26 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-01-28 22:12 | 2028-01-31 11:35 | 77323.6967 | [6 empty] | 77324 | 58529 | 4.88 | 0 | 0 | 6.94 | 5804
TS6060#1 | W2\02\008\B | W2 | 2 | 8 | B | 8 Coal Mining | 87.9 | 0 | 87.9 | 2028-01-30 00:22 | 2028-02-01 17:45 | 88507.4059 | [6 empty] | 88507 | 62076 | 3.1 | 0 | 0 | 9.92 | 5304
TS5500Shv | GG\31\019\B | GG | 31 | 19 | B | 1 Prestrip - Thick | 5.2666 | 5.2666 | 5.2666 | 2028-01-30 13:42 | 2028-01-31 03:37 | 14914.8535 | 14915 | [7 empty] | 0 | 0 | 1.48 | 20.94 | 4663.05
TS5500Shv | GG\31\020\D | GG | 31 | 20 | D | 1 Prestrip - Thick | 20.7621 | 20.7621 | 20.7621 | 2028-01-31 03:37 | 2028-01-31 22:01 | 19756.5629 | 19757 | [7 empty] | 0 | 0 | 1.98 | 6.75 | 5792.49
TS5500Exc | SC\48\018\D | SC | 48 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-01-31 11:35 | 2028-02-02 20:08 | 71226.9561 | [6 empty] | 71227 | 53230 | 4.44 | 0 | 0 | 7.17 | 5781
DRE2 | GG\27\006\D | GG | 27 | 6 | D | 6 DL | 100 | 100 | 100 | 2028-01-31 13:18 | 2028-02-06 16:09 | 493968.187 |  |  |  | 11501 | 493968 | 218519 |  |  | 0 | 20.04 | 0 | 6.54 | 5810.93
TS5500Shv | GG\27\007\D | GG | 27 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-01-31 22:01 | 2028-02-03 00:10 | 61139.3598 | [6 empty] | 61139 | 45816 | 4.58 | 0 | 0 | 6.55 | 5810
TS6060#1 | W2\03\007\D | W2 | 3 | 7 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2028-02-01 17:45 | 2028-02-03 21:59 | 53883.5963 |  |  | 53884 | [5 empty] | 0 | 0 | 0 | 5.83 | 5751.4
DRE1 | SC\49\020\D | SC | 49 | 20 | D | 6 DL | 100 | 0 | 100 | 2028-02-02 00:16 | 2028-02-09 13:22 | 632604.1515 |  |  |  | 48107 | 632604 | 432961 |  |  | 0 | 40 | 0 | 7.21 | 5777.44
TS5500Exc | SC\48\019\D | SC | 48 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-02-02 20:08 | 2028-02-05 04:43 | 71261.2232 | [6 empty] | 71261 | 53298 | 4.44 | 0 | 0 | 7.09 | 5789
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 16:00 |  | 3d 16:00 | 2028-02-03 00:10 | 2028-02-06 16:09
TS6060#1 | W1\06\002\D | W1 | 6 | 2 | D | 7 PostStrip | 41.7006 | 0 | 41.7006 | 2028-02-03 21:59 | 2028-02-06 08:03 | 59923.9571 |  |  | 59924 | [5 empty] | 0 | 0 | 0 | 7.64 | 5591.51
TS5500Exc | SC\48\020\D | SC | 48 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-02-05 04:43 | 2028-02-07 11:46 | 69340.4946 | [6 empty] | 69340 | 51902 | 4.32 | 0 | 0 | 7.15 | 5782
TS6060#1 | CP\03\004\B | CP | 3 | 4 | B | 8 Coal Mining | 76.4 | 0 | 76.4 | 2028-02-06 08:03 | 2028-02-14 05:55 | 256956.862 | [6 empty] | 256957 | 184306 | 3.43 | 0 | 0 | 8.84 | 5585
DRE2 | GG\28\014\B | GG | 28 | 14 | B | 6 DL | 100 | 0 | 100 | 2028-02-06 16:09 | 2028-02-09 01:20 | 192310.9751 |  |  |  |  | 192311 | 160259 |  |  | 0 | 16.37 | 0 | 12.16 | 5299.19
TS5500Shv | GG\27\006\D | GG | 27 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-02-06 16:09 | 2028-02-09 01:16 | 69637.5907 | [6 empty] | 69638 | 52225 | 4.55 | 0 | 0 | 6.54 | 5811
TS5500Exc | SC\48\021\D | SC | 48 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-02-07 11:46 | 2028-02-09 17:31 | 67704.9103 | [6 empty] | 67705 | 50676 | 4.22 | 0 | 0 | 7.27 | 5771
TS Fleet 5 | GG\31\009\X1 | GG | 31 | 9 | X1 | 1 Prestrip - Thick | 5.6684 | 0 | 5.6684 | 2028-02-07 13:24 | 2028-02-08 11:41 | 43663.02 | 43663 | [7 empty] | 0 | 0 | 5.41 | 13.97 | 5162.47
TS Fleet 5 | GG\31\009\X1 | GG | 31 | 9 | X1 | 1 Prestrip - Thick | 33.4162 | 7.6155 | 4.9481 | 2028-02-08 11:41 | 2028-02-09 07:08 | 38114.6423 | 38115 | [7 empty] | 0 | 0 | 4.72 | 13.97 | 5162.47
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 00:04 |  | 0d 00:04 | 2028-02-09 01:16 | 2028-02-09 01:20
DRE2 | GG\28\017\B | GG | 28 | 17 | B | 6 DL | 100 | 0 | 100 | 2028-02-09 01:20 | 2028-02-11 10:05 | 190942.4553 |  |  |  |  | 190942 | 159119 |  |  | 0 | 15.83 | 0 | 14.44 | 5130.79
TS5500Shv | GG\28\014\B | GG | 28 | 14 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-02-09 01:20 | 2028-02-10 14:58 | 45900.4921 | [6 empty] | 45900 | 33317 | 3.5 | 0 | 0 | 12.16 | 5299
PH4100XPC#1 | GG\31\010\X1 | GG | 31 | 10 | X1 | 1 Prestrip - Thick | 100 | 53.4073 | 53.4073 | 2028-02-09 07:08 | 2028-02-16 23:56 | 397907.6516 | 397908 | [7 empty] | 0 | 0 | 41.92 | 14.23 | 5152.96
TS Fleet 5 | GG\31\010\X1 | GG | 31 | 10 | X1 | 1 Prestrip - Thick | 46.5927 | 46.5927 | 46.5927 | 2028-02-09 07:08 | 2028-02-16 16:14 | 347135.3364 | 347135 | [7 empty] | 0 | 0 | 36.57 | 14.23 | 5152.96
DRE1 | SC\49\021\D | SC | 49 | 21 | D | 6 DL | 100 | 0 | 100 | 2028-02-09 13:22 | 2028-02-17 01:06 | 627853.6965 |  |  |  | 47746 | 627854 | 429710 |  |  | 0 | 40 | 0 | 7.28 | 5770.08
TS5500Exc | SC\48\022\D | SC | 48 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-02-09 17:31 | 2028-02-12 02:41 | 72012.4425 | [6 empty] | 72012 | 53861 | 4.49 | 0 | 0 | 7.37 | 5765
TS5500Shv | GG\31\009\X1 | GG | 31 | 9 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2028-02-10 14:58 | 2028-02-11 05:42 | 17961.8654 | [6 empty] | 17962 | 12935 | 1.29 | 0 | 0 | 13.97 | 5162
TS5500Shv | GG\31\009\X2 | GG | 31 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2028-02-11 05:42 | 2028-02-13 21:29 | 68371.027 | 68371 | [7 empty] | 0 | 0 | 6.82 | 0 | 0
DRE2 | GG\28\018\B | GG | 28 | 18 | B | 6 DL | 100 | 0 | 100 | 2028-02-11 10:05 | 2028-02-13 19:23 | 192724.9309 |  |  |  |  | 192725 | 160604 |  |  | 0 | 16.17 | 0 | 15.47 | 5073.72
TS5500Exc | SC\48\023\D | SC | 48 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-02-12 02:41 | 2028-02-14 15:42 | 76852.0204 | [6 empty] | 76852 | 57575 | 4.8 | 0 | 0 | 7.38 | 5765
DRE2 | GG\28\019\B | GG | 28 | 19 | B | 6 DL | 100 | 0 | 100 | 2028-02-13 19:23 | 2028-02-16 03:33 | 188943.352 |  |  |  |  | 188943 | 157453 |  |  | 0 | 16.55 | 0 | 17.37 | 4942.41
TS5500Shv | GG\31\009\B | GG | 31 | 9 | B | 1 Prestrip - Thick | 27.1427 | 27.1427 | 27.1427 | 2028-02-13 21:29 | 2028-02-14 16:48 | 20707.0362 | 20707 | [7 empty] | 0 | 0 | 2.08 | 10.66 | 5471.26
TS6060#1 | CP\03\005\B | CP | 3 | 5 | B | 1 Prestrip - Thick | 56.0036 | 56.0036 | 56.0036 | 2028-02-14 05:55 | 2028-05-28 03:34 | 2561063.821 | 2561064 | [7 empty] | 0 | 0 | 26.28 | 8.68 | 5597.69
TS5500Exc | SC\48\024\D | SC | 48 | 24 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-02-14 15:42 | 2028-02-17 03:42 | 75579.6428 | [6 empty] | 75580 | 56711 | 4.72 | 0 | 0 | 7.5 | 5754
TS5500Shv | GG\28\017\B | GG | 28 | 17 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-02-14 16:48 | 2028-02-16 05:42 | 45003.5084 | [6 empty] | 45004 | 32252 | 3.28 | 0 | 0 | 14.44 | 5131
DRE2 | GG\28\020\B | GG | 28 | 20 | B | 6 DL | 100 | 0 | 100 | 2028-02-16 03:33 | 2028-02-18 01:43 | 155256.7618 |  |  |  |  | 155257 | 119428 |  |  | 0 | 17.78 | 0 | 0 | 0
TS5500Shv | GG\28\018\B | GG | 28 | 18 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-02-16 05:42 | 2028-02-17 17:36 | 43777.0122 | [6 empty] | 43777 | 31149 | 3.11 | 0 | 0 | 15.47 | 5074
TS Fleet 5 | GG\31\009\B | GG | 31 | 9 | B | 1 Prestrip - Thick | 33.8341 | 33.8341 | 33.8341 | 2028-02-16 16:14 | 2028-02-17 05:25 | 25811.8875 | 25812 | [7 empty] | 0 | 0 | 2.59 | 10.66 | 5471.26
PH4100XPC#1 | GG\31\009\B | GG | 31 | 9 | B | 1 Prestrip - Thick | 100 | 39.0233 | 39.0233 | 2028-02-16 23:56 | 2028-02-17 13:40 | 29770.7137 | 29771 | [7 empty] | 0 | 0 | 2.99 | 10.66 | 5471.26
DRE1 | SC\49\022\D | SC | 49 | 22 | D | 6 DL | 100 | 0 | 100 | 2028-02-17 01:06 | 2028-02-23 19:38 | 567753.9968 |  |  |  | 40378 | 567754 | 408262 |  |  | 0 | 37.68 | 0 | 7.35 | 5766.21
TS5500Exc | CP\03\003\D | CP | 3 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-02-17 03:42 | 2028-02-26 06:47 | 275958.7314 | [6 empty] | 275959 | 196571 | 5.11 | 0 | 0 | 6.54 | 5832
TS Fleet 5 | GG\31\011\X1 | GG | 31 | 11 | X1 | 1 Prestrip - Thick | 46.6213 | 46.6213 | 46.6213 | 2028-02-17 05:25 | 2028-02-23 22:41 | 316087.5578 | 316088 | [7 empty] | 0 | 0 | 29.97 | 14.4 | 5144.82
PH4100XPC#1 | GG\31\011\X1 | GG | 31 | 11 | X1 | 1 Prestrip - Thick | 100 | 53.3787 | 53.3787 | 2028-02-17 13:40 | 2028-02-24 13:57 | 361902.3484 | 361902 | [7 empty] | 0 | 0 | 34.31 | 14.4 | 5144.82
TS5500Shv | GG\31\010\X1 | GG | 31 | 10 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2028-02-17 17:36 | 2028-02-18 07:53 | 17413.9928 | [6 empty] | 17414 | 12510 | 1.25 | 0 | 0 | 14.23 | 5153
DRE2 | GG\27\014\D | GG | 27 | 14 | D | 6 DL | 100 | 100 | 100 | 2028-02-18 01:43 | 2028-02-23 07:24 | 422788.0456 |  |  |  | 9844 | 422788 | 187031 |  |  | 0 | 23.65 | 0 | 6.93 | 5774.51
TS5500Shv | GG\31\010\X2 | GG | 31 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2028-02-18 07:53 | 2028-02-21 00:56 | 69740.262 | 69740 | [7 empty] | 0 | 0 | 7 | 0 | 0
TS5500Shv | GG\31\010\B | GG | 31 | 10 | B | 1 Prestrip - Thick | 66.2529 | 66.2529 | 66.2529 | 2028-02-21 00:56 | 2028-02-22 21:47 | 48081.8419 | 48082 | [7 empty] | 0 | 0 | 4.8 | 11.04 | 5445.71
TS5500Shv | GG\28\019\B | GG | 28 | 19 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-02-22 21:47 | 2028-02-24 05:06 | 38170.1952 | [6 empty] | 38170 | 26876 | 2.69 | 0 | 0 | 17.37 | 4942
DRE2 | GG\27\017\D | GG | 27 | 17 | D | 6 DL | 100 | 100 | 100 | 2028-02-23 07:24 | 2028-02-28 18:21 | 440465.6424 |  |  |  | 10255 | 440466 | 194851 |  |  | 0 | 24.1 | 0 | 6.99 | 5772.84
DRE1 | SC\49\023\D | SC | 49 | 23 | D | 6 DL | 100 | 0 | 100 | 2028-02-23 19:38 | 2028-02-29 09:51 | 468806.5626 |  |  |  | 26756 | 468807 | 355475 |  |  | 0 | 32.1 | 0 | 7.31 | 5771.08
TS Fleet 5 | GG\31\010\B | GG | 31 | 10 | B | 1 Prestrip - Thick | 15.6717 | 15.6717 | 15.6717 | 2028-02-23 22:41 | 2028-02-24 04:29 | 11373.491 | 11373 | [7 empty] | 0 | 0 | 1.14 | 11.04 | 5445.71
TS Fleet 5 | GG\31\012\X1 | GG | 31 | 12 | X1 | 1 Prestrip - Thick | 46.6189 | 46.6189 | 46.6189 | 2028-02-24 04:29 | 2028-03-01 02:10 | 277693.1334 | 277693 | [7 empty] | 0 | 0 | 25.76 | 14.55 | 5133.44
TS5500Shv | GG\27\014\D | GG | 27 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-02-24 05:06 | 2028-02-25 20:52 | 48508.3584 | [6 empty] | 48508 | 36147 | 4.38 | 0 | 0 | 6.93 | 5775
PH4100A | SC\48\017\D | SC | 48 | 17 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-02-24 08:17 | 2028-02-24 08:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\49\017\D | SC | 49 | 17 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-02-24 08:17 | 2028-02-24 08:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | W2\06\003\D | W2 | 6 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-02-24 08:17 | 2028-03-03 05:28 | 328427.2186 | 328427 | [7 empty] | 0 | 0 | 20.31 | 5.77 | 5760.59
PH4100XPC#1 | GG\31\010\B | GG | 31 | 10 | B | 1 Prestrip - Thick | 100 | 18.0754 | 18.0754 | 2028-02-24 13:57 | 2028-02-24 20:00 | 13117.8684 | 13118 | [7 empty] | 0 | 0 | 1.31 | 11.04 | 5445.71
PH4100XPC#1 | GG\31\012\X1 | GG | 31 | 12 | X1 | 1 Prestrip - Thick | 100 | 53.3811 | 53.3811 | 2028-02-24 20:00 | 2028-03-01 23:50 | 317973.187 | 317973 | [7 empty] | 0 | 0 | 29.49 | 14.55 | 5133.44
TS5500Shv | GG\31\011\X1 | GG | 31 | 11 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2028-02-25 20:52 | 2028-02-26 10:04 | 16090.2404 | [6 empty] | 16090 | 11548 | 1.16 | 0 | 0 | 14.4 | 5145
TS5500Exc | W2\03\008\B | W2 | 3 | 8 | B | 8 Coal Mining | 50.4 | 0 | 50.4 | 2028-02-26 06:47 | 2028-02-27 22:40 | 50231.7396 | [6 empty] | 50232 | 35181 | 1.76 | 0 | 0 | 9.99 | 5290
TS5500Shv | GG\31\011\X2 | GG | 31 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2028-02-26 10:04 | 2028-02-29 03:52 | 70531.789 | 70532 | [7 empty] | 0 | 0 | 7.09 | 0 | 0
TS5500Exc | SC\48\025\D | SC | 48 | 25 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-02-27 22:40 | 2028-03-01 11:19 | 76393.6417 | [6 empty] | 76394 | 57505 | 4.79 | 0 | 0 | 7.06 | 5793
DRE2 | GG\27\018\D | GG | 27 | 18 | D | 6 DL | 100 | 100 | 100 | 2028-02-28 18:21 | 2028-03-06 01:50 | 509554.6659 |  |  |  | 11864 | 509555 | 225414 |  |  | 0 | 23.72 | 0 | 6.97 | 5774.12
TS5500Shv | GG\27\017\D | GG | 27 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-02-29 03:52 | 2028-03-01 22:55 | 52505.2045 | [6 empty] | 52505 | 39097 | 4.63 | 0 | 0 | 6.99 | 5773
DRE1 | SC\49\024\D | SC | 49 | 24 | D | 6 DL | 100 | 0 | 100 | 2028-02-29 09:51 | 2028-03-05 04:55 | 401942.6692 |  |  |  | 20665 | 401943 | 323758 |  |  | 0 | 28.75 | 0 | 7.37 | 5766.1
TS Fleet 5 | GG\31\011\A | GG | 31 | 11 | A | 1 Prestrip - Thick | 46.4388 | 0 | 46.4388 | 2028-03-01 02:10 | 2028-03-01 20:11 | 35314.9451 | 35315 | [7 empty] | 0 | 0 | 3.54 | 0 | 0
TS5500Exc | W1\06\002\D | W1 | 6 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-03-01 11:19 | 2028-03-07 07:55 | 177114.0015 | [6 empty] | 177114 | 127637 | 4.53 | 0 | 0 | 7.64 | 5592
TS Fleet 5 | GG\31\013\X1 | GG | 31 | 13 | X1 | 1 Prestrip - Thick | 46.6518 | 46.6518 | 46.6518 | 2028-03-01 20:11 | 2028-03-06 18:27 | 231799.5179 | 231800 | [7 empty] | 0 | 0 | 19.31 | 14.61 | 5127.99
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 00:55 |  | 0d 00:55 | 2028-03-01 22:55 | 2028-03-01 23:50
PH4100XPC#1 | GG\31\011\A | GG | 31 | 11 | A | 1 Prestrip - Thick | 100 | 0 | 53.5612 | 2028-03-01 23:50 | 2028-03-02 18:38 | 40731.2761 | 40731 | [7 empty] | 0 | 0 | 4.08 | 0 | 0
TS5500Shv | GG\31\012\X1 | GG | 31 | 12 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2028-03-01 23:50 | 2028-03-02 12:02 | 14868.6142 | [6 empty] | 14869 | 10668 | 1.07 | 0 | 0 | 14.55 | 5133
TS5500Shv | GG\31\012\X2 | GG | 31 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 62.9266 | 2028-03-02 12:02 | 2028-03-04 06:14 | 45234.5202 | 45235 | [7 empty] | 0 | 0 | 4.55 | 0 | 0
PH4100XPC#1 | GG\31\011\B | GG | 31 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-03-02 18:38 | 2028-03-03 17:55 | 50454.7591 | 50455 | [7 empty] | 0 | 0 | 5.04 | 11.69 | 5392.03
PH4100A | W2\07\003\B | W2 | 7 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-03-03 05:28 | 2028-04-22 19:58 | 2142581.673 | 2142582 | [7 empty] | 0 | 0 | 73.66 | 9.59 | 5320.63
PH4100XPC#1 | GG\31\012\X2 | GG | 31 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 37.0734 | 2028-03-03 17:55 | 2028-03-04 06:14 | 26650.0458 | 26650 | [7 empty] | 0 | 0 | 2.68 | 0 | 0
PH4100XPC#1 | GG\31\012\A | GG | 31 | 12 | A | 1 Prestrip - Thick | 100 | 0 | 100 | 2028-03-04 06:14 | 2028-03-05 21:26 | 84961.304 | 84961 | [7 empty] | 0 | 0 | 8.52 | 0 | 0
TS5500Shv | GG\31\011\B | GG | 31 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-03-04 06:14 | 2028-03-06 00:06 | 51052.6358 | [6 empty] | 51053 | 36959 | 3.7 | 0 | 0 | 11.69 | 5392
DRE1 | SC\49\025\D | SC | 49 | 25 | D | 6 DL | 100 | 0 | 100 | 2028-03-05 04:55 | 2028-03-09 04:38 | 334333.8773 |  |  |  | 14959 | 334334 | 284221 |  |  | 0 | 24.64 | 0 | 6.87 | 5809.74
PH4100XPC#1 | GG\31\012\B | GG | 31 | 12 | B | 1 Prestrip - Thick | 100 | 96.7039 | 96.7039 | 2028-03-05 21:26 | 2028-03-06 19:16 | 47285.0355 | 47285 | [7 empty] | 0 | 0 | 4.73 | 12.18 | 5340.84
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 01:44 |  | 0d 01:44 | 2028-03-06 00:06 | 2028-03-06 01:50
DRE2 | GG\27\019\D | GG | 27 | 19 | D | 6 DL | 100 | 100 | 100 | 2028-03-06 01:50 | 2028-03-12 06:44 | 500872.8971 |  |  |  | 11662 | 500873 | 221574 |  |  | 0 | 23.31 | 0 | 6.91 | 5780.2
TS5500Shv | GG\27\018\D | GG | 27 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-03-06 01:50 | 2028-03-08 04:57 | 62334.4058 | [6 empty] | 62334 | 46453 | 4.65 | 0 | 0 | 6.97 | 5774
TS Fleet 5 | GG\31\012\B | GG | 31 | 12 | B | 1 Prestrip - Thick | 46.4388 | 3.2961 | 3.2961 | 2028-03-06 18:27 | 2028-03-06 19:16 | 1611.7042 | 1612 | [7 empty] | 0 | 0 | 0.16 | 12.18 | 5340.84
TS Fleet 5 | GG\31\014\X1 | GG | 31 | 14 | X1 | 1 Prestrip - Thick | 47.0307 | 47.0307 | 47.0307 | 2028-03-06 19:16 | 2028-03-12 14:25 | 272723.9022 | 272724 | [7 empty] | 0 | 0 | 16.45 | 14.7 | 5119.65
PH4100XPC#1 | GG\31\013\X1 | GG | 31 | 13 | X1 | 1 Prestrip - Thick | 100 | 53.3482 | 53.3482 | 2028-03-06 19:16 | 2028-03-11 22:40 | 265072.0415 | 265072 | [7 empty] | 0 | 0 | 22.09 | 14.61 | 5127.99
TS5500Exc | SC\49\018\D | SC | 49 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-03-07 07:55 | 2028-03-09 16:28 | 71216.8437 | [6 empty] | 71217 | 53223 | 4.44 | 0 | 0 | 7.22 | 5777
TS5500Shv | GG\31\012\B | GG | 31 | 12 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-03-08 04:57 | 2028-03-09 22:24 | 50540.5966 | [6 empty] | 50541 | 36488 | 3.66 | 0 | 0 | 12.18 | 5341
DRE1 | SC\49\026\D | SC | 49 | 26 | D | 6 DL | 100 | 0 | 100 | 2028-03-09 04:38 | 2028-03-13 08:05 | 347440.325 |  |  |  | 13787 | 347440 | 199868 |  |  | 0 | 20.66 | 0 | 6.86 | 5811.36
TS5500Exc | SC\49\019\D | SC | 49 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-03-09 16:28 | 2028-03-12 00:39 | 70785.9983 | [6 empty] | 70786 | 52900 | 4.41 | 0 | 0 | 7.15 | 5783
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 00:16 |  | 2d 00:16 | 2028-03-09 22:24 | 2028-03-11 22:40
PH4100XPC#1 | GG\31\014\X1 | GG | 31 | 14 | X1 | 1 Prestrip - Thick | 100 | 52.9693 | 52.9693 | 2028-03-11 22:40 | 2028-03-17 23:51 | 307161.0361 | 307161 | [7 empty] | 0 | 0 | 18.53 | 14.7 | 5119.65
TS5500Shv | GG\31\013\X1 | GG | 31 | 13 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2028-03-11 22:40 | 2028-03-12 10:08 | 13984.1129 | [6 empty] | 13984 | 10032 | 1.01 | 0 | 0 | 14.61 | 5128
TS5500Exc | W1\06\003\D | W1 | 6 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-03-12 00:39 | 2028-03-15 21:46 | 117271.1581 | [6 empty] | 117271 | 84492 | 4.23 | 0 | 0 | 7.93 | 5562
DRE2 | GG\27\020\D | GG | 27 | 20 | D | 6 DL | 100 | 100 | 100 | 2028-03-12 06:44 | 2028-03-18 01:32 | 466908.2892 |  |  |  | 7287 | 466908 | 133638 |  |  | 0 | 22.08 | 0 | 6.81 | 5786
TS5500Shv | GG\27\019\D | GG | 27 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-03-12 10:08 | 2028-03-14 13:15 | 62319.1481 | [6 empty] | 62319 | 46515 | 4.65 | 0 | 0 | 6.91 | 5780
TS Fleet 5 | GG\31\013\X2 | GG | 31 | 13 | X2 | 1 Prestrip - Thick | 46.4388 | 0 | 46.4388 | 2028-03-12 14:25 | 2028-03-13 08:02 | 34545.9651 | 34546 | [7 empty] | 0 | 0 | 3.48 | 0 | 0
TS Fleet 5 | GG\31\017\X2 | GG | 31 | 17 | X2 | 1 Prestrip - Thick | 47.725 | 0 | 47.725 | 2028-03-13 08:02 | 2028-03-16 10:27 | 145835.9682 | 145836 | [7 empty] | 0 | 0 | 15.13 | 0 | 0
DRE1 | End of Schedule | End of Schedule | [7 empty] | 2028-03-13 08:05 | 2028-03-13 08:05
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 10:37 |  | 3d 10:37 | 2028-03-14 13:15 | 2028-03-17 23:51
TS5500Exc | W1\06\004\D | W1 | 6 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-03-15 21:46 | 2028-03-19 02:18 | 96414.1742 | [6 empty] | 96414 | 69397 | 3.97 | 0 | 0 | 7.9 | 5560
TS Fleet 5 | GG\31\018\B | GG | 31 | 18 | B | 1 Prestrip - Thick | 36.8559 | 36.8559 | 36.8559 | 2028-03-16 10:27 | 2028-03-19 03:05 | 126702.6125 | 126703 | [7 empty] | 0 | 0 | 13.15 | 17.81 | 4899.54
PH4100XPC#1 | GG\31\013\X2 | GG | 31 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.5612 | 2028-03-17 23:51 | 2028-03-18 18:15 | 39844.3559 | 39844 | [7 empty] | 0 | 0 | 4.01 | 0 | 0
TS5500Shv | GG\31\014\X1 | GG | 31 | 14 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2028-03-17 23:51 | 2028-03-18 15:56 | 19605.5084 | [6 empty] | 19606 | 14067 | 0.93 | 0 | 0 | 14.7 | 5120
DRE2 | GG\29\013\B | GG | 29 | 13 | B | 6 DL | 100 | 0 | 100 | 2028-03-18 01:32 | 2028-03-20 15:08 | 207192.8971 |  |  |  |  | 207193 | 172661 |  |  | 0 | 17.3 | 0 | 12.12 | 5318.79
TS5500Shv | GG\31\014\X2 | GG | 31 | 14 | X2 | 1 Prestrip - Thick | 45.3479 | 0 | 42.5606 | 2028-03-18 15:56 | 2028-03-20 16:50 | 52422.8792 | 52423 | [7 empty] | 0 | 0 | 3.51 | 0 | 0
PH4100XPC#1 | GG\31\013\B | GG | 31 | 13 | B | 1 Prestrip - Thick | 100 | 61.6251 | 61.6251 | 2028-03-18 18:15 | 2028-03-19 22:37 | 61446.8848 | 61447 | [7 empty] | 0 | 0 | 6.16 | 12.17 | 5322.94
TS5500Exc | SC\49\020\D | SC | 49 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-03-19 02:18 | 2028-03-21 08:54 | 68767.7495 | [6 empty] | 68768 | 51432 | 4.29 | 0 | 0 | 7.21 | 5777
TS Fleet 5 | GG\31\013\B | GG | 31 | 13 | B | 1 Prestrip - Thick | 46.4388 | 38.3749 | 38.3749 | 2028-03-19 03:05 | 2028-03-19 22:37 | 38263.9564 | 38264 | [7 empty] | 0 | 0 | 3.84 | 12.17 | 5322.94
TS Fleet 5 | GG\31\014\X2 | GG | 31 | 14 | X2 | 1 Prestrip - Thick | 25.3798 | 0 | 25.3798 | 2028-03-19 22:37 | 2028-03-20 14:34 | 31260.8321 | 31261 | [7 empty] | 0 | 0 | 2.09 | 0 | 0
PH4100XPC#1 | GG\31\014\X2 | GG | 31 | 14 | X2 | 1 Prestrip - Thick | 100 | 0 | 32.0596 | 2028-03-19 22:37 | 2028-03-20 16:50 | 39488.5696 | 39489 | [7 empty] | 0 | 0 | 2.65 | 0 | 0
TS Fleet 5 | GG\31\019\B | GG | 31 | 19 | B | 1 Prestrip - Thick | 43.1378 | 43.1378 | 43.1378 | 2028-03-20 14:34 | 2028-03-23 04:53 | 122163.9869 | 122164 | [7 empty] | 0 | 0 | 12.13 | 20.94 | 4663.05
DRE2 | GG\29\011\B | GG | 29 | 11 | B | 6 DL | 100 | 0 | 100 | 2028-03-20 15:08 | 2028-03-23 16:12 | 245777.4598 |  |  |  |  | 245777 | 189060 |  |  | 0 | 18.92 | 0 | 11.58 | 5401.12
PH4100XPC#1 | GG\31\014\B | GG | 31 | 14 | B | 1 Prestrip - Thick | 100 | 95.7984 | 95.7984 | 2028-03-20 16:50 | 2028-03-23 07:57 | 136730.2006 | 136730 | [7 empty] | 0 | 0 | 9.48 | 13.3 | 5220.29
TS5500Shv | GG\27\020\D | GG | 27 | 20 | D | 7 PostStrip | 100 | 0 | 100 | 2028-03-20 16:50 | 2028-03-22 07:19 | 41244.6779 |  |  | 41245 | [5 empty] | 0 | 0 | 0 | 6.81 | 5786
TS5500Exc | W1\07\002\B | W1 | 7 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-03-21 08:54 | 2028-03-23 21:59 | 76945.4939 | [6 empty] | 76945 | 54128 | 2.32 | 0 | 0 | 10.79 | 5180
TS5500Shv | GG\27\020\D | GG | 27 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-03-22 07:19 | 2028-03-23 20:04 | 44810.4905 | [6 empty] | 44810 | 33476 | 4.43 | 0 | 0 | 6.81 | 5786
TS Fleet 5 | GG\31\014\B | GG | 31 | 14 | B | 1 Prestrip - Thick | 46.4388 | 4.2016 | 4.2016 | 2028-03-23 04:53 | 2028-03-23 07:57 | 5996.7718 | 5997 | [7 empty] | 0 | 0 | 0.42 | 13.3 | 5220.29
TS Fleet 5 | GG\31\020\D | GG | 31 | 20 | D | 1 Prestrip - Thick | 36.3214 | 36.3214 | 36.3214 | 2028-03-23 07:57 | 2028-03-24 01:35 | 34562.3304 | 34562 | [7 empty] | 0 | 0 | 3.47 | 6.75 | 5792.49
PH4100XPC#1 | GG\31\017\X2 | GG | 31 | 17 | X2 | 1 Prestrip - Thick | 100 | 0 | 52.275 | 2028-03-23 07:57 | 2028-03-26 13:35 | 159739.6768 | 159740 | [7 empty] | 0 | 0 | 16.58 | 0 | 0
DRE2 | GG\29\010\B | GG | 29 | 10 | B | 6 DL | 100 | 0 | 100 | 2028-03-23 16:12 | 2028-03-26 13:37 | 233519.9716 |  |  |  |  | 233520 | 194600 |  |  | 0 | 19.42 | 0 | 10.99 | 5451.69
TS5500Shv | GG\29\013\B | GG | 29 | 13 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-03-23 20:04 | 2028-03-25 12:24 | 49189.016 | [6 empty] | 49189 | 35636 | 3.57 | 0 | 0 | 12.12 | 5319
TS5500Exc | W1\07\003\B | W1 | 7 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-03-23 21:59 | 2028-03-25 22:57 | 61675.9298 | [6 empty] | 61676 | 43092 | 2.14 | 0 | 0 | 11.43 | 5111
TS Fleet 5 | GG\32\009\X1 | GG | 32 | 9 | X1 | 1 Prestrip - Thick | 66.0201 | 66.0201 | 66.0201 | 2028-03-24 01:35 | 2028-04-04 01:21 | 516976.0126 | 516976 | [7 empty] | 0 | 0 | 66.82 | 14 | 5159.77
TS5500Shv | GG\32\009\X1 | GG | 32 | 9 | X1 | 1 Prestrip - Thick | 33.9799 | 32.3755 | 32.3755 | 2028-03-25 12:24 | 2028-04-04 09:17 | 253519.3923 | 253519 | [7 empty] | 0 | 0 | 32.77 | 14 | 5159.77
TS5500Exc | SC\49\021\D | SC | 49 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-03-25 22:57 | 2028-03-28 04:42 | 67695.0537 | [6 empty] | 67695 | 50629 | 4.22 | 0 | 0 | 7.28 | 5770
PH4100XPC#1 | GG\31\017\B | GG | 31 | 17 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-03-26 13:35 | 2028-03-28 20:46 | 119534.4705 | 119534 | [7 empty] | 0 | 0 | 11.91 | 15.54 | 5062.21
DRE2 | GG\29\009\B | GG | 29 | 9 | B | 6 DL | 100 | 0 | 100 | 2028-03-26 13:37 | 2028-03-29 13:13 | 240842.5392 |  |  |  |  | 240843 | 200702 |  |  | 0 | 19.97 | 0 | 10.58 | 5478.98
TS5500Exc | W2\03\005\D | W2 | 3 | 5 | D | 8 Coal Mining | 29.1 | 0 | 29.1 | 2028-03-28 04:42 | 2028-03-29 10:34 | 37620.0763 | [6 empty] | 37620 | 27408 | 1.37 | 0 | 0 | 5.72 | 5762
PH4100XPC#1 | GG\31\018\B | GG | 31 | 18 | B | 1 Prestrip - Thick | 100 | 42.2718 | 42.2718 | 2028-03-28 20:46 | 2028-03-31 16:13 | 145321.3141 | 145321 | [7 empty] | 0 | 0 | 15.08 | 17.81 | 4899.54
TS5500Exc | W2\03\006\D | W2 | 3 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-03-29 10:34 | 2028-04-02 13:56 | 125173.2198 | [6 empty] | 125173 | 91045 | 4.55 | 0 | 0 | 5.74 | 5758
DRE2 | GG\29\008\B | GG | 29 | 8 | B | 6 DL | 100 | 0 | 0 | 2028-03-29 13:13 | 2028-03-29 13:13 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\28\012\D | GG | 28 | 12 | D | 6 DL | 100 | 100 | 100 | 2028-03-29 13:13 | 2028-04-04 10:40 | 475781.6137 |  |  |  | 11078 | 475782 | 210474 |  |  | 0 | 22.18 | 0 | 6.69 | 5797.66
PH4100XPC#1 | GG\31\019\B | GG | 31 | 19 | B | 1 Prestrip - Thick | 100 | 51.5955 | 51.5955 | 2028-03-31 16:13 | 2028-04-03 09:15 | 146115.6194 | 146116 | [7 empty] | 0 | 0 | 14.51 | 20.94 | 4663.05
TS5500Exc | SC\49\022\D | SC | 49 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-04-02 13:56 | 2028-04-04 23:02 | 71918.536 | [6 empty] | 71919 | 53790 | 4.48 | 0 | 0 | 7.35 | 5766
PH4100XPC#1 | GG\31\020\D | GG | 31 | 20 | D | 1 Prestrip - Thick | 100 | 42.9165 | 42.9165 | 2028-04-03 09:15 | 2028-04-04 03:39 | 40838.0799 | 40838 | [7 empty] | 0 | 0 | 4.1 | 6.75 | 5792.49
TS Fleet 5 | GG\32\010\X1 | GG | 32 | 10 | X1 | 1 Prestrip - Thick | 89.6495 | 48.5651 | 48.5651 | 2028-04-04 01:21 | 2028-04-11 19:08 | 364152.2201 | 364152 | [7 empty] | 0 | 0 | 41.19 | 14.2 | 5153.81
PH4100XPC#1 | GG\32\008\X1 | GG | 32 | 8 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-04-04 03:39 | 2028-04-04 03:39 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\32\008\B | GG | 32 | 8 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-04-04 03:39 | 2028-04-04 03:39 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\32\009\X1 | GG | 32 | 9 | X1 | 1 Prestrip - Thick | 100 | 1.6044 | 1.6044 | 2028-04-04 03:39 | 2028-04-04 09:17 | 12563.0178 | 12563 | [7 empty] | 0 | 0 | 1.62 | 14 | 5159.77
PH4100XPC#1 | GG\32\010\X1 | GG | 32 | 10 | X1 | 1 Prestrip - Thick | 100 | 51.4349 | 51.4349 | 2028-04-04 09:17 | 2028-04-11 19:08 | 385670.4006 | 385670 | [7 empty] | 0 | 0 | 43.63 | 14.2 | 5153.81
TS5500Shv | GG\32\009\X1 | GG | 32 | 9 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2028-04-04 09:17 | 2028-04-04 23:30 | 17348.6635 | [6 empty] | 17349 | 12490 | 1.26 | 0 | 0 | 14 | 5160
DRE2 | GG\28\011\D | GG | 28 | 11 | D | 6 DL | 100 | 100 | 100 | 2028-04-04 10:40 | 2028-04-10 06:58 | 471948.1874 |  |  |  | 8547 | 471948 | 205117 |  |  | 0 | 21.39 | 0 | 6.59 | 5807.95
TS5500Exc | W2\03\007\D | W2 | 3 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-04-04 23:02 | 2028-04-09 05:19 | 128834.6257 | [6 empty] | 128835 | 93570 | 4.68 | 0 | 0 | 5.83 | 5751
TS5500Shv | GG\32\014\X1 | GG | 32 | 14 | X1 | 1 Prestrip - Thick | 3.4017 | 3.4017 | 3.4017 | 2028-04-04 23:30 | 2028-04-05 20:28 | 22086.9516 | 22087 | [7 empty] | 0 | 0 | 1.23 | 14.63 | 5124.76
TS5500Shv | GG\32\018\B | GG | 32 | 18 | B | 1 Prestrip - Thick | 17.3868 | 17.3868 | 17.3868 | 2028-04-05 20:28 | 2028-04-08 04:36 | 59550.9978 | 59551 | [7 empty] | 0 | 0 | 6.1 | 16.96 | 4972.05
TS5500Shv | GG\32\019\B | GG | 32 | 19 | B | 1 Prestrip - Thick | 11.5446 | 11.5446 | 11.5446 | 2028-04-08 04:36 | 2028-04-09 07:33 | 28859.915 | 28860 | [7 empty] | 0 | 0 | 2.67 | 20.38 | 4708.29
TS5500Exc | SC\49\023\D | SC | 49 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-04-09 05:19 | 2028-04-11 17:55 | 76339.7197 | [6 empty] | 76340 | 57191 | 4.77 | 0 | 0 | 7.31 | 5771
TS5500Shv | GG\32\020\B | GG | 32 | 20 | B | 1 Prestrip - Thick | 17.3891 | 17.3891 | 17.3891 | 2028-04-09 07:33 | 2028-04-10 16:12 | 34986.1408 | 34986 | [7 empty] | 0 | 0 | 3.57 | 14.65 | 5159.25
DRE2 | GG\28\010\D | GG | 28 | 10 | D | 6 DL | 100 | 100 | 100 | 2028-04-10 06:58 | 2028-04-15 20:05 | 447759.7639 |  |  |  | 10425 | 447760 | 198078 |  |  | 0 | 20.87 | 0 | 6.56 | 5811.03
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 03:53 |  | 5d 03:53 | 2028-04-10 16:12 | 2028-04-15 20:05
TS5500Exc | SC\49\024\D | SC | 49 | 24 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-04-11 17:55 | 2028-04-14 05:44 | 75343.0025 | [6 empty] | 75343 | 56534 | 4.71 | 0 | 0 | 7.37 | 5766
TS Fleet 5 | GG\32\014\X1 | GG | 32 | 14 | X1 | 1 Prestrip - Thick | 37.4171 | 37.4171 | 37.4171 | 2028-04-11 19:08 | 2028-04-16 23:05 | 242949.0484 | 242949 | [7 empty] | 0 | 0 | 13.56 | 14.63 | 5124.76
PH4100XPC#1 | GG\32\009\X2 | GG | 32 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2028-04-11 19:08 | 2028-04-13 02:44 | 68471.336 | 68471 | [7 empty] | 0 | 0 | 6.83 | 0 | 0
PH4100XPC#1 | GG\32\009\B | GG | 32 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-04-13 02:44 | 2028-04-14 13:49 | 76007.5777 | 76008 | [7 empty] | 0 | 0 | 7.64 | 10.75 | 5463.19
TS5500Exc | SC\49\025\D | SC | 49 | 25 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-04-14 05:44 | 2028-04-16 18:26 | 76446.8296 | [6 empty] | 76447 | 57500 | 4.79 | 0 | 0 | 6.87 | 5810
PH4100XPC#1 | GG\32\011\X1 | GG | 32 | 11 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-04-14 13:49 | 2028-04-27 22:10 | 688516.8988 | 688517 | [7 empty] | 0 | 0 | 68.23 | 14.35 | 5147.13
DRE2 | GG\28\009\D | GG | 28 | 9 | D | 6 DL | 100 | 100 | 100 | 2028-04-15 20:05 | 2028-04-21 04:35 | 432255.2564 |  |  |  | 10064 | 432255 | 191219 |  |  | 0 | 20.13 | 0 | 6.57 | 5809.3
TS5500Shv | GG\28\010\D | GG | 28 | 10 | D | 8 Coal Mining | 57.2 | 0 | 57.2 | 2028-04-15 20:05 | 2028-04-17 01:19 | 35645.0514 | [6 empty] | 35645 | 26712 | 2.67 | 0 | 0 | 6.56 | 5811
TS5500Exc | CP\03\004\B | CP | 3 | 4 | B | 8 Coal Mining | 23.6 | 0 | 23.6 | 2028-04-16 18:26 | 2028-04-19 09:35 | 79543.4837 | [6 empty] | 79543 | 57054 | 1.06 | 0 | 0 | 8.84 | 5585
TS Fleet 5 | GG\32\017\X2 | GG | 32 | 17 | X2 | 1 Prestrip - Thick | 47.8177 | 0 | 47.8177 | 2028-04-16 23:05 | 2028-04-20 04:17 | 151291.2951 | 151291 | [7 empty] | 0 | 0 | 15.62 | 0 | 0
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 10d 20:51 |  | 10d 20:51 | 2028-04-17 01:19 | 2028-04-27 22:10
TS5500Exc | SC\48\026\D | SC | 48 | 26 | D | 7 PostStrip | 100 | 0 | 100 | 2028-04-19 09:35 | 2028-04-22 07:25 | 61768.2755 |  |  | 61768 | [5 empty] | 0 | 0 | 0 | 6.9 | 5807.72
TS Fleet 5 | GG\32\018\B | GG | 32 | 18 | B | 1 Prestrip - Thick | 34.8553 | 34.8553 | 34.8553 | 2028-04-20 04:17 | 2028-04-22 17:11 | 119381.4411 | 119381 | [7 empty] | 0 | 0 | 12.23 | 16.96 | 4972.05
DRE2 | GG\28\008\D | GG | 28 | 8 | D | 6 DL | 100 | 100 | 100 | 2028-04-21 04:35 | 2028-04-26 10:57 | 425062.3291 |  |  |  | 7915 | 425062 | 189972 |  |  | 0 | 19.79 | 0 | 6.56 | 5809.85
TS5500Exc | SC\48\026\D | SC | 48 | 26 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-04-22 07:25 | 2028-04-24 21:29 | 78166.4254 | [6 empty] | 78166 | 59123 | 4.92 | 0 | 0 | 6.9 | 5808
TS Fleet 5 | GG\32\019\B | GG | 32 | 19 | B | 1 Prestrip - Thick | 35.4473 | 35.4473 | 35.4473 | 2028-04-22 17:11 | 2028-04-24 14:24 | 88613.6264 | 88614 | [7 empty] | 0 | 0 | 8.19 | 20.38 | 4708.29
PH4100A | W2\06\004\D | W2 | 6 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-04-22 19:58 | 2028-04-29 20:41 | 292893.336 | 292893 | [7 empty] | 0 | 0 | 19.63 | 5.71 | 5764.5
TS Fleet 5 | GG\32\020\B | GG | 32 | 20 | B | 1 Prestrip - Thick | 30.4796 | 30.4796 | 30.4796 | 2028-04-24 14:24 | 2028-04-25 21:41 | 61323.639 | 61324 | [7 empty] | 0 | 0 | 6.25 | 14.65 | 5159.25
TS5500Exc | W2\07\003\B | W2 | 7 | 3 | B | 8 Coal Mining | 68.8 | 0 | 68.8 | 2028-04-24 21:29 | 2028-04-27 15:16 | 82875.0548 | [6 empty] | 82875 | 58523 | 2.12 | 0 | 0 | 9.59 | 5321
TS Fleet 5 | W1\07\002\D | W1 | 7 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-04-25 21:41 | 2028-05-06 19:11 | 512527.667 | 512528 | [7 empty] | 0 | 0 | 28.43 | 7.91 | 5566.64
DRE2 | GG\28\007\D | GG | 28 | 7 | D | 6 DL | 100 | 100 | 100 | 2028-04-26 10:57 | 2028-04-30 21:46 | 359288.0326 |  |  |  | 6691 | 359288 | 160576 |  |  | 0 | 19.89 | 0 | 6.54 | 5811.39
TS5500Exc | SC\49\026\D | SC | 49 | 26 | D | 7 PostStrip | 100 | 0 | 100 | 2028-04-27 15:16 | 2028-04-30 13:28 | 62087.871 |  |  | 62088 | [5 empty] | 0 | 0 | 0 | 6.86 | 5811.36
PH4100XPC#1 | GG\32\012\X1 | GG | 32 | 12 | X1 | 1 Prestrip - Thick | 100 | 90.3412 | 90.3412 | 2028-04-27 22:10 | 2028-05-08 16:07 | 554251.894 | 554252 | [7 empty] | 0 | 0 | 54.53 | 14.49 | 5137.67
TS5500Shv | GG\32\011\X1 | GG | 32 | 11 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2028-04-27 22:10 | 2028-04-28 04:31 | 7748.6995 | [6 empty] | 7749 | 5566 | 0.56 | 0 | 0 | 14.35 | 5147
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 11:14 |  | 5d 11:14 | 2028-04-28 04:31 | 2028-05-03 15:45
PH4100A | W2\07\004\B | W2 | 7 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-04-29 20:41 | 2028-05-29 08:03 | 1228007.273 | 1228007 | [7 empty] | 0 | 0 | 61.33 | 9.82 | 5294.43
TS5500Exc | SC\49\026\D | SC | 49 | 26 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-04-30 13:28 | 2028-05-03 02:51 | 77309.7091 | [6 empty] | 77310 | 58476 | 4.92 | 0 | 0 | 6.86 | 5811
DRE2 | GG\29\014\B | GG | 29 | 14 | B | 6 DL | 100 | 0 | 100 | 2028-04-30 21:46 | 2028-05-03 15:45 | 221929.5207 |  |  |  |  | 221930 | 184941 |  |  | 0 | 16.51 | 0 | 12.26 | 5291.84
TS5500Exc | W2\06\004\D | W2 | 6 | 4 | D | 7 PostStrip | 58.5701 | 0 | 58.5701 | 2028-05-03 02:51 | 2028-05-05 21:09 | 58634.3868 |  |  | 58634 | [5 empty] | 0 | 0 | 0 | 5.71 | 5764.5
DRE2 | GG\29\017\B | GG | 29 | 17 | B | 6 DL | 100 | 0 | 100 | 2028-05-03 15:45 | 2028-05-05 23:46 | 188454.4091 |  |  |  |  | 188454 | 157045 |  |  | 0 | 15.77 | 0 | 14.75 | 5107.03
TS5500Shv | GG\29\014\B | GG | 29 | 14 | B | 8 Coal Mining | 39.3 | 0 | 39.3 | 2028-05-03 15:45 | 2028-05-04 08:35 | 20540.445 | [6 empty] | 20540 | 14893 | 1.4 | 0 | 0 | 12.26 | 5292
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 15:11 |  | 1d 15:11 | 2028-05-04 08:35 | 2028-05-05 23:46
TS5500Exc | GG\32\012\X1 | GG | 32 | 12 | X1 | 1 Prestrip - Thick | 10.5287 | 9.6588 | 9.6588 | 2028-05-05 21:09 | 2028-05-08 16:07 | 59257.9822 | 59258 | [7 empty] | 0 | 0 | 5.83 | 14.49 | 5137.67
DRE2 | GG\29\018\B | GG | 29 | 18 | B | 6 DL | 100 | 0 | 100 | 2028-05-05 23:46 | 2028-05-08 08:15 | 189966.7762 |  |  |  |  | 189967 | 158306 |  |  | 0 | 16.06 | 0 | 16.33 | 5007.3
TS5500Shv | GG\29\017\B | GG | 29 | 17 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2028-05-05 23:46 | 2028-05-06 17:45 | 21923.4674 | [6 empty] | 21923 | 15681 | 1.54 | 0 | 0 | 14.75 | 5107
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 14:30 |  | 1d 14:30 | 2028-05-06 17:45 | 2028-05-08 08:15
TS Fleet 5 | SC\61\001\D | SC | 61 | 1 | D | 1 Prestrip - Thick | 100 | 83.2882 | 83.2882 | 2028-05-06 19:11 | 2028-06-05 00:55 | 1375403.706 | 1375404 | [7 empty] | 0 | 0 | 35.15 | 6.8 | 5816.13
DRE2 | GG\29\019\B | GG | 29 | 19 | B | 6 DL | 100 | 0 | 100 | 2028-05-08 08:15 | 2028-05-10 10:15 | 168235.5656 |  |  |  |  | 168236 | 140196 |  |  | 0 | 16.42 | 0 | 18.44 | 4858.73
TS5500Shv | GG\29\018\B | GG | 29 | 18 | B | 8 Coal Mining | 41 | 0 | 41 | 2028-05-08 08:15 | 2028-05-08 22:11 | 17006.938 | [6 empty] | 17007 | 12044 | 1.2 | 0 | 0 | 16.33 | 5007
TS5500Exc | GG\32\014\X1 | GG | 32 | 14 | X1 | 1 Prestrip - Thick | 17.2416 | 17.2416 | 17.2416 | 2028-05-08 16:07 | 2028-05-13 22:26 | 111949.5292 | 111950 | [7 empty] | 0 | 0 | 6.25 | 14.63 | 5124.76
PH4100XPC#1 | GG\32\013\X1 | GG | 32 | 13 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-05-08 16:07 | 2028-05-18 20:34 | 520926.0605 | 520926 | [7 empty] | 0 | 0 | 49.83 | 14.55 | 5132.06
TS5500Shv | GG\32\012\X1 | GG | 32 | 12 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2028-05-08 22:11 | 2028-05-09 04:03 | 7154.0953 | [6 empty] | 7154 | 5134 | 0.52 | 0 | 0 | 14.49 | 5138
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 06:12 |  | 1d 06:12 | 2028-05-09 04:03 | 2028-05-10 10:15
DRE2 | GG\29\020\B | GG | 29 | 20 | B | 6 DL | 100 | 0 | 100 | 2028-05-10 10:15 | 2028-05-12 13:35 | 172653.8866 |  |  |  |  | 172654 | 132811 |  |  | 0 | 18.97 | 0 | 0 | 0
TS5500Shv | GG\29\019\B | GG | 29 | 19 | B | 8 Coal Mining | 32.7 | 0 | 32.7 | 2028-05-10 10:15 | 2028-05-10 19:50 | 11666.7513 | [6 empty] | 11667 | 8167 | 0.82 | 0 | 0 | 18.44 | 4859
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 7d 20:23 |  | 7d 20:23 | 2028-05-10 19:50 | 2028-05-18 16:13
DRE2 | GG\28\013\D | GG | 28 | 13 | D | 6 DL | 100 | 100 | 100 | 2028-05-12 13:35 | 2028-05-18 16:13 | 493215.2868 |  |  |  | 11483 | 493215 | 218186 |  |  | 0 | 22.99 | 0 | 6.82 | 5784.57
TS5500Exc | W1\07\004\D | W1 | 7 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2028-05-13 22:26 | 2028-05-15 03:56 | 26099.6745 |  |  | 26100 | [5 empty] | 0 | 0 | 0 | 8.05 | 5547.71
TS5500Exc | W1\07\004\D | W1 | 7 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-05-15 03:56 | 2028-05-15 23:13 | 24288.6721 | [6 empty] | 24289 | 17484 | 4.03 | 0 | 0 | 8.05 | 5548
TS5500Exc | W1\08\002\B | W1 | 8 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-05-15 23:13 | 2028-05-17 19:03 | 55198.8937 | [6 empty] | 55199 | 38827 | 2.11 | 0 | 0 | 10.87 | 5178
TS5500Exc | W1\08\003\B | W1 | 8 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-05-17 19:03 | 2028-05-19 00:20 | 36887.8844 | [6 empty] | 36888 | 25644 | 1.16 | 0 | 0 | 12.71 | 5024
DRE2 | GG\28\014\D | GG | 28 | 14 | D | 6 DL | 100 | 100 | 100 | 2028-05-18 16:13 | 2028-05-24 09:32 | 461915.9741 |  |  |  | 10755 | 461916 | 204340 |  |  | 0 | 23.63 | 0 | 6.9 | 5776.43
TS5500Shv | GG\28\013\D | GG | 28 | 13 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2028-05-18 16:13 | 2028-05-19 14:58 | 27751.2399 | [6 empty] | 27751 | 20712 | 2.07 | 0 | 0 | 6.82 | 5785
PH4100XPC#1 | GG\32\014\X1 | GG | 32 | 14 | X1 | 1 Prestrip - Thick | 100 | 41.9397 | 41.9397 | 2028-05-18 20:34 | 2028-05-24 05:54 | 272314.8483 | 272315 | [7 empty] | 0 | 0 | 15.2 | 14.63 | 5124.76
TS5500Exc | W1\09\002\B | W1 | 9 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-05-19 00:20 | 2028-05-20 12:24 | 45432.0907 | [6 empty] | 45432 | 31959 | 1.83 | 0 | 0 | 11.01 | 5175
TS5500Shv | GG\32\013\X1 | GG | 32 | 13 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2028-05-19 14:58 | 2028-05-19 20:29 | 6719.2757 | [6 empty] | 6719 | 4821 | 0.49 | 0 | 0 | 14.55 | 5132
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 09:25 |  | 4d 09:25 | 2028-05-19 20:29 | 2028-05-24 05:54
TS5500Exc | SC\50\020\D | SC | 50 | 20 | D | 1 Prestrip - Thick | 35.4771 | 35.4771 | 35.4771 | 2028-05-20 12:24 | 2028-06-09 08:15 | 421508.1328 | 421508 | [7 empty] | 0 | 0 | 19.46 | 7.29 | 5770.13
PH4100XPC#1 | GG\32\017\X2 | GG | 32 | 17 | X2 | 1 Prestrip - Thick | 100 | 0 | 52.1823 | 2028-05-24 05:54 | 2028-05-27 14:27 | 165100.4978 | 165100 | [7 empty] | 0 | 0 | 17.05 | 0 | 0
TS5500Shv | GG\32\014\X1 | GG | 32 | 14 | X1 | 8 Coal Mining | 47.4 | 0 | 47.4 | 2028-05-24 05:54 | 2028-05-24 14:26 | 10396.4092 | [6 empty] | 10396 | 7462 | 0.45 | 0 | 0 | 14.63 | 5125
DRE2 | GG\28\017\D | GG | 28 | 17 | D | 6 DL | 100 | 100 | 100 | 2028-05-24 09:32 | 2028-05-30 08:52 | 482111.25 |  |  |  | 11225 | 482111 | 213274 |  |  | 0 | 24.17 | 0 | 6.96 | 5775.1
TS5500Shv | GG\28\014\D | GG | 28 | 14 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2028-05-24 14:26 | 2028-05-25 10:39 | 24662.4113 | [6 empty] | 24662 | 18377 | 2.03 | 0 | 0 | 6.9 | 5776
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 03:47 |  | 2d 03:47 | 2028-05-25 10:39 | 2028-05-27 14:27
PH4100XPC#1 | GG\32\017\B | GG | 32 | 17 | B | 1 Prestrip - Thick | 100 | 64.617 | 64.617 | 2028-05-27 14:27 | 2028-05-28 21:57 | 68252.4144 | 68252 | [7 empty] | 0 | 0 | 6.8 | 15.03 | 5112.23
TS5500Shv | GG\32\017\B | GG | 32 | 17 | B | 1 Prestrip - Thick | 17.4345 | 17.4345 | 17.4345 | 2028-05-27 14:27 | 2028-05-28 07:37 | 18415.3845 | 18415 | [7 empty] | 0 | 0 | 1.83 | 15.03 | 5112.23
TS6060#1 | GG\32\017\B | GG | 32 | 17 | B | 1 Prestrip - Thick | 100 | 17.9485 | 17.9485 | 2028-05-28 03:34 | 2028-05-28 21:57 | 18958.2993 | 18958 | [7 empty] | 0 | 0 | 1.89 | 15.03 | 5112.23
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 01:14 |  | 2d 01:14 | 2028-05-28 07:37 | 2028-05-30 08:52
PH4100XPC#1 | GG\32\018\B | GG | 32 | 18 | B | 1 Prestrip - Thick | 100 | 47.7579 | 47.7579 | 2028-05-28 21:57 | 2028-06-01 02:12 | 163573.7184 | 163574 | [7 empty] | 0 | 0 | 16.76 | 16.96 | 4972.05
TS6060#1 | W2\03\008\B | W2 | 3 | 8 | B | 8 Coal Mining | 49.6 | 0 | 49.6 | 2028-05-28 21:57 | 2028-05-30 10:29 | 49457.004 | [6 empty] | 49457 | 34639 | 1.73 | 0 | 0 | 9.99 | 5290
PH4100A | SC\61\001\D | SC | 61 | 1 | D | 1 Prestrip - Thick | 100 | 16.7118 | 16.7118 | 2028-05-29 08:03 | 2028-06-05 00:55 | 275975.1743 | 275975 | [7 empty] | 0 | 0 | 7.05 | 6.8 | 5816.13
DRE2 | GG\28\018\D | GG | 28 | 18 | D | 6 DL | 100 | 100 | 100 | 2028-05-30 08:52 | 2028-06-05 17:02 | 511883.721 |  |  |  | 11918 | 511884 | 226444 |  |  | 0 | 23.83 | 0 | 6.94 | 5776.82
TS5500Shv | GG\28\017\D | GG | 28 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-05-30 08:52 | 2028-06-01 07:30 | 56872.9543 | [6 empty] | 56873 | 42349 | 4.59 | 0 | 0 | 6.96 | 5775
TS6060#1 | W2\06\003\D | W2 | 6 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2028-05-30 10:29 | 2028-06-03 18:27 | 107267.023 |  |  | 107267 | [5 empty] | 0 | 0 | 0 | 5.77 | 5760.59
PH4100XPC#1 | GG\32\019\B | GG | 32 | 19 | B | 1 Prestrip - Thick | 100 | 53.0081 | 53.0081 | 2028-06-01 02:12 | 2028-06-03 13:36 | 132513.2634 | 132513 | [7 empty] | 0 | 0 | 12.25 | 20.38 | 4708.29
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 09:32 |  | 4d 09:32 | 2028-06-01 07:30 | 2028-06-05 17:02
PH4100XPC#1 | GG\32\020\B | GG | 32 | 20 | B | 1 Prestrip - Thick | 100 | 52.1314 | 52.1314 | 2028-06-03 13:36 | 2028-06-05 13:34 | 104886.1828 | 104886 | [7 empty] | 0 | 0 | 10.69 | 14.65 | 5159.25
TS6060#1 | GG\29\011\B | GG | 29 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-06-03 18:27 | 2028-06-05 07:34 | 50239.1519 | [6 empty] | 50239 | 36441 | 3.65 | 0 | 0 | 11.58 | 5401
PH4100A | W2\08\003\B | W2 | 8 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-06-05 00:55 | 2028-07-13 02:09 | 1584879.968 | 1584880 | [7 empty] | 0 | 0 | 55.7 | 9.47 | 5333.45
TS Fleet 5 | W1\07\003\D | W1 | 7 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-06-05 00:55 | 2028-06-13 12:54 | 399810.2047 | 399810 | [7 empty] | 0 | 0 | 24.78 | 8.11 | 5544.88
TS6060#1 | GG\29\010\B | GG | 29 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-06-05 07:34 | 2028-06-06 21:05 | 50771.1322 | [6 empty] | 50771 | 36971 | 3.7 | 0 | 0 | 10.99 | 5452
PH4100XPC#1 | W2\02\008\D | W2 | 2 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-06-05 13:34 | 2028-06-11 13:59 | 312887.8445 | 312888 | [7 empty] | 0 | 0 | 20.63 | 5.95 | 5739.55
DRE2 | GG\28\019\D | GG | 28 | 19 | D | 6 DL | 100 | 100 | 100 | 2028-06-05 17:02 | 2028-06-11 22:48 | 503747.6152 |  |  |  | 11729 | 503748 | 222845 |  |  | 0 | 23.45 | 0 | 6.88 | 5782.56
TS5500Shv | GG\28\018\D | GG | 28 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-06-05 17:02 | 2028-06-07 20:02 | 62176.7461 | [6 empty] | 62177 | 46335 | 4.63 | 0 | 0 | 6.94 | 5777
TS6060#1 | W2\06\003\D | W2 | 6 | 3 | D | 8 Coal Mining | 34.6 | 0 | 34.6 | 2028-06-06 21:05 | 2028-06-08 09:33 | 49341.2152 | [6 empty] | 49341 | 36091 | 1.73 | 0 | 0 | 5.77 | 5761
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 07:19 |  | 3d 07:19 | 2028-06-07 20:02 | 2028-06-11 03:20
TS6060#1 | GG\29\009\B | GG | 29 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-06-08 09:33 | 2028-06-09 23:37 | 51532.3867 | [6 empty] | 51532 | 37602 | 3.76 | 0 | 0 | 10.58 | 5479
TS5500Exc | W2\06\003\D | W2 | 6 | 3 | D | 8 Coal Mining | 65.4 | 0 | 65.4 | 2028-06-09 08:15 | 2028-06-12 10:14 | 93173.8678 | [6 empty] | 93174 | 68153 | 3.26 | 0 | 0 | 5.77 | 5761
TS6060#1 | W2\07\003\B | W2 | 7 | 3 | B | 8 Coal Mining | 31.2 | 0 | 31.2 | 2028-06-09 23:37 | 2028-06-11 03:20 | 37514.2147 | [6 empty] | 37514 | 26491 | 0.96 | 0 | 0 | 9.59 | 5321
TS6060#1 | W2\07\004\B | W2 | 7 | 4 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2028-06-11 03:20 | 2028-06-12 15:32 | 48977.3314 | [6 empty] | 48977 | 34463 | 1.72 | 0 | 0 | 9.82 | 5294
TS5500Shv | W2\07\003\D | W2 | 7 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-06-11 03:20 | 2028-06-25 21:26 | 379589.5692 | 379590 | [7 empty] | 0 | 0 | 20.59 | 5.78 | 5760.37
PH4100XPC#1 | W2\03\008\D | W2 | 3 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-06-11 13:59 | 2028-06-17 17:04 | 318675.9751 | 318676 | [7 empty] | 0 | 0 | 20.92 | 5.96 | 5739.71
DRE2 | GG\28\020\D | GG | 28 | 20 | D | 6 DL | 100 | 100 | 100 | 2028-06-11 22:48 | 2028-06-17 17:22 | 466135.0356 |  |  |  | 7259 | 466135 | 133384 |  |  | 0 | 22.22 | 0 | 6.8 | 5787.91
TS5500Exc | W2\07\004\B | W2 | 7 | 4 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2028-06-12 10:14 | 2028-06-13 22:25 | 45582.8629 | [6 empty] | 45583 | 32075 | 1.6 | 0 | 0 | 9.82 | 5294
TS6060#1 | W2\02\008\D | W2 | 2 | 8 | D | 7 PostStrip | 100 | 0 | 100 | 2028-06-12 15:32 | 2028-06-16 16:31 | 100073.7117 |  |  | 100074 | [5 empty] | 0 | 0 | 0 | 5.95 | 5739.55
TS Fleet 5 | W1\08\002\D | W1 | 8 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-06-13 12:54 | 2028-06-21 20:22 | 390956.7853 | 390957 | [7 empty] | 0 | 0 | 29.26 | 8.16 | 5544.72
TS5500Exc | SC\61\001\D | SC | 61 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2028-06-13 22:25 | 2028-06-24 11:38 | 223939.591 |  |  | 223940 | [5 empty] | 0 | 0 | 0 | 6.8 | 5816.13
TS6060#1 | W2\02\008\D | W2 | 2 | 8 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2028-06-16 16:31 | 2028-06-18 16:29 | 64930.2494 | [6 empty] | 64930 | 47154 | 2.36 | 0 | 0 | 5.95 | 5740
PH4100XPC#1 | W2\02\009\B | W2 | 2 | 9 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-06-17 17:04 | 2028-06-17 17:04 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\03\009\D | W2 | 3 | 9 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-06-17 17:04 | 2028-06-17 17:04 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\02\009\D | W2 | 2 | 9 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-06-17 17:04 | 2028-06-17 17:04 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\04\003\D | W2 | 4 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-06-17 17:04 | 2028-07-22 05:43 | 1889351.861 | 1889352 | [7 empty] | 0 | 0 | 86.36 | 5.72 | 5762.6
DRE2 | GG\30\010\B | GG | 30 | 10 | B | 6 DL | 100 | 0 | 100 | 2028-06-17 17:22 | 2028-06-20 15:52 | 237144.1436 |  |  |  |  | 237144 | 197620 |  |  | 0 | 19.71 | 0 | 11.02 | 5448.44
TS6060#1 | W2\03\008\D | W2 | 3 | 8 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2028-06-18 16:29 | 2028-06-20 20:43 | 53884.4966 |  |  | 53884 | [5 empty] | 0 | 0 | 0 | 5.96 | 5739.71
DRE2 | GG\30\009\B | GG | 30 | 9 | B | 6 DL | 100 | 0 | 100 | 2028-06-20 15:52 | 2028-06-23 21:45 | 261979.4606 |  |  |  |  | 261979 | 201523 |  |  | 0 | 20.19 | 0 | 10.61 | 5476.63
TS6060#1 | GG\28\012\D | GG | 28 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-06-20 20:43 | 2028-06-22 17:32 | 60646.7405 | [6 empty] | 60647 | 45338 | 4.53 | 0 | 0 | 6.69 | 5798
TS Fleet 5 | W1\08\003\D | W1 | 8 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-06-21 20:22 | 2028-06-30 13:26 | 409765.5645 | 409766 | [7 empty] | 0 | 0 | 24.94 | 8.23 | 5535.18
TS6060#1 | W1\07\002\D | W1 | 7 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2028-06-22 17:32 | 2028-06-27 03:31 | 109354.1116 |  |  | 109354 | [5 empty] | 0 | 0 | 0 | 7.91 | 5566.64
DRE2 | GG\30\008\B | GG | 30 | 8 | B | 6 DL | 100 | 0 | 0 | 2028-06-23 21:45 | 2028-06-23 21:45 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\29\012\D | GG | 29 | 12 | D | 6 DL | 100 | 100 | 100 | 2028-06-23 21:45 | 2028-06-29 16:59 | 468338.0724 |  |  |  | 10904 | 468338 | 207181 |  |  | 0 | 21.84 | 0 | 6.69 | 5798.14
TS5500Exc | W2\02\008\D | W2 | 2 | 8 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2028-06-24 11:38 | 2028-06-26 11:36 | 60430.1331 | [6 empty] | 60430 | 43886 | 2.19 | 0 | 0 | 5.95 | 5740
TS5500Shv | GG\28\019\D | GG | 28 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-06-25 21:26 | 2028-06-28 00:32 | 62319.164 | [6 empty] | 62319 | 46515 | 4.65 | 0 | 0 | 6.88 | 5783
TS5500Exc | W2\03\008\D | W2 | 3 | 8 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2028-06-26 11:36 | 2028-06-28 15:50 | 46186.7114 |  |  | 46187 | [5 empty] | 0 | 0 | 0 | 5.96 | 5739.71
TS6060#1 | GG\28\011\D | GG | 28 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-06-27 03:31 | 2028-06-29 01:43 | 62539.4527 | [6 empty] | 62539 | 46828 | 4.68 | 0 | 0 | 6.59 | 5808
TS5500Shv | GG\28\020\D | GG | 28 | 20 | D | 7 PostStrip | 100 | 0 | 100 | 2028-06-28 00:32 | 2028-06-29 14:37 | 40827.0484 |  |  | 40827 | [5 empty] | 0 | 0 | 0 | 6.8 | 5787.91
TS5500Exc | W2\03\008\D | W2 | 3 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-06-28 15:50 | 2028-07-02 21:40 | 128283.4885 | [6 empty] | 128283 | 93025 | 4.65 | 0 | 0 | 5.96 | 5740
TS6060#1 | GG\32\010\X1 | GG | 32 | 10 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2028-06-29 01:43 | 2028-06-29 14:37 | 17458.5685 | [6 empty] | 17459 | 12551 | 1.26 | 0 | 0 | 14.2 | 5154
TS6060#1 | W1\07\002\D | W1 | 7 | 2 | D | 8 Coal Mining | 78.1 | 0 | 78.1 | 2028-06-29 14:37 | 2028-07-02 19:14 | 103686.9456 | [6 empty] | 103687 | 74720 | 3.5 | 0 | 0 | 7.91 | 5567
TS5500Shv | GG\28\020\D | GG | 28 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-06-29 14:37 | 2028-07-01 03:30 | 44973.653 | [6 empty] | 44974 | 33624 | 4.44 | 0 | 0 | 6.8 | 5788
DRE2 | GG\29\011\D | GG | 29 | 11 | D | 6 DL | 100 | 100 | 100 | 2028-06-29 16:59 | 2028-07-05 11:19 | 465311.311 |  |  |  | 8423 | 465311 | 202150 |  |  | 0 | 21.08 | 0 | 6.6 | 5807.45
TS Fleet 5 | W1\09\002\D | W1 | 9 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-06-30 13:26 | 2028-07-08 11:10 | 371882.5413 | 371883 | [7 empty] | 0 | 0 | 30.36 | 8.23 | 5538.75
TS5500Shv | GG\30\009\B | GG | 30 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-07-01 03:30 | 2028-07-02 21:56 | 51726.2588 | [6 empty] | 51726 | 37733 | 3.78 | 0 | 0 | 10.61 | 5477
TS6060#1 | GG\28\010\D | GG | 28 | 10 | D | 8 Coal Mining | 42.8 | 0 | 42.8 | 2028-07-02 19:14 | 2028-07-03 14:59 | 26725.4183 | [6 empty] | 26725 | 20027 | 2 | 0 | 0 | 6.56 | 5811
TS5500Exc | W1\07\002\D | W1 | 7 | 2 | D | 8 Coal Mining | 21.9 | 0 | 21.9 | 2028-07-02 21:40 | 2028-07-03 20:43 | 29017.741 | [6 empty] | 29018 | 20911 | 0.98 | 0 | 0 | 7.91 | 5567
TS5500Shv | GG\30\010\B | GG | 30 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-07-02 21:56 | 2028-07-04 15:54 | 51175.0423 | [6 empty] | 51175 | 37236 | 3.73 | 0 | 0 | 11.02 | 5448
TS6060#1 | GG\32\011\X1 | GG | 32 | 11 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2028-07-03 14:59 | 2028-07-03 21:20 | 8600.205 | [6 empty] | 8600 | 6178 | 0.62 | 0 | 0 | 14.35 | 5147
TS5500Exc | W2\07\003\D | W2 | 7 | 3 | D | 7 PostStrip | 63.9159 | 0 | 63.9159 | 2028-07-03 20:43 | 2028-07-07 12:42 | 77820.0418 |  |  | 77820 | [5 empty] | 0 | 0 | 0 | 5.78 | 5760.37
TS6060#1 | W2\06\004\D | W2 | 6 | 4 | D | 7 PostStrip | 41.4299 | 0 | 41.4299 | 2028-07-03 21:20 | 2028-07-05 13:32 | 41475.3688 |  |  | 41475 | [5 empty] | 0 | 0 | 0 | 5.71 | 5764.5
TS5500Shv | GG\29\012\D | GG | 29 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-07-04 15:54 | 2028-07-06 17:48 | 60862.7198 | [6 empty] | 60863 | 45499 | 4.55 | 0 | 0 | 6.69 | 5798
DRE2 | GG\29\010\D | GG | 29 | 10 | D | 6 DL | 100 | 100 | 100 | 2028-07-05 11:19 | 2028-07-10 22:34 | 441524.1546 |  |  |  | 10280 | 441524 | 195319 |  |  | 0 | 20.58 | 0 | 6.56 | 5810.29
TS6060#1 | W2\06\004\D | W2 | 6 | 4 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2028-07-05 13:32 | 2028-07-07 16:34 | 69064.4043 | [6 empty] | 69064 | 50437 | 2.52 | 0 | 0 | 5.71 | 5765
TS5500Shv | GG\29\011\D | GG | 29 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-07-06 17:48 | 2028-07-08 21:03 | 62498.3394 | [6 empty] | 62498 | 46798 | 4.68 | 0 | 0 | 6.6 | 5807
TS5500Exc | W2\06\004\D | W2 | 6 | 4 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2028-07-07 12:42 | 2028-07-09 15:44 | 64277.7624 | [6 empty] | 64278 | 46941 | 2.35 | 0 | 0 | 5.71 | 5765
TS6060#1 | GG\28\009\D | GG | 28 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-07-07 16:34 | 2028-07-09 13:58 | 61460.9409 | [6 empty] | 61461 | 46057 | 4.61 | 0 | 0 | 6.57 | 5809
TS Fleet 5 | GG\32\011\X2 | GG | 32 | 11 | X2 | 1 Prestrip - Thick | 46.4388 | 0 | 46.4388 | 2028-07-08 11:10 | 2028-07-09 04:02 | 33069.1911 | 33069 | [7 empty] | 0 | 0 | 3.32 | 0 | 0
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 01:31 |  | 2d 01:31 | 2028-07-08 21:03 | 2028-07-10 22:34
TS Fleet 5 | W2\13\005\B | W2 | 13 | 5 | B | 1 Prestrip - Thick | 16.5564 | 16.5564 | 16.5564 | 2028-07-09 04:02 | 2028-07-11 02:42 | 91466.5888 | 91467 | [7 empty] | 0 | 0 | 8.59 | 9.5 | 5359.32
TS6060#1 | W2\07\003\D | W2 | 7 | 3 | D | 7 PostStrip | 36.0841 | 0 | 36.0841 | 2028-07-09 13:58 | 2028-07-11 08:33 | 43933.6879 |  |  | 43934 | [5 empty] | 0 | 0 | 0 | 5.78 | 5760.37
TS5500Exc | SC\61\001\D | SC | 61 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-07-09 15:44 | 2028-07-20 04:53 | 318873.6534 | [6 empty] | 318874 | 238138 | 4.84 | 0 | 0 | 6.8 | 5816
DRE2 | GG\29\009\D | GG | 29 | 9 | D | 6 DL | 100 | 100 | 100 | 2028-07-10 22:34 | 2028-07-16 06:24 | 429990.672 |  |  |  | 10011 | 429991 | 190217 |  |  | 0 | 20.03 | 0 | 6.56 | 5810.03
TS5500Shv | GG\29\010\D | GG | 29 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-07-10 22:34 | 2028-07-13 01:40 | 62311.9051 | [6 empty] | 62312 | 46695 | 4.67 | 0 | 0 | 6.56 | 5810
TS Fleet 5 | W2\14\003\B | W2 | 14 | 3 | B | 1 Prestrip - Thick | 44.9228 | 44.9228 | 44.9228 | 2028-07-11 02:42 | 2028-07-30 07:36 | 903357.9637 | 903358 | [7 empty] | 0 | 0 | 38.16 | 8.89 | 5421.06
TS6060#1 | GG\28\008\D | GG | 28 | 8 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-07-11 08:33 | 2028-07-13 06:02 | 61545.6744 | [6 empty] | 61546 | 46120 | 4.61 | 0 | 0 | 6.56 | 5810
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 04:44 |  | 3d 04:44 | 2028-07-13 01:40 | 2028-07-16 06:24
PH4100A | W2\09\003\B | W2 | 9 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-07-13 02:09 | 2028-09-06 14:49 | 2406572.757 | 2406573 | [7 empty] | 0 | 0 | 112.39 | 9.64 | 5325.99
TS6060#1 | W2\08\003\B | W2 | 8 | 3 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2028-07-13 06:02 | 2028-07-15 06:01 | 64955.573 | [6 empty] | 64956 | 45960 | 1.63 | 0 | 0 | 9.47 | 5333
TS6060#1 | W2\07\003\D | W2 | 7 | 3 | D | 8 Coal Mining | 33.8 | 0 | 33.8 | 2028-07-15 06:01 | 2028-07-16 23:18 | 55867.3863 | [6 empty] | 55867 | 40866 | 1.72 | 0 | 0 | 5.78 | 5760
DRE2 | GG\29\008\D | GG | 29 | 8 | D | 6 DL | 100 | 0 | 0 | 2028-07-16 06:24 | 2028-07-16 06:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\30\013\B | GG | 30 | 13 | B | 6 DL | 100 | 0 | 100 | 2028-07-16 06:24 | 2028-07-18 21:14 | 211314.125 |  |  |  |  | 211314 | 176095 |  |  | 0 | 17.65 | 0 | 12.15 | 5319.97
TS5500Shv | GG\29\009\D | GG | 29 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-07-16 06:24 | 2028-07-18 09:06 | 61826.1616 | [6 empty] | 61826 | 46331 | 4.63 | 0 | 0 | 6.56 | 5810
TS6060#1 | GG\28\007\D | GG | 28 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-07-16 23:18 | 2028-07-18 13:18 | 51431.1832 | [6 empty] | 51431 | 38541 | 4.58 | 0 | 0 | 6.54 | 5811
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 12:07 |  | 0d 12:07 | 2028-07-18 09:06 | 2028-07-18 21:14
TS6060#1 | GG\29\014\B | GG | 29 | 14 | B | 8 Coal Mining | 60.7 | 0 | 60.7 | 2028-07-18 13:18 | 2028-07-19 12:43 | 31684.3733 | [6 empty] | 31684 | 22973 | 2.15 | 0 | 0 | 12.26 | 5292
DRE2 | GG\30\014\B | GG | 30 | 14 | B | 6 DL | 100 | 0 | 100 | 2028-07-18 21:14 | 2028-07-22 02:20 | 259380.2842 |  |  |  |  | 259380 | 216150 |  |  | 0 | 16.85 | 0 | 12.71 | 5259.97
TS5500Shv | GG\30\013\B | GG | 30 | 13 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-07-18 21:14 | 2028-07-20 13:52 | 49552.0959 | [6 empty] | 49552 | 35876 | 3.59 | 0 | 0 | 12.15 | 5320
TS6060#1 | GG\32\012\X1 | GG | 32 | 12 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2028-07-19 12:43 | 2028-07-19 18:35 | 7940.2596 | [6 empty] | 7940 | 5698 | 0.57 | 0 | 0 | 14.49 | 5138
TS6060#1 | GG\29\017\B | GG | 29 | 17 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2028-07-19 18:35 | 2028-07-20 12:33 | 24332.6396 | [6 empty] | 24333 | 17405 | 1.71 | 0 | 0 | 14.75 | 5107
TS5500Exc | W2\08\003\B | W2 | 8 | 3 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2028-07-20 04:53 | 2028-07-22 04:53 | 60453.7016 | [6 empty] | 60454 | 42774 | 1.51 | 0 | 0 | 9.47 | 5333
TS6060#1 | GG\29\018\B | GG | 29 | 18 | B | 8 Coal Mining | 59 | 0 | 59 | 2028-07-20 12:33 | 2028-07-21 06:38 | 24459.6852 | [6 empty] | 24460 | 17322 | 1.73 | 0 | 0 | 16.33 | 5007
TS5500Shv | GG\32\012\X2 | GG | 32 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2028-07-20 13:52 | 2028-07-23 09:25 | 72425.781 | 72426 | [7 empty] | 0 | 0 | 7.28 | 0 | 0
TS6060#1 | GG\29\019\B | GG | 29 | 19 | B | 8 Coal Mining | 67.3 | 0 | 67.3 | 2028-07-21 06:38 | 2028-07-22 00:20 | 23963.7721 | [6 empty] | 23964 | 16774 | 1.68 | 0 | 0 | 18.44 | 4859
TS6060#1 | GG\32\013\X1 | GG | 32 | 13 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2028-07-22 00:20 | 2028-07-22 05:51 | 7457.6577 | [6 empty] | 7458 | 5351 | 0.54 | 0 | 0 | 14.55 | 5132
DRE2 | GG\30\017\B | GG | 30 | 17 | B | 6 DL | 100 | 0 | 100 | 2028-07-22 02:20 | 2028-07-24 10:50 | 190035.7269 |  |  |  |  | 190036 | 158363 |  |  | 0 | 15.78 | 0 | 15.33 | 5068.63
TS5500Exc | W2\07\003\D | W2 | 7 | 3 | D | 8 Coal Mining | 66.2 | 0 | 66.2 | 2028-07-22 04:53 | 2028-07-25 19:38 | 109275.5218 | [6 empty] | 109276 | 79934 | 3.36 | 0 | 0 | 5.78 | 5760
PH4100XPC#1 | GG\32\010\X2 | GG | 32 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2028-07-22 05:43 | 2028-07-23 14:11 | 70337.076 | 70337 | [7 empty] | 0 | 0 | 7.04 | 0 | 0
TS6060#1 | GG\32\013\X2 | GG | 32 | 13 | X2 | 1 Prestrip - Thick | 49.0446 | 0 | 49.0446 | 2028-07-22 05:51 | 2028-07-23 17:27 | 36728.9519 | 36729 | [7 empty] | 0 | 0 | 3.7 | 0 | 0
TS5500Shv | W2\08\003\D | W2 | 8 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-07-23 09:25 | 2028-08-08 08:58 | 411154.1209 | 411154 | [7 empty] | 0 | 0 | 20.9 | 5.77 | 5761.5
PH4100XPC#1 | GG\32\010\B | GG | 32 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-07-23 14:11 | 2028-07-24 22:19 | 69621.5799 | 69622 | [7 empty] | 0 | 0 | 6.97 | 11.08 | 5441.85
TS6060#1 | GG\28\013\D | GG | 28 | 13 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2028-07-23 17:27 | 2028-07-24 16:12 | 30800.8268 | [6 empty] | 30801 | 22988 | 2.3 | 0 | 0 | 6.82 | 5785
DRE2 | GG\30\018\B | GG | 30 | 18 | B | 6 DL | 100 | 0 | 100 | 2028-07-24 10:50 | 2028-07-26 18:01 | 185623.9008 |  |  |  |  | 185624 | 154687 |  |  | 0 | 15.93 | 0 | 17.36 | 4930.25
TS6060#1 | GG\32\014\X1 | GG | 32 | 14 | X1 | 8 Coal Mining | 52.6 | 0 | 52.6 | 2028-07-24 16:12 | 2028-07-25 00:44 | 11538.8718 | [6 empty] | 11539 | 8282 | 0.5 | 0 | 0 | 14.63 | 5125
PH4100XPC#1 | GG\32\011\X2 | GG | 32 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.5612 | 2028-07-24 22:19 | 2028-07-25 15:56 | 38141.0859 | 38141 | [7 empty] | 0 | 0 | 3.83 | 0 | 0
TS6060#1 | GG\32\014\X2 | GG | 32 | 14 | X2 | 1 Prestrip - Thick | 41.3921 | 0 | 41.3921 | 2028-07-25 00:44 | 2028-07-27 07:14 | 56231.4966 | 56231 | [7 empty] | 0 | 0 | 3.43 | 0 | 0
PH4100XPC#1 | GG\32\011\B | GG | 32 | 11 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-07-25 15:56 | 2028-07-27 00:51 | 71311.2974 | 71311 | [7 empty] | 0 | 0 | 7.14 | 11.73 | 5387.95
TS5500Exc | W2\04\003\D | W2 | 4 | 3 | D | 7 PostStrip | 58.9035 | 0 | 58.9035 | 2028-07-25 19:38 | 2028-07-29 01:09 | 68555.4847 |  |  | 68555 | [5 empty] | 0 | 0 | 0 | 5.72 | 5762.6
DRE2 | GG\30\019\B | GG | 30 | 19 | B | 6 DL | 100 | 0 | 100 | 2028-07-26 18:01 | 2028-07-28 18:33 | 163277.5414 |  |  |  |  | 163278 | 136065 |  |  | 0 | 16.29 | 0 | 19.74 | 4756.77
PH4100XPC#1 | GG\32\012\A | GG | 32 | 12 | A | 1 Prestrip - Thick | 100 | 0 | 100 | 2028-07-27 00:51 | 2028-07-28 13:22 | 79117.7493 | 79118 | [7 empty] | 0 | 0 | 7.93 | 0 | 0
TS6060#1 | GG\28\014\D | GG | 28 | 14 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2028-07-27 07:14 | 2028-07-28 03:27 | 27372.5664 | [6 empty] | 27373 | 20397 | 2.26 | 0 | 0 | 6.9 | 5776
TS6060#1 | CP\03\004\D | CP | 3 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-07-28 03:27 | 2028-11-09 09:58 | 2582098.685 | 2582099 | [7 empty] | 0 | 0 | 52.29 | 6.26 | 5856.3
PH4100XPC#1 | GG\32\012\B | GG | 32 | 12 | B | 1 Prestrip - Thick | 100 | 85.601 | 85.601 | 2028-07-28 13:22 | 2028-07-29 09:25 | 43448.7475 | 43449 | [7 empty] | 0 | 0 | 4.34 | 12.26 | 5336.58
DRE2 | GG\29\014\D | GG | 29 | 14 | D | 6 DL | 100 | 100 | 100 | 2028-07-28 18:33 | 2028-08-04 00:39 | 504870.796 |  |  |  | 11755 | 504871 | 223342 |  |  | 0 | 23.49 | 0 | 6.87 | 5778.1
TS5500Exc | GG\32\012\B | GG | 32 | 12 | B | 1 Prestrip - Thick | 100 | 14.399 | 14.399 | 2028-07-29 01:09 | 2028-07-29 09:25 | 7308.5695 | 7309 | [7 empty] | 0 | 0 | 0.73 | 12.26 | 5336.58
TS5500Exc | W2\04\003\D | W2 | 4 | 3 | D | 7 PostStrip | 41.0965 | 0 | 41.0965 | 2028-07-29 09:25 | 2028-07-31 15:30 | 47830.6232 |  |  | 47831 | [5 empty] | 0 | 0 | 0 | 5.72 | 5762.6
PH4100XPC#1 | GG\32\013\X2 | GG | 32 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 50.9554 | 2028-07-29 09:25 | 2028-07-30 03:02 | 38159.9501 | 38160 | [7 empty] | 0 | 0 | 3.85 | 0 | 0
PH4100XPC#1 | GG\32\013\B | GG | 32 | 13 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-07-30 03:02 | 2028-07-31 22:11 | 93487.2465 | 93487 | [7 empty] | 0 | 0 | 9.37 | 12.21 | 5324.33
TS Fleet 5 | GG\32\014\X2 | GG | 32 | 14 | X2 | 1 Prestrip - Thick | 56.9953 | 0 | 56.9953 | 2028-07-30 07:36 | 2028-07-31 23:07 | 77428.5839 | 77429 | [7 empty] | 0 | 0 | 4.73 | 0 | 0
TS5500Exc | W2\04\003\D | W2 | 4 | 3 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2028-07-31 15:30 | 2028-08-02 05:34 | 47956.6542 | [6 empty] | 47957 | 35049 | 2.32 | 0 | 0 | 5.72 | 5763
PH4100XPC#1 | GG\32\014\X2 | GG | 32 | 14 | X2 | 1 Prestrip - Thick | 100 | 0 | 1.6127 | 2028-07-31 22:11 | 2028-07-31 23:11 | 2190.8375 | 2191 | [7 empty] | 0 | 0 | 0.13 | 0 | 0
TS Fleet 5 | SC\61\002\D | SC | 61 | 2 | D | 1 Prestrip - Thick | 84.4528 | 84.4528 | 84.4528 | 2028-07-31 23:07 | 2028-08-24 21:12 | 1125215.556 | 1125216 | [7 empty] | 0 | 0 | 32.83 | 6.34 | 5856
PH4100XPC#1 | GG\32\014\B | GG | 32 | 14 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-07-31 23:11 | 2028-08-03 16:34 | 141650.7864 | 141651 | [7 empty] | 0 | 0 | 8.88 | 13.66 | 5201.45
TS5500Exc | W1\07\003\D | W1 | 7 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2028-08-02 05:34 | 2028-08-06 23:50 | 101047.4057 |  |  | 101047 | [5 empty] | 0 | 0 | 0 | 8.11 | 5544.88
PH4100XPC#1 | GG\33\007\X1 | GG | 33 | 7 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-08-03 16:34 | 2028-08-03 16:34 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\33\007\B | GG | 33 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-08-03 16:34 | 2028-08-03 16:34 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\33\008\X1 | GG | 33 | 8 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-08-03 16:34 | 2028-08-03 16:34 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\33\008\X2 | GG | 33 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-08-03 16:34 | 2028-08-03 16:34 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\33\008\B | GG | 33 | 8 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-08-03 16:34 | 2028-08-03 16:34 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\33\009\X1 | GG | 33 | 9 | X1 | 1 Prestrip - Thick | 100 | 79.6454 | 79.6454 | 2028-08-03 16:34 | 2028-08-15 14:18 | 643755.4217 | 643755 | [7 empty] | 0 | 0 | 80.57 | 14.7 | 5105.86
DRE2 | GG\29\017\D | GG | 29 | 17 | D | 6 DL | 100 | 100 | 100 | 2028-08-04 00:39 | 2028-08-10 10:17 | 516765.3707 |  |  |  | 12032 | 516765 | 228604 |  |  | 0 | 24.23 | 0 | 6.93 | 5777.25
TS5500Exc | W1\07\003\D | W1 | 7 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-08-06 23:50 | 2028-08-10 19:50 | 115901.9614 | [6 empty] | 115902 | 83503 | 4.18 | 0 | 0 | 8.11 | 5545
TS5500Shv | GG\32\012\B | GG | 32 | 12 | B | 8 Coal Mining | 47.4 | 0 | 47.4 | 2028-08-08 08:58 | 2028-08-09 04:46 | 24143.6152 | [6 empty] | 24144 | 17408 | 1.74 | 0 | 0 | 12.26 | 5337
TS5500Shv | GG\33\009\X1 | GG | 33 | 9 | X1 | 1 Prestrip - Thick | 30.9943 | 20.3546 | 20.3546 | 2028-08-09 04:46 | 2028-08-15 14:18 | 164521.2405 | 164521 | [7 empty] | 0 | 0 | 20.59 | 14.7 | 5105.86
DRE2 | GG\29\018\D | GG | 29 | 18 | D | 6 DL | 100 | 100 | 100 | 2028-08-10 10:17 | 2028-08-16 19:12 | 514404.8994 |  |  |  | 11977 | 514405 | 227560 |  |  | 0 | 23.94 | 0 | 6.91 | 5779.62
TS5500Exc | W2\08\003\D | W2 | 8 | 3 | D | 7 PostStrip | 49.3844 | 0 | 49.3844 | 2028-08-10 19:50 | 2028-08-13 20:03 | 63860.714 |  |  | 63861 | [5 empty] | 0 | 0 | 0 | 5.77 | 5761.5
TS5500Exc | GG\33\012\X1 | GG | 33 | 12 | X1 | 1 Prestrip - Thick | 25.7101 | 25.7101 | 25.7101 | 2028-08-13 20:03 | 2028-08-21 11:15 | 162104.6435 | 162105 | [7 empty] | 0 | 0 | 15.98 | 14.42 | 5141.57
TS5500Shv | GG\33\009\X1 | GG | 33 | 9 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2028-08-15 14:18 | 2028-08-16 01:15 | 13345.2496 | [6 empty] | 13345 | 9573 | 0.96 | 0 | 0 | 14.7 | 5106
PH4100XPC#1 | GG\33\010\X1 | GG | 33 | 10 | X1 | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-08-15 14:18 | 2028-08-29 23:14 | 755547.2154 | 755547 | [7 empty] | 0 | 0 | 91.79 | 14.2 | 5152.83
TS5500Shv | GG\33\009\X2 | GG | 33 | 9 | X2 | 1 Prestrip - Thick | 49.0245 | 0 | 49.0245 | 2028-08-16 01:15 | 2028-08-17 08:17 | 33269.0489 | 33269 | [7 empty] | 0 | 0 | 3.33 | 0 | 0
DRE2 | GG\29\019\D | GG | 29 | 19 | D | 6 DL | 100 | 100 | 100 | 2028-08-16 19:12 | 2028-08-23 01:48 | 506600.8683 |  |  |  | 11795 | 506601 | 224107 |  |  | 0 | 23.58 | 0 | 6.85 | 5784.91
TS5500Shv | GG\33\011\X1 | GG | 33 | 11 | X1 | 1 Prestrip - Thick | 14.6307 | 14.6307 | 14.6307 | 2028-08-17 08:17 | 2028-08-21 08:13 | 102416.1629 | 102416 | [7 empty] | 0 | 0 | 10.17 | 14.3 | 5149.53
TS5500Shv | GG\30\014\B | GG | 30 | 14 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-08-21 08:13 | 2028-08-23 10:46 | 61656.1343 | [6 empty] | 61656 | 44585 | 3.62 | 0 | 0 | 12.71 | 5260
TS5500Exc | GG\33\013\X1 | GG | 33 | 13 | X1 | 1 Prestrip - Thick | 27.851 | 27.851 | 27.851 | 2028-08-21 11:15 | 2028-08-28 09:51 | 147472.6237 | 147473 | [7 empty] | 0 | 0 | 14.44 | 14.5 | 5136
DRE2 | GG\29\020\D | GG | 29 | 20 | D | 6 DL | 100 | 100 | 100 | 2028-08-23 01:48 | 2028-08-28 06:26 | 419191.0827 |  |  |  | 6658 | 419191 | 120209 |  |  | 0 | 21.03 | 0 | 6.78 | 5789.85
TS5500Shv | GG\30\017\B | GG | 30 | 17 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-08-23 10:46 | 2028-08-25 00:04 | 45471.1908 | [6 empty] | 45471 | 32406 | 3.23 | 0 | 0 | 15.33 | 5069
TS Fleet 5 | GG\33\011\X1 | GG | 33 | 11 | X1 | 1 Prestrip - Thick | 39.8052 | 39.8052 | 39.8052 | 2028-08-24 21:12 | 2028-08-30 19:22 | 278640.4257 | 278640 | [7 empty] | 0 | 0 | 27.68 | 14.3 | 5149.53
TS5500Shv | GG\30\018\B | GG | 30 | 18 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-08-25 00:04 | 2028-08-26 08:00 | 38946.2766 | [6 empty] | 38946 | 27427 | 2.74 | 0 | 0 | 17.36 | 4930
TS5500Shv | GG\30\019\B | GG | 30 | 19 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-08-26 08:00 | 2028-08-27 11:00 | 32917.4163 | [6 empty] | 32917 | 22875 | 2.29 | 0 | 0 | 19.74 | 4757
TS5500Shv | GG\29\014\D | GG | 29 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-08-27 11:00 | 2028-08-29 09:10 | 56300.6606 | [6 empty] | 56301 | 41952 | 4.23 | 0 | 0 | 6.87 | 5778
DRE2 | GG\29\013\D | GG | 29 | 13 | D | 6 DL | 100 | 100 | 100 | 2028-08-28 06:26 | 2028-09-03 07:09 | 486794.7531 |  |  |  | 11334 | 486795 | 215346 |  |  | 0 | 22.7 | 0 | 6.8 | 5785.98
TS5500Exc | W1\08\002\D | W1 | 8 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2028-08-28 09:51 | 2028-09-01 04:58 | 80572.5538 |  |  | 80573 | [5 empty] | 0 | 0 | 0 | 8.16 | 5544.72
TS5500Shv | GG\29\017\D | GG | 29 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-08-29 09:10 | 2028-08-31 10:51 | 60591.1722 | [6 empty] | 60591 | 45117 | 4.56 | 0 | 0 | 6.93 | 5777
PH4100XPC#1 | GG\33\009\X2 | GG | 33 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 50.9755 | 2028-08-29 23:14 | 2028-08-30 15:12 | 34592.989 | 34593 | [7 empty] | 0 | 0 | 3.46 | 0 | 0
PH4100XPC#1 | GG\33\009\B | GG | 33 | 9 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-08-30 15:12 | 2028-09-01 02:13 | 75842.9974 | 75843 | [7 empty] | 0 | 0 | 7.62 | 10.85 | 5455.22
TS Fleet 5 | GG\33\012\X1 | GG | 33 | 12 | X1 | 1 Prestrip - Thick | 34.6388 | 34.6388 | 34.6388 | 2028-08-30 19:22 | 2028-09-04 10:47 | 218401.1708 | 218401 | [7 empty] | 0 | 0 | 21.53 | 14.42 | 5141.57
TS5500Shv | GG\33\010\X1 | GG | 33 | 10 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2028-08-31 10:51 | 2028-09-01 01:04 | 17316.8652 | [6 empty] | 17317 | 12448 | 1.24 | 0 | 0 | 14.2 | 5153
TS5500Shv | GG\29\018\D | GG | 29 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-09-01 01:04 | 2028-09-03 03:59 | 62088.9859 | [6 empty] | 62089 | 46270 | 4.63 | 0 | 0 | 6.91 | 5780
PH4100XPC#1 | GG\33\010\X2 | GG | 33 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2028-09-01 02:13 | 2028-09-02 10:51 | 70698.888 | 70699 | [7 empty] | 0 | 0 | 7.06 | 0 | 0
TS5500Exc | W1\08\002\D | W1 | 8 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-09-01 04:58 | 2028-09-04 09:07 | 95919.9133 | [6 empty] | 95920 | 69122 | 4.45 | 0 | 0 | 8.16 | 5545
PH4100XPC#1 | GG\33\010\B | GG | 33 | 10 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-09-02 10:51 | 2028-09-03 18:24 | 68365.8325 | 68366 | [7 empty] | 0 | 0 | 6.87 | 11.15 | 5435.16
TS5500Shv | GG\29\019\D | GG | 29 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-09-03 03:59 | 2028-09-05 07:04 | 62307.6121 | [6 empty] | 62308 | 46507 | 4.65 | 0 | 0 | 6.85 | 5785
DRE2 | GG\31\010\B | GG | 31 | 10 | B | 6 DL | 100 | 0 | 100 | 2028-09-03 07:09 | 2028-09-06 12:37 | 260585.77 |  |  |  |  | 260586 | 200451 |  |  | 0 | 20.01 | 0 | 11.04 | 5445.71
PH4100XPC#1 | GG\33\011\X1 | GG | 33 | 11 | X1 | 1 Prestrip - Thick | 100 | 45.5641 | 45.5641 | 2028-09-03 18:24 | 2028-09-09 22:44 | 318953.0131 | 318953 | [7 empty] | 0 | 0 | 31.69 | 14.3 | 5149.53
TS5500Exc | W1\08\003\D | W1 | 8 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2028-09-04 09:07 | 2028-09-09 05:18 | 102763.9 |  |  | 102764 | [5 empty] | 0 | 0 | 0 | 8.23 | 5535.18
TS Fleet 5 | GG\33\013\X1 | GG | 33 | 13 | X1 | 1 Prestrip - Thick | 33.7477 | 33.7477 | 33.7477 | 2028-09-04 10:47 | 2028-09-08 05:58 | 178696.2176 | 178696 | [7 empty] | 0 | 0 | 17.5 | 14.5 | 5136
TS5500Shv | GG\29\020\D | GG | 29 | 20 | D | 7 PostStrip | 100 | 0 | 100 | 2028-09-05 07:04 | 2028-09-06 20:00 | 39583.7084 |  |  | 39584 | [5 empty] | 0 | 0 | 0 | 6.78 | 5789.85
DRE2 | GG\31\009\B | GG | 31 | 9 | B | 6 DL | 100 | 0 | 100 | 2028-09-06 12:37 | 2028-09-09 19:07 | 264054.6545 |  |  |  |  | 264055 | 203119 |  |  | 0 | 20.4 | 0 | 10.66 | 5471.26
PH4100A | SC\61\002\D | SC | 61 | 2 | D | 1 Prestrip - Thick | 100 | 15.5472 | 15.5472 | 2028-09-06 14:49 | 2028-09-11 16:35 | 207144.5603 | 207145 | [7 empty] | 0 | 0 | 6.04 | 6.34 | 5856
TS5500Shv | GG\29\020\D | GG | 29 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-09-06 20:00 | 2028-09-08 09:05 | 45218.3379 | [6 empty] | 45218 | 33807 | 4.47 | 0 | 0 | 6.78 | 5790
TS Fleet 5 | GG\33\014\X1 | GG | 33 | 14 | X1 | 1 Prestrip - Thick | 47.1908 | 47.1908 | 47.1908 | 2028-09-08 05:58 | 2028-09-15 14:18 | 345614.3032 | 345614 | [7 empty] | 0 | 0 | 17.45 | 14.57 | 5129.61
TS5500Shv | GG\29\013\D | GG | 29 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-09-08 09:05 | 2028-09-10 09:02 | 58481.8663 | [6 empty] | 58482 | 43648 | 4.37 | 0 | 0 | 6.8 | 5786
TS5500Exc | W2\09\003\B | W2 | 9 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-09-09 05:18 | 2028-09-12 09:48 | 96341.5374 | [6 empty] | 96342 | 68170 | 2.56 | 0 | 0 | 9.64 | 5326
DRE2 | GG\31\008\B | GG | 31 | 8 | B | 6 DL | 100 | 0 | 0 | 2028-09-09 19:07 | 2028-09-09 19:07 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\30\012\D | GG | 30 | 12 | D | 6 DL | 100 | 100 | 100 | 2028-09-09 19:07 | 2028-09-15 12:10 | 461026.0402 |  |  |  | 10734 | 461026 | 203946 |  |  | 0 | 21.49 | 0 | 6.69 | 5798.33
PH4100XPC#1 | GG\33\012\X1 | GG | 33 | 12 | X1 | 1 Prestrip - Thick | 100 | 39.6511 | 39.6511 | 2028-09-09 22:44 | 2028-09-14 19:01 | 250003.7332 | 250004 | [7 empty] | 0 | 0 | 24.65 | 14.42 | 5141.57
TS5500Shv | GG\33\011\X1 | GG | 33 | 11 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2028-09-10 09:02 | 2028-09-10 22:39 | 16595.0273 | [6 empty] | 16595 | 11923 | 1.2 | 0 | 0 | 14.3 | 5150
TS5500Shv | GG\31\010\B | GG | 31 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-09-10 22:39 | 2028-09-12 16:57 | 51581.1851 | [6 empty] | 51581 | 37495 | 3.75 | 0 | 0 | 11.04 | 5446
PH4100A | W2\08\004\B | W2 | 8 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-09-11 16:35 | 2028-10-13 01:25 | 1306635.042 | 1306635 | [7 empty] | 0 | 0 | 65.2 | 9.73 | 5305.96
TS5500Exc | SC\61\002\D | SC | 61 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2028-09-12 09:48 | 2028-09-21 18:34 | 198793.6516 |  |  | 198794 | [5 empty] | 0 | 0 | 0 | 6.34 | 5856
TS5500Shv | GG\33\020\B | GG | 33 | 20 | B | 1 Prestrip - Thick | 20.9167 | 20.9167 | 20.9167 | 2028-09-12 16:57 | 2028-09-14 09:45 | 43660.8858 | 43661 | [7 empty] | 0 | 0 | 4.97 | 13.17 | 5279.32
TS5500Shv | GG\31\009\B | GG | 31 | 9 | B | 8 Coal Mining | 43.2 | 0 | 43.2 | 2028-09-14 09:45 | 2028-09-15 04:10 | 22452.1566 | [6 empty] | 22452 | 16366 | 1.64 | 0 | 0 | 10.66 | 5471
PH4100XPC#1 | GG\33\011\X2 | GG | 33 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 80.1019 | 2028-09-14 19:01 | 2028-09-15 21:36 | 57604.1037 | 57604 | [7 empty] | 0 | 0 | 5.79 | 0 | 0
TS5500Shv | GG\33\012\X1 | GG | 33 | 12 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2028-09-15 04:10 | 2028-09-15 16:43 | 15313.5247 | [6 empty] | 15314 | 10999 | 1.1 | 0 | 0 | 14.42 | 5142
DRE2 | GG\30\011\D | GG | 30 | 11 | D | 6 DL | 100 | 100 | 100 | 2028-09-15 12:10 | 2028-09-21 04:34 | 458791.8961 |  |  |  | 8302 | 458792 | 199237 |  |  | 0 | 20.78 | 0 | 6.6 | 5806.89
TS Fleet 5 | GG\33\011\X2 | GG | 33 | 11 | X2 | 1 Prestrip - Thick | 46.4388 | 0 | 19.8981 | 2028-09-15 14:18 | 2028-09-15 21:36 | 14309.4123 | 14309 | [7 empty] | 0 | 0 | 1.44 | 0 | 0
TS5500Shv | GG\30\012\D | GG | 30 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-09-15 16:43 | 2028-09-17 18:47 | 61053.8169 | [6 empty] | 61054 | 45642 | 4.56 | 0 | 0 | 6.69 | 5798
TS Fleet 5 | GG\33\011\B | GG | 33 | 11 | B | 1 Prestrip - Thick | 46.4388 | 46.4388 | 46.4388 | 2028-09-15 21:36 | 2028-09-16 13:24 | 30984.6862 | 30985 | [7 empty] | 0 | 0 | 3.1 | 11.77 | 5384.47
PH4100XPC#1 | GG\33\011\B | GG | 33 | 11 | B | 1 Prestrip - Thick | 100 | 53.5612 | 53.5612 | 2028-09-15 21:36 | 2028-09-16 14:06 | 35736.8759 | 35737 | [7 empty] | 0 | 0 | 3.58 | 11.77 | 5384.47
TS Fleet 5 | GG\33\012\X2 | GG | 33 | 12 | X2 | 1 Prestrip - Thick | 46.4388 | 0 | 46.4388 | 2028-09-16 13:24 | 2028-09-17 06:42 | 33889.4176 | 33889 | [7 empty] | 0 | 0 | 3.41 | 0 | 0
PH4100XPC#1 | GG\33\012\X2 | GG | 33 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.5612 | 2028-09-16 14:06 | 2028-09-17 08:08 | 39087.1124 | 39087 | [7 empty] | 0 | 0 | 3.93 | 0 | 0
TS Fleet 5 | GG\33\017\B | GG | 33 | 17 | B | 1 Prestrip - Thick | 47.1475 | 47.1475 | 47.1475 | 2028-09-17 06:42 | 2028-09-21 11:46 | 198100.2472 | 198100 | [7 empty] | 0 | 0 | 19.69 | 14.2 | 5188.15
PH4100XPC#1 | GG\33\012\A | GG | 33 | 12 | A | 1 Prestrip - Thick | 100 | 0 | 100 | 2028-09-17 08:08 | 2028-09-18 18:01 | 73409.5733 | 73410 | [7 empty] | 0 | 0 | 7.36 | 0 | 0
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 23:34 |  | 1d 23:34 | 2028-09-17 18:47 | 2028-09-19 18:21
PH4100XPC#1 | GG\33\012\B | GG | 33 | 12 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-09-18 18:01 | 2028-09-19 18:21 | 52728.5621 | 52729 | [7 empty] | 0 | 0 | 5.27 | 12.32 | 5333.9
PH4100XPC#1 | GG\33\013\X1 | GG | 33 | 13 | X1 | 1 Prestrip - Thick | 100 | 38.4013 | 38.4013 | 2028-09-19 18:21 | 2028-09-23 17:29 | 203337.5266 | 203338 | [7 empty] | 0 | 0 | 19.92 | 14.5 | 5136
TS5500Shv | GG\33\012\B | GG | 33 | 12 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-09-19 18:21 | 2028-09-21 12:28 | 51350.8806 | [6 empty] | 51351 | 36980 | 3.7 | 0 | 0 | 12.32 | 5334
DRE2 | GG\30\010\D | GG | 30 | 10 | D | 6 DL | 100 | 100 | 100 | 2028-09-21 04:34 | 2028-09-26 13:56 | 435144.0354 |  |  |  | 10131 | 435144 | 192497 |  |  | 0 | 20.29 | 0 | 6.57 | 5809.6
TS Fleet 5 | GG\33\018\B | GG | 33 | 18 | B | 1 Prestrip - Thick | 46.7928 | 46.7928 | 46.7928 | 2028-09-21 11:46 | 2028-09-24 16:51 | 151093.8394 | 151094 | [7 empty] | 0 | 0 | 15.29 | 15.82 | 5067.91
TS5500Shv | GG\30\011\D | GG | 30 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-09-21 12:28 | 2028-09-23 15:39 | 62413.3277 | [6 empty] | 62413 | 46734 | 4.67 | 0 | 0 | 6.6 | 5807
TS5500Exc | SC\61\002\D | SC | 61 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-09-21 18:34 | 2028-10-01 17:10 | 300531.2277 | [6 empty] | 300531 | 225503 | 4.7 | 0 | 0 | 6.34 | 5856
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 01:50 |  | 0d 01:50 | 2028-09-23 15:39 | 2028-09-23 17:29
PH4100XPC#1 | GG\33\014\X1 | GG | 33 | 14 | X1 | 1 Prestrip - Thick | 100 | 52.8092 | 52.8092 | 2028-09-23 17:29 | 2028-10-01 09:29 | 386761.9394 | 386762 | [7 empty] | 0 | 0 | 19.53 | 14.57 | 5129.61
TS5500Shv | GG\33\013\X1 | GG | 33 | 13 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2028-09-23 17:29 | 2028-09-24 05:15 | 14352.4914 | [6 empty] | 14352 | 10308 | 1.04 | 0 | 0 | 14.5 | 5136
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 08:40 |  | 2d 08:40 | 2028-09-24 05:15 | 2028-09-26 13:56
TS Fleet 5 | GG\33\013\X2 | GG | 33 | 13 | X2 | 1 Prestrip - Thick | 46.4388 | 0 | 46.4388 | 2028-09-24 16:51 | 2028-09-25 10:45 | 35076.5654 | 35077 | [7 empty] | 0 | 0 | 3.54 | 0 | 0
TS Fleet 5 | GG\33\019\B | GG | 33 | 19 | B | 1 Prestrip - Thick | 45.9931 | 45.9931 | 45.9931 | 2028-09-25 10:45 | 2028-09-27 14:45 | 101928.0618 | 101928 | [7 empty] | 0 | 0 | 9.58 | 18.68 | 4843.95
DRE2 | GG\30\009\D | GG | 30 | 9 | D | 6 DL | 100 | 100 | 100 | 2028-09-26 13:56 | 2028-10-01 20:22 | 425289.1939 |  |  |  | 7920 | 425289 | 190073 |  |  | 0 | 19.81 | 0 | 6.56 | 5810.48
TS5500Shv | GG\30\010\D | GG | 30 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-09-26 13:56 | 2028-09-28 16:53 | 62132.4694 | [6 empty] | 62132 | 46561 | 4.66 | 0 | 0 | 6.57 | 5810
TS Fleet 5 | GG\33\020\B | GG | 33 | 20 | B | 1 Prestrip - Thick | 36.7169 | 36.7169 | 36.7169 | 2028-09-27 14:45 | 2028-09-29 05:52 | 76641.5813 | 76642 | [7 empty] | 0 | 0 | 8.72 | 13.17 | 5279.32
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 16:36 |  | 2d 16:36 | 2028-09-28 16:53 | 2028-10-01 09:29
TS Fleet 5 | W2\09\003\D | W2 | 9 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-09-29 05:52 | 2028-10-07 21:47 | 407543.6955 | 407544 | [7 empty] | 0 | 0 | 21.53 | 5.72 | 5765.29
PH4100XPC#1 | GG\33\013\X2 | GG | 33 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 53.5612 | 2028-10-01 09:29 | 2028-10-02 04:09 | 40456.3356 | 40456 | [7 empty] | 0 | 0 | 4.08 | 0 | 0
TS5500Shv | GG\33\014\X1 | GG | 33 | 14 | X1 | 8 Coal Mining | 100 | 0 | 100 | 2028-10-01 09:29 | 2028-10-02 05:53 | 24878.6578 | [6 empty] | 24879 | 17861 | 0.97 | 0 | 0 | 14.57 | 5130
TS5500Exc | W1\08\003\D | W1 | 8 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-10-01 17:10 | 2028-10-05 15:37 | 118981.106 | [6 empty] | 118981 | 85725 | 4.22 | 0 | 0 | 8.23 | 5535
DRE2 | GG\30\008\D | GG | 30 | 8 | D | 6 DL | 100 | 0 | 0 | 2028-10-01 20:22 | 2028-10-01 20:22 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\31\013\B | GG | 31 | 13 | B | 6 DL | 100 | 0 | 100 | 2028-10-01 20:22 | 2028-10-04 12:24 | 215396.6515 |  |  |  |  | 215397 | 179497 |  |  | 0 | 17.99 | 0 | 12.17 | 5322.94
PH4100XPC#1 | GG\33\013\B | GG | 33 | 13 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-10-02 04:09 | 2028-10-03 20:08 | 86605.8945 | 86606 | [7 empty] | 0 | 0 | 8.68 | 12.3 | 5322.29
TS5500Shv | GG\30\009\D | GG | 30 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-10-02 05:53 | 2028-10-04 08:37 | 61866.9455 | [6 empty] | 61867 | 46361 | 4.64 | 0 | 0 | 6.56 | 5810
PH4100XPC#1 | GG\33\014\X2 | GG | 33 | 14 | X2 | 1 Prestrip - Thick | 100 | 0 | 100 | 2028-10-03 20:08 | 2028-10-06 17:25 | 150108.201 | 150108 | [7 empty] | 0 | 0 | 8.22 | 0 | 0
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 03:47 |  | 0d 03:47 | 2028-10-04 08:37 | 2028-10-04 12:24
DRE2 | GG\31\014\B | GG | 31 | 14 | B | 6 DL | 100 | 0 | 100 | 2028-10-04 12:24 | 2028-10-08 05:12 | 298730.0755 |  |  |  |  | 298730 | 248942 |  |  | 0 | 17.26 | 0 | 13.3 | 5220.29
TS5500Shv | GG\31\013\B | GG | 31 | 13 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-10-04 12:24 | 2028-10-06 05:21 | 49936.1318 | [6 empty] | 49936 | 36112 | 3.62 | 0 | 0 | 12.17 | 5323
TS5500Exc | SC\50\020\D | SC | 50 | 20 | D | 1 Prestrip - Thick | 64.5229 | 64.5229 | 64.5229 | 2028-10-05 15:37 | 2028-11-10 17:05 | 766603.7289 | 766604 | [7 empty] | 0 | 0 | 35.39 | 7.29 | 5770.13
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 12:04 |  | 0d 12:04 | 2028-10-06 05:21 | 2028-10-06 17:25
PH4100XPC#1 | GG\33\014\B | GG | 33 | 14 | B | 1 Prestrip - Thick | 100 | 62.5252 | 62.5252 | 2028-10-06 17:25 | 2028-10-08 11:38 | 91483.1626 | 91483 | [7 empty] | 0 | 0 | 5.18 | 13.55 | 5219.65
TS5500Shv | GG\33\014\B | GG | 33 | 14 | B | 1 Prestrip - Thick | 18.9225 | 18.9225 | 18.9225 | 2028-10-06 17:25 | 2028-10-07 19:14 | 27686.3594 | 27686 | [7 empty] | 0 | 0 | 1.57 | 13.55 | 5219.65
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 09:58 |  | 0d 09:58 | 2028-10-07 19:14 | 2028-10-08 05:12
TS Fleet 5 | GG\33\014\B | GG | 33 | 14 | B | 1 Prestrip - Thick | 37.6514 | 18.5523 | 18.5523 | 2028-10-07 21:47 | 2028-10-08 11:38 | 27144.5893 | 27145 | [7 empty] | 0 | 0 | 1.54 | 13.55 | 5219.65
DRE2 | GG\31\017\B | GG | 31 | 17 | B | 6 DL | 100 | 0 | 100 | 2028-10-08 05:12 | 2028-10-10 14:12 | 191712.9482 |  |  |  |  | 191713 | 159761 |  |  | 0 | 15.91 | 0 | 15.54 | 5062.21
TS5500Shv | GG\31\014\B | GG | 31 | 14 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-10-08 05:12 | 2028-10-10 15:28 | 71055.4068 | [6 empty] | 71055 | 51181 | 3.69 | 0 | 0 | 13.3 | 5220
PH4100XPC#1 | GG\33\017\B | GG | 33 | 17 | B | 1 Prestrip - Thick | 100 | 52.8525 | 52.8525 | 2028-10-08 11:38 | 2028-10-12 21:06 | 222071.0509 | 222071 | [7 empty] | 0 | 0 | 22.07 | 14.2 | 5188.15
TS Fleet 5 | SC\61\003\D | SC | 61 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-10-08 11:38 | 2028-11-03 01:10 | 1202505.57 | 1202506 | [7 empty] | 0 | 0 | 34.48 | 6.41 | 5850.01
DRE2 | GG\31\018\B | GG | 31 | 18 | B | 6 DL | 100 | 0 | 100 | 2028-10-10 14:12 | 2028-10-12 21:01 | 184412.7297 |  |  |  |  | 184413 | 153677 |  |  | 0 | 15.81 | 0 | 17.81 | 4899.54
TS5500Shv | GG\31\017\B | GG | 31 | 17 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-10-10 15:28 | 2028-10-12 06:20 | 47389.5663 | [6 empty] | 47390 | 33698 | 3.36 | 0 | 0 | 15.54 | 5062
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 14:41 |  | 0d 14:41 | 2028-10-12 06:20 | 2028-10-12 21:01
DRE2 | GG\31\019\B | GG | 31 | 19 | B | 6 DL | 100 | 0 | 100 | 2028-10-12 21:01 | 2028-10-15 07:42 | 197396.0855 |  |  |  |  | 197396 | 164497 |  |  | 0 | 16.16 | 0 | 20.94 | 4663.05
TS5500Shv | GG\31\018\B | GG | 31 | 18 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-10-12 21:01 | 2028-10-14 04:01 | 37796.9689 | [6 empty] | 37797 | 26536 | 2.64 | 0 | 0 | 17.81 | 4900
PH4100XPC#1 | GG\33\018\B | GG | 33 | 18 | B | 1 Prestrip - Thick | 100 | 53.2072 | 53.2072 | 2028-10-12 21:06 | 2028-10-16 05:32 | 171805.9246 | 171806 | [7 empty] | 0 | 0 | 17.39 | 15.82 | 5067.91
PH4100A | W2\09\004\B | W2 | 9 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-10-13 01:25 | 2028-11-14 12:22 | 1356142.017 | 1356142 | [7 empty] | 0 | 0 | 68.06 | 9.6 | 5321.82
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 03:41 |  | 1d 03:41 | 2028-10-14 04:01 | 2028-10-15 07:42
DRE2 | GG\30\013\D | GG | 30 | 13 | D | 6 DL | 100 | 100 | 100 | 2028-10-15 07:42 | 2028-10-21 06:13 | 479351.1757 |  |  |  | 11161 | 479351 | 212053 |  |  | 0 | 22.35 | 0 | 6.79 | 5787.33
TS5500Shv | GG\31\019\B | GG | 31 | 19 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-10-15 07:42 | 2028-10-16 09:11 | 31069.2368 | [6 empty] | 31069 | 21454 | 2.14 | 0 | 0 | 20.94 | 4663
PH4100XPC#1 | GG\33\019\B | GG | 33 | 19 | B | 1 Prestrip - Thick | 100 | 54.0069 | 54.0069 | 2028-10-16 05:32 | 2028-10-18 11:48 | 119687.837 | 119688 | [7 empty] | 0 | 0 | 11.25 | 18.68 | 4843.95
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 21:02 |  | 4d 21:02 | 2028-10-16 09:11 | 2028-10-21 06:13
PH4100XPC#1 | GG\33\020\B | GG | 33 | 20 | B | 1 Prestrip - Thick | 100 | 42.3664 | 42.3664 | 2028-10-18 11:48 | 2028-10-20 04:36 | 88434.3296 | 88434 | [7 empty] | 0 | 0 | 10.06 | 13.17 | 5279.32
PH4100XPC#1 | GG\34\007\X1 | GG | 34 | 7 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\007\B | GG | 34 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\008\X1 | GG | 34 | 8 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\008\X2 | GG | 34 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\008\B | GG | 34 | 8 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\009\X2 | GG | 34 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\009\B | GG | 34 | 9 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\010\X1 | GG | 34 | 10 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\010\X2 | GG | 34 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\010\B | GG | 34 | 10 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\011\X1 | GG | 34 | 11 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\011\X2 | GG | 34 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\011\B | GG | 34 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\012\X1 | GG | 34 | 12 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\012\X2 | GG | 34 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\012\A | GG | 34 | 12 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\012\B | GG | 34 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\013\X1 | GG | 34 | 13 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\013\X2 | GG | 34 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\013\B | GG | 34 | 13 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\014\X1 | GG | 34 | 14 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\014\X2 | GG | 34 | 14 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\014\B | GG | 34 | 14 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\015\X1 | GG | 34 | 15 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\015\B | GG | 34 | 15 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\016\X1 | GG | 34 | 16 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\016\B | GG | 34 | 16 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\017\B | GG | 34 | 17 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\018\B | GG | 34 | 18 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\019\B | GG | 34 | 19 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\34\020\B | GG | 34 | 20 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\007\X1 | GG | 39 | 7 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\007\B | GG | 39 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\008\X2 | GG | 39 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\008\B | GG | 39 | 8 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\009\X2 | GG | 39 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\009\A | GG | 39 | 9 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\009\B | GG | 39 | 9 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\010\X2 | GG | 39 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\010\B | GG | 39 | 10 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\011\X1 | GG | 39 | 11 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\011\X2 | GG | 39 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\011\A | GG | 39 | 11 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\011\B | GG | 39 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\012\X1 | GG | 39 | 12 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\012\B | GG | 39 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\013\X1 | GG | 39 | 13 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\013\B | GG | 39 | 13 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\014\X1 | GG | 39 | 14 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\014\B | GG | 39 | 14 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\015\X1 | GG | 39 | 15 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\015\B | GG | 39 | 15 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\016\X1 | GG | 39 | 16 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\016\B | GG | 39 | 16 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\017\B | GG | 39 | 17 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\018\B | GG | 39 | 18 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\39\019\B | GG | 39 | 19 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\44\009\X2 | GG | 44 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\44\009\A | GG | 44 | 9 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\44\009\B | GG | 44 | 9 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\44\010\A | GG | 44 | 10 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\44\010\B | GG | 44 | 10 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\44\011\X1 | GG | 44 | 11 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\44\011\B | GG | 44 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\44\012\X1 | GG | 44 | 12 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\44\012\B | GG | 44 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\44\013\X1 | GG | 44 | 13 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\44\013\B | GG | 44 | 13 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\44\014\B | GG | 44 | 14 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\44\015\B | GG | 44 | 15 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\44\016\B | GG | 44 | 16 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\44\017\B | GG | 44 | 17 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\49\013\B | GG | 49 | 13 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-10-20 04:36 | 2028-10-20 04:36 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\05\003\B | W2 | 5 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-10-20 04:36 | 2028-11-26 13:13 | 2012707.143 | 2012707 | [7 empty] | 0 | 0 | 71.37 | 9.78 | 5300.21
DRE2 | GG\30\014\D | GG | 30 | 14 | D | 6 DL | 100 | 100 | 100 | 2028-10-21 06:13 | 2028-10-28 07:59 | 571077.2277 |  |  |  | 13296 | 571077 | 252630 |  |  | 0 | 23.15 | 0 | 6.85 | 5779.94
TS5500Shv | GG\30\013\D | GG | 30 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-10-21 06:13 | 2028-10-23 06:21 | 58698.0955 | [6 empty] | 58698 | 43810 | 4.38 | 0 | 0 | 6.79 | 5787
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 01:38 |  | 5d 01:38 | 2028-10-23 06:21 | 2028-10-28 07:59
DRE2 | GG\30\017\D | GG | 30 | 17 | D | 6 DL | 100 | 100 | 100 | 2028-10-28 07:59 | 2028-11-03 18:35 | 520036.6562 |  |  |  | 12108 | 520037 | 230051 |  |  | 0 | 24.22 | 0 | 6.9 | 5779.45
TS5500Shv | GG\30\014\D | GG | 30 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-10-28 07:59 | 2028-10-30 13:25 | 65152.5551 | [6 empty] | 65153 | 48549 | 4.27 | 0 | 0 | 6.85 | 5780
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 05:10 |  | 4d 05:10 | 2028-10-30 13:25 | 2028-11-03 18:35
TS Fleet 5 | W2\14\004\B | W2 | 14 | 4 | B | 1 Prestrip - Thick | 98.4702 | 98.4702 | 98.4702 | 2028-11-03 01:10 | 2028-11-26 07:27 | 1094255.066 | 1094255 | [7 empty] | 0 | 0 | 52.35 | 8.98 | 5423.66
DRE2 | GG\30\018\D | GG | 30 | 18 | D | 6 DL | 100 | 100 | 100 | 2028-11-03 18:35 | 2028-11-10 04:20 | 517176.7855 |  |  |  | 12041 | 517177 | 228786 |  |  | 0 | 24.07 | 0 | 6.88 | 5782.26
TS5500Shv | GG\30\017\D | GG | 30 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-11-03 18:35 | 2028-11-05 20:35 | 60979.4768 | [6 empty] | 60979 | 45442 | 4.55 | 0 | 0 | 6.9 | 5779
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 07:45 |  | 4d 07:45 | 2028-11-05 20:35 | 2028-11-10 04:20
TS6060#1 | W2\04\003\D | W2 | 4 | 3 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2028-11-09 09:58 | 2028-11-11 00:03 | 51527.8944 | [6 empty] | 51528 | 37659 | 2.49 | 0 | 0 | 5.72 | 5763
DRE2 | GG\30\019\D | GG | 30 | 19 | D | 6 DL | 100 | 100 | 100 | 2028-11-10 04:20 | 2028-11-16 11:48 | 509474.0238 |  |  |  | 11862 | 509474 | 225378 |  |  | 0 | 23.71 | 0 | 6.83 | 5787.11
TS5500Shv | GG\30\018\D | GG | 30 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-11-10 04:20 | 2028-11-12 07:10 | 61995.0329 | [6 empty] | 61995 | 46236 | 4.62 | 0 | 0 | 6.88 | 5782
TS5500Exc | W2\08\004\B | W2 | 8 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-11-10 17:05 | 2028-11-13 20:53 | 95489.0156 | [6 empty] | 95489 | 67281 | 3.37 | 0 | 0 | 9.73 | 5306
TS6060#1 | W2\08\003\D | W2 | 8 | 3 | D | 7 PostStrip | 50.6156 | 0 | 50.6156 | 2028-11-11 00:03 | 2028-11-13 15:29 | 65452.8175 |  |  | 65453 | [5 empty] | 0 | 0 | 0 | 5.77 | 5761.5
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 04:37 |  | 4d 04:37 | 2028-11-12 07:10 | 2028-11-16 11:48
TS6060#1 | W2\08\003\D | W2 | 8 | 3 | D | 8 Coal Mining | 45.1 | 0 | 45.1 | 2028-11-13 15:29 | 2028-11-16 02:26 | 79783.8562 | [6 empty] | 79784 | 58361 | 2.29 | 0 | 0 | 5.77 | 5762
TS5500Exc | W2\08\003\D | W2 | 8 | 3 | D | 8 Coal Mining | 54.9 | 0 | 54.9 | 2028-11-13 20:53 | 2028-11-17 01:55 | 97018.7414 | [6 empty] | 97019 | 70968 | 2.79 | 0 | 0 | 5.77 | 5762
PH4100A | W2\06\005\D | W2 | 6 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-11-14 12:22 | 2028-11-21 11:16 | 289723.6078 | 289724 | [7 empty] | 0 | 0 | 19.49 | 5.65 | 5768.37
TS6060#1 | GG\32\012\B | GG | 32 | 12 | B | 8 Coal Mining | 52.6 | 0 | 52.6 | 2028-11-16 02:26 | 2028-11-16 22:14 | 26796.7598 | [6 empty] | 26797 | 19321 | 1.94 | 0 | 0 | 12.26 | 5337
DRE2 | GG\30\020\D | GG | 30 | 20 | D | 6 DL | 100 | 0 | 100 | 2028-11-16 11:48 | 2028-11-24 07:50 | 632495.0916 |  |  |  | 34794 | 632495 | 274472 |  |  | 0 | 40 | 0 | 6.76 | 5791.71
TS5500Shv | GG\30\019\D | GG | 30 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-11-16 11:48 | 2028-11-18 14:50 | 62246.2093 | [6 empty] | 62246 | 46498 | 4.65 | 0 | 0 | 6.83 | 5787
TS6060#1 | GG\31\009\B | GG | 31 | 9 | B | 8 Coal Mining | 56.8 | 0 | 56.8 | 2028-11-16 22:14 | 2028-11-17 20:02 | 29510.2306 | [6 empty] | 29510 | 21511 | 2.15 | 0 | 0 | 10.66 | 5471
TS5500Exc | W2\09\004\B | W2 | 9 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-11-17 01:55 | 2028-11-20 06:02 | 95883.1165 | [6 empty] | 95883 | 67692 | 3.38 | 0 | 0 | 9.6 | 5322
TS6060#1 | CP\03\005\B | CP | 3 | 5 | B | 1 Prestrip - Thick | 43.9964 | 23.805 | 23.805 | 2028-11-17 20:02 | 2029-01-01 | 1088610.169 | 1088610 | [7 empty] | 0 | 0 | 11.17 | 8.68 | 5597.69
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 20:26 |  | 2d 20:26 | 2028-11-18 14:50 | 2028-11-21 11:16
TS5500Exc | SC\61\003\D | SC | 61 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2028-11-20 06:02 | 2028-11-29 23:02 | 206060.9242 |  |  | 206061 | [5 empty] | 0 | 0 | 0 | 6.41 | 5850.01
PH4100A | W2\07\005\B | W2 | 7 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-11-21 11:16 | 2028-12-19 11:02 | 1164863.675 | 1164864 | [7 empty] | 0 | 0 | 58.04 | 9.97 | 5277.58
TS5500Shv | W2\06\005\D | W2 | 6 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2028-11-21 11:16 | 2028-11-25 08:30 | 99948.6355 |  |  | 99949 | [5 empty] | 0 | 0 | 0 | 5.65 | 5768.37
DRE2 | GG\32\011\B | GG | 32 | 11 | B | 6 DL | 100 | 0 | 100 | 2028-11-24 07:50 | 2028-11-27 12:21 | 257426.4787 |  |  |  |  | 257426 | 198020 |  |  | 0 | 19.82 | 0 | 11.73 | 5387.95
TS5500Shv | W2\06\005\D | W2 | 6 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-11-25 08:30 | 2028-11-29 20:18 | 131453.6545 | [6 empty] | 131454 | 95773 | 4.79 | 0 | 0 | 5.65 | 5768
TS Fleet 5 | W2\08\004\D | W2 | 8 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-11-26 07:27 | 2028-12-02 13:44 | 294556.9837 | 294557 | [7 empty] | 0 | 0 | 19.73 | 5.67 | 5768.94
PH4100XPC#1 | W2\02\010\D | W2 | 2 | 10 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-11-26 13:13 | 2028-11-26 13:13 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\02\011\B | W2 | 2 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-11-26 13:13 | 2028-11-26 13:13 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\03\010\D | W2 | 3 | 10 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-11-26 13:13 | 2028-11-26 13:13 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\02\011\D | W2 | 2 | 11 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-11-26 13:13 | 2028-11-26 13:13 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\03\011\B | W2 | 3 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-11-26 13:13 | 2028-11-26 13:13 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\02\012\A | W2 | 2 | 12 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-11-26 13:13 | 2028-11-26 13:13 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\03\011\D | W2 | 3 | 11 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-11-26 13:13 | 2028-11-26 13:13 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\02\012\B | W2 | 2 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-11-26 13:13 | 2028-11-26 13:13 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\03\012\B | W2 | 3 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-11-26 13:13 | 2028-11-26 13:13 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\02\012\D | W2 | 2 | 12 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-11-26 13:13 | 2028-11-26 13:13 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\03\012\D | W2 | 3 | 12 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-11-26 13:13 | 2028-11-26 13:13 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\04\004\B | W2 | 4 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-11-26 13:13 | 2028-12-19 03:16 | 1237317.259 | 1237317 | [7 empty] | 0 | 0 | 66.31 | 10.76 | 5223.13
DRE2 | GG\32\010\B | GG | 32 | 10 | B | 6 DL | 100 | 0 | 100 | 2028-11-27 12:21 | 2028-11-30 18:43 | 263603.4091 |  |  |  |  | 263603 | 202772 |  |  | 0 | 20.3 | 0 | 11.08 | 5441.85
TS5500Shv | GG\30\020\D | GG | 30 | 20 | D | 7 PostStrip | 100 | 0 | 100 | 2028-11-29 20:18 | 2028-12-01 08:23 | 38671.7959 |  |  | 38672 | [5 empty] | 0 | 0 | 0 | 6.76 | 5791.71
TS5500Exc | W2\05\003\B | W2 | 5 | 3 | B | 8 Coal Mining | 74.2 | 0 | 74.2 | 2028-11-29 23:02 | 2028-12-02 05:55 | 69143.0271 | [6 empty] | 69143 | 48700 | 2.21 | 0 | 0 | 9.78 | 5300
DRE2 | GG\32\009\B | GG | 32 | 9 | B | 6 DL | 100 | 0 | 100 | 2028-11-30 18:43 | 2028-12-04 01:46 | 265897.4609 |  |  |  |  | 265897 | 204537 |  |  | 0 | 20.56 | 0 | 10.75 | 5463.19
TS5500Shv | GG\30\020\D | GG | 30 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-12-01 08:23 | 2028-12-02 21:42 | 45514.0677 | [6 empty] | 45514 | 34029 | 4.49 | 0 | 0 | 6.76 | 5792
TS5500Exc | SC\61\003\D | SC | 61 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-12-02 05:55 | 2028-12-11 01:32 | 266555.1171 | [6 empty] | 266555 | 201133 | 4.8 | 0 | 0 | 6.41 | 5850
TS Fleet 5 | W2\09\004\D | W2 | 9 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-12-02 13:44 | 2028-12-08 19:57 | 294414.8493 | 294415 | [7 empty] | 0 | 0 | 19.72 | 5.61 | 5774.47
TS5500Shv | GG\32\011\B | GG | 32 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-12-02 21:42 | 2028-12-04 15:54 | 51461.7611 | [6 empty] | 51462 | 37220 | 3.73 | 0 | 0 | 11.73 | 5388
DRE2 | GG\32\008\B | GG | 32 | 8 | B | 6 DL | 100 | 0 | 0 | 2028-12-04 01:46 | 2028-12-04 01:46 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\31\012\D | GG | 31 | 12 | D | 6 DL | 100 | 100 | 100 | 2028-12-04 01:46 | 2028-12-09 16:39 | 453728.6185 |  |  |  | 10564 | 453729 | 200718 |  |  | 0 | 21.15 | 0 | 6.69 | 5798.34
TS5500Shv | GG\32\009\B | GG | 32 | 9 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-12-04 15:54 | 2028-12-06 10:40 | 52145.6445 | [6 empty] | 52146 | 37963 | 3.8 | 0 | 0 | 10.75 | 5463
TS5500Shv | GG\32\010\B | GG | 32 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2028-12-06 10:40 | 2028-12-08 05:15 | 51923.4174 | [6 empty] | 51923 | 37731 | 3.78 | 0 | 0 | 11.08 | 5442
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 11:24 |  | 1d 11:24 | 2028-12-08 05:15 | 2028-12-09 16:39
TS Fleet 5 | W2\15\004\B | W2 | 15 | 4 | B | 1 Prestrip - Thick | 46.1927 | 46.1927 | 46.1927 | 2028-12-08 19:57 | 2028-12-15 02:43 | 295489.9277 | 295490 | [7 empty] | 0 | 0 | 24.61 | 8.85 | 5442.76
DRE2 | GG\31\011\D | GG | 31 | 11 | D | 6 DL | 100 | 100 | 100 | 2028-12-09 16:39 | 2028-12-15 07:09 | 452407.6139 |  |  |  | 8183 | 452408 | 196383 |  |  | 0 | 20.48 | 0 | 6.61 | 5806.18
TS5500Shv | GG\31\012\D | GG | 31 | 12 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-12-09 16:39 | 2028-12-11 18:53 | 61237.1135 | [6 empty] | 61237 | 45780 | 4.58 | 0 | 0 | 6.69 | 5798
TS5500Exc | CP\03\004\D | CP | 3 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2028-12-11 01:32 | 2028-12-23 22:13 | 272999.8727 |  |  | 273000 | [5 empty] | 0 | 0 | 0 | 6.26 | 5856.3
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 12:17 |  | 3d 12:17 | 2028-12-11 18:53 | 2028-12-15 07:09
TS Fleet 5 | W2\16\003\B | W2 | 16 | 3 | B | 1 Prestrip - Thick | 45.5884 | 44.1554 | 44.1554 | 2028-12-15 02:43 | 2029-01-01 | 794347.4564 | 794347 | [7 empty] | 0 | 0 | 26.5 | 9.01 | 5420.67
DRE2 | GG\31\010\D | GG | 31 | 10 | D | 6 DL | 100 | 100 | 100 | 2028-12-15 07:09 | 2028-12-20 14:40 | 428910.4401 |  |  |  | 7987 | 428910 | 191692 |  |  | 0 | 19.99 | 0 | 6.57 | 5809.19
TS5500Shv | GG\31\011\D | GG | 31 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-12-15 07:09 | 2028-12-17 10:14 | 62289.8223 | [6 empty] | 62290 | 46641 | 4.66 | 0 | 0 | 6.61 | 5806
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 04:26 |  | 3d 04:26 | 2028-12-17 10:14 | 2028-12-20 14:40
PH4100XPC#1 | GG\35\007\X1 | GG | 35 | 7 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\35\007\B | GG | 35 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\35\008\X2 | GG | 35 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\35\008\B | GG | 35 | 8 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\35\009\X2 | GG | 35 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\35\009\B | GG | 35 | 9 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\35\010\X1 | GG | 35 | 10 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\35\010\X2 | GG | 35 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\35\010\B | GG | 35 | 10 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\35\011\X1 | GG | 35 | 11 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\35\011\X2 | GG | 35 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\35\011\B | GG | 35 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\35\012\X1 | GG | 35 | 12 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\35\012\X2 | GG | 35 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\35\012\A | GG | 35 | 12 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\35\012\B | GG | 35 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\007\X1 | GG | 40 | 7 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\007\X2 | GG | 40 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\007\B | GG | 40 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\008\X2 | GG | 40 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\008\B | GG | 40 | 8 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\009\X2 | GG | 40 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\009\A | GG | 40 | 9 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\009\B | GG | 40 | 9 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\010\X2 | GG | 40 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\010\A | GG | 40 | 10 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\010\B | GG | 40 | 10 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\011\X1 | GG | 40 | 11 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\011\X2 | GG | 40 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\011\A | GG | 40 | 11 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\011\B | GG | 40 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\012\X1 | GG | 40 | 12 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\012\B | GG | 40 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\013\X1 | GG | 40 | 13 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\013\B | GG | 40 | 13 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\014\X1 | GG | 40 | 14 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\014\B | GG | 40 | 14 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\015\X1 | GG | 40 | 15 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\015\B | GG | 40 | 15 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\016\B | GG | 40 | 16 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\017\B | GG | 40 | 17 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\018\B | GG | 40 | 18 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\40\019\B | GG | 40 | 19 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\45\010\B | GG | 45 | 10 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\45\011\B | GG | 45 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\45\012\X1 | GG | 45 | 12 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\45\012\B | GG | 45 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\45\013\X1 | GG | 45 | 13 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\45\013\B | GG | 45 | 13 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\45\014\B | GG | 45 | 14 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\45\015\B | GG | 45 | 15 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\45\016\B | GG | 45 | 16 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\45\017\B | GG | 45 | 17 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2028-12-19 03:16 | 2028-12-19 03:16 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\05\004\D | W2 | 5 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2028-12-19 03:16 | 2028-12-24 01:53 | 256985.7022 | 256986 | [7 empty] | 0 | 0 | 17.79 | 5.71 | 5763.53
PH4100A | W2\08\005\B | W2 | 8 | 5 | B | 1 Prestrip - Thick | 100 | 44.8374 | 44.8374 | 2028-12-19 11:02 | 2029-01-01 | 522320.3114 | 522320 | [7 empty] | 0 | 0 | 25.95 | 9.91 | 5286.25
DRE2 | GG\31\009\D | GG | 31 | 9 | D | 6 DL | 100 | 100 | 100 | 2028-12-20 14:40 | 2028-12-25 19:42 | 420619.2397 |  |  |  | 7833 | 420619 | 187986 |  |  | 0 | 19.6 | 0 | 6.55 | 5810.76
TS5500Shv | GG\31\010\D | GG | 31 | 10 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-12-20 14:40 | 2028-12-22 17:31 | 62020.0296 | [6 empty] | 62020 | 46439 | 4.64 | 0 | 0 | 6.57 | 5809
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 08:22 |  | 1d 08:22 | 2028-12-22 17:31 | 2028-12-24 01:53
TS5500Exc | W2\04\004\B | W2 | 4 | 4 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2028-12-23 22:13 | 2028-12-24 16:55 | 23556.0476 | [6 empty] | 23556 | 16470 | 0.84 | 0 | 0 | 10.76 | 5223
PH4100XPC#1 | W2\04\005\B | W2 | 4 | 5 | B | 1 Prestrip - Thick | 100 | 40.355 | 40.355 | 2028-12-24 01:53 | 2029-01-01 | 414915.2156 | 414915 | [7 empty] | 0 | 0 | 21.26 | 10.04 | 5272.98
TS5500Shv | W2\05\004\D | W2 | 5 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2028-12-24 01:53 | 2028-12-27 23:35 | 100430.8093 |  |  | 100431 | [5 empty] | 0 | 0 | 0 | 5.71 | 5763.53
TS5500Exc | W2\07\005\B | W2 | 7 | 5 | B | 8 Coal Mining | 91.1 | 0 | 91.1 | 2028-12-24 16:55 | 2028-12-27 15:26 | 88810.5781 | [6 empty] | 88811 | 62310 | 3.11 | 0 | 0 | 9.97 | 5278
DRE2 | GG\31\008\D | GG | 31 | 8 | D | 6 DL | 100 | 0 | 0 | 2028-12-25 19:42 | 2028-12-25 19:42 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\32\013\B | GG | 32 | 13 | B | 6 DL | 100 | 0 | 100 | 2028-12-25 19:42 | 2028-12-28 12:57 | 219443.5028 |  |  |  |  | 219444 | 182870 |  |  | 0 | 18.33 | 0 | 12.21 | 5324.33
TS5500Exc | CP\03\004\D | CP | 3 | 4 | D | 8 Coal Mining | 100 | 0 | 34.8 | 2028-12-27 15:26 | 2029-01-01 | 131703.9312 | [6 empty] | 131704 | 94807 | 1.75 | 0 | 0 | 6.26 | 5856
TS5500Shv | W2\05\004\D | W2 | 5 | 4 | D | 8 Coal Mining | 8.5 | 0 | 8.5 | 2028-12-27 23:35 | 2028-12-28 08:48 | 11244.5089 | [6 empty] | 11245 | 8211 | 0.41 | 0 | 0 | 5.71 | 5764
TS5500Shv | GG\31\009\D | GG | 31 | 9 | D | 8 Coal Mining | 100 | 0 | 100 | 2028-12-28 08:48 | 2028-12-30 11:25 | 61725.8415 | [6 empty] | 61726 | 46256 | 4.63 | 0 | 0 | 6.55 | 5811
DRE2 | GG\32\014\B | GG | 32 | 14 | B | 6 DL | 100 | 0 | 82.736 | 2028-12-28 12:57 | 2029-01-01 | 279349.9896 |  |  |  |  | 279350 | 232792 |  |  | 0 | 17.64 | 0 | 13.66 | 5201.45
TS5500Shv | GG\32\013\B | GG | 32 | 13 | B | 8 Coal Mining | 100 | 0 | 88.6 | 2028-12-30 11:25 | 2029-01-01 | 44597.823 | [6 empty] | 44598 | 32226 | 3.23 | 0 | 0 | 12.21 | 5324
| EOP 81 : 2028 | EOP 81 : 2028 | [7 empty] | 2029-01-01 | 2029-01-01 |  | 62051133 |  | 3278799 | 885021 | 35611587 | 19893289 | 12359308 | 9038661 | 636.22 | 0 | 3662.65 | 8.22 | 5618.38
PH4100A | W2\08\005\B | W2 | 8 | 5 | B | 1 Prestrip - Thick | 100 | 55.1626 | 55.1626 | 2029-01-01 | 2029-01-16 10:16 | 642601.088 | 642601 | [7 empty] | 0 | 0 | 31.92 | 9.91 | 5286.25
TS Fleet 5 | W2\16\003\B | W2 | 16 | 3 | B | 1 Prestrip - Thick | 45.5884 | 1.433 | 1.433 | 2029-01-01 | 2029-01-01 13:09 | 25780.2761 | 25780 | [7 empty] | 0 | 0 | 0.86 | 9.01 | 5420.67
DRE2 | GG\32\014\B | GG | 32 | 14 | B | 6 DL | 100 | 0 | 17.264 | 2029-01-01 | 2029-01-01 19:23 | 58290.2179 |  |  |  |  | 58290 | 48575 |  |  | 0 | 17.64 | 0 | 13.66 | 5201.45
PH4100XPC#1 | W2\04\005\B | W2 | 4 | 5 | B | 1 Prestrip - Thick | 100 | 59.645 | 59.645 | 2029-01-01 | 2029-01-12 04:55 | 613246.6929 | 613247 | [7 empty] | 0 | 0 | 31.43 | 10.04 | 5272.98
TS6060#1 | CP\03\005\B | CP | 3 | 5 | B | 1 Prestrip - Thick | 43.9964 | 20.1914 | 20.1914 | 2029-01-01 | 2029-02-07 11:03 | 923360.3057 | 923360 | [7 empty] | 0 | 0 | 9.47 | 8.68 | 5597.69
TS5500Exc | CP\03\004\D | CP | 3 | 4 | D | 8 Coal Mining | 100 | 0 | 65.2 | 2029-01-01 | 2029-01-09 03:51 | 246703.7513 | [6 empty] | 246704 | 177590 | 3.29 | 0 | 0 | 6.26 | 5856
TS5500Shv | GG\32\013\B | GG | 32 | 13 | B | 8 Coal Mining | 100 | 0 | 11.4 | 2029-01-01 | 2029-01-01 04:41 | 5714.4524 | [6 empty] | 5714 | 4129 | 0.41 | 0 | 0 | 12.21 | 5324
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 14:43 |  | 0d 14:43 | 2029-01-01 04:41 | 2029-01-01 19:23
TS Fleet 5 | CP\05\002\B | CP | 5 | 2 | B | 1 Prestrip - Thick | 45.4934 | 45.4934 | 45.4934 | 2029-01-01 13:09 | 2029-01-11 05:24 | 455208.0775 | 455208 | [7 empty] | 0 | 0 | 11.32 | 9.57 | 5564.15
DRE2 | GG\32\017\B | GG | 32 | 17 | B | 6 DL | 100 | 0 | 100 | 2029-01-01 19:23 | 2029-01-04 12:28 | 195572.9936 |  |  |  |  | 195573 | 162977 |  |  | 0 | 16.23 | 0 | 15.03 | 5112.23
TS5500Shv | GG\32\014\B | GG | 32 | 14 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-01-01 19:23 | 2029-01-04 13:04 | 80094.6639 | [6 empty] | 80095 | 57540 | 3.73 | 0 | 0 | 13.66 | 5201
DRE2 | GG\32\018\B | GG | 32 | 18 | B | 6 DL | 100 | 0 | 100 | 2029-01-04 12:28 | 2029-01-07 02:37 | 186748.793 |  |  |  |  | 186749 | 155624 |  |  | 0 | 15.81 | 0 | 16.96 | 4972.05
TS5500Shv | GG\32\017\B | GG | 32 | 17 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-01-04 13:04 | 2029-01-06 05:26 | 49216.7678 | [6 empty] | 49217 | 35048 | 3.51 | 0 | 0 | 15.03 | 5112
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 21:11 |  | 0d 21:11 | 2029-01-06 05:26 | 2029-01-07 02:37
DRE2 | GG\32\019\B | GG | 32 | 19 | B | 6 DL | 100 | 0 | 100 | 2029-01-07 02:37 | 2029-01-10 00:56 | 211262.0857 |  |  |  |  | 211262 | 176052 |  |  | 0 | 16.08 | 0 | 20.38 | 4708.29
TS5500Shv | GG\32\018\B | GG | 32 | 18 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-01-07 02:37 | 2029-01-08 10:51 | 39295.6906 | [6 empty] | 39296 | 27692 | 2.76 | 0 | 0 | 16.96 | 4972
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 14:05 |  | 1d 14:05 | 2029-01-08 10:51 | 2029-01-10 00:56
TS5500Exc | W2\05\004\D | W2 | 5 | 4 | D | 8 Coal Mining | 91.5 | 0 | 91.5 | 2029-01-09 03:51 | 2029-01-13 03:36 | 120604.2745 | [6 empty] | 120604 | 88073 | 4.4 | 0 | 0 | 5.71 | 5764
DRE2 | GG\32\020\B | GG | 32 | 20 | B | 6 DL | 100 | 0 | 100 | 2029-01-10 00:56 | 2029-01-13 04:17 | 226458.28 |  |  |  |  | 226458 | 174199 |  |  | 0 | 17.56 | 0 | 14.65 | 5159.25
TS5500Shv | GG\32\019\B | GG | 32 | 19 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-01-10 00:56 | 2029-01-11 03:52 | 32858.3131 | [6 empty] | 32858 | 22747 | 2.27 | 0 | 0 | 20.38 | 4708
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 00:25 |  | 2d 00:25 | 2029-01-11 03:52 | 2029-01-13 04:17
TS Fleet 5 | CP\05\003\B | CP | 5 | 3 | B | 1 Prestrip - Thick | 45.386 | 45.386 | 45.386 | 2029-01-11 05:24 | 2029-01-24 20:06 | 640359.6778 | 640360 | [7 empty] | 0 | 0 | 21.48 | 8.89 | 5595.99
PH4100XPC#1 | W2\05\005\D | W2 | 5 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-01-12 04:55 | 2029-01-17 17:27 | 299994.0772 | 299994 | [7 empty] | 0 | 0 | 20.01 | 5.68 | 5766.08
TS5500Exc | W2\04\005\B | W2 | 4 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-01-13 03:36 | 2029-01-16 07:46 | 95951.0029 | [6 empty] | 95951 | 67249 | 3.37 | 0 | 0 | 10.04 | 5273
DRE2 | GG\31\013\D | GG | 31 | 13 | D | 6 DL | 100 | 100 | 100 | 2029-01-13 04:17 | 2029-01-19 17:23 | 472056.9177 |  |  |  | 10991 | 472057 | 208826 |  |  | 0 | 22.01 | 0 | 6.78 | 5788.48
TS5500Shv | GG\32\020\B | GG | 32 | 20 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-01-13 04:17 | 2029-01-13 13:51 | 11669.7188 | [6 empty] | 11670 | 8328 | 0.92 | 0 | 0 | 14.65 | 5159
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 17:55 |  | 2d 17:55 | 2029-01-13 13:51 | 2029-01-16 07:46
TS5500Exc | W1\10\002\B | W1 | 10 | 2 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-01-16 07:46 | 2029-01-16 23:54 | 20321.3632 | [6 empty] | 20321 | 14289 | 1.65 | 0 | 0 | 11.18 | 5167
TS5500Shv | W2\04\005\D | W2 | 4 | 5 | D | 1 Prestrip - Thick | 100 | 40.0132 | 40.0132 | 2029-01-16 07:46 | 2029-01-21 03:55 | 124499.7483 | 124500 | [7 empty] | 0 | 0 | 8.23 | 5.7 | 5763.89
PH4100A | W2\09\005\B | W2 | 9 | 5 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-01-16 10:16 | 2029-02-13 05:08 | 1157308.667 | 1157309 | [7 empty] | 0 | 0 | 57.57 | 9.84 | 5296
TS5500Exc | W2\08\005\B | W2 | 8 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-01-16 23:54 | 2029-01-20 05:11 | 97332.7722 | [6 empty] | 97333 | 68365 | 3.41 | 0 | 0 | 9.91 | 5286
PH4100XPC#1 | W2\04\005\D | W2 | 4 | 5 | D | 1 Prestrip - Thick | 100 | 59.9868 | 59.9868 | 2029-01-17 17:27 | 2029-01-21 03:55 | 186646.7686 | 186647 | [7 empty] | 0 | 0 | 12.34 | 5.7 | 5763.89
DRE2 | GG\31\014\D | GG | 31 | 14 | D | 6 DL | 100 | 100 | 100 | 2029-01-19 17:23 | 2029-01-28 13:17 | 636735.9762 |  |  |  | 14825 | 636736 | 281676 |  |  | 0 | 22.74 | 0 | 6.85 | 5781.67
TS5500Exc | SC\50\020\D | SC | 50 | 20 | D | 7 PostStrip | 100 | 0 | 100 | 2029-01-20 05:11 | 2029-01-25 20:44 | 119889.9743 |  |  | 119890 | [5 empty] | 0 | 0 | 0 | 7.29 | 5770.13
PH4100XPC#1 | W2\04\006\B | W2 | 4 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-01-21 03:55 | 2029-02-09 13:17 | 1041645.308 | 1041645 | [7 empty] | 0 | 0 | 51.95 | 10.05 | 5272.13
TS5500Shv | W2\05\005\D | W2 | 5 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2029-01-21 03:55 | 2029-01-25 01:06 | 99900.3633 |  |  | 99900 | [5 empty] | 0 | 0 | 0 | 5.68 | 5766.08
TS Fleet 5 | W1\10\002\D | W1 | 10 | 2 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-01-24 20:06 | 2029-01-29 05:56 | 207417.566 | 207418 | [7 empty] | 0 | 0 | 31.63 | 8.22 | 5539.36
TS5500Shv | W2\05\005\D | W2 | 5 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-01-25 01:06 | 2029-01-29 12:26 | 130883.2206 | [6 empty] | 130883 | 95356 | 4.77 | 0 | 0 | 5.68 | 5766
TS5500Exc | W2\04\005\D | W2 | 4 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2029-01-25 20:44 | 2029-01-30 13:42 | 99902.5462 |  |  | 99903 | [5 empty] | 0 | 0 | 0 | 5.7 | 5763.89
DRE2 | GG\31\017\D | GG | 31 | 17 | D | 6 DL | 100 | 100 | 100 | 2029-01-28 13:17 | 2029-02-04 17:15 | 516751.0222 |  |  |  | 12031 | 516751 | 228598 |  |  | 0 | 24.09 | 0 | 6.87 | 5781.94
TS Fleet 5 | W2\08\005\D | W2 | 8 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-01-29 05:56 | 2029-02-04 11:26 | 293031.9203 | 293032 | [7 empty] | 0 | 0 | 19.64 | 5.58 | 5775.04
TS5500Shv | GG\31\013\D | GG | 31 | 13 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-01-29 12:26 | 2029-01-31 12:44 | 58883.4168 | [6 empty] | 58883 | 43948 | 4.39 | 0 | 0 | 6.78 | 5788
TS5500Exc | W2\04\005\D | W2 | 4 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-01-30 13:42 | 2029-02-03 21:09 | 130299.2214 | [6 empty] | 130299 | 94930 | 4.75 | 0 | 0 | 5.7 | 5764
TS5500Shv | GG\31\014\D | GG | 31 | 14 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-01-31 12:44 | 2029-02-03 02:45 | 75626.6587 | [6 empty] | 75627 | 56355 | 4.36 | 0 | 0 | 6.85 | 5782
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 14:30 |  | 1d 14:30 | 2029-02-03 02:45 | 2029-02-04 17:15
TS5500Exc | SC\50\020\D | SC | 50 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-02-03 21:09 | 2029-02-08 10:44 | 138031.6002 | [6 empty] | 138032 | 103070 | 4.29 | 0 | 0 | 7.29 | 5770
TS Fleet 5 | CP\05\004\B | CP | 5 | 4 | B | 1 Prestrip - Thick | 45.5922 | 45.5922 | 45.5922 | 2029-02-04 11:26 | 2029-02-19 00:04 | 683306.708 | 683307 | [7 empty] | 0 | 0 | 22.82 | 8.6 | 5606.7
DRE2 | GG\31\018\D | GG | 31 | 18 | D | 6 DL | 100 | 100 | 100 | 2029-02-04 17:15 | 2029-02-11 22:12 | 519713.0997 |  |  |  | 12100 | 519713 | 229908 |  |  | 0 | 24.19 | 0 | 6.85 | 5784.76
TS5500Shv | GG\31\017\D | GG | 31 | 17 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-02-04 17:15 | 2029-02-06 19:22 | 61124.1303 | [6 empty] | 61124 | 45586 | 4.56 | 0 | 0 | 6.87 | 5782
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 02:50 |  | 5d 02:50 | 2029-02-06 19:22 | 2029-02-11 22:12
TS6060#1 | W2\05\003\B | W2 | 5 | 3 | B | 8 Coal Mining | 25.8 | 0 | 25.8 | 2029-02-07 11:03 | 2029-02-08 04:49 | 24052.824 | [6 empty] | 24053 | 16941 | 0.77 | 0 | 0 | 9.78 | 5300
TS6060#1 | W2\04\004\B | W2 | 4 | 4 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-02-08 04:49 | 2029-02-08 23:31 | 25310.2213 | [6 empty] | 25310 | 17697 | 0.9 | 0 | 0 | 10.76 | 5223
TS5500Exc | W1\09\002\D | W1 | 9 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2029-02-08 10:44 | 2029-02-11 21:39 | 73327.6902 |  |  | 73328 | [5 empty] | 0 | 0 | 0 | 8.23 | 5538.75
TS6060#1 | W2\07\005\B | W2 | 7 | 5 | B | 8 Coal Mining | 8.9 | 0 | 8.9 | 2029-02-08 23:31 | 2029-02-09 05:54 | 8641.1211 | [6 empty] | 8641 | 6063 | 0.3 | 0 | 0 | 9.97 | 5278
TS6060#1 | CP\03\005\B | CP | 3 | 5 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-02-09 05:54 | 2029-02-16 06:13 | 227800.2553 | [6 empty] | 227800 | 161384 | 1.71 | 0 | 0 | 8.68 | 5598
PH4100XPC#1 | W2\05\003\D | W2 | 5 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-02-09 13:17 | 2029-02-14 15:13 | 276006.3304 | 276006 | [7 empty] | 0 | 0 | 19.87 | 5.74 | 5761.73
TS5500Exc | W2\04\006\B | W2 | 4 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-02-11 21:39 | 2029-02-15 04:12 | 98943.5527 | [6 empty] | 98944 | 69302 | 3.47 | 0 | 0 | 10.05 | 5272
DRE2 | GG\31\019\D | GG | 31 | 19 | D | 6 DL | 100 | 100 | 100 | 2029-02-11 22:12 | 2029-02-19 00:39 | 512233.585 |  |  |  | 11926 | 512234 | 226599 |  |  | 0 | 23.84 | 0 | 6.81 | 5788.5
TS5500Shv | GG\31\018\D | GG | 31 | 18 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-02-11 22:12 | 2029-02-14 00:57 | 61896.1064 | [6 empty] | 61896 | 46199 | 4.62 | 0 | 0 | 6.85 | 5785
PH4100A | W2\10\003\B | W2 | 10 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-02-13 05:08 | 2029-04-17 09:03 | 2778777.096 | 2778777 | [7 empty] | 0 | 0 | 122.09 | 10.79 | 5244.92
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 14:16 |  | 0d 14:16 | 2029-02-14 00:57 | 2029-02-14 15:13
PH4100XPC#1 | W2\04\004\D | W2 | 4 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-02-14 15:13 | 2029-02-19 11:53 | 264096.9531 | 264097 | [7 empty] | 0 | 0 | 18.28 | 5.71 | 5763.11
TS5500Shv | W2\05\003\D | W2 | 5 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2029-02-14 15:13 | 2029-02-18 05:49 | 92833.3748 |  |  | 92833 | [5 empty] | 0 | 0 | 0 | 5.74 | 5761.73
TS5500Exc | W2\09\005\B | W2 | 9 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-02-15 04:12 | 2029-02-18 08:49 | 96519.3405 | [6 empty] | 96519 | 67915 | 3.39 | 0 | 0 | 9.84 | 5296
TS6060#1 | W1\10\003\D | W1 | 10 | 3 | D | 7 PostStrip | 51.7854 | 0 | 51.7854 | 2029-02-16 06:13 | 2029-02-18 00:36 | 43714.4459 |  |  | 43714 | [5 empty] | 0 | 0 | 0 | 8.28 | 5534.31
TS6060#1 | W2\08\006\B | W2 | 8 | 6 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-02-18 00:36 | 2029-02-19 06:14 | 40111.359 | [6 empty] | 40111 | 28094 | 1.39 | 0 | 0 | 10.24 | 5257
TS5500Shv | W2\05\003\D | W2 | 5 | 3 | D | 8 Coal Mining | 38.6 | 0 | 38.6 | 2029-02-18 05:49 | 2029-02-19 19:48 | 46319.3519 | [6 empty] | 46319 | 33879 | 1.88 | 0 | 0 | 5.74 | 5762
TS5500Exc | W2\05\003\D | W2 | 5 | 3 | D | 8 Coal Mining | 61.4 | 0 | 61.4 | 2029-02-18 08:49 | 2029-02-20 19:22 | 73751.3953 | [6 empty] | 73751 | 53944 | 3 | 0 | 0 | 5.74 | 5762
TS Fleet 5 | W2\09\005\D | W2 | 9 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-02-19 00:04 | 2029-02-25 10:07 | 301931.3661 | 301931 | [7 empty] | 0 | 0 | 20.08 | 5.54 | 5779.13
DRE2 | GG\31\020\D | GG | 31 | 20 | D | 6 DL | 100 | 0 | 100 | 2029-02-19 00:39 | 2029-03-01 09:11 | 746819.4593 |  |  |  | 40785 | 746819 | 323731 |  |  | 0 | 40 | 0 | 6.75 | 5792.49
TS6060#1 | W2\08\004\D | W2 | 8 | 4 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-02-19 06:14 | 2029-02-21 10:24 | 53836.2494 |  |  | 53836 | [5 empty] | 0 | 0 | 0 | 5.67 | 5768.94
PH4100XPC#1 | W2\04\006\D | W2 | 4 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-02-19 11:53 | 2029-02-25 02:42 | 305132.2408 | 305132 | [7 empty] | 0 | 0 | 20.26 | 5.72 | 5761.5
TS5500Shv | W2\04\004\D | W2 | 4 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2029-02-19 19:48 | 2029-02-23 16:34 | 99446.5471 |  |  | 99447 | [5 empty] | 0 | 0 | 0 | 5.71 | 5763.11
TS5500Exc | W1\09\002\D | W1 | 9 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-02-20 19:22 | 2029-02-23 15:40 | 86015.4508 | [6 empty] | 86015 | 61984 | 4.43 | 0 | 0 | 8.23 | 5539
TS6060#1 | W2\08\005\D | W2 | 8 | 5 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-02-21 10:24 | 2029-02-23 14:38 | 53883.2611 |  |  | 53883 | [5 empty] | 0 | 0 | 0 | 5.58 | 5775.04
TS6060#1 | W2\09\003\D | W2 | 9 | 3 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-02-23 14:38 | 2029-02-26 06:57 | 66374.5023 |  |  | 66375 | [5 empty] | 0 | 0 | 0 | 5.72 | 5765.29
TS5500Exc | W1\09\003\D | W1 | 9 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2029-02-23 15:40 | 2029-02-27 18:49 | 87687.6331 |  |  | 87688 | [5 empty] | 0 | 0 | 0 | 8.32 | 5529.02
TS5500Shv | GG\31\019\D | GG | 31 | 19 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-02-23 16:34 | 2029-02-25 19:37 | 62248.4885 | [6 empty] | 62248 | 46499 | 4.65 | 0 | 0 | 6.81 | 5789
PH4100XPC#1 | W2\05\006\D | W2 | 5 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-02-25 02:42 | 2029-03-02 16:43 | 303372.9696 | 303373 | [7 empty] | 0 | 0 | 20.17 | 5.68 | 5765.23
TS Fleet 5 | CP\05\005\B | CP | 5 | 5 | B | 1 Prestrip - Thick | 36.35 | 36.35 | 36.35 | 2029-02-25 10:07 | 2029-03-11 02:38 | 643905.8739 | 643906 | [7 empty] | 0 | 0 | 21.42 | 8.53 | 5610.65
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 13:35 |  | 3d 13:35 | 2029-02-25 19:37 | 2029-03-01 09:11
TS6060#1 | W2\09\004\D | W2 | 9 | 4 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-02-26 06:57 | 2029-02-28 11:10 | 53865.3126 |  |  | 53865 | [5 empty] | 0 | 0 | 0 | 5.61 | 5774.47
TS5500Exc | W2\04\004\D | W2 | 4 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-02-27 18:49 | 2029-03-04 02:56 | 131144.2392 | [6 empty] | 131144 | 95769 | 4.79 | 0 | 0 | 5.71 | 5763
TS6060#1 | W2\09\005\D | W2 | 9 | 5 | D | 7 PostStrip | 52.3022 | 0 | 52.3022 | 2029-02-28 11:10 | 2029-03-02 13:55 | 52368.6464 |  |  | 52369 | [5 empty] | 0 | 0 | 0 | 5.54 | 5779.13
DRE2 | GG\33\013\B | GG | 33 | 13 | B | 6 DL | 100 | 0 | 100 | 2029-03-01 09:11 | 2029-03-04 11:34 | 223506.1201 |  |  |  |  | 223506 | 186255 |  |  | 0 | 18.68 | 0 | 12.3 | 5322.29
TS5500Shv | GG\31\020\D | GG | 31 | 20 | D | 7 PostStrip | 100 | 0 | 100 | 2029-03-01 09:11 | 2029-03-03 01:37 | 43331.1758 |  |  | 43331 | [5 empty] | 0 | 0 | 0 | 6.75 | 5792.49
TS6060#1 | W2\10\005\B | W2 | 10 | 5 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-03-02 13:55 | 2029-03-04 02:41 | 49762.3879 | [6 empty] | 49762 | 35069 | 1.74 | 0 | 0 | 9.74 | 5309
PH4100XPC#1 | W2\04\007\B | W2 | 4 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-03-02 16:43 | 2029-03-22 19:55 | 1087049.796 | 1087050 | [7 empty] | 0 | 0 | 54.47 | 10.05 | 5274.64
TS5500Shv | GG\31\020\D | GG | 31 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-03-03 01:37 | 2029-03-04 15:13 | 45852.175 | [6 empty] | 45852 | 34282 | 4.53 | 0 | 0 | 6.75 | 5792
TS6060#1 | CP\04\002\B | CP | 4 | 2 | B | 1 Prestrip - Thick | 24.5703 | 24.5703 | 24.5703 | 2029-03-04 02:41 | 2029-03-12 12:21 | 207191.7314 | 207192 | [7 empty] | 0 | 0 | 5.74 | 9.44 | 5576.4
TS5500Exc | W2\05\006\D | W2 | 5 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2029-03-04 02:56 | 2029-03-08 20:00 | 100004.1703 |  |  | 100004 | [5 empty] | 0 | 0 | 0 | 5.68 | 5765.23
DRE2 | GG\33\011\B | GG | 33 | 11 | B | 6 DL | 100 | 0 | 100 | 2029-03-04 11:34 | 2029-03-08 02:30 | 261228.7704 |  |  |  |  | 261229 | 200945 |  |  | 0 | 20.11 | 0 | 11.77 | 5384.47
TS5500Shv | GG\33\013\B | GG | 33 | 13 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-03-04 15:13 | 2029-03-06 08:51 | 50772.4804 | [6 empty] | 50772 | 36631 | 3.67 | 0 | 0 | 12.3 | 5322
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 17:39 |  | 1d 17:39 | 2029-03-06 08:51 | 2029-03-08 02:30
DRE2 | GG\33\010\B | GG | 33 | 10 | B | 6 DL | 100 | 0 | 100 | 2029-03-08 02:30 | 2029-03-11 18:59 | 265889.7319 |  |  |  |  | 265890 | 204531 |  |  | 0 | 20.54 | 0 | 11.15 | 5435.16
TS5500Shv | GG\33\011\B | GG | 33 | 11 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-03-08 02:30 | 2029-03-09 21:02 | 51873.668 | [6 empty] | 51874 | 37482 | 3.75 | 0 | 0 | 11.77 | 5384
TS5500Exc | W2\05\006\D | W2 | 5 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-03-08 20:00 | 2029-03-13 03:11 | 129973.2183 | [6 empty] | 129973 | 94472 | 4.72 | 0 | 0 | 5.68 | 5765
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 21:57 |  | 1d 21:57 | 2029-03-09 21:02 | 2029-03-11 18:59
TS Fleet 5 | CP\06\002\B | CP | 6 | 2 | B | 1 Prestrip - Thick | 45.4675 | 45.4675 | 45.4675 | 2029-03-11 02:38 | 2029-03-22 21:57 | 555285.9836 | 555286 | [7 empty] | 0 | 0 | 12.98 | 9.52 | 5565.86
DRE2 | GG\33\009\B | GG | 33 | 9 | B | 6 DL | 100 | 0 | 100 | 2029-03-11 18:59 | 2029-03-15 12:02 | 267571.5991 |  |  |  |  | 267572 | 205824 |  |  | 0 | 20.69 | 0 | 10.85 | 5455.22
TS5500Shv | GG\33\010\B | GG | 33 | 10 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-03-11 18:59 | 2029-03-13 13:49 | 52221.5738 | [6 empty] | 52222 | 37908 | 3.8 | 0 | 0 | 11.15 | 5435
TS6060#1 | CP\05\005\B | CP | 5 | 5 | B | 1 Prestrip - Thick | 19.8599 | 19.8599 | 19.8599 | 2029-03-12 12:21 | 2029-03-26 18:13 | 351799.1972 | 351799 | [7 empty] | 0 | 0 | 11.7 | 8.53 | 5610.65
TS5500Exc | W2\04\006\D | W2 | 4 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2029-03-13 03:11 | 2029-03-17 20:15 | 99990.4327 |  |  | 99990 | [5 empty] | 0 | 0 | 0 | 5.72 | 5761.5
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 22:13 |  | 1d 22:13 | 2029-03-13 13:49 | 2029-03-15 12:02
DRE2 | GG\33\008\B | GG | 33 | 8 | B | 6 DL | 100 | 0 | 0 | 2029-03-15 12:02 | 2029-03-15 12:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\33\007\B | GG | 33 | 7 | B | 6 DL | 100 | 0 | 0 | 2029-03-15 12:02 | 2029-03-15 12:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\32\013\D | GG | 32 | 13 | D | 6 DL | 100 | 100 | 100 | 2029-03-15 12:02 | 2029-03-21 22:41 | 464754.4361 |  |  |  | 10821 | 464754 | 205596 |  |  | 0 | 21.67 | 0 | 6.77 | 5789.43
TS5500Shv | GG\33\009\B | GG | 33 | 9 | B | 8 Coal Mining | 63.2 | 0 | 63.2 | 2029-03-15 12:02 | 2029-03-16 15:06 | 33015.6574 | [6 empty] | 33016 | 24018 | 2.4 | 0 | 0 | 10.85 | 5455
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 07:35 |  | 5d 07:35 | 2029-03-16 15:06 | 2029-03-21 22:41
TS5500Exc | W2\04\006\D | W2 | 4 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-03-17 20:15 | 2029-03-22 03:19 | 129828.5209 | [6 empty] | 129829 | 94367 | 4.72 | 0 | 0 | 5.72 | 5762
DRE2 | GG\32\012\D | GG | 32 | 12 | D | 6 DL | 100 | 100 | 100 | 2029-03-21 22:41 | 2029-03-28 03:17 | 446495.087 |  |  |  | 10396 | 446495 | 197518 |  |  | 0 | 20.82 | 0 | 6.69 | 5798.24
TS5500Shv | GG\32\013\D | GG | 32 | 13 | D | 8 Coal Mining | 91.6 | 0 | 91.6 | 2029-03-21 22:41 | 2029-03-23 19:04 | 54119.7622 | [6 empty] | 54120 | 40393 | 4.04 | 0 | 0 | 6.77 | 5789
TS5500Exc | W1\09\003\D | W1 | 9 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-03-22 03:19 | 2029-03-25 09:24 | 98350.6057 | [6 empty] | 98351 | 70868 | 4.34 | 0 | 0 | 8.32 | 5529
PH4100XPC#1 | GG\36\007\X1 | GG | 36 | 7 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\36\007\B | GG | 36 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\36\008\X2 | GG | 36 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\36\008\B | GG | 36 | 8 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\36\009\X2 | GG | 36 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\36\009\B | GG | 36 | 9 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\36\010\X2 | GG | 36 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\36\010\B | GG | 36 | 10 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\36\011\X1 | GG | 36 | 11 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\36\011\X2 | GG | 36 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\36\011\B | GG | 36 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\007\X2 | GG | 41 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\007\B | GG | 41 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\008\X2 | GG | 41 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\008\B | GG | 41 | 8 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\009\X2 | GG | 41 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\009\A | GG | 41 | 9 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\009\B | GG | 41 | 9 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\010\X2 | GG | 41 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\010\A | GG | 41 | 10 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\010\B | GG | 41 | 10 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\011\X1 | GG | 41 | 11 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\011\A | GG | 41 | 11 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\011\B | GG | 41 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\012\X1 | GG | 41 | 12 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\012\B | GG | 41 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\013\X1 | GG | 41 | 13 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\013\B | GG | 41 | 13 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\014\X1 | GG | 41 | 14 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\014\B | GG | 41 | 14 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\015\X1 | GG | 41 | 15 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\015\B | GG | 41 | 15 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\016\B | GG | 41 | 16 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\017\B | GG | 41 | 17 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\018\B | GG | 41 | 18 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\41\019\B | GG | 41 | 19 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\46\011\B | GG | 46 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\46\012\X1 | GG | 46 | 12 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\46\012\B | GG | 46 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\46\013\B | GG | 46 | 13 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\46\014\B | GG | 46 | 14 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\46\015\B | GG | 46 | 15 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-03-22 19:55 | 2029-03-22 19:55 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\05\007\D | W2 | 5 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-03-22 19:55 | 2029-03-28 16:53 | 319080.3357 | 319080 | [7 empty] | 0 | 0 | 20.95 | 5.77 | 5758.52
TS Fleet 5 | CP\06\003\B | CP | 6 | 3 | B | 1 Prestrip - Thick | 45.1744 | 45.1744 | 45.1744 | 2029-03-22 21:57 | 2029-04-06 22:23 | 706458.7302 | 706459 | [7 empty] | 0 | 0 | 23.95 | 8.93 | 5592.93
TS5500Shv | W2\04\007\B | W2 | 4 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-03-23 19:04 | 2029-03-27 04:04 | 98765.7108 | [6 empty] | 98766 | 69130 | 3.45 | 0 | 0 | 10.05 | 5275
TS5500Exc | W1\10\002\D | W1 | 10 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2029-03-25 09:24 | 2029-03-27 05:26 | 38947.2027 |  |  | 38947 | [5 empty] | 0 | 0 | 0 | 8.22 | 5539.36
TS6060#1 | GG\33\009\B | GG | 33 | 9 | B | 8 Coal Mining | 36.8 | 0 | 36.8 | 2029-03-26 18:13 | 2029-03-27 08:27 | 19263.3189 | [6 empty] | 19263 | 14013 | 1.4 | 0 | 0 | 10.85 | 5455
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 23:13 |  | 0d 23:13 | 2029-03-27 04:04 | 2029-03-28 03:17
TS5500Exc | W1\10\002\D | W1 | 10 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-03-27 05:26 | 2029-03-28 18:33 | 46741.4451 | [6 empty] | 46741 | 33683 | 4.46 | 0 | 0 | 8.22 | 5539
TS6060#1 | GG\32\013\D | GG | 32 | 13 | D | 8 Coal Mining | 8.4 | 0 | 8.4 | 2029-03-27 08:27 | 2029-03-27 12:06 | 4943.8205 | [6 empty] | 4944 | 3690 | 0.37 | 0 | 0 | 6.77 | 5789
TS6060#1 | CP\07\004\B | CP | 7 | 4 | B | 1 Prestrip - Thick | 19.9317 | 19.9317 | 19.9317 | 2029-03-27 12:06 | 2029-04-09 19:10 | 328435.3116 | 328435 | [7 empty] | 0 | 0 | 11 | 8.43 | 5622.47
DRE2 | GG\32\011\D | GG | 32 | 11 | D | 6 DL | 100 | 100 | 100 | 2029-03-28 03:17 | 2029-04-03 07:43 | 446056.5909 |  |  |  | 8064 | 446057 | 193545 |  |  | 0 | 20.18 | 0 | 6.62 | 5805.42
TS5500Shv | GG\32\012\D | GG | 32 | 12 | D | 8 Coal Mining | 72.6 | 0 | 72.6 | 2029-03-28 03:17 | 2029-03-29 15:51 | 44602.7058 | [6 empty] | 44603 | 33344 | 3.33 | 0 | 0 | 6.69 | 5798
PH4100XPC#1 | W2\04\007\D | W2 | 4 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-03-28 16:53 | 2029-04-03 11:30 | 313777.0609 | 313777 | [7 empty] | 0 | 0 | 20.68 | 5.81 | 5754.5
TS5500Exc | W2\05\007\D | W2 | 5 | 7 | D | 7 PostStrip | 100 | 0 | 100 | 2029-03-28 18:33 | 2029-04-02 11:40 | 100047.739 |  |  | 100048 | [5 empty] | 0 | 0 | 0 | 5.77 | 5758.52
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 15:52 |  | 4d 15:52 | 2029-03-29 15:51 | 2029-04-03 07:43
TS5500Exc | W2\05\007\D | W2 | 5 | 7 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-04-02 11:40 | 2029-04-06 20:50 | 132456.4643 | [6 empty] | 132456 | 96133 | 4.81 | 0 | 0 | 5.77 | 5759
DRE2 | GG\32\010\D | GG | 32 | 10 | D | 6 DL | 100 | 100 | 100 | 2029-04-03 07:43 | 2029-04-09 04:25 | 422802.1454 |  |  |  | 7873 | 422802 | 188962 |  |  | 0 | 19.7 | 0 | 6.58 | 5808.81
TS5500Shv | GG\32\011\D | GG | 32 | 11 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2029-04-03 07:43 | 2029-04-04 08:47 | 30560.2987 | [6 empty] | 30560 | 22883 | 2.29 | 0 | 0 | 6.62 | 5805
PH4100XPC#1 | W2\04\008\B | W2 | 4 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-04-03 11:30 | 2029-04-24 08:06 | 1176136.571 | 1176137 | [7 empty] | 0 | 0 | 64.72 | 10.12 | 5275.03
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 19:38 |  | 4d 19:38 | 2029-04-04 08:47 | 2029-04-09 04:25
TS5500Exc | W2\04\007\D | W2 | 4 | 7 | D | 7 PostStrip | 100 | 0 | 100 | 2029-04-06 20:50 | 2029-04-11 13:59 | 100068.8027 |  |  | 100069 | [5 empty] | 0 | 0 | 0 | 5.81 | 5754.5
TS Fleet 5 | CP\06\004\B | CP | 6 | 4 | B | 1 Prestrip - Thick | 45.57 | 45.57 | 45.57 | 2029-04-06 22:23 | 2029-04-22 04:40 | 717931.758 | 717932 | [7 empty] | 0 | 0 | 23.99 | 8.52 | 5613.9
DRE2 | GG\32\009\D | GG | 32 | 9 | D | 6 DL | 100 | 100 | 100 | 2029-04-09 04:25 | 2029-04-14 23:18 | 417342.7983 |  |  |  | 7772 | 417343 | 186522 |  |  | 0 | 19.44 | 0 | 6.55 | 5811.1
TS5500Shv | GG\32\010\D | GG | 32 | 10 | D | 8 Coal Mining | 77.6 | 0 | 77.6 | 2029-04-09 04:25 | 2029-04-10 19:48 | 48030.2113 | [6 empty] | 48030 | 35964 | 3.6 | 0 | 0 | 6.58 | 5809
TS6060#1 | GG\32\012\D | GG | 32 | 12 | D | 8 Coal Mining | 27.4 | 0 | 27.4 | 2029-04-09 19:10 | 2029-04-10 07:35 | 16801.6886 | [6 empty] | 16802 | 12561 | 1.26 | 0 | 0 | 6.69 | 5798
TS6060#1 | GG\32\011\D | GG | 32 | 11 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2029-04-10 07:35 | 2029-04-11 06:55 | 31579.9832 | [6 empty] | 31580 | 23646 | 2.36 | 0 | 0 | 6.62 | 5805
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 03:30 |  | 4d 03:30 | 2029-04-10 19:48 | 2029-04-14 23:18
TS6060#1 | GG\32\010\D | GG | 32 | 10 | D | 8 Coal Mining | 22.4 | 0 | 22.4 | 2029-04-11 06:55 | 2029-04-11 17:08 | 13833.0166 | [6 empty] | 13833 | 10358 | 1.04 | 0 | 0 | 6.58 | 5809
TS5500Exc | W2\04\007\D | W2 | 4 | 7 | D | 8 Coal Mining | 29.3 | 0 | 29.3 | 2029-04-11 13:59 | 2029-04-12 20:28 | 38401.7471 | [6 empty] | 38402 | 27870 | 1.39 | 0 | 0 | 5.81 | 5755
TS6060#1 | CP\09\003\B | CP | 9 | 3 | B | 1 Prestrip - Thick | 12.4642 | 12.4642 | 12.4642 | 2029-04-11 17:08 | 2029-04-20 12:51 | 216040.4119 | 216040 | [7 empty] | 0 | 0 | 6.84 | 8.9 | 5596.18
TS5500Exc | W2\04\007\D | W2 | 4 | 7 | D | 8 Coal Mining | 70.7 | 0 | 70.7 | 2029-04-12 20:28 | 2029-04-15 22:11 | 92851.5992 | [6 empty] | 92852 | 67388 | 3.37 | 0 | 0 | 5.81 | 5755
DRE2 | GG\32\008\D | GG | 32 | 8 | D | 6 DL | 100 | 0 | 0 | 2029-04-14 23:18 | 2029-04-14 23:18 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\33\014\B | GG | 33 | 14 | B | 6 DL | 100 | 0 | 100 | 2029-04-14 23:18 | 2029-04-20 05:14 | 378392.3929 |  |  |  |  | 378392 | 315327 |  |  | 0 | 17.85 | 0 | 13.55 | 5219.65
TS5500Shv | GG\32\009\D | GG | 32 | 9 | D | 8 Coal Mining | 75.4 | 0 | 75.4 | 2029-04-14 23:18 | 2029-04-16 13:22 | 46418.13 | [6 empty] | 46418 | 34784 | 3.48 | 0 | 0 | 6.55 | 5811
TS5500Exc | CP\03\005\B | CP | 3 | 5 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-04-15 22:11 | 2029-04-22 22:39 | 212200.7617 | [6 empty] | 212201 | 150333 | 1.6 | 0 | 0 | 8.68 | 5598
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 15:51 |  | 3d 15:51 | 2029-04-16 13:22 | 2029-04-20 05:14
PH4100A | W2\11\003\D | W2 | 11 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-04-17 09:03 | 2029-06-13 11:12 | 2485544.902 | 2485545 | [7 empty] | 0 | 0 | 80.06 | 5.5 | 5784.34
DRE2 | GG\33\017\B | GG | 33 | 17 | B | 6 DL | 100 | 0 | 100 | 2029-04-20 05:14 | 2029-04-22 22:49 | 197114.7892 |  |  |  |  | 197115 | 164262 |  |  | 0 | 16.21 | 0 | 14.2 | 5188.15
TS5500Shv | GG\33\014\B | GG | 33 | 14 | B | 8 Coal Mining | 73.1 | 0 | 73.1 | 2029-04-20 05:14 | 2029-04-22 10:09 | 64533.4345 | [6 empty] | 64533 | 46341 | 2.73 | 0 | 0 | 13.55 | 5220
TS6060#1 | GG\32\009\D | GG | 32 | 9 | D | 8 Coal Mining | 24.6 | 0 | 24.6 | 2029-04-20 12:51 | 2029-04-21 00:04 | 15177.048 | [6 empty] | 15177 | 11373 | 1.14 | 0 | 0 | 6.55 | 5811
TS6060#1 | GG\33\014\B | GG | 33 | 14 | B | 8 Coal Mining | 26.9 | 0 | 26.9 | 2029-04-21 00:04 | 2029-04-21 17:35 | 23708.3411 | [6 empty] | 23708 | 17025 | 1 | 0 | 0 | 13.55 | 5220
TS6060#1 | CP\12\001\B | CP | 12 | 1 | B | 1 Prestrip - Thick | 9.1719 | 9.1719 | 9.1719 | 2029-04-21 17:35 | 2029-04-24 16:36 | 72647.3862 | 72647 | [7 empty] | 0 | 0 | 3.39 | 9.96 | 5492.25
TS Fleet 5 | CP\06\005\B | CP | 6 | 5 | B | 1 Prestrip - Thick | 45.3134 | 45.3134 | 45.3134 | 2029-04-22 04:40 | 2029-05-10 10:08 | 857407.4623 | 857407 | [7 empty] | 0 | 0 | 28.52 | 8.54 | 5610.71
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 12:40 |  | 0d 12:40 | 2029-04-22 10:09 | 2029-04-22 22:49
TS5500Exc | W2\10\003\B | W2 | 10 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-04-22 22:39 | 2029-04-24 09:03 | 43341.9578 | [6 empty] | 43342 | 30517 | 1.26 | 0 | 0 | 10.79 | 5245
DRE2 | GG\33\018\B | GG | 33 | 18 | B | 6 DL | 100 | 0 | 100 | 2029-04-22 22:49 | 2029-04-25 14:01 | 189877.8166 |  |  |  |  | 189878 | 158232 |  |  | 0 | 15.86 | 0 | 15.82 | 5067.91
TS5500Shv | GG\33\017\B | GG | 33 | 17 | B | 8 Coal Mining | 87.1 | 0 | 87.1 | 2029-04-22 22:49 | 2029-04-24 10:13 | 43150.4146 | [6 empty] | 43150 | 30840 | 3.08 | 0 | 0 | 14.2 | 5188
PH4100XPC#1 | W2\05\008\D | W2 | 5 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-04-24 08:06 | 2029-04-30 04:55 | 318734.5109 | 318735 | [7 empty] | 0 | 0 | 20.99 | 5.95 | 5743.12
TS5500Exc | GG\33\017\B | GG | 33 | 17 | B | 8 Coal Mining | 100 | 0 | 12.9 | 2029-04-24 09:03 | 2029-04-24 14:08 | 6391.3395 | [6 empty] | 6391 | 4568 | 0.46 | 0 | 0 | 14.2 | 5188
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 03:48 |  | 1d 03:48 | 2029-04-24 10:13 | 2029-04-25 14:01
TS5500Exc | W2\04\008\B | W2 | 4 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-04-24 14:08 | 2029-04-27 15:01 | 91797.3899 | [6 empty] | 91797 | 64193 | 3.21 | 0 | 0 | 10.12 | 5275
TS6060#1 | CP\03\005\D | CP | 3 | 5 | D | 1 Prestrip - Thick | 33.1915 | 33.1915 | 33.1915 | 2029-04-24 16:36 | 2029-06-24 09:31 | 1503255.335 | 1503255 | [7 empty] | 0 | 0 | 17.47 | 6.06 | 5873.34
DRE2 | GG\33\019\B | GG | 33 | 19 | B | 6 DL | 100 | 0 | 100 | 2029-04-25 14:01 | 2029-04-28 10:37 | 206165.914 |  |  |  |  | 206166 | 171805 |  |  | 0 | 15.94 | 0 | 18.68 | 4843.95
TS5500Shv | GG\33\018\B | GG | 33 | 18 | B | 8 Coal Mining | 81.1 | 0 | 81.1 | 2029-04-25 14:01 | 2029-04-26 18:09 | 34308.4903 | [6 empty] | 34308 | 24315 | 2.42 | 0 | 0 | 15.82 | 5068
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 16:28 |  | 1d 16:28 | 2029-04-26 18:09 | 2029-04-28 10:37
TS5500Exc | W1\10\003\D | W1 | 10 | 3 | D | 7 PostStrip | 48.2146 | 0 | 48.2146 | 2029-04-27 15:01 | 2029-04-29 13:02 | 40700.1405 |  |  | 40700 | [5 empty] | 0 | 0 | 0 | 8.28 | 5534.31
DRE2 | GG\34\014\B | GG | 34 | 14 | B | 6 DL | 100 | 0 | 0 | 2029-04-28 10:37 | 2029-04-28 10:37 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\015\B | GG | 34 | 15 | B | 6 DL | 100 | 0 | 0 | 2029-04-28 10:37 | 2029-04-28 10:37 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\016\B | GG | 34 | 16 | B | 6 DL | 100 | 0 | 0 | 2029-04-28 10:37 | 2029-04-28 10:37 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\017\B | GG | 34 | 17 | B | 6 DL | 100 | 0 | 0 | 2029-04-28 10:37 | 2029-04-28 10:37 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\018\B | GG | 34 | 18 | B | 6 DL | 100 | 0 | 0 | 2029-04-28 10:37 | 2029-04-28 10:37 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\019\B | GG | 34 | 19 | B | 6 DL | 100 | 0 | 0 | 2029-04-28 10:37 | 2029-04-28 10:37 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\020\B | GG | 34 | 20 | B | 6 DL | 100 | 0 | 0 | 2029-04-28 10:37 | 2029-04-28 10:37 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\33\014\D | GG | 33 | 14 | D | 6 DL | 100 | 100 | 100 | 2029-04-28 10:37 | 2029-05-09 02:30 | 768922.2587 |  |  |  | 17903 | 768922 | 340152 |  |  | 0 | 22.15 | 0 | 6.84 | 5784.76
TS5500Shv | GG\33\019\B | GG | 33 | 19 | B | 8 Coal Mining | 59.9 | 0 | 59.9 | 2029-04-28 10:37 | 2029-04-29 04:51 | 22226.6282 | [6 empty] | 22227 | 15526 | 1.54 | 0 | 0 | 18.68 | 4844
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 9d 21:39 |  | 9d 21:39 | 2029-04-29 04:51 | 2029-05-09 02:30
TS5500Exc | W1\10\003\D | W1 | 10 | 3 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-04-29 13:02 | 2029-04-30 22:48 | 42543.8573 | [6 empty] | 42544 | 30635 | 2.15 | 0 | 0 | 8.28 | 5534
PH4100XPC#1 | W2\04\008\D | W2 | 4 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-04-30 04:55 | 2029-05-06 04:17 | 324516.4045 | 324516 | [7 empty] | 0 | 0 | 21.21 | 5.97 | 5740.62
TS5500Exc | W2\05\008\D | W2 | 5 | 8 | D | 7 PostStrip | 57.3023 | 0 | 57.3023 | 2029-04-30 22:48 | 2029-05-03 15:23 | 57114.6954 |  |  | 57115 | [5 empty] | 0 | 0 | 0 | 5.95 | 5743.12
TS5500Exc | W2\08\006\B | W2 | 8 | 6 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-05-03 15:23 | 2029-05-04 21:01 | 37331.3638 | [6 empty] | 37331 | 26147 | 1.29 | 0 | 0 | 10.24 | 5257
TS5500Exc | W2\08\004\D | W2 | 8 | 4 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-05-04 21:01 | 2029-05-07 01:12 | 46145.3566 |  |  | 46145 | [5 empty] | 0 | 0 | 0 | 5.67 | 5768.94
PH4100XPC#1 | W2\04\009\D | W2 | 4 | 9 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\05\009\D | W2 | 5 | 9 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\04\010\B | W2 | 4 | 10 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\05\010\B | W2 | 5 | 10 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\04\010\D | W2 | 4 | 10 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\05\010\D | W2 | 5 | 10 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\04\011\B | W2 | 4 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\05\011\B | W2 | 5 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\04\011\D | W2 | 4 | 11 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\05\011\D | W2 | 5 | 11 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\04\012\B | W2 | 4 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\04\012\D | W2 | 4 | 12 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\05\012\B | W2 | 5 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\03\013\B | W2 | 3 | 13 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\05\012\D | W2 | 5 | 12 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\03\013\D | W2 | 3 | 13 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\05\013\B | W2 | 5 | 13 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\06\009\B | W2 | 6 | 9 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\05\013\D | W2 | 5 | 13 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\06\009\D | W2 | 6 | 9 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\07\009\D | W2 | 7 | 9 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-05-06 04:17 | 2029-05-06 04:17 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\07\008\B | W2 | 7 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-05-06 04:17 | 2029-05-24 07:53 | 1010047.408 | 1010047 | [7 empty] | 0 | 0 | 44.44 | 10.27 | 5253.84
TS5500Exc | W2\04\008\D | W2 | 4 | 8 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-05-07 01:12 | 2029-05-09 05:25 | 46187.3794 |  |  | 46187 | [5 empty] | 0 | 0 | 0 | 5.97 | 5740.62
DRE2 | GG\33\017\D | GG | 33 | 17 | D | 6 DL | 100 | 100 | 100 | 2029-05-09 02:30 | 2029-05-16 04:38 | 511214.8049 |  |  |  | 11903 | 511215 | 226149 |  |  | 0 | 23.79 | 0 | 6.82 | 5786.83
TS5500Shv | GG\33\014\D | GG | 33 | 14 | D | 8 Coal Mining | 63.7 | 0 | 63.7 | 2029-05-09 02:30 | 2029-05-11 05:16 | 61887.1829 | [6 empty] | 61887 | 46155 | 2.88 | 0 | 0 | 6.84 | 5785
TS5500Exc | W2\08\004\D | W2 | 8 | 4 | D | 8 Coal Mining | 53.9 | 0 | 53.9 | 2029-05-09 05:25 | 2029-05-11 15:37 | 73305.8275 | [6 empty] | 73306 | 53536 | 2.68 | 0 | 0 | 5.67 | 5769
TS Fleet 5 | W2\08\006\D | W2 | 8 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-05-10 10:08 | 2029-05-16 22:51 | 307173.2076 | 307173 | [7 empty] | 0 | 0 | 20.32 | 5.55 | 5776.11
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 23:22 |  | 4d 23:22 | 2029-05-11 05:16 | 2029-05-16 04:38
TS5500Exc | W2\08\005\D | W2 | 8 | 5 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-05-11 15:37 | 2029-05-13 19:51 | 46185.6524 |  |  | 46186 | [5 empty] | 0 | 0 | 0 | 5.58 | 5775.04
TS5500Exc | W2\08\005\D | W2 | 8 | 5 | D | 8 Coal Mining | 59.8 | 0 | 59.8 | 2029-05-13 19:51 | 2029-05-16 10:52 | 79378.5072 | [6 empty] | 79379 | 57834 | 2.89 | 0 | 0 | 5.58 | 5775
DRE2 | GG\33\020\B | GG | 33 | 20 | B | 6 DL | 100 | 0 | 100 | 2029-05-16 04:38 | 2029-05-18 17:21 | 182458.4378 |  |  |  |  | 182458 | 140353 |  |  | 0 | 15.8 | 0 | 13.17 | 5279.32
TS5500Shv | GG\33\017\D | GG | 33 | 17 | D | 8 Coal Mining | 73.4 | 0 | 73.4 | 2029-05-16 04:38 | 2029-05-17 17:15 | 44644.4599 | [6 empty] | 44644 | 33349 | 3.33 | 0 | 0 | 6.82 | 5787
TS5500Exc | W2\09\003\D | W2 | 9 | 3 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-05-16 10:52 | 2029-05-19 03:11 | 56892.4305 |  |  | 56892 | [5 empty] | 0 | 0 | 0 | 5.72 | 5765.29
TS Fleet 5 | W2\10\003\D | W2 | 10 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-05-16 22:51 | 2029-05-22 15:47 | 268401.6905 | 268402 | [7 empty] | 0 | 0 | 16.75 | 5.63 | 5773.48
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 00:06 |  | 1d 00:06 | 2029-05-17 17:15 | 2029-05-18 17:21
DRE2 | GG\32\014\D | GG | 32 | 14 | D | 6 DL | 100 | 100 | 100 | 2029-05-18 17:21 | 2029-05-28 10:41 | 701170.6657 |  |  |  | 16325 | 701171 | 310180 |  |  | 0 | 22.36 | 0 | 6.84 | 5783.35
TS5500Shv | GG\33\020\B | GG | 33 | 20 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-05-18 17:21 | 2029-05-19 07:43 | 17526.92 | [6 empty] | 17527 | 12603 | 1.43 | 0 | 0 | 13.17 | 5279
TS5500Exc | W2\08\006\D | W2 | 8 | 6 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-05-19 03:11 | 2029-05-21 07:31 | 46282.3268 |  |  | 46282 | [5 empty] | 0 | 0 | 0 | 5.55 | 5776.11
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 9d 02:58 |  | 9d 02:58 | 2029-05-19 07:43 | 2029-05-28 10:41
TS5500Exc | W2\09\003\D | W2 | 9 | 3 | D | 8 Coal Mining | 54.7 | 0 | 54.7 | 2029-05-21 07:31 | 2029-05-24 08:52 | 92391.6463 | [6 empty] | 92392 | 67583 | 2.78 | 0 | 0 | 5.72 | 5765
TS Fleet 5 | CP\03\005\D | CP | 3 | 5 | D | 1 Prestrip - Thick | 21.7834 | 21.7834 | 21.7834 | 2029-05-22 15:47 | 2029-06-12 15:09 | 986579.5052 | 986580 | [7 empty] | 0 | 0 | 11.46 | 6.06 | 5873.34
PH4100XPC#1 | W2\06\007\D | W2 | 6 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-05-24 07:53 | 2029-05-30 00:41 | 309650.492 | 309650 | [7 empty] | 0 | 0 | 20.54 | 5.71 | 5763.44
TS5500Exc | W2\07\008\B | W2 | 7 | 8 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-05-24 08:52 | 2029-05-27 04:33 | 85236.5329 | [6 empty] | 85237 | 59572 | 2.91 | 0 | 0 | 10.27 | 5254
TS5500Exc | W2\09\004\D | W2 | 9 | 4 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-05-27 04:33 | 2029-05-29 08:45 | 46170.268 |  |  | 46170 | [5 empty] | 0 | 0 | 0 | 5.61 | 5774.47
DRE2 | GG\32\017\D | GG | 32 | 17 | D | 6 DL | 100 | 100 | 100 | 2029-05-28 10:41 | 2029-06-04 12:23 | 509946.678 |  |  |  | 11873 | 509947 | 225588 |  |  | 0 | 23.77 | 0 | 6.85 | 5784.42
TS5500Shv | GG\32\014\D | GG | 32 | 14 | D | 8 Coal Mining | 73.6 | 0 | 73.6 | 2029-05-28 10:41 | 2029-05-30 14:57 | 63731.4224 | [6 empty] | 63731 | 47530 | 3.28 | 0 | 0 | 6.84 | 5783
TS5500Exc | W2\09\004\D | W2 | 9 | 4 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-05-29 08:45 | 2029-05-31 12:53 | 65676.6186 | [6 empty] | 65677 | 48002 | 2.4 | 0 | 0 | 5.61 | 5774
PH4100XPC#1 | W2\07\008\D | W2 | 7 | 8 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-05-30 00:41 | 2029-06-05 01:26 | 327639.3806 | 327639 | [7 empty] | 0 | 0 | 21.22 | 5.88 | 5749.17
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 21:26 |  | 4d 21:26 | 2029-05-30 14:57 | 2029-06-04 12:23
TS5500Exc | W2\06\007\D | W2 | 6 | 7 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-05-31 12:53 | 2029-06-02 16:53 | 45981.4441 |  |  | 45981 | [5 empty] | 0 | 0 | 0 | 5.71 | 5763.44
TS5500Exc | W2\09\005\D | W2 | 9 | 5 | D | 7 PostStrip | 47.6978 | 0 | 47.6978 | 2029-06-02 16:53 | 2029-06-04 22:53 | 47758.3252 |  |  | 47758 | [5 empty] | 0 | 0 | 0 | 5.54 | 5779.13
DRE2 | GG\32\018\D | GG | 32 | 18 | D | 6 DL | 100 | 100 | 100 | 2029-06-04 12:23 | 2029-06-11 17:15 | 519457.6998 |  |  |  | 12094 | 519458 | 229795 |  |  | 0 | 24.19 | 0 | 6.82 | 5787.12
TS5500Shv | GG\32\017\D | GG | 32 | 17 | D | 8 Coal Mining | 92.8 | 0 | 92.8 | 2029-06-04 12:23 | 2029-06-06 11:02 | 56876.1905 | [6 empty] | 56876 | 42452 | 4.24 | 0 | 0 | 6.85 | 5784
TS5500Exc | W2\09\005\D | W2 | 9 | 5 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-06-04 22:53 | 2029-06-07 01:49 | 64149.4648 | [6 empty] | 64149 | 46775 | 2.34 | 0 | 0 | 5.54 | 5779
PH4100XPC#1 | W2\07\007\B | W2 | 7 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-06-05 01:26 | 2029-06-23 19:42 | 1046941.647 | 1046942 | [7 empty] | 0 | 0 | 47.77 | 11.62 | 5152.16
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 06:13 |  | 5d 06:13 | 2029-06-06 11:02 | 2029-06-11 17:15
TS5500Exc | W2\07\008\D | W2 | 7 | 8 | D | 7 PostStrip | 58.4411 | 0 | 58.4411 | 2029-06-07 01:49 | 2029-06-09 20:34 | 59034.4622 |  |  | 59034 | [5 empty] | 0 | 0 | 0 | 5.88 | 5749.17
TS5500Exc | W2\10\003\D | W2 | 10 | 3 | D | 7 PostStrip | 55.9033 | 0 | 55.9033 | 2029-06-09 20:34 | 2029-06-12 20:45 | 63844.4852 |  |  | 63844 | [5 empty] | 0 | 0 | 0 | 5.63 | 5773.48
DRE2 | GG\32\019\D | GG | 32 | 19 | D | 6 DL | 100 | 100 | 100 | 2029-06-11 17:15 | 2029-06-18 20:17 | 513915.0186 |  |  |  | 11965 | 513915 | 227343 |  |  | 0 | 23.92 | 0 | 6.79 | 5789.8
TS5500Shv | GG\32\018\D | GG | 32 | 18 | D | 8 Coal Mining | 82.7 | 0 | 82.7 | 2029-06-11 17:15 | 2029-06-13 10:59 | 50884.7382 | [6 empty] | 50885 | 38010 | 3.8 | 0 | 0 | 6.82 | 5787
TS Fleet 5 | CP\07\001\B | CP | 7 | 1 | B | 1 Prestrip - Thick | 45.6887 | 45.6887 | 45.6887 | 2029-06-12 15:09 | 2029-06-15 15:50 | 142470.2685 | 142470 | [7 empty] | 0 | 0 | 9.98 | 9.14 | 5596.2
TS5500Exc | W2\10\005\B | W2 | 10 | 5 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-06-12 20:45 | 2029-06-14 09:31 | 46313.5096 | [6 empty] | 46314 | 32638 | 1.62 | 0 | 0 | 9.74 | 5309
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 09:18 |  | 5d 09:18 | 2029-06-13 10:59 | 2029-06-18 20:17
PH4100A | W2\10\004\B | W2 | 10 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-06-13 11:12 | 2029-07-15 05:16 | 1341658.161 | 1341658 | [7 empty] | 0 | 0 | 71.73 | 9.49 | 5338.13
TS5500Exc | W2\11\003\D | W2 | 11 | 3 | D | 7 PostStrip | 51.2179 | 0 | 51.2179 | 2029-06-14 09:31 | 2029-06-18 09:40 | 85031.1659 |  |  | 85031 | [5 empty] | 0 | 0 | 0 | 5.5 | 5784.34
TS Fleet 5 | W2\10\005\D | W2 | 10 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-06-15 15:50 | 2029-06-22 13:40 | 325026.6291 | 325027 | [7 empty] | 0 | 0 | 21.2 | 5.48 | 5784.61
TS5500Exc | SC\50\021\D | SC | 50 | 21 | D | 1 Prestrip - Thick | 73.0487 | 73.0487 | 73.0487 | 2029-06-18 09:40 | 2029-07-24 22:41 | 776611.125 | 776611 | [7 empty] | 0 | 0 | 36.39 | 7.31 | 5768.58
DRE2 | GG\32\020\D | GG | 32 | 20 | D | 6 DL | 100 | 100 | 100 | 2029-06-18 20:17 | 2029-06-25 07:56 | 467725.1378 |  |  |  | 7259 | 467725 | 133790 |  |  | 0 | 22.44 | 0 | 6.75 | 5793.08
TS5500Shv | GG\32\019\D | GG | 32 | 19 | D | 8 Coal Mining | 69.4 | 0 | 69.4 | 2029-06-18 20:17 | 2029-06-20 07:39 | 43136.5939 | [6 empty] | 43137 | 32223 | 3.22 | 0 | 0 | 6.79 | 5790
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 00:17 |  | 5d 00:17 | 2029-06-20 07:39 | 2029-06-25 07:56
TS Fleet 5 | CP\07\002\B | CP | 7 | 2 | B | 1 Prestrip - Thick | 45.3644 | 45.3644 | 45.3644 | 2029-06-22 13:40 | 2029-07-03 08:51 | 508020.2995 | 508020 | [7 empty] | 0 | 0 | 16.89 | 9.59 | 5557.75
PH4100XPC#1 | W2\07\006\B | W2 | 7 | 6 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-06-23 19:42 | 2029-07-13 09:08 | 1086166.502 | 1086167 | [7 empty] | 0 | 0 | 62.01 | 10.39 | 5244.59
TS6060#1 | W1\10\003\D | W1 | 10 | 3 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-06-24 09:31 | 2029-06-25 19:18 | 45712.0169 | [6 empty] | 45712 | 32916 | 2.31 | 0 | 0 | 8.28 | 5534
DRE2 | GG\34\013\B | GG | 34 | 13 | B | 6 DL | 100 | 0 | 0 | 2029-06-25 07:56 | 2029-06-25 07:56 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\011\B | GG | 34 | 11 | B | 6 DL | 100 | 0 | 0 | 2029-06-25 07:56 | 2029-06-25 07:56 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\010\B | GG | 34 | 10 | B | 6 DL | 100 | 0 | 0 | 2029-06-25 07:56 | 2029-06-25 07:56 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\009\B | GG | 34 | 9 | B | 6 DL | 100 | 0 | 0 | 2029-06-25 07:56 | 2029-06-25 07:56 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\008\B | GG | 34 | 8 | B | 6 DL | 100 | 0 | 0 | 2029-06-25 07:56 | 2029-06-25 07:56 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\007\B | GG | 34 | 7 | B | 6 DL | 100 | 0 | 0 | 2029-06-25 07:56 | 2029-06-25 07:56 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\33\013\D | GG | 33 | 13 | D | 6 DL | 100 | 100 | 100 | 2029-06-25 07:56 | 2029-07-01 16:08 | 457334.5774 |  |  |  | 10648 | 457335 | 202313 |  |  | 0 | 21.32 | 0 | 6.76 | 5790.11
TS5500Shv | GG\32\020\D | GG | 32 | 20 | D | 7 PostStrip | 86.1144 | 0 | 86.1144 | 2029-06-25 07:56 | 2029-06-26 16:25 | 34818.6409 |  |  | 34819 | [5 empty] | 0 | 0 | 0 | 6.75 | 5793.08
TS6060#1 | W2\04\008\D | W2 | 4 | 8 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-06-25 19:18 | 2029-06-27 23:31 | 53885.276 |  |  | 53885 | [5 empty] | 0 | 0 | 0 | 5.97 | 5740.62
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 23:43 |  | 4d 23:43 | 2029-06-26 16:25 | 2029-07-01 16:08
TS6060#1 | W2\04\008\D | W2 | 4 | 8 | D | 8 Coal Mining | 45.6 | 0 | 45.6 | 2029-06-27 23:31 | 2029-06-29 19:46 | 59876.4596 | [6 empty] | 59876 | 43355 | 2.17 | 0 | 0 | 5.97 | 5741
TS6060#1 | W2\05\008\D | W2 | 5 | 8 | D | 7 PostStrip | 42.6977 | 0 | 42.6977 | 2029-06-29 19:46 | 2029-07-01 13:01 | 42557.9825 |  |  | 42558 | [5 empty] | 0 | 0 | 0 | 5.95 | 5743.12
TS6060#1 | W2\05\008\D | W2 | 5 | 8 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-07-01 13:01 | 2029-07-03 16:22 | 69514.8238 | [6 empty] | 69515 | 50337 | 2.52 | 0 | 0 | 5.95 | 5743
DRE2 | GG\33\012\D | GG | 33 | 12 | D | 6 DL | 100 | 100 | 100 | 2029-07-01 16:08 | 2029-07-07 18:20 | 439356.9046 |  |  |  | 10229 | 439357 | 194360 |  |  | 0 | 20.48 | 0 | 6.69 | 5798.09
TS5500Shv | GG\33\013\D | GG | 33 | 13 | D | 8 Coal Mining | 56.3 | 0 | 56.3 | 2029-07-01 16:08 | 2029-07-02 19:31 | 33402.6556 | [6 empty] | 33403 | 24931 | 2.49 | 0 | 0 | 6.76 | 5790
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 22:49 |  | 4d 22:49 | 2029-07-02 19:31 | 2029-07-07 18:20
TS Fleet 5 | CP\07\003\B | CP | 7 | 3 | B | 1 Prestrip - Thick | 45.0378 | 45.0378 | 45.0378 | 2029-07-03 08:51 | 2029-07-19 00:36 | 736469.3621 | 736469 | [7 empty] | 0 | 0 | 25.13 | 8.96 | 5590.85
TS6060#1 | W2\06\007\D | W2 | 6 | 7 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-07-03 16:22 | 2029-07-05 20:22 | 53645.0181 |  |  | 53645 | [5 empty] | 0 | 0 | 0 | 5.71 | 5763.44
TS6060#1 | W2\06\007\D | W2 | 6 | 7 | D | 8 Coal Mining | 46.2 | 0 | 46.2 | 2029-07-05 20:22 | 2029-07-07 17:17 | 60784.7648 | [6 empty] | 60785 | 44115 | 2.21 | 0 | 0 | 5.71 | 5763
TS6060#1 | GG\33\018\B | GG | 33 | 18 | B | 8 Coal Mining | 18.9 | 0 | 18.9 | 2029-07-07 17:17 | 2029-07-07 23:11 | 8002.4367 | [6 empty] | 8002 | 5672 | 0.56 | 0 | 0 | 15.82 | 5068
DRE2 | GG\33\011\D | GG | 33 | 11 | D | 6 DL | 100 | 100 | 100 | 2029-07-07 18:20 | 2029-07-13 20:40 | 439732.7959 |  |  |  | 7947 | 439733 | 190719 |  |  | 0 | 19.89 | 0 | 6.62 | 5804.68
TS5500Shv | GG\33\012\D | GG | 33 | 12 | D | 8 Coal Mining | 61.2 | 0 | 61.2 | 2029-07-07 18:20 | 2029-07-09 01:12 | 37644.0412 | [6 empty] | 37644 | 28142 | 2.81 | 0 | 0 | 6.69 | 5798
TS6060#1 | GG\33\019\B | GG | 33 | 19 | B | 8 Coal Mining | 40.1 | 0 | 40.1 | 2029-07-07 23:11 | 2029-07-08 10:10 | 14853.1701 | [6 empty] | 14853 | 10375 | 1.03 | 0 | 0 | 18.68 | 4844
TS6060#1 | GG\33\014\D | GG | 33 | 14 | D | 8 Coal Mining | 36.3 | 0 | 36.3 | 2029-07-08 10:10 | 2029-07-09 12:14 | 35274.7915 | [6 empty] | 35275 | 26308 | 1.64 | 0 | 0 | 6.84 | 5785
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 19:28 |  | 4d 19:28 | 2029-07-09 01:12 | 2029-07-13 20:40
TS6060#1 | W2\07\008\D | W2 | 7 | 8 | D | 7 PostStrip | 41.5589 | 0 | 41.5589 | 2029-07-09 12:14 | 2029-07-11 04:55 | 41980.8764 |  |  | 41981 | [5 empty] | 0 | 0 | 0 | 5.88 | 5749.17
TS6060#1 | W2\07\008\D | W2 | 7 | 8 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-07-11 04:55 | 2029-07-13 08:06 | 69278.9949 | [6 empty] | 69279 | 50127 | 2.51 | 0 | 0 | 5.88 | 5749
TS6060#1 | GG\33\017\D | GG | 33 | 17 | D | 8 Coal Mining | 26.6 | 0 | 26.6 | 2029-07-13 08:06 | 2029-07-13 20:02 | 16147.4063 | [6 empty] | 16147 | 12062 | 1.21 | 0 | 0 | 6.82 | 5787
PH4100XPC#1 | W2\06\006\D | W2 | 6 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-07-13 09:08 | 2029-07-18 23:51 | 304925.3672 | 304925 | [7 empty] | 0 | 0 | 20.24 | 5.63 | 5769.31
TS6060#1 | W2\08\004\D | W2 | 8 | 4 | D | 8 Coal Mining | 46.1 | 0 | 46.1 | 2029-07-13 20:02 | 2029-07-15 18:18 | 62617.3658 | [6 empty] | 62617 | 45730 | 2.29 | 0 | 0 | 5.67 | 5769
DRE2 | GG\33\018\D | GG | 33 | 18 | D | 6 DL | 100 | 100 | 100 | 2029-07-13 20:40 | 2029-07-21 01:10 | 518310.2301 |  |  |  | 12068 | 518310 | 229287 |  |  | 0 | 24.14 | 0 | 6.79 | 5789.44
TS5500Shv | GG\33\011\D | GG | 33 | 11 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-07-13 20:40 | 2029-07-15 23:32 | 62027.3059 | [6 empty] | 62027 | 46408 | 4.64 | 0 | 0 | 6.62 | 5805
PH4100A | W2\11\004\B | W2 | 11 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-07-15 05:16 | 2029-08-16 15:39 | 1396479.754 | 1396480 | [7 empty] | 0 | 0 | 83.08 | 9.65 | 5333.14
TS6060#1 | W2\10\004\B | W2 | 10 | 4 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-07-15 18:18 | 2029-07-17 06:38 | 49175.5506 | [6 empty] | 49176 | 34798 | 1.73 | 0 | 0 | 9.49 | 5338
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 01:37 |  | 5d 01:37 | 2029-07-15 23:32 | 2029-07-21 01:10
TS6060#1 | W2\08\005\D | W2 | 8 | 5 | D | 8 Coal Mining | 40.2 | 0 | 40.2 | 2029-07-17 06:38 | 2029-07-18 22:00 | 53283.1677 | [6 empty] | 53283 | 38821 | 1.94 | 0 | 0 | 5.58 | 5775
TS6060#1 | W2\08\006\D | W2 | 8 | 6 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-07-18 22:00 | 2029-07-21 02:20 | 53996.0479 |  |  | 53996 | [5 empty] | 0 | 0 | 0 | 5.55 | 5776.11
PH4100XPC#1 | W2\07\005\D | W2 | 7 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-07-18 23:51 | 2029-07-24 06:50 | 287445.5857 | 287446 | [7 empty] | 0 | 0 | 19.37 | 5.62 | 5771.42
TS Fleet 5 | CP\07\004\B | CP | 7 | 4 | B | 1 Prestrip - Thick | 36.4723 | 36.4723 | 36.4723 | 2029-07-19 00:36 | 2029-07-31 19:14 | 600992.8324 | 600993 | [7 empty] | 0 | 0 | 20.13 | 8.43 | 5622.47
DRE2 | GG\33\019\D | GG | 33 | 19 | D | 6 DL | 100 | 100 | 100 | 2029-07-21 01:10 | 2029-07-28 05:15 | 517108.0815 |  |  |  | 12040 | 517108 | 228756 |  |  | 0 | 24.06 | 0 | 6.78 | 5790.95
TS5500Shv | GG\33\018\D | GG | 33 | 18 | D | 8 Coal Mining | 47.6 | 0 | 47.6 | 2029-07-21 01:10 | 2029-07-22 01:00 | 29068.8531 | [6 empty] | 29069 | 21714 | 2.17 | 0 | 0 | 6.79 | 5789
TS6060#1 | W2\06\006\D | W2 | 6 | 6 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-07-21 02:20 | 2029-07-23 06:32 | 53858.0488 |  |  | 53858 | [5 empty] | 0 | 0 | 0 | 5.63 | 5769.31
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 6d 04:15 |  | 6d 04:15 | 2029-07-22 01:00 | 2029-07-28 05:15
TS6060#1 | GG\33\018\D | GG | 33 | 18 | D | 8 Coal Mining | 52.4 | 0 | 52.4 | 2029-07-23 06:32 | 2029-07-24 06:11 | 32006.505 | [6 empty] | 32007 | 23908 | 2.39 | 0 | 0 | 6.79 | 5789
TS6060#1 | W2\08\006\D | W2 | 8 | 6 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-07-24 06:11 | 2029-07-26 07:47 | 67123.8257 | [6 empty] | 67124 | 48789 | 2.44 | 0 | 0 | 5.55 | 5776
PH4100XPC#1 | W2\07\004\D | W2 | 7 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-07-24 06:50 | 2029-07-29 17:45 | 296324.6469 | 296325 | [7 empty] | 0 | 0 | 19.81 | 5.7 | 5766
TS5500Exc | W2\07\007\B | W2 | 7 | 7 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-07-24 22:41 | 2029-07-26 02:27 | 34978.6832 | [6 empty] | 34979 | 24333 | 1.22 | 0 | 0 | 11.62 | 5152
TS5500Exc | W2\07\006\B | W2 | 7 | 6 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-07-26 02:27 | 2029-07-28 09:39 | 69516.0333 | [6 empty] | 69516 | 48638 | 2.43 | 0 | 0 | 10.39 | 5245
TS6060#1 | W2\07\005\D | W2 | 7 | 5 | D | 7 PostStrip | 51.598 | 0 | 51.598 | 2029-07-26 07:47 | 2029-07-28 09:48 | 51615.2383 |  |  | 51615 | [5 empty] | 0 | 0 | 0 | 5.62 | 5771.42
DRE2 | GG\33\010\D | GG | 33 | 10 | D | 6 DL | 100 | 100 | 100 | 2029-07-28 05:15 | 2029-08-03 00:15 | 417700.9999 |  |  |  | 7778 | 417701 | 186682 |  |  | 0 | 19.46 | 0 | 6.58 | 5808.59
TS5500Shv | GG\33\019\D | GG | 33 | 19 | D | 8 Coal Mining | 94.5 | 0 | 94.5 | 2029-07-28 05:15 | 2029-07-30 05:07 | 58371.94 | [6 empty] | 58372 | 43638 | 4.36 | 0 | 0 | 6.78 | 5791
TS5500Exc | W2\04\008\D | W2 | 4 | 8 | D | 8 Coal Mining | 54.4 | 0 | 54.4 | 2029-07-28 09:39 | 2029-07-30 18:18 | 71363.8211 | [6 empty] | 71364 | 51673 | 2.58 | 0 | 0 | 5.97 | 5741
TS6060#1 | GG\33\019\D | GG | 33 | 19 | D | 8 Coal Mining | 5.5 | 0 | 5.5 | 2029-07-28 09:48 | 2029-07-28 12:19 | 3392.8687 | [6 empty] | 3393 | 2536 | 0.25 | 0 | 0 | 6.78 | 5791
TS6060#1 | GG\32\014\D | GG | 32 | 14 | D | 8 Coal Mining | 26.4 | 0 | 26.4 | 2029-07-28 12:19 | 2029-07-29 05:11 | 22820.7485 | [6 empty] | 22821 | 17019 | 1.17 | 0 | 0 | 6.84 | 5783
TS6060#1 | W2\09\003\D | W2 | 9 | 3 | D | 8 Coal Mining | 45.3 | 0 | 45.3 | 2029-07-29 05:11 | 2029-07-31 13:40 | 76451.1268 | [6 empty] | 76451 | 55923 | 2.3 | 0 | 0 | 5.72 | 5765
PH4100XPC#1 | W2\07\007\D | W2 | 7 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-07-29 17:45 | 2029-08-03 16:36 | 269013.6292 | 269014 | [7 empty] | 0 | 0 | 18.42 | 5.64 | 5768.94
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 19:08 |  | 3d 19:08 | 2029-07-30 05:07 | 2029-08-03 00:15
TS5500Exc | W2\10\004\B | W2 | 10 | 4 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-07-30 18:18 | 2029-08-01 06:38 | 45767.3441 | [6 empty] | 45767 | 32387 | 1.61 | 0 | 0 | 9.49 | 5338
TS6060#1 | W2\07\004\D | W2 | 7 | 4 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-07-31 13:40 | 2029-08-02 17:51 | 53853.0395 |  |  | 53853 | [5 empty] | 0 | 0 | 0 | 5.7 | 5766
TS Fleet 5 | CP\07\005\B | CP | 7 | 5 | B | 1 Prestrip - Thick | 45.2751 | 45.2751 | 45.2751 | 2029-07-31 19:14 | 2029-08-19 21:17 | 897775.9106 | 897776 | [7 empty] | 0 | 0 | 29.86 | 8.55 | 5609.62
TS5500Exc | W2\05\008\D | W2 | 5 | 8 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-08-01 06:38 | 2029-08-03 10:00 | 64696.9647 | [6 empty] | 64697 | 46848 | 2.34 | 0 | 0 | 5.95 | 5743
TS6060#1 | W2\09\004\D | W2 | 9 | 4 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-08-02 17:51 | 2029-08-04 22:00 | 70567.4306 | [6 empty] | 70567 | 51577 | 2.58 | 0 | 0 | 5.61 | 5774
DRE2 | GG\33\009\D | GG | 33 | 9 | D | 6 DL | 100 | 100 | 100 | 2029-08-03 00:15 | 2029-08-08 18:15 | 414709.3757 |  |  |  | 7723 | 414709 | 185345 |  |  | 0 | 19.31 | 0 | 6.54 | 5811.71
TS5500Shv | GG\33\010\D | GG | 33 | 10 | D | 8 Coal Mining | 87.4 | 0 | 87.4 | 2029-08-03 00:15 | 2029-08-04 20:29 | 53942.7482 | [6 empty] | 53943 | 40391 | 4.04 | 0 | 0 | 6.58 | 5809
TS5500Exc | W2\06\006\D | W2 | 6 | 6 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-08-03 10:00 | 2029-08-05 14:12 | 46164.0419 |  |  | 46164 | [5 empty] | 0 | 0 | 0 | 5.63 | 5769.31
PH4100XPC#1 | W2\07\006\D | W2 | 7 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-08-03 16:36 | 2029-08-09 04:21 | 298215.1692 | 298215 | [7 empty] | 0 | 0 | 19.94 | 5.59 | 5772.77
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 21:46 |  | 3d 21:46 | 2029-08-04 20:29 | 2029-08-08 18:15
TS6060#1 | W2\07\007\D | W2 | 7 | 7 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-08-04 22:00 | 2029-08-07 02:18 | 53968.2192 |  |  | 53968 | [5 empty] | 0 | 0 | 0 | 5.64 | 5768.94
TS5500Exc | W2\06\006\D | W2 | 6 | 6 | D | 8 Coal Mining | 53.3 | 0 | 53.3 | 2029-08-05 14:12 | 2029-08-07 21:08 | 69203.4843 | [6 empty] | 69203 | 50301 | 2.52 | 0 | 0 | 5.63 | 5769
TS6060#1 | W2\06\006\D | W2 | 6 | 6 | D | 8 Coal Mining | 46.7 | 0 | 46.7 | 2029-08-07 02:18 | 2029-08-08 23:01 | 60523.9187 | [6 empty] | 60524 | 43992 | 2.2 | 0 | 0 | 5.63 | 5769
TS5500Exc | W2\06\007\D | W2 | 6 | 7 | D | 8 Coal Mining | 53.8 | 0 | 53.8 | 2029-08-07 21:08 | 2029-08-10 05:16 | 70697.1327 | [6 empty] | 70697 | 51309 | 2.57 | 0 | 0 | 5.71 | 5763
DRE2 | GG\33\008\D | GG | 33 | 8 | D | 6 DL | 100 | 0 | 0 | 2029-08-08 18:15 | 2029-08-08 18:15 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\33\007\D | GG | 33 | 7 | D | 6 DL | 100 | 0 | 0 | 2029-08-08 18:15 | 2029-08-08 18:15 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\33\020\D | GG | 33 | 20 | D | 6 DL | 100 | 100 | 100 | 2029-08-08 18:15 | 2029-08-16 00:24 | 523269.3548 |  |  |  | 7925 | 523269 | 149268 |  |  | 0 | 24.2 | 0 | 6.75 | 5793.59
TS5500Shv | GG\33\009\D | GG | 33 | 9 | D | 8 Coal Mining | 83.6 | 0 | 83.6 | 2029-08-08 18:15 | 2029-08-10 12:24 | 51379.15 | [6 empty] | 51379 | 38502 | 3.85 | 0 | 0 | 6.54 | 5812
TS6060#1 | GG\32\017\D | GG | 32 | 17 | D | 8 Coal Mining | 7.2 | 0 | 7.2 | 2029-08-08 23:01 | 2029-08-09 02:16 | 4393.3684 | [6 empty] | 4393 | 3279 | 0.33 | 0 | 0 | 6.85 | 5784
TS6060#1 | W2\09\005\D | W2 | 9 | 5 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-08-09 02:16 | 2029-08-11 05:12 | 68926.5526 | [6 empty] | 68927 | 50258 | 2.51 | 0 | 0 | 5.54 | 5779
PH4100XPC#1 | W2\08\008\B | W2 | 8 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-08-09 04:21 | 2029-09-07 07:02 | 1623479.443 | 1623479 | [7 empty] | 0 | 0 | 61.79 | 10.6 | 5228.42
TS5500Exc | W2\07\004\D | W2 | 7 | 4 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-08-10 05:16 | 2029-08-12 09:27 | 46159.7481 |  |  | 46160 | [5 empty] | 0 | 0 | 0 | 5.7 | 5766
TS5500Shv | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 12:00 |  | 5d 12:00 | 2029-08-10 12:24 | 2029-08-16 00:24
TS6060#1 | W2\07\006\D | W2 | 7 | 6 | D | 7 PostStrip | 48.6094 | 0 | 48.6094 | 2029-08-11 05:12 | 2029-08-13 04:13 | 48512.1159 |  |  | 48512 | [5 empty] | 0 | 0 | 0 | 5.59 | 5772.77
TS5500Exc | W2\07\004\D | W2 | 7 | 4 | D | 8 Coal Mining | 56.7 | 0 | 56.7 | 2029-08-12 09:27 | 2029-08-14 22:19 | 76654.456 | [6 empty] | 76654 | 55981 | 2.8 | 0 | 0 | 5.7 | 5766
TS6060#1 | W2\07\004\D | W2 | 7 | 4 | D | 8 Coal Mining | 43.3 | 0 | 43.3 | 2029-08-13 04:13 | 2029-08-14 23:33 | 58654.4254 | [6 empty] | 58654 | 42836 | 2.14 | 0 | 0 | 5.7 | 5766
TS5500Exc | W2\07\005\D | W2 | 7 | 5 | D | 7 PostStrip | 48.402 | 0 | 48.402 | 2029-08-14 22:19 | 2029-08-17 05:04 | 48418.1517 |  |  | 48418 | [5 empty] | 0 | 0 | 0 | 5.62 | 5771.42
TS6060#1 | GG\32\018\D | GG | 32 | 18 | D | 8 Coal Mining | 17.3 | 0 | 17.3 | 2029-08-14 23:33 | 2029-08-15 07:27 | 10677.6432 | [6 empty] | 10678 | 7976 | 0.8 | 0 | 0 | 6.82 | 5787
TS6060#1 | GG\32\019\D | GG | 32 | 19 | D | 8 Coal Mining | 30.6 | 0 | 30.6 | 2029-08-15 07:27 | 2029-08-15 21:28 | 18986.3571 | [6 empty] | 18986 | 14183 | 1.42 | 0 | 0 | 6.79 | 5790
TS6060#1 | GG\32\020\D | GG | 32 | 20 | D | 7 PostStrip | 13.8856 | 0 | 13.8856 | 2029-08-15 21:28 | 2029-08-16 02:55 | 5614.3529 |  |  | 5614 | [5 empty] | 0 | 0 | 0 | 6.75 | 5793.08
DRE2 | GG\35\013\B | GG | 35 | 13 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\011\B | GG | 35 | 11 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\010\B | GG | 35 | 10 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\009\B | GG | 35 | 9 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\008\B | GG | 35 | 8 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\007\B | GG | 35 | 7 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\013\D | GG | 34 | 13 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\012\D | GG | 34 | 12 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\011\D | GG | 34 | 11 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\010\D | GG | 34 | 10 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\009\D | GG | 34 | 9 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\008\D | GG | 34 | 8 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\007\D | GG | 34 | 7 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\014\B | GG | 35 | 14 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\015\B | GG | 35 | 15 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\016\B | GG | 35 | 16 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\017\B | GG | 35 | 17 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\018\B | GG | 35 | 18 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\019\B | GG | 35 | 19 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\020\B | GG | 35 | 20 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\36\007\B | GG | 36 | 7 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\36\008\B | GG | 36 | 8 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\36\009\B | GG | 36 | 9 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\36\010\B | GG | 36 | 10 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\36\011\B | GG | 36 | 11 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\007\D | GG | 35 | 7 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\008\D | GG | 35 | 8 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\009\D | GG | 35 | 9 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\010\D | GG | 35 | 10 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\35\011\D | GG | 35 | 11 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\014\D | GG | 34 | 14 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\016\D | GG | 34 | 16 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\015\D | GG | 34 | 15 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\017\D | GG | 34 | 17 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\018\D | GG | 34 | 18 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\019\D | GG | 34 | 19 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\34\020\D | GG | 34 | 20 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\36\007\D | GG | 36 | 7 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\36\008\D | GG | 36 | 8 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\36\009\D | GG | 36 | 9 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\36\010\D | GG | 36 | 10 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\36\011\D | GG | 36 | 11 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\39\007\B | GG | 39 | 7 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\39\008\B | GG | 39 | 8 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\39\010\B | GG | 39 | 10 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\40\007\B | GG | 40 | 7 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\40\008\B | GG | 40 | 8 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\39\007\D | GG | 39 | 7 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\39\008\D | GG | 39 | 8 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\39\009\D | GG | 39 | 9 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\39\010\D | GG | 39 | 10 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\41\007\B | GG | 41 | 7 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\41\008\B | GG | 41 | 8 | B | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\40\007\D | GG | 40 | 7 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\40\008\D | GG | 40 | 8 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\40\009\D | GG | 40 | 9 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\40\010\D | GG | 40 | 10 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\41\007\D | GG | 41 | 7 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\41\008\D | GG | 41 | 8 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\41\009\D | GG | 41 | 9 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\41\010\D | GG | 41 | 10 | D | 6 DL | 100 | 0 | 0 | 2029-08-16 00:24 | 2029-08-16 00:24 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
TS5500Shv | GG\33\020\D | GG | 33 | 20 | D | 7 PostStrip | 100 | 0 | 100 | 2029-08-16 00:24 | 2029-08-17 14:35 | 40936.5071 |  |  | 40937 | [5 empty] | 0 | 0 | 0 | 6.75 | 5793.59
DRE2 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 08:08 |  | 2d 08:08 | 2029-08-16 00:24 | 2029-08-18 08:31
TS6060#1 | GG\32\020\D | GG | 32 | 20 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2029-08-16 02:55 | 2029-08-16 20:51 | 24279.6144 | [6 empty] | 24280 | 18153 | 2.4 | 0 | 0 | 6.75 | 5793
PH4100A | W2\12\003\B | W2 | 12 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-08-16 15:39 | 2029-10-07 12:16 | 2185114.862 | 2185115 | [7 empty] | 0 | 0 | 84.43 | 9.11 | 5389.11
TS6060#1 | W2\11\004\B | W2 | 11 | 4 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-08-16 20:51 | 2029-08-18 00:52 | 37908.5465 | [6 empty] | 37909 | 26830 | 1.35 | 0 | 0 | 9.65 | 5333
TS5500Exc | W2\07\005\D | W2 | 7 | 5 | D | 8 Coal Mining | 51.1 | 0 | 51.1 | 2029-08-17 05:04 | 2029-08-19 10:42 | 67563.5075 | [6 empty] | 67564 | 49225 | 2.46 | 0 | 0 | 5.62 | 5771
TS5500Shv | GG\32\020\D | GG | 32 | 20 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2029-08-17 14:35 | 2029-08-18 08:31 | 21875.6922 | [6 empty] | 21876 | 16356 | 2.16 | 0 | 0 | 6.75 | 5793
TS6060#1 | W2\07\005\D | W2 | 7 | 5 | D | 8 Coal Mining | 48.9 | 0 | 48.9 | 2029-08-18 00:52 | 2029-08-20 00:35 | 64592.3959 | [6 empty] | 64592 | 47060 | 2.35 | 0 | 0 | 5.62 | 5771
DRE2 | GG\37\007\B | GG | 37 | 7 | B | 6 DL | 100 | 0 | 0 | 2029-08-18 08:31 | 2029-08-18 08:31 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\37\008\B | GG | 37 | 8 | B | 6 DL | 100 | 0 | 0 | 2029-08-18 08:31 | 2029-08-18 08:31 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\37\009\B | GG | 37 | 9 | B | 6 DL | 100 | 0 | 0 | 2029-08-18 08:31 | 2029-08-18 08:31 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\37\010\B | GG | 37 | 10 | B | 6 DL | 100 | 0 | 0 | 2029-08-18 08:31 | 2029-08-18 08:31 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\37\011\B | GG | 37 | 11 | B | 6 DL | 100 | 0 | 0 | 2029-08-18 08:31 | 2029-08-18 08:31 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
TS5500Shv | GG\33\020\D | GG | 33 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-08-18 08:31 | 2029-08-19 22:22 | 46158.5221 | [6 empty] | 46159 | 34511 | 4.55 | 0 | 0 | 6.75 | 5794
DRE2 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 10d 00:00 |  | 10d 00:00 | 2029-08-18 08:31 | 2029-08-28 08:31
TS5500Exc | W2\07\006\D | W2 | 7 | 6 | D | 7 PostStrip | 51.3906 | 0 | 51.3906 | 2029-08-19 10:42 | 2029-08-21 20:41 | 51287.8456 |  |  | 51288 | [5 empty] | 0 | 0 | 0 | 5.59 | 5772.77
TS Fleet 5 | W2\10\004\D | W2 | 10 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-08-19 21:17 | 2029-08-26 10:19 | 307766.7652 | 307767 | [7 empty] | 0 | 0 | 20.35 | 5.52 | 5782.28
TS5500Shv | End of Schedule | End of Schedule | [7 empty] | 2029-08-19 22:22 | 2029-08-19 22:22
TS6060#1 | W2\10\003\D | W2 | 10 | 3 | D | 7 PostStrip | 44.0967 | 0 | 44.0967 | 2029-08-20 00:35 | 2029-08-22 01:24 | 50360.6787 |  |  | 50361 | [5 empty] | 0 | 0 | 0 | 5.63 | 5773.48
TS5500Exc | W2\07\006\D | W2 | 7 | 6 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-08-21 20:41 | 2029-08-23 22:16 | 62439.5186 | [6 empty] | 62440 | 45384 | 2.27 | 0 | 0 | 5.59 | 5773
TS6060#1 | W2\07\006\D | W2 | 7 | 6 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-08-22 01:24 | 2029-08-24 02:58 | 67089.2699 | [6 empty] | 67089 | 48764 | 2.44 | 0 | 0 | 5.59 | 5773
TS5500Exc | W2\11\004\B | W2 | 11 | 4 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-08-23 22:16 | 2029-08-25 02:16 | 35281.2215 | [6 empty] | 35281 | 24971 | 1.25 | 0 | 0 | 9.65 | 5333
TS6060#1 | W2\10\003\D | W2 | 10 | 3 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-08-24 02:58 | 2029-08-26 16:12 | 82871.1555 | [6 empty] | 82871 | 60665 | 2.62 | 0 | 0 | 5.63 | 5773
TS5500Exc | W2\07\007\D | W2 | 7 | 7 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-08-25 02:16 | 2029-08-27 06:35 | 46258.4736 |  |  | 46258 | [5 empty] | 0 | 0 | 0 | 5.64 | 5768.94
TS Fleet 5 | W2\11\004\D | W2 | 11 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-08-26 10:19 | 2029-09-02 07:06 | 322978.0112 | 322978 | [7 empty] | 0 | 0 | 21.19 | 5.39 | 5793.56
TS6060#1 | GG\33\013\D | GG | 33 | 13 | D | 8 Coal Mining | 43.7 | 0 | 43.7 | 2029-08-26 16:12 | 2029-08-27 11:20 | 25885.4664 | [6 empty] | 25885 | 19320 | 1.93 | 0 | 0 | 6.76 | 5790
TS5500Exc | W2\07\007\D | W2 | 7 | 7 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-08-27 06:35 | 2029-08-29 08:24 | 62759.5298 | [6 empty] | 62760 | 45547 | 2.28 | 0 | 0 | 5.64 | 5769
TS6060#1 | W2\07\007\D | W2 | 7 | 7 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-08-27 11:20 | 2029-08-29 13:09 | 67433.1118 | [6 empty] | 67433 | 48939 | 2.45 | 0 | 0 | 5.64 | 5769
DRE2 | GG\37\007\D | GG | 37 | 7 | D | 6 DL | 100 | 0 | 0 | 2029-08-28 08:31 | 2029-08-28 08:31 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\37\008\D | GG | 37 | 8 | D | 6 DL | 100 | 0 | 0 | 2029-08-28 08:31 | 2029-08-28 08:31 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\37\009\D | GG | 37 | 9 | D | 6 DL | 100 | 0 | 0 | 2029-08-28 08:31 | 2029-08-28 08:31 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\37\010\D | GG | 37 | 10 | D | 6 DL | 100 | 0 | 0 | 2029-08-28 08:31 | 2029-08-28 08:31 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\37\011\D | GG | 37 | 11 | D | 6 DL | 100 | 0 | 0 | 2029-08-28 08:31 | 2029-08-28 08:31 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 16d 01:43 |  | 16d 01:43 | 2029-08-28 08:31 | 2029-09-13 10:14
TS5500Exc | W2\07\008\D | W2 | 7 | 8 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-08-29 08:24 | 2029-08-31 11:35 | 64477.4804 | [6 empty] | 64477 | 46653 | 2.33 | 0 | 0 | 5.88 | 5749
TS6060#1 | W2\10\004\D | W2 | 10 | 4 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-08-29 13:09 | 2029-08-31 17:27 | 53967.0766 |  |  | 53967 | [5 empty] | 0 | 0 | 0 | 5.52 | 5782.28
TS5500Exc | W2\08\006\D | W2 | 8 | 6 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-08-31 11:35 | 2029-09-02 13:11 | 62471.6793 | [6 empty] | 62472 | 45408 | 2.27 | 0 | 0 | 5.55 | 5776
TS6060#1 | GG\33\012\D | GG | 33 | 12 | D | 8 Coal Mining | 38.8 | 0 | 38.8 | 2029-08-31 17:27 | 2029-09-01 11:07 | 23893.2675 | [6 empty] | 23893 | 17862 | 1.79 | 0 | 0 | 6.69 | 5798
TS6060#1 | W2\11\003\D | W2 | 11 | 3 | D | 7 PostStrip | 48.7821 | 0 | 48.7821 | 2029-09-01 11:07 | 2029-09-04 17:36 | 80987.3675 |  |  | 80987 | [5 empty] | 0 | 0 | 0 | 5.5 | 5784.34
TS Fleet 5 | CP\08\001\B | CP | 8 | 1 | B | 1 Prestrip - Thick | 45.7164 | 45.7164 | 45.7164 | 2029-09-02 07:06 | 2029-09-06 02:08 | 178445.3831 | 178445 | [7 empty] | 0 | 0 | 11 | 9.04 | 5602.34
TS5500Exc | W2\10\003\D | W2 | 10 | 3 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-09-02 13:11 | 2029-09-05 02:25 | 77127.61 | [6 empty] | 77128 | 56461 | 2.44 | 0 | 0 | 5.63 | 5773
TS6060#1 | W2\11\003\D | W2 | 11 | 3 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-09-04 17:36 | 2029-09-07 03:31 | 78386.7611 | [6 empty] | 78387 | 57382 | 2.61 | 0 | 0 | 5.5 | 5784
TS5500Exc | W2\10\004\D | W2 | 10 | 4 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-09-05 02:25 | 2029-09-07 06:43 | 46257.4943 |  |  | 46257 | [5 empty] | 0 | 0 | 0 | 5.52 | 5782.28
TS Fleet 5 | CP\08\002\B | CP | 8 | 2 | B | 1 Prestrip - Thick | 45.3574 | 45.3574 | 45.3574 | 2029-09-06 02:08 | 2029-09-17 12:51 | 538425.0539 | 538425 | [7 empty] | 0 | 0 | 17.99 | 9.48 | 5565.21
TS6060#1 | GG\33\010\D | GG | 33 | 10 | D | 8 Coal Mining | 12.6 | 0 | 12.6 | 2029-09-07 03:31 | 2029-09-07 09:16 | 7771.0209 | [6 empty] | 7771 | 5819 | 0.58 | 0 | 0 | 6.58 | 5809
TS5500Exc | W2\10\004\D | W2 | 10 | 4 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-09-07 06:43 | 2029-09-09 10:53 | 65697.6849 | [6 empty] | 65698 | 48017 | 2.4 | 0 | 0 | 5.52 | 5782
PH4100XPC#1 | GG\37\007\X1 | GG | 37 | 7 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\37\007\B | GG | 37 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\37\008\X2 | GG | 37 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\37\008\B | GG | 37 | 8 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\37\009\X2 | GG | 37 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\37\009\B | GG | 37 | 9 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\37\010\X2 | GG | 37 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\37\010\B | GG | 37 | 10 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\37\011\X1 | GG | 37 | 11 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\37\011\X2 | GG | 37 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\37\011\B | GG | 37 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\007\X2 | GG | 42 | 7 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\007\B | GG | 42 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\008\X2 | GG | 42 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\008\B | GG | 42 | 8 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\009\X2 | GG | 42 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\009\A | GG | 42 | 9 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\009\B | GG | 42 | 9 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\010\X2 | GG | 42 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\010\A | GG | 42 | 10 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\010\B | GG | 42 | 10 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\011\X1 | GG | 42 | 11 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\011\B | GG | 42 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\012\X1 | GG | 42 | 12 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\012\B | GG | 42 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\013\X1 | GG | 42 | 13 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\013\B | GG | 42 | 13 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\014\X1 | GG | 42 | 14 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\014\B | GG | 42 | 14 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\015\B | GG | 42 | 15 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\016\B | GG | 42 | 16 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\017\B | GG | 42 | 17 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\018\B | GG | 42 | 18 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\42\019\B | GG | 42 | 19 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\47\012\B | GG | 47 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\47\013\B | GG | 47 | 13 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\47\014\B | GG | 47 | 14 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\47\015\B | GG | 47 | 15 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-07 07:02 | 2029-09-07 07:02 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\09\008\B | W2 | 9 | 8 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-09-07 07:02 | 2029-09-27 14:14 | 1126161.046 | 1126161 | [7 empty] | 0 | 0 | 49.71 | 10.6 | 5226.57
TS6060#1 | W2\08\008\B | W2 | 8 | 8 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-09-07 09:16 | 2029-09-08 18:16 | 44681.9904 | [6 empty] | 44682 | 31171 | 1.14 | 0 | 0 | 10.6 | 5228
TS6060#1 | W2\10\004\D | W2 | 10 | 4 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-09-08 18:16 | 2029-09-10 22:26 | 70590.0657 | [6 empty] | 70590 | 51593 | 2.58 | 0 | 0 | 5.52 | 5782
TS5500Exc | W2\08\008\B | W2 | 8 | 8 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-09-09 10:53 | 2029-09-10 19:54 | 41585.2187 | [6 empty] | 41585 | 29011 | 1.06 | 0 | 0 | 10.6 | 5228
TS5500Exc | W2\11\003\D | W2 | 11 | 3 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-09-10 19:54 | 2029-09-13 05:49 | 72954.0153 | [6 empty] | 72954 | 53405 | 2.43 | 0 | 0 | 5.5 | 5784
TS6060#1 | W2\10\005\D | W2 | 10 | 5 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-09-10 22:26 | 2029-09-13 02:46 | 54003.9538 |  |  | 54004 | [5 empty] | 0 | 0 | 0 | 5.48 | 5784.61
TS6060#1 | GG\33\009\D | GG | 33 | 9 | D | 8 Coal Mining | 16.4 | 0 | 16.4 | 2029-09-13 02:46 | 2029-09-13 10:14 | 10098.5148 | [6 empty] | 10099 | 7568 | 0.76 | 0 | 0 | 6.54 | 5812
TS5500Exc | W2\10\005\D | W2 | 10 | 5 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-09-13 05:49 | 2029-09-15 10:09 | 46289.1033 |  |  | 46289 | [5 empty] | 0 | 0 | 0 | 5.48 | 5784.61
DRE2 | GG\38\007\B | GG | 38 | 7 | B | 6 DL | 100 | 0 | 0 | 2029-09-13 10:14 | 2029-09-13 10:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\38\008\B | GG | 38 | 8 | B | 6 DL | 100 | 0 | 0 | 2029-09-13 10:14 | 2029-09-13 10:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\38\009\B | GG | 38 | 9 | B | 6 DL | 100 | 0 | 0 | 2029-09-13 10:14 | 2029-09-13 10:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\38\010\B | GG | 38 | 10 | B | 6 DL | 100 | 0 | 0 | 2029-09-13 10:14 | 2029-09-13 10:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\38\011\B | GG | 38 | 11 | B | 6 DL | 100 | 0 | 0 | 2029-09-13 10:14 | 2029-09-13 10:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\38\007\D | GG | 38 | 7 | D | 6 DL | 100 | 0 | 0 | 2029-09-13 10:14 | 2029-09-13 10:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\38\008\D | GG | 38 | 8 | D | 6 DL | 100 | 0 | 0 | 2029-09-13 10:14 | 2029-09-13 10:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\38\009\D | GG | 38 | 9 | D | 6 DL | 100 | 0 | 0 | 2029-09-13 10:14 | 2029-09-13 10:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\38\010\D | GG | 38 | 10 | D | 6 DL | 100 | 0 | 0 | 2029-09-13 10:14 | 2029-09-13 10:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
DRE2 | GG\38\011\D | GG | 38 | 11 | D | 6 DL | 100 | 0 | 0 | 2029-09-13 10:14 | 2029-09-13 10:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
TS6060#1 | W2\11\004\D | W2 | 11 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2029-09-13 10:14 | 2029-09-17 10:53 | 99725.5025 |  |  | 99726 | [5 empty] | 0 | 0 | 0 | 5.39 | 5793.56
DRE2 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 30d 00:00 |  | 30d 00:00 | 2029-09-13 10:14 | 2029-10-13 10:14
TS5500Exc | W2\10\005\D | W2 | 10 | 5 | D | 8 Coal Mining | 51.9 | 0 | 51.9 | 2029-09-15 10:09 | 2029-09-17 16:54 | 68963.2561 | [6 empty] | 68963 | 50324 | 2.52 | 0 | 0 | 5.48 | 5785
TS6060#1 | W2\10\005\D | W2 | 10 | 5 | D | 8 Coal Mining | 48.1 | 0 | 48.1 | 2029-09-17 10:53 | 2029-09-19 10:10 | 64000.3029 | [6 empty] | 64000 | 46702 | 2.34 | 0 | 0 | 5.48 | 5785
TS Fleet 5 | W2\08\008\D | W2 | 8 | 8 | D | 1 Prestrip - Thick | 53.9906 | 53.9906 | 53.9906 | 2029-09-17 12:51 | 2029-09-22 13:53 | 237222.4331 | 237222 | [7 empty] | 0 | 0 | 11.85 | 5.93 | 5743.63
TS5500Exc | SC\50\023\D | SC | 50 | 23 | D | 1 Prestrip - Thick | 16.6871 | 16.6871 | 16.6871 | 2029-09-17 16:54 | 2029-09-24 20:24 | 152028.6454 | 152029 | [7 empty] | 0 | 0 | 7.26 | 7.21 | 5779.9
TS6060#1 | W2\11\004\D | W2 | 11 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2029-09-19 10:10 | 2029-09-23 14:10 | 135331.2467 | [6 empty] | 135331 | 99063 | 4.95 | 0 | 0 | 5.39 | 5794
TS Fleet 5 | CP\08\003\B | CP | 8 | 3 | B | 1 Prestrip - Thick | 44.9133 | 44.9133 | 44.9133 | 2029-09-22 13:53 | 2029-10-08 18:52 | 762426.5402 | 762427 | [7 empty] | 0 | 0 | 25.88 | 8.95 | 5591.45
TS6060#1 | CP\03\005\D | CP | 3 | 5 | D | 1 Prestrip - Thick | 18.8475 | 18.8475 | 18.8475 | 2029-09-23 14:10 | 2029-10-28 01:28 | 853609.6236 | 853610 | [7 empty] | 0 | 0 | 9.92 | 6.06 | 5873.34
TS5500Exc | SC\50\024\D | SC | 50 | 24 | D | 1 Prestrip - Thick | 12.7194 | 12.7194 | 12.7194 | 2029-09-24 20:24 | 2029-09-30 04:45 | 113815.2332 | 113815 | [7 empty] | 0 | 0 | 5.44 | 7.12 | 5787.44
PH4100XPC#1 | GG\38\007\X1 | GG | 38 | 7 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\007\B | GG | 38 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\008\X2 | GG | 38 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\008\B | GG | 38 | 8 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\009\X2 | GG | 38 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\009\B | GG | 38 | 9 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\010\X2 | GG | 38 | 10 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\010\B | GG | 38 | 10 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\011\X1 | GG | 38 | 11 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\011\X2 | GG | 38 | 11 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\011\B | GG | 38 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\012\X1 | GG | 38 | 12 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\012\X2 | GG | 38 | 12 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\012\B | GG | 38 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\013\X1 | GG | 38 | 13 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\013\X2 | GG | 38 | 13 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\013\B | GG | 38 | 13 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\014\X1 | GG | 38 | 14 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\014\X2 | GG | 38 | 14 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\014\B | GG | 38 | 14 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\015\X1 | GG | 38 | 15 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\015\B | GG | 38 | 15 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\016\X1 | GG | 38 | 16 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\016\B | GG | 38 | 16 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\017\B | GG | 38 | 17 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\018\B | GG | 38 | 18 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\019\B | GG | 38 | 19 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\38\020\B | GG | 38 | 20 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\008\X2 | GG | 43 | 8 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\008\B | GG | 43 | 8 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\009\X2 | GG | 43 | 9 | X2 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\009\A | GG | 43 | 9 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\009\B | GG | 43 | 9 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\010\A | GG | 43 | 10 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\010\B | GG | 43 | 10 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\011\X1 | GG | 43 | 11 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\011\B | GG | 43 | 11 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\012\X1 | GG | 43 | 12 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\012\B | GG | 43 | 12 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\013\X1 | GG | 43 | 13 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\013\B | GG | 43 | 13 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\014\X1 | GG | 43 | 14 | X1 | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\014\B | GG | 43 | 14 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\015\B | GG | 43 | 15 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\016\B | GG | 43 | 16 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\017\B | GG | 43 | 17 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\43\018\B | GG | 43 | 18 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\48\013\B | GG | 48 | 13 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | GG\48\014\B | GG | 48 | 14 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2029-09-27 14:14 | 2029-09-27 14:14 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100XPC#1 | W2\08\008\D | W2 | 8 | 8 | D | 1 Prestrip - Thick | 100 | 46.0094 | 46.0094 | 2029-09-27 14:14 | 2029-10-01 07:33 | 202154.4879 | 202154 | [7 empty] | 0 | 0 | 10.1 | 5.93 | 5743.63
TS5500Exc | W2\09\008\B | W2 | 9 | 8 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-09-30 04:45 | 2029-10-01 06:54 | 32945.3345 | [6 empty] | 32945 | 22986 | 1.06 | 0 | 0 | 10.6 | 5227
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 00:39 |  | 0d 00:39 | 2029-10-01 06:54 | 2029-10-01 07:33
PH4100XPC#1 | W2\08\007\B | W2 | 8 | 7 | B | 1 Prestrip - Thick | 100 | 30.8355 | 30.8355 | 2029-10-01 07:33 | 2029-10-06 19:24 | 298460.2645 | 298460 | [7 empty] | 0 | 0 | 14.4 | 10.1 | 5265.2
TS5500Exc | W2\08\008\D | W2 | 8 | 8 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-10-01 07:33 | 2029-10-04 03:13 | 59849.1589 |  |  | 59849 | [5 empty] | 0 | 0 | 0 | 5.93 | 5743.63
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 16:11 |  | 2d 16:11 | 2029-10-04 03:13 | 2029-10-06 19:24
PH4100XPC#1 | W2\09\007\B | W2 | 9 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-10-06 19:24 | 2029-10-24 03:29 | 937641.6351 | 937642 | [7 empty] | 0 | 0 | 47.14 | 10.03 | 5271.48
TS5500Exc | W2\08\007\B | W2 | 8 | 7 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-10-06 19:24 | 2029-10-08 07:01 | 44864.9173 | [6 empty] | 44865 | 31414 | 1.56 | 0 | 0 | 10.1 | 5265
PH4100A | W2\13\003\B | W2 | 13 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-10-07 12:16 | 2029-11-25 08:07 | 2048017.511 | 2048018 | [7 empty] | 0 | 0 | 80.84 | 8.92 | 5412.09
TS5500Exc | W2\12\003\B | W2 | 12 | 3 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-10-08 07:01 | 2029-10-09 20:10 | 46792.4999 | [6 empty] | 46792 | 33365 | 1.35 | 0 | 0 | 9.11 | 5389
TS Fleet 5 | CP\08\004\B | CP | 8 | 4 | B | 1 Prestrip - Thick | 32.5342 | 32.5342 | 32.5342 | 2029-10-08 18:52 | 2029-10-20 14:33 | 556022.7612 | 556023 | [7 empty] | 0 | 0 | 18.65 | 8.2 | 5642.08
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 14d 07:19 |  | 14d 07:19 | 2029-10-09 20:10 | 2029-10-24 03:29
DRE2 | End of Schedule | End of Schedule | [7 empty] | 2029-10-13 10:14 | 2029-10-13 10:14
TS Fleet 5 | CP\08\005\B | CP | 8 | 5 | B | 1 Prestrip - Thick | 31.1844 | 31.1844 | 31.1844 | 2029-10-20 14:33 | 2029-11-03 01:01 | 632012.3001 | 632012 | [7 empty] | 0 | 0 | 21.15 | 8.5 | 5614.12
PH4100XPC#1 | W2\09\006\B | W2 | 9 | 6 | B | 1 Prestrip - Thick | 100 | 88.0573 | 88.0573 | 2029-10-24 03:29 | 2029-11-08 23:20 | 878495.717 | 878496 | [7 empty] | 0 | 0 | 40.87 | 9.98 | 5278.79
TS5500Exc | W2\09\007\B | W2 | 9 | 7 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-10-24 03:29 | 2029-10-25 17:03 | 47328.2705 | [6 empty] | 47328 | 33166 | 1.65 | 0 | 0 | 10.03 | 5271
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 9d 07:26 |  | 9d 07:26 | 2029-10-25 17:03 | 2029-11-04 00:29
TS6060#1 | W2\09\008\B | W2 | 9 | 8 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-10-28 01:28 | 2029-10-29 03:37 | 35398.7105 | [6 empty] | 35399 | 24698 | 1.14 | 0 | 0 | 10.6 | 5227
TS6060#1 | W2\08\007\B | W2 | 8 | 7 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-10-29 03:37 | 2029-10-30 15:15 | 48205.9218 | [6 empty] | 48206 | 33753 | 1.68 | 0 | 0 | 10.1 | 5265
TS6060#1 | W2\09\007\B | W2 | 9 | 7 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-10-30 15:15 | 2029-11-01 04:49 | 50852.7162 | [6 empty] | 50853 | 35636 | 1.77 | 0 | 0 | 10.03 | 5271
TS6060#1 | W2\08\008\D | W2 | 8 | 8 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-11-01 04:49 | 2029-11-04 00:29 | 69824.0187 |  |  | 69824 | [5 empty] | 0 | 0 | 0 | 5.93 | 5743.63
TS Fleet 5 | W2\09\008\D | W2 | 9 | 8 | D | 1 Prestrip - Thick | 45.419 | 45.419 | 45.419 | 2029-11-03 01:01 | 2029-11-06 10:10 | 159068.9572 | 159069 | [7 empty] | 0 | 0 | 9.97 | 5.92 | 5744.29
TS6060#1 | W2\08\008\D | W2 | 8 | 8 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-11-04 00:29 | 2029-11-06 17:23 | 87821.5591 | [6 empty] | 87822 | 63493 | 2.47 | 0 | 0 | 5.93 | 5744
TS5500Exc | W2\08\008\D | W2 | 8 | 8 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-11-04 00:29 | 2029-11-06 17:23 | 81734.9164 | [6 empty] | 81735 | 59093 | 2.3 | 0 | 0 | 5.93 | 5744
TS Fleet 5 | W2\08\007\D | W2 | 8 | 7 | D | 1 Prestrip - Thick | 45.419 | 45.419 | 45.419 | 2029-11-06 10:10 | 2029-11-09 14:33 | 149702.4866 | 149702 | [7 empty] | 0 | 0 | 9.74 | 5.59 | 5772.7
TS6060#1 | W2\12\003\B | W2 | 12 | 3 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-11-06 17:23 | 2029-11-08 06:32 | 50277.0477 | [6 empty] | 50277 | 35850 | 1.45 | 0 | 0 | 9.11 | 5389
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 05:58 |  | 2d 05:58 | 2029-11-06 17:23 | 2029-11-08 23:20
TS6060#1 | W2\12\003\D | W2 | 12 | 3 | D | 1 Prestrip - Thick | 47.1597 | 47.1597 | 47.1597 | 2029-11-08 06:32 | 2029-11-15 15:07 | 182207.6427 | 182208 | [7 empty] | 0 | 0 | 10.69 | 5.36 | 5796.46
PH4100XPC#1 | W2\09\008\D | W2 | 9 | 8 | D | 1 Prestrip - Thick | 100 | 54.581 | 54.581 | 2029-11-08 23:20 | 2029-11-12 11:47 | 191156.8794 | 191157 | [7 empty] | 0 | 0 | 11.98 | 5.92 | 5744.29
TS5500Exc | W2\09\006\B | W2 | 9 | 6 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-11-08 23:20 | 2029-11-10 11:57 | 46122.5571 | [6 empty] | 46123 | 32372 | 1.61 | 0 | 0 | 9.98 | 5279
TS Fleet 5 | W2\09\007\D | W2 | 9 | 7 | D | 1 Prestrip - Thick | 45.419 | 45.419 | 45.419 | 2029-11-09 14:33 | 2029-11-12 21:31 | 154784.1826 | 154784 | [7 empty] | 0 | 0 | 10 | 5.56 | 5774.54
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 23:50 |  | 1d 23:50 | 2029-11-10 11:57 | 2029-11-12 11:47
PH4100XPC#1 | W2\08\007\D | W2 | 8 | 7 | D | 1 Prestrip - Thick | 100 | 54.581 | 54.581 | 2029-11-12 11:47 | 2029-11-15 19:16 | 179900.973 | 179901 | [7 empty] | 0 | 0 | 11.7 | 5.59 | 5772.7
TS5500Exc | W2\09\008\D | W2 | 9 | 8 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-11-12 11:47 | 2029-11-14 17:41 | 47667.3801 |  |  | 47667 | [5 empty] | 0 | 0 | 0 | 5.92 | 5744.29
TS Fleet 5 | W2\12\003\D | W2 | 12 | 3 | D | 1 Prestrip - Thick | 25.6025 | 25.6025 | 25.6025 | 2029-11-12 21:31 | 2029-11-14 23:59 | 98918.8074 | 98919 | [7 empty] | 0 | 0 | 5.8 | 5.36 | 5796.46
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 01:35 |  | 1d 01:35 | 2029-11-14 17:41 | 2029-11-15 19:16
TS Fleet 5 | CP\09\001\B | CP | 9 | 1 | B | 1 Prestrip - Thick | 31.5988 | 31.5988 | 31.5988 | 2029-11-14 23:59 | 2029-11-18 05:41 | 152292.2443 | 152292 | [7 empty] | 0 | 0 | 8.51 | 9.01 | 5603.17
TS6060#1 | W2\09\006\B | W2 | 9 | 6 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-11-15 15:07 | 2029-11-17 03:44 | 49557.2156 | [6 empty] | 49557 | 34782 | 1.73 | 0 | 0 | 9.98 | 5279
PH4100XPC#1 | W2\09\007\D | W2 | 9 | 7 | D | 1 Prestrip - Thick | 100 | 54.581 | 54.581 | 2029-11-15 19:16 | 2029-11-19 05:27 | 186007.7657 | 186008 | [7 empty] | 0 | 0 | 12.02 | 5.56 | 5774.54
TS5500Exc | W2\08\007\D | W2 | 8 | 7 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-11-15 19:16 | 2029-11-17 23:35 | 46263.8869 |  |  | 46264 | [5 empty] | 0 | 0 | 0 | 5.59 | 5772.7
TS6060#1 | W2\08\007\D | W2 | 8 | 7 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-11-17 03:44 | 2029-11-19 08:03 | 53974.5347 |  |  | 53975 | [5 empty] | 0 | 0 | 0 | 5.59 | 5772.7
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 05:52 |  | 1d 05:52 | 2029-11-17 23:35 | 2029-11-19 05:27
TS Fleet 5 | CP\09\002\B | CP | 9 | 2 | B | 1 Prestrip - Thick | 31.3222 | 31.3222 | 31.3222 | 2029-11-18 05:41 | 2029-11-26 16:04 | 396668.4556 | 396668 | [7 empty] | 0 | 0 | 13.15 | 9.34 | 5575.02
PH4100XPC#1 | W2\09\006\D | W2 | 9 | 6 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-11-19 05:27 | 2029-11-25 04:38 | 324104.7858 | 324105 | [7 empty] | 0 | 0 | 21.17 | 5.52 | 5778.82
TS5500Exc | W2\09\007\D | W2 | 9 | 7 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2029-11-19 05:27 | 2029-11-21 09:42 | 46217.5269 |  |  | 46218 | [5 empty] | 0 | 0 | 0 | 5.56 | 5774.54
TS6060#1 | W2\08\007\D | W2 | 8 | 7 | D | 8 Coal Mining | 50.5 | 0 | 50.5 | 2029-11-19 08:03 | 2029-11-21 08:08 | 65076.7848 | [6 empty] | 65077 | 47228 | 2.36 | 0 | 0 | 5.59 | 5773
TS6060#1 | W2\09\007\D | W2 | 9 | 7 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-11-21 08:08 | 2029-11-23 12:23 | 53920.448 |  |  | 53920 | [5 empty] | 0 | 0 | 0 | 5.56 | 5774.54
TS5500Exc | W2\08\007\D | W2 | 8 | 7 | D | 8 Coal Mining | 49.5 | 0 | 49.5 | 2029-11-21 09:42 | 2029-11-23 12:18 | 63724.2319 | [6 empty] | 63724 | 46246 | 2.31 | 0 | 0 | 5.59 | 5773
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 00:06 |  | 0d 00:06 | 2029-11-23 12:18 | 2029-11-23 12:23
TS6060#1 | W2\09\007\D | W2 | 9 | 7 | D | 8 Coal Mining | 44.7 | 0 | 44.7 | 2029-11-23 12:23 | 2029-11-25 06:40 | 57210.0394 | [6 empty] | 57210 | 41518 | 2.08 | 0 | 0 | 5.56 | 5775
TS5500Exc | W2\09\007\D | W2 | 9 | 7 | D | 8 Coal Mining | 55.3 | 0 | 55.3 | 2029-11-23 12:23 | 2029-11-25 20:41 | 70915.4582 | [6 empty] | 70915 | 51464 | 2.57 | 0 | 0 | 5.56 | 5775
PH4100XPC#1 | W2\10\007\B | W2 | 10 | 7 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-11-25 04:38 | 2029-12-09 11:17 | 764625.4806 | 764625 | [7 empty] | 0 | 0 | 46.17 | 10.4 | 5240.27
TS6060#1 | W2\09\006\D | W2 | 9 | 6 | D | 7 PostStrip | 50.0969 | 0 | 50.0969 | 2029-11-25 06:40 | 2029-11-27 07:19 | 50201.8713 |  |  | 50202 | [5 empty] | 0 | 0 | 0 | 5.52 | 5778.82
PH4100A | W2\12\004\B | W2 | 12 | 4 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-11-25 08:07 | 2029-12-22 22:42 | 1184109.468 | 1184109 | [7 empty] | 0 | 0 | 52.87 | 9.89 | 5325.69
TS5500Exc | W2\09\006\D | W2 | 9 | 6 | D | 7 PostStrip | 49.9031 | 0 | 49.9031 | 2029-11-25 20:41 | 2029-11-28 05:14 | 50007.6452 |  |  | 50008 | [5 empty] | 0 | 0 | 0 | 5.52 | 5778.82
TS Fleet 5 | CP\09\003\B | CP | 9 | 3 | B | 1 Prestrip - Thick | 27.0698 | 27.0698 | 27.0698 | 2029-11-26 16:04 | 2029-12-06 15:27 | 469198.8636 | 469199 | [7 empty] | 0 | 0 | 14.86 | 8.9 | 5596.18
TS6060#1 | W2\09\008\D | W2 | 9 | 8 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2029-11-27 07:19 | 2029-11-29 13:13 | 55611.9435 |  |  | 55612 | [5 empty] | 0 | 0 | 0 | 5.92 | 5744.29
TS5500Exc | W2\09\006\D | W2 | 9 | 6 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-11-28 05:14 | 2029-11-30 06:58 | 62635.9297 | [6 empty] | 62636 | 45527 | 2.28 | 0 | 0 | 5.52 | 5779
TS6060#1 | W2\09\006\D | W2 | 9 | 6 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-11-29 13:13 | 2029-12-01 14:56 | 67300.3075 | [6 empty] | 67300 | 48918 | 2.45 | 0 | 0 | 5.52 | 5779
TS5500Exc | W2\09\008\D | W2 | 9 | 8 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-11-30 06:58 | 2029-12-02 10:06 | 64423.1437 | [6 empty] | 64423 | 46612 | 2.28 | 0 | 0 | 5.92 | 5744
TS6060#1 | W2\09\008\D | W2 | 9 | 8 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-12-01 14:56 | 2029-12-03 18:05 | 69220.6119 | [6 empty] | 69221 | 50083 | 2.45 | 0 | 0 | 5.92 | 5744
TS5500Exc | W2\13\003\B | W2 | 13 | 3 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-12-02 10:06 | 2029-12-04 00:51 | 48811.5079 | [6 empty] | 48812 | 34892 | 1.45 | 0 | 0 | 8.92 | 5412
TS6060#1 | W2\13\003\B | W2 | 13 | 3 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-12-03 18:05 | 2029-12-05 08:50 | 52446.4074 | [6 empty] | 52446 | 37490 | 1.55 | 0 | 0 | 8.92 | 5412
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 10:26 |  | 5d 10:26 | 2029-12-04 00:51 | 2029-12-09 11:17
TS6060#1 | CP\12\004\B | CP | 12 | 4 | B | 1 Prestrip - Thick | 15.0923 | 15.0923 | 15.0923 | 2029-12-05 08:50 | 2029-12-17 09:44 | 297781.6406 | 297782 | [7 empty] | 0 | 0 | 9.97 | 9.52 | 5504.47
TS Fleet 5 | CP\09\004\B | CP | 9 | 4 | B | 1 Prestrip - Thick | 31.3768 | 31.3768 | 31.3768 | 2029-12-06 15:27 | 2029-12-18 09:58 | 553711.1264 | 553711 | [7 empty] | 0 | 0 | 18.57 | 8.17 | 5645.01
PH4100XPC#1 | W2\10\006\B | W2 | 10 | 6 | B | 1 Prestrip - Thick | 100 | 96.8503 | 96.8503 | 2029-12-09 11:17 | 2029-12-26 20:44 | 938858.9747 | 938859 | [7 empty] | 0 | 0 | 46.85 | 9.94 | 5283.14
TS5500Exc | W2\10\007\B | W2 | 10 | 7 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-12-09 11:17 | 2029-12-10 08:31 | 26744.5946 | [6 empty] | 26745 | 18709 | 1.15 | 0 | 0 | 10.4 | 5240
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 14d 10:46 |  | 14d 10:46 | 2029-12-10 08:31 | 2029-12-24 19:18
TS6060#1 | W2\10\007\B | W2 | 10 | 7 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-12-17 09:44 | 2029-12-18 06:58 | 28736.2134 | [6 empty] | 28736 | 20102 | 1.24 | 0 | 0 | 10.4 | 5240
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 15:45 |  | 4d 15:45 | 2029-12-18 06:58 | 2029-12-22 22:42
TS Fleet 5 | W2\10\007\D | W2 | 10 | 7 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-12-18 09:58 | 2029-12-24 19:18 | 300529.6043 | 300530 | [7 empty] | 0 | 0 | 24.24 | 5.6 | 5771.69
PH4100A | W2\13\004\B | W2 | 13 | 4 | B | 1 Prestrip - Thick | 100 | 34.3467 | 34.3467 | 2029-12-22 22:42 | 2030-01-01 | 373916.4978 | 373916 | [7 empty] | 0 | 0 | 18.83 | 9.11 | 5401.63
TS6060#1 | W2\12\004\B | W2 | 12 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2029-12-22 22:42 | 2029-12-24 15:00 | 54532.2496 | [6 empty] | 54532 | 38651 | 1.9 | 0 | 0 | 9.89 | 5326
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 04:18 |  | 0d 04:18 | 2029-12-24 15:00 | 2029-12-24 19:18
TS Fleet 5 | W2\12\004\D | W2 | 12 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2029-12-24 19:18 | 2029-12-31 03:49 | 298942.185 | 298942 | [7 empty] | 0 | 0 | 19.83 | 5.22 | 5807.51
TS6060#1 | W2\10\007\D | W2 | 10 | 7 | D | 7 PostStrip | 50.3451 | 0 | 50.3451 | 2029-12-24 19:18 | 2029-12-26 09:24 | 39319.7347 |  |  | 39320 | [5 empty] | 0 | 0 | 0 | 5.6 | 5771.69
TS5500Exc | W2\10\007\D | W2 | 10 | 7 | D | 7 PostStrip | 49.6549 | 0 | 49.6549 | 2029-12-24 19:18 | 2029-12-26 15:09 | 38780.7227 |  |  | 38781 | [5 empty] | 0 | 0 | 0 | 5.6 | 5771.69
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 05:45 |  | 0d 05:45 | 2029-12-26 09:24 | 2029-12-26 15:09
TS6060#1 | W2\10\007\D | W2 | 10 | 7 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2029-12-26 15:09 | 2029-12-28 05:08 | 51425.6159 | [6 empty] | 51426 | 37349 | 2.41 | 0 | 0 | 5.6 | 5772
TS5500Exc | W2\10\007\D | W2 | 10 | 7 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2029-12-26 15:09 | 2029-12-28 05:08 | 47861.4642 | [6 empty] | 47861 | 34761 | 2.24 | 0 | 0 | 5.6 | 5772
PH4100XPC#1 | W2\11\006\B | W2 | 11 | 6 | B | 1 Prestrip - Thick | 100 | 39.9722 | 39.9722 | 2029-12-26 20:44 | 2030-01-01 | 276647.3484 | 276647 | [7 empty] | 0 | 0 | 19.57 | 10.21 | 5265.94
TS6060#1 | W2\10\006\B | W2 | 10 | 6 | B | 8 Coal Mining | 38.8 | 0 | 38.8 | 2029-12-28 05:08 | 2029-12-29 08:43 | 37318.1946 | [6 empty] | 37318 | 26204 | 1.3 | 0 | 0 | 9.94 | 5283
TS5500Exc | W2\10\006\B | W2 | 10 | 6 | B | 8 Coal Mining | 61.2 | 0 | 61.2 | 2029-12-28 05:08 | 2029-12-30 03:50 | 58823.2093 | [6 empty] | 58823 | 41304 | 2.05 | 0 | 0 | 9.94 | 5283
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 19:06 |  | 1d 19:06 | 2029-12-29 08:43 | 2029-12-31 03:49
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 20:09 |  | 1d 20:09 | 2029-12-30 03:50 | 2030-01-01
TS Fleet 5 | W2\10\006\D | W2 | 10 | 6 | D | 1 Prestrip - Thick | 100 | 11.1728 | 11.1728 | 2029-12-31 03:49 | 2030-01-01 | 39548.7336 | 39549 | [7 empty] | 0 | 0 | 2.53 | 5.52 | 5778.79
TS6060#1 | W2\12\004\D | W2 | 12 | 4 | D | 7 PostStrip | 100 | 0 | 20.6615 | 2029-12-31 03:49 | 2030-01-01 | 20819.5833 |  |  | 20820 | [5 empty] | 0 | 0 | 0 | 5.22 | 5807.51
| EOP 82 : 2029 | EOP 82 : 2029 | [7 empty] | 2030-01-01 | 2030-01-01 |  | 58859912 |  | 4058327 | 313266 | 16372174 | 8196168 | 10191271 | 7378894 | 429.78 | 0 | 2617.19 | 7.21 | 5655.88
PH4100A | W2\13\004\B | W2 | 13 | 4 | B | 1 Prestrip - Thick | 100 | 65.6533 | 65.6533 | 2030-01-01 | 2030-01-19 01:56 | 714737.7174 | 714738 | [7 empty] | 0 | 0 | 35.99 | 9.11 | 5401.63
TS Fleet 5 | W2\10\006\D | W2 | 10 | 6 | D | 1 Prestrip - Thick | 100 | 88.8272 | 88.8272 | 2030-01-01 | 2030-01-07 23:36 | 314423.0841 | 314423 | [7 empty] | 0 | 0 | 20.11 | 5.52 | 5778.79
PH4100XPC#1 | W2\11\006\B | W2 | 11 | 6 | B | 1 Prestrip - Thick | 100 | 60.0278 | 60.0278 | 2030-01-01 | 2030-01-08 17:06 | 415452.6103 | 415453 | [7 empty] | 0 | 0 | 29.39 | 10.21 | 5265.94
TS6060#1 | W2\12\004\D | W2 | 12 | 4 | D | 7 PostStrip | 100 | 0 | 79.3385 | 2030-01-01 | 2030-01-04 05:28 | 79945.4241 |  |  | 79945 | [5 empty] | 0 | 0 | 0 | 5.22 | 5807.51
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 6d 23:36 |  | 6d 23:36 | 2030-01-01 | 2030-01-07 23:36
TS6060#1 | W2\12\004\D | W2 | 12 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-01-04 05:28 | 2030-01-08 08:38 | 134195.349 | [6 empty] | 134195 | 98307 | 4.92 | 0 | 0 | 5.22 | 5808
TS Fleet 5 | CP\09\005\B | CP | 9 | 5 | B | 1 Prestrip - Thick | 31.1606 | 31.1606 | 31.1606 | 2030-01-07 23:36 | 2030-01-22 04:34 | 639668.5968 | 639669 | [7 empty] | 0 | 0 | 21.55 | 8.49 | 5615.29
TS5500Exc | W2\10\006\D | W2 | 10 | 6 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2030-01-07 23:36 | 2030-01-10 03:56 | 46294.1896 |  |  | 46294 | [5 empty] | 0 | 0 | 0 | 5.52 | 5778.79
TS6060#1 | W2\10\006\D | W2 | 10 | 6 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2030-01-08 08:38 | 2030-01-10 12:58 | 54009.8879 |  |  | 54010 | [5 empty] | 0 | 0 | 0 | 5.52 | 5778.79
PH4100XPC#1 | W2\11\005\B | W2 | 11 | 5 | B | 1 Prestrip - Thick | 100 | 92.744 | 92.744 | 2030-01-08 17:06 | 2030-01-26 07:59 | 956737.1355 | 956737 | [7 empty] | 0 | 0 | 47.95 | 9.65 | 5321.18
TS5500Exc | W2\11\006\B | W2 | 11 | 6 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2030-01-10 03:56 | 2030-01-10 21:49 | 22514.1922 | [6 empty] | 22514 | 15813 | 1.13 | 0 | 0 | 10.21 | 5266
TS6060#1 | W2\11\006\B | W2 | 11 | 6 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2030-01-10 12:58 | 2030-01-11 06:51 | 24190.781 | [6 empty] | 24191 | 16990 | 1.21 | 0 | 0 | 10.21 | 5266
TS5500Exc | W2\10\006\D | W2 | 10 | 6 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2030-01-10 21:49 | 2030-01-12 23:23 | 62434.8656 | [6 empty] | 62435 | 45416 | 2.27 | 0 | 0 | 5.52 | 5779
TS6060#1 | W2\10\006\D | W2 | 10 | 6 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2030-01-11 06:51 | 2030-01-13 08:25 | 67084.2705 | [6 empty] | 67084 | 48798 | 2.44 | 0 | 0 | 5.52 | 5779
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 13d 08:58 |  | 13d 08:58 | 2030-01-12 23:23 | 2030-01-26 08:21
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 17:31 |  | 5d 17:31 | 2030-01-13 08:25 | 2030-01-19 01:56
PH4100A | SC\50\017\D | SC | 50 | 17 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2030-01-19 01:56 | 2030-01-19 01:56 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\50\018\D | SC | 50 | 18 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2030-01-19 01:56 | 2030-01-19 01:56 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\50\019\D | SC | 50 | 19 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2030-01-19 01:56 | 2030-01-19 01:56 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\50\021\D | SC | 50 | 21 | D | 1 Prestrip - Thick | 100 | 26.9513 | 26.9513 | 2030-01-19 01:56 | 2030-01-26 08:21 | 286530.1407 | 286530 | [7 empty] | 0 | 0 | 13.42 | 7.31 | 5768.58
TS6060#1 | W2\13\004\B | W2 | 13 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2030-01-19 01:56 | 2030-01-21 08:12 | 73445.2808 | [6 empty] | 73445 | 52482 | 2.61 | 0 | 0 | 9.11 | 5402
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 23:47 |  | 4d 23:47 | 2030-01-21 08:12 | 2030-01-26 07:59
TS Fleet 5 | W2\11\006\D | W2 | 11 | 6 | D | 1 Prestrip - Thick | 45.419 | 45.419 | 45.419 | 2030-01-22 04:34 | 2030-01-24 21:01 | 120895.7403 | 120896 | [7 empty] | 0 | 0 | 11.35 | 5.52 | 5778.69
TS Fleet 5 | CP\10\001\B | CP | 10 | 1 | B | 1 Prestrip - Thick | 31.5963 | 31.5963 | 31.5963 | 2030-01-24 21:01 | 2030-01-28 21:46 | 181496.1698 | 181496 | [7 empty] | 0 | 0 | 9.17 | 8.85 | 5615.47
PH4100XPC#1 | W2\11\006\D | W2 | 11 | 6 | D | 1 Prestrip - Thick | 100 | 54.581 | 54.581 | 2030-01-26 07:59 | 2030-01-29 00:10 | 145283.2335 | 145283 | [7 empty] | 0 | 0 | 13.64 | 5.52 | 5778.69
TS6060#1 | W2\11\005\B | W2 | 11 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2030-01-26 07:59 | 2030-01-29 07:38 | 96974.9018 | [6 empty] | 96975 | 68424 | 3.4 | 0 | 0 | 9.65 | 5321
PH4100A | SC\50\022\D | SC | 50 | 22 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2030-01-26 08:21 | 2030-02-19 23:48 | 967207.5967 | 967208 | [7 empty] | 0 | 0 | 45.86 | 7.33 | 5767.91
TS5500Exc | SC\50\021\D | SC | 50 | 21 | D | 7 PostStrip | 100 | 0 | 100 | 2030-01-26 08:21 | 2030-01-31 23:24 | 119430.2589 |  |  | 119430 | [5 empty] | 0 | 0 | 0 | 7.31 | 5768.58
TS Fleet 5 | CP\10\002\B | CP | 10 | 2 | B | 1 Prestrip - Thick | 31.322 | 31.322 | 31.322 | 2030-01-28 21:46 | 2030-02-07 12:25 | 432712.8799 | 432713 | [7 empty] | 0 | 0 | 14.53 | 9.18 | 5587.13
PH4100XPC#1 | W2\12\003\D | W2 | 12 | 3 | D | 1 Prestrip - Thick | 100 | 27.2378 | 27.2378 | 2030-01-29 00:10 | 2030-01-30 22:39 | 105236.6976 | 105237 | [7 empty] | 0 | 0 | 6.18 | 5.36 | 5796.46
TS6060#1 | W2\11\006\D | W2 | 11 | 6 | D | 7 PostStrip | 100 | 0 | 100 | 2030-01-29 07:38 | 2030-02-01 00:10 | 66580.7941 |  |  | 66581 | [5 empty] | 0 | 0 | 0 | 5.52 | 5778.69
PH4100XPC#1 | W2\11\005\D | W2 | 11 | 5 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2030-01-30 22:39 | 2030-02-06 12:50 | 358049.2997 | 358049 | [7 empty] | 0 | 0 | 22.85 | 5.4 | 5790.72
TS5500Exc | SC\50\021\D | SC | 50 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-01-31 23:24 | 2030-02-05 13:05 | 138166.1939 | [6 empty] | 138166 | 103253 | 4.3 | 0 | 0 | 7.31 | 5769
TS6060#1 | W2\11\006\D | W2 | 11 | 6 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-02-01 00:10 | 2030-02-03 15:07 | 85206.1679 | [6 empty] | 85206 | 62028 | 4.71 | 0 | 0 | 5.52 | 5779
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 21:43 |  | 2d 21:43 | 2030-02-03 15:07 | 2030-02-06 12:50
TS5500Exc | W2\12\003\D | W2 | 12 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2030-02-05 13:05 | 2030-02-10 16:42 | 109316.0407 |  |  | 109316 | [5 empty] | 0 | 0 | 0 | 5.36 | 5796.46
PH4100XPC#1 | W2\13\003\D | W2 | 13 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2030-02-06 12:50 | 2030-02-14 11:38 | 431874.0609 | 431874 | [7 empty] | 0 | 0 | 25.22 | 5.2 | 5810.51
TS6060#1 | W2\11\005\D | W2 | 11 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2030-02-06 12:50 | 2030-02-10 14:03 | 100295.5834 |  |  | 100296 | [5 empty] | 0 | 0 | 0 | 5.4 | 5790.72
TS Fleet 5 | CP\10\003\B | CP | 10 | 3 | B | 1 Prestrip - Thick | 31.0746 | 31.0746 | 31.0746 | 2030-02-07 12:25 | 2030-02-19 18:07 | 550995.1001 | 550995 | [7 empty] | 0 | 0 | 17.67 | 8.78 | 5605.52
TS6060#1 | W2\11\005\D | W2 | 11 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-02-10 14:03 | 2030-02-14 15:48 | 132312.1835 | [6 empty] | 132312 | 96624 | 4.83 | 0 | 0 | 5.4 | 5791
TS5500Exc | W2\12\003\D | W2 | 12 | 3 | D | 8 Coal Mining | 52.6 | 0 | 52.6 | 2030-02-10 16:42 | 2030-02-13 05:02 | 76007.4262 | [6 empty] | 76007 | 55726 | 2.64 | 0 | 0 | 5.36 | 5796
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 13:25 |  | 5d 13:25 | 2030-02-13 05:02 | 2030-02-18 18:27
PH4100XPC#1 | W2\12\005\B | W2 | 12 | 5 | B | 1 Prestrip - Thick | 100 | 21.4212 | 21.4212 | 2030-02-14 11:38 | 2030-02-18 18:27 | 231986.4703 | 231986 | [7 empty] | 0 | 0 | 10.86 | 9.76 | 5323.19
TS6060#1 | W2\13\003\D | W2 | 13 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2030-02-14 15:48 | 2030-02-18 23:18 | 106776.1519 |  |  | 106776 | [5 empty] | 0 | 0 | 0 | 5.2 | 5810.51
PH4100XPC#1 | W2\13\005\B | W2 | 13 | 5 | B | 1 Prestrip - Thick | 100 | 83.4436 | 83.4436 | 2030-02-18 18:27 | 2030-02-27 09:44 | 460987.9517 | 460988 | [7 empty] | 0 | 0 | 43.31 | 9.5 | 5359.32
TS5500Exc | W2\12\005\B | W2 | 12 | 5 | B | 8 Coal Mining | 34.4 | 0 | 34.4 | 2030-02-18 18:27 | 2030-02-19 13:55 | 24506.6136 | [6 empty] | 24507 | 17346 | 0.83 | 0 | 0 | 9.76 | 5323
TS6060#1 | W2\12\005\B | W2 | 12 | 5 | B | 8 Coal Mining | 65.6 | 0 | 65.6 | 2030-02-18 23:18 | 2030-02-20 09:52 | 46791.5209 | [6 empty] | 46792 | 33119 | 1.58 | 0 | 0 | 9.76 | 5323
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 09:53 |  | 0d 09:53 | 2030-02-19 13:55 | 2030-02-19 23:48
TS Fleet 5 | CP\10\004\B | CP | 10 | 4 | B | 1 Prestrip - Thick | 31.3408 | 31.3408 | 31.3408 | 2030-02-19 18:07 | 2030-03-04 13:43 | 577053.4787 | 577053 | [7 empty] | 0 | 0 | 19.35 | 8.18 | 5645.32
PH4100A | SC\50\023\D | SC | 50 | 23 | D | 1 Prestrip - Thick | 100 | 83.3129 | 83.3129 | 2030-02-19 23:48 | 2030-03-11 10:41 | 759026.0998 | 759026 | [7 empty] | 0 | 0 | 36.26 | 7.21 | 5779.9
TS5500Exc | SC\50\022\D | SC | 50 | 22 | D | 7 PostStrip | 100 | 0 | 100 | 2030-02-19 23:48 | 2030-02-25 14:38 | 119243.0092 |  |  | 119243 | [5 empty] | 0 | 0 | 0 | 7.33 | 5767.91
TS6060#1 | W2\13\003\D | W2 | 13 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-02-20 09:52 | 2030-02-24 18:48 | 142006.7562 | [6 empty] | 142007 | 104195 | 5 | 0 | 0 | 5.2 | 5811
TS6060#1 | W2\12\003\D | W2 | 12 | 3 | D | 8 Coal Mining | 47.4 | 0 | 47.4 | 2030-02-24 18:48 | 2030-02-26 21:22 | 68438.5586 | [6 empty] | 68439 | 50177 | 2.38 | 0 | 0 | 5.36 | 5796
TS5500Exc | SC\50\022\D | SC | 50 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-02-25 14:38 | 2030-03-02 08:25 | 143328.1181 | [6 empty] | 143328 | 107115 | 4.46 | 0 | 0 | 7.33 | 5768
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 8d 00:31 |  | 8d 00:31 | 2030-02-26 21:22 | 2030-03-06 21:53
PH4100XPC#1 | W2\13\004\D | W2 | 13 | 4 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2030-02-27 09:44 | 2030-03-06 21:53 | 407787.5253 | 407788 | [7 empty] | 0 | 0 | 25.33 | 5.05 | 5821.6
TS5500Exc | W2\13\005\B | W2 | 13 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2030-03-02 08:25 | 2030-03-03 11:32 | 34152.8076 | [6 empty] | 34153 | 24289 | 2.37 | 0 | 0 | 9.5 | 5359
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 6d 10:03 |  | 6d 10:03 | 2030-03-03 11:32 | 2030-03-09 21:35
TS Fleet 5 | W2\12\005\D | W2 | 12 | 5 | D | 1 Prestrip - Thick | 91.4744 | 59.6454 | 59.6454 | 2030-03-04 13:43 | 2030-03-09 21:35 | 239865.1911 | 239865 | [7 empty] | 0 | 0 | 15.13 | 5.32 | 5797.77
PH4100XPC#1 | W2\12\005\D | W2 | 12 | 5 | D | 1 Prestrip - Thick | 100 | 40.3546 | 40.3546 | 2030-03-06 21:53 | 2030-03-09 21:35 | 162286.7176 | 162287 | [7 empty] | 0 | 0 | 10.24 | 5.32 | 5797.77
TS6060#1 | W2\13\004\D | W2 | 13 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2030-03-06 21:53 | 2030-03-10 23:06 | 100312.4562 |  |  | 100312 | [5 empty] | 0 | 0 | 0 | 5.05 | 5821.6
TS Fleet 5 | W2\13\005\D | W2 | 13 | 5 | D | 1 Prestrip - Thick | 45.419 | 45.3193 | 45.3193 | 2030-03-09 21:35 | 2030-03-11 20:24 | 87822.3463 | 87822 | [7 empty] | 0 | 0 | 11.98 | 5.13 | 5814.44
PH4100XPC#1 | W2\13\005\D | W2 | 13 | 5 | D | 1 Prestrip - Thick | 100 | 54.6807 | 54.6807 | 2030-03-09 21:35 | 2030-03-11 20:24 | 105963.5593 | 105964 | [7 empty] | 0 | 0 | 14.45 | 5.13 | 5814.44
TS5500Exc | W2\12\005\D | W2 | 12 | 5 | D | 7 PostStrip | 46.1538 | 0 | 46.1538 | 2030-03-09 21:35 | 2030-03-12 01:06 | 45559.4329 |  |  | 45559 | [5 empty] | 0 | 0 | 0 | 5.32 | 5797.77
TS6060#1 | W2\12\005\D | W2 | 12 | 5 | D | 7 PostStrip | 53.8462 | 0 | 53.8462 | 2030-03-10 23:06 | 2030-03-13 02:37 | 53152.6717 |  |  | 53153 | [5 empty] | 0 | 0 | 0 | 5.32 | 5797.77
PH4100A | SC\50\024\D | SC | 50 | 24 | D | 1 Prestrip - Thick | 100 | 87.2806 | 87.2806 | 2030-03-11 10:41 | 2030-03-31 12:14 | 781002.2902 | 781002 | [7 empty] | 0 | 0 | 37.32 | 7.12 | 5787.44
PH4100XPC#1 | W2\14\003\B | W2 | 14 | 3 | B | 1 Prestrip - Thick | 100 | 55.0772 | 55.0772 | 2030-03-11 20:24 | 2030-03-31 20:00 | 1107553.326 | 1107553 | [7 empty] | 0 | 0 | 46.79 | 8.89 | 5421.06
TS Fleet 5 | CP\10\005\B | CP | 10 | 5 | B | 1 Prestrip - Thick | 3.9224 | 3.9224 | 3.9224 | 2030-03-11 20:24 | 2030-03-13 16:15 | 82266.4982 | 82266 | [7 empty] | 0 | 0 | 2.8 | 8.45 | 5618.52
TS5500Exc | SC\50\023\D | SC | 50 | 23 | D | 7 PostStrip | 100 | 0 | 100 | 2030-03-12 01:06 | 2030-03-17 15:50 | 119168.216 |  |  | 119168 | [5 empty] | 0 | 0 | 0 | 7.21 | 5779.9
TS6060#1 | W2\12\005\D | W2 | 12 | 5 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2030-03-13 02:37 | 2030-03-15 03:35 | 66260.1101 | [6 empty] | 66260 | 48425 | 2.49 | 0 | 0 | 5.32 | 5798
TS Fleet 5 | CP\10\005\B | CP | 10 | 5 | B | 1 Prestrip - Thick | 28.0719 | 28.0719 | 28.0719 | 2030-03-13 16:15 | 2030-03-26 18:06 | 588773.4386 | 588773 | [7 empty] | 0 | 0 | 20.02 | 8.45 | 5618.52
TS6060#1 | W2\13\004\D | W2 | 13 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-03-15 03:35 | 2030-03-19 05:44 | 132841.2421 | [6 empty] | 132841 | 97464 | 4.87 | 0 | 0 | 5.05 | 5822
TS5500Exc | W2\12\005\D | W2 | 12 | 5 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2030-03-17 15:50 | 2030-03-19 16:48 | 61667.8252 | [6 empty] | 61668 | 45069 | 2.31 | 0 | 0 | 5.32 | 5798
TS6060#1 | W2\13\005\D | W2 | 13 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2030-03-19 05:44 | 2030-03-21 01:33 | 45216.8746 |  |  | 45217 | [5 empty] | 0 | 0 | 0 | 5.13 | 5814.44
TS5500Exc | SC\50\023\D | SC | 50 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-03-19 16:48 | 2030-03-24 17:15 | 151713.446 | [6 empty] | 151713 | 113568 | 4.73 | 0 | 0 | 7.21 | 5780
TS6060#1 | W2\13\005\D | W2 | 13 | 5 | D | 8 Coal Mining | 62.5 | 0 | 62.5 | 2030-03-21 01:33 | 2030-03-22 04:07 | 35940.9576 | [6 empty] | 35941 | 26328 | 2.99 | 0 | 0 | 5.13 | 5814
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 83d 05:53 |  | 83d 05:53 | 2030-03-22 04:07 | 2030-06-13 10:00
TS5500Exc | W2\13\005\D | W2 | 13 | 5 | D | 8 Coal Mining | 37.5 | 0 | 37.5 | 2030-03-24 17:15 | 2030-03-25 10:23 | 21584.536 | [6 empty] | 21585 | 15811 | 1.8 | 0 | 0 | 5.13 | 5814
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 6d 01:51 |  | 6d 01:51 | 2030-03-25 10:23 | 2030-03-31 12:14
TS Fleet 5 | CP\11\001\B | CP | 11 | 1 | B | 1 Prestrip - Thick | 32.6111 | 32.6111 | 32.6111 | 2030-03-26 18:06 | 2030-03-31 17:53 | 224733.53 | 224734 | [7 empty] | 0 | 0 | 10.5 | 8.68 | 5627.98
PH4100A | SC\50\025\D | SC | 50 | 25 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2030-03-31 12:14 | 2030-05-05 07:40 | 1357862.099 | 1357862 | [7 empty] | 0 | 0 | 38.6 | 6.69 | 5825.62
TS5500Exc | SC\50\024\D | SC | 50 | 24 | D | 7 PostStrip | 100 | 0 | 100 | 2030-03-31 12:14 | 2030-04-06 03:19 | 119461.469 |  |  | 119461 | [5 empty] | 0 | 0 | 0 | 7.12 | 5787.44
TS Fleet 5 | CP\11\002\B | CP | 11 | 2 | B | 1 Prestrip - Thick | 32.1909 | 32.1909 | 32.1909 | 2030-03-31 17:53 | 2030-04-11 20:01 | 499264.8743 | 499265 | [7 empty] | 0 | 0 | 17.46 | 9.03 | 5597.58
PH4100XPC#1 | W2\15\003\B | W2 | 15 | 3 | B | 1 Prestrip - Thick | 100 | 100 | 100 | 2030-03-31 20:00 | 2030-05-04 18:36 | 1872467.753 | 1872468 | [7 empty] | 0 | 0 | 74.99 | 9.01 | 5414.08
TS5500Exc | W2\14\003\B | W2 | 14 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2030-04-06 03:19 | 2030-04-09 08:41 | 97460.3819 | [6 empty] | 97460 | 69767 | 2.88 | 0 | 0 | 8.89 | 5421
TS5500Exc | SC\50\024\D | SC | 50 | 24 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-04-09 08:41 | 2030-04-14 08:10 | 150502.3131 | [6 empty] | 150502 | 112930 | 4.71 | 0 | 0 | 7.12 | 5787
TS Fleet 5 | W2\14\003\D | W2 | 14 | 3 | D | 1 Prestrip - Thick | 14.81 | 14.81 | 14.81 | 2030-04-11 20:01 | 2030-04-13 07:54 | 67322.7331 | 67323 | [7 empty] | 0 | 0 | 3.88 | 5.06 | 5822.5
TS Fleet 5 | W2\14\003\D | W2 | 14 | 3 | D | 1 Prestrip - Thick | 85.19 | 85.19 | 85.19 | 2030-04-13 07:54 | 2030-04-21 22:20 | 387254.646 | 387255 | [7 empty] | 0 | 0 | 22.29 | 5.06 | 5822.5
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 7d 14:10 |  | 7d 14:10 | 2030-04-14 08:10 | 2030-04-21 22:20
TS Fleet 5 | CP\11\003\B | CP | 11 | 3 | B | 1 Prestrip - Thick | 32.1725 | 32.1725 | 32.1725 | 2030-04-21 22:20 | 2030-05-04 23:05 | 586736.5197 | 586737 | [7 empty] | 0 | 0 | 18.78 | 8.76 | 5607.11
TS5500Exc | W2\14\003\D | W2 | 14 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2030-04-21 22:20 | 2030-04-26 23:45 | 107379.5168 |  |  | 107380 | [5 empty] | 0 | 0 | 0 | 5.06 | 5822.5
TS5500Exc | W2\14\003\D | W2 | 14 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-04-26 23:45 | 2030-05-01 16:19 | 141786.0564 | [6 empty] | 141786 | 104194 | 4.98 | 0 | 0 | 5.06 | 5823
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 02:17 |  | 3d 02:17 | 2030-05-01 16:19 | 2030-05-04 18:36
PH4100XPC#1 | W2\14\004\B | W2 | 14 | 4 | B | 1 Prestrip - Thick | 100 | 1.5298 | 1.5298 | 2030-05-04 18:36 | 2030-05-05 02:17 | 16999.9968 | 17000 | [7 empty] | 0 | 0 | 0.81 | 8.98 | 5423.66
TS5500Exc | W2\15\003\B | W2 | 15 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2030-05-04 18:36 | 2030-05-07 16:19 | 87819.8976 | [6 empty] | 87820 | 62827 | 2.61 | 0 | 0 | 9.01 | 5414
TS Fleet 5 | CP\11\004\B | CP | 11 | 4 | B | 1 Prestrip - Thick | 32.3506 | 32.3506 | 32.3506 | 2030-05-04 23:05 | 2030-05-18 15:43 | 616491.9694 | 616492 | [7 empty] | 0 | 0 | 20.65 | 8.2 | 5644.14
PH4100XPC#1 | W2\15\004\B | W2 | 15 | 4 | B | 1 Prestrip - Thick | 100 | 53.8073 | 53.8073 | 2030-05-05 02:17 | 2030-05-11 15:10 | 344200.3893 | 344200 | [7 empty] | 0 | 0 | 28.66 | 8.85 | 5442.76
PH4100A | SC\51\016\D | SC | 51 | 16 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2030-05-05 07:40 | 2030-05-05 07:40 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\51\017\D | SC | 51 | 17 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2030-05-05 07:40 | 2030-05-05 07:40 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\51\018\D | SC | 51 | 18 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2030-05-05 07:40 | 2030-05-05 07:40 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\51\019\D | SC | 51 | 19 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2030-05-05 07:40 | 2030-05-05 07:40 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\51\021\D | SC | 51 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2030-05-05 07:40 | 2030-05-31 16:14 | 1036532.021 | 1036532 | [7 empty] | 0 | 0 | 48.75 | 7.32 | 5768.43
TS5500Exc | W2\14\004\B | W2 | 14 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2030-05-07 16:19 | 2030-05-10 00:40 | 70984.6275 | [6 empty] | 70985 | 50887 | 2.47 | 0 | 0 | 8.98 | 5424
TS5500Exc | SC\50\025\D | SC | 50 | 25 | D | 7 PostStrip | 100 | 0 | 100 | 2030-05-10 00:40 | 2030-05-19 15:01 | 203718.0934 |  |  | 203718 | [5 empty] | 0 | 0 | 0 | 6.69 | 5825.62
PH4100XPC#1 | W2\15\003\D | W2 | 15 | 3 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2030-05-11 15:10 | 2030-05-20 11:44 | 481170.0571 | 481170 | [7 empty] | 0 | 0 | 27.33 | 5.03 | 5825.02
TS Fleet 5 | W2\14\004\D | W2 | 14 | 4 | D | 1 Prestrip - Thick | 97.4855 | 56.0796 | 56.0796 | 2030-05-18 15:43 | 2030-05-23 21:11 | 235386.7504 | 235387 | [7 empty] | 0 | 0 | 15.13 | 4.88 | 5836.43
TS5500Exc | W2\15\004\B | W2 | 15 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2030-05-19 15:01 | 2030-05-20 21:37 | 38541.5387 | [6 empty] | 38542 | 27702 | 2.38 | 0 | 0 | 8.85 | 5443
PH4100XPC#1 | W2\14\004\D | W2 | 14 | 4 | D | 1 Prestrip - Thick | 100 | 43.9204 | 43.9204 | 2030-05-20 11:44 | 2030-05-23 21:11 | 184349.8405 | 184350 | [7 empty] | 0 | 0 | 11.85 | 4.88 | 5836.43
TS5500Exc | SC\50\025\D | SC | 50 | 25 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-05-20 21:37 | 2030-05-28 16:19 | 235169.6102 | [6 empty] | 235170 | 177028 | 4.82 | 0 | 0 | 6.69 | 5826
TS Fleet 5 | W2\15\004\D | W2 | 15 | 4 | D | 1 Prestrip - Thick | 45.419 | 45.419 | 45.419 | 2030-05-23 21:11 | 2030-05-26 06:49 | 108123.3735 | 108123 | [7 empty] | 0 | 0 | 12.91 | 4.74 | 5848.45
PH4100XPC#1 | W2\16\003\B | W2 | 16 | 3 | B | 1 Prestrip - Thick | 100 | 54.4116 | 54.4116 | 2030-05-23 21:11 | 2030-06-11 00:36 | 978854.9347 | 978855 | [7 empty] | 0 | 0 | 32.66 | 9.01 | 5420.67
TS Fleet 5 | CP\11\005\B | CP | 11 | 5 | B | 1 Prestrip - Thick | 32.0302 | 32.0302 | 32.0302 | 2030-05-26 06:49 | 2030-06-10 12:38 | 686274.3071 | 686274 | [7 empty] | 0 | 0 | 23.35 | 8.41 | 5622.14
TS5500Exc | W2\14\004\D | W2 | 14 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2030-05-28 16:19 | 2030-06-02 04:15 | 95457.5589 |  |  | 95458 | [5 empty] | 0 | 0 | 0 | 4.88 | 5836.43
PH4100A | SC\51\022\D | SC | 51 | 22 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2030-05-31 16:14 | 2030-06-26 12:16 | 1008775.946 | 1008776 | [7 empty] | 0 | 0 | 47.57 | 7.31 | 5769.04
TS5500Exc | W2\14\004\D | W2 | 14 | 4 | D | 8 Coal Mining | 72.7 | 0 | 72.7 | 2030-06-02 04:15 | 2030-06-05 03:37 | 89895.7106 | [6 empty] | 89896 | 66109 | 3.52 | 0 | 0 | 4.88 | 5836
TS5500Exc | W2\14\004\D | W2 | 14 | 4 | D | 8 Coal Mining | 27.3 | 0 | 27.3 | 2030-06-05 03:37 | 2030-06-06 06:22 | 33699.0799 | [6 empty] | 33699 | 24782 | 1.32 | 0 | 0 | 4.88 | 5836
TS5500Exc | W2\15\003\D | W2 | 15 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2030-06-06 06:22 | 2030-06-11 08:11 | 107725.7778 |  |  | 107726 | [5 empty] | 0 | 0 | 0 | 5.03 | 5825.02
TS Fleet 5 | CP\12\001\B | CP | 12 | 1 | B | 1 Prestrip - Thick | 29.5975 | 29.5975 | 29.5975 | 2030-06-10 12:38 | 2030-06-15 17:36 | 234430.8266 | 234431 | [7 empty] | 0 | 0 | 10.94 | 9.96 | 5492.25
PH4100XPC#1 | W2\15\004\D | W2 | 15 | 4 | D | 1 Prestrip - Thick | 100 | 54.581 | 54.581 | 2030-06-11 00:36 | 2030-06-13 10:00 | 129934.3821 | 129934 | [7 empty] | 0 | 0 | 15.52 | 4.74 | 5848.45
TS5500Exc | W2\16\003\B | W2 | 16 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2030-06-11 08:11 | 2030-06-14 06:07 | 88103.7242 | [6 empty] | 88104 | 63208 | 2.22 | 0 | 0 | 9.01 | 5421
PH4100XPC#1 | CP\03\005\D | CP | 3 | 5 | D | 1 Prestrip - Thick | 100 | 26.1776 | 26.1776 | 2030-06-13 10:00 | 2030-07-05 05:47 | 1185595.624 | 1185596 | [7 empty] | 0 | 0 | 13.78 | 6.06 | 5873.34
TS6060#1 | W2\15\004\D | W2 | 15 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2030-06-13 10:00 | 2030-06-15 11:15 | 50810.8125 |  |  | 50811 | [5 empty] | 0 | 0 | 0 | 4.74 | 5848.45
TS5500Exc | W2\15\003\D | W2 | 15 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-06-14 06:07 | 2030-06-18 22:24 | 141416.5958 | [6 empty] | 141417 | 103921 | 4.94 | 0 | 0 | 5.03 | 5825
TS6060#1 | W2\15\004\D | W2 | 15 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-06-15 11:15 | 2030-06-17 11:03 | 64693.5973 | [6 empty] | 64694 | 47650 | 4.83 | 0 | 0 | 4.74 | 5848
TS Fleet 5 | W2\16\003\D | W2 | 16 | 3 | D | 1 Prestrip - Thick | 45.419 | 45.419 | 45.419 | 2030-06-15 17:36 | 2030-06-21 18:43 | 272240.5035 | 272241 | [7 empty] | 0 | 0 | 13.26 | 5.03 | 5823.27
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 30d 05:27 |  | 30d 05:27 | 2030-06-17 11:03 | 2030-07-17 16:30
TS5500Exc | SC\51\021\D | SC | 51 | 21 | D | 7 PostStrip | 100 | 0 | 100 | 2030-06-18 22:24 | 2030-06-24 13:15 | 119273.1261 |  |  | 119273 | [5 empty] | 0 | 0 | 0 | 7.32 | 5768.43
TS Fleet 5 | CP\12\002\B | CP | 12 | 2 | B | 1 Prestrip - Thick | 32.0368 | 32.0368 | 32.0368 | 2030-06-21 18:43 | 2030-07-04 00:36 | 551331.8727 | 551332 | [7 empty] | 0 | 0 | 19.69 | 10.32 | 5452.26
TS5500Exc | SC\51\021\D | SC | 51 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-06-24 13:15 | 2030-06-29 07:47 | 144257.2607 | [6 empty] | 144257 | 107724 | 4.49 | 0 | 0 | 7.32 | 5768
PH4100A | SC\51\023\D | SC | 51 | 23 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2030-06-26 12:16 | 2030-07-19 15:30 | 898554.946 | 898555 | [7 empty] | 0 | 0 | 43.33 | 7.06 | 5792.37
TS5500Exc | SC\51\022\D | SC | 51 | 22 | D | 7 PostStrip | 100 | 0 | 100 | 2030-06-29 07:47 | 2030-07-04 22:43 | 119327.6565 |  |  | 119328 | [5 empty] | 0 | 0 | 0 | 7.31 | 5769.04
TS Fleet 5 | CP\12\003\B | CP | 12 | 3 | B | 1 Prestrip - Thick | 32.3046 | 32.3046 | 32.3046 | 2030-07-04 00:36 | 2030-07-16 07:04 | 552411.5195 | 552412 | [7 empty] | 0 | 0 | 19.16 | 9.95 | 5511.33
TS5500Exc | SC\51\022\D | SC | 51 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-07-04 22:43 | 2030-07-09 16:37 | 143476.5743 | [6 empty] | 143477 | 107055 | 4.46 | 0 | 0 | 7.31 | 5769
PH4100XPC#1 | W2\16\003\D | W2 | 16 | 3 | D | 1 Prestrip - Thick | 100 | 54.581 | 54.581 | 2030-07-05 05:47 | 2030-07-11 06:19 | 327157.7686 | 327158 | [7 empty] | 0 | 0 | 15.93 | 5.03 | 5823.27
TS5500Exc | CP\03\005\D | CP | 3 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2030-07-09 16:37 | 2030-08-01 02:13 | 475461.6566 |  |  | 475462 | [5 empty] | 0 | 0 | 0 | 6.06 | 5873.34
PH4100XPC#1 | CP\04\002\B | CP | 4 | 2 | B | 1 Prestrip - Thick | 100 | 40.9904 | 40.9904 | 2030-07-11 06:19 | 2030-07-17 16:30 | 345656.506 | 345657 | [7 empty] | 0 | 0 | 9.58 | 9.44 | 5576.4
TS Fleet 5 | CP\12\004\B | CP | 12 | 4 | B | 1 Prestrip - Thick | 27.5031 | 27.5031 | 27.5031 | 2030-07-16 07:04 | 2030-07-28 08:20 | 542654.2692 | 542654 | [7 empty] | 0 | 0 | 18.17 | 9.52 | 5504.47
PH4100XPC#1 | CP\04\003\B | CP | 4 | 3 | B | 1 Prestrip - Thick | 100 | 54.4458 | 54.4458 | 2030-07-17 16:30 | 2030-07-30 09:24 | 686383.8355 | 686384 | [7 empty] | 0 | 0 | 22.6 | 8.84 | 5599.54
TS6060#1 | CP\04\002\B | CP | 4 | 2 | B | 8 Coal Mining | 56.8 | 0 | 56.8 | 2030-07-17 16:30 | 2030-07-20 06:45 | 84241.1245 | [6 empty] | 84241 | 59383 | 1.99 | 0 | 0 | 9.44 | 5576
PH4100A | SC\51\024\D | SC | 51 | 24 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2030-07-19 15:30 | 2030-08-30 17:22 | 1640537.106 | 1640537 | [7 empty] | 0 | 0 | 41.27 | 6.59 | 5833.91
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 10d 02:39 |  | 10d 02:39 | 2030-07-20 06:45 | 2030-07-30 09:24
TS Fleet 5 | CP\12\005\B | CP | 12 | 5 | B | 1 Prestrip - Thick | 32.011 | 32.011 | 32.011 | 2030-07-28 08:20 | 2030-08-13 00:56 | 706526.1415 | 706526 | [7 empty] | 0 | 0 | 23.5 | 9.82 | 5469.26
PH4100XPC#1 | CP\04\004\B | CP | 4 | 4 | B | 1 Prestrip - Thick | 100 | 54.3138 | 54.3138 | 2030-07-30 09:24 | 2030-08-14 02:13 | 790056.1 | 790056 | [7 empty] | 0 | 0 | 26.33 | 8.7 | 5598.26
TS6060#1 | CP\04\003\B | CP | 4 | 3 | B | 8 Coal Mining | 17.4 | 0 | 17.4 | 2030-07-30 09:24 | 2030-07-31 10:25 | 33849.6412 | [6 empty] | 33850 | 24172 | 0.81 | 0 | 0 | 8.84 | 5600
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 15:49 |  | 0d 15:49 | 2030-07-31 10:25 | 2030-08-01 02:13
TS6060#1 | CP\03\005\D | CP | 3 | 5 | D | 8 Coal Mining | 50.8 | 0 | 50.8 | 2030-08-01 02:13 | 2030-08-11 09:18 | 334381.1512 | [6 empty] | 334381 | 239454 | 2.53 | 0 | 0 | 6.06 | 5873
TS5500Exc | W2\16\003\D | W2 | 16 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2030-08-01 02:13 | 2030-08-06 22:19 | 123897.6707 |  |  | 123898 | [5 empty] | 0 | 0 | 0 | 5.03 | 5823.27
TS5500Exc | CP\04\002\B | CP | 4 | 2 | B | 8 Coal Mining | 43.2 | 0 | 43.2 | 2030-08-06 22:19 | 2030-08-09 01:16 | 64184.4649 | [6 empty] | 64184 | 45244 | 1.52 | 0 | 0 | 9.44 | 5576
TS5500Exc | W2\16\003\D | W2 | 16 | 3 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2030-08-09 01:16 | 2030-08-11 13:38 | 76023.2657 | [6 empty] | 76023 | 55865 | 2.34 | 0 | 0 | 5.03 | 5823
TS6060#1 | W2\16\003\D | W2 | 16 | 3 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2030-08-11 09:18 | 2030-08-13 21:39 | 81684.5727 | [6 empty] | 81685 | 60025 | 2.52 | 0 | 0 | 5.03 | 5823
TS5500Exc | CP\04\003\B | CP | 4 | 3 | B | 8 Coal Mining | 82.6 | 0 | 82.6 | 2030-08-11 13:38 | 2030-08-16 20:46 | 160136.429 | [6 empty] | 160136 | 114355 | 3.81 | 0 | 0 | 8.84 | 5600
TS Fleet 5 | CP\04\002\D | CP | 4 | 2 | D | 1 Prestrip - Thick | 29.9257 | 29.9257 | 29.9257 | 2030-08-13 00:56 | 2030-08-20 02:17 | 317674.9162 | 317675 | [7 empty] | 0 | 0 | 16.64 | 5.88 | 5889.64
TS6060#1 | CP\04\002\D | CP | 4 | 2 | D | 1 Prestrip - Thick | 34.1119 | 22.2462 | 22.2462 | 2030-08-13 21:39 | 2030-08-23 10:31 | 236153.5592 | 236154 | [7 empty] | 0 | 0 | 12.37 | 5.88 | 5889.64
PH4100XPC#1 | CP\04\002\D | CP | 4 | 2 | D | 1 Prestrip - Thick | 100 | 47.8281 | 47.8281 | 2030-08-14 02:13 | 2030-08-23 10:31 | 507717.5096 | 507718 | [7 empty] | 0 | 0 | 26.6 | 5.88 | 5889.64
TS5500Exc | CP\03\005\D | CP | 3 | 5 | D | 8 Coal Mining | 49.2 | 0 | 49.2 | 2030-08-16 20:46 | 2030-08-27 14:22 | 324472.9429 | [6 empty] | 324473 | 232359 | 2.45 | 0 | 0 | 6.06 | 5873
TS Fleet 5 | CP\04\003\D | CP | 4 | 3 | D | 1 Prestrip - Thick | 36.7279 | 36.7279 | 36.7279 | 2030-08-20 02:17 | 2030-09-01 03:54 | 543320.0873 | 543320 | [7 empty] | 0 | 0 | 19.97 | 6.52 | 5833.91
PH4100XPC#1 | CP\04\003\D | CP | 4 | 3 | D | 1 Prestrip - Thick | 100 | 43.4609 | 43.4609 | 2030-08-23 10:31 | 2030-09-04 06:34 | 642922.8008 | 642923 | [7 empty] | 0 | 0 | 23.63 | 6.52 | 5833.91
TS6060#1 | CP\04\003\D | CP | 4 | 3 | D | 1 Prestrip - Thick | 38.2321 | 19.8112 | 19.8112 | 2030-08-23 10:31 | 2030-09-04 06:34 | 293069.0897 | 293069 | [7 empty] | 0 | 0 | 10.77 | 6.52 | 5833.91
TS5500Exc | CP\04\004\B | CP | 4 | 4 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2030-08-27 14:22 | 2030-08-30 13:54 | 90107.8148 | [6 empty] | 90108 | 64623 | 2.15 | 0 | 0 | 8.7 | 5598
TS5500Exc | SC\51\023\D | SC | 51 | 23 | D | 7 PostStrip | 100 | 0 | 100 | 2030-08-30 13:54 | 2030-09-05 03:31 | 118167.0925 |  |  | 118167 | [5 empty] | 0 | 0 | 0 | 7.06 | 5792.37
PH4100A | SC\52\016\D | SC | 52 | 16 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2030-08-30 17:22 | 2030-08-30 17:22 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\52\017\D | SC | 52 | 17 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2030-08-30 17:22 | 2030-08-30 17:22 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\52\018\D | SC | 52 | 18 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2030-08-30 17:22 | 2030-08-30 17:22 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\52\019\D | SC | 52 | 19 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2030-08-30 17:22 | 2030-08-30 17:22 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\52\020\D | SC | 52 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2030-08-30 17:22 | 2030-09-27 07:23 | 1095071.851 | 1095072 | [7 empty] | 0 | 0 | 50.86 | 7.43 | 5759.54
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 6d 02:12 |  | 6d 02:12 | 2030-09-01 03:54 | 2030-09-07 06:06
PH4100XPC#1 | CP\04\005\B | CP | 4 | 5 | B | 1 Prestrip - Thick | 100 | 54.5823 | 54.5823 | 2030-09-04 06:34 | 2030-09-20 08:24 | 873394.1255 | 873394 | [7 empty] | 0 | 0 | 29.14 | 8.6 | 5604.54
TS6060#1 | CP\04\004\B | CP | 4 | 4 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2030-09-04 06:34 | 2030-09-07 06:06 | 96817.9713 | [6 empty] | 96818 | 69435 | 2.31 | 0 | 0 | 8.7 | 5598
TS5500Exc | SC\51\023\D | SC | 51 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-09-05 03:31 | 2030-09-10 03:13 | 150786.7931 | [6 empty] | 150787 | 112874 | 4.7 | 0 | 0 | 7.06 | 5792
TS Fleet 5 | CP\04\004\D | CP | 4 | 4 | D | 1 Prestrip - Thick | 34.6096 | 34.6096 | 34.6096 | 2030-09-07 06:06 | 2030-09-18 06:30 | 496025.5429 | 496026 | [7 empty] | 0 | 0 | 18.08 | 6.27 | 5854.95
TS6060#1 | CP\04\004\D | CP | 4 | 4 | D | 1 Prestrip - Thick | 23.7992 | 23.7992 | 23.7992 | 2030-09-07 06:06 | 2030-09-21 00:40 | 341089.7717 | 341090 | [7 empty] | 0 | 0 | 12.43 | 6.27 | 5854.95
TS5500Exc | SC\51\024\D | SC | 51 | 24 | D | 7 PostStrip | 100 | 0 | 100 | 2030-09-10 03:13 | 2030-09-20 20:55 | 227907.3878 |  |  | 227907 | [5 empty] | 0 | 0 | 0 | 6.59 | 5833.91
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 6d 13:40 |  | 6d 13:40 | 2030-09-18 06:30 | 2030-09-24 20:10
PH4100XPC#1 | CP\04\004\D | CP | 4 | 4 | D | 1 Prestrip - Thick | 100 | 41.5912 | 41.5912 | 2030-09-20 08:24 | 2030-10-01 07:44 | 596085.4749 | 596085 | [7 empty] | 0 | 0 | 21.73 | 6.27 | 5854.95
TS5500Exc | CP\04\005\B | CP | 4 | 5 | B | 8 Coal Mining | 83.1 | 0 | 83.1 | 2030-09-20 20:55 | 2030-09-24 20:10 | 119976.403 | [6 empty] | 119976 | 85141 | 2.84 | 0 | 0 | 8.6 | 5605
TS6060#1 | CP\04\005\B | CP | 4 | 5 | B | 8 Coal Mining | 16.9 | 0 | 16.9 | 2030-09-21 00:40 | 2030-09-21 18:40 | 24354.4058 | [6 empty] | 24354 | 17283 | 0.58 | 0 | 0 | 8.6 | 5605
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 01:30 |  | 3d 01:30 | 2030-09-21 18:40 | 2030-09-24 20:10
TS Fleet 5 | CP\04\005\D | CP | 4 | 5 | D | 1 Prestrip - Thick | 33.555 | 33.555 | 33.555 | 2030-09-24 20:10 | 2030-10-05 13:49 | 483358.8957 | 483359 | [7 empty] | 0 | 0 | 17.7 | 6.11 | 5869.22
TS6060#1 | CP\04\005\D | CP | 4 | 5 | D | 1 Prestrip - Thick | 32.7529 | 28.4589 | 28.4589 | 2030-09-24 20:10 | 2030-10-11 09:29 | 409949.9659 | 409950 | [7 empty] | 0 | 0 | 15.01 | 6.11 | 5869.22
TS5500Exc | SC\51\024\D | SC | 51 | 24 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-09-24 20:10 | 2030-10-03 16:12 | 267075.8848 | [6 empty] | 267076 | 200405 | 4.75 | 0 | 0 | 6.59 | 5834
PH4100A | SC\52\021\D | SC | 52 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2030-09-27 07:23 | 2030-10-24 01:25 | 1047289.688 | 1047290 | [7 empty] | 0 | 0 | 49.21 | 7.31 | 5770.86
PH4100XPC#1 | CP\04\005\D | CP | 4 | 5 | D | 1 Prestrip - Thick | 100 | 37.986 | 37.986 | 2030-10-01 07:44 | 2030-10-11 09:29 | 547187.3608 | 547187 | [7 empty] | 0 | 0 | 20.04 | 6.11 | 5869.22
TS5500Exc | CP\04\002\D | CP | 4 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2030-10-03 16:12 | 2030-10-08 14:46 | 104858.6808 |  |  | 104859 | [5 empty] | 0 | 0 | 0 | 5.88 | 5889.64
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 20d 19:30 |  | 20d 19:30 | 2030-10-05 13:49 | 2030-10-26 09:19
TS5500Exc | CP\04\002\D | CP | 4 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-10-08 14:46 | 2030-10-13 01:44 | 134735.5398 | [6 empty] | 134736 | 96432 | 5.07 | 0 | 0 | 5.88 | 5890
PH4100XPC#1 | CP\05\002\B | CP | 5 | 2 | B | 1 Prestrip - Thick | 100 | 54.5066 | 54.5066 | 2030-10-11 09:29 | 2030-10-21 11:09 | 545393.7476 | 545394 | [7 empty] | 0 | 0 | 13.57 | 9.57 | 5564.15
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 10d 01:40 |  | 10d 01:40 | 2030-10-11 09:29 | 2030-10-21 11:09
TS5500Exc | SC\52\020\D | SC | 52 | 20 | D | 7 PostStrip | 100 | 0 | 100 | 2030-10-13 01:44 | 2030-10-18 17:37 | 120182.9984 |  |  | 120183 | [5 empty] | 0 | 0 | 0 | 7.43 | 5759.54
TS5500Exc | SC\52\020\D | SC | 52 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-10-18 17:37 | 2030-10-23 13:15 | 145635.468 | [6 empty] | 145635 | 108582 | 4.52 | 0 | 0 | 7.43 | 5760
PH4100XPC#1 | CP\05\003\B | CP | 5 | 3 | B | 1 Prestrip - Thick | 100 | 54.614 | 54.614 | 2030-10-21 11:09 | 2030-11-04 15:08 | 770559.1434 | 770559 | [7 empty] | 0 | 0 | 25.85 | 8.89 | 5595.99
TS6060#1 | CP\05\002\B | CP | 5 | 2 | B | 8 Coal Mining | 56 | 0 | 56 | 2030-10-21 11:09 | 2030-10-24 19:42 | 109007.7791 | [6 empty] | 109008 | 77194 | 2.19 | 0 | 0 | 9.57 | 5564
TS5500Exc | CP\05\002\B | CP | 5 | 2 | B | 8 Coal Mining | 44 | 0 | 44 | 2030-10-23 13:15 | 2030-10-26 09:19 | 85750.2146 | [6 empty] | 85750 | 60724 | 1.72 | 0 | 0 | 9.57 | 5564
PH4100A | SC\52\022\D | SC | 52 | 22 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2030-10-24 01:25 | 2030-11-19 14:50 | 1032772.932 | 1032773 | [7 empty] | 0 | 0 | 48.46 | 7.29 | 5771.88
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 13:37 |  | 1d 13:37 | 2030-10-24 19:42 | 2030-10-26 09:19
TS Fleet 5 | CP\05\002\D | CP | 5 | 2 | D | 1 Prestrip - Thick | 31.2679 | 31.2679 | 31.2679 | 2030-10-26 09:19 | 2030-11-05 01:13 | 435048.9427 | 435049 | [7 empty] | 0 | 0 | 17.31 | 5.79 | 5897.46
TS6060#1 | CP\05\002\D | CP | 5 | 2 | D | 1 Prestrip - Thick | 35.3289 | 32.8193 | 32.8193 | 2030-10-26 09:19 | 2030-11-13 19:53 | 456633.7725 | 456634 | [7 empty] | 0 | 0 | 18.16 | 5.79 | 5897.46
TS5500Exc | CP\04\003\D | CP | 4 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2030-10-26 09:19 | 2030-11-02 10:45 | 149838.8495 |  |  | 149839 | [5 empty] | 0 | 0 | 0 | 6.52 | 5833.91
TS5500Exc | CP\04\003\D | CP | 4 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-11-02 10:45 | 2030-11-09 13:40 | 215288.144 | [6 empty] | 215288 | 153352 | 5.11 | 0 | 0 | 6.52 | 5834
PH4100XPC#1 | CP\05\002\D | CP | 5 | 2 | D | 1 Prestrip - Thick | 100 | 35.9128 | 35.9128 | 2030-11-04 15:08 | 2030-11-13 19:53 | 499676.5754 | 499677 | [7 empty] | 0 | 0 | 19.88 | 5.79 | 5897.46
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 11d 21:36 |  | 11d 21:36 | 2030-11-05 01:13 | 2030-11-16 22:49
TS5500Exc | CP\05\003\B | CP | 5 | 3 | B | 8 Coal Mining | 48 | 0 | 48 | 2030-11-09 13:40 | 2030-11-12 15:58 | 93588.5425 | [6 empty] | 93589 | 66881 | 2.23 | 0 | 0 | 8.89 | 5596
TS5500Exc | SC\52\021\D | SC | 52 | 21 | D | 7 PostStrip | 100 | 0 | 100 | 2030-11-12 15:58 | 2030-11-18 06:48 | 119255.217 |  |  | 119255 | [5 empty] | 0 | 0 | 0 | 7.31 | 5770.86
TS6060#1 | CP\05\003\B | CP | 5 | 3 | B | 8 Coal Mining | 52 | 0 | 52 | 2030-11-13 19:53 | 2030-11-16 22:49 | 101426.1926 | [6 empty] | 101426 | 72482 | 2.42 | 0 | 0 | 8.89 | 5596
PH4100XPC#1 | CP\05\004\B | CP | 5 | 4 | B | 1 Prestrip - Thick | 100 | 54.4078 | 54.4078 | 2030-11-13 19:53 | 2030-11-28 22:39 | 815430.345 | 815430 | [7 empty] | 0 | 0 | 27.23 | 8.6 | 5606.7
TS Fleet 5 | CP\05\003\D | CP | 5 | 3 | D | 1 Prestrip - Thick | 29.0667 | 29.0667 | 29.0667 | 2030-11-16 22:49 | 2030-11-26 11:58 | 429882.3687 | 429882 | [7 empty] | 0 | 0 | 15.83 | 6.48 | 5836.58
TS6060#1 | CP\05\003\D | CP | 5 | 3 | D | 1 Prestrip - Thick | 36.0032 | 36.0032 | 36.0032 | 2030-11-16 22:49 | 2030-12-08 10:53 | 532471.1516 | 532471 | [7 empty] | 0 | 0 | 19.61 | 6.48 | 5836.58
TS5500Exc | SC\52\021\D | SC | 52 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-11-18 06:48 | 2030-11-23 06:18 | 150504.1665 | [6 empty] | 150504 | 112394 | 4.68 | 0 | 0 | 7.31 | 5771
PH4100A | SC\52\023\D | SC | 52 | 23 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2030-11-19 14:50 | 2030-12-12 16:37 | 892011.8985 | 892012 | [7 empty] | 0 | 0 | 42.53 | 6.97 | 5800.23
TS5500Exc | CP\04\004\D | CP | 4 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2030-11-23 06:18 | 2030-11-30 09:48 | 151675.2705 |  |  | 151675 | [5 empty] | 0 | 0 | 0 | 6.27 | 5854.95
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 10d 01:37 |  | 10d 01:37 | 2030-11-26 11:58 | 2030-12-06 13:35
PH4100XPC#1 | CP\05\003\D | CP | 5 | 3 | D | 1 Prestrip - Thick | 100 | 34.9301 | 34.9301 | 2030-11-28 22:39 | 2030-12-08 10:53 | 516599.6783 | 516600 | [7 empty] | 0 | 0 | 19.03 | 6.48 | 5836.58
TS5500Exc | CP\05\004\B | CP | 5 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2030-11-30 09:48 | 2030-12-06 13:35 | 186159.2525 | [6 empty] | 186159 | 133552 | 4.45 | 0 | 0 | 8.6 | 5607
TS Fleet 5 | CP\05\004\D | CP | 5 | 4 | D | 1 Prestrip - Thick | 36.37 | 36.37 | 36.37 | 2030-12-06 13:35 | 2030-12-18 03:20 | 521047.0124 | 521047 | [7 empty] | 0 | 0 | 19.01 | 6.28 | 5854.07
TS5500Exc | CP\04\004\D | CP | 4 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-12-06 13:35 | 2030-12-13 12:35 | 210340.8575 | [6 empty] | 210341 | 151307 | 5.04 | 0 | 0 | 6.27 | 5855
PH4100XPC#1 | CP\05\004\D | CP | 5 | 4 | D | 1 Prestrip - Thick | 100 | 43.7067 | 43.7067 | 2030-12-08 10:53 | 2030-12-19 23:31 | 626154.3589 | 626154 | [7 empty] | 0 | 0 | 22.84 | 6.28 | 5854.07
TS6060#1 | CP\05\004\D | CP | 5 | 4 | D | 1 Prestrip - Thick | 19.9232 | 19.9232 | 19.9232 | 2030-12-08 10:53 | 2030-12-19 23:31 | 285425.385 | 285425 | [7 empty] | 0 | 0 | 10.41 | 6.28 | 5854.07
PH4100A | SC\52\024\D | SC | 52 | 24 | D | 1 Prestrip - Thick | 100 | 74.6918 | 74.6918 | 2030-12-12 16:37 | 2031-01-01 | 747381.4004 | 747381 | [7 empty] | 0 | 0 | 31.81 | 6.48 | 5843.94
TS5500Exc | SC\52\022\D | SC | 52 | 22 | D | 7 PostStrip | 100 | 0 | 100 | 2030-12-13 12:35 | 2030-12-19 03:51 | 119635.4362 |  |  | 119635 | [5 empty] | 0 | 0 | 0 | 7.29 | 5771.88
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 13d 20:40 |  | 13d 20:40 | 2030-12-18 03:20 | 2031-01-01
TS5500Exc | SC\52\022\D | SC | 52 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2030-12-19 03:51 | 2030-12-23 23:50 | 146089.5541 | [6 empty] | 146090 | 109007 | 4.54 | 0 | 0 | 7.29 | 5772
PH4100XPC#1 | CP\05\005\B | CP | 5 | 5 | B | 1 Prestrip - Thick | 100 | 36.953 | 36.953 | 2030-12-19 23:31 | 2031-01-01 | 654587.6802 | 654588 | [7 empty] | 0 | 0 | 21.78 | 8.53 | 5610.65
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 12d 00:29 |  | 12d 00:29 | 2030-12-19 23:31 | 2031-01-01
TS5500Exc | CP\04\005\D | CP | 4 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2030-12-23 23:50 | 2030-12-31 02:24 | 150857.7957 |  |  | 150858 | [5 empty] | 0 | 0 | 0 | 6.11 | 5869.22
TS5500Exc | CP\04\005\D | CP | 4 | 5 | D | 8 Coal Mining | 100 | 0 | 13 | 2030-12-31 02:24 | 2031-01-01 | 27189.7457 | [6 empty] | 27190 | 19487 | 0.65 | 0 | 0 | 6.11 | 5869
| EOP 83 : 2030 | EOP 83 : 2030 | [7 empty] | 2031-01-01 | 2031-01-01 |  | 49961335 |  | 3950193 |  |  |  | 6883379 | 5014560 | 198.81 | 0 | 2095.42 | 6.8 | 5758
PH4100A | SC\52\024\D | SC | 52 | 24 | D | 1 Prestrip - Thick | 100 | 25.3082 | 25.3082 | 2031-01-01 | 2031-01-06 20:15 | 253239.0476 | 253239 | [7 empty] | 0 | 0 | 10.78 | 6.48 | 5843.94
PH4100XPC#1 | CP\05\005\B | CP | 5 | 5 | B | 1 Prestrip - Thick | 100 | 6.8372 | 6.8372 | 2031-01-01 | 2031-01-03 05:22 | 121114.8235 | 121115 | [7 empty] | 0 | 0 | 4.03 | 8.53 | 5610.65
TS5500Exc | CP\04\005\D | CP | 4 | 5 | D | 8 Coal Mining | 100 | 0 | 87 | 2031-01-01 | 2031-01-07 00:15 | 181710.265 | [6 empty] | 181710 | 130236 | 4.34 | 0 | 0 | 6.11 | 5869
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 6d 18:38 |  | 6d 18:38 | 2031-01-01 | 2031-01-07 18:37
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 05:23 |  | 2d 05:23 | 2031-01-01 | 2031-01-03 05:22
PH4100XPC#1 | CP\06\002\B | CP | 6 | 2 | B | 1 Prestrip - Thick | 100 | 54.5325 | 54.5325 | 2031-01-03 05:22 | 2031-01-15 12:10 | 665995.9648 | 665996 | [7 empty] | 0 | 0 | 15.57 | 9.52 | 5565.86
TS6060#1 | CP\05\005\B | CP | 5 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2031-01-03 05:22 | 2031-01-07 18:37 | 147865.603 | [6 empty] | 147866 | 105085 | 3.5 | 0 | 0 | 8.53 | 5611
PH4100A | SC\53\017\D | SC | 53 | 17 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-01-06 20:15 | 2031-01-06 20:15 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\53\018\D | SC | 53 | 18 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-01-06 20:15 | 2031-01-06 20:15 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\53\019\D | SC | 53 | 19 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-01-06 20:15 | 2031-01-06 20:15 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\53\020\D | SC | 53 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2031-01-06 20:15 | 2031-01-31 11:19 | 1096267.375 | 1096267 | [7 empty] | 0 | 0 | 49.83 | 7.37 | 5764.4
TS5500Exc | SC\52\023\D | SC | 52 | 23 | D | 7 PostStrip | 100 | 0 | 100 | 2031-01-07 00:15 | 2031-01-12 15:42 | 119796.2231 |  |  | 119796 | [5 empty] | 0 | 0 | 0 | 6.97 | 5800.23
TS Fleet 5 | CP\05\005\D | CP | 5 | 5 | D | 1 Prestrip - Thick | 31.5402 | 31.5402 | 31.5402 | 2031-01-07 18:37 | 2031-01-17 10:37 | 454709.3377 | 454709 | [7 empty] | 0 | 0 | 16.66 | 6.13 | 5867.29
TS6060#1 | CP\05\005\D | CP | 5 | 5 | D | 1 Prestrip - Thick | 30.5572 | 30.5572 | 30.5572 | 2031-01-07 18:37 | 2031-01-25 13:35 | 440538.135 | 440538 | [7 empty] | 0 | 0 | 16.14 | 6.13 | 5867.29
TS5500Exc | SC\52\023\D | SC | 52 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-01-12 15:42 | 2031-01-17 13:52 | 148825.1414 | [6 empty] | 148825 | 111492 | 4.64 | 0 | 0 | 6.97 | 5800
PH4100XPC#1 | CP\05\005\D | CP | 5 | 5 | D | 1 Prestrip - Thick | 100 | 37.9026 | 37.9026 | 2031-01-15 12:10 | 2031-01-25 13:35 | 546434.8265 | 546435 | [7 empty] | 0 | 0 | 20.02 | 6.13 | 5867.29
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 11d 16:18 |  | 11d 16:18 | 2031-01-17 10:37 | 2031-01-29 02:55
TS5500Exc | CP\06\002\B | CP | 6 | 2 | B | 8 Coal Mining | 48.8 | 0 | 48.8 | 2031-01-17 13:52 | 2031-01-21 05:19 | 110165.3701 | [6 empty] | 110165 | 78162 | 2 | 0 | 0 | 9.52 | 5566
TS5500Exc | SC\52\024\D | SC | 52 | 24 | D | 7 PostStrip | 100 | 0 | 100 | 2031-01-21 05:19 | 2031-01-27 12:54 | 134057.2886 |  |  | 134057 | [5 empty] | 0 | 0 | 0 | 6.48 | 5843.94
PH4100XPC#1 | CP\06\003\B | CP | 6 | 3 | B | 1 Prestrip - Thick | 100 | 54.8256 | 54.8256 | 2031-01-25 13:35 | 2031-02-10 04:39 | 857387.7477 | 857388 | [7 empty] | 0 | 0 | 29.06 | 8.93 | 5592.93
TS6060#1 | CP\06\002\B | CP | 6 | 2 | B | 8 Coal Mining | 51.2 | 0 | 51.2 | 2031-01-25 13:35 | 2031-01-29 02:55 | 115487.3513 | [6 empty] | 115487 | 81938 | 2.09 | 0 | 0 | 9.52 | 5566
TS5500Exc | SC\52\024\D | SC | 52 | 24 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-01-27 12:54 | 2031-02-01 11:37 | 149538.4773 | [6 empty] | 149538 | 112209 | 4.74 | 0 | 0 | 6.48 | 5844
TS Fleet 5 | CP\06\002\D | CP | 6 | 2 | D | 1 Prestrip - Thick | 29.8583 | 29.8583 | 29.8583 | 2031-01-29 02:55 | 2031-02-08 17:16 | 498544.8634 | 498545 | [7 empty] | 0 | 0 | 16.43 | 5.71 | 5904.07
TS6060#1 | CP\06\002\D | CP | 6 | 2 | D | 1 Prestrip - Thick | 34.2603 | 34.2603 | 34.2603 | 2031-01-29 02:55 | 2031-02-21 05:20 | 572046.5162 | 572047 | [7 empty] | 0 | 0 | 18.86 | 5.71 | 5904.07
PH4100A | SC\53\021\D | SC | 53 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2031-01-31 11:19 | 2031-02-24 13:52 | 1060651.908 | 1060652 | [7 empty] | 0 | 0 | 49.08 | 7.22 | 5779.76
TS5500Exc | CP\05\002\D | CP | 5 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2031-02-01 11:37 | 2031-02-07 23:51 | 138173.7938 |  |  | 138174 | [5 empty] | 0 | 0 | 0 | 5.79 | 5897.46
TS5500Exc | CP\05\002\D | CP | 5 | 2 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-02-07 23:51 | 2031-02-13 19:39 | 176084.8831 | [6 empty] | 176085 | 126060 | 5.02 | 0 | 0 | 5.79 | 5897
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 15d 00:24 |  | 15d 00:24 | 2031-02-08 17:16 | 2031-02-23 17:40
PH4100XPC#1 | CP\06\002\D | CP | 6 | 2 | D | 1 Prestrip - Thick | 100 | 35.8814 | 35.8814 | 2031-02-10 04:39 | 2031-02-21 05:20 | 599113.0011 | 599113 | [7 empty] | 0 | 0 | 19.75 | 5.71 | 5904.07
TS5500Exc | CP\06\003\B | CP | 6 | 3 | B | 8 Coal Mining | 58.4 | 0 | 58.4 | 2031-02-13 19:39 | 2031-02-17 14:30 | 114438.1827 | [6 empty] | 114438 | 81790 | 2.72 | 0 | 0 | 8.93 | 5593
TS5500Exc | SC\53\020\D | SC | 53 | 20 | D | 7 PostStrip | 100 | 0 | 100 | 2031-02-17 14:30 | 2031-02-23 09:40 | 123074.2899 |  |  | 123074 | [5 empty] | 0 | 0 | 0 | 7.37 | 5764.4
PH4100XPC#1 | CP\06\004\B | CP | 6 | 4 | B | 1 Prestrip - Thick | 100 | 54.43 | 54.43 | 2031-02-21 05:20 | 2031-03-09 02:29 | 857516.8429 | 857517 | [7 empty] | 0 | 0 | 28.65 | 8.52 | 5613.9
TS6060#1 | CP\06\003\B | CP | 6 | 3 | B | 8 Coal Mining | 41.6 | 0 | 41.6 | 2031-02-21 05:20 | 2031-02-23 17:40 | 81668.4304 | [6 empty] | 81668 | 58369 | 1.94 | 0 | 0 | 8.93 | 5593
TS5500Exc | SC\53\020\D | SC | 53 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-02-23 09:40 | 2031-02-28 06:12 | 146796.4572 | [6 empty] | 146796 | 109535 | 4.56 | 0 | 0 | 7.37 | 5764
TS Fleet 5 | CP\06\003\D | CP | 6 | 3 | D | 1 Prestrip - Thick | 28.2321 | 28.2321 | 28.2321 | 2031-02-23 17:40 | 2031-03-04 14:46 | 417658.1529 | 417658 | [7 empty] | 0 | 0 | 15.39 | 6.45 | 5839.22
TS6060#1 | CP\06\003\D | CP | 6 | 3 | D | 1 Prestrip - Thick | 37.8407 | 37.8407 | 37.8407 | 2031-02-23 17:40 | 2031-03-18 08:14 | 559804.9978 | 559805 | [7 empty] | 0 | 0 | 20.63 | 6.45 | 5839.22
PH4100A | SC\53\022\D | SC | 53 | 22 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2031-02-24 13:52 | 2031-03-19 15:19 | 1005208.586 | 1005209 | [7 empty] | 0 | 0 | 46.87 | 7.22 | 5779.08
TS5500Exc | CP\05\003\D | CP | 5 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2031-02-28 06:12 | 2031-03-07 07:14 | 149488.4675 |  |  | 149488 | [5 empty] | 0 | 0 | 0 | 6.48 | 5836.58
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 16d 20:58 |  | 16d 20:58 | 2031-03-04 14:46 | 2031-03-21 11:44
TS5500Exc | CP\05\003\D | CP | 5 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-03-07 07:14 | 2031-03-14 09:01 | 213855.5465 | [6 empty] | 213856 | 152392 | 5.08 | 0 | 0 | 6.48 | 5837
PH4100XPC#1 | CP\06\003\D | CP | 6 | 3 | D | 1 Prestrip - Thick | 100 | 33.9272 | 33.9272 | 2031-03-09 02:29 | 2031-03-18 08:14 | 501909.5527 | 501910 | [7 empty] | 0 | 0 | 18.5 | 6.45 | 5839.22
TS5500Exc | CP\06\004\B | CP | 6 | 4 | B | 8 Coal Mining | 45 | 0 | 45 | 2031-03-14 09:01 | 2031-03-17 03:21 | 83550.3578 | [6 empty] | 83550 | 59916 | 2 | 0 | 0 | 8.52 | 5614
TS5500Exc | SC\53\021\D | SC | 53 | 21 | D | 7 PostStrip | 100 | 0 | 100 | 2031-03-17 03:21 | 2031-03-22 20:19 | 121139.4355 |  |  | 121139 | [5 empty] | 0 | 0 | 0 | 7.22 | 5779.76
PH4100XPC#1 | CP\06\005\B | CP | 6 | 5 | B | 1 Prestrip - Thick | 100 | 54.6866 | 54.6866 | 2031-03-18 08:14 | 2031-04-06 07:26 | 1034763.462 | 1034763 | [7 empty] | 0 | 0 | 34.41 | 8.54 | 5610.71
TS6060#1 | CP\06\004\B | CP | 6 | 4 | B | 8 Coal Mining | 55 | 0 | 55 | 2031-03-18 08:14 | 2031-03-21 11:44 | 102196.9502 | [6 empty] | 102197 | 73287 | 2.44 | 0 | 0 | 8.52 | 5614
PH4100A | SC\53\023\D | SC | 53 | 23 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2031-03-19 15:19 | 2031-04-19 03:45 | 1318886.716 | 1318887 | [7 empty] | 0 | 0 | 44.69 | 6.89 | 5808.07
TS Fleet 5 | CP\06\004\D | CP | 6 | 4 | D | 1 Prestrip - Thick | 0.94895 | 0.94895 | 0.94895 | 2031-03-21 11:44 | 2031-03-21 18:41 | 13603.3483 | 13603 | [7 empty] | 0 | 0 | 0.5 | 6.29 | 5853.29
TS6060#1 | CP\06\004\D | CP | 6 | 4 | D | 1 Prestrip - Thick | 41.8077 | 41.8077 | 41.8077 | 2031-03-21 11:44 | 2031-04-14 16:35 | 599316.505 | 599317 | [7 empty] | 0 | 0 | 21.9 | 6.29 | 5853.29
TS Fleet 5 | CP\06\004\D | CP | 6 | 4 | D | 1 Prestrip - Thick | 25.4814 | 25.4814 | 25.4814 | 2031-03-21 18:41 | 2031-03-29 13:03 | 365277.838 | 365278 | [7 empty] | 0 | 0 | 13.35 | 6.29 | 5853.29
TS5500Exc | SC\53\021\D | SC | 53 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-03-22 20:19 | 2031-03-27 23:25 | 155062.0041 | [6 empty] | 155062 | 115984 | 4.83 | 0 | 0 | 7.22 | 5780
TS5500Exc | CP\05\004\D | CP | 5 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2031-03-27 23:25 | 2031-04-04 02:49 | 151584.0568 |  |  | 151584 | [5 empty] | 0 | 0 | 0 | 6.28 | 5854.07
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 18d 23:32 |  | 18d 23:32 | 2031-03-29 13:03 | 2031-04-17 12:34
TS5500Exc | CP\05\004\D | CP | 5 | 4 | D | 8 Coal Mining | 83.3 | 0 | 83.3 | 2031-04-04 02:49 | 2031-04-09 21:55 | 175217.6457 | [6 empty] | 175218 | 126045 | 4.2 | 0 | 0 | 6.28 | 5854
PH4100XPC#1 | CP\06\004\D | CP | 6 | 4 | D | 1 Prestrip - Thick | 100 | 31.762 | 31.762 | 2031-04-06 07:26 | 2031-04-14 16:35 | 455310.3667 | 455310 | [7 empty] | 0 | 0 | 16.64 | 6.29 | 5853.29
TS5500Exc | CP\06\005\B | CP | 6 | 5 | B | 8 Coal Mining | 40.6 | 0 | 40.6 | 2031-04-09 21:55 | 2031-04-11 23:53 | 62917.9833 | [6 empty] | 62918 | 44807 | 1.49 | 0 | 0 | 8.54 | 5611
TS5500Exc | SC\53\022\D | SC | 53 | 22 | D | 7 PostStrip | 100 | 0 | 100 | 2031-04-11 23:53 | 2031-04-17 16:34 | 120885.9777 |  |  | 120886 | [5 empty] | 0 | 0 | 0 | 7.22 | 5779.08
PH4100XPC#1 | CP\07\001\B | CP | 7 | 1 | B | 1 Prestrip - Thick | 100 | 54.3113 | 54.3113 | 2031-04-14 16:35 | 2031-04-17 20:13 | 169357.9315 | 169358 | [7 empty] | 0 | 0 | 11.87 | 9.14 | 5596.2
TS6060#1 | CP\06\005\B | CP | 6 | 5 | B | 8 Coal Mining | 59.4 | 0 | 59.4 | 2031-04-14 16:35 | 2031-04-17 12:34 | 92019.7445 | [6 empty] | 92020 | 65531 | 2.18 | 0 | 0 | 8.54 | 5611
TS Fleet 5 | CP\06\005\D | CP | 6 | 5 | D | 1 Prestrip - Thick | 36.171 | 36.171 | 36.171 | 2031-04-17 12:34 | 2031-04-28 14:36 | 521396.9188 | 521397 | [7 empty] | 0 | 0 | 19.1 | 6.15 | 5865.38
TS6060#1 | CP\06\005\D | CP | 6 | 5 | D | 1 Prestrip - Thick | 20.3615 | 20.3615 | 20.3615 | 2031-04-17 12:34 | 2031-04-29 09:02 | 293507.4677 | 293507 | [7 empty] | 0 | 0 | 10.75 | 6.15 | 5865.38
TS5500Exc | SC\53\022\D | SC | 53 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-04-17 16:34 | 2031-04-22 17:12 | 151958.8981 | [6 empty] | 151959 | 113571 | 4.73 | 0 | 0 | 7.22 | 5779
PH4100XPC#1 | CP\06\005\D | CP | 6 | 5 | D | 1 Prestrip - Thick | 100 | 43.4675 | 43.4675 | 2031-04-17 20:13 | 2031-04-29 09:02 | 626574.8496 | 626575 | [7 empty] | 0 | 0 | 22.96 | 6.15 | 5865.38
PH4100A | SC\54\017\D | SC | 54 | 17 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-04-19 03:45 | 2031-04-19 03:45 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\54\018\D | SC | 54 | 18 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-04-19 03:45 | 2031-04-19 03:45 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\54\019\D | SC | 54 | 19 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-04-19 03:45 | 2031-04-19 03:45 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\54\020\D | SC | 54 | 20 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2031-04-19 03:45 | 2031-05-15 00:51 | 1158897.603 | 1158898 | [7 empty] | 0 | 0 | 54.39 | 7.27 | 5773.21
TS5500Exc | CP\07\001\B | CP | 7 | 1 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2031-04-22 17:12 | 2031-04-23 13:05 | 25048.1874 | [6 empty] | 25048 | 17580 | 1.47 | 0 | 0 | 9.14 | 5596
TS5500Exc | CP\05\005\D | CP | 5 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2031-04-23 13:05 | 2031-04-30 15:35 | 150781.118 |  |  | 150781 | [5 empty] | 0 | 0 | 0 | 6.13 | 5867.29
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 2d 16:22 |  | 2d 16:22 | 2031-04-28 14:36 | 2031-05-01 06:58
PH4100XPC#1 | CP\07\002\B | CP | 7 | 2 | B | 1 Prestrip - Thick | 100 | 54.6356 | 54.6356 | 2031-04-29 09:02 | 2031-05-10 14:45 | 611844.319 | 611844 | [7 empty] | 0 | 0 | 20.34 | 9.59 | 5557.75
TS6060#1 | CP\05\004\D | CP | 5 | 4 | D | 8 Coal Mining | 16.7 | 0 | 16.7 | 2031-04-29 09:02 | 2031-04-30 11:05 | 35244.995 | [6 empty] | 35245 | 25354 | 0.85 | 0 | 0 | 6.28 | 5854
TS6060#1 | CP\07\001\B | CP | 7 | 1 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2031-04-30 11:05 | 2031-05-01 06:58 | 26913.478 | [6 empty] | 26913 | 18890 | 1.58 | 0 | 0 | 9.14 | 5596
TS5500Exc | CP\05\005\D | CP | 5 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-04-30 15:35 | 2031-05-07 13:42 | 209248.2499 | [6 empty] | 209248 | 149988 | 5 | 0 | 0 | 6.13 | 5867
TS Fleet 5 | CP\07\001\D | CP | 7 | 1 | D | 1 Prestrip - Thick | 12.8796 | 12.8796 | 12.8796 | 2031-05-01 06:58 | 2031-05-02 06:27 | 46044.8569 | 46045 | [7 empty] | 0 | 0 | 6.98 | 5.34 | 5936.65
TS6060#1 | CP\07\001\D | CP | 7 | 1 | D | 1 Prestrip - Thick | 71.6427 | 71.6427 | 71.6427 | 2031-05-01 06:58 | 2031-05-11 15:12 | 256124.3174 | 256124 | [7 empty] | 0 | 0 | 38.83 | 5.34 | 5936.65
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 16d 02:56 |  | 16d 02:56 | 2031-05-02 06:27 | 2031-05-18 09:23
TS5500Exc | SC\53\023\D | SC | 53 | 23 | D | 7 PostStrip | 22.311 | 0 | 22.311 | 2031-05-07 13:42 | 2031-05-09 07:54 | 37313.336 |  |  | 37313 | [5 empty] | 0 | 0 | 0 | 6.89 | 5808.07
TS5500Exc | SC\53\023\D | SC | 53 | 23 | D | 7 PostStrip | 77.689 | 0 | 77.689 | 2031-05-09 07:54 | 2031-05-15 10:48 | 129928.4422 |  |  | 129928 | [5 empty] | 0 | 0 | 0 | 6.89 | 5808.07
PH4100XPC#1 | CP\07\001\D | CP | 7 | 1 | D | 1 Prestrip - Thick | 100 | 15.4777 | 15.4777 | 2031-05-10 14:45 | 2031-05-11 15:12 | 55333.1795 | 55333 | [7 empty] | 0 | 0 | 8.39 | 5.34 | 5936.65
PH4100XPC#1 | CP\07\003\B | CP | 7 | 3 | B | 1 Prestrip - Thick | 100 | 54.9622 | 54.9622 | 2031-05-11 15:12 | 2031-05-27 22:12 | 898754.4457 | 898754 | [7 empty] | 0 | 0 | 30.67 | 8.96 | 5590.85
TS6060#1 | CP\07\002\B | CP | 7 | 2 | B | 8 Coal Mining | 54.8 | 0 | 54.8 | 2031-05-11 15:12 | 2031-05-14 22:52 | 107839.1765 | [6 empty] | 107839 | 76832 | 2.55 | 0 | 0 | 9.59 | 5558
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 10:31 |  | 3d 10:31 | 2031-05-14 22:52 | 2031-05-18 09:23
PH4100A | SC\54\021\D | SC | 54 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2031-05-15 00:51 | 2031-06-09 15:04 | 1150964.184 | 1150964 | [7 empty] | 0 | 0 | 53.96 | 7.07 | 5792.3
TS5500Exc | CP\07\002\B | CP | 7 | 2 | B | 8 Coal Mining | 45.2 | 0 | 45.2 | 2031-05-15 10:48 | 2031-05-18 09:23 | 88906.5827 | [6 empty] | 88907 | 63343 | 2.1 | 0 | 0 | 9.59 | 5558
TS Fleet 5 | CP\07\002\D | CP | 7 | 2 | D | 1 Prestrip - Thick | 31.2407 | 31.2407 | 31.2407 | 2031-05-18 09:23 | 2031-05-28 10:04 | 471717.8181 | 471718 | [7 empty] | 0 | 0 | 17.28 | 5.73 | 5901.99
TS6060#1 | CP\07\002\D | CP | 7 | 2 | D | 1 Prestrip - Thick | 36.5514 | 32.2689 | 32.2689 | 2031-05-18 09:23 | 2031-06-07 01:37 | 487241.9449 | 487242 | [7 empty] | 0 | 0 | 17.85 | 5.73 | 5901.99
TS5500Exc | SC\53\023\D | SC | 53 | 23 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-05-18 09:23 | 2031-05-24 11:19 | 183820.935 | [6 empty] | 183821 | 138153 | 4.73 | 0 | 0 | 6.89 | 5808
TS5500Exc | CP\06\002\D | CP | 6 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2031-05-24 11:19 | 2031-06-01 07:59 | 166845.6789 |  |  | 166846 | [5 empty] | 0 | 0 | 0 | 5.71 | 5904.07
PH4100XPC#1 | CP\07\002\D | CP | 7 | 2 | D | 1 Prestrip - Thick | 100 | 36.4904 | 36.4904 | 2031-05-27 22:12 | 2031-06-07 01:37 | 550985.2634 | 550985 | [7 empty] | 0 | 0 | 20.19 | 5.73 | 5901.99
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 10d 10:01 |  | 10d 10:01 | 2031-05-28 10:04 | 2031-06-07 20:04
TS5500Exc | CP\07\003\B | CP | 7 | 3 | B | 8 Coal Mining | 100 | 0 | 100 | 2031-06-01 07:59 | 2031-06-07 20:04 | 196615.4166 | [6 empty] | 196615 | 140521 | 4.67 | 0 | 0 | 8.96 | 5591
PH4100XPC#1 | CP\07\004\B | CP | 7 | 4 | B | 1 Prestrip - Thick | 100 | 43.596 | 43.596 | 2031-06-07 01:37 | 2031-06-20 08:41 | 718378.5336 | 718379 | [7 empty] | 0 | 0 | 24.06 | 8.43 | 5622.47
TS6060#1 | CP\06\002\D | CP | 6 | 2 | D | 8 Coal Mining | 13.5 | 0 | 13.5 | 2031-06-07 01:37 | 2031-06-07 23:30 | 29633.5569 | [6 empty] | 29634 | 21222 | 0.67 | 0 | 0 | 5.71 | 5904
TS Fleet 5 | CP\07\003\D | CP | 7 | 3 | D | 1 Prestrip - Thick | 36.37 | 36.37 | 36.37 | 2031-06-07 20:04 | 2031-06-19 06:50 | 538535.2438 | 538535 | [7 empty] | 0 | 0 | 19.8 | 6.4 | 5842.93
TS5500Exc | CP\06\002\D | CP | 6 | 2 | D | 8 Coal Mining | 86.5 | 0 | 86.5 | 2031-06-07 20:04 | 2031-06-14 03:24 | 190621.5857 | [6 empty] | 190622 | 136510 | 4.31 | 0 | 0 | 5.71 | 5904
TS6060#1 | CP\07\003\D | CP | 7 | 3 | D | 1 Prestrip - Thick | 19.9232 | 19.9232 | 19.9232 | 2031-06-07 23:30 | 2031-06-19 21:25 | 295005.2983 | 295005 | [7 empty] | 0 | 0 | 10.85 | 6.4 | 5842.93
PH4100A | SC\54\022\D | SC | 54 | 22 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2031-06-09 15:04 | 2031-07-14 03:07 | 1506340.273 | 1506340 | [7 empty] | 0 | 0 | 44.08 | 7.04 | 5795.85
TS5500Exc | SC\54\020\D | SC | 54 | 20 | D | 7 PostStrip | 100 | 0 | 100 | 2031-06-14 03:24 | 2031-06-19 16:54 | 118060.5007 |  |  | 118061 | [5 empty] | 0 | 0 | 0 | 7.27 | 5773.21
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 8d 03:37 |  | 8d 03:37 | 2031-06-19 06:50 | 2031-06-27 10:27
TS5500Exc | SC\54\020\D | SC | 54 | 20 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-06-19 16:54 | 2031-06-24 11:22 | 144180.6382 | [6 empty] | 144181 | 107752 | 4.49 | 0 | 0 | 7.27 | 5773
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 11:16 |  | 0d 11:16 | 2031-06-19 21:25 | 2031-06-20 08:41
PH4100XPC#1 | CP\07\003\D | CP | 7 | 3 | D | 1 Prestrip - Thick | 100 | 43.7067 | 43.7067 | 2031-06-20 08:41 | 2031-07-02 06:36 | 647170.3748 | 647170 | [7 empty] | 0 | 0 | 23.8 | 6.4 | 5842.93
TS6060#1 | CP\07\004\B | CP | 7 | 4 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2031-06-20 08:41 | 2031-06-23 07:46 | 96204.8988 | [6 empty] | 96205 | 69022 | 2.3 | 0 | 0 | 8.43 | 5622
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 02:41 |  | 4d 02:41 | 2031-06-23 07:46 | 2031-06-27 10:27
TS5500Exc | CP\07\004\B | CP | 7 | 4 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2031-06-24 11:22 | 2031-06-27 10:27 | 89537.2326 | [6 empty] | 89537 | 64238 | 2.14 | 0 | 0 | 8.43 | 5622
TS Fleet 5 | CP\07\004\D | CP | 7 | 4 | D | 1 Prestrip - Thick | 33.7367 | 33.7367 | 33.7367 | 2031-06-27 10:27 | 2031-07-07 17:35 | 484385.5964 | 484386 | [7 empty] | 0 | 0 | 17.75 | 6.29 | 5853.22
TS6060#1 | CP\07\004\D | CP | 7 | 4 | D | 1 Prestrip - Thick | 42.0011 | 26.4812 | 26.4812 | 2031-06-27 10:27 | 2031-07-12 18:56 | 380212.0415 | 380212 | [7 empty] | 0 | 0 | 13.93 | 6.29 | 5853.22
TS5500Exc | CP\06\003\D | CP | 6 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2031-06-27 10:27 | 2031-07-04 11:19 | 149342.8151 |  |  | 149343 | [5 empty] | 0 | 0 | 0 | 6.45 | 5839.22
PH4100XPC#1 | CP\07\004\D | CP | 7 | 4 | D | 1 Prestrip - Thick | 100 | 39.7821 | 39.7821 | 2031-07-02 06:36 | 2031-07-12 18:56 | 571183.4605 | 571183 | [7 empty] | 0 | 0 | 20.93 | 6.29 | 5853.22
TS5500Exc | CP\06\003\D | CP | 6 | 3 | D | 8 Coal Mining | 99.9 | 0 | 99.9 | 2031-07-04 11:19 | 2031-07-11 11:08 | 211399.7014 | [6 empty] | 211400 | 150550 | 5.02 | 0 | 0 | 6.45 | 5839
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 30d 18:01 |  | 30d 18:01 | 2031-07-07 17:35 | 2031-08-07 11:36
TS5500Exc | SC\54\021\D | SC | 54 | 21 | D | 7 PostStrip | 100 | 0 | 100 | 2031-07-11 11:08 | 2031-07-17 00:53 | 118281.1719 |  |  | 118281 | [5 empty] | 0 | 0 | 0 | 7.07 | 5792.3
PH4100XPC#1 | CP\07\005\B | CP | 7 | 5 | B | 1 Prestrip - Thick | 100 | 54.7249 | 54.7249 | 2031-07-12 18:56 | 2031-08-01 15:35 | 1085158.271 | 1085158 | [7 empty] | 0 | 0 | 36.1 | 8.55 | 5609.62
TS6060#1 | CP\06\003\D | CP | 6 | 3 | D | 8 Coal Mining | 0.1 | 0 | 0.1 | 2031-07-12 18:56 | 2031-07-12 19:08 | 261.618 | [6 empty] | 262 | 186 | 0.01 | 0 | 0 | 6.45 | 5839
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 16d 10:01 |  | 16d 10:01 | 2031-07-12 19:08 | 2031-07-29 05:09
PH4100A | SC\55\017\D | SC | 55 | 17 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-07-14 03:07 | 2031-07-14 03:07 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\55\018\D | SC | 55 | 18 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-07-14 03:07 | 2031-07-14 03:07 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\55\019\D | SC | 55 | 19 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-07-14 03:07 | 2031-07-14 03:07 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\55\020\D | SC | 55 | 20 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-07-14 03:07 | 2031-07-14 03:07 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\55\021\D | SC | 55 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2031-07-14 03:07 | 2031-08-05 23:17 | 1032787.05 | 1032787 | [7 empty] | 0 | 0 | 47.34 | 6.9 | 5807.2
TS5500Exc | SC\54\021\D | SC | 54 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-07-17 00:53 | 2031-07-22 02:06 | 152689.4102 | [6 empty] | 152689 | 114572 | 4.77 | 0 | 0 | 7.07 | 5792
TS5500Exc | CP\06\004\D | CP | 6 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2031-07-22 02:06 | 2031-07-29 05:09 | 151278.2571 |  |  | 151278 | [5 empty] | 0 | 0 | 0 | 6.29 | 5853.29
TS6060#1 | CP\06\004\D | CP | 6 | 4 | D | 8 Coal Mining | 4.8 | 0 | 4.8 | 2031-07-29 05:09 | 2031-07-29 12:34 | 10031.8392 | [6 empty] | 10032 | 7211 | 0.24 | 0 | 0 | 6.29 | 5853
TS5500Exc | CP\06\004\D | CP | 6 | 4 | D | 8 Coal Mining | 95.2 | 0 | 95.2 | 2031-07-29 05:09 | 2031-08-04 20:16 | 200424.3327 | [6 empty] | 200424 | 144064 | 4.8 | 0 | 0 | 6.29 | 5853
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 03:01 |  | 3d 03:01 | 2031-07-29 12:34 | 2031-08-01 15:35
PH4100XPC#1 | CP\08\001\B | CP | 8 | 1 | B | 1 Prestrip - Thick | 100 | 54.2836 | 54.2836 | 2031-08-01 15:35 | 2031-08-05 14:19 | 211886.2129 | 211886 | [7 empty] | 0 | 0 | 13.06 | 9.04 | 5602.34
TS6060#1 | CP\07\005\B | CP | 7 | 5 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2031-08-01 15:35 | 2031-08-04 06:55 | 85711.1943 | [6 empty] | 85711 | 61156 | 2.03 | 0 | 0 | 8.55 | 5610
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 07:24 |  | 1d 07:24 | 2031-08-04 06:55 | 2031-08-05 14:19
TS5500Exc | CP\07\005\B | CP | 7 | 5 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2031-08-04 20:16 | 2031-08-07 11:36 | 79770.8145 | [6 empty] | 79771 | 56917 | 1.89 | 0 | 0 | 8.55 | 5610
PH4100XPC#1 | CP\08\002\B | CP | 8 | 2 | B | 1 Prestrip - Thick | 100 | 54.6426 | 54.6426 | 2031-08-05 14:19 | 2031-08-17 12:10 | 648646.8631 | 648647 | [7 empty] | 0 | 0 | 21.67 | 9.48 | 5565.21
TS6060#1 | CP\08\001\B | CP | 8 | 1 | B | 8 Coal Mining | 4.5 | 0 | 4.5 | 2031-08-05 14:19 | 2031-08-05 16:31 | 2980.5643 | [6 empty] | 2981 | 2105 | 0.16 | 0 | 0 | 9.04 | 5602
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 19:05 |  | 1d 19:05 | 2031-08-05 16:31 | 2031-08-07 11:36
PH4100A | SC\55\022\D | SC | 55 | 22 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2031-08-05 23:17 | 2031-08-24 08:43 | 808409.8978 | 808410 | [7 empty] | 0 | 0 | 45.77 | 6.86 | 5810.85
TS Fleet 5 | CP\07\005\D | CP | 7 | 5 | D | 1 Prestrip - Thick | 35.5563 | 35.5563 | 35.5563 | 2031-08-07 11:36 | 2031-08-18 08:44 | 511831.6156 | 511832 | [7 empty] | 0 | 0 | 18.76 | 6.17 | 5863.59
TS6060#1 | CP\07\005\D | CP | 7 | 5 | D | 1 Prestrip - Thick | 21.7149 | 21.7149 | 21.7149 | 2031-08-07 11:36 | 2031-08-20 02:33 | 312584.5885 | 312585 | [7 empty] | 0 | 0 | 11.45 | 6.17 | 5863.59
TS5500Exc | CP\08\001\B | CP | 8 | 1 | B | 8 Coal Mining | 95.5 | 0 | 95.5 | 2031-08-07 11:36 | 2031-08-09 13:48 | 63220.2877 | [6 empty] | 63220 | 44654 | 3.32 | 0 | 0 | 9.04 | 5602
TS5500Exc | SC\54\022\D | SC | 54 | 22 | D | 7 PostStrip | 100 | 0 | 100 | 2031-08-09 13:48 | 2031-08-18 17:12 | 194044.6867 |  |  | 194045 | [5 empty] | 0 | 0 | 0 | 7.04 | 5795.85
PH4100XPC#1 | CP\07\005\D | CP | 7 | 5 | D | 1 Prestrip - Thick | 100 | 42.7288 | 42.7288 | 2031-08-17 12:10 | 2031-08-28 19:54 | 615080.0014 | 615080 | [7 empty] | 0 | 0 | 22.54 | 6.17 | 5863.59
TS Fleet 5 | CP\08\001\D | CP | 8 | 1 | D | 1 Prestrip - Thick | 21.3064 | 21.3064 | 21.3064 | 2031-08-18 08:44 | 2031-08-20 14:34 | 105507.0209 | 105507 | [7 empty] | 0 | 0 | 11.63 | 5.35 | 5935.2
TS5500Exc | CP\08\002\B | CP | 8 | 2 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2031-08-18 17:12 | 2031-08-21 20:36 | 94976.3989 | [6 empty] | 94976 | 67703 | 2.25 | 0 | 0 | 9.48 | 5565
TS6060#1 | CP\08\001\D | CP | 8 | 1 | D | 1 Prestrip - Thick | 67.2511 | 54.6032 | 54.6032 | 2031-08-20 02:33 | 2031-08-31 00:37 | 270389.6252 | 270390 | [7 empty] | 0 | 0 | 29.81 | 5.35 | 5935.2
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 13d 13:26 |  | 13d 13:26 | 2031-08-20 14:34 | 2031-09-03 04:01
TS5500Exc | SC\54\022\D | SC | 54 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-08-21 20:36 | 2031-08-29 07:10 | 224908.9336 | [6 empty] | 224909 | 168767 | 4.87 | 0 | 0 | 7.04 | 5796
PH4100A | SC\56\018\D | SC | 56 | 18 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-08-24 08:43 | 2031-08-24 08:43 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\56\019\D | SC | 56 | 19 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-08-24 08:43 | 2031-08-24 08:43 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\56\020\D | SC | 56 | 20 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-08-24 08:43 | 2031-08-24 08:43 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | SC\56\021\D | SC | 56 | 21 | D | 1 Prestrip - Thick | 100 | 100 | 100 | 2031-08-24 08:43 | 2031-09-21 02:00 | 1217632.679 | 1217633 | [7 empty] | 0 | 0 | 45.77 | 6.82 | 5814.16
PH4100XPC#1 | CP\08\001\D | CP | 8 | 1 | D | 1 Prestrip - Thick | 100 | 24.0904 | 24.0904 | 2031-08-28 19:54 | 2031-08-31 00:37 | 119293.5275 | 119294 | [7 empty] | 0 | 0 | 13.15 | 5.35 | 5935.2
TS5500Exc | SC\55\021\D | SC | 55 | 21 | D | 7 PostStrip | 100 | 0 | 100 | 2031-08-29 07:10 | 2031-09-04 02:02 | 122824.5908 |  |  | 122825 | [5 empty] | 0 | 0 | 0 | 6.9 | 5807.2
PH4100XPC#1 | CP\08\003\B | CP | 8 | 3 | B | 1 Prestrip - Thick | 100 | 55.0867 | 55.0867 | 2031-08-31 00:37 | 2031-09-16 21:23 | 935126.5033 | 935127 | [7 empty] | 0 | 0 | 31.74 | 8.95 | 5591.45
TS6060#1 | CP\08\002\B | CP | 8 | 2 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2031-08-31 00:37 | 2031-09-03 04:01 | 102049.1095 | [6 empty] | 102049 | 72745 | 2.42 | 0 | 0 | 9.48 | 5565
TS Fleet 5 | CP\08\002\D | CP | 8 | 2 | D | 1 Prestrip - Thick | 28.3656 | 28.3656 | 28.3656 | 2031-09-03 04:01 | 2031-09-12 06:28 | 428165.1028 | 428165 | [7 empty] | 0 | 0 | 15.7 | 5.73 | 5901.94
TS6060#1 | CP\08\002\D | CP | 8 | 2 | D | 1 Prestrip - Thick | 37.5467 | 34.8271 | 34.8271 | 2031-09-03 04:01 | 2031-09-24 09:30 | 525697.9596 | 525698 | [7 empty] | 0 | 0 | 19.28 | 5.73 | 5901.94
TS5500Exc | SC\55\021\D | SC | 55 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-09-04 02:02 | 2031-09-09 00:49 | 149612.014 | [6 empty] | 149612 | 112800 | 4.7 | 0 | 0 | 6.9 | 5807
TS5500Exc | CP\06\005\D | CP | 6 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2031-09-09 00:49 | 2031-09-16 03:15 | 150728.7933 |  |  | 150729 | [5 empty] | 0 | 0 | 0 | 6.15 | 5865.38
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 17d 04:29 |  | 17d 04:29 | 2031-09-12 06:28 | 2031-09-29 10:57
TS5500Exc | CP\06\005\D | CP | 6 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-09-16 03:15 | 2031-09-23 01:40 | 209624.2816 | [6 empty] | 209624 | 150154 | 5.01 | 0 | 0 | 6.15 | 5865
PH4100XPC#1 | CP\08\002\D | CP | 8 | 2 | D | 1 Prestrip - Thick | 100 | 27.01 | 27.01 | 2031-09-16 21:23 | 2031-09-24 09:30 | 407702.5909 | 407703 | [7 empty] | 0 | 0 | 14.95 | 5.73 | 5901.94
PH4100A | SC\62\001\D | SC | 62 | 1 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-09-21 02:00 | 2031-09-21 02:00 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\03\006\B | CP | 3 | 6 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-09-21 02:00 | 2031-09-21 02:00 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\03\006\D | CP | 3 | 6 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-09-21 02:00 | 2031-09-21 02:00 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\04\006\B | CP | 4 | 6 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-09-21 02:00 | 2031-09-21 02:00 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\04\006\D | CP | 4 | 6 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-09-21 02:00 | 2031-09-21 02:00 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\05\006\B | CP | 5 | 6 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-09-21 02:00 | 2031-09-21 02:00 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\05\006\D | CP | 5 | 6 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-09-21 02:00 | 2031-09-21 02:00 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\06\006\B | CP | 6 | 6 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-09-21 02:00 | 2031-09-21 02:00 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\06\006\D | CP | 6 | 6 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-09-21 02:00 | 2031-09-21 02:00 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\07\006\B | CP | 7 | 6 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-09-21 02:00 | 2031-09-21 02:00 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\07\006\D | CP | 7 | 6 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-09-21 02:00 | 2031-09-21 02:00 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\08\002\D | CP | 8 | 2 | D | 1 Prestrip - Thick | 100 | 9.7972 | 9.7972 | 2031-09-21 02:00 | 2031-09-24 09:30 | 147884.1746 | 147884 | [7 empty] | 0 | 0 | 5.42 | 5.73 | 5901.94
TS5500Exc | CP\08\003\B | CP | 8 | 3 | B | 8 Coal Mining | 98.6 | 0 | 98.6 | 2031-09-23 01:40 | 2031-09-29 10:57 | 193074.389 | [6 empty] | 193074 | 137993 | 4.6 | 0 | 0 | 8.95 | 5591
PH4100A | CP\08\004\B | CP | 8 | 4 | B | 1 Prestrip - Thick | 100 | 30.4583 | 30.4583 | 2031-09-24 09:30 | 2031-10-06 01:58 | 520545.3012 | 520545 | [7 empty] | 0 | 0 | 17.46 | 8.2 | 5642.08
PH4100XPC#1 | CP\08\004\B | CP | 8 | 4 | B | 1 Prestrip - Thick | 100 | 37.0074 | 37.0074 | 2031-09-24 09:30 | 2031-10-06 01:58 | 632472.0956 | 632472 | [7 empty] | 0 | 0 | 21.21 | 8.2 | 5642.08
TS6060#1 | CP\08\003\B | CP | 8 | 3 | B | 8 Coal Mining | 1.4 | 0 | 1.4 | 2031-09-24 09:30 | 2031-09-24 11:28 | 2659.2336 | [6 empty] | 2659 | 1901 | 0.06 | 0 | 0 | 8.95 | 5591
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 23:29 |  | 4d 23:29 | 2031-09-24 11:28 | 2031-09-29 10:57
TS Fleet 5 | CP\08\003\D | CP | 8 | 3 | D | 1 Prestrip - Thick | 22.7758 | 22.7758 | 22.7758 | 2031-09-29 10:57 | 2031-10-06 15:03 | 337324.4525 | 337324 | [7 empty] | 0 | 0 | 12.39 | 6.36 | 5847.04
TS6060#1 | CP\08\003\D | CP | 8 | 3 | D | 1 Prestrip - Thick | 42.85 | 24.3166 | 24.3166 | 2031-09-29 10:57 | 2031-10-14 | 360144.4584 | 360144 | [7 empty] | 0 | 0 | 13.22 | 6.36 | 5847.04
TS5500Exc | SC\55\022\D | SC | 55 | 22 | D | 7 PostStrip | 100 | 0 | 100 | 2031-09-29 10:57 | 2031-10-04 03:44 | 99742.3532 |  |  | 99742 | [5 empty] | 0 | 0 | 0 | 6.86 | 5810.85
TS5500Exc | SC\55\022\D | SC | 55 | 22 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-10-04 03:44 | 2031-10-07 13:29 | 102977.5372 | [6 empty] | 102978 | 77643 | 4.81 | 0 | 0 | 6.86 | 5811
PH4100A | CP\08\003\D | CP | 8 | 3 | D | 1 Prestrip - Thick | 100 | 23.8651 | 23.8651 | 2031-10-06 01:58 | 2031-10-14 | 353457.9235 | 353458 | [7 empty] | 0 | 0 | 12.98 | 6.36 | 5847.04
PH4100XPC#1 | CP\08\003\D | CP | 8 | 3 | D | 1 Prestrip - Thick | 100 | 29.0425 | 29.0425 | 2031-10-06 01:58 | 2031-10-14 | 430139.2898 | 430139 | [7 empty] | 0 | 0 | 15.79 | 6.36 | 5847.04
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 9d 21:46 |  | 9d 21:46 | 2031-10-06 15:03 | 2031-10-16 12:49
TS5500Exc | CP\08\004\B | CP | 8 | 4 | B | 8 Coal Mining | 55.5 | 0 | 55.5 | 2031-10-07 13:29 | 2031-10-10 22:53 | 102524.4081 | [6 empty] | 102524 | 73572 | 2.45 | 0 | 0 | 8.2 | 5642
TS5500Exc | CP\07\001\D | CP | 7 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2031-10-10 22:53 | 2031-10-12 15:57 | 36329.2269 |  |  | 36329 | [5 empty] | 0 | 0 | 0 | 5.34 | 5936.65
TS5500Exc | CP\07\001\D | CP | 7 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-10-12 15:57 | 2031-10-14 00:12 | 40606.992 | [6 empty] | 40607 | 29212 | 4.98 | 0 | 0 | 5.34 | 5937
PH4100A | CP\08\005\B | CP | 8 | 5 | B | 1 Prestrip - Thick | 100 | 31.0466 | 31.0466 | 2031-10-14 | 2031-10-27 23:32 | 629218.4305 | 629218 | [7 empty] | 0 | 0 | 21.06 | 8.5 | 5614.12
PH4100XPC#1 | CP\08\005\B | CP | 8 | 5 | B | 1 Prestrip - Thick | 100 | 37.769 | 37.769 | 2031-10-14 | 2031-10-27 23:32 | 765460.5802 | 765461 | [7 empty] | 0 | 0 | 25.62 | 8.5 | 5614.12
TS6060#1 | CP\08\004\B | CP | 8 | 4 | B | 8 Coal Mining | 44.5 | 0 | 44.5 | 2031-10-14 | 2031-10-16 12:49 | 82321.1786 | [6 empty] | 82321 | 59074 | 1.97 | 0 | 0 | 8.2 | 5642
TS5500Exc | CP\07\002\D | CP | 7 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2031-10-14 00:12 | 2031-10-21 01:49 | 150015.4784 |  |  | 150015 | [5 empty] | 0 | 0 | 0 | 5.73 | 5901.99
TS Fleet 5 | CP\08\004\D | CP | 8 | 4 | D | 1 Prestrip - Thick | 21.4826 | 21.4826 | 21.4826 | 2031-10-16 12:49 | 2031-10-23 02:22 | 308798.029 | 308798 | [7 empty] | 0 | 0 | 11.35 | 6.29 | 5853.25
TS6060#1 | CP\08\004\D | CP | 8 | 4 | D | 1 Prestrip - Thick | 39.0312 | 31.4873 | 31.4873 | 2031-10-16 12:49 | 2031-11-03 19:29 | 452608.6614 | 452609 | [7 empty] | 0 | 0 | 16.64 | 6.29 | 5853.25
TS5500Exc | CP\07\002\D | CP | 7 | 2 | D | 8 Coal Mining | 81.6 | 0 | 81.6 | 2031-10-21 01:49 | 2031-10-26 16:14 | 169299.9423 | [6 empty] | 169300 | 121189 | 4.04 | 0 | 0 | 5.73 | 5902
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 15d 15:15 |  | 15d 15:15 | 2031-10-23 02:22 | 2031-11-07 17:37
TS5500Exc | SC\56\021\D | SC | 56 | 21 | D | 7 PostStrip | 100 | 0 | 100 | 2031-10-26 16:14 | 2031-11-02 18:04 | 150203.4938 |  |  | 150203 | [5 empty] | 0 | 0 | 0 | 6.82 | 5814.16
PH4100A | CP\08\004\D | CP | 8 | 4 | D | 1 Prestrip - Thick | 100 | 21.2139 | 21.2139 | 2031-10-27 23:32 | 2031-11-03 19:29 | 304935.2464 | 304935 | [7 empty] | 0 | 0 | 11.21 | 6.29 | 5853.25
PH4100XPC#1 | CP\08\004\D | CP | 8 | 4 | D | 1 Prestrip - Thick | 100 | 25.8162 | 25.8162 | 2031-10-27 23:32 | 2031-11-03 19:29 | 371089.8004 | 371090 | [7 empty] | 0 | 0 | 13.64 | 6.29 | 5853.25
TS5500Exc | CP\08\005\B | CP | 8 | 5 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2031-11-02 18:04 | 2031-11-05 12:05 | 83149.131 | [6 empty] | 83149 | 59447 | 1.98 | 0 | 0 | 8.5 | 5614
PH4100A | CP\08\006\B | CP | 8 | 6 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-11-03 19:29 | 2031-11-03 19:29 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\08\006\D | CP | 8 | 6 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-11-03 19:29 | 2031-11-03 19:29 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\08\007\B | CP | 8 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-11-03 19:29 | 2031-11-03 19:29 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\08\007\D | CP | 8 | 7 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2031-11-03 19:29 | 2031-11-03 19:29 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\09\001\B | CP | 9 | 1 | B | 1 Prestrip - Thick | 100 | 30.9549 | 30.9549 | 2031-11-03 19:29 | 2031-11-07 04:20 | 149188.8119 | 149189 | [7 empty] | 0 | 0 | 8.34 | 9.01 | 5603.17
PH4100XPC#1 | CP\09\001\B | CP | 9 | 1 | B | 1 Prestrip - Thick | 100 | 37.4462 | 37.4462 | 2031-11-03 19:29 | 2031-11-07 04:20 | 180474.1341 | 180474 | [7 empty] | 0 | 0 | 10.09 | 9.01 | 5603.17
TS6060#1 | CP\07\002\D | CP | 7 | 2 | D | 8 Coal Mining | 18.4 | 0 | 18.4 | 2031-11-03 19:29 | 2031-11-04 23:36 | 38066.2172 | [6 empty] | 38066 | 27249 | 0.91 | 0 | 0 | 5.73 | 5902
TS6060#1 | CP\08\005\B | CP | 8 | 5 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2031-11-04 23:36 | 2031-11-07 17:37 | 89341.0876 | [6 empty] | 89341 | 63873 | 2.13 | 0 | 0 | 8.5 | 5614
TS5500Exc | SC\56\021\D | SC | 56 | 21 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-11-05 12:05 | 2031-11-10 09:03 | 147350.0228 | [6 empty] | 147350 | 111366 | 4.72 | 0 | 0 | 6.82 | 5814
PH4100A | CP\09\002\B | CP | 9 | 2 | B | 1 Prestrip - Thick | 100 | 31.0403 | 31.0403 | 2031-11-07 04:20 | 2031-11-15 22:56 | 393098.3924 | 393098 | [7 empty] | 0 | 0 | 13.04 | 9.34 | 5575.02
PH4100XPC#1 | CP\09\002\B | CP | 9 | 2 | B | 1 Prestrip - Thick | 100 | 37.6374 | 37.6374 | 2031-11-07 04:20 | 2031-11-15 22:56 | 476644.9876 | 476645 | [7 empty] | 0 | 0 | 15.81 | 9.34 | 5575.02
TS Fleet 5 | CP\08\005\D | CP | 8 | 5 | D | 1 Prestrip - Thick | 23.519 | 23.519 | 23.519 | 2031-11-07 17:37 | 2031-11-14 21:58 | 337797.2761 | 337797 | [7 empty] | 0 | 0 | 12.39 | 6.19 | 5861.75
TS6060#1 | CP\09\001\B | CP | 9 | 1 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2031-11-07 17:37 | 2031-11-08 22:22 | 38902.7832 | [6 empty] | 38903 | 27511 | 1.84 | 0 | 0 | 9.01 | 5603
TS6060#1 | CP\08\005\D | CP | 8 | 5 | D | 1 Prestrip - Thick | 24.993 | 24.993 | 24.993 | 2031-11-08 22:22 | 2031-11-23 10:16 | 358968.066 | 358968 | [7 empty] | 0 | 0 | 13.16 | 6.19 | 5861.75
TS5500Exc | CP\09\001\B | CP | 9 | 1 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2031-11-10 09:03 | 2031-11-11 13:48 | 36206.5507 | [6 empty] | 36207 | 25604 | 1.72 | 0 | 0 | 9.01 | 5603
TS5500Exc | CP\07\003\D | CP | 7 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2031-11-11 13:48 | 2031-11-18 15:06 | 149720.9106 |  |  | 149721 | [5 empty] | 0 | 0 | 0 | 6.4 | 5842.93
TS Fleet 5 | CP\09\001\D | CP | 9 | 1 | D | 1 Prestrip - Thick | 28.916 | 28.916 | 28.916 | 2031-11-14 21:58 | 2031-11-18 12:23 | 169367.3858 | 169367 | [7 empty] | 0 | 0 | 15.61 | 5.38 | 5933.16
PH4100A | CP\08\005\D | CP | 8 | 5 | D | 1 Prestrip - Thick | 100 | 23.2248 | 23.2248 | 2031-11-15 22:56 | 2031-11-23 10:16 | 333571.7392 | 333572 | [7 empty] | 0 | 0 | 12.23 | 6.19 | 5861.75
PH4100XPC#1 | CP\08\005\D | CP | 8 | 5 | D | 1 Prestrip - Thick | 100 | 28.2633 | 28.2633 | 2031-11-15 22:56 | 2031-11-23 10:16 | 405938.8727 | 405939 | [7 empty] | 0 | 0 | 14.89 | 6.19 | 5861.75
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 6d 19:39 |  | 6d 19:39 | 2031-11-18 12:23 | 2031-11-25 08:01
TS5500Exc | CP\09\002\B | CP | 9 | 2 | B | 8 Coal Mining | 68.5 | 0 | 68.5 | 2031-11-18 15:06 | 2031-11-23 01:56 | 134571.6737 | [6 empty] | 134572 | 95986 | 3.2 | 0 | 0 | 9.34 | 5575
TS5500Exc | CP\07\003\D | CP | 7 | 3 | D | 8 Coal Mining | 75.9 | 0 | 75.9 | 2031-11-23 01:56 | 2031-11-28 08:07 | 158952.5709 | [6 empty] | 158953 | 113220 | 3.77 | 0 | 0 | 6.4 | 5843
PH4100A | CP\09\001\D | CP | 9 | 1 | D | 1 Prestrip - Thick | 100 | 28.5543 | 28.5543 | 2031-11-23 10:16 | 2031-11-27 04:11 | 167248.7537 | 167249 | [7 empty] | 0 | 0 | 15.42 | 5.38 | 5933.16
PH4100XPC#1 | CP\09\001\D | CP | 9 | 1 | D | 1 Prestrip - Thick | 100 | 34.749 | 34.749 | 2031-11-23 10:16 | 2031-11-27 04:11 | 203532.7414 | 203533 | [7 empty] | 0 | 0 | 18.76 | 5.38 | 5933.16
TS6060#1 | CP\09\002\B | CP | 9 | 2 | B | 8 Coal Mining | 31.5 | 0 | 31.5 | 2031-11-23 10:16 | 2031-11-25 08:01 | 61918.5107 | [6 empty] | 61919 | 44165 | 1.47 | 0 | 0 | 9.34 | 5575
TS Fleet 5 | CP\09\002\D | CP | 9 | 2 | D | 1 Prestrip - Thick | 26.7594 | 26.7594 | 26.7594 | 2031-11-25 08:01 | 2031-12-03 21:36 | 402948.7255 | 402949 | [7 empty] | 0 | 0 | 14.79 | 5.73 | 5902.12
TS6060#1 | CP\09\001\D | CP | 9 | 1 | D | 1 Prestrip - Thick | 7.7806 | 7.7806 | 7.7806 | 2031-11-25 08:01 | 2031-11-27 04:11 | 45572.8977 | 45573 | [7 empty] | 0 | 0 | 4.2 | 5.38 | 5933.16
PH4100A | CP\09\002\D | CP | 9 | 2 | D | 1 Prestrip - Thick | 100 | 26.4247 | 26.4247 | 2031-11-27 04:11 | 2031-12-06 02:07 | 397908.2032 | 397908 | [7 empty] | 0 | 0 | 14.61 | 5.73 | 5902.12
PH4100XPC#1 | CP\09\002\D | CP | 9 | 2 | D | 1 Prestrip - Thick | 100 | 32.1574 | 32.1574 | 2031-11-27 04:11 | 2031-12-06 02:07 | 484232.8904 | 484233 | [7 empty] | 0 | 0 | 17.77 | 5.73 | 5902.12
TS6060#1 | CP\09\002\D | CP | 9 | 2 | D | 1 Prestrip - Thick | 14.6586 | 14.6586 | 14.6586 | 2031-11-27 04:11 | 2031-12-06 02:07 | 220732.0882 | 220732 | [7 empty] | 0 | 0 | 8.1 | 5.73 | 5902.12
TS5500Exc | CP\07\004\D | CP | 7 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2031-11-28 08:07 | 2031-12-05 10:35 | 150755.3219 |  |  | 150755 | [5 empty] | 0 | 0 | 0 | 6.29 | 5853.22
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 15d 23:33 |  | 15d 23:33 | 2031-12-03 21:36 | 2031-12-19 21:10
TS5500Exc | CP\07\004\D | CP | 7 | 4 | D | 8 Coal Mining | 61 | 0 | 61 | 2031-12-05 10:35 | 2031-12-09 16:31 | 128397.313 | [6 empty] | 128397 | 92217 | 3.07 | 0 | 0 | 6.29 | 5853
PH4100A | CP\09\003\B | CP | 9 | 3 | B | 1 Prestrip - Thick | 100 | 27.2857 | 27.2857 | 2031-12-06 02:07 | 2031-12-16 11:13 | 472939.8656 | 472940 | [7 empty] | 0 | 0 | 14.98 | 8.9 | 5596.18
PH4100XPC#1 | CP\09\003\B | CP | 9 | 3 | B | 1 Prestrip - Thick | 100 | 33.1803 | 33.1803 | 2031-12-06 02:07 | 2031-12-16 11:13 | 575110.6958 | 575111 | [7 empty] | 0 | 0 | 18.22 | 8.9 | 5596.18
TS6060#1 | CP\07\003\D | CP | 7 | 3 | D | 8 Coal Mining | 24.1 | 0 | 24.1 | 2031-12-06 02:07 | 2031-12-07 15:30 | 50598.6902 | [6 empty] | 50599 | 36041 | 1.2 | 0 | 0 | 6.4 | 5843
TS6060#1 | CP\07\004\D | CP | 7 | 4 | D | 8 Coal Mining | 39 | 0 | 39 | 2031-12-07 15:30 | 2031-12-10 04:11 | 82124.2626 | [6 empty] | 82124 | 58983 | 1.97 | 0 | 0 | 6.29 | 5853
TS5500Exc | CP\07\005\D | CP | 7 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2031-12-09 16:31 | 2031-12-16 18:57 | 150737.2813 |  |  | 150737 | [5 empty] | 0 | 0 | 0 | 6.17 | 5863.59
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 6d 07:02 |  | 6d 07:02 | 2031-12-10 04:11 | 2031-12-16 11:13
PH4100A | CP\09\004\B | CP | 9 | 4 | B | 1 Prestrip - Thick | 100 | 30.9727 | 30.9727 | 2031-12-16 11:13 | 2031-12-28 17:11 | 546578.3189 | 546578 | [7 empty] | 0 | 0 | 18.34 | 8.17 | 5645.01
PH4100XPC#1 | CP\09\004\B | CP | 9 | 4 | B | 1 Prestrip - Thick | 100 | 37.6505 | 37.6505 | 2031-12-16 11:13 | 2031-12-28 17:11 | 664422.8985 | 664423 | [7 empty] | 0 | 0 | 22.29 | 8.17 | 5645.01
TS6060#1 | CP\09\003\B | CP | 9 | 3 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2031-12-16 11:13 | 2031-12-19 13:25 | 100424.8855 | [6 empty] | 100425 | 71782 | 2.4 | 0 | 0 | 8.9 | 5596
TS5500Exc | CP\09\003\B | CP | 9 | 3 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2031-12-16 18:57 | 2031-12-19 21:10 | 93464.7449 | [6 empty] | 93465 | 66807 | 2.23 | 0 | 0 | 8.9 | 5596
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 07:44 |  | 0d 07:44 | 2031-12-19 13:25 | 2031-12-19 21:10
TS Fleet 5 | CP\09\003\D | CP | 9 | 3 | D | 1 Prestrip - Thick | 25.0944 | 25.0944 | 25.0944 | 2031-12-19 21:10 | 2031-12-27 18:46 | 371617.7716 | 371618 | [7 empty] | 0 | 0 | 13.65 | 6.31 | 5851.39
TS6060#1 | CP\09\003\D | CP | 9 | 3 | D | 1 Prestrip - Thick | 24.1182 | 20.2637 | 20.2637 | 2031-12-19 21:10 | 2032-01-01 | 300080.7731 | 300081 | [7 empty] | 0 | 0 | 11.02 | 6.31 | 5851.39
TS5500Exc | CP\07\005\D | CP | 7 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2031-12-19 21:10 | 2031-12-26 19:37 | 209671.2585 | [6 empty] | 209671 | 150190 | 5.01 | 0 | 0 | 6.17 | 5864
TS5500Exc | CP\08\001\D | CP | 8 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2031-12-26 19:37 | 2031-12-29 04:05 | 49932.2099 |  |  | 49932 | [5 empty] | 0 | 0 | 0 | 5.35 | 5935.2
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 4d 05:14 |  | 4d 05:14 | 2031-12-27 18:46 | 2032-01-01
PH4100A | CP\09\003\D | CP | 9 | 3 | D | 1 Prestrip - Thick | 100 | 9.8979 | 9.8979 | 2031-12-28 17:11 | 2032-01-01 | 146575.3355 | 146575 | [7 empty] | 0 | 0 | 5.38 | 6.31 | 5851.39
PH4100XPC#1 | CP\09\003\D | CP | 9 | 3 | D | 1 Prestrip - Thick | 100 | 12.0452 | 12.0452 | 2031-12-28 17:11 | 2032-01-01 | 178374.3028 | 178374 | [7 empty] | 0 | 0 | 6.55 | 6.31 | 5851.39
TS5500Exc | CP\09\004\B | CP | 9 | 4 | B | 8 Coal Mining | 51.4 | 0 | 45.8 | 2031-12-29 04:05 | 2032-01-01 | 85545.5422 | [6 empty] | 85546 | 61421 | 2.04 | 0 | 0 | 8.17 | 5645
| EOP 84 : 2031 | EOP 84 : 2031 | [7 empty] | 2032-01-01 | 2032-01-01 |  | 49568160 |  | 3485065 |  |  |  | 7652984 | 5535848 | 203.43 | 0 | 1952.84 | 7.09 | 5778.14
PH4100A | CP\09\003\D | CP | 9 | 3 | D | 1 Prestrip - Thick | 100 | 12.2105 | 12.2105 | 2032-01-01 | 2032-01-05 12:49 | 180822.9726 | 180823 | [7 empty] | 0 | 0 | 6.64 | 6.31 | 5851.39
PH4100XPC#1 | CP\09\003\D | CP | 9 | 3 | D | 1 Prestrip - Thick | 100 | 16.6338 | 16.6338 | 2032-01-01 | 2032-01-05 12:49 | 246326.6821 | 246327 | [7 empty] | 0 | 0 | 9.05 | 6.31 | 5851.39
TS6060#1 | CP\09\003\D | CP | 9 | 3 | D | 1 Prestrip - Thick | 24.1182 | 3.8545 | 3.8545 | 2032-01-01 | 2032-01-03 07:19 | 57080.6879 | 57081 | [7 empty] | 0 | 0 | 2.1 | 6.31 | 5851.39
TS5500Exc | CP\09\004\B | CP | 9 | 4 | B | 8 Coal Mining | 51.4 | 0 | 5.6 | 2032-01-01 | 2032-01-01 08:20 | 10508.6195 | [6 empty] | 10509 | 7545 | 0.25 | 0 | 0 | 8.17 | 5645
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 02:19 |  | 5d 02:19 | 2032-01-01 | 2032-01-06 02:19
TS5500Exc | CP\08\001\D | CP | 8 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2032-01-01 08:20 | 2032-01-03 09:55 | 62456.8094 | [6 empty] | 62457 | 44902 | 4.99 | 0 | 0 | 5.35 | 5935
TS6060#1 | CP\09\004\B | CP | 9 | 4 | B | 8 Coal Mining | 48.6 | 0 | 48.6 | 2032-01-03 07:19 | 2032-01-06 02:19 | 90681.4115 | [6 empty] | 90681 | 65108 | 2.17 | 0 | 0 | 8.17 | 5645
TS5500Exc | CP\08\002\D | CP | 8 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2032-01-03 09:55 | 2032-01-10 11:25 | 149897.1712 |  |  | 149897 | [5 empty] | 0 | 0 | 0 | 5.73 | 5901.94
PH4100XPC#1 | CP\09\005\B | CP | 9 | 5 | B | 1 Prestrip - Thick | 100 | 39.6937 | 39.6937 | 2032-01-05 12:49 | 2032-01-20 09:35 | 814838.6987 | 814839 | [7 empty] | 0 | 0 | 27.45 | 8.49 | 5615.29
PH4100A | CP\09\005\B | CP | 9 | 5 | B | 1 Prestrip - Thick | 100 | 29.1457 | 29.1457 | 2032-01-05 12:49 | 2032-01-20 09:35 | 598307.6749 | 598308 | [7 empty] | 0 | 0 | 20.16 | 8.49 | 5615.29
TS Fleet 5 | CP\09\004\D | CP | 9 | 4 | D | 1 Prestrip - Thick | 21.528 | 21.528 | 21.528 | 2032-01-06 02:19 | 2032-01-12 16:21 | 309736.4487 | 309736 | [7 empty] | 0 | 0 | 11.4 | 6.29 | 5853.38
TS6060#1 | CP\09\004\D | CP | 9 | 4 | D | 1 Prestrip - Thick | 31.3425 | 31.3425 | 31.3425 | 2032-01-06 02:19 | 2032-01-24 07:22 | 450943.1354 | 450943 | [7 empty] | 0 | 0 | 16.59 | 6.29 | 5853.38
TS5500Exc | CP\08\002\D | CP | 8 | 2 | D | 8 Coal Mining | 99 | 0 | 99 | 2032-01-10 11:25 | 2032-01-17 06:31 | 205446.2048 | [6 empty] | 205446 | 147072 | 4.9 | 0 | 0 | 5.73 | 5902
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 14d 09:36 |  | 14d 09:36 | 2032-01-12 16:21 | 2032-01-27 01:57
TS5500Exc | CP\08\003\D | CP | 8 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2032-01-17 06:31 | 2032-01-24 08:04 | 149951.108 |  |  | 149951 | [5 empty] | 0 | 0 | 0 | 6.36 | 5847.04
PH4100XPC#1 | CP\09\004\D | CP | 9 | 4 | D | 1 Prestrip - Thick | 100 | 27.1784 | 27.1784 | 2032-01-20 09:35 | 2032-01-27 14:21 | 391031.7121 | 391032 | [7 empty] | 0 | 0 | 14.39 | 6.29 | 5853.38
PH4100A | CP\09\004\D | CP | 9 | 4 | D | 1 Prestrip - Thick | 100 | 19.9511 | 19.9511 | 2032-01-20 09:35 | 2032-01-27 14:21 | 287047.7366 | 287048 | [7 empty] | 0 | 0 | 10.56 | 6.29 | 5853.38
TS6060#1 | CP\08\002\D | CP | 8 | 2 | D | 8 Coal Mining | 1 | 0 | 1 | 2032-01-24 07:22 | 2032-01-24 08:57 | 2155.9061 | [6 empty] | 2156 | 1543 | 0.05 | 0 | 0 | 5.73 | 5902
TS5500Exc | CP\09\005\B | CP | 9 | 5 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2032-01-24 08:04 | 2032-01-27 01:04 | 81868.8096 | [6 empty] | 81869 | 58507 | 1.95 | 0 | 0 | 8.49 | 5615
TS6060#1 | CP\09\005\B | CP | 9 | 5 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2032-01-24 08:57 | 2032-01-27 01:57 | 87965.4231 | [6 empty] | 87965 | 62864 | 2.1 | 0 | 0 | 8.49 | 5615
TS5500Exc | CP\08\003\D | CP | 8 | 3 | D | 8 Coal Mining | 66.6 | 0 | 66.6 | 2032-01-27 01:04 | 2032-01-31 15:37 | 139258.5745 | [6 empty] | 139259 | 99257 | 3.31 | 0 | 0 | 6.36 | 5847
TS Fleet 5 | CP\09\005\D | CP | 9 | 5 | D | 1 Prestrip - Thick | 26.1845 | 26.1845 | 26.1845 | 2032-01-27 01:57 | 2032-02-04 00:57 | 374349.1374 | 374349 | [7 empty] | 0 | 0 | 13.77 | 6.21 | 5859.96
TS6060#1 | CP\09\005\D | CP | 9 | 5 | D | 1 Prestrip - Thick | 16.4921 | 16.0733 | 16.0733 | 2032-01-27 01:57 | 2032-02-05 08:40 | 229793.4588 | 229793 | [7 empty] | 0 | 0 | 8.45 | 6.21 | 5859.96
PH4100XPC#1 | CP\09\005\D | CP | 9 | 5 | D | 1 Prestrip - Thick | 100 | 33.2985 | 33.2985 | 2032-01-27 14:21 | 2032-02-05 08:40 | 476056.0429 | 476056 | [7 empty] | 0 | 0 | 17.51 | 6.21 | 5859.96
PH4100A | CP\09\005\D | CP | 9 | 5 | D | 1 Prestrip - Thick | 100 | 24.4437 | 24.4437 | 2032-01-27 14:21 | 2032-02-05 08:40 | 349462.2186 | 349462 | [7 empty] | 0 | 0 | 12.86 | 6.21 | 5859.96
TS5500Exc | CP\08\004\D | CP | 8 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2032-01-31 15:37 | 2032-02-07 17:29 | 150221.3406 |  |  | 150221 | [5 empty] | 0 | 0 | 0 | 6.29 | 5853.25
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 9d 12:10 |  | 9d 12:10 | 2032-02-04 00:57 | 2032-02-13 13:06
PH4100A | CP\09\006\B | CP | 9 | 6 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-02-05 08:40 | 2032-02-05 08:40 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\09\006\D | CP | 9 | 6 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-02-05 08:40 | 2032-02-05 08:40 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\09\007\B | CP | 9 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-02-05 08:40 | 2032-02-05 08:40 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\09\007\D | CP | 9 | 7 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-02-05 08:40 | 2032-02-05 08:40 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\10\001\B | CP | 10 | 1 | B | 1 Prestrip - Thick | 100 | 29.0585 | 29.0585 | 2032-02-05 08:40 | 2032-02-09 13:54 | 166918.6094 | 166919 | [7 empty] | 0 | 0 | 8.43 | 8.85 | 5615.47
PH4100XPC#1 | CP\10\001\B | CP | 10 | 1 | B | 1 Prestrip - Thick | 100 | 39.3452 | 39.3452 | 2032-02-05 08:40 | 2032-02-09 13:54 | 226007.4874 | 226007 | [7 empty] | 0 | 0 | 11.42 | 8.85 | 5615.47
TS6060#1 | CP\08\003\D | CP | 8 | 3 | D | 8 Coal Mining | 33.4 | 0 | 33.4 | 2032-02-05 08:40 | 2032-02-07 12:15 | 69828.0158 | [6 empty] | 69828 | 49770 | 1.66 | 0 | 0 | 6.36 | 5847
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 05:13 |  | 0d 05:13 | 2032-02-07 12:15 | 2032-02-07 17:29
TS6060#1 | CP\08\004\D | CP | 8 | 4 | D | 8 Coal Mining | 37 | 0 | 37 | 2032-02-07 17:29 | 2032-02-10 03:04 | 77942.9386 | [6 empty] | 77943 | 55940 | 1.86 | 0 | 0 | 6.29 | 5853
TS5500Exc | CP\08\004\D | CP | 8 | 4 | D | 8 Coal Mining | 63 | 0 | 63 | 2032-02-07 17:29 | 2032-02-12 02:57 | 132847.0506 | [6 empty] | 132847 | 95344 | 3.18 | 0 | 0 | 6.29 | 5853
PH4100XPC#1 | CP\10\002\B | CP | 10 | 2 | B | 1 Prestrip - Thick | 100 | 39.5362 | 39.5362 | 2032-02-09 13:54 | 2032-02-19 15:17 | 546191.9139 | 546192 | [7 empty] | 0 | 0 | 18.34 | 9.18 | 5587.13
PH4100A | CP\10\002\B | CP | 10 | 2 | B | 1 Prestrip - Thick | 100 | 29.1418 | 29.1418 | 2032-02-09 13:54 | 2032-02-19 15:17 | 402593.0112 | 402593 | [7 empty] | 0 | 0 | 13.52 | 9.18 | 5587.13
TS6060#1 | CP\10\001\B | CP | 10 | 1 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2032-02-10 03:04 | 2032-02-11 13:14 | 46233.844 | [6 empty] | 46234 | 32790 | 1.94 | 0 | 0 | 8.85 | 5615
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 23:53 |  | 1d 23:53 | 2032-02-11 13:14 | 2032-02-13 13:06
TS5500Exc | CP\10\001\B | CP | 10 | 1 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2032-02-12 02:57 | 2032-02-13 13:06 | 43029.5182 | [6 empty] | 43030 | 30517 | 1.81 | 0 | 0 | 8.85 | 5615
TS Fleet 5 | CP\10\001\D | CP | 10 | 1 | D | 1 Prestrip - Thick | 20.8061 | 20.8061 | 20.8061 | 2032-02-13 13:06 | 2032-02-16 11:59 | 138928.7481 | 138929 | [7 empty] | 0 | 0 | 11.33 | 5.4 | 5931.38
TS6060#1 | CP\10\001\D | CP | 10 | 1 | D | 1 Prestrip - Thick | 33.6449 | 33.6449 | 33.6449 | 2032-02-13 13:06 | 2032-02-22 14:50 | 224657.9067 | 224658 | [7 empty] | 0 | 0 | 18.32 | 5.4 | 5931.38
TS5500Exc | CP\08\005\D | CP | 8 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2032-02-13 13:06 | 2032-02-20 15:27 | 150649.5954 |  |  | 150650 | [5 empty] | 0 | 0 | 0 | 6.19 | 5861.75
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 9d 04:56 |  | 9d 04:56 | 2032-02-16 11:59 | 2032-02-25 16:55
PH4100A | CP\10\001\D | CP | 10 | 1 | D | 1 Prestrip - Thick | 100 | 19.282 | 19.282 | 2032-02-19 15:17 | 2032-02-22 20:46 | 128751.9853 | 128752 | [7 empty] | 0 | 0 | 10.5 | 5.4 | 5931.38
PH4100XPC#1 | CP\10\001\D | CP | 10 | 1 | D | 1 Prestrip - Thick | 100 | 26.267 | 26.267 | 2032-02-19 15:17 | 2032-02-22 20:46 | 175392.8105 | 175393 | [7 empty] | 0 | 0 | 14.3 | 5.4 | 5931.38
TS5500Exc | CP\10\002\B | CP | 10 | 2 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2032-02-20 15:27 | 2032-02-23 17:31 | 93305.7573 | [6 empty] | 93306 | 66566 | 2.22 | 0 | 0 | 9.18 | 5587
TS6060#1 | CP\10\002\B | CP | 10 | 2 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2032-02-22 14:50 | 2032-02-25 16:55 | 100254.0584 | [6 empty] | 100254 | 71523 | 2.39 | 0 | 0 | 9.18 | 5587
PH4100A | CP\10\003\B | CP | 10 | 3 | B | 1 Prestrip - Thick | 100 | 29.1955 | 29.1955 | 2032-02-22 20:46 | 2032-03-06 16:05 | 517675.454 | 517675 | [7 empty] | 0 | 0 | 16.61 | 8.78 | 5605.52
PH4100XPC#1 | CP\10\003\B | CP | 10 | 3 | B | 1 Prestrip - Thick | 100 | 39.7299 | 39.7299 | 2032-02-22 20:46 | 2032-03-06 16:05 | 704466.2125 | 704466 | [7 empty] | 0 | 0 | 22.6 | 8.78 | 5605.52
TS5500Exc | CP\08\005\D | CP | 8 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2032-02-23 17:31 | 2032-03-01 16:00 | 209702.7799 | [6 empty] | 209703 | 150092 | 5 | 0 | 0 | 6.19 | 5862
TS Fleet 5 | CP\10\002\D | CP | 10 | 2 | D | 1 Prestrip - Thick | 23.8051 | 23.8051 | 23.8051 | 2032-02-25 16:55 | 2032-03-04 07:31 | 357888.7131 | 357889 | [7 empty] | 0 | 0 | 13.14 | 5.73 | 5902.53
TS6060#1 | CP\10\002\D | CP | 10 | 2 | D | 1 Prestrip - Thick | 24.0803 | 24.0803 | 24.0803 | 2032-02-25 16:55 | 2032-03-11 07:47 | 362026.1257 | 362026 | [7 empty] | 0 | 0 | 13.29 | 5.73 | 5902.53
TS5500Exc | CP\09\001\D | CP | 9 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2032-03-01 16:00 | 2032-03-04 11:36 | 59783.7265 |  |  | 59784 | [5 empty] | 0 | 0 | 0 | 5.38 | 5933.16
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 9d 15:44 |  | 9d 15:44 | 2032-03-04 07:31 | 2032-03-13 23:14
TS5500Exc | CP\09\001\D | CP | 9 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2032-03-04 11:36 | 2032-03-07 00:06 | 76193.4052 | [6 empty] | 76193 | 54787 | 5.01 | 0 | 0 | 5.38 | 5933
PH4100XPC#1 | CP\10\002\D | CP | 10 | 2 | D | 1 Prestrip - Thick | 100 | 30.0532 | 30.0532 | 2032-03-06 16:05 | 2032-03-14 23:42 | 451822.305 | 451822 | [7 empty] | 0 | 0 | 16.59 | 5.73 | 5902.53
PH4100A | CP\10\002\D | CP | 10 | 2 | D | 1 Prestrip - Thick | 100 | 22.0614 | 22.0614 | 2032-03-06 16:05 | 2032-03-14 23:42 | 331672.7672 | 331673 | [7 empty] | 0 | 0 | 12.18 | 5.73 | 5902.53
TS5500Exc | CP\10\003\B | CP | 10 | 3 | B | 8 Coal Mining | 53.2 | 0 | 53.2 | 2032-03-07 00:06 | 2032-03-10 05:36 | 97618.6932 | [6 empty] | 97619 | 69687 | 2.33 | 0 | 0 | 8.78 | 5606
TS5500Exc | CP\09\002\D | CP | 9 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2032-03-10 05:36 | 2032-03-17 06:56 | 149759.3589 |  |  | 149759 | [5 empty] | 0 | 0 | 0 | 5.73 | 5902.12
TS6060#1 | CP\10\003\B | CP | 10 | 3 | B | 8 Coal Mining | 46.8 | 0 | 46.8 | 2032-03-11 07:47 | 2032-03-13 23:14 | 85881.2094 | [6 empty] | 85881 | 61308 | 2.05 | 0 | 0 | 8.78 | 5606
TS Fleet 5 | CP\10\003\D | CP | 10 | 3 | D | 1 Prestrip - Thick | 22.2311 | 22.2311 | 22.2311 | 2032-03-13 23:14 | 2032-03-20 23:14 | 329257.1758 | 329257 | [7 empty] | 0 | 0 | 12.1 | 6.27 | 5855.14
TS6060#1 | CP\10\003\D | CP | 10 | 3 | D | 1 Prestrip - Thick | 29.1004 | 17.5372 | 17.5372 | 2032-03-13 23:14 | 2032-03-24 10:58 | 259737.4536 | 259737 | [7 empty] | 0 | 0 | 9.54 | 6.27 | 5855.14
PH4100A | CP\10\003\D | CP | 10 | 3 | D | 1 Prestrip - Thick | 100 | 25.4976 | 25.4976 | 2032-03-14 23:42 | 2032-03-24 10:58 | 377636.4714 | 377636 | [7 empty] | 0 | 0 | 13.88 | 6.27 | 5855.14
PH4100XPC#1 | CP\10\003\D | CP | 10 | 3 | D | 1 Prestrip - Thick | 100 | 34.7342 | 34.7342 | 2032-03-14 23:42 | 2032-03-24 10:58 | 514436.5105 | 514437 | [7 empty] | 0 | 0 | 18.9 | 6.27 | 5855.14
TS5500Exc | CP\09\002\D | CP | 9 | 2 | D | 8 Coal Mining | 85.5 | 0 | 85.5 | 2032-03-17 06:56 | 2032-03-23 05:46 | 179914.0603 | [6 empty] | 179914 | 128797 | 4.29 | 0 | 0 | 5.73 | 5902
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 26d 08:48 |  | 26d 08:48 | 2032-03-20 23:14 | 2032-04-16 08:02
TS5500Exc | CP\09\003\D | CP | 9 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2032-03-23 05:46 | 2032-03-30 07:14 | 149885.4264 |  |  | 149885 | [5 empty] | 0 | 0 | 0 | 6.31 | 5851.39
PH4100A | CP\10\004\B | CP | 10 | 4 | B | 1 Prestrip - Thick | 100 | 29.0782 | 29.0782 | 2032-03-24 10:58 | 2032-04-06 20:50 | 535394.4962 | 535394 | [7 empty] | 0 | 0 | 17.95 | 8.18 | 5645.32
PH4100XPC#1 | CP\10\004\B | CP | 10 | 4 | B | 1 Prestrip - Thick | 100 | 39.581 | 39.581 | 2032-03-24 10:58 | 2032-04-06 20:50 | 728773.5949 | 728774 | [7 empty] | 0 | 0 | 24.43 | 8.18 | 5645.32
TS6060#1 | CP\09\002\D | CP | 9 | 2 | D | 8 Coal Mining | 14.5 | 0 | 14.5 | 2032-03-24 10:58 | 2032-03-25 09:31 | 30511.3891 | [6 empty] | 30511 | 21843 | 0.73 | 0 | 0 | 5.73 | 5902
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 12d 11:19 |  | 12d 11:19 | 2032-03-25 09:31 | 2032-04-06 20:50
TS5500Exc | CP\09\003\D | CP | 9 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2032-03-30 07:14 | 2032-04-06 06:08 | 210218.712 | [6 empty] | 210219 | 149884 | 5 | 0 | 0 | 6.31 | 5851
TS5500Exc | CP\09\004\D | CP | 9 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2032-04-06 06:08 | 2032-04-13 07:49 | 150066.4534 |  |  | 150066 | [5 empty] | 0 | 0 | 0 | 6.29 | 5853.38
PH4100A | CP\10\005\B | CP | 10 | 5 | B | 1 Prestrip - Thick | 100 | 28.7906 | 28.7906 | 2032-04-06 20:50 | 2032-04-21 20:09 | 603847.873 | 603848 | [7 empty] | 0 | 0 | 20.53 | 8.45 | 5618.52
TS6060#1 | CP\10\004\B | CP | 10 | 4 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2032-04-06 20:50 | 2032-04-09 21:03 | 97740.477 | [6 empty] | 97740 | 70205 | 2.34 | 0 | 0 | 8.18 | 5645
PH4100XPC#1 | CP\10\005\B | CP | 10 | 5 | B | 1 Prestrip - Thick | 100 | 39.2151 | 39.2151 | 2032-04-06 20:50 | 2032-04-21 20:09 | 822488.4306 | 822488 | [7 empty] | 0 | 0 | 27.96 | 8.45 | 5618.52
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 3d 10:46 |  | 3d 10:46 | 2032-04-09 21:03 | 2032-04-13 07:49
TS6060#1 | CP\09\004\D | CP | 9 | 4 | D | 8 Coal Mining | 17.5 | 0 | 17.5 | 2032-04-13 07:49 | 2032-04-14 11:10 | 37011.5413 | [6 empty] | 37012 | 26545 | 0.88 | 0 | 0 | 6.29 | 5853
TS5500Exc | CP\10\004\B | CP | 10 | 4 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2032-04-13 07:49 | 2032-04-16 08:02 | 90966.3845 | [6 empty] | 90966 | 65339 | 2.18 | 0 | 0 | 8.18 | 5645
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 20:52 |  | 1d 20:52 | 2032-04-14 11:10 | 2032-04-16 08:02
TS Fleet 5 | CP\10\004\D | CP | 10 | 4 | D | 1 Prestrip - Thick | 22.6407 | 22.6407 | 22.6407 | 2032-04-16 08:02 | 2032-04-23 06:23 | 326035.7199 | 326036 | [7 empty] | 0 | 0 | 12 | 6.29 | 5853.63
TS6060#1 | CP\10\004\D | CP | 10 | 4 | D | 1 Prestrip - Thick | 30.0494 | 23.5986 | 23.5986 | 2032-04-16 08:02 | 2032-04-30 01:23 | 339829.5932 | 339830 | [7 empty] | 0 | 0 | 12.5 | 6.29 | 5853.63
TS5500Exc | CP\09\004\D | CP | 9 | 4 | D | 8 Coal Mining | 82.5 | 0 | 82.5 | 2032-04-16 08:02 | 2032-04-22 02:17 | 174142.1313 | [6 empty] | 174142 | 124894 | 4.16 | 0 | 0 | 6.29 | 5853
PH4100A | CP\10\004\D | CP | 10 | 4 | D | 1 Prestrip - Thick | 100 | 22.7582 | 22.7582 | 2032-04-21 20:09 | 2032-04-30 01:23 | 327727.5894 | 327728 | [7 empty] | 0 | 0 | 12.06 | 6.29 | 5853.63
PH4100XPC#1 | CP\10\004\D | CP | 10 | 4 | D | 1 Prestrip - Thick | 100 | 31.0025 | 31.0025 | 2032-04-21 20:09 | 2032-04-30 01:23 | 446447.9737 | 446448 | [7 empty] | 0 | 0 | 16.43 | 6.29 | 5853.63
TS5500Exc | CP\10\005\B | CP | 10 | 5 | B | 8 Coal Mining | 80.9 | 0 | 80.9 | 2032-04-22 02:17 | 2032-04-26 12:39 | 133974.0463 | [6 empty] | 133974 | 95667 | 3.2 | 0 | 0 | 8.45 | 5619
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 7d 18:21 |  | 7d 18:21 | 2032-04-23 06:23 | 2032-05-01 00:44
TS5500Exc | CP\09\005\D | CP | 9 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2032-04-26 12:39 | 2032-05-03 14:29 | 150201.8707 |  |  | 150202 | [5 empty] | 0 | 0 | 0 | 6.21 | 5859.96
PH4100A | CP\10\006\B | CP | 10 | 6 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-04-30 01:23 | 2032-04-30 01:23 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\10\006\D | CP | 10 | 6 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-04-30 01:23 | 2032-04-30 01:23 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\10\007\B | CP | 10 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-04-30 01:23 | 2032-04-30 01:23 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\10\007\D | CP | 10 | 7 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-04-30 01:23 | 2032-04-30 01:23 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\11\001\B | CP | 11 | 1 | B | 1 Prestrip - Thick | 100 | 28.631 | 28.631 | 2032-04-30 01:23 | 2032-05-05 01:02 | 197304.9283 | 197305 | [7 empty] | 0 | 0 | 9.22 | 8.68 | 5627.98
PH4100XPC#1 | CP\11\001\B | CP | 11 | 1 | B | 1 Prestrip - Thick | 100 | 38.7579 | 38.7579 | 2032-04-30 01:23 | 2032-05-05 01:02 | 267093.0526 | 267093 | [7 empty] | 0 | 0 | 12.48 | 8.68 | 5627.98
TS6060#1 | CP\10\005\B | CP | 10 | 5 | B | 8 Coal Mining | 19.1 | 0 | 19.1 | 2032-04-30 01:23 | 2032-05-01 00:44 | 31595.5066 | [6 empty] | 31596 | 22562 | 0.75 | 0 | 0 | 8.45 | 5619
TS Fleet 5 | CP\10\005\D | CP | 10 | 5 | D | 1 Prestrip - Thick | 25.8398 | 25.8398 | 25.8398 | 2032-05-01 00:44 | 2032-05-08 20:04 | 367164.0919 | 367164 | [7 empty] | 0 | 0 | 13.52 | 6.23 | 5858.42
TS6060#1 | CP\10\005\D | CP | 10 | 5 | D | 1 Prestrip - Thick | 20.3747 | 20.3747 | 20.3747 | 2032-05-01 00:44 | 2032-05-12 17:19 | 289509.151 | 289509 | [7 empty] | 0 | 0 | 10.66 | 6.23 | 5858.42
TS5500Exc | CP\09\005\D | CP | 9 | 5 | D | 8 Coal Mining | 78.8 | 0 | 78.8 | 2032-05-03 14:29 | 2032-05-09 01:27 | 164965.2686 | [6 empty] | 164965 | 118062 | 3.94 | 0 | 0 | 6.21 | 5860
PH4100A | CP\10\005\D | CP | 10 | 5 | D | 1 Prestrip - Thick | 100 | 22.7687 | 22.7687 | 2032-05-05 01:02 | 2032-05-13 03:44 | 323525.3527 | 323525 | [7 empty] | 0 | 0 | 11.92 | 6.23 | 5858.42
PH4100XPC#1 | CP\10\005\D | CP | 10 | 5 | D | 1 Prestrip - Thick | 100 | 31.0167 | 31.0167 | 2032-05-05 01:02 | 2032-05-13 03:44 | 440723.4631 | 440723 | [7 empty] | 0 | 0 | 16.23 | 6.23 | 5858.42
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 5d 11:11 |  | 5d 11:11 | 2032-05-08 20:04 | 2032-05-14 07:15
TS5500Exc | CP\11\001\B | CP | 11 | 1 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2032-05-09 01:27 | 2032-05-10 15:23 | 47774.3497 | [6 empty] | 47774 | 33945 | 1.86 | 0 | 0 | 8.68 | 5628
TS5500Exc | CP\10\001\D | CP | 10 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2032-05-10 15:23 | 2032-05-13 19:43 | 67515.9083 |  |  | 67516 | [5 empty] | 0 | 0 | 0 | 5.4 | 5931.38
TS6060#1 | CP\11\001\B | CP | 11 | 1 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2032-05-12 17:19 | 2032-05-14 07:15 | 51332.014 | [6 empty] | 51332 | 36472 | 2 | 0 | 0 | 8.68 | 5628
PH4100A | CP\11\002\B | CP | 11 | 2 | B | 1 Prestrip - Thick | 100 | 28.7737 | 28.7737 | 2032-05-13 03:44 | 2032-05-24 05:32 | 446266.1005 | 446266 | [7 empty] | 0 | 0 | 15.61 | 9.03 | 5597.58
PH4100XPC#1 | CP\11\002\B | CP | 11 | 2 | B | 1 Prestrip - Thick | 100 | 39.0354 | 39.0354 | 2032-05-13 03:44 | 2032-05-24 05:32 | 605420.4744 | 605420 | [7 empty] | 0 | 0 | 21.17 | 9.03 | 5597.58
TS5500Exc | CP\10\001\D | CP | 10 | 1 | D | 8 Coal Mining | 34.1 | 0 | 34.1 | 2032-05-13 19:43 | 2032-05-14 19:39 | 30154.7558 | [6 empty] | 30155 | 21670 | 1.71 | 0 | 0 | 5.4 | 5931
TS Fleet 5 | CP\11\001\D | CP | 11 | 1 | D | 1 Prestrip - Thick | 20.209 | 20.209 | 20.209 | 2032-05-14 07:15 | 2032-05-17 11:09 | 148761.3967 | 148761 | [7 empty] | 0 | 0 | 10.91 | 5.42 | 5929.79
TS6060#1 | CP\11\001\D | CP | 11 | 1 | D | 1 Prestrip - Thick | 37.5623 | 37.5623 | 37.5623 | 2032-05-14 07:15 | 2032-05-25 11:14 | 276501.3494 | 276501 | [7 empty] | 0 | 0 | 20.28 | 5.42 | 5929.79
TS5500Exc | CP\10\001\D | CP | 10 | 1 | D | 8 Coal Mining | 65.9 | 0 | 65.9 | 2032-05-14 19:39 | 2032-05-16 17:53 | 58218.4175 | [6 empty] | 58218 | 41837 | 3.31 | 0 | 0 | 5.4 | 5931
TS5500Exc | CP\10\002\D | CP | 10 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2032-05-16 17:53 | 2032-05-23 19:14 | 149772.4125 |  |  | 149772 | [5 empty] | 0 | 0 | 0 | 5.73 | 5902.53
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 14d 07:21 |  | 14d 07:21 | 2032-05-17 11:09 | 2032-05-31 18:30
TS5500Exc | CP\10\002\D | CP | 10 | 2 | D | 8 Coal Mining | 71.1 | 0 | 71.1 | 2032-05-23 19:14 | 2032-05-28 19:35 | 151603.6527 | [6 empty] | 151604 | 108622 | 3.62 | 0 | 0 | 5.73 | 5903
PH4100XPC#1 | CP\11\001\D | CP | 11 | 1 | D | 1 Prestrip - Thick | 100 | 24.3522 | 24.3522 | 2032-05-24 05:32 | 2032-05-27 12:43 | 179259.8242 | 179260 | [7 empty] | 0 | 0 | 13.15 | 5.42 | 5929.79
PH4100A | CP\11\001\D | CP | 11 | 1 | D | 1 Prestrip - Thick | 100 | 17.8764 | 17.8764 | 2032-05-24 05:32 | 2032-05-27 12:43 | 131590.6747 | 131591 | [7 empty] | 0 | 0 | 9.65 | 5.42 | 5929.79
TS6060#1 | CP\09\005\D | CP | 9 | 5 | D | 8 Coal Mining | 21.2 | 0 | 21.2 | 2032-05-25 11:14 | 2032-05-26 20:03 | 44420.7059 | [6 empty] | 44421 | 31791 | 1.06 | 0 | 0 | 6.21 | 5860
TS6060#1 | CP\11\002\B | CP | 11 | 2 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2032-05-26 20:03 | 2032-05-29 18:58 | 95973.0521 | [6 empty] | 95973 | 68413 | 2.29 | 0 | 0 | 9.03 | 5598
PH4100A | CP\11\003\B | CP | 11 | 3 | B | 1 Prestrip - Thick | 100 | 28.7351 | 28.7351 | 2032-05-27 12:43 | 2032-06-09 13:05 | 524047.711 | 524048 | [7 empty] | 0 | 0 | 16.77 | 8.76 | 5607.11
PH4100XPC#1 | CP\11\003\B | CP | 11 | 3 | B | 1 Prestrip - Thick | 100 | 39.0924 | 39.0924 | 2032-05-27 12:43 | 2032-06-09 13:05 | 712935.5376 | 712936 | [7 empty] | 0 | 0 | 22.82 | 8.76 | 5607.11
TS5500Exc | CP\11\002\B | CP | 11 | 2 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2032-05-28 19:35 | 2032-05-31 18:30 | 89321.4544 | [6 empty] | 89321 | 63672 | 2.13 | 0 | 0 | 9.03 | 5598
TS6060#1 | CP\10\002\D | CP | 10 | 2 | D | 8 Coal Mining | 28.9 | 0 | 28.9 | 2032-05-29 18:58 | 2032-05-31 16:36 | 61759.6292 | [6 empty] | 61760 | 44250 | 1.47 | 0 | 0 | 5.73 | 5903
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 01:54 |  | 0d 01:54 | 2032-05-31 16:36 | 2032-05-31 18:30
TS Fleet 5 | CP\11\002\D | CP | 11 | 2 | D | 1 Prestrip - Thick | 23.6746 | 23.6746 | 23.6746 | 2032-05-31 18:30 | 2032-06-08 07:45 | 355268.5545 | 355269 | [7 empty] | 0 | 0 | 13.04 | 5.73 | 5903.01
TS6060#1 | CP\11\002\D | CP | 11 | 2 | D | 1 Prestrip - Thick | 6.8951 | 6.8951 | 6.8951 | 2032-05-31 18:30 | 2032-06-04 22:47 | 103469.7958 | 103470 | [7 empty] | 0 | 0 | 3.8 | 5.73 | 5903.01
TS5500Exc | CP\10\003\D | CP | 10 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2032-05-31 18:30 | 2032-06-07 19:56 | 149849.6697 |  |  | 149850 | [5 empty] | 0 | 0 | 0 | 6.27 | 5855.14
TS6060#1 | CP\11\002\D | CP | 11 | 2 | D | 1 Prestrip - Thick | 19.96 | 19.96 | 19.96 | 2032-06-04 22:47 | 2032-06-17 01:04 | 299525.933 | 299526 | [7 empty] | 0 | 0 | 11 | 5.73 | 5903.01
TS5500Exc | CP\10\003\D | CP | 10 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2032-06-07 19:56 | 2032-06-14 19:51 | 211507.6799 | [6 empty] | 211508 | 150979 | 5.03 | 0 | 0 | 6.27 | 5855
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 11d 12:52 |  | 11d 12:52 | 2032-06-08 07:45 | 2032-06-19 20:37
PH4100XPC#1 | CP\11\002\D | CP | 11 | 2 | D | 1 Prestrip - Thick | 100 | 28.5283 | 28.5283 | 2032-06-09 13:05 | 2032-06-17 10:13 | 428104.1995 | 428104 | [7 empty] | 0 | 0 | 15.72 | 5.73 | 5903.01
PH4100A | CP\11\002\D | CP | 11 | 2 | D | 1 Prestrip - Thick | 100 | 20.942 | 20.942 | 2032-06-09 13:05 | 2032-06-17 10:13 | 314261.8302 | 314262 | [7 empty] | 0 | 0 | 11.54 | 5.73 | 5903.01
TS5500Exc | CP\11\003\B | CP | 11 | 3 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2032-06-14 19:51 | 2032-06-17 15:24 | 85086.8372 | [6 empty] | 85087 | 60656 | 2.02 | 0 | 0 | 8.76 | 5607
TS6060#1 | CP\11\003\B | CP | 11 | 3 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2032-06-17 01:04 | 2032-06-19 20:37 | 91423.091 | [6 empty] | 91423 | 65173 | 2.17 | 0 | 0 | 8.76 | 5607
PH4100A | CP\11\004\B | CP | 11 | 4 | B | 1 Prestrip - Thick | 100 | 28.6474 | 28.6474 | 2032-06-17 10:13 | 2032-07-01 02:24 | 545921.606 | 545922 | [7 empty] | 0 | 0 | 18.29 | 8.2 | 5644.14
PH4100XPC#1 | CP\11\004\B | CP | 11 | 4 | B | 1 Prestrip - Thick | 100 | 39.002 | 39.002 | 2032-06-17 10:13 | 2032-07-01 02:24 | 743245.2097 | 743245 | [7 empty] | 0 | 0 | 24.9 | 8.2 | 5644.14
TS5500Exc | CP\10\004\D | CP | 10 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2032-06-17 15:24 | 2032-06-24 17:04 | 150057.2586 |  |  | 150057 | [5 empty] | 0 | 0 | 0 | 6.29 | 5853.63
TS Fleet 5 | CP\11\003\D | CP | 11 | 3 | D | 1 Prestrip - Thick | 23.3641 | 23.3641 | 23.3641 | 2032-06-19 20:37 | 2032-06-27 05:09 | 345997.5874 | 345998 | [7 empty] | 0 | 0 | 12.72 | 6.23 | 5858.53
TS6060#1 | CP\11\003\D | CP | 11 | 3 | D | 1 Prestrip - Thick | 27.8146 | 27.8146 | 27.8146 | 2032-06-19 20:37 | 2032-07-06 11:50 | 411905.7178 | 411906 | [7 empty] | 0 | 0 | 15.14 | 6.23 | 5858.53
TS5500Exc | CP\10\004\D | CP | 10 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2032-06-24 17:04 | 2032-07-01 17:02 | 211560.5553 | [6 empty] | 211561 | 151626 | 5.05 | 0 | 0 | 6.29 | 5854
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 11d 01:52 |  | 11d 01:52 | 2032-06-27 05:09 | 2032-07-08 07:01
PH4100XPC#1 | CP\11\003\D | CP | 11 | 3 | D | 1 Prestrip - Thick | 100 | 28.1541 | 28.1541 | 2032-07-01 02:24 | 2032-07-08 18:36 | 416932.5382 | 416933 | [7 empty] | 0 | 0 | 15.32 | 6.23 | 5858.53
PH4100A | CP\11\003\D | CP | 11 | 3 | D | 1 Prestrip - Thick | 100 | 20.6673 | 20.6673 | 2032-07-01 02:24 | 2032-07-08 18:36 | 306060.9606 | 306061 | [7 empty] | 0 | 0 | 11.25 | 6.23 | 5858.53
TS5500Exc | CP\11\004\B | CP | 11 | 4 | B | 8 Coal Mining | 69.4 | 0 | 69.4 | 2032-07-01 17:02 | 2032-07-06 02:04 | 132312.9404 | [6 empty] | 132313 | 94995 | 3.16 | 0 | 0 | 8.2 | 5644
TS5500Exc | CP\10\005\D | CP | 10 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2032-07-06 02:04 | 2032-07-13 03:47 | 150093.062 |  |  | 150093 | [5 empty] | 0 | 0 | 0 | 6.23 | 5858.42
TS6060#1 | CP\11\004\B | CP | 11 | 4 | B | 8 Coal Mining | 30.6 | 0 | 30.6 | 2032-07-06 11:50 | 2032-07-08 07:01 | 58447.7717 | [6 empty] | 58448 | 41963 | 1.4 | 0 | 0 | 8.2 | 5644
TS Fleet 5 | CP\11\004\D | CP | 11 | 4 | D | 1 Prestrip - Thick | 21.4123 | 21.4123 | 21.4123 | 2032-07-08 07:01 | 2032-07-14 20:29 | 308635.7829 | 308636 | [7 empty] | 0 | 0 | 11.36 | 6.28 | 5853.97
TS6060#1 | CP\11\004\D | CP | 11 | 4 | D | 1 Prestrip - Thick | 34.6754 | 17.015 | 17.015 | 2032-07-08 07:01 | 2032-07-18 04:43 | 245252.7161 | 245253 | [7 empty] | 0 | 0 | 9.02 | 6.28 | 5853.97
PH4100A | CP\11\004\D | CP | 11 | 4 | D | 1 Prestrip - Thick | 100 | 26.0652 | 26.0652 | 2032-07-08 18:36 | 2032-07-18 04:43 | 375702.683 | 375703 | [7 empty] | 0 | 0 | 13.82 | 6.28 | 5853.97
PH4100XPC#1 | CP\11\004\D | CP | 11 | 4 | D | 1 Prestrip - Thick | 100 | 35.5075 | 35.5075 | 2032-07-08 18:36 | 2032-07-18 04:43 | 511802.201 | 511802 | [7 empty] | 0 | 0 | 18.83 | 6.28 | 5853.97
TS5500Exc | CP\10\005\D | CP | 10 | 5 | D | 8 Coal Mining | 65.2 | 0 | 65.2 | 2032-07-13 03:47 | 2032-07-17 16:07 | 136449.3964 | [6 empty] | 136449 | 97572 | 3.25 | 0 | 0 | 6.23 | 5858
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 27d 00:21 |  | 27d 00:21 | 2032-07-14 20:29 | 2032-08-10 20:51
TS5500Exc | CP\11\001\D | CP | 11 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2032-07-17 16:07 | 2032-07-21 05:04 | 75129.0833 |  |  | 75129 | [5 empty] | 0 | 0 | 0 | 5.42 | 5929.79
TS6060#1 | CP\10\005\D | CP | 10 | 5 | D | 8 Coal Mining | 34.8 | 0 | 34.8 | 2032-07-18 04:43 | 2032-07-20 10:30 | 72805.2377 | [6 empty] | 72805 | 52062 | 1.74 | 0 | 0 | 6.23 | 5858
PH4100A | CP\11\005\B | CP | 11 | 5 | B | 1 Prestrip - Thick | 100 | 28.7721 | 28.7721 | 2032-07-18 04:43 | 2032-08-02 10:04 | 616467.5524 | 616468 | [7 empty] | 0 | 0 | 20.97 | 8.41 | 5622.14
PH4100XPC#1 | CP\11\005\B | CP | 11 | 5 | B | 1 Prestrip - Thick | 100 | 39.1977 | 39.1977 | 2032-07-18 04:43 | 2032-08-02 10:04 | 839845.0769 | 839845 | [7 empty] | 0 | 0 | 28.57 | 8.41 | 5622.14
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 18:33 |  | 0d 18:33 | 2032-07-20 10:30 | 2032-07-21 05:04
TS6060#1 | CP\11\001\D | CP | 11 | 1 | D | 8 Coal Mining | 9.6 | 0 | 9.6 | 2032-07-21 05:04 | 2032-07-21 12:06 | 9518.5808 | [6 empty] | 9519 | 6841 | 0.48 | 0 | 0 | 5.42 | 5930
TS5500Exc | CP\11\001\D | CP | 11 | 1 | D | 8 Coal Mining | 90.4 | 0 | 90.4 | 2032-07-21 05:04 | 2032-07-24 04:08 | 89521.8188 | [6 empty] | 89522 | 64340 | 4.55 | 0 | 0 | 5.42 | 5930
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 9d 17:24 |  | 9d 17:24 | 2032-07-21 12:06 | 2032-07-31 05:29
TS5500Exc | CP\11\002\D | CP | 11 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2032-07-24 04:08 | 2032-07-31 05:29 | 149776.2661 |  |  | 149776 | [5 empty] | 0 | 0 | 0 | 5.73 | 5903.01
TS6060#1 | CP\11\002\D | CP | 11 | 2 | D | 8 Coal Mining | 13.9 | 0 | 13.9 | 2032-07-31 05:29 | 2032-08-01 03:45 | 30133.6632 | [6 empty] | 30134 | 21607 | 0.72 | 0 | 0 | 5.73 | 5903
TS5500Exc | CP\11\002\D | CP | 11 | 2 | D | 8 Coal Mining | 86.1 | 0 | 86.1 | 2032-07-31 05:29 | 2032-08-06 09:13 | 186071.3402 | [6 empty] | 186071 | 133423 | 4.45 | 0 | 0 | 5.73 | 5903
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 6d 11:07 |  | 6d 11:07 | 2032-08-01 03:45 | 2032-08-07 14:52
PH4100A | CP\11\006\B | CP | 11 | 6 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-08-02 10:04 | 2032-08-02 10:04 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\11\006\D | CP | 11 | 6 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-08-02 10:04 | 2032-08-02 10:04 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\11\007\B | CP | 11 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-08-02 10:04 | 2032-08-02 10:04 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\11\007\D | CP | 11 | 7 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-08-02 10:04 | 2032-08-02 10:04 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\12\001\B | CP | 12 | 1 | B | 1 Prestrip - Thick | 100 | 26.0179 | 26.0179 | 2032-08-02 10:04 | 2032-08-07 14:52 | 206078.1471 | 206078 | [7 empty] | 0 | 0 | 9.61 | 9.96 | 5492.25
PH4100XPC#1 | CP\12\001\B | CP | 12 | 1 | B | 1 Prestrip - Thick | 100 | 35.2126 | 35.2126 | 2032-08-02 10:04 | 2032-08-07 14:52 | 278906.1728 | 278906 | [7 empty] | 0 | 0 | 13.01 | 9.96 | 5492.25
TS5500Exc | CP\11\005\B | CP | 11 | 5 | B | 8 Coal Mining | 100 | 0 | 100 | 2032-08-06 09:13 | 2032-08-11 18:39 | 163050.2867 | [6 empty] | 163050 | 116379 | 3.88 | 0 | 0 | 8.41 | 5622
PH4100A | CP\12\002\B | CP | 12 | 2 | B | 1 Prestrip - Thick | 100 | 28.842 | 28.842 | 2032-08-07 14:52 | 2032-08-19 20:22 | 496351.6174 | 496352 | [7 empty] | 0 | 0 | 17.73 | 10.32 | 5452.26
PH4100XPC#1 | CP\12\002\B | CP | 12 | 2 | B | 1 Prestrip - Thick | 100 | 39.1212 | 39.1212 | 2032-08-07 14:52 | 2032-08-19 20:22 | 673249.0339 | 673249 | [7 empty] | 0 | 0 | 24.04 | 10.32 | 5452.26
TS6060#1 | CP\12\001\B | CP | 12 | 1 | B | 8 Coal Mining | 100 | 0 | 100 | 2032-08-07 14:52 | 2032-08-10 20:51 | 105537.6257 | [6 empty] | 105538 | 77013 | 4 | 0 | 0 | 9.96 | 5492
TS Fleet 5 | CP\12\001\D | CP | 12 | 1 | D | 1 Prestrip - Thick | 20.1381 | 20.1381 | 20.1381 | 2032-08-10 20:51 | 2032-08-14 07:34 | 162134.691 | 162135 | [7 empty] | 0 | 0 | 10.89 | 5.54 | 5928.06
TS6060#1 | CP\12\001\D | CP | 12 | 1 | D | 1 Prestrip - Thick | 37.7816 | 37.7816 | 37.7816 | 2032-08-10 20:51 | 2032-08-23 03:39 | 304185.9287 | 304186 | [7 empty] | 0 | 0 | 20.42 | 5.54 | 5928.06
TS5500Exc | CP\11\003\D | CP | 11 | 3 | D | 7 PostStrip | 100 | 0 | 100 | 2032-08-11 18:39 | 2032-08-18 20:03 | 149815.2097 |  |  | 149815 | [5 empty] | 0 | 0 | 0 | 6.23 | 5858.53
TS Fleet 5 | CP\11\005\D | CP | 11 | 5 | D | 1 Prestrip - Thick | 27.481 | 27.481 | 27.481 | 2032-08-14 07:34 | 2032-08-22 13:52 | 388674.1436 | 388674 | [7 empty] | 0 | 0 | 14.32 | 6.24 | 5857.12
TS5500Exc | CP\11\003\D | CP | 11 | 3 | D | 8 Coal Mining | 100 | 0 | 100 | 2032-08-18 20:03 | 2032-08-25 21:16 | 213145.0092 | [6 empty] | 213145 | 152218 | 5.07 | 0 | 0 | 6.23 | 5859
PH4100A | CP\11\005\D | CP | 11 | 5 | D | 1 Prestrip - Thick | 100 | 26.2478 | 26.2478 | 2032-08-19 20:22 | 2032-08-29 03:47 | 371232.518 | 371233 | [7 empty] | 0 | 0 | 13.67 | 6.24 | 5857.12
PH4100XPC#1 | CP\11\005\D | CP | 11 | 5 | D | 1 Prestrip - Thick | 100 | 35.7561 | 35.7561 | 2032-08-19 20:22 | 2032-08-29 03:47 | 505712.704 | 505713 | [7 empty] | 0 | 0 | 18.63 | 6.24 | 5857.12
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 9d 02:02 |  | 9d 02:02 | 2032-08-22 13:52 | 2032-08-31 15:54
TS6060#1 | CP\11\005\D | CP | 11 | 5 | D | 1 Prestrip - Thick | 15.0951 | 10.5152 | 10.5152 | 2032-08-23 03:39 | 2032-08-29 03:47 | 148720.7398 | 148721 | [7 empty] | 0 | 0 | 5.48 | 6.24 | 5857.12
TS5500Exc | CP\12\002\B | CP | 12 | 2 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2032-08-25 21:16 | 2032-08-28 09:23 | 75718.2955 | [6 empty] | 75718 | 55061 | 1.86 | 0 | 0 | 10.32 | 5452
TS5500Exc | CP\11\004\D | CP | 11 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2032-08-28 09:23 | 2032-09-04 11:02 | 150040.7108 |  |  | 150041 | [5 empty] | 0 | 0 | 0 | 6.28 | 5853.97
TS6060#1 | CP\12\002\B | CP | 12 | 2 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2032-08-29 03:47 | 2032-08-31 15:54 | 81356.892 | [6 empty] | 81357 | 59161 | 1.99 | 0 | 0 | 10.32 | 5452
PH4100A | CP\12\001\D | CP | 12 | 1 | D | 1 Prestrip - Thick | 100 | 17.8136 | 17.8136 | 2032-08-29 03:47 | 2032-09-01 18:06 | 143420.3621 | 143420 | [7 empty] | 0 | 0 | 9.63 | 5.54 | 5928.06
PH4100XPC#1 | CP\12\001\D | CP | 12 | 1 | D | 1 Prestrip - Thick | 100 | 24.2667 | 24.2667 | 2032-08-29 03:47 | 2032-09-01 18:06 | 195374.8544 | 195375 | [7 empty] | 0 | 0 | 13.12 | 5.54 | 5928.06
TS Fleet 5 | CP\12\002\D | CP | 12 | 2 | D | 1 Prestrip - Thick | 23.7018 | 23.7018 | 23.7018 | 2032-08-31 15:54 | 2032-09-08 04:34 | 354093.5564 | 354094 | [7 empty] | 0 | 0 | 13.01 | 5.86 | 5900.82
TS6060#1 | CP\12\002\D | CP | 12 | 2 | D | 1 Prestrip - Thick | 27.5094 | 17.3147 | 17.3147 | 2032-08-31 15:54 | 2032-09-11 02:36 | 258673.3076 | 258673 | [7 empty] | 0 | 0 | 9.5 | 5.86 | 5900.82
PH4100A | CP\12\002\D | CP | 12 | 2 | D | 1 Prestrip - Thick | 100 | 24.9692 | 24.9692 | 2032-09-01 18:06 | 2032-09-11 02:36 | 373028.1541 | 373028 | [7 empty] | 0 | 0 | 13.7 | 5.86 | 5900.82
PH4100XPC#1 | CP\12\002\D | CP | 12 | 2 | D | 1 Prestrip - Thick | 100 | 34.0144 | 34.0144 | 2032-09-01 18:06 | 2032-09-11 02:36 | 508158.8152 | 508159 | [7 empty] | 0 | 0 | 18.66 | 5.86 | 5900.82
TS5500Exc | CP\11\004\D | CP | 11 | 4 | D | 8 Coal Mining | 100 | 0 | 100 | 2032-09-04 11:02 | 2032-09-11 11:13 | 211841.2979 | [6 empty] | 211841 | 151839 | 5.06 | 0 | 0 | 6.28 | 5854
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 32d 22:36 |  | 32d 22:36 | 2032-09-08 04:34 | 2032-10-11 03:09
PH4100A | CP\12\003\B | CP | 12 | 3 | B | 1 Prestrip - Thick | 100 | 28.6895 | 28.6895 | 2032-09-11 02:36 | 2032-09-23 08:41 | 490593.5469 | 490594 | [7 empty] | 0 | 0 | 17.01 | 9.95 | 5511.33
PH4100XPC#1 | CP\12\003\B | CP | 12 | 3 | B | 1 Prestrip - Thick | 100 | 39.006 | 39.006 | 2032-09-11 02:36 | 2032-09-23 08:41 | 667006.1242 | 667006 | [7 empty] | 0 | 0 | 23.13 | 9.95 | 5511.33
TS6060#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 24d 06:58 |  | 24d 06:58 | 2032-09-11 02:36 | 2032-10-05 09:35
TS5500Exc | CP\11\005\D | CP | 11 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2032-09-11 11:13 | 2032-09-18 13:00 | 150155.2085 |  |  | 150155 | [5 empty] | 0 | 0 | 0 | 6.24 | 5857.12
TS5500Exc | CP\11\005\D | CP | 11 | 5 | D | 8 Coal Mining | 100 | 0 | 100 | 2032-09-18 13:00 | 2032-09-25 10:55 | 209000.6907 | [6 empty] | 209001 | 149440 | 4.98 | 0 | 0 | 6.24 | 5857
PH4100A | CP\12\004\B | CP | 12 | 4 | B | 1 Prestrip - Thick | 100 | 24.3113 | 24.3113 | 2032-09-23 08:41 | 2032-10-05 09:35 | 479678.2492 | 479678 | [7 empty] | 0 | 0 | 16.06 | 9.52 | 5504.47
PH4100XPC#1 | CP\12\004\B | CP | 12 | 4 | B | 1 Prestrip - Thick | 100 | 33.0933 | 33.0933 | 2032-09-23 08:41 | 2032-10-05 09:35 | 652952.874 | 652953 | [7 empty] | 0 | 0 | 21.87 | 9.52 | 5504.47
TS5500Exc | CP\12\001\D | CP | 12 | 1 | D | 7 PostStrip | 100 | 0 | 100 | 2032-09-25 10:55 | 2032-09-29 07:43 | 82062.9271 |  |  | 82063 | [5 empty] | 0 | 0 | 0 | 5.54 | 5928.06
TS5500Exc | CP\12\001\D | CP | 12 | 1 | D | 8 Coal Mining | 100 | 0 | 100 | 2032-09-29 07:43 | 2032-10-02 17:47 | 103367.7196 | [6 empty] | 103368 | 78248 | 5.02 | 0 | 0 | 5.54 | 5928
TS5500Exc | CP\12\002\D | CP | 12 | 2 | D | 7 PostStrip | 100 | 0 | 100 | 2032-10-02 17:47 | 2032-10-09 19:08 | 149779.4141 |  |  | 149779 | [5 empty] | 0 | 0 | 0 | 5.86 | 5900.82
PH4100A | CP\12\005\B | CP | 12 | 5 | B | 1 Prestrip - Thick | 100 | 28.7844 | 28.7844 | 2032-10-05 09:35 | 2032-10-21 01:42 | 635311.2771 | 635311 | [7 empty] | 0 | 0 | 21.13 | 9.82 | 5469.26
PH4100XPC#1 | CP\12\005\B | CP | 12 | 5 | B | 1 Prestrip - Thick | 100 | 39.2045 | 39.2045 | 2032-10-05 09:35 | 2032-10-21 01:42 | 865296.6799 | 865297 | [7 empty] | 0 | 0 | 28.78 | 9.82 | 5469.26
TS6060#1 | CP\12\004\B | CP | 12 | 4 | B | 8 Coal Mining | 100 | 0 | 100 | 2032-10-05 09:35 | 2032-10-11 03:09 | 186198.5532 | [6 empty] | 186199 | 136376 | 4.54 | 0 | 0 | 9.52 | 5504
TS5500Exc | CP\12\002\D | CP | 12 | 2 | D | 8 Coal Mining | 59.8 | 0 | 59.8 | 2032-10-09 19:08 | 2032-10-13 21:31 | 123921.1205 | [6 empty] | 123921 | 93508 | 3.12 | 0 | 0 | 5.86 | 5901
TS Fleet 5 | CP\12\004\D | CP | 12 | 4 | D | 1 Prestrip - Thick | 22.7954 | 22.7954 | 22.7954 | 2032-10-11 03:09 | 2032-10-18 03:03 | 329070.5331 | 329071 | [7 empty] | 0 | 0 | 12.11 | 6.43 | 5850.2
TS6060#1 | CP\12\004\D | CP | 12 | 4 | D | 1 Prestrip - Thick | 29.5717 | 29.5717 | 29.5717 | 2032-10-11 03:09 | 2032-10-28 08:54 | 426892.4446 | 426892 | [7 empty] | 0 | 0 | 15.71 | 6.43 | 5850.2
TS5500Exc | CP\12\003\B | CP | 12 | 3 | B | 7 PostStrip | 100 | 0 | 100 | 2032-10-13 21:31 | 2032-10-21 07:32 | 157440.8345 |  |  | 157441 | [5 empty] | 0 | 0 | 0 | 9.95 | 5511.33
TS Fleet 5 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 11d 16:36 |  | 11d 16:36 | 2032-10-18 03:03 | 2032-10-29 19:39
PH4100A | CP\12\004\D | CP | 12 | 4 | D | 1 Prestrip - Thick | 100 | 20.1642 | 20.1642 | 2032-10-21 01:42 | 2032-10-28 08:54 | 291087.7044 | 291088 | [7 empty] | 0 | 0 | 10.71 | 6.43 | 5850.2
PH4100XPC#1 | CP\12\004\D | CP | 12 | 4 | D | 1 Prestrip - Thick | 100 | 27.4688 | 27.4688 | 2032-10-21 01:42 | 2032-10-28 08:54 | 396535.1713 | 396535 | [7 empty] | 0 | 0 | 14.59 | 6.43 | 5850.2
TS5500Exc | CP\12\005\B | CP | 12 | 5 | B | 8 Coal Mining | 69.8 | 0 | 69.8 | 2032-10-21 07:32 | 2032-10-24 21:48 | 108655.5515 | [6 empty] | 108656 | 79398 | 2.65 | 0 | 0 | 9.82 | 5469
TS5500Exc | CP\12\003\B | CP | 12 | 3 | B | 8 Coal Mining | 48.2 | 0 | 48.2 | 2032-10-24 21:48 | 2032-10-27 14:43 | 81765.4804 | [6 empty] | 81765 | 60027 | 2 | 0 | 0 | 9.95 | 5511
TS5500Exc | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 0d 18:11 |  | 0d 18:11 | 2032-10-27 14:43 | 2032-10-28 08:54
PH4100A | CP\12\006\B | CP | 12 | 6 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\12\006\D | CP | 12 | 6 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\12\007\D | CP | 12 | 7 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\13\001\B | CP | 13 | 1 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\13\001\D | CP | 13 | 1 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\13\002\B | CP | 13 | 2 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\13\002\D | CP | 13 | 2 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\13\003\B | CP | 13 | 3 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\13\004\B | CP | 13 | 4 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\13\004\D | CP | 13 | 4 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\13\005\B | CP | 13 | 5 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\13\005\D | CP | 13 | 5 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\13\006\B | CP | 13 | 6 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\13\007\B | CP | 13 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\13\007\D | CP | 13 | 7 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\14\001\B | CP | 14 | 1 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\14\001\D | CP | 14 | 1 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\14\003\B | CP | 14 | 3 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\14\004\B | CP | 14 | 4 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\14\004\D | CP | 14 | 4 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\14\005\B | CP | 14 | 5 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\14\005\D | CP | 14 | 5 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\14\006\B | CP | 14 | 6 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\14\007\B | CP | 14 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\14\007\D | CP | 14 | 7 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\15\001\B | CP | 15 | 1 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\15\001\D | CP | 15 | 1 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\15\003\B | CP | 15 | 3 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\15\004\B | CP | 15 | 4 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\15\004\D | CP | 15 | 4 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\15\005\B | CP | 15 | 5 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\15\005\D | CP | 15 | 5 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\15\007\B | CP | 15 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\15\007\D | CP | 15 | 7 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\16\001\B | CP | 16 | 1 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\16\001\D | CP | 16 | 1 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\16\003\B | CP | 16 | 3 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\16\004\B | CP | 16 | 4 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\16\004\D | CP | 16 | 4 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\16\005\B | CP | 16 | 5 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\16\005\D | CP | 16 | 5 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\16\007\B | CP | 16 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\16\007\D | CP | 16 | 7 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\17\001\B | CP | 17 | 1 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\17\001\D | CP | 17 | 1 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\17\003\B | CP | 17 | 3 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\17\004\B | CP | 17 | 4 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\17\004\D | CP | 17 | 4 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\17\005\B | CP | 17 | 5 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\17\005\D | CP | 17 | 5 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\17\007\A | CP | 17 | 7 | A | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\17\007\B | CP | 17 | 7 | B | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
PH4100A | CP\17\007\D | CP | 17 | 7 | D | 1 Prestrip - Thick | 100 | 0 | 0 | 2032-10-28 08:54 | 2032-10-28 08:54 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
TS5500Exc | CP\12\004\D | CP | 12 | 4 | D | 7 PostStrip | 100 | 0 | 100 | 2032-10-28 08:54 | 2032-11-04 10:32 | 150027.7632 |  |  | 150028 | [5 empty] | 0 | 0 | 0 | 6.43 | 5850.2
PH4100A | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 10:45 |  | 1d 10:45 | 2032-10-28 08:54 | 2032-10-29 19:39
PH4100XPC#1 | In Path Delay | In Path Delay |  |  |  | 105 Wait on Block | 1d 10:45 |  | 1d 10:45 | 2032-10-28 08:54 | 2032-10-29 19:39
TS6060#1 | CP\12\005\B | CP | 12 | 5 | B | 8 Coal Mining | 30.2 | 0 | 30.2 | 2032-10-28 08:54 | 2032-10-29 19:39 | 47038.9855 | [6 empty] | 47039 | 34373 | 1.15 | 0 | 0 | 9.82 | 5469
PH4100A | CP\12\005\D | CP | 12 | 5 | D | 1 Prestrip - Thick | 100 | 24.309 | 24.309 | 2032-10-29 19:39 | 2032-11-07 09:54 | 342700.6802 | 342701 | [7 empty] | 0 | 0 | 12.62 | 6.4 | 5852.26
TS Fleet 5 | CP\12\005\D | CP | 12 | 5 | D | 1 Prestrip - Thick | 27.481 | 27.481 | 27.481 | 2032-10-29 19:39 | 2032-11-07 01:19 | 387418.2723 | 387418 | [7 empty] | 0 | 0 | 14.27 | 6.4 | 5852.26
PH4100XPC#1 | CP\12\005\D | CP | 12 | 5 | D | 1 Prestrip - Thick | 100 | 33.115 | 33.115 | 2032-10-29 19:39 | 2032-11-07 09:54 | 466845.1154 | 466845 | [7 empty] | 0 | 0 | 17.2 | 6.4 | 5852.26
TS6060#1 | CP\12\005\D | CP | 12 | 5 | D | 1 Prestrip - Thick | 15.0951 | 15.0951 | 15.0951 | 2032-10-29 19:39 | 2032-11-07 09:54 | 212806.0676 | 212806 | [7 empty] | 0 | 0 | 7.84 | 6.4 | 5852.26
TS5500Exc | CP\12\004\D | CP | 12 | 4 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2032-11-04 10:32 | 2032-11-07 15:15 | 96638.071 | [6 empty] | 96638 | 72920 | 2.43 | 0 | 0 | 6.43 | 5850
TS Fleet 5 | End of Schedule | End of Schedule | [7 empty] | 2032-11-07 01:19 | 2032-11-07 01:19
TS6060#1 | CP\12\002\D | CP | 12 | 2 | D | 8 Coal Mining | 40.2 | 0 | 40.2 | 2032-11-07 09:54 | 2032-11-09 23:23 | 83221.9488 | [6 empty] | 83222 | 62798 | 2.09 | 0 | 0 | 5.86 | 5901
PH4100A | End of Schedule | End of Schedule | [7 empty] | 2032-11-07 09:54 | 2032-11-07 09:54
TS5500Exc | CP\12\005\D | CP | 12 | 5 | D | 7 PostStrip | 100 | 0 | 100 | 2032-11-07 15:15 | 2032-11-14 17:05 | 150200.3033 |  |  | 150200 | [5 empty] | 0 | 0 | 0 | 6.4 | 5852.26
TS6060#1 | CP\12\003\B | CP | 12 | 3 | B | 8 Coal Mining | 51.8 | 0 | 51.8 | 2032-11-09 23:23 | 2032-11-12 16:18 | 87854.3992 | [6 empty] | 87854 | 64497 | 2.15 | 0 | 0 | 9.95 | 5511
TS6060#1 | CP\12\004\D | CP | 12 | 4 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2032-11-12 16:18 | 2032-11-15 21:01 | 103834.5231 | [6 empty] | 103835 | 78351 | 2.61 | 0 | 0 | 6.43 | 5850
TS5500Exc | CP\12\005\D | CP | 12 | 5 | D | 8 Coal Mining | 48.2 | 0 | 48.2 | 2032-11-14 17:05 | 2032-11-17 20:30 | 94998.3374 | [6 empty] | 94998 | 71569 | 2.39 | 0 | 0 | 6.4 | 5852
TS6060#1 | CP\12\005\D | CP | 12 | 5 | D | 8 Coal Mining | 51.8 | 0 | 51.8 | 2032-11-15 21:01 | 2032-11-19 00:26 | 102072.6817 | [6 empty] | 102073 | 76898 | 2.56 | 0 | 0 | 6.4 | 5852
TS5500Exc | End of Schedule | End of Schedule | [7 empty] | 2032-11-17 20:30 | 2032-11-17 20:30
TS6060#1 | End of Schedule | End of Schedule | [7 empty] | 2032-11-19 00:26 | 2032-11-19 00:26