## Working Locations
Work Zone
Spring Creek | SC
|  | Distance | Av Speed | Time
|  | km | km/h | min
Start of Shift | Office to Parkup | 3.7 | 50 | 4.44
Start of Shift | Parkup to Pit | 2.4 | 30 | 4.8
Crib | Pit To Parkup | 2.4 | 30 | 4.8
Crib | Parkup to Pit | 2.4 | 30 | 4.8
End of Shift | Pit To Parkup | 2.4 | 30 | 4.8
End of Shift | Parkup to Office | 3.7 | 50 | 4.44
|  | Distance | Av Speed | Time |  | Distance | Av Speed | Time
Haul Travel Times |  | km | km/h | min |  | km | km/h | min
Loaded Haul to start of ROM | Typical haul |  | 50 | 0 |  | 24.1667 | 50 | 29
| Long haul option |  | 30 | 0 |  | 15.5 | 30 | 31
| Short haul option |  | 30 | 0 |  | 14 | 30 | 28
Empty Transit to Excavator | Typical travel |  | 30 | 0 |  | 0 | 30 | 0
| Long haul option |  | 30 | 0 |  | 0 | 30 | 0
| Short haul option |  | 50 | 0 |  | 0 | 50 | 0
Production | Current year. Selected peak year.
|  | Seams | [5 empty] | Percentages of total
| Units | X | A | B | D | None | Total | X | A | B | D | None | Total
Total Production | kt | 0 | 0 | 1462 | 3265 | 0 | 4727 | 0% | 0% | 30.93% | 69.07% | 0% | 100%
Monthly Production
January | kt | 0 | 0 | 94 | 387 | 0 | 481 | 0% | 0% | 6.43% | 11.85% | 0% | 10.18%
February | kt | 0 | 0 | 61 | 120 | 0 | 181 | 0% | 0% | 4.172% | 3.675% | 0% | 3.829%
March | kt | 0 | 0 | 226 | 337 | 0 | 563 | 0% | 0% | 15.46% | 10.32% | 0% | 11.91%
April | kt | 0 | 0 | 181 | 250 | 0 | 431 | 0% | 0% | 12.38% | 7.657% | 0% | 9.118%
May | kt | 0 | 0 | 159 | 127 | 0 | 286 | 0% | 0% | 10.88% | 3.89% | 0% | 6.05%
June | kt | 0 | 0 | 99 | 435 | 0 | 534 | 0% | 0% | 6.772% | 13.32% | 0% | 11.3%
July | kt | 0 | 0 | 61 | 243 | 0 | 304 | 0% | 0% | 4.172% | 7.443% | 0% | 6.431%
August | kt | 0 | 0 | 232 | 132 | 0 | 364 | 0% | 0% | 15.87% | 4.043% | 0% | 7.7%
September | kt | 0 | 0 | 91 | 431 | 0 | 522 | 0% | 0% | 6.224% | 13.2% | 0% | 11.04%
October | kt | 0 | 0 | 37 | 245 | 0 | 282 | 0% | 0% | 2.531% | 7.504% | 0% | 5.966%
November | kt | 0 | 0 | 181 | 324 | 0 | 505 | 0% | 0% | 12.38% | 9.923% | 0% | 10.68%
December | kt | 0 | 0 | 40 | 234 | 0 | 274 | 0% | 0% | 2.736% | 7.167% | 0% | 5.796%
Number of Shifts between tasks | # | 4 | Number of shifts to work at one location before rechecking for new location
Dig Rates | [6 empty] | Percent of production
EX5500 | t/h | 1750 | 1750 | 1750 | 1750 | 1750 | 48%
EX6060 | t/h | 1900 | 1900 | 1900 | 1900 | 1900 | 52%
FEL2 | t/h | 800 | 800 | 800 | 800 | 800 | 0%
Truck Loading
Spot time | min | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 |  | Value for 793s found in TUM |  |  |  | (time from haul circuit to spotting under load for first bucket)
Loading time
789 Trucks with tailgate | min | 5.1557 | 5.1557 | 5.1557 | 5.1557 | 5.1557 | [5 empty] | 789 Trucks loaded by FEL2 = 5.25min loading - not entered, current value is calculated
789 Trucks no tailgate | min | 4.47 | 4.47 | 4.47 | 4.47 | 4.47 | Calculated from dig rates and tray capacity
793 Trucks | min | 5.8414 | 5.8414 | 5.8414 | 5.8414 | 5.8414 | [5 empty] | 793 loaded by EX5600 = 4.1min
Clear dig zone time | min | [10 empty] | (time to travel from loader to start of haul circuit)
Maximum # of Trucks | # | unlimited
Walking time
Leaving from: | to: | X | A | B | D | None
X | min | 0 | 0 | 0 | 0 | 0
A | min | 0 | 0 | 0 | 0 | 0 |  | N/A
B | min | 0 | 0 | 0 | 0 | 0
D | min | 0 | 0 | 0 | 0 | 0
None | min | 0 | 0 | 0 | 0 | 0
Blasting Delays
Mean time between blasts | h
Blast delay | h/event
Bootes Creek/Meteor Creek | BCMC
|  | Distance | Av Speed | Time
|  | km | km/h | min
Start of Shift | Office to Parkup | 2.5 | 50 | 3
Start of Shift | Parkup to Pit | 2.6 | 30 | 5.2
Crib | Pit To Parkup | 2.6 | 30 | 5.2
Crib | Parkup to Pit | 2.6 | 30 | 5.2
End of Shift | Pit To Parkup | 2.6 | 30 | 5.2
End of Shift | Parkup to Office | 2.5 | 50 | 3
|  | Distance | Av Speed | Time
Haul Travel Times |  | km | km/h | min
Loaded Haul to start of ROM | Typical haul | 16.6667 | 50 | 20
| Long haul option | 10 | 30 | 20
| Short haul option | 10 | 30 | 20
Empty Transit to Excavator | Typical travel | 0 | 30 | 0
| Long haul option | 0 | 30 | 0
| Short haul option | 0 | 50 | 0
Production
|  | Seams | [5 empty] | Percentages of total
| Units | X | A | B | D | None | Total | X | A | B | D | None | Total
Total Production | kt | 0 | 8 | 409 | 2631 | 0 | 3048 | 0% | 0.2625% | 13.42% | 86.32% | 0% | 100%
Monthly Production
January | kt | 0 | 0 | 45 | 0 | 0 | 45 | 0% | 0% | 11% | 0% | 0% | 1.476%
February | kt | 0 | 8 | 115 | 282 | 0 | 405 | 0% | 100% | 28.12% | 10.72% | 0% | 13.29%
March | kt | 0 | 0 | 0 | 352 | 0 | 352 | 0% | 0% | 0% | 13.38% | 0% | 11.55%
April | kt | 0 | 0 | 0 | 272 | 0 | 272 | 0% | 0% | 0% | 10.34% | 0% | 8.924%
May | kt | 0 | 0 | 0 | 263 | 0 | 263 | 0% | 0% | 0% | 9.996% | 0% | 8.629%
June | kt | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
July | kt | 0 | 0 | 0 | 66 | 0 | 66 | 0% | 0% | 0% | 2.509% | 0% | 2.165%
August | kt | 0 | 0 | 0 | 253 | 0 | 253 | 0% | 0% | 0% | 9.616% | 0% | 8.301%
September | kt | 0 | 0 | 181 | 292 | 0 | 473 | 0% | 0% | 44.25% | 11.1% | 0% | 15.52%
October | kt | 0 | 0 | 0 | 204 | 0 | 204 | 0% | 0% | 0% | 7.754% | 0% | 6.693%
November | kt | 0 | 0 | 45 | 300 | 0 | 345 | 0% | 0% | 11% | 11.4% | 0% | 11.32%
December | kt | 0 | 0 | 23 | 347 | 0 | 370 | 0% | 0% | 5.623% | 13.19% | 0% | 12.14%
Number of Shifts between tasks | # | 4 | Number of shifts to work at one location before rechecking for new location
Dig Rates |  | X | A | B | D | None | Percent of production
EX5500 | t/h | 1750 | 1750 | 1750 | 1750 | 1750 | 48%
EX6060 | t/h | 1900 | 1900 | 1900 | 1900 | 1900 | 52%
FEL2 | t/h | 800 | 800 | 800 | 800 | 800 | 0%
Truck Loading
Spot time under loader | min | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 |  | Value for 793s found in TUM |  |  |  | (time from haul circuit to spotting under load for first bucket)
Loading time
789 Trucks with tailgate | min | 5.1557 | 5.1557 | 5.1557 | 5.1557 | 5.1557 | [5 empty] | 789 Trucks loaded by FEL2 = 5.25min loading - not entered, current value is calculated
789 Trucks no tailgate | min | 4.47 | 4.47 | 4.47 | 4.47 | 4.47 | Calculated from dig rates and tray capacity
793 Trucks | min | 5.8414 | 5.8414 | 5.8414 | 5.8414 | 5.8414 | [5 empty] | 793 loaded by EX5600 = 4.1min
Clear dig zone time | min | [10 empty] | (time to travel from loader to start of haul circuit)
Maximum # of Trucks | # | unlimited
Walking time
Leaving from: | to: | X | A | B | D | None
X | min | 0 | 0 | 0 | 0 | 0
A | min | 0 | 0 | 0 | 0 | 0
B | min | 0 | 0 | 0 | 0 | 0
D | min | 0 | 0 | 0 | 0 | 0
None | min | 0 | 0 | 0 | 0 | 0
Blasting Delays
Mean time between blasts | h
Blast delay | h/event
Bootes West/Meteor West | BMMW
|  | Distance | Av Speed | Time
|  | km | km/h | min
Start of Shift | Office to Parkup | 9 | 50 | 10.8
Start of Shift | Parkup to Pit | 3.4 | 30 | 6.8
Crib | Pit To Parkup | 3.4 | 30 | 6.8
Crib | Parkup to Pit | 3.4 | 30 | 6.8
End of Shift | Pit To Parkup | 3.4 | 30 | 6.8
End of Shift | Parkup to Office | 9 | 50 | 10.8
|  | Distance | Av Speed | Time
Haul Travel Times |  | km | km/h | min
TotalCycle Time | Typical haul | 23.75 | 50 | 28.5
| Long haul option | 15.25 | 30 | 30.5
| Short haul option | 13.25 | 30 | 26.5
Empty Transit to Excavator | Typical travel | 0 | 30 | 0
| Long haul option | 0 | 30 | 0
| Short haul option | 0 | 50 | 0
Production
|  | Seams | [5 empty] | Percentages of total
| Units | X | A | B | D | None | Total | X | A | B | D | None | Total
Total Production | kt | 0 | 469 | 1526 | 2589 | 0 | 4584 | 0% | 10.23% | 33.29% | 56.48% | 0% | 100%
Monthly Production
January | kt | 0 | 0 | 173 | 420 | 0 | 593 | 0% | 0% | 11.34% | 16.22% | 0% | 12.94%
February | kt | 0 | 0 | 48 | 120 | 0 | 168 | 0% | 0% | 3.145% | 4.635% | 0% | 3.665%
March | kt | 0 | 1 | 0 | 173 | 0 | 174 | 0% | 0.2132% | 0% | 6.682% | 0% | 3.796%
April | kt | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
May | kt | 0 | 32 | 15 | 454 | 0 | 501 | 0% | 6.823% | 0.983% | 17.54% | 0% | 10.93%
June | kt | 0 | 1 | 90 | 317 | 0 | 408 | 0% | 0.2132% | 5.898% | 12.24% | 0% | 8.901%
July | kt | 0 | 25 | 154 | 311 | 0 | 490 | 0% | 5.33% | 10.09% | 12.01% | 0% | 10.69%
August | kt | 0 | 106 | 14 | 176 | 0 | 296 | 0% | 22.6% | 0.9174% | 6.798% | 0% | 6.457%
September | kt | 0 | 16 | 230 | 0 | 0 | 246 | 0% | 3.412% | 15.07% | 0% | 0% | 5.366%
October | kt | 0 | 75 | 458 | 121 | 0 | 654 | 0% | 15.99% | 30.01% | 4.674% | 0% | 14.27%
November | kt | 0 | 12 | 81 | 346 | 0 | 439 | 0% | 2.559% | 5.308% | 13.36% | 0% | 9.577%
December | kt | 0 | 201 | 263 | 151 | 0 | 615 | 0% | 42.86% | 17.23% | 5.832% | 0% | 13.42%
Number of Shifts between tasks | # | 4 | Number of shifts to work at one location before rechecking for new location
Dig Rates | [6 empty] | Percent of production
EX5500 | t/h | 1750 | 1750 | 1750 | 1750 | 1750 | 48%
EX6060 | t/h | 1900 | 1900 | 1900 | 1900 | 1900 | 52%
FEL2 | t/h | 800 | 800 | 800 | 800 | 800 | 0%
Truck Loading
Spot time under loader | min | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 |  | Value for 793s found in TUM |  |  |  | (time from haul circuit to spotting under load for first bucket)
Loading time
789 Trucks with tailgate | min | 5.1557 | 5.1557 | 5.1557 | 5.1557 | 5.1557 | [5 empty] | 789 Trucks loaded by FEL2 = 5.25min loading - not entered, current value is calculated
789 Trucks no tailgate | min | 4.47 | 4.47 | 4.47 | 4.47 | 4.47 | Calculated from dig rates and tray capacity
793 Trucks | min | 5.8414 | 5.8414 | 5.8414 | 5.8414 | 5.8414 | [5 empty] | 793 loaded by EX5600 = 4.1min
Clear dig zone time | min | [10 empty] | (time to travel from loader to start of haul circuit)
Maximum # of Trucks | # | unlimited
Walking time
Leaving from: | to: | X | A | B | D | None
X | min | 0 | 0 | 0 | 0 | 0
A | min | 0 | 0 | 0 | 0 | 0
B | min | 0 | 0 | 0 | 0 | 0
D | min | 0 | 0 | 0 | 0 | 0
None | min | 0 | 0 | 0 | 0 | 0
Blasting Delays
Mean time between blasts | h
Blast delay | h/event
ROM Area | ROM
|  | Distance | Av Speed | Time
|  | km | km/h | min
Start of Shift | Office to Parkup | 1 | 50 | 1.2
Start of Shift | Parkup to Pit | 0.2 | 30 | 0.4 |  |  |  |  | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41
Crib | Pit To Parkup | 0.2 | 30 | 0.4 |  |  |  |  | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41
Crib | Parkup to Pit | 0.2 | 30 | 0.4 |  |  |  |  | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41
End of Shift | Pit To Parkup | 0.2 | 30 | 0.4
End of Shift | Parkup to Office | 1 | 50 | 1.2
Production
|  | Seams | [5 empty] | Percentages of total
| Units | X | A | B | D | None | Total | X | A | B | D | None | Total
Total Production | kt | 0 | 142.27 | 1232.05 | 3316.49 | 0 | 4690.81 | 0% | 3.033% | 26.27% | 70.7% | 0% | 100%
Monthly Production
January | kt | 0 | 0 | 28.7 | 361.21 | 0 | 389.91 | 0% | 0% | 2.329% | 10.89% | 0% | 8.312%
February | kt | 0 | 30.75 | 69.7 | 289.05 | 0 | 389.5 | 0% | 21.61% | 5.657% | 8.716% | 0% | 8.303%
March | kt | 0 | 37.31 | 123 | 250.1 | 0 | 410.41 | 0% | 26.22% | 9.983% | 7.541% | 0% | 8.749%
April | kt | 0 | 0 | 73.8 | 317.75 | 0 | 391.55 | 0% | 0% | 5.99% | 9.581% | 0% | 8.347%
May | kt | 0 | 0 | 96.35 | 307.5 | 0 | 403.85 | 0% | 0% | 7.82% | 9.272% | 0% | 8.609%
June | kt | 0 | 2.87 | 145.55 | 247.23 | 0 | 395.65 | 0% | 2.017% | 11.81% | 7.455% | 0% | 8.435% |  | Using assumption of 41% ROM rehandle
July | kt | 0 | 0 | 92.25 | 123 | 0 | 215.25 | 0% | 0% | 7.488% | 3.709% | 0% | 4.589%
August | kt | 0 | 12.3 | 137.35 | 287 | 0 | 436.65 | 0% | 8.646% | 11.15% | 8.654% | 0% | 9.309%
September | kt | 0 | 9.84 | 112.75 | 307.5 | 0 | 430.09 | 0% | 6.916% | 9.151% | 9.272% | 0% | 9.169%
October | kt | 0 | 0 | 135.3 | 291.1 | 0 | 426.4 | 0% | 0% | 10.98% | 8.777% | 0% | 9.09%
November | kt | 0 | 24.6 | 98.4 | 287 | 0 | 410 | 0% | 17.29% | 7.987% | 8.654% | 0% | 8.74%
December | kt | 0 | 24.6 | 118.9 | 248.05 | 0 | 391.55 | 0% | 17.29% | 9.651% | 7.479% | 0% | 8.347%
Number of Shifts between tasks | # | 4 | Number of shifts to work at one location before rechecking for new location
Dig Rates | [6 empty] | Percent of production
EX5500 | t/h | 0 | 0 | 0 | 0 | 0 | 0%
EX6060 | t/h | 0 | 0 | 0 | 0 | 0 | 0%
FEL2 | t/h | 1500 | 1500 | 1500 | 1500 | 1500 | 100%
Truck Loading
Spot time under loader | min | [5 empty] | (time from haul circuit to spotting under load for first bucket)
Loading time
789 Trucks with tailgate | min | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
789 Trucks no tailgate | min | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | N/A On ROM
793 Trucks | min | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Clear dig zone time | min | [5 empty] | (time to travel from loader to start of haul circuit)
Maximum # of Trucks | # | 2
Walking time
Leaving from: | to: | X | A | B | D | None
X | min | 0 | 1 | 1 | 1 | 1
A | min | 1 | 0 | 1 | 1 | 1
B | min | 1 | 1 | 0 | 1 | 1
D | min | 1 | 1 | 1 | 0 | 1
None | min | 1 | 1 | 1 | 1 | 0
Blasting Delays
Mean time between blasts | h
Blast delay | h/event

## SimioInputs
Seam Product Split
Area | Percent X | Percent A | Percent B | Percent D | Percent None | TotalProduct
SpringCreek | 0 | 0 | 0.30929 | 0.69071 | 0 | 4727000
BootesWestMeteorWest | 0 | 0.10231 | 0.3329 | 0.56479 | 0 | 4584000
BootesCreekMeteorCreek | 0 | 0.0026247 | 0.13419 | 0.86319 | 0 | 3048000
Spring Creek Monthly Split | [6 empty] | Month | Units | X Seam | A Seam | B Seam | D Seam | Total
Monthly Production | Percent X | Percent A | Percent B | Percent D | Percent None |  | Total Tonnes | Kt | 0 | 0 | 1462 | 3265 | 4727
2014-01-01 | 0 | 0 | 0.064295 | 0.11853 | 0 |  | Jan | % | 0% | 0% | 6.43% | 11.85% | 10.18%
2014-02-01 | 0 | 0 | 0.041724 | 0.036753 | 0 |  | Feb | % | 0% | 0% | 4.172% | 3.675% | 3.829%
2014-03-01 | 0 | 0 | 0.15458 | 0.10322 | 0 |  | Mar | % | 0% | 0% | 15.46% | 10.32% | 11.91%
2014-04-01 | 0 | 0 | 0.1238 | 0.07657 | 0 |  | Apr | % | 0% | 0% | 12.38% | 7.657% | 9.118%
2014-05-01 | 0 | 0 | 0.10876 | 0.038897 | 0 |  | May | % | 0% | 0% | 10.88% | 3.89% | 6.05%
2014-06-01 | 0 | 0 | 0.067715 | 0.13323 | 0 |  | June | % | 0% | 0% | 6.772% | 13.32% | 11.3%
2014-07-01 | 0 | 0 | 0.041724 | 0.074426 | 0 |  | July | % | 0% | 0% | 4.172% | 7.443% | 6.431%
2014-08-01 | 0 | 0 | 0.15869 | 0.040429 | 0 |  | August | % | 0% | 0% | 15.87% | 4.043% | 7.7%
2014-09-01 | 0 | 0 | 0.062244 | 0.13201 | 0 |  | September | % | 0% | 0% | 6.224% | 13.2% | 11.04%
2014-10-01 | 0 | 0 | 0.025308 | 0.075038 | 0 |  | October | % | 0% | 0% | 2.531% | 7.504% | 5.966%
2014-11-01 | 0 | 0 | 0.1238 | 0.099234 | 0 |  | November | % | 0% | 0% | 12.38% | 9.923% | 10.68%
2014-12-01 | 0 | 0 | 0.02736 | 0.071669 | 0 |  | December | % | 0% | 0% | 2.736% | 7.167% | 5.796%
[7 empty] | Total Percent | % | 0% | 0% | 100% | 100% | 100%
BCMC | [6 empty] | Month | Units | X Seam | A Seam | B Seam | D Seam | Total
Monthly Production | Percent X | Percent A | Percent B | Percent D | Percent None |  | Total Tonnes | Kt | 0 | 8 | 409 | 2631 | 3048
2014-01-01 | 0 | 0 | 0.11002 | 0 | 0 |  | Jan | % | 0% | 0% | 11% | 0% | 1.476%
2014-02-01 | 0 | 1 | 0.28117 | 0.10718 | 0 |  | Feb | % | 0% | 100% | 28.12% | 10.72% | 13.29%
2014-03-01 | 0 | 0 | 0 | 0.13379 | 0 |  | Mar | % | 0% | 0% | 0% | 13.38% | 11.55%
2014-04-01 | 0 | 0 | 0 | 0.10338 | 0 |  | Apr | % | 0% | 0% | 0% | 10.34% | 8.924%
2014-05-01 | 0 | 0 | 0 | 0.099962 | 0 |  | May | % | 0% | 0% | 0% | 9.996% | 8.629%
2014-06-01 | 0 | 0 | 0 | 0 | 0 |  | June | % | 0% | 0% | 0% | 0% | 0%
2014-07-01 | 0 | 0 | 0 | 0.025086 | 0 |  | July | % | 0% | 0% | 0% | 2.509% | 2.165%
2014-08-01 | 0 | 0 | 0 | 0.096161 | 0 |  | August | % | 0% | 0% | 0% | 9.616% | 8.301%
2014-09-01 | 0 | 0 | 0.44254 | 0.11098 | 0 |  | September | % | 0% | 0% | 44.25% | 11.1% | 15.52%
2014-10-01 | 0 | 0 | 0 | 0.077537 | 0 |  | October | % | 0% | 0% | 0% | 7.754% | 6.693%
2014-11-01 | 0 | 0 | 0.11002 | 0.11403 | 0 |  | November | % | 0% | 0% | 11% | 11.4% | 11.32%
2014-12-01 | 0 | 0 | 0.056235 | 0.13189 | 0 |  | December | % | 0% | 0% | 5.623% | 13.19% | 12.14%
[7 empty] | Total Percent | % | 0% | 100% | 100% | 100% | 100%
BWMW | [6 empty] | Month | Units | X Seam | A Seam | B Seam | D Seam | Total
Monthly Production | Percent X | Percent A | Percent B | Percent D | Percent None |  | Total Tonnes | Kt | 0 | 469 | 1526 | 2589 | 4584
2014-01-01 | 0 | 0 | 0.11337 | 0.16222 | 0 |  | Jan | % | 0% | 0% | 11.34% | 16.22% | 12.94%
2014-02-01 | 0 | 0 | 0.031455 | 0.04635 | 0 |  | Feb | % | 0% | 0% | 3.145% | 4.635% | 3.665%
2014-03-01 | 0 | 0.0021322 | 0 | 0.066821 | 0 |  | Mar | % | 0% | 0.2132% | 0% | 6.682% | 3.796%
2014-04-01 | 0 | 0 | 0 | 0 | 0 |  | Apr | % | 0% | 0% | 0% | 0% | 0%
2014-05-01 | 0 | 0.06823 | 0.0098296 | 0.17536 | 0 |  | May | % | 0% | 6.823% | 0.983% | 17.54% | 10.93%
2014-06-01 | 0 | 0.0021322 | 0.058978 | 0.12244 | 0 |  | June | % | 0% | 0.2132% | 5.898% | 12.24% | 8.901%
2014-07-01 | 0 | 0.053305 | 0.10092 | 0.12012 | 0 |  | July | % | 0% | 5.33% | 10.09% | 12.01% | 10.69%
2014-08-01 | 0 | 0.22601 | 0.0091743 | 0.06798 | 0 |  | August | % | 0% | 22.6% | 0.9174% | 6.798% | 6.457%
2014-09-01 | 0 | 0.034115 | 0.15072 | 0 | 0 |  | September | % | 0% | 3.412% | 15.07% | 0% | 5.366%
2014-10-01 | 0 | 0.15991 | 0.30013 | 0.046736 | 0 |  | October | % | 0% | 15.99% | 30.01% | 4.674% | 14.27%
2014-11-01 | 0 | 0.025586 | 0.05308 | 0.13364 | 0 |  | November | % | 0% | 2.559% | 5.308% | 13.36% | 9.577%
2014-12-01 | 0 | 0.42857 | 0.17235 | 0.058324 | 0 |  | December | % | 0% | 42.86% | 17.23% | 5.832% | 13.42%
[7 empty] | Total Percent | % | 0% | 100% | 100% | 100% | 100%

## Weather
Average weather for Rolleston Mine region
Statistic Element | January | February | March | April | May | June | July | August | September | October | November | December | Annual | Number of Years | Start Year | End Year
Mean rainfall (mm) | 94.1 | 80.68 | 60.24 | 36.34 | 38.99 | 37.06 | 35.26 | 27.85 | 30.55 | 53.32 | 68.88 | 86.57 | 649.63 | 123.4 | 1881.5 | 2008.3
Highest rainfall (mm) | 302.48 | 336.3 | 424.14 | 217.13 | 251.31 | 201.03 | 246.21 | 170.33 | 165.5 | 212.24 | 266.5 | 384.23 | 1237.17 | 123.4 | 1881.5 | 2008.3
Date of Highest rainfall | 1926.3 | 1930 | 1897.3 | 1980.2 | 1983 | 1912.5 | 1956.6 | 1983.6 | 1919.6 | 1957 | 1924.8 | 1966.1 | 1923 |  | 1881.5 | 2008.3
Lowest rainfall (mm) | 4.6 | 1.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21 | 0.08 | 0.6 | 244.08 | 123.4 | 1881.5 | 2008.3
Date of Lowest rainfall | 1920 | 1926.6 | 1998.7 | 2003.4 | 1959.8 | 1993.2 | 2003.2 | 1995.2 | 1983.6 | 1992.4 | 1943.8 | 1915.6 | 1918.7 |  | 1881.5 | 2008.3
Decile 1 monthly rainfall (mm) | 25.18 | 12.8 | 7.47 | 1.25 | 2.38 | 1.4 | 1 | 1.25 | 0.98 | 9.18 | 13.46 | 22.81 | 444.34 | 116.6 | 1881.5 | 2008.3
Decile 5 (median) monthly rainfall (mm) | 81.11 | 59.31 | 44.46 | 21.98 | 25.46 | 27.7 | 24.76 | 18.77 | 20.99 | 45.76 | 59.24 | 73.74 | 632.43 | 116.6 | 1881.5 | 2008.3
Decile 9 monthly rainfall (mm) | 191.5 | 182.62 | 132.29 | 88.42 | 86.82 | 85.88 | 75.9 | 69.02 | 71.77 | 103.78 | 135.66 | 154.69 | 899.06 | 116.6 | 1881.5 | 2008.3
Highest daily rainfall (mm) | 156.16 | 127.94 | 129.4 | 96.35 | 128.57 | 87.0778 | 107.37 | 77.6 | 68.8 | 119.01 | 106.05 | 144.62 | 178.6222 | 117.3 | 1883.7 | 2008.3
Date of Highest daily rainfall
Mean number of days of rain | 7.7 | 6.65 | 5.62 | 3.85 | 4.08 | 4.1 | 4.16 | 3.63 | 3.79 | 5.83 | 6.68 | 7.69 | 63.78 | 116.6 | 1881.5 | 2008.3
Mean number of days of rain >= 1 mm | 6.22 | 5.34 | 4.43 | 3.02 | 3.05 | 3.09 | 3.17 | 2.78 | 2.98 | 4.7 | 5.39 | 6.27 | 50.44 | 117.3 | 1883.7 | 2008.3
Mean number of days of rain >= 10 mm | 2.57 | 2.27 | 1.72 | 1.1 | 1.07 | 1.07 | 0.99 | 0.84 | 0.93 | 1.7 | 2.09 | 2.6 | 18.95 | 117.3 | 1883.7 | 2008.3
Mean number of days of rain >= 25 mm | 1.03 | 0.95 | 0.62 | 0.35 | 0.35 | 0.38 | 0.35 | 0.2 | 0.24 | 0.48 | 0.69 | 0.92 | 6.56 | 117.3 | 1883.7 | 2008.3
Weather Inputs
Days in month | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 365
Change of rain day (%/d) | 24.84% | 23.75% | 18.13% | 12.83% | 13.16% | 13.67% | 13.42% | 11.71% | 12.63% | 18.81% | 22.27% | 24.81% | 17.47%
Mean rainfall (mm/rain day) | 12.2208 | 12.1323 | 10.7189 | 9.439 | 9.5564 | 9.039 | 8.476 | 7.6722 | 8.0607 | 9.1458 | 10.3114 | 11.2575 | 10.1855
Time Lost (h/mm rain) | bar: January to December

## Equipment
Dig Units
Item | Unit | Value | Comments
EX5500 | # | 1
Work Zones |  | SC/BCMC/BMMW
Rate | t/h | By work zone and seam
Reliability | %
MTBF | h
MTTR | h/event
Maintenance | h | 14 h every 28 days
Idle time before new truck assigned | h | 1/2 of loading time | Time take when excavator idle/waiting for truck
Queue time to take truck off shift | h | 1/2 of loading time | Time take for trucks queuing at the excavator
EX6060 | # | 1
Work Zones |  | SC/BCMC/BMMW
Rate | t/h | By work zone and seam
Reliability | %
MTBF | h
MTTR | h/event
Maintenance | h | 14 h every 28 days
Idle time before new truck assigned | h | 1/2 of loading time | Time take when excavator idle/waiting for truck
Queue time to take truck off shift | h | 1/2 of loading time | Time take for trucks queuing at the excavator
FEL2 | # | 1
Work Zones |  | ROM
Rate | t/h | 1200
Reliability | %
MTBF | h
MTTR | h/event
Maintenance | h | 14 h every 28 days
Idle time before new truck assigned | h | 1/2 of loading time | Time take when excavator idle/waiting for truck
Queue time to take truck off shift | h | 1/2 of loading time | Time take for trucks queuing at the excavator
Haul Trucks
Item | Unit | Value | Comments
789 Trucks | # | 8 | Initially at ROM parking
Capacity | t | 160
Haul cycle time | h | based on zone
Reliability | %
MTBF | h
MTTR | h/event
Maintenance schedule |  | 14 h every 500 op hours
789 Trucks - No tailgate | # | 4 | Initially at ROM parking
Capacity | t | 140
Haul cycle time | h | based on zone
Reliability | %
MTBF | h
MTTR | h/event
Maintenance schedule |  | 14 h every 500 op hours
793 Trucks | # | 4 | Initially at ROM parking
Capacity | t | 180
Haul cycle time | h | based on zone
Reliability | %
MTBF | h
MTTR | h/event
Maintenance schedule |  | 14 h every 500 op hours

## Shifts
Delay
|  | Hours | Min |  | Day Shift | Task
5:50 | Day Shift Staff Arrive | 0 | 0 |  | 5:50 | Day Shift Staff Arrive
6:00
6:20 | Preshift Finishes, Excavator Product Begin, Trucks Cycles Begin | 0.5 | 30 |  | 6:20 | Preshift Finishes, Excavator Product Begin, Trucks Cycles Begin
9:52 | Excavator Stops Loading Trucks, Truck Cycles Stop | 3.5417 | 212.5 |  | 9:52 | Excavator Stops Loading Trucks, Truck Cycles Stop
10:00 | First Break Start | 0.125 | 7.5 | 4 | 10:00 | First Break Start
10:30 | First break End | 0.5 | 30 |  | 10:30 | First break End
10:38 | Excavator product begins, Trucks Cycles Begin | 0.125 | 7.5 |  | 10:38 | Excavator product begins, Trucks Cycles Begin
13:52 | Excavator Stops Loading Trucks, Trucks Cycles Stop | 3.25 | 195 |  | 13:52 | Excavator Stops Loading Trucks, Trucks Cycles Stop
14:00 | Second Break Start | 0.125 | 7.5 | 3.5 | 14:00 | Second Break Start
14:30 | Second break End | 0.5 | 30 |  | 14:30 | Second break End
14:38 | Excavator product begins, Trucks Cycles Begin | 0.125 | 7.5 |  | 14:38 | Excavator product begins, Trucks Cycles Begin
17:55 | Excavator Stops Loading Trucks, Trucks Cycles Stop | 3.2917 | 197.5 |  | 17:55 | Excavator Stops Loading Trucks, Trucks Cycles Stop
18:00 | Day Shift Ends | 5 | 300 | 3.5 | 18:00 | Day Shift Ends
[5 empty] | Night Shift | Task
17:50 | Night Shift Staff Arrive |  | 0 |  | 17:50 | Night Shift Staff Arrive
18:20 | Preshift Finishes, Excavator Product Begin, Trucks Cycles Begin | 0.5 | 30 |  | 18:20 | Preshift Finishes, Excavator Product Begin, Trucks Cycles Begin
21:52 | Excavator Stops Loading Trucks, Truck Cycles Stop | 3.5417 | 212.5 |  | 21:52 | Excavator Stops Loading Trucks, Truck Cycles Stop
22:00 | First Break Start | 0.125 | 7.5 |  | 22:00 | First Break Start
22:30 | First break End | 0.5 | 30 |  | 22:30 | First break End
22:38 | Excavator product begins, Trucks Cycles Begin | 0.125 | 7.5 |  | 22:38 | Excavator product begins, Trucks Cycles Begin
1:52 | Excavator Stops Loading Trucks, Trucks Cycles Stop | -20.75 | -1245 |  | 1:52 | Excavator Stops Loading Trucks, Trucks Cycles Stop
2:00 | Second Break Start | 0.125 | 7.5 |  | 2:00 | Second Break Start
2:30 | Second break End | 0.5 | 30 |  | 2:30 | Second break End
2:38 | Excavator product begins, Trucks Cycles Begin | 0.125 | 7.5 |  | 2:38 | Excavator product begins, Trucks Cycles Begin
5:55 | Excavator Stops Loading Trucks, Trucks Cycles Stop | 3.2917 | 197.5 |  | 5:55 | Excavator Stops Loading Trucks, Trucks Cycles Stop
6:00 | Night Shift Ends | 0.083333 | 5 |  | 6:00 | Night Shift Ends

## ROM
ROM Operations
Item | Unit | Value | Comments
ROM Stockpile size | Mt | 1.4
Simultaneous trucks dumping to ROM | # trucks | 1
Hopper max capacity | t | 400 | Initially at ROM parking
Hopper working capacity | t | 260
Max hopper feed by Seam
X | t/h
A | t/h
B | t/h | 1750
D | t/h | 1950
Hopper considered full mark | t |  | Above this mark trucks will dump to ROM
Hopper feed reduced mark | t |  | Feed slowed to keep contents in hopper
Hopper feed stopped mark | t |  | Hopper considered empty
Hopper almost available (flashing green) | t |  | Trucks will queue for hopper access
Hopper Dump Times
Direct truck spot time to hopper | s | 33 | Spot time over hopper with no interruption |  | Stop watch measurements on 16/04/2014
Spot time when queued | s | 33 | Spot time when queued for other truck or flashing green light (treated as minimum time between trucks) |  | Stop watch measurements on 16/04/2014
Dumping time on Hopper | s | 30 | Time to actually dump into the hopper |  | Stop watch measurements on 16/04/2014
Clear time back to circuit | s | 10 | time to drive clear of the hopper back to the haul circuit |  | Stop watch measurements on 16/04/2014
ROM Dump Times
Spot time to ROM pile | min |  | distribution of time to ROM dump location and reverse in
Dumping time on ROM | min
Clear ROM time | min |  | treated as minimum time between trucks at the ROM
Hopper Level Marks
Hopper max capacity | t | 400 |  | 180 | 1750
Hopper working capacity | t | 188
Hopper full - stop trucks | % | 67% |  |  | 35 | 30
Hopper almost ready - allow trucks | % | 63% |  | 252 | 17.0139 | 14.5833 | 400.4028
Hopper almost empty - limit outfeed | % | 40%
Hopper empty - stop outfeed | % | 20%
Limited flow rate factor | % | 30% | Percent of full working rate to limit outfeed to while nearly empty

## CHF
Coal Handling Facility
Item | Unit | Value | Comments
Maximum conveyor rate to stacker | t/h | 2100
Sizing rate by seam |  | 1
X | t/h
A | t/h
B | t/h | 1750
D | t/h | 1950
Stacking rate | t |  | Above this mark trucks will dump to ROM
Stockpile capacity | kt | 170
Stacking circuit reliability | %
Stacking MTBF | h |  | This is to include all delays/interruptions from the hopper to the stacker
Stacking MTTR | h/event
Target Operating hours | h | 7200
Holiday shutdowns | days | 3 | Three day shut over Christmas
Stacking Maintenance schedule |  | 14 h every 28 days
Train Load Out
Number of reclaim valves | # | 4 | will change to 5
Total reclaim rate to TLO | t/h | 4200
TLO Bin max capacity | t | 450
TLO working capacity | t | 360
Train size | t/train | 8100
Loading factor | % | 100 | Fill factor on train loading
Train loading time | h | 2.25
Train interarrival time
Average | h | 4.1739 | Typical time between trains is 8760h/# trains per year
Min | h | 0.25 | Minimum time between queued up trains
Max | h | 16.6955 | Maximum gap between train loading